## B250_Amt Rs.3.93
Vendor Name | Vendor No. | SAP Doc. No. | Amt. | Reason for Delay in release | Remark of Retention/LD
M/s Metcon India Realty & Infra. Pvt. Ltd | 53476 | 1051911 | 9059158 | Fouling of 11 Kv & 33 Kv high tesion electrified line within the existing railway lines and proposed new railway lines. These electrified overhead lines belongs to Mahatransco & Mahadiscom. | Retention Release
M/s Metcon India Realty & Infra. Pvt. Ltd | 53476 | 1051916 | 8564152 | Fouling of 11 Kv & 33 Kv high tesion electrified line within the existing railway lines and proposed new railway lines. These electrified overhead lines belongs to Mahatransco & Mahadiscom. | Retention Release
M/s Metcon India Realty & Infra. Pvt. Ltd | 53476 | 1051917 | 4917274 | Fouling of 11 Kv & 33 Kv high tesion electrified line within the existing railway lines and proposed new railway lines. These electrified overhead lines belongs to Mahatransco & Mahadiscom. | Retention Release
M/s Metcon India Realty & Infra. Pvt. Ltd | 53476 | 1051918 | 5814875 | Fouling of 11 Kv & 33 Kv high tesion electrified line within the existing railway lines and proposed new railway lines. These electrified overhead lines belongs to Mahatransco & Mahadiscom. | Retention Release
M/s Prime Security Services Pvt. Ltd. | 70454 | 1056853 | 107339 | Labour Bonus retention released | Retention Release
M/s K. M. Patil | 54042 | 1077469 | 9790 | Labour Bonus & Wage difference of labour retention released | Retention Release
M/s Metcon India Realty & Infra. Pvt. Ltd | 53476 | 1096620 | 3309394 | Fouling of 11 Kv & 33 Kv high tesion electrified line within the existing railway lines and proposed new railway lines. These electrified overhead lines belongs to Mahatransco & Mahadiscom. | Retention Release
Vijaywargi Infrastructure Pvt. Ltd | 72146 | 1141192 | 138141 | Non completion of CTR work by Central railway nagpur which was alloted by MSPGCL to central railway on deposit basis. | Retention Release
Abhi Engineering | 71858 | 1141632 | 291622 | Retention released after submission of Statutory documents. (Royalty, labour cess) | Retention Release
M/s Metcon India Realty & Infra. Pvt. Ltd | 53476 | 19005960 | 337870 | Fouling of 11 Kv & 33 Kv high tesion electrified line within the existing railway lines and proposed new railway lines. These electrified overhead lines belongs to Mahatransco & Mahadiscom. | Retention Release
Abhi Engineering | 71858 | 19013690 | 1754248 | Retention released after submission of Statutory documents. (Royalty, labour cess) | Retention Release
M/s Metcon India Realty & Infra. Pvt. Ltd | 53476 | 19014922 | 3433503 | Fouling of 11 Kv & 33 Kv high tesion electrified line within the existing railway lines and proposed new railway lines. These electrified overhead lines belongs to Mahatransco & Mahadiscom. | Retention Release
M/s Metcon India Realty & Infra. Pvt. Ltd | 53476 | 19014924 | 1507663 | Fouling of 11 Kv & 33 Kv high tesion electrified line within the existing railway lines and proposed new railway lines. These electrified overhead lines belongs to Mahatransco & Mahadiscom. | Retention Release
VAIBHAV CONSTRUCTION COMPANY CBD BELAPUR | 74918 | 1080550 | 15743 | BOCW cess retention release. | Retention Release
|  | Total | 39260772

## B250_Amt Rs.1.81
Vendor Name | Vendor No. | SAP Doc. No. | Amt. | Reason for Delay in release | Remark of Retention/LD
Vijaywargi Infrastructure Pvt. Ltd | 72146 | 1234824 | 545041 | Non completion of CTR work by Central railway nagpur which was alloted by MSPGCL to central railway on deposit basis. | Retention Release
Vijaywargi Infrastructure Pvt. Ltd | 72146 | 1234823 | 937470 | Non completion of CTR work by Central railway nagpur which was alloted by MSPGCL to central railway on deposit basis. | Retention Release
Vijaywargi Infrastructure Pvt. Ltd | 72146 | 1234822 | 1471837 | Non completion of CTR work by Central railway nagpur which was alloted by MSPGCL to central railway on deposit basis. | Retention Release
Vijaywargi Infrastructure Pvt. Ltd | 72146 | 1234826 | 15108722 | Non completion of CTR work by Central railway nagpur which was alloted by MSPGCL to central railway on deposit basis. | Retention Release
18063070

## B234_Amt Rs. 9.50
Vendor Name | Vendor No. | SAP Doc. No. | Amt. | Reason for Delay in release | Remark of Retention/LD
BGR ENERGY SYSTEMS LTD., CHENNAI | 50213 | 1236792 | 1345000 | Vendor Subcontractor payments from available retentions of vendor against LD | Retention Release
BGR ENERGY SYSTEMS LTD., CHENNAI | 50213 | 1092071 | 33654830 | Vendor Subcontractor payments from available retentions of vendor against LD | Retention Release
BGR ENERGY SYSTEMS LTD., CHENNAI | 50213 | 1102203 | 57500000 | Vendor Subcontractor payments from available retentions of vendor against LD | Retention Release
BHEL NEW DELHI | 50225 | 1102190 | 2050000 | Retention transfer to CSTPS for Balance work | Retention Release
ELECON EPC PROJECTS LTD ANAND | 54370 | 1102201 | 400000 | Retention transfer to CSTPS for Balance work | Retention Release
Total |  |  | 94949830

## B234_Amt Rs.0.26
Vendor Name | Vendor No. | SAP Doc. No. | Amt. | Reason for Delay in release | Remark of Retention/LD
ION EXCHANGE INDIA LIMITED MUMBAI | 50644 | 1269580 | 2501518 | Retention Release after FTLE | Retention Release
ION EXCHANGE INDIA LIMITED MUMBAI | 50644 | 1269580 | 96938 | Retention Release after FTLE | Applicable LD
2598456