## F4
MSPGCL: Bhusawal U # 3
MTR Petition Formats - Generation
Form 4: Summary of Capital Expenditure and Capitalisation
Sr. No. | Particulars | FY 2022-23 |  |  | FY 2023-24 |  |  | FY 2024-25 |  |  |  |  | Ensuing Years |  |  |  |  | Remarks
|  | MYT Order (227 of 2022) | April-March (Audited ) | True-Up requirement | MYT Order (227 of 2022) | April-March (Audited ) | True-Up requirement | MYT Order (227 of 2022) | Apr-Sep (Estimated) | Oct-Mar (Projected) | April - March (Projected) | Provisional True-Up requirement | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30
|  | (a) | (b) | (c) = (b) - (a) | (d) | (e) | (f) = (e) - (d) | (j) | (k) | (l) | (m) = (k)+(l) | (n) = (m) - (j) | Projected | Projected | Projected | Projected | Projected
1 | Capital Expenditure |  | 0.26236 | 0.26236 |  | 0.21359 | 0.21359 |  | 5.54 |  | 5.54 | 5.54 | 0 | 398 | 0 | 0 | 0
2 | Capitalisation | 0 | 0.26236 | 0.26236 | 5.54 | 0.40793 | -5.1321 | 0 | 5.63 |  | 5.63 | 5.63 | 0 | 398 | 0 | 0 | 0
3 | IDC |  |  | 0 |  |  | 0 |  |  |  | 0 | 0
4 | Capitalisation + IDC | 0 | 0.26236 | 0.26236 | 5.54 | 0.40793 | -5.1321 | 0 | 5.63 | 0 | 5.63 | 5.63 | 0 | 398 | 0 | 0 | 0
Note: * - Truing Up for FY 2022-23 & FY 2023-24 to be done under MERC MYT Regulations 2019 with reference to amounts approved in the MYT Order for FY 2020-21 to FY 2024-25
Detailed Justification shall be provided for variation in approved capital expenditure and capitalisation vis-a-vis actual capital expenditure and capitalisation

## F4.1
MSPGCL: Bhusawal U # 3
MTR Petition Formats - Generation
| Project Details |  |  |  |  | Form 4.1: Capital Expenditure Plan | [11 empty] | (Rs. Crore)
Sr. No. | Project Code | Project Title | MERC Approval No. | MERC Approval Date | Project Purpose | Project Start Date |  |  | Project Completion date (Scheduled) |  |  | Capital Cost
[6 empty] | Original | Revised | Actual | Original | Revised | Actual | Approved | Actual Capital Cost Incurred | Deviation = Approved - Actual on account of
[14 empty] | Change in Scope of Work (a) | Material Cost (b) | IDC (c) | Others (d) | Total Deviation (a+b+c+d)
A) DPR Schemes
(i) In-principle approved by MERC
1 | Replacement of economizer & LTSH coils at Unit # 2 | DPR | MERC/CAPEX/20122013/00179 | 2012-04-23 |  | 2012-04-23 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
1.1 | Replacement of Economiser Coil | Scheme | MERC/CAPEX/20122013/00179 | 2012-04-23 |  | 2012-04-23 |  | 2011-08-30 | 2013-04-23 |  | 2011-09-27 | 3.524 | 3.47 |  | 0.054 |  |  | 0.054
0 | IDC | IDC | MERC/CAPEX/20122013/00179 | 2012-04-23 |  | 2012-04-23 |  | - | - |  | - | 0.203 | 0 |  | 0.203 |  |  | 0.203
1.2 | Replacement of LTSH Coil | Scheme | MERC/CAPEX/20122013/00179 | 2012-04-23 |  | 2012-04-23 |  | 2011-08-30 | 2013-04-23 |  | 2011-09-27 | 6.094 | 5.32 |  | 0.774 |  |  | 0.774
0 | IDC | IDC | MERC/CAPEX/20122013/00179 | 2012-04-23 |  | 2012-04-23 |  | - | - |  | - | 0.357 | 0 |  | 0.357 |  |  | 0.357
2 | Boiler and Turbine improvement (Station Heat Rate Improvement) | DPR | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 |  | 2013-01-11 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
2.1 | Vent condenser performance improvement by replacement of eroded tube nest by unit 3. | Scheme | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 |  | 2013-01-11 |  | - | 2016-01-11 |  | - | 0.286 | 0 |  | 0.286 |  |  | 0.286
2.2 | Replacement of major extraction valves &NRVs of unit 3 | Scheme | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 |  | 2013-01-11 |  | - | 2016-01-11 |  | - | 0.519 | 0 |  | 0.519 |  |  | 0.519
2.3 | 60% replacement of boiler skin insulation (Unit 2) | Scheme | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 |  | 2013-01-11 |  | - | 2016-01-11 |  | - | 0.293 | 0 |  | 0.293 |  |  | 0.293
2.4 | Replacement of DM make up ( unit 3) and GSH water pump.( units 2 &3) | Scheme | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 |  | 2013-01-11 |  | 2013-10-07 | 2016-01-11 |  | - | 0.206 | 0.26354 |  | -0.057541 |  |  | -0.057541
2.5 | Replacement of LTSH coils (unit 3) | Scheme | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 |  | 2013-01-11 |  | 2016-08-04 | 2016-01-11 |  | 2016-10-18 | 8.369 | 5.32 |  | 3.049 |  |  | 3.049
2.6 | Replacement of ECO coils (unit 3) | Scheme | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 |  | 2013-01-11 |  | 2016-08-04 | 2016-01-11 |  | 2016-10-13 | 6.032 | 3.4728 |  | 2.5592 |  |  | 2.5592
2.7 | Replacement of old LT AHP pump impeller by energy efficient stainless steel impeller | Scheme | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 |  | 2013-01-11 |  | 2015-06-30 | 2016-01-11 |  | 2015-11-30 | 0.14881 | 0.14881 |  | 0 |  |  | 0
0 | IDC | IDC | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 |  | 2013-01-11 |  | - | - |  | - | 0.93 | 0 |  | 0.93 |  |  | 0.93
3 | Measuring and Monitoring of Coal consumption | DPR | MERC/CAPEX/20122013/00912 | 2012-07-24 |  | 2012-07-24 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
3.1 | Belt Weighers | Scheme | MERC/CAPEX/20122013/00912 | 2012-07-24 |  | 2012-07-24 |  | - | 2014-07-24 |  | - | 0.8044 | 0 |  | 0.8044 |  |  | 0.8044
3.2 | Fully automatic pit-less in motion weigh bridges | Scheme | MERC/CAPEX/20122013/00912 | 2012-07-24 |  | 2012-07-24 |  | - | 2014-07-24 |  | - | 0.4115 | 0 |  | 0.4115 |  |  | 0.4115
3.3 | Installation side arm charger for Wagon tippler 1A & 1B | Scheme | MERC/CAPEX/20122013/00912 | 2012-07-24 |  | 2012-07-24 |  | - | 2014-07-24 |  | - | 21.96 | 0 |  | 21.96 |  |  | 21.96
3.4 | Dust Extraction System at Secondary Crusher house & Conveyor 6A/B at stage II CHP | Scheme | MERC/CAPEX/20122013/00912 | 2012-07-24 |  | 2012-07-24 |  | - | 2014-07-24 |  | - | 2.0715 | 0 |  | 2.0715 |  |  | 2.0715
3.5 | Fogging system at a) WT old along with PCR, SCR and bunker level belt at Stage I CHP b) Conveyor 7A/B c) 100 Mtrx100 Mtr Coal stock area d) 200 Mtrx200 Mtr Coal stock area | Scheme | MERC/CAPEX/20122013/00912 | 2012-07-24 |  | 2012-07-24 |  | 2014-02-06 | 2014-07-24 |  | 2018-06-26 | 2.2831 | 0.46954 |  | 1.8136 |  |  | 1.8136
3.6 | Bunker level montoring system for 12 bunkers | Scheme | MERC/CAPEX/20122013/00912 | 2012-07-24 |  | 2012-07-24 |  | - | 2014-07-24 |  | - | 2.5038 | 0 |  | 2.5038 |  |  | 2.5038
3.7 | Rotary pneumatic or electrical hammers | Scheme | MERC/CAPEX/20122013/00912 | 2012-07-24 |  | 2012-07-24 |  | - | 2014-07-24 |  | - | 0.097 | 0 |  | 0.097 |  |  | 0.097
3.8 | Enhancement of unloading capacity of CHP from 360 TPH to 500 TPH | Scheme | MERC/CAPEX/20122013/00912 | 2012-07-24 |  | 2012-07-24 |  | - | 2014-07-24 |  | - | 7.6508 | 0 |  | 7.6508 |  |  | 7.6508
3.9 | Quick detection of poor coal quality through CCTV on overhead watch tower focused onto the wagons, over which the rake passes at low speed & various conveyor tunnels | Scheme | MERC/CAPEX/20122013/00912 | 2012-07-24 |  | 2012-07-24 |  | - | 2014-07-24 |  | - | 0.2968 | 0 |  | 0.2968 |  |  | 0.2968
3.1 | Motor controller for conveyor motors of Stage II CHP | Scheme | MERC/CAPEX/20122013/00912 | 2012-07-24 |  | 2012-07-24 |  | 2012-07-24 | 2014-07-24 |  | 2013-03-31 | 0.9607 | 0.9607 |  | 0 |  |  | 0
3.11 | Procurement of a CHN apparatus for ultimate analysis for operational optimization and coal mapping studies. | Scheme | MERC/CAPEX/20122013/00912 | 2012-07-24 |  | 2012-07-24 |  | - | 2014-07-24 |  | - | 0.63617 | 0 |  | 0.63617 |  |  | 0.63617
3.12 | Additional bomb calorimeter | Scheme | MERC/CAPEX/20122013/00912 | 2012-07-24 |  | 2012-07-24 |  | 2013-10-14 | 2014-07-24 |  | 2014-04-07 | 0.44012 | 0.19 |  | 0.25012 |  |  | 0.25012
3.13 | TGA analysis of the coal for operational optimization. | Scheme | MERC/CAPEX/20122013/00912 | 2012-07-24 |  | 2012-07-24 |  | - | 2014-07-24 |  | - | 0.53214 | 0 |  | 0.53214 |  |  | 0.53214
0 | IDC | IDC | MERC/CAPEX/20122013/00912 | 2012-07-24 |  | 2012-07-24 |  | - | - |  | - | 5.27 | 0 |  | 5.27 |  |  | 5.27
4 | Turbine Auxiliary Performance Improvements | DPR | MERC/CAPEX/20122013/00912 | 2013-01-07 |  | 2013-01-07 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
4.1 | Procurement and installation and commissioning of modified upgraded boiler feed pump (Type -200KHI/S) having energy efficient cartridge for unit 2 & 3 , BTPS. | Scheme | MERC/CAPEX/20122013/00912 | 2013-01-07 |  | 2013-01-07 |  | 2015-08-28 | 2014-01-07 |  | 2016-03-15 | 17.47 | 8.6557 |  | 8.8143 |  |  | 8.8143
4.2 | Replacement of brine pumps with modified pumps complete with S.S material in new WTP | Scheme | MERC/CAPEX/20122013/00912 | 2013-01-07 |  | 2013-01-07 |  | - | 2014-01-07 |  | - | 1.029 | 0.3016 |  | 0.7274 |  |  | 0.7274
0 | IDC | IDC | MERC/CAPEX/20122013/00912 | 2013-01-07 |  | 2013-01-07 |  | - | - |  | - | 1.61 | 0 |  | 1.61 |  |  | 1.61
5 | Replacement of Platen water wall coils U#2,Super Heater & Platen Super Heater Coils for U#2 and Cold Reheater coils for U#2 & U#3 | DPR | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 |  | 2014-10-16 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
5.1 | Supply & Erection of Platen Water wall coils Assembly from inlet header to outlet header in pent house for Unit No 2 | Scheme | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 |  | 2014-10-16 |  | 2014-11-15 | 2015-10-16 |  | 2014-11-15 | 1.104 | 0.54 |  | 0.564 |  |  | 0.564
5.2 | Complete Supply & Erection of Super Heater Radiant Roof Panel Tube with Attachment for Unit No 2 Boiler From front side of Boiler to rear side of boiler & Vertical Platen Super Heater coils Assembly for Unit No 2, 210 MW Boiler. | Scheme | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 |  | 2014-10-16 |  | 2015-08-11 | 2015-10-16 |  | 2015-10-12 | 5.477 | 5.4649 |  | 0.012096 |  |  | 0.012096
5.3 | Supply & Erection of Reheater front Pendent Assembly consisting Full set of Cold Reheater coil assembly For Unit No 2 with necessary attachments, Crown Plate. Heat shield, roof seal bend, steam cooled spacer tube with necessary attachment. | Scheme | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 |  | 2014-10-16 |  | 2014-10-17 | 2015-10-16 |  | - | 2.711 | 2.6625 |  | 0.048544 |  |  | 0.048544
5.4 | Supply & Erection of Reheater front Pendent Assembly consisting Full set of Cold Reheater coil assembly For Unit No 3 with necessary attachments, Crown Plate. Heat shield, roof seal bend, steam cooled spacer tube with necessary attachment. | Scheme | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 |  | 2014-10-16 |  | 2014-11-01 | 2015-10-16 |  | 2015-02-16 | 2.711 | 2.3531 |  | 0.3579 |  |  | 0.3579
0 | IDC | IDC | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 |  | 2014-10-16 |  | - | - |  | - | 1.689 | 0 |  | 1.689 |  |  | 1.689
6 | Boiler Process Improvement by replacement of damaged valves and Boiler Perfm Imp by Air Pre-Heater Up gradation of U#2 & U#3 at BTPS | DPR | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 |  | 2014-06-02 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
6.1 | Replacement of boiler outlet valves and damaged valves of units 2 & 3 | Scheme | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 |  | 2014-06-02 |  | 2014-06-03 | 2017-06-02 |  | 2015-10-20 | 2.62 | 1.3984 |  | 1.2216 |  |  | 1.2216
6.2 | Air pre heater up gradation of heat exchanger matrix & regenerative dynamic sealing of units 2 & 3 | Scheme | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 |  | 2014-06-02 |  | 2014-06-03 | 2017-06-02 |  | 2015-08-31 | 13.405 | 1.2086 |  | 12.1964 |  |  | 12.1964
0 | IDC | IDC | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 |  | 2014-06-02 |  | - | - |  | - | 1.345 | 0 |  | 1.345 |  |  | 1.345
8 | Stack management by procurement of Bulldozer & LOCO and CHP area schemes for performance & unloading improvement | DPR | MERC/CAPEX/20162017/01426 | 2017-02-02 |  | 2017-02-02 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
8.1 | Procurement of Locomotive 800 HP (2 No.’s) | Scheme | MERC/CAPEX/20162017/01426 | 2017-02-02 |  | 2017-02-02 |  | 2018-06-11 | 2018-02-02 |  | 1st loco - 23-11-2018 2nd loco -13-02-2019 | 1.0396 | 1.0135 |  | 0.02611 |  |  | 0.02611
8.2 | Procurement of 2 No’s of Bulldozer Model D-155(2 No.’s) | Scheme | MERC/CAPEX/20162017/01426 | 2017-02-02 |  | 2017-02-02 |  | 2017-06-17 | 2018-02-02 |  | 2017-09-13 | 0.53802 | 0.72969 |  | -0.19167 |  |  | -0.19167
8.3 | Modification below primary crusher chutes 15A/B & Conv.02 | Scheme | MERC/CAPEX/20162017/01426 | 2017-02-02 |  | 2017-02-02 |  | 2018-01-21 | 2019-02-02 |  | 2018-02-01 | 0.090248 | 0.079869 |  | 0.010379 |  |  | 0.010379
8.4 | New helical gear box for various conveyors | Scheme | MERC/CAPEX/20162017/01426 | 2017-02-02 |  | 2017-02-02 |  | - | - |  | - | 0.16661 | 0 |  | 0.16661 |  |  | 0.16661
8.5 | Procurement of Elecon Make Ring Granulator Type TK-09-38B | Scheme | MERC/CAPEX/20162017/01426 | 2017-02-02 |  | 2017-02-02 |  | - | - |  | - | 0.11281 | 0 |  | 0.11281 |  |  | 0.11281
8.6 | Procurement of Elecon Make Ring Granulator Type TK6 32B Ring Granulator | Scheme | MERC/CAPEX/20162017/01426 | 2017-02-02 |  | 2017-02-02 |  | - | - |  | - | 0.071157 | 0 |  | 0.071157 |  |  | 0.071157
0 | IDC | IDC | MERC/CAPEX/20162017/01426 | 2017-02-02 |  | 2017-02-02 |  | - | - |  | - | 0.074628 | 0 |  | 0.074628 |  |  | 0.074628
14 | Upgradation of Symphony Harmony DCS, 220V 1285 AH Battery & Charger and Replacement of 6.6 kV HT MOCB by VCB at BTPS, Bhusawal | DPR | MERC/CAPEX/20162017/01426 | 2019-10-22 |  | 2019-10-22 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
14.1 | HMI Up-gradation of Symphony Harmony DCS Unit-3, 210MW, BTPS. | Scheme | MERC/CAPEX/2019-2020/915 | 2019-10-22 |  | 2019-10-22 |  | 2019-07-09 | 2020-10-22 |  | - | 5.54 | 0 |  | 5.54 |  |  | 5.54
14.2 | Supply, erection, commissioning and site testing of Plante 220V DC, 1285 AH, Station Battery Set and charging equipment for 1285 AH Plante battery for Unit 3. | Scheme | MERC/CAPEX/2019-2020/915 | 2019-10-22 |  | 2019-10-22 |  | 2021-09-13 | 2020-10-22 |  | 2021-09-27 | 1.7186 | 1.7186 |  | 0 |  |  | 0
14.3 | Retrofitting of 6.6 kv breakers of unit -3 along without door plant boards by vacuum circuit breakers. | Scheme | MERC/CAPEX/2019-2020/915 | 2019-10-22 |  | 2019-10-22 |  | 2020-02-26 | 2020-10-22 |  | 2022-07-20 | 6.47 | 6.1083 |  | 0.36173 |  |  | 0.36173
0 | IDC | IDC | MERC/CAPEX/2019-2020/915 | 2019-10-22 |  | 2019-10-22 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR-5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | DPR | MERC/CAPEX/2019-2020/915 | 2014-11-25 |  | 2014-11-25 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 5.1 | Bhusawal: Procurement of HT motors (Coal Mill/CEP/CWP) for U-3 | Scheme | MERC/CAPEX/2019-2020/915 | 2014-11-25 |  | 2014-11-25 |  | 2016-07-25 | 2016-11-25 |  | 2018-12-17 | 1.91 | 0.69703 |  | 1.213 |  |  | 1.213
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | DPR | MERC/CAPEX/20162017/00423 | 2016-08-03 |  | 2016-08-03 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 6.1 | Bhusawal: Unit 2-3 (1 Nos.) | Scheme | MERC/CAPEX/20162017/00423 | 2016-08-03 |  | 2016-08-03 |  | 2019-01-31 | 2018-08-03 |  | 2019-06-05 | 1.3258 | 0.9384 |  | 0.38735 |  |  | 0.38735
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | DPR | MERC/CAPEX/20162017/00423 | 2016-09-30 |  | 2016-09-30 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 7.1 | Bhusawal: Unit 2-3 | Scheme | MERC/CAPEX/20162017/00423 | 2016-09-30 |  | 2016-09-30 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | DPR | MERC/CAPEX/20162017/00423 | 2022-02-12 |  | 2022-02-12 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 13.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | Scheme | MERC/CAPEX/20162017/00423 | 2022-02-12 |  | 2022-02-12 |  | - | - |  | - | 54.24 | 0 |  | 54.24 |  |  | 54.24
0 | IDC | IDC | MERC/CAPEX/20162017/00423 | 2022-02-12 |  | 2022-02-12 |  | - | - |  | - | 2.76 | 0 |  | 2.76 |  |  | 2.76
HO DPR 16 | Centralized Monitoring Solution | DPR | MERC/CAPEX/20162017/00423 | 2023-11-02 |  | 2023-11-02 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 16.1 | Centralized Monitoring Solution | Scheme | MERC/CAPEX/20162017/00423 | 2023-11-02 |  | 2023-11-02 |  | - | - |  | - | 66.009 | 0 |  | 66.009 |  |  | 66.009
0 | IDC | IDC | MERC/CAPEX/20162017/00423 | 2023-11-02 |  | 2023-11-02 |  | - | - |  | - | 3.3 | 0 |  | 3.3 |  |  | 3.3
Formulas:
Project Start Date = [MERC Approval Date]

## F4.2
| MSPGCL: Bhusawal U # 3 | [54 empty] | DPR | Not Initiated
| MTR Petition Formats - Generation | [54 empty] | Scheme | WIP
| Form 4.2: Capitalisation Plan | [54 empty] | IDC | Partially Capitalised
Sr. No. | Project Code | DPR | MERC Approval No. | Date of Submission | MERC Approval Date | Cost as per DPR Crs. | MERC Approved Cost | Debt Equity Ratio | Grant Funding | Approved Start Date | Actual Start Date | Approved Date of Completion | Actual Date of Completion | Benefits in Quantified Terms | Capital Expenditure | [12 empty] | Physical Progress (%) | [11 empty] | Capitalisation | [12 empty] | Old Asset retired against capitalised item (in Rs. Cr) | Remarks | Current Status | Non-DPR | Capitalised
[15 empty] | Actual Capex till FY 2018-19 | Actual | Actual | Actual | Actual Capex till FY 2021-22 | Actual | Actual | Revised Projected | Projected | Projected | Projected | Projected | Projected | Actual Progress till FY 2018-19 | Actual | Actual | Actual | Actual | Actual | Revised Projected | Projected | Projected | Projected | Projected | Projected | Actual Capitalization till FY 2018-19 | Actual | Actual | Actual | Actual Capitalization till FY 2021-22 | Actual | Actual | Revised Projected | Projected | Projected | Projected | Projected | Projected |  |  |  |  | Cancelled
[16 empty] | FY 2019-20 | FY 2020-21 | FY 2021-22 |  | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 |  | FY 2019-20 | FY 2020-21 | FY 2021-22 | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 |  | FY 2019-20 | FY 2020-21 | FY 2021-22 |  | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 |  |  |  |  | To be cancelled
[55 empty] | N.A. |  | N.A.
| A) DPR Schemes | [53 empty] | N.A. |  | To be confirmed
| (i) In-principle approved by MERC | [53 empty] | N.A.
1 | Replacement of economizer & LTSH coils at Unit # 2 | DPR | MERC/CAPEX/20122013/00179 | 2011-10-10 | 2012-04-23 | 10.178 | 10.178 |  |  | 2012-04-23 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
1.1 | Replacement of Economiser Coil | Scheme | MERC/CAPEX/20122013/00179 | 2011-10-10 | 2012-04-23 | 3.524 | 3.524 |  |  | 2012-04-23 | 2011-08-30 | 2013-04-23 | 2011-09-27 | • Reduction in Boiler Tube leakages. • Increasing loadability of unit. • Reduction in DM Water consumption. • Improvement in performance of unit. • Improvement in Boiler efficiency. | 3.47 |  |  |  | 3.47 | [8 empty] | 100% | [11 empty] | 3.47 |  |  |  | 3.47 | [9 empty] | Capitalization done in FY-2011-12 of Rs.3.47 Cr.. | Capitalised
| IDC | IDC | MERC/CAPEX/20122013/00179 | 2011-10-10 | 2012-04-23 | 0.203 | 0.203 |  |  | 2012-04-23 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | N.A.
1.2 | Replacement of LTSH Coil | Scheme | MERC/CAPEX/20122013/00179 | 2011-10-10 | 2012-04-23 | 6.094 | 6.094 |  |  | 2012-04-23 | 2011-08-30 | 2013-04-23 | 2011-09-27 | • Reduction in Boiler Tube leakages. • Increasing availability of units. • Improving reliability of unit. • Reduction in DM Water consumption. • Improvement in performance of unit. | 5.32 |  |  |  | 5.32 | [8 empty] | 100% | [11 empty] | 5.32 |  |  |  | 5.32 | [9 empty] | Capitalization done in FY-2011-12 of Rs.5.32 Cr. | Capitalised
| IDC | IDC | MERC/CAPEX/20122013/00179 | 2011-10-10 | 2012-04-23 | 0.357 | 0.357 |  |  | 2012-04-23 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | N.A.
2 | Boiler and Turbine improvement (Station Heat Rate Improvement) | DPR | MERC/TECH 1/CAPEX/20122013/02325 | 2011-12-01 | 2013-01-11 | 16.783 | 16.7838 |  |  | 2013-01-11 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
2.1 | Vent condenser performance improvement by replacement of eroded tube nest by unit 3. | Scheme | MERC/TECH 1/CAPEX/20122013/02325 | 2011-12-01 | 2013-01-11 | 0.286 | 0.286 |  |  | 2013-01-11 |  | 2016-01-11 |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [9 empty] | The scheme implemented via R&M expenditure. | Cancelled
2.2 | Replacement of major extraction valves &NRVs of unit 3 | Scheme | MERC/TECH 1/CAPEX/20122013/02325 | 2011-12-01 | 2013-01-11 | 0.519 | 0.519 |  |  | 2013-01-11 |  | 2016-01-11 |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [9 empty] | Deffered | Not Initiated
2.3 | 60% replacement of boiler skin insulation (Unit 2) | Scheme | MERC/TECH 1/CAPEX/20122013/02325 | 2011-12-01 | 2013-01-11 | 0.293 | 0.293 |  |  | 2013-01-11 |  | 2016-01-11 |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [9 empty] | Deffered | Not Initiated
2.4 | Replacement of DM make up ( unit 3) and GSH water pump.( units 2 &3) | Scheme | MERC/TECH 1/CAPEX/20122013/02325 | 2011-12-01 | 2013-01-11 | 0.206 | 0.206 |  |  | 2013-01-11 | 2013-10-07 | 2016-01-11 |  |  | 0.26354 |  |  |  | 0.26354 | [8 empty] | 100% | [11 empty] | 0.26354 |  |  |  | 0.26354 | [9 empty] | Capitalization done in FY-2015-16 of Rs.0.26 Cr. | Capitalised
2.5 | Replacement of LTSH coils (unit 3) | Scheme | MERC/TECH 1/CAPEX/20122013/02325 | 2011-12-01 | 2013-01-11 | 8.369 | 8.369 |  |  | 2013-01-11 | 2016-08-04 | 2016-01-11 | 2016-10-18 | • Reduction in Boiler Tube leakages. • Increasing loadability of unit. • Reduction in DM Water consumption. | 5.32 |  |  |  | 5.32 | [8 empty] | 100% | [11 empty] | 5.32 |  |  |  | 5.32 | [9 empty] | Capitalization done in FY-2016-17 of Rs.5.32 Cr. | Capitalised
2.6 | Replacement of ECO coils (unit 3) | Scheme | MERC/TECH 1/CAPEX/20122013/02325 | 2011-12-01 | 2013-01-11 | 6.032 | 6.032 |  |  | 2013-01-11 | 2016-08-04 | 2016-01-11 | 2016-10-13 | • Improving reliability of unit. • Reduction in DM Water consumption. • Reduction in Boiler Tube leakages. • Improvement in performance of unit. | 3.4728 |  |  |  | 3.4728 | [8 empty] | 100% | [11 empty] | 3.4728 |  |  |  | 3.4728 | [9 empty] | Capitalization done in FY-2016-17 of Rs.3.47 Cr. | Capitalised
2.7 | Replacement of old LT AHP pump impeller by energy efficient stainless steel impeller | Scheme | MERC/TECH 1/CAPEX/20122013/02325 | 2011-12-01 | 2013-01-11 | 0.148 | 0.14881 |  |  | 2013-01-11 | 2015-06-30 | 2016-01-11 | 2015-11-30 |  | 0.14881 |  |  |  | 0.14881 | [8 empty] | 100% | [11 empty] | 0.14881 |  |  |  | 0.14881 | [9 empty] | Capitalization done in FY-2015-16 of Rs.0.15 Cr. | Capitalised
| IDC | IDC | MERC/TECH 1/CAPEX/20122013/02325 | 2011-12-01 | 2013-01-11 | 0.93 | 0.93 |  |  | 2013-01-11 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | N.A.
3 | Measuring and Monitoring of Coal consumption | DPR | MERC/CAPEX/20122013/00912 | 2012-03-12 | 2012-07-24 | 45.918 | 45.918 |  |  | 2012-07-24 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
3.1 | Belt Weighers | Scheme | MERC/CAPEX/20122013/00912 | 2012-03-12 | 2012-07-24 | 0.8044 | 0.8044 |  |  | 2012-07-24 |  | 2014-07-24 |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
3.2 | Fully automatic pit-less in motion weigh bridges | Scheme | MERC/CAPEX/20122013/00912 | 2012-03-12 | 2012-07-24 | 0.4115 | 0.4115 |  |  | 2012-07-24 |  | 2014-07-24 |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
3.3 | Installation side arm charger for Wagon tippler 1A & 1B | Scheme | MERC/CAPEX/20122013/00912 | 2012-03-12 | 2012-07-24 | 21.96 | 21.96 |  |  | 2012-07-24 |  | 2014-07-24 |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
3.4 | Dust Extraction System at Secondary Crusher house & Conveyor 6A/B at stage II CHP | Scheme | MERC/CAPEX/20122013/00912 | 2012-03-12 | 2012-07-24 | 2.0715 | 2.0715 |  |  | 2012-07-24 |  | 2014-07-24 |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
3.5 | Fogging system at a) WT old along with PCR, SCR and bunker level belt at Stage I CHP b) Conveyor 7A/B c) 100 Mtrx100 Mtr Coal stock area d) 200 Mtrx200 Mtr Coal stock area | Scheme | MERC/CAPEX/20122013/00912 | 2012-03-12 | 2012-07-24 | 2.2831 | 2.2831 |  |  | 2012-07-24 | 2014-02-06 | 2014-07-24 | 2018-06-26 | Fugitive dust will be controlled. | 0.46954 |  |  |  | 0.46954 | [8 empty] | 100% | [11 empty] | 0.46954 |  |  |  | 0.46954 | [10 empty] | Capitalised
3.6 | Bunker level montoring system for 12 bunkers | Scheme | MERC/CAPEX/20122013/00912 | 2012-03-12 | 2012-07-24 | 2.5038 | 2.5038 |  |  | 2012-07-24 |  | 2014-07-24 |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
3.7 | Rotary pneumatic or electrical hammers | Scheme | MERC/CAPEX/20122013/00912 | 2012-03-12 | 2012-07-24 | 0.097 | 0.097 |  |  | 2012-07-24 |  | 2014-07-24 |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
3.8 | Enhancement of unloading capacity of CHP from 360 TPH to 500 TPH | Scheme | MERC/CAPEX/20122013/00912 | 2012-03-12 | 2012-07-24 | 7.6508 | 7.6508 |  |  | 2012-07-24 |  | 2014-07-24 |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
3.9 | Quick detection of poor coal quality through CCTV on overhead watch tower focused onto the wagons, over which the rake passes at low speed & various conveyor tunnels | Scheme | MERC/CAPEX/20122013/00912 | 2012-03-12 | 2012-07-24 | 0.2968 | 0.2968 |  |  | 2012-07-24 |  | 2014-07-24 |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
3.1 | Motor controller for conveyor motors of Stage II CHP | Scheme | MERC/CAPEX/20122013/00912 | 2012-03-12 | 2012-07-24 | 0.9607 | 0.9607 |  |  | 2012-07-24 | 2012-07-24 | 2014-07-24 | 2013-03-31 | We can monitor the condition of coal & hence work monitoring system will be improved. | 0.9607 |  |  |  | 0.9607 | [8 empty] | 100% | [11 empty] | 0.9607 |  |  |  | 0.9607 | [10 empty] | Capitalised
3.11 | Procurement of a CHN apparatus for ultimate analysis for operational optimization and coal mapping studies. | Scheme | MERC/CAPEX/20122013/00912 | 2012-03-12 | 2012-07-24 | 0.63617 | 0.63617 |  |  | 2012-07-24 |  | 2014-07-24 |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
3.12 | Additional bomb calorimeter | Scheme | MERC/CAPEX/20122013/00912 | 2012-03-12 | 2012-07-24 | 0.44012 | 0.44012 |  |  | 2012-07-24 | 2013-10-14 | 2014-07-24 | 2014-04-07 | Statutory requirement as per CSA | 0.19 |  |  |  | 0.19 | [8 empty] | 100% | [11 empty] | 0.19 |  |  |  | 0.19 | [10 empty] | Capitalised
3.13 | TGA analysis of the coal for operational optimization. | Scheme | MERC/CAPEX/20122013/00912 | 2012-03-12 | 2012-07-24 | 0.53214 | 0.53214 |  |  | 2012-07-24 |  | 2014-07-24 |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | Not Initiated
| IDC | IDC | MERC/CAPEX/20122013/00912 | 2012-03-12 | 2012-07-24 | 5.27 | 5.27 |  |  | 2012-07-24 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | N.A.
4 | Turbine Auxiliary Performance Improvements | DPR | MERC/CAPEX/20122013/02107 | 2012-05-11 | 2013-01-07 | 20.109 | 20.109 |  |  | 2013-01-07 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
4.1 | Procurement and installation and commissioning of modified upgraded boiler feed pump (Type -200KHI/S) having energy efficient cartridge for unit 2 & 3 , BTPS. | Scheme | MERC/CAPEX/20122013/02107 | 2012-05-11 | 2013-01-07 | 17.47 | 17.47 |  |  | 2013-01-07 | 2015-08-28 | 2014-01-07 | 2016-03-15 | • Reduction in auxiliary consumption by installing energy efficient pumps. • Increase in life of equipment. • Reduction in maintenance costs • Increase in efficiency of the pump. • Increase in availability of the equipment. | 8.6041 | 0 | 0 | 0.051572 | 8.6557 | [8 empty] | 100% | [11 empty] | 8.6041 | 0 | 0 | 0.051572 | 8.6557 | [9 empty] | Capitalization done in FY-2015-16 of Rs.8.60 Cr.+Add Cap-0.05 Cr (FY 2021-2022). | Capitalised
4.2 | Replacement of brine pumps with modified pumps complete with S.S material in new WTP | Scheme | MERC/CAPEX/20122013/02107 | 2012-05-11 | 2013-01-07 | 1.029 | 1.029 |  |  | 2013-01-07 |  | 2014-01-07 |  | • Reduction in auxiliary consumption by installing energy efficient pumps. • Increase in life of equipment. • Reduction in maintenance costs • Increase in efficiency of the pump. • Increase in availability of the equipment. | 0.3016 |  |  |  | 0.3016 | [8 empty] | 100% | [11 empty] | 0.3016 |  |  |  | 0.3016 | [9 empty] | Capitalization done in FY-2014-15 of Rs.0.17 & FY-2015-16 of Rs.0.13 Cr. | Capitalised
| IDC | IDC | MERC/CAPEX/20122013/02107 | 2012-05-11 | 2013-01-07 | 1.61 | 1.61 |  |  | 2013-01-07 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | N.A.
5 | Replacement of Platen water wall coils U#2,Super Heater & Platen Super Heater Coils for U#2 and Cold Reheater coils for U#2 & U#3 | DPR | MERC/TECH-1/CAPEX/20142015/006 | 2014-06-09 | 2014-10-16 | 13.692 | 13.692 |  |  | 2014-10-16 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
5.1 | Supply & Erection of Platen Water wall coils Assembly from inlet header to outlet header in pent house for Unit No 2 | Scheme | MERC/TECH-1/CAPEX/20142015/006 | 2014-06-09 | 2014-10-16 | 1.104 | 1.104 |  |  | 2014-10-16 | 2014-11-15 | 2015-10-16 | 2014-11-15 | • Reduction in boiler tube leakage area at least by 1 per year. • Reduction in maintenance costs. • Reduction in Gen Loss in frequent start ups due to BTL. • Increases in loadability and long term availability of the Unit. | 0.54 |  |  |  | 0.54 | [8 empty] | 100% | [11 empty] | 0.54 |  |  |  | 0.54 | [10 empty] | Capitalised
5.2 | Complete Supply & Erection of Super Heater Radiant Roof Panel Tube with Attachment for Unit No 2 Boiler From front side of Boiler to rear side of boiler & Vertical Platen Super Heater coils Assembly for Unit No 2, 210 MW Boiler. | Scheme | MERC/TECH-1/CAPEX/20142015/006 | 2014-06-09 | 2014-10-16 | 5.477 | 5.477 |  |  | 2014-10-16 | 2015-08-11 | 2015-10-16 | 2015-10-12 | • Reduction in boiler tube leakage area at least by 1 per year • Reduction in maintenance costs. • Increases in availability ad loadability and long term availability of the Unit. • Increase in MTBF • Reduction in Heat Loss in frequent start ups due to BTL. | 5.4649 |  |  |  | 5.4649 | [8 empty] | 100% | [11 empty] | 5.4649 |  |  |  | 5.4649 | [10 empty] | Capitalised
5.3 | Supply & Erection of Reheater front Pendent Assembly consisting Full set of Cold Reheater coil assembly For Unit No 2 with necessary attachments, Crown Plate. Heat shield, roof seal bend, steam cooled spacer tube with necessary attachment. | Scheme | MERC/TECH-1/CAPEX/20142015/006 | 2014-06-09 | 2014-10-16 | 2.711 | 2.711 |  |  | 2014-10-16 | 2014-10-17 | 2015-10-16 |  | • Reduction in boiler tube leakage area at least by 1 per year • Increase in MTBF • Reduction in Heat Loss in frequent start ups due to BTL • Increases in loadability and long term availability of the Unit. • Reduction in maintenance costs. | 2.6625 |  |  |  | 2.6625 | [8 empty] | 100% | [11 empty] | 2.6625 |  |  |  | 2.6625 | [9 empty] | Capitalization done in FY-2014-15 of Rs.4.07 & FY-2015-16 of Rs.1.40 Cr. | Capitalised
5.4 | Supply & Erection of Reheater front Pendent Assembly consisting Full set of Cold Reheater coil assembly For Unit No 3 with necessary attachments, Crown Plate. Heat shield, roof seal bend, steam cooled spacer tube with necessary attachment. | Scheme | MERC/TECH-1/CAPEX/20142015/006 | 2014-06-09 | 2014-10-16 | 2.711 | 2.711 |  |  | 2014-10-16 | 2014-11-01 | 2015-10-16 | 2015-02-16 | • Reduction in boiler tube leakage area at least by 1 per year • Increase in MTBF • Reduction in Heat Loss in frequent start ups due to BTL • Increases in loadability and long term availability of the Unit. • Reduction in maintenance costs | 2.3531 |  |  |  | 2.3531 | [8 empty] | 100% | [11 empty] | 2.3531 |  |  |  | 2.3531 | [9 empty] | Capitalization done in FY-2014-15 of Rs.2.35 Cr. | Capitalised
| IDC | IDC | MERC/TECH-1/CAPEX/20142015/006 | 2014-06-09 | 2014-10-16 | 1.689 | 1.689 |  |  | 2014-10-16 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | N.A.
6 | Boiler Process Improvement by replacement of damaged valves and Boiler Perfm Imp by Air Pre-Heater Up gradation of U#2 & U#3 at BTPS | DPR | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-01-02 | 2014-06-02 | 17.37 | 17.37 |  |  | 2014-06-02 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
6.1 | Replacement of boiler outlet valves and damaged valves of units 2 & 3 | Scheme | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-01-02 | 2014-06-02 | 2.62 | 2.62 |  |  | 2014-06-02 | 2014-06-03 | 2017-06-02 | 2015-10-20 | • Replacement of drain valves will reduce steam leakages and passing. • Saving in DM water consumption by 20 MT per day .. • Replacement of Boiler outlet valve will reduce steam leakages and passing (During hydraulic test of boiler no passing is expected). | 1.3984 |  |  |  | 1.3984 | [8 empty] | 100% | [11 empty] | 1.3984 |  |  |  | 1.3984 | [9 empty] | U#2 -Scheme is defered as per competent authority. U#3 - Capitalization done in FY-2014-15 of Rs.0.45 & FY-2015-16 of Rs.0.95 Cr. | Capitalised
6.2 | Air pre heater up gradation of heat exchanger matrix & regenerative dynamic sealing of units 2 & 3 | Scheme | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-01-02 | 2014-06-02 | 13.405 | 13.405 |  |  | 2014-06-02 | 2014-06-03 | 2017-06-02 | 2015-08-31 | • Up gradation of heat exchanger matrix will increase the life of basket there by reduces the frequency of basket replacement. • Upgraded material for heat exchanger matrix will improve heat transfer which will improve APH flue gas outlet temperatures. • Dynamic sealing will improve air pre heater performance • Auxiliary consumption of ID/PA fan will be reduced. | 1.2086 |  |  |  | 1.2086 | [8 empty] | 100% | [11 empty] | 1.2086 |  |  |  | 1.2086 | [9 empty] | Capitalization done in FY-2014-15 of Rs.0.91 & FY-2015-16 of Rs.0.30 Cr. | Capitalised
| IDC | IDC | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-01-02 | 2014-06-02 | 1.345 | 1.345 |  |  | 2014-06-02 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | N.A.
8 | Stack management by procurement of Bulldozer & LOCO and CHP area schemes for performance & unloading improvement | DPR | MERC/CAPEX/20162017/01426 | 2016-02-03 | 2017-02-02 | 2.0931 | 2.0931 |  |  | 2017-02-02 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
8.1 | Procurement of Locomotive 800 HP (2 No.’s) | Scheme | MERC/CAPEX/20162017/01426 | 2016-02-03 | 2017-02-02 | 1.0396 | 1.0396 |  |  | 2017-02-02 | 2018-06-11 | 2018-02-02 | 1st loco - 23-11-2018 2nd loco -13-02-2019 | * Improvement in coal rake movement, shunting operation and placement of coal wagons at different tippler units at CHP-500 MW, BTPS.It results in increase in average unloading rate of rakes. Average unloading rate of coal wagons per hour is increased to 12 wagons/hrs from 6 to 8 wagons /hr at CHP-500 MW, BTPS. * Average unloading of coal wagons per day is increased to 300 to 350.Avg unloading time per rake in hour is reduced from 10 hr to 6 hr since commissioning. * Reduction in demurrage hours & maintain sufficient bunker level by maintaining coal feeding rate due to efficient coal rake movement with the help of new locomotives. * R&M expenditure against the locomotives since commissioning is nil. * Availability & reliability of new locomotives is maximum i.e. 90 to 95 % since commissioning. * Performance and efficiency of locomotives since commissioning is maximum. * Procurement for maintenance against these locomotives since commissioning is almost Nil. * Decrease in downtime of system resulting into overall improvement in system efficiency | 1.0135 |  |  |  | 1.0135 | [8 empty] | 100% | [11 empty] | 1.0135 |  |  |  | 1.0135 | [9 empty] | PO placed vide-HO/4370001547/No-07347 dated 19-06-2018. 1st loco- Material received on dtd. 23-11-2018. Commisioning done on dtd.01-12-2018. 2nd loco - Material received on dtd. 13-02-2019. Commisioning done on dtd.26-03-2019. Total Capitalization done in FY-2018-19 of Rs. 5.84 Cr.. Rs.4.83 Cr. amount capitalized in U#4 & 5 and Rs. 1.01 capitalized in U#3. | Capitalised
8.2 | Procurement of 2 No’s of Bulldozer Model D-155(2 No.’s) | Scheme | MERC/CAPEX/20162017/01426 | 2016-02-03 | 2017-02-02 | 0.53802 | 0.53802 |  |  | 2017-02-02 | 2017-06-17 | 2018-02-02 | 2017-09-13 | * Contribution in reduction of demurrage hours by doing proper coal stack management with help of bulldozers. * For maintaining the proper coal flow rate as per load demand while in reclaiming mode (dozing the coal from remote location to vicinity of the stacker reclaimer area). * O&M expenditure on these bulldozers since commissioning is very less i.e. around 5 to 6.20 % per year asset cost. * Availability and reliability of bulldozers are around 90 to 95% since commissioning. * Performance and efficiency of bulldozers since commissioning is maximum. * Procurement for maintenance against these bulldozers since commissioning is almost nil. * Decrease in downtime of system resulting into overall improvement in system efficiency. | 0.72969 |  |  |  | 0.72969 | [8 empty] | 100% | [11 empty] | 0.72969 |  |  |  | 0.72969 | [9 empty] | PO placed vide-HO/4370001085/No-010160 dated 18-08-2017. Work completed on 13-09-2017. Capitalization done in FY-2017-18 of Rs. 4.2 Cr. Rs. 3.47 Cr. amount capitalized in U#4 & 5 and Rs.0.73 capitalized in U#3. | Capitalised
8.3 | Modification below primary crusher chutes 15A/B & Conv.02 | Scheme | MERC/CAPEX/20162017/01426 | 2016-02-03 | 2017-02-02 | 0.090248 | 0.090248 |  |  | 2017-02-02 | 2018-01-21 | 2019-02-02 | 2018-02-01 | 1)Daily outage of the system is reduced almost 100% 2)Wear and tear of the plates reduced.Due to these scheme system failure reduced in finacial year 20-21 around 20 lakh Rs saving done & in finacial year 21-22 around 17 lakh Rs saving done | 0.079869 |  |  |  | 0.079869 | [8 empty] | 100% | [11 empty] | 0.079869 |  |  |  | 0.079869 | [9 empty] | PO placed vide-HO/4370000471/No-04816 dated 19-07-2017. Work completed on 01-02-2018. Capitalization done in FY-2017-18 of Rs. 0.38 Cr in U#4 &5 and Rs.0.08 in U#3. | Capitalised
8.4 | New helical gear box for various conveyors | Scheme | MERC/CAPEX/20162017/01426 | 2016-02-03 | 2017-02-02 | 0.16661 | 0.16661 |  |  | 2017-02-02 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
8.5 | Procurement of Elecon Make Ring Granulator Type TK-09-38B | Scheme | MERC/CAPEX/20162017/01426 | 2016-02-03 | 2017-02-02 | 0.11281 | 0.11281 |  |  | 2017-02-02 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
8.6 | Procurement of Elecon Make Ring Granulator Type TK6 32B Ring Granulator | Scheme | MERC/CAPEX/20162017/01426 | 2016-02-03 | 2017-02-02 | 0.071157 | 0.071157 |  |  | 2017-02-02 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
| IDC | IDC | MERC/CAPEX/20162017/01426 | 2016-02-03 | 2017-02-02 | 0.074628 | 0.074628 |  |  | 2017-02-02 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | N.A.
14 | Upgradation of Symphony Harmony DCS, 220V 1285 AH Battery & Charger and Replacement of 6.6 kV HT MOCB by VCB at BTPS, Bhusawal | DPR | MERC/CAPEX/2019-2020/915 | 2019-05-20 | 2019-10-22 | 13.72 | 13.7286 |  |  | 2019-10-22 |  |  |  |  | 0 |  |  |  | 0 | [24 empty] | 0 | [10 empty] | N.A.
14.1 | HMI Up-gradation of Symphony Harmony DCS Unit-3, 210MW, BTPS. | Scheme | MERC/CAPEX/2019-2020/915 | 2019-05-20 | 2019-10-22 | 5.54 | 5.54 |  |  | 2019-10-22 | 2019-07-09 | 2020-10-22 |  | • Asset investment including Spares inventory protected. • Improved System Operation & Monitoring Functions. • Significant avoidance of ‘Generation Loss’; Proposed Upgrades can be implemented in short planned shutdown | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.54 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 100% | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 5.54 | [6 empty] | •Approval for Amendment PO ( Disp No.05342; Date:03-06-2024. •Material awaited | WIP
14.2 | Supply, erection, commissioning and site testing of Plante 220V DC, 1285 AH, Station Battery Set and charging equipment for 1285 AH Plante battery for Unit 3. | Scheme | MERC/CAPEX/2019-2020/915 | 2019-05-20 | 2019-10-22 | 1.71 | 1.7186 |  |  | 2019-10-22 | 2021-09-13 | 2020-10-22 | 2021-09-27 | • 100% availability of Battery Sets • The overall reliability of power plant will increase. • New battery set will help to enhance the life of system. | 0 | 0 | 0 | 1.7186 | 1.7186 | [8 empty] | 0% | 0% | 0% | 100% | [8 empty] | 0 | 0 | 0 | 1.7186 | 1.7186 | [9 empty] | Order dispatched vide PO. No. 4370002528/0144 dtd.11-03-2021. Capitalization done in FY-2021-22 of Rs.1.72 Cr. | Capitalised
14.3 | Retrofitting of 6.6 kv breakers of unit -3 along without door plant boards by vacuum circuit breakers. | Scheme | MERC/CAPEX/2019-2020/915 | 2019-05-20 | 2019-10-22 | 6.47 | 6.47 |  |  | 2019-10-22 | 2020-02-26 | 2020-10-22 | 2022-07-20 | • Improvement in availability of auxiliaries due to reduced problems of breakers. • Reduced down time for the auxiliaries. • Easy handling of breakers and therefore ease of operation. • Reduced incidents of flashovers and increased safety to operating personnel. | 0 | 6.1083 |  |  | 6.1083 | [8 empty] | 0% | 100% | [10 empty] | 0 | 0 | 6.1083 |  | 6.1083 | [9 empty] | Order dispatched vide PO. No. 4370002074/856 dtd.08-11-2019. Capitalization done in FY-2020-21 of Rs.6.11Cr. | Capitalised
| IDC | IDC | MERC/CAPEX/2019-2020/915 | 2019-05-20 | 2019-10-22 | 0 | 0 |  |  | 2019-10-22 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | N.A.
HO DPR-5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | DPR | MERC/TECH 1/CAPEX/20142015/01218 | 2014-10-01 | 2014-11-25 | 1.91 | 1.91 |  |  | 2014-11-25 |  |  |  |  | 0 |  |  |  | 0 | [24 empty] | 0 | [10 empty] | N.A.
HO DPR 5.1 | Bhusawal: Procurement of HT motors (Coal Mill/CEP/CWP) for U-3 | Scheme | MERC/TECH 1/CAPEX/20142015/01218 | 2014-10-01 | 2014-11-25 | 1.91 | 1.91 |  |  | 2014-11-25 | 2016-07-25 | 2016-11-25 | 2018-12-17 | To reduce auxilliary consumption & spares and maintenance cost. To improve reliability of motors. | 0.69703 |  |  |  | 0.69703 | [8 empty] | 100% | [11 empty] | 0.69703 |  |  |  | 0.69703 | [9 empty] | Order dispatched vide PO. No. 4370000782 dtd.08-11-2016. Capitalization done in FY-2018-19 of Rs.0.7 Cr. | Capitalised
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | DPR | MERC/CAPEX/20162017/00423 | 2016-02-03 | 2016-08-03 | 2.6515 | 1.3258 |  |  | 2016-08-03 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
HO DPR 6.1 | Bhusawal: Unit 2-3 (1 Nos.) | Scheme | MERC/CAPEX/20162017/00423 | 2016-02-03 | 2016-08-03 | 2.6515 | 1.3258 |  |  | 2016-08-03 | 2019-01-31 | 2018-08-03 | 2019-06-05 | • Statutory norms of MPCB/CPCB/NGT achieved. • Continuous monitoring of ambient air quality. • Reduction in air pollution. | 0 | 0.9384 |  |  | 0.9384 | [9 empty] | 100% | [10 empty] | 0 | 0.9384 |  |  | 0.9384 | [9 empty] | PO placed vide -HO/4370001152/No-0386 dated 08-01-2019. Capitalization done in FY-2019-20 of Rs.1.88 Cr in U#4 & 5 and Rs.0.94 Cr. In U#3. | Capitalised
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | DPR | MERC/CAPEX/20162017/00774 | 2016-08-26 | 2016-09-30 | 0 | 0 |  |  | 2016-09-30 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
HO DPR 7.1 | Bhusawal: Unit 2-3 | Scheme | MERC/CAPEX/20162017/00774 | 2016-08-26 | 2016-09-30 |  |  |  |  | 2016-09-30 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | To be cancelled
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | DPR | MERC/CAPEX/2021-2022/MSPGCL/063 | 2018-08-31 | 2022-02-12 | 113.91 | 57 |  |  | 2022-02-12 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
HO DPR 13.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | Scheme | MERC/CAPEX/2021-2022/MSPGCL/063 | 2018-08-31 | 2022-02-12 | 108.48 | 54.24 |  |  | 2022-02-12 | [8 empty] | 0 | [20 empty] | 0 | 0 | 0 | 0 | 0 | [10 empty] | To be confirmed
| IDC | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2018-08-31 | 2022-02-12 | 5.43 | 2.76 |  |  | 2022-02-12 | [8 empty] | 0 | [20 empty] | 0 | 0 | 0 | 0 | 0 | [10 empty] | To be confirmed
HO DPR 16 | Centralized Monitoring Solution | DPR | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-03-28 | 2023-11-02 | 69.309 | 69.309 |  |  | 2023-11-02 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
HO DPR 16.1 | Centralized Monitoring Solution | Scheme | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-03-28 | 2023-11-02 | 66.009 | 66.009 |  |  | 2023-11-02 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | To be confirmed
| IDC | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-03-28 | 2023-11-02 | 3.3 | 3.3 |  |  | 2023-11-02 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
[19 empty] | 0 | [24 empty] | 0
[19 empty] | 0 | [24 empty] | 0
| (ii) Submitted to MERC but yet to be approved | [17 empty] | 0 | [24 empty] | 0
[19 empty] | 0 | [24 empty] | 0
| (iii) Yet to be submitted to MERC | [8 empty] | - | [8 empty] | 0 | [24 empty] | 0
| FY 2026-27 | [17 empty] | 0 | [24 empty] | 0
1 | R&M/LE for Identified Thermal units of MSPGCL of BTPS U-3 (210 MW) | DPR | [16 empty] | 0 | [24 empty] | 0
1.1 | R&M/LE for Identified Thermal units of MSPGCL of BTPS U-3 (210 MW) | Scheme | [16 empty] | 0 |  |  |  |  | 398 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 398
[10 empty] | - | [8 empty] | 0 | [24 empty] | 0
| B) Non-DPR Schemes | [8 empty] | - | [8 empty] | 0 | [24 empty] | 0
1 | Design, Supply and Installation for capacity enhancement of conveyor No. 08 at CHP210MW, BTPS. | [8 empty] | - | [5 empty] | 1.8001 |  |  | 1.8001 | [21 empty] | 1.8001 |  |  | 1.8001
2 | SPEAKER & PTZ CAMER | [8 empty] | - | [7 empty] | 0.031968 | 0.031968 | [23 empty] | 0.031968 | 0.031968
3 | 50 INCH TV & 2TN AC | [8 empty] | - | [6 empty] | 0.06453 |  | 0.06453 | [22 empty] | 0.06453 |  | 0.06453
4 | Fixtures & Fitting (10801) | [8 empty] | - | [5 empty] | 0.02209 |  |  | 0.02209 | [21 empty] | 0.02209 |  |  | 0.02209
5 | Office equpment (10901) | [8 empty] | - | [5 empty] | 0.60697 |  |  | 0.60697 | [21 empty] | 0.60697 |  |  | 0.60697
6 | Gearboxes for CHP Elecon Make | [8 empty] | - | [5 empty] | 0.34574 |  |  | 0.34574 | [21 empty] | 0.34574 |  |  | 0.34574
7 | General Assets | [8 empty] | - | [8 empty] | 0 | [24 empty] | 0
8 | Furniture & Fixture | [8 empty] | - | [8 empty] | 0 | 0.0035 | [23 empty] | 0 | 0.0035 |  | 0.09 | [6 empty] | Air Purifier - 13-04-2022 | Capitalised
9 | Office Equipment | [17 empty] | 0 | 0.25886 | [23 empty] | 0 | 0.25886 | [8 empty] | Multifunction Laser Printer - 21-06-2022 Computer System foe 1A Wagon Tippler - 31-05-2022 Thinclient - 20-12-2022 | Capitalised
10 | Furniture & Fixture | [17 empty] | 0 |  | 0.2072 | [22 empty] | 0 |  | 0.2072 | [7 empty] | Exe Chairs and Office Chairs - 08-11-2023 FANS - 30-06-2023 Mid Back Chairs - 14-06-2023 Office Chairs - 01-01-2024 2T Split AC - 30-03-2024 | Capitalised
11 | Office Equipment | [17 empty] | 0 |  | 0.0063897 | [22 empty] | 0 |  | 0.0063897 | [7 empty] | Laser All in One Printer - 26-05-2023 | Capitalised
12 | Land | [17 empty] | 0 | [24 empty] | 0 |  | 0.19434 | [7 empty] | Additional Compensation out of Court Dispute with Land Holder Tryamba Zambre
-
| Total | [13 empty] | 44.6687 | 9.8216 | 0.06453 | 1.8022 | 56.3569 | 0.26236 | 0.21359 | 5.54 | 0 | 398 | 0 | 0 | 0 | [12 empty] | 44.6687 | 3.7133 | 6.1728 | 1.8022 | 56.3569 | 0.26236 | 0.40793 | 5.63 | 0 | 398 | 0 | 0 | 0
[45 empty] | 0.26236 | 0.40793 | 0.09
Formulas:
Approved Start Date = IF([MERC Approval Date]=0,"-",[MERC Approval Date])
Date of Submission = [Date of Submission, row above]
MERC Approval Date = IF([MERC Approval Date, row above]=0,"-",[MERC Approval Date, row above])
Note on M4: SSP-RCD As per the implementation plan submitted in the DPR/ Approved by MERC
Note on H69: SUSHANT: 2 quantity proposed, 1 approved

## F4.3
MSPGCL: Bhusawal U # 3
MTR Petition Formats - Generation
| Project Details |  |  |  |  | Form 4.3: Capital Work-in-progress - Project-wise details | [5 empty] | (Rs. Crore)
Sr. No. | Project Code | MERC Approval No. | MERC Approval Date | Approved Project Cost | Cumulative Expenditure Incurred till beginning of the Year | Capital Expenditure Capitalised | Opening CWIP | Investment during the year | Capital Work in Progress |  |  |  | Closing CWIP
[9 empty] | Works Capitalised | Interest Capitalised | Expenses Capitalised | Total Capitalisation |  | Allowable Capitalisation | Probable Disallowance
FY 2022-23
a) DPR Schemes
(i) In-principle approved by MERC
1 | Replacement of economizer & LTSH coils at Unit # 2 | MERC/CAPEX/20122013/00179 | 2012-04-23 | 10.178 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Replacement of Economiser Coil | MERC/CAPEX/20122013/00179 | 2012-04-23 | 3.524 | 3.47 | 3.47 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/00179 | 2012-04-23 | 0.203 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | Replacement of LTSH Coil | MERC/CAPEX/20122013/00179 | 2012-04-23 | 6.094 | 5.32 | 5.32 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/00179 | 2012-04-23 | 0.357 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Boiler and Turbine improvement (Station Heat Rate Improvement) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 16.7838 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Vent condenser performance improvement by replacement of eroded tube nest by unit 3. | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.286 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Replacement of major extraction valves &NRVs of unit 3 | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.519 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | 60% replacement of boiler skin insulation (Unit 2) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.293 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Replacement of DM make up ( unit 3) and GSH water pump.( units 2 &3) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.206 | 0.26354 | 0.26354 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Replacement of LTSH coils (unit 3) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 8.369 | 5.32 | 5.32 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.6 | Replacement of ECO coils (unit 3) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 6.032 | 3.4728 | 3.4728 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.7 | Replacement of old LT AHP pump impeller by energy efficient stainless steel impeller | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.14881 | 0.14881 | 0.14881 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Measuring and Monitoring of Coal consumption | MERC/CAPEX/20122013/00912 | 2012-07-24 | 45.918 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Belt Weighers | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.8044 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.2 | Fully automatic pit-less in motion weigh bridges | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.4115 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.3 | Installation side arm charger for Wagon tippler 1A & 1B | MERC/CAPEX/20122013/00912 | 2012-07-24 | 21.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.4 | Dust Extraction System at Secondary Crusher house & Conveyor 6A/B at stage II CHP | MERC/CAPEX/20122013/00912 | 2012-07-24 | 2.0715 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.5 | Fogging system at a) WT old along with PCR, SCR and bunker level belt at Stage I CHP b) Conveyor 7A/B c) 100 Mtrx100 Mtr Coal stock area d) 200 Mtrx200 Mtr Coal stock area | MERC/CAPEX/20122013/00912 | 2012-07-24 | 2.2831 | 0.46954 | 0.46954 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.6 | Bunker level montoring system for 12 bunkers | MERC/CAPEX/20122013/00912 | 2012-07-24 | 2.5038 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.7 | Rotary pneumatic or electrical hammers | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.097 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.8 | Enhancement of unloading capacity of CHP from 360 TPH to 500 TPH | MERC/CAPEX/20122013/00912 | 2012-07-24 | 7.6508 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.9 | Quick detection of poor coal quality through CCTV on overhead watch tower focused onto the wagons, over which the rake passes at low speed & various conveyor tunnels | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.2968 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Motor controller for conveyor motors of Stage II CHP | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.9607 | 0.9607 | 0.9607 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.11 | Procurement of a CHN apparatus for ultimate analysis for operational optimization and coal mapping studies. | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.63617 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.12 | Additional bomb calorimeter | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.44012 | 0.19 | 0.19 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.13 | TGA analysis of the coal for operational optimization. | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.53214 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/00912 | 2012-07-24 | 5.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Turbine Auxiliary Performance Improvements | MERC/CAPEX/20122013/02107 | 2013-01-07 | 20.109 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Procurement and installation and commissioning of modified upgraded boiler feed pump (Type -200KHI/S) having energy efficient cartridge for unit 2 & 3 , BTPS. | MERC/CAPEX/20122013/02107 | 2013-01-07 | 17.47 | 8.6557 | 8.6557 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Replacement of brine pumps with modified pumps complete with S.S material in new WTP | MERC/CAPEX/20122013/02107 | 2013-01-07 | 1.029 | 0.3016 | 0.3016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/02107 | 2013-01-07 | 1.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Replacement of Platen water wall coils U#2,Super Heater & Platen Super Heater Coils for U#2 and Cold Reheater coils for U#2 & U#3 | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 13.692 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Supply & Erection of Platen Water wall coils Assembly from inlet header to outlet header in pent house for Unit No 2 | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 1.104 | 0.54 | 0.54 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Complete Supply & Erection of Super Heater Radiant Roof Panel Tube with Attachment for Unit No 2 Boiler From front side of Boiler to rear side of boiler & Vertical Platen Super Heater coils Assembly for Unit No 2, 210 MW Boiler. | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 5.477 | 5.4649 | 5.4649 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Supply & Erection of Reheater front Pendent Assembly consisting Full set of Cold Reheater coil assembly For Unit No 2 with necessary attachments, Crown Plate. Heat shield, roof seal bend, steam cooled spacer tube with necessary attachment. | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 2.711 | 2.6625 | 2.6625 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Supply & Erection of Reheater front Pendent Assembly consisting Full set of Cold Reheater coil assembly For Unit No 3 with necessary attachments, Crown Plate. Heat shield, roof seal bend, steam cooled spacer tube with necessary attachment. | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 2.711 | 2.3531 | 2.3531 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 1.689 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Boiler Process Improvement by replacement of damaged valves and Boiler Perfm Imp by Air Pre-Heater Up gradation of U#2 & U#3 at BTPS | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 17.37 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Replacement of boiler outlet valves and damaged valves of units 2 & 3 | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 2.62 | 1.3984 | 1.3984 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.2 | Air pre heater up gradation of heat exchanger matrix & regenerative dynamic sealing of units 2 & 3 | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 13.405 | 1.2086 | 1.2086 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 1.345 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Stack management by procurement of Bulldozer & LOCO and CHP area schemes for performance & unloading improvement | MERC/CAPEX/20162017/01426 | 2017-02-02 | 2.0931 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement of Locomotive 800 HP (2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 1.0396 | 1.0135 | 1.0135 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Procurement of 2 No’s of Bulldozer Model D-155(2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.53802 | 0.72969 | 0.72969 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.3 | Modification below primary crusher chutes 15A/B & Conv.02 | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.090248 | 0.079869 | 0.079869 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.4 | New helical gear box for various conveyors | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.16661 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.5 | Procurement of Elecon Make Ring Granulator Type TK-09-38B | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.11281 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.6 | Procurement of Elecon Make Ring Granulator Type TK6 32B Ring Granulator | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.071157 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.074628 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Upgradation of Symphony Harmony DCS, 220V 1285 AH Battery & Charger and Replacement of 6.6 kV HT MOCB by VCB at BTPS, Bhusawal | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 13.7286 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | HMI Up-gradation of Symphony Harmony DCS Unit-3, 210MW, BTPS. | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 5.54 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Supply, erection, commissioning and site testing of Plante 220V DC, 1285 AH, Station Battery Set and charging equipment for 1285 AH Plante battery for Unit 3. | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 1.7186 | 1.7186 | 1.7186 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Retrofitting of 6.6 kv breakers of unit -3 along without door plant boards by vacuum circuit breakers. | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 6.47 | 6.1083 | 6.1083 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 1.91 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.1 | Bhusawal: Procurement of HT motors (Coal Mill/CEP/CWP) for U-3 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 1.91 | 0.69703 | 0.69703 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.1 | Bhusawal: Unit 2-3 (1 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0.9384 | 0.9384 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.1 | Bhusawal: Unit 2-3 | MERC/CAPEX/20162017/00774 | 2016-09-30 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 13.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (ii) Submitted to MERC but yet to be approved |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (iii) Yet to be submitted to MERC |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| FY 2026-27 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | R&M/LE for Identified Thermal units of MSPGCL of BTPS U-3 (210 MW) |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | R&M/LE for Identified Thermal units of MSPGCL of BTPS U-3 (210 MW) |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| B) Non-DPR Schemes |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Design, Supply and Installation for capacity enhancement of conveyor No. 08 at CHP210MW, BTPS. |  |  | 0 | 1.8001 | 1.8001 | 0 | 0 | 0 |  |  | 0 | 0
2 | SPEAKER & PTZ CAMER |  |  | 0 | 0.031968 | 0.031968 | 0 | 0 | 0 |  |  | 0 | 0
3 | 50 INCH TV & 2TN AC |  |  | 0 | 0.06453 | 0.06453 | 0 | 0 | 0 |  |  | 0 | 0
4 | Fixtures & Fitting (10801) |  |  | 0 | 0.02209 | 0.02209 | 0 | 0 | 0 |  |  | 0 | 0
5 | Office equpment (10901) |  |  | 0 | 0.60697 | 0.60697 | 0 | 0 | 0 |  |  | 0 | 0
6 | Gearboxes for CHP Elecon Make |  |  | 0 | 0.34574 | 0.34574 | 0 | 0 | 0 |  |  | 0 | 0
7 | General Assets |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Furniture & Fixture |  |  | 0 | 0 | 0 | 0 | 0.0035 | 0.0035 |  |  | 0.0035 | 0
9 | Office Equipment |  |  | 0 | 0 | 0 | 0 | 0.25886 | 0.25886 |  |  | 0.25886 | 0
10 | Furniture & Fixture |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Office Equipment |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Land |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 56.3569 | 56.3569 | 0 | 0.26236 | 0.26236 | 0 | 0 | 0.26236 | 0
FY 2023-24
a) DPR Schemes
(i) In-principle approved by MERC
1 | Replacement of economizer & LTSH coils at Unit # 2 | MERC/CAPEX/20122013/00179 | 2012-04-23 | 10.178 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Replacement of Economiser Coil | MERC/CAPEX/20122013/00179 | 2012-04-23 | 3.524 | 3.47 | 3.47 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/00179 | 2012-04-23 | 0.203 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | Replacement of LTSH Coil | MERC/CAPEX/20122013/00179 | 2012-04-23 | 6.094 | 5.32 | 5.32 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/00179 | 2012-04-23 | 0.357 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Boiler and Turbine improvement (Station Heat Rate Improvement) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 16.7838 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Vent condenser performance improvement by replacement of eroded tube nest by unit 3. | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.286 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Replacement of major extraction valves &NRVs of unit 3 | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.519 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | 60% replacement of boiler skin insulation (Unit 2) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.293 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Replacement of DM make up ( unit 3) and GSH water pump.( units 2 &3) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.206 | 0.26354 | 0.26354 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Replacement of LTSH coils (unit 3) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 8.369 | 5.32 | 5.32 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.6 | Replacement of ECO coils (unit 3) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 6.032 | 3.4728 | 3.4728 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.7 | Replacement of old LT AHP pump impeller by energy efficient stainless steel impeller | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.14881 | 0.14881 | 0.14881 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Measuring and Monitoring of Coal consumption | MERC/CAPEX/20122013/00912 | 2012-07-24 | 45.918 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Belt Weighers | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.8044 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.2 | Fully automatic pit-less in motion weigh bridges | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.4115 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.3 | Installation side arm charger for Wagon tippler 1A & 1B | MERC/CAPEX/20122013/00912 | 2012-07-24 | 21.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.4 | Dust Extraction System at Secondary Crusher house & Conveyor 6A/B at stage II CHP | MERC/CAPEX/20122013/00912 | 2012-07-24 | 2.0715 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.5 | Fogging system at a) WT old along with PCR, SCR and bunker level belt at Stage I CHP b) Conveyor 7A/B c) 100 Mtrx100 Mtr Coal stock area d) 200 Mtrx200 Mtr Coal stock area | MERC/CAPEX/20122013/00912 | 2012-07-24 | 2.2831 | 0.46954 | 0.46954 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.6 | Bunker level montoring system for 12 bunkers | MERC/CAPEX/20122013/00912 | 2012-07-24 | 2.5038 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.7 | Rotary pneumatic or electrical hammers | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.097 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.8 | Enhancement of unloading capacity of CHP from 360 TPH to 500 TPH | MERC/CAPEX/20122013/00912 | 2012-07-24 | 7.6508 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.9 | Quick detection of poor coal quality through CCTV on overhead watch tower focused onto the wagons, over which the rake passes at low speed & various conveyor tunnels | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.2968 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Motor controller for conveyor motors of Stage II CHP | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.9607 | 0.9607 | 0.9607 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.11 | Procurement of a CHN apparatus for ultimate analysis for operational optimization and coal mapping studies. | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.63617 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.12 | Additional bomb calorimeter | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.44012 | 0.19 | 0.19 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.13 | TGA analysis of the coal for operational optimization. | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.53214 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/00912 | 2012-07-24 | 5.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Turbine Auxiliary Performance Improvements | MERC/CAPEX/20122013/02107 | 2013-01-07 | 20.109 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Procurement and installation and commissioning of modified upgraded boiler feed pump (Type -200KHI/S) having energy efficient cartridge for unit 2 & 3 , BTPS. | MERC/CAPEX/20122013/02107 | 2013-01-07 | 17.47 | 8.6557 | 8.6557 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Replacement of brine pumps with modified pumps complete with S.S material in new WTP | MERC/CAPEX/20122013/02107 | 2013-01-07 | 1.029 | 0.3016 | 0.3016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/02107 | 2013-01-07 | 1.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Replacement of Platen water wall coils U#2,Super Heater & Platen Super Heater Coils for U#2 and Cold Reheater coils for U#2 & U#3 | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 13.692 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Supply & Erection of Platen Water wall coils Assembly from inlet header to outlet header in pent house for Unit No 2 | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 1.104 | 0.54 | 0.54 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Complete Supply & Erection of Super Heater Radiant Roof Panel Tube with Attachment for Unit No 2 Boiler From front side of Boiler to rear side of boiler & Vertical Platen Super Heater coils Assembly for Unit No 2, 210 MW Boiler. | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 5.477 | 5.4649 | 5.4649 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Supply & Erection of Reheater front Pendent Assembly consisting Full set of Cold Reheater coil assembly For Unit No 2 with necessary attachments, Crown Plate. Heat shield, roof seal bend, steam cooled spacer tube with necessary attachment. | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 2.711 | 2.6625 | 2.6625 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Supply & Erection of Reheater front Pendent Assembly consisting Full set of Cold Reheater coil assembly For Unit No 3 with necessary attachments, Crown Plate. Heat shield, roof seal bend, steam cooled spacer tube with necessary attachment. | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 2.711 | 2.3531 | 2.3531 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 1.689 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Boiler Process Improvement by replacement of damaged valves and Boiler Perfm Imp by Air Pre-Heater Up gradation of U#2 & U#3 at BTPS | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 17.37 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Replacement of boiler outlet valves and damaged valves of units 2 & 3 | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 2.62 | 1.3984 | 1.3984 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.2 | Air pre heater up gradation of heat exchanger matrix & regenerative dynamic sealing of units 2 & 3 | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 13.405 | 1.2086 | 1.2086 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 1.345 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Stack management by procurement of Bulldozer & LOCO and CHP area schemes for performance & unloading improvement | MERC/CAPEX/20162017/01426 | 2017-02-02 | 2.0931 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement of Locomotive 800 HP (2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 1.0396 | 1.0135 | 1.0135 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Procurement of 2 No’s of Bulldozer Model D-155(2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.53802 | 0.72969 | 0.72969 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.3 | Modification below primary crusher chutes 15A/B & Conv.02 | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.090248 | 0.079869 | 0.079869 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.4 | New helical gear box for various conveyors | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.16661 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.5 | Procurement of Elecon Make Ring Granulator Type TK-09-38B | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.11281 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.6 | Procurement of Elecon Make Ring Granulator Type TK6 32B Ring Granulator | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.071157 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.074628 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Upgradation of Symphony Harmony DCS, 220V 1285 AH Battery & Charger and Replacement of 6.6 kV HT MOCB by VCB at BTPS, Bhusawal | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 13.7286 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | HMI Up-gradation of Symphony Harmony DCS Unit-3, 210MW, BTPS. | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 5.54 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Supply, erection, commissioning and site testing of Plante 220V DC, 1285 AH, Station Battery Set and charging equipment for 1285 AH Plante battery for Unit 3. | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 1.7186 | 1.7186 | 1.7186 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Retrofitting of 6.6 kv breakers of unit -3 along without door plant boards by vacuum circuit breakers. | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 6.47 | 6.1083 | 6.1083 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 1.91 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.1 | Bhusawal: Procurement of HT motors (Coal Mill/CEP/CWP) for U-3 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 1.91 | 0.69703 | 0.69703 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.1 | Bhusawal: Unit 2-3 (1 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0.9384 | 0.9384 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.1 | Bhusawal: Unit 2-3 | MERC/CAPEX/20162017/00774 | 2016-09-30 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 13.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (ii) Submitted to MERC but yet to be approved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (iii) Yet to be submitted to MERC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| FY 2026-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | R&M/LE for Identified Thermal units of MSPGCL of BTPS U-3 (210 MW) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | R&M/LE for Identified Thermal units of MSPGCL of BTPS U-3 (210 MW) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| B) Non-DPR Schemes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Design, Supply and Installation for capacity enhancement of conveyor No. 08 at CHP210MW, BTPS. | 0 | 0 | 0 | 1.8001 | 1.8001 | 0 | 0 | 0 |  |  | 0 | 0
2 | SPEAKER & PTZ CAMER | 0 | 0 | 0 | 0.031968 | 0.031968 | 0 | 0 | 0 |  |  | 0 | 0
3 | 50 INCH TV & 2TN AC | 0 | 0 | 0 | 0.06453 | 0.06453 | 0 | 0 | 0 |  |  | 0 | 0
4 | Fixtures & Fitting (10801) | 0 | 0 | 0 | 0.02209 | 0.02209 | 0 | 0 | 0 |  |  | 0 | 0
5 | Office equpment (10901) | 0 | 0 | 0 | 0.60697 | 0.60697 | 0 | 0 | 0 |  |  | 0 | 0
6 | Gearboxes for CHP Elecon Make | 0 | 0 | 0 | 0.34574 | 0.34574 | 0 | 0 | 0 |  |  | 0 | 0
7 | General Assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Furniture & Fixture | 0 | 0 | 0 | 0.0035 | 0.0035 | 0 | 0 | 0 |  |  | 0 | 0
9 | Office Equipment | 0 | 0 | 0 | 0.25886 | 0.25886 | 0 | 0 | 0 |  |  | 0 | 0
10 | Furniture & Fixture | 0 | 0 | 0 | 0 | 0 | 0 | 0.2072 | 0.2072 |  |  | 0.2072 | 0
11 | Office Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0.0063897 | 0.0063897 |  |  | 0.0063897 | 0
12 | Land | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19434 |  |  | 0.19434 | -0.19434
| Total |  |  |  | 56.6192 | 56.6192 | 0 | 0.21359 | 0.40793 | 0 | 0 | 0.40793 | -0.19434
FY 2024-25
a) DPR Schemes
(i) In-principle approved by MERC
1 | Replacement of economizer & LTSH coils at Unit # 2 | MERC/CAPEX/20122013/00179 | 2012-04-23 | 10.178 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Replacement of Economiser Coil | MERC/CAPEX/20122013/00179 | 2012-04-23 | 3.524 | 3.47 | 3.47 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/00179 | 2012-04-23 | 0.203 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | Replacement of LTSH Coil | MERC/CAPEX/20122013/00179 | 2012-04-23 | 6.094 | 5.32 | 5.32 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/00179 | 2012-04-23 | 0.357 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Boiler and Turbine improvement (Station Heat Rate Improvement) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 16.7838 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Vent condenser performance improvement by replacement of eroded tube nest by unit 3. | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.286 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Replacement of major extraction valves &NRVs of unit 3 | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.519 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | 60% replacement of boiler skin insulation (Unit 2) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.293 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Replacement of DM make up ( unit 3) and GSH water pump.( units 2 &3) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.206 | 0.26354 | 0.26354 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Replacement of LTSH coils (unit 3) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 8.369 | 5.32 | 5.32 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.6 | Replacement of ECO coils (unit 3) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 6.032 | 3.4728 | 3.4728 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.7 | Replacement of old LT AHP pump impeller by energy efficient stainless steel impeller | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.14881 | 0.14881 | 0.14881 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Measuring and Monitoring of Coal consumption | MERC/CAPEX/20122013/00912 | 2012-07-24 | 45.918 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Belt Weighers | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.8044 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.2 | Fully automatic pit-less in motion weigh bridges | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.4115 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.3 | Installation side arm charger for Wagon tippler 1A & 1B | MERC/CAPEX/20122013/00912 | 2012-07-24 | 21.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.4 | Dust Extraction System at Secondary Crusher house & Conveyor 6A/B at stage II CHP | MERC/CAPEX/20122013/00912 | 2012-07-24 | 2.0715 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.5 | Fogging system at a) WT old along with PCR, SCR and bunker level belt at Stage I CHP b) Conveyor 7A/B c) 100 Mtrx100 Mtr Coal stock area d) 200 Mtrx200 Mtr Coal stock area | MERC/CAPEX/20122013/00912 | 2012-07-24 | 2.2831 | 0.46954 | 0.46954 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.6 | Bunker level montoring system for 12 bunkers | MERC/CAPEX/20122013/00912 | 2012-07-24 | 2.5038 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.7 | Rotary pneumatic or electrical hammers | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.097 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.8 | Enhancement of unloading capacity of CHP from 360 TPH to 500 TPH | MERC/CAPEX/20122013/00912 | 2012-07-24 | 7.6508 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.9 | Quick detection of poor coal quality through CCTV on overhead watch tower focused onto the wagons, over which the rake passes at low speed & various conveyor tunnels | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.2968 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Motor controller for conveyor motors of Stage II CHP | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.9607 | 0.9607 | 0.9607 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.11 | Procurement of a CHN apparatus for ultimate analysis for operational optimization and coal mapping studies. | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.63617 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.12 | Additional bomb calorimeter | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.44012 | 0.19 | 0.19 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.13 | TGA analysis of the coal for operational optimization. | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.53214 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/00912 | 2012-07-24 | 5.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Turbine Auxiliary Performance Improvements | MERC/CAPEX/20122013/02107 | 2013-01-07 | 20.109 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Procurement and installation and commissioning of modified upgraded boiler feed pump (Type -200KHI/S) having energy efficient cartridge for unit 2 & 3 , BTPS. | MERC/CAPEX/20122013/02107 | 2013-01-07 | 17.47 | 8.6557 | 8.6557 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Replacement of brine pumps with modified pumps complete with S.S material in new WTP | MERC/CAPEX/20122013/02107 | 2013-01-07 | 1.029 | 0.3016 | 0.3016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/02107 | 2013-01-07 | 1.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Replacement of Platen water wall coils U#2,Super Heater & Platen Super Heater Coils for U#2 and Cold Reheater coils for U#2 & U#3 | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 13.692 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Supply & Erection of Platen Water wall coils Assembly from inlet header to outlet header in pent house for Unit No 2 | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 1.104 | 0.54 | 0.54 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Complete Supply & Erection of Super Heater Radiant Roof Panel Tube with Attachment for Unit No 2 Boiler From front side of Boiler to rear side of boiler & Vertical Platen Super Heater coils Assembly for Unit No 2, 210 MW Boiler. | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 5.477 | 5.4649 | 5.4649 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Supply & Erection of Reheater front Pendent Assembly consisting Full set of Cold Reheater coil assembly For Unit No 2 with necessary attachments, Crown Plate. Heat shield, roof seal bend, steam cooled spacer tube with necessary attachment. | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 2.711 | 2.6625 | 2.6625 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Supply & Erection of Reheater front Pendent Assembly consisting Full set of Cold Reheater coil assembly For Unit No 3 with necessary attachments, Crown Plate. Heat shield, roof seal bend, steam cooled spacer tube with necessary attachment. | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 2.711 | 2.3531 | 2.3531 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 1.689 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Boiler Process Improvement by replacement of damaged valves and Boiler Perfm Imp by Air Pre-Heater Up gradation of U#2 & U#3 at BTPS | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 17.37 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Replacement of boiler outlet valves and damaged valves of units 2 & 3 | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 2.62 | 1.3984 | 1.3984 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.2 | Air pre heater up gradation of heat exchanger matrix & regenerative dynamic sealing of units 2 & 3 | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 13.405 | 1.2086 | 1.2086 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 1.345 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Stack management by procurement of Bulldozer & LOCO and CHP area schemes for performance & unloading improvement | MERC/CAPEX/20162017/01426 | 2017-02-02 | 2.0931 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement of Locomotive 800 HP (2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 1.0396 | 1.0135 | 1.0135 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Procurement of 2 No’s of Bulldozer Model D-155(2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.53802 | 0.72969 | 0.72969 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.3 | Modification below primary crusher chutes 15A/B & Conv.02 | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.090248 | 0.079869 | 0.079869 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.4 | New helical gear box for various conveyors | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.16661 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.5 | Procurement of Elecon Make Ring Granulator Type TK-09-38B | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.11281 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.6 | Procurement of Elecon Make Ring Granulator Type TK6 32B Ring Granulator | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.071157 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.074628 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Upgradation of Symphony Harmony DCS, 220V 1285 AH Battery & Charger and Replacement of 6.6 kV HT MOCB by VCB at BTPS, Bhusawal | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 13.7286 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | HMI Up-gradation of Symphony Harmony DCS Unit-3, 210MW, BTPS. | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 5.54 | 0 | 0 | 0 | 5.54 | 5.54 |  |  | 5.54 | 0 | 5.54 | 0
14.2 | Supply, erection, commissioning and site testing of Plante 220V DC, 1285 AH, Station Battery Set and charging equipment for 1285 AH Plante battery for Unit 3. | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 1.7186 | 1.7186 | 1.7186 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Retrofitting of 6.6 kv breakers of unit -3 along without door plant boards by vacuum circuit breakers. | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 6.47 | 6.1083 | 6.1083 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 1.91 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.1 | Bhusawal: Procurement of HT motors (Coal Mill/CEP/CWP) for U-3 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 1.91 | 0.69703 | 0.69703 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.1 | Bhusawal: Unit 2-3 (1 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0.9384 | 0.9384 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.1 | Bhusawal: Unit 2-3 | MERC/CAPEX/20162017/00774 | 2016-09-30 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 13.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (ii) Submitted to MERC but yet to be approved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (iii) Yet to be submitted to MERC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| FY 2026-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | R&M/LE for Identified Thermal units of MSPGCL of BTPS U-3 (210 MW) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | R&M/LE for Identified Thermal units of MSPGCL of BTPS U-3 (210 MW) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| B) Non-DPR Schemes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Design, Supply and Installation for capacity enhancement of conveyor No. 08 at CHP210MW, BTPS. | 0 | 0 | 0 | 1.8001 | 1.8001 | 0 | 0 | 0 |  |  | 0 | 0
2 | SPEAKER & PTZ CAMER | 0 | 0 | 0 | 0.031968 | 0.031968 | 0 | 0 | 0 |  |  | 0 | 0
3 | 50 INCH TV & 2TN AC | 0 | 0 | 0 | 0.06453 | 0.06453 | 0 | 0 | 0 |  |  | 0 | 0
4 | Fixtures & Fitting (10801) | 0 | 0 | 0 | 0.02209 | 0.02209 | 0 | 0 | 0 |  |  | 0 | 0
5 | Office equpment (10901) | 0 | 0 | 0 | 0.60697 | 0.60697 | 0 | 0 | 0 |  |  | 0 | 0
6 | Gearboxes for CHP Elecon Make | 0 | 0 | 0 | 0.34574 | 0.34574 | 0 | 0 | 0 |  |  | 0 | 0
7 | General Assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Furniture & Fixture | 0 | 0 | 0 | 0.0035 | 0.0035 | 0 | 0 | 0.09 |  |  | 0.09 | -0.09
9 | Office Equipment | 0 | 0 | 0 | 0.25886 | 0.25886 | 0 | 0 | 0 |  |  | 0 | 0
10 | Furniture & Fixture | 0 | 0 | 0 | 0.2072 | 0.2072 | 0 | 0 | 0 |  |  | 0 | 0
11 | Office Equipment | 0 | 0 | 0 | 0.0063897 | 0.0063897 | 0 | 0 | 0 |  |  | 0 | 0
12 | Land | 0 | 0 | 0 | 0 | 0.19434 | -0.19434 | 0 | 0 |  |  | 0 | -0.19434
| Total |  |  |  | 56.8328 | 57.0272 | -0.19434 | 5.54 | 5.63 | 0 | 0 | 5.63 | -0.28434
FY 2025-26
a) DPR Schemes
(i) In-principle approved by MERC
1 | Replacement of economizer & LTSH coils at Unit # 2 | MERC/CAPEX/20122013/00179 | 2012-04-23 | 10.178 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Replacement of Economiser Coil | MERC/CAPEX/20122013/00179 | 2012-04-23 | 3.524 | 3.47 | 3.47 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/00179 | 2012-04-23 | 0.203 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | Replacement of LTSH Coil | MERC/CAPEX/20122013/00179 | 2012-04-23 | 6.094 | 5.32 | 5.32 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/00179 | 2012-04-23 | 0.357 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Boiler and Turbine improvement (Station Heat Rate Improvement) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 16.7838 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Vent condenser performance improvement by replacement of eroded tube nest by unit 3. | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.286 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Replacement of major extraction valves &NRVs of unit 3 | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.519 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | 60% replacement of boiler skin insulation (Unit 2) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.293 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Replacement of DM make up ( unit 3) and GSH water pump.( units 2 &3) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.206 | 0.26354 | 0.26354 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Replacement of LTSH coils (unit 3) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 8.369 | 5.32 | 5.32 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.6 | Replacement of ECO coils (unit 3) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 6.032 | 3.4728 | 3.4728 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.7 | Replacement of old LT AHP pump impeller by energy efficient stainless steel impeller | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.14881 | 0.14881 | 0.14881 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Measuring and Monitoring of Coal consumption | MERC/CAPEX/20122013/00912 | 2012-07-24 | 45.918 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Belt Weighers | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.8044 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.2 | Fully automatic pit-less in motion weigh bridges | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.4115 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.3 | Installation side arm charger for Wagon tippler 1A & 1B | MERC/CAPEX/20122013/00912 | 2012-07-24 | 21.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.4 | Dust Extraction System at Secondary Crusher house & Conveyor 6A/B at stage II CHP | MERC/CAPEX/20122013/00912 | 2012-07-24 | 2.0715 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.5 | Fogging system at a) WT old along with PCR, SCR and bunker level belt at Stage I CHP b) Conveyor 7A/B c) 100 Mtrx100 Mtr Coal stock area d) 200 Mtrx200 Mtr Coal stock area | MERC/CAPEX/20122013/00912 | 2012-07-24 | 2.2831 | 0.46954 | 0.46954 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.6 | Bunker level montoring system for 12 bunkers | MERC/CAPEX/20122013/00912 | 2012-07-24 | 2.5038 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.7 | Rotary pneumatic or electrical hammers | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.097 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.8 | Enhancement of unloading capacity of CHP from 360 TPH to 500 TPH | MERC/CAPEX/20122013/00912 | 2012-07-24 | 7.6508 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.9 | Quick detection of poor coal quality through CCTV on overhead watch tower focused onto the wagons, over which the rake passes at low speed & various conveyor tunnels | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.2968 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Motor controller for conveyor motors of Stage II CHP | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.9607 | 0.9607 | 0.9607 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.11 | Procurement of a CHN apparatus for ultimate analysis for operational optimization and coal mapping studies. | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.63617 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.12 | Additional bomb calorimeter | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.44012 | 0.19 | 0.19 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.13 | TGA analysis of the coal for operational optimization. | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.53214 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/00912 | 2012-07-24 | 5.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Turbine Auxiliary Performance Improvements | MERC/CAPEX/20122013/02107 | 2013-01-07 | 20.109 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Procurement and installation and commissioning of modified upgraded boiler feed pump (Type -200KHI/S) having energy efficient cartridge for unit 2 & 3 , BTPS. | MERC/CAPEX/20122013/02107 | 2013-01-07 | 17.47 | 8.6557 | 8.6557 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Replacement of brine pumps with modified pumps complete with S.S material in new WTP | MERC/CAPEX/20122013/02107 | 2013-01-07 | 1.029 | 0.3016 | 0.3016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/02107 | 2013-01-07 | 1.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Replacement of Platen water wall coils U#2,Super Heater & Platen Super Heater Coils for U#2 and Cold Reheater coils for U#2 & U#3 | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 13.692 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Supply & Erection of Platen Water wall coils Assembly from inlet header to outlet header in pent house for Unit No 2 | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 1.104 | 0.54 | 0.54 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Complete Supply & Erection of Super Heater Radiant Roof Panel Tube with Attachment for Unit No 2 Boiler From front side of Boiler to rear side of boiler & Vertical Platen Super Heater coils Assembly for Unit No 2, 210 MW Boiler. | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 5.477 | 5.4649 | 5.4649 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Supply & Erection of Reheater front Pendent Assembly consisting Full set of Cold Reheater coil assembly For Unit No 2 with necessary attachments, Crown Plate. Heat shield, roof seal bend, steam cooled spacer tube with necessary attachment. | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 2.711 | 2.6625 | 2.6625 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Supply & Erection of Reheater front Pendent Assembly consisting Full set of Cold Reheater coil assembly For Unit No 3 with necessary attachments, Crown Plate. Heat shield, roof seal bend, steam cooled spacer tube with necessary attachment. | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 2.711 | 2.3531 | 2.3531 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 1.689 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Boiler Process Improvement by replacement of damaged valves and Boiler Perfm Imp by Air Pre-Heater Up gradation of U#2 & U#3 at BTPS | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 17.37 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Replacement of boiler outlet valves and damaged valves of units 2 & 3 | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 2.62 | 1.3984 | 1.3984 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.2 | Air pre heater up gradation of heat exchanger matrix & regenerative dynamic sealing of units 2 & 3 | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 13.405 | 1.2086 | 1.2086 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 1.345 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Stack management by procurement of Bulldozer & LOCO and CHP area schemes for performance & unloading improvement | MERC/CAPEX/20162017/01426 | 2017-02-02 | 2.0931 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement of Locomotive 800 HP (2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 1.0396 | 1.0135 | 1.0135 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Procurement of 2 No’s of Bulldozer Model D-155(2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.53802 | 0.72969 | 0.72969 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.3 | Modification below primary crusher chutes 15A/B & Conv.02 | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.090248 | 0.079869 | 0.079869 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.4 | New helical gear box for various conveyors | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.16661 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.5 | Procurement of Elecon Make Ring Granulator Type TK-09-38B | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.11281 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.6 | Procurement of Elecon Make Ring Granulator Type TK6 32B Ring Granulator | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.071157 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.074628 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Upgradation of Symphony Harmony DCS, 220V 1285 AH Battery & Charger and Replacement of 6.6 kV HT MOCB by VCB at BTPS, Bhusawal | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 13.7286 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | HMI Up-gradation of Symphony Harmony DCS Unit-3, 210MW, BTPS. | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 5.54 | 5.54 | 5.54 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Supply, erection, commissioning and site testing of Plante 220V DC, 1285 AH, Station Battery Set and charging equipment for 1285 AH Plante battery for Unit 3. | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 1.7186 | 1.7186 | 1.7186 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Retrofitting of 6.6 kv breakers of unit -3 along without door plant boards by vacuum circuit breakers. | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 6.47 | 6.1083 | 6.1083 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 1.91 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.1 | Bhusawal: Procurement of HT motors (Coal Mill/CEP/CWP) for U-3 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 1.91 | 0.69703 | 0.69703 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.1 | Bhusawal: Unit 2-3 (1 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0.9384 | 0.9384 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.1 | Bhusawal: Unit 2-3 | MERC/CAPEX/20162017/00774 | 2016-09-30 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 13.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (ii) Submitted to MERC but yet to be approved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (iii) Yet to be submitted to MERC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| FY 2026-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | R&M/LE for Identified Thermal units of MSPGCL of BTPS U-3 (210 MW) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | R&M/LE for Identified Thermal units of MSPGCL of BTPS U-3 (210 MW) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| B) Non-DPR Schemes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Design, Supply and Installation for capacity enhancement of conveyor No. 08 at CHP210MW, BTPS. | 0 | 0 | 0 | 1.8001 | 1.8001 | 0 | 0 | 0 |  |  | 0 | 0
2 | SPEAKER & PTZ CAMER | 0 | 0 | 0 | 0.031968 | 0.031968 | 0 | 0 | 0 |  |  | 0 | 0
3 | 50 INCH TV & 2TN AC | 0 | 0 | 0 | 0.06453 | 0.06453 | 0 | 0 | 0 |  |  | 0 | 0
4 | Fixtures & Fitting (10801) | 0 | 0 | 0 | 0.02209 | 0.02209 | 0 | 0 | 0 |  |  | 0 | 0
5 | Office equpment (10901) | 0 | 0 | 0 | 0.60697 | 0.60697 | 0 | 0 | 0 |  |  | 0 | 0
6 | Gearboxes for CHP Elecon Make | 0 | 0 | 0 | 0.34574 | 0.34574 | 0 | 0 | 0 |  |  | 0 | 0
7 | General Assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Furniture & Fixture | 0 | 0 | 0 | 0.0035 | 0.0935 | -0.09 | 0 | 0 |  |  | 0 | -0.09
9 | Office Equipment | 0 | 0 | 0 | 0.25886 | 0.25886 | 0 | 0 | 0 |  |  | 0 | 0
10 | Furniture & Fixture | 0 | 0 | 0 | 0.2072 | 0.2072 | 0 | 0 | 0 |  |  | 0 | 0
11 | Office Equipment | 0 | 0 | 0 | 0.0063897 | 0.0063897 | 0 | 0 | 0 |  |  | 0 | 0
12 | Land | 0 | 0 | 0 | 0 | 0.19434 | -0.19434 | 0 | 0 |  |  | 0 | -0.19434
| Total |  |  |  | 62.3728 | 62.6572 | -0.28434 | 0 | 0 | 0 | 0 | 0 | -0.28434
FY 2026-27
a) DPR Schemes
(i) In-principle approved by MERC
1 | Replacement of economizer & LTSH coils at Unit # 2 | MERC/CAPEX/20122013/00179 | 2012-04-23 | 10.178 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Replacement of Economiser Coil | MERC/CAPEX/20122013/00179 | 2012-04-23 | 3.524 | 3.47 | 3.47 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/00179 | 2012-04-23 | 0.203 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | Replacement of LTSH Coil | MERC/CAPEX/20122013/00179 | 2012-04-23 | 6.094 | 5.32 | 5.32 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/00179 | 2012-04-23 | 0.357 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Boiler and Turbine improvement (Station Heat Rate Improvement) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 16.7838 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Vent condenser performance improvement by replacement of eroded tube nest by unit 3. | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.286 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Replacement of major extraction valves &NRVs of unit 3 | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.519 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | 60% replacement of boiler skin insulation (Unit 2) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.293 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Replacement of DM make up ( unit 3) and GSH water pump.( units 2 &3) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.206 | 0.26354 | 0.26354 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Replacement of LTSH coils (unit 3) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 8.369 | 5.32 | 5.32 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.6 | Replacement of ECO coils (unit 3) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 6.032 | 3.4728 | 3.4728 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.7 | Replacement of old LT AHP pump impeller by energy efficient stainless steel impeller | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.14881 | 0.14881 | 0.14881 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Measuring and Monitoring of Coal consumption | MERC/CAPEX/20122013/00912 | 2012-07-24 | 45.918 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Belt Weighers | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.8044 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.2 | Fully automatic pit-less in motion weigh bridges | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.4115 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.3 | Installation side arm charger for Wagon tippler 1A & 1B | MERC/CAPEX/20122013/00912 | 2012-07-24 | 21.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.4 | Dust Extraction System at Secondary Crusher house & Conveyor 6A/B at stage II CHP | MERC/CAPEX/20122013/00912 | 2012-07-24 | 2.0715 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.5 | Fogging system at a) WT old along with PCR, SCR and bunker level belt at Stage I CHP b) Conveyor 7A/B c) 100 Mtrx100 Mtr Coal stock area d) 200 Mtrx200 Mtr Coal stock area | MERC/CAPEX/20122013/00912 | 2012-07-24 | 2.2831 | 0.46954 | 0.46954 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.6 | Bunker level montoring system for 12 bunkers | MERC/CAPEX/20122013/00912 | 2012-07-24 | 2.5038 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.7 | Rotary pneumatic or electrical hammers | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.097 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.8 | Enhancement of unloading capacity of CHP from 360 TPH to 500 TPH | MERC/CAPEX/20122013/00912 | 2012-07-24 | 7.6508 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.9 | Quick detection of poor coal quality through CCTV on overhead watch tower focused onto the wagons, over which the rake passes at low speed & various conveyor tunnels | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.2968 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Motor controller for conveyor motors of Stage II CHP | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.9607 | 0.9607 | 0.9607 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.11 | Procurement of a CHN apparatus for ultimate analysis for operational optimization and coal mapping studies. | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.63617 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.12 | Additional bomb calorimeter | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.44012 | 0.19 | 0.19 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.13 | TGA analysis of the coal for operational optimization. | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.53214 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/00912 | 2012-07-24 | 5.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Turbine Auxiliary Performance Improvements | MERC/CAPEX/20122013/02107 | 2013-01-07 | 20.109 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Procurement and installation and commissioning of modified upgraded boiler feed pump (Type -200KHI/S) having energy efficient cartridge for unit 2 & 3 , BTPS. | MERC/CAPEX/20122013/02107 | 2013-01-07 | 17.47 | 8.6557 | 8.6557 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Replacement of brine pumps with modified pumps complete with S.S material in new WTP | MERC/CAPEX/20122013/02107 | 2013-01-07 | 1.029 | 0.3016 | 0.3016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/02107 | 2013-01-07 | 1.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Replacement of Platen water wall coils U#2,Super Heater & Platen Super Heater Coils for U#2 and Cold Reheater coils for U#2 & U#3 | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 13.692 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Supply & Erection of Platen Water wall coils Assembly from inlet header to outlet header in pent house for Unit No 2 | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 1.104 | 0.54 | 0.54 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Complete Supply & Erection of Super Heater Radiant Roof Panel Tube with Attachment for Unit No 2 Boiler From front side of Boiler to rear side of boiler & Vertical Platen Super Heater coils Assembly for Unit No 2, 210 MW Boiler. | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 5.477 | 5.4649 | 5.4649 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Supply & Erection of Reheater front Pendent Assembly consisting Full set of Cold Reheater coil assembly For Unit No 2 with necessary attachments, Crown Plate. Heat shield, roof seal bend, steam cooled spacer tube with necessary attachment. | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 2.711 | 2.6625 | 2.6625 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Supply & Erection of Reheater front Pendent Assembly consisting Full set of Cold Reheater coil assembly For Unit No 3 with necessary attachments, Crown Plate. Heat shield, roof seal bend, steam cooled spacer tube with necessary attachment. | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 2.711 | 2.3531 | 2.3531 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 1.689 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Boiler Process Improvement by replacement of damaged valves and Boiler Perfm Imp by Air Pre-Heater Up gradation of U#2 & U#3 at BTPS | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 17.37 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Replacement of boiler outlet valves and damaged valves of units 2 & 3 | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 2.62 | 1.3984 | 1.3984 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.2 | Air pre heater up gradation of heat exchanger matrix & regenerative dynamic sealing of units 2 & 3 | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 13.405 | 1.2086 | 1.2086 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 1.345 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Stack management by procurement of Bulldozer & LOCO and CHP area schemes for performance & unloading improvement | MERC/CAPEX/20162017/01426 | 2017-02-02 | 2.0931 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement of Locomotive 800 HP (2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 1.0396 | 1.0135 | 1.0135 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Procurement of 2 No’s of Bulldozer Model D-155(2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.53802 | 0.72969 | 0.72969 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.3 | Modification below primary crusher chutes 15A/B & Conv.02 | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.090248 | 0.079869 | 0.079869 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.4 | New helical gear box for various conveyors | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.16661 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.5 | Procurement of Elecon Make Ring Granulator Type TK-09-38B | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.11281 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.6 | Procurement of Elecon Make Ring Granulator Type TK6 32B Ring Granulator | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.071157 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.074628 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Upgradation of Symphony Harmony DCS, 220V 1285 AH Battery & Charger and Replacement of 6.6 kV HT MOCB by VCB at BTPS, Bhusawal | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 13.7286 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | HMI Up-gradation of Symphony Harmony DCS Unit-3, 210MW, BTPS. | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 5.54 | 5.54 | 5.54 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Supply, erection, commissioning and site testing of Plante 220V DC, 1285 AH, Station Battery Set and charging equipment for 1285 AH Plante battery for Unit 3. | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 1.7186 | 1.7186 | 1.7186 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Retrofitting of 6.6 kv breakers of unit -3 along without door plant boards by vacuum circuit breakers. | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 6.47 | 6.1083 | 6.1083 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 1.91 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.1 | Bhusawal: Procurement of HT motors (Coal Mill/CEP/CWP) for U-3 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 1.91 | 0.69703 | 0.69703 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.1 | Bhusawal: Unit 2-3 (1 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0.9384 | 0.9384 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.1 | Bhusawal: Unit 2-3 | MERC/CAPEX/20162017/00774 | 2016-09-30 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 13.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (ii) Submitted to MERC but yet to be approved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (iii) Yet to be submitted to MERC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| FY 2026-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | R&M/LE for Identified Thermal units of MSPGCL of BTPS U-3 (210 MW) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | R&M/LE for Identified Thermal units of MSPGCL of BTPS U-3 (210 MW) | 0 | 0 | 0 | 0 | 0 | 0 | 398 | 398 |  |  | 398 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| B) Non-DPR Schemes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Design, Supply and Installation for capacity enhancement of conveyor No. 08 at CHP210MW, BTPS. | 0 | 0 | 0 | 1.8001 | 1.8001 | 0 | 0 | 0 |  |  | 0 | 0
2 | SPEAKER & PTZ CAMER | 0 | 0 | 0 | 0.031968 | 0.031968 | 0 | 0 | 0 |  |  | 0 | 0
3 | 50 INCH TV & 2TN AC | 0 | 0 | 0 | 0.06453 | 0.06453 | 0 | 0 | 0 |  |  | 0 | 0
4 | Fixtures & Fitting (10801) | 0 | 0 | 0 | 0.02209 | 0.02209 | 0 | 0 | 0 |  |  | 0 | 0
5 | Office equpment (10901) | 0 | 0 | 0 | 0.60697 | 0.60697 | 0 | 0 | 0 |  |  | 0 | 0
6 | Gearboxes for CHP Elecon Make | 0 | 0 | 0 | 0.34574 | 0.34574 | 0 | 0 | 0 |  |  | 0 | 0
7 | General Assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Furniture & Fixture | 0 | 0 | 0 | 0.0035 | 0.0935 | -0.09 | 0 | 0 |  |  | 0 | -0.09
9 | Office Equipment | 0 | 0 | 0 | 0.25886 | 0.25886 | 0 | 0 | 0 |  |  | 0 | 0
10 | Furniture & Fixture | 0 | 0 | 0 | 0.2072 | 0.2072 | 0 | 0 | 0 |  |  | 0 | 0
11 | Office Equipment | 0 | 0 | 0 | 0.0063897 | 0.0063897 | 0 | 0 | 0 |  |  | 0 | 0
12 | Land | 0 | 0 | 0 | 0 | 0.19434 | -0.19434 | 0 | 0 |  |  | 0 | -0.19434
| Total |  |  |  | 62.3728 | 62.6572 | -0.28434 | 398 | 398 | 0 | 0 | 398 | -0.28434
FY 2027-28
a) DPR Schemes
(i) In-principle approved by MERC
1 | Replacement of economizer & LTSH coils at Unit # 2 | MERC/CAPEX/20122013/00179 | 2012-04-23 | 10.178 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Replacement of Economiser Coil | MERC/CAPEX/20122013/00179 | 2012-04-23 | 3.524 | 3.47 | 3.47 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/00179 | 2012-04-23 | 0.203 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | Replacement of LTSH Coil | MERC/CAPEX/20122013/00179 | 2012-04-23 | 6.094 | 5.32 | 5.32 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/00179 | 2012-04-23 | 0.357 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Boiler and Turbine improvement (Station Heat Rate Improvement) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 16.7838 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Vent condenser performance improvement by replacement of eroded tube nest by unit 3. | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.286 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Replacement of major extraction valves &NRVs of unit 3 | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.519 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | 60% replacement of boiler skin insulation (Unit 2) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.293 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Replacement of DM make up ( unit 3) and GSH water pump.( units 2 &3) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.206 | 0.26354 | 0.26354 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Replacement of LTSH coils (unit 3) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 8.369 | 5.32 | 5.32 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.6 | Replacement of ECO coils (unit 3) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 6.032 | 3.4728 | 3.4728 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.7 | Replacement of old LT AHP pump impeller by energy efficient stainless steel impeller | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.14881 | 0.14881 | 0.14881 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Measuring and Monitoring of Coal consumption | MERC/CAPEX/20122013/00912 | 2012-07-24 | 45.918 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Belt Weighers | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.8044 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.2 | Fully automatic pit-less in motion weigh bridges | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.4115 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.3 | Installation side arm charger for Wagon tippler 1A & 1B | MERC/CAPEX/20122013/00912 | 2012-07-24 | 21.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.4 | Dust Extraction System at Secondary Crusher house & Conveyor 6A/B at stage II CHP | MERC/CAPEX/20122013/00912 | 2012-07-24 | 2.0715 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.5 | Fogging system at a) WT old along with PCR, SCR and bunker level belt at Stage I CHP b) Conveyor 7A/B c) 100 Mtrx100 Mtr Coal stock area d) 200 Mtrx200 Mtr Coal stock area | MERC/CAPEX/20122013/00912 | 2012-07-24 | 2.2831 | 0.46954 | 0.46954 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.6 | Bunker level montoring system for 12 bunkers | MERC/CAPEX/20122013/00912 | 2012-07-24 | 2.5038 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.7 | Rotary pneumatic or electrical hammers | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.097 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.8 | Enhancement of unloading capacity of CHP from 360 TPH to 500 TPH | MERC/CAPEX/20122013/00912 | 2012-07-24 | 7.6508 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.9 | Quick detection of poor coal quality through CCTV on overhead watch tower focused onto the wagons, over which the rake passes at low speed & various conveyor tunnels | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.2968 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Motor controller for conveyor motors of Stage II CHP | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.9607 | 0.9607 | 0.9607 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.11 | Procurement of a CHN apparatus for ultimate analysis for operational optimization and coal mapping studies. | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.63617 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.12 | Additional bomb calorimeter | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.44012 | 0.19 | 0.19 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.13 | TGA analysis of the coal for operational optimization. | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.53214 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/00912 | 2012-07-24 | 5.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Turbine Auxiliary Performance Improvements | MERC/CAPEX/20122013/02107 | 2013-01-07 | 20.109 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Procurement and installation and commissioning of modified upgraded boiler feed pump (Type -200KHI/S) having energy efficient cartridge for unit 2 & 3 , BTPS. | MERC/CAPEX/20122013/02107 | 2013-01-07 | 17.47 | 8.6557 | 8.6557 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Replacement of brine pumps with modified pumps complete with S.S material in new WTP | MERC/CAPEX/20122013/02107 | 2013-01-07 | 1.029 | 0.3016 | 0.3016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/02107 | 2013-01-07 | 1.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Replacement of Platen water wall coils U#2,Super Heater & Platen Super Heater Coils for U#2 and Cold Reheater coils for U#2 & U#3 | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 13.692 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Supply & Erection of Platen Water wall coils Assembly from inlet header to outlet header in pent house for Unit No 2 | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 1.104 | 0.54 | 0.54 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Complete Supply & Erection of Super Heater Radiant Roof Panel Tube with Attachment for Unit No 2 Boiler From front side of Boiler to rear side of boiler & Vertical Platen Super Heater coils Assembly for Unit No 2, 210 MW Boiler. | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 5.477 | 5.4649 | 5.4649 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Supply & Erection of Reheater front Pendent Assembly consisting Full set of Cold Reheater coil assembly For Unit No 2 with necessary attachments, Crown Plate. Heat shield, roof seal bend, steam cooled spacer tube with necessary attachment. | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 2.711 | 2.6625 | 2.6625 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Supply & Erection of Reheater front Pendent Assembly consisting Full set of Cold Reheater coil assembly For Unit No 3 with necessary attachments, Crown Plate. Heat shield, roof seal bend, steam cooled spacer tube with necessary attachment. | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 2.711 | 2.3531 | 2.3531 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 1.689 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Boiler Process Improvement by replacement of damaged valves and Boiler Perfm Imp by Air Pre-Heater Up gradation of U#2 & U#3 at BTPS | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 17.37 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Replacement of boiler outlet valves and damaged valves of units 2 & 3 | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 2.62 | 1.3984 | 1.3984 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.2 | Air pre heater up gradation of heat exchanger matrix & regenerative dynamic sealing of units 2 & 3 | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 13.405 | 1.2086 | 1.2086 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 1.345 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Stack management by procurement of Bulldozer & LOCO and CHP area schemes for performance & unloading improvement | MERC/CAPEX/20162017/01426 | 2017-02-02 | 2.0931 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement of Locomotive 800 HP (2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 1.0396 | 1.0135 | 1.0135 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Procurement of 2 No’s of Bulldozer Model D-155(2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.53802 | 0.72969 | 0.72969 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.3 | Modification below primary crusher chutes 15A/B & Conv.02 | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.090248 | 0.079869 | 0.079869 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.4 | New helical gear box for various conveyors | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.16661 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.5 | Procurement of Elecon Make Ring Granulator Type TK-09-38B | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.11281 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.6 | Procurement of Elecon Make Ring Granulator Type TK6 32B Ring Granulator | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.071157 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.074628 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Upgradation of Symphony Harmony DCS, 220V 1285 AH Battery & Charger and Replacement of 6.6 kV HT MOCB by VCB at BTPS, Bhusawal | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 13.7286 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | HMI Up-gradation of Symphony Harmony DCS Unit-3, 210MW, BTPS. | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 5.54 | 5.54 | 5.54 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Supply, erection, commissioning and site testing of Plante 220V DC, 1285 AH, Station Battery Set and charging equipment for 1285 AH Plante battery for Unit 3. | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 1.7186 | 1.7186 | 1.7186 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Retrofitting of 6.6 kv breakers of unit -3 along without door plant boards by vacuum circuit breakers. | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 6.47 | 6.1083 | 6.1083 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 1.91 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.1 | Bhusawal: Procurement of HT motors (Coal Mill/CEP/CWP) for U-3 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 1.91 | 0.69703 | 0.69703 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.1 | Bhusawal: Unit 2-3 (1 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0.9384 | 0.9384 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.1 | Bhusawal: Unit 2-3 | MERC/CAPEX/20162017/00774 | 2016-09-30 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 13.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (ii) Submitted to MERC but yet to be approved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (iii) Yet to be submitted to MERC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| FY 2026-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | R&M/LE for Identified Thermal units of MSPGCL of BTPS U-3 (210 MW) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | R&M/LE for Identified Thermal units of MSPGCL of BTPS U-3 (210 MW) | 0 | 0 | 0 | 398 | 398 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| B) Non-DPR Schemes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Design, Supply and Installation for capacity enhancement of conveyor No. 08 at CHP210MW, BTPS. | 0 | 0 | 0 | 1.8001 | 1.8001 | 0 | 0 | 0 |  |  | 0 | 0
2 | SPEAKER & PTZ CAMER | 0 | 0 | 0 | 0.031968 | 0.031968 | 0 | 0 | 0 |  |  | 0 | 0
3 | 50 INCH TV & 2TN AC | 0 | 0 | 0 | 0.06453 | 0.06453 | 0 | 0 | 0 |  |  | 0 | 0
4 | Fixtures & Fitting (10801) | 0 | 0 | 0 | 0.02209 | 0.02209 | 0 | 0 | 0 |  |  | 0 | 0
5 | Office equpment (10901) | 0 | 0 | 0 | 0.60697 | 0.60697 | 0 | 0 | 0 |  |  | 0 | 0
6 | Gearboxes for CHP Elecon Make | 0 | 0 | 0 | 0.34574 | 0.34574 | 0 | 0 | 0 |  |  | 0 | 0
7 | General Assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Furniture & Fixture | 0 | 0 | 0 | 0.0035 | 0.0935 | -0.09 | 0 | 0 |  |  | 0 | -0.09
9 | Office Equipment | 0 | 0 | 0 | 0.25886 | 0.25886 | 0 | 0 | 0 |  |  | 0 | 0
10 | Furniture & Fixture | 0 | 0 | 0 | 0.2072 | 0.2072 | 0 | 0 | 0 |  |  | 0 | 0
11 | Office Equipment | 0 | 0 | 0 | 0.0063897 | 0.0063897 | 0 | 0 | 0 |  |  | 0 | 0
12 | Land | 0 | 0 | 0 | 0 | 0.19434 | -0.19434 | 0 | 0 |  |  | 0 | -0.19434
| Total |  |  |  | 460.3728 | 460.6572 | -0.28434 | 0 | 0 | 0 | 0 | 0 | -0.28434
FY 2028-29
a) DPR Schemes
(i) In-principle approved by MERC
1 | Replacement of economizer & LTSH coils at Unit # 2 | MERC/CAPEX/20122013/00179 | 2012-04-23 | 10.178 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Replacement of Economiser Coil | MERC/CAPEX/20122013/00179 | 2012-04-23 | 3.524 | 3.47 | 3.47 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/00179 | 2012-04-23 | 0.203 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | Replacement of LTSH Coil | MERC/CAPEX/20122013/00179 | 2012-04-23 | 6.094 | 5.32 | 5.32 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/00179 | 2012-04-23 | 0.357 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Boiler and Turbine improvement (Station Heat Rate Improvement) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 16.7838 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Vent condenser performance improvement by replacement of eroded tube nest by unit 3. | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.286 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Replacement of major extraction valves &NRVs of unit 3 | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.519 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | 60% replacement of boiler skin insulation (Unit 2) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.293 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Replacement of DM make up ( unit 3) and GSH water pump.( units 2 &3) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.206 | 0.26354 | 0.26354 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Replacement of LTSH coils (unit 3) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 8.369 | 5.32 | 5.32 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.6 | Replacement of ECO coils (unit 3) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 6.032 | 3.4728 | 3.4728 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.7 | Replacement of old LT AHP pump impeller by energy efficient stainless steel impeller | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.14881 | 0.14881 | 0.14881 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Measuring and Monitoring of Coal consumption | MERC/CAPEX/20122013/00912 | 2012-07-24 | 45.918 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Belt Weighers | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.8044 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.2 | Fully automatic pit-less in motion weigh bridges | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.4115 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.3 | Installation side arm charger for Wagon tippler 1A & 1B | MERC/CAPEX/20122013/00912 | 2012-07-24 | 21.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.4 | Dust Extraction System at Secondary Crusher house & Conveyor 6A/B at stage II CHP | MERC/CAPEX/20122013/00912 | 2012-07-24 | 2.0715 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.5 | Fogging system at a) WT old along with PCR, SCR and bunker level belt at Stage I CHP b) Conveyor 7A/B c) 100 Mtrx100 Mtr Coal stock area d) 200 Mtrx200 Mtr Coal stock area | MERC/CAPEX/20122013/00912 | 2012-07-24 | 2.2831 | 0.46954 | 0.46954 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.6 | Bunker level montoring system for 12 bunkers | MERC/CAPEX/20122013/00912 | 2012-07-24 | 2.5038 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.7 | Rotary pneumatic or electrical hammers | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.097 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.8 | Enhancement of unloading capacity of CHP from 360 TPH to 500 TPH | MERC/CAPEX/20122013/00912 | 2012-07-24 | 7.6508 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.9 | Quick detection of poor coal quality through CCTV on overhead watch tower focused onto the wagons, over which the rake passes at low speed & various conveyor tunnels | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.2968 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Motor controller for conveyor motors of Stage II CHP | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.9607 | 0.9607 | 0.9607 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.11 | Procurement of a CHN apparatus for ultimate analysis for operational optimization and coal mapping studies. | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.63617 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.12 | Additional bomb calorimeter | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.44012 | 0.19 | 0.19 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.13 | TGA analysis of the coal for operational optimization. | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.53214 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/00912 | 2012-07-24 | 5.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Turbine Auxiliary Performance Improvements | MERC/CAPEX/20122013/02107 | 2013-01-07 | 20.109 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Procurement and installation and commissioning of modified upgraded boiler feed pump (Type -200KHI/S) having energy efficient cartridge for unit 2 & 3 , BTPS. | MERC/CAPEX/20122013/02107 | 2013-01-07 | 17.47 | 8.6557 | 8.6557 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Replacement of brine pumps with modified pumps complete with S.S material in new WTP | MERC/CAPEX/20122013/02107 | 2013-01-07 | 1.029 | 0.3016 | 0.3016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/02107 | 2013-01-07 | 1.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Replacement of Platen water wall coils U#2,Super Heater & Platen Super Heater Coils for U#2 and Cold Reheater coils for U#2 & U#3 | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 13.692 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Supply & Erection of Platen Water wall coils Assembly from inlet header to outlet header in pent house for Unit No 2 | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 1.104 | 0.54 | 0.54 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Complete Supply & Erection of Super Heater Radiant Roof Panel Tube with Attachment for Unit No 2 Boiler From front side of Boiler to rear side of boiler & Vertical Platen Super Heater coils Assembly for Unit No 2, 210 MW Boiler. | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 5.477 | 5.4649 | 5.4649 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Supply & Erection of Reheater front Pendent Assembly consisting Full set of Cold Reheater coil assembly For Unit No 2 with necessary attachments, Crown Plate. Heat shield, roof seal bend, steam cooled spacer tube with necessary attachment. | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 2.711 | 2.6625 | 2.6625 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Supply & Erection of Reheater front Pendent Assembly consisting Full set of Cold Reheater coil assembly For Unit No 3 with necessary attachments, Crown Plate. Heat shield, roof seal bend, steam cooled spacer tube with necessary attachment. | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 2.711 | 2.3531 | 2.3531 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 1.689 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Boiler Process Improvement by replacement of damaged valves and Boiler Perfm Imp by Air Pre-Heater Up gradation of U#2 & U#3 at BTPS | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 17.37 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Replacement of boiler outlet valves and damaged valves of units 2 & 3 | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 2.62 | 1.3984 | 1.3984 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.2 | Air pre heater up gradation of heat exchanger matrix & regenerative dynamic sealing of units 2 & 3 | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 13.405 | 1.2086 | 1.2086 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 1.345 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Stack management by procurement of Bulldozer & LOCO and CHP area schemes for performance & unloading improvement | MERC/CAPEX/20162017/01426 | 2017-02-02 | 2.0931 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement of Locomotive 800 HP (2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 1.0396 | 1.0135 | 1.0135 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Procurement of 2 No’s of Bulldozer Model D-155(2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.53802 | 0.72969 | 0.72969 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.3 | Modification below primary crusher chutes 15A/B & Conv.02 | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.090248 | 0.079869 | 0.079869 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.4 | New helical gear box for various conveyors | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.16661 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.5 | Procurement of Elecon Make Ring Granulator Type TK-09-38B | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.11281 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.6 | Procurement of Elecon Make Ring Granulator Type TK6 32B Ring Granulator | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.071157 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.074628 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Upgradation of Symphony Harmony DCS, 220V 1285 AH Battery & Charger and Replacement of 6.6 kV HT MOCB by VCB at BTPS, Bhusawal | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 13.7286 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | HMI Up-gradation of Symphony Harmony DCS Unit-3, 210MW, BTPS. | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 5.54 | 5.54 | 5.54 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Supply, erection, commissioning and site testing of Plante 220V DC, 1285 AH, Station Battery Set and charging equipment for 1285 AH Plante battery for Unit 3. | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 1.7186 | 1.7186 | 1.7186 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Retrofitting of 6.6 kv breakers of unit -3 along without door plant boards by vacuum circuit breakers. | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 6.47 | 6.1083 | 6.1083 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 1.91 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.1 | Bhusawal: Procurement of HT motors (Coal Mill/CEP/CWP) for U-3 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 1.91 | 0.69703 | 0.69703 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.1 | Bhusawal: Unit 2-3 (1 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0.9384 | 0.9384 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.1 | Bhusawal: Unit 2-3 | MERC/CAPEX/20162017/00774 | 2016-09-30 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 13.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (ii) Submitted to MERC but yet to be approved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (iii) Yet to be submitted to MERC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| FY 2026-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | R&M/LE for Identified Thermal units of MSPGCL of BTPS U-3 (210 MW) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | R&M/LE for Identified Thermal units of MSPGCL of BTPS U-3 (210 MW) | 0 | 0 | 0 | 398 | 398 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| B) Non-DPR Schemes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Design, Supply and Installation for capacity enhancement of conveyor No. 08 at CHP210MW, BTPS. | 0 | 0 | 0 | 1.8001 | 1.8001 | 0 | 0 | 0 |  |  | 0 | 0
2 | SPEAKER & PTZ CAMER | 0 | 0 | 0 | 0.031968 | 0.031968 | 0 | 0 | 0 |  |  | 0 | 0
3 | 50 INCH TV & 2TN AC | 0 | 0 | 0 | 0.06453 | 0.06453 | 0 | 0 | 0 |  |  | 0 | 0
4 | Fixtures & Fitting (10801) | 0 | 0 | 0 | 0.02209 | 0.02209 | 0 | 0 | 0 |  |  | 0 | 0
5 | Office equpment (10901) | 0 | 0 | 0 | 0.60697 | 0.60697 | 0 | 0 | 0 |  |  | 0 | 0
6 | Gearboxes for CHP Elecon Make | 0 | 0 | 0 | 0.34574 | 0.34574 | 0 | 0 | 0 |  |  | 0 | 0
7 | General Assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Furniture & Fixture | 0 | 0 | 0 | 0.0035 | 0.0935 | -0.09 | 0 | 0 |  |  | 0 | -0.09
9 | Office Equipment | 0 | 0 | 0 | 0.25886 | 0.25886 | 0 | 0 | 0 |  |  | 0 | 0
10 | Furniture & Fixture | 0 | 0 | 0 | 0.2072 | 0.2072 | 0 | 0 | 0 |  |  | 0 | 0
11 | Office Equipment | 0 | 0 | 0 | 0.0063897 | 0.0063897 | 0 | 0 | 0 |  |  | 0 | 0
12 | Land | 0 | 0 | 0 | 0 | 0.19434 | -0.19434 | 0 | 0 |  |  | 0 | -0.19434
| Total |  |  |  | 460.3728 | 460.6572 | -0.28434 | 0 | 0 | 0 | 0 | 0 | -0.28434
FY 2029-30
a) DPR Schemes
(i) In-principle approved by MERC
1 | Replacement of economizer & LTSH coils at Unit # 2 | MERC/CAPEX/20122013/00179 | 2012-04-23 | 10.178 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Replacement of Economiser Coil | MERC/CAPEX/20122013/00179 | 2012-04-23 | 3.524 | 3.47 | 3.47 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/00179 | 2012-04-23 | 0.203 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | Replacement of LTSH Coil | MERC/CAPEX/20122013/00179 | 2012-04-23 | 6.094 | 5.32 | 5.32 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/00179 | 2012-04-23 | 0.357 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Boiler and Turbine improvement (Station Heat Rate Improvement) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 16.7838 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Vent condenser performance improvement by replacement of eroded tube nest by unit 3. | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.286 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Replacement of major extraction valves &NRVs of unit 3 | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.519 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | 60% replacement of boiler skin insulation (Unit 2) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.293 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Replacement of DM make up ( unit 3) and GSH water pump.( units 2 &3) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.206 | 0.26354 | 0.26354 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Replacement of LTSH coils (unit 3) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 8.369 | 5.32 | 5.32 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.6 | Replacement of ECO coils (unit 3) | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 6.032 | 3.4728 | 3.4728 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.7 | Replacement of old LT AHP pump impeller by energy efficient stainless steel impeller | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.14881 | 0.14881 | 0.14881 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/TECH 1/CAPEX/20122013/02325 | 2013-01-11 | 0.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Measuring and Monitoring of Coal consumption | MERC/CAPEX/20122013/00912 | 2012-07-24 | 45.918 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Belt Weighers | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.8044 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.2 | Fully automatic pit-less in motion weigh bridges | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.4115 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.3 | Installation side arm charger for Wagon tippler 1A & 1B | MERC/CAPEX/20122013/00912 | 2012-07-24 | 21.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.4 | Dust Extraction System at Secondary Crusher house & Conveyor 6A/B at stage II CHP | MERC/CAPEX/20122013/00912 | 2012-07-24 | 2.0715 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.5 | Fogging system at a) WT old along with PCR, SCR and bunker level belt at Stage I CHP b) Conveyor 7A/B c) 100 Mtrx100 Mtr Coal stock area d) 200 Mtrx200 Mtr Coal stock area | MERC/CAPEX/20122013/00912 | 2012-07-24 | 2.2831 | 0.46954 | 0.46954 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.6 | Bunker level montoring system for 12 bunkers | MERC/CAPEX/20122013/00912 | 2012-07-24 | 2.5038 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.7 | Rotary pneumatic or electrical hammers | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.097 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.8 | Enhancement of unloading capacity of CHP from 360 TPH to 500 TPH | MERC/CAPEX/20122013/00912 | 2012-07-24 | 7.6508 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.9 | Quick detection of poor coal quality through CCTV on overhead watch tower focused onto the wagons, over which the rake passes at low speed & various conveyor tunnels | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.2968 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Motor controller for conveyor motors of Stage II CHP | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.9607 | 0.9607 | 0.9607 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.11 | Procurement of a CHN apparatus for ultimate analysis for operational optimization and coal mapping studies. | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.63617 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.12 | Additional bomb calorimeter | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.44012 | 0.19 | 0.19 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.13 | TGA analysis of the coal for operational optimization. | MERC/CAPEX/20122013/00912 | 2012-07-24 | 0.53214 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/00912 | 2012-07-24 | 5.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Turbine Auxiliary Performance Improvements | MERC/CAPEX/20122013/02107 | 2013-01-07 | 20.109 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Procurement and installation and commissioning of modified upgraded boiler feed pump (Type -200KHI/S) having energy efficient cartridge for unit 2 & 3 , BTPS. | MERC/CAPEX/20122013/02107 | 2013-01-07 | 17.47 | 8.6557 | 8.6557 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Replacement of brine pumps with modified pumps complete with S.S material in new WTP | MERC/CAPEX/20122013/02107 | 2013-01-07 | 1.029 | 0.3016 | 0.3016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20122013/02107 | 2013-01-07 | 1.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Replacement of Platen water wall coils U#2,Super Heater & Platen Super Heater Coils for U#2 and Cold Reheater coils for U#2 & U#3 | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 13.692 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Supply & Erection of Platen Water wall coils Assembly from inlet header to outlet header in pent house for Unit No 2 | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 1.104 | 0.54 | 0.54 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Complete Supply & Erection of Super Heater Radiant Roof Panel Tube with Attachment for Unit No 2 Boiler From front side of Boiler to rear side of boiler & Vertical Platen Super Heater coils Assembly for Unit No 2, 210 MW Boiler. | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 5.477 | 5.4649 | 5.4649 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Supply & Erection of Reheater front Pendent Assembly consisting Full set of Cold Reheater coil assembly For Unit No 2 with necessary attachments, Crown Plate. Heat shield, roof seal bend, steam cooled spacer tube with necessary attachment. | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 2.711 | 2.6625 | 2.6625 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Supply & Erection of Reheater front Pendent Assembly consisting Full set of Cold Reheater coil assembly For Unit No 3 with necessary attachments, Crown Plate. Heat shield, roof seal bend, steam cooled spacer tube with necessary attachment. | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 2.711 | 2.3531 | 2.3531 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/TECH-1/CAPEX/20142015/006 | 2014-10-16 | 1.689 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Boiler Process Improvement by replacement of damaged valves and Boiler Perfm Imp by Air Pre-Heater Up gradation of U#2 & U#3 at BTPS | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 17.37 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Replacement of boiler outlet valves and damaged valves of units 2 & 3 | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 2.62 | 1.3984 | 1.3984 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.2 | Air pre heater up gradation of heat exchanger matrix & regenerative dynamic sealing of units 2 & 3 | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 13.405 | 1.2086 | 1.2086 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/Tech-1/CAPEX /2014-15/00433 | 2014-06-02 | 1.345 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Stack management by procurement of Bulldozer & LOCO and CHP area schemes for performance & unloading improvement | MERC/CAPEX/20162017/01426 | 2017-02-02 | 2.0931 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement of Locomotive 800 HP (2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 1.0396 | 1.0135 | 1.0135 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Procurement of 2 No’s of Bulldozer Model D-155(2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.53802 | 0.72969 | 0.72969 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.3 | Modification below primary crusher chutes 15A/B & Conv.02 | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.090248 | 0.079869 | 0.079869 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.4 | New helical gear box for various conveyors | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.16661 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.5 | Procurement of Elecon Make Ring Granulator Type TK-09-38B | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.11281 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.6 | Procurement of Elecon Make Ring Granulator Type TK6 32B Ring Granulator | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.071157 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.074628 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Upgradation of Symphony Harmony DCS, 220V 1285 AH Battery & Charger and Replacement of 6.6 kV HT MOCB by VCB at BTPS, Bhusawal | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 13.7286 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | HMI Up-gradation of Symphony Harmony DCS Unit-3, 210MW, BTPS. | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 5.54 | 5.54 | 5.54 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Supply, erection, commissioning and site testing of Plante 220V DC, 1285 AH, Station Battery Set and charging equipment for 1285 AH Plante battery for Unit 3. | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 1.7186 | 1.7186 | 1.7186 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Retrofitting of 6.6 kv breakers of unit -3 along without door plant boards by vacuum circuit breakers. | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 6.47 | 6.1083 | 6.1083 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/2019-2020/915 | 2019-10-22 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 1.91 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.1 | Bhusawal: Procurement of HT motors (Coal Mill/CEP/CWP) for U-3 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 1.91 | 0.69703 | 0.69703 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.1 | Bhusawal: Unit 2-3 (1 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0.9384 | 0.9384 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.1 | Bhusawal: Unit 2-3 | MERC/CAPEX/20162017/00774 | 2016-09-30 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 13.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (ii) Submitted to MERC but yet to be approved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (iii) Yet to be submitted to MERC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| FY 2026-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | R&M/LE for Identified Thermal units of MSPGCL of BTPS U-3 (210 MW) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | R&M/LE for Identified Thermal units of MSPGCL of BTPS U-3 (210 MW) | 0 | 0 | 0 | 398 | 398 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| B) Non-DPR Schemes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Design, Supply and Installation for capacity enhancement of conveyor No. 08 at CHP210MW, BTPS. | 0 | 0 | 0 | 1.8001 | 1.8001 | 0 | 0 | 0 |  |  | 0 | 0
2 | SPEAKER & PTZ CAMER | 0 | 0 | 0 | 0.031968 | 0.031968 | 0 | 0 | 0 |  |  | 0 | 0
3 | 50 INCH TV & 2TN AC | 0 | 0 | 0 | 0.06453 | 0.06453 | 0 | 0 | 0 |  |  | 0 | 0
4 | Fixtures & Fitting (10801) | 0 | 0 | 0 | 0.02209 | 0.02209 | 0 | 0 | 0 |  |  | 0 | 0
5 | Office equpment (10901) | 0 | 0 | 0 | 0.60697 | 0.60697 | 0 | 0 | 0 |  |  | 0 | 0
6 | Gearboxes for CHP Elecon Make | 0 | 0 | 0 | 0.34574 | 0.34574 | 0 | 0 | 0 |  |  | 0 | 0
7 | General Assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Furniture & Fixture | 0 | 0 | 0 | 0.0035 | 0.0935 | -0.09 | 0 | 0 |  |  | 0 | -0.09
9 | Office Equipment | 0 | 0 | 0 | 0.25886 | 0.25886 | 0 | 0 | 0 |  |  | 0 | 0
10 | Furniture & Fixture | 0 | 0 | 0 | 0.2072 | 0.2072 | 0 | 0 | 0 |  |  | 0 | 0
11 | Office Equipment | 0 | 0 | 0 | 0.0063897 | 0.0063897 | 0 | 0 | 0 |  |  | 0 | 0
12 | Land | 0 | 0 | 0 | 0 | 0.19434 | -0.19434 | 0 | 0 |  |  | 0 | -0.19434
| Total |  |  |  | 460.3728 | 460.6572 | -0.28434 | 0 | 0 | 0 | 0 | 0 | -0.28434