## F4
MSPGCL: Bhusawal U # 4-5
MTR Petition Formats - Generation
Form 4: Summary of Capital Expenditure and Capitalisation
Sr. No. | Particulars | FY 2022-23 |  |  | FY 2023-24 |  |  | FY 2024-24 |  |  |  |  | Ensuing Years |  |  |  |  | Remarks
|  | MYT Order (227 of 2022) | April-March (Audited ) | True-Up requirement | MYT Order (227 of 2022) | April-March (Audited ) | True-Up requirement | MYT Order (227 of 2022) | Apr-Sep (Estimated) | Oct-Mar (Projected) | April - March (Projected) | Provisional True-Up requirement | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30
|  | (a) | (b) | (c) = (b) - (a) | (d) | (e) | (f) = (e) - (d) | (j) | (k) | (l) | (m) = (k)+(l) | (n) = (m) - (j) | Projected | Projected | Projected | Projected | Projected
1 | Capital Expenditure |  | 14.829 | 14.829 |  | 10.8339 | 10.8339 |  |  |  | 164.5185 | 164.5185 | 811.31 | 532.6 | 243 | 257 | 145
2 | Capitalisation | 18.87 | 13.9194 | -4.9506 | 7.89 | 16.578 | 8.688 | 481.48 | 17.51 | 134.27 | 151.7831 | -329.6969 | 643.77 | 532.6 | 243 | 257 | 145
3 | IDC |  |  | 0 |  |  | 0 |  |  |  |  | 0
4 | Capitalisation + IDC | 18.87 | 13.9194 | -4.9506 | 7.89 | 16.578 | 8.688 | 481.48 | 17.51 | 134.27 | 151.7831 | -329.6969 | 643.77 | 532.6 | 243 | 257 | 145
Note: * - Truing Up for FY 2022-23 & FY 2023-24 to be done under MERC MYT Regulations 2019 with reference to amounts approved in the MYT Order for FY 2020-21 to FY 2024-25
Detailed Justification shall be provided for variation in approved capital expenditure and capitalisation vis-a-vis actual capital expenditure and capitalisation

## F4.1
MSPGCL: Bhusawal U # 4-5
MTR Petition Formats - Generation
| Project Details |  |  |  |  | Form 4.1: Capital Expenditure Plan | [11 empty] | (Rs. Crore)
Sr. No. | Project Code | Project Title | MERC Approval No. | MERC Approval Date | Project Purpose | Project Start Date |  |  | Project Completion date (Scheduled) |  |  | Capital Cost
[6 empty] | Original | Revised | Actual | Original | Revised | Actual | Approved | Actual Capital Cost Incurred | Deviation = Approved - Actual on account of
[14 empty] | Change in Scope of Work (a) | Material Cost (b) | IDC (c) | Others (d) | Total Deviation (a+b+c+d)
A) DPR Schemes
(i) Submitted to MERC
7 | Interconnection of 210 MW CHP to 500 MW CHP through Conveyors BC-02 & BC-03 having capacity of 500 TPH | DPR | MERC/CAPEX/20162017/00227 | 2016-05-24 |  | 2016-05-24 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
7.1 | Interconnection of 210 MW CHP to 500 MW CHP through Conveyors BC-02 & BC-03 having capacity of 500 TPH | Scheme | MERC/CAPEX/20162017/00227 | 2016-05-24 |  | 2016-05-24 |  | 05.12.2016 | 2018-05-24 |  | 2019-04-03 | 22.73 | 19.1067 |  | 3.6233 |  |  | 3.6233
0 | IDC | IDC | MERC/CAPEX/20162017/00227 | 2016-05-24 |  | 2016-05-24 |  | - | - |  | - | 1.27 | 0 |  | 1.27 |  |  | 1.27
8 | Stack management by procurement of Bulldozer & LOCO and CHP area schemes for performance & unloading improvement | DPR | MERC/CAPEX/20162017/01426 | 2017-02-02 |  | 2017-02-02 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
8.1 | Procurement of Locomotive 800 HP (2 No.’s) | Scheme | MERC/CAPEX/20162017/01426 | 2017-02-02 |  | 2017-02-02 |  | 2018-06-11 | 2018-02-02 |  | 1st loco - 01-12-2018 2nd loco - 26-03-2019 | 4.9504 | 4.8261 |  | 0.12433 |  |  | 0.12433
8.2 | Procurement of 2 No’s of Bulldozer Model D-155(2 No.’s) | Scheme | MERC/CAPEX/20162017/01426 | 2017-02-02 |  | 2017-02-02 |  | 2017-06-17 | 2018-02-02 |  | 2017-09-13 | 2.562 | 3.4747 |  | -0.91273 |  |  | -0.91273
8.3 | Modification below primary crusher chutes 15A/B & Conv.02 | Scheme | MERC/CAPEX/20162017/01426 | 2017-02-02 |  | 2017-02-02 |  | 2018-01-21 | 2019-02-02 |  | 2018-02-01 | 0.42975 | 0.38033 |  | 0.049421 |  |  | 0.049421
8.4 | New helical gear box for various conveyors | Scheme | MERC/CAPEX/20162017/01426 | 2017-02-02 |  | 2017-02-02 |  | - | 2019-02-02 |  | - | 0.79339 | 0 |  | 0.79339 |  |  | 0.79339
8.5 | Procurement of Elecon Make Ring Granulator Type TK-09-38B | Scheme | MERC/CAPEX/20162017/01426 | 2017-02-02 |  | 2017-02-02 |  | - | 2019-02-02 |  | - | 0.53719 | 0 |  | 0.53719 |  |  | 0.53719
8.6 | Procurement of Elecon Make Ring Granulator Type TK6 32B Ring Granulator | Scheme | MERC/CAPEX/20162017/01426 | 2017-02-02 |  | 2017-02-02 |  | - | 2019-02-02 |  | - | 0.33884 | 0 |  | 0.33884 |  |  | 0.33884
0 | IDC | IDC | MERC/CAPEX/20162017/01426 | 2017-02-02 |  | 2017-02-02 |  | - | - |  | - | 0.35537 | 0 |  | 0.35537 |  |  | 0.35537
9 | Construction of 1st raising of Ash bund from T.B.L. 258M to 264M at Bhusawal TPS | DPR | MERC/CAPEX/20172018/4267 | 2017-09-28 |  | 2017-09-28 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
9.1 | Construction of 1st raising of Ash bund from T.B.L. 258M to 264M at Bhusawal TPS | Scheme | MERC/CAPEX/20172018/4267 | 2017-09-28 |  | 2017-09-28 |  | 2017-10-27 | 2019-09-28 |  | 2019-04-20 | 64.22 | 64.4982 |  | -0.27824 |  |  | -0.27824
10 | Augmentation of Ash Evacuation System & Procurement of BCW Pump Motors at Bhusawal & Khaperkheda TPS 500 MW Units | DPR | MERC/CAPEX/20172018/4782 | 2017-11-28 |  | 2017-11-28 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
10.1 | Installation of standby Buffer Hopper parallel to existing pair of buffer hoppers | Scheme | MERC/CAPEX/20172018/4782 | 2017-11-28 |  | 2017-11-28 |  | - | 2018-11-28 |  | - | 11.5 | 0 |  | 11.5 |  |  | 11.5
10.2 | Installation of additional vacuum pump for every two passes, near to intermediate hopper. | Scheme | MERC/CAPEX/20172018/4782 | 2017-11-28 |  | 2017-11-28 |  | - | 2018-11-28 |  | - | 0.6 | 0 |  | 0.6 |  |  | 0.6
10.3 | Procurement of 02 Nos of M/s Torishima, Japan make, 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motors (without pump casing) with 02 lots of recommended Electrical & C&I spares for Bhusawal and Khaparkheda TPS 500MW. | Scheme | MERC/CAPEX/20172018/4782 | 2017-11-28 |  | 2017-11-28 |  | 2018-03-19 | 2018-11-28 |  | 2019-09-24 | 4.24 | 4.6696 |  | -0.42964 |  |  | -0.42964
10.4 | Procurement of complete ACVF drive module comprising of 2 Nos. of Supply and 3 Nos. of Inverter modules for GEHO pumps | Scheme | MERC/CAPEX/20172018/4782 | 2017-11-28 |  | 2017-11-28 |  | 2018-10-22 | 2018-11-28 |  | 2019-07-17 | 0.95 | 0.92864 |  | 0.021357 |  |  | 0.021357
10.5 | Supply, erection and commissioning of 24VDC, 100A Float & Float cum Boost Battery Charger with 325Ah Battery Bank for CWPH at BTPS 2x500 MW. | Scheme | MERC/CAPEX/20172018/4782 | 2017-11-28 |  | 2017-11-28 |  | 2018-02-12 | 2018-11-28 |  | 2018-12-13 | 0.15 | 0.15788 |  | -0.007884 |  |  | -0.007884
0 | IDC | IDC | MERC/CAPEX/20172018/4782 | 2017-11-28 |  | 2017-11-28 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
11 | Various schemes for renovation of colony at Bhusawal TPS | DPR | MERC/CAPEX/20172018/0221 | 2018-02-12 |  | 2018-02-12 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
11.1 | Renovation of staff quarters & related work at BTPS Deepnagar | Scheme | MERC/CAPEX/20172018/0221 | 2018-02-12 |  | 2018-02-12 |  | a) 05-09-2018 b)05-09-2018 c) 16-11-2018 d) 16-11-2018 e)19-11-2018 | a) 05-06-2019 b) 05-09-2019 c) 16-11-2019 d) 16-11-2019 e) 19-05-2019 |  | a) 04-06-2019 b) 04-09-2019 c) 31-12-2019 d) 31-12-2019 e) 20-03-2020 | 7.021 | 5.4584 |  | 1.5626 |  |  | 1.5626
11.2 | Colony Internal Roads at BTPS, Deepnagar | Scheme | MERC/CAPEX/20172018/0221 | 2018-02-12 |  | 2018-02-12 |  | a) 15-05-2018 b) 13-08-2018 | a) 15-02-2019 b) 13-02-2019 |  | a) 20-12-2018 b) 12-02-2019 | 3.85 | 3.2501 |  | 0.59993 |  |  | 0.59993
11.3 | Water supply , sanitary & drainage works at BTPS, Deepnagar | Scheme | MERC/CAPEX/20172018/0221 | 2018-02-12 |  | 2018-02-12 |  | a) 07-08-2018 b) 23-11-2018 c) 16-11-2018 d) 16-11-2018 | a) 07-08-2019 b) 23-08-2019 c) 16-08-2019 d) 16-08-2019 |  | a) 06-08-2019 b) 25-07-2019 c) 31-12-2019 d) 31-12-2019 | 7.3 | 5.8361 |  | 1.4639 |  |  | 1.4639
11.4 | Plinth protection to existing buildings at BTPS, Deepnagar | Scheme | MERC/CAPEX/20172018/0221 | 2018-02-12 |  | 2018-02-12 |  | 2018-09-24 | 2019-06-24 |  | 2018-12-30 | 1.1631 | 0.91823 |  | 0.24489 |  |  | 0.24489
12 | Pipeline from River Water Pump House (RWPH) to aquaduct over Bhogawati River and Other allied power house road works under DPR scheme at BTPS, Bhusawal | DPR | MERC/CAPEX/2018-2019/0104 | 2019-04-04 |  | 2019-04-04 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
12.1 | Providing supplying laying, jointing, testing and commissioning of 1650 mm Ø ID 8 mm thick M.S. pipeline for raw water supply from RWPH to aquaduct over Bhogawati river at, BTPS, Bhusawal. | Scheme | MERC/CAPEX/2018-2019/0104 | 2019-04-04 |  | 2019-04-04 |  | - | 2020-04-04 |  | - | 7.257 | 0 |  | 7.257 |  |  | 7.257
12.2 | Construction of WBM and Bituminous road along inlet & outlet canals and concreate road along periphery of Major store at BTPS, Bhusawal. | Scheme | MERC/CAPEX/2018-2019/0104 | 2019-04-04 |  | 2019-04-04 |  | a) 20-08-2021 b) 27-03-2021 c) 01-12-2022 | 2020-04-04 |  | a) 10-04-2023 b) 25-04-2023 c) 20-03-2023 | 4.22 | 3.8305 |  | 0.38953 |  |  | 0.38953
12.3 | Work of construction of self-supporting steel roofing system for a major store godown shed of span 25M at BTPS, Deepnagar. | Scheme | MERC/CAPEX/2018-2019/0104 | 2019-04-04 |  | 2019-04-04 |  | 2019-08-31 | 2020-04-04 |  | 2022-03-28 | 1.6402 | 0.27 |  | 1.3702 |  |  | 1.3702
0 | IDC | IDC | MERC/CAPEX/2018-2019/0104 | 2019-04-04 |  | 2019-04-04 |  | - | - |  | - | 0 | 0.14918 |  | -0.14918 |  |  | -0.14918
13 | Supply, erection, commissioning & site testing of 220 V, 2035 AH, Station Battery Sets (4 Nos.) and 24 V, 2250 AH, SG/TG & BOP Battery Sets (8 Nos.) for U# 4 & 5 along with accessories at 2 x 500 MW BTPS, Bhusawal | DPR | MERC/CAPEX/2017-2018/1226 | 2018-08-10 |  | 2018-08-10 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
13.1 | Supply, erection, commissioning & site testing of 220V, 2035 AH Station Battery Sets (02 Nos.) and 24V, 2250AH, SG/TG & BOP Battery Set (04 Nos.) along with accessories for Unit No.5 at BTPS 2x500MW. | Scheme | MERC/CAPEX/2017-2018/1226 | 2018-08-10 |  | 2018-08-10 |  | 2018-10-22 | 2019-08-10 |  | 2019-09-27 | 5.795 | 6.374 |  | -0.57896 |  |  | -0.57896
13.2 | Supply, erection, commissioning & site testing of 220V, 2035 AH Station Battery Sets (02 Nos.) and 24V, 2250AH, SG/TG & BOP Battery Set (04 Nos.) along with accessories for Unit No.4 at BTPS 2x500MW. | Scheme | MERC/CAPEX/2017-2018/1226 | 2018-08-10 |  | 2018-08-10 |  | 2019-02-26 | 2019-08-10 |  | 2022-02-12 | 5.795 | 6.3227 |  | -0.52773 |  |  | -0.52773
15 | Flue Gas Desulphurization (FGD) System for 500 MW Units (Total 8 Nos) of MSPGCL | DPR | MERC/CAPEX/2020-2021/WFH/SBR/45 | 2021-02-05 |  | 2021-02-05 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
15.1 | Flue Gas Desulphurization (FGD) System for Bhusawal Unit 4-5 | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/45 | 2021-02-05 |  | 2021-02-05 |  | - | - |  | - | 830.4 | 0 |  | 830.4 |  |  | 830.4
0 | IDC | IDC | MERC/CAPEX/2020-2021/WFH/SBR/45 | 2021-02-05 |  | 2021-02-05 |  | - | - |  | - | 39.1 | 0 |  | 39.1 |  |  | 39.1
16 | Procurement of two BFP Cartridges & one rotor of Turbine driven BFP & at 500MW BTPS, Bhusawal | DPR | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 |  | 2021-03-08 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
16.1 | Procurement of two BFP Cartridges at 500MW BTPS, Bhusawal | Scheme | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 |  | 2021-03-08 |  | 2021-10-26 | 2023-09-08 |  | - | 3.84 | 2.24 |  | 1.6 |  |  | 1.6
16.2 | Procurement of one rotor of Turbine driven BFP at 500MW BTPS, Bhusawal | Scheme | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 |  | 2021-03-08 |  | 2021-07-16 | 2023-09-08 |  | 2022-03-21 | 6.46 | 7.6136 |  | -1.1536 |  |  | -1.1536
0 | IDC | IDC | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 |  | 2021-03-08 |  | - | - |  | - | 0.22 | 0 |  | 0.22 |  |  | 0.22
17 | CHP Improvement Schemes at 2X500MW, BTPS, Bhusawal | DPR | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 |  | 2021-06-10 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
17.1 | Revamping of Apron Feeder in CHP at 2X500MW, BTPS | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 |  | 2021-06-10 |  | a) 01-09-2022 (Apron Feeder -2) b) 05-11-2022 (Apron Feeder-3) | 2022-06-10 |  | - | 4.67 | 4.6492 |  | 0.0208 |  |  | 0.0208
17.2 | Design, engineering, manufacturing, supply, Erection and commissioning of short conveyor from stack yard to belt feeder 112 in CHP 2x500MW BTPS. | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 |  | 2021-06-10 |  | 2023-03-27 | 2022-06-10 |  | 2024-02-20 | 3.53 | 3.9648 |  | -0.43475 |  |  | -0.43475 | Justification provided in annexure
17.3 | Design, engineering, manufacturing, supply, Erection and commissioning of stone grappler at Wagon Tippler No.3 in CHP 2x500MW BTPS. | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 |  | 2021-06-10 |  | - | 2022-06-10 |  | - | 0.84 | 0 |  | 0.84 |  |  | 0.84
17.4 | Procurement of suspended magnets in CHP 2x500MW BTPS. | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 |  | 2021-06-10 |  | 2021-03-22 | 2022-06-10 |  | 2022-05-04 | 2.95 | 2.947 |  | 0.00295 |  |  | 0.00295
17.5 | Supply, Erection And Commissioning of Electro-Mechanical Drive to Apron Feeder at CHP 500MW | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 |  | 2021-06-10 |  | - | 2022-06-10 |  | - | 7.57 | 0 |  | 7.57 |  |  | 7.57
0 | IDC | IDC | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 |  | 2021-06-10 |  | - | - |  | - | 1.66 | 0.067524 |  | 1.5925 |  |  | 1.5925
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | DPR | MERC/CAPEX/20162017/00423 | 2016-08-03 |  | 2016-08-03 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
1 | Bhusawal: Unit 4-5 (3 Nos.) | Scheme | MERC/CAPEX/20162017/00423 | 2016-08-03 |  | 2016-08-03 |  | 2017-06-17 | 2018-08-03 |  | 2019-06-05 | 3.9773 | 1.9468 |  | 2.0305 |  |  | 2.0305
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | DPR | MERC/CAPEX/20162017/00774 | 2016-09-30 |  | 2016-09-30 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
1 | Bhusawal: Unit 4-5 | Scheme | MERC/CAPEX/20162017/00774 | 2016-09-30 |  | 2016-09-30 |  | - | - |  | - | 4.0552 | 0 |  | 4.0552 |  |  | 4.0552
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | DPR | MERC/CAPEX/20172018/4653 | 2017-11-13 |  | 2017-11-13 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
1 | Advance Multipurpose Fire Tender for BTPS 4-5 | Scheme | MERC/CAPEX/20172018/4653 | 2017-11-13 |  | 2017-11-13 |  | 2019-01-16 | 2019-11-13 |  | 2021-09-03 | 1.45 | 1.7765 |  | -0.3265 |  |  | -0.3265
2 | Normal Multipurpose Fire Tender for BTPS 4-5 | Scheme | MERC/CAPEX/20172018/4653 | 2017-11-13 |  | 2017-11-13 |  | 2022-02-18 | 2019-11-13 |  | 2023-02-27 | 2.5 | 2.1847 |  | 0.31535 |  |  | 0.31535
0 | IDC | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 |  | 2017-11-13 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | DPR | MERC/CAPEX/20172018/0177 | 2018-02-06 |  | 2018-02-06 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
1 | Bhusawal: Unit 4-5 | Scheme | MERC/CAPEX/20172018/0177 | 2018-02-06 |  | 2018-02-06 |  | 2018-09-06 | 2019-08-06 |  | 2021-07-15 | 10.0654 | 9.1854 |  | 0.87996 |  |  | 0.87996
18 | Procurement of assembly of baskets for Air Pre-heater of type 31.5 VIM 2000 (72° PA), Replacement of thermal insulation of Boiler, Ducts & Steam Pipelines and Coal Mill Gear Box in 2x500MW at BTPS, Bhusawal | DPR | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 |  | 2021-09-22 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
18.1 | Procurement of assembly of baskets for Air Preheater of type 31.5 VIM 2000 (72° PA) for Unit-4&5 | Scheme | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 |  | 2021-09-22 |  | 2021-09-22 | 2022-09-22 |  | 2022-02-11 | 5.53 | 8.411 |  | -2.881 |  |  | -2.881
18.2 | Replacement of thermal insulation of Boiler, Ducts & Steam Pipelines along with supply | Scheme | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 |  | 2021-09-22 |  | 2021-09-23 | 2022-09-22 |  | - | 3.52 | 0 |  | 3.52 |  |  | 3.52
18.3 | Supply of XRP-1043 coal mill gearbox spares in unit-4&5. | Scheme | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 |  | 2021-09-22 |  | 2024-03-14 | 2022-09-22 |  | 2024-04-02 | 5.39 | 0 |  | 5.39 |  |  | 5.39
0 | IDC | IDC | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 |  | 2021-09-22 |  | - | - |  | - | 0.52 | 0 |  | 0.52 |  |  | 0.52
19 | Up-gradation of Operating System of Max DNA DCS, GE Fanuc PLC system & Schneider PLC system & Procurement of Critical Insurance spares for PA and FD fans System at 2 x 500 MW Units BTPS Bhusawal | DPR | MERC/CAPEX/2023-2024/0178 | 2024-03-11 |  | 2024-03-11 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
19.1 | Up-gradation of Existing MaxDNA System (HMI) at 500MW BTPS, Bhusawal | Scheme | MERC/CAPEX/2023-2024/0178 | 2024-03-11 |  | 2024-03-11 |  | - | - |  | - | 8.69 | 0 |  | 8.69 |  |  | 8.69
19.2 | Up-gradation of GE IP (GE-Fanuc) make PLC system (HMI) installed at AHP, CPU plant, FOPH, FWPH and Mill Reject system at 2x500MW BTPS, Bhusawal. | Scheme | MERC/CAPEX/2023-2024/0178 | 2024-03-11 |  | 2024-03-11 |  | - | - |  | - | 1.35 | 0 |  | 1.35 |  |  | 1.35
19.3 | Up-gradation of Schneider PLC System at 2x500MW, BTPS, Bhusawal | Scheme | MERC/CAPEX/2023-2024/0178 | 2024-03-11 |  | 2024-03-11 |  | - | - |  | - | 2.33 | 0 |  | 2.33 |  |  | 2.33
19.4 | Procurement of Rotor assembly with blade set for PA and FD fan at 2 X 500 MW BTPS Bhusawal | Scheme | MERC/CAPEX/2023-2024/0178 | 2024-03-11 |  | 2024-03-11 |  | - | - |  | - | 18.18 | 0 |  | 18.18 |  |  | 18.18
0 | IDC | IDC | MERC/CAPEX/2023-2024/0178 | 2024-03-11 |  | 2024-03-11 |  | - | - |  | - | 0.5 | 0 |  | 0.5 |  |  | 0.5
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | DPR | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 |  | 2022-02-12 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | Scheme | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 |  | 2022-02-12 |  | - | - |  | - | 54.24 | 0 |  | 54.24 |  |  | 54.24
0 | IDC | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 |  | 2022-02-12 |  | - | - |  | - | 2.76 | 0 |  | 2.76 |  |  | 2.76
HO DPR 16 | Centralized Monitoring Solution | DPR | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 |  | 2023-11-02 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
1 | Centralized Monitoring Solution | Scheme | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 |  | 2023-11-02 |  | - | - |  | - | 66.009 | 0 |  | 66.009 |  |  | 66.009
0 | IDC | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 |  | 2023-11-02 |  | - | - |  | - | 3.3 | 0 |  | 3.3 |  |  | 3.3
20 | Improvement of Loadability and Availability of Coal Handling Plant at BTPS, Bhusawal | DPR | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 |  | 2024-05-17 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
20.1 | Scheme-1:-Design Engineering, Supply, Erection, commissioning, Extension of travel Length & Capacity Enhancement of coal yard with additional drive system of stacker reclaimer conveyor No. 110 at in coal handling Plant BTPS. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 |  | 2024-05-17 |  | - | - |  | - | 14.27 | 0 |  | 14.27 |  |  | 14.27
20.2 | Scheme-2:-Design, Engineering, Rectification, Erection & Commissioning of Z point at Conveyor 108A & B at CHP-500MW. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 |  | 2024-05-17 |  | - | - |  | - | 8.18 | 0 |  | 8.18 |  |  | 8.18
20.3 | Scheme-3:-Design, Engineering and provision of material lifting arrangement for crusher floor, wobbler feeder & C-105 floor In CHP BTPS. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 |  | 2024-05-17 |  | - | - |  | - | 1.88 | 0 |  | 1.88 |  |  | 1.88
20.4 | Scheme-4:-Structural up-gradation and rehabilitation of reversible yard conveyor in coal handling plant. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 |  | 2024-05-17 |  | - | - |  | - | 4.21 | 0 |  | 4.21 |  |  | 4.21
20.5 | Scheme-5:-Design, Engineering, Erection and commissioning of Receiving and discharge chutes of wobbler feeders in CHP BTPS. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 |  | 2024-05-17 |  | - | - |  | - | 6.25 | 0 |  | 6.25 |  |  | 6.25
20.6 | Scheme-6: Procurement of 3 Nos. of Bulldozers at BTPS, Bhusawal. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 |  | 2024-05-17 |  | - | - |  | - | 7.35 | 0 |  | 7.35 |  |  | 7.35
0 | IDC | 0 | 0 | - |  | - |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
21 | Performance Improvement of Coal Handling Plant at BTPS-U4 & 5, Bhusawal | DPR | MERC/CAPEX/MSPGCL/2024-25/0310 | - |  | - |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
21.1 | Scheme-1: Revamping, Modification of Gravity take-up and Drive Augmentation of Bunkering conveyor in CHP BTPS | Scheme | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 |  | 2024-05-17 |  | - | - |  | - | 11.35 | 0 |  | 11.35 |  |  | 11.35
21.2 | Scheme-2: Revamping of coal diverting chutes in CHP 2x500 MW BTPS | Scheme | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 |  | 2024-05-17 |  | - | - |  | - | 5.73 | 0 |  | 5.73 |  |  | 5.73
21.3 | Scheme-3: Revamping and structural augmentation of Reversible feeder conveyors in CHP-BTPS. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 |  | 2024-05-17 |  | - | - |  | - | 1.77 | 0 |  | 1.77 |  |  | 1.77
21.4 | Scheme-4: Revamping and up-gradation of air & ventilation system in Coal Handling Plant-BTPS. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 |  | 2024-05-17 |  | - | - |  | - | 9.01 | 0 |  | 9.01 |  |  | 9.01
21.5 | Scheme-5: Revamping, Structural & drive up-gradation of conveyor-111 in CHP-BTPS. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 |  | 2024-05-17 |  | - | - |  | - | 3.85 | 0 |  | 3.85 |  |  | 3.85
21.6 | Scheme-6: Revamping and structural up-gradation of conveyor system in tunnel area in Coal Handling Plant-BTPS. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 |  | 2024-05-17 |  | - | - |  | - | 8.62 | 0 |  | 8.62 |  |  | 8.62
21.7 | Scheme-7: Erection & Commissioning of Travelling type coal chutes in CHP BTPS. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 |  | 2024-05-17 |  | - | - |  | - | 8.06 | 0 |  | 8.06 |  |  | 8.06
21.8 | Scheme-8: Revamping of scoop cooling system installed in coal handling plant BTPS. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 |  | 2024-05-17 |  | - | - |  | - | 4.98 | 0 |  | 4.98 |  |  | 4.98
21.9 | Scheme-9: Retrofitting and Up-gradation of Dewatering system in CHP-BTPS. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 |  | 2024-05-17 |  | - | - |  | - | 3.92 | 0 |  | 3.92 |  |  | 3.92
0 | IDC | 0 | 0 | - |  | - |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
Formulas:
Project Start Date = [MERC Approval Date]

## F4.2
|  |  | MSPGCL: Bhusawal U # 4-5 | [52 empty] | DPR | Not Initiated
|  |  | MTR Petition Formats - Generation | [52 empty] | Scheme | WIP
| Project Details |  | Form 4.2: Capitalisation Plan | [43 empty] | (Rs. Crore) | [8 empty] | IDC | Partially Capitalised
Sr. No. | Project Code | Project Title | MERC Approval No. | Date of Submission | MERC Approval Date | Cost as per DPR Crs. | MERC Approved Cost | Debt Equity Ratio | Grant Funding | Approved Start Date | Actual Start Date | Approved Date of Completion | Actual Date of Completion | Benefits in Quantified Terms | Capital Expenditure | [12 empty] | Physical Progress (%) | [11 empty] | Capitalisation | [12 empty] | Old Asset retired against capitalised item (in Rs. Cr) | Remarks | Current Status | Non-DPR | Capitalised
[15 empty] | Actual Capex till FY 2018-19 | Actual | Actual | Actual | Actual Capex till FY 2021-22 | Actual | Actual | Revised Projected | Projected | Projected | Projected | Projected | Projected | Actual Progress till FY 2018-19 | Actual | Actual | Actual | Actual | Actual | Revised Projected | Projected | Projected | Projected | Projected | Projected | Actual Capitalization till FY 2018-19 | Actual | Actual | Actual | Actual Capitalization till FY 2021-22 | Actual | Actual | Revised Projected | Projected | Projected | Projected | Projected | Projected |  |  |  |  | Cancelled
[16 empty] | FY 2019-20 | FY 2020-21 | FY 2021-22 |  | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 |  | FY 2019-20 | FY 2020-21 | FY 2021-22 | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 |  | FY 2019-20 | FY 2020-21 | FY 2021-22 |  | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 |  |  |  |  | To be cancelled
[55 empty] | N.A. |  | N.A.
| A) DPR Schemes | [53 empty] | N.A. |  | To be confirmed
| (i) Submitted to MERC | [53 empty] | N.A.
7 | Interconnection of 210 MW CHP to 500 MW CHP through Conveyors BC-02 & BC-03 having capacity of 500 TPH | DPR | MERC/CAPEX/20162017/00227 | 2015-10-30 | 2016-05-24 | 24 | 24 |  |  | 2016-05-24 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
7.1 | Interconnection of 210 MW CHP to 500 MW CHP through Conveyors BC-02 & BC-03 having capacity of 500 TPH | Scheme | MERC/CAPEX/20162017/00227 | 2015-10-30 | 2016-05-24 | 22.73 | 22.73 |  |  | 2016-05-24 | 05.12.2016 | 2018-05-24 | 2019-04-03 | • Reduction in Cost of Road Transportation . 1) In finacial year 2020-21:687075 MT coal is transported from these belts. Rs.1.49 Cr. saving is done 2) In finacial year 2020-21:520483 MT coal is transported from these belts. Rs.1.12 Cr. saving is done • Reduction in Demurrage charges. | 18.8298 | 0.27691 |  |  | 19.1067 | [8 empty] | 96% | 100% | [10 empty] | 0 | 19.1067 |  |  | 19.1067 | [10 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/20162017/00227 | 2015-10-30 | 2016-05-24 | 1.27 | 1.27 |  |  | 2016-05-24 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
8 | Stack management by procurement of Bulldozer & LOCO and CHP area schemes for performance & unloading improvement | DPR | MERC/CAPEX/20162017/01426 | 2016-02-03 | 2017-02-02 | 9.9669 | 9.9669 |  |  | 2017-02-02 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
8.1 | Procurement of Locomotive 800 HP (2 No.’s) | Scheme | MERC/CAPEX/20162017/01426 | 2016-02-03 | 2017-02-02 | 4.9504 | 4.9504 |  |  | 2017-02-02 | 2018-06-11 | 2018-02-02 | 1st loco - 01-12-2018 2nd loco - 26-03-2019 | * Improvement in coal rake movement, shunting operation and placement of coal wagons at different tippler units at CHP-500 MW, BTPS.It results in increase in average unloading rate of rakes. Average unloading rate of coal wagons per hour is increased to 12 wagons/hrs from 6 to 8 wagons /hr at CHP-500 MW, BTPS. * Average unloading of coal wagons per day is increased to 300 to 350.Avg unloading time per rake in hour is reduced from 10 hr to 6 hr since commissioning. * Reduction in demurrage hours & maintain sufficient bunker level by maintaining coal feeding rate due to efficient coal rake movement with the help of new locomotives. * R&M expenditure against the locomotives since commissioning is nil. * Availability & reliability of new locomotives is maximum i.e. 90 to 95 % since commissioning. * Performance and efficiency of locomotives since commissioning is maximum. * Procurement for maintenance against these locomotives since commissioning is almost Nil. * Decrease in downtime of system resulting into overall improvement in system efficiency | 4.8261 |  |  |  | 4.8261 | [8 empty] | 100% | [11 empty] | 4.8261 |  |  |  | 4.8261 | [9 empty] | PO placed vide-HO/4370001547/No-07347 dated 19-06-2018. 1st loco- Material received on dtd. 23-11-2018. Commisioning done on dtd.01-12-2018. 2nd loco - Material received on dtd. 13-02-2019. Commisioning done on dtd.26-03-2019. Capitalization done in FY-2018-19 of Rs. 5.84 Cr. 4.83 Cr. amount capitalized in U#4 & 5. Remaining amount capitalised in U#3. | Capitalised
8.2 | Procurement of 2 No’s of Bulldozer Model D-155(2 No.’s) | Scheme | MERC/CAPEX/20162017/01426 | 2016-02-03 | 2017-02-02 | 2.562 | 2.562 |  |  | 2017-02-02 | 2017-06-17 | 2018-02-02 | 2017-09-13 | * Contribution in reduction of demurrage hours by doing proper coal stack management with help of bulldozers. * For maintaining the proper coal flow rate as per load demand while in reclaiming mode (dozing the coal from remote location to vicinity of the stacker reclaimer area). * O&M expenditure on these bulldozers since commissioning is very less i.e. around 5 to 6.20 % per year asset cost. * Availability and reliability of bulldozers are around 90 to 95% since commissioning. * Performance and efficiency of bulldozers since commissioning is maximum. * Procurement for maintenance against these bulldozers since commissioning is almost nil. * Decrease in downtime of system resulting into overall improvement in system efficiency. | 3.4747 |  |  |  | 3.4747 | [8 empty] | 100% | [11 empty] | 3.4747 |  |  |  | 3.4747 | [9 empty] | PO placed vide-HO/4370001085/No-010160 dated 18-08-2017. Work completed on 13-09-2017. Capitalization done in FY-2017-18 of Rs. 4.2 Cr. 3.47 Cr. amount capitalized in U#4 & 5. Remaining amount capitalised in U#3. | Capitalised
8.3 | Modification below primary crusher chutes 15A/B & Conv.02 | Scheme | MERC/CAPEX/20162017/01426 | 2016-02-03 | 2017-02-02 | 0.42975 | 0.42975 |  |  | 2017-02-02 | 2018-01-21 | 2019-02-02 | 2018-02-01 | 1)Daily outage of the system is reduced almost 100% 2)Wear and tear of the plates reduced.Due to these scheme system failure reduced in finacial year 20-21 around 20 lakh Rs saving done & in finacial year 21-22 around 17 lakh Rs saving done | 0.38033 |  |  |  | 0.38033 | [8 empty] | 100% | [11 empty] | 0.38033 |  |  |  | 0.38033 | [9 empty] | PO placed vide-HO/4370000471/No-04816 dated 19-07-2017. Work completed on 01-02-2018. Capitalization done in FY-2017-18 of Rs. 0.46 Cr. 0.38 Cr. amount capitalized in U#4 & 5. Remaining amount capitalised in U#3. | Capitalised
8.4 | New helical gear box for various conveyors | Scheme | MERC/CAPEX/20162017/01426 | 2016-02-03 | 2017-02-02 | 0.79339 | 0.79339 |  |  | 2017-02-02 |  | 2019-02-02 |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
8.5 | Procurement of Elecon Make Ring Granulator Type TK-09-38B | Scheme | MERC/CAPEX/20162017/01426 | 2016-02-03 | 2017-02-02 | 0.53719 | 0.53719 |  |  | 2017-02-02 |  | 2019-02-02 |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [9 empty] | Reason for cancellation- Due to urgency of spares for Ring granulators, BTPS requested Parli TPS to issue spares of ring granulator from the decommissioned units. Accordingly Parli TPS issued the material to BTPS. | Cancelled
8.6 | Procurement of Elecon Make Ring Granulator Type TK6 32B Ring Granulator | Scheme | MERC/CAPEX/20162017/01426 | 2016-02-03 | 2017-02-02 | 0.33884 | 0.33884 |  |  | 2017-02-02 |  | 2019-02-02 |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [9 empty] | Reason for cancellation- Due to urgency of spares for Ring granulators, BTPS requested Parli TPS to issue spares of ring granulator from the decommissioned units. Accordingly Parli TPS issued the material to BTPS. | Cancelled
| IDC | IDC | MERC/CAPEX/20162017/01426 | 2016-02-03 | 2017-02-02 | 0.35537 | 0.35537 |  |  | 2017-02-02 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
9 | Construction of 1st raising of Ash bund from T.B.L. 258M to 264M at Bhusawal TPS | DPR | MERC/CAPEX/20172018/4267 | 2017-05-12 | 2017-09-28 | 64.22 | 64.22 |  |  | 2017-09-28 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
9.1 | Construction of 1st raising of Ash bund from T.B.L. 258M to 264M at Bhusawal TPS | Scheme | MERC/CAPEX/20172018/4267 | 2017-05-12 | 2017-09-28 | 64.22 | 64.22 |  |  | 2017-09-28 | 2017-10-27 | 2019-09-28 | 2019-04-20 | • Storage capacity of ash bund increased. • Air pollution reduced. • Increased qty of ash water from bund for re-utilization. • Safeguard stability of bund increased. | 60.5458 | 3.9524 |  |  | 64.4982 | [8 empty] | 80% | 100% | [10 empty] | 0 | 64.4982 |  |  | 64.4982 | [9 empty] | Revised PO No-4370001610, Work completed on 20-04-2019. Capitalization done in FY-2019-20 of Rs. 64.50 Cr. | Capitalised
10 | Augmentation of Ash Evacuation System & Procurement of BCW Pump Motors at Bhusawal & Khaperkheda TPS 500 MW Units | DPR | MERC/CAPEX/20172018/4782 | 2017-05-20 | 2017-11-28 | 43.98 | 17.44 |  |  | 2017-11-28 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
10.1 | Installation of standby Buffer Hopper parallel to existing pair of buffer hoppers | Scheme | MERC/CAPEX/20172018/4782 | 2017-05-20 | 2017-11-28 | 34.5 | 11.5 |  |  | 2017-11-28 |  | 2018-11-28 |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
10.2 | Installation of additional vacuum pump for every two passes, near to intermediate hopper. | Scheme | MERC/CAPEX/20172018/4782 | 2017-05-20 | 2017-11-28 | 1.8 | 0.6 |  |  | 2017-11-28 |  | 2018-11-28 |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
10.3 | Procurement of 02 Nos of M/s Torishima, Japan make, 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motors (without pump casing) with 02 lots of recommended Electrical & C&I spares for Bhusawal and Khaparkheda TPS 500MW. | Scheme | MERC/CAPEX/20172018/4782 | 2017-05-20 | 2017-11-28 | 4.24 | 4.24 |  |  | 2017-11-28 | 2018-03-19 | 2018-11-28 | 2019-09-24 | * Although the scheme does not have direct measurable benefit, however, there is improvement in availability and reliability of the BCW system. * In case of failure of running equipment,following Generation loss - If two BCW pumps are not available & only one BCW Pump is in service, (Partial Load Loss) Assume Gross Gen@280MW, Gen Loss will be 220MW. AFC for one Unit- Rs. 1.47 Cr/day Loading will be 56% only. Then, AFC recovery- Rs. 0.82 Cr. Hence, AFC Loss- Rs. 0.65 Cr/day . | 0 | 4.6696 |  |  | 4.6696 | [8 empty] | 0% | 100% | [10 empty] | 0 | 4.6696 |  |  | 4.6696 | [9 empty] | *PO placed vide BTPS/4370001282/No-01961 dated 19-03-2018. PO amount is Rs. 4.50 Cr. * Work completed on 24-09-2019. Capitalization done in FY-2019-20 of Rs.4.67 Cr. (4.50 Cr+Intrest 0.17) Reason for cost Overrun- Rate rise due to exchange rate variation, rate rise in duties, freight & insurance & basic rate rise. | Capitalised
10.4 | Procurement of complete ACVF drive module comprising of 2 Nos. of Supply and 3 Nos. of Inverter modules for GEHO pumps | Scheme | MERC/CAPEX/20172018/4782 | 2017-05-20 | 2017-11-28 | 0.95 | 0.95 |  |  | 2017-11-28 | 2018-10-22 | 2018-11-28 | 2019-07-17 | •The ACVFD drive are installed & in service. * Due to availablity of this module, down time of HCSD pump was reduced. • The availability of the ash evacuation system is improved. • Availability of GEHO pumps is improved. • Due to availaility of module, It was replaced in shortest time when VFD failure. | 0 | 0.92864 |  |  | 0.92864 | [8 empty] | 0% | 100% | [10 empty] | 0 | 0.92864 |  |  | 0.92864 | [9 empty] | *PO placed vide BTPS/4370001776/No-0125 dated 12-04-2019. * Work completed on 17-07-2019. Capitalization done in FY-2019-20 of Rs.0.93 Cr. | Capitalised
10.5 | Supply, erection and commissioning of 24VDC, 100A Float & Float cum Boost Battery Charger with 325Ah Battery Bank for CWPH at BTPS 2x500 MW. | Scheme | MERC/CAPEX/20172018/4782 | 2017-05-20 | 2017-11-28 | 0.15 | 0.15 |  |  | 2017-11-28 | 2018-02-12 | 2018-11-28 | 2018-12-13 | • Redundant 24V DC supply source is available at CWPH. • Improved availability of CWP Pumps. • System performance improved. • With second 24VDC supply source, availability of standby source at CWPH. • Due to availability of standby 24VDC source, generation loss due to tripping of all auxiliary is avoided which results due to failure of previous single 24V DC supply source. | 0.15788 |  |  |  | 0.15788 | [8 empty] | 100% | [11 empty] | 0.15788 |  |  |  | 0.15788 | [9 empty] | * PO placed vide BTPS/4370000787/No-01153 dated 12-02-2018. * Work completed on 13-12-2018. Capitalization done in FY-2018-19 of Rs.0.16 Cr. | Capitalised
| IDC | IDC | MERC/CAPEX/20172018/4782 | 2017-05-20 | 2017-11-28 | 2.34 | 0 |  |  | 2017-11-28 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
11 | Various schemes for renovation of colony at Bhusawal TPS | DPR | MERC/CAPEX/20172018/0221 | 2018-01-30 | 2018-02-12 | 19.3341 | 19.3341 |  |  | 2018-02-12 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
11.1 | Renovation of staff quarters & related work at BTPS Deepnagar | Scheme | MERC/CAPEX/20172018/0221 | 2018-01-30 | 2018-02-12 | 7.021 | 7.021 |  |  | 2018-02-12 | a) 05-09-2018 b)05-09-2018 c) 16-11-2018 d) 16-11-2018 e)19-11-2018 | a) 05-06-2019 b) 05-09-2019 c) 16-11-2019 d) 16-11-2019 e) 19-05-2019 | a) 04-06-2019 b) 04-09-2019 c) 31-12-2019 d) 31-12-2019 e) 20-03-2020 | • Provided good aesthetic in colony premises. • Ambience improvement. • Provided safe conveyance to residential families in colony premises. • Provided good aesthetic in colony premises. | 1.0585 | 4.3999 |  |  | 5.4584 | [9 empty] | 100% | [10 empty] | 0 | 5.4584 |  |  | 5.4584 | [10 empty] | Capitalised
11.2 | Colony Internal Roads at BTPS, Deepnagar | Scheme | MERC/CAPEX/20172018/0221 | 2018-01-30 | 2018-02-12 | 3.85 | 3.85 |  |  | 2018-02-12 | a) 15-05-2018 b) 13-08-2018 | a) 15-02-2019 b) 13-02-2019 | a) 20-12-2018 b) 12-02-2019 | • Convenient transportation facilities. • Proper approaches to everywhere. | 2.4234 | 0.82665 |  |  | 3.2501 | [8 empty] | 75% | 25% | [10 empty] | 2.4247 | 0.82665 |  |  | 3.2514 | [10 empty] | Capitalised
11.3 | Water supply , sanitary & drainage works at BTPS, Deepnagar | Scheme | MERC/CAPEX/20172018/0221 | 2018-01-30 | 2018-02-12 | 7.3 | 7.3 |  |  | 2018-02-12 | a) 07-08-2018 b) 23-11-2018 c) 16-11-2018 d) 16-11-2018 | a) 07-08-2019 b) 23-08-2019 c) 16-08-2019 d) 16-08-2019 | a) 06-08-2019 b) 25-07-2019 c) 31-12-2019 d) 31-12-2019 | • Rain water not getting accumulated on road side. • Health and hygiene of colony people is maintained. • Stoppage of leakages from Sanitary. • Provided safe conveyance to residential families in colony premises. • Provided good aesthetic in colony premises. • Ambience improvement. • Leakage problem from building sanitary system are minimize. • To increase the extended life of building and increase in hygiene of colony premises. • Smooth flow of surface runoff water and to avoid water logging near building premises and on roads. | 0.36608 | 5.47 |  |  | 5.8361 | [9 empty] | 100% | [10 empty] | 0 | 5.8109 |  |  | 5.8109 | [10 empty] | Capitalised
11.4 | Plinth protection to existing buildings at BTPS, Deepnagar | Scheme | MERC/CAPEX/20172018/0221 | 2018-01-30 | 2018-02-12 | 1.1631 | 1.1631 |  |  | 2018-02-12 | 2018-09-24 | 2019-06-24 | 2018-12-30 | * Due to which dampness during rain is avoided. | 0.91823 |  |  |  | 0.91823 | [8 empty] | 100% | [11 empty] | 0.91823 |  |  |  | 0.91823 | [10 empty] | Capitalised
12 | Pipeline from River Water Pump House (RWPH) to aquaduct over Bhogawati River and Other allied power house road works under DPR scheme at BTPS, Bhusawal | DPR | MERC/CAPEX/2018-2019/0104 | 2018-06-27 | 2019-04-04 | 13.1172 | 13.1172 |  |  | 2019-04-04 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
12.1 | Providing supplying laying, jointing, testing and commissioning of 1650 mm Ø ID 8 mm thick M.S. pipeline for raw water supply from RWPH to aquaduct over Bhogawati river at, BTPS, Bhusawal. | Scheme | MERC/CAPEX/2018-2019/0104 | 2018-06-27 | 2019-04-04 | 7.257 | 7.257 |  |  | 2019-04-04 |  | 2020-04-04 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | • As per CE(Civil-III) letter dated 22-02-2021, “ Status-Work orders are not issued/Tender not invited, Directives of Hon. CMD- Not to initiate for placement of Work orders/invitation of tender.” •As per discussion with 660MW project team, line erection is in scope of M/s. BHEL under 660MW Project | Not Initiated
12.2 | Construction of WBM and Bituminous road along inlet & outlet canals and concreate road along periphery of Major store at BTPS, Bhusawal. | Scheme | MERC/CAPEX/2018-2019/0104 | 2018-06-27 | 2019-04-04 | 4.22 | 4.22 |  |  | 2019-04-04 | a) 20-08-2021 b) 27-03-2021 c) 01-12-2022 | 2020-04-04 | a) 10-04-2023 b) 25-04-2023 c) 20-03-2023 | •Easy approach to canal site. •Safe conveyance for inspection of canal site. •Heavy grass and thorny bushes will not increase on canal road side. | 0 | 0 | 0 | 1.27 | 1.27 | 1.9032 | 0.6572 | [9 empty] | 90% | 100% | [7 empty] | 0 | 0 | 0 | 0 | 0 | 1.1932 | 2.6373 | [7 empty] | WBM Road : • PO placed vide-BTPS/4370002413/No-0180 dated 18-03-2020. • Work completed on 10-04-2023. Capitalization done in FY-2022-23 of Rs.0.84 Cr. Bituminous road : • PO placed vide-BTPS/4370002358/No-0176 dated 17-03-2020. • Work completed on 25-04-2023.Capitalization done in FY-2022-23 of Rs.1.83 Cr. Tremix • PO placed vide-BTPS/4370002610/No- 0959dated 15-07-2022. • Work completed on 20-03-2023.Capitalization done in FY-2022-23 of Rs.1.19 Cr. | Capitalised
12.3 | Work of construction of self-supporting steel roofing system for a major store godown shed of span 25M at BTPS, Deepnagar. | Scheme | MERC/CAPEX/2018-2019/0104 | 2018-06-27 | 2019-04-04 | 1.6402 | 1.6402 |  |  | 2019-04-04 | 2019-08-31 | 2020-04-04 | 2022-03-28 | Due to this the spare parts of machineries and other material are protected from rain. | 0 | 0 | 0.27 |  | 0.27 | [11 empty] | 100% | [8 empty] | 0 | 0 | 0 | 1.6376 | 1.6376 | [9 empty] | PO Placed vide- PO placed vide-BTPS/4370002455/No-0224 dated 26-03-2020. 100% work Completed.WCR submitted on 28-03-2022 & Scheme capitalized in FY 2021-22. Capitalization of 1.64 Cr. In FY-2022-23. | Capitalised
| IDC | IDC | MERC/CAPEX/2018-2019/0104 | 2018-06-27 | 2019-04-04 | 0 | 0 |  |  | 2019-04-04 | [8 empty] | 0 | 0.059623 | 0.089552 | [22 empty] | 0 |  | 0.14918 | [8 empty] | N.A.
13 | Supply, erection, commissioning & site testing of 220 V, 2035 AH, Station Battery Sets (4 Nos.) and 24 V, 2250 AH, SG/TG & BOP Battery Sets (8 Nos.) for U# 4 & 5 along with accessories at 2 x 500 MW BTPS, Bhusawal | DPR | MERC/CAPEX/2017-2018/1226 | 2018-07-17 | 2018-08-10 | 11.59 | 11.59 |  |  | 2018-08-10 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
13.1 | Supply, erection, commissioning & site testing of 220V, 2035 AH Station Battery Sets (02 Nos.) and 24V, 2250AH, SG/TG & BOP Battery Set (04 Nos.) along with accessories for Unit No.5 at BTPS 2x500MW. | Scheme | MERC/CAPEX/2017-2018/1226 | 2018-07-17 | 2018-08-10 | 5.795 | 5.795 |  |  | 2018-08-10 | 2018-10-22 | 2019-08-10 | 2019-09-27 | In case AC failure, if 220V battery is not available / failed, the severe damages may occur to all seven bearings of Turbine, Generator & exciter. Loss due to bearing failure is uncountable. Approximate estimate cost of Turbine bearing is Rs. 50 Lakhs & at least 2 months period is required for rehabilitation of system causing generation loss for next Two months period | 0 | 6.374 |  |  | 6.374 | [9 empty] | 100% | [10 empty] | 0 | 6.374 |  |  | 6.374 | [8 empty] | -3.9346 | PO placed vide BTPS/4370001843/No-0230 dated-14-05-2019. Work completed on dtd.27.09.2019. Capitalization done in FY-2019-20 of Rs.6.37 Cr. Reason for Cost overrun:- The BTPS has floated the Open Tender vide e-tender No-77527. In this open tender, the lowest L1 bidder was quoted the rate 4.81 Cr-Without GST( PO amount was 6.42 Cr-With GST).Bidder also submitted the other Utility work order Ref No-Slpp/matt/Exide Plante Battery/1504 dated 12-05-2015 of M/s. Gujarat Industries Power Company Ltd, Surat Lignite power plant, Surat-394110 for rate justification. | Capitalised
13.2 | Supply, erection, commissioning & site testing of 220V, 2035 AH Station Battery Sets (02 Nos.) and 24V, 2250AH, SG/TG & BOP Battery Set (04 Nos.) along with accessories for Unit No.4 at BTPS 2x500MW. | Scheme | MERC/CAPEX/2017-2018/1226 | 2018-07-17 | 2018-08-10 | 5.795 | 5.795 |  |  | 2018-08-10 | 2019-02-26 | 2019-08-10 | 2022-02-12 | In case AC failure, if 220V battery is not available / failed, the severe damages may occur to all seven bearings of Turbine, Generator & exciter. Loss due to bearing failure is uncountable. Approximate estimate cost of Turbine bearing is Rs. 50 Lakhs & at least 2 months period is required for rehabilitation of system causing generation loss for next Two months period | 0 | 0 | 0 | 6.3227 | 6.3227 | [11 empty] | 100% | [8 empty] | 0 | 0 | 0 | 6.3227 | 6.3227 | [8 empty] | -3.7918 | PO placed vide BTPS/4385000469/No-0923 dated-28-09-2021. Work completed on 12-02-2022 during AOH U-4. Capitalization done in FY-2021-22 of Rs.6.32 Cr . Reason for Cost overrun:- The BTPS has floated the Open Tender vide RFx No-3000019299, In this open tender, the lowest L1 bidder was quoted the rate 4.96 Cr-Without GST ( PO amount was 6.32 Cr-With GST). Bidder also submitted the other Utility PO No-4000121930-M92-2018 dated 05-03-2018 of M/s. NTPC limited, Mouda Super Thermal Power Project, Mouda, Maharashtra-441104 for rate justification. | Capitalised
15 | Flue Gas Desulphurization (FGD) System for 500 MW Units (Total 8 Nos) of MSPGCL | DPR | MERC/CAPEX/2020-2021/WFH/SBR/45 | 2019-12-09 | 2021-02-05 | 869.5 | 869.5 |  |  | 2021-02-05 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
15.1 | Flue Gas Desulphurization (FGD) System for Bhusawal Unit 4-5 | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/45 | 2019-12-09 | 2021-02-05 | 830.4 | 830.4 |  |  | 2021-02-05 |  |  |  | Statutory requirement. |  |  | 0 | 0 | 0 | 0 | 0 | 127.37 | 467.04 | 254.75 | [12 empty] | 100% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 127.37 | 467.04 | 254.75 |  |  |  |  | •LOA (EPC Contract) : CE (P&P)/3x500MW /Sch-B/FGD/No. 1239; Date:16-11-2023. •Unit-4 completion period - April 2026 (29 months) •Unit-5 completion period - July 2026 (32 months) | WIP
| IDC | IDC | MERC/CAPEX/2020-2021/WFH/SBR/45 | 2019-12-09 | 2021-02-05 | 39.1 | 39.1 |  |  | 2021-02-05 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
16 | Procurement of two BFP Cartridges & one rotor of Turbine driven BFP & at 500MW BTPS, Bhusawal | DPR | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2020-09-21 | 2021-03-08 | 10.52 | 10.52 |  |  | 2021-03-08 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
16.1 | Procurement of two BFP Cartridges at 500MW BTPS, Bhusawal | Scheme | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2020-09-21 | 2021-03-08 | 3.84 | 3.84 |  |  | 2021-03-08 | 2021-10-26 | 2023-09-08 |  | Material is received recently but not installed/ not put in service till now. Hence, actual benefits are not calculated. Expected benifites- * Reduction in forced outages of pump. * Reduction in downtime of machine during repair work. * Increase in availability/healthiness of the pumps. *Reduction in Auxiliary power consumption due to increase in efficiency of pumps. |  |  | 0 | 0 | 0 | 2.24 | [11 empty] | 100% | [9 empty] | 0 | 0 | 0 | 2.24 | 0 | 0 | [6 empty] | • PO dispatched vide BTPS/4385000468 /No-1014 dated 26-10-2021. • WCR Date-07-06-2022 and 16-07-2022 | Capitalised
16.2 | Procurement of one rotor of Turbine driven BFP at 500MW BTPS, Bhusawal | Scheme | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2020-09-21 | 2021-03-08 | 6.46 | 6.46 |  |  | 2021-03-08 | 2021-07-16 | 2023-09-08 | 2022-03-21 | Material is received but not installed/ not put in service till now. Hence, actual benefits are not calculated. Expected benifites- * Reduction in forced outages of pump. * Reduction in downtime of machine during repair work. * Increase in availability/healthiness of the pumps. *Reduction in Auxiliary power consumption due to increase in efficiency of pumps. |  |  | 0 | 7.6136 | 7.6136 | [11 empty] | 100% | [10 empty] | 0 | 7.6136 | 7.6136 | [9 empty] | * PO dispatched-4385000447/No-0668 dated 16-07-2021. * Material received at BTPS on 02-03-2022. * WCR submitted on 11-04-2022. * Capitalized in FY 2021-2022 of Rs.7.61 Cr. Reason for Cost overrun- Approval of DPR scheme is proposed as per the budgetary offer received from M/s. BHEL Ref No. SB317M48008HYU017 dtd. 23.102.17. However, MERC in principle clearance for Procurement of one rotor of Turbine driven BFP is received vide letter No MERC/CAPEX/2020-2021/WFO/SBR/49 dtd. 08.03.2021. Accordingly, proposal is processed and enquiry for OEM procurement is sent to M/s. BHEL. But M/s. BHEL has quoted the price approx. 24.73% higher than the previously quoted price. Therefore, deviation clarification is demanded from M/s. BHEL for the quoted price and also asked for rate reasonability on the basis of NTPC Deepshikha, Angul P.O. No. 4000219019-M51-1026 dtdt. 08.04.219 available with this office. In reply M/s. BHEL provided justification for rate rise and also provided latest similar P.O. from NTPC Ltd SSC WR-I (Kawas) P.O. Aditya Nagar, Surat, Gujrat P.O. No. 4000256337-M51-1020 Dtd: 30.03.2021. Also, as a very special case, M/s. BHEL agreed to offer same price to MSPGCL as that of NTPC Ltd SSC WR-I (Kawas) subject to P.O. placement on or before 20.07.2021. Hence as per BHEL new offered price, the rate is higher by 19% than estimated rate. | Capitalised
| IDC | IDC | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2020-09-21 | 2021-03-08 | 0.22 | 0.22 |  |  | 2021-03-08 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
17 | CHP Improvement Schemes at 2X500MW, BTPS, Bhusawal | DPR | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2020-11-27 | 2021-06-10 | 21.22 | 21.22 |  |  | 2021-06-10 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
17.1 | Revamping of Apron Feeder in CHP at 2X500MW, BTPS | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2020-11-27 | 2021-06-10 | 4.67 | 4.67 |  |  | 2021-06-10 | a) 01-09-2022 (Apron Feeder -2) b) 05-11-2022 (Apron Feeder-3) | 2022-06-10 |  | Expected benefits- • Reduction in plant outages. • Reduction in maintenance cost. • Reduction in wagon tippler outages. • Improvement in performance of unloading. • Demurrages will be reduced. |  |  |  | 0 | 0 | 4.6492 | [11 empty] | 100% | [10 empty] | 0 | 0 | 4.6492 | 0 | 0 | [6 empty] | • PO dispatched vide BTPS/ 4385000536/No-0128 dtd.27-01-2022. • Work completed on 14-09-2022 and 20-11-2022. | Capitalised
17.2 | Design, engineering, manufacturing, supply, Erection and commissioning of short conveyor from stack yard to belt feeder 112 in CHP 2x500MW BTPS. | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2020-11-27 | 2021-06-10 | 3.53 | 3.53 |  |  | 2021-06-10 | 2023-03-27 | 2022-06-10 | 2024-02-20 | Expected benefits- • Improvement in reclaiming facility. •Avoid generation loss in case of unavailability of stacker or conveyor 110. •Enhance conveyor stream flexibility to operate stacking and reclaiming simultaneously. |  |  |  | 0 | 0 | 0 | 3.9648 | [11 empty] | 100% | [9 empty] | 0 | 0 | 0 | 3.9648 | 0 | [6 empty] | • PO Placed vide BTPS /4385000597/0267) on 01-03-2023 • Work completed on 20-02-2024. Capitalization done in FY 2023-24 of Rs.3.96 Cr. • IDC Component Rs. 0.0675241 Crore | Capitalised
17.3 | Design, engineering, manufacturing, supply, Erection and commissioning of stone grappler at Wagon Tippler No.3 in CHP 2x500MW BTPS. | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2020-11-27 | 2021-06-10 | 0.84 | 0.84 |  |  | 2021-06-10 |  | 2022-06-10 |  | Expected benefits- •Reduction in grilling work expenses. •Reduction in time for grilling. •Reduction in conveyor stream outages. •Reduction in demurrages. •Improved safety in grilling work. |  |  |  | 0 | 0 | 0 | 0 | 0.84 | [10 empty] | 50% | 50% | [8 empty] | 0 | 0 | 0 | 0 | 0.84 | [6 empty] | • PO Dispatched vide BTPS /4385000667/1584) on 17-10-2023 • Material Expected in Nov -24 | WIP
17.4 | Procurement of suspended magnets in CHP 2x500MW BTPS. | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2020-11-27 | 2021-06-10 | 2.95 | 2.95 |  |  | 2021-06-10 | 2021-03-22 | 2022-06-10 | 2022-05-04 | There is lots of foreign material received through coal rakes. This foreign material is prone to damage auxiliary such as wobbler feeder, crusher and conveyor belts etc. Hence, oil cooled suspended magnets are installed on conveyor belts. Due to these magnets foreign material arrested to go through wobbler and crusher. There is net following benefits are achieved by installation of magnets. 1) Conveyor belts tearing reduced by 40% tentatively. 2) Wobbler feeder outages reduced to 80% 3) Crusher hammer and internals damages reduced to 80% 4) Auxiliary availability increased effectively. 5) There is net saving in demurrage charges to be paid to railway on account of system failure. The expenditure towards demurrage charges saving is approx. 25 to 40K daily. 6) There is net saving in maintenance expenditure towards outages of conveyor belts, wobbler feeder, crusher and chute damages. 7) There is material saving achieved for attending various faults. 8) There are several unmeasured benefits achieved due to which overall system outages are reduced and unloading constraints are overcome. 9) There is net 25L to 30L approx. cost saving expected till end of the year from date of installation of suspended magnets. |  |  |  | 0 | 0 | 2.947 | [11 empty] | 100% | [10 empty] | 0 | 0 | 2.947 | 0 | [7 empty] | * (T-272/2020)-PO distatched vide PO No. 4385000557/501/dtd.04-04-2022. * Material received on dated 06-04-2022. 100% Work Completed on 04-05-2022. WCR submitted on 10-05-2022. Capitalization done FY-2022-23 of Rs. 2.95 Cr. * Work Completion date 04-05-2022 | Capitalised
17.5 | Supply, Erection And Commissioning of Electro-Mechanical Drive to Apron Feeder at CHP 500MW | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2020-11-27 | 2021-06-10 | 7.57 | 7.57 |  |  | 2021-06-10 |  | 2022-06-10 |  | • Reduction in plant outages. • Reduction in maintenance cost. • Reduction in wagon tippler outages. • Improvement in performance of unloading. • Demurrages will be reduced. |  |  |  | 0 | 0 | 0 | 0 | 7.57 | [11 empty] | 1 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [6 empty] | Tenderization is in process. Under Final Scrutiny. | WIP
| IDC | IDC | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2020-11-27 | 2021-06-10 | 1.66 | 1.66 |  |  | 2021-06-10 | [8 empty] | 0 |  | 0.067524 | [22 empty] | 0 |  | 0.067524 | [7 empty] | IDC on Short Conveyor | N.A.
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | DPR | MERC/CAPEX/20162017/00423 | 2016-02-03 | 2016-08-03 | 3.9773 | 3.9773 |  |  | 2016-08-03 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
1 | Bhusawal: Unit 4-5 (3 Nos.) | Scheme | MERC/CAPEX/20162017/00423 | 2016-02-03 | 2016-08-03 | 3.9773 | 3.9773 |  |  | 2016-08-03 | 2017-06-17 | 2018-08-03 | 2019-06-05 | • Statutory norms of MPCB/CPCB/NGT achieved. • Continuous monitoring of ambient air quality. • Reduction in air pollution. | 0 | 1.8768 | 0 | 0 | 1.8768 | 0.07 | 0 | 0 | [6 empty] | 100% | [10 empty] | 0 | 1.8768 | 0 | 0 | 1.8768 | 0.069 | [8 empty] | PO placed vide -HO/4370001152/No-0386 dated 08-01-2019. Work completed on dtd.05-06-2019. Capitalization done in FY-2019-20 of Rs.1.88 Cr in U#4 & 5 and Rs.0.94 Cr. In U#3. Addcap of maintenance period completed on 31-03-2023 | Capitalised
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | DPR | MERC/CAPEX/20162017/00774 | 2016-08-26 | 2016-09-30 | 4.0552 | 4.0552 |  |  | 2016-09-30 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
1 | Bhusawal: Unit 4-5 | Scheme | MERC/CAPEX/20162017/00774 | 2016-08-26 | 2016-09-30 | 4.0552 | 4.0552 |  |  | 2016-09-30 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [9 empty] | As per CPA, HO Email dated 15-09-2022, Procurement proposal for this scheme is to be cancelled on the basis of MoEF&CC Notification No. S.O. 1561(E), dated 21.05.2020. | To be cancelled
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | DPR | MERC/CAPEX/20172018/4653 | 2017-04-19 | 2017-11-13 | 3.95 | 3.95 |  |  | 2017-11-13 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
1 | Advance Multipurpose Fire Tender for BTPS 4-5 | Scheme | MERC/CAPEX/20172018/4653 | 2017-04-19 | 2017-11-13 | 1.45 | 1.45 |  |  | 2017-11-13 | 2019-01-16 | 2019-11-13 | 2021-09-03 | * Replacement of Fire Tenders may be treated as direct benefits towards life and property safety measures, not only to the organization but also to the Nation. | 0 | 0 | 0 | 1.7765 | 1.7765 | [11 empty] | 100% | [8 empty] | 0 | 0 | 0 | 1.7765 | 1.7765 | [9 empty] | * PO dispatched vide. HO/4370001800/5197 dtd.24-05-2019. Adv 1.78 cr. *Advanced MFT 1 No. is received at BTPS on 26-08-2021. *Capitalization done in FY-2021-22 of Rs.1.78 Cr. | Capitalised
2 | Normal Multipurpose Fire Tender for BTPS 4-5 | Scheme | MERC/CAPEX/20172018/4653 | 2017-04-19 | 2017-11-13 | 2.5 | 2.5 |  |  | 2017-11-13 | 2022-02-18 | 2019-11-13 | 2023-02-27 | * Replacement of Fire Tenders may be treated as direct benefits towards life and property safety measures, not only to the organization but also to the Nation. | 0 | 0 | 0 | 0 | 0 | 2.1847 | [11 empty] | 100% | [7 empty] | 0 | 0 | 0 | 0 | 0 | 2.1847 | [8 empty] | • Normal MFT-PO placed vide-HO/ 4370002840/02009 dated 02-03-2022 on M/s. Hi-Tech Services, Pune. • NMFT received at BTPS on 22-02-2023. • Work completed on 27-02-2023. Capitalization done in FY 2022-23 of Rs.2.18 Cr. | Capitalised
| IDC | IDC | MERC/CAPEX/20172018/4653 | 2017-04-19 | 2017-11-13 |  |  |  |  | 2017-11-13 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | DPR | MERC/CAPEX/20172018/0177 | 2018-01-12 | 2018-02-06 | 10.0654 | 10.0654 |  |  | 2018-02-06 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
1 | Bhusawal: Unit 4-5 | Scheme | MERC/CAPEX/20172018/0177 | 2018-01-12 | 2018-02-06 | 10.0654 | 10.0654 |  |  | 2018-02-06 | 2018-09-06 | 2019-08-06 | 2021-07-15 | *Concrete compound wall construction with concertina coil around periphery of plant at various locations for Safety and security of plant and colony residence area . | 3.15 | 5.1516 |  |  | 8.3016 | 0.49389 | 0.38999 | [9 empty] | 100% | [8 empty] | 0 | 0 | 0 | 8.2998 | 8.2998 | 0.49389 | 0.38999 | [7 empty] | * Purchase Order placed vide No.4370001644 dtd.19/09/2018. * 100% Work Completed on 15-07-2021.WCR is submitted on 05-10-2021. *Scheme capitalized in FY 2021-22 of Rs.8.30 Cr. * Add Cap of Compound wall 0.49 Cr and Price Variation 0.39 Cr | Capitalised
18 | Procurement of assembly of baskets for Air Pre-heater of type 31.5 VIM 2000 (72° PA), Replacement of thermal insulation of Boiler, Ducts & Steam Pipelines and Coal Mill Gear Box in 2x500MW at BTPS, Bhusawal | DPR | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-02-23 | 2021-09-22 | 14.96 | 14.96 |  |  | 2021-09-22 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
18.1 | Procurement of assembly of baskets for Air Preheater of type 31.5 VIM 2000 (72° PA) for Unit-4&5 | Scheme | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-02-23 | 2021-09-22 | 5.53 | 5.53 |  |  | 2021-09-22 | 2021-09-22 | 2022-09-22 | 2022-02-11 | * Total Heat Rate improved by 26.12 Kcal/Kwh. * Coal saved =78.36 MT/Per day. * Amount Saved= 12.01 Cr./ Year. |  |  |  | 8.411 | 8.411 | [11 empty] | 100% | [11 empty] | 8.411 | 8.411 | [9 empty] | * PO dispatched -vide -HO/4370002768/No- 9480 dated 22-09-2021. * Work completed in U#4 AOH. WCR submitted on dtd.17-02-2022. *Scheme capitalized in FY 2021-22 of Rs.8.41 Cr. Reason for Cost Overrun- The major components of APH Baskets is Steel (85%). From the various statistics taken from web sites of some reputed organization involved in maintaining, analyzing and forecasting the demand, supply and price data of various metal components and their alloys, It can be seen that there has been tremendous rise in steel prices by almost 60-100 % and the rising trend is still continue. Further, there has been a rise of almost 22% in transportation cost. | Capitalised
18.2 | Replacement of thermal insulation of Boiler, Ducts & Steam Pipelines along with supply | Scheme | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-02-23 | 2021-09-22 | 3.52 | 3.52 |  |  | 2021-09-22 | 2021-09-23 | 2022-09-22 |  | • The Generation loss will be avoided due to heat loss to environment. • Heat rate of boiler will be improved. • This scheme will improve Boiler life by avoiding further degradation due to aging. • Improvement in working environment as reduction in heat loss to environment. |  |  |  | 0 | 0 | 0 | 0 | 3.52 | [20 empty] | 0 | 0 | 0 | 0 | 2 | [6 empty] | • Tender -T-74/2021, RFx No-3000025763 (2nd Time) was published from 17-02-2022 & further extended up to 13-04-2022. • No bidder is participated, Hence, Amendmend in QR is proposed & submitted to HO for approval vide ltr No-1008 dated 07-05-2022. QR approval received dtd.17-06-2022. •Implementation of scheme in phase manner for Unit-4&5. •Seprate proposal for U-4 & U-5 are prepared are under process at CPA. • PR approval received (110015621) on Dated: 30/7/24. (UNIT-4) • PR approval received (110015623) on Dated: 29/8/24.(UNIT-5) • Tender Published. | WIP
18.3 | Supply of XRP-1043 coal mill gearbox spares in unit-4&5. | Scheme | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-02-23 | 2021-09-22 | 5.39 | 5.39 |  |  | 2021-09-22 | 2024-03-14 | 2022-09-22 | 2024-04-02 | • Huge Generation loss on account of non availability of coal mill will be reduced. • Mill availability will be maintained. |  |  |  | 0 | 0 |  |  | 3.7044 | [10 empty] | 100% | [9 empty] | 0 | 0 | 0 | 3.7044 | 0 | [6 empty] | • PO approval received dtd.17-09-2022. • Work completed on 02-04-2024. Capitalization done in FY 2024-25 of Rs.3.70 Cr. | Capitalised
| IDC | IDC | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-02-23 | 2021-09-22 | 0.52 | 0.52 |  |  | 2021-09-22 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
19 | Up-gradation of Operating System of Max DNA DCS, GE Fanuc PLC system & Schneider PLC system & Procurement of Critical Insurance spares for PA and FD fans System at 2 x 500 MW Units BTPS Bhusawal | DPR | MERC/CAPEX/2023-2024/0178 | 2023-10-31 | 2024-03-11 | 31.05 | 31.05 |  |  | 2024-03-11 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
19.1 | Up-gradation of Existing MaxDNA System (HMI) at 500MW BTPS, Bhusawal | Scheme | MERC/CAPEX/2023-2024/0178 | 2023-10-31 | 2024-03-11 | 8.69 | 8.69 |  |  | 2024-03-11 |  |  |  | • Emergency can be avoided by smooth operation of operating station by HMI Upgradation. • The possibilities of catastrophic failures are minimum. |  |  |  |  | 0 |  |  | 0 | 8.69 | [20 empty] | 0 |  |  | 0 | 8.69 | [5 empty] | • MERC In-Principal Clearance Ref. No.0178; Date:11-03-2024. • Tender Published. • Approval for Deviations to Terms & Conditions & opening price bid on single bid.( Disp No.10667; Date: 11-10-24) | WIP
19.2 | Up-gradation of GE IP (GE-Fanuc) make PLC system (HMI) installed at AHP, CPU plant, FOPH, FWPH and Mill Reject system at 2x500MW BTPS, Bhusawal. | Scheme | MERC/CAPEX/2023-2024/0178 | 2023-10-31 | 2024-03-11 | 1.35 | 1.35 |  |  | 2024-03-11 |  |  |  | •To avoid generation loss due to emergency caused due to malfunctioned in HMI. •Reduce repair & maintenance cost. •Increased reliability & stability of process. |  |  |  |  | 0 |  |  | 1.2948 | [21 empty] | 0 |  |  | 1.3538 | [6 empty] | • MERC In-Principal Clearance Ref. No.0178; Date:11-03-2024. • PO submitted to HO for approval on 31-03-2024 • PO approval no 04587 on dated 8-05-2024 • Material delivery period 12 weeks from the date of techno- commercially PO. • WCR received on 05.09.2024 | Capitalised
19.3 | Up-gradation of Schneider PLC System at 2x500MW, BTPS, Bhusawal | Scheme | MERC/CAPEX/2023-2024/0178 | 2023-10-31 | 2024-03-11 | 2.33 | 2.33 |  |  | 2024-03-11 |  |  |  | •To avoid generation loss due to emergency caused due to malfunctioned in HMI. •Reduce repair & maintenance cost. •Increased reliability & stability of process. |  |  |  |  | 0 |  |  | 2.3093 | [21 empty] | 0 |  |  | 2.3093 | [6 empty] | • Approval of PO ( Disp No.03784; Date:08-04-2024. • Material delivery period 18 Months expected delivery in Oct-2025. • Material received on 24 June-24 | WIP
19.4 | Procurement of Rotor assembly with blade set for PA and FD fan at 2 X 500 MW BTPS Bhusawal | Scheme | MERC/CAPEX/2023-2024/0178 | 2023-10-31 | 2024-03-11 | 18.18 | 18.18 |  |  | 2024-03-11 |  |  |  | •Increase in Fan loading capacity. •Furnace draft will be maintained. •Reduction in coal consumption. •Improvement in unit heat rate •Improvement in PLF. |  |  |  |  | 0 |  |  | 16.16 | [21 empty] | 0 |  |  | 16.16 | [6 empty] | PA FAN: •PO Placed (Disp. No 2358) on 22-04-2024. •Material delivery period 12 Months expected delivery in April-2025. • WCR received on 07-10-24 FD Fan: • PO Placed (Disp. No 0017) on 03-04-2024. • Material delivery period 12 Months expected delivery in April-2025. • WCR received on 07-10-24 | Capitalised
| IDC | IDC | MERC/CAPEX/2023-2024/0178 | 2023-10-31 | 2024-03-11 | 0.5 | 0.5 |  |  | 2024-03-11 | [8 empty] | 0 |  |  |  | 0.5 | [20 empty] | 0 |  |  |  | 0.5 | [5 empty] | PA FAN: •PO Placed (Disp. No 2358) on 22-04-2024. •Material delivery period 12 Months expected delivery in April-2025. • WCR received on 07-10-24 FD Fan: • PO Placed (Disp. No 0017) on 03-04-2024. • Material delivery period 12 Months expected delivery in April-2025. • WCR received on 07-10-24 | N.A.
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | DPR | MERC/CAPEX/2021-2022/MSPGCL/063 | 2018-08-31 | 2022-02-12 | 113.91 | 57 |  |  | 2022-02-12 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | Scheme | MERC/CAPEX/2021-2022/MSPGCL/063 | 2018-08-31 | 2022-02-12 | 108.48 | 54.24 |  |  | 2022-02-12 | [8 empty] | 0 | [20 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | Status to be updated by HO | WIP
| IDC | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2018-08-31 | 2022-02-12 | 5.43 | 2.76 |  |  | 2022-02-12 | [8 empty] | 0 | [20 empty] | 0 | 0 | 0 | 0 | 0 | [10 empty] | WIP
HO DPR 16 | Centralized Monitoring Solution | DPR | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-03-28 | 2023-11-02 | 69.309 | 69.309 |  |  | 2023-11-02 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
1 | Centralized Monitoring Solution | Scheme | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-03-28 | 2023-11-02 | 66.009 | 66.009 |  |  | 2023-11-02 | [8 empty] | 0 | [24 empty] | 0 | [9 empty] | Status to be updated by HO | WIP
| IDC | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-03-28 | 2023-11-02 | 3.3 | 3.3 |  |  | 2023-11-02 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | WIP
20 | Improvement of Loadability and Availability of Coal Handling Plant at BTPS, Bhusawal | DPR | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-04-12 | 2024-05-17 | 42.14 | [12 empty] | 0 | [24 empty] | 0
20.1 | Scheme-1:-Design Engineering, Supply, Erection, commissioning, Extension of travel Length & Capacity Enhancement of coal yard with additional drive system of stacker reclaimer conveyor No. 110 at in coal handling Plant BTPS. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-04-12 | 2024-05-17 | 14.27 | 14.27 |  |  | 2024-05-17 |  |  |  | • Increased Stack Yard capacity. • Loadability and availability will get increased. • Will minimize dozer operation. • Dedicated stacking can be done. • Effective bunkering can be done. |  |  |  |  | 0 |  |  | 0 |  | 14.27 | [19 empty] | 0 |  |  | 0 |  | 14.27 |  |  |  |  | • MERC In-Principal Clearance Ref. No.0309 Date:17-06-2024. • PR approval received 11.10.24 • Tender will be further processed at HO. | WIP
20.2 | Scheme-2:-Design, Engineering, Rectification, Erection & Commissioning of Z point at Conveyor 108A & B at CHP-500MW. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-04-12 | 2024-05-17 | 8.18 | 8.18 |  |  | 2024-05-17 |  |  |  | • No. of Z points of conveyor 108A and B will be reduced. • Reduction in fatigue failures of conveyor belts. • Reduction in belt joint failures. • Increase belt life. • Reduction in probability of hampering complete bunkering of unit 4 and 5. |  |  |  |  | 0 |  |  | 0 |  | 8.18 | [19 empty] | 0 |  |  | 0 |  | 8.18 |  |  |  |  | • MERC In-Principal Clearance Ref. No.0309 Date:17-06-2024. • PR Approval received on 11-10-24 • Tender is published. | WIP
20.3 | Scheme-3:-Design, Engineering and provision of material lifting arrangement for crusher floor, wobbler feeder & C-105 floor In CHP BTPS. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-04-12 | 2024-05-17 | 1.88 | 1.88 |  |  | 2024-05-17 |  |  |  | • Safely lifting and shifting of material can be done. • Shifting of material can be done in minimum possible time. • Outage hours will get reduced. • Shifting of material without damages can be ensured. |  |  |  |  | 0 |  |  | 0 |  | 1.88 | [19 empty] | 0 |  |  | 0 |  | 1.88 |  |  |  |  | • MERC In-Principal Clearance Ref. No.0309 Date:17-06-2024. • PO Placed (Disp. No 1026) on 27-09-2024. • Delivery Period: 06 Months (Feb-2025) | WIP
20.4 | Scheme-4:-Structural up-gradation and rehabilitation of reversible yard conveyor in coal handling plant. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-04-12 | 2024-05-17 | 4.21 | 4.21 |  |  | 2024-05-17 |  |  |  | • Availability of conveyor will get increased. • Capacity will get restored. • Structural damages will get nullified. • Major outages can be avoided. |  |  |  |  | 0 |  |  | 0 |  | 4.21 | [19 empty] | 0 |  |  | 0 |  | 4.21 |  |  |  |  | • MERC In-Principal Clearance Ref. No.0309 Date:17-06-2024. • PR Approval received (Disp no.10679 on 11-10-24) • Tender is published. | WIP
20.5 | Scheme-5:-Design, Engineering, Erection and commissioning of Receiving and discharge chutes of wobbler feeders in CHP BTPS. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-04-12 | 2024-05-17 | 6.25 | 6.25 |  |  | 2024-05-17 |  |  |  | • Coal leakages will get minimized. • Fugitive emission of dust can be restricted. • Availability will get increased. • Chute choke ups will get minimized. • Better coal flow can be ensured. |  |  |  |  | 0 |  |  | 0 |  | 6.25 | [19 empty] | 0 |  |  | 0 |  | 6.25 |  |  |  |  | •MERC In-Principal Clearance Ref. No.0309 Date:17-06-2024. • PR Approval received on 11-10-24 • Tender is published. | WIP
20.6 | Scheme-6: Procurement of 3 Nos. of Bulldozers at BTPS, Bhusawal. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-04-12 | 2024-05-17 | 7.35 | 7.35 |  |  | 2024-05-17 |  |  |  | • To avoid generation loss due to poor bunkering. • Reduce the recurring expenditure on repair & maintenance. • Increased reliability & availability of dozers. • Helps in improving the system performance & efficiency by purchasing new dozers. |  |  |  |  | 0 |  |  | 0 |  | 7.35 | [19 empty] | 0 |  |  | 0 |  | 7.35 |  |  |  |  | • Capex PO under process at HO | WIP
| IDC | [17 empty] | 0 |  |  |  |  | 0.42 | [19 empty] | 0 |  |  |  |  | 0.42
21 | Performance Improvement of Coal Handling Plant at BTPS-U4 & 5, Bhusawal | DPR | MERC/CAPEX/MSPGCL/2024-25/0310 |  |  | 57.29 | [12 empty] | 0 | [24 empty] | 0
21.1 | Scheme-1: Revamping, Modification of Gravity take-up and Drive Augmentation of Bunkering conveyor in CHP BTPS | Scheme | MERC/CAPEX/MSPGCL/2024-25/0310 |  | 2024-05-17 | 11.35 | 11.35 |  |  | 2024-05-17 |  |  |  | •Unloading and bunkering rate will be improved. • System availability will get increased. •Outage during Belt replacement will reduce. •Cost saving on account of wastage of belt can be saved, Cost of belt joint and maintenance can be saved. |  |  |  |  | 0 |  |  | 0 |  | 11.35 | [19 empty] | 0 |  |  | 0 |  | 11.35 |  |  |  |  | • MERC In-Principal Clearance Ref. No.0310 Date:17-06-2024. • PR approval received 04.10.24 • Tender is published. | WIP
21.2 | Scheme-2: Revamping of coal diverting chutes in CHP 2x500 MW BTPS | Scheme | MERC/CAPEX/MSPGCL/2024-25/0310 |  | 2024-05-17 | 5.73 | 5.73 |  |  | 2024-05-17 |  |  |  | •Conveyor system availability will increase. •Smooth coal flow can be establishing avoiding chute choke up incidences. •Cleaning will get improved. •Demurrage charges will get reduced. •Maintenance of chutes will get reduced. |  |  |  |  | 0 |  |  | 0 |  | 5.73 | [19 empty] | 0 |  |  | 0 |  | 5.73 |  |  |  |  | • MERC In-Principal Clearance Ref. No.0310 Date:17-06-2024. • PR approval received 23.09.24 • Deviation open. | WIP
21.3 | Scheme-3: Revamping and structural augmentation of Reversible feeder conveyors in CHP-BTPS. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0310 |  | 2024-05-17 | 1.77 | 1.77 |  |  | 2024-05-17 |  |  |  | •Belt will be running with sufficient tension. •Belt running out problems will be reduced. •Coal spillages problems will be reduced. •Coal chokes up & overloading problems will be reduced |  |  |  |  | 0 |  |  | 1.75 |  | 1.77 | [19 empty] | 0 |  |  | 1.75 |  | 1.77 |  |  |  |  | • MERC In-Principal Clearance Ref. No.0310 Date:17-06-2024. • PO Placed (Disp. No 0890) on 23-08-2024. • Delivery Period: 06 Months (Feb-2025) | WIP
21.4 | Scheme-4: Revamping and up-gradation of air & ventilation system in Coal Handling Plant-BTPS. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0310 |  | 2024-05-17 | 9.01 | 9.01 |  |  | 2024-05-17 |  |  |  | •Enhance capacity of air handling unit or ventilation system will get improved. •Energy efficiency can be improved. •100% fresh air. •Better working atmosphere can be ensured and efficiency of working area can be improved. |  |  |  |  | 0 |  |  | 0 |  | 3.85 | [19 empty] | 0 |  |  | 0 |  | 3.85 |  |  |  |  | • MERC In-Principal Clearance Ref. No.0310 Date:17-06-2024. • PR Approval received on 11-10-24 • Tender is published. | WIP
21.5 | Scheme-5: Revamping, Structural & drive up-gradation of conveyor-111 in CHP-BTPS. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0310 |  | 2024-05-17 | 3.85 | 3.85 |  |  | 2024-05-17 |  |  |  | • Conveyor system availability will increase. • Conveyor Loadability will get increased. • Demurrage charges will get reduced. • Chute leakages will get reduced. |  |  |  |  | 0 |  |  | 0 |  | 8.62 | [19 empty] | 0 |  |  | 0 |  | 8.62 |  |  |  |  | • MERC In-Principal Clearance Ref. No.0310 Date:17-06-2024. • PR approval received 04.10.24 • Tender is published. | WIP
21.6 | Scheme-6: Revamping and structural up-gradation of conveyor system in tunnel area in Coal Handling Plant-BTPS. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0310 |  | 2024-05-17 | 8.62 | 8.62 |  |  | 2024-05-17 |  |  |  | •Coal chokes up & overloading problems will be reduced. •Cleaning becomes easier. •Avoidance of generation loss due to on availability coal feeding of streams. •Structural stability will be improved. •Leakages to chute will be minimized. •Unloading of coal will get improved. |  |  |  |  | 0 |  |  | 0 |  | 8.06 | [19 empty] | 0 |  |  | 0 |  | 8.06 |  |  |  |  | MERC In-Principal Clearance Ref. No.0310 Date:17-06-2024.
21.7 | Scheme-7: Erection & Commissioning of Travelling type coal chutes in CHP BTPS. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0310 |  | 2024-05-17 | 8.06 | 8.06 |  |  | 2024-05-17 |  |  |  | •Reliability will be improved. •System outages will be reduced. •Unloading & stacking outages will be reduced. •Structural stability will be improved. |  |  |  |  | 0 |  |  | 0 |  | 4.98 | [19 empty] | 0 |  |  | 0 |  | 4.98 |  |  |  |  | • MERC In-Principal Clearance Ref. No.0310 Date:17-06-2024. • PR approval received 24.10.24 | WIP
21.8 | Scheme-8: Revamping of scoop cooling system installed in coal handling plant BTPS. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0310 |  | 2024-05-17 | 4.98 | 4.98 |  |  | 2024-05-17 |  |  |  | •Effective cooling can be ensured. •Efficiency of Fluid coupling will get increased. |  |  |  |  | 0 |  |  | 0 |  | 3.92 | [19 empty] | 0 |  |  | 0 |  | 3.92 |  |  |  |  | • MERC In-Principal Clearance Ref. No.0310 Date:17-06-2024. • PR Approval received on 11-10-24 • Tender is published. | WIP
21.9 | Scheme-9: Retrofitting and Up-gradation of Dewatering system in CHP-BTPS. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0310 |  | 2024-05-17 | 3.92 | 3.92 |  |  | 2024-05-17 |  |  |  | • All the drain water will be pumped to ETP and system availability on account of accumulation of water at the tunnel will not get hampered. |  |  |  |  | 0 |  |  | 0 |  | 9.01 | [19 empty] | 0 |  |  | 0 |  | 9.01 |  |  |  |  | • MERC In-Principal Clearance Ref. No.0310 Date:17-06-2024. • PR Approval received on 11-10-24 • Tender is published. | WIP
| IDC | [17 empty] | 0 |  |  |  |  | 0.53 | [19 empty] | 0 |  |  |  |  | 0.53
| Asset Transfer from Projects | [17 empty] | 0 | [24 empty] | 0
| SP Busduct Unit 4&5 | [14 empty] | 0.30072 |  |  | 0.30072 | [21 empty] | 0.30072 |  |  | 0.30072
| ESP,ID,FD,PA Fans &Other Boiler Auxiliaries | [8 empty] | - | [7 empty] | 1.0283 | 1.0283 | [23 empty] | 1.0283 | 1.0283
| (ii) DPR Yet to be Submitted to MERC | [17 empty] | 0 | [24 empty] | 0
| FY 2025-26 | [17 empty] | 0 | [24 empty] | 0
1 | Up gradation of coal mill reject system, Procurement of Air heater baskets & spare Air heater gearbox at 2X500MW, Bhusawal TPS | DPR |  |  |  | 31.75 | [12 empty] | 0 |  |  |  | 31.75 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0
1.1 | Work of Capacity enhancement, Engineering, modification, upgradation including spares and consumables and complete commissioning including operation and comprehensive maintenance for 12 months for coal mill reject handling system in Unit-4&5, 2X500MW, BTPS, Bhusawal | Scheme |  |  |  | 15.05 | [7 empty] | Avalibility of coal mill system will be improved. • Saving of avg. load loss per day = Rs 16.67 Crore ( outage of 1 coal mill for 4-5 hrs due to choke -up problem) |  |  |  |  | 0 |  |  |  | 15.05 | [10 empty] | 100% | [9 empty] | 0 |  |  |  | 15.05 | [5 empty] | • BR Approved Ref No : 09835 , Date : 23.09.24
1.2 | Procurement of assembly of baskets & seals for Air Preheater of type 31.5 VIM 2000 (72° PA), in Unit-5 2x500MW, BTPS Bhusawal | Scheme |  |  |  | 7.45 | [7 empty] | Unit performance improvement. • Heat rate improvement by 20 kcal/Kwh • Saving of coal cost per year = Rs 9.50 Crore |  |  |  |  | 0 |  |  |  | 7.45 | [10 empty] | 100% | [9 empty] | 0 |  |  |  | 7.45 | [5 empty] | • BR Approved Ref No : 09835 , Date : 23.09.24
1.3 | Procurement of APH Gearbox to improve availability and performance of Air preheaters at 2 x 500 MW Units, BTPS, Bhusawal. | Scheme |  |  |  | 9.25 | [7 empty] | Reduction in generation loss & to improve unit availability. • Saving in term of AFC per year = Rs 28.20 crore. ( Considering 20 days of unit outage on account of non availabilty of APH) |  |  |  |  | 0 |  |  |  | 9.25 | [10 empty] | 100% | [9 empty] | 0 |  |  |  | 9.25 | [5 empty] | • BR Approved Ref No : 09835 , Date : 23.09.24
2 | Boiler Reliability & Availability improvement at 2x500MW, Bhusawal TPS. | DPR |  |  |  | 83.63 | [12 empty] | 0 |  |  |  | 83.63 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0
2.1 | Procurement & Replacement Of LTSH Coils for Unit - 4 & 5 (500MW) TPS, Bhusawal. | Scheme |  |  |  | 19.11 | [7 empty] | Reduction in boiler tube leakages , to improve unit availability & boiler performance. • Saving in term of AFC per year = Rs 4.91 crore. ( Considering 3 days of unit outage on account of 1 BTL occasion) |  |  |  |  | 0 |  |  |  | 19.11 | [10 empty] | 100% | [9 empty] | 0 |  |  |  | 19.11 | [5 empty] | • DPR in preparation
2.2 | Procurement & Replacement Of Economiser Coils For Unit - 4 & 5 (500MW) TPS, Bhusawal | Scheme |  |  |  | 47.6 | [7 empty] | Reduction in boiler tube leakages , to improve unit availability & boiler performance. • Saving in term of AFC per year = Rs 4.91 crore. ( Considering 3 days of unit outage on account of 1 BTL occasion) |  |  |  |  | 0 |  |  |  | 47.6 | [10 empty] | 100% | [9 empty] | 0 |  |  |  | 47.6 | [5 empty] | • DPR in preparation
2.3 | Procurement of assembly of APH Baskets Unit-4 | Scheme |  |  |  | 7.55 | [7 empty] | Unit performance improvement. • Heat rate improvement by 20 kcal/Kwh • Saving of coal cost per year = Rs 9.50 Crore |  |  |  |  | 0 |  |  |  | 7.55 | [10 empty] | 100% | [9 empty] | 0 |  |  |  | 7.55 | [5 empty] | • DPR in preparation
2.4 | Procurement of APH Gearbox Unit-4&5 | Scheme |  |  |  | 9.37 | [7 empty] | Reduction in generation loss & to improve unit availability. • Saving in term of AFC per year = Rs 28.20 crore. ( Considering 20 days of unit outage on account of non availabilty of APH) |  |  |  |  | 0 |  |  |  | 9.37 | [10 empty] | 100% | [9 empty] | 0 |  |  |  | 9.37 | [5 empty] | • DPR in preparation
3 | Various Turbine side reliability improvement schemes at 2x500MW, BTPS | DPR |  |  |  | 41.4 | [12 empty] | 0 |  |  |  | 41.4 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0
3.1 | Reliability improvement of Atlas copco make (mode -ZR -500) | Scheme |  |  |  | 2.4 | [7 empty] | Reliability & performance of the compressor improved. • Saving in term of AFC per year = Rs 2.08 crore. ( Considering 1day of unit outage on account of non availabilty of instrument air) |  |  |  |  | 0 |  |  |  | 2.4 | [10 empty] | 100% | [9 empty] | 0 |  |  |  | 2.4 | [5 empty] | • DPR in preparation
3.2 | Reliability improvement of HPCV Valve with procurment cone assy | Scheme |  |  |  | 2 | [7 empty] | • Improve availability & realiability of plant. |  |  |  |  | 0 |  |  |  | 2 | [10 empty] | 100% | [9 empty] | 0 |  |  |  | 2 | [5 empty] | • DPR in preparation
3.3 | Reliability improvement of Alfa Laval make Portable COP | Scheme |  |  |  | 3 | [7 empty] | • Improve availability & realiability of plant. |  |  |  |  | 0 |  |  |  | 3 | [10 empty] | 100% | [9 empty] | 0 |  |  |  | 3 | [5 empty] | • DPR in preparation
3.4 | Reliability improvement of Seal Oil System with procurement of various U Seal rings | Scheme |  |  |  | 2 | [7 empty] | • Improve availability & realiability of plant. |  |  |  |  | 0 |  |  |  | 2 | [10 empty] | 100% | [9 empty] | 0 |  |  |  | 2 | [5 empty] | • DPR in preparation
3.5 | Reliability improvement of Unit-4 & 5 NDCT with replacement of PVC fills and allied work | Scheme |  |  |  | 30 | [7 empty] | • Overall unit efficiency will increase. • APC reduction by 0.073 % • Generation loss will be 0.72 MUs |  |  |  |  | 0 |  |  |  | 30 | [10 empty] | 100% | [9 empty] | 0 |  |  |  | 30 | [5 empty] | • DPR in preparation
3.6 | Upgradation of Chiller plant, GEHO pump house & OLTC PLC system. |  |  |  |  | 2 | [7 empty] | • Improve availability & realiability of plant. |  |  |  |  | 0 |  |  |  | 2 | [10 empty] | 100% | [9 empty] | 0 |  |  |  | 2 | [5 empty] | • DPR in preparation
4 | IB recommended scheme related (Civil and Electrical) | DPR |  |  |  | 10.76 | [12 empty] | 0 |  |  |  | 10.76 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0
4.1 | Work of fabricating and erecting structural steel watch tower (10 Nos.) in major store, plant area, ash pipe line and ash bund area at BTPS, Deepnagar. | Scheme |  |  |  | 0.86 | [7 empty] | To insure safety of plant. • Plant security will be improved. • Minimize the thefts. • Improve shelter facilities for guards, so they can observe longer distances by covering the maximum area. |  |  |  |  | 0 |  |  |  | 0.86 | [10 empty] | 100% | [9 empty] | 0 |  |  |  | 0.86 | [5 empty] | • DPR send to HO for approval on 14-08-2024
4.2 | Work of construction of ladies frisking room for security section and visitors room near factory gate and providing at 2x500MW, BTPS, Deepnagar. | Scheme |  |  |  | 0.43 | [7 empty] | To insure safety of plant. • It is comfortable and easy for lady security guards to check female employees/ labours visitors & Ensures total privacy of the female employees /labours/ visitors. |  |  |  |  | 0 |  |  |  | 0.43 | [10 empty] | 100% | [9 empty] | 0 |  |  |  | 0.43
4.3 | Work of dismantling and construction old weathered UCR compound wall on bhogawati riverside in 2x500 MW at BTPS. | Scheme |  |  |  | 3.29 | [7 empty] | To insure safety of plant. • Threat to valuable of company, entry of unsocial elements to functional plant and machinery of BTPS will be controlled. |  |  |  |  | 0 |  |  |  | 3.29 | [10 empty] | 100% | [9 empty] | 0 |  |  |  | 3.29
4.4 | Construcion of RCC comppund wall from remote silo to pimpri sekam railway siding cabin at BTPS | Scheme |  |  |  | 2.02 | [7 empty] | To insure safety of plant. • Protection from external threat to functional plants and machinery. • Security of BTPS will be improved. |  |  |  |  | 0 |  |  |  | 2.02 | [10 empty] | 100% | [9 empty] | 0 |  |  |  | 2.02
4.5 | Installation of Highmast towers | Scheme |  |  |  | 4.16 | [7 empty] | To insure safety of plant. • LED consume less enegry so energy will be saved. • Maintenance & replacement cost will be reduced. • IB recommendation. |  |  |  |  | 0 |  |  |  | 4.16 | [10 empty] | 100% | [9 empty] | 0 |  |  |  | 4.16
| FY 2026-27 | [17 empty] | 0 | [24 empty] | 0
1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | DPR |  |  |  | 50 | [12 empty] | 0 |  |  |  | 0 |  | 0 | 0 | 0 | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0
1.1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | Scheme |  |  |  | 50 | [7 empty] | Avalibility of coal mill system will be improved. • Saving of avg. load loss per day = Rs 16.67 Crore ( outage of 1 coal mill for 4-5 hrs ) |  |  |  |  | 0 |  |  |  |  | 50 | [10 empty] | 100% | [8 empty] | 0 |  |  |  |  | 50
2 | Upgradation of Coal feeder weighing system and revamping of Boiler side pneumatic dampers system of Hot air, cold air, FD,PA and burner tilt at Bhusawal TPS 2x500W | DPR |  |  |  | 35 | [12 empty] | 0 |  |  |  | 0 |  | 0 | 0 | 0 | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0
2.1 | Upgradation of Coal feeder weighing system at Bhusawal TPS 2x500W | Scheme |  |  |  | 11.42 | [7 empty] | • This scheme lead to process improvement. |  |  |  |  | 0 |  |  |  |  | 11.42 | [10 empty] | 100% | [8 empty] | 0 |  |  |  |  | 11.42
2.2 | Up-gradation of carbon monoxide analyzer in flue gas installed | Scheme |  |  |  | 2.16 | [7 empty] | Unit performance improvement. • Heat rate improvement by 4 kcal/Kwh • Saving of coal cost per year = Rs 1.9 Crore |  |  |  |  | 0 |  |  |  |  | 2.16 | [10 empty] | 100% | [8 empty] | 0 |  |  |  |  | 2.16
2.3 | Up- Gradation of condition monitoring & analysis system for TSI of Main Turbine , TDBFP & BOP System 2x500 MW BTPS. | Scheme |  |  |  | 13.2 | [7 empty] | • To ensure safety of turbine & avoid falls tripping unit. • To improve the system availability. |  |  |  |  | 0 |  |  |  |  | 13.2 | [10 empty] | 100% | [8 empty] | 0 |  |  |  |  | 13.2
2.5 | Revamping of Boiler side pneumatic dampers system of Hot air, cold air, FD,PA and burner tilt at BTPS 2X500MW | Scheme |  |  |  | 6 | [7 empty] | • Improves flame stability & load variation can be possible. • Reduces auxiliary consumption such as PA, FA fans. • Boiler efficiency will be improved. |  |  |  |  | 0 |  |  |  |  | 6 | [10 empty] | 100% | [8 empty] | 0 |  |  |  |  | 6
2.6 | Procurement of various high pressure valves at 2x500 MW. | Scheme |  |  |  | 2.22 | [7 empty] | • Reduce the loss of steam/water and improve the boiler heat rate. |  |  |  |  | 0 |  |  |  |  | 2.22 | [10 empty] | 100% | [8 empty] | 0 |  |  |  |  | 2.22
3 | Schemes for Turbine side auxiliaries systems Performance & efficiency improvement schemes at 2X500MW, Bhusawal TPS | DPR |  |  |  | 42.47 | [12 empty] | 0 |  |  |  | 0 |  | 0 | 0 | 0 | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0
3.1 | Procurement of BFP Booster Pump (FA-1B-75) complete assembly (04 Nos) at 500MW BTPS, Bhusawal. | Scheme |  |  |  | 3.16 | [7 empty] | • Improvement in auxillary power consumption. • Total Saving in power per year = Rs 0.54 Cr |  |  |  |  | 0 |  |  |  |  | 3.16 | [10 empty] | 100% | [8 empty] | 0 |  |  |  |  | 3.16 |  |  |  |  | • Revised DPR send to HO for approval on 01-08-2024. • Data gap received on 12-08-2024.
3.2 | Procurement of Vacuum Pump complete assembly with recirculation Pump (01 No) and Impeller assembly (2 Nos) at 500MW BTPS, Bhusawal. | Scheme |  |  |  | 5.2 | [7 empty] | Availability of unit • Saving in term of AFC per year = Rs 8.57 crore. ( Considering 6 days of unit outage on account of 1 event) |  |  |  |  | 0 |  |  |  |  | 5.2 | [10 empty] | 100% | [8 empty] | 0 |  |  |  |  | 5.2
3.3 | Revamping, modification of outdoor ducting of Air ventilation system at 2x500MW BTPS, Bhusawal. | Scheme |  |  |  | 8.72 | [7 empty] | • For safety and health of human and plant auxiliaries |  |  |  |  | 0 |  |  |  |  | 8.72 | [10 empty] | 100% | [8 empty] | 0 |  |  |  |  | 8.72
3.4 | Performance improvement of compressors | Scheme |  |  |  | 12.99 | [7 empty] | •Reliability & performance of the compressor improved. • Total Saving in power per year = Rs 1.28 Crore • R&M Cost saving per year = Rs 0.62 Crore. • Fixed Cost saving per year = Rs 0.96 Crore. |  |  |  |  | 0 |  |  |  |  | 12.99 | [10 empty] | 100% | [8 empty] | 0 |  |  |  |  | 12.99
3.5 | Centralized Water Management System at BTPS, Deepnagar, Bhusawal | Scheme |  |  |  | 2.29 | [7 empty] | • Annual Savings in terms of Water Charges = Rs 1.04 Crore |  |  |  |  | 0 |  |  |  |  | 2.29 | [10 empty] | 100% | [8 empty] | 0 |  |  |  |  | 2.29
3.6 | Revamping and upgradation of Forbes Marshal make Steam & Water Analysis System Installed at 2x500MW BTPS. | Scheme |  |  |  | 10.11 | [7 empty] | • Availability of boiler by reduction in Boiler tube leakages. • Savings in terms of AFC & Fuel Oil Consumption per year = Rs 4.09 Crore |  |  |  |  | 0 |  |  |  |  | 10.11 | [19 empty] | 0 |  |  |  |  | 10.11
4 | Implementation of flexible operation solutions for technical minimum operation of 2x500MW, BTPS. | DPR |  |  |  | 50 | [12 empty] | 0 | [5 empty] | 0 | 0 | 0 | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0
4.1 | Implementation of flexible operation solutions for technical minimum operation of 2x500MW, BTPS. | Scheme |  |  |  | 50 | [7 empty] | • As per GoI, increasing contribution from renewable energy sources. So to achieve flexible operation of thermal units scheme is mandatory. |  |  |  |  | 0 |  |  |  |  | 50 | [10 empty] | 100% | [8 empty] | 0 |  |  |  |  | 50
| FY 2027-28 | [17 empty] | 0 | [24 empty] | 0
1 | Supply,Installation and commissioning of Boiler performance and reliability improvement schemes at BTPS 2x500MW. | DPR |  |  |  | 25.08 | [12 empty] | 0 |  |  |  | 0 | 0 |  | 0 | 0 | [6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0
1.1 | Procurement of M/s Torishima, Japan make, 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motors at BTPS 2x500MW. | Scheme |  |  |  | 5.58 | [7 empty] | • Reduce auxiliary power consumption. • Reduce maintenance cost. • Less maintenance. |  |  |  |  | 0 | [5 empty] | 5.58 | [10 empty] | 100% | [7 empty] | 0 | [5 empty] | 5.58 |  |  |  | • DPR yet to be prepared.
1.2 | Installation commissioning of Online DC Earth fault monitoring system at 220V DCDB at 500MW U-4&5. | Scheme |  |  |  | 2.5 | [7 empty] | • For realability of protection of sysytem. |  |  |  |  | 0 | [5 empty] | 2.5 | [10 empty] | 100% | [7 empty] | 0 | [5 empty] | 2.5 |  |  |  | • DPR yet to be prepared.
1.3 | Design, supply, erection, comms. Of ID VFD & AHP transformers for 2x500MW BTPS. | Scheme |  |  |  | 2 | [7 empty] | • Electrical power saving by 5 Amp per pump. • Power saving per year = Rs 0.35 Crore |  |  |  |  | 0 | [5 empty] | 2 | [10 empty] | 100% | [7 empty] | 0 | [5 empty] | 2 |  |  |  | • DPR yet to be prepared.
1.4 | Design,supply,installation and commissioning of Energy efficient System for illumination at BTPS 2x500MW. | Scheme |  |  |  | 4 | [7 empty] | • Annual energy saving per year = Rs 0.743 Crore. |  |  |  |  | 0 | [5 empty] | 4 | [10 empty] | 100% | [7 empty] | 0 | [5 empty] | 4 |  |  |  | • DPR yet to be prepared.
1.5 | Procurement of Main Gear unit assembly of electrical Actuators in 2x500MW BTPS | Scheme |  |  |  | 6 | [7 empty] | • The reliability of system improves. • Reduction in R&M cost per year = Rs 0.40 Crore. • Non availability of critical valves hampers reliability of the system. |  |  |  |  | 0 | [5 empty] | 6 | [10 empty] | 100% | [7 empty] | 0 | [5 empty] | 6 |  |  |  | • DPR yet to be prepared.
1.6 | Supply, erection, commissioning & site testing of 360V, 750 AH Station UPS Battery Sets along with accessories for Unit No.5 at BTPS 2x500MW. | Scheme |  |  |  | 4 | [7 empty] | • Availability & Reliability of Unit get Increased. |  |  |  |  | 0 | [5 empty] | 4 | [10 empty] | 100% | [7 empty] | 0 | [5 empty] | 4 |  |  |  | • DPR yet to be prepared.
1.7 | Upgradation of EWLI system at Bhusawal TPS 2x500W | Scheme |  |  |  | 1 | [7 empty] | • Availability & Reliability of Unit get Increased. |  |  |  |  | 0 | [5 empty] | 1 | [10 empty] | 100% | [7 empty] | 0 | [5 empty] | 1 |  |  |  | • DPR yet to be prepared.
2 | Performance improvement of Bottom ash evacualtion system to reduce auxillary power consumption, water consumption & environmental pollution at 2X500MW, Bhusawal TPS | DPR |  |  |  | 42.33 | [12 empty] | 0 |  |  |  | 0 | 0 |  | 0 | 0 | [6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0
2.1 | Modification of latest design AR 200/550 Ash slurry pump assembly including auxillaries at AHP, 2x500MW, BTPS. | Scheme |  |  |  | 4.69 | [7 empty] | • Fixed Cost saving per year = Rs 5.04 Crore. • Saving in cost of electrical power & water = Rs 1.67 Crore. |  |  |  |  | 0 | [5 empty] | 4.69 | [10 empty] | 100% | [7 empty] | 0 | [5 empty] | 4.69 |  |  |  | • DPR send to HO for approval on 22-08-2024. • Data Gap received on 03-09-2024
2.2 | Modification of single roll reversible clinker grinder system at AHP, 2x500MW, BTPS | Scheme |  |  |  | 3.09 | [7 empty] | • Fixed Cost saving per year = Rs 5.04 Crore. • R&M Cost saving per year = Rs 0.38 Crore. • Saving in cost of electrical power & water = Rs 0.17 Crore. |  |  |  |  | 0 | [5 empty] | 3.09 | [10 empty] | 100% | [7 empty] | 0 | [5 empty] | 3.09
2.3 | Modification of bottom ash & coarse ash slurry pipe line disposal system at AHP 2X500 MW BTPS | Scheme |  |  |  | 34.55 | [7 empty] | • Fixed Cost saving per year = Rs 5.04 Crore. • Variable Cost saving per year = Rs 1.73 Crore. • Saving in cost of electrical power & water = Rs 0.167 Crore. |  |  |  |  | 0 | [5 empty] | 34.55 | [10 empty] | 100% | [7 empty] | 0 | [5 empty] | 34.55
3 | Boiler Reliability & Availability improvement at 2x500MW, Bhusawal TPS. | DPR |  |  |  | 45 | [12 empty] | 0 |  |  |  | 0 | 0 |  | 0 | 0 | [6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0
3.1 | Procurement of Boiler Coils (CRH &HRH) at 2x500MW BTPS. | Scheme |  |  |  | 25 | [7 empty] | Reduction in boiler tube leakages , to improve unit availability & boiler performance. • Saving in term of AFC per year = Rs 4.91 crore. ( Considering 3 days of unit outage on account of 1 BTL occasion) |  |  |  |  | 0 | [5 empty] | 25 | [10 empty] | 100% | [7 empty] | 0 | [5 empty] | 25 |  |  |  | • DPR yet to be prepared.
3.2 | Procurement of ID fan impeller with shaft at 2x500 MW BTPS. | Scheme |  |  |  | 15 | [7 empty] | • Avalability of unit increased . • Savings in partial loading of unit for 7 days ( Considering non- avalability of 1 ID fan) |  |  |  |  | 0 | [5 empty] | 15 | [10 empty] | 100% | [7 empty] | 0 | [5 empty] | 15 |  |  |  | • DPR yet to be prepared.
3.3 | Procurement SH,RH,MS outlet valves with actuator and motor at 2x500 MW BTPS. | Scheme |  |  |  | 5 | [7 empty] | • Improved the boiler heat rate. • Saving of coal cost per year = Rs 2.11 Crore. |  |  |  |  | 0 | [5 empty] | 5 | [10 empty] | 100% | [7 empty] | 0 | [5 empty] | 5 |  |  |  | • DPR yet to be prepared.
4 | CHP Infrastructure Development Schemes | DPR |  |  |  | 46.9 | [12 empty] | 0 |  |  |  | 0 | 0 |  | 0 | 0 | [6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0
4.1 | Supply, installation and commissioning PLC system on a single platform to match with external aspect & process improvement at CHP 2x500MW BTPS. | Scheme |  |  |  | 18.4 | [7 empty] | • Maximum Coal Handling Plant availability • Faster coal wagon Unloading • Reduction in maintenance and operational cost. • Release of spare time to maintain other auxiliaries. • Utilization of rated capacity of conveyor belts • Reduction in auxiliary consumption • Reduction in breakdown time. |  |  |  |  | 0 | [5 empty] | 18.4 | [10 empty] | 100% | [7 empty] | 0 | [5 empty] | 18.4 |  |  |  | • DPR yet to be prepared.
4.2 | Supply, installation, retrofitting and commissioning of HT breaker at HT Switchgear in CHP 2x500MW BTPS | Scheme |  |  |  | 6.9 | [7 empty] | • Maximum Coal Handling Plant availability • Faster coal wagon Unloading • Reduction in maintenance and operational cost. • Release of spare time to maintain other auxiliaries. • Utilization of rated capacity of conveyor belts • Reduction in auxiliary consumption • Reduction in breakdown time. |  |  |  |  | 0 | [5 empty] | 6.9 | [10 empty] | 100% | [7 empty] | 0 | [5 empty] | 6.9 |  |  |  | • DPR yet to be prepared.
4.3 | Supply, installation, retrofitting and commissioning of LT breaker at LT Switchgear in CHP 2x500MW BTPS. | Scheme |  |  |  | 4.4 | [7 empty] | • Maximum Coal Handling Plant availability • Faster coal wagon Unloading • Reduction in maintenance and operational cost. • Release of spare time to maintain other auxiliaries. • Utilization of rated capacity of conveyor belts • Reduction in auxiliary consumption • Reduction in breakdown time. |  |  |  |  | 0 | [5 empty] | 4.4 | [10 empty] | 100% | [7 empty] | 0 | [5 empty] | 4.4 |  |  |  | • DPR yet to be prepared.
4.4 | Supply, Installation & Commissioning of Magnetic Separators at CHP 2x 500MW BTPS Deepnagar | Scheme |  |  |  | 3.73 | [7 empty] | • Reduction in maintenance and operational cost. • Release of spare time to maintain other auxiliaries. • Utilization of rated capacity of conveyor belts • Reduction in auxiliary consumption • Reduction in breakdown time. |  |  |  |  | 0 | [5 empty] | 3.73 | [10 empty] | 100% | [7 empty] | 0 | [5 empty] | 3.73 |  |  |  | • DPR yet to be prepared.
4.5 | Supply, Installation & Commissioning Flameproof lighting at CHP 2x 500MW BTPS Deepnagar | Scheme |  |  |  | 10.47 | [7 empty] | • minimize the risk of ignition in hazardous environment. • Reduce procurement & maintenance cost. |  |  |  |  | 0 | [5 empty] | 10.47 | [10 empty] | 100% | [7 empty] | 0 | [5 empty] | 10.47 |  |  |  | • DPR yet to be prepared.
4.6 | Supply, Installation & upgradation of HT /LT relay at CHP BTPS. | Scheme |  |  |  | 3 | [7 empty] | • Improved the safety & protection under faulty condition. • Enhanced system reliability. • Reduced the cost & extends the life of the HT/LT systems. |  |  |  |  | 0 | [5 empty] | 3 | [18 empty] | 0 | [5 empty] | 3 |  |  |  | • DPR yet to be prepared.
5 | Detail Project report of improvement of Unloading in Coal handling Plant BTPS. | DPR |  |  |  | 35.89 | [12 empty] | 0 |  |  |  | 0 | 0 |  | 0 | 0 | [6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0
5.1 | Procurement of 04 no of locomotives for Coal handling Plant BTPS. | Scheme |  |  |  | 13.68 | [7 empty] | • Reduction in outage hours in account of Locomotives will get reduced, hence improvement in availability & reliability of Locomotives. Coal wagon movement can be possible more rapidly & efficiently. |  |  |  |  | 0 | [5 empty] | 13.68 | [10 empty] | 100% | [7 empty] | 0 | [5 empty] | 13.68 |  |  |  | • DPR yet to be prepared.
5.2 | Design Supply Erection and Comission of Hour glass shape Coal diverting chutes with extra life wear resistant plates in CHP, BTPS. | Scheme |  |  |  | 5.67 | [7 empty] | • Reduced wear & tear & lower the maintenance cost. • Improved coal flow efficiency . |  |  |  |  | 0 | [5 empty] | 5.67 | [10 empty] | 100% | [7 empty] | 0 | [5 empty] | 5.67
5.3 | Design Supply Erection and Comission of Inverted Y Shape Coal diverting chutes with extra life wear resistant plates in CHP, BTPS. | Scheme |  |  |  | 4.72 | [7 empty] | • Reduced wear & tear & lower the maintenance cost. • Improved coal flow efficiency . |  |  |  |  | 0 | [5 empty] | 4.72 | [10 empty] | 100% | [7 empty] | 0 | [5 empty] | 4.72
5.4 | Design Supply Erection and Comission of coal diverting chutes with extra life wear resistant plates in CHP BTPS. | Scheme |  |  |  | 4.72 | [7 empty] | • Reduced wear & tear & lower the maintenance cost. • Improved coal flow efficiency . |  |  |  |  | 0 | [5 empty] | 4.72 | [10 empty] | 100% | [7 empty] | 0 | [5 empty] | 4.72
5.5 | Work of Revamping and structural up-gradation of conveyor 104A&B in Coal Handling Plant-BTPS. | Scheme |  |  |  | 7.1 | [7 empty] | • Conveyor system availability will increase. • Demurrage charges will get reduced. • Overloading of conveyor will be minimized. • Low auxiliary consumption can be achieved. |  |  |  |  | 0 | [5 empty] | 7.1 | [10 empty] | 100% | [7 empty] | 0 | [5 empty] | 7.1
6 | Supply and Installation of reliability improvement schemes for HT/LT switchgears and auxilliaries at BTPS 2x500MW. | DPR |  |  |  | 47.8 | [12 empty] | 0 |  |  |  | 0 | 0 |  | 0 | 0 | [6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0
6.1 | Procurement of HT Motors of various ratings at 2x500MW. | Scheme |  |  |  | 4 | [7 empty] | • Energy efficient motor for auxillary power reduction • Saving in term of AFC per year = Rs 1 crore. |  |  |  |  | 0 | [5 empty] | 4 | [10 empty] | 100% | [7 empty] | 0 | [5 empty] | 4 |  |  |  | • DPR yet to be prepared.
6.2 | Procurement of Dry type transformers of varoius ratings at 2x500MW. | Scheme |  |  |  | 4 | [7 empty] | • Reduce auxiliary power consumption. |  |  |  |  | 0 | [5 empty] | 4 | [10 empty] | 100% | [7 empty] | 0 | [5 empty] | 4
6.3 | Procurement of Inverter and converter trolleys of GEHO Pump at 2x500MW. | Scheme |  |  |  | 2 | [7 empty] | • System relability will be improved. |  |  |  |  | 0 | [5 empty] | 2 | [10 empty] | 100% | [7 empty] | 0 | [5 empty] | 2
6.4 | Procurement of Vacuum Contactors of various ratings for HT Switchgears at BTPS 2x500MW. | Scheme |  |  |  | 2.5 | [7 empty] | • Relable operation & protection of plant auxillary. |  |  |  |  | 0 | [5 empty] | 2.5 | [10 empty] | 100% | [7 empty] | 0 | [5 empty] | 2.5
6.5 | Supply, erection, commissioning & site testing of 360V, 750 AH Station UPS Battery Sets along with accessories for Unit No.4 at BTPS 2x500MW’. | Scheme |  |  |  | 4 | [7 empty] | • Relability of plant relay protection system. |  |  |  |  | 0 | [5 empty] | 4 | [10 empty] | 100% | [7 empty] | 0 | [5 empty] | 4
6.6 | Updragation of Sox-Nox analyzer,PM analyzer, ETP analyzer at BTPS 2X500MW. | Scheme |  |  |  | 1.05 | [7 empty] | • Increased reliability & stability of process . • Reduces environmental losses. |  |  |  |  | 0 | [5 empty] | 1.05 | [10 empty] | 100% | [7 empty] | 0 | [5 empty] | 1.05
6.7 | Upgradation of O2 analyzer at BTPS 2X500MW | Scheme |  |  |  | 3.4 | [7 empty] | Unit performance improvement. • Heat rate improvement by 4 kcal/Kwh • Saving of coal cost per year = Rs 1.9 Crore |  |  |  |  | 0 | [5 empty] | 3.4 | [10 empty] | 100% | [7 empty] | 0 | [5 empty] | 3.4
6.8 | Revamping & Upgradation Of Vibration Monitoring Rack From VM7 TO VM7B at BTPS 2X500MW | Scheme |  |  |  | 5 | [7 empty] | • Realability of the system will improved. |  |  |  |  | 0 | [5 empty] | 5 | [10 empty] | 100% | [7 empty] | 0 | [5 empty] | 5
6.9 | Procurement & Installation of High Mast towers in various location in BTPS | Scheme |  |  |  | 2 | [7 empty] | • IB recommondation. |  |  |  |  | 0 | [5 empty] | 2 | [18 empty] | 0 | [5 empty] | 2
6.1 | Renovation and Modification of Colony Electric Supply System to improve availability and reliability of supply system at BTPS Colony, Deepnagar | Scheme |  |  |  | 15.85 | [7 empty] | • Reduction in power distribution losses • Improvement in system reliability & uninterrupted power supply as system is too old. |  |  |  |  | 0 | [5 empty] | 15.85 | [18 empty] | 0 | [5 empty] | 15.85
6.11 | Work of Overhauling repairs of U-5 350KW BCWP motor of M/s Torishima make at BTPS 2x500MW. | Scheme |  |  |  | 4 | [7 empty] | • Reduce auxiliary power consumption. • Reduce maintenance cost. • Less maintenance. |  |  |  |  | 0 | [5 empty] | 4 | [18 empty] | 0 | [5 empty] | 4
| FY 2028-29 | [17 empty] | 0 | [24 empty] | 0
1 | APH baskets with main drive Gear box and lub oil skids with motor at 2x500MW BTPS | DPR |  |  |  | 50 | [12 empty] | 0 |  |  |  | 0 | 0 | 0 |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 |  | 0
1.1 | APH baskets with main drive Gear box and lub oil skids with motor at 2x500MW BTPS | Scheme |  |  |  | 50 | [7 empty] | Unit performance improvement. • Heat rate improvement by 20 kcal/Kwh • Saving of coal cost per year = Rs 9.50 Crore |  |  |  |  | 0 | [6 empty] | 50 | [10 empty] | 100% | [6 empty] | 0 | [6 empty] | 50 |  |  | • DPR yet to be prepared.
2 | Detail Project Report for Design, Engineering, Supply, Installation and commissioning of 1500TPH Stacker cum re-claimer in Coal Handling Plant-BTPS. | DPR |  |  |  | 118 | [12 empty] | 0 |  |  |  | 0 | 0 | 0 |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 |  | 0
2.1 | Design, Engineering, Supply, Installation and commissioning of 1500TPH Stacker cum re-claimer in Coal Handling Plant-BTPS. | Scheme |  |  |  | 118 | [7 empty] | • Reduction in R&M cost per year = Rs 2 Crore. |  |  |  |  | 0 | [6 empty] | 118 | [10 empty] | 100% | [6 empty] | 0 | [6 empty] | 118 |  |  | • DPR yet to be prepared.
3 | Enhancement of Unloading & Stacking Capacity of CHP. | DPR |  |  |  | 89 | [12 empty] | 0 |  |  |  | 0 | 0 | 0 |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 |  | 0
3.1 | Design Supply errection & Comissioning of Open Wagon Tippler along with stacking and reclaiming yard conveyors at CHP stack yard. | Scheme |  |  |  | 89 | [7 empty] | • The reliability of system improves. • Reduction in R&M cost per year = Rs 0.5 Crore. |  |  |  |  | 0 | [6 empty] | 89 | [10 empty] | 100% | [6 empty] | 0 | [6 empty] | 89 |  |  | • DPR yet to be prepared.
| FY 2029-30 | [17 empty] | 0 | [24 empty] | 0
1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | DPR |  |  |  | 70 | [12 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
1.1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | Scheme |  |  |  | 70 | [7 empty] | Avalibility of coal mill system will be improved. • Saving of avg. load loss per day = Rs 20.00 Crore ( outage of 1 coal mill for 4-5 hrs due to choke -up problem) |  |  |  |  | 0 | [7 empty] | 70 | [10 empty] | 100% | [5 empty] | 0 | [7 empty] | 70 |  | • DPR yet to be prepared.
2 | Upgradation rail track in CHP -BTPS | DPR |  |  |  | 75 | [12 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
2.1 | Revamping and Upgradation of rail track from 52KG to 60KG in CHP-BTPS. | Scheme |  |  |  | 75 | [7 empty] | • Improment in system reliability as railway track is old . • It is necessary for safety and efficiency. • Reduction in dummage charges. |  |  |  |  | 0 | [7 empty] | 75 | [10 empty] | 100% | [5 empty] | 0 | [7 empty] | 75 |  | • DPR yet to be prepared.
[19 empty] | 0 | [24 empty] | 0
| B) Non-DPR Schemes | [17 empty] | 0 | [24 empty] | 0
1 | Contract for modification of Wobbler feeder in CHP-2X500MW | Non-DPR | [13 empty] | 1.4733 |  |  | 1.4733 | [21 empty] | 1.4733 |  |  | 1.4733 | [10 empty] | Capitalised
2 | Contract for Revamping of Apron Feeder in CHP-2X500MW | Non-DPR | [13 empty] | 2.3246 |  |  | 2.3246 | [21 empty] | 2.3246 |  |  | 2.3246 | [10 empty] | Capitalised
3 | Procurement of double lip skirt sealing & tracking idler in CHP at 2x500MW, BTPS | Non-DPR | [13 empty] | 0.57025 |  |  | 0.57025 | [21 empty] | 0.57025 |  |  | 0.57025 | [10 empty] | Capitalised
4 | Supply, erection & commissioning of vibrating feeder in CHP at 2x500MW, BTPS | Non-DPR | [13 empty] | 0.57796 |  |  | 0.57796 | [21 empty] | 0.57796 |  |  | 0.57796 | [10 empty] | Capitalised
5 | Coal chutes with extra life wear resistance plates in CHP at 2X500MW | Non-DPR | [13 empty] | 2.0319 |  |  | 2.0319 | [21 empty] | 2.0319 |  |  | 2.0319 | [10 empty] | Capitalised
6 | Epoxy Painting upto all height to structural steel work in main plant boiler side area and CHP area | Non-DPR | [13 empty] | 5.8625 |  |  | 5.8625 | [21 empty] | 5.8625 |  |  | 5.8625 | [10 empty] | Capitalised
7 | Rectification of Belt feeder & Gravity Take-up in CHP-2X500MW. | Non-DPR | [13 empty] | 1.6479 |  |  | 1.6479 | [21 empty] | 1.6479 |  |  | 1.6479 | [10 empty] | Capitalised
8 | Coal diverting chutes in CHP at 2X500MW. | Non-DPR | [13 empty] | 2.2184 |  |  | 2.2184 | [21 empty] | 2.2184 |  |  | 2.2184 | [10 empty] | Capitalised
9 | Supply of Conveyor Pulleys with Ceramic lagging at CHP-2X500MW, BTPS, Bhusawal | Non-DPR | [13 empty] | 0.58051 |  |  | 0.58051 | [21 empty] | 0.58051 |  |  | 0.58051 | [10 empty] | Capitalised
10 | Non-DPR Project Report for Design, Supply,Erection & Commissioning of High Performance Energy Chain System for Side Arm Charger at 2x500 at CHP | Non-DPR | [14 empty] | 1.5015 |  | 1.5015 | [22 empty] | 1.5015 |  | 1.5015 | [10 empty] | Capitalised
11 | Implementation of Energy Conservation Demonstration Project in buildings of BTPS 2x500MW | Non-DPR | [16 empty] | 0 | [24 empty] | 0 | [10 empty] | Capitalised
12 | Installation of Fire & Explosion Prevention system at Bhusawal 500MW Unit-4. | Non-DPR | [15 empty] | 2.4539 | 2.4539 | [23 empty] | 2.4539 | 2.4539 | [10 empty] | Capitalised
13 | Fixtures & Fitting (10801) | Non-DPR | [13 empty] | 0.21334 |  |  | 0.21334 | [21 empty] | 0.21334 |  |  | 0.21334 | [10 empty] | Capitalised
14 | Office equpment (10901) | Non-DPR | [13 empty] | 0.22996 |  |  | 0.22996 | [21 empty] | 0.22996 |  |  | 0.22996 | [10 empty] | Capitalised
15 | 150 W & 40 W LED FIXTURES AT TG HOUSE BUILDING 2X500MW | Non-DPR | [14 empty] | 0.52807 |  | 0.52807 | [22 empty] | 0.27807 |  | 0.27807 | [10 empty] | Capitalised
16 | JUMBO DEESERT AIR COOLERS FOR POWER TRANSFORERS | Non-DPR | [14 empty] | 0.10143 |  | 0.10143 | [22 empty] | 0.10143 |  | 0.10143 | [10 empty] | Capitalised
17 | GEN ASSET (ALMIRAH,TABLE & CHAIR) (10801) | Non-DPR | [14 empty] | 0.23454 |  | 0.23454 | [22 empty] | 0.23454 |  | 0.23454 | [10 empty] | Capitalised
18 | LAPTOP, 50 INCH TV,PRINTER,PROJECTOR,DESKTOP,UPS & ETS. (10901) | Non-DPR | [14 empty] | 0.55035 |  | 0.55035 | [22 empty] | 0.55035 |  | 0.55035 | [10 empty] | Capitalised
19 | RESTAURANT EQUIP COMPOSTING MACHINE | Non-DPR | [15 empty] | 0.05049 | 0.05049 | [23 empty] | 0.05049 | 0.05049 | [10 empty] | Capitalised
20 | OFFICE TABLE,STORGE RACK,FAN | Non-DPR | [15 empty] | 0.57869 | 0.57869 | [23 empty] | 0.57869 | 0.57869 | [10 empty] | Capitalised
21 | CAMERAS | Non-DPR | [15 empty] | 0.038468 | 0.038468 | [23 empty] | 0.038468 | 0.038468 | [10 empty] | Capitalised
22 | VELHALA ASH BUND RD WORK | Non-DPR | [13 empty] | 2.4645 |  |  | 2.4645 | [21 empty] | 2.4645 |  |  | 2.4645 | [10 empty] | Capitalised
23 | CONCERETE ROAD FROM DIESEL PUMP TO 500MW FACTORY G | Non-DPR | [13 empty] | 0.98449 |  |  | 0.98449 | [21 empty] | 0.98449 |  |  | 0.98449 | [10 empty] | Capitalised
24 | Admin Building | [13 empty] | 0.05175 |  |  |  | 0.05175 | [8 empty] | 0% |  |  |  |  | 0% | [10 empty] | 0 | [9 empty] | The expenditure is on Architectural Design and Conceptual Planning of Admin Building at Bhusawal. The PO is initiated by O/o CE (Civil III) | WIP
25 | Furniture & Fixture | [17 empty] | 0 | 0.13712 | [23 empty] | 0 | 0.13712 | [8 empty] | Air Purifiers 13-04-2022 Office Chairs & Exec Chairs - 28-11-2022 Watr cooler 29-08-2022 Ice lined Refridgerator - 30-09-2022 Split Air Conditioner - 12-09-2022 | Capitalised
26 | Office Equipment | [17 empty] | 0 | 0.14424 | [23 empty] | 0 | 0.14424 | [8 empty] | Multifeeder Scanner - 13-05-2022 Dot Matri Printer - 03-04-2022 | Capitalised
27 | Furniture & Fixture | [17 empty] | 0 |  | 0.073968 | [22 empty] | 0 | 0 | 0.073968 | 0 | [6 empty] | S Type Chairs - 10-10-2023 Water Heaters - 14-03-2024 | Capitalised
28 | Office Equipment | [17 empty] | 0 |  | 0.15891 | [22 empty] | 0 | 0 | 0.15891 | 0 | [6 empty] | CCTV - 07-11-2023 Printers - 31-03-2024 Franking Machine - 31-03-024 | Capitalised
29 | Work of repairs of 350 KW BCWP-4B & BCWP-5B motor of M/s. Torishima make at BTPS 2x500 MW | Non-DPR | [11 empty] | •Due to availability of spare motor, failed motor can be replaced in short duration. •Generation loss will be minimized |  |  |  |  | 0 |  | 4.8465 | [22 empty] | 0 | 0 | 4.8465 | 0 | [6 empty] | * PO Number 4385000600 * WCR Date - 15-05-2023 and 22-07-2023 | Capitalised
30 | ABC Powder Type and Foam Type Composite Fire Extinguisher | Non-DPR | [11 empty] | • Ensure Avaiilabilty of fire extinguisher and for the Safety of Plant. |  |  |  |  | 0 |  | 0.58548 | [22 empty] | 0 | 0 | 0.58548 | 0 | [6 empty] | * PO Number 4500128925 * WCR Date - 03-01-2024 | Capitalised
31 | Withdrawal of capex from Project (LD - Passenger Lifts) | [17 empty] | 0 | [24 empty] | 0 | -0.13899 | [8 empty] | Asset No 1501005993
| Total | [5 empty] | 1255.2751 | [7 empty] | 96.1825 | 55.4069 | 3.1859 | 29.5437 | 184.319 | 14.829 | 10.8339 | 164.5185 | 811.31 | 532.6 | 243 | 257 | 145 | 7.51 | 8.25 | 0 | 6.9 | 5 | 2.5 | 19.5 | [5 empty] | 12.182 | 131.0302 | 2.6659 | 38.2111 | 184.0892 | 13.9194 | 16.578 | 151.7831 | 643.77 | 532.6 | 243 | 257 | 145 | -7.7263
[45 empty] | 0.28136 | 5.6649 | 0
Formulas:
Approved Start Date = IF([MERC Approval Date]=0,"-",[MERC Approval Date])
Approved Start Date = [MERC Approval Date]
Date of Submission = [Date of Submission, row above]
MERC Approval Date = IF([MERC Approval Date, row above]=0,"-",[MERC Approval Date, row above])
MERC Approval Date = [MERC Approval Date, row above]
Note on M4: SSP-RCD As per the implementation plan submitted in the DPR/ Approved by MERC
Note on G11: RCD-SSP: 15% Discount
Note on G23: SUSHANT: Scheme No. 3: Cost related to KPKD 5 is deducted here & added in KPKD 5
Note on H23: SSP-RCD: Scheme No. 3: Cost related to KPKD 5 is deducted here & added in KPKD 5
Note on G26: SUSHANT: Cost related to KPKD 5 is deducted here & added in KPKD 5

## F4.3
MSPGCL: Bhusawal U # 4-5
MTR Petition Formats - Generation
| Project Details |  |  |  |  | Form 4.3: Capital Work-in-progress - Project-wise details | [5 empty] | (Rs. Crore)
Sr. No. | Project Code | MERC Approval No. | MERC Approval Date | Approved Project Cost | Cumulative Expenditure Incurred till beginning of the Year | Capital Expenditure Capitalised | Opening CWIP | Investment during the year | Capital Work in Progress |  |  |  | Closing CWIP
[9 empty] | Works Capitalised | Interest Capitalised | Expenses Capitalised | Total Capitalisation |  | Allowable Capitalisation | Probable Disallowance
FY 2022-23
a) DPR Schemes
(i) Submitted to MERC
7 | Interconnection of 210 MW CHP to 500 MW CHP through Conveyors BC-02 & BC-03 having capacity of 500 TPH | MERC/CAPEX/20162017/00227 | 2016-05-24 | 24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Interconnection of 210 MW CHP to 500 MW CHP through Conveyors BC-02 & BC-03 having capacity of 500 TPH | MERC/CAPEX/20162017/00227 | 2016-05-24 | 22.73 | 19.1067 | 19.1067 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/00227 | 2016-05-24 | 1.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Stack management by procurement of Bulldozer & LOCO and CHP area schemes for performance & unloading improvement | MERC/CAPEX/20162017/01426 | 2017-02-02 | 9.9669 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement of Locomotive 800 HP (2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 4.9504 | 4.8261 | 4.8261 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Procurement of 2 No’s of Bulldozer Model D-155(2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 2.562 | 3.4747 | 3.4747 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.3 | Modification below primary crusher chutes 15A/B & Conv.02 | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.42975 | 0.38033 | 0.38033 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.4 | New helical gear box for various conveyors | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.79339 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.5 | Procurement of Elecon Make Ring Granulator Type TK-09-38B | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.53719 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.6 | Procurement of Elecon Make Ring Granulator Type TK6 32B Ring Granulator | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.33884 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.35537 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Construction of 1st raising of Ash bund from T.B.L. 258M to 264M at Bhusawal TPS | MERC/CAPEX/20172018/4267 | 2017-09-28 | 64.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Construction of 1st raising of Ash bund from T.B.L. 258M to 264M at Bhusawal TPS | MERC/CAPEX/20172018/4267 | 2017-09-28 | 64.22 | 64.4982 | 64.4982 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Augmentation of Ash Evacuation System & Procurement of BCW Pump Motors at Bhusawal & Khaperkheda TPS 500 MW Units | MERC/CAPEX/20172018/4782 | 2017-11-28 | 17.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Installation of standby Buffer Hopper parallel to existing pair of buffer hoppers | MERC/CAPEX/20172018/4782 | 2017-11-28 | 11.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | Installation of additional vacuum pump for every two passes, near to intermediate hopper. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.3 | Procurement of 02 Nos of M/s Torishima, Japan make, 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motors (without pump casing) with 02 lots of recommended Electrical & C&I spares for Bhusawal and Khaparkheda TPS 500MW. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 4.24 | 4.6696 | 4.6696 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.4 | Procurement of complete ACVF drive module comprising of 2 Nos. of Supply and 3 Nos. of Inverter modules for GEHO pumps | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0.95 | 0.92864 | 0.92864 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.5 | Supply, erection and commissioning of 24VDC, 100A Float & Float cum Boost Battery Charger with 325Ah Battery Bank for CWPH at BTPS 2x500 MW. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0.15 | 0.15788 | 0.15788 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Various schemes for renovation of colony at Bhusawal TPS | MERC/CAPEX/20172018/0221 | 2018-02-12 | 19.3341 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Renovation of staff quarters & related work at BTPS Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 7.021 | 5.4584 | 5.4584 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Colony Internal Roads at BTPS, Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 3.85 | 3.2501 | 3.2514 | -0.001329 | 0 | 0 |  |  | 0 | -0.001329 | 0 | 0
11.3 | Water supply , sanitary & drainage works at BTPS, Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 7.3 | 5.8361 | 5.8109 | 0.025229 | 0 | 0 |  |  | 0 | 0.025229 | 0 | 0
11.4 | Plinth protection to existing buildings at BTPS, Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 1.1631 | 0.91823 | 0.91823 | -2.2e-08 | 0 | 0 |  |  | 0 | -2.2e-08 | 0 | 0
12 | Pipeline from River Water Pump House (RWPH) to aquaduct over Bhogawati River and Other allied power house road works under DPR scheme at BTPS, Bhusawal | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 13.1172 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Providing supplying laying, jointing, testing and commissioning of 1650 mm Ø ID 8 mm thick M.S. pipeline for raw water supply from RWPH to aquaduct over Bhogawati river at, BTPS, Bhusawal. | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 7.257 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.2 | Construction of WBM and Bituminous road along inlet & outlet canals and concreate road along periphery of Major store at BTPS, Bhusawal. | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 4.22 | 1.27 | 0 | 1.27 | 1.9032 | 1.1932 |  |  | 1.1932 | 1.9801 | 1.1932 | 0
12.3 | Work of construction of self-supporting steel roofing system for a major store godown shed of span 25M at BTPS, Deepnagar. | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 1.6402 | 0.27 | 1.6376 | -1.3676 | 0 | 0 |  |  | 0 | -1.3676 | 0 | 0
0 | IDC | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 0 | 0 | 0 | 0 | 0.059623 | 0 |  |  | 0 | 0.059623 | 0 | 0
13 | Supply, erection, commissioning & site testing of 220 V, 2035 AH, Station Battery Sets (4 Nos.) and 24 V, 2250 AH, SG/TG & BOP Battery Sets (8 Nos.) for U# 4 & 5 along with accessories at 2 x 500 MW BTPS, Bhusawal | MERC/CAPEX/2017-2018/1226 | 2018-08-10 | 11.59 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Supply, erection, commissioning & site testing of 220V, 2035 AH Station Battery Sets (02 Nos.) and 24V, 2250AH, SG/TG & BOP Battery Set (04 Nos.) along with accessories for Unit No.5 at BTPS 2x500MW. | MERC/CAPEX/2017-2018/1226 | 2018-08-10 | 5.795 | 6.374 | 6.374 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Supply, erection, commissioning & site testing of 220V, 2035 AH Station Battery Sets (02 Nos.) and 24V, 2250AH, SG/TG & BOP Battery Set (04 Nos.) along with accessories for Unit No.4 at BTPS 2x500MW. | MERC/CAPEX/2017-2018/1226 | 2018-08-10 | 5.795 | 6.3227 | 6.3227 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Flue Gas Desulphurization (FGD) System for 500 MW Units (Total 8 Nos) of MSPGCL | MERC/CAPEX/2020-2021/WFH/SBR/45 | 2021-02-05 | 869.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | Flue Gas Desulphurization (FGD) System for Bhusawal Unit 4-5 | MERC/CAPEX/2020-2021/WFH/SBR/45 | 2021-02-05 | 830.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/45 | 2021-02-05 | 39.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Procurement of two BFP Cartridges & one rotor of Turbine driven BFP & at 500MW BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 10.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Procurement of two BFP Cartridges at 500MW BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 3.84 | 0 | 0 | 0 | 2.24 | 2.24 |  |  | 2.24 | 0 | 2.24 | 0
16.2 | Procurement of one rotor of Turbine driven BFP at 500MW BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 6.46 | 7.6136 | 7.6136 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 0.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | CHP Improvement Schemes at 2X500MW, BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 21.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Revamping of Apron Feeder in CHP at 2X500MW, BTPS | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 4.67 | 0 | 0 | 0 | 4.6492 | 4.6492 |  |  | 4.6492 | 0 | 4.6492 | 0
17.2 | Design, engineering, manufacturing, supply, Erection and commissioning of short conveyor from stack yard to belt feeder 112 in CHP 2x500MW BTPS. | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 3.53 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.3 | Design, engineering, manufacturing, supply, Erection and commissioning of stone grappler at Wagon Tippler No.3 in CHP 2x500MW BTPS. | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 0.84 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.4 | Procurement of suspended magnets in CHP 2x500MW BTPS. | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 2.95 | 0 | 0 | 0 | 2.947 | 2.947 |  |  | 2.947 | 0 | 2.947 | 0
17.5 | Supply, Erection And Commissioning of Electro-Mechanical Drive to Apron Feeder at CHP 500MW | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 7.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 1.66 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Bhusawal: Unit 4-5 (3 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 1.8768 | 1.8768 | 0 | 0.07 | 0.069 |  |  | 0.069 | 0.001 | 0.069 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Bhusawal: Unit 4-5 | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 3.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Advance Multipurpose Fire Tender for BTPS 4-5 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 1.7765 | 1.7765 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Normal Multipurpose Fire Tender for BTPS 4-5 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.5 | 0 | 0 | 0 | 2.1847 | 2.1847 |  |  | 2.1847 | 0 | 2.1847 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 10.0654 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Bhusawal: Unit 4-5 | MERC/CAPEX/20172018/0177 | 2018-02-06 | 10.0654 | 8.3016 | 8.2998 | 0.0017614 | 0.49389 | 0.49389 |  |  | 0.49389 | 0.0017614 | 0.49389 | 0
18 | Procurement of assembly of baskets for Air Pre-heater of type 31.5 VIM 2000 (72° PA), Replacement of thermal insulation of Boiler, Ducts & Steam Pipelines and Coal Mill Gear Box in 2x500MW at BTPS, Bhusawal | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 14.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Procurement of assembly of baskets for Air Preheater of type 31.5 VIM 2000 (72° PA) for Unit-4&5 | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 5.53 | 8.411 | 8.411 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.2 | Replacement of thermal insulation of Boiler, Ducts & Steam Pipelines along with supply | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 3.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.3 | Supply of XRP-1043 coal mill gearbox spares in unit-4&5. | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 5.39 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 0.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | Up-gradation of Operating System of Max DNA DCS, GE Fanuc PLC system & Schneider PLC system & Procurement of Critical Insurance spares for PA and FD fans System at 2 x 500 MW Units BTPS Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 31.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Up-gradation of Existing MaxDNA System (HMI) at 500MW BTPS, Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 8.69 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Up-gradation of GE IP (GE-Fanuc) make PLC system (HMI) installed at AHP, CPU plant, FOPH, FWPH and Mill Reject system at 2x500MW BTPS, Bhusawal. | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 1.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.3 | Up-gradation of Schneider PLC System at 2x500MW, BTPS, Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 2.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.4 | Procurement of Rotor assembly with blade set for PA and FD fan at 2 X 500 MW BTPS Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 18.18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Improvement of Loadability and Availability of Coal Handling Plant at BTPS, Bhusawal | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Scheme-1:-Design Engineering, Supply, Erection, commissioning, Extension of travel Length & Capacity Enhancement of coal yard with additional drive system of stacker reclaimer conveyor No. 110 at in coal handling Plant BTPS. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 14.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.2 | Scheme-2:-Design, Engineering, Rectification, Erection & Commissioning of Z point at Conveyor 108A & B at CHP-500MW. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 8.18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.3 | Scheme-3:-Design, Engineering and provision of material lifting arrangement for crusher floor, wobbler feeder & C-105 floor In CHP BTPS. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 1.88 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.4 | Scheme-4:-Structural up-gradation and rehabilitation of reversible yard conveyor in coal handling plant. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 4.21 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.5 | Scheme-5:-Design, Engineering, Erection and commissioning of Receiving and discharge chutes of wobbler feeders in CHP BTPS. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 6.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.6 | Scheme-6: Procurement of 3 Nos. of Bulldozers at BTPS, Bhusawal. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 7.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Performance Improvement of Coal Handling Plant at BTPS-U4 & 5, Bhusawal | MERC/CAPEX/MSPGCL/2024-25/0310 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Scheme-1: Revamping, Modification of Gravity take-up and Drive Augmentation of Bunkering conveyor in CHP BTPS | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 11.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.2 | Scheme-2: Revamping of coal diverting chutes in CHP 2x500 MW BTPS | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 5.73 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.3 | Scheme-3: Revamping and structural augmentation of Reversible feeder conveyors in CHP-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 1.77 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.4 | Scheme-4: Revamping and up-gradation of air & ventilation system in Coal Handling Plant-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 9.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.5 | Scheme-5: Revamping, Structural & drive up-gradation of conveyor-111 in CHP-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 3.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.6 | Scheme-6: Revamping and structural up-gradation of conveyor system in tunnel area in Coal Handling Plant-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 8.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.7 | Scheme-7: Erection & Commissioning of Travelling type coal chutes in CHP BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 8.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.8 | Scheme-8: Revamping of scoop cooling system installed in coal handling plant BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 4.98 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.9 | Scheme-9: Retrofitting and Up-gradation of Dewatering system in CHP-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 3.92 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Asset Transfer from Projects |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | SP Busduct Unit 4&5 |  | - | 0 | 0.30072 | 0.30072 | 0 | 0 | 0 |  |  | 0 | 0
0 | ESP,ID,FD,PA Fans &Other Boiler Auxiliaries |  | - | 0 | 1.0283 | 1.0283 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) DPR Yet to be Submitted to MERC |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2025-26 |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Up gradation of coal mill reject system, Procurement of Air heater baskets & spare Air heater gearbox at 2X500MW, Bhusawal TPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Work of Capacity enhancement, Engineering, modification, upgradation including spares and consumables and complete commissioning including operation and comprehensive maintenance for 12 months for coal mill reject handling system in Unit-4&5, 2X500MW, BTPS, Bhusawal |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Procurement of assembly of baskets & seals for Air Preheater of type 31.5 VIM 2000 (72° PA), in Unit-5 2x500MW, BTPS Bhusawal |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.3 | Procurement of APH Gearbox to improve availability and performance of Air preheaters at 2 x 500 MW Units, BTPS, Bhusawal. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Boiler Reliability & Availability improvement at 2x500MW, Bhusawal TPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Procurement & Replacement Of LTSH Coils for Unit - 4 & 5 (500MW) TPS, Bhusawal. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Procurement & Replacement Of Economiser Coils For Unit - 4 & 5 (500MW) TPS, Bhusawal |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Procurement of assembly of APH Baskets Unit-4 |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.4 | Procurement of APH Gearbox Unit-4&5 |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Various Turbine side reliability improvement schemes at 2x500MW, BTPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Reliability improvement of Atlas copco make (mode -ZR -500) |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Reliability improvement of HPCV Valve with procurment cone assy |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Reliability improvement of Alfa Laval make Portable COP |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.4 | Reliability improvement of Seal Oil System with procurement of various U Seal rings |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.5 | Reliability improvement of Unit-4 & 5 NDCT with replacement of PVC fills and allied work |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.6 | Upgradation of Chiller plant, GEHO pump house & OLTC PLC system. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | IB recommended scheme related (Civil and Electrical) |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Work of fabricating and erecting structural steel watch tower (10 Nos.) in major store, plant area, ash pipe line and ash bund area at BTPS, Deepnagar. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.2 | Work of construction of ladies frisking room for security section and visitors room near factory gate and providing at 2x500MW, BTPS, Deepnagar. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.3 | Work of dismantling and construction old weathered UCR compound wall on bhogawati riverside in 2x500 MW at BTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.4 | Construcion of RCC comppund wall from remote silo to pimpri sekam railway siding cabin at BTPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.5 | Installation of Highmast towers |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2026-27 |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgradation of Coal feeder weighing system and revamping of Boiler side pneumatic dampers system of Hot air, cold air, FD,PA and burner tilt at Bhusawal TPS 2x500W |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Upgradation of Coal feeder weighing system at Bhusawal TPS 2x500W |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Up-gradation of carbon monoxide analyzer in flue gas installed |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Up- Gradation of condition monitoring & analysis system for TSI of Main Turbine , TDBFP & BOP System 2x500 MW BTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.5 | Revamping of Boiler side pneumatic dampers system of Hot air, cold air, FD,PA and burner tilt at BTPS 2X500MW |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.6 | Procurement of various high pressure valves at 2x500 MW. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Schemes for Turbine side auxiliaries systems Performance & efficiency improvement schemes at 2X500MW, Bhusawal TPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement of BFP Booster Pump (FA-1B-75) complete assembly (04 Nos) at 500MW BTPS, Bhusawal. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Procurement of Vacuum Pump complete assembly with recirculation Pump (01 No) and Impeller assembly (2 Nos) at 500MW BTPS, Bhusawal. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Revamping, modification of outdoor ducting of Air ventilation system at 2x500MW BTPS, Bhusawal. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.4 | Performance improvement of compressors |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.5 | Centralized Water Management System at BTPS, Deepnagar, Bhusawal |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.6 | Revamping and upgradation of Forbes Marshal make Steam & Water Analysis System Installed at 2x500MW BTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Implementation of flexible operation solutions for technical minimum operation of 2x500MW, BTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Implementation of flexible operation solutions for technical minimum operation of 2x500MW, BTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2027-28 |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply,Installation and commissioning of Boiler performance and reliability improvement schemes at BTPS 2x500MW. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Procurement of M/s Torishima, Japan make, 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motors at BTPS 2x500MW. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Installation commissioning of Online DC Earth fault monitoring system at 220V DCDB at 500MW U-4&5. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.3 | Design, supply, erection, comms. Of ID VFD & AHP transformers for 2x500MW BTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.4 | Design,supply,installation and commissioning of Energy efficient System for illumination at BTPS 2x500MW. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.5 | Procurement of Main Gear unit assembly of electrical Actuators in 2x500MW BTPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.6 | Supply, erection, commissioning & site testing of 360V, 750 AH Station UPS Battery Sets along with accessories for Unit No.5 at BTPS 2x500MW. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.7 | Upgradation of EWLI system at Bhusawal TPS 2x500W |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Performance improvement of Bottom ash evacualtion system to reduce auxillary power consumption, water consumption & environmental pollution at 2X500MW, Bhusawal TPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Modification of latest design AR 200/550 Ash slurry pump assembly including auxillaries at AHP, 2x500MW, BTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Modification of single roll reversible clinker grinder system at AHP, 2x500MW, BTPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Modification of bottom ash & coarse ash slurry pipe line disposal system at AHP 2X500 MW BTPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Boiler Reliability & Availability improvement at 2x500MW, Bhusawal TPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement of Boiler Coils (CRH &HRH) at 2x500MW BTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Procurement of ID fan impeller with shaft at 2x500 MW BTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Procurement SH,RH,MS outlet valves with actuator and motor at 2x500 MW BTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | CHP Infrastructure Development Schemes |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Supply, installation and commissioning PLC system on a single platform to match with external aspect & process improvement at CHP 2x500MW BTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.2 | Supply, installation, retrofitting and commissioning of HT breaker at HT Switchgear in CHP 2x500MW BTPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.3 | Supply, installation, retrofitting and commissioning of LT breaker at LT Switchgear in CHP 2x500MW BTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.4 | Supply, Installation & Commissioning of Magnetic Separators at CHP 2x 500MW BTPS Deepnagar |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.5 | Supply, Installation & Commissioning Flameproof lighting at CHP 2x 500MW BTPS Deepnagar |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.6 | Supply, Installation & upgradation of HT /LT relay at CHP BTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Detail Project report of improvement of Unloading in Coal handling Plant BTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Procurement of 04 no of locomotives for Coal handling Plant BTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.2 | Design Supply Erection and Comission of Hour glass shape Coal diverting chutes with extra life wear resistant plates in CHP, BTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.3 | Design Supply Erection and Comission of Inverted Y Shape Coal diverting chutes with extra life wear resistant plates in CHP, BTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.4 | Design Supply Erection and Comission of coal diverting chutes with extra life wear resistant plates in CHP BTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.5 | Work of Revamping and structural up-gradation of conveyor 104A&B in Coal Handling Plant-BTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Supply and Installation of reliability improvement schemes for HT/LT switchgears and auxilliaries at BTPS 2x500MW. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Procurement of HT Motors of various ratings at 2x500MW. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.2 | Procurement of Dry type transformers of varoius ratings at 2x500MW. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.3 | Procurement of Inverter and converter trolleys of GEHO Pump at 2x500MW. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.4 | Procurement of Vacuum Contactors of various ratings for HT Switchgears at BTPS 2x500MW. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.5 | Supply, erection, commissioning & site testing of 360V, 750 AH Station UPS Battery Sets along with accessories for Unit No.4 at BTPS 2x500MW’. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.6 | Updragation of Sox-Nox analyzer,PM analyzer, ETP analyzer at BTPS 2X500MW. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.7 | Upgradation of O2 analyzer at BTPS 2X500MW |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.8 | Revamping & Upgradation Of Vibration Monitoring Rack From VM7 TO VM7B at BTPS 2X500MW |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.9 | Procurement & Installation of High Mast towers in various location in BTPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Renovation and Modification of Colony Electric Supply System to improve availability and reliability of supply system at BTPS Colony, Deepnagar |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.11 | Work of Overhauling repairs of U-5 350KW BCWP motor of M/s Torishima make at BTPS 2x500MW. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2028-29 |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | APH baskets with main drive Gear box and lub oil skids with motor at 2x500MW BTPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | APH baskets with main drive Gear box and lub oil skids with motor at 2x500MW BTPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Detail Project Report for Design, Engineering, Supply, Installation and commissioning of 1500TPH Stacker cum re-claimer in Coal Handling Plant-BTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Design, Engineering, Supply, Installation and commissioning of 1500TPH Stacker cum re-claimer in Coal Handling Plant-BTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Enhancement of Unloading & Stacking Capacity of CHP. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Design Supply errection & Comissioning of Open Wagon Tippler along with stacking and reclaiming yard conveyors at CHP stack yard. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2029-30 |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgradation rail track in CHP -BTPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Revamping and Upgradation of rail track from 52KG to 60KG in CHP-BTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Contract for modification of Wobbler feeder in CHP-2X500MW |  | - | 0 | 1.4733 | 1.4733 | 0 | 0 | 0 |  |  | 0 | 0
2 | Contract for Revamping of Apron Feeder in CHP-2X500MW |  | - | 0 | 2.3246 | 2.3246 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of double lip skirt sealing & tracking idler in CHP at 2x500MW, BTPS |  | - | 0 | 0.57025 | 0.57025 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, erection & commissioning of vibrating feeder in CHP at 2x500MW, BTPS |  | - | 0 | 0.57796 | 0.57796 | 0 | 0 | 0 |  |  | 0 | 0
5 | Coal chutes with extra life wear resistance plates in CHP at 2X500MW |  | - | 0 | 2.0319 | 2.0319 | 0 | 0 | 0 |  |  | 0 | 0
6 | Epoxy Painting upto all height to structural steel work in main plant boiler side area and CHP area |  | - | 0 | 5.8625 | 5.8625 | 0 | 0 | 0 |  |  | 0 | 0
7 | Rectification of Belt feeder & Gravity Take-up in CHP-2X500MW. |  | - | 0 | 1.6479 | 1.6479 | 0 | 0 | 0 |  |  | 0 | 0
8 | Coal diverting chutes in CHP at 2X500MW. |  | - | 0 | 2.2184 | 2.2184 | 0 | 0 | 0 |  |  | 0 | 0
9 | Supply of Conveyor Pulleys with Ceramic lagging at CHP-2X500MW, BTPS, Bhusawal |  | - | 0 | 0.58051 | 0.58051 | 0 | 0 | 0 |  |  | 0 | 0
10 | Non-DPR Project Report for Design, Supply,Erection & Commissioning of High Performance Energy Chain System for Side Arm Charger at 2x500 at CHP |  | - | 0 | 1.5015 | 1.5015 | 0 | 0 | 0 |  |  | 0 | 0
11 | Implementation of Energy Conservation Demonstration Project in buildings of BTPS 2x500MW |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Installation of Fire & Explosion Prevention system at Bhusawal 500MW Unit-4. |  | - | 0 | 2.4539 | 2.4539 | 0 | 0 | 0 |  |  | 0 | 0
13 | Fixtures & Fitting (10801) |  | - | 0 | 0.21334 | 0.21334 | 0 | 0 | 0 |  |  | 0 | 0
14 | Office equpment (10901) |  | - | 0 | 0.22996 | 0.22996 | 0 | 0 | 0 |  |  | 0 | 0
15 | 150 W & 40 W LED FIXTURES AT TG HOUSE BUILDING 2X500MW |  | - | 0 | 0.52807 | 0.27807 | 0.25 | 0 | 0 |  |  | 0 | 0.25
16 | JUMBO DEESERT AIR COOLERS FOR POWER TRANSFORERS |  | - | 0 | 0.10143 | 0.10143 | 0 | 0 | 0 |  |  | 0 | 0
17 | GEN ASSET (ALMIRAH,TABLE & CHAIR) (10801) |  | - | 0 | 0.23454 | 0.23454 | 0 | 0 | 0 |  |  | 0 | 0
18 | LAPTOP, 50 INCH TV,PRINTER,PROJECTOR,DESKTOP,UPS & ETS. (10901) |  | - | 0 | 0.55035 | 0.55035 | 0 | 0 | 0 |  |  | 0 | 0
19 | RESTAURANT EQUIP COMPOSTING MACHINE |  | - | 0 | 0.05049 | 0.05049 | 0 | 0 | 0 |  |  | 0 | 0
20 | OFFICE TABLE,STORGE RACK,FAN |  | - | 0 | 0.57869 | 0.57869 | 0 | 0 | 0 |  |  | 0 | 0
21 | CAMERAS |  | - | 0 | 0.038468 | 0.038468 | 0 | 0 | 0 |  |  | 0 | 0
22 | VELHALA ASH BUND RD WORK |  | - | 0 | 2.4645 | 2.4645 | 0 | 0 | 0 |  |  | 0 | 0
23 | CONCERETE ROAD FROM DIESEL PUMP TO 500MW FACTORY G |  | - | 0 | 0.98449 | 0.98449 | 0 | 0 | 0 |  |  | 0 | 0
24 | Admin Building |  | - | 0 | 0.05175 | 0 | 0.05175 | 0 | 0 |  |  | 0 | 0.05175
25 | Furniture & Fixture |  | - | 0 | 0 | 0 | 0 | 0.13712 | 0.13712 |  |  | 0.13712 | 0
26 | Office Equipment |  | - | 0 | 0 | 0 | 0 | 0.14424 | 0.14424 |  |  | 0.14424 | 0
27 | Furniture & Fixture |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28 | Office Equipment |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29 | Work of repairs of 350 KW BCWP-4B & BCWP-5B motor of M/s. Torishima make at BTPS 2x500 MW |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30 | ABC Powder Type and Foam Type Composite Fire Extinguisher |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31 | Withdrawal of capex from Project (LD - Passenger Lifts) |  | - | 0 | 0 | 0 | 0 | 0 | -0.13899 |  |  | -0.13899 | 0.13899
| Total |  |  |  | 184.319 | 184.0892 | 0.22981 | 14.829 | 13.9194 | 0 | 0 | 13.9194 | 1.1395
FY 2023-24
a) DPR Schemes
(i) Submitted to MERC
7 | Interconnection of 210 MW CHP to 500 MW CHP through Conveyors BC-02 & BC-03 having capacity of 500 TPH | MERC/CAPEX/20162017/00227 | 2016-05-24 | 24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Interconnection of 210 MW CHP to 500 MW CHP through Conveyors BC-02 & BC-03 having capacity of 500 TPH | MERC/CAPEX/20162017/00227 | 2016-05-24 | 22.73 | 19.1067 | 19.1067 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/00227 | 2016-05-24 | 1.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Stack management by procurement of Bulldozer & LOCO and CHP area schemes for performance & unloading improvement | MERC/CAPEX/20162017/01426 | 2017-02-02 | 9.9669 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement of Locomotive 800 HP (2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 4.9504 | 4.8261 | 4.8261 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Procurement of 2 No’s of Bulldozer Model D-155(2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 2.562 | 3.4747 | 3.4747 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.3 | Modification below primary crusher chutes 15A/B & Conv.02 | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.42975 | 0.38033 | 0.38033 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.4 | New helical gear box for various conveyors | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.79339 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.5 | Procurement of Elecon Make Ring Granulator Type TK-09-38B | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.53719 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.6 | Procurement of Elecon Make Ring Granulator Type TK6 32B Ring Granulator | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.33884 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.35537 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Construction of 1st raising of Ash bund from T.B.L. 258M to 264M at Bhusawal TPS | MERC/CAPEX/20172018/4267 | 2017-09-28 | 64.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Construction of 1st raising of Ash bund from T.B.L. 258M to 264M at Bhusawal TPS | MERC/CAPEX/20172018/4267 | 2017-09-28 | 64.22 | 64.4982 | 64.4982 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Augmentation of Ash Evacuation System & Procurement of BCW Pump Motors at Bhusawal & Khaperkheda TPS 500 MW Units | MERC/CAPEX/20172018/4782 | 2017-11-28 | 17.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Installation of standby Buffer Hopper parallel to existing pair of buffer hoppers | MERC/CAPEX/20172018/4782 | 2017-11-28 | 11.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | Installation of additional vacuum pump for every two passes, near to intermediate hopper. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.3 | Procurement of 02 Nos of M/s Torishima, Japan make, 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motors (without pump casing) with 02 lots of recommended Electrical & C&I spares for Bhusawal and Khaparkheda TPS 500MW. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 4.24 | 4.6696 | 4.6696 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.4 | Procurement of complete ACVF drive module comprising of 2 Nos. of Supply and 3 Nos. of Inverter modules for GEHO pumps | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0.95 | 0.92864 | 0.92864 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.5 | Supply, erection and commissioning of 24VDC, 100A Float & Float cum Boost Battery Charger with 325Ah Battery Bank for CWPH at BTPS 2x500 MW. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0.15 | 0.15788 | 0.15788 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Various schemes for renovation of colony at Bhusawal TPS | MERC/CAPEX/20172018/0221 | 2018-02-12 | 19.3341 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Renovation of staff quarters & related work at BTPS Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 7.021 | 5.4584 | 5.4584 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Colony Internal Roads at BTPS, Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 3.85 | 3.2501 | 3.2514 | -0.001329 | 0 | 0 |  |  | 0 | -0.001329 | 0 | 0
11.3 | Water supply , sanitary & drainage works at BTPS, Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 7.3 | 5.8361 | 5.8109 | 0.025229 | 0 | 0 |  |  | 0 | 0.025229 | 0 | 0
11.4 | Plinth protection to existing buildings at BTPS, Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 1.1631 | 0.91823 | 0.91823 | -2.2e-08 | 0 | 0 |  |  | 0 | -2.2e-08 | 0 | 0
12 | Pipeline from River Water Pump House (RWPH) to aquaduct over Bhogawati River and Other allied power house road works under DPR scheme at BTPS, Bhusawal | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 13.1172 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Providing supplying laying, jointing, testing and commissioning of 1650 mm Ø ID 8 mm thick M.S. pipeline for raw water supply from RWPH to aquaduct over Bhogawati river at, BTPS, Bhusawal. | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 7.257 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.2 | Construction of WBM and Bituminous road along inlet & outlet canals and concreate road along periphery of Major store at BTPS, Bhusawal. | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 4.22 | 3.1733 | 1.1932 | 1.9801 | 0.6572 | 2.6373 |  |  | 2.6373 | -2.7e-08 | 2.6373 | 0
12.3 | Work of construction of self-supporting steel roofing system for a major store godown shed of span 25M at BTPS, Deepnagar. | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 1.6402 | 0.27 | 1.6376 | -1.3676 | 0 | 0 |  |  | 0 | -1.3676 | 0 | 0
0 | IDC | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 0 | 0.059623 | 0 | 0.059623 | 0.089552 | 0.14918 |  |  | 0.14918 | 0 | 0 | 0.14918
13 | Supply, erection, commissioning & site testing of 220 V, 2035 AH, Station Battery Sets (4 Nos.) and 24 V, 2250 AH, SG/TG & BOP Battery Sets (8 Nos.) for U# 4 & 5 along with accessories at 2 x 500 MW BTPS, Bhusawal | MERC/CAPEX/2017-2018/1226 | 2018-08-10 | 11.59 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Supply, erection, commissioning & site testing of 220V, 2035 AH Station Battery Sets (02 Nos.) and 24V, 2250AH, SG/TG & BOP Battery Set (04 Nos.) along with accessories for Unit No.5 at BTPS 2x500MW. | MERC/CAPEX/2017-2018/1226 | 2018-08-10 | 5.795 | 6.374 | 6.374 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Supply, erection, commissioning & site testing of 220V, 2035 AH Station Battery Sets (02 Nos.) and 24V, 2250AH, SG/TG & BOP Battery Set (04 Nos.) along with accessories for Unit No.4 at BTPS 2x500MW. | MERC/CAPEX/2017-2018/1226 | 2018-08-10 | 5.795 | 6.3227 | 6.3227 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Flue Gas Desulphurization (FGD) System for 500 MW Units (Total 8 Nos) of MSPGCL | MERC/CAPEX/2020-2021/WFH/SBR/45 | 2021-02-05 | 869.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | Flue Gas Desulphurization (FGD) System for Bhusawal Unit 4-5 | MERC/CAPEX/2020-2021/WFH/SBR/45 | 2021-02-05 | 830.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/45 | 2021-02-05 | 39.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Procurement of two BFP Cartridges & one rotor of Turbine driven BFP & at 500MW BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 10.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Procurement of two BFP Cartridges at 500MW BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 3.84 | 2.24 | 2.24 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.2 | Procurement of one rotor of Turbine driven BFP at 500MW BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 6.46 | 7.6136 | 7.6136 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 0.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | CHP Improvement Schemes at 2X500MW, BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 21.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Revamping of Apron Feeder in CHP at 2X500MW, BTPS | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 4.67 | 4.6492 | 4.6492 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.2 | Design, engineering, manufacturing, supply, Erection and commissioning of short conveyor from stack yard to belt feeder 112 in CHP 2x500MW BTPS. | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 3.53 | 0 | 0 | 0 | 3.9648 | 3.9648 |  |  | 3.9648 | 0 | 3.53 | 0.43475
17.3 | Design, engineering, manufacturing, supply, Erection and commissioning of stone grappler at Wagon Tippler No.3 in CHP 2x500MW BTPS. | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 0.84 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.4 | Procurement of suspended magnets in CHP 2x500MW BTPS. | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 2.95 | 2.947 | 2.947 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.5 | Supply, Erection And Commissioning of Electro-Mechanical Drive to Apron Feeder at CHP 500MW | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 7.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 1.66 | 0 | 0 | 0 | 0.067524 | 0.067524 |  |  | 0.067524 | 0 | 0.067524 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Bhusawal: Unit 4-5 (3 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 1.9468 | 1.9458 | 0.001 | 0 | 0 |  |  | 0 | 0.001 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Bhusawal: Unit 4-5 | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 3.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Advance Multipurpose Fire Tender for BTPS 4-5 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 1.7765 | 1.7765 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Normal Multipurpose Fire Tender for BTPS 4-5 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.5 | 2.1847 | 2.1847 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 10.0654 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Bhusawal: Unit 4-5 | MERC/CAPEX/20172018/0177 | 2018-02-06 | 10.0654 | 8.7954 | 8.7937 | 0.0017614 | 0.38999 | 0.38999 |  |  | 0.38999 | 0.0017614 | 0.38999 | 0
18 | Procurement of assembly of baskets for Air Pre-heater of type 31.5 VIM 2000 (72° PA), Replacement of thermal insulation of Boiler, Ducts & Steam Pipelines and Coal Mill Gear Box in 2x500MW at BTPS, Bhusawal | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 14.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Procurement of assembly of baskets for Air Preheater of type 31.5 VIM 2000 (72° PA) for Unit-4&5 | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 5.53 | 8.411 | 8.411 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.2 | Replacement of thermal insulation of Boiler, Ducts & Steam Pipelines along with supply | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 3.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.3 | Supply of XRP-1043 coal mill gearbox spares in unit-4&5. | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 5.39 | 0 | 0 | 0 | 0 | 3.7044 |  |  | 3.7044 | -3.7044 | 3.7044 | 0
0 | IDC | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 0.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | Up-gradation of Operating System of Max DNA DCS, GE Fanuc PLC system & Schneider PLC system & Procurement of Critical Insurance spares for PA and FD fans System at 2 x 500 MW Units BTPS Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 31.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Up-gradation of Existing MaxDNA System (HMI) at 500MW BTPS, Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 8.69 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Up-gradation of GE IP (GE-Fanuc) make PLC system (HMI) installed at AHP, CPU plant, FOPH, FWPH and Mill Reject system at 2x500MW BTPS, Bhusawal. | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 1.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.3 | Up-gradation of Schneider PLC System at 2x500MW, BTPS, Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 2.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.4 | Procurement of Rotor assembly with blade set for PA and FD fan at 2 X 500 MW BTPS Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 18.18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Improvement of Loadability and Availability of Coal Handling Plant at BTPS, Bhusawal | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Scheme-1:-Design Engineering, Supply, Erection, commissioning, Extension of travel Length & Capacity Enhancement of coal yard with additional drive system of stacker reclaimer conveyor No. 110 at in coal handling Plant BTPS. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 14.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.2 | Scheme-2:-Design, Engineering, Rectification, Erection & Commissioning of Z point at Conveyor 108A & B at CHP-500MW. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 8.18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.3 | Scheme-3:-Design, Engineering and provision of material lifting arrangement for crusher floor, wobbler feeder & C-105 floor In CHP BTPS. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 1.88 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.4 | Scheme-4:-Structural up-gradation and rehabilitation of reversible yard conveyor in coal handling plant. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 4.21 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.5 | Scheme-5:-Design, Engineering, Erection and commissioning of Receiving and discharge chutes of wobbler feeders in CHP BTPS. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 6.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.6 | Scheme-6: Procurement of 3 Nos. of Bulldozers at BTPS, Bhusawal. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 7.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Performance Improvement of Coal Handling Plant at BTPS-U4 & 5, Bhusawal | MERC/CAPEX/MSPGCL/2024-25/0310 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Scheme-1: Revamping, Modification of Gravity take-up and Drive Augmentation of Bunkering conveyor in CHP BTPS | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 11.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.2 | Scheme-2: Revamping of coal diverting chutes in CHP 2x500 MW BTPS | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 5.73 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.3 | Scheme-3: Revamping and structural augmentation of Reversible feeder conveyors in CHP-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 1.77 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.4 | Scheme-4: Revamping and up-gradation of air & ventilation system in Coal Handling Plant-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 9.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.5 | Scheme-5: Revamping, Structural & drive up-gradation of conveyor-111 in CHP-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 3.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.6 | Scheme-6: Revamping and structural up-gradation of conveyor system in tunnel area in Coal Handling Plant-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 8.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.7 | Scheme-7: Erection & Commissioning of Travelling type coal chutes in CHP BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 8.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.8 | Scheme-8: Revamping of scoop cooling system installed in coal handling plant BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 4.98 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.9 | Scheme-9: Retrofitting and Up-gradation of Dewatering system in CHP-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 3.92 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Asset Transfer from Projects | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | SP Busduct Unit 4&5 | 0 | - | 0 | 0.30072 | 0.30072 | 0 | 0 | 0 |  |  | 0 | 0
0 | ESP,ID,FD,PA Fans &Other Boiler Auxiliaries | 0 | - | 0 | 1.0283 | 1.0283 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) DPR Yet to be Submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2025-26 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Up gradation of coal mill reject system, Procurement of Air heater baskets & spare Air heater gearbox at 2X500MW, Bhusawal TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Work of Capacity enhancement, Engineering, modification, upgradation including spares and consumables and complete commissioning including operation and comprehensive maintenance for 12 months for coal mill reject handling system in Unit-4&5, 2X500MW, BTPS, Bhusawal | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Procurement of assembly of baskets & seals for Air Preheater of type 31.5 VIM 2000 (72° PA), in Unit-5 2x500MW, BTPS Bhusawal | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.3 | Procurement of APH Gearbox to improve availability and performance of Air preheaters at 2 x 500 MW Units, BTPS, Bhusawal. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Boiler Reliability & Availability improvement at 2x500MW, Bhusawal TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Procurement & Replacement Of LTSH Coils for Unit - 4 & 5 (500MW) TPS, Bhusawal. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Procurement & Replacement Of Economiser Coils For Unit - 4 & 5 (500MW) TPS, Bhusawal | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Procurement of assembly of APH Baskets Unit-4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.4 | Procurement of APH Gearbox Unit-4&5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Various Turbine side reliability improvement schemes at 2x500MW, BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Reliability improvement of Atlas copco make (mode -ZR -500) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Reliability improvement of HPCV Valve with procurment cone assy | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Reliability improvement of Alfa Laval make Portable COP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.4 | Reliability improvement of Seal Oil System with procurement of various U Seal rings | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.5 | Reliability improvement of Unit-4 & 5 NDCT with replacement of PVC fills and allied work | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.6 | Upgradation of Chiller plant, GEHO pump house & OLTC PLC system. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | IB recommended scheme related (Civil and Electrical) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Work of fabricating and erecting structural steel watch tower (10 Nos.) in major store, plant area, ash pipe line and ash bund area at BTPS, Deepnagar. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.2 | Work of construction of ladies frisking room for security section and visitors room near factory gate and providing at 2x500MW, BTPS, Deepnagar. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.3 | Work of dismantling and construction old weathered UCR compound wall on bhogawati riverside in 2x500 MW at BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.4 | Construcion of RCC comppund wall from remote silo to pimpri sekam railway siding cabin at BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.5 | Installation of Highmast towers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2026-27 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgradation of Coal feeder weighing system and revamping of Boiler side pneumatic dampers system of Hot air, cold air, FD,PA and burner tilt at Bhusawal TPS 2x500W | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Upgradation of Coal feeder weighing system at Bhusawal TPS 2x500W | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Up-gradation of carbon monoxide analyzer in flue gas installed | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Up- Gradation of condition monitoring & analysis system for TSI of Main Turbine , TDBFP & BOP System 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.5 | Revamping of Boiler side pneumatic dampers system of Hot air, cold air, FD,PA and burner tilt at BTPS 2X500MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.6 | Procurement of various high pressure valves at 2x500 MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Schemes for Turbine side auxiliaries systems Performance & efficiency improvement schemes at 2X500MW, Bhusawal TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement of BFP Booster Pump (FA-1B-75) complete assembly (04 Nos) at 500MW BTPS, Bhusawal. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Procurement of Vacuum Pump complete assembly with recirculation Pump (01 No) and Impeller assembly (2 Nos) at 500MW BTPS, Bhusawal. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Revamping, modification of outdoor ducting of Air ventilation system at 2x500MW BTPS, Bhusawal. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.4 | Performance improvement of compressors | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.5 | Centralized Water Management System at BTPS, Deepnagar, Bhusawal | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.6 | Revamping and upgradation of Forbes Marshal make Steam & Water Analysis System Installed at 2x500MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Implementation of flexible operation solutions for technical minimum operation of 2x500MW, BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Implementation of flexible operation solutions for technical minimum operation of 2x500MW, BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2027-28 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply,Installation and commissioning of Boiler performance and reliability improvement schemes at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Procurement of M/s Torishima, Japan make, 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motors at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Installation commissioning of Online DC Earth fault monitoring system at 220V DCDB at 500MW U-4&5. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.3 | Design, supply, erection, comms. Of ID VFD & AHP transformers for 2x500MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.4 | Design,supply,installation and commissioning of Energy efficient System for illumination at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.5 | Procurement of Main Gear unit assembly of electrical Actuators in 2x500MW BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.6 | Supply, erection, commissioning & site testing of 360V, 750 AH Station UPS Battery Sets along with accessories for Unit No.5 at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.7 | Upgradation of EWLI system at Bhusawal TPS 2x500W | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Performance improvement of Bottom ash evacualtion system to reduce auxillary power consumption, water consumption & environmental pollution at 2X500MW, Bhusawal TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Modification of latest design AR 200/550 Ash slurry pump assembly including auxillaries at AHP, 2x500MW, BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Modification of single roll reversible clinker grinder system at AHP, 2x500MW, BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Modification of bottom ash & coarse ash slurry pipe line disposal system at AHP 2X500 MW BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Boiler Reliability & Availability improvement at 2x500MW, Bhusawal TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement of Boiler Coils (CRH &HRH) at 2x500MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Procurement of ID fan impeller with shaft at 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Procurement SH,RH,MS outlet valves with actuator and motor at 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | CHP Infrastructure Development Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Supply, installation and commissioning PLC system on a single platform to match with external aspect & process improvement at CHP 2x500MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.2 | Supply, installation, retrofitting and commissioning of HT breaker at HT Switchgear in CHP 2x500MW BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.3 | Supply, installation, retrofitting and commissioning of LT breaker at LT Switchgear in CHP 2x500MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.4 | Supply, Installation & Commissioning of Magnetic Separators at CHP 2x 500MW BTPS Deepnagar | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.5 | Supply, Installation & Commissioning Flameproof lighting at CHP 2x 500MW BTPS Deepnagar | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.6 | Supply, Installation & upgradation of HT /LT relay at CHP BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Detail Project report of improvement of Unloading in Coal handling Plant BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Procurement of 04 no of locomotives for Coal handling Plant BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.2 | Design Supply Erection and Comission of Hour glass shape Coal diverting chutes with extra life wear resistant plates in CHP, BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.3 | Design Supply Erection and Comission of Inverted Y Shape Coal diverting chutes with extra life wear resistant plates in CHP, BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.4 | Design Supply Erection and Comission of coal diverting chutes with extra life wear resistant plates in CHP BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.5 | Work of Revamping and structural up-gradation of conveyor 104A&B in Coal Handling Plant-BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Supply and Installation of reliability improvement schemes for HT/LT switchgears and auxilliaries at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Procurement of HT Motors of various ratings at 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.2 | Procurement of Dry type transformers of varoius ratings at 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.3 | Procurement of Inverter and converter trolleys of GEHO Pump at 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.4 | Procurement of Vacuum Contactors of various ratings for HT Switchgears at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.5 | Supply, erection, commissioning & site testing of 360V, 750 AH Station UPS Battery Sets along with accessories for Unit No.4 at BTPS 2x500MW’. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.6 | Updragation of Sox-Nox analyzer,PM analyzer, ETP analyzer at BTPS 2X500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.7 | Upgradation of O2 analyzer at BTPS 2X500MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.8 | Revamping & Upgradation Of Vibration Monitoring Rack From VM7 TO VM7B at BTPS 2X500MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.9 | Procurement & Installation of High Mast towers in various location in BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Renovation and Modification of Colony Electric Supply System to improve availability and reliability of supply system at BTPS Colony, Deepnagar | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.11 | Work of Overhauling repairs of U-5 350KW BCWP motor of M/s Torishima make at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2028-29 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | APH baskets with main drive Gear box and lub oil skids with motor at 2x500MW BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | APH baskets with main drive Gear box and lub oil skids with motor at 2x500MW BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Detail Project Report for Design, Engineering, Supply, Installation and commissioning of 1500TPH Stacker cum re-claimer in Coal Handling Plant-BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Design, Engineering, Supply, Installation and commissioning of 1500TPH Stacker cum re-claimer in Coal Handling Plant-BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Enhancement of Unloading & Stacking Capacity of CHP. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Design Supply errection & Comissioning of Open Wagon Tippler along with stacking and reclaiming yard conveyors at CHP stack yard. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2029-30 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgradation rail track in CHP -BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Revamping and Upgradation of rail track from 52KG to 60KG in CHP-BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Contract for modification of Wobbler feeder in CHP-2X500MW | 0 | - | 0 | 1.4733 | 1.4733 | 0 | 0 | 0 |  |  | 0 | 0
2 | Contract for Revamping of Apron Feeder in CHP-2X500MW | 0 | - | 0 | 2.3246 | 2.3246 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of double lip skirt sealing & tracking idler in CHP at 2x500MW, BTPS | 0 | - | 0 | 0.57025 | 0.57025 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, erection & commissioning of vibrating feeder in CHP at 2x500MW, BTPS | 0 | - | 0 | 0.57796 | 0.57796 | 0 | 0 | 0 |  |  | 0 | 0
5 | Coal chutes with extra life wear resistance plates in CHP at 2X500MW | 0 | - | 0 | 2.0319 | 2.0319 | 0 | 0 | 0 |  |  | 0 | 0
6 | Epoxy Painting upto all height to structural steel work in main plant boiler side area and CHP area | 0 | - | 0 | 5.8625 | 5.8625 | 0 | 0 | 0 |  |  | 0 | 0
7 | Rectification of Belt feeder & Gravity Take-up in CHP-2X500MW. | 0 | - | 0 | 1.6479 | 1.6479 | 0 | 0 | 0 |  |  | 0 | 0
8 | Coal diverting chutes in CHP at 2X500MW. | 0 | - | 0 | 2.2184 | 2.2184 | 0 | 0 | 0 |  |  | 0 | 0
9 | Supply of Conveyor Pulleys with Ceramic lagging at CHP-2X500MW, BTPS, Bhusawal | 0 | - | 0 | 0.58051 | 0.58051 | 0 | 0 | 0 |  |  | 0 | 0
10 | Non-DPR Project Report for Design, Supply,Erection & Commissioning of High Performance Energy Chain System for Side Arm Charger at 2x500 at CHP | 0 | - | 0 | 1.5015 | 1.5015 | 0 | 0 | 0 |  |  | 0 | 0
11 | Implementation of Energy Conservation Demonstration Project in buildings of BTPS 2x500MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Installation of Fire & Explosion Prevention system at Bhusawal 500MW Unit-4. | 0 | - | 0 | 2.4539 | 2.4539 | 0 | 0 | 0 |  |  | 0 | 0
13 | Fixtures & Fitting (10801) | 0 | - | 0 | 0.21334 | 0.21334 | 0 | 0 | 0 |  |  | 0 | 0
14 | Office equpment (10901) | 0 | - | 0 | 0.22996 | 0.22996 | 0 | 0 | 0 |  |  | 0 | 0
15 | 150 W & 40 W LED FIXTURES AT TG HOUSE BUILDING 2X500MW | 0 | - | 0 | 0.52807 | 0.27807 | 0.25 | 0 | 0 |  |  | 0 | 0.25
16 | JUMBO DEESERT AIR COOLERS FOR POWER TRANSFORERS | 0 | - | 0 | 0.10143 | 0.10143 | 0 | 0 | 0 |  |  | 0 | 0
17 | GEN ASSET (ALMIRAH,TABLE & CHAIR) (10801) | 0 | - | 0 | 0.23454 | 0.23454 | 0 | 0 | 0 |  |  | 0 | 0
18 | LAPTOP, 50 INCH TV,PRINTER,PROJECTOR,DESKTOP,UPS & ETS. (10901) | 0 | - | 0 | 0.55035 | 0.55035 | 0 | 0 | 0 |  |  | 0 | 0
19 | RESTAURANT EQUIP COMPOSTING MACHINE | 0 | - | 0 | 0.05049 | 0.05049 | 0 | 0 | 0 |  |  | 0
20 | OFFICE TABLE,STORGE RACK,FAN | 0 | - | 0 | 0.57869 | 0.57869 | 0 | 0 | 0 |  |  | 0
21 | CAMERAS | 0 | - | 0 | 0.038468 | 0.038468 | 0 | 0 | 0 |  |  | 0
22 | VELHALA ASH BUND RD WORK | 0 | - | 0 | 2.4645 | 2.4645 | 0 | 0 | 0 |  |  | 0
23 | CONCERETE ROAD FROM DIESEL PUMP TO 500MW FACTORY G | 0 | - | 0 | 0.98449 | 0.98449 | 0 | 0 | 0 |  |  | 0
24 | Admin Building | 0 | - | 0 | 0.05175 | 0 | 0.05175 | 0 | 0 |  |  | 0
25 | Furniture & Fixture | 0 | - | 0 | 0.13712 | 0.13712 | 0 | 0 | 0 |  |  | 0
26 | Office Equipment | 0 | - | 0 | 0.14424 | 0.14424 | 0 | 0 | 0 |  |  | 0
27 | Furniture & Fixture | 0 | - | 0 | 0 | 0 | 0 | 0.073968 | 0.073968 |  |  | 0.073968
28 | Office Equipment | 0 | - | 0 | 0 | 0 | 0 | 0.15891 | 0.15891 |  |  | 0.15891
29 | Work of repairs of 350 KW BCWP-4B & BCWP-5B motor of M/s. Torishima make at BTPS 2x500 MW | 0 | - | 0 | 0 | 0 | 0 | 4.8465 | 4.8465 |  |  | 4.8465
30 | ABC Powder Type and Foam Type Composite Fire Extinguisher | 0 | - | 0 | 0 | 0 | 0 | 0.58548 | 0.58548 |  |  | 0.58548
31 | Withdrawal of capex from Project (LD - Passenger Lifts) | 0 | - | 0 | 0 | -0.13899 | 0.13899 | 0 | 0 |  |  | 0
| Total |  |  |  | 199.148 | 198.0086 | 1.1395 | 10.8339 | 16.578 | 0 | 0 | 16.578 | -4.7953
FY 2024-25
a) DPR Schemes
(i) Submitted to MERC
7 | Interconnection of 210 MW CHP to 500 MW CHP through Conveyors BC-02 & BC-03 having capacity of 500 TPH | MERC/CAPEX/20162017/00227 | 2016-05-24 | 24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Interconnection of 210 MW CHP to 500 MW CHP through Conveyors BC-02 & BC-03 having capacity of 500 TPH | MERC/CAPEX/20162017/00227 | 2016-05-24 | 22.73 | 19.1067 | 19.1067 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/00227 | 2016-05-24 | 1.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Stack management by procurement of Bulldozer & LOCO and CHP area schemes for performance & unloading improvement | MERC/CAPEX/20162017/01426 | 2017-02-02 | 9.9669 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement of Locomotive 800 HP (2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 4.9504 | 4.8261 | 4.8261 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Procurement of 2 No’s of Bulldozer Model D-155(2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 2.562 | 3.4747 | 3.4747 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.3 | Modification below primary crusher chutes 15A/B & Conv.02 | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.42975 | 0.38033 | 0.38033 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.4 | New helical gear box for various conveyors | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.79339 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.5 | Procurement of Elecon Make Ring Granulator Type TK-09-38B | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.53719 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.6 | Procurement of Elecon Make Ring Granulator Type TK6 32B Ring Granulator | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.33884 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.35537 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Construction of 1st raising of Ash bund from T.B.L. 258M to 264M at Bhusawal TPS | MERC/CAPEX/20172018/4267 | 2017-09-28 | 64.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Construction of 1st raising of Ash bund from T.B.L. 258M to 264M at Bhusawal TPS | MERC/CAPEX/20172018/4267 | 2017-09-28 | 64.22 | 64.4982 | 64.4982 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Augmentation of Ash Evacuation System & Procurement of BCW Pump Motors at Bhusawal & Khaperkheda TPS 500 MW Units | MERC/CAPEX/20172018/4782 | 2017-11-28 | 17.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Installation of standby Buffer Hopper parallel to existing pair of buffer hoppers | MERC/CAPEX/20172018/4782 | 2017-11-28 | 11.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | Installation of additional vacuum pump for every two passes, near to intermediate hopper. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.3 | Procurement of 02 Nos of M/s Torishima, Japan make, 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motors (without pump casing) with 02 lots of recommended Electrical & C&I spares for Bhusawal and Khaparkheda TPS 500MW. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 4.24 | 4.6696 | 4.6696 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.4 | Procurement of complete ACVF drive module comprising of 2 Nos. of Supply and 3 Nos. of Inverter modules for GEHO pumps | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0.95 | 0.92864 | 0.92864 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.5 | Supply, erection and commissioning of 24VDC, 100A Float & Float cum Boost Battery Charger with 325Ah Battery Bank for CWPH at BTPS 2x500 MW. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0.15 | 0.15788 | 0.15788 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Various schemes for renovation of colony at Bhusawal TPS | MERC/CAPEX/20172018/0221 | 2018-02-12 | 19.3341 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Renovation of staff quarters & related work at BTPS Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 7.021 | 5.4584 | 5.4584 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Colony Internal Roads at BTPS, Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 3.85 | 3.2501 | 3.2514 | -0.001329 | 0 | 0 |  |  | 0 | -0.001329 | 0 | 0
11.3 | Water supply , sanitary & drainage works at BTPS, Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 7.3 | 5.8361 | 5.8109 | 0.025229 | 0 | 0 |  |  | 0 | 0.025229 | 0 | 0
11.4 | Plinth protection to existing buildings at BTPS, Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 1.1631 | 0.91823 | 0.91823 | -2.2e-08 | 0 | 0 |  |  | 0 | -2.2e-08 | 0 | 0
12 | Pipeline from River Water Pump House (RWPH) to aquaduct over Bhogawati River and Other allied power house road works under DPR scheme at BTPS, Bhusawal | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 13.1172 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Providing supplying laying, jointing, testing and commissioning of 1650 mm Ø ID 8 mm thick M.S. pipeline for raw water supply from RWPH to aquaduct over Bhogawati river at, BTPS, Bhusawal. | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 7.257 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.2 | Construction of WBM and Bituminous road along inlet & outlet canals and concreate road along periphery of Major store at BTPS, Bhusawal. | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 4.22 | 3.8305 | 3.8305 | -2.7e-08 | 0 | 0 |  |  | 0 | -2.7e-08 | 0 | 0
12.3 | Work of construction of self-supporting steel roofing system for a major store godown shed of span 25M at BTPS, Deepnagar. | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 1.6402 | 0.27 | 1.6376 | -1.3676 | 0 | 0 |  |  | 0 | -1.3676 | 0 | 0
0 | IDC | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 0 | 0.14918 | 0.14918 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Supply, erection, commissioning & site testing of 220 V, 2035 AH, Station Battery Sets (4 Nos.) and 24 V, 2250 AH, SG/TG & BOP Battery Sets (8 Nos.) for U# 4 & 5 along with accessories at 2 x 500 MW BTPS, Bhusawal | MERC/CAPEX/2017-2018/1226 | 2018-08-10 | 11.59 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Supply, erection, commissioning & site testing of 220V, 2035 AH Station Battery Sets (02 Nos.) and 24V, 2250AH, SG/TG & BOP Battery Set (04 Nos.) along with accessories for Unit No.5 at BTPS 2x500MW. | MERC/CAPEX/2017-2018/1226 | 2018-08-10 | 5.795 | 6.374 | 6.374 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Supply, erection, commissioning & site testing of 220V, 2035 AH Station Battery Sets (02 Nos.) and 24V, 2250AH, SG/TG & BOP Battery Set (04 Nos.) along with accessories for Unit No.4 at BTPS 2x500MW. | MERC/CAPEX/2017-2018/1226 | 2018-08-10 | 5.795 | 6.3227 | 6.3227 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Flue Gas Desulphurization (FGD) System for 500 MW Units (Total 8 Nos) of MSPGCL | MERC/CAPEX/2020-2021/WFH/SBR/45 | 2021-02-05 | 869.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | Flue Gas Desulphurization (FGD) System for Bhusawal Unit 4-5 | MERC/CAPEX/2020-2021/WFH/SBR/45 | 2021-02-05 | 830.4 | 0 | 0 | 0 | 127.37 | 127.37 |  |  | 127.37 | 0 | 127.37 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/45 | 2021-02-05 | 39.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Procurement of two BFP Cartridges & one rotor of Turbine driven BFP & at 500MW BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 10.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Procurement of two BFP Cartridges at 500MW BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 3.84 | 2.24 | 2.24 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.2 | Procurement of one rotor of Turbine driven BFP at 500MW BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 6.46 | 7.6136 | 7.6136 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 0.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | CHP Improvement Schemes at 2X500MW, BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 21.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Revamping of Apron Feeder in CHP at 2X500MW, BTPS | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 4.67 | 4.6492 | 4.6492 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.2 | Design, engineering, manufacturing, supply, Erection and commissioning of short conveyor from stack yard to belt feeder 112 in CHP 2x500MW BTPS. | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 3.53 | 3.9648 | 3.9648 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.3 | Design, engineering, manufacturing, supply, Erection and commissioning of stone grappler at Wagon Tippler No.3 in CHP 2x500MW BTPS. | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 0.84 | 0 | 0 | 0 | 0.84 | 0.84 |  |  | 0.84 | 0 | 0.84 | 0
17.4 | Procurement of suspended magnets in CHP 2x500MW BTPS. | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 2.95 | 2.947 | 2.947 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.5 | Supply, Erection And Commissioning of Electro-Mechanical Drive to Apron Feeder at CHP 500MW | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 7.57 | 0 | 0 | 0 | 7.57 | 0 |  |  | 0 | 7.57 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 1.66 | 0.067524 | 0.067524 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Bhusawal: Unit 4-5 (3 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 1.9468 | 1.9458 | 0.001 | 0 | 0 |  |  | 0 | 0.001 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Bhusawal: Unit 4-5 | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 3.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Advance Multipurpose Fire Tender for BTPS 4-5 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 1.7765 | 1.7765 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Normal Multipurpose Fire Tender for BTPS 4-5 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.5 | 2.1847 | 2.1847 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 10.0654 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Bhusawal: Unit 4-5 | MERC/CAPEX/20172018/0177 | 2018-02-06 | 10.0654 | 9.1854 | 9.1837 | 0.0017614 | 0 | 0 |  |  | 0 | 0.0017614 | 0 | 0
18 | Procurement of assembly of baskets for Air Pre-heater of type 31.5 VIM 2000 (72° PA), Replacement of thermal insulation of Boiler, Ducts & Steam Pipelines and Coal Mill Gear Box in 2x500MW at BTPS, Bhusawal | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 14.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Procurement of assembly of baskets for Air Preheater of type 31.5 VIM 2000 (72° PA) for Unit-4&5 | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 5.53 | 8.411 | 8.411 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.2 | Replacement of thermal insulation of Boiler, Ducts & Steam Pipelines along with supply | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 3.52 | 0 | 0 | 0 | 3.52 | 2 |  |  | 2 | 1.52 | 2 | 0
18.3 | Supply of XRP-1043 coal mill gearbox spares in unit-4&5. | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 5.39 | 0 | 3.7044 | -3.7044 | 3.7044 | 0 |  |  | 0 | -2.6e-08 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 0.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | Up-gradation of Operating System of Max DNA DCS, GE Fanuc PLC system & Schneider PLC system & Procurement of Critical Insurance spares for PA and FD fans System at 2 x 500 MW Units BTPS Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 31.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Up-gradation of Existing MaxDNA System (HMI) at 500MW BTPS, Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 8.69 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Up-gradation of GE IP (GE-Fanuc) make PLC system (HMI) installed at AHP, CPU plant, FOPH, FWPH and Mill Reject system at 2x500MW BTPS, Bhusawal. | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 1.35 | 0 | 0 | 0 | 1.2948 | 1.3538 |  |  | 1.3538 | -0.059 | 1.35 | 0.003801
19.3 | Up-gradation of Schneider PLC System at 2x500MW, BTPS, Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 2.33 | 0 | 0 | 0 | 2.3093 | 2.3093 |  |  | 2.3093 | 0 | 2.3093 | 0
19.4 | Procurement of Rotor assembly with blade set for PA and FD fan at 2 X 500 MW BTPS Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 18.18 | 0 | 0 | 0 | 16.16 | 16.16 |  |  | 16.16 | 0 | 16.16 | 0
0 | IDC | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Improvement of Loadability and Availability of Coal Handling Plant at BTPS, Bhusawal | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Scheme-1:-Design Engineering, Supply, Erection, commissioning, Extension of travel Length & Capacity Enhancement of coal yard with additional drive system of stacker reclaimer conveyor No. 110 at in coal handling Plant BTPS. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 14.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.2 | Scheme-2:-Design, Engineering, Rectification, Erection & Commissioning of Z point at Conveyor 108A & B at CHP-500MW. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 8.18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.3 | Scheme-3:-Design, Engineering and provision of material lifting arrangement for crusher floor, wobbler feeder & C-105 floor In CHP BTPS. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 1.88 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.4 | Scheme-4:-Structural up-gradation and rehabilitation of reversible yard conveyor in coal handling plant. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 4.21 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.5 | Scheme-5:-Design, Engineering, Erection and commissioning of Receiving and discharge chutes of wobbler feeders in CHP BTPS. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 6.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.6 | Scheme-6: Procurement of 3 Nos. of Bulldozers at BTPS, Bhusawal. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 7.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Performance Improvement of Coal Handling Plant at BTPS-U4 & 5, Bhusawal | MERC/CAPEX/MSPGCL/2024-25/0310 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Scheme-1: Revamping, Modification of Gravity take-up and Drive Augmentation of Bunkering conveyor in CHP BTPS | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 11.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.2 | Scheme-2: Revamping of coal diverting chutes in CHP 2x500 MW BTPS | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 5.73 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.3 | Scheme-3: Revamping and structural augmentation of Reversible feeder conveyors in CHP-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 1.77 | 0 | 0 | 0 | 1.75 | 1.75 |  |  | 1.75 | 0
21.4 | Scheme-4: Revamping and up-gradation of air & ventilation system in Coal Handling Plant-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 9.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.5 | Scheme-5: Revamping, Structural & drive up-gradation of conveyor-111 in CHP-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 3.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.6 | Scheme-6: Revamping and structural up-gradation of conveyor system in tunnel area in Coal Handling Plant-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 8.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.7 | Scheme-7: Erection & Commissioning of Travelling type coal chutes in CHP BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 8.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.8 | Scheme-8: Revamping of scoop cooling system installed in coal handling plant BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 4.98 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.9 | Scheme-9: Retrofitting and Up-gradation of Dewatering system in CHP-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 3.92 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Asset Transfer from Projects | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | SP Busduct Unit 4&5 | 0 | - | 0 | 0.30072 | 0.30072 | 0 | 0 | 0 |  |  | 0 | 0
0 | ESP,ID,FD,PA Fans &Other Boiler Auxiliaries | 0 | - | 0 | 1.0283 | 1.0283 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) DPR Yet to be Submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2025-26 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Up gradation of coal mill reject system, Procurement of Air heater baskets & spare Air heater gearbox at 2X500MW, Bhusawal TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Work of Capacity enhancement, Engineering, modification, upgradation including spares and consumables and complete commissioning including operation and comprehensive maintenance for 12 months for coal mill reject handling system in Unit-4&5, 2X500MW, BTPS, Bhusawal | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Procurement of assembly of baskets & seals for Air Preheater of type 31.5 VIM 2000 (72° PA), in Unit-5 2x500MW, BTPS Bhusawal | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.3 | Procurement of APH Gearbox to improve availability and performance of Air preheaters at 2 x 500 MW Units, BTPS, Bhusawal. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Boiler Reliability & Availability improvement at 2x500MW, Bhusawal TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Procurement & Replacement Of LTSH Coils for Unit - 4 & 5 (500MW) TPS, Bhusawal. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Procurement & Replacement Of Economiser Coils For Unit - 4 & 5 (500MW) TPS, Bhusawal | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Procurement of assembly of APH Baskets Unit-4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.4 | Procurement of APH Gearbox Unit-4&5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Various Turbine side reliability improvement schemes at 2x500MW, BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Reliability improvement of Atlas copco make (mode -ZR -500) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Reliability improvement of HPCV Valve with procurment cone assy | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Reliability improvement of Alfa Laval make Portable COP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.4 | Reliability improvement of Seal Oil System with procurement of various U Seal rings | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.5 | Reliability improvement of Unit-4 & 5 NDCT with replacement of PVC fills and allied work | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.6 | Upgradation of Chiller plant, GEHO pump house & OLTC PLC system. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | IB recommended scheme related (Civil and Electrical) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Work of fabricating and erecting structural steel watch tower (10 Nos.) in major store, plant area, ash pipe line and ash bund area at BTPS, Deepnagar. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.2 | Work of construction of ladies frisking room for security section and visitors room near factory gate and providing at 2x500MW, BTPS, Deepnagar. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.3 | Work of dismantling and construction old weathered UCR compound wall on bhogawati riverside in 2x500 MW at BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.4 | Construcion of RCC comppund wall from remote silo to pimpri sekam railway siding cabin at BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.5 | Installation of Highmast towers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2026-27 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgradation of Coal feeder weighing system and revamping of Boiler side pneumatic dampers system of Hot air, cold air, FD,PA and burner tilt at Bhusawal TPS 2x500W | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Upgradation of Coal feeder weighing system at Bhusawal TPS 2x500W | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Up-gradation of carbon monoxide analyzer in flue gas installed | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Up- Gradation of condition monitoring & analysis system for TSI of Main Turbine , TDBFP & BOP System 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.5 | Revamping of Boiler side pneumatic dampers system of Hot air, cold air, FD,PA and burner tilt at BTPS 2X500MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.6 | Procurement of various high pressure valves at 2x500 MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Schemes for Turbine side auxiliaries systems Performance & efficiency improvement schemes at 2X500MW, Bhusawal TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement of BFP Booster Pump (FA-1B-75) complete assembly (04 Nos) at 500MW BTPS, Bhusawal. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Procurement of Vacuum Pump complete assembly with recirculation Pump (01 No) and Impeller assembly (2 Nos) at 500MW BTPS, Bhusawal. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Revamping, modification of outdoor ducting of Air ventilation system at 2x500MW BTPS, Bhusawal. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.4 | Performance improvement of compressors | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.5 | Centralized Water Management System at BTPS, Deepnagar, Bhusawal | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.6 | Revamping and upgradation of Forbes Marshal make Steam & Water Analysis System Installed at 2x500MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Implementation of flexible operation solutions for technical minimum operation of 2x500MW, BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Implementation of flexible operation solutions for technical minimum operation of 2x500MW, BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2027-28 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply,Installation and commissioning of Boiler performance and reliability improvement schemes at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Procurement of M/s Torishima, Japan make, 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motors at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Installation commissioning of Online DC Earth fault monitoring system at 220V DCDB at 500MW U-4&5. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.3 | Design, supply, erection, comms. Of ID VFD & AHP transformers for 2x500MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.4 | Design,supply,installation and commissioning of Energy efficient System for illumination at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.5 | Procurement of Main Gear unit assembly of electrical Actuators in 2x500MW BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.6 | Supply, erection, commissioning & site testing of 360V, 750 AH Station UPS Battery Sets along with accessories for Unit No.5 at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.7 | Upgradation of EWLI system at Bhusawal TPS 2x500W | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Performance improvement of Bottom ash evacualtion system to reduce auxillary power consumption, water consumption & environmental pollution at 2X500MW, Bhusawal TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Modification of latest design AR 200/550 Ash slurry pump assembly including auxillaries at AHP, 2x500MW, BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Modification of single roll reversible clinker grinder system at AHP, 2x500MW, BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Modification of bottom ash & coarse ash slurry pipe line disposal system at AHP 2X500 MW BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Boiler Reliability & Availability improvement at 2x500MW, Bhusawal TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement of Boiler Coils (CRH &HRH) at 2x500MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Procurement of ID fan impeller with shaft at 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Procurement SH,RH,MS outlet valves with actuator and motor at 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | CHP Infrastructure Development Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Supply, installation and commissioning PLC system on a single platform to match with external aspect & process improvement at CHP 2x500MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.2 | Supply, installation, retrofitting and commissioning of HT breaker at HT Switchgear in CHP 2x500MW BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.3 | Supply, installation, retrofitting and commissioning of LT breaker at LT Switchgear in CHP 2x500MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.4 | Supply, Installation & Commissioning of Magnetic Separators at CHP 2x 500MW BTPS Deepnagar | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.5 | Supply, Installation & Commissioning Flameproof lighting at CHP 2x 500MW BTPS Deepnagar | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.6 | Supply, Installation & upgradation of HT /LT relay at CHP BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Detail Project report of improvement of Unloading in Coal handling Plant BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Procurement of 04 no of locomotives for Coal handling Plant BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.2 | Design Supply Erection and Comission of Hour glass shape Coal diverting chutes with extra life wear resistant plates in CHP, BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.3 | Design Supply Erection and Comission of Inverted Y Shape Coal diverting chutes with extra life wear resistant plates in CHP, BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.4 | Design Supply Erection and Comission of coal diverting chutes with extra life wear resistant plates in CHP BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.5 | Work of Revamping and structural up-gradation of conveyor 104A&B in Coal Handling Plant-BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Supply and Installation of reliability improvement schemes for HT/LT switchgears and auxilliaries at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Procurement of HT Motors of various ratings at 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.2 | Procurement of Dry type transformers of varoius ratings at 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.3 | Procurement of Inverter and converter trolleys of GEHO Pump at 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.4 | Procurement of Vacuum Contactors of various ratings for HT Switchgears at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.5 | Supply, erection, commissioning & site testing of 360V, 750 AH Station UPS Battery Sets along with accessories for Unit No.4 at BTPS 2x500MW’. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.6 | Updragation of Sox-Nox analyzer,PM analyzer, ETP analyzer at BTPS 2X500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.7 | Upgradation of O2 analyzer at BTPS 2X500MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.8 | Revamping & Upgradation Of Vibration Monitoring Rack From VM7 TO VM7B at BTPS 2X500MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.9 | Procurement & Installation of High Mast towers in various location in BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Renovation and Modification of Colony Electric Supply System to improve availability and reliability of supply system at BTPS Colony, Deepnagar | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.11 | Work of Overhauling repairs of U-5 350KW BCWP motor of M/s Torishima make at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2028-29 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | APH baskets with main drive Gear box and lub oil skids with motor at 2x500MW BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | APH baskets with main drive Gear box and lub oil skids with motor at 2x500MW BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Detail Project Report for Design, Engineering, Supply, Installation and commissioning of 1500TPH Stacker cum re-claimer in Coal Handling Plant-BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Design, Engineering, Supply, Installation and commissioning of 1500TPH Stacker cum re-claimer in Coal Handling Plant-BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Enhancement of Unloading & Stacking Capacity of CHP. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Design Supply errection & Comissioning of Open Wagon Tippler along with stacking and reclaiming yard conveyors at CHP stack yard. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2029-30 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgradation rail track in CHP -BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Revamping and Upgradation of rail track from 52KG to 60KG in CHP-BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Contract for modification of Wobbler feeder in CHP-2X500MW | 0 | - | 0 | 1.4733 | 1.4733 | 0 | 0 | 0 |  |  | 0 | 0
2 | Contract for Revamping of Apron Feeder in CHP-2X500MW | 0 | - | 0 | 2.3246 | 2.3246 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of double lip skirt sealing & tracking idler in CHP at 2x500MW, BTPS | 0 | - | 0 | 0.57025 | 0.57025 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, erection & commissioning of vibrating feeder in CHP at 2x500MW, BTPS | 0 | - | 0 | 0.57796 | 0.57796 | 0 | 0 | 0 |  |  | 0 | 0
5 | Coal chutes with extra life wear resistance plates in CHP at 2X500MW | 0 | - | 0 | 2.0319 | 2.0319 | 0 | 0 | 0 |  |  | 0 | 0
6 | Epoxy Painting upto all height to structural steel work in main plant boiler side area and CHP area | 0 | - | 0 | 5.8625 | 5.8625 | 0 | 0 | 0 |  |  | 0 | 0
7 | Rectification of Belt feeder & Gravity Take-up in CHP-2X500MW. | 0 | - | 0 | 1.6479 | 1.6479 | 0 | 0 | 0 |  |  | 0 | 0
8 | Coal diverting chutes in CHP at 2X500MW. | 0 | - | 0 | 2.2184 | 2.2184 | 0 | 0 | 0 |  |  | 0 | 0
9 | Supply of Conveyor Pulleys with Ceramic lagging at CHP-2X500MW, BTPS, Bhusawal | 0 | - | 0 | 0.58051 | 0.58051 | 0 | 0 | 0 |  |  | 0 | 0
10 | Non-DPR Project Report for Design, Supply,Erection & Commissioning of High Performance Energy Chain System for Side Arm Charger at 2x500 at CHP | 0 | - | 0 | 1.5015 | 1.5015 | 0 | 0 | 0 |  |  | 0 | 0
11 | Implementation of Energy Conservation Demonstration Project in buildings of BTPS 2x500MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Installation of Fire & Explosion Prevention system at Bhusawal 500MW Unit-4. | 0 | - | 0 | 2.4539 | 2.4539 | 0 | 0 | 0 |  |  | 0 | 0
13 | Fixtures & Fitting (10801) | 0 | - | 0 | 0.21334 | 0.21334 | 0 | 0 | 0 |  |  | 0 | 0
14 | Office equpment (10901) | 0 | - | 0 | 0.22996 | 0.22996 | 0 | 0 | 0 |  |  | 0 | 0
15 | 150 W & 40 W LED FIXTURES AT TG HOUSE BUILDING 2X500MW | 0 | - | 0 | 0.52807 | 0.27807 | 0.25 | 0 | 0 |  |  | 0 | 0.25
16 | JUMBO DEESERT AIR COOLERS FOR POWER TRANSFORERS | 0 | - | 0 | 0.10143 | 0.10143 | 0 | 0 | 0 |  |  | 0 | 0
17 | GEN ASSET (ALMIRAH,TABLE & CHAIR) (10801) | 0 | - | 0 | 0.23454 | 0.23454 | 0 | 0 | 0 |  |  | 0 | 0
18 | LAPTOP, 50 INCH TV,PRINTER,PROJECTOR,DESKTOP,UPS & ETS. (10901) | 0 | - | 0 | 0.55035 | 0.55035 | 0 | 0 | 0 |  |  | 0 | 0
19 | RESTAURANT EQUIP COMPOSTING MACHINE | 0 | - | 0 | 0.05049 | 0.05049 | 0 | 0 | 0 |  |  | 0
20 | OFFICE TABLE,STORGE RACK,FAN | 0 | - | 0 | 0.57869 | 0.57869 | 0 | 0 | 0 |  |  | 0
21 | CAMERAS | 0 | - | 0 | 0.038468 | 0.038468 | 0 | 0 | 0 |  |  | 0
22 | VELHALA ASH BUND RD WORK | 0 | - | 0 | 2.4645 | 2.4645 | 0 | 0 | 0 |  |  | 0
23 | CONCERETE ROAD FROM DIESEL PUMP TO 500MW FACTORY G | 0 | - | 0 | 0.98449 | 0.98449 | 0 | 0 | 0 |  |  | 0
24 | Admin Building | 0 | - | 0 | 0.05175 | 0 | 0.05175 | 0 | 0 |  |  | 0
25 | Furniture & Fixture | 0 | - | 0 | 0.13712 | 0.13712 | 0 | 0 | 0 |  |  | 0
26 | Office Equipment | 0 | - | 0 | 0.14424 | 0.14424 | 0 | 0 | 0 |  |  | 0
27 | Furniture & Fixture | 0 | - | 0 | 0.073968 | 0.073968 | 0 | 0 | 0 |  |  | 0
28 | Office Equipment | 0 | - | 0 | 0.15891 | 0.15891 | 0 | 0 | 0 |  |  | 0
29 | Work of repairs of 350 KW BCWP-4B & BCWP-5B motor of M/s. Torishima make at BTPS 2x500 MW | 0 | - | 0 | 4.8465 | 4.8465 | 0 | 0 | 0 |  |  | 0
30 | ABC Powder Type and Foam Type Composite Fire Extinguisher | 0 | - | 0 | 0.58548 | 0.58548 | 0 | 0 | 0 |  |  | 0
31 | Withdrawal of capex from Project (LD - Passenger Lifts) | 0 | - | 0 | 0 | -0.13899 | 0.13899 | 0 | 0 |  |  | 0
| Total |  |  |  | 209.982 | 214.5865 | -4.6046 | 164.5185 | 151.7831 | 0 | 0 | 151.7831 | 7.94
FY 2025-26
a) DPR Schemes
(i) Submitted to MERC
7 | Interconnection of 210 MW CHP to 500 MW CHP through Conveyors BC-02 & BC-03 having capacity of 500 TPH | MERC/CAPEX/20162017/00227 | 2016-05-24 | 24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Interconnection of 210 MW CHP to 500 MW CHP through Conveyors BC-02 & BC-03 having capacity of 500 TPH | MERC/CAPEX/20162017/00227 | 2016-05-24 | 22.73 | 19.1067 | 19.1067 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/00227 | 2016-05-24 | 1.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Stack management by procurement of Bulldozer & LOCO and CHP area schemes for performance & unloading improvement | MERC/CAPEX/20162017/01426 | 2017-02-02 | 9.9669 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement of Locomotive 800 HP (2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 4.9504 | 4.8261 | 4.8261 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Procurement of 2 No’s of Bulldozer Model D-155(2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 2.562 | 3.4747 | 3.4747 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.3 | Modification below primary crusher chutes 15A/B & Conv.02 | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.42975 | 0.38033 | 0.38033 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.4 | New helical gear box for various conveyors | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.79339 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.5 | Procurement of Elecon Make Ring Granulator Type TK-09-38B | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.53719 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.6 | Procurement of Elecon Make Ring Granulator Type TK6 32B Ring Granulator | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.33884 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.35537 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Construction of 1st raising of Ash bund from T.B.L. 258M to 264M at Bhusawal TPS | MERC/CAPEX/20172018/4267 | 2017-09-28 | 64.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Construction of 1st raising of Ash bund from T.B.L. 258M to 264M at Bhusawal TPS | MERC/CAPEX/20172018/4267 | 2017-09-28 | 64.22 | 64.4982 | 64.4982 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Augmentation of Ash Evacuation System & Procurement of BCW Pump Motors at Bhusawal & Khaperkheda TPS 500 MW Units | MERC/CAPEX/20172018/4782 | 2017-11-28 | 17.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Installation of standby Buffer Hopper parallel to existing pair of buffer hoppers | MERC/CAPEX/20172018/4782 | 2017-11-28 | 11.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | Installation of additional vacuum pump for every two passes, near to intermediate hopper. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.3 | Procurement of 02 Nos of M/s Torishima, Japan make, 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motors (without pump casing) with 02 lots of recommended Electrical & C&I spares for Bhusawal and Khaparkheda TPS 500MW. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 4.24 | 4.6696 | 4.6696 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.4 | Procurement of complete ACVF drive module comprising of 2 Nos. of Supply and 3 Nos. of Inverter modules for GEHO pumps | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0.95 | 0.92864 | 0.92864 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.5 | Supply, erection and commissioning of 24VDC, 100A Float & Float cum Boost Battery Charger with 325Ah Battery Bank for CWPH at BTPS 2x500 MW. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0.15 | 0.15788 | 0.15788 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Various schemes for renovation of colony at Bhusawal TPS | MERC/CAPEX/20172018/0221 | 2018-02-12 | 19.3341 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Renovation of staff quarters & related work at BTPS Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 7.021 | 5.4584 | 5.4584 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Colony Internal Roads at BTPS, Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 3.85 | 3.2501 | 3.2514 | -0.001329 | 0 | 0 |  |  | 0 | -0.001329 | 0 | 0
11.3 | Water supply , sanitary & drainage works at BTPS, Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 7.3 | 5.8361 | 5.8109 | 0.025229 | 0 | 0 |  |  | 0 | 0.025229 | 0 | 0
11.4 | Plinth protection to existing buildings at BTPS, Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 1.1631 | 0.91823 | 0.91823 | -2.2e-08 | 0 | 0 |  |  | 0 | -2.2e-08 | 0 | 0
12 | Pipeline from River Water Pump House (RWPH) to aquaduct over Bhogawati River and Other allied power house road works under DPR scheme at BTPS, Bhusawal | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 13.1172 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Providing supplying laying, jointing, testing and commissioning of 1650 mm Ø ID 8 mm thick M.S. pipeline for raw water supply from RWPH to aquaduct over Bhogawati river at, BTPS, Bhusawal. | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 7.257 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.2 | Construction of WBM and Bituminous road along inlet & outlet canals and concreate road along periphery of Major store at BTPS, Bhusawal. | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 4.22 | 3.8305 | 3.8305 | -2.7e-08 | 0 | 0 |  |  | 0 | -2.7e-08 | 0 | 0
12.3 | Work of construction of self-supporting steel roofing system for a major store godown shed of span 25M at BTPS, Deepnagar. | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 1.6402 | 0.27 | 1.6376 | -1.3676 | 0 | 0 |  |  | 0 | -1.3676 | 0 | 0
0 | IDC | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 0 | 0.14918 | 0.14918 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Supply, erection, commissioning & site testing of 220 V, 2035 AH, Station Battery Sets (4 Nos.) and 24 V, 2250 AH, SG/TG & BOP Battery Sets (8 Nos.) for U# 4 & 5 along with accessories at 2 x 500 MW BTPS, Bhusawal | MERC/CAPEX/2017-2018/1226 | 2018-08-10 | 11.59 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Supply, erection, commissioning & site testing of 220V, 2035 AH Station Battery Sets (02 Nos.) and 24V, 2250AH, SG/TG & BOP Battery Set (04 Nos.) along with accessories for Unit No.5 at BTPS 2x500MW. | MERC/CAPEX/2017-2018/1226 | 2018-08-10 | 5.795 | 6.374 | 6.374 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Supply, erection, commissioning & site testing of 220V, 2035 AH Station Battery Sets (02 Nos.) and 24V, 2250AH, SG/TG & BOP Battery Set (04 Nos.) along with accessories for Unit No.4 at BTPS 2x500MW. | MERC/CAPEX/2017-2018/1226 | 2018-08-10 | 5.795 | 6.3227 | 6.3227 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Flue Gas Desulphurization (FGD) System for 500 MW Units (Total 8 Nos) of MSPGCL | MERC/CAPEX/2020-2021/WFH/SBR/45 | 2021-02-05 | 869.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | Flue Gas Desulphurization (FGD) System for Bhusawal Unit 4-5 | MERC/CAPEX/2020-2021/WFH/SBR/45 | 2021-02-05 | 830.4 | 127.37 | 127.37 | 0 | 467.04 | 467.04 |  |  | 467.04 | 0 | 467.04 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/45 | 2021-02-05 | 39.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Procurement of two BFP Cartridges & one rotor of Turbine driven BFP & at 500MW BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 10.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Procurement of two BFP Cartridges at 500MW BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 3.84 | 2.24 | 2.24 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.2 | Procurement of one rotor of Turbine driven BFP at 500MW BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 6.46 | 7.6136 | 7.6136 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 0.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | CHP Improvement Schemes at 2X500MW, BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 21.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Revamping of Apron Feeder in CHP at 2X500MW, BTPS | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 4.67 | 4.6492 | 4.6492 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.2 | Design, engineering, manufacturing, supply, Erection and commissioning of short conveyor from stack yard to belt feeder 112 in CHP 2x500MW BTPS. | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 3.53 | 3.9648 | 3.9648 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.3 | Design, engineering, manufacturing, supply, Erection and commissioning of stone grappler at Wagon Tippler No.3 in CHP 2x500MW BTPS. | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 0.84 | 0.84 | 0.84 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.4 | Procurement of suspended magnets in CHP 2x500MW BTPS. | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 2.95 | 2.947 | 2.947 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.5 | Supply, Erection And Commissioning of Electro-Mechanical Drive to Apron Feeder at CHP 500MW | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 7.57 | 7.57 | 0 | 7.57 | 0 | 0 |  |  | 0 | 7.57 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 1.66 | 0.067524 | 0.067524 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Bhusawal: Unit 4-5 (3 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 1.9468 | 1.9458 | 0.001 | 0 | 0 |  |  | 0 | 0.001 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Bhusawal: Unit 4-5 | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 3.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Advance Multipurpose Fire Tender for BTPS 4-5 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 1.7765 | 1.7765 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Normal Multipurpose Fire Tender for BTPS 4-5 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.5 | 2.1847 | 2.1847 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 10.0654 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Bhusawal: Unit 4-5 | MERC/CAPEX/20172018/0177 | 2018-02-06 | 10.0654 | 9.1854 | 9.1837 | 0.0017614 | 0 | 0 |  |  | 0 | 0.0017614 | 0 | 0
18 | Procurement of assembly of baskets for Air Pre-heater of type 31.5 VIM 2000 (72° PA), Replacement of thermal insulation of Boiler, Ducts & Steam Pipelines and Coal Mill Gear Box in 2x500MW at BTPS, Bhusawal | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 14.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Procurement of assembly of baskets for Air Preheater of type 31.5 VIM 2000 (72° PA) for Unit-4&5 | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 5.53 | 8.411 | 8.411 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.2 | Replacement of thermal insulation of Boiler, Ducts & Steam Pipelines along with supply | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 3.52 | 3.52 | 2 | 1.52 | 0 | 0 |  |  | 0 | 1.52 | 0 | 0
18.3 | Supply of XRP-1043 coal mill gearbox spares in unit-4&5. | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 5.39 | 3.7044 | 3.7044 | -2.6e-08 | 0 | 0 |  |  | 0 | -2.6e-08 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 0.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | Up-gradation of Operating System of Max DNA DCS, GE Fanuc PLC system & Schneider PLC system & Procurement of Critical Insurance spares for PA and FD fans System at 2 x 500 MW Units BTPS Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 31.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Up-gradation of Existing MaxDNA System (HMI) at 500MW BTPS, Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 8.69 | 0 | 0 | 0 | 8.69 | 8.69 |  |  | 8.69 | 0 | 8.69 | 0
19.2 | Up-gradation of GE IP (GE-Fanuc) make PLC system (HMI) installed at AHP, CPU plant, FOPH, FWPH and Mill Reject system at 2x500MW BTPS, Bhusawal. | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 1.35 | 1.2948 | 1.3538 | -0.059 | 0 | 0 |  |  | 0 | -0.059 | 0 | 0
19.3 | Up-gradation of Schneider PLC System at 2x500MW, BTPS, Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 2.33 | 2.3093 | 2.3093 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.4 | Procurement of Rotor assembly with blade set for PA and FD fan at 2 X 500 MW BTPS Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 18.18 | 16.16 | 16.16 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 0.5 | 0 | 0 | 0 | 0.5 | 0.5 |  |  | 0.5 | 0 | 0.5 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Improvement of Loadability and Availability of Coal Handling Plant at BTPS, Bhusawal | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Scheme-1:-Design Engineering, Supply, Erection, commissioning, Extension of travel Length & Capacity Enhancement of coal yard with additional drive system of stacker reclaimer conveyor No. 110 at in coal handling Plant BTPS. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 14.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.2 | Scheme-2:-Design, Engineering, Rectification, Erection & Commissioning of Z point at Conveyor 108A & B at CHP-500MW. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 8.18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.3 | Scheme-3:-Design, Engineering and provision of material lifting arrangement for crusher floor, wobbler feeder & C-105 floor In CHP BTPS. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 1.88 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.4 | Scheme-4:-Structural up-gradation and rehabilitation of reversible yard conveyor in coal handling plant. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 4.21 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.5 | Scheme-5:-Design, Engineering, Erection and commissioning of Receiving and discharge chutes of wobbler feeders in CHP BTPS. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 6.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.6 | Scheme-6: Procurement of 3 Nos. of Bulldozers at BTPS, Bhusawal. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 7.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Performance Improvement of Coal Handling Plant at BTPS-U4 & 5, Bhusawal | MERC/CAPEX/MSPGCL/2024-25/0310 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Scheme-1: Revamping, Modification of Gravity take-up and Drive Augmentation of Bunkering conveyor in CHP BTPS | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 11.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.2 | Scheme-2: Revamping of coal diverting chutes in CHP 2x500 MW BTPS | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 5.73 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.3 | Scheme-3: Revamping and structural augmentation of Reversible feeder conveyors in CHP-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 1.77 | 1.75 | 1.75 | 0 | 0 | 0 |  |  | 0 | 0
21.4 | Scheme-4: Revamping and up-gradation of air & ventilation system in Coal Handling Plant-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 9.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.5 | Scheme-5: Revamping, Structural & drive up-gradation of conveyor-111 in CHP-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 3.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.6 | Scheme-6: Revamping and structural up-gradation of conveyor system in tunnel area in Coal Handling Plant-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 8.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.7 | Scheme-7: Erection & Commissioning of Travelling type coal chutes in CHP BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 8.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.8 | Scheme-8: Revamping of scoop cooling system installed in coal handling plant BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 4.98 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.9 | Scheme-9: Retrofitting and Up-gradation of Dewatering system in CHP-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 3.92 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Asset Transfer from Projects | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | SP Busduct Unit 4&5 | 0 | - | 0 | 0.30072 | 0.30072 | 0 | 0 | 0 |  |  | 0 | 0
0 | ESP,ID,FD,PA Fans &Other Boiler Auxiliaries | 0 | - | 0 | 1.0283 | 1.0283 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) DPR Yet to be Submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2025-26 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Up gradation of coal mill reject system, Procurement of Air heater baskets & spare Air heater gearbox at 2X500MW, Bhusawal TPS | 0 | - | 0 | 0 | 0 | 0 | 31.75 | 0 |  |  | 0 | 31.75
1.1 | Work of Capacity enhancement, Engineering, modification, upgradation including spares and consumables and complete commissioning including operation and comprehensive maintenance for 12 months for coal mill reject handling system in Unit-4&5, 2X500MW, BTPS, Bhusawal | 0 | - | 0 | 0 | 0 | 0 | 15.05 | 15.05 |  |  | 15.05 | 0
1.2 | Procurement of assembly of baskets & seals for Air Preheater of type 31.5 VIM 2000 (72° PA), in Unit-5 2x500MW, BTPS Bhusawal | 0 | - | 0 | 0 | 0 | 0 | 7.45 | 7.45 |  |  | 7.45 | 0
1.3 | Procurement of APH Gearbox to improve availability and performance of Air preheaters at 2 x 500 MW Units, BTPS, Bhusawal. | 0 | - | 0 | 0 | 0 | 0 | 9.25 | 9.25 |  |  | 9.25 | 0
2 | Boiler Reliability & Availability improvement at 2x500MW, Bhusawal TPS. | 0 | - | 0 | 0 | 0 | 0 | 83.63 | 0 |  |  | 0 | 83.63
2.1 | Procurement & Replacement Of LTSH Coils for Unit - 4 & 5 (500MW) TPS, Bhusawal. | 0 | - | 0 | 0 | 0 | 0 | 19.11 | 19.11 |  |  | 19.11 | 0
2.2 | Procurement & Replacement Of Economiser Coils For Unit - 4 & 5 (500MW) TPS, Bhusawal | 0 | - | 0 | 0 | 0 | 0 | 47.6 | 47.6 |  |  | 47.6 | 0
2.3 | Procurement of assembly of APH Baskets Unit-4 | 0 | - | 0 | 0 | 0 | 0 | 7.55 | 7.55 |  |  | 7.55 | 0
2.4 | Procurement of APH Gearbox Unit-4&5 | 0 | - | 0 | 0 | 0 | 0 | 9.37 | 9.37 |  |  | 9.37 | 0
3 | Various Turbine side reliability improvement schemes at 2x500MW, BTPS | 0 | - | 0 | 0 | 0 | 0 | 41.4 | 0 |  |  | 0 | 41.4
3.1 | Reliability improvement of Atlas copco make (mode -ZR -500) | 0 | - | 0 | 0 | 0 | 0 | 2.4 | 2.4 |  |  | 2.4 | 0
3.2 | Reliability improvement of HPCV Valve with procurment cone assy | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
3.3 | Reliability improvement of Alfa Laval make Portable COP | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
3.4 | Reliability improvement of Seal Oil System with procurement of various U Seal rings | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
3.5 | Reliability improvement of Unit-4 & 5 NDCT with replacement of PVC fills and allied work | 0 | - | 0 | 0 | 0 | 0 | 30 | 30 |  |  | 30 | 0
3.6 | Upgradation of Chiller plant, GEHO pump house & OLTC PLC system. | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
4 | IB recommended scheme related (Civil and Electrical) | 0 | - | 0 | 0 | 0 | 0 | 10.76 | 0 |  |  | 0 | 10.76
4.1 | Work of fabricating and erecting structural steel watch tower (10 Nos.) in major store, plant area, ash pipe line and ash bund area at BTPS, Deepnagar. | 0 | - | 0 | 0 | 0 | 0 | 0.86 | 0.86 |  |  | 0.86 | 0
4.2 | Work of construction of ladies frisking room for security section and visitors room near factory gate and providing at 2x500MW, BTPS, Deepnagar. | 0 | - | 0 | 0 | 0 | 0 | 0.43 | 0.43 |  |  | 0.43 | 0
4.3 | Work of dismantling and construction old weathered UCR compound wall on bhogawati riverside in 2x500 MW at BTPS. | 0 | - | 0 | 0 | 0 | 0 | 3.29 | 3.29 |  |  | 3.29 | 0
4.4 | Construcion of RCC comppund wall from remote silo to pimpri sekam railway siding cabin at BTPS | 0 | - | 0 | 0 | 0 | 0 | 2.02 | 2.02 |  |  | 2.02 | 0
4.5 | Installation of Highmast towers | 0 | - | 0 | 0 | 0 | 0 | 4.16 | 4.16 |  |  | 4.16 | 0
0 | FY 2026-27 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgradation of Coal feeder weighing system and revamping of Boiler side pneumatic dampers system of Hot air, cold air, FD,PA and burner tilt at Bhusawal TPS 2x500W | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Upgradation of Coal feeder weighing system at Bhusawal TPS 2x500W | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Up-gradation of carbon monoxide analyzer in flue gas installed | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Up- Gradation of condition monitoring & analysis system for TSI of Main Turbine , TDBFP & BOP System 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.5 | Revamping of Boiler side pneumatic dampers system of Hot air, cold air, FD,PA and burner tilt at BTPS 2X500MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.6 | Procurement of various high pressure valves at 2x500 MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Schemes for Turbine side auxiliaries systems Performance & efficiency improvement schemes at 2X500MW, Bhusawal TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement of BFP Booster Pump (FA-1B-75) complete assembly (04 Nos) at 500MW BTPS, Bhusawal. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Procurement of Vacuum Pump complete assembly with recirculation Pump (01 No) and Impeller assembly (2 Nos) at 500MW BTPS, Bhusawal. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Revamping, modification of outdoor ducting of Air ventilation system at 2x500MW BTPS, Bhusawal. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.4 | Performance improvement of compressors | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.5 | Centralized Water Management System at BTPS, Deepnagar, Bhusawal | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.6 | Revamping and upgradation of Forbes Marshal make Steam & Water Analysis System Installed at 2x500MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Implementation of flexible operation solutions for technical minimum operation of 2x500MW, BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Implementation of flexible operation solutions for technical minimum operation of 2x500MW, BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2027-28 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply,Installation and commissioning of Boiler performance and reliability improvement schemes at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Procurement of M/s Torishima, Japan make, 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motors at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Installation commissioning of Online DC Earth fault monitoring system at 220V DCDB at 500MW U-4&5. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.3 | Design, supply, erection, comms. Of ID VFD & AHP transformers for 2x500MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.4 | Design,supply,installation and commissioning of Energy efficient System for illumination at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.5 | Procurement of Main Gear unit assembly of electrical Actuators in 2x500MW BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.6 | Supply, erection, commissioning & site testing of 360V, 750 AH Station UPS Battery Sets along with accessories for Unit No.5 at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.7 | Upgradation of EWLI system at Bhusawal TPS 2x500W | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Performance improvement of Bottom ash evacualtion system to reduce auxillary power consumption, water consumption & environmental pollution at 2X500MW, Bhusawal TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Modification of latest design AR 200/550 Ash slurry pump assembly including auxillaries at AHP, 2x500MW, BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Modification of single roll reversible clinker grinder system at AHP, 2x500MW, BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Modification of bottom ash & coarse ash slurry pipe line disposal system at AHP 2X500 MW BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Boiler Reliability & Availability improvement at 2x500MW, Bhusawal TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement of Boiler Coils (CRH &HRH) at 2x500MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Procurement of ID fan impeller with shaft at 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Procurement SH,RH,MS outlet valves with actuator and motor at 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | CHP Infrastructure Development Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Supply, installation and commissioning PLC system on a single platform to match with external aspect & process improvement at CHP 2x500MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.2 | Supply, installation, retrofitting and commissioning of HT breaker at HT Switchgear in CHP 2x500MW BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.3 | Supply, installation, retrofitting and commissioning of LT breaker at LT Switchgear in CHP 2x500MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.4 | Supply, Installation & Commissioning of Magnetic Separators at CHP 2x 500MW BTPS Deepnagar | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.5 | Supply, Installation & Commissioning Flameproof lighting at CHP 2x 500MW BTPS Deepnagar | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.6 | Supply, Installation & upgradation of HT /LT relay at CHP BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Detail Project report of improvement of Unloading in Coal handling Plant BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Procurement of 04 no of locomotives for Coal handling Plant BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.2 | Design Supply Erection and Comission of Hour glass shape Coal diverting chutes with extra life wear resistant plates in CHP, BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.3 | Design Supply Erection and Comission of Inverted Y Shape Coal diverting chutes with extra life wear resistant plates in CHP, BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.4 | Design Supply Erection and Comission of coal diverting chutes with extra life wear resistant plates in CHP BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.5 | Work of Revamping and structural up-gradation of conveyor 104A&B in Coal Handling Plant-BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Supply and Installation of reliability improvement schemes for HT/LT switchgears and auxilliaries at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Procurement of HT Motors of various ratings at 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.2 | Procurement of Dry type transformers of varoius ratings at 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.3 | Procurement of Inverter and converter trolleys of GEHO Pump at 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.4 | Procurement of Vacuum Contactors of various ratings for HT Switchgears at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.5 | Supply, erection, commissioning & site testing of 360V, 750 AH Station UPS Battery Sets along with accessories for Unit No.4 at BTPS 2x500MW’. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.6 | Updragation of Sox-Nox analyzer,PM analyzer, ETP analyzer at BTPS 2X500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.7 | Upgradation of O2 analyzer at BTPS 2X500MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.8 | Revamping & Upgradation Of Vibration Monitoring Rack From VM7 TO VM7B at BTPS 2X500MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.9 | Procurement & Installation of High Mast towers in various location in BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Renovation and Modification of Colony Electric Supply System to improve availability and reliability of supply system at BTPS Colony, Deepnagar | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.11 | Work of Overhauling repairs of U-5 350KW BCWP motor of M/s Torishima make at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2028-29 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | APH baskets with main drive Gear box and lub oil skids with motor at 2x500MW BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | APH baskets with main drive Gear box and lub oil skids with motor at 2x500MW BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Detail Project Report for Design, Engineering, Supply, Installation and commissioning of 1500TPH Stacker cum re-claimer in Coal Handling Plant-BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Design, Engineering, Supply, Installation and commissioning of 1500TPH Stacker cum re-claimer in Coal Handling Plant-BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Enhancement of Unloading & Stacking Capacity of CHP. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Design Supply errection & Comissioning of Open Wagon Tippler along with stacking and reclaiming yard conveyors at CHP stack yard. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2029-30 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgradation rail track in CHP -BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Revamping and Upgradation of rail track from 52KG to 60KG in CHP-BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Contract for modification of Wobbler feeder in CHP-2X500MW | 0 | - | 0 | 1.4733 | 1.4733 | 0 | 0 | 0 |  |  | 0 | 0
2 | Contract for Revamping of Apron Feeder in CHP-2X500MW | 0 | - | 0 | 2.3246 | 2.3246 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of double lip skirt sealing & tracking idler in CHP at 2x500MW, BTPS | 0 | - | 0 | 0.57025 | 0.57025 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, erection & commissioning of vibrating feeder in CHP at 2x500MW, BTPS | 0 | - | 0 | 0.57796 | 0.57796 | 0 | 0 | 0 |  |  | 0 | 0
5 | Coal chutes with extra life wear resistance plates in CHP at 2X500MW | 0 | - | 0 | 2.0319 | 2.0319 | 0 | 0 | 0 |  |  | 0 | 0
6 | Epoxy Painting upto all height to structural steel work in main plant boiler side area and CHP area | 0 | - | 0 | 5.8625 | 5.8625 | 0 | 0 | 0 |  |  | 0 | 0
7 | Rectification of Belt feeder & Gravity Take-up in CHP-2X500MW. | 0 | - | 0 | 1.6479 | 1.6479 | 0 | 0 | 0 |  |  | 0 | 0
8 | Coal diverting chutes in CHP at 2X500MW. | 0 | - | 0 | 2.2184 | 2.2184 | 0 | 0 | 0 |  |  | 0 | 0
9 | Supply of Conveyor Pulleys with Ceramic lagging at CHP-2X500MW, BTPS, Bhusawal | 0 | - | 0 | 0.58051 | 0.58051 | 0 | 0 | 0 |  |  | 0 | 0
10 | Non-DPR Project Report for Design, Supply,Erection & Commissioning of High Performance Energy Chain System for Side Arm Charger at 2x500 at CHP | 0 | - | 0 | 1.5015 | 1.5015 | 0 | 0 | 0 |  |  | 0 | 0
11 | Implementation of Energy Conservation Demonstration Project in buildings of BTPS 2x500MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Installation of Fire & Explosion Prevention system at Bhusawal 500MW Unit-4. | 0 | - | 0 | 2.4539 | 2.4539 | 0 | 0 | 0 |  |  | 0 | 0
13 | Fixtures & Fitting (10801) | 0 | - | 0 | 0.21334 | 0.21334 | 0 | 0 | 0 |  |  | 0 | 0
14 | Office equpment (10901) | 0 | - | 0 | 0.22996 | 0.22996 | 0 | 0 | 0 |  |  | 0 | 0
15 | 150 W & 40 W LED FIXTURES AT TG HOUSE BUILDING 2X500MW | 0 | - | 0 | 0.52807 | 0.27807 | 0.25 | 0 | 0 |  |  | 0 | 0.25
16 | JUMBO DEESERT AIR COOLERS FOR POWER TRANSFORERS | 0 | - | 0 | 0.10143 | 0.10143 | 0 | 0 | 0 |  |  | 0 | 0
17 | GEN ASSET (ALMIRAH,TABLE & CHAIR) (10801) | 0 | - | 0 | 0.23454 | 0.23454 | 0 | 0 | 0 |  |  | 0 | 0
18 | LAPTOP, 50 INCH TV,PRINTER,PROJECTOR,DESKTOP,UPS & ETS. (10901) | 0 | - | 0 | 0.55035 | 0.55035 | 0 | 0 | 0 |  |  | 0 | 0
19 | RESTAURANT EQUIP COMPOSTING MACHINE | 0 | - | 0 | 0.05049 | 0.05049 | 0 | 0 | 0 |  |  | 0
20 | OFFICE TABLE,STORGE RACK,FAN | 0 | - | 0 | 0.57869 | 0.57869 | 0 | 0 | 0 |  |  | 0
21 | CAMERAS | 0 | - | 0 | 0.038468 | 0.038468 | 0 | 0 | 0 |  |  | 0
22 | VELHALA ASH BUND RD WORK | 0 | - | 0 | 2.4645 | 2.4645 | 0 | 0 | 0 |  |  | 0
23 | CONCERETE ROAD FROM DIESEL PUMP TO 500MW FACTORY G | 0 | - | 0 | 0.98449 | 0.98449 | 0 | 0 | 0 |  |  | 0
24 | Admin Building | 0 | - | 0 | 0.05175 | 0 | 0.05175 | 0 | 0 |  |  | 0
25 | Furniture & Fixture | 0 | - | 0 | 0.13712 | 0.13712 | 0 | 0 | 0 |  |  | 0
26 | Office Equipment | 0 | - | 0 | 0.14424 | 0.14424 | 0 | 0 | 0 |  |  | 0
27 | Furniture & Fixture | 0 | - | 0 | 0.073968 | 0.073968 | 0 | 0 | 0 |  |  | 0
28 | Office Equipment | 0 | - | 0 | 0.15891 | 0.15891 | 0 | 0 | 0 |  |  | 0
29 | Work of repairs of 350 KW BCWP-4B & BCWP-5B motor of M/s. Torishima make at BTPS 2x500 MW | 0 | - | 0 | 4.8465 | 4.8465 | 0 | 0 | 0 |  |  | 0
30 | ABC Powder Type and Foam Type Composite Fire Extinguisher | 0 | - | 0 | 0.58548 | 0.58548 | 0 | 0 | 0 |  |  | 0
31 | Withdrawal of capex from Project (LD - Passenger Lifts) | 0 | - | 0 | 0 | -0.13899 | 0.13899 | 0 | 0 |  |  | 0
| Total |  |  |  | 374.5005 | 366.3697 | 8.1308 | 811.31 | 643.77 | 0 | 0 | 643.77 | 175.48
FY 2026-27
a) DPR Schemes
(i) Submitted to MERC
7 | Interconnection of 210 MW CHP to 500 MW CHP through Conveyors BC-02 & BC-03 having capacity of 500 TPH | MERC/CAPEX/20162017/00227 | 2016-05-24 | 24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Interconnection of 210 MW CHP to 500 MW CHP through Conveyors BC-02 & BC-03 having capacity of 500 TPH | MERC/CAPEX/20162017/00227 | 2016-05-24 | 22.73 | 19.1067 | 19.1067 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/00227 | 2016-05-24 | 1.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Stack management by procurement of Bulldozer & LOCO and CHP area schemes for performance & unloading improvement | MERC/CAPEX/20162017/01426 | 2017-02-02 | 9.9669 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement of Locomotive 800 HP (2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 4.9504 | 4.8261 | 4.8261 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Procurement of 2 No’s of Bulldozer Model D-155(2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 2.562 | 3.4747 | 3.4747 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.3 | Modification below primary crusher chutes 15A/B & Conv.02 | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.42975 | 0.38033 | 0.38033 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.4 | New helical gear box for various conveyors | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.79339 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.5 | Procurement of Elecon Make Ring Granulator Type TK-09-38B | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.53719 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.6 | Procurement of Elecon Make Ring Granulator Type TK6 32B Ring Granulator | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.33884 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.35537 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Construction of 1st raising of Ash bund from T.B.L. 258M to 264M at Bhusawal TPS | MERC/CAPEX/20172018/4267 | 2017-09-28 | 64.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Construction of 1st raising of Ash bund from T.B.L. 258M to 264M at Bhusawal TPS | MERC/CAPEX/20172018/4267 | 2017-09-28 | 64.22 | 64.4982 | 64.4982 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Augmentation of Ash Evacuation System & Procurement of BCW Pump Motors at Bhusawal & Khaperkheda TPS 500 MW Units | MERC/CAPEX/20172018/4782 | 2017-11-28 | 17.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Installation of standby Buffer Hopper parallel to existing pair of buffer hoppers | MERC/CAPEX/20172018/4782 | 2017-11-28 | 11.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | Installation of additional vacuum pump for every two passes, near to intermediate hopper. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.3 | Procurement of 02 Nos of M/s Torishima, Japan make, 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motors (without pump casing) with 02 lots of recommended Electrical & C&I spares for Bhusawal and Khaparkheda TPS 500MW. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 4.24 | 4.6696 | 4.6696 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.4 | Procurement of complete ACVF drive module comprising of 2 Nos. of Supply and 3 Nos. of Inverter modules for GEHO pumps | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0.95 | 0.92864 | 0.92864 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.5 | Supply, erection and commissioning of 24VDC, 100A Float & Float cum Boost Battery Charger with 325Ah Battery Bank for CWPH at BTPS 2x500 MW. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0.15 | 0.15788 | 0.15788 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Various schemes for renovation of colony at Bhusawal TPS | MERC/CAPEX/20172018/0221 | 2018-02-12 | 19.3341 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Renovation of staff quarters & related work at BTPS Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 7.021 | 5.4584 | 5.4584 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Colony Internal Roads at BTPS, Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 3.85 | 3.2501 | 3.2514 | -0.001329 | 0 | 0 |  |  | 0 | -0.001329 | 0 | 0
11.3 | Water supply , sanitary & drainage works at BTPS, Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 7.3 | 5.8361 | 5.8109 | 0.025229 | 0 | 0 |  |  | 0 | 0.025229 | 0 | 0
11.4 | Plinth protection to existing buildings at BTPS, Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 1.1631 | 0.91823 | 0.91823 | -2.2e-08 | 0 | 0 |  |  | 0 | -2.2e-08 | 0 | 0
12 | Pipeline from River Water Pump House (RWPH) to aquaduct over Bhogawati River and Other allied power house road works under DPR scheme at BTPS, Bhusawal | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 13.1172 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Providing supplying laying, jointing, testing and commissioning of 1650 mm Ø ID 8 mm thick M.S. pipeline for raw water supply from RWPH to aquaduct over Bhogawati river at, BTPS, Bhusawal. | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 7.257 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.2 | Construction of WBM and Bituminous road along inlet & outlet canals and concreate road along periphery of Major store at BTPS, Bhusawal. | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 4.22 | 3.8305 | 3.8305 | -2.7e-08 | 0 | 0 |  |  | 0 | -2.7e-08 | 0 | 0
12.3 | Work of construction of self-supporting steel roofing system for a major store godown shed of span 25M at BTPS, Deepnagar. | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 1.6402 | 0.27 | 1.6376 | -1.3676 | 0 | 0 |  |  | 0 | -1.3676 | 0 | 0
0 | IDC | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 0 | 0.14918 | 0.14918 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Supply, erection, commissioning & site testing of 220 V, 2035 AH, Station Battery Sets (4 Nos.) and 24 V, 2250 AH, SG/TG & BOP Battery Sets (8 Nos.) for U# 4 & 5 along with accessories at 2 x 500 MW BTPS, Bhusawal | MERC/CAPEX/2017-2018/1226 | 2018-08-10 | 11.59 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Supply, erection, commissioning & site testing of 220V, 2035 AH Station Battery Sets (02 Nos.) and 24V, 2250AH, SG/TG & BOP Battery Set (04 Nos.) along with accessories for Unit No.5 at BTPS 2x500MW. | MERC/CAPEX/2017-2018/1226 | 2018-08-10 | 5.795 | 6.374 | 6.374 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Supply, erection, commissioning & site testing of 220V, 2035 AH Station Battery Sets (02 Nos.) and 24V, 2250AH, SG/TG & BOP Battery Set (04 Nos.) along with accessories for Unit No.4 at BTPS 2x500MW. | MERC/CAPEX/2017-2018/1226 | 2018-08-10 | 5.795 | 6.3227 | 6.3227 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Flue Gas Desulphurization (FGD) System for 500 MW Units (Total 8 Nos) of MSPGCL | MERC/CAPEX/2020-2021/WFH/SBR/45 | 2021-02-05 | 869.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | Flue Gas Desulphurization (FGD) System for Bhusawal Unit 4-5 | MERC/CAPEX/2020-2021/WFH/SBR/45 | 2021-02-05 | 830.4 | 594.41 | 594.41 | 0 | 254.75 | 254.75 |  |  | 254.75 | 0 | 235.99 | 18.76
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/45 | 2021-02-05 | 39.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Procurement of two BFP Cartridges & one rotor of Turbine driven BFP & at 500MW BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 10.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Procurement of two BFP Cartridges at 500MW BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 3.84 | 2.24 | 2.24 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.2 | Procurement of one rotor of Turbine driven BFP at 500MW BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 6.46 | 7.6136 | 7.6136 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 0.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | CHP Improvement Schemes at 2X500MW, BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 21.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Revamping of Apron Feeder in CHP at 2X500MW, BTPS | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 4.67 | 4.6492 | 4.6492 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.2 | Design, engineering, manufacturing, supply, Erection and commissioning of short conveyor from stack yard to belt feeder 112 in CHP 2x500MW BTPS. | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 3.53 | 3.9648 | 3.9648 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.3 | Design, engineering, manufacturing, supply, Erection and commissioning of stone grappler at Wagon Tippler No.3 in CHP 2x500MW BTPS. | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 0.84 | 0.84 | 0.84 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.4 | Procurement of suspended magnets in CHP 2x500MW BTPS. | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 2.95 | 2.947 | 2.947 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.5 | Supply, Erection And Commissioning of Electro-Mechanical Drive to Apron Feeder at CHP 500MW | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 7.57 | 7.57 | 0 | 7.57 | 0 | 0 |  |  | 0 | 7.57 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 1.66 | 0.067524 | 0.067524 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Bhusawal: Unit 4-5 (3 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 1.9468 | 1.9458 | 0.001 | 0 | 0 |  |  | 0 | 0.001 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Bhusawal: Unit 4-5 | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 3.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Advance Multipurpose Fire Tender for BTPS 4-5 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 1.7765 | 1.7765 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Normal Multipurpose Fire Tender for BTPS 4-5 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.5 | 2.1847 | 2.1847 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 10.0654 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Bhusawal: Unit 4-5 | MERC/CAPEX/20172018/0177 | 2018-02-06 | 10.0654 | 9.1854 | 9.1837 | 0.0017614 | 0 | 0 |  |  | 0 | 0.0017614 | 0 | 0
18 | Procurement of assembly of baskets for Air Pre-heater of type 31.5 VIM 2000 (72° PA), Replacement of thermal insulation of Boiler, Ducts & Steam Pipelines and Coal Mill Gear Box in 2x500MW at BTPS, Bhusawal | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 14.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Procurement of assembly of baskets for Air Preheater of type 31.5 VIM 2000 (72° PA) for Unit-4&5 | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 5.53 | 8.411 | 8.411 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.2 | Replacement of thermal insulation of Boiler, Ducts & Steam Pipelines along with supply | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 3.52 | 3.52 | 2 | 1.52 | 0 | 0 |  |  | 0 | 1.52 | 0 | 0
18.3 | Supply of XRP-1043 coal mill gearbox spares in unit-4&5. | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 5.39 | 3.7044 | 3.7044 | -2.6e-08 | 0 | 0 |  |  | 0 | -2.6e-08 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 0.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | Up-gradation of Operating System of Max DNA DCS, GE Fanuc PLC system & Schneider PLC system & Procurement of Critical Insurance spares for PA and FD fans System at 2 x 500 MW Units BTPS Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 31.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Up-gradation of Existing MaxDNA System (HMI) at 500MW BTPS, Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 8.69 | 8.69 | 8.69 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Up-gradation of GE IP (GE-Fanuc) make PLC system (HMI) installed at AHP, CPU plant, FOPH, FWPH and Mill Reject system at 2x500MW BTPS, Bhusawal. | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 1.35 | 1.2948 | 1.3538 | -0.059 | 0 | 0 |  |  | 0 | -0.059 | 0 | 0
19.3 | Up-gradation of Schneider PLC System at 2x500MW, BTPS, Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 2.33 | 2.3093 | 2.3093 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.4 | Procurement of Rotor assembly with blade set for PA and FD fan at 2 X 500 MW BTPS Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 18.18 | 16.16 | 16.16 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Improvement of Loadability and Availability of Coal Handling Plant at BTPS, Bhusawal | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Scheme-1:-Design Engineering, Supply, Erection, commissioning, Extension of travel Length & Capacity Enhancement of coal yard with additional drive system of stacker reclaimer conveyor No. 110 at in coal handling Plant BTPS. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 14.27 | 0 | 0 | 0 | 14.27 | 14.27 |  |  | 14.27 | 0
20.2 | Scheme-2:-Design, Engineering, Rectification, Erection & Commissioning of Z point at Conveyor 108A & B at CHP-500MW. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 8.18 | 0 | 0 | 0 | 8.18 | 8.18 |  |  | 8.18 | 0
20.3 | Scheme-3:-Design, Engineering and provision of material lifting arrangement for crusher floor, wobbler feeder & C-105 floor In CHP BTPS. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 1.88 | 0 | 0 | 0 | 1.88 | 1.88 |  |  | 1.88 | 0
20.4 | Scheme-4:-Structural up-gradation and rehabilitation of reversible yard conveyor in coal handling plant. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 4.21 | 0 | 0 | 0 | 4.21 | 4.21 |  |  | 4.21 | 0
20.5 | Scheme-5:-Design, Engineering, Erection and commissioning of Receiving and discharge chutes of wobbler feeders in CHP BTPS. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 6.25 | 0 | 0 | 0 | 6.25 | 6.25 |  |  | 6.25 | 0
20.6 | Scheme-6: Procurement of 3 Nos. of Bulldozers at BTPS, Bhusawal. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 7.35 | 0 | 0 | 0 | 7.35 | 7.35 |  |  | 7.35 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0.42 | 0.42 |  |  | 0.42 | 0
21 | Performance Improvement of Coal Handling Plant at BTPS-U4 & 5, Bhusawal | MERC/CAPEX/MSPGCL/2024-25/0310 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Scheme-1: Revamping, Modification of Gravity take-up and Drive Augmentation of Bunkering conveyor in CHP BTPS | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 11.35 | 0 | 0 | 0 | 11.35 | 11.35 |  |  | 11.35 | 0
21.2 | Scheme-2: Revamping of coal diverting chutes in CHP 2x500 MW BTPS | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 5.73 | 0 | 0 | 0 | 5.73 | 5.73 |  |  | 5.73 | 0
21.3 | Scheme-3: Revamping and structural augmentation of Reversible feeder conveyors in CHP-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 1.77 | 1.75 | 1.75 | 0 | 1.77 | 1.77 |  |  | 1.77 | 0
21.4 | Scheme-4: Revamping and up-gradation of air & ventilation system in Coal Handling Plant-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 9.01 | 0 | 0 | 0 | 3.85 | 3.85 |  |  | 3.85 | 0
21.5 | Scheme-5: Revamping, Structural & drive up-gradation of conveyor-111 in CHP-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 3.85 | 0 | 0 | 0 | 8.62 | 8.62 |  |  | 8.62 | 0
21.6 | Scheme-6: Revamping and structural up-gradation of conveyor system in tunnel area in Coal Handling Plant-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 8.62 | 0 | 0 | 0 | 8.06 | 8.06 |  |  | 8.06 | 0
21.7 | Scheme-7: Erection & Commissioning of Travelling type coal chutes in CHP BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 8.06 | 0 | 0 | 0 | 4.98 | 4.98 |  |  | 4.98 | 0
21.8 | Scheme-8: Revamping of scoop cooling system installed in coal handling plant BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 4.98 | 0 | 0 | 0 | 3.92 | 3.92 |  |  | 3.92 | 0
21.9 | Scheme-9: Retrofitting and Up-gradation of Dewatering system in CHP-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 3.92 | 0 | 0 | 0 | 9.01 | 9.01 |  |  | 9.01 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0.53 | 0.53 |  |  | 0.53 | 0
0 | Asset Transfer from Projects | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | SP Busduct Unit 4&5 | 0 | - | 0 | 0.30072 | 0.30072 | 0 | 0 | 0 |  |  | 0 | 0
0 | ESP,ID,FD,PA Fans &Other Boiler Auxiliaries | 0 | - | 0 | 1.0283 | 1.0283 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) DPR Yet to be Submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2025-26 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Up gradation of coal mill reject system, Procurement of Air heater baskets & spare Air heater gearbox at 2X500MW, Bhusawal TPS | 0 | - | 0 | 31.75 | 0 | 31.75 | 0 | 0 |  |  | 0 | 31.75
1.1 | Work of Capacity enhancement, Engineering, modification, upgradation including spares and consumables and complete commissioning including operation and comprehensive maintenance for 12 months for coal mill reject handling system in Unit-4&5, 2X500MW, BTPS, Bhusawal | 0 | - | 0 | 15.05 | 15.05 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Procurement of assembly of baskets & seals for Air Preheater of type 31.5 VIM 2000 (72° PA), in Unit-5 2x500MW, BTPS Bhusawal | 0 | - | 0 | 7.45 | 7.45 | 0 | 0 | 0 |  |  | 0 | 0
1.3 | Procurement of APH Gearbox to improve availability and performance of Air preheaters at 2 x 500 MW Units, BTPS, Bhusawal. | 0 | - | 0 | 9.25 | 9.25 | 0 | 0 | 0 |  |  | 0 | 0
2 | Boiler Reliability & Availability improvement at 2x500MW, Bhusawal TPS. | 0 | - | 0 | 83.63 | 0 | 83.63 | 0 | 0 |  |  | 0 | 83.63
2.1 | Procurement & Replacement Of LTSH Coils for Unit - 4 & 5 (500MW) TPS, Bhusawal. | 0 | - | 0 | 19.11 | 19.11 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Procurement & Replacement Of Economiser Coils For Unit - 4 & 5 (500MW) TPS, Bhusawal | 0 | - | 0 | 47.6 | 47.6 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Procurement of assembly of APH Baskets Unit-4 | 0 | - | 0 | 7.55 | 7.55 | 0 | 0 | 0 |  |  | 0 | 0
2.4 | Procurement of APH Gearbox Unit-4&5 | 0 | - | 0 | 9.37 | 9.37 | 0 | 0 | 0 |  |  | 0 | 0
3 | Various Turbine side reliability improvement schemes at 2x500MW, BTPS | 0 | - | 0 | 41.4 | 0 | 41.4 | 0 | 0 |  |  | 0 | 41.4
3.1 | Reliability improvement of Atlas copco make (mode -ZR -500) | 0 | - | 0 | 2.4 | 2.4 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Reliability improvement of HPCV Valve with procurment cone assy | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Reliability improvement of Alfa Laval make Portable COP | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
3.4 | Reliability improvement of Seal Oil System with procurement of various U Seal rings | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
3.5 | Reliability improvement of Unit-4 & 5 NDCT with replacement of PVC fills and allied work | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
3.6 | Upgradation of Chiller plant, GEHO pump house & OLTC PLC system. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
4 | IB recommended scheme related (Civil and Electrical) | 0 | - | 0 | 10.76 | 0 | 10.76 | 0 | 0 |  |  | 0 | 10.76
4.1 | Work of fabricating and erecting structural steel watch tower (10 Nos.) in major store, plant area, ash pipe line and ash bund area at BTPS, Deepnagar. | 0 | - | 0 | 0.86 | 0.86 | 0 | 0 | 0 |  |  | 0 | 0
4.2 | Work of construction of ladies frisking room for security section and visitors room near factory gate and providing at 2x500MW, BTPS, Deepnagar. | 0 | - | 0 | 0.43 | 0.43 | 0 | 0 | 0 |  |  | 0 | 0
4.3 | Work of dismantling and construction old weathered UCR compound wall on bhogawati riverside in 2x500 MW at BTPS. | 0 | - | 0 | 3.29 | 3.29 | 0 | 0 | 0 |  |  | 0 | 0
4.4 | Construcion of RCC comppund wall from remote silo to pimpri sekam railway siding cabin at BTPS | 0 | - | 0 | 2.02 | 2.02 | 0 | 0 | 0 |  |  | 0 | 0
4.5 | Installation of Highmast towers | 0 | - | 0 | 4.16 | 4.16 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2026-27 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 50 | 50 |  |  | 50 | 0
2 | Upgradation of Coal feeder weighing system and revamping of Boiler side pneumatic dampers system of Hot air, cold air, FD,PA and burner tilt at Bhusawal TPS 2x500W | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Upgradation of Coal feeder weighing system at Bhusawal TPS 2x500W | 0 | - | 0 | 0 | 0 | 0 | 11.42 | 11.42 |  |  | 11.42 | 0
2.2 | Up-gradation of carbon monoxide analyzer in flue gas installed | 0 | - | 0 | 0 | 0 | 0 | 2.16 | 2.16 |  |  | 2.16 | 0
2.3 | Up- Gradation of condition monitoring & analysis system for TSI of Main Turbine , TDBFP & BOP System 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 13.2 | 13.2 |  |  | 13.2 | 0
2.5 | Revamping of Boiler side pneumatic dampers system of Hot air, cold air, FD,PA and burner tilt at BTPS 2X500MW | 0 | - | 0 | 0 | 0 | 0 | 6 | 6 |  |  | 6 | 0
2.6 | Procurement of various high pressure valves at 2x500 MW. | 0 | - | 0 | 0 | 0 | 0 | 2.22 | 2.22 |  |  | 2.22 | 0
3 | Schemes for Turbine side auxiliaries systems Performance & efficiency improvement schemes at 2X500MW, Bhusawal TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement of BFP Booster Pump (FA-1B-75) complete assembly (04 Nos) at 500MW BTPS, Bhusawal. | 0 | - | 0 | 0 | 0 | 0 | 3.16 | 3.16 |  |  | 3.16 | 0
3.2 | Procurement of Vacuum Pump complete assembly with recirculation Pump (01 No) and Impeller assembly (2 Nos) at 500MW BTPS, Bhusawal. | 0 | - | 0 | 0 | 0 | 0 | 5.2 | 5.2 |  |  | 5.2 | 0
3.3 | Revamping, modification of outdoor ducting of Air ventilation system at 2x500MW BTPS, Bhusawal. | 0 | - | 0 | 0 | 0 | 0 | 8.72 | 8.72 |  |  | 8.72 | 0
3.4 | Performance improvement of compressors | 0 | - | 0 | 0 | 0 | 0 | 12.99 | 12.99 |  |  | 12.99 | 0
3.5 | Centralized Water Management System at BTPS, Deepnagar, Bhusawal | 0 | - | 0 | 0 | 0 | 0 | 2.29 | 2.29 |  |  | 2.29 | 0
3.6 | Revamping and upgradation of Forbes Marshal make Steam & Water Analysis System Installed at 2x500MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 10.11 | 10.11 |  |  | 10.11 | 0
4 | Implementation of flexible operation solutions for technical minimum operation of 2x500MW, BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Implementation of flexible operation solutions for technical minimum operation of 2x500MW, BTPS. | 0 | - | 0 | 0 | 0 | 0 | 50 | 50 |  |  | 50 | 0
0 | FY 2027-28 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply,Installation and commissioning of Boiler performance and reliability improvement schemes at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Procurement of M/s Torishima, Japan make, 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motors at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Installation commissioning of Online DC Earth fault monitoring system at 220V DCDB at 500MW U-4&5. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.3 | Design, supply, erection, comms. Of ID VFD & AHP transformers for 2x500MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.4 | Design,supply,installation and commissioning of Energy efficient System for illumination at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.5 | Procurement of Main Gear unit assembly of electrical Actuators in 2x500MW BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.6 | Supply, erection, commissioning & site testing of 360V, 750 AH Station UPS Battery Sets along with accessories for Unit No.5 at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.7 | Upgradation of EWLI system at Bhusawal TPS 2x500W | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Performance improvement of Bottom ash evacualtion system to reduce auxillary power consumption, water consumption & environmental pollution at 2X500MW, Bhusawal TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Modification of latest design AR 200/550 Ash slurry pump assembly including auxillaries at AHP, 2x500MW, BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Modification of single roll reversible clinker grinder system at AHP, 2x500MW, BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Modification of bottom ash & coarse ash slurry pipe line disposal system at AHP 2X500 MW BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Boiler Reliability & Availability improvement at 2x500MW, Bhusawal TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement of Boiler Coils (CRH &HRH) at 2x500MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Procurement of ID fan impeller with shaft at 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Procurement SH,RH,MS outlet valves with actuator and motor at 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | CHP Infrastructure Development Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Supply, installation and commissioning PLC system on a single platform to match with external aspect & process improvement at CHP 2x500MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.2 | Supply, installation, retrofitting and commissioning of HT breaker at HT Switchgear in CHP 2x500MW BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.3 | Supply, installation, retrofitting and commissioning of LT breaker at LT Switchgear in CHP 2x500MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.4 | Supply, Installation & Commissioning of Magnetic Separators at CHP 2x 500MW BTPS Deepnagar | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.5 | Supply, Installation & Commissioning Flameproof lighting at CHP 2x 500MW BTPS Deepnagar | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.6 | Supply, Installation & upgradation of HT /LT relay at CHP BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Detail Project report of improvement of Unloading in Coal handling Plant BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Procurement of 04 no of locomotives for Coal handling Plant BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.2 | Design Supply Erection and Comission of Hour glass shape Coal diverting chutes with extra life wear resistant plates in CHP, BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.3 | Design Supply Erection and Comission of Inverted Y Shape Coal diverting chutes with extra life wear resistant plates in CHP, BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.4 | Design Supply Erection and Comission of coal diverting chutes with extra life wear resistant plates in CHP BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.5 | Work of Revamping and structural up-gradation of conveyor 104A&B in Coal Handling Plant-BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Supply and Installation of reliability improvement schemes for HT/LT switchgears and auxilliaries at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Procurement of HT Motors of various ratings at 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.2 | Procurement of Dry type transformers of varoius ratings at 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.3 | Procurement of Inverter and converter trolleys of GEHO Pump at 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.4 | Procurement of Vacuum Contactors of various ratings for HT Switchgears at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.5 | Supply, erection, commissioning & site testing of 360V, 750 AH Station UPS Battery Sets along with accessories for Unit No.4 at BTPS 2x500MW’. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.6 | Updragation of Sox-Nox analyzer,PM analyzer, ETP analyzer at BTPS 2X500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.7 | Upgradation of O2 analyzer at BTPS 2X500MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.8 | Revamping & Upgradation Of Vibration Monitoring Rack From VM7 TO VM7B at BTPS 2X500MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.9 | Procurement & Installation of High Mast towers in various location in BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Renovation and Modification of Colony Electric Supply System to improve availability and reliability of supply system at BTPS Colony, Deepnagar | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.11 | Work of Overhauling repairs of U-5 350KW BCWP motor of M/s Torishima make at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2028-29 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | APH baskets with main drive Gear box and lub oil skids with motor at 2x500MW BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | APH baskets with main drive Gear box and lub oil skids with motor at 2x500MW BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Detail Project Report for Design, Engineering, Supply, Installation and commissioning of 1500TPH Stacker cum re-claimer in Coal Handling Plant-BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Design, Engineering, Supply, Installation and commissioning of 1500TPH Stacker cum re-claimer in Coal Handling Plant-BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Enhancement of Unloading & Stacking Capacity of CHP. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Design Supply errection & Comissioning of Open Wagon Tippler along with stacking and reclaiming yard conveyors at CHP stack yard. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2029-30 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgradation rail track in CHP -BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Revamping and Upgradation of rail track from 52KG to 60KG in CHP-BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Contract for modification of Wobbler feeder in CHP-2X500MW | 0 | - | 0 | 1.4733 | 1.4733 | 0 | 0 | 0 |  |  | 0 | 0
2 | Contract for Revamping of Apron Feeder in CHP-2X500MW | 0 | - | 0 | 2.3246 | 2.3246 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of double lip skirt sealing & tracking idler in CHP at 2x500MW, BTPS | 0 | - | 0 | 0.57025 | 0.57025 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, erection & commissioning of vibrating feeder in CHP at 2x500MW, BTPS | 0 | - | 0 | 0.57796 | 0.57796 | 0 | 0 | 0 |  |  | 0 | 0
5 | Coal chutes with extra life wear resistance plates in CHP at 2X500MW | 0 | - | 0 | 2.0319 | 2.0319 | 0 | 0 | 0 |  |  | 0 | 0
6 | Epoxy Painting upto all height to structural steel work in main plant boiler side area and CHP area | 0 | - | 0 | 5.8625 | 5.8625 | 0 | 0 | 0 |  |  | 0 | 0
7 | Rectification of Belt feeder & Gravity Take-up in CHP-2X500MW. | 0 | - | 0 | 1.6479 | 1.6479 | 0 | 0 | 0 |  |  | 0 | 0
8 | Coal diverting chutes in CHP at 2X500MW. | 0 | - | 0 | 2.2184 | 2.2184 | 0 | 0 | 0 |  |  | 0 | 0
9 | Supply of Conveyor Pulleys with Ceramic lagging at CHP-2X500MW, BTPS, Bhusawal | 0 | - | 0 | 0.58051 | 0.58051 | 0 | 0 | 0 |  |  | 0 | 0
10 | Non-DPR Project Report for Design, Supply,Erection & Commissioning of High Performance Energy Chain System for Side Arm Charger at 2x500 at CHP | 0 | - | 0 | 1.5015 | 1.5015 | 0 | 0 | 0 |  |  | 0 | 0
11 | Implementation of Energy Conservation Demonstration Project in buildings of BTPS 2x500MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Installation of Fire & Explosion Prevention system at Bhusawal 500MW Unit-4. | 0 | - | 0 | 2.4539 | 2.4539 | 0 | 0 | 0 |  |  | 0 | 0
13 | Fixtures & Fitting (10801) | 0 | - | 0 | 0.21334 | 0.21334 | 0 | 0 | 0 |  |  | 0 | 0
14 | Office equpment (10901) | 0 | - | 0 | 0.22996 | 0.22996 | 0 | 0 | 0 |  |  | 0 | 0
15 | 150 W & 40 W LED FIXTURES AT TG HOUSE BUILDING 2X500MW | 0 | - | 0 | 0.52807 | 0.27807 | 0.25 | 0 | 0 |  |  | 0 | 0.25
16 | JUMBO DEESERT AIR COOLERS FOR POWER TRANSFORERS | 0 | - | 0 | 0.10143 | 0.10143 | 0 | 0 | 0 |  |  | 0 | 0
17 | GEN ASSET (ALMIRAH,TABLE & CHAIR) (10801) | 0 | - | 0 | 0.23454 | 0.23454 | 0 | 0 | 0 |  |  | 0 | 0
18 | LAPTOP, 50 INCH TV,PRINTER,PROJECTOR,DESKTOP,UPS & ETS. (10901) | 0 | - | 0 | 0.55035 | 0.55035 | 0 | 0 | 0 |  |  | 0 | 0
19 | RESTAURANT EQUIP COMPOSTING MACHINE | 0 | - | 0 | 0.05049 | 0.05049 | 0 | 0 | 0 |  |  | 0
20 | OFFICE TABLE,STORGE RACK,FAN | 0 | - | 0 | 0.57869 | 0.57869 | 0 | 0 | 0 |  |  | 0
21 | CAMERAS | 0 | - | 0 | 0.038468 | 0.038468 | 0 | 0 | 0 |  |  | 0
22 | VELHALA ASH BUND RD WORK | 0 | - | 0 | 2.4645 | 2.4645 | 0 | 0 | 0 |  |  | 0
23 | CONCERETE ROAD FROM DIESEL PUMP TO 500MW FACTORY G | 0 | - | 0 | 0.98449 | 0.98449 | 0 | 0 | 0 |  |  | 0
24 | Admin Building | 0 | - | 0 | 0.05175 | 0 | 0.05175 | 0 | 0 |  |  | 0
25 | Furniture & Fixture | 0 | - | 0 | 0.13712 | 0.13712 | 0 | 0 | 0 |  |  | 0
26 | Office Equipment | 0 | - | 0 | 0.14424 | 0.14424 | 0 | 0 | 0 |  |  | 0
27 | Furniture & Fixture | 0 | - | 0 | 0.073968 | 0.073968 | 0 | 0 | 0 |  |  | 0
28 | Office Equipment | 0 | - | 0 | 0.15891 | 0.15891 | 0 | 0 | 0 |  |  | 0
29 | Work of repairs of 350 KW BCWP-4B & BCWP-5B motor of M/s. Torishima make at BTPS 2x500 MW | 0 | - | 0 | 4.8465 | 4.8465 | 0 | 0 | 0 |  |  | 0
30 | ABC Powder Type and Foam Type Composite Fire Extinguisher | 0 | - | 0 | 0.58548 | 0.58548 | 0 | 0 | 0 |  |  | 0
31 | Withdrawal of capex from Project (LD - Passenger Lifts) | 0 | - | 0 | 0 | -0.13899 | 0.13899 | 0 | 0 |  |  | 0
| Total |  |  |  | 1185.8105 | 1010.1397 | 175.6708 | 532.6 | 532.6 | 0 | 0 | 532.6 | 175.48
FY 2027-28
a) DPR Schemes
(i) Submitted to MERC
7 | Interconnection of 210 MW CHP to 500 MW CHP through Conveyors BC-02 & BC-03 having capacity of 500 TPH | MERC/CAPEX/20162017/00227 | 2016-05-24 | 24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Interconnection of 210 MW CHP to 500 MW CHP through Conveyors BC-02 & BC-03 having capacity of 500 TPH | MERC/CAPEX/20162017/00227 | 2016-05-24 | 22.73 | 19.1067 | 19.1067 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/00227 | 2016-05-24 | 1.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Stack management by procurement of Bulldozer & LOCO and CHP area schemes for performance & unloading improvement | MERC/CAPEX/20162017/01426 | 2017-02-02 | 9.9669 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement of Locomotive 800 HP (2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 4.9504 | 4.8261 | 4.8261 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Procurement of 2 No’s of Bulldozer Model D-155(2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 2.562 | 3.4747 | 3.4747 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.3 | Modification below primary crusher chutes 15A/B & Conv.02 | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.42975 | 0.38033 | 0.38033 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.4 | New helical gear box for various conveyors | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.79339 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.5 | Procurement of Elecon Make Ring Granulator Type TK-09-38B | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.53719 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.6 | Procurement of Elecon Make Ring Granulator Type TK6 32B Ring Granulator | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.33884 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.35537 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Construction of 1st raising of Ash bund from T.B.L. 258M to 264M at Bhusawal TPS | MERC/CAPEX/20172018/4267 | 2017-09-28 | 64.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Construction of 1st raising of Ash bund from T.B.L. 258M to 264M at Bhusawal TPS | MERC/CAPEX/20172018/4267 | 2017-09-28 | 64.22 | 64.4982 | 64.4982 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Augmentation of Ash Evacuation System & Procurement of BCW Pump Motors at Bhusawal & Khaperkheda TPS 500 MW Units | MERC/CAPEX/20172018/4782 | 2017-11-28 | 17.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Installation of standby Buffer Hopper parallel to existing pair of buffer hoppers | MERC/CAPEX/20172018/4782 | 2017-11-28 | 11.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | Installation of additional vacuum pump for every two passes, near to intermediate hopper. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.3 | Procurement of 02 Nos of M/s Torishima, Japan make, 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motors (without pump casing) with 02 lots of recommended Electrical & C&I spares for Bhusawal and Khaparkheda TPS 500MW. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 4.24 | 4.6696 | 4.6696 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.4 | Procurement of complete ACVF drive module comprising of 2 Nos. of Supply and 3 Nos. of Inverter modules for GEHO pumps | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0.95 | 0.92864 | 0.92864 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.5 | Supply, erection and commissioning of 24VDC, 100A Float & Float cum Boost Battery Charger with 325Ah Battery Bank for CWPH at BTPS 2x500 MW. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0.15 | 0.15788 | 0.15788 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Various schemes for renovation of colony at Bhusawal TPS | MERC/CAPEX/20172018/0221 | 2018-02-12 | 19.3341 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Renovation of staff quarters & related work at BTPS Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 7.021 | 5.4584 | 5.4584 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Colony Internal Roads at BTPS, Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 3.85 | 3.2501 | 3.2514 | -0.001329 | 0 | 0 |  |  | 0 | -0.001329 | 0 | 0
11.3 | Water supply , sanitary & drainage works at BTPS, Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 7.3 | 5.8361 | 5.8109 | 0.025229 | 0 | 0 |  |  | 0 | 0.025229 | 0 | 0
11.4 | Plinth protection to existing buildings at BTPS, Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 1.1631 | 0.91823 | 0.91823 | -2.2e-08 | 0 | 0 |  |  | 0 | -2.2e-08 | 0 | 0
12 | Pipeline from River Water Pump House (RWPH) to aquaduct over Bhogawati River and Other allied power house road works under DPR scheme at BTPS, Bhusawal | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 13.1172 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Providing supplying laying, jointing, testing and commissioning of 1650 mm Ø ID 8 mm thick M.S. pipeline for raw water supply from RWPH to aquaduct over Bhogawati river at, BTPS, Bhusawal. | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 7.257 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.2 | Construction of WBM and Bituminous road along inlet & outlet canals and concreate road along periphery of Major store at BTPS, Bhusawal. | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 4.22 | 3.8305 | 3.8305 | -2.7e-08 | 0 | 0 |  |  | 0 | -2.7e-08 | 0 | 0
12.3 | Work of construction of self-supporting steel roofing system for a major store godown shed of span 25M at BTPS, Deepnagar. | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 1.6402 | 0.27 | 1.6376 | -1.3676 | 0 | 0 |  |  | 0 | -1.3676 | 0 | 0
0 | IDC | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 0 | 0.14918 | 0.14918 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Supply, erection, commissioning & site testing of 220 V, 2035 AH, Station Battery Sets (4 Nos.) and 24 V, 2250 AH, SG/TG & BOP Battery Sets (8 Nos.) for U# 4 & 5 along with accessories at 2 x 500 MW BTPS, Bhusawal | MERC/CAPEX/2017-2018/1226 | 2018-08-10 | 11.59 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Supply, erection, commissioning & site testing of 220V, 2035 AH Station Battery Sets (02 Nos.) and 24V, 2250AH, SG/TG & BOP Battery Set (04 Nos.) along with accessories for Unit No.5 at BTPS 2x500MW. | MERC/CAPEX/2017-2018/1226 | 2018-08-10 | 5.795 | 6.374 | 6.374 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Supply, erection, commissioning & site testing of 220V, 2035 AH Station Battery Sets (02 Nos.) and 24V, 2250AH, SG/TG & BOP Battery Set (04 Nos.) along with accessories for Unit No.4 at BTPS 2x500MW. | MERC/CAPEX/2017-2018/1226 | 2018-08-10 | 5.795 | 6.3227 | 6.3227 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Flue Gas Desulphurization (FGD) System for 500 MW Units (Total 8 Nos) of MSPGCL | MERC/CAPEX/2020-2021/WFH/SBR/45 | 2021-02-05 | 869.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | Flue Gas Desulphurization (FGD) System for Bhusawal Unit 4-5 | MERC/CAPEX/2020-2021/WFH/SBR/45 | 2021-02-05 | 830.4 | 849.16 | 849.16 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/45 | 2021-02-05 | 39.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Procurement of two BFP Cartridges & one rotor of Turbine driven BFP & at 500MW BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 10.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Procurement of two BFP Cartridges at 500MW BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 3.84 | 2.24 | 2.24 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.2 | Procurement of one rotor of Turbine driven BFP at 500MW BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 6.46 | 7.6136 | 7.6136 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 0.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | CHP Improvement Schemes at 2X500MW, BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 21.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Revamping of Apron Feeder in CHP at 2X500MW, BTPS | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 4.67 | 4.6492 | 4.6492 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.2 | Design, engineering, manufacturing, supply, Erection and commissioning of short conveyor from stack yard to belt feeder 112 in CHP 2x500MW BTPS. | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 3.53 | 3.9648 | 3.9648 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.3 | Design, engineering, manufacturing, supply, Erection and commissioning of stone grappler at Wagon Tippler No.3 in CHP 2x500MW BTPS. | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 0.84 | 0.84 | 0.84 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.4 | Procurement of suspended magnets in CHP 2x500MW BTPS. | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 2.95 | 2.947 | 2.947 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.5 | Supply, Erection And Commissioning of Electro-Mechanical Drive to Apron Feeder at CHP 500MW | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 7.57 | 7.57 | 0 | 7.57 | 0 | 0 |  |  | 0 | 7.57 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 1.66 | 0.067524 | 0.067524 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Bhusawal: Unit 4-5 (3 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 1.9468 | 1.9458 | 0.001 | 0 | 0 |  |  | 0 | 0.001 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Bhusawal: Unit 4-5 | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 3.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Advance Multipurpose Fire Tender for BTPS 4-5 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 1.7765 | 1.7765 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Normal Multipurpose Fire Tender for BTPS 4-5 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.5 | 2.1847 | 2.1847 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 10.0654 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Bhusawal: Unit 4-5 | MERC/CAPEX/20172018/0177 | 2018-02-06 | 10.0654 | 9.1854 | 9.1837 | 0.0017614 | 0 | 0 |  |  | 0 | 0.0017614 | 0 | 0
18 | Procurement of assembly of baskets for Air Pre-heater of type 31.5 VIM 2000 (72° PA), Replacement of thermal insulation of Boiler, Ducts & Steam Pipelines and Coal Mill Gear Box in 2x500MW at BTPS, Bhusawal | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 14.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Procurement of assembly of baskets for Air Preheater of type 31.5 VIM 2000 (72° PA) for Unit-4&5 | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 5.53 | 8.411 | 8.411 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.2 | Replacement of thermal insulation of Boiler, Ducts & Steam Pipelines along with supply | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 3.52 | 3.52 | 2 | 1.52 | 0 | 0 |  |  | 0 | 1.52 | 0 | 0
18.3 | Supply of XRP-1043 coal mill gearbox spares in unit-4&5. | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 5.39 | 3.7044 | 3.7044 | -2.6e-08 | 0 | 0 |  |  | 0 | -2.6e-08 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 0.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | Up-gradation of Operating System of Max DNA DCS, GE Fanuc PLC system & Schneider PLC system & Procurement of Critical Insurance spares for PA and FD fans System at 2 x 500 MW Units BTPS Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 31.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Up-gradation of Existing MaxDNA System (HMI) at 500MW BTPS, Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 8.69 | 8.69 | 8.69 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Up-gradation of GE IP (GE-Fanuc) make PLC system (HMI) installed at AHP, CPU plant, FOPH, FWPH and Mill Reject system at 2x500MW BTPS, Bhusawal. | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 1.35 | 1.2948 | 1.3538 | -0.059 | 0 | 0 |  |  | 0 | -0.059 | 0 | 0
19.3 | Up-gradation of Schneider PLC System at 2x500MW, BTPS, Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 2.33 | 2.3093 | 2.3093 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.4 | Procurement of Rotor assembly with blade set for PA and FD fan at 2 X 500 MW BTPS Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 18.18 | 16.16 | 16.16 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Improvement of Loadability and Availability of Coal Handling Plant at BTPS, Bhusawal | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Scheme-1:-Design Engineering, Supply, Erection, commissioning, Extension of travel Length & Capacity Enhancement of coal yard with additional drive system of stacker reclaimer conveyor No. 110 at in coal handling Plant BTPS. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 14.27 | 14.27 | 14.27 | 0 | 0 | 0 |  |  | 0 | 0
20.2 | Scheme-2:-Design, Engineering, Rectification, Erection & Commissioning of Z point at Conveyor 108A & B at CHP-500MW. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 8.18 | 8.18 | 8.18 | 0 | 0 | 0 |  |  | 0 | 0
20.3 | Scheme-3:-Design, Engineering and provision of material lifting arrangement for crusher floor, wobbler feeder & C-105 floor In CHP BTPS. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 1.88 | 1.88 | 1.88 | 0 | 0 | 0 |  |  | 0 | 0
20.4 | Scheme-4:-Structural up-gradation and rehabilitation of reversible yard conveyor in coal handling plant. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 4.21 | 4.21 | 4.21 | 0 | 0 | 0 |  |  | 0 | 0
20.5 | Scheme-5:-Design, Engineering, Erection and commissioning of Receiving and discharge chutes of wobbler feeders in CHP BTPS. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 6.25 | 6.25 | 6.25 | 0 | 0 | 0 |  |  | 0 | 0
20.6 | Scheme-6: Procurement of 3 Nos. of Bulldozers at BTPS, Bhusawal. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 7.35 | 7.35 | 7.35 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0.42 | 0.42 | 0 | 0 | 0 |  |  | 0 | 0
21 | Performance Improvement of Coal Handling Plant at BTPS-U4 & 5, Bhusawal | MERC/CAPEX/MSPGCL/2024-25/0310 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Scheme-1: Revamping, Modification of Gravity take-up and Drive Augmentation of Bunkering conveyor in CHP BTPS | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 11.35 | 11.35 | 11.35 | 0 | 0 | 0 |  |  | 0 | 0
21.2 | Scheme-2: Revamping of coal diverting chutes in CHP 2x500 MW BTPS | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 5.73 | 5.73 | 5.73 | 0 | 0 | 0 |  |  | 0 | 0
21.3 | Scheme-3: Revamping and structural augmentation of Reversible feeder conveyors in CHP-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 1.77 | 3.52 | 3.52 | 0 | 0 | 0 |  |  | 0 | 0
21.4 | Scheme-4: Revamping and up-gradation of air & ventilation system in Coal Handling Plant-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 9.01 | 3.85 | 3.85 | 0 | 0 | 0 |  |  | 0 | 0
21.5 | Scheme-5: Revamping, Structural & drive up-gradation of conveyor-111 in CHP-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 3.85 | 8.62 | 8.62 | 0 | 0 | 0 |  |  | 0 | 0
21.6 | Scheme-6: Revamping and structural up-gradation of conveyor system in tunnel area in Coal Handling Plant-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 8.62 | 8.06 | 8.06 | 0 | 0 | 0 |  |  | 0 | 0
21.7 | Scheme-7: Erection & Commissioning of Travelling type coal chutes in CHP BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 8.06 | 4.98 | 4.98 | 0 | 0 | 0 |  |  | 0 | 0
21.8 | Scheme-8: Revamping of scoop cooling system installed in coal handling plant BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 4.98 | 3.92 | 3.92 | 0 | 0 | 0 |  |  | 0 | 0
21.9 | Scheme-9: Retrofitting and Up-gradation of Dewatering system in CHP-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 3.92 | 9.01 | 9.01 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0.53 | 0.53 | 0 | 0 | 0 |  |  | 0 | 0
0 | Asset Transfer from Projects | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | SP Busduct Unit 4&5 | 0 | - | 0 | 0.30072 | 0.30072 | 0 | 0 | 0 |  |  | 0 | 0
0 | ESP,ID,FD,PA Fans &Other Boiler Auxiliaries | 0 | - | 0 | 1.0283 | 1.0283 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) DPR Yet to be Submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2025-26 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Up gradation of coal mill reject system, Procurement of Air heater baskets & spare Air heater gearbox at 2X500MW, Bhusawal TPS | 0 | - | 0 | 31.75 | 0 | 31.75 | 0 | 0 |  |  | 0 | 31.75
1.1 | Work of Capacity enhancement, Engineering, modification, upgradation including spares and consumables and complete commissioning including operation and comprehensive maintenance for 12 months for coal mill reject handling system in Unit-4&5, 2X500MW, BTPS, Bhusawal | 0 | - | 0 | 15.05 | 15.05 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Procurement of assembly of baskets & seals for Air Preheater of type 31.5 VIM 2000 (72° PA), in Unit-5 2x500MW, BTPS Bhusawal | 0 | - | 0 | 7.45 | 7.45 | 0 | 0 | 0 |  |  | 0 | 0
1.3 | Procurement of APH Gearbox to improve availability and performance of Air preheaters at 2 x 500 MW Units, BTPS, Bhusawal. | 0 | - | 0 | 9.25 | 9.25 | 0 | 0 | 0 |  |  | 0 | 0
2 | Boiler Reliability & Availability improvement at 2x500MW, Bhusawal TPS. | 0 | - | 0 | 83.63 | 0 | 83.63 | 0 | 0 |  |  | 0 | 83.63
2.1 | Procurement & Replacement Of LTSH Coils for Unit - 4 & 5 (500MW) TPS, Bhusawal. | 0 | - | 0 | 19.11 | 19.11 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Procurement & Replacement Of Economiser Coils For Unit - 4 & 5 (500MW) TPS, Bhusawal | 0 | - | 0 | 47.6 | 47.6 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Procurement of assembly of APH Baskets Unit-4 | 0 | - | 0 | 7.55 | 7.55 | 0 | 0 | 0 |  |  | 0 | 0
2.4 | Procurement of APH Gearbox Unit-4&5 | 0 | - | 0 | 9.37 | 9.37 | 0 | 0 | 0 |  |  | 0 | 0
3 | Various Turbine side reliability improvement schemes at 2x500MW, BTPS | 0 | - | 0 | 41.4 | 0 | 41.4 | 0 | 0 |  |  | 0 | 41.4
3.1 | Reliability improvement of Atlas copco make (mode -ZR -500) | 0 | - | 0 | 2.4 | 2.4 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Reliability improvement of HPCV Valve with procurment cone assy | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Reliability improvement of Alfa Laval make Portable COP | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
3.4 | Reliability improvement of Seal Oil System with procurement of various U Seal rings | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
3.5 | Reliability improvement of Unit-4 & 5 NDCT with replacement of PVC fills and allied work | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
3.6 | Upgradation of Chiller plant, GEHO pump house & OLTC PLC system. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
4 | IB recommended scheme related (Civil and Electrical) | 0 | - | 0 | 10.76 | 0 | 10.76 | 0 | 0 |  |  | 0 | 10.76
4.1 | Work of fabricating and erecting structural steel watch tower (10 Nos.) in major store, plant area, ash pipe line and ash bund area at BTPS, Deepnagar. | 0 | - | 0 | 0.86 | 0.86 | 0 | 0 | 0 |  |  | 0 | 0
4.2 | Work of construction of ladies frisking room for security section and visitors room near factory gate and providing at 2x500MW, BTPS, Deepnagar. | 0 | - | 0 | 0.43 | 0.43 | 0 | 0 | 0 |  |  | 0 | 0
4.3 | Work of dismantling and construction old weathered UCR compound wall on bhogawati riverside in 2x500 MW at BTPS. | 0 | - | 0 | 3.29 | 3.29 | 0 | 0 | 0 |  |  | 0 | 0
4.4 | Construcion of RCC comppund wall from remote silo to pimpri sekam railway siding cabin at BTPS | 0 | - | 0 | 2.02 | 2.02 | 0 | 0 | 0 |  |  | 0 | 0
4.5 | Installation of Highmast towers | 0 | - | 0 | 4.16 | 4.16 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2026-27 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | 0 | - | 0 | 50 | 50 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgradation of Coal feeder weighing system and revamping of Boiler side pneumatic dampers system of Hot air, cold air, FD,PA and burner tilt at Bhusawal TPS 2x500W | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Upgradation of Coal feeder weighing system at Bhusawal TPS 2x500W | 0 | - | 0 | 11.42 | 11.42 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Up-gradation of carbon monoxide analyzer in flue gas installed | 0 | - | 0 | 2.16 | 2.16 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Up- Gradation of condition monitoring & analysis system for TSI of Main Turbine , TDBFP & BOP System 2x500 MW BTPS. | 0 | - | 0 | 13.2 | 13.2 | 0 | 0 | 0 |  |  | 0 | 0
2.5 | Revamping of Boiler side pneumatic dampers system of Hot air, cold air, FD,PA and burner tilt at BTPS 2X500MW | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
2.6 | Procurement of various high pressure valves at 2x500 MW. | 0 | - | 0 | 2.22 | 2.22 | 0 | 0 | 0 |  |  | 0 | 0
3 | Schemes for Turbine side auxiliaries systems Performance & efficiency improvement schemes at 2X500MW, Bhusawal TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement of BFP Booster Pump (FA-1B-75) complete assembly (04 Nos) at 500MW BTPS, Bhusawal. | 0 | - | 0 | 3.16 | 3.16 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Procurement of Vacuum Pump complete assembly with recirculation Pump (01 No) and Impeller assembly (2 Nos) at 500MW BTPS, Bhusawal. | 0 | - | 0 | 5.2 | 5.2 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Revamping, modification of outdoor ducting of Air ventilation system at 2x500MW BTPS, Bhusawal. | 0 | - | 0 | 8.72 | 8.72 | 0 | 0 | 0 |  |  | 0 | 0
3.4 | Performance improvement of compressors | 0 | - | 0 | 12.99 | 12.99 | 0 | 0 | 0 |  |  | 0 | 0
3.5 | Centralized Water Management System at BTPS, Deepnagar, Bhusawal | 0 | - | 0 | 2.29 | 2.29 | 0 | 0 | 0 |  |  | 0 | 0
3.6 | Revamping and upgradation of Forbes Marshal make Steam & Water Analysis System Installed at 2x500MW BTPS. | 0 | - | 0 | 10.11 | 10.11 | 0 | 0 | 0 |  |  | 0 | 0
4 | Implementation of flexible operation solutions for technical minimum operation of 2x500MW, BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Implementation of flexible operation solutions for technical minimum operation of 2x500MW, BTPS. | 0 | - | 0 | 50 | 50 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2027-28 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply,Installation and commissioning of Boiler performance and reliability improvement schemes at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Procurement of M/s Torishima, Japan make, 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motors at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 5.58 | 5.58 |  |  | 5.58 | 0
1.2 | Installation commissioning of Online DC Earth fault monitoring system at 220V DCDB at 500MW U-4&5. | 0 | - | 0 | 0 | 0 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
1.3 | Design, supply, erection, comms. Of ID VFD & AHP transformers for 2x500MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
1.4 | Design,supply,installation and commissioning of Energy efficient System for illumination at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 4 | 4 |  |  | 4 | 0
1.5 | Procurement of Main Gear unit assembly of electrical Actuators in 2x500MW BTPS | 0 | - | 0 | 0 | 0 | 0 | 6 | 6 |  |  | 6 | 0
1.6 | Supply, erection, commissioning & site testing of 360V, 750 AH Station UPS Battery Sets along with accessories for Unit No.5 at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 4 | 4 |  |  | 4 | 0
1.7 | Upgradation of EWLI system at Bhusawal TPS 2x500W | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
2 | Performance improvement of Bottom ash evacualtion system to reduce auxillary power consumption, water consumption & environmental pollution at 2X500MW, Bhusawal TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Modification of latest design AR 200/550 Ash slurry pump assembly including auxillaries at AHP, 2x500MW, BTPS. | 0 | - | 0 | 0 | 0 | 0 | 4.69 | 4.69 |  |  | 4.69 | 0
2.2 | Modification of single roll reversible clinker grinder system at AHP, 2x500MW, BTPS | 0 | - | 0 | 0 | 0 | 0 | 3.09 | 3.09 |  |  | 3.09 | 0
2.3 | Modification of bottom ash & coarse ash slurry pipe line disposal system at AHP 2X500 MW BTPS | 0 | - | 0 | 0 | 0 | 0 | 34.55 | 34.55 |  |  | 34.55 | 0
3 | Boiler Reliability & Availability improvement at 2x500MW, Bhusawal TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement of Boiler Coils (CRH &HRH) at 2x500MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 25 | 25 |  |  | 25 | 0
3.2 | Procurement of ID fan impeller with shaft at 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 15 | 15 |  |  | 15 | 0
3.3 | Procurement SH,RH,MS outlet valves with actuator and motor at 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
4 | CHP Infrastructure Development Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Supply, installation and commissioning PLC system on a single platform to match with external aspect & process improvement at CHP 2x500MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 18.4 | 18.4 |  |  | 18.4 | 0
4.2 | Supply, installation, retrofitting and commissioning of HT breaker at HT Switchgear in CHP 2x500MW BTPS | 0 | - | 0 | 0 | 0 | 0 | 6.9 | 6.9 |  |  | 6.9 | 0
4.3 | Supply, installation, retrofitting and commissioning of LT breaker at LT Switchgear in CHP 2x500MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 4.4 | 4.4 |  |  | 4.4 | 0
4.4 | Supply, Installation & Commissioning of Magnetic Separators at CHP 2x 500MW BTPS Deepnagar | 0 | - | 0 | 0 | 0 | 0 | 3.73 | 3.73 |  |  | 3.73 | 0
4.5 | Supply, Installation & Commissioning Flameproof lighting at CHP 2x 500MW BTPS Deepnagar | 0 | - | 0 | 0 | 0 | 0 | 10.47 | 10.47 |  |  | 10.47 | 0
4.6 | Supply, Installation & upgradation of HT /LT relay at CHP BTPS. | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
5 | Detail Project report of improvement of Unloading in Coal handling Plant BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Procurement of 04 no of locomotives for Coal handling Plant BTPS. | 0 | - | 0 | 0 | 0 | 0 | 13.68 | 13.68 |  |  | 13.68 | 0
5.2 | Design Supply Erection and Comission of Hour glass shape Coal diverting chutes with extra life wear resistant plates in CHP, BTPS. | 0 | - | 0 | 0 | 0 | 0 | 5.67 | 5.67 |  |  | 5.67 | 0
5.3 | Design Supply Erection and Comission of Inverted Y Shape Coal diverting chutes with extra life wear resistant plates in CHP, BTPS. | 0 | - | 0 | 0 | 0 | 0 | 4.72 | 4.72 |  |  | 4.72 | 0
5.4 | Design Supply Erection and Comission of coal diverting chutes with extra life wear resistant plates in CHP BTPS. | 0 | - | 0 | 0 | 0 | 0 | 4.72 | 4.72 |  |  | 4.72 | 0
5.5 | Work of Revamping and structural up-gradation of conveyor 104A&B in Coal Handling Plant-BTPS. | 0 | - | 0 | 0 | 0 | 0 | 7.1 | 7.1 |  |  | 7.1 | 0
6 | Supply and Installation of reliability improvement schemes for HT/LT switchgears and auxilliaries at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Procurement of HT Motors of various ratings at 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 4 | 4 |  |  | 4 | 0
6.2 | Procurement of Dry type transformers of varoius ratings at 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 4 | 4 |  |  | 4 | 0
6.3 | Procurement of Inverter and converter trolleys of GEHO Pump at 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
6.4 | Procurement of Vacuum Contactors of various ratings for HT Switchgears at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
6.5 | Supply, erection, commissioning & site testing of 360V, 750 AH Station UPS Battery Sets along with accessories for Unit No.4 at BTPS 2x500MW’. | 0 | - | 0 | 0 | 0 | 0 | 4 | 4 |  |  | 4 | 0
6.6 | Updragation of Sox-Nox analyzer,PM analyzer, ETP analyzer at BTPS 2X500MW. | 0 | - | 0 | 0 | 0 | 0 | 1.05 | 1.05 |  |  | 1.05 | 0
6.7 | Upgradation of O2 analyzer at BTPS 2X500MW | 0 | - | 0 | 0 | 0 | 0 | 3.4 | 3.4 |  |  | 3.4 | 0
6.8 | Revamping & Upgradation Of Vibration Monitoring Rack From VM7 TO VM7B at BTPS 2X500MW | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
6.9 | Procurement & Installation of High Mast towers in various location in BTPS | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
6.1 | Renovation and Modification of Colony Electric Supply System to improve availability and reliability of supply system at BTPS Colony, Deepnagar | 0 | - | 0 | 0 | 0 | 0 | 15.85 | 15.85 |  |  | 15.85 | 0
6.11 | Work of Overhauling repairs of U-5 350KW BCWP motor of M/s Torishima make at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 4 | 4 |  |  | 4 | 0
0 | FY 2028-29 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | APH baskets with main drive Gear box and lub oil skids with motor at 2x500MW BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | APH baskets with main drive Gear box and lub oil skids with motor at 2x500MW BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Detail Project Report for Design, Engineering, Supply, Installation and commissioning of 1500TPH Stacker cum re-claimer in Coal Handling Plant-BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Design, Engineering, Supply, Installation and commissioning of 1500TPH Stacker cum re-claimer in Coal Handling Plant-BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Enhancement of Unloading & Stacking Capacity of CHP. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Design Supply errection & Comissioning of Open Wagon Tippler along with stacking and reclaiming yard conveyors at CHP stack yard. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2029-30 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgradation rail track in CHP -BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Revamping and Upgradation of rail track from 52KG to 60KG in CHP-BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Contract for modification of Wobbler feeder in CHP-2X500MW | 0 | - | 0 | 1.4733 | 1.4733 | 0 | 0 | 0 |  |  | 0 | 0
2 | Contract for Revamping of Apron Feeder in CHP-2X500MW | 0 | - | 0 | 2.3246 | 2.3246 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of double lip skirt sealing & tracking idler in CHP at 2x500MW, BTPS | 0 | - | 0 | 0.57025 | 0.57025 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, erection & commissioning of vibrating feeder in CHP at 2x500MW, BTPS | 0 | - | 0 | 0.57796 | 0.57796 | 0 | 0 | 0 |  |  | 0 | 0
5 | Coal chutes with extra life wear resistance plates in CHP at 2X500MW | 0 | - | 0 | 2.0319 | 2.0319 | 0 | 0 | 0 |  |  | 0 | 0
6 | Epoxy Painting upto all height to structural steel work in main plant boiler side area and CHP area | 0 | - | 0 | 5.8625 | 5.8625 | 0 | 0 | 0 |  |  | 0 | 0
7 | Rectification of Belt feeder & Gravity Take-up in CHP-2X500MW. | 0 | - | 0 | 1.6479 | 1.6479 | 0 | 0 | 0 |  |  | 0 | 0
8 | Coal diverting chutes in CHP at 2X500MW. | 0 | - | 0 | 2.2184 | 2.2184 | 0 | 0 | 0 |  |  | 0 | 0
9 | Supply of Conveyor Pulleys with Ceramic lagging at CHP-2X500MW, BTPS, Bhusawal | 0 | - | 0 | 0.58051 | 0.58051 | 0 | 0 | 0 |  |  | 0 | 0
10 | Non-DPR Project Report for Design, Supply,Erection & Commissioning of High Performance Energy Chain System for Side Arm Charger at 2x500 at CHP | 0 | - | 0 | 1.5015 | 1.5015 | 0 | 0 | 0 |  |  | 0 | 0
11 | Implementation of Energy Conservation Demonstration Project in buildings of BTPS 2x500MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Installation of Fire & Explosion Prevention system at Bhusawal 500MW Unit-4. | 0 | - | 0 | 2.4539 | 2.4539 | 0 | 0 | 0 |  |  | 0 | 0
13 | Fixtures & Fitting (10801) | 0 | - | 0 | 0.21334 | 0.21334 | 0 | 0 | 0 |  |  | 0 | 0
14 | Office equpment (10901) | 0 | - | 0 | 0.22996 | 0.22996 | 0 | 0 | 0 |  |  | 0 | 0
15 | 150 W & 40 W LED FIXTURES AT TG HOUSE BUILDING 2X500MW | 0 | - | 0 | 0.52807 | 0.27807 | 0.25 | 0 | 0 |  |  | 0 | 0.25
16 | JUMBO DEESERT AIR COOLERS FOR POWER TRANSFORERS | 0 | - | 0 | 0.10143 | 0.10143 | 0 | 0 | 0 |  |  | 0 | 0
17 | GEN ASSET (ALMIRAH,TABLE & CHAIR) (10801) | 0 | - | 0 | 0.23454 | 0.23454 | 0 | 0 | 0 |  |  | 0 | 0
18 | LAPTOP, 50 INCH TV,PRINTER,PROJECTOR,DESKTOP,UPS & ETS. (10901) | 0 | - | 0 | 0.55035 | 0.55035 | 0 | 0 | 0 |  |  | 0 | 0
19 | RESTAURANT EQUIP COMPOSTING MACHINE | 0 | - | 0 | 0.05049 | 0.05049 | 0 | 0 | 0 |  |  | 0
20 | OFFICE TABLE,STORGE RACK,FAN | 0 | - | 0 | 0.57869 | 0.57869 | 0 | 0 | 0 |  |  | 0
21 | CAMERAS | 0 | - | 0 | 0.038468 | 0.038468 | 0 | 0 | 0 |  |  | 0
22 | VELHALA ASH BUND RD WORK | 0 | - | 0 | 2.4645 | 2.4645 | 0 | 0 | 0 |  |  | 0
23 | CONCERETE ROAD FROM DIESEL PUMP TO 500MW FACTORY G | 0 | - | 0 | 0.98449 | 0.98449 | 0 | 0 | 0 |  |  | 0
24 | Admin Building | 0 | - | 0 | 0.05175 | 0 | 0.05175 | 0 | 0 |  |  | 0
25 | Furniture & Fixture | 0 | - | 0 | 0.13712 | 0.13712 | 0 | 0 | 0 |  |  | 0
26 | Office Equipment | 0 | - | 0 | 0.14424 | 0.14424 | 0 | 0 | 0 |  |  | 0
27 | Furniture & Fixture | 0 | - | 0 | 0.073968 | 0.073968 | 0 | 0 | 0 |  |  | 0
28 | Office Equipment | 0 | - | 0 | 0.15891 | 0.15891 | 0 | 0 | 0 |  |  | 0
29 | Work of repairs of 350 KW BCWP-4B & BCWP-5B motor of M/s. Torishima make at BTPS 2x500 MW | 0 | - | 0 | 4.8465 | 4.8465 | 0 | 0 | 0 |  |  | 0
30 | ABC Powder Type and Foam Type Composite Fire Extinguisher | 0 | - | 0 | 0.58548 | 0.58548 | 0 | 0 | 0 |  |  | 0
31 | Withdrawal of capex from Project (LD - Passenger Lifts) | 0 | - | 0 | 0 | -0.13899 | 0.13899 | 0 | 0 |  |  | 0
| Total |  |  |  | 1718.4105 | 1542.7397 | 175.6708 | 243 | 243 | 0 | 0 | 243 | 175.48
FY 2028-29
a) DPR Schemes
(i) Submitted to MERC
7 | Interconnection of 210 MW CHP to 500 MW CHP through Conveyors BC-02 & BC-03 having capacity of 500 TPH | MERC/CAPEX/20162017/00227 | 2016-05-24 | 24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Interconnection of 210 MW CHP to 500 MW CHP through Conveyors BC-02 & BC-03 having capacity of 500 TPH | MERC/CAPEX/20162017/00227 | 2016-05-24 | 22.73 | 19.1067 | 19.1067 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/00227 | 2016-05-24 | 1.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Stack management by procurement of Bulldozer & LOCO and CHP area schemes for performance & unloading improvement | MERC/CAPEX/20162017/01426 | 2017-02-02 | 9.9669 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement of Locomotive 800 HP (2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 4.9504 | 4.8261 | 4.8261 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Procurement of 2 No’s of Bulldozer Model D-155(2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 2.562 | 3.4747 | 3.4747 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.3 | Modification below primary crusher chutes 15A/B & Conv.02 | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.42975 | 0.38033 | 0.38033 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.4 | New helical gear box for various conveyors | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.79339 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.5 | Procurement of Elecon Make Ring Granulator Type TK-09-38B | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.53719 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.6 | Procurement of Elecon Make Ring Granulator Type TK6 32B Ring Granulator | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.33884 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.35537 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Construction of 1st raising of Ash bund from T.B.L. 258M to 264M at Bhusawal TPS | MERC/CAPEX/20172018/4267 | 2017-09-28 | 64.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Construction of 1st raising of Ash bund from T.B.L. 258M to 264M at Bhusawal TPS | MERC/CAPEX/20172018/4267 | 2017-09-28 | 64.22 | 64.4982 | 64.4982 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Augmentation of Ash Evacuation System & Procurement of BCW Pump Motors at Bhusawal & Khaperkheda TPS 500 MW Units | MERC/CAPEX/20172018/4782 | 2017-11-28 | 17.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Installation of standby Buffer Hopper parallel to existing pair of buffer hoppers | MERC/CAPEX/20172018/4782 | 2017-11-28 | 11.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | Installation of additional vacuum pump for every two passes, near to intermediate hopper. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.3 | Procurement of 02 Nos of M/s Torishima, Japan make, 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motors (without pump casing) with 02 lots of recommended Electrical & C&I spares for Bhusawal and Khaparkheda TPS 500MW. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 4.24 | 4.6696 | 4.6696 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.4 | Procurement of complete ACVF drive module comprising of 2 Nos. of Supply and 3 Nos. of Inverter modules for GEHO pumps | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0.95 | 0.92864 | 0.92864 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.5 | Supply, erection and commissioning of 24VDC, 100A Float & Float cum Boost Battery Charger with 325Ah Battery Bank for CWPH at BTPS 2x500 MW. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0.15 | 0.15788 | 0.15788 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Various schemes for renovation of colony at Bhusawal TPS | MERC/CAPEX/20172018/0221 | 2018-02-12 | 19.3341 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Renovation of staff quarters & related work at BTPS Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 7.021 | 5.4584 | 5.4584 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Colony Internal Roads at BTPS, Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 3.85 | 3.2501 | 3.2514 | -0.001329 | 0 | 0 |  |  | 0 | -0.001329 | 0 | 0
11.3 | Water supply , sanitary & drainage works at BTPS, Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 7.3 | 5.8361 | 5.8109 | 0.025229 | 0 | 0 |  |  | 0 | 0.025229 | 0 | 0
11.4 | Plinth protection to existing buildings at BTPS, Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 1.1631 | 0.91823 | 0.91823 | -2.2e-08 | 0 | 0 |  |  | 0 | -2.2e-08 | 0 | 0
12 | Pipeline from River Water Pump House (RWPH) to aquaduct over Bhogawati River and Other allied power house road works under DPR scheme at BTPS, Bhusawal | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 13.1172 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Providing supplying laying, jointing, testing and commissioning of 1650 mm Ø ID 8 mm thick M.S. pipeline for raw water supply from RWPH to aquaduct over Bhogawati river at, BTPS, Bhusawal. | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 7.257 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.2 | Construction of WBM and Bituminous road along inlet & outlet canals and concreate road along periphery of Major store at BTPS, Bhusawal. | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 4.22 | 3.8305 | 3.8305 | -2.7e-08 | 0 | 0 |  |  | 0 | -2.7e-08 | 0 | 0
12.3 | Work of construction of self-supporting steel roofing system for a major store godown shed of span 25M at BTPS, Deepnagar. | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 1.6402 | 0.27 | 1.6376 | -1.3676 | 0 | 0 |  |  | 0 | -1.3676 | 0 | 0
0 | IDC | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 0 | 0.14918 | 0.14918 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Supply, erection, commissioning & site testing of 220 V, 2035 AH, Station Battery Sets (4 Nos.) and 24 V, 2250 AH, SG/TG & BOP Battery Sets (8 Nos.) for U# 4 & 5 along with accessories at 2 x 500 MW BTPS, Bhusawal | MERC/CAPEX/2017-2018/1226 | 2018-08-10 | 11.59 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Supply, erection, commissioning & site testing of 220V, 2035 AH Station Battery Sets (02 Nos.) and 24V, 2250AH, SG/TG & BOP Battery Set (04 Nos.) along with accessories for Unit No.5 at BTPS 2x500MW. | MERC/CAPEX/2017-2018/1226 | 2018-08-10 | 5.795 | 6.374 | 6.374 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Supply, erection, commissioning & site testing of 220V, 2035 AH Station Battery Sets (02 Nos.) and 24V, 2250AH, SG/TG & BOP Battery Set (04 Nos.) along with accessories for Unit No.4 at BTPS 2x500MW. | MERC/CAPEX/2017-2018/1226 | 2018-08-10 | 5.795 | 6.3227 | 6.3227 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Flue Gas Desulphurization (FGD) System for 500 MW Units (Total 8 Nos) of MSPGCL | MERC/CAPEX/2020-2021/WFH/SBR/45 | 2021-02-05 | 869.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | Flue Gas Desulphurization (FGD) System for Bhusawal Unit 4-5 | MERC/CAPEX/2020-2021/WFH/SBR/45 | 2021-02-05 | 830.4 | 849.16 | 849.16 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/45 | 2021-02-05 | 39.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Procurement of two BFP Cartridges & one rotor of Turbine driven BFP & at 500MW BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 10.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Procurement of two BFP Cartridges at 500MW BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 3.84 | 2.24 | 2.24 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.2 | Procurement of one rotor of Turbine driven BFP at 500MW BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 6.46 | 7.6136 | 7.6136 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 0.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | CHP Improvement Schemes at 2X500MW, BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 21.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Revamping of Apron Feeder in CHP at 2X500MW, BTPS | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 4.67 | 4.6492 | 4.6492 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.2 | Design, engineering, manufacturing, supply, Erection and commissioning of short conveyor from stack yard to belt feeder 112 in CHP 2x500MW BTPS. | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 3.53 | 3.9648 | 3.9648 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.3 | Design, engineering, manufacturing, supply, Erection and commissioning of stone grappler at Wagon Tippler No.3 in CHP 2x500MW BTPS. | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 0.84 | 0.84 | 0.84 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.4 | Procurement of suspended magnets in CHP 2x500MW BTPS. | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 2.95 | 2.947 | 2.947 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.5 | Supply, Erection And Commissioning of Electro-Mechanical Drive to Apron Feeder at CHP 500MW | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 7.57 | 7.57 | 0 | 7.57 | 0 | 0 |  |  | 0 | 7.57 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 1.66 | 0.067524 | 0.067524 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Bhusawal: Unit 4-5 (3 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 1.9468 | 1.9458 | 0.001 | 0 | 0 |  |  | 0 | 0.001 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Bhusawal: Unit 4-5 | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 3.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Advance Multipurpose Fire Tender for BTPS 4-5 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 1.7765 | 1.7765 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Normal Multipurpose Fire Tender for BTPS 4-5 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.5 | 2.1847 | 2.1847 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 10.0654 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Bhusawal: Unit 4-5 | MERC/CAPEX/20172018/0177 | 2018-02-06 | 10.0654 | 9.1854 | 9.1837 | 0.0017614 | 0 | 0 |  |  | 0 | 0.0017614 | 0 | 0
18 | Procurement of assembly of baskets for Air Pre-heater of type 31.5 VIM 2000 (72° PA), Replacement of thermal insulation of Boiler, Ducts & Steam Pipelines and Coal Mill Gear Box in 2x500MW at BTPS, Bhusawal | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 14.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Procurement of assembly of baskets for Air Preheater of type 31.5 VIM 2000 (72° PA) for Unit-4&5 | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 5.53 | 8.411 | 8.411 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.2 | Replacement of thermal insulation of Boiler, Ducts & Steam Pipelines along with supply | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 3.52 | 3.52 | 2 | 1.52 | 0 | 0 |  |  | 0 | 1.52 | 0 | 0
18.3 | Supply of XRP-1043 coal mill gearbox spares in unit-4&5. | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 5.39 | 3.7044 | 3.7044 | -2.6e-08 | 0 | 0 |  |  | 0 | -2.6e-08 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 0.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | Up-gradation of Operating System of Max DNA DCS, GE Fanuc PLC system & Schneider PLC system & Procurement of Critical Insurance spares for PA and FD fans System at 2 x 500 MW Units BTPS Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 31.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Up-gradation of Existing MaxDNA System (HMI) at 500MW BTPS, Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 8.69 | 8.69 | 8.69 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Up-gradation of GE IP (GE-Fanuc) make PLC system (HMI) installed at AHP, CPU plant, FOPH, FWPH and Mill Reject system at 2x500MW BTPS, Bhusawal. | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 1.35 | 1.2948 | 1.3538 | -0.059 | 0 | 0 |  |  | 0 | -0.059 | 0 | 0
19.3 | Up-gradation of Schneider PLC System at 2x500MW, BTPS, Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 2.33 | 2.3093 | 2.3093 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.4 | Procurement of Rotor assembly with blade set for PA and FD fan at 2 X 500 MW BTPS Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 18.18 | 16.16 | 16.16 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Improvement of Loadability and Availability of Coal Handling Plant at BTPS, Bhusawal | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Scheme-1:-Design Engineering, Supply, Erection, commissioning, Extension of travel Length & Capacity Enhancement of coal yard with additional drive system of stacker reclaimer conveyor No. 110 at in coal handling Plant BTPS. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 14.27 | 14.27 | 14.27 | 0 | 0 | 0 |  |  | 0 | 0
20.2 | Scheme-2:-Design, Engineering, Rectification, Erection & Commissioning of Z point at Conveyor 108A & B at CHP-500MW. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 8.18 | 8.18 | 8.18 | 0 | 0 | 0 |  |  | 0 | 0
20.3 | Scheme-3:-Design, Engineering and provision of material lifting arrangement for crusher floor, wobbler feeder & C-105 floor In CHP BTPS. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 1.88 | 1.88 | 1.88 | 0 | 0 | 0 |  |  | 0 | 0
20.4 | Scheme-4:-Structural up-gradation and rehabilitation of reversible yard conveyor in coal handling plant. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 4.21 | 4.21 | 4.21 | 0 | 0 | 0 |  |  | 0 | 0
20.5 | Scheme-5:-Design, Engineering, Erection and commissioning of Receiving and discharge chutes of wobbler feeders in CHP BTPS. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 6.25 | 6.25 | 6.25 | 0 | 0 | 0 |  |  | 0 | 0
20.6 | Scheme-6: Procurement of 3 Nos. of Bulldozers at BTPS, Bhusawal. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 7.35 | 7.35 | 7.35 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0.42 | 0.42 | 0 | 0 | 0 |  |  | 0 | 0
21 | Performance Improvement of Coal Handling Plant at BTPS-U4 & 5, Bhusawal | MERC/CAPEX/MSPGCL/2024-25/0310 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Scheme-1: Revamping, Modification of Gravity take-up and Drive Augmentation of Bunkering conveyor in CHP BTPS | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 11.35 | 11.35 | 11.35 | 0 | 0 | 0 |  |  | 0 | 0
21.2 | Scheme-2: Revamping of coal diverting chutes in CHP 2x500 MW BTPS | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 5.73 | 5.73 | 5.73 | 0 | 0 | 0 |  |  | 0 | 0
21.3 | Scheme-3: Revamping and structural augmentation of Reversible feeder conveyors in CHP-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 1.77 | 3.52 | 3.52 | 0 | 0 | 0 |  |  | 0 | 0
21.4 | Scheme-4: Revamping and up-gradation of air & ventilation system in Coal Handling Plant-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 9.01 | 3.85 | 3.85 | 0 | 0 | 0 |  |  | 0 | 0
21.5 | Scheme-5: Revamping, Structural & drive up-gradation of conveyor-111 in CHP-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 3.85 | 8.62 | 8.62 | 0 | 0 | 0 |  |  | 0 | 0
21.6 | Scheme-6: Revamping and structural up-gradation of conveyor system in tunnel area in Coal Handling Plant-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 8.62 | 8.06 | 8.06 | 0 | 0 | 0 |  |  | 0 | 0
21.7 | Scheme-7: Erection & Commissioning of Travelling type coal chutes in CHP BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 8.06 | 4.98 | 4.98 | 0 | 0 | 0 |  |  | 0 | 0
21.8 | Scheme-8: Revamping of scoop cooling system installed in coal handling plant BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 4.98 | 3.92 | 3.92 | 0 | 0 | 0 |  |  | 0 | 0
21.9 | Scheme-9: Retrofitting and Up-gradation of Dewatering system in CHP-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 3.92 | 9.01 | 9.01 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0.53 | 0.53 | 0 | 0 | 0 |  |  | 0 | 0
0 | Asset Transfer from Projects | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | SP Busduct Unit 4&5 | 0 | - | 0 | 0.30072 | 0.30072 | 0 | 0 | 0 |  |  | 0 | 0
0 | ESP,ID,FD,PA Fans &Other Boiler Auxiliaries | 0 | - | 0 | 1.0283 | 1.0283 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) DPR Yet to be Submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2025-26 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Up gradation of coal mill reject system, Procurement of Air heater baskets & spare Air heater gearbox at 2X500MW, Bhusawal TPS | 0 | - | 0 | 31.75 | 0 | 31.75 | 0 | 0 |  |  | 0 | 31.75
1.1 | Work of Capacity enhancement, Engineering, modification, upgradation including spares and consumables and complete commissioning including operation and comprehensive maintenance for 12 months for coal mill reject handling system in Unit-4&5, 2X500MW, BTPS, Bhusawal | 0 | - | 0 | 15.05 | 15.05 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Procurement of assembly of baskets & seals for Air Preheater of type 31.5 VIM 2000 (72° PA), in Unit-5 2x500MW, BTPS Bhusawal | 0 | - | 0 | 7.45 | 7.45 | 0 | 0 | 0 |  |  | 0 | 0
1.3 | Procurement of APH Gearbox to improve availability and performance of Air preheaters at 2 x 500 MW Units, BTPS, Bhusawal. | 0 | - | 0 | 9.25 | 9.25 | 0 | 0 | 0 |  |  | 0 | 0
2 | Boiler Reliability & Availability improvement at 2x500MW, Bhusawal TPS. | 0 | - | 0 | 83.63 | 0 | 83.63 | 0 | 0 |  |  | 0 | 83.63
2.1 | Procurement & Replacement Of LTSH Coils for Unit - 4 & 5 (500MW) TPS, Bhusawal. | 0 | - | 0 | 19.11 | 19.11 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Procurement & Replacement Of Economiser Coils For Unit - 4 & 5 (500MW) TPS, Bhusawal | 0 | - | 0 | 47.6 | 47.6 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Procurement of assembly of APH Baskets Unit-4 | 0 | - | 0 | 7.55 | 7.55 | 0 | 0 | 0 |  |  | 0 | 0
2.4 | Procurement of APH Gearbox Unit-4&5 | 0 | - | 0 | 9.37 | 9.37 | 0 | 0 | 0 |  |  | 0 | 0
3 | Various Turbine side reliability improvement schemes at 2x500MW, BTPS | 0 | - | 0 | 41.4 | 0 | 41.4 | 0 | 0 |  |  | 0 | 41.4
3.1 | Reliability improvement of Atlas copco make (mode -ZR -500) | 0 | - | 0 | 2.4 | 2.4 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Reliability improvement of HPCV Valve with procurment cone assy | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Reliability improvement of Alfa Laval make Portable COP | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
3.4 | Reliability improvement of Seal Oil System with procurement of various U Seal rings | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
3.5 | Reliability improvement of Unit-4 & 5 NDCT with replacement of PVC fills and allied work | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
3.6 | Upgradation of Chiller plant, GEHO pump house & OLTC PLC system. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
4 | IB recommended scheme related (Civil and Electrical) | 0 | - | 0 | 10.76 | 0 | 10.76 | 0 | 0 |  |  | 0 | 10.76
4.1 | Work of fabricating and erecting structural steel watch tower (10 Nos.) in major store, plant area, ash pipe line and ash bund area at BTPS, Deepnagar. | 0 | - | 0 | 0.86 | 0.86 | 0 | 0 | 0 |  |  | 0 | 0
4.2 | Work of construction of ladies frisking room for security section and visitors room near factory gate and providing at 2x500MW, BTPS, Deepnagar. | 0 | - | 0 | 0.43 | 0.43 | 0 | 0 | 0 |  |  | 0 | 0
4.3 | Work of dismantling and construction old weathered UCR compound wall on bhogawati riverside in 2x500 MW at BTPS. | 0 | - | 0 | 3.29 | 3.29 | 0 | 0 | 0 |  |  | 0 | 0
4.4 | Construcion of RCC comppund wall from remote silo to pimpri sekam railway siding cabin at BTPS | 0 | - | 0 | 2.02 | 2.02 | 0 | 0 | 0 |  |  | 0 | 0
4.5 | Installation of Highmast towers | 0 | - | 0 | 4.16 | 4.16 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2026-27 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | 0 | - | 0 | 50 | 50 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgradation of Coal feeder weighing system and revamping of Boiler side pneumatic dampers system of Hot air, cold air, FD,PA and burner tilt at Bhusawal TPS 2x500W | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Upgradation of Coal feeder weighing system at Bhusawal TPS 2x500W | 0 | - | 0 | 11.42 | 11.42 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Up-gradation of carbon monoxide analyzer in flue gas installed | 0 | - | 0 | 2.16 | 2.16 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Up- Gradation of condition monitoring & analysis system for TSI of Main Turbine , TDBFP & BOP System 2x500 MW BTPS. | 0 | - | 0 | 13.2 | 13.2 | 0 | 0 | 0 |  |  | 0 | 0
2.5 | Revamping of Boiler side pneumatic dampers system of Hot air, cold air, FD,PA and burner tilt at BTPS 2X500MW | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
2.6 | Procurement of various high pressure valves at 2x500 MW. | 0 | - | 0 | 2.22 | 2.22 | 0 | 0 | 0 |  |  | 0 | 0
3 | Schemes for Turbine side auxiliaries systems Performance & efficiency improvement schemes at 2X500MW, Bhusawal TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement of BFP Booster Pump (FA-1B-75) complete assembly (04 Nos) at 500MW BTPS, Bhusawal. | 0 | - | 0 | 3.16 | 3.16 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Procurement of Vacuum Pump complete assembly with recirculation Pump (01 No) and Impeller assembly (2 Nos) at 500MW BTPS, Bhusawal. | 0 | - | 0 | 5.2 | 5.2 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Revamping, modification of outdoor ducting of Air ventilation system at 2x500MW BTPS, Bhusawal. | 0 | - | 0 | 8.72 | 8.72 | 0 | 0 | 0 |  |  | 0 | 0
3.4 | Performance improvement of compressors | 0 | - | 0 | 12.99 | 12.99 | 0 | 0 | 0 |  |  | 0 | 0
3.5 | Centralized Water Management System at BTPS, Deepnagar, Bhusawal | 0 | - | 0 | 2.29 | 2.29 | 0 | 0 | 0 |  |  | 0 | 0
3.6 | Revamping and upgradation of Forbes Marshal make Steam & Water Analysis System Installed at 2x500MW BTPS. | 0 | - | 0 | 10.11 | 10.11 | 0 | 0 | 0 |  |  | 0 | 0
4 | Implementation of flexible operation solutions for technical minimum operation of 2x500MW, BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Implementation of flexible operation solutions for technical minimum operation of 2x500MW, BTPS. | 0 | - | 0 | 50 | 50 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2027-28 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply,Installation and commissioning of Boiler performance and reliability improvement schemes at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Procurement of M/s Torishima, Japan make, 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motors at BTPS 2x500MW. | 0 | - | 0 | 5.58 | 5.58 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Installation commissioning of Online DC Earth fault monitoring system at 220V DCDB at 500MW U-4&5. | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
1.3 | Design, supply, erection, comms. Of ID VFD & AHP transformers for 2x500MW BTPS. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
1.4 | Design,supply,installation and commissioning of Energy efficient System for illumination at BTPS 2x500MW. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
1.5 | Procurement of Main Gear unit assembly of electrical Actuators in 2x500MW BTPS | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
1.6 | Supply, erection, commissioning & site testing of 360V, 750 AH Station UPS Battery Sets along with accessories for Unit No.5 at BTPS 2x500MW. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
1.7 | Upgradation of EWLI system at Bhusawal TPS 2x500W | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
2 | Performance improvement of Bottom ash evacualtion system to reduce auxillary power consumption, water consumption & environmental pollution at 2X500MW, Bhusawal TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Modification of latest design AR 200/550 Ash slurry pump assembly including auxillaries at AHP, 2x500MW, BTPS. | 0 | - | 0 | 4.69 | 4.69 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Modification of single roll reversible clinker grinder system at AHP, 2x500MW, BTPS | 0 | - | 0 | 3.09 | 3.09 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Modification of bottom ash & coarse ash slurry pipe line disposal system at AHP 2X500 MW BTPS | 0 | - | 0 | 34.55 | 34.55 | 0 | 0 | 0 |  |  | 0 | 0
3 | Boiler Reliability & Availability improvement at 2x500MW, Bhusawal TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement of Boiler Coils (CRH &HRH) at 2x500MW BTPS. | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Procurement of ID fan impeller with shaft at 2x500 MW BTPS. | 0 | - | 0 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Procurement SH,RH,MS outlet valves with actuator and motor at 2x500 MW BTPS. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
4 | CHP Infrastructure Development Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Supply, installation and commissioning PLC system on a single platform to match with external aspect & process improvement at CHP 2x500MW BTPS. | 0 | - | 0 | 18.4 | 18.4 | 0 | 0 | 0 |  |  | 0 | 0
4.2 | Supply, installation, retrofitting and commissioning of HT breaker at HT Switchgear in CHP 2x500MW BTPS | 0 | - | 0 | 6.9 | 6.9 | 0 | 0 | 0 |  |  | 0 | 0
4.3 | Supply, installation, retrofitting and commissioning of LT breaker at LT Switchgear in CHP 2x500MW BTPS. | 0 | - | 0 | 4.4 | 4.4 | 0 | 0 | 0 |  |  | 0 | 0
4.4 | Supply, Installation & Commissioning of Magnetic Separators at CHP 2x 500MW BTPS Deepnagar | 0 | - | 0 | 3.73 | 3.73 | 0 | 0 | 0 |  |  | 0 | 0
4.5 | Supply, Installation & Commissioning Flameproof lighting at CHP 2x 500MW BTPS Deepnagar | 0 | - | 0 | 10.47 | 10.47 | 0 | 0 | 0 |  |  | 0 | 0
4.6 | Supply, Installation & upgradation of HT /LT relay at CHP BTPS. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
5 | Detail Project report of improvement of Unloading in Coal handling Plant BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Procurement of 04 no of locomotives for Coal handling Plant BTPS. | 0 | - | 0 | 13.68 | 13.68 | 0 | 0 | 0 |  |  | 0 | 0
5.2 | Design Supply Erection and Comission of Hour glass shape Coal diverting chutes with extra life wear resistant plates in CHP, BTPS. | 0 | - | 0 | 5.67 | 5.67 | 0 | 0 | 0 |  |  | 0 | 0
5.3 | Design Supply Erection and Comission of Inverted Y Shape Coal diverting chutes with extra life wear resistant plates in CHP, BTPS. | 0 | - | 0 | 4.72 | 4.72 | 0 | 0 | 0 |  |  | 0 | 0
5.4 | Design Supply Erection and Comission of coal diverting chutes with extra life wear resistant plates in CHP BTPS. | 0 | - | 0 | 4.72 | 4.72 | 0 | 0 | 0 |  |  | 0 | 0
5.5 | Work of Revamping and structural up-gradation of conveyor 104A&B in Coal Handling Plant-BTPS. | 0 | - | 0 | 7.1 | 7.1 | 0 | 0 | 0 |  |  | 0 | 0
6 | Supply and Installation of reliability improvement schemes for HT/LT switchgears and auxilliaries at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Procurement of HT Motors of various ratings at 2x500MW. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
6.2 | Procurement of Dry type transformers of varoius ratings at 2x500MW. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
6.3 | Procurement of Inverter and converter trolleys of GEHO Pump at 2x500MW. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
6.4 | Procurement of Vacuum Contactors of various ratings for HT Switchgears at BTPS 2x500MW. | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
6.5 | Supply, erection, commissioning & site testing of 360V, 750 AH Station UPS Battery Sets along with accessories for Unit No.4 at BTPS 2x500MW’. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
6.6 | Updragation of Sox-Nox analyzer,PM analyzer, ETP analyzer at BTPS 2X500MW. | 0 | - | 0 | 1.05 | 1.05 | 0 | 0 | 0 |  |  | 0 | 0
6.7 | Upgradation of O2 analyzer at BTPS 2X500MW | 0 | - | 0 | 3.4 | 3.4 | 0 | 0 | 0 |  |  | 0 | 0
6.8 | Revamping & Upgradation Of Vibration Monitoring Rack From VM7 TO VM7B at BTPS 2X500MW | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
6.9 | Procurement & Installation of High Mast towers in various location in BTPS | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Renovation and Modification of Colony Electric Supply System to improve availability and reliability of supply system at BTPS Colony, Deepnagar | 0 | - | 0 | 15.85 | 15.85 | 0 | 0 | 0 |  |  | 0 | 0
6.11 | Work of Overhauling repairs of U-5 350KW BCWP motor of M/s Torishima make at BTPS 2x500MW. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2028-29 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | APH baskets with main drive Gear box and lub oil skids with motor at 2x500MW BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | APH baskets with main drive Gear box and lub oil skids with motor at 2x500MW BTPS | 0 | - | 0 | 0 | 0 | 0 | 50 | 50 |  |  | 50 | 0
2 | Detail Project Report for Design, Engineering, Supply, Installation and commissioning of 1500TPH Stacker cum re-claimer in Coal Handling Plant-BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Design, Engineering, Supply, Installation and commissioning of 1500TPH Stacker cum re-claimer in Coal Handling Plant-BTPS. | 0 | - | 0 | 0 | 0 | 0 | 118 | 118 |  |  | 118 | 0
3 | Enhancement of Unloading & Stacking Capacity of CHP. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Design Supply errection & Comissioning of Open Wagon Tippler along with stacking and reclaiming yard conveyors at CHP stack yard. | 0 | - | 0 | 0 | 0 | 0 | 89 | 89 |  |  | 89 | 0
0 | FY 2029-30 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgradation rail track in CHP -BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Revamping and Upgradation of rail track from 52KG to 60KG in CHP-BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Contract for modification of Wobbler feeder in CHP-2X500MW | 0 | - | 0 | 1.4733 | 1.4733 | 0 | 0 | 0 |  |  | 0 | 0
2 | Contract for Revamping of Apron Feeder in CHP-2X500MW | 0 | - | 0 | 2.3246 | 2.3246 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of double lip skirt sealing & tracking idler in CHP at 2x500MW, BTPS | 0 | - | 0 | 0.57025 | 0.57025 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, erection & commissioning of vibrating feeder in CHP at 2x500MW, BTPS | 0 | - | 0 | 0.57796 | 0.57796 | 0 | 0 | 0 |  |  | 0 | 0
5 | Coal chutes with extra life wear resistance plates in CHP at 2X500MW | 0 | - | 0 | 2.0319 | 2.0319 | 0 | 0 | 0 |  |  | 0 | 0
6 | Epoxy Painting upto all height to structural steel work in main plant boiler side area and CHP area | 0 | - | 0 | 5.8625 | 5.8625 | 0 | 0 | 0 |  |  | 0 | 0
7 | Rectification of Belt feeder & Gravity Take-up in CHP-2X500MW. | 0 | - | 0 | 1.6479 | 1.6479 | 0 | 0 | 0 |  |  | 0 | 0
8 | Coal diverting chutes in CHP at 2X500MW. | 0 | - | 0 | 2.2184 | 2.2184 | 0 | 0 | 0 |  |  | 0 | 0
9 | Supply of Conveyor Pulleys with Ceramic lagging at CHP-2X500MW, BTPS, Bhusawal | 0 | - | 0 | 0.58051 | 0.58051 | 0 | 0 | 0 |  |  | 0 | 0
10 | Non-DPR Project Report for Design, Supply,Erection & Commissioning of High Performance Energy Chain System for Side Arm Charger at 2x500 at CHP | 0 | - | 0 | 1.5015 | 1.5015 | 0 | 0 | 0 |  |  | 0 | 0
11 | Implementation of Energy Conservation Demonstration Project in buildings of BTPS 2x500MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Installation of Fire & Explosion Prevention system at Bhusawal 500MW Unit-4. | 0 | - | 0 | 2.4539 | 2.4539 | 0 | 0 | 0 |  |  | 0 | 0
13 | Fixtures & Fitting (10801) | 0 | - | 0 | 0.21334 | 0.21334 | 0 | 0 | 0 |  |  | 0 | 0
14 | Office equpment (10901) | 0 | - | 0 | 0.22996 | 0.22996 | 0 | 0 | 0 |  |  | 0 | 0
15 | 150 W & 40 W LED FIXTURES AT TG HOUSE BUILDING 2X500MW | 0 | - | 0 | 0.52807 | 0.27807 | 0.25 | 0 | 0 |  |  | 0 | 0.25
16 | JUMBO DEESERT AIR COOLERS FOR POWER TRANSFORERS | 0 | - | 0 | 0.10143 | 0.10143 | 0 | 0 | 0 |  |  | 0 | 0
17 | GEN ASSET (ALMIRAH,TABLE & CHAIR) (10801) | 0 | - | 0 | 0.23454 | 0.23454 | 0 | 0 | 0 |  |  | 0 | 0
18 | LAPTOP, 50 INCH TV,PRINTER,PROJECTOR,DESKTOP,UPS & ETS. (10901) | 0 | - | 0 | 0.55035 | 0.55035 | 0 | 0 | 0 |  |  | 0 | 0
19 | RESTAURANT EQUIP COMPOSTING MACHINE | 0 | - | 0 | 0.05049 | 0.05049 | 0 | 0 | 0 |  |  | 0
20 | OFFICE TABLE,STORGE RACK,FAN | 0 | - | 0 | 0.57869 | 0.57869 | 0 | 0 | 0 |  |  | 0
21 | CAMERAS | 0 | - | 0 | 0.038468 | 0.038468 | 0 | 0 | 0 |  |  | 0
22 | VELHALA ASH BUND RD WORK | 0 | - | 0 | 2.4645 | 2.4645 | 0 | 0 | 0 |  |  | 0
23 | CONCERETE ROAD FROM DIESEL PUMP TO 500MW FACTORY G | 0 | - | 0 | 0.98449 | 0.98449 | 0 | 0 | 0 |  |  | 0
24 | Admin Building | 0 | - | 0 | 0.05175 | 0 | 0.05175 | 0 | 0 |  |  | 0
25 | Furniture & Fixture | 0 | - | 0 | 0.13712 | 0.13712 | 0 | 0 | 0 |  |  | 0
26 | Office Equipment | 0 | - | 0 | 0.14424 | 0.14424 | 0 | 0 | 0 |  |  | 0
27 | Furniture & Fixture | 0 | - | 0 | 0.073968 | 0.073968 | 0 | 0 | 0 |  |  | 0
28 | Office Equipment | 0 | - | 0 | 0.15891 | 0.15891 | 0 | 0 | 0 |  |  | 0
29 | Work of repairs of 350 KW BCWP-4B & BCWP-5B motor of M/s. Torishima make at BTPS 2x500 MW | 0 | - | 0 | 4.8465 | 4.8465 | 0 | 0 | 0 |  |  | 0
30 | ABC Powder Type and Foam Type Composite Fire Extinguisher | 0 | - | 0 | 0.58548 | 0.58548 | 0 | 0 | 0 |  |  | 0
31 | Withdrawal of capex from Project (LD - Passenger Lifts) | 0 | - | 0 | 0 | -0.13899 | 0.13899 | 0 | 0 |  |  | 0
| Total |  |  |  | 1961.4105 | 1785.7397 | 175.6708 | 257 | 257 | 0 | 0 | 257 | 175.48
FY 2029-30
a) DPR Schemes
(i) Submitted to MERC
7 | Interconnection of 210 MW CHP to 500 MW CHP through Conveyors BC-02 & BC-03 having capacity of 500 TPH | MERC/CAPEX/20162017/00227 | 2016-05-24 | 24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Interconnection of 210 MW CHP to 500 MW CHP through Conveyors BC-02 & BC-03 having capacity of 500 TPH | MERC/CAPEX/20162017/00227 | 2016-05-24 | 22.73 | 19.1067 | 19.1067 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/00227 | 2016-05-24 | 1.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Stack management by procurement of Bulldozer & LOCO and CHP area schemes for performance & unloading improvement | MERC/CAPEX/20162017/01426 | 2017-02-02 | 9.9669 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement of Locomotive 800 HP (2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 4.9504 | 4.8261 | 4.8261 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Procurement of 2 No’s of Bulldozer Model D-155(2 No.’s) | MERC/CAPEX/20162017/01426 | 2017-02-02 | 2.562 | 3.4747 | 3.4747 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.3 | Modification below primary crusher chutes 15A/B & Conv.02 | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.42975 | 0.38033 | 0.38033 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.4 | New helical gear box for various conveyors | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.79339 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.5 | Procurement of Elecon Make Ring Granulator Type TK-09-38B | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.53719 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.6 | Procurement of Elecon Make Ring Granulator Type TK6 32B Ring Granulator | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.33884 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01426 | 2017-02-02 | 0.35537 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Construction of 1st raising of Ash bund from T.B.L. 258M to 264M at Bhusawal TPS | MERC/CAPEX/20172018/4267 | 2017-09-28 | 64.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Construction of 1st raising of Ash bund from T.B.L. 258M to 264M at Bhusawal TPS | MERC/CAPEX/20172018/4267 | 2017-09-28 | 64.22 | 64.4982 | 64.4982 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Augmentation of Ash Evacuation System & Procurement of BCW Pump Motors at Bhusawal & Khaperkheda TPS 500 MW Units | MERC/CAPEX/20172018/4782 | 2017-11-28 | 17.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Installation of standby Buffer Hopper parallel to existing pair of buffer hoppers | MERC/CAPEX/20172018/4782 | 2017-11-28 | 11.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | Installation of additional vacuum pump for every two passes, near to intermediate hopper. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.3 | Procurement of 02 Nos of M/s Torishima, Japan make, 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motors (without pump casing) with 02 lots of recommended Electrical & C&I spares for Bhusawal and Khaparkheda TPS 500MW. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 4.24 | 4.6696 | 4.6696 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.4 | Procurement of complete ACVF drive module comprising of 2 Nos. of Supply and 3 Nos. of Inverter modules for GEHO pumps | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0.95 | 0.92864 | 0.92864 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.5 | Supply, erection and commissioning of 24VDC, 100A Float & Float cum Boost Battery Charger with 325Ah Battery Bank for CWPH at BTPS 2x500 MW. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0.15 | 0.15788 | 0.15788 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Various schemes for renovation of colony at Bhusawal TPS | MERC/CAPEX/20172018/0221 | 2018-02-12 | 19.3341 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Renovation of staff quarters & related work at BTPS Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 7.021 | 5.4584 | 5.4584 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Colony Internal Roads at BTPS, Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 3.85 | 3.2501 | 3.2514 | -0.001329 | 0 | 0 |  |  | 0 | -0.001329 | 0 | 0
11.3 | Water supply , sanitary & drainage works at BTPS, Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 7.3 | 5.8361 | 5.8109 | 0.025229 | 0 | 0 |  |  | 0 | 0.025229 | 0 | 0
11.4 | Plinth protection to existing buildings at BTPS, Deepnagar | MERC/CAPEX/20172018/0221 | 2018-02-12 | 1.1631 | 0.91823 | 0.91823 | -2.2e-08 | 0 | 0 |  |  | 0 | -2.2e-08 | 0 | 0
12 | Pipeline from River Water Pump House (RWPH) to aquaduct over Bhogawati River and Other allied power house road works under DPR scheme at BTPS, Bhusawal | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 13.1172 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Providing supplying laying, jointing, testing and commissioning of 1650 mm Ø ID 8 mm thick M.S. pipeline for raw water supply from RWPH to aquaduct over Bhogawati river at, BTPS, Bhusawal. | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 7.257 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.2 | Construction of WBM and Bituminous road along inlet & outlet canals and concreate road along periphery of Major store at BTPS, Bhusawal. | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 4.22 | 3.8305 | 3.8305 | -2.7e-08 | 0 | 0 |  |  | 0 | -2.7e-08 | 0 | 0
12.3 | Work of construction of self-supporting steel roofing system for a major store godown shed of span 25M at BTPS, Deepnagar. | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 1.6402 | 0.27 | 1.6376 | -1.3676 | 0 | 0 |  |  | 0 | -1.3676 | 0 | 0
0 | IDC | MERC/CAPEX/2018-2019/0104 | 2019-04-04 | 0 | 0.14918 | 0.14918 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Supply, erection, commissioning & site testing of 220 V, 2035 AH, Station Battery Sets (4 Nos.) and 24 V, 2250 AH, SG/TG & BOP Battery Sets (8 Nos.) for U# 4 & 5 along with accessories at 2 x 500 MW BTPS, Bhusawal | MERC/CAPEX/2017-2018/1226 | 2018-08-10 | 11.59 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Supply, erection, commissioning & site testing of 220V, 2035 AH Station Battery Sets (02 Nos.) and 24V, 2250AH, SG/TG & BOP Battery Set (04 Nos.) along with accessories for Unit No.5 at BTPS 2x500MW. | MERC/CAPEX/2017-2018/1226 | 2018-08-10 | 5.795 | 6.374 | 6.374 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Supply, erection, commissioning & site testing of 220V, 2035 AH Station Battery Sets (02 Nos.) and 24V, 2250AH, SG/TG & BOP Battery Set (04 Nos.) along with accessories for Unit No.4 at BTPS 2x500MW. | MERC/CAPEX/2017-2018/1226 | 2018-08-10 | 5.795 | 6.3227 | 6.3227 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Flue Gas Desulphurization (FGD) System for 500 MW Units (Total 8 Nos) of MSPGCL | MERC/CAPEX/2020-2021/WFH/SBR/45 | 2021-02-05 | 869.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | Flue Gas Desulphurization (FGD) System for Bhusawal Unit 4-5 | MERC/CAPEX/2020-2021/WFH/SBR/45 | 2021-02-05 | 830.4 | 849.16 | 849.16 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/45 | 2021-02-05 | 39.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Procurement of two BFP Cartridges & one rotor of Turbine driven BFP & at 500MW BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 10.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Procurement of two BFP Cartridges at 500MW BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 3.84 | 2.24 | 2.24 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.2 | Procurement of one rotor of Turbine driven BFP at 500MW BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 6.46 | 7.6136 | 7.6136 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFO/SBR/49 | 2021-03-08 | 0.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | CHP Improvement Schemes at 2X500MW, BTPS, Bhusawal | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 21.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Revamping of Apron Feeder in CHP at 2X500MW, BTPS | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 4.67 | 4.6492 | 4.6492 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.2 | Design, engineering, manufacturing, supply, Erection and commissioning of short conveyor from stack yard to belt feeder 112 in CHP 2x500MW BTPS. | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 3.53 | 3.9648 | 3.9648 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.3 | Design, engineering, manufacturing, supply, Erection and commissioning of stone grappler at Wagon Tippler No.3 in CHP 2x500MW BTPS. | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 0.84 | 0.84 | 0.84 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.4 | Procurement of suspended magnets in CHP 2x500MW BTPS. | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 2.95 | 2.947 | 2.947 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.5 | Supply, Erection And Commissioning of Electro-Mechanical Drive to Apron Feeder at CHP 500MW | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 7.57 | 7.57 | 0 | 7.57 | 0 | 0 |  |  | 0 | 7.57 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/09 | 2021-06-10 | 1.66 | 0.067524 | 0.067524 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Bhusawal: Unit 4-5 (3 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 1.9468 | 1.9458 | 0.001 | 0 | 0 |  |  | 0 | 0.001 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Bhusawal: Unit 4-5 | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 3.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Advance Multipurpose Fire Tender for BTPS 4-5 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 1.7765 | 1.7765 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Normal Multipurpose Fire Tender for BTPS 4-5 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.5 | 2.1847 | 2.1847 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 10.0654 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Bhusawal: Unit 4-5 | MERC/CAPEX/20172018/0177 | 2018-02-06 | 10.0654 | 9.1854 | 9.1837 | 0.0017614 | 0 | 0 |  |  | 0 | 0.0017614 | 0 | 0
18 | Procurement of assembly of baskets for Air Pre-heater of type 31.5 VIM 2000 (72° PA), Replacement of thermal insulation of Boiler, Ducts & Steam Pipelines and Coal Mill Gear Box in 2x500MW at BTPS, Bhusawal | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 14.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Procurement of assembly of baskets for Air Preheater of type 31.5 VIM 2000 (72° PA) for Unit-4&5 | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 5.53 | 8.411 | 8.411 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.2 | Replacement of thermal insulation of Boiler, Ducts & Steam Pipelines along with supply | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 3.52 | 3.52 | 2 | 1.52 | 0 | 0 |  |  | 0 | 1.52 | 0 | 0
18.3 | Supply of XRP-1043 coal mill gearbox spares in unit-4&5. | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 5.39 | 3.7044 | 3.7044 | -2.6e-08 | 0 | 0 |  |  | 0 | -2.6e-08 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/ SBR/ 15 | 2021-09-22 | 0.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | Up-gradation of Operating System of Max DNA DCS, GE Fanuc PLC system & Schneider PLC system & Procurement of Critical Insurance spares for PA and FD fans System at 2 x 500 MW Units BTPS Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 31.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Up-gradation of Existing MaxDNA System (HMI) at 500MW BTPS, Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 8.69 | 8.69 | 8.69 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Up-gradation of GE IP (GE-Fanuc) make PLC system (HMI) installed at AHP, CPU plant, FOPH, FWPH and Mill Reject system at 2x500MW BTPS, Bhusawal. | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 1.35 | 1.2948 | 1.3538 | -0.059 | 0 | 0 |  |  | 0 | -0.059 | 0 | 0
19.3 | Up-gradation of Schneider PLC System at 2x500MW, BTPS, Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 2.33 | 2.3093 | 2.3093 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.4 | Procurement of Rotor assembly with blade set for PA and FD fan at 2 X 500 MW BTPS Bhusawal | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 18.18 | 16.16 | 16.16 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/0178 | 2024-03-11 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Improvement of Loadability and Availability of Coal Handling Plant at BTPS, Bhusawal | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Scheme-1:-Design Engineering, Supply, Erection, commissioning, Extension of travel Length & Capacity Enhancement of coal yard with additional drive system of stacker reclaimer conveyor No. 110 at in coal handling Plant BTPS. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 14.27 | 14.27 | 14.27 | 0 | 0 | 0 |  |  | 0 | 0
20.2 | Scheme-2:-Design, Engineering, Rectification, Erection & Commissioning of Z point at Conveyor 108A & B at CHP-500MW. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 8.18 | 8.18 | 8.18 | 0 | 0 | 0 |  |  | 0 | 0
20.3 | Scheme-3:-Design, Engineering and provision of material lifting arrangement for crusher floor, wobbler feeder & C-105 floor In CHP BTPS. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 1.88 | 1.88 | 1.88 | 0 | 0 | 0 |  |  | 0 | 0
20.4 | Scheme-4:-Structural up-gradation and rehabilitation of reversible yard conveyor in coal handling plant. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 4.21 | 4.21 | 4.21 | 0 | 0 | 0 |  |  | 0 | 0
20.5 | Scheme-5:-Design, Engineering, Erection and commissioning of Receiving and discharge chutes of wobbler feeders in CHP BTPS. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 6.25 | 6.25 | 6.25 | 0 | 0 | 0 |  |  | 0 | 0
20.6 | Scheme-6: Procurement of 3 Nos. of Bulldozers at BTPS, Bhusawal. | MERC/CAPEX/MSPGCL/2024-25/0309 | 2024-05-17 | 7.35 | 7.35 | 7.35 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0.42 | 0.42 | 0 | 0 | 0 |  |  | 0 | 0
21 | Performance Improvement of Coal Handling Plant at BTPS-U4 & 5, Bhusawal | MERC/CAPEX/MSPGCL/2024-25/0310 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Scheme-1: Revamping, Modification of Gravity take-up and Drive Augmentation of Bunkering conveyor in CHP BTPS | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 11.35 | 11.35 | 11.35 | 0 | 0 | 0 |  |  | 0 | 0
21.2 | Scheme-2: Revamping of coal diverting chutes in CHP 2x500 MW BTPS | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 5.73 | 5.73 | 5.73 | 0 | 0 | 0 |  |  | 0 | 0
21.3 | Scheme-3: Revamping and structural augmentation of Reversible feeder conveyors in CHP-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 1.77 | 3.52 | 3.52 | 0 | 0 | 0 |  |  | 0 | 0
21.4 | Scheme-4: Revamping and up-gradation of air & ventilation system in Coal Handling Plant-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 9.01 | 3.85 | 3.85 | 0 | 0 | 0 |  |  | 0 | 0
21.5 | Scheme-5: Revamping, Structural & drive up-gradation of conveyor-111 in CHP-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 3.85 | 8.62 | 8.62 | 0 | 0 | 0 |  |  | 0 | 0
21.6 | Scheme-6: Revamping and structural up-gradation of conveyor system in tunnel area in Coal Handling Plant-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 8.62 | 8.06 | 8.06 | 0 | 0 | 0 |  |  | 0 | 0
21.7 | Scheme-7: Erection & Commissioning of Travelling type coal chutes in CHP BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 8.06 | 4.98 | 4.98 | 0 | 0 | 0 |  |  | 0 | 0
21.8 | Scheme-8: Revamping of scoop cooling system installed in coal handling plant BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 4.98 | 3.92 | 3.92 | 0 | 0 | 0 |  |  | 0 | 0
21.9 | Scheme-9: Retrofitting and Up-gradation of Dewatering system in CHP-BTPS. | MERC/CAPEX/MSPGCL/2024-25/0310 | 2024-05-17 | 3.92 | 9.01 | 9.01 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0.53 | 0.53 | 0 | 0 | 0 |  |  | 0 | 0
0 | Asset Transfer from Projects | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | SP Busduct Unit 4&5 | 0 | - | 0 | 0.30072 | 0.30072 | 0 | 0 | 0 |  |  | 0 | 0
0 | ESP,ID,FD,PA Fans &Other Boiler Auxiliaries | 0 | - | 0 | 1.0283 | 1.0283 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) DPR Yet to be Submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2025-26 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Up gradation of coal mill reject system, Procurement of Air heater baskets & spare Air heater gearbox at 2X500MW, Bhusawal TPS | 0 | - | 0 | 31.75 | 0 | 31.75 | 0 | 0 |  |  | 0 | 31.75
1.1 | Work of Capacity enhancement, Engineering, modification, upgradation including spares and consumables and complete commissioning including operation and comprehensive maintenance for 12 months for coal mill reject handling system in Unit-4&5, 2X500MW, BTPS, Bhusawal | 0 | - | 0 | 15.05 | 15.05 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Procurement of assembly of baskets & seals for Air Preheater of type 31.5 VIM 2000 (72° PA), in Unit-5 2x500MW, BTPS Bhusawal | 0 | - | 0 | 7.45 | 7.45 | 0 | 0 | 0 |  |  | 0 | 0
1.3 | Procurement of APH Gearbox to improve availability and performance of Air preheaters at 2 x 500 MW Units, BTPS, Bhusawal. | 0 | - | 0 | 9.25 | 9.25 | 0 | 0 | 0 |  |  | 0 | 0
2 | Boiler Reliability & Availability improvement at 2x500MW, Bhusawal TPS. | 0 | - | 0 | 83.63 | 0 | 83.63 | 0 | 0 |  |  | 0 | 83.63
2.1 | Procurement & Replacement Of LTSH Coils for Unit - 4 & 5 (500MW) TPS, Bhusawal. | 0 | - | 0 | 19.11 | 19.11 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Procurement & Replacement Of Economiser Coils For Unit - 4 & 5 (500MW) TPS, Bhusawal | 0 | - | 0 | 47.6 | 47.6 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Procurement of assembly of APH Baskets Unit-4 | 0 | - | 0 | 7.55 | 7.55 | 0 | 0 | 0 |  |  | 0 | 0
2.4 | Procurement of APH Gearbox Unit-4&5 | 0 | - | 0 | 9.37 | 9.37 | 0 | 0 | 0 |  |  | 0 | 0
3 | Various Turbine side reliability improvement schemes at 2x500MW, BTPS | 0 | - | 0 | 41.4 | 0 | 41.4 | 0 | 0 |  |  | 0 | 41.4
3.1 | Reliability improvement of Atlas copco make (mode -ZR -500) | 0 | - | 0 | 2.4 | 2.4 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Reliability improvement of HPCV Valve with procurment cone assy | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Reliability improvement of Alfa Laval make Portable COP | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
3.4 | Reliability improvement of Seal Oil System with procurement of various U Seal rings | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
3.5 | Reliability improvement of Unit-4 & 5 NDCT with replacement of PVC fills and allied work | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
3.6 | Upgradation of Chiller plant, GEHO pump house & OLTC PLC system. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
4 | IB recommended scheme related (Civil and Electrical) | 0 | - | 0 | 10.76 | 0 | 10.76 | 0 | 0 |  |  | 0 | 10.76
4.1 | Work of fabricating and erecting structural steel watch tower (10 Nos.) in major store, plant area, ash pipe line and ash bund area at BTPS, Deepnagar. | 0 | - | 0 | 0.86 | 0.86 | 0 | 0 | 0 |  |  | 0 | 0
4.2 | Work of construction of ladies frisking room for security section and visitors room near factory gate and providing at 2x500MW, BTPS, Deepnagar. | 0 | - | 0 | 0.43 | 0.43 | 0 | 0 | 0 |  |  | 0 | 0
4.3 | Work of dismantling and construction old weathered UCR compound wall on bhogawati riverside in 2x500 MW at BTPS. | 0 | - | 0 | 3.29 | 3.29 | 0 | 0 | 0 |  |  | 0 | 0
4.4 | Construcion of RCC comppund wall from remote silo to pimpri sekam railway siding cabin at BTPS | 0 | - | 0 | 2.02 | 2.02 | 0 | 0 | 0 |  |  | 0 | 0
4.5 | Installation of Highmast towers | 0 | - | 0 | 4.16 | 4.16 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2026-27 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | 0 | - | 0 | 50 | 50 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgradation of Coal feeder weighing system and revamping of Boiler side pneumatic dampers system of Hot air, cold air, FD,PA and burner tilt at Bhusawal TPS 2x500W | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Upgradation of Coal feeder weighing system at Bhusawal TPS 2x500W | 0 | - | 0 | 11.42 | 11.42 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Up-gradation of carbon monoxide analyzer in flue gas installed | 0 | - | 0 | 2.16 | 2.16 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Up- Gradation of condition monitoring & analysis system for TSI of Main Turbine , TDBFP & BOP System 2x500 MW BTPS. | 0 | - | 0 | 13.2 | 13.2 | 0 | 0 | 0 |  |  | 0 | 0
2.5 | Revamping of Boiler side pneumatic dampers system of Hot air, cold air, FD,PA and burner tilt at BTPS 2X500MW | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
2.6 | Procurement of various high pressure valves at 2x500 MW. | 0 | - | 0 | 2.22 | 2.22 | 0 | 0 | 0 |  |  | 0 | 0
3 | Schemes for Turbine side auxiliaries systems Performance & efficiency improvement schemes at 2X500MW, Bhusawal TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement of BFP Booster Pump (FA-1B-75) complete assembly (04 Nos) at 500MW BTPS, Bhusawal. | 0 | - | 0 | 3.16 | 3.16 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Procurement of Vacuum Pump complete assembly with recirculation Pump (01 No) and Impeller assembly (2 Nos) at 500MW BTPS, Bhusawal. | 0 | - | 0 | 5.2 | 5.2 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Revamping, modification of outdoor ducting of Air ventilation system at 2x500MW BTPS, Bhusawal. | 0 | - | 0 | 8.72 | 8.72 | 0 | 0 | 0 |  |  | 0 | 0
3.4 | Performance improvement of compressors | 0 | - | 0 | 12.99 | 12.99 | 0 | 0 | 0 |  |  | 0 | 0
3.5 | Centralized Water Management System at BTPS, Deepnagar, Bhusawal | 0 | - | 0 | 2.29 | 2.29 | 0 | 0 | 0 |  |  | 0 | 0
3.6 | Revamping and upgradation of Forbes Marshal make Steam & Water Analysis System Installed at 2x500MW BTPS. | 0 | - | 0 | 10.11 | 10.11 | 0 | 0 | 0 |  |  | 0 | 0
4 | Implementation of flexible operation solutions for technical minimum operation of 2x500MW, BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Implementation of flexible operation solutions for technical minimum operation of 2x500MW, BTPS. | 0 | - | 0 | 50 | 50 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2027-28 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply,Installation and commissioning of Boiler performance and reliability improvement schemes at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Procurement of M/s Torishima, Japan make, 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motors at BTPS 2x500MW. | 0 | - | 0 | 5.58 | 5.58 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Installation commissioning of Online DC Earth fault monitoring system at 220V DCDB at 500MW U-4&5. | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
1.3 | Design, supply, erection, comms. Of ID VFD & AHP transformers for 2x500MW BTPS. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
1.4 | Design,supply,installation and commissioning of Energy efficient System for illumination at BTPS 2x500MW. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
1.5 | Procurement of Main Gear unit assembly of electrical Actuators in 2x500MW BTPS | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
1.6 | Supply, erection, commissioning & site testing of 360V, 750 AH Station UPS Battery Sets along with accessories for Unit No.5 at BTPS 2x500MW. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
1.7 | Upgradation of EWLI system at Bhusawal TPS 2x500W | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
2 | Performance improvement of Bottom ash evacualtion system to reduce auxillary power consumption, water consumption & environmental pollution at 2X500MW, Bhusawal TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Modification of latest design AR 200/550 Ash slurry pump assembly including auxillaries at AHP, 2x500MW, BTPS. | 0 | - | 0 | 4.69 | 4.69 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Modification of single roll reversible clinker grinder system at AHP, 2x500MW, BTPS | 0 | - | 0 | 3.09 | 3.09 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Modification of bottom ash & coarse ash slurry pipe line disposal system at AHP 2X500 MW BTPS | 0 | - | 0 | 34.55 | 34.55 | 0 | 0 | 0 |  |  | 0 | 0
3 | Boiler Reliability & Availability improvement at 2x500MW, Bhusawal TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement of Boiler Coils (CRH &HRH) at 2x500MW BTPS. | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Procurement of ID fan impeller with shaft at 2x500 MW BTPS. | 0 | - | 0 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Procurement SH,RH,MS outlet valves with actuator and motor at 2x500 MW BTPS. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
4 | CHP Infrastructure Development Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Supply, installation and commissioning PLC system on a single platform to match with external aspect & process improvement at CHP 2x500MW BTPS. | 0 | - | 0 | 18.4 | 18.4 | 0 | 0 | 0 |  |  | 0 | 0
4.2 | Supply, installation, retrofitting and commissioning of HT breaker at HT Switchgear in CHP 2x500MW BTPS | 0 | - | 0 | 6.9 | 6.9 | 0 | 0 | 0 |  |  | 0 | 0
4.3 | Supply, installation, retrofitting and commissioning of LT breaker at LT Switchgear in CHP 2x500MW BTPS. | 0 | - | 0 | 4.4 | 4.4 | 0 | 0 | 0 |  |  | 0 | 0
4.4 | Supply, Installation & Commissioning of Magnetic Separators at CHP 2x 500MW BTPS Deepnagar | 0 | - | 0 | 3.73 | 3.73 | 0 | 0 | 0 |  |  | 0 | 0
4.5 | Supply, Installation & Commissioning Flameproof lighting at CHP 2x 500MW BTPS Deepnagar | 0 | - | 0 | 10.47 | 10.47 | 0 | 0 | 0 |  |  | 0 | 0
4.6 | Supply, Installation & upgradation of HT /LT relay at CHP BTPS. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
5 | Detail Project report of improvement of Unloading in Coal handling Plant BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Procurement of 04 no of locomotives for Coal handling Plant BTPS. | 0 | - | 0 | 13.68 | 13.68 | 0 | 0 | 0 |  |  | 0 | 0
5.2 | Design Supply Erection and Comission of Hour glass shape Coal diverting chutes with extra life wear resistant plates in CHP, BTPS. | 0 | - | 0 | 5.67 | 5.67 | 0 | 0 | 0 |  |  | 0 | 0
5.3 | Design Supply Erection and Comission of Inverted Y Shape Coal diverting chutes with extra life wear resistant plates in CHP, BTPS. | 0 | - | 0 | 4.72 | 4.72 | 0 | 0 | 0 |  |  | 0 | 0
5.4 | Design Supply Erection and Comission of coal diverting chutes with extra life wear resistant plates in CHP BTPS. | 0 | - | 0 | 4.72 | 4.72 | 0 | 0 | 0 |  |  | 0 | 0
5.5 | Work of Revamping and structural up-gradation of conveyor 104A&B in Coal Handling Plant-BTPS. | 0 | - | 0 | 7.1 | 7.1 | 0 | 0 | 0 |  |  | 0 | 0
6 | Supply and Installation of reliability improvement schemes for HT/LT switchgears and auxilliaries at BTPS 2x500MW. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Procurement of HT Motors of various ratings at 2x500MW. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
6.2 | Procurement of Dry type transformers of varoius ratings at 2x500MW. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
6.3 | Procurement of Inverter and converter trolleys of GEHO Pump at 2x500MW. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
6.4 | Procurement of Vacuum Contactors of various ratings for HT Switchgears at BTPS 2x500MW. | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
6.5 | Supply, erection, commissioning & site testing of 360V, 750 AH Station UPS Battery Sets along with accessories for Unit No.4 at BTPS 2x500MW’. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
6.6 | Updragation of Sox-Nox analyzer,PM analyzer, ETP analyzer at BTPS 2X500MW. | 0 | - | 0 | 1.05 | 1.05 | 0 | 0 | 0 |  |  | 0 | 0
6.7 | Upgradation of O2 analyzer at BTPS 2X500MW | 0 | - | 0 | 3.4 | 3.4 | 0 | 0 | 0 |  |  | 0 | 0
6.8 | Revamping & Upgradation Of Vibration Monitoring Rack From VM7 TO VM7B at BTPS 2X500MW | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
6.9 | Procurement & Installation of High Mast towers in various location in BTPS | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Renovation and Modification of Colony Electric Supply System to improve availability and reliability of supply system at BTPS Colony, Deepnagar | 0 | - | 0 | 15.85 | 15.85 | 0 | 0 | 0 |  |  | 0 | 0
6.11 | Work of Overhauling repairs of U-5 350KW BCWP motor of M/s Torishima make at BTPS 2x500MW. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2028-29 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | APH baskets with main drive Gear box and lub oil skids with motor at 2x500MW BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | APH baskets with main drive Gear box and lub oil skids with motor at 2x500MW BTPS | 0 | - | 0 | 50 | 50 | 0 | 0 | 0 |  |  | 0 | 0
2 | Detail Project Report for Design, Engineering, Supply, Installation and commissioning of 1500TPH Stacker cum re-claimer in Coal Handling Plant-BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Design, Engineering, Supply, Installation and commissioning of 1500TPH Stacker cum re-claimer in Coal Handling Plant-BTPS. | 0 | - | 0 | 118 | 118 | 0 | 0 | 0 |  |  | 0 | 0
3 | Enhancement of Unloading & Stacking Capacity of CHP. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Design Supply errection & Comissioning of Open Wagon Tippler along with stacking and reclaiming yard conveyors at CHP stack yard. | 0 | - | 0 | 89 | 89 | 0 | 0 | 0 |  |  | 0 | 0
0 | FY 2029-30 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in 2x500 MW BTPS. | 0 | - | 0 | 0 | 0 | 0 | 70 | 70 |  |  | 70 | 0
2 | Upgradation rail track in CHP -BTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Revamping and Upgradation of rail track from 52KG to 60KG in CHP-BTPS. | 0 | - | 0 | 0 | 0 | 0 | 75 | 75 |  |  | 75 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Contract for modification of Wobbler feeder in CHP-2X500MW | 0 | - | 0 | 1.4733 | 1.4733 | 0 | 0 | 0 |  |  | 0 | 0
2 | Contract for Revamping of Apron Feeder in CHP-2X500MW | 0 | - | 0 | 2.3246 | 2.3246 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of double lip skirt sealing & tracking idler in CHP at 2x500MW, BTPS | 0 | - | 0 | 0.57025 | 0.57025 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, erection & commissioning of vibrating feeder in CHP at 2x500MW, BTPS | 0 | - | 0 | 0.57796 | 0.57796 | 0 | 0 | 0 |  |  | 0 | 0
5 | Coal chutes with extra life wear resistance plates in CHP at 2X500MW | 0 | - | 0 | 2.0319 | 2.0319 | 0 | 0 | 0 |  |  | 0 | 0
6 | Epoxy Painting upto all height to structural steel work in main plant boiler side area and CHP area | 0 | - | 0 | 5.8625 | 5.8625 | 0 | 0 | 0 |  |  | 0 | 0
7 | Rectification of Belt feeder & Gravity Take-up in CHP-2X500MW. | 0 | - | 0 | 1.6479 | 1.6479 | 0 | 0 | 0 |  |  | 0 | 0
8 | Coal diverting chutes in CHP at 2X500MW. | 0 | - | 0 | 2.2184 | 2.2184 | 0 | 0 | 0 |  |  | 0 | 0
9 | Supply of Conveyor Pulleys with Ceramic lagging at CHP-2X500MW, BTPS, Bhusawal | 0 | - | 0 | 0.58051 | 0.58051 | 0 | 0 | 0 |  |  | 0 | 0
10 | Non-DPR Project Report for Design, Supply,Erection & Commissioning of High Performance Energy Chain System for Side Arm Charger at 2x500 at CHP | 0 | - | 0 | 1.5015 | 1.5015 | 0 | 0 | 0 |  |  | 0 | 0
11 | Implementation of Energy Conservation Demonstration Project in buildings of BTPS 2x500MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Installation of Fire & Explosion Prevention system at Bhusawal 500MW Unit-4. | 0 | - | 0 | 2.4539 | 2.4539 | 0 | 0 | 0 |  |  | 0 | 0
13 | Fixtures & Fitting (10801) | 0 | - | 0 | 0.21334 | 0.21334 | 0 | 0 | 0 |  |  | 0 | 0
14 | Office equpment (10901) | 0 | - | 0 | 0.22996 | 0.22996 | 0 | 0 | 0 |  |  | 0 | 0
15 | 150 W & 40 W LED FIXTURES AT TG HOUSE BUILDING 2X500MW | 0 | - | 0 | 0.52807 | 0.27807 | 0.25 | 0 | 0 |  |  | 0 | 0.25
16 | JUMBO DEESERT AIR COOLERS FOR POWER TRANSFORERS | 0 | - | 0 | 0.10143 | 0.10143 | 0 | 0 | 0 |  |  | 0 | 0
17 | GEN ASSET (ALMIRAH,TABLE & CHAIR) (10801) | 0 | - | 0 | 0.23454 | 0.23454 | 0 | 0 | 0 |  |  | 0 | 0
18 | LAPTOP, 50 INCH TV,PRINTER,PROJECTOR,DESKTOP,UPS & ETS. (10901) | 0 | - | 0 | 0.55035 | 0.55035 | 0 | 0 | 0 |  |  | 0 | 0
19 | RESTAURANT EQUIP COMPOSTING MACHINE | 0 | - | 0 | 0.05049 | 0.05049 | 0 | 0 | 0 |  |  | 0
20 | OFFICE TABLE,STORGE RACK,FAN | 0 | - | 0 | 0.57869 | 0.57869 | 0 | 0 | 0 |  |  | 0
21 | CAMERAS | 0 | - | 0 | 0.038468 | 0.038468 | 0 | 0 | 0 |  |  | 0
22 | VELHALA ASH BUND RD WORK | 0 | - | 0 | 2.4645 | 2.4645 | 0 | 0 | 0 |  |  | 0
23 | CONCERETE ROAD FROM DIESEL PUMP TO 500MW FACTORY G | 0 | - | 0 | 0.98449 | 0.98449 | 0 | 0 | 0 |  |  | 0
24 | Admin Building | 0 | - | 0 | 0.05175 | 0 | 0.05175 | 0 | 0 |  |  | 0
25 | Furniture & Fixture | 0 | - | 0 | 0.13712 | 0.13712 | 0 | 0 | 0 |  |  | 0
26 | Office Equipment | 0 | - | 0 | 0.14424 | 0.14424 | 0 | 0 | 0 |  |  | 0
27 | Furniture & Fixture | 0 | - | 0 | 0.073968 | 0.073968 | 0 | 0 | 0 |  |  | 0
28 | Office Equipment | 0 | - | 0 | 0.15891 | 0.15891 | 0 | 0 | 0 |  |  | 0
29 | Work of repairs of 350 KW BCWP-4B & BCWP-5B motor of M/s. Torishima make at BTPS 2x500 MW | 0 | - | 0 | 4.8465 | 4.8465 | 0 | 0 | 0 |  |  | 0
30 | ABC Powder Type and Foam Type Composite Fire Extinguisher | 0 | - | 0 | 0.58548 | 0.58548 | 0 | 0 | 0 |  |  | 0
31 | Withdrawal of capex from Project (LD - Passenger Lifts) | 0 | - | 0 | 0 | -0.13899 | 0.13899 | 0 | 0 |  |  | 0
| Total |  |  |  | 2218.4105 | 2042.7397 | 175.6708 | 145 | 145 | 0 | 0 | 145 | 175.48