## F4
MSPGCL-Chandrapur U# 8-9
MTR Petition Formats - Generation
Form 4: Summary of Capital Expenditure and Capitalisation
(Rs. Crore)
Sr. No. | Particulars | FY 2022-23 |  |  | FY 2023-24 |  |  | FY 2024-25 |  |  |  |  | Ensuing Years |  |  |  |  | Remarks
|  | MYT Order (227 of 2022) | April-March (Audited ) | True-Up requirement | MYT Order (227 of 2022) | April-March (Audited ) | True-Up requirement | MYT Order (227 of 2022) | Apr-Sep (Estimated) | Oct-Mar (Projected) | April - March (Projected) | Provisional True-Up requirement | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30
|  | (a) | (b) | (c) = (b) - (a) | (d) | (e) | (f) = (e) - (d) | (g) | (h) | (i) | (j) = (h )+ (i) | (k) = (j) - (g) | Projected | Projected | Projected | Projected | Projected
1 | Capital Expenditure |  | 83.5669 | 83.5669 |  | 74.7693 | 74.7693 |  | 13.69 | 73.886 | 207.236 | 207.236 | 965.855 | 1002.8795 | 360.555 | 107 | 212.5
2 | Capitalisation | 158.42 | 81.5397 | -76.8803 | 301.75 | 85.3855 | -216.3645 | 220.27 | 13.69 | 201.79 | 215.4756 | -4.7944 | 965.855 | 1002.8795 | 360.555 | 107 | 212.5
3 | IDC |  |  | 0 |  |  | 0 |  |  |  |  | 0
4 | Capitalisation + IDC | 158.42 | 81.5397 | -76.8803 | 301.75 | 85.3855 | -216.3645 | 220.27 | 13.69 | 201.79 | 215.4756 | -4.7944 | 965.855 | 1002.8795 | 360.555 | 107 | 212.5
Note: * - Truing Up for FY 2022-23 & FY 2023-24 to be done under MERC MYT Regulations 2019 with reference to amounts approved in the MYT Order for FY 2020-21 to FY 2024-25
Detailed Justification shall be provided for variation in approved capital expenditure and capitalisation vis-a-vis actual capital expenditure and capitalisation

## F4.1
MSPGCL-Chandrapur U# 8-9
MTR Petition Formats - Generation
| Project Details |  | Form 4.1: Capital Expenditure Plan | [14 empty] | (Rs. Crore)
Sr. No. | Project Code | Project Title | MERC Approval No. | MERC Approval Date | Project Purpose | Project Start Date |  |  | Project Completion date (Scheduled) |  |  | Capital Cost
[6 empty] | Original | Revised | Actual | Original | Revised | Actual | Approved | Actual Capital Cost Incurred | Deviation = Approved - Actual on account of
[14 empty] | Change in Scope of Work (a) | Material Cost (b) | IDC (c) | Others (d) | Total Deviation (a+b+c+d)
(i) In Principally Approved By MERC
HO DPR 1 | HMI (Human Machine Interface) Upgradation of ‘SSPA-T3000’ DCS (Distribution Control System), Rockwell make PLC System installed at 3x660MW Unit No. 8, 9 & 10 at Koradi TPS and HMI (Human Machine Interface) Upgradation of MaxDNA DCS System at Unit 8-9, CSTPS, Chandrapur | DPR | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 |  | 2023-10-09 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 1.1 | Supply: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 |  | 2023-10-09 |  | - | - |  | - | 10.52 | 0 |  | 10.52 |  |  | 10.52
HO DPR 1.2 | Works: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 |  | 2023-10-09 |  | - | - |  | - | 0.41 | 0 |  | 0.41 |  |  | 0.41
0 | IDC | IDC | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 |  | 2023-10-09 |  | - | - |  | - | 0.15 | 0 |  | 0.15 |  |  | 0.15
40 | Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M with construction of concrete dam (Waste Weir & Non overflow structure), construction of drain wells, approach to drain wells and raising of ash compartment for ash bund along with renewal of Ash Disposal Pipe Line Service Road with WBM treatment at CSTPS, Chandrapur | DPR | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 |  | 2023-09-05 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
0 | Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M | Scheme | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 |  | 2023-09-05 |  | - | - |  | - | 34.8665 | 0 |  | 34.8665 |  |  | 34.8665
0 | Construction of New Drain Wells (12 Nos.) along with necessary connection to existing drain wells at CSTPS | 0 | 0 | - |  | - |  | - | - |  | - | 0.58493 | 0 |  | 0.58493 |  |  | 0.58493
0 | Construction of waste weir for raising of ash bund (Waste Weir & Non overflow structure) | 0 | 0 | - |  | - |  | - | - |  | - | 1.4621 | 0 |  | 1.4621 |  |  | 1.4621
0 | Raising of Ash Compartment i.e. Lagoon in Ash Bund | 0 | 0 | - |  | - |  | - | - |  | - | 8.7868 | 0 |  | 8.7868 |  |  | 8.7868
0 | IDC | Scheme | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 |  | 2023-09-05 |  | - | - |  | - | 7.634 | 0 |  | 7.634 |  |  | 7.634
0 | IDC | IDC | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 |  | 2023-09-05 |  | - | - |  | - | 4.9692 | 0 |  | 4.9692 |  |  | 4.9692
39 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 8-9) | DPR | MERC/CAPEX/2020-2021/WFH/SBR/21 | 2020-07-24 |  | 2020-07-24 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
39.1 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 8-9) | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/21 | 2020-07-24 |  | 2020-07-24 |  | - | - |  | - | 440.54 | 0 |  | 440.54 |  |  | 440.54
0 | IDC | IDC | MERC/CAPEX/2020-2021/WFH/SBR/21 | 2020-07-24 |  | 2020-07-24 |  | - | - |  | - | 38.96 | 0 |  | 38.96 |  |  | 38.96
41 | CHP Performance Improvement Schemes at Unit 8-9 of CSTPS, Chandrapur. | DPR | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 |  | 2023-11-03 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
41.1 | Work of Design engineering , supply and installation of modular chutes with sintered silicon carbide for smooth flow &center feeding in CHP 2x500MW CSTPS | Scheme | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 |  | 2023-11-03 |  | - | - |  | - | 9.43 | 0 |  | 9.43 |  |  | 9.43
41.2 | Supply erection & commissioning of set of internal of impact crusher spares installed at CHPP-D, CSTPS | Scheme | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 |  | 2023-11-03 |  | - | - |  | - | 8.05 | 0 |  | 8.05 |  |  | 8.05
41.3 | Scheme for replacement of Scoop coupling/Fluid coupling of conveyor BC-101A/B/C, BC-102A/B, BC-104A/B, BC-105A/B ,BC-106A/B, BC-111A/B/C/D, BC-110A1/B1, BC-110A/B Installed at CHP-D, CSTPS Chandrapur | Scheme | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 |  | 2023-11-03 |  | - | - |  | - | 4.67 | 0 |  | 4.67 |  |  | 4.67
41.4 | Supply erection & commissioning of set of internal of spares of stacker reclaimer installed at CHP-D, CSTPS Chandrapur | Scheme | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 |  | 2023-11-03 |  | - | - |  | - | 1.96 | 0 |  | 1.96 |  |  | 1.96
41.5 | Supply erection & commissioning of set of internal of spares of Wagon tippler installed at CHP-D, CSTPS Chandrapur | Scheme | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 |  | 2023-11-03 |  | - | - |  | - | 2.12 | 0 |  | 2.12 |  |  | 2.12
0 | IDC | IDC | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 |  | 2023-11-03 |  | - | - |  | - | 0.38 | 0 |  | 0.38 |  |  | 0.38
HO DPR 2 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | DPR | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 |  | 2022-02-12 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 2.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | Scheme | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 |  | 2022-02-12 |  | - | - |  | - | 54.24 | 0 |  | 54.24 |  |  | 54.24
0 | IDC | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 |  | 2022-02-12 |  | - | - |  | - | 2.76 | 0 |  | 2.76 |  |  | 2.76
Formulas:
Project Start Date = [MERC Approval Date]

## F4.2
MSPGCL-Chandrapur U# 8-9
MTR Petition Formats - Generation
| Project Details |  | Form 4.2: Capitalisation Plan | [18 empty] | (Rs. Crore) | [19 empty] | (Rs. Crore)
Sr. No. | Project Code | DPR | MERC Approval No. | Date of Submission | MERC Approval Date | Cost as per DPR Crs. | MERC Approved Cost | Debt Equity Ratio | Grant Funding | Approved Start Date | Actual Start Date | Approved Date of Completion | Actual Date of Completion | Benefits in Quantified Terms | Capital Expenditure | [12 empty] | Physical Progress (%) | [6 empty] | Capitalisation | [12 empty] | Remarks | Current Status
[15 empty] | Actual Capex till FY 2018-19 | Actual | Actual | Actual | Actual Capex till FY 2021-22 | Actual | Actual | Revised Projected | Projected |  |  |  |  | Actual Progress till FY 2018-19 | Actual | Actual | Actual | Estimated | Revised Projected |  | Actual Capitalization till FY 2018-19 | Actual | Actual | Actual | Actual Capitalization till FY 2021-22 | Actual | Actual | Revised Projected | Projected
[16 empty] | FY 2019-20 | FY 2020-21 | FY 2021-22 |  | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 |  | FY 2019-20 | FY 2020-21 | FY 2021-22 | FY 2022-23 | FY 2023-24 | FY 2024-25 |  | FY 2019-20 | FY 2020-21 | FY 2021-22 |  | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30
[52 empty] | DPR | Not Initiated
| A) Approved Add Cap (Case No. 296 of 2019) | [50 empty] | Scheme | WIP
1 | Initial Spares |  | Approved Add Cap (Case No. 296 of 2019) | [6 empty] | - | [41 empty] | IDC | Capitalised
| Boiler & Auxiliaries | [5 empty] | 10.36 | [11 empty] | 0 | [19 empty] | 0
| Procurement of Bevel Helical Gear box KMP-350 for XRP 1043 coal mills at unit-8&9,CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0 | 0 | 0 |  | 7.4087 | [14 empty] | 0 | 0 | 0 | 0 |  | 7.4087 | [6 empty] | PO placed on dtd 29.06.2022 . As per terms and conditions of the order, delivery period is 15 months from the dispatched date . |  | 7.4087 | FALSE
| Procurement of Hydraulic Adjustment (Actuating) Device for PA fan model PAF 19/10.6-2 and FD fan FAF 23/12.5-1 at Unit 8&9, CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0 | 1.3971 | 1.3971 | 0 | [15 empty] | 0 | 0 | 1.3971 | 1.3971 | [10 empty] | 2.7942 | FALSE
| Procurement of Yokogawa make Zirconia Oxygen Analyser spares for C&I-III, Unit-8&9, CSTPS, Chandrapur | [13 empty] | 0 | 0 | 0 | 0.51933 | 0.51933 | 0 | [15 empty] | 0 | 0 | 0.51933 | 0.51933 | [10 empty] | 1.0387 | FALSE
| Procurement of High pressure valves installed at unit-8&9 ( 2x500 MW),CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 | 0 | 0 | 0 | [8 empty] | PR was initiated in the month of Sep-2021 with estimated cost Rs 1.38 Cr . However due to ADDCAPP budget Constraint, Proposal was reestimated several times and final estimated cost of the proposal reduced to 49.53 lakh resulted into delay in tender processsing . However , revised / restimated proposal initiation is in process for further processing . |  | 0 | FALSE
| Turbine & Aux | [5 empty] | 1.33 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
| Procurement of IMI Norgren Herion make Trip solenoid valves for Main Turbine, MD-BFP & TD-BFP of Unit 8 & 9, CSTPS, Chandrapur | [13 empty] | 0 | 0 | 0.37354 | 0 | 0.37354 | 0 | [15 empty] | 0 | 0.37354 | 0 | 0.37354 | [10 empty] | 0.74709 | FALSE
| Procurement of Speed Sensors for 500 MW KWU Turbine for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | [13 empty] | 0 | 0 | 0.038232 | 0 | 0.038232 | 0 | [15 empty] | 0 | 0.038232 | 0 | 0.038232 | [10 empty] | 0.076464 | FALSE
| Procurement of Position Feedback Transmitters for Starting Device and Speeder Gear of Main Turbine for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | [13 empty] | 0 | 0 | 0.11225 | 0 | 0.11225 | 0 | [15 empty] | 0 | 0.11225 | 0 | 0.11225 | [10 empty] | 0.22451 | FALSE
| Procurement of spares for LP bypass system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur on OEM Basis. | [13 empty] | 0 | 0 | 0 | 0.43645 | 0.43645 | 0 | [15 empty] | 0 | 0 | 0.43645 | 0.43645 | [10 empty] | 0.87289 | FALSE
| Procurement of TSE (Turbine Stress Evaluator) temperature elements for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | [13 empty] | 0 | 0 | 0 | 0.061505 | 0.061505 | 0.14579 | [15 empty] | 0 | 0 | 0.061505 | 0.061505 | 0.12252 | 0.023164 | [6 empty] | PO placed, 16 Items of worth Rs.1354388.13 /- (With Tax) are supplied before 31.03.2022 & 01 Item of worth Rs. 145791.36/- (With Taxes) supply still pending. Various letters & emails communication made with the OEM M/s BHEL for supply of balance material but till date balance material awaited.M/s BHEL replied vide email dated 24.09.2022 & stated that "During 2nd wave of covid19, most of the manufacturing unit of BHEL incl. Haridwar were under shutdown. Further supply chain disturbed resulting in delay in procurement of raw material. However BHEL is committed to supply balance material by Dec-2022" |  | 0.2687 | FALSE
| Generator and Auxiliries | [5 empty] | 0.9 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
| Procurement of complete set of water cooled bushing for 500MW Generator installed at Unit-8 & 9, CSTPS Chandrapur. | [12 empty] | Reliability and availability of the auxiliary | 0 | 0 | 0 | 0 | 0 |  | 0.26409 | [14 empty] | 0 | 0 | 0 | 0 |  | 0.26409 | [6 empty] | Delivery period of the material is 12 months from the date of PO. Accordingly, the delivery date is 27.11.2021. However, material not delivered by OEM (M/s BHEL) yet. Correspondence regarding the same has done vide email dated 05.11.2021, 02.06.2022 and letter no. 1326, Dtd. 20.07.2022. However, no response from the OEM. |  | 0.26409 | FALSE
| Procurement of Tushaco make complete AC Jacking Oil Pump for Unit-8 & 9, CSTPS, Chandrapur | [12 empty] | Reliability and availability of the auxiliary | 0 | 0 | 0.20013 | -0.00064513 | 0.19949 | 0 | [15 empty] | 0 | 0.20013 | -0.00064513 | 0.19949 | [8 empty] | Material Received within Timeline |  | 0.39897 | FALSE
| Procurement of oil filled Neutral Grounding Transformer for AHP Unit-8&9 CSTPS , Chandrapur. | [12 empty] | Reliability and availability of the auxiliary | 0 | 0.34775 | 0 | 0 | 0.34775 | 0 | [15 empty] | 0.34775 | 0 | 0 | 0.34775 | [10 empty] | 0.6955 | FALSE
| Electrical and Instrumentation | [5 empty] | 29.23 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
| ‘Procurement of various spares of BHEL make Vacuum Circuit Breakers’ , for Unit-8 & 9, CSTPS, Chandrapur. | [12 empty] | Reliability of the supply system and auxiliary availability | 0 | 0 | 0 | 0.49498 | 0.49498 | 0 | [15 empty] | 0 | 0 | 0.49498 | 0.49498 | [10 empty] | 0.98995 | FALSE
| Supply, erection and commissioning of floor mounted 500KW Resistor Load Bank for D.G. sets installed at Unit-8 & 9, CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0.27536 | 0 | 0.27536 | 0 | [15 empty] | 0 | 0.27536 | 0 | 0.27536 | [10 empty] | 0.55073 | FALSE
| Procurement of Turbosupervisory system spares of main turbine for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | [13 empty] | 0 | 0 | 1.0366 | 0 | 1.0366 | 0 | [15 empty] | 0 | 1.0366 | 0 | 1.0366 | [10 empty] | 2.0732 | FALSE
| Procurement of Level transmitters for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | [13 empty] | 0 | 0 | 0.15999 | 0 | 0.15999 | 0 | [15 empty] | 0 | 0.15999 | 0 | 0.15999 | [10 empty] | 0.31998 | FALSE
| Procurement of Level transmitters for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | [12 empty] | Improvement in availability. | 0 | 0 | 0 | 0 | 0 | 0.018125 |  | 0.01448 | [13 empty] | 0 | 0 | 0 | 0 | 0.018125 |  | 0.01448 | [5 empty] | PO placed on M/s K P Instruments, Nagpur, 01 Item of worth Rs.181248/- (With Tax) are supplied on 07.07.2022 & 01 Item of worth Rs. 145281.60/- (With Taxes) supply still pending. For these items, this offiice made various letters & emails communication for supply of balance material before 31.03.2022 ,but till date balance material awaited.M/s KP instruments replied vide email dated 24.09.2022 stated that due to Covid-19, there has been significant rise in raw material resulting in rise in product prices. The old models has also been phased out and the new models came with stupendous increase in price. |  | 0.032605 | FALSE
| Procurement of Level transmitters for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | [13 empty] | 0 | 0 | 0.046973 | 0 | 0.046973 | 0 | [15 empty] | 0 | 0.046973 | 0 | 0.046973 | [10 empty] | 0.093945 | FALSE
| Procurement of GE PLC spares for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0.57304 | 0 | 0.57304 | 0 | [15 empty] | 0 | 0.57304 | 0 | 0.57304 | [10 empty] | 1.1461 | FALSE
| Procurement of spares for GEHO pumps PLC control panels for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0.036915 | 0.047463 | 0.084378 | 0 | [15 empty] | 0 | 0.036915 | 0.047463 | 0.084378 | [10 empty] | 0.16876 | FALSE
| Procurement of master calibration lab Instruments for C&I-III, Unit 8 & 9,CSTPS,Chandrapur | [13 empty] | 0 | 0 | 0.12701 | 0.1743 | 0.30131 | 0 | [15 empty] | 0 | 0.12701 | 0.1743 | 0.30131 | [10 empty] | 0.60262 | FALSE
| Procurement of Coal Feeder panel spares for C&I-III, Unit 8 & 9,CSTPS, Chandrapur | [13 empty] | 0 | 0.58701 | 0 | 0 | 0.58701 | 0 | [15 empty] | 0.58701 | 0 | 0 | 0.58701 | [10 empty] | 1.174 | FALSE
| Procurement of Opacity Monitor (Stack Particulate matter-SPM) spares for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | [13 empty] | 0 | 0.14051 | 0 | 0 | 0.14051 | 0 | [15 empty] | 0.14051 | 0 | 0 | 0.14051 | [10 empty] | 0.28102 | FALSE
| Procurement of Forbes Marshall Supervisory system spares For Turbine driven boiler feed pumps (TDBFP) of Unit 8 & 9, CSTPS, Chandrapur | [13 empty] | 0 | 0.22449 | 0 | 0 | 0.22449 | 0 | [15 empty] | 0.22449 | 0 | 0 | 0.22449 | [10 empty] | 0.44897 | FALSE
| Procurement of spares for hydraulic panel of CW pumps for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0 | 0.12949 | 0.12949 | 0.0091301 | [15 empty] | 0 | 0 | 0.12949 | 0.12949 | 0.0091129 | [7 empty] | PO placed on Sankalp Hydraulics, Mumbai, 36 Items of worth Rs.1365125.48/- (With Tax) are supplied before 31.03.2022. 2 Items of worth Rs. 21046.48/- (With Tax) received on 25.05.2022. For these items, this offiice made various letters & emails communication for supply of balance material before 31.03.2022 . |  | 0.26809 | FALSE
| Procurement of H2 Dew point analyzer spares for Unit 8 & 9, CSTPS, Chandrapur | [13 empty] | 0 | 0 | 0 | 0.049938 | 0.049938 | 0 | [15 empty] | 0 | 0 | 0.049938 | 0.049938 | [10 empty] | 0.099875 | FALSE
| Procurement of spares for HP bypass system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | [13 empty] | 0 | 0 | 0.090583 | 0.24906 | 0.33965 | 0 | [15 empty] | 0 | 0.090583 | 0.24906 | 0.33965 | [10 empty] | 0.67929 | FALSE
| Procurement of spares for Position feedback transmitter for HP bypass system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | [13 empty] | 0 | 0.0354 | 0 | 0 | 0.0354 | 0 | [15 empty] | 0.0354 | 0 | 0 | 0.0354 | [10 empty] | 0.0708 | FALSE
| Procurement of spares for Atlas Copco make Instrument, Service and Conveying air Compressors for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0 | 0.2265 | 0.2265 | -0.001407 | [15 empty] | 0 | 0 | 0.2265 | 0.2265 | -0.001407 | [9 empty] | 0.45159 | FALSE
| Procurement of spares for HEA Ignitors and Flame Scanners for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0.037701 | 0 | 0.037701 | [16 empty] | 0 | 0.037701 | 0 | 0.037701 | [8 empty] | PO placed on 15.09.2020 and 100% supply completed on 22.10.2020 vide GRN No. 5000459326. No delay occured. Rs. 3.77 Lacs utilised against allocated amount of Rs. 15 Lacs. Balance amount not needed. |  | 0.075402 | FALSE
| Procurement of spares for GEHO pumps of Ash Handling System at C&I-III, Unit 8 & 9, CSTPS, Chandrapur | [13 empty] | 0 | 0.28861 | 0 | 0 | 0.28861 | 0 | [15 empty] | 0.28861 | 0 | 0 | 0.28861 | [10 empty] | 0.57722 | FALSE
| Procurement of Turbine side control valve spares for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | [13 empty] | 0 | 0 | 0.17974 | 0 | 0.17974 | 0 | [15 empty] | 0 | 0.17974 | 0 | 0.17974 | [10 empty] | 0.35948 | FALSE
| Procurement of various numerical protection relays for Unit-8 & 9, CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0.12307 | 0 | 0.12307 | 0 | [15 empty] | 0 | 0.12307 | 0 | 0.12307 | [8 empty] | All quantity received within a stipulated time as per purchase order |  | 0.24615 | FALSE
| Procurement of various numerical protection relays for Unit-8 & 9, CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0.14207 | 0 | 0.14207 | -0.010231 | [15 empty] | 0 | 0.14207 | 0 | 0.14207 | -0.010231 | [7 empty] | All quantity received within a stipulated time as per purchase order |  | 0.27391 | FALSE
| Procurement of various numerical protection relays for Unit-8 & 9, CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0.13863 | 0 | 0.13863 | 0 | [15 empty] | 0 | 0.13863 | 0 | 0.13863 | [8 empty] | All quantity received within a stipulated time as per purchase order |  | 0.27725 | FALSE
| Procurement of spares for DB POWER make UPS system installed at HCSD Pump House, Unit-8 & 9, CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0.064757 | 0 | 0.064757 | 0 | [15 empty] | 0 | 0.054879 | 0.0098782 | 0.064757 | [8 empty] | All quantity received within a stipulated time as per purchase order |  | 0.12951 | FALSE
| Procurement of Fully Automatic Capacitance & Dissipation Factor (Tan- Delta) measuring kit for Unit-8 &9, CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0.48288 | 0 | 0.48288 | 0 | [15 empty] | 0 | 0.48288 | 0 | 0.48288 | [8 empty] | All quantity received within a stipulated time as per purchase order |  | 0.96576 | FALSE
| Supply of various VFD spares for ID fans of Unit-8 & 9, CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0.10101 | 0.12126 | 0.22227 | 0.23399 |  | 0.08974 | [13 empty] | 0 | 0.075328 | 0.14694 | 0.22227 | 0.23399 |  | 0.08974 | [5 empty] | PO placed on M/s.BHEL on 24.04.2020. Supply of 03 items of worth Rs. 5,32,698/- (With taxes )still pending. Various letters & emails communication made with the OEM M/s BHEL for supply of balance material but till date balance material awaited. |  | 0.76827 | FALSE
| Procurement of DAVR spares installed at Unit -8&9 CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0.56174 | 0 | 0.56174 | 0.01005 |  | 0.02271 | [13 empty] | 0 | 0.56174 | 0 | 0.56174 | 0.01005 |  | 0.02271 | [5 empty] | All quantity received within a stipulated time as per purchase order |  | 1.1562 | FALSE
| Procurement of 3 phase relay test kit for Unit-8 &9, CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0.35388 | 0 | 0.35388 | 0 | [15 empty] | 0 | 0.35388 | 0 | 0.35388 | [8 empty] | All quantity received within a stipulated time as per purchase order. |  | 0.70776 | FALSE
| Procurement of spares for Fast Bus Transfer System (FBTS) installed at Unit-8 & 9, CSTPS, Chandrapur. | [13 empty] | 0 | 0.37288 | 0 | 0 | 0.37288 | 0 | [15 empty] | 0.37288 | 0 | 0 | 0.37288 | [8 empty] | All quantity received within a stipulated time as per purchase order. |  | 0.74576 | FALSE
| Procurement of various spares for battery chargers installed at Unit-8&9, CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0 | 0.40022 | 0.40022 | 0 | [15 empty] | 0 | 0 | 0.40022 | 0.40022 | [8 empty] | All quantity received within a stipulated time as per purchase order. |  | 0.80043 | FALSE
| Procurement of Auto synchronizing Relay (ASR) & Load Shedding Relay (LSR) installed at Unit-8 &9, CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0.34973 | 0 | 0.34973 | [16 empty] | 0 | 0.35683 | -0.0071003 | 0.34973 | [8 empty] | All quantity received within a stipulated time as per purchase order. |  | 0.69946 | FALSE
| Procurement of ESP spares i.e. Field Controller, Thyristor and Trigger card for ESP of Unit-8 & 9, CSTPS Chandrapur. | [13 empty] | 0 | 0 | 0.26745 | 0 | 0.26745 | [16 empty] | 0 | 0.26745 | 0 | 0.26745 | [8 empty] | All quantity received within a stipulated time as per purchase order. |  | 0.53489 | FALSE
| Procurement of various VFD spares for GEHO pump of Unit-8 & 9, CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0.54416 | 0 | 0.54416 | [16 empty] | 0 | 0.54416 | 0 | 0.54416 | [8 empty] | All quantity received within a stipulated time as per purchase order. |  | 1.0883 | FALSE
| Design, Supply, Erection & Commissioning of On-Line Dissolved Gas Analyzers for various Transformers installed at Unit-8 & 9, CSTPS, Chandrapur. | [12 empty] | Close monitoring of the system to ensure timely detection of faults and corrective actions can be taken to ensure availability | 0 | 0 | 3.1775 | 0 | 3.1775 | 0 | [15 empty] | 0 | 3.1775 | 0 | 3.1775 | [10 empty] | 6.355 | FALSE
| Supply, Erection & Commissioning of On-Line Dissolved Gas Analyzers for Station Transformers -8B, Unit-8 & 9, CSTPS, Chandrapur | [12 empty] | Close monitoring of the system to ensure timely detection of faults and corrective actions can be taken to ensure availability | 0 | 0 | 0.30519 | 0 | 0.30519 | 0 | [15 empty] | 0 | 0 | 0.30519 | 0.30519 | [10 empty] | 0.61038 | FALSE
| Procurement of ‘TOROSHIMA’ make 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motor (without pump casing) for Unit-8&9, CSTPS Chandrapur. | [12 empty] | Reliability and availability of the auxiliary | 0 | 0 | 4.2037 | 0 | 4.2037 | 0 | [15 empty] | 0 | 4.2037 | 0 | 4.2037 | [10 empty] | 8.4073 | FALSE
| Procurement of 90kVA ESP Rectiformer for Unit-8 & 9, CSTPS, Chandrapur. | [12 empty] | Reliability and availability of the auxiliary | 0 | 0 | 0.29878 | 0 | 0.29878 | 0 | [15 empty] | 0 | 0.29878 | 0 | 0.29878 | [10 empty] | 0.59755 | FALSE
| Supply erection & commissioning of Aviation Lighting for NDCT of Unit-8&9, CSTPS Chandrapur | [12 empty] | Compulsory as per statutory norms of Ministry of Civil aviation in view of aviation safety | 0.43543 | 0.13718 | 0 | 0 | 0.57261 | 0 | [15 empty] | 0.57261 | 0 | 0 | 0.57261 | [10 empty] | 1.1452 | FALSE
| Procurement of Transformer oil storage tanks of different capacity for Unit-8&9 CSTPS Chandrapur. | [12 empty] | Ease of maintenance/ oil storage during maintenance activities | 0 | 0 | 0.57024 | 0 | 0.57024 | 0 | [15 empty] | 0 | 0.57024 | 0 | 0.57024 | [10 empty] | 1.1405 | FALSE
| Procurement of 2000kW & 315kW, 6.6 kV HT motors for CW & ACW Pump installed at Unit-8&9, CSTPS, Chandrapur. | [12 empty] | Reliability and availability of the auxiliary | 0 | 0 | 0 | 1.4505 | 1.4505 | 0 | [15 empty] | 0 | 0 | 1.4505 | 1.4505 | [10 empty] | 2.901 | FALSE
| Procurement of 3.25MVA, 6.6/2.3kV VFD Transformers of vector group DY11 for Unit-8 & 9, CSTPS, Chandrapur. | [12 empty] | Reliability and availability of the auxiliary | 0 | 0 | 0 | 0 | 0 |  |  | 0.3941 | [13 empty] | 0 | 0 | 0 | 0 |  |  | 0.3941 | [5 empty] | GA Drg not submitted yet for approval. Supplier not responding to PO. Warnning letter regarding de-barring of the same issued to M/s Sanjivani Trading Co., Parli Vaijnath. Supplier ensure to deliver the matrial by Oct-2022. At present , material not yet received |  | 0.3941 | FALSE
| Procurement of 3.25MVA, 6.6/2.3kV VFD Transformer of vector group ‘Dd0’ for Unit-8 & 9, CSTPS, Chandrapur. | [12 empty] | Reliability and availability of the auxiliary | 0 | 0 | 0 | 0 | 0 |  |  | 0.3905 | [13 empty] | 0 | 0 | 0 | 0 |  |  | 0.3905 | [5 empty] | GA Drg not submitted yet for approval. Supplier not responding to PO. Warnning letter regarding de-barring of the same issued to M/s Sanjivani Trading Co., Parli Vaijnath. Supplier ensure to deliver the matrial by Oct-2022. At present , material not yet received |  | 0.3905 | FALSE
| Procurement of ‘MARATHON’ makes HT/LT Induction motors for various Critical auxiliaries installed at Unit-8 &9, CSTPS Chandrapur. | [12 empty] | Reliability and availability of the auxiliary | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 | 0 | 0 | 0 | [8 empty] | The PO is not placed yet |  | 0 | FALSE
| Supply of 1.2V, Ni-Cd battery cells for Unit-8&9, CSTPS Chandrapur. | [12 empty] | Reliability and availability of the auxiliary | 0 | 0 | 0.12496 | 0 | 0.12496 | 0 | [15 empty] | 0 | 0.12496 | 0 | 0.12496 | [10 empty] | 0.24992 | FALSE
| Supply of 1.2V, Ni-Cd battery cells for Unit-8&9, CSTPS Chandrapur. | [12 empty] | Reliability and availability of the auxiliary | 0 | 0 | 0.18931 | 0 | 0.18931 | 0 | [15 empty] | 0 | 0.18931 | 0 | 0.18931 | [10 empty] | 0.37862 | FALSE
| Procurement of ‘Air Core DC Reactor’ for VFD and ‘NGR’ for UAT/ Station Transformers installed at Unit-8 & 9, CSTPS, Chandrapur. | [12 empty] | Reliability and availability of the auxiliary | 0 | 0.44368 | 0 | 0 | 0.44368 | 0 | [15 empty] | 0 | 0 | 0.44368 | 0.44368 | [10 empty] | 0.88736 | FALSE
| Procurement of ‘Air Core DC Reactor’ for VFD and ‘NGR’ for UAT/ Station Transformers installed at Unit-8 & 9, CSTPS, Chandrapur. | [12 empty] | Reliability and availability of the auxiliary | 0 | 0.12551 | 0 | 0 | 0.12551 | 0 | [15 empty] | 0.12551 | 0 | 0 | 0.12551 | [10 empty] | 0.25102 | FALSE
| Procurement of ‘BHEL’ make 680 KW, 6.6KV, Coal Mill Motor for Unit-8&9, CSTPS Chandrapur. | [12 empty] | Reliability and availability of the auxiliary | 0 | 0 | 0 | 0.37913 | 0.37913 | 0 | [15 empty] | 0 | 0 | 0.37913 | 0.37913 | [10 empty] | 0.75827 | FALSE
| Procurement of 400kV OIP Condenser Bushing for Generator Transformer & Station Transformer of Unit-8&9, CSTPS, Chandrapur. | [12 empty] | Reliability and availability of the auxiliary | 0 | 0 | 0.49064 | 0 | 0.49064 | 0 | [15 empty] | 0 | 0.49064 | 0 | 0.49064 | [10 empty] | 0.98127 | FALSE
| Procurement of ‘11kW DC motor with Control Cabinet’ for Unit-8 & 9, CSTPS, Chandrapur. | [12 empty] | Reliability and availability of the auxiliary | 0 | 0 | 0 | 0 | 0 |  |  | 0.2242 | [13 empty] | 0 | 0 | 0 | 0 |  |  | 0.2242 | [5 empty] | Supplier not responding to PO. Warnning letter regarding de-barring of the same issued to M/s Nakul Corporation, Nagpur. In response of this M/s Nakul Corporation submitted GAD for approval as per email received on dtd. 27.05.2022. Material not yet received. |  | 0.2242 | FALSE
| Procurement of 37kW, 415V motors for Primary Water Pump installed at Unit-8 &9, CSTPS Chandrapur. | [12 empty] | Reliability and availability of the auxiliary | 0 | 0 | 0.0096851 | 0 | 0.0096851 | 0 | [15 empty] | 0 | 0.0096851 | 0 | 0.0096851 | [10 empty] | 0.01937 | FALSE
| Procurement of 15 KW, 415V LT Motor for Service Building & TG Building Lift installed at Unit-8&9, CSTPS Chandrapur. | [12 empty] | Reliability and availability of the auxiliary | 0 | 0 | 0 | 0.095155 | 0.095155 | 0 | [15 empty] | 0 | 0 | 0.095155 | 0.095155 | [10 empty] | 0.19031 | FALSE
| Procurement of 16KW, 415V LT Motor for Boiler Lift installed at Unit-8&9, CSTPS Chandrapur. | [12 empty] | Reliability and availability of the auxiliary | 0 | 0 | 0.044179 | 0 | 0.044179 | 0 | [15 empty] | 0 | 0.044179 | 0 | 0.044179 | [10 empty] | 0.088358 | FALSE
| Supply, Erection, Testing and Commissioning of Hydrastep-Electronic Drum Level Indicator and its associated accessories for Unit-9, CSTPS, Chandrapur | [13 empty] | 0 | 0.2537 | 0 | 0.02006 | 0.27376 | 0 | [15 empty] | 0.2537 | 0 | 0.02006 | 0.27376 | [10 empty] | 0.54752 | FALSE
| Procurement of spares for BHEL make Hydrastep (Electronic Water Level Indicator -BHELVISION 20M) for Unit 8 & 9, CSTPS, Chandrapur on OEM basis. | [13 empty] | 0 | 0 | 0.04157 | 0.042601 | 0.084172 | 0 | [15 empty] | 0 | 0.04157 | 0.042601 | 0.084172 | [8 empty] | PO placed on M/s BHEL, 08 Items of worth Rs.814715.6/- (With Tax) are supplied before 31.03.2022 & 01 Item of worth Rs. 145791.36/- (With Taxes) supply still pending. Various letters & emails communication made with the OEM M/s BHEL for supply of balance material but till date balance material awaited. M/s BHEL replied vide email dated 24.09.2022 & stated that "Though all the material were supplied, one item is rejected at site. We received rejection report at later stage in the month of July 2022 vide mail. BHEL is committed to resupply the item by the month of Dec-2022." |  | 0.16834 | FALSE
| Procurement of Electrodes for Hydrastep (Electronic Water Level Indicator -BHELVISION 20M) for Unit 8 & 9, CSTPS, Chandrapur. | [13 empty] | 0 | 0.10384 | 0 | 0 | 0.10384 | 0 | [15 empty] | 0.10384 | 0 | 0 | 0.10384 | [10 empty] | 0.20768 | FALSE
| Engineering & Retrofitting of 196 NT Controller to DT 9 Controller for Unit-8 & 9 Coal Feeder System. | [13 empty] | 0.38076 | 0 | 0 | 0 | 0.38076 | 0 | [15 empty] | 0.38076 | 0 | 0 | 0.38076 | [10 empty] | 0.76152 | FALSE
| Procurement of spares for BHEL make Acoustic steam leak detection system (BHELSONIC) (BS10) for Unit 8 & 9, CSTPS, Chandrapur | [13 empty] | 0 | 0 | 0 | 0.038929 | 0.038929 | 0.038878 | [15 empty] | 0 | 0 | 0.038929 | 0.038929 | 0.038878 | [9 empty] | 0.11674 | FALSE
| Procurement of LT Circuit Breaker assemblies for ESP LT Panels (LTMSB & ACP) of Unit-8&9, CSTPS, Chandrapur. | [12 empty] | Reliability and availability of the auxiliary | 0 | 0 | 0.25429 | 0 | 0.25429 | 0 | [15 empty] | 0 | 0.25429 | 0 | 0.25429 | [10 empty] | 0.50858 | FALSE
| Procurement of spares for BHEL make maxDNA Distributed control system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | [13 empty] | 0 | 0 | 0 | 0.99745 | 0.99745 | 0.06777 | 0.051819 | [14 empty] | 0 | 0 | 0.99792 | 0.99792 | 0.067302 | 0.051819 | [6 empty] | PO placed M/s BHEL, 20 Items of worth Rs.10705481.11 /- (With Tax) are supplied before expiry of delivery period i.e on or before 12.04.2022 & 01 Items of worth Rs. 569004.31 /- (With Taxes) supply still pending. Various letters & emails communication made with the OEM M/s BHEL for supply of balance material but till date balance material awaited.M/s BHEL replied vide email dated 24.09.2022 & stated that "BHEL has supplied almost 95% of material. However, due to Russia-Ukrain crises during Feb-2022, raw material cost for electronics item have increased a lot. BHEL being the PSU, revising estimates and procuring raw material for balance items through govt. lay down procedure. However these balance items shall be supplied within Dec-2022" |  | 2.115 | FALSE
| Supply of Transformer oil BDV test kit DTA 100C and Oil Tan Delta & Resistivity Tester DTL C at Unit-8&9, CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0 | 0.47598 | 0.47598 | 0 | [15 empty] | 0 | 0 | 0.47598 | 0.47598 | [10 empty] | 0.95195 | FALSE
| Outdoor Plant ( CHP/AHP/WTP) | [5 empty] | 5 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
| Procurement of spares for Elecon make KCN-560 type Gearbox for Apron Feeder installed at CHPD, CSTPS. | [13 empty] | 1.6717 | 0 | 0 | 0 | 1.6717 | [16 empty] | 0 | 0 | 1.6717 | 1.6717 | [8 empty] | All quantity received within a stipulated time as per purchase order. SD/Retention amount considered in 22-23 |  | 3.3433 | FALSE
| Procurement of spares of CKB-280,225,200,8180 typ gearbox installed at CHP-D | [13 empty] | 0 | 0.90759 | 0.09396 | 0 | 1.0015 | 0 | [15 empty] | 0 | 0.09396 | 0.90759 | 1.0015 | [8 empty] | Due to rise in market rates over the approved rates in due course of time |  | 2.0031 | FALSE
| Procurement of Gear Box (MAKE: NEW ALLENBERRY) Spares at CHP-D; CSTPS, Chandrapur. | [13 empty] | 0 | 0.5177 | 0 | 0 | 0.5177 | [16 empty] | 0 | 0 | 0.5177 | 0.5177 | [8 empty] | All quantity received within a stipulated time as per purchase order. SD/Retention amount considered in 22-23 |  | 1.0354 | FALSE
| Procurement of spares for m/s Elecon make Impact Crusher installed at CHP Unit 8&9 CSTPS, Chandrapur | [13 empty] | 0 | 0.8509 | -0.0098736 | 0 | 0.84103 | [16 empty] | 0 | 0 | 0.84103 | 0.84103 | [8 empty] | All quantity received within a stipulated time as per purchase order. SD/Retention amount considered in 22-23 |  | 1.6821 | FALSE
| Procurement of V belt pulley of rotor for Impact crusher installed at CHP-D, CSTPS | [13 empty] | 0 | 0.11864 | 0 | 0 | 0.11864 | 0 | [15 empty] | 0 | 0 | 0.11864 | 0.11864 | [8 empty] | Due to rise in market rates over the approved rates in due course of time |  | 0.23728 | FALSE
| Procurement of Spares for hydraulic systems installed at CHPD, CSTPS. | [13 empty] | 0 | 0.23375 | 0.24162 | 0 | 0.47537 | 0 | [15 empty] | 0 | 0.24162 | 0.23375 | 0.47537 | [8 empty] | Due to rise in market rates over the approved rates in due course of time |  | 0.95075 | FALSE
| Procurement of Spares for hydraulic systems installed at CHPD, CSTPS. | [13 empty] | 0 | 0 | 0.028604 | 0 | 0.028604 | [16 empty] | 0 | 0 | 0.028604 | 0.028604 | [8 empty] | Due to rise in market rates over the approved rates in due course of time |  | 0.057208 | FALSE
| Procurement of drive & non drive pulley for various conveyors installed at CHP D, CSTPS, Chandrapur. | [13 empty] | 0 | 0.14223 | 0.11569 | 0 | 0.25792 | 0 | [15 empty] | 0 | 0.11569 | 0.14223 | 0.25792 | [8 empty] | Due to rise in market rates over the approved rates in due course of time |  | 0.51583 | FALSE
| Procurement of drive & non drive pulley for various conveyors installed at CHP D, CSTPS, Chandrapur. | [13 empty] | 0 | 0.0914 | 0 | 0 | 0.0914 | 0 | [15 empty] | 0.0914 | 0 | 0 | 0.0914 | [8 empty] | Due to rise in market rates over the approved rates in due course of time |  | 0.1828 | FALSE
| Procurement of Chain links for apron feeder installed at CHP D, CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0.40289 | 0 | 0.40289 | 0 | [15 empty] | 0 | 0.40289 | 0 | 0.40289 | [8 empty] | Due to rise in market rates over the approved rates in due course of time |  | 0.80578 | FALSE
| Procurement of internal spares for Elecon make PWD-18, PLB-25 & SCN-180 type Gearbox for Stacker Reclaimer & wobbler feeder installed at CHP D, CSTPS. | [13 empty] | 0.52774 | 0 | 0 | 0 | 0.52774 | 0 | [15 empty] | 0 | 0 | 0.52774 | 0.52774 | [8 empty] | Due to rise in market rates over the approved rates in due course of time |  | 1.0555 | FALSE
| Supply of GE Make Switchgear Spares for GE Make LT Feeders | [13 empty] | 0 | 0 | 0 | 0.10198 | 0.10198 | 0.022868 | [15 empty] | 0 | 0 | 0.089824 | 0.089824 | 0.035022 | [7 empty] | Completed within time |  | 0.21467 | FALSE
| Procurement of spares for Fluidomat make scoop coupling installed at CHP–D, CSTPS, Chandrapur | [13 empty] | 0 | 0.48355 | 0 | 0 | 0.48355 | [16 empty] | 0 | 0 | 0.48355 | 0.48355 | [8 empty] | Completed within time |  | 0.96711 | FALSE
| Procurement of Oil Filtering machine for hydraulic power packs installed at CHPD, CSTPS | [13 empty] | 0 | 0 | 0.10592 | 0 | 0.10592 | 0 | [15 empty] | 0 | 0.10592 | 0 | 0.10592 | [8 empty] | Due to rise in market rates over the approved rates in due course of time |  | 0.21184 | FALSE
| Supply of LT Motors at CHP-D (U#8&9), CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0.11302 | 0 | 0.11302 | 0 | [15 empty] | 0 | 0.11302 | 0 | 0.11302 | [8 empty] | Due to rise in market rates over the approved rates in due course of time |  | 0.22604 | FALSE
| Supply and Installation of Oil Cooled Suspended Anodized Winding Magnet & Control Panel at CHP, Unit 8&9, CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0 | 2.2967 | 2.2967 | 0 | [15 empty] | 0 | 0 | 2.2967 | 2.2967 | [8 empty] | Due to rise in market rates over the approved rates in due course of time |  | 4.5934 | FALSE
| Supply of LT power and control cable for CHP-D | [13 empty] | 0 | 0 | 0.26256 | 0 | 0.26256 | 0 | [15 empty] | 0 | 0.18127 | 0.081294 | 0.26256 | [8 empty] | Due to rise in market rates over the approved rates in due course of time |  | 0.52513 | FALSE
| Supply of LT power and control cable for CHP-D | [13 empty] | 0 | 0 | 0.022125 | 0 | 0.022125 |  |  | 0.025575 | [13 empty] | 0 | 0.022125 | 0 | 0.022125 |  |  | 0.025575 | [7 empty] | 0.069825 | FALSE
2 | Capital Spare |  | Approved Add Cap (Case No. 296 of 2019) | [6 empty] | - | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE |  | Cancelled
| HPT MODULE | [5 empty] | 45.3 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
| Procurement of HP turbine Module along with breach nuts and pipe spool pieces (Type: H30-100-2) for Unit-8 & 9, CSTPS, Chandrapur | [12 empty] | Newly procured HPT module is installed at Unit 8. U8 load loss of 70-80 MW/HR is saved. | 0 | 0 | 0 | 0 | 0 |  | 32.332 | [14 empty] | 0 | 0 | 0 | 0 |  | 32.332 | [6 empty] | 1. CHNN/TM-III/D.P./0982, Dt. 15.07.2020 2. CHN/TM-III/LT-1158/RFx-3000004782/000526, Dt. 05.05.2021 3. CHNN/TM-III/D.P./LT-1158/0160, Dt. 29.01.2022 4. Letter from Siemens: SL/CSTPS-CHANDRAPUR/2021-22/014 Dt. 28.03.2022 Letter (1), (2), & (3) were sent to M/s. Siemens for supply the material on or before 31.03.2022. M/s. Siemens vide their letter (4) mention the reasons for not supplying the material on or before 31.03.2022 as "This is a huge machine for which various component need to be sourced from various suppliers spread across geographies which have posed serious challanges due to most recent event of Russia-Ukraine war. In view of the currently prevailing fluid situation, it will be pre-mature to judge if the supply-chain disruptions would be controlled. At the same time, it is worth nothing that most of these events are beyond control of both of us." |  | 32.332 | FALSE
| LPT ROTOR | [5 empty] | 40.7 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
| Procurement of Fully Bladed & Dynamically Balanced LP Rotor (N30-2X10-2) for Unit-8 & 9, CSTPS, Chandrapur | [12 empty] | Material is yet to be used. It is maintained as spares to avoid unforeseen urgency. | 0 | 0 | 0 | 0 | 0 | 29.03 | [15 empty] | 0 | 0 | 0 | 0 | 29.03 | [7 empty] | 1. CHNN/TM-III/D.P./LT-1174/1188, Dt. 10.08.2020 2. Letter from GEPL Ref No.: 1327441/LP Rotor/2020/001, Dt. 21.08.2020 3. CHNN/TM-III/D.P./LT-1174/2009, Dt. 04.12.2021 4. Letter from GEPL Ref No.: ESO-012465/01, Dt. 21.01.2022 5. CHNN/TM-III/D.P./LT-1174/0155, Dt. 28.01.2022 6. Letter from GEPL Ref No.: ESO- 012465/03, Dt. 15.03.2022. Letter (1),(3) & (5) were sent to M/s. GEPIL for supply the material on or before 31.03.2022. In response M/s. GEPIL vide their letter (2),(4) & (6) mention the reasons for not supplying the material on or before 31.03.2022 as "The raw material required for manufacturing of LP Rotor is imported. Due to pandemic third wave globally all the outsorcing facilities are working with limited operation . Due to this fact manufacturing process getting prolonged. International movement/logistics of materials were restricted due to limited flights and vessel/ships operations. Also,due to Russian-Ukraine war had impact on receipt of raw material ( Long lead time of the forgings). and consequently impacted on factory work schedules of manufacturer." |  | 29.03 | FALSE
| Procurement of set of Free Standing Moving Blades for LP Rotor (N30-2X10-2) for Unit-8 & 9, CSTPS, Chandrapur | [12 empty] | Material is yet to be used. It is maintained as spares to avoid unforeseen urgency. | 0 | 0 | 0 | 0 | 0 |  | 4.5629 | [14 empty] | 0 | 0 | 0 | 0 |  | 4.5629 | [6 empty] | 1. CHN/TM-III/LT-256/PO-4385000504/003425, Dt. 16.12.2021. 2. Letter from GEPIL Ref No.: T21W1523611-C, Dt. 17.12.2021. 3. Letter from GEPIL Ref No.: T21W1523611-D, Dt. 06.01.2022. 4. CHNN/TM-III/LT-256/0244, Dt. 08.02.2022. 5. Letter No. ED(O&M-I)/ Mahagenco/Add cap/4210, Dt. 09.05.2022. Letter (1) was sent to M/s. GEPIL to supply the material before 31.03.2022 before placing of P.O. In response M/s. GEPIL vide their Letter (2) & (3) shown their inability to supply the material before the deadline stating the reasons as " The Omicron variant of SARS- CoV-2/ third wave as per the situation it may again disturbing the manufacturing activities and already started restrictions in all over the world mainly in European countries and soon starting in India. Besides, transportation links has disturbed, and manufacturer have to pay more in freight charges as the supply chain is stressed because of limited pre book logistic on account of covid pandamic." Hence letter under ref. (4) was sent to HO to issue necessary guideline regarding dispatch of P.O. and submitted the reasons quoted by M/s. GEPIL for its inability to supply the material before 31.03.2022. However after receipt of letter from Hon. ED (O&M-I) & approval of office note by C.A. the P.O. was dispatched finally on 14.05.2022 and as per P.O. the delivery period falls on 13.05.2023. |  | 4.5629 | FALSE
| BFP CARTRIDGE ( 2NOS ) | [5 empty] | 4.4 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
| Procurement of cartridge assembly for Boiler Feed Pump model FK-4E-36 (with Four S/H & 2 R/H spray branches) installed at 2X 500MW, CSTPS, Chandrapur. | [12 empty] | Both BFP cartridges are installed Unit 9 TDBFPs. U9 load loss of about 20 MW/HR is saved. | 0 | 0 | 0 | 1.2575 | 1.2575 | 1.2575 | [15 empty] | 0 | 0 | 1.2575 | 1.2575 | 1.2574 | [7 empty] | 1. CHNN/TM-III/D.P./T-1102/2010, Dt. 04.12.2021 2. CHNN/TM-III/D.P./T-1102/0483, Dt. 15.03.2022 3. Email from BHEL on Dt.13.05.2022. Letter (1) & (2) was sent to M/s. BHEL to supply the material before 31.03.2022. However no reply received from M/s. BHEL regarding delay in delivery of material. One Cartridge assembly received within Timeframe. While other cartridge assembly received on 17.06.2022. |  | 3.7724 | FALSE
| BCW PUMP | [5 empty] | 3.5 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
| Procurement of spares for ‘TOROSHIMA’ make 350KW BCW Pump-Motor installed at Unit-8 &9, CSTPS Chandrapur. | [13 empty] | 0 | 0 | 0 | 1.3283 | 1.3283 | 0 | [15 empty] | 0 | 0 | 1.3283 | 1.3283 | [10 empty] | 2.6565 | FALSE
| Procurement of various spares for ‘TOROSHIMA’ make Boiler Circulating Water (BCW) pump-motor installed at Unit-8&9, CSTPS Chandrapur. | [13 empty] | 0 | 0 | 0 | 0 | 0 | 2.2326 | [15 empty] | 0 | 0 | 0 | 0 | 2.2326 | [7 empty] | Delivery period as per the PO is 10 months from the date of PO. The material delivered o date 27.06.2022 (PO date 25.09.2021) |  | 2.2326 | FALSE
| 15 MVA DRY TYPE TRANSFORMER | [5 empty] | 35 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
| Procurement of spare ‘Cast Resin Dry Type Transformers (CRTs)’ of different ratings for Unit-8&9, CSTPS Chandrapur. | [13 empty] | 0 | 0 | 0 | 1.5275 | 1.5275 | 4.4938 | [15 empty] | 0 | 0 | 1.5275 | 1.5275 | 4.4938 | [7 empty] | As per PO terms of condition, the manufacturer should submit the drawing for approval within one month from the date of dispatch of PO, all material shall be delivered within the period of 4 months(120 days) from the date of approval of drawings. Accordingly, drawings were submitted one by one by the manufacturer and last approval was given by this office is on date 29/1/2022. Presently, all the material of this PO has been delivered and scheme completed.Hence, can be considered it in FY 22-23 |  | 7.5488 | FALSE
| Procurement of phase coil limb and spares of Cast Resin Dry Type Transformers of different ratings for Unit-8&9, CSTPS Chandrapur. | [13 empty] | 0 | 0 | 0 | 0 | 0 | 7.9255 | [15 empty] | 0 | 0 | 0 | 0 | 7.9255 | [7 empty] | The supplier had requested for delivery period extension. Accordingly, delivery period of the material extended up to 03.11.2022 vide letter No. CE(CPA)/Gr-IVB/CSTPS/Time Limit extn approval/8473, Dtd. 15.09.2022. Partial material (appx. 25%) recived till date. Rest of the material is in transit. |  | 7.9255 | FALSE
| BTG+BOP& Other Works | [5 empty] | 20.48 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
| Work of Design, Supply & Installation, Testing & Commissioning of Public Addressing System for tunnels of CHP-D, CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0 | 1.1544 | 1.1544 | 0 | [15 empty] | 0 | 0 | 1.1544 | 1.1544 | [8 empty] | Completed within time |  | 2.3088 | FALSE
| Work of upgradation, installation and extension of 220VDC control supply to various PMCC of CHPD, CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0 | 0.68441 | 0.68441 | 0 | [15 empty] | 0 | 0 | 0.68441 | 0.68441 | [8 empty] | Completed within time |  | 1.3688 | FALSE
| Work of Apron Feeder in CHP Unit 8&9 (2x500) MW at CHP-D, CSTPS. | [13 empty] | 0 | 0 | 0 | 2.3388 | 2.3388 | 0 | [15 empty] | 0 | 0 | 2.3388 | 2.3388 | [10 empty] | 4.6777 | FALSE
| Supply of spares for up gradation of rotary parts of travelling conveyor system installed at CHPD, CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0 | 0.58939 | 0.58939 | 0 | [15 empty] | 0 | 0 | 0.58939 | 0.58939 | [10 empty] | 1.1788 | FALSE
| The Work of Design, Engineering, Manufacturing, Supply, Erection & Commissioning of Short Conveyor belt from stack yard of CHP of Unit 5,6&7 to Belt Conveyor 104 A/B at CHP of Unit 8&9, CSTPS, Chandrapur | [13 empty] | 0 | 0 | 0 | 0 | 0 | 2.9173 | 2.2467 | 0.51846 | [13 empty] | 0 | 0 | 0 | 0 |  | 5.164 | 0.51846 | [5 empty] | Due to extended monsoon season works are delayed |  | 5.6825 | FALSE
| Work of design, supply, erection, commissioning of overhead cable tray along with removal & re-routing of power and control cables at CHP-D, CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0 | 0.51324 | 0.51324 | 0 | [15 empty] | 0 | 0 | 0.51324 | 0.51324 | [8 empty] | Completed within time |  | 1.0265 | FALSE
| Work of provision, modification, retrofitting and revamping of lighting system of transfers points, crusher house and bunker area of CHP-D, CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0 | 1.0105 | 1.0105 | 0 | [15 empty] | 0 | 0 | 1.0105 | 1.0105 | [8 empty] | Completed within time |  | 2.0209 | FALSE
| Procurement of spares for M/s. Weir Minerals make (GEHO pump Model TZPM-1200) for Ash Handling Plant Unit# 8 &9 CSTPS Chandrapur. AHP-III | [13 empty] | 0 | 0 | 0 | 0.30372 | 0.30372 | 1.8023 | [15 empty] | 0 | 0 | 0.30372 | 0.30372 | 1.8023 | [7 empty] | As the material is tailor made and specific to the site at Chandrapur, thus is not in ready stock. The lead time to manufacture this material is minimum within 4-6 months. Also in these times of covid, there are certain travel restrictions and material movement is also impaired. 100 % Material received on dt. 15.06.2022 |  | 2.4097 | FALSE
| Procurement of Gear Box set of internal (MAKE: NEW ALLENBERRY) Spares at CHP-D; CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0 | 0.2315 | 0.2315 | 1.4589 | [15 empty] | 0 | 0 | 0.2315 | 0.2315 | 1.4589 | [7 empty] | One gear box No: CKB200 supply pending |  | 1.9219 | FALSE
| Supply and Installation of Oil Cooled Suspended Anodized Winding Magnet & Control Panel at CHP, Unit 8&9, CSTPS, Chandrapur. | [17 empty] | 0 | [19 empty] | 0 | [8 empty] | To be deleted (PB opened on 05.08.2022, RR submitted to RP for higher quoted rates on 21.09.2022) |  | 0 | FALSE
| 196 NT Controller by DT 9 Controller alongwith HMI units for Unit- 8&9 coal feeder system | [13 empty] | 0 | 0 | 0 | 2.0774 | 2.0774 | 0 | [15 empty] | 0 | 0 | 2.0774 | 2.0774 | [10 empty] | 4.1548 | FALSE
| Procurement of set of CW Impeller duly fitted with wear rings & ACW Impeller duly fitted with wear rings of Mather & Platt make Pumps installed at Unit-8 & 9,CSTPS,Chandrapur | [12 empty] | CW pump impeller is installed at U9. Condensor vaccum improved & CW pump availability & reliability is improved. | 0 | 0 | 0 | 0 | 0 | 0.70379 | [15 empty] | 0 | 0 | 0 | 0 | 0.70379 | [7 empty] | Material Received in CSTPS. 1.E-mail dtd.24.03.2022 . 2. Letter No.CHNN/TM-III/PO Approval/E-333/PO-4385000478/5668 Dt. 24.03.2022. 3. E-mail dtd. 09.04.2022 . Letter (1), & E-mail (2) were sent to M/s.Wilo Mather & Platt for supply the material on or before 31.03.2022. In response M/s. Wilo Mather & Platt vide their E-mail under (3) mention the reasons for not supplying the material on or before 31.03.2022 as "The spare parts against your requirement are of tailor made non-std design specifically manufactured suiting to your requirement. The manufacturing process of these spare parts includes modification to the existing patterns, making casting at foundry, machining, followed by dynamic ballancing, quality checks at various stages". |  | 0.70379 | FALSE
| CHP System U#8 | [13 empty] | 0.05 |  |  |  | 0.05 | [16 empty] | 0.05 |  |  | 0.05 | [8 empty] | WIP from FY 2018-19 |  | 0.1 | FALSE
| ISOLATED PHASE BUS DUCT | [13 empty] | 0.04 |  |  |  | 0.04 | [16 empty] | 0.04 |  |  | 0.04 | [10 empty] | 0.08 | FALSE
| SEGREGATED PHASE BUS DUCT U#8 | [13 empty] | 0.04 |  |  |  | 0.04 | [16 empty] | 0.04 |  |  | 0.04 | [10 empty] | 0.08 | FALSE
| SEGREGATED PHASE BUS DUCT U#9 | [13 empty] | 0.04 |  |  |  | 0.04 | [16 empty] | 0.04 |  |  | 0.04 | [10 empty] | 0.08 | FALSE
| ISOLATED PHASE BUS DUCT U#9 | [13 empty] | 0.04 |  |  |  | 0.04 | [16 empty] | 0.04 |  |  | 0.04 | [10 empty] | 0.08 | FALSE
| DTT & UAT U#8 | [13 empty] | 0.03 |  |  |  | 0.03 | [16 empty] | 0.03 |  |  | 0.03 | [10 empty] | 0.06 | FALSE
| DTT & UAT U#9 | [13 empty] | 0.03 |  |  |  | 0.03 | [16 empty] | 0.03 |  |  | 0.03 | [10 empty] | 0.06 | FALSE
| Cranes and hoists U#8 | [13 empty] | 0.03 |  |  |  | 0.03 | [16 empty] | 0.03 |  |  | 0.03 | [10 empty] | 0.06 | FALSE
| RCC Chimney U#8 | [13 empty] | 9.29 |  |  |  | 9.29 | [18 empty] | 9.29 | 9.29 | [10 empty] | 18.58 | FALSE
| Coal Handling Plant | [13 empty] | 41.79 |  |  |  | 41.79 | [18 empty] | 41.79 | 41.79 | [10 empty] | 83.58 | FALSE
| Bunker foundation & civil works (Unit 8) U#8 | [13 empty] | 18.58 |  |  |  | 18.58 | [18 empty] | 18.58 | 18.58 | [10 empty] | 37.16 | FALSE
| Boiler & Auxiliaries U#9 | [13 empty] | 9.28 |  |  |  | 9.28 | 0.008909 | [17 empty] | 9.28 | 9.28 | 0.0071752 | [9 empty] | 18.5672 | FALSE
| ESP U#9 | [13 empty] | 2.15 |  |  |  | 2.15 | 0.008909 | [17 empty] | 2.15 | 2.15 | 0.008909 | [9 empty] | 4.3089 | FALSE
| ID fan foundations (Unit 9) U#9 | [13 empty] | 1.74 |  |  |  | 1.74 | 0.008909 | [17 empty] | 1.74 | 1.74 | 0.008909 | [9 empty] | 3.4889 | FALSE
| DRY ASH SILO-12M DIA U#8 | [13 empty] | 1.22 |  |  |  | 1.22 | [18 empty] | 1.22 | 1.22 | [10 empty] | 2.44 | FALSE
| FD fan foundations (Unit 9) U#9 | [13 empty] | 0.62 |  |  |  | 0.62 | 0.008909 | [17 empty] | 0.62 | 0.62 | 0.008909 | [9 empty] | 1.2489 | FALSE
| PA fan foundations (Unit 9) U#9 | [13 empty] | 0.54 |  |  |  | 0.54 | 0.008909 | [17 empty] | 0.54 | 0.54 | 0.008909 | [9 empty] | 1.0889 | FALSE
| Natural Draft cooling tower- Unit 8 U#8 | [13 empty] | 0.32 |  |  |  | 0.32 | [18 empty] | 0.32 | 0.32 | [10 empty] | 0.64 | FALSE
| Main power house building-Civil Works-Unit no.-9 U | [13 empty] | 0.15 |  |  |  | 0.15 | [18 empty] | 0.15 | 0.15 | [10 empty] | 0.3 | FALSE
| Structural Steel works for main power house buildi | [13 empty] | 0.15 |  |  |  | 0.15 | [18 empty] | 0.15 | 0.15 | [10 empty] | 0.3 | FALSE
| Canteen U#8 | [13 empty] | 0.12 |  |  |  | 0.12 | [18 empty] | 0.12 | 0.12 | [10 empty] | 0.24 | FALSE
| Security and time office U#8 | [13 empty] | 0.12 |  |  |  | 0.12 | [18 empty] | 0.12 | 0.12 | [10 empty] | 0.24 | FALSE
| CARS SCOOTERS AND CYCLE SHED U#8 | [13 empty] | 0.12 |  |  |  | 0.12 | [18 empty] | 0.12 | 0.12 | [10 empty] | 0.24 | FALSE
| Fire Station U#8 | [13 empty] | 0.12 |  |  |  | 0.12 | [18 empty] | 0.12 | 0.12 | [10 empty] | 0.24 | FALSE
| Watch towers U#8 | [13 empty] | 0.12 |  |  |  | 0.12 | [18 empty] | 0.12 | 0.12 | [10 empty] | 0.24 | FALSE
| First aid station | [13 empty] | 0.12 |  |  |  | 0.12 | [18 empty] | 0.12 | 0.12 | [10 empty] | 0.24 | FALSE
| Tranformer yard U#8 | [13 empty] | 0.02 |  |  |  | 0.02 | [18 empty] | 0.02 | 0.02 | [10 empty] | 0.04 | FALSE
| Rain Water Harvesting Scheme U#8&9 | [13 empty] | -0.01 |  |  |  | -0.01 | [18 empty] | -0.01 | -0.01 | [10 empty] | -0.02 | FALSE
| Procurement of Advance Multipurpose Fire Tender | [15 empty] | 3.45 |  | 3.45 | [17 empty] | 3.45 |  | 3.45 | [10 empty] | 6.9 | FALSE
| DM Stream | [5 empty] | 29.65 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
| DM Stream capacity of 100 M3/Hr in addition to existing stream of WTP. | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0 | 0 | 0 |  | 0 | [6 empty] | The PO is not placed yet. To be deleted |  | 0 | FALSE
| CIVIL | [17 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
1 | Bridge | [5 empty] | 4.11 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
2 | Railway, CHP, AHP etc | [5 empty] | 152.96 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
| B. G. railway siding Pway works | [15 empty] | 30.41 | 0.62285 | 31.0329 | 8.544 | 1.9396 | [15 empty] | 30.41 | 0.62285 | 31.0329 | 8.544 | 1.9396 | [8 empty] | 72.5494 | FALSE
| S & T work for B.G. railway siding | [17 empty] | 0 | 0.023574 | [18 empty] | 0 | 0.023574 | [9 empty] | 0.023574 | FALSE
| Consultancy services for B. G. railway siding | [17 empty] | 0 | 0.035636 | [18 empty] | 0 | 0.035636 | [9 empty] | 0.035636 | FALSE
| Ash infra in Railway | [17 empty] | 0 | [19 empty] | 0 | [8 empty] | to be deleted |  | 0 | FALSE
| Bunker structure (Unit 8) U#8 | [13 empty] | 18.57 |  |  |  | 18.57 | [18 empty] | 18.57 | 18.57 | [10 empty] | 37.14 | FALSE
| Coal Mills | [13 empty] | 1.13 |  |  |  | 1.13 | 0.008909 | [17 empty] | 1.13 | 1.13 | 0.008909 | [9 empty] | 2.2689 | FALSE
| Bunker foundation & civil works (Unit 9) U#9 | [13 empty] | 0.12 |  |  |  | 0.12 | [18 empty] | 0.12 | 0.12 | [10 empty] | 0.24 | FALSE
| Bunker structure (Unit 9) U#9 | [13 empty] | 0.11 |  |  |  | 0.11 | [18 empty] | 0.11 | 0.11 | [10 empty] | 0.22 | FALSE
| HCSS silo-12m dia U#8 | [13 empty] | 1.16 |  |  |  | 1.16 | [18 empty] | 1.16 | 1.16 | [10 empty] | 2.32 | FALSE
| Ash water PH, HCSD PH, Bottom ash slurry PH U#8 | [13 empty] | 1.16 |  |  |  | 1.16 | [18 empty] | 1.16 | 1.16 | [10 empty] | 2.32 | FALSE
| Ash compressor house & Control room U#8 | [13 empty] | 1.16 |  |  |  | 1.16 | [18 empty] | 1.16 | 1.16 | [10 empty] | 2.32 | FALSE
| MILL REJECT SILO U#8 | [13 empty] | 1.16 |  |  |  | 1.16 | [18 empty] | 1.16 | 1.16 | [10 empty] | 2.32 | FALSE
| Fire protection & Detection system U#8 | [13 empty] | 0.66 |  |  |  | 0.66 | 0.054226 | [17 empty] | 0.66 | 0.66 | 0.054226 | [9 empty] | 1.3742 | FALSE
| DM Water Pump room U#8 | [13 empty] | 4.25 |  |  |  | 4.25 | [19 empty] | 0 | [10 empty] | 0 | FALSE
| Filter water reservoir & pump house U#8 | [13 empty] | 4.29 |  |  |  | 4.29 | [19 empty] | 0 | [10 empty] | 0 | FALSE
| ACW + RW + Filtered water piping U#8 | [13 empty] | 2.35 |  | -0.099378 |  | 2.2506 |  | -0.0096938 | [9 empty] | -0.099378 | [7 empty] | 0 |  | -0.0096938 | [8 empty] | -0.0096938 | FALSE
| Laboratory Building U#8 | [13 empty] | 0.12 |  |  |  | 0.12 | [19 empty] | 0 | [10 empty] | 0 | FALSE
3 | Staff quarters | [5 empty] | 15.04 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
| Work of exterior repair, providing painting to A, D & E type residential buildings and Public Buildings and allied civil works in Urjanagar Colony, CSTPS Chandrapur. | [13 empty] | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 | 0 | 0 | 0 | [8 empty] | To be deleted 1. At present, many buildings of A, D & E type are in damaged conditions. Therefore the said proposal is initiated to strenghen the building and increase the life of building. Therefore it is neccessary work. 2. Work is in progress and delay is due to heavy rainfall in FY 2022-23. All the work proposed under the scheme Staff quarters will be executed in the appoved amount. |  | 0 | FALSE
| Staff Quarters- Repair and renovation of E type staff quarters to extend the life of buildings at CSTPS Chandrapur. | [13 empty] | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 | 0 | 0 | 0 | [8 empty] | To be deleted 1. At present, many buildings of E type are in damaged conditions. Therefore the said proposal is initiated to strenghen the building and increase the life of building. Therefore it is neccessary work. 2. Work will be executed after finalization of agency. All the work proposed under the scheme Staff quarters will be executed in the appoved amount. |  | 0 | FALSE
| Staff Quarters - Repair and renovation of 'B' type staff quarters in residential colony at CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 | 0 | 0 | 0 | [8 empty] | To be deleted 1. At present, many buildings of B type are in damaged conditions. Therefore the said proposal is initiated to strenghen the building and increase the life of building. Therefore it is neccessary work. 2. Work will be executed after finalization of agency. All the work proposed under the scheme Staff quarters will be executed in the appoved amount. |  | 0 | FALSE
| Repair of D type quarters in colony at CSTPS Chandrapur. | [13 empty] | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 | 0 | 0 | 0 | [8 empty] | To be deleted 1. At present, many buildings of D type are in damaged conditions. Therefore the said proposal is initiated to strenghen the building and increase the life of building. Therefore it is neccessary work. 2. Work will be executed after finalization of agency. All the work proposed under the scheme Staff quarters will be executed in the appoved amount. |  | 0 | FALSE
| Repair of C type quarters in colony at CSTPS Chandrapur. | [17 empty] | 0 | [19 empty] | 0 | [8 empty] | To be deleted 1. At present, many buildings of C type are in damaged conditions. Therefore the said proposal is initiated to strenghen the building and increase the life of building. Therefore it is neccessary work. 2. Work will be executed after finalization of agency. All the work proposed under the scheme Staff quarters will be executed in the appoved amount. |  | 0 | FALSE
| Staff Quarters- Repair and renovation of F and NF type staff quarters to extend the life of buildings at CSTPS Chandrapur. | [17 empty] | 0 | [19 empty] | 0 | [8 empty] | To be deleted 1. At present, many buildings of F & NF type are in damaged conditions. Therefore the said proposal is initiated to strenghen the building and increase the life of building. Therefore it is neccessary work. 2. Work will be executed after finalization of agency. All the work proposed under the scheme Staff quarters will be executed in the appoved amount. |  | 0 | FALSE
| Repair and replacement of existing drinking water supply pipelines in E & F type area in colony at CSTPS, Chandrapur. | [17 empty] | 0 | [19 empty] | 0 | [8 empty] | To be deleted 1. At present, drinking water supply lines are in damaged conditions. Therefore the said proposal is initiated to provide the facility of drinking water line. Therefore it is neccessary work. 2. Work will be executed after finalization of agency. All the work proposed under the scheme Staff quarters will be executed in the appoved amount. |  | 0 | FALSE
| Repair and replacement of existing sewer lines in E & F type area in colony at CSTPS, Chandrapur. | [17 empty] | 0 | [19 empty] | 0 | [8 empty] | To be deleted 1. At present, sewer lines are in damaged conditions. Therefore the said proposal is initiated to provide the facility of sewer line. Therefore it is neccessary work. 2. Work will be executed after finalization of agency. All the work proposed under the scheme Staff quarters will be executed in the appoved amount. |  | 0 | FALSE
| Work of providing RCC drain along main roads in colony at CSTPS, Chandrapur. | [17 empty] | 0 | [19 empty] | 0 | [8 empty] | To be deleted 1. At present, storm water drains are in damaged conditions. Therefore the said proposal is initiated to provide the facility of storm water drains. Therefore it is neccessary work. 2. Work will be executed after finalization of agency. All the work proposed under the scheme Staff quarters will be executed in the appoved amount. |  | 0 | FALSE
| Rerouting and replacement of domestic water supply pipeline from WTP to ESR in colony at CSTPS, Chandrapur. | [17 empty] | 0 | [19 empty] | 0 | [8 empty] | To be deleted 1. At present, main drinking water supply line is in damaged conditions. Therefore the said proposal is initiated to provide the facility of main drinking water line. Therefore it is neccessary work. 2. Work will be executed after finalization of agency. All the work proposed under the scheme Staff quarters will be executed in the appoved amount. |  | 0 | FALSE
4 | Additional Contengencies approved vide e BR No. MSPGCL/BM-162/165, Dt.29.10.2016 vide resolution no. 2016/2085 | [5 empty] | 7.46 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
| Landscaping and plantation work at various locations inside plant area at CSTPS, chandrapur. | [14 empty] | 0.6 | 0.52 | 0.69 | 1.81 | 1.6166 | [18 empty] | 0 | 3.4266 | [9 empty] | 3.4266 | FALSE
| Construction of WBM approach road from point- N to Z Area along ash bund periphery at CSTPS Chandrapur. | [13 empty] | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 | 0 | 0 | 0 | [8 empty] | P.O NO 4550012673/001054 DT 07.07.2022 ,Work could not get started due to heavy rainfall at site i.i Ash bund area. Work proposed under the scheme of add. Contingencies & will be executed in approved amount. |  | 0 | FALSE
5 | Design, Engineering, Supply and commissioning of ash-bund water recovery system (Phase II) at CSTPS Chandrapur | [5 empty] | 27.7 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
| Design, Engineering, Supply and commissioning of ash-bund water recovery system (Phase II) at CSTPS Chandrapur | [13 empty] | 0 | 0 | 13.5434 | 0 | 13.5434 | 4.364 | 12.1288 | [14 empty] | 0 | 13.5434 | 0 | 13.5434 |  | 16.4928 | [6 empty] | 1. Nationwide lockdown due to COVID-19 2. Non availability of materials and manpower due to post COVID-19 effect. 3. Non availability of Sand due to non auction of sand 4. Heavy rainfall in year 2022-23 Proposed work will be executed in the appoved amount. |  | 43.5795 | FALSE
| Providing Consultancy Services for work of Design, Engineering, Supply, Installation & Commissioning of ash bund water recovery system (Phase-II) at CSTPS, Chandrapur (on EPC contract basis). | [13 empty] | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 | 0 | 0 | 0 | [8 empty] | Consultancy work ,depends on progress of above work. Proposed work will be executed in the appoved amount. |  | 0 | FALSE
6 | Providing laying, jointing and commissioning of 1600 mm dia. M.S. Pipe line from Erai dam to one day reservoir of stage II, III & IV at CTPS | [5 empty] | 73.62 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
| Providing laying, jointing and commissioning of 1600 mm dia. M.S. Pipe line from Erai dam to one day reservoir of stage II, III & IV at CTPS | [13 empty] | 0 | 23.0494 | 27.8542 | 23.5828 | 74.4864 | -3.9773 |  | 3.1 | [13 empty] | 0 | 0 | 62.2542 | 62.2542 | 8.1084 |  | 3.2465 | [5 empty] | 1. Nationwide lockdown due to COVID-19 2. Non availability of materials and manpower due to post COVID-19 effect. 3. Non availability of Sand due to non auction of sand 4. Heavy rainfall in year 2022-23 |  | 135.8634 | FALSE
| Work of construction of Control Valve rooms on newly laid 1600 mm M.S. Pipeline no. 6 from Erai dam to One day reservoir at CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 | 0 | 0 | 0 | [8 empty] | 1. The said work is necessary for easy operation of valves and will be taken in FY 2022-23 considering the urgency of work. 2. Work will be taken up after finalization of agency. |  | 0 | FALSE
7 | Providing OHE facility for BG Rly siding of proposed Expansion Project at Chandrapur, for Supply of Materials. | [5 empty] | 0.5 | [7 empty] | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 | 0 | 0 | 0 | [10 empty] | 0 | FALSE
8 | Providing OHE facility for BG Rly siding of proposed Expansion Project at Chandrapur, for errection of OHE Items. | [5 empty] | 2.5 | [10 empty] | 0.7 | 0.7 | [19 empty] | 0 | [8 empty] | Work is delayed for want of working Power Blocks from Railway Authority. |  | 0 | FALSE
9 | Irrigation scheme for landscaping and Plantation work at Chandrapur expansion project chandrapur. | [5 empty] | 1 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
10 | Asphalting of WBM road from Nagpur gate to Awanda gate. | [5 empty] | 2 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
| Asphalting of WBM road from Nagpur gate to Awanda gate. | [13 empty] | 0 | 0 | 0 | 0.65141 | 0.65141 | 0 | [15 empty] | 0 | 0 | 0 | 0 | [8 empty] | Work completed within contractual time limit. |  | 0 | FALSE
| Asphalting over WBM Road of ADP line Service road from Nagpur gate opening to Awandha junction gate at CSTPS Chandrapur | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0.84833 | [15 empty] | 0 | 0 | 0 | 0 | 0.84833 | [7 empty] | P.O dt 03.02.2022 & Site was handed over on 18.02.22 after execution of agreement and getting of valid gate pass and work completed on dt 15.06.2022 as per time period. |  | 0.84833 | FALSE
| Asphalting of WBM road from Nagpur gate to Awandha gate at CSTPS Chandrapur - Asphalting of road from Reject coal gate to Motghat nallah at CSTPS Chandrapur (PHASE - I) | [13 empty] | 0 | 0 | 0 | 0.47941 | 0.47941 | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0.47941 | [7 empty] | PO(PO No.4385000565) placed on dt.25.03.2022. Work completed on 31.03.2022 within contractual time limit. |  | 0.47941 | FALSE
11 | Foot Over Bridge | [5 empty] | 2 | [11 empty] | 0 | [19 empty] | 0 | [8 empty] | The PO is not placed yet |  | 0 | FALSE
12 | Work of Providing retaining wall for sand hump at Vivekanand nagar station yard under modification work in wardha end fro 2 x 500 MW Expn. Project at CSTPS, Chandrapur. | [5 empty] | 0.3 | [7 empty] | 0 | 0 | 0.25515 | 0 | 0.25515 | 0 | [15 empty] | 0 | 0 | 0.25515 | 0.25515 | [10 empty] | 0.51029 | FALSE
| Additional Capitalization by O & M | [17 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
1 | Procurement of GE make 4000Amp LT Air Circuit Breakers for Unit-8 & 9, CSTPS, Chandrapur. | [5 empty] | 0.9 | [7 empty] | 0 | 0 | 0 | 1.0308 | 1.0308 | 0 | [15 empty] | 0 | 0 | 1.0308 | 1.0308 | [8 empty] | The proposal of estimated value 0.9CR (without Tax) was initiated. Accordingly, the PO placed of value 0.87CR(without Tax) , 1.03CR (With Tax). Hence, the cost overrun is because of Tax amount. At time of submission in addcap during MYT the tax was not considered in estimation. |  | 2.0617 | FALSE
2 | Air Compressor System | [5 empty] | 0.2 | [11 empty] | 0 | [19 empty] | 0 | [8 empty] | The PO is not placed yet |  | 0 | FALSE
3 | Energy management Sysytem | [5 empty] | 0.3 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
| Supply, Installation, Testing & Commissioning of Energy Management System for Unit#8 & 9 for CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0.18579 | 0.01475 | 0.20054 | 0 | [15 empty] | 0 | 0.18579 | 0.01475 | 0.20054 | [8 empty] | All material received and Energy Management System installation and commissioning work completed. |  | 0.40108 | FALSE
| Procurement of Tri-vector 0.2s class Digital Energy meter for Unit-8&9, CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0 | 0.094872 | 0.094872 | 0 | [15 empty] | 0 | 0 | 0.094872 | 0.094872 | [8 empty] | All quantity received within a stipulated time as per purchase order. |  | 0.18974 | FALSE
4 | Supply, Installation & Commissioning of 3D Level Scanners to 64 nos. of ESP hoppers at Unit-8&9 (2X500MW), CSTPS, Chandrapur. | [5 empty] | 3.24 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
| Procurement of internal spares for Elecon make PWD-18, PLB-25 ,Pbh-71 type Gearbox for Stacker Reclaimer installed at CHPD, CSTPS. | [13 empty] | 0 | 0 | 0 | 0 | 0 | 1.1089 | [15 empty] | 0 | 0 | 0 | 0 | 1.1089 | [7 empty] | Delay from vendor due to covid-19 pandemic One PBH-71 Gearbox supply pending |  | 1.1089 | FALSE
5 | 4000/2500/1800/800 A GE make LT CKT Brkr | [5 empty] | 0.5 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
| LT Air Circuit Breakers for Incomer Feeders at CHP-D, CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0 | 0 | 0 | 1.4207 | [15 empty] | 0 | 0 | 0 | 0 | 1.4207 | [7 empty] | Minimum delivery period after dispatch of PO.Due to obsuletion of technology, more quantam of work is proposed to meet with plant requirements with the approval of competent authority Supply: 100% Completed on 06.08.2022 Works: 100% Balance As per delivery period work shall complete by 20.11.2022 |  | 1.4207 | FALSE
| LT Air Circuit Breakers at CHP, Unit 8&9, CSTPS | [13 empty] | 0 | 0 | 1.0141 | 0 | 1.0141 | 0 | [15 empty] | 0 | 1.0141 | 0 | 1.0141 | [8 empty] | .Due to obsuletion of technology, more quantam of work is proposed to meet with plant requirements with the approval of competent authority |  | 2.0282 | FALSE
6 | Replacement of Impact crusher by hammer mill crusher (installed qty.2 No) | [5 empty] | 2 | [7 empty] | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 | 0 | 0 | 0 | [10 empty] | 0 | FALSE
7 | Replacement of wobbler feeder 1&2 by grizzly screen at CHP-D | [5 empty] | 1.5 | [7 empty] | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 | 0 | 0 | 0 | [10 empty] | 0 | FALSE
8 | Installation of conveyor system from rope way of CHP-A and crusher house of CHP-D | [5 empty] | 10 | [7 empty] | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 | 0 | 0 | 0 | [10 empty] | 0 | FALSE
| PLC based control & instrumentation of 6.6 KV HT motors of 1250 KW of Crusher I & II and 200 KW of BC 108A1 & A2 at CHP-D, CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0 | 0.93628 | 0.93628 | 0 | [15 empty] | 0 | 0 | 0.93628 | 0.93628 | [8 empty] | Completed within time. Considering the installations at other power stations and for reliable auxiliary performance, this scheme is proposed with the approval of competent authority instead of replacement of impact crusher by hammer mill |  | 1.8726 | FALSE
| Work of Design, Supply, Erection & Commissioning of Complete Electrical Automation for Short Conveyor from stack yard of CHP-D to Belt Conveyor 107 A/B of CHP-D, CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0 | 0.70095 | 0.70095 | 0 | [15 empty] | 0 | 0 | 0.70095 | 0.70095 | [8 empty] | Completed within time. This conveyor system is proposed as per most suitable site condition and requirements with the approval of competent authority. |  | 1.4019 | FALSE
| Work of Design, Supply, Erection & Commissioning of Complete Electrical Automation for Short Conveyor from stack yard of CHP-B to Belt Conveyor 104 A/B of CHP-D, CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0 | 2.2368 | 2.2368 | 0 | [15 empty] | 0 | 0 | 2.2368 | 2.2368 | [8 empty] | Completed within time. This conveyor system is proposed as per most suitable site condition and requirements with the approval of competent authority. |  | 4.4735 | FALSE
| WORK OF DESIGN, ENGINEERING, MANUFACTURING, SUPPLY, ERECTION &COMMISSIONING OF SHORT CONVEYOR BELT FROM STACK YARD OF CHP UNIT-8&9 TO CONVEYOR BELT 107A AND B AT CHP UNIT 8&9, CSTPS, CHANDRAPUR. | [13 empty] | 0 | 0 | 0 | 0.46948 | 0.46948 | 3.7558 | 0.46948 | [14 empty] | 0 | 0 | 0 | 0 |  | 4.6948 | [6 empty] | Due to extended monsoon season works are delayed. This conveyor system is proposed as per most suitable site condition and requirements with the approval of competent authority. |  | 4.6948 | FALSE
| Design, Supply, Installation and Commissioning of High Performance Energy Chain System for Side Arm Charger and Stacker Reclaimer of CHP-D, CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0 | 3.8916 | 3.8916 | 0 | [15 empty] | 0 | 0 | 3.8916 | 3.8916 | [8 empty] | Completed within time. For sustainable operation of plant, reliable and improved auxiliary performance this scheme is proposed within approved budget with the approval of competent authority. |  | 7.7833 | FALSE
9 | RBF 103 &104,105 & 106, 107 & 108, and 109 & 110 in to modular Y chute | [5 empty] | 4 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
| RBF-103 & RBF-104 with Design, development, Manufacturing, Supply & erection of modular Chute as per site condition in place of RBF using sintered silicon Carbide plate with motorized Flap Gate at CHP-D, CSTPS. | [13 empty] | 0 | 0 | 1.1741 | 0 | 1.1741 | 0 | [15 empty] | 0 | 1.1741 | 0 | 1.1741 | [8 empty] | Due to rise in raw material, labour wages, transportation cost during the period |  | 2.3482 | FALSE
| RBF-105 & RBF-106 with Design, development, Manufacturing, Supply & erection of modular Chute as per site condition in place of RBF using sintered silicon Carbide plate with motorized Flap Gate at CHP-D, CSTPS. | [13 empty] | 0 | 0 | 1.3169 | 0 | 1.3169 | 0 | [15 empty] | 0 | 1.3169 | 0 | 1.3169 | [8 empty] | Due to rise in raw material, labour wages, transportation cost during the period |  | 2.6338 | FALSE
| RBF-107 & RBF-108 with Design, development, Manufacturing, Supply & erection of modular Chute as per site condition in place of RBF using Tungsten Carbide plate with Flap Gate at CHP-D, CSTPS. | [13 empty] | 0 | 0 | 0.94164 | 0.21122 | 1.1529 | 0 | [15 empty] | 0 | 0 | 1.1529 | 1.1529 | [8 empty] | Due to rise in raw material, labour wages, transportation cost during the period |  | 2.3057 | FALSE
| RBF-109 & RBF-110 with design, erection & Installation by trajectory calculation & removal of existing RBF with Y Chute assembly by flow control with Flap Gate arrangement at TP-107 of CHP-D, CSTPS. | [13 empty] | 1.1506 | 0 | 0 | 0 | 1.1506 | 0 | [15 empty] | 1.1506 | 0 | 0 | 1.1506 | [8 empty] | Due to rise in raw material, labour wages, transportation cost during the period |  | 2.3012 | FALSE
10 | Procurment , Installation and commissioning of Online Insertable Camera systems for Unit-8, 500MW, CSTPS | [5 empty] | 8.62 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
| Design, Supply, Installation & Commissioning of Energy efficient system for Illumination at Unit 8&9 CSTPS, Chandrapur. | [13 empty] | 0 | 0 | 0 | 0 | 0 | 4.9494 | [15 empty] | 0 | 0 | 0 | 0 | 4.9494 | [7 empty] | The proposal was approved vide letter ref. no. CE(CPA)/Gr-IVB/CSTPS/PR approval/8891, Dtd. 07.09.2021. Accordingly, PO was placed and scheme was executed. |  | 4.9494 | FALSE
11 | Construction of Chemical godown shed for unit 8 & 9 at CSTPS,Chandrapur. | [5 empty] | 1.2 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
| Construction of Chemical godown shed for unit 8 & 9 at CSTPS,Chandrapur. | [13 empty] | 0 | 0 | 0.12156 | 0.26551 | 0.38706 | 0.042392 | [15 empty] | 0 | 0 | 0.40653 | 0.40653 | 0.02293 | [9 empty] | 0.83598 | FALSE
| Comprehencive work of installation, erection, testing and commissioning of MVWS spray system/ Fire safety system for new Bulk Chemical storage godown at CSTPS, Unit 8&9 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0.27583 | [15 empty] | 0 | 0 | 0 | 0 | 0.27583 | [9 empty] | 0.27583 | FALSE
| Work of electrification of godown for bulk chemical storage near FOPH building at Chandrapur project site. | [13 empty] | 0 | 0 | 0 | 0.018322 | 0.018322 | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0.018322 | [9 empty] | 0.018322 | FALSE
| Construction of additional Chemical godown shed for storage of Lube oil at CSTPS Chandrapur. | [17 empty] | 0 | [19 empty] | 0 | [8 empty] | The PO is not placed yet |  | 0 | FALSE
12 | Construction of RCC retaining wall for approach to RCC Bridge across Irai River, ADPL line at CSTPS | [5 empty] | 8.76 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
| Construction of RCC retaining wall for approach to RCC Bridge across Irai River, ADPL line at CSTPS | [13 empty] | 0 | 0 | 0.8983 | 0.93062 | 1.8289 |  | 2.2193 | 0.3 | [13 empty] | 0 | 0 | 0 | 0 |  | 4.0482 | 0.3 | [7 empty] | 4.3482 | FALSE
| Asphalting of road from Reject coal gate to Motghat nallah at CSTPS Chandrapur (PHASE - II) | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0.87403 | [15 empty] | 0 | 0 | 0 | 0 | 0.87403 | [7 empty] | PO(PO No.4370002873) placed on dt.26.03.2022. Work completed on 12.06.2022 within contractual time limit. |  | 0.87403 | FALSE
| Providing extension to approaches of RCC bridge across Erai river by constructing WBM road at CSTPS, Chandrapur | [13 empty] | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 | 0 | 0 | 0 | [8 empty] | P.O NO 4370002895/001051 dt 07.07.2022,The Work can not get started due non submission of Valid bank guarntee amount of below quoted amount as per term and conition of contract Sr no 18 of Annexure A. & due to heavy rainfall at site |  | 0 | FALSE
| UDL | [8 empty] | - | [5 empty] | 2.19 | 2.58 | 0.08 | 4.85 | [16 empty] | 2.19 | 2.58 | 0.08 | 4.85 | [10 empty] | 9.7 | FALSE
| B) DPR Schemes | [8 empty] | - | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
| (i) In Principally Approved By MERC | [17 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
HO DPR 1 | HMI (Human Machine Interface) Upgradation of ‘SSPA-T3000’ DCS (Distribution Control System), Rockwell make PLC System installed at 3x660MW Unit No. 8, 9 & 10 at Koradi TPS and HMI (Human Machine Interface) Upgradation of MaxDNA DCS System at Unit 8-9, CSTPS, Chandrapur | DPR | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-03-28 | 2023-10-09 | 11.08 | 11.08 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
HO DPR 1.1 | Supply: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-03-28 | 2023-10-09 | 10.52 | 10.52 | [6 empty] | Improvent in relability of process control and operation. |  |  |  |  | 0 |  |  | 10.52 | [13 empty] | 5.25 | 5.25 |  | 10.5 |  |  | 10.52 | 0 | 0 | [5 empty] | 31.52 | FALSE
HO DPR 1.2 | Works: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-03-28 | 2023-10-09 | 0.41 | 0.41 | [6 empty] | Improvent in relability of process control and operation. |  |  |  |  | 0 |  |  | 0.41 | [13 empty] | 0.2 | 0.2 |  | 0.4 |  |  | 0.41 | 0 | 0 | [5 empty] | 1.21 | FALSE
| IDC | IDC | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-03-28 | 2023-10-09 | 0.15 | 0.15 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
40 | Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M with construction of concrete dam (Waste Weir & Non overflow structure), construction of drain wells, approach to drain wells and raising of ash compartment for ash bund along with renewal of Ash Disposal Pipe Line Service Road with WBM treatment at CSTPS, Chandrapur | DPR | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2021-09-03 | 2023-09-05 |  | 4.9692 |  |  | 2023-09-05 |  |  |  | This scheme is a part and parcle of each Thermal Power Station, hence it is essential for all running Power Plants, however the cost benifits may not be analyzed. Therefore by implementing the scheme, following benefits will be achieved. 1) After implementation of the scheme, the ash disposal problem shall be resolved. 2) After implementation of the scheme, the storage capacity of ash bund shall be increased. 3) It helps to run units efficiently by disposing off generated fly ash hygenically . 4) Healthy and hygenic condition shall be maintained. |  |  |  |  | 0 |  | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | [6 empty] | N.A. | 0 | FALSE
| Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M | Scheme | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2021-09-03 | 2023-09-05 |  | 34.8665 |  |  | 2023-09-05 | [8 empty] | 0 |  |  | 34.8665 | [12 empty] | 34.8665 |  |  |  | 34.8665 |  |  | 34.8665 | [6 empty] | Not Initiated | 104.5995 | FALSE
| Construction of New Drain Wells (12 Nos.) along with necessary connection to existing drain wells at CSTPS | [5 empty] | 0.58493 | [11 empty] | 0 |  |  | 0.58493 | [12 empty] | 0.58493 |  |  |  | 0.58493 |  |  | 0.58493 | [7 empty] | 1.7548 | FALSE
| Construction of waste weir for raising of ash bund (Waste Weir & Non overflow structure) | [5 empty] | 1.4621 | [11 empty] | 0 |  |  | 1.4621 | [12 empty] | 1.4621 |  |  |  | 1.4621 |  |  | 1.4621 | [7 empty] | 4.3862 | FALSE
| Raising of Ash Compartment i.e. Lagoon in Ash Bund | [5 empty] | 8.7868 | [11 empty] | 0 |  |  | 8.7868 | [12 empty] | 8.7868 |  |  |  | 8.7868 |  |  | 8.7868 | [7 empty] | 26.3605 | FALSE
| IDC | Scheme | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2021-09-03 | 2023-09-05 |  | 7.634 |  |  | 2023-09-05 | [8 empty] | 0 |  |  | 7.634 | [12 empty] | 7.634 |  |  |  | 7.634 |  |  | 7.634 | [6 empty] | Not Initiated | 22.9019 | FALSE
0 | IDC | IDC | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2021-09-03 | 2023-09-05 |  | 4.9692 |  |  | 2023-09-05 | [8 empty] | 0 |  | 0 | [17 empty] | 0 |  | 0 | [7 empty] | N.A. | 0 | FALSE
39 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 8-9) | DPR | MERC/CAPEX/2020-2021/WFH/SBR/21 | 2019-12-09 | 2020-07-24 | 479.5 | 479.5 |  |  | 2020-07-24 | [8 empty] | 0 | [19 empty] | 0 | [9 empty] | N.A. | 0 | FALSE
39.1 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 8-9) | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/21 | 2019-12-09 | 2020-07-24 | 440.54 | 440.54 |  |  | 2020-07-24 |  |  |  | Sox reduction |  |  |  |  | 0 |  |  | 119.66 | 438.74 | 239.31 | [14 empty] | 0 |  |  | 119.66 | 438.74 | 239.31 |  |  |  |  | WIP | 119.66 | 0
0 | IDC | IDC | MERC/CAPEX/2020-2021/WFH/SBR/21 | 2019-12-09 | 2020-07-24 | 38.96 | 38.96 |  |  | 2020-07-24 | [8 empty] | 0 | [19 empty] | 0 | [9 empty] | N.A. | 0 | FALSE
41 | CHP Performance Improvement Schemes at Unit 8-9 of CSTPS, Chandrapur. | DPR | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-08-31 | 2023-11-03 | 26.61 | 26.61 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
41.1 | Work of Design engineering , supply and installation of modular chutes with sintered silicon carbide for smooth flow &center feeding in CHP 2x500MW CSTPS | Scheme | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-08-31 | 2023-11-03 | 9.43 | 9.43 | [11 empty] | 0 |  |  | 4.715 | 4.715 | [15 empty] | 0 |  |  | 4.715 | 4.715 | [6 empty] | 4.715 | FALSE
41.2 | Supply erection & commissioning of set of internal of impact crusher spares installed at CHPP-D, CSTPS | Scheme | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-08-31 | 2023-11-03 | 8.05 | 8.05 | [11 empty] | 0 |  |  | 4.025 | 4.025 | [15 empty] | 0 |  |  | 4.025 | 4.025 | [6 empty] | 4.025 | FALSE
41.3 | Scheme for replacement of Scoop coupling/Fluid coupling of conveyor BC-101A/B/C, BC-102A/B, BC-104A/B, BC-105A/B ,BC-106A/B, BC-111A/B/C/D, BC-110A1/B1, BC-110A/B Installed at CHP-D, CSTPS Chandrapur | Scheme | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-08-31 | 2023-11-03 | 4.67 | 4.67 | [11 empty] | 0 |  |  | 2.335 | 2.335 | [15 empty] | 0 |  |  | 2.335 | 2.335 | [6 empty] | 2.335 | FALSE
41.4 | Supply erection & commissioning of set of internal of spares of stacker reclaimer installed at CHP-D, CSTPS Chandrapur | Scheme | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-08-31 | 2023-11-03 | 1.96 | 1.96 | [11 empty] | 0 |  |  | 0.98 | 0.98 | [15 empty] | 0 |  |  | 0.98 | 0.98 | [6 empty] | 0.98 | FALSE
41.5 | Supply erection & commissioning of set of internal of spares of Wagon tippler installed at CHP-D, CSTPS Chandrapur | Scheme | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-08-31 | 2023-11-03 | 2.12 | 2.12 | [11 empty] | 0 |  |  | 1.06 | 1.06 | [15 empty] | 0 |  |  | 1.06 | 1.06 | [6 empty] | 1.06 | FALSE
| IDC | IDC | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-08-31 | 2023-11-03 | 0.38 | 0.38 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
HO DPR 2 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | DPR | MERC/CAPEX/2021-2022/MSPGCL/063 | 2018-08-31 | 2022-02-12 | 113.91 | 57 |  |  | 2022-02-12 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
HO DPR 2.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | Scheme | MERC/CAPEX/2021-2022/MSPGCL/063 | 2018-08-31 | 2022-02-12 | 108.48 | 54.24 |  |  | 2022-02-12 | [8 empty] | 0 |  |  |  |  | 27.12 | [10 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 27.12 | [5 empty] | 0 | 0
| IDC | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2018-08-31 | 2022-02-12 | 5.43 | 2.76 |  |  | 2022-02-12 | [8 empty] | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | FALSE
A6 | Supply, Installation & Commissioning of Online Coal Flow Monitoring & Balancing System at Unit-8-9, CSTPS, Chandrapur | DPR | MERC/CAPEX/2024-2025/MSPGCL/0457 Dt 26.07.2024 | 2024-01-31 | 2024-07-26 | 34.52 | 34.21 | [11 empty] | 0 | [19 empty] | 0
| Supply, installation and commissioning of Online Coal flow monitoring and balancing system for U- 8 & 9, CSTPS, Chandrapur. | Scheme | MERC/CAPEX/2024-2025/MSPGCL/0457 Dt 26.07.2024 | 2024-01-31 | 2024-07-26 | 34.21 | 34.21 | [6 empty] | Improvement in stability of Boiler for Flexible operation of units. |  |  |  |  | 0 |  |  |  |  | 17.105 | 17.105 | [13 empty] | 0 |  |  |  |  | 17.105 | 17.105 |  |  |  | Proposal in process
| IDC | IDC | MERC/CAPEX/2024-2025/MSPGCL/0457 Dt 26.07.2024 | 2024-01-31 | 2024-07-26 | 0.31 | 0.31 | [11 empty] | 0 | [19 empty] | 0
A7 | Providing, supplying, laying and commissioning of 1600 mm dia. M.S. Pipe by replacement of existing PSC raw water line from Erai dam to reservoir at CSTPS, Chandrapur | DPR | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-01-31 | 2024-08-06 | 127.95 | 40.7945 | [11 empty] | 0 | [19 empty] | 0
| Providing, supplying, laying and commissioning of 1600mm dia. M.S. pipe by replacement of existing PSC raw water line from Erai dam to reservoir at CSTPS, Chandrapur | Scheme | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-01-31 | 2024-08-06 | 119.12 | 40.7945 | [11 empty] | 0 |  |  |  |  | 40.7945 | [14 empty] | 0 |  |  |  |  | 40.7945 |  |  |  |  | Proposal in process
| IDC | IDC | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-01-31 | 2024-08-06 | 8.83 | 8.83 | [11 empty] | 0 | [19 empty] | 0
A8 | Adoption of Ozonization technique for disinfection of Cooling Water System at U # 8 & 9 | DPR | MERC/CAPEX/MSPGCL/2023-2024/0467 Dt 02.08.2024 | 2024-04-12 | 2024-08-02 | 69.41 | 67 | [11 empty] | 0 | [19 empty] | 0
| Adoption of Ozonization technique for disinfection of Unit 8&9 Cooling Water at CSTPS. | Scheme | MERC/CAPEX/MSPGCL/2023-2024/0467 Dt 02.08.2024 | 2024-04-12 | 2024-08-02 | 67.21 | 67 | [11 empty] | 0 |  |  |  | 33.5 | 33.5 | [14 empty] | 0 |  |  |  | 33.5 | 33.5
| IDC | IDC | MERC/CAPEX/MSPGCL/2023-2024/0467 Dt 02.08.2024 | 2024-04-12 | 2024-08-02 | 2.2 | 2.2 | [11 empty] | 0 | [19 empty] | 0
[19 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
[19 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
[19 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
[19 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
| (ii) Submitted to MERC | [8 empty] | - | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
Y1 | Multiple Schemes for Electrical Maintenance Section and Design, Engineering, Manufacturing, Testing, Unloading at site, E&C of 200MVA, 21/420KV Single Phase Generator Transformer for Unit # 8 & 9, CSTPS | DPR | To be resubmitted | 2024-01-31 |  | 13.25 | [12 empty] | 0 | [19 empty] | 0
| Procurement of 10MW, 11kV Motor and its recommended spare for Boiler Feed Pump (BFP) | Scheme | To be resubmitted | 2024-01-31 |  | 4.95 | [12 empty] | 0 |  |  |  |  | 4.95 | [14 empty] | 0 |  |  |  |  | 4.95 | [5 empty] | Plant & Machinery
| Replacement of NiCd battery sets installed for UPS of Fire Water Pump House, CMRH & SWAS lab of Unit 8 & 9, CSTPS, Chandrapur. | Scheme | To be resubmitted | 2024-01-31 |  | 0.86 | [12 empty] | 0 |  |  |  |  | 0.86 | [14 empty] | 0 |  |  |  |  | 0.86 | [5 empty] | Plant & Machinery
| Retrofitting of GE make LT Air Circuit Breakers of various current ratings and procurement of their recommended spares for Unit-8&9, CSTPS | Scheme | To be resubmitted | 2024-01-31 |  | 4.85 | [12 empty] | 0 |  |  |  |  | 4.85 | [14 empty] | 0 |  |  |  |  | 4.85 | [5 empty] | Plant & Machinery
| Procurement of BHEL make 6.6kV and 11kV Vacuum Circuit Breakers for Unit-8&9, CSTPS Chandrapur | Scheme | To be resubmitted | 2024-01-31 |  | 2.07 | [12 empty] | 0 |  |  |  |  | 2.07 | [14 empty] | 0 |  |  |  |  | 2.07 | [5 empty] | Plant & Machinery
| IDC | IDC | To be resubmitted | 2024-01-31 |  | 0.52 | [12 empty] | 0 | [19 empty] | 0 | [10 empty] | Plant & Machinery
Y5 | Scheme-1: Procurement of assembly of baskets for Air Preheater of type 31.05 VIMT 2000 (72° PA), Scheme-2: Procurement of spares for PRDS station pressure control valves and Desuperheating spray Control valves in Boiler at U-8&9, CSTPS, Chandrapur, Scheme-3: Procurement of complete set of sky climber at U-8&9, CSTPS, Chandrapur. Scheme-4: Supply, erction, commissioning of oil free rotary screw compressors (including all Civil Electrical, C&I, Testing work) for CMRH system at U-8&9, CSTPS, Chandrapur. | DPR | To be resubmitted | 2024-04-12 |  | 34.23 | [12 empty] | 0 | [19 empty] | 0
| Scheme-1: Procurement of assembly of baskets for Air Preheater of type 31.5 VIMT 2000 (72° PA) at U-8&9, CSTPS, Chandrapur. | Scheme | To be resubmitted | 2024-04-12 |  | 15.78 | [12 empty] | 0 |  |  |  | 15.78 | [15 empty] | 0 |  |  |  | 15.78 | [6 empty] | Plant & Machinery
| Scheme-2: Procurement of spares for PRDS station pressure control valves and Desuperheating spray control valves in Boiler at U-8&9, CSTPS, Chandrapur. | Scheme | To be resubmitted | 2024-04-12 |  | 6.09 | [12 empty] | 0 |  |  |  | 6.09 | [15 empty] | 0 |  |  |  | 6.09 | [6 empty] | Plant & Machinery
| Scheme-3: Procurement of complete set of sky climber at U-8&9, CSTPS, Chandrapur. | Scheme | To be resubmitted | 2024-04-12 |  | 3.16 | [12 empty] | 0 |  |  |  | 3.16 | [15 empty] | 0 |  |  |  | 3.16 | [6 empty] | Plant & Machinery
| Scheme-4: Supply, erection, commissioning of oil free rotary screw compressors (including all Civil Electrical, C&I, Testing work) for CMRH system at U-8&9, CSTPS, Chandrapur. | Scheme | To be resubmitted | 2024-04-12 |  | 8.3 | [12 empty] | 0 |  |  |  | 8.3 | [15 empty] | 0 |  |  |  | 8.3 | [6 empty] | Plant & Machinery
| IDC | IDC | To be resubmitted | 2024-04-12 |  | 0.9 | [12 empty] | 0 | [19 empty] | 0 | [10 empty] | Plant & Machinery
Y6 &Y7 | Supply, Erection & commissioning/retrofitting of HT Circuit Breaker with SF6 Contactor at AHP at Unit-8&9 & CHP#D and Supply, Installation and Commissioning of MV VFD panel along with integrated online cell redundancy technology with VFD bypass feature arrangement for conveyors 103 A & B of CHP-B, C.S.T.P.S., Chandrapur & Design, engineering, manufacturing, testing, unloading at site, E&C of Two No of 200 MVA, 21/420 KV Single Phase Generator Transformers for Unit-8&9, CSTPS, Chandrapur. Through OEM | DPR | To be resubmitted |  |  | 38.33 | [12 empty] | 0 | [19 empty] | 0
| Scheme 1: Retrofitting of BHEL make HT Circuit Breaker with SF6 contactor at AHP, Unit#8&9, CSTPS. | Scheme | To be resubmitted |  |  | 5.64 | [12 empty] | 0 |  |  |  | 38.33 | [15 empty] | 0 |  |  |  | 38.33 | [6 empty] | Plant & Machinery
| Scheme 2: Retrofitting of BHEL make HT Circuit Breaker with SF6 contactor at CHP#D, Unit#8&9, CSTPS. | Scheme | To be resubmitted |  |  | 4.03 | [12 empty] | 0 |  |  |  | 5.64 | [15 empty] | 0 |  |  |  | 5.64 | [6 empty] | Plant & Machinery
| Scheme 3: Supply, Installation and Commissioning of MV VFD panel along with integrated online cell redundancy technology with VFD bypass feature arrangement for conveyors 103 A & B of CHP-B. | Scheme | To be resubmitted |  |  | 6.2 | [12 empty] | 0 |  |  |  | 4.03 | [15 empty] | 0 |  |  |  | 4.03 | [6 empty] | Plant & Machinery
| Design, engineering, manufacturing, testing, unloading at site, E&C of Two No of 200 MVA, 21/420 KV Single Phase Generator Transformers for Unit-8&9, CSTPS, Chandrapur. Through OEM | Scheme | To be resubmitted |  |  | 21.07 | [12 empty] | 0 |  |  |  |  | 21.07 | [14 empty] | 0 |  |  |  |  | 21.07 | [5 empty] | Plant & Machinery
| IDC | IDC | To be resubmitted |  |  | 1.39 | [12 empty] | 0 | [19 empty] | 0 | [10 empty] | Plant & Machinery
[19 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
| (iii) Yet to be Submitted to MERC | [17 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
[19 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
| Boiler Maintenance -III | [17 empty] | 0 | [19 empty] | 0
1 | Procurement of Air & Flue gas ducts of Boiler , Blade set and HAD for PA and FD Fan , SCAPH Coil, ID Fan spares at Unit-8&9 CSTPS, Chandrapur | DPR |  |  |  | 77 | [12 empty] | 0 | [19 empty] | 0
| Scheme-1 Procurement of Air & flue gas expansion joints | Scheme |  |  |  | 40 | [7 empty] | • Boiler efficiency will be improved. • Improved Heat Rate. • Reduction in Auxiliray power consumption |  |  |  |  | 0 |  |  |  |  | 40 | [14 empty] | 0 |  |  |  |  | 40 | [5 empty] | Plant & Machinery
| Scheme-2 :Procurement of Blade Set and 2 sets of HAD of PA Fan. | Scheme |  |  |  | 10 | [7 empty] | • Availability and Reliability of auxiliary will be increased & saves genearation loss in case of HAD Failure. |  |  |  |  | 0 |  |  |  |  | 10 | [14 empty] | 0 |  |  |  |  | 10 | [5 empty] | Plant & Machinery
| Scheme -3 Procurement of Blade Set and 2 sets of HAD of FD Fan. | Scheme |  |  |  | 10 | [7 empty] | • Availability and Reliability of auxiliary will be increased & saves genearation loss in case of HAD Failure. |  |  |  |  | 0 |  |  |  |  | 10 | [14 empty] | 0 |  |  |  |  | 10 | [5 empty] | Plant & Machinery
| Scheme-4 Procurement of SCAPH Coil for unit- 8&9 | Scheme |  |  |  | 6 | [7 empty] | • Increases Cold end basket Life. |  |  |  |  | 0 |  |  |  |  | 6 | [14 empty] | 0 |  |  |  |  | 6 | [5 empty] | Plant & Machinery
| Scheme-5 :Procurement of ID Fan Impeller , Shaft and Blade set at unit-8 & 9, CSTPS | Scheme |  |  |  | 6 | [7 empty] | • Availability and Reliability of auxiliary will be increased & saves genearation loss in case of material Failure. |  |  |  |  | 0 |  |  |  |  | 6 | [14 empty] | 0 |  |  |  |  | 6 | [5 empty] | Plant & Machinery
| Scheme 6: Procurment of Coal Fuel pipes for unit -8 &9 , CSTPS | Scheme |  |  |  | 5 | [7 empty] | Coal leakages will be reduced by replacing damaged coal pipes |  |  |  |  | 0 |  |  |  |  | 5 | [14 empty] | 0 |  |  |  |  | 5 | [5 empty] | Plant & Machinery
2 | Procurement of LTSH and economiser for unit-8&9 CSTPS, Chandrapur | DPR |  |  |  | 55.03 | [12 empty] | 0 | [19 empty] | 0
| Procurement of LTSH Coil assemsblies unit- 8&9 | Scheme |  |  |  | 20 | [7 empty] | 1.Reduce BTL 2.Boiler efficiency will be improved. 3.Availability and Reliability of unit will be increased |  |  |  |  | 0 | [7 empty] | 20 | [11 empty] | 0 | [7 empty] | 20 |  |  | Plant & Machinery
| Procurement of economiser coil asemblies | Scheme |  |  |  | 25 | [7 empty] | 1.Reduce BTL 2.Boiler efficiency will be improved. 3.Availability and Reliability of unit will be increased |  |  |  |  | 0 | [7 empty] | 25 | [11 empty] | 0 | [7 empty] | 25 |  |  | Plant & Machinery
| Up-gradation of existing belt type gravimetric coal feeders to gravimetric rotary weigh coal feeders of unit- 8&9, at CSTPS, Chandrapur | Scheme |  |  |  | 10.03 | [7 empty] | 1.Availability of coal feeder will be improved |  |  |  |  | 0 |  |  |  | 10.03 | [15 empty] | 0 |  |  |  | 10.03 | [6 empty] | Plant & Machinery
3 | Supply of Quick Erect Aluminum Boiler Scaffolding system or unit- 8 & 9, (2X500MW), CSTPS, Chandrapur. | DPR |  |  |  | 35 | [12 empty] | 0 | [19 empty] | 0
| Supply of Quick Erect Aluminum Boiler Scaffolding system or unit- 8 & 9, (2X500MW), CSTPS, Chandrapur. | Scheme |  |  |  | 35 | [7 empty] | Saves outage time during overhaul. |  |  |  |  | 0 |  |  |  | 35 | [15 empty] | 0 |  |  |  | 35 | [6 empty] | Plant & Machinery
| Turbine Maintenance -III | [17 empty] | 0 | [19 empty] | 0
1 | Schemes for Improvement in availability & performance of TG auxiliaries at U-8&9, CSTPS, Chandrapur. | DPR |  |  |  | 37.9 | [7 empty] | • Auxiliary efficiency will be improved. • Improvement in Heat Rate. • Reduction in Auxiliray power consumption. |  |  |  |  | 0 | [19 empty] | 0
| 1. Procurement of BFP Booster Pump assembly for Unit-8 & 9, CSTPS Chandrapur | Scheme |  |  |  | 3.2 | [7 empty] | • Auxiliary efficiency will be improved. • Improvement in Heat Rate. • Reduction in Auxiliray power consumption. |  |  |  |  | 0 |  |  |  |  | 3.2 | [14 empty] | 0 |  |  |  |  | 3.2 | [5 empty] | Plant & Machinery
| 2. Procurement of Boiler Feed Pump catridge with CI sealing for Unit- 8 & 9, CSTPS Chandrapur | Scheme |  |  |  | 5.2 | [7 empty] | • Auxiliary efficiency will be improved. • Improvement in Heat Rate. • Reduction in Auxiliray power consumption. |  |  |  |  | 0 | [5 empty] | 5.2 | [13 empty] | 0 | [5 empty] | 5.2 |  |  |  |  | Plant & Machinery
| 3. Procurement of Modulating type Boiler Feed Pump Recirculation valve (06 Nos) assembly for Unit- 8 & 9, CSTPS Chandrapur | Scheme |  |  |  | 3 | [7 empty] | • Auxiliary efficiency will be improved. • Improvement in Heat Rate. • Reduction in Auxiliray power consumption. Improvement in systen reliability & availability. |  |  |  |  | 0 |  |  |  | 3 | [15 empty] | 0 |  |  |  | 3 | [6 empty] | Plant & Machinery
| 4. Procurement of HP Heater HPH-5B assembly for Unit- 8 & 9, CSTPS Chandrapur | Scheme |  |  |  | 8 | [7 empty] | • Improvement in Heat Rate. • Improvement in systen reliability & availability. |  |  |  |  | 0 |  |  |  |  | 8 | [14 empty] | 0 |  |  |  |  | 8 | [5 empty] | Plant & Machinery
| 5. Procurement of MDBFP working oil & lube oil coolers for Unit- 8 & 9, CSTPS Chandrapur | Scheme |  |  |  | 1.5 | [7 empty] | • Auxiliary efficiency will be improved. Improvement in systen reliability & availability. |  |  |  |  | 0 | [5 empty] | 1.5 | [13 empty] | 0 | [5 empty] | 1.5 |  |  |  |  | Plant & Machinery
| 6. Procurement of TDBFP Turbine rotor K1401-2 at Unit- 8 & 9, CSTPS Chandrapur | Scheme |  |  |  | 7.5 | [7 empty] | • Auxiliary efficiency will be improved. • Improvement in Heat Rate. • Reduction in Auxiliray power consumption. |  |  |  |  | 0 |  |  |  |  | 7.5 | [14 empty] | 0 |  |  |  |  | 7.5 | [5 empty] | Plant & Machinery
| 7. Procurement of Main TG Jacking oil pumps (2 Nos.) at Unit- 8 & 9, CSTPS Chandrapur | Scheme |  |  |  | 0.5 | [7 empty] | • Improvement in systen reliability & availability. |  |  |  |  | 0 |  |  |  | 0.5 | [15 empty] | 0 |  |  |  | 0.5 | [6 empty] | Plant & Machinery
| 8. Procurement of HP elements of ZR500 Atlas Copco make compressors along with inter & after coolers tube nest at Unit- 8 & 9, CSTPS Chandrapur | Scheme |  |  |  | 2 | [7 empty] | • Auxiliary efficiency will be improved. • Improvement in systen reliability & availability.. • Reduction in Auxiliray power consumption. |  |  |  |  | 0 |  |  |  | 2 | [15 empty] | 0 |  |  |  | 2 | [6 empty] | Plant & Machinery
| 9. Procurement of CW & ACW Pump spares at Unit- 8 & 9, CSTPS Chandrapur | Scheme |  |  |  | 1.5 | [7 empty] | • Auxiliary efficiency will be improved. • Improvement in systen reliability & availability.. • Reduction in Auxiliray power consumption. |  |  |  |  | 0 |  |  |  | 1.5 | [15 empty] | 0 |  |  |  | 1.5 | [6 empty] | Plant & Machinery
| 10. Procurement of condenser tubes at Unit- 8 & 9, CSTPS Chandrapur | Scheme |  |  |  | 2.5 | [7 empty] | • Auxiliary efficiency will be improved. • Improvement in Heat Rate. • Reduction in Auxiliray power consumption. |  |  |  |  | 0 | [6 empty] | 2.5 | [12 empty] | 0 | [6 empty] | 2.5 |  |  |  | Plant & Machinery
| 11. Procurement of HPCF Pump at Unit- 8 & 9, CSTPS Chandrapur | Scheme |  |  |  | 3 | [7 empty] | • Auxiliary efficiency will be improved. • Improvement in systen reliability & availability.. |  |  |  |  | 0 | [6 empty] | 3 | [12 empty] | 0 | [6 empty] | 3 |  |  |  | Plant & Machinery
2 | DPR for performance improvement of Condenser Cooling water system & improvement in system reliability of auxiliary cooling water system installed at Unit-8&9, 2x500MW, CSTPS, Chandrapur | DPR |  |  |  | 34 | [7 empty] | • Auxiliary efficiency will be improved. • Improvement in Heat Rate. • Reduction in Auxiliray power consumption. |  |  |  |  | 0 | [19 empty] | 0
| DPR for performance improvement of Condenser Cooling water system & improvement in system reliability of auxiliary cooling water system installed at Unit-8&9, 2x500MW, CSTPS, Chandrapur | Scheme |  |  |  | 34 | [7 empty] | • Auxiliary efficiency will be improved. • Improvement in Heat Rate. • Reduction in Auxiliray power consumption. |  |  |  |  | 0 |  |  |  |  | 17 | 17 | [13 empty] | 0 |  |  |  |  | 17 | 17 |  |  |  |  | Plant & Machinery
3 | Procurement of main turbine IPT module at Unit- 8 & 9, CSTPS Chandrapur | DPR |  |  |  | 50 | [7 empty] | • Auxiliary efficiency will be improved. • Improvement in Heat Rate. • Improvement in system Availability & reliability |  |  |  |  | 0 | [19 empty] | 0
| Procurement of main turbine IPT module at Unit- 8 & 9, CSTPS Chandrapur | Scheme |  |  |  | 50 | [7 empty] | • Auxiliary efficiency will be improved. • Improvement in Heat Rate. • Improvement in system Availability & reliability |  |  |  |  | 0 | [7 empty] | 50 | [11 empty] | 0 | [7 empty] | 50 |  |  | Plant & Machinery
| Electrical Maintenance -III | [17 empty] | 0 | [19 empty] | 0
1 | Proc of GTR, MDBFP, UPS battery, breakers | DPR |  |  |  | 37 | [12 empty] | 0 | [19 empty] | 0
| Design, engineering, manufacturing, testing, unloading at site, E&C of 200 MVA, 21/420 KV Single Phase Generator Transformer for Unit-8&9, CSTPS, Chandrapur | Scheme |  |  |  | 21.07 | [12 empty] | 0 |  |  |  | 21.07 | [15 empty] | 0 |  |  |  | 21.07 | [6 empty] | Plant & Machinery
| Procurement of MDBFP motor and recommended spares The Fire Water Pump House UPS Battery set of 240V, 40AH Capacity (1.2V X 176 Cells ) Ni Cd Type Make- HBL The UPS Battery Set at SWAS Lab (Outdoor Area), 45AH Capacity (1.2 V X 276 Cells) Ni Cd type Make- HBL for Unit#8&9 The UPS Battery Set at CMRH (Outdoor Area), 69AH Capacity (1.2 V X 280 Cells) Ni Cd type Make- HBL for Unit#8&9 Retrofitting of 415V GE make ACB of various ratings along with allied spares. BHEL make Breakers and spares for 6.6 kV and 11kV panels | Scheme |  |  |  | 15.07 | [12 empty] | 0 |  |  |  | 15.07 | [15 empty] | 0 |  |  |  | 15.07 | [6 empty] | Plant & Machinery
2 | Design, engineering, manufacturing, testing, unloading at site, E&C of 80 MVA, 420/11/6.9 KV three Phase Station Transformer & 25MVA 21/6.9KV Three phase Unit Aux Transformer as a common pool spares for BTPS 500MW, Khaparkheda 500 MW and Unit-8&9, CSTPS, Chandrapur & Supply, installation, commissioning and testing of Station Batteries of Unit-8&9 CSTPS alongwith all outdoor batteries | DPR |  |  |  | 34 | [12 empty] | 0 | [19 empty] | 0
| Design, engineering, manufacturing, testing, unloading at site, E&C of 80 MVA, 420/11/6.9 KV three Phase Station Transformer & 25MVA 21/6.9KV Three phase Unit Aux Transformer as a common pool spares for BTPS 500MW, Khaparkheda 500 MW and Unit-8&9, CSTPS, Chandrapur | Scheme |  |  |  | 22 | [12 empty] | 0 |  |  |  |  | 22 | [14 empty] | 0 |  |  |  |  | 22 | [5 empty] | Plant & Machinery
| Supply, installation, commissioning and testing of Station Batteries of Unit-8&9 CSTPS alongwith all outdoor batteries | Scheme |  |  |  | 12 | [12 empty] | 0 | [5 empty] | 12 | [13 empty] | 0 | [5 empty] | 12 |  |  |  |  | Plant & Machinery
| I&C -III | [17 empty] | 0 | [19 empty] | 0
1 | Upgradation of Analysis & Diagnostics system (A&D) for VMS and TSI system at Unit-8&9, CSTPS, Chandrapur.& other schemes | DPR |  |  |  | 25.5 | [12 empty] | 0 | [19 empty] | 0
| Upgradation of Analysis & Diagnostics system (A&D) for VMS and TSI system at Unit-8&9, CSTPS, Chandrapur. | Scheme |  |  |  | 17 | [7 empty] | Improvement in condition monitoring and Preventive measure before break down of critical Auxillary. |  |  |  |  | 0 |  |  |  | 17 | [15 empty] | 0 |  |  |  | 17 | [6 empty] | Plant & Machinery
| Installation of CO analysers at Eco outlet at Unit-8&9, CSTPS Chandrapur. | Scheme |  |  |  | 2.5 | [7 empty] | Improvement in coal combustion by optimising secondary air. |  |  |  |  | 0 |  |  |  | 2.5 | [15 empty] | 0 |  |  |  | 2.5 | [6 empty] | Plant & Machinery
| Complete Engineering Retrofitting of Existing 196 NT Controller by DT 9 Controller alongwith HMI units for Unit 8/9 coal feeder system. | Scheme |  |  |  | 2 | [7 empty] | Due to Obslence of controllers for relibility improvement. |  |  |  |  | 0 |  |  |  | 2 | [15 empty] | 0 |  |  |  | 2 | [6 empty] | Plant & Machinery
| Supply of spares for LP bypass system. | Scheme |  |  |  | 2 | [7 empty] | Improvement in availability. |  |  |  |  | 0 |  |  |  | 2 | [15 empty] | 0 |  |  |  | 2 | [6 empty] | Plant & Machinery
| Supply of spares for maxDNA DCS system | Scheme |  |  |  | 2 | [7 empty] | Improvement in availability. |  |  |  |  | 0 |  |  |  | 2 | [15 empty] | 0 |  |  |  | 2 | [6 empty] | Plant & Machinery
2 | Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-9, CSTPS, Chandrapur. | DPR |  |  |  | 30 | [12 empty] | 0 | [19 empty] | 0
| Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-9, CSTPS, Chandrapur. | Scheme |  |  |  | 30 | [7 empty] | To improve relibility of units on lower load. |  |  |  |  | 0 |  |  |  | 30 | [15 empty] | 0 |  |  |  | 30 | [6 empty] | Plant & Machinery
3 | Upgradation of HMI and hardware of GE make PLCs installed at Unit-8&9, CSTPS, Chandrapur. & other schemes | DPR |  |  |  | 27 | [12 empty] | 0 | [19 empty] | 0
| Upgradation of HMI and hardware of GE make PLCs installed at Unit-8&9, CSTPS, Chandrapur. | Scheme |  |  |  | 15 | [7 empty] | Due to Obslence of controllers for relibility improvement. |  |  |  |  | 0 |  |  |  |  | 15 | [14 empty] | 0 |  |  |  |  | 15 | [5 empty] | Plant & Machinery
| Upgradation of TD-BFP Turbovisory system installed at Unit-8&9, CSTPS, Chandrapur | Scheme |  |  |  | 5 | [7 empty] | Due to Obslence of controllers for relibility improvement. |  |  |  |  | 0 |  |  |  |  | 5 | [14 empty] | 0 |  |  |  |  | 5 | [5 empty] | Plant & Machinery
| Upgradation of EWLI system installed at Unit-8&9, CSTPS, Chandrapur | Scheme |  |  |  | 1.5 | [7 empty] | Due to Obslence of controllers for relibility improvement. |  |  |  |  | 0 |  |  |  |  | 1.5 | [14 empty] | 0 |  |  |  |  | 1.5 | [5 empty] | Plant & Machinery
| Upgradation of O2 analysers installed at Unit-8&9, CSTPS, Chandrapur | Scheme |  |  |  | 1 | [7 empty] | Improvement in coal combustion by optimising secondary air. |  |  |  |  | 0 |  |  |  |  | 1 | [14 empty] | 0 |  |  |  |  | 1 | [5 empty] | Plant & Machinery
| Installation of High temperature Camera system at Unit-8&9, CSTPS, Chandrapur. | Scheme |  |  |  | 1.5 | [7 empty] | To improve monitoring of Flame. |  |  |  |  | 0 |  |  |  |  | 1.5 | [14 empty] | 0 |  |  |  |  | 1.5 | [5 empty] | Plant & Machinery
| Up-gradation of HEA igniter system at Unit-8&9, CSTPS, Chandrapur. | Scheme |  |  |  | 1 | [7 empty] | Improvement in operation of oil Guns. |  |  |  |  | 0 |  |  |  |  | 1 | [14 empty] | 0 |  |  |  |  | 1 | [5 empty] | Plant & Machinery
| Up-gradation of Flue Gas Analysers and Opacity Analysers at Unit-8&9, CSTPS, Chandrapur. | Scheme |  |  |  | 2 | [7 empty] | To comply MPCB normative. |  |  |  |  | 0 |  |  |  |  | 2 | [14 empty] | 0 |  |  |  |  | 2 | [5 empty] | Plant & Machinery
4 | Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-8, CSTPS, Chandrapur. | DPR |  |  |  | 30 | [12 empty] | 0 | [19 empty] | 0
| Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-8, CSTPS, Chandrapur. | Scheme |  |  |  | 30 | [7 empty] | To improve relibility of units on lower load. |  |  |  |  | 0 | [5 empty] | 30 | [13 empty] | 0 | [5 empty] | 30 |  |  |  |  | Plant & Machinery
5 | Multiple schemes C&I-3 | DPR |  |  |  | 42.5 | [12 empty] | 0 | [19 empty] | 0
| Total Mercury (Gaseous) Analyzers along with their online data connectivity & Remote calibration U-3 to 9 | Scheme |  |  |  | 9 | [7 empty] | To comply MPCB normative. |  |  |  |  | 0 |  |  |  |  | 3 | 6 | [13 empty] | 0 |  |  |  |  | 3 | 6 |  |  |  |  | Plant & Machinery
| Procurement of Controllers & Com Boxes for Air Compressors of Unit-8&9. | Scheme |  |  |  | 5.5 | [7 empty] | Due to Obslence of controllers for relibility improvement. |  |  |  |  | 0 |  |  |  |  | 5.5 | [14 empty] | 0 |  |  |  |  | 5.5 | [5 empty] | Plant & Machinery
| Up-gradation of Steam and Water Analysis System (SWAS) for Unit – 8 & 9 | Scheme |  |  |  | 13 | [7 empty] | To improve monitoring of critical parameters of feed water and steam. |  |  |  |  | 0 |  |  |  |  | 13 | [14 empty] | 0 |  |  |  |  | 13 | [5 empty] | Plant & Machinery
| Up-gradation of Servo valve (ST) with proportional valves (PV) for HP bypass system at Unit – 8 & 9 | Scheme |  |  |  | 6 | [7 empty] | Due to Obslence of Servo valvls for relibility improvement. |  |  |  |  | 0 |  |  |  |  | 6 | [14 empty] | 0 |  |  |  |  | 6 | [5 empty] | Plant & Machinery
| Upgradation of GEHO pump VFD panels for Unit – 8 & 9 | Scheme |  |  |  | 9 | [7 empty] | Due to Obslence of VFD for relibility improvement. |  |  |  |  | 0 |  |  |  |  | 9 | [14 empty] | 0 |  |  |  |  | 9 | [5 empty] | Plant & Machinery
6 | Upgradation of measurement and control system installed at CSTPS Unit 8&9 & Upgradation of Numerical Protection Relay of Alstom / Schnieder make installed at Unit-8&9, CSTPS, Chandrapur. | DPR |  |  |  | 25 | [12 empty] | 0 | [19 empty] | 0
| Upgradation of measurement and control system installed at CSTPS Unit 8&9 | Scheme |  |  |  | 20 | [12 empty] | 0 | [5 empty] | 20 | [13 empty] | 0 | [5 empty] | 20 |  |  |  |  | Plant & Machinery
| Upgradation of Numerical Protection Relay of Alstom / Schnieder make installed at Unit-8&9, CSTPS, Chandrapur. | Scheme |  |  |  | 5 | [7 empty] | As such this DPR is for upgradation of the numerical protection relay for system improvement, whereas the existing installed relay was obsoleted as per OEM. If availability of the new spares is not ensured, then there can be possibility of auxiliary performance declination & finally breakdown, resulting huge generation loss. Consider the situation where unit is tripped on account of malfunction or failure of numerical protection relay, there is generation loss for 05 hours to synchronising the Unit. The generation loss for 05 hour will be 41,00,000.00/- (Rs. Forty-one Lakhs) a day which is very heavy, and this type of tripping may be progressively increased accordingly due to failure of numerical protection relay. Hence, it is not catastrophic to invest small amount of investment on upgradation of numerical protection relay to save huge amount. |  |  |  |  | 0 | [5 empty] | 5 | [13 empty] | 0 | [5 empty] | 5 |  |  |  |  | Plant & Machinery
| AHP-III | [17 empty] | 0 | [19 empty] | 0
1 | supply of piston cylinder assembly, diaphragm assembly, Suction and discharge valve housing assembly of GEHO pump (Model- TZPM 1200). & other schemes | DPR |  |  |  | 43 | [12 empty] | 0 | [19 empty] | 0
| Scheme-1 :supply of piston cylinder assembly, diaphragm assembly, Suction and discharge valve housing assembly of GEHO pump (Model- TZPM 1200). | Scheme |  |  |  | 13 | [7 empty] | Improvement in availability. |  |  |  |  | 0 |  |  |  |  | 13 | [14 empty] | 0 |  |  |  |  | 13 | [5 empty] | Plant & Machinery
| Scheme -2 :Procurement of sub assemblies for conveying air compressor model ZR 275 and instrument air compressor model ZR 110 in Ash handling plant Unit-8&9 (2x500MW) at CSTPS, Chandrapur. | Scheme |  |  |  | 18 | [7 empty] | Improvement in availability. |  |  |  |  | 0 |  |  |  |  | 18 | [14 empty] | 0 |  |  |  |  | 18 | [5 empty] | Plant & Machinery
| Scheme -3 Supply of 10/8 FAH Warman make slurry pump impeller element assembly, Bearing assembly unit, jacket assembly. | Scheme |  |  |  | 12 | [7 empty] | Improvement in availability. |  |  |  |  | 0 |  |  |  |  | 12 | [14 empty] | 0 |  |  |  |  | 12 | [5 empty] | Plant & Machinery
2 | Supply and replacement of 400 NB MSERW pipeline of ash disposal system of unit 8&9 at CSTPS, Chandrapur. | DPR |  |  |  | 70 | [12 empty] | 0 | [19 empty] | 0
| Scheme-1 :Supply and replacement of 400 NB MSERW pipeline of ash disposal system of unit 8&9 at CSTPS, Chandrapur. | Scheme |  |  |  | 70 | [12 empty] | 0 | [5 empty] | 70 | [13 empty] | 0 | [5 empty] | 70 |  |  |  |  | Other & Civil work
3 | Complete ESP Refurbishment of 1st & 2 nd Row Field of Unit 8&9 at CSTPS. | DPR |  |  |  | 25 | [12 empty] | 0 | [19 empty] | 0
| Scheme-1 : Complete ESP Refurbishment of 1st & 2 nd Row Field of Unit 8&9 at CSTPS. | Scheme |  |  |  | 25 | [12 empty] | 0 | [6 empty] | 12.5 | 12.5 | [11 empty] | 0 | [6 empty] | 12.5 | 12.5 |  |  | Plant & Machinery
| CHP - D | [17 empty] | 0 | [19 empty] | 0
1 | Upgradation Of Hydraulic Systems with Safety Mechanism for wagon unloading system at CHP-D CSTPS. | DPR |  |  |  | 30 | [12 empty] | 0 | [19 empty] | 0
| Supply erection & commissioning of wagon tippler, Side Arm Charger, apron feeder and stacker hydraulic drive system with online NAS value monitoring systems. | Scheme |  |  |  | 24 | [7 empty] | Will improve Performance of systemand unloading of wagons .Reduction in R.D.T. and demmurage. |  |  |  |  | 0 |  |  |  | 8 | 8 | 8 | [13 empty] | 0 |  |  |  | 8 | 8 | 8 |  |  |  |  | Plant & Machinery
| Wagon stopping mechanism (Safety) | Scheme |  |  |  | 6 | [7 empty] | Will reduce accidents. |  |  |  |  | 0 |  |  |  | 2 | 2 | 2 | [13 empty] | 0 |  |  |  | 2 | 2 | 2 |  |  |  |  | Plant & Machinery
2 | Upgardation and Capacity Enhancement of Side Arm Charger Apron Feeder and Bunker Conveyors at CHP-D CSTPS. | DPR |  |  |  | 94.5 | [12 empty] | 0 | [19 empty] | 0
| capacity enhancement to 60 wagons pulling capacity and associated modification of existing side arm charger | Scheme |  |  |  | 30 | [7 empty] | 60wagons will be pulled by SIde arm charger. Improves performance and reduction in RDT. |  |  |  |  | 0 |  |  |  |  | 10 | 10 | 10 | [12 empty] | 0 |  |  |  |  | 10 | 10 | 10 |  |  |  | Plant & Machinery
| Capacity enhancement , Commissionng of apron feeder drive | Scheme |  |  |  | 6 | [7 empty] | Increase in capacity, 3nos.of unloaded coal wagons can be evacuated . |  |  |  |  | 0 |  |  |  | 2 | 2 | 2 | [13 empty] | 0 |  |  |  | 2 | 2 | 2 |  |  |  |  | Plant & Machinery
| Modification and revamping of Apron Feeder 101,102,103 | Scheme |  |  |  | 23.5 | [7 empty] | Improvement in performance of system and reduction in RDT |  |  |  |  | 0 |  |  |  | 5 | 2.5 | 6 | 3 | 7 | [11 empty] | 0 |  |  |  | 5 | 2.5 | 6 | 3 | 7 |  |  | Plant & Machinery
| Supply,Installation and Commissioning of double drive Mechanism with Split Case Bearings for Tripper Trolley and bunkering conevyor belts of CHP-D, CSTPS | Scheme |  |  |  | 15 | [7 empty] | Improvement in performance of system, bunkering and reduction in Maintenance down time and generation loss |  |  |  |  | 0 |  |  |  |  | 15 | [14 empty] | 0 |  |  |  |  | 15 | [5 empty] | Plant & Machinery
| Modification of Fixed Tripper Head Pulley(Z-Point) of BC110A&B at CHP-D CSTPS. | Scheme |  |  |  | 8 | [7 empty] | Reduction in maintenance down time. |  |  |  |  | 0 |  |  |  |  | 8 | [14 empty] | 0 |  |  |  |  | 8 | [5 empty] | Plant & Machinery
| Modification, Errection & Commissioning of drive unit capacity enhancement for conveyor at CHP-D, Chandrapur TPS. | Scheme |  |  |  | 12 | [7 empty] | Reduction in RDT, Maintenance down time and improvement in performance of system. |  |  |  |  | 0 |  |  |  |  | 3 | 3 | 3 | 3 | [11 empty] | 0 |  |  |  |  | 3 | 3 | 3 | 3 |  |  | Plant & Machinery
3 | Performance Improvement Schemes of CHP-D CSTPS | DPR |  |  |  | 185 | [12 empty] | 0 | [19 empty] | 0
| Design engineering , supply and installation of modular chutes with weld cast Liners ,flap gates and actuators. | Scheme |  |  |  | 85 | [7 empty] | Improvement in performance and cleaning of system, reduction in RDT and generation loss. |  |  |  |  | 0 |  |  |  | 20 | 15 | 15 | 20 | 15 | [11 empty] | 0 |  |  |  | 20 | 15 | 15 | 20 | 15 |  |  | Plant & Machinery
| Supply erection & commissioning of set of internal of spares of Wagon tippler and Side Arm Charger installed at CHP-D, CSTPS Chandrapur | Scheme |  |  |  | 15 | [7 empty] | Will improve Performance of systemand unloading of wagons .Reduction in R.D.T. and demmurage. |  |  |  |  | 0 |  |  |  |  | 5 |  |  | 10 | [11 empty] | 0 |  |  |  |  | 5 |  |  | 10 |  |  | Plant & Machinery
| Supply erection & commissioning of set of internal of spares of stacker reclaimer installed at CHP-D, CSTPS Chandrapur | Scheme |  |  |  | 20 | [7 empty] | Will improve Performance of system and reduces generation loss. |  |  |  |  | 0 |  |  |  |  | 10 |  |  | 10 | [11 empty] | 0 |  |  |  |  | 10 |  |  | 10 |  |  | Plant & Machinery
| Supply erection & commissioning of set of internal of spares of Impact crusher installed at CHP-D, CSTPS Chandrapur | Scheme |  |  |  | 20 | [7 empty] | Will improve Performance of systemand unloading of wagons .Reduction in R.D.T. and demmurage. |  |  |  |  | 0 |  |  |  |  | 10 |  |  | 10 | [11 empty] | 0 |  |  |  |  | 10 |  |  | 10 |  |  | Plant & Machinery
| Supply erection & commissioning of set of internal of spares of wobbler feeder installed at CHP-D, CSTPS Chandrapur | Scheme |  |  |  | 20 | [7 empty] | Will improve Performance of systemand unloading of wagons .Reduction in R.D.T. and demmurage. |  |  |  |  | 0 |  |  |  |  | 10 |  |  | 10 | [11 empty] | 0 |  |  |  |  | 10 |  |  | 10 |  |  | Plant & Machinery
| Supply erection & commissioning of 1500 TPH capacity Stacker Recliamer sleeving bearing with fastener of CHP-D (U8&9), CSTPS, Chandrapur | Scheme |  |  |  | 5 | [7 empty] | Will improve Performance of system and reduces generation loss. |  |  |  |  | 0 |  |  |  |  | 5 | [14 empty] | 0 |  |  |  |  | 5 | [5 empty] | Plant & Machinery
| Supply of Gearbox assemblies at CHP-D CSTPS. | Scheme |  |  |  | 14 | [7 empty] | Will improve performance of system , reduces R.D.T and generation loss. |  |  |  |  | 0 |  |  |  | 7 |  |  | 7 | [12 empty] | 0 |  |  |  | 7 |  |  | 7 |  |  |  | Plant & Machinery
| Structure Strengthening,Modification works of Conveyors at CHP-D CSTPS | Scheme |  |  |  | 6 | [7 empty] | Will improve performance of system , reduces R.D.T and generation loss. |  |  |  |  | 0 |  |  |  | 3 |  |  | 3 | [12 empty] | 0 |  |  |  | 3 |  |  | 3 |  |  |  | Plant & Machinery
4 | Design, Installation, testing and commissioning of new conveyor systems of CHP-D, CSTPS, Chandrapur. | DPR |  |  |  | 65 | [12 empty] | 0 | [19 empty] | 0
| Design, Installation, testing and commissioning of conveyor system from crusher house to TP-108 of CHP-D, CSTPS, Chandrapur. | Scheme |  |  |  | 50 | [7 empty] | will improve performance of system ,unloading reduces R.D.T and generation loss. |  |  |  |  | 0 |  |  |  |  | 50 | [14 empty] | 0 |  |  |  |  | 50 | [5 empty] | Plant & Machinery
| Supply, Engineering, erection and commissioning of one 1500TPH crusher, short conveyors from TP 106 and open space of near Stack yard A pile to Crusher inlet and a telescopic conveyor at the output of crusher to Stack Yard B pile of CHPD Unit 8&9, CSTPS. | Scheme |  |  |  | 15 | [7 empty] | Reduction in R.D.T. |  |  |  |  | 0 |  |  |  |  | 15 | [14 empty] | 0 |  |  |  |  | 15 | [5 empty] | Plant & Machinery
5 | Design, Installation and commissioning of conveyor system from rope way of CHP-A to crusher house of CHP-D, CSTPS, Chandrapur. | DPR |  |  |  | 50 | [12 empty] | 0 | [19 empty] | 0
| Design, Installation and commissioning of conveyor system from rope way of CHP-A to crusher house of CHP-D, CSTPS, Chandrapur. | Scheme |  |  |  | 50 | [7 empty] | Improvement in performance of system, reduction in R.D.T ,demurrages and genertaion loss. |  |  |  |  | 0 | [5 empty] | 50 | [13 empty] | 0 | [5 empty] | 50 |  |  |  |  | Plant & Machinery
6 | Infrastructure Development Schemes at CHP-D CSTPS | DPR |  |  |  | 133 | [12 empty] | 0 | [19 empty] | 0
| Design, Supply,Installation and Commissioning of EOT Cranes at Wagon Tippler area of CHP-D CSTPS. | Scheme |  |  |  | 22 | [7 empty] | Reduction in maintenance downtime. |  |  |  |  | 0 | [5 empty] | 15 | 7 | [12 empty] | 0 | [5 empty] | 15 | 7 |  |  |  | Plant & Machinery
| Belt Tracking systems for Carrying/Return 1400/1600 mm belt width | Scheme |  |  |  | 2.5 | [7 empty] | improvement in performance of system. |  |  |  |  | 0 |  |  |  |  | 1.25 | 1.25 | [13 empty] | 0 |  |  |  |  | 1.25 | 1.25 |  |  |  |  | Plant & Machinery
| Ceramic Lagging by direct bonding on Conveyor Pulleys without Rubber Pad/Rubber Sheets. | Scheme |  |  |  | 3 | [7 empty] | improvement in performance of system. |  |  |  |  | 0 |  |  |  |  | 1.5 | 1.5 | [13 empty] | 0 |  |  |  |  | 1.5 | 1.5 |  |  |  |  | Plant & Machinery
| Rewamping of crane and hoist of CHP, Unit 8&9, CSTPS, Chandrapur | Scheme |  |  |  | 2.5 | [7 empty] | Reduction in maintenance downtime. |  |  |  |  | 0 |  |  |  | 2.5 | [15 empty] | 0 |  |  |  | 2.5 | [6 empty] | Plant & Machinery
| Material lifting mechanism at Crusher, bunker and Tunnel area of CHP-D CSTPS. | Scheme |  |  |  | 10 | [7 empty] | Reduction in maintenance downtime. |  |  |  |  | 0 |  |  |  | 10 | [15 empty] | 0 |  |  |  | 10 | [6 empty] | Plant & Machinery
| Revamping, modification of TunnelAir ventilation system | Scheme |  |  |  | 20 | [7 empty] | Improvement in working environment ,effficiency of working persons and meet statutory requirement of pollution control board |  |  |  |  | 0 |  |  |  | 20 | [15 empty] | 0 |  |  |  | 20 | [6 empty] | Plant & Machinery
| Revamping, modification of DE and DS system | Scheme |  |  |  | 30 | [7 empty] | Improvement in working environment and meet statutory requirement of pollution control board |  |  |  |  | 0 |  |  |  | 30 | [15 empty] | 0 |  |  |  | 30 | [6 empty] | Plant & Machinery
| Revamping, modification of Dewatering and water recirculation system | Scheme |  |  |  | 30 | [7 empty] | improvement in performance of system,reduction in maintenance down time. |  |  |  |  | 0 |  |  |  | 30 | [15 empty] | 0 |  |  |  | 30 | [6 empty] | Plant & Machinery
| Provision of New Office Building with Infrastructure ,Interior Development at CHP-D CSTPS. | Scheme |  |  |  | 10 | [7 empty] | Improvement in healthy working environment,efficiency of working persons. |  |  |  |  | 0 | [5 empty] | 10 | [13 empty] | 0 | [5 empty] | 10 |  |  |  |  | Plant & Machinery
| Material Storage Shed Fabrication work at CHP-D CSTPS | Scheme |  |  |  | 3 | [7 empty] | improves proper preservation of material , increases life of material further improves performance of auxiliaries. |  |  |  |  | 0 |  |  |  | 3 | [15 empty] | 0 |  |  |  | 3 | [6 empty] | Plant & Machinery
7 | Electrical schemes for improvement in availability & Reliability of CHP-D,CSTPS, Chandrapur | DPR |  |  |  | 127 | [12 empty] | 0 | [19 empty] | 0
| Design supply installation and commisioning of LED based energy efficient system for illumination at CHPD |  |  |  |  | 10 | [12 empty] | 0 |  |  |  |  | 5 | 5 | [13 empty] | 0 |  |  |  |  | 5 | 5 |  |  |  |  | Plant & Machinery
| Supply, Erection, Commissioning and Testing of 7.2KV SF6 HT Contactor for retrofitting of existing BHEL make Vacuum Circuit Breakers of CHP-D, CSTPS | Scheme |  |  |  | 4 | [12 empty] | 0 |  |  |  | 4 | [15 empty] | 0 |  |  |  | 4 | [6 empty] | Plant & Machinery
| Upgradation of GE make 90-30 series PLC system installed at stacker rclaimer and wagon tippler at CHP-D, CSTPS | Scheme |  |  |  | 10 | [12 empty] | 0 |  |  |  | 10 | [15 empty] | 0 |  |  |  | 10 | [6 empty] | Plant & Machinery
| Installation of energy efficient air temperature controlling system at various MCC rooms of CHPD, CSTPS | Scheme |  |  |  | 5 | [12 empty] | 0 |  |  |  |  | 5 | [14 empty] | 0 |  |  |  |  | 5 | [5 empty] | Plant & Machinery
| Alterration, upgradation of tunnel ventilation system of CHPD, CSTPS | Scheme |  |  |  | 10 | [12 empty] | 0 | [7 empty] | 10 | [11 empty] | 0 | [7 empty] | 10 |  |  | Plant & Machinery
| Design, Fabrication, Erection & commissioning of cable support structure along with re-routing & trial of auxiliaries at Crusher PMCC, compressor house & short conveyor area at CHP-D, CSTPS | Scheme |  |  |  | 5 | [12 empty] | 0 |  |  |  |  | 5 | [14 empty] | 0 |  |  |  |  | 5 | [5 empty] | Plant & Machinery
| Supply and installation of LT air circuit breakes at CHP-D, CSTPS | Scheme |  |  |  | 2 | [12 empty] | 0 | [5 empty] | 2 | [13 empty] | 0 | [5 empty] | 2 |  |  |  |  | Plant & Machinery
| Design, supply, installation & commissioning of solar based energy efficient illumination system at CHP-D, CSTPS | Scheme |  |  |  | 10 | [12 empty] | 0 |  |  |  |  | 10 | [14 empty] | 0 |  |  |  |  | 10 | [5 empty] | Plant & Machinery
| Procurement of HT motors for various auxiliaries at CHP-D, CSTPS. | Scheme |  |  |  | 5 | [12 empty] | 0 | [5 empty] | 5 | [13 empty] | 0 | [5 empty] | 5 |  |  |  |  | Plant & Machinery
| Supply & installation of high capacity submersible slurry pump at CHP-D, CSTPS | Scheme |  |  |  | 7 | [12 empty] | 0 | [6 empty] | 7 | [12 empty] | 0 | [6 empty] | 7 |  |  |  | Plant & Machinery
| Reconditioning of MCC Board feeder panels at CHP-D,U #8&9.CSTPS,Chandrapur. | Scheme |  |  |  | 10 | [12 empty] | 0 | [6 empty] | 10 | [12 empty] | 0 | [6 empty] | 10 |  |  |  | Plant & Machinery
| Supply & installation of anoodized winding magnets along with control panels for installation at various conveyor belts of CHP-D, CSTPS | Scheme |  |  |  | 4 | [12 empty] | 0 | [6 empty] | 4 | [12 empty] | 0 | [6 empty] | 4 |  |  |  | Plant & Machinery
| Supply of 69 AH HBL make battery set of CHP-D (U8&9), CSTPS, Chandrapur. | Scheme |  |  |  | 5 | [12 empty] | 0 | [6 empty] | 5 | [12 empty] | 0 | [6 empty] | 5 |  |  |  | Plant & Machinery
| Supply of 100 AH Exide make battery banks (2 Set/ 110 Nos battery cells) & battery charge at CHP-D (U8&9), CSTPS, Chandrapur. | Scheme |  |  |  | 10 | [12 empty] | 0 | [6 empty] | 10 | [12 empty] | 0 | [6 empty] | 10 |  |  |  | Plant & Machinery
| Alterration, upgradation of tunnel ventilation system of CHPD, CSTPS | Scheme |  |  |  | 10 | [12 empty] | 0 | [7 empty] | 10 | [11 empty] | 0 | [7 empty] | 10 |  |  | Plant & Machinery
| Supply of HT/LT Xmers assy of CHP-D (U8&9), CSTPS, Chandrapur. | Scheme |  |  |  | 10 | [12 empty] | 0 | [7 empty] | 10 | [11 empty] | 0 | [7 empty] | 10 |  |  | Plant & Machinery
| Supply of HT/LT Xmers assy of CHP-D (U8&9), CSTPS, Chandrapur. | Scheme |  |  |  | 10 | [12 empty] | 0 | [7 empty] | 10 | [11 empty] | 0 | [7 empty] | 10 |  |  | Plant & Machinery
| WTP-III | [17 empty] | 0 | [19 empty] | 0
1 | Engineering, installation and commissioning of DM stream capacity of 4800M3/Day for U # 8 & 9 in addition to existing DM stream at WTP, CSTPS, Chandrapur | DPR |  |  |  | 46.4 | [12 empty] | 0 | [19 empty] | 0
| Engineering, installation and commissioning of DM stream capacity of 4800M3/Day for U # 8 & 9 in addition to existing DM stream at WTP, CSTPS, Chandrapur | Scheme |  |  |  | 46.4 | [12 empty] | 0 |  |  |  |  | 46.4 | [14 empty] | 0 |  |  |  |  | 46.4 | [5 empty] | Plant & Machinery
| Civil - 8&9 | [17 empty] | 0 | [19 empty] | 0
1 | Work of diversion of peripheral nallah towards ash water recovery pump house alogwith construction of waste wear at ash bund area CSTPS, Chandrapur. | DPR |  |  |  | 35.4 | [12 empty] | 0 | [19 empty] | 0
| Work of diversion of peripheral nallah towards ash water recovery pump house alogwith construction of waste wear at ash bund area CSTPS, Chandrapur. | Scheme |  |  |  | 35.4 | [12 empty] | 0 |  |  |  | 10 | 25.4 | [14 empty] | 0 |  |  |  | 10 | 25.4 | [5 empty] | Other & Civil work
2 | Infrastructure development of CHP-D area at U-8, 9, CSTPS | DPR |  |  |  | 41 | [12 empty] | 0 | [19 empty] | 0
| Provision of platform for unloading of coal near TP-106 upto stack pile A of CHP-D | Scheme |  |  |  | 2.5 | [12 empty] | 0 | [5 empty] | 2.5 | [13 empty] | 0 | [5 empty] | 2.5 |  |  |  |  | Other & Civil work
| Provision of WBM Road for fire fighting arrangement at CHP-D U-8,9 | Scheme |  |  |  | 2.5 | [12 empty] | 0 | [5 empty] | 2.5 | [13 empty] | 0 | [5 empty] | 2.5 |  |  |  |  | Other & Civil work
| Construction & Pushing RCC box of size 2mx2m under railway track to drain out the surface water near Rly - A cabin Unit-8,9 | Scheme |  |  |  | 6 | [12 empty] | 0 | [5 empty] | 6 | [13 empty] | 0 | [5 empty] | 6 |  |  |  |  | Other & Civil work
| Construction of concrete pavement road connecting to reject gate & vinchoda chowk , Y point to ash recovery pump house | Scheme |  |  |  | 30 | [12 empty] | 0 | [5 empty] | 30 | [13 empty] | 0 | [5 empty] | 30 |  |  |  |  | Other & Civil work
HO1 | CHP Improvement Schemes | DPR |  |  |  | 100 | [12 empty] | 0 | [19 empty] | 0
| CHP Improvement Schemes at CHP-D | Scheme |  |  |  | 100 | [12 empty] | 0 |  |  |  |  | 100 | [14 empty] | 0 |  |  |  |  | 100 | [5 empty] | Plant & Machinery
HO2 | Developlment & Upgradation of DSM software system for MSPGCL | DPR |  |  |  | 55 | [12 empty] | 0 | [19 empty] | 0
| Developlment & Upgradation of DSM software system for MSPGCL | Scheme |  |  |  | 55 | [12 empty] | 0 |  |  |  | 55 | [15 empty] | 0 |  |  |  | 55 | [6 empty] | Software
1 | Implementation of Flexible Operation Solutions | DPR |  |  |  | 34 | [12 empty] | 0 | [19 empty] | 0
| Implementation of Flexible Operation Solutions | Scheme |  |  |  | 34 | [12 empty] | 0 |  |  |  | 34 | [15 empty] | 0 |  |  |  | 34 | [6 empty] | Plant & Machinery
[19 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
| B) Non-DPR Schemes | [8 empty] | - | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | 0 | FALSE
1 | General asset | [8 empty] | - | [8 empty] | 0 | 1.87 | 0.83962 | 0.5 | [16 empty] | 0 | 1.87 | 0.83962 | 0.5
2 | Supply, Operation & Maintenance of Mobile Coal Sampling Equipment (MCSE) for coal sampling at loading ends of WCL for Mahagenco | [8 empty] | - | [8 empty] | 0 |  | 3.1648 | [17 empty] | 0 |  | 3.1648
3 | ABC Powder Type and Foam Type Composite Fire Extinguisher |  |  |  |  | 1.53 |  |  |  | - | [8 empty] | 0 |  | 1.528 | [17 empty] | 0 |  | 1.528
4 | NON-Detailed Project Report for the Work of Upgradation/Renovation of Crusher House of CHPB of Unit-5, 6&7 at CSTPS Chandrapur (benefit U-8,9 by short conveyor coal stacking in catering emergency) |  |  |  |  | 4.7 |  |  |  | - | [8 empty] | 0 | 1.4404 | 1.4404 | [17 empty] | 0 |  | 2.8807
5 | Extention of stacker reclaimer area for improvement in coal stack management at CHP-D CSTPS Chandrapur U-8,9 | [8 empty] | - | [8 empty] | 0 | 3.9102 | 4.1828 | 0.36697 | [16 empty] | 0 |  |  | 8.46
6 | Retrofitting of BHEL make HT Circuit Breaker with SF6 Contactor at CHP-D, Unit-8&9 | [17 empty] | 0 |  |  | 4.25 | [16 empty] | 0 |  |  | 4.25
| Total | [13 empty] | 127.2662 | 32.2457 | 101.6697 | 60.8297 | 322.0114 | 83.5669 | 74.7693 | 207.236 | 965.855 | 1002.8795 | 360.555 | 107 | 212.5 | 0 | 0 | 0 | -0.099378 | 0 | 0 | 0 | 53.3343 | 12.6151 | 76.1945 | 215.0092 | 357.1531 | 81.5397 | 85.3855 | 215.4756 | 965.855 | 1002.8795 | 360.555 | 107 | 212.5
[40 empty] | 1.87 | 8.4131 | 13.21
Formulas:
Date of Submission = [Date of Submission, row above]
MERC Approval Date = [MERC Approval Date, row above]
Note on M4: SSP-RCD As per the implementation plan submitted in the DPR/ Approved by MERC

## F4.3
MSPGCL-Chandrapur U# 8-9
MTR Petition Formats - Generation
| Project Details | Form 4.3: Capital Work-in-progress - Project-wise details | [9 empty] | (Rs. Crore)
Sr. No. | Project Code | MERC Approval No. | MERC Approval Date | Approved Project Cost | Cumulative Expenditure Incurred till beginning of the Year | Capital Expenditure Capitalised | Opening CWIP | Investment during the year | Capitalization |  |  |  | Closing CWIP
[9 empty] | Works Capitalised | Interest Capitalised | Expenses Capitalised | Total Capitalisation |  | Allowable Capitalisation | Probable Disallowance
FY 2022-23
A) Approved Add Cap (Case No. 296 of 2019)
1 | Initial Spares | Approved Add Cap (Case No. 296 of 2019)
| Boiler & Auxiliaries |  | - | 10.36 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Bevel Helical Gear box KMP-350 for XRP 1043 coal mills at unit-8&9,CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Hydraulic Adjustment (Actuating) Device for PA fan model PAF 19/10.6-2 and FD fan FAF 23/12.5-1 at Unit 8&9, CSTPS, Chandrapur. |  | - | 0 | 1.3971 | 1.3971 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Yokogawa make Zirconia Oxygen Analyser spares for C&I-III, Unit-8&9, CSTPS, Chandrapur |  | - | 0 | 0.51933 | 0.51933 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of High pressure valves installed at unit-8&9 ( 2x500 MW),CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Turbine & Aux |  | - | 1.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of IMI Norgren Herion make Trip solenoid valves for Main Turbine, MD-BFP & TD-BFP of Unit 8 & 9, CSTPS, Chandrapur |  | - | 0 | 0.37354 | 0.37354 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Speed Sensors for 500 MW KWU Turbine for C&I-III, Unit 8 & 9, CSTPS, Chandrapur |  | - | 0 | 0.038232 | 0.038232 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Position Feedback Transmitters for Starting Device and Speeder Gear of Main Turbine for C&I-III, Unit 8 & 9, CSTPS, Chandrapur |  | - | 0 | 0.11225 | 0.11225 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for LP bypass system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur on OEM Basis. |  | - | 0 | 0.43645 | 0.43645 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of TSE (Turbine Stress Evaluator) temperature elements for C&I-III, Unit 8 & 9, CSTPS, Chandrapur |  | - | 0 | 0.061505 | 0.061505 | 0 | 0.14579 | 0.12252 |  |  | 0.12252 | 0.023271
| Generator and Auxiliries |  | - | 0.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of complete set of water cooled bushing for 500MW Generator installed at Unit-8 & 9, CSTPS Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Tushaco make complete AC Jacking Oil Pump for Unit-8 & 9, CSTPS, Chandrapur |  | - | 0 | 0.19949 | 0.19949 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of oil filled Neutral Grounding Transformer for AHP Unit-8&9 CSTPS , Chandrapur. |  | - | 0 | 0.34775 | 0.34775 | 0 | 0 | 0 |  |  | 0 | 0
| Electrical and Instrumentation |  | - | 29.23 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| ‘Procurement of various spares of BHEL make Vacuum Circuit Breakers’ , for Unit-8 & 9, CSTPS, Chandrapur. |  | - | 0 | 0.49498 | 0.49498 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, erection and commissioning of floor mounted 500KW Resistor Load Bank for D.G. sets installed at Unit-8 & 9, CSTPS, Chandrapur. |  | - | 0 | 0.27536 | 0.27536 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Turbosupervisory system spares of main turbine for C&I-III, Unit 8 & 9, CSTPS, Chandrapur |  | - | 0 | 1.0366 | 1.0366 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Level transmitters for C&I-III, Unit 8 & 9, CSTPS, Chandrapur |  | - | 0 | 0.15999 | 0.15999 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Level transmitters for C&I-III, Unit 8 & 9, CSTPS, Chandrapur |  | - | 0 | 0 | 0 | 0 | 0.018125 | 0.018125 |  |  | 0.018125 | 0
| Procurement of Level transmitters for C&I-III, Unit 8 & 9, CSTPS, Chandrapur |  | - | 0 | 0.046973 | 0.046973 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of GE PLC spares for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. |  | - | 0 | 0.57304 | 0.57304 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for GEHO pumps PLC control panels for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. |  | - | 0 | 0.084378 | 0.084378 | 2.6e-08 | 0 | 0 |  |  | 0 | 2.6e-08
| Procurement of master calibration lab Instruments for C&I-III, Unit 8 & 9,CSTPS,Chandrapur |  | - | 0 | 0.30131 | 0.30131 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Coal Feeder panel spares for C&I-III, Unit 8 & 9,CSTPS, Chandrapur |  | - | 0 | 0.58701 | 0.58701 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Opacity Monitor (Stack Particulate matter-SPM) spares for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. |  | - | 0 | 0.14051 | 0.14051 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Forbes Marshall Supervisory system spares For Turbine driven boiler feed pumps (TDBFP) of Unit 8 & 9, CSTPS, Chandrapur |  | - | 0 | 0.22449 | 0.22449 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for hydraulic panel of CW pumps for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. |  | - | 0 | 0.12949 | 0.12949 | 0 | 0.0091301 | 0.0091129 |  |  | 0.0091129 | 1.7196e-05
| Procurement of H2 Dew point analyzer spares for Unit 8 & 9, CSTPS, Chandrapur |  | - | 0 | 0.049938 | 0.049938 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for HP bypass system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur |  | - | 0 | 0.33965 | 0.33965 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Position feedback transmitter for HP bypass system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur |  | - | 0 | 0.0354 | 0.0354 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Atlas Copco make Instrument, Service and Conveying air Compressors for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. |  | - | 0 | 0.2265 | 0.2265 | 0 | -0.001407 | -0.001407 |  |  | -0.001407 | 1.7347e-18
| Procurement of spares for HEA Ignitors and Flame Scanners for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. |  | - | 0 | 0.037701 | 0.037701 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for GEHO pumps of Ash Handling System at C&I-III, Unit 8 & 9, CSTPS, Chandrapur |  | - | 0 | 0.28861 | 0.28861 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Turbine side control valve spares for C&I-III, Unit 8 & 9, CSTPS, Chandrapur |  | - | 0 | 0.17974 | 0.17974 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various numerical protection relays for Unit-8 & 9, CSTPS, Chandrapur. |  | - | 0 | 0.12307 | 0.12307 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various numerical protection relays for Unit-8 & 9, CSTPS, Chandrapur. |  | - | 0 | 0.14207 | 0.14207 | 0 | -0.010231 | -0.010231 |  |  | -0.010231 | 0
| Procurement of various numerical protection relays for Unit-8 & 9, CSTPS, Chandrapur. |  | - | 0 | 0.13863 | 0.13863 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for DB POWER make UPS system installed at HCSD Pump House, Unit-8 & 9, CSTPS, Chandrapur. |  | - | 0 | 0.064757 | 0.064757 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Fully Automatic Capacitance & Dissipation Factor (Tan- Delta) measuring kit for Unit-8 &9, CSTPS, Chandrapur. |  | - | 0 | 0.48288 | 0.48288 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of various VFD spares for ID fans of Unit-8 & 9, CSTPS, Chandrapur. |  | - | 0 | 0.22227 | 0.22227 | 0 | 0.23399 | 0.23399 |  |  | 0.23399 | 0
| Procurement of DAVR spares installed at Unit -8&9 CSTPS, Chandrapur. |  | - | 0 | 0.56174 | 0.56174 | 0 | 0.01005 | 0.01005 |  |  | 0.01005 | -1.5613e-17
| Procurement of 3 phase relay test kit for Unit-8 &9, CSTPS, Chandrapur. |  | - | 0 | 0.35388 | 0.35388 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Fast Bus Transfer System (FBTS) installed at Unit-8 & 9, CSTPS, Chandrapur. |  | - | 0 | 0.37288 | 0.37288 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various spares for battery chargers installed at Unit-8&9, CSTPS, Chandrapur. |  | - | 0 | 0.40022 | 0.40022 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Auto synchronizing Relay (ASR) & Load Shedding Relay (LSR) installed at Unit-8 &9, CSTPS, Chandrapur. |  | - | 0 | 0.34973 | 0.34973 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ESP spares i.e. Field Controller, Thyristor and Trigger card for ESP of Unit-8 & 9, CSTPS Chandrapur. |  | - | 0 | 0.26745 | 0.26745 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various VFD spares for GEHO pump of Unit-8 & 9, CSTPS, Chandrapur. |  | - | 0 | 0.54416 | 0.54416 | 0 | 0 | 0 |  |  | 0 | 0
| Design, Supply, Erection & Commissioning of On-Line Dissolved Gas Analyzers for various Transformers installed at Unit-8 & 9, CSTPS, Chandrapur. |  | - | 0 | 3.1775 | 3.1775 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, Erection & Commissioning of On-Line Dissolved Gas Analyzers for Station Transformers -8B, Unit-8 & 9, CSTPS, Chandrapur |  | - | 0 | 0.30519 | 0.30519 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘TOROSHIMA’ make 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motor (without pump casing) for Unit-8&9, CSTPS Chandrapur. |  | - | 0 | 4.2037 | 4.2037 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 90kVA ESP Rectiformer for Unit-8 & 9, CSTPS, Chandrapur. |  | - | 0 | 0.29878 | 0.29878 | 0 | 0 | 0 |  |  | 0 | 0
| Supply erection & commissioning of Aviation Lighting for NDCT of Unit-8&9, CSTPS Chandrapur |  | - | 0 | 0.57261 | 0.57261 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Transformer oil storage tanks of different capacity for Unit-8&9 CSTPS Chandrapur. |  | - | 0 | 0.57024 | 0.57024 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 2000kW & 315kW, 6.6 kV HT motors for CW & ACW Pump installed at Unit-8&9, CSTPS, Chandrapur. |  | - | 0 | 1.4505 | 1.4505 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 3.25MVA, 6.6/2.3kV VFD Transformers of vector group DY11 for Unit-8 & 9, CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 3.25MVA, 6.6/2.3kV VFD Transformer of vector group ‘Dd0’ for Unit-8 & 9, CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘MARATHON’ makes HT/LT Induction motors for various Critical auxiliaries installed at Unit-8 &9, CSTPS Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of 1.2V, Ni-Cd battery cells for Unit-8&9, CSTPS Chandrapur. |  | - | 0 | 0.12496 | 0.12496 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of 1.2V, Ni-Cd battery cells for Unit-8&9, CSTPS Chandrapur. |  | - | 0 | 0.18931 | 0.18931 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘Air Core DC Reactor’ for VFD and ‘NGR’ for UAT/ Station Transformers installed at Unit-8 & 9, CSTPS, Chandrapur. |  | - | 0 | 0.44368 | 0.44368 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘Air Core DC Reactor’ for VFD and ‘NGR’ for UAT/ Station Transformers installed at Unit-8 & 9, CSTPS, Chandrapur. |  | - | 0 | 0.12551 | 0.12551 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘BHEL’ make 680 KW, 6.6KV, Coal Mill Motor for Unit-8&9, CSTPS Chandrapur. |  | - | 0 | 0.37913 | 0.37913 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 400kV OIP Condenser Bushing for Generator Transformer & Station Transformer of Unit-8&9, CSTPS, Chandrapur. |  | - | 0 | 0.49064 | 0.49064 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘11kW DC motor with Control Cabinet’ for Unit-8 & 9, CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 37kW, 415V motors for Primary Water Pump installed at Unit-8 &9, CSTPS Chandrapur. |  | - | 0 | 0.0096851 | 0.0096851 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 15 KW, 415V LT Motor for Service Building & TG Building Lift installed at Unit-8&9, CSTPS Chandrapur. |  | - | 0 | 0.095155 | 0.095155 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 16KW, 415V LT Motor for Boiler Lift installed at Unit-8&9, CSTPS Chandrapur. |  | - | 0 | 0.044179 | 0.044179 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, Erection, Testing and Commissioning of Hydrastep-Electronic Drum Level Indicator and its associated accessories for Unit-9, CSTPS, Chandrapur |  | - | 0 | 0.27376 | 0.27376 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for BHEL make Hydrastep (Electronic Water Level Indicator -BHELVISION 20M) for Unit 8 & 9, CSTPS, Chandrapur on OEM basis. |  | - | 0 | 0.084172 | 0.084172 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Electrodes for Hydrastep (Electronic Water Level Indicator -BHELVISION 20M) for Unit 8 & 9, CSTPS, Chandrapur. |  | - | 0 | 0.10384 | 0.10384 | 0 | 0 | 0 |  |  | 0 | 0
| Engineering & Retrofitting of 196 NT Controller to DT 9 Controller for Unit-8 & 9 Coal Feeder System. |  | - | 0 | 0.38076 | 0.38076 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for BHEL make Acoustic steam leak detection system (BHELSONIC) (BS10) for Unit 8 & 9, CSTPS, Chandrapur |  | - | 0 | 0.038929 | 0.038929 | -3.5e-08 | 0.038878 | 0.038878 |  |  | 0.038878 | 0
| Procurement of LT Circuit Breaker assemblies for ESP LT Panels (LTMSB & ACP) of Unit-8&9, CSTPS, Chandrapur. |  | - | 0 | 0.25429 | 0.25429 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for BHEL make maxDNA Distributed control system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur |  | - | 0 | 0.99745 | 0.99792 | -0.00046842 | 0.06777 | 0.067302 |  |  | 0.067302 | 0
| Supply of Transformer oil BDV test kit DTA 100C and Oil Tan Delta & Resistivity Tester DTL C at Unit-8&9, CSTPS, Chandrapur. |  | - | 0 | 0.47598 | 0.47598 | 0 | 0 | 0 |  |  | 0 | 0
| Outdoor Plant ( CHP/AHP/WTP) |  | - | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Elecon make KCN-560 type Gearbox for Apron Feeder installed at CHPD, CSTPS. |  | - | 0 | 1.6717 | 1.6717 | -6e-08 | 0 | 0 |  |  | 0 | -6e-08
| Procurement of spares of CKB-280,225,200,8180 typ gearbox installed at CHP-D |  | - | 0 | 1.0015 | 1.0015 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Gear Box (MAKE: NEW ALLENBERRY) Spares at CHP-D; CSTPS, Chandrapur. |  | - | 0 | 0.5177 | 0.5177 | 1.8e-08 | 0 | 0 |  |  | 0 | 1.8e-08
| Procurement of spares for m/s Elecon make Impact Crusher installed at CHP Unit 8&9 CSTPS, Chandrapur |  | - | 0 | 0.84103 | 0.84103 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of V belt pulley of rotor for Impact crusher installed at CHP-D, CSTPS |  | - | 0 | 0.11864 | 0.11864 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Spares for hydraulic systems installed at CHPD, CSTPS. |  | - | 0 | 0.47537 | 0.47537 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Spares for hydraulic systems installed at CHPD, CSTPS. |  | - | 0 | 0.028604 | 0.028604 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of drive & non drive pulley for various conveyors installed at CHP D, CSTPS, Chandrapur. |  | - | 0 | 0.25792 | 0.25792 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of drive & non drive pulley for various conveyors installed at CHP D, CSTPS, Chandrapur. |  | - | 0 | 0.0914 | 0.0914 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Chain links for apron feeder installed at CHP D, CSTPS, Chandrapur. |  | - | 0 | 0.40289 | 0.40289 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of internal spares for Elecon make PWD-18, PLB-25 & SCN-180 type Gearbox for Stacker Reclaimer & wobbler feeder installed at CHP D, CSTPS. |  | - | 0 | 0.52774 | 0.52774 | 3.1e-08 | 0 | 0 |  |  | 0 | 3.1e-08
| Supply of GE Make Switchgear Spares for GE Make LT Feeders |  | - | 0 | 0.10198 | 0.089824 | 0.012154 | 0.022868 | 0.035022 |  |  | 0.035022 | 0
| Procurement of spares for Fluidomat make scoop coupling installed at CHP–D, CSTPS, Chandrapur |  | - | 0 | 0.48355 | 0.48355 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Oil Filtering machine for hydraulic power packs installed at CHPD, CSTPS |  | - | 0 | 0.10592 | 0.10592 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of LT Motors at CHP-D (U#8&9), CSTPS, Chandrapur. |  | - | 0 | 0.11302 | 0.11302 | 0 | 0 | 0 |  |  | 0 | 0
| Supply and Installation of Oil Cooled Suspended Anodized Winding Magnet & Control Panel at CHP, Unit 8&9, CSTPS, Chandrapur. |  | - | 0 | 2.2967 | 2.2967 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of LT power and control cable for CHP-D |  | - | 0 | 0.26256 | 0.26256 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of LT power and control cable for CHP-D |  | - | 0 | 0.022125 | 0.022125 | 0 | 0 | 0 |  |  | 0 | 0
2 | Capital Spare |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| HPT MODULE |  | - | 45.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of HP turbine Module along with breach nuts and pipe spool pieces (Type: H30-100-2) for Unit-8 & 9, CSTPS, Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| LPT ROTOR |  | - | 40.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Fully Bladed & Dynamically Balanced LP Rotor (N30-2X10-2) for Unit-8 & 9, CSTPS, Chandrapur |  | - | 0 | 0 | 0 | 0 | 29.03 | 29.03 |  |  | 29.03 | 0
| Procurement of set of Free Standing Moving Blades for LP Rotor (N30-2X10-2) for Unit-8 & 9, CSTPS, Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| BFP CARTRIDGE ( 2NOS ) |  | - | 4.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of cartridge assembly for Boiler Feed Pump model FK-4E-36 (with Four S/H & 2 R/H spray branches) installed at 2X 500MW, CSTPS, Chandrapur. |  | - | 0 | 1.2575 | 1.2575 | 0 | 1.2575 | 1.2574 |  |  | 1.2574 | 6e-05
| BCW PUMP |  | - | 3.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for ‘TOROSHIMA’ make 350KW BCW Pump-Motor installed at Unit-8 &9, CSTPS Chandrapur. |  | - | 0 | 1.3283 | 1.3283 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various spares for ‘TOROSHIMA’ make Boiler Circulating Water (BCW) pump-motor installed at Unit-8&9, CSTPS Chandrapur. |  | - | 0 | 0 | 0 | 0 | 2.2326 | 2.2326 |  |  | 2.2326 | 0
| 15 MVA DRY TYPE TRANSFORMER |  | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spare ‘Cast Resin Dry Type Transformers (CRTs)’ of different ratings for Unit-8&9, CSTPS Chandrapur. |  | - | 0 | 1.5275 | 1.5275 | 0 | 4.4938 | 4.4938 |  |  | 4.4938 | 0
| Procurement of phase coil limb and spares of Cast Resin Dry Type Transformers of different ratings for Unit-8&9, CSTPS Chandrapur. |  | - | 0 | 0 | 0 | 0 | 7.9255 | 7.9255 |  |  | 7.9255 | 0
| BTG+BOP& Other Works |  | - | 20.48 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Design, Supply & Installation, Testing & Commissioning of Public Addressing System for tunnels of CHP-D, CSTPS, Chandrapur. |  | - | 0 | 1.1544 | 1.1544 | 0 | 0 | 0 |  |  | 0 | 0
| Work of upgradation, installation and extension of 220VDC control supply to various PMCC of CHPD, CSTPS, Chandrapur. |  | - | 0 | 0.68441 | 0.68441 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Apron Feeder in CHP Unit 8&9 (2x500) MW at CHP-D, CSTPS. |  | - | 0 | 2.3388 | 2.3388 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of spares for up gradation of rotary parts of travelling conveyor system installed at CHPD, CSTPS, Chandrapur. |  | - | 0 | 0.58939 | 0.58939 | 0 | 0 | 0 |  |  | 0 | 0
| The Work of Design, Engineering, Manufacturing, Supply, Erection & Commissioning of Short Conveyor belt from stack yard of CHP of Unit 5,6&7 to Belt Conveyor 104 A/B at CHP of Unit 8&9, CSTPS, Chandrapur |  | - | 0 | 0 | 0 | 0 | 2.9173 | 0 |  |  | 0 | 2.9173
| Work of design, supply, erection, commissioning of overhead cable tray along with removal & re-routing of power and control cables at CHP-D, CSTPS, Chandrapur. |  | - | 0 | 0.51324 | 0.51324 | 0 | 0 | 0 |  |  | 0 | 0
| Work of provision, modification, retrofitting and revamping of lighting system of transfers points, crusher house and bunker area of CHP-D, CSTPS, Chandrapur. |  | - | 0 | 1.0105 | 1.0105 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for M/s. Weir Minerals make (GEHO pump Model TZPM-1200) for Ash Handling Plant Unit# 8 &9 CSTPS Chandrapur. AHP-III |  | - | 0 | 0.30372 | 0.30372 | 0 | 1.8023 | 1.8023 |  |  | 1.8023 | 0
| Procurement of Gear Box set of internal (MAKE: NEW ALLENBERRY) Spares at CHP-D; CSTPS, Chandrapur. |  | - | 0 | 0.2315 | 0.2315 | 3.8e-08 | 1.4589 | 1.4589 |  |  | 1.4589 | 0
| Supply and Installation of Oil Cooled Suspended Anodized Winding Magnet & Control Panel at CHP, Unit 8&9, CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 196 NT Controller by DT 9 Controller alongwith HMI units for Unit- 8&9 coal feeder system |  | - | 0 | 2.0774 | 2.0774 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of set of CW Impeller duly fitted with wear rings & ACW Impeller duly fitted with wear rings of Mather & Platt make Pumps installed at Unit-8 & 9,CSTPS,Chandrapur |  | - | 0 | 0 | 0 | 0 | 0.70379 | 0.70379 |  |  | 0.70379 | 0
| CHP System U#8 |  | - | 0 | 0.05 | 0.05 | 0 | 0 | 0 |  |  | 0 | 0
| ISOLATED PHASE BUS DUCT |  | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| SEGREGATED PHASE BUS DUCT U#8 |  | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| SEGREGATED PHASE BUS DUCT U#9 |  | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| ISOLATED PHASE BUS DUCT U#9 |  | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| DTT & UAT U#8 |  | - | 0 | 0.03 | 0.03 | 0 | 0 | 0 |  |  | 0 | 0
| DTT & UAT U#9 |  | - | 0 | 0.03 | 0.03 | 0 | 0 | 0 |  |  | 0 | 0
| Cranes and hoists U#8 |  | - | 0 | 0.03 | 0.03 | 0 | 0 | 0 |  |  | 0 | 0
| RCC Chimney U#8 |  | - | 0 | 9.29 | 9.29 | 0 | 0 | 0 |  |  | 0 | 0
| Coal Handling Plant |  | - | 0 | 41.79 | 41.79 | 0 | 0 | 0 |  |  | 0 | 0
| Bunker foundation & civil works (Unit 8) U#8 |  | - | 0 | 18.58 | 18.58 | 0 | 0 | 0 |  |  | 0 | 0
| Boiler & Auxiliaries U#9 |  | - | 0 | 9.28 | 9.28 | 0 | 0.008909 | 0.0071752 |  |  | 0.0071752 | 0.0017338
| ESP U#9 |  | - | 0 | 2.15 | 2.15 | 0 | 0.008909 | 0.008909 |  |  | 0.008909 | 0
| ID fan foundations (Unit 9) U#9 |  | - | 0 | 1.74 | 1.74 | 0 | 0.008909 | 0.008909 |  |  | 0.008909 | 0
| DRY ASH SILO-12M DIA U#8 |  | - | 0 | 1.22 | 1.22 | 0 | 0 | 0 |  |  | 0 | 0
| FD fan foundations (Unit 9) U#9 |  | - | 0 | 0.62 | 0.62 | 0 | 0.008909 | 0.008909 |  |  | 0.008909 | 0
| PA fan foundations (Unit 9) U#9 |  | - | 0 | 0.54 | 0.54 | 0 | 0.008909 | 0.008909 |  |  | 0.008909 | 0
| Natural Draft cooling tower- Unit 8 U#8 |  | - | 0 | 0.32 | 0.32 | 0 | 0 | 0 |  |  | 0 | 0
| Main power house building-Civil Works-Unit no.-9 U |  | - | 0 | 0.15 | 0.15 | 0 | 0 | 0 |  |  | 0 | 0
| Structural Steel works for main power house buildi |  | - | 0 | 0.15 | 0.15 | 0 | 0 | 0 |  |  | 0 | 0
| Canteen U#8 |  | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Security and time office U#8 |  | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| CARS SCOOTERS AND CYCLE SHED U#8 |  | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Fire Station U#8 |  | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Watch towers U#8 |  | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| First aid station |  | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Tranformer yard U#8 |  | - | 0 | 0.02 | 0.02 | 0 | 0 | 0 |  |  | 0 | 0
| Rain Water Harvesting Scheme U#8&9 |  | - | 0 | -0.01 | -0.01 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Advance Multipurpose Fire Tender |  | - | 0 | 3.45 | 3.45 | 0 | 0 | 0 |  |  | 0 | 0
| DM Stream |  | - | 29.65 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| DM Stream capacity of 100 M3/Hr in addition to existing stream of WTP. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| CIVIL |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Bridge |  | - | 4.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Railway, CHP, AHP etc |  | - | 152.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| B. G. railway siding Pway works |  | - | 0 | 31.0329 | 31.0329 | 0 | 8.544 | 8.544 |  |  | 8.544 | 0
| S & T work for B.G. railway siding |  | - | 0 | 0 | 0 | 0 | 0.023574 | 0.023574 |  |  | 0.023574 | 0
| Consultancy services for B. G. railway siding |  | - | 0 | 0 | 0 | 0 | 0.035636 | 0.035636 |  |  | 0.035636 | 0
| Ash infra in Railway |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Bunker structure (Unit 8) U#8 |  | - | 0 | 18.57 | 18.57 | 0 | 0 | 0 |  |  | 0 | 0
| Coal Mills |  | - | 0 | 1.13 | 1.13 | 0 | 0.008909 | 0.008909 |  |  | 0.008909 | 0
| Bunker foundation & civil works (Unit 9) U#9 |  | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Bunker structure (Unit 9) U#9 |  | - | 0 | 0.11 | 0.11 | 0 | 0 | 0 |  |  | 0 | 0
| HCSS silo-12m dia U#8 |  | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| Ash water PH, HCSD PH, Bottom ash slurry PH U#8 |  | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| Ash compressor house & Control room U#8 |  | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| MILL REJECT SILO U#8 |  | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| Fire protection & Detection system U#8 |  | - | 0 | 0.66 | 0.66 | 0 | 0.054226 | 0.054226 |  |  | 0.054226 | 0
| DM Water Pump room U#8 |  | - | 0 | 4.25 | 0 | 4.25 | 0 | 0 |  |  | 0 | 4.25
| Filter water reservoir & pump house U#8 |  | - | 0 | 4.29 | 0 | 4.29 | 0 | 0 |  |  | 0 | 4.29
| ACW + RW + Filtered water piping U#8 |  | - | 0 | 2.2506 | 0 | 2.2506 | 0 | 0 |  |  | 0 | 2.2506
| Laboratory Building U#8 |  | - | 0 | 0.12 | 0 | 0.12 | 0 | 0 |  |  | 0 | 0.12
3 | Staff quarters |  | - | 15.04 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Work of exterior repair, providing painting to A, D & E type residential buildings and Public Buildings and allied civil works in Urjanagar Colony, CSTPS Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Staff Quarters- Repair and renovation of E type staff quarters to extend the life of buildings at CSTPS Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Staff Quarters - Repair and renovation of 'B' type staff quarters in residential colony at CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair of D type quarters in colony at CSTPS Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair of C type quarters in colony at CSTPS Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Staff Quarters- Repair and renovation of F and NF type staff quarters to extend the life of buildings at CSTPS Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair and replacement of existing drinking water supply pipelines in E & F type area in colony at CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair and replacement of existing sewer lines in E & F type area in colony at CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Work of providing RCC drain along main roads in colony at CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Rerouting and replacement of domestic water supply pipeline from WTP to ESR in colony at CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Additional Contengencies approved vide e BR No. MSPGCL/BM-162/165, Dt.29.10.2016 vide resolution no. 2016/2085 |  | - | 7.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Landscaping and plantation work at various locations inside plant area at CSTPS, chandrapur. |  | - | 0 | 1.81 | 0 | 1.81 | 1.6166 | 3.4266 |  |  | 3.4266 | 0
| Construction of WBM approach road from point- N to Z Area along ash bund periphery at CSTPS Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design, Engineering, Supply and commissioning of ash-bund water recovery system (Phase II) at CSTPS Chandrapur |  | - | 27.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, Engineering, Supply and commissioning of ash-bund water recovery system (Phase II) at CSTPS Chandrapur |  | - | 0 | 13.5434 | 13.5434 | 0 | 4.364 | 0 |  |  | 0 | 4.364
| Providing Consultancy Services for work of Design, Engineering, Supply, Installation & Commissioning of ash bund water recovery system (Phase-II) at CSTPS, Chandrapur (on EPC contract basis). |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Providing laying, jointing and commissioning of 1600 mm dia. M.S. Pipe line from Erai dam to one day reservoir of stage II, III & IV at CTPS |  | - | 73.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Providing laying, jointing and commissioning of 1600 mm dia. M.S. Pipe line from Erai dam to one day reservoir of stage II, III & IV at CTPS |  | - | 0 | 74.4864 | 62.2542 | 12.2322 | -3.9773 | 8.1084 |  |  | 8.1084 | 0.1465
| Work of construction of Control Valve rooms on newly laid 1600 mm M.S. Pipeline no. 6 from Erai dam to One day reservoir at CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Providing OHE facility for BG Rly siding of proposed Expansion Project at Chandrapur, for Supply of Materials. |  | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Providing OHE facility for BG Rly siding of proposed Expansion Project at Chandrapur, for errection of OHE Items. |  | - | 2.5 | 0.7 | 0 | 0.7 | 0 | 0 |  |  | 0 | 0.7
9 | Irrigation scheme for landscaping and Plantation work at Chandrapur expansion project chandrapur. |  | - | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Asphalting of WBM road from Nagpur gate to Awanda gate. |  | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Asphalting of WBM road from Nagpur gate to Awanda gate. |  | - | 0 | 0.65141 | 0 | 0.65141 | 0 | 0 |  |  | 0 | 0.65141
| Asphalting over WBM Road of ADP line Service road from Nagpur gate opening to Awandha junction gate at CSTPS Chandrapur |  | - | 0 | 0 | 0 | 0 | 0.84833 | 0.84833 |  |  | 0.84833 | 0
| Asphalting of WBM road from Nagpur gate to Awandha gate at CSTPS Chandrapur - Asphalting of road from Reject coal gate to Motghat nallah at CSTPS Chandrapur (PHASE - I) |  | - | 0 | 0.47941 | 0 | 0.47941 | 0 | 0.47941 |  |  | 0.47941 | 0
11 | Foot Over Bridge |  | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Work of Providing retaining wall for sand hump at Vivekanand nagar station yard under modification work in wardha end fro 2 x 500 MW Expn. Project at CSTPS, Chandrapur. |  | - | 0.3 | 0.25515 | 0.25515 | 0 | 0 | 0 |  |  | 0 | 0
| Additional Capitalization by O & M |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of GE make 4000Amp LT Air Circuit Breakers for Unit-8 & 9, CSTPS, Chandrapur. |  | - | 0.9 | 1.0308 | 1.0308 | 0 | 0 | 0 |  |  | 0 | 0
2 | Air Compressor System |  | - | 0.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Energy management Sysytem |  | - | 0.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, Installation, Testing & Commissioning of Energy Management System for Unit#8 & 9 for CSTPS, Chandrapur. |  | - | 0 | 0.20054 | 0.20054 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Tri-vector 0.2s class Digital Energy meter for Unit-8&9, CSTPS, Chandrapur. |  | - | 0 | 0.094872 | 0.094872 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, Installation & Commissioning of 3D Level Scanners to 64 nos. of ESP hoppers at Unit-8&9 (2X500MW), CSTPS, Chandrapur. |  | - | 3.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of internal spares for Elecon make PWD-18, PLB-25 ,Pbh-71 type Gearbox for Stacker Reclaimer installed at CHPD, CSTPS. |  | - | 0 | 0 | 0 | 0 | 1.1089 | 1.1089 |  |  | 1.1089 | 0
5 | 4000/2500/1800/800 A GE make LT CKT Brkr |  | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| LT Air Circuit Breakers for Incomer Feeders at CHP-D, CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 1.4207 | 1.4207 |  |  | 1.4207 | 0
| LT Air Circuit Breakers at CHP, Unit 8&9, CSTPS |  | - | 0 | 1.0141 | 1.0141 | 0 | 0 | 0 |  |  | 0 | 0
6 | Replacement of Impact crusher by hammer mill crusher (installed qty.2 No) |  | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Replacement of wobbler feeder 1&2 by grizzly screen at CHP-D |  | - | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Installation of conveyor system from rope way of CHP-A and crusher house of CHP-D |  | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| PLC based control & instrumentation of 6.6 KV HT motors of 1250 KW of Crusher I & II and 200 KW of BC 108A1 & A2 at CHP-D, CSTPS, Chandrapur. |  | - | 0 | 0.93628 | 0.93628 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Design, Supply, Erection & Commissioning of Complete Electrical Automation for Short Conveyor from stack yard of CHP-D to Belt Conveyor 107 A/B of CHP-D, CSTPS, Chandrapur. |  | - | 0 | 0.70095 | 0.70095 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Design, Supply, Erection & Commissioning of Complete Electrical Automation for Short Conveyor from stack yard of CHP-B to Belt Conveyor 104 A/B of CHP-D, CSTPS, Chandrapur. |  | - | 0 | 2.2368 | 2.2368 | 0 | 0 | 0 |  |  | 0 | 0
| WORK OF DESIGN, ENGINEERING, MANUFACTURING, SUPPLY, ERECTION &COMMISSIONING OF SHORT CONVEYOR BELT FROM STACK YARD OF CHP UNIT-8&9 TO CONVEYOR BELT 107A AND B AT CHP UNIT 8&9, CSTPS, CHANDRAPUR. |  | - | 0 | 0.46948 | 0 | 0.46948 | 3.7558 | 0 |  |  | 0 | 4.2253
| Design, Supply, Installation and Commissioning of High Performance Energy Chain System for Side Arm Charger and Stacker Reclaimer of CHP-D, CSTPS, Chandrapur. |  | - | 0 | 3.8916 | 3.8916 | 0 | 0 | 0 |  |  | 0 | 0
9 | RBF 103 &104,105 & 106, 107 & 108, and 109 & 110 in to modular Y chute |  | - | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-103 & RBF-104 with Design, development, Manufacturing, Supply & erection of modular Chute as per site condition in place of RBF using sintered silicon Carbide plate with motorized Flap Gate at CHP-D, CSTPS. |  | - | 0 | 1.1741 | 1.1741 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-105 & RBF-106 with Design, development, Manufacturing, Supply & erection of modular Chute as per site condition in place of RBF using sintered silicon Carbide plate with motorized Flap Gate at CHP-D, CSTPS. |  | - | 0 | 1.3169 | 1.3169 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-107 & RBF-108 with Design, development, Manufacturing, Supply & erection of modular Chute as per site condition in place of RBF using Tungsten Carbide plate with Flap Gate at CHP-D, CSTPS. |  | - | 0 | 1.1529 | 1.1529 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-109 & RBF-110 with design, erection & Installation by trajectory calculation & removal of existing RBF with Y Chute assembly by flow control with Flap Gate arrangement at TP-107 of CHP-D, CSTPS. |  | - | 0 | 1.1506 | 1.1506 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurment , Installation and commissioning of Online Insertable Camera systems for Unit-8, 500MW, CSTPS |  | - | 8.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, Supply, Installation & Commissioning of Energy efficient system for Illumination at Unit 8&9 CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 4.9494 | 4.9494 |  |  | 4.9494 | 0
11 | Construction of Chemical godown shed for unit 8 & 9 at CSTPS,Chandrapur. |  | - | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of Chemical godown shed for unit 8 & 9 at CSTPS,Chandrapur. |  | - | 0 | 0.38706 | 0.40653 | -0.019462 | 0.042392 | 0.02293 |  |  | 0.02293 | 0
| Comprehencive work of installation, erection, testing and commissioning of MVWS spray system/ Fire safety system for new Bulk Chemical storage godown at CSTPS, Unit 8&9 |  | - | 0 | 0 | 0 | 0 | 0.27583 | 0.27583 |  |  | 0.27583 | 0
| Work of electrification of godown for bulk chemical storage near FOPH building at Chandrapur project site. |  | - | 0 | 0.018322 | 0 | 0.018322 | 0 | 0.018322 |  |  | 0.018322 | 0
| Construction of additional Chemical godown shed for storage of Lube oil at CSTPS Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Construction of RCC retaining wall for approach to RCC Bridge across Irai River, ADPL line at CSTPS |  | - | 8.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of RCC retaining wall for approach to RCC Bridge across Irai River, ADPL line at CSTPS |  | - | 0 | 1.8289 | 0 | 1.8289 | 0 | 0 |  |  | 0 | 1.8289
| Asphalting of road from Reject coal gate to Motghat nallah at CSTPS Chandrapur (PHASE - II) |  | - | 0 | 0 | 0 | 0 | 0.87403 | 0.87403 |  |  | 0.87403 | 0
| Providing extension to approaches of RCC bridge across Erai river by constructing WBM road at CSTPS, Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| UDL |  | - | 0 | 4.85 | 4.85 | 0 | 0 | 0 |  |  | 0 | 0
| B) DPR Schemes |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (i) In Principally Approved By MERC |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 1 | HMI (Human Machine Interface) Upgradation of ‘SSPA-T3000’ DCS (Distribution Control System), Rockwell make PLC System installed at 3x660MW Unit No. 8, 9 & 10 at Koradi TPS and HMI (Human Machine Interface) Upgradation of MaxDNA DCS System at Unit 8-9, CSTPS, Chandrapur | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 11.08 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 1.1 | Supply: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 10.52 | 0 | 10.5 | -10.5 | 0 | 0 |  |  | 0 | -10.5
HO DPR 1.2 | Works: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.41 | 0 | 0.4 | -0.4 | 0 | 0 |  |  | 0 | -0.4
| IDC | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
40 | Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M with construction of concrete dam (Waste Weir & Non overflow structure), construction of drain wells, approach to drain wells and raising of ash compartment for ash bund along with renewal of Ash Disposal Pipe Line Service Road with WBM treatment at CSTPS, Chandrapur | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 4.9692 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 34.8665 | 0 | 34.8665 | -34.8665 | 0 | 0 |  |  | 0 | -34.8665
| Construction of New Drain Wells (12 Nos.) along with necessary connection to existing drain wells at CSTPS |  | - | 0.58493 | 0 | 0.58493 | -0.58493 | 0 | 0 |  |  | 0 | -0.58493
| Construction of waste weir for raising of ash bund (Waste Weir & Non overflow structure) |  | - | 1.4621 | 0 | 1.4621 | -1.4621 | 0 | 0 |  |  | 0 | -1.4621
| Raising of Ash Compartment i.e. Lagoon in Ash Bund |  | - | 8.7868 | 0 | 8.7868 | -8.7868 | 0 | 0 |  |  | 0 | -8.7868
| IDC | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 7.634 | 0 | 7.634 | -7.634 | 0 | 0 |  |  | 0 | -7.634
| IDC | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 4.9692 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
39 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 8-9) | MERC/CAPEX/2020-2021/WFH/SBR/21 | 2020-07-24 | 479.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
39.1 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 8-9) | MERC/CAPEX/2020-2021/WFH/SBR/21 | 2020-07-24 | 440.54 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/2020-2021/WFH/SBR/21 | 2020-07-24 | 38.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41 | CHP Performance Improvement Schemes at Unit 8-9 of CSTPS, Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 26.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.1 | Work of Design engineering , supply and installation of modular chutes with sintered silicon carbide for smooth flow &center feeding in CHP 2x500MW CSTPS | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 9.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.2 | Supply erection & commissioning of set of internal of impact crusher spares installed at CHPP-D, CSTPS | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 8.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.3 | Scheme for replacement of Scoop coupling/Fluid coupling of conveyor BC-101A/B/C, BC-102A/B, BC-104A/B, BC-105A/B ,BC-106A/B, BC-111A/B/C/D, BC-110A1/B1, BC-110A/B Installed at CHP-D, CSTPS Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 4.67 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.4 | Supply erection & commissioning of set of internal of spares of stacker reclaimer installed at CHP-D, CSTPS Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 1.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.5 | Supply erection & commissioning of set of internal of spares of Wagon tippler installed at CHP-D, CSTPS Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 2.12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 0.38 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 2 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 2.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
A6 | Supply, Installation & Commissioning of Online Coal Flow Monitoring & Balancing System at Unit-8-9, CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0457 Dt 26.07.2024 | 2024-07-26 | 34.21 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, installation and commissioning of Online Coal flow monitoring and balancing system for U- 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2024-2025/MSPGCL/0457 Dt 26.07.2024 | 2024-07-26 | 34.21 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | MERC/CAPEX/2024-2025/MSPGCL/0457 Dt 26.07.2024 | 2024-07-26 | 0.31 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
A7 | Providing, supplying, laying and commissioning of 1600 mm dia. M.S. Pipe by replacement of existing PSC raw water line from Erai dam to reservoir at CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 40.7945 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Providing, supplying, laying and commissioning of 1600mm dia. M.S. pipe by replacement of existing PSC raw water line from Erai dam to reservoir at CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 40.7945 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 8.83 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
A8 | Adoption of Ozonization technique for disinfection of Cooling Water System at U # 8 & 9 | MERC/CAPEX/MSPGCL/2023-2024/0467 Dt 02.08.2024 | 2024-08-02 | 67 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Adoption of Ozonization technique for disinfection of Unit 8&9 Cooling Water at CSTPS. | MERC/CAPEX/MSPGCL/2023-2024/0467 Dt 02.08.2024 | 2024-08-02 | 67 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | MERC/CAPEX/MSPGCL/2023-2024/0467 Dt 02.08.2024 | 2024-08-02 | 2.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (ii) Submitted to MERC |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y1 | Multiple Schemes for Electrical Maintenance Section and Design, Engineering, Manufacturing, Testing, Unloading at site, E&C of 200MVA, 21/420KV Single Phase Generator Transformer for Unit # 8 & 9, CSTPS | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 10MW, 11kV Motor and its recommended spare for Boiler Feed Pump (BFP) | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Replacement of NiCd battery sets installed for UPS of Fire Water Pump House, CMRH & SWAS lab of Unit 8 & 9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Retrofitting of GE make LT Air Circuit Breakers of various current ratings and procurement of their recommended spares for Unit-8&9, CSTPS | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of BHEL make 6.6kV and 11kV Vacuum Circuit Breakers for Unit-8&9, CSTPS Chandrapur | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y5 | Scheme-1: Procurement of assembly of baskets for Air Preheater of type 31.05 VIMT 2000 (72° PA), Scheme-2: Procurement of spares for PRDS station pressure control valves and Desuperheating spray Control valves in Boiler at U-8&9, CSTPS, Chandrapur, Scheme-3: Procurement of complete set of sky climber at U-8&9, CSTPS, Chandrapur. Scheme-4: Supply, erction, commissioning of oil free rotary screw compressors (including all Civil Electrical, C&I, Testing work) for CMRH system at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-1: Procurement of assembly of baskets for Air Preheater of type 31.5 VIMT 2000 (72° PA) at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-2: Procurement of spares for PRDS station pressure control valves and Desuperheating spray control valves in Boiler at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-3: Procurement of complete set of sky climber at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-4: Supply, erection, commissioning of oil free rotary screw compressors (including all Civil Electrical, C&I, Testing work) for CMRH system at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y6 &Y7 | Supply, Erection & commissioning/retrofitting of HT Circuit Breaker with SF6 Contactor at AHP at Unit-8&9 & CHP#D and Supply, Installation and Commissioning of MV VFD panel along with integrated online cell redundancy technology with VFD bypass feature arrangement for conveyors 103 A & B of CHP-B, C.S.T.P.S., Chandrapur & Design, engineering, manufacturing, testing, unloading at site, E&C of Two No of 200 MVA, 21/420 KV Single Phase Generator Transformers for Unit-8&9, CSTPS, Chandrapur. Through OEM | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme 1: Retrofitting of BHEL make HT Circuit Breaker with SF6 contactor at AHP, Unit#8&9, CSTPS. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme 2: Retrofitting of BHEL make HT Circuit Breaker with SF6 contactor at CHP#D, Unit#8&9, CSTPS. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme 3: Supply, Installation and Commissioning of MV VFD panel along with integrated online cell redundancy technology with VFD bypass feature arrangement for conveyors 103 A & B of CHP-B. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, engineering, manufacturing, testing, unloading at site, E&C of Two No of 200 MVA, 21/420 KV Single Phase Generator Transformers for Unit-8&9, CSTPS, Chandrapur. Through OEM | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (iii) Yet to be Submitted to MERC |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Boiler Maintenance -III |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of Air & Flue gas ducts of Boiler , Blade set and HAD for PA and FD Fan , SCAPH Coil, ID Fan spares at Unit-8&9 CSTPS, Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-1 Procurement of Air & flue gas expansion joints |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-2 :Procurement of Blade Set and 2 sets of HAD of PA Fan. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme -3 Procurement of Blade Set and 2 sets of HAD of FD Fan. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-4 Procurement of SCAPH Coil for unit- 8&9 |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-5 :Procurement of ID Fan Impeller , Shaft and Blade set at unit-8 & 9, CSTPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme 6: Procurment of Coal Fuel pipes for unit -8 &9 , CSTPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of LTSH and economiser for unit-8&9 CSTPS, Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of LTSH Coil assemsblies unit- 8&9 |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of economiser coil asemblies |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of existing belt type gravimetric coal feeders to gravimetric rotary weigh coal feeders of unit- 8&9, at CSTPS, Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of Quick Erect Aluminum Boiler Scaffolding system or unit- 8 & 9, (2X500MW), CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of Quick Erect Aluminum Boiler Scaffolding system or unit- 8 & 9, (2X500MW), CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Turbine Maintenance -III |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Schemes for Improvement in availability & performance of TG auxiliaries at U-8&9, CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 1. Procurement of BFP Booster Pump assembly for Unit-8 & 9, CSTPS Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 2. Procurement of Boiler Feed Pump catridge with CI sealing for Unit- 8 & 9, CSTPS Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 3. Procurement of Modulating type Boiler Feed Pump Recirculation valve (06 Nos) assembly for Unit- 8 & 9, CSTPS Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 4. Procurement of HP Heater HPH-5B assembly for Unit- 8 & 9, CSTPS Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 5. Procurement of MDBFP working oil & lube oil coolers for Unit- 8 & 9, CSTPS Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 6. Procurement of TDBFP Turbine rotor K1401-2 at Unit- 8 & 9, CSTPS Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 7. Procurement of Main TG Jacking oil pumps (2 Nos.) at Unit- 8 & 9, CSTPS Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 8. Procurement of HP elements of ZR500 Atlas Copco make compressors along with inter & after coolers tube nest at Unit- 8 & 9, CSTPS Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 9. Procurement of CW & ACW Pump spares at Unit- 8 & 9, CSTPS Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 10. Procurement of condenser tubes at Unit- 8 & 9, CSTPS Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 11. Procurement of HPCF Pump at Unit- 8 & 9, CSTPS Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | DPR for performance improvement of Condenser Cooling water system & improvement in system reliability of auxiliary cooling water system installed at Unit-8&9, 2x500MW, CSTPS, Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| DPR for performance improvement of Condenser Cooling water system & improvement in system reliability of auxiliary cooling water system installed at Unit-8&9, 2x500MW, CSTPS, Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of main turbine IPT module at Unit- 8 & 9, CSTPS Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of main turbine IPT module at Unit- 8 & 9, CSTPS Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Electrical Maintenance -III |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Proc of GTR, MDBFP, UPS battery, breakers |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, engineering, manufacturing, testing, unloading at site, E&C of 200 MVA, 21/420 KV Single Phase Generator Transformer for Unit-8&9, CSTPS, Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of MDBFP motor and recommended spares The Fire Water Pump House UPS Battery set of 240V, 40AH Capacity (1.2V X 176 Cells ) Ni Cd Type Make- HBL The UPS Battery Set at SWAS Lab (Outdoor Area), 45AH Capacity (1.2 V X 276 Cells) Ni Cd type Make- HBL for Unit#8&9 The UPS Battery Set at CMRH (Outdoor Area), 69AH Capacity (1.2 V X 280 Cells) Ni Cd type Make- HBL for Unit#8&9 Retrofitting of 415V GE make ACB of various ratings along with allied spares. BHEL make Breakers and spares for 6.6 kV and 11kV panels |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Design, engineering, manufacturing, testing, unloading at site, E&C of 80 MVA, 420/11/6.9 KV three Phase Station Transformer & 25MVA 21/6.9KV Three phase Unit Aux Transformer as a common pool spares for BTPS 500MW, Khaparkheda 500 MW and Unit-8&9, CSTPS, Chandrapur & Supply, installation, commissioning and testing of Station Batteries of Unit-8&9 CSTPS alongwith all outdoor batteries |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, engineering, manufacturing, testing, unloading at site, E&C of 80 MVA, 420/11/6.9 KV three Phase Station Transformer & 25MVA 21/6.9KV Three phase Unit Aux Transformer as a common pool spares for BTPS 500MW, Khaparkheda 500 MW and Unit-8&9, CSTPS, Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, installation, commissioning and testing of Station Batteries of Unit-8&9 CSTPS alongwith all outdoor batteries |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| I&C -III |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Upgradation of Analysis & Diagnostics system (A&D) for VMS and TSI system at Unit-8&9, CSTPS, Chandrapur.& other schemes |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of Analysis & Diagnostics system (A&D) for VMS and TSI system at Unit-8&9, CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Installation of CO analysers at Eco outlet at Unit-8&9, CSTPS Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Complete Engineering Retrofitting of Existing 196 NT Controller by DT 9 Controller alongwith HMI units for Unit 8/9 coal feeder system. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of spares for LP bypass system. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of spares for maxDNA DCS system |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-9, CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-9, CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Upgradation of HMI and hardware of GE make PLCs installed at Unit-8&9, CSTPS, Chandrapur. & other schemes |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of HMI and hardware of GE make PLCs installed at Unit-8&9, CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of TD-BFP Turbovisory system installed at Unit-8&9, CSTPS, Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of EWLI system installed at Unit-8&9, CSTPS, Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of O2 analysers installed at Unit-8&9, CSTPS, Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Installation of High temperature Camera system at Unit-8&9, CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of HEA igniter system at Unit-8&9, CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of Flue Gas Analysers and Opacity Analysers at Unit-8&9, CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-8, CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-8, CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Multiple schemes C&I-3 |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Total Mercury (Gaseous) Analyzers along with their online data connectivity & Remote calibration U-3 to 9 |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Controllers & Com Boxes for Air Compressors of Unit-8&9. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of Steam and Water Analysis System (SWAS) for Unit – 8 & 9 |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of Servo valve (ST) with proportional valves (PV) for HP bypass system at Unit – 8 & 9 |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of GEHO pump VFD panels for Unit – 8 & 9 |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Upgradation of measurement and control system installed at CSTPS Unit 8&9 & Upgradation of Numerical Protection Relay of Alstom / Schnieder make installed at Unit-8&9, CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of measurement and control system installed at CSTPS Unit 8&9 |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of Numerical Protection Relay of Alstom / Schnieder make installed at Unit-8&9, CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| AHP-III |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | supply of piston cylinder assembly, diaphragm assembly, Suction and discharge valve housing assembly of GEHO pump (Model- TZPM 1200). & other schemes |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-1 :supply of piston cylinder assembly, diaphragm assembly, Suction and discharge valve housing assembly of GEHO pump (Model- TZPM 1200). |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme -2 :Procurement of sub assemblies for conveying air compressor model ZR 275 and instrument air compressor model ZR 110 in Ash handling plant Unit-8&9 (2x500MW) at CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme -3 Supply of 10/8 FAH Warman make slurry pump impeller element assembly, Bearing assembly unit, jacket assembly. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply and replacement of 400 NB MSERW pipeline of ash disposal system of unit 8&9 at CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-1 :Supply and replacement of 400 NB MSERW pipeline of ash disposal system of unit 8&9 at CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Complete ESP Refurbishment of 1st & 2 nd Row Field of Unit 8&9 at CSTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-1 : Complete ESP Refurbishment of 1st & 2 nd Row Field of Unit 8&9 at CSTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| CHP - D |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Upgradation Of Hydraulic Systems with Safety Mechanism for wagon unloading system at CHP-D CSTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply erection & commissioning of wagon tippler, Side Arm Charger, apron feeder and stacker hydraulic drive system with online NAS value monitoring systems. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Wagon stopping mechanism (Safety) |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgardation and Capacity Enhancement of Side Arm Charger Apron Feeder and Bunker Conveyors at CHP-D CSTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| capacity enhancement to 60 wagons pulling capacity and associated modification of existing side arm charger |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Capacity enhancement , Commissionng of apron feeder drive |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Modification and revamping of Apron Feeder 101,102,103 |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply,Installation and Commissioning of double drive Mechanism with Split Case Bearings for Tripper Trolley and bunkering conevyor belts of CHP-D, CSTPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Modification of Fixed Tripper Head Pulley(Z-Point) of BC110A&B at CHP-D CSTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Modification, Errection & Commissioning of drive unit capacity enhancement for conveyor at CHP-D, Chandrapur TPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Performance Improvement Schemes of CHP-D CSTPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design engineering , supply and installation of modular chutes with weld cast Liners ,flap gates and actuators. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply erection & commissioning of set of internal of spares of Wagon tippler and Side Arm Charger installed at CHP-D, CSTPS Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply erection & commissioning of set of internal of spares of stacker reclaimer installed at CHP-D, CSTPS Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply erection & commissioning of set of internal of spares of Impact crusher installed at CHP-D, CSTPS Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply erection & commissioning of set of internal of spares of wobbler feeder installed at CHP-D, CSTPS Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply erection & commissioning of 1500 TPH capacity Stacker Recliamer sleeving bearing with fastener of CHP-D (U8&9), CSTPS, Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of Gearbox assemblies at CHP-D CSTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Structure Strengthening,Modification works of Conveyors at CHP-D CSTPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Design, Installation, testing and commissioning of new conveyor systems of CHP-D, CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, Installation, testing and commissioning of conveyor system from crusher house to TP-108 of CHP-D, CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, Engineering, erection and commissioning of one 1500TPH crusher, short conveyors from TP 106 and open space of near Stack yard A pile to Crusher inlet and a telescopic conveyor at the output of crusher to Stack Yard B pile of CHPD Unit 8&9, CSTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design, Installation and commissioning of conveyor system from rope way of CHP-A to crusher house of CHP-D, CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, Installation and commissioning of conveyor system from rope way of CHP-A to crusher house of CHP-D, CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Infrastructure Development Schemes at CHP-D CSTPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, Supply,Installation and Commissioning of EOT Cranes at Wagon Tippler area of CHP-D CSTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Belt Tracking systems for Carrying/Return 1400/1600 mm belt width |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Ceramic Lagging by direct bonding on Conveyor Pulleys without Rubber Pad/Rubber Sheets. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Rewamping of crane and hoist of CHP, Unit 8&9, CSTPS, Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Material lifting mechanism at Crusher, bunker and Tunnel area of CHP-D CSTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Revamping, modification of TunnelAir ventilation system |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Revamping, modification of DE and DS system |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Revamping, modification of Dewatering and water recirculation system |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Provision of New Office Building with Infrastructure ,Interior Development at CHP-D CSTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Material Storage Shed Fabrication work at CHP-D CSTPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Electrical schemes for improvement in availability & Reliability of CHP-D,CSTPS, Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design supply installation and commisioning of LED based energy efficient system for illumination at CHPD |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, Erection, Commissioning and Testing of 7.2KV SF6 HT Contactor for retrofitting of existing BHEL make Vacuum Circuit Breakers of CHP-D, CSTPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of GE make 90-30 series PLC system installed at stacker rclaimer and wagon tippler at CHP-D, CSTPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Installation of energy efficient air temperature controlling system at various MCC rooms of CHPD, CSTPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Alterration, upgradation of tunnel ventilation system of CHPD, CSTPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, Fabrication, Erection & commissioning of cable support structure along with re-routing & trial of auxiliaries at Crusher PMCC, compressor house & short conveyor area at CHP-D, CSTPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply and installation of LT air circuit breakes at CHP-D, CSTPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, supply, installation & commissioning of solar based energy efficient illumination system at CHP-D, CSTPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of HT motors for various auxiliaries at CHP-D, CSTPS. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply & installation of high capacity submersible slurry pump at CHP-D, CSTPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Reconditioning of MCC Board feeder panels at CHP-D,U #8&9.CSTPS,Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply & installation of anoodized winding magnets along with control panels for installation at various conveyor belts of CHP-D, CSTPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of 69 AH HBL make battery set of CHP-D (U8&9), CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of 100 AH Exide make battery banks (2 Set/ 110 Nos battery cells) & battery charge at CHP-D (U8&9), CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Alterration, upgradation of tunnel ventilation system of CHPD, CSTPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of HT/LT Xmers assy of CHP-D (U8&9), CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of HT/LT Xmers assy of CHP-D (U8&9), CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| WTP-III |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Engineering, installation and commissioning of DM stream capacity of 4800M3/Day for U # 8 & 9 in addition to existing DM stream at WTP, CSTPS, Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Engineering, installation and commissioning of DM stream capacity of 4800M3/Day for U # 8 & 9 in addition to existing DM stream at WTP, CSTPS, Chandrapur |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Civil - 8&9 |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work of diversion of peripheral nallah towards ash water recovery pump house alogwith construction of waste wear at ash bund area CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Work of diversion of peripheral nallah towards ash water recovery pump house alogwith construction of waste wear at ash bund area CSTPS, Chandrapur. |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Infrastructure development of CHP-D area at U-8, 9, CSTPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Provision of platform for unloading of coal near TP-106 upto stack pile A of CHP-D |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Provision of WBM Road for fire fighting arrangement at CHP-D U-8,9 |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction & Pushing RCC box of size 2mx2m under railway track to drain out the surface water near Rly - A cabin Unit-8,9 |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of concrete pavement road connecting to reject gate & vinchoda chowk , Y point to ash recovery pump house |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO1 | CHP Improvement Schemes |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at CHP-D |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO2 | Developlment & Upgradation of DSM software system for MSPGCL |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Developlment & Upgradation of DSM software system for MSPGCL |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Implementation of Flexible Operation Solutions |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Implementation of Flexible Operation Solutions |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| B) Non-DPR Schemes |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | General asset |  | - | 0 | 0 | 0 | 0 | 1.87 | 1.87 |  |  | 1.87 | 0
2 | Supply, Operation & Maintenance of Mobile Coal Sampling Equipment (MCSE) for coal sampling at loading ends of WCL for Mahagenco |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | ABC Powder Type and Foam Type Composite Fire Extinguisher |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | NON-Detailed Project Report for the Work of Upgradation/Renovation of Crusher House of CHPB of Unit-5, 6&7 at CSTPS Chandrapur (benefit U-8,9 by short conveyor coal stacking in catering emergency) |  | - | 0 | 0 | 0 | 0 | 1.4404 | 0 |  |  | 0 | 1.4404
5 | Extention of stacker reclaimer area for improvement in coal stack management at CHP-D CSTPS Chandrapur U-8,9 |  | - | 0 | 0 | 0 | 0 | 3.9102 | 0 |  |  | 0 | 3.9102
6 | Retrofitting of BHEL make HT Circuit Breaker with SF6 Contactor at CHP-D, Unit-8&9 |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 322.0114 | 357.1531 | -35.1417 | 83.5669 | 81.5397 | 0 | 0 | 81.5397 | -33.1145
FY 2023-24
A) Approved Add Cap (Case No. 296 of 2019)
1 | Initial Spares | Approved Add Cap (Case No. 296 of 2019)
| Boiler & Auxiliaries | 0 | - | 10.36 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Bevel Helical Gear box KMP-350 for XRP 1043 coal mills at unit-8&9,CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 7.4087 | 7.4087 |  |  | 7.4087 | 0
| Procurement of Hydraulic Adjustment (Actuating) Device for PA fan model PAF 19/10.6-2 and FD fan FAF 23/12.5-1 at Unit 8&9, CSTPS, Chandrapur. | 0 | - | 0 | 1.3971 | 1.3971 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Yokogawa make Zirconia Oxygen Analyser spares for C&I-III, Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 0.51933 | 0.51933 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of High pressure valves installed at unit-8&9 ( 2x500 MW),CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Turbine & Aux | 0 | - | 1.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of IMI Norgren Herion make Trip solenoid valves for Main Turbine, MD-BFP & TD-BFP of Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.37354 | 0.37354 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Speed Sensors for 500 MW KWU Turbine for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.038232 | 0.038232 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Position Feedback Transmitters for Starting Device and Speeder Gear of Main Turbine for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.11225 | 0.11225 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for LP bypass system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur on OEM Basis. | 0 | - | 0 | 0.43645 | 0.43645 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of TSE (Turbine Stress Evaluator) temperature elements for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.2073 | 0.18403 | 0.023271 | 0 | 0.023164 |  |  | 0.023164 | 0.00010699
| Generator and Auxiliries | 0 | - | 0.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of complete set of water cooled bushing for 500MW Generator installed at Unit-8 & 9, CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0.26409 | 0.26409 |  |  | 0.26409 | 0
| Procurement of Tushaco make complete AC Jacking Oil Pump for Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.19949 | 0.19949 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of oil filled Neutral Grounding Transformer for AHP Unit-8&9 CSTPS , Chandrapur. | 0 | - | 0 | 0.34775 | 0.34775 | 0 | 0 | 0 |  |  | 0 | 0
| Electrical and Instrumentation | 0 | - | 29.23 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| ‘Procurement of various spares of BHEL make Vacuum Circuit Breakers’ , for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.49498 | 0.49498 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, erection and commissioning of floor mounted 500KW Resistor Load Bank for D.G. sets installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.27536 | 0.27536 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Turbosupervisory system spares of main turbine for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 1.0366 | 1.0366 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Level transmitters for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.15999 | 0.15999 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Level transmitters for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.018125 | 0.018125 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Level transmitters for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.046973 | 0.046973 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of GE PLC spares for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.57304 | 0.57304 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for GEHO pumps PLC control panels for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.084378 | 0.084378 | 2.6e-08 | 0 | 0 |  |  | 0 | 2.6e-08
| Procurement of master calibration lab Instruments for C&I-III, Unit 8 & 9,CSTPS,Chandrapur | 0 | - | 0 | 0.30131 | 0.30131 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Coal Feeder panel spares for C&I-III, Unit 8 & 9,CSTPS, Chandrapur | 0 | - | 0 | 0.58701 | 0.58701 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Opacity Monitor (Stack Particulate matter-SPM) spares for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.14051 | 0.14051 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Forbes Marshall Supervisory system spares For Turbine driven boiler feed pumps (TDBFP) of Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.22449 | 0.22449 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for hydraulic panel of CW pumps for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.13862 | 0.1386 | 1.7196e-05 | 0 | 0 |  |  | 0 | 1.7196e-05
| Procurement of H2 Dew point analyzer spares for Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.049938 | 0.049938 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for HP bypass system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.33965 | 0.33965 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Position feedback transmitter for HP bypass system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.0354 | 0.0354 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Atlas Copco make Instrument, Service and Conveying air Compressors for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.22509 | 0.22509 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for HEA Ignitors and Flame Scanners for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.037701 | 0.037701 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for GEHO pumps of Ash Handling System at C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.28861 | 0.28861 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Turbine side control valve spares for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.17974 | 0.17974 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various numerical protection relays for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.12307 | 0.12307 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various numerical protection relays for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.13184 | 0.13184 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various numerical protection relays for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.13863 | 0.13863 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for DB POWER make UPS system installed at HCSD Pump House, Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.064757 | 0.064757 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Fully Automatic Capacitance & Dissipation Factor (Tan- Delta) measuring kit for Unit-8 &9, CSTPS, Chandrapur. | 0 | - | 0 | 0.48288 | 0.48288 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of various VFD spares for ID fans of Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.45626 | 0.45626 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of DAVR spares installed at Unit -8&9 CSTPS, Chandrapur. | 0 | - | 0 | 0.57179 | 0.57179 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 3 phase relay test kit for Unit-8 &9, CSTPS, Chandrapur. | 0 | - | 0 | 0.35388 | 0.35388 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Fast Bus Transfer System (FBTS) installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.37288 | 0.37288 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various spares for battery chargers installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.40022 | 0.40022 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Auto synchronizing Relay (ASR) & Load Shedding Relay (LSR) installed at Unit-8 &9, CSTPS, Chandrapur. | 0 | - | 0 | 0.34973 | 0.34973 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ESP spares i.e. Field Controller, Thyristor and Trigger card for ESP of Unit-8 & 9, CSTPS Chandrapur. | 0 | - | 0 | 0.26745 | 0.26745 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various VFD spares for GEHO pump of Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.54416 | 0.54416 | 0 | 0 | 0 |  |  | 0 | 0
| Design, Supply, Erection & Commissioning of On-Line Dissolved Gas Analyzers for various Transformers installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 3.1775 | 3.1775 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, Erection & Commissioning of On-Line Dissolved Gas Analyzers for Station Transformers -8B, Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.30519 | 0.30519 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘TOROSHIMA’ make 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motor (without pump casing) for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 4.2037 | 4.2037 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 90kVA ESP Rectiformer for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.29878 | 0.29878 | 0 | 0 | 0 |  |  | 0 | 0
| Supply erection & commissioning of Aviation Lighting for NDCT of Unit-8&9, CSTPS Chandrapur | 0 | - | 0 | 0.57261 | 0.57261 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Transformer oil storage tanks of different capacity for Unit-8&9 CSTPS Chandrapur. | 0 | - | 0 | 0.57024 | 0.57024 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 2000kW & 315kW, 6.6 kV HT motors for CW & ACW Pump installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 1.4505 | 1.4505 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 3.25MVA, 6.6/2.3kV VFD Transformers of vector group DY11 for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 3.25MVA, 6.6/2.3kV VFD Transformer of vector group ‘Dd0’ for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘MARATHON’ makes HT/LT Induction motors for various Critical auxiliaries installed at Unit-8 &9, CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of 1.2V, Ni-Cd battery cells for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.12496 | 0.12496 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of 1.2V, Ni-Cd battery cells for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.18931 | 0.18931 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘Air Core DC Reactor’ for VFD and ‘NGR’ for UAT/ Station Transformers installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.44368 | 0.44368 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘Air Core DC Reactor’ for VFD and ‘NGR’ for UAT/ Station Transformers installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.12551 | 0.12551 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘BHEL’ make 680 KW, 6.6KV, Coal Mill Motor for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.37913 | 0.37913 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 400kV OIP Condenser Bushing for Generator Transformer & Station Transformer of Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.49064 | 0.49064 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘11kW DC motor with Control Cabinet’ for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 37kW, 415V motors for Primary Water Pump installed at Unit-8 &9, CSTPS Chandrapur. | 0 | - | 0 | 0.0096851 | 0.0096851 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 15 KW, 415V LT Motor for Service Building & TG Building Lift installed at Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.095155 | 0.095155 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 16KW, 415V LT Motor for Boiler Lift installed at Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.044179 | 0.044179 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, Erection, Testing and Commissioning of Hydrastep-Electronic Drum Level Indicator and its associated accessories for Unit-9, CSTPS, Chandrapur | 0 | - | 0 | 0.27376 | 0.27376 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for BHEL make Hydrastep (Electronic Water Level Indicator -BHELVISION 20M) for Unit 8 & 9, CSTPS, Chandrapur on OEM basis. | 0 | - | 0 | 0.084172 | 0.084172 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Electrodes for Hydrastep (Electronic Water Level Indicator -BHELVISION 20M) for Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.10384 | 0.10384 | 0 | 0 | 0 |  |  | 0 | 0
| Engineering & Retrofitting of 196 NT Controller to DT 9 Controller for Unit-8 & 9 Coal Feeder System. | 0 | - | 0 | 0.38076 | 0.38076 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for BHEL make Acoustic steam leak detection system (BHELSONIC) (BS10) for Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.077807 | 0.077807 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of LT Circuit Breaker assemblies for ESP LT Panels (LTMSB & ACP) of Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.25429 | 0.25429 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for BHEL make maxDNA Distributed control system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 1.0652 | 1.0652 | 0 | 0.051819 | 0.051819 |  |  | 0.051819 | 0
| Supply of Transformer oil BDV test kit DTA 100C and Oil Tan Delta & Resistivity Tester DTL C at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.47598 | 0.47598 | 0 | 0 | 0 |  |  | 0 | 0
| Outdoor Plant ( CHP/AHP/WTP) | 0 | - | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Elecon make KCN-560 type Gearbox for Apron Feeder installed at CHPD, CSTPS. | 0 | - | 0 | 1.6717 | 1.6717 | -6e-08 | 0 | 0 |  |  | 0 | -6e-08
| Procurement of spares of CKB-280,225,200,8180 typ gearbox installed at CHP-D | 0 | - | 0 | 1.0015 | 1.0015 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Gear Box (MAKE: NEW ALLENBERRY) Spares at CHP-D; CSTPS, Chandrapur. | 0 | - | 0 | 0.5177 | 0.5177 | 1.8e-08 | 0 | 0 |  |  | 0 | 1.8e-08
| Procurement of spares for m/s Elecon make Impact Crusher installed at CHP Unit 8&9 CSTPS, Chandrapur | 0 | - | 0 | 0.84103 | 0.84103 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of V belt pulley of rotor for Impact crusher installed at CHP-D, CSTPS | 0 | - | 0 | 0.11864 | 0.11864 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Spares for hydraulic systems installed at CHPD, CSTPS. | 0 | - | 0 | 0.47537 | 0.47537 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Spares for hydraulic systems installed at CHPD, CSTPS. | 0 | - | 0 | 0.028604 | 0.028604 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of drive & non drive pulley for various conveyors installed at CHP D, CSTPS, Chandrapur. | 0 | - | 0 | 0.25792 | 0.25792 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of drive & non drive pulley for various conveyors installed at CHP D, CSTPS, Chandrapur. | 0 | - | 0 | 0.0914 | 0.0914 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Chain links for apron feeder installed at CHP D, CSTPS, Chandrapur. | 0 | - | 0 | 0.40289 | 0.40289 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of internal spares for Elecon make PWD-18, PLB-25 & SCN-180 type Gearbox for Stacker Reclaimer & wobbler feeder installed at CHP D, CSTPS. | 0 | - | 0 | 0.52774 | 0.52774 | 3.1e-08 | 0 | 0 |  |  | 0 | 3.1e-08
| Supply of GE Make Switchgear Spares for GE Make LT Feeders | 0 | - | 0 | 0.12485 | 0.12485 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Fluidomat make scoop coupling installed at CHP–D, CSTPS, Chandrapur | 0 | - | 0 | 0.48355 | 0.48355 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Oil Filtering machine for hydraulic power packs installed at CHPD, CSTPS | 0 | - | 0 | 0.10592 | 0.10592 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of LT Motors at CHP-D (U#8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0.11302 | 0.11302 | 0 | 0 | 0 |  |  | 0 | 0
| Supply and Installation of Oil Cooled Suspended Anodized Winding Magnet & Control Panel at CHP, Unit 8&9, CSTPS, Chandrapur. | 0 | - | 0 | 2.2967 | 2.2967 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of LT power and control cable for CHP-D | 0 | - | 0 | 0.26256 | 0.26256 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of LT power and control cable for CHP-D | 0 | - | 0 | 0.022125 | 0.022125 | 0 | 0 | 0 |  |  | 0 | 0
2 | Capital Spare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| HPT MODULE | 0 | - | 45.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of HP turbine Module along with breach nuts and pipe spool pieces (Type: H30-100-2) for Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 32.332 | 32.332 |  |  | 32.332 | 0
| LPT ROTOR | 0 | - | 40.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Fully Bladed & Dynamically Balanced LP Rotor (N30-2X10-2) for Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 29.03 | 29.03 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of set of Free Standing Moving Blades for LP Rotor (N30-2X10-2) for Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 4.5629 | 4.5629 |  |  | 4.5629 | 0
| BFP CARTRIDGE ( 2NOS ) | 0 | - | 4.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of cartridge assembly for Boiler Feed Pump model FK-4E-36 (with Four S/H & 2 R/H spray branches) installed at 2X 500MW, CSTPS, Chandrapur. | 0 | - | 0 | 2.515 | 2.5149 | 6e-05 | 0 | 0 |  |  | 0 | 6e-05
| BCW PUMP | 0 | - | 3.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for ‘TOROSHIMA’ make 350KW BCW Pump-Motor installed at Unit-8 &9, CSTPS Chandrapur. | 0 | - | 0 | 1.3283 | 1.3283 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various spares for ‘TOROSHIMA’ make Boiler Circulating Water (BCW) pump-motor installed at Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 2.2326 | 2.2326 | 0 | 0 | 0 |  |  | 0 | 0
| 15 MVA DRY TYPE TRANSFORMER | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spare ‘Cast Resin Dry Type Transformers (CRTs)’ of different ratings for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 6.0213 | 6.0213 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of phase coil limb and spares of Cast Resin Dry Type Transformers of different ratings for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 7.9255 | 7.9255 | 0 | 0 | 0 |  |  | 0 | 0
| BTG+BOP& Other Works | 0 | - | 20.48 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Design, Supply & Installation, Testing & Commissioning of Public Addressing System for tunnels of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 1.1544 | 1.1544 | 0 | 0 | 0 |  |  | 0 | 0
| Work of upgradation, installation and extension of 220VDC control supply to various PMCC of CHPD, CSTPS, Chandrapur. | 0 | - | 0 | 0.68441 | 0.68441 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Apron Feeder in CHP Unit 8&9 (2x500) MW at CHP-D, CSTPS. | 0 | - | 0 | 2.3388 | 2.3388 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of spares for up gradation of rotary parts of travelling conveyor system installed at CHPD, CSTPS, Chandrapur. | 0 | - | 0 | 0.58939 | 0.58939 | 0 | 0 | 0 |  |  | 0 | 0
| The Work of Design, Engineering, Manufacturing, Supply, Erection & Commissioning of Short Conveyor belt from stack yard of CHP of Unit 5,6&7 to Belt Conveyor 104 A/B at CHP of Unit 8&9, CSTPS, Chandrapur | 0 | - | 0 | 2.9173 | 0 | 2.9173 | 2.2467 | 5.164 |  |  | 5.164 | 0
| Work of design, supply, erection, commissioning of overhead cable tray along with removal & re-routing of power and control cables at CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0.51324 | 0.51324 | 0 | 0 | 0 |  |  | 0 | 0
| Work of provision, modification, retrofitting and revamping of lighting system of transfers points, crusher house and bunker area of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 1.0105 | 1.0105 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for M/s. Weir Minerals make (GEHO pump Model TZPM-1200) for Ash Handling Plant Unit# 8 &9 CSTPS Chandrapur. AHP-III | 0 | - | 0 | 2.106 | 2.106 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Gear Box set of internal (MAKE: NEW ALLENBERRY) Spares at CHP-D; CSTPS, Chandrapur. | 0 | - | 0 | 1.6904 | 1.6904 | 0 | 0 | 0 |  |  | 0 | 0
| Supply and Installation of Oil Cooled Suspended Anodized Winding Magnet & Control Panel at CHP, Unit 8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 196 NT Controller by DT 9 Controller alongwith HMI units for Unit- 8&9 coal feeder system | 0 | - | 0 | 2.0774 | 2.0774 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of set of CW Impeller duly fitted with wear rings & ACW Impeller duly fitted with wear rings of Mather & Platt make Pumps installed at Unit-8 & 9,CSTPS,Chandrapur | 0 | - | 0 | 0.70379 | 0.70379 | 0 | 0 | 0 |  |  | 0 | 0
| CHP System U#8 | 0 | - | 0 | 0.05 | 0.05 | 0 | 0 | 0 |  |  | 0 | 0
| ISOLATED PHASE BUS DUCT | 0 | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| SEGREGATED PHASE BUS DUCT U#8 | 0 | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| SEGREGATED PHASE BUS DUCT U#9 | 0 | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| ISOLATED PHASE BUS DUCT U#9 | 0 | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| DTT & UAT U#8 | 0 | - | 0 | 0.03 | 0.03 | 0 | 0 | 0 |  |  | 0 | 0
| DTT & UAT U#9 | 0 | - | 0 | 0.03 | 0.03 | 0 | 0 | 0 |  |  | 0 | 0
| Cranes and hoists U#8 | 0 | - | 0 | 0.03 | 0.03 | 0 | 0 | 0 |  |  | 0 | 0
| RCC Chimney U#8 | 0 | - | 0 | 9.29 | 9.29 | 0 | 0 | 0 |  |  | 0 | 0
| Coal Handling Plant | 0 | - | 0 | 41.79 | 41.79 | 0 | 0 | 0 |  |  | 0 | 0
| Bunker foundation & civil works (Unit 8) U#8 | 0 | - | 0 | 18.58 | 18.58 | 0 | 0 | 0 |  |  | 0 | 0
| Boiler & Auxiliaries U#9 | 0 | - | 0 | 9.2889 | 9.2872 | 0.0017338 | 0 | 0 |  |  | 0 | 0.0017338
| ESP U#9 | 0 | - | 0 | 2.1589 | 2.1589 | 0 | 0 | 0 |  |  | 0 | 0
| ID fan foundations (Unit 9) U#9 | 0 | - | 0 | 1.7489 | 1.7489 | 0 | 0 | 0 |  |  | 0 | 0
| DRY ASH SILO-12M DIA U#8 | 0 | - | 0 | 1.22 | 1.22 | 0 | 0 | 0 |  |  | 0 | 0
| FD fan foundations (Unit 9) U#9 | 0 | - | 0 | 0.62891 | 0.62891 | 0 | 0 | 0 |  |  | 0 | 0
| PA fan foundations (Unit 9) U#9 | 0 | - | 0 | 0.54891 | 0.54891 | 0 | 0 | 0 |  |  | 0 | 0
| Natural Draft cooling tower- Unit 8 U#8 | 0 | - | 0 | 0.32 | 0.32 | 0 | 0 | 0 |  |  | 0 | 0
| Main power house building-Civil Works-Unit no.-9 U | 0 | - | 0 | 0.15 | 0.15 | 0 | 0 | 0 |  |  | 0 | 0
| Structural Steel works for main power house buildi | 0 | - | 0 | 0.15 | 0.15 | 0 | 0 | 0 |  |  | 0 | 0
| Canteen U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Security and time office U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| CARS SCOOTERS AND CYCLE SHED U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Fire Station U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Watch towers U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| First aid station | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Tranformer yard U#8 | 0 | - | 0 | 0.02 | 0.02 | 0 | 0 | 0 |  |  | 0 | 0
| Rain Water Harvesting Scheme U#8&9 | 0 | - | 0 | -0.01 | -0.01 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Advance Multipurpose Fire Tender | 0 | - | 0 | 3.45 | 3.45 | 0 | 0 | 0 |  |  | 0 | 0
| DM Stream | 0 | - | 29.65 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| DM Stream capacity of 100 M3/Hr in addition to existing stream of WTP. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| CIVIL | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Bridge | 0 | - | 4.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Railway, CHP, AHP etc | 0 | - | 152.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| B. G. railway siding Pway works | 0 | - | 0 | 39.5769 | 39.5769 | 0 | 1.9396 | 1.9396 |  |  | 1.9396 | 0
| S & T work for B.G. railway siding | 0 | - | 0 | 0.023574 | 0.023574 | 0 | 0 | 0 |  |  | 0 | 0
| Consultancy services for B. G. railway siding | 0 | - | 0 | 0.035636 | 0.035636 | 0 | 0 | 0 |  |  | 0 | 0
| Ash infra in Railway | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Bunker structure (Unit 8) U#8 | 0 | - | 0 | 18.57 | 18.57 | 0 | 0 | 0 |  |  | 0 | 0
| Coal Mills | 0 | - | 0 | 1.1389 | 1.1389 | 0 | 0 | 0 |  |  | 0 | 0
| Bunker foundation & civil works (Unit 9) U#9 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Bunker structure (Unit 9) U#9 | 0 | - | 0 | 0.11 | 0.11 | 0 | 0 | 0 |  |  | 0 | 0
| HCSS silo-12m dia U#8 | 0 | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| Ash water PH, HCSD PH, Bottom ash slurry PH U#8 | 0 | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| Ash compressor house & Control room U#8 | 0 | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| MILL REJECT SILO U#8 | 0 | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| Fire protection & Detection system U#8 | 0 | - | 0 | 0.71423 | 0.71423 | 0 | 0 | 0 |  |  | 0 | 0
| DM Water Pump room U#8 | 0 | - | 0 | 4.25 | 0 | 4.25 | 0 | 0 |  |  | 0 | 4.25
| Filter water reservoir & pump house U#8 | 0 | - | 0 | 4.29 | 0 | 4.29 | 0 | 0 |  |  | 0 | 4.29
| ACW + RW + Filtered water piping U#8 | 0 | - | 0 | 2.2506 | 0 | 2.2506 | -0.0096938 | -0.0096938 |  |  | -0.0096938 | 2.2506
| Laboratory Building U#8 | 0 | - | 0 | 0.12 | 0 | 0.12 | 0 | 0 |  |  | 0 | 0.12
3 | Staff quarters | 0 | - | 15.04 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Work of exterior repair, providing painting to A, D & E type residential buildings and Public Buildings and allied civil works in Urjanagar Colony, CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Staff Quarters- Repair and renovation of E type staff quarters to extend the life of buildings at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Staff Quarters - Repair and renovation of 'B' type staff quarters in residential colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair of D type quarters in colony at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair of C type quarters in colony at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Staff Quarters- Repair and renovation of F and NF type staff quarters to extend the life of buildings at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair and replacement of existing drinking water supply pipelines in E & F type area in colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair and replacement of existing sewer lines in E & F type area in colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Work of providing RCC drain along main roads in colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Rerouting and replacement of domestic water supply pipeline from WTP to ESR in colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Additional Contengencies approved vide e BR No. MSPGCL/BM-162/165, Dt.29.10.2016 vide resolution no. 2016/2085 | 0 | - | 7.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Landscaping and plantation work at various locations inside plant area at CSTPS, chandrapur. | 0 | - | 0 | 3.4266 | 3.4266 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of WBM approach road from point- N to Z Area along ash bund periphery at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design, Engineering, Supply and commissioning of ash-bund water recovery system (Phase II) at CSTPS Chandrapur | 0 | - | 27.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, Engineering, Supply and commissioning of ash-bund water recovery system (Phase II) at CSTPS Chandrapur | 0 | - | 0 | 17.9073 | 13.5434 | 4.364 | 12.1288 | 16.4928 |  |  | 16.4928 | 0
| Providing Consultancy Services for work of Design, Engineering, Supply, Installation & Commissioning of ash bund water recovery system (Phase-II) at CSTPS, Chandrapur (on EPC contract basis). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Providing laying, jointing and commissioning of 1600 mm dia. M.S. Pipe line from Erai dam to one day reservoir of stage II, III & IV at CTPS | 0 | - | 73.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Providing laying, jointing and commissioning of 1600 mm dia. M.S. Pipe line from Erai dam to one day reservoir of stage II, III & IV at CTPS | 0 | - | 0 | 70.5091 | 70.3626 | 0.1465 | 0 | 0 |  |  | 0 | 0.1465
| Work of construction of Control Valve rooms on newly laid 1600 mm M.S. Pipeline no. 6 from Erai dam to One day reservoir at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Providing OHE facility for BG Rly siding of proposed Expansion Project at Chandrapur, for Supply of Materials. | 0 | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Providing OHE facility for BG Rly siding of proposed Expansion Project at Chandrapur, for errection of OHE Items. | 0 | - | 2.5 | 0.7 | 0 | 0.7 | 0 | 0 |  |  | 0 | 0.7
9 | Irrigation scheme for landscaping and Plantation work at Chandrapur expansion project chandrapur. | 0 | - | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Asphalting of WBM road from Nagpur gate to Awanda gate. | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Asphalting of WBM road from Nagpur gate to Awanda gate. | 0 | - | 0 | 0.65141 | 0 | 0.65141 | 0 | 0 |  |  | 0 | 0.65141
| Asphalting over WBM Road of ADP line Service road from Nagpur gate opening to Awandha junction gate at CSTPS Chandrapur | 0 | - | 0 | 0.84833 | 0.84833 | 0 | 0 | 0 |  |  | 0 | 0
| Asphalting of WBM road from Nagpur gate to Awandha gate at CSTPS Chandrapur - Asphalting of road from Reject coal gate to Motghat nallah at CSTPS Chandrapur (PHASE - I) | 0 | - | 0 | 0.47941 | 0.47941 | 0 | 0 | 0 |  |  | 0 | 0
11 | Foot Over Bridge | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Work of Providing retaining wall for sand hump at Vivekanand nagar station yard under modification work in wardha end fro 2 x 500 MW Expn. Project at CSTPS, Chandrapur. | 0 | - | 0.3 | 0.25515 | 0.25515 | 0 | 0 | 0 |  |  | 0 | 0
| Additional Capitalization by O & M | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of GE make 4000Amp LT Air Circuit Breakers for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0.9 | 1.0308 | 1.0308 | 0 | 0 | 0 |  |  | 0 | 0
2 | Air Compressor System | 0 | - | 0.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Energy management Sysytem | 0 | - | 0.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, Installation, Testing & Commissioning of Energy Management System for Unit#8 & 9 for CSTPS, Chandrapur. | 0 | - | 0 | 0.20054 | 0.20054 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Tri-vector 0.2s class Digital Energy meter for Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.094872 | 0.094872 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, Installation & Commissioning of 3D Level Scanners to 64 nos. of ESP hoppers at Unit-8&9 (2X500MW), CSTPS, Chandrapur. | 0 | - | 3.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of internal spares for Elecon make PWD-18, PLB-25 ,Pbh-71 type Gearbox for Stacker Reclaimer installed at CHPD, CSTPS. | 0 | - | 0 | 1.1089 | 1.1089 | 0 | 0 | 0 |  |  | 0 | 0
5 | 4000/2500/1800/800 A GE make LT CKT Brkr | 0 | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| LT Air Circuit Breakers for Incomer Feeders at CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 1.4207 | 1.4207 | 0 | 0 | 0 |  |  | 0 | 0
| LT Air Circuit Breakers at CHP, Unit 8&9, CSTPS | 0 | - | 0 | 1.0141 | 1.0141 | 0 | 0 | 0 |  |  | 0 | 0
6 | Replacement of Impact crusher by hammer mill crusher (installed qty.2 No) | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Replacement of wobbler feeder 1&2 by grizzly screen at CHP-D | 0 | - | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Installation of conveyor system from rope way of CHP-A and crusher house of CHP-D | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| PLC based control & instrumentation of 6.6 KV HT motors of 1250 KW of Crusher I & II and 200 KW of BC 108A1 & A2 at CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0.93628 | 0.93628 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Design, Supply, Erection & Commissioning of Complete Electrical Automation for Short Conveyor from stack yard of CHP-D to Belt Conveyor 107 A/B of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0.70095 | 0.70095 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Design, Supply, Erection & Commissioning of Complete Electrical Automation for Short Conveyor from stack yard of CHP-B to Belt Conveyor 104 A/B of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 2.2368 | 2.2368 | 0 | 0 | 0 |  |  | 0 | 0
| WORK OF DESIGN, ENGINEERING, MANUFACTURING, SUPPLY, ERECTION &COMMISSIONING OF SHORT CONVEYOR BELT FROM STACK YARD OF CHP UNIT-8&9 TO CONVEYOR BELT 107A AND B AT CHP UNIT 8&9, CSTPS, CHANDRAPUR. | 0 | - | 0 | 4.2253 | 0 | 4.2253 | 0.46948 | 4.6948 |  |  | 4.6948 | -2.4e-08
| Design, Supply, Installation and Commissioning of High Performance Energy Chain System for Side Arm Charger and Stacker Reclaimer of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 3.8916 | 3.8916 | 0 | 0 | 0 |  |  | 0 | 0
| RBF 103 &104,105 & 106, 107 & 108, and 109 & 110 in to modular Y chute | 0 | - | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-103 & RBF-104 with Design, development, Manufacturing, Supply & erection of modular Chute as per site condition in place of RBF using sintered silicon Carbide plate with motorized Flap Gate at CHP-D, CSTPS. | 0 | - | 0 | 1.1741 | 1.1741 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-105 & RBF-106 with Design, development, Manufacturing, Supply & erection of modular Chute as per site condition in place of RBF using sintered silicon Carbide plate with motorized Flap Gate at CHP-D, CSTPS. | 0 | - | 0 | 1.3169 | 1.3169 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-107 & RBF-108 with Design, development, Manufacturing, Supply & erection of modular Chute as per site condition in place of RBF using Tungsten Carbide plate with Flap Gate at CHP-D, CSTPS. | 0 | - | 0 | 1.1529 | 1.1529 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-109 & RBF-110 with design, erection & Installation by trajectory calculation & removal of existing RBF with Y Chute assembly by flow control with Flap Gate arrangement at TP-107 of CHP-D, CSTPS. | 0 | - | 0 | 1.1506 | 1.1506 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurment , Installation and commissioning of Online Insertable Camera systems for Unit-8, 500MW, CSTPS | 0 | - | 8.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, Supply, Installation & Commissioning of Energy efficient system for Illumination at Unit 8&9 CSTPS, Chandrapur. | 0 | - | 0 | 4.9494 | 4.9494 | 0 | 0 | 0 |  |  | 0 | 0
11 | Construction of Chemical godown shed for unit 8 & 9 at CSTPS,Chandrapur. | 0 | - | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of Chemical godown shed for unit 8 & 9 at CSTPS,Chandrapur. | 0 | - | 0 | 0.42946 | 0.42946 | 0 | 0 | 0 |  |  | 0 | 0
| Comprehencive work of installation, erection, testing and commissioning of MVWS spray system/ Fire safety system for new Bulk Chemical storage godown at CSTPS, Unit 8&9 | 0 | - | 0 | 0.27583 | 0.27583 | 0 | 0 | 0 |  |  | 0 | 0
| Work of electrification of godown for bulk chemical storage near FOPH building at Chandrapur project site. | 0 | - | 0 | 0.018322 | 0.018322 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of additional Chemical godown shed for storage of Lube oil at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Construction of RCC retaining wall for approach to RCC Bridge across Irai River, ADPL line at CSTPS | 0 | - | 8.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of RCC retaining wall for approach to RCC Bridge across Irai River, ADPL line at CSTPS | 0 | - | 0 | 1.8289 | 0 | 1.8289 | 2.2193 | 4.0482 |  |  | 4.0482 | 0
| Asphalting of road from Reject coal gate to Motghat nallah at CSTPS Chandrapur (PHASE - II) | 0 | - | 0 | 0.87403 | 0.87403 | 0 | 0 | 0 |  |  | 0 | 0
| Providing extension to approaches of RCC bridge across Erai river by constructing WBM road at CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| UDL | 0 | - | 0 | 4.85 | 4.85 | 0 | 0 | 0 |  |  | 0 | 0
| B) DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (i) In Principally Approved By MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 1 | HMI (Human Machine Interface) Upgradation of ‘SSPA-T3000’ DCS (Distribution Control System), Rockwell make PLC System installed at 3x660MW Unit No. 8, 9 & 10 at Koradi TPS and HMI (Human Machine Interface) Upgradation of MaxDNA DCS System at Unit 8-9, CSTPS, Chandrapur | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 11.08 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 1.1 | Supply: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 10.52 | 0 | 10.5 | -10.5 | 0 | 0 |  |  | 0 | -10.5
HO DPR 1.2 | Works: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.41 | 0 | 0.4 | -0.4 | 0 | 0 |  |  | 0 | -0.4
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
40 | Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M with construction of concrete dam (Waste Weir & Non overflow structure), construction of drain wells, approach to drain wells and raising of ash compartment for ash bund along with renewal of Ash Disposal Pipe Line Service Road with WBM treatment at CSTPS, Chandrapur | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 4.9692 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 34.8665 | 0 | 34.8665 | -34.8665 | 0 | 0 |  |  | 0 | -34.8665
| Construction of New Drain Wells (12 Nos.) along with necessary connection to existing drain wells at CSTPS | 0 | - | 0.58493 | 0 | 0.58493 | -0.58493 | 0 | 0 |  |  | 0 | -0.58493
| Construction of waste weir for raising of ash bund (Waste Weir & Non overflow structure) | 0 | - | 1.4621 | 0 | 1.4621 | -1.4621 | 0 | 0 |  |  | 0 | -1.4621
| Raising of Ash Compartment i.e. Lagoon in Ash Bund | 0 | - | 8.7868 | 0 | 8.7868 | -8.7868 | 0 | 0 |  |  | 0 | -8.7868
| IDC | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 7.634 | 0 | 7.634 | -7.634 | 0 | 0 |  |  | 0 | -7.634
| IDC | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 4.9692 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
39 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 8-9) | MERC/CAPEX/2020-2021/WFH/SBR/21 | 2020-07-24 | 479.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
39.1 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 8-9) | MERC/CAPEX/2020-2021/WFH/SBR/21 | 2020-07-24 | 440.54 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/2020-2021/WFH/SBR/21 | 2020-07-24 | 38.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41 | CHP Performance Improvement Schemes at Unit 8-9 of CSTPS, Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 26.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.1 | Work of Design engineering , supply and installation of modular chutes with sintered silicon carbide for smooth flow &center feeding in CHP 2x500MW CSTPS | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 9.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.2 | Supply erection & commissioning of set of internal of impact crusher spares installed at CHPP-D, CSTPS | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 8.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.3 | Scheme for replacement of Scoop coupling/Fluid coupling of conveyor BC-101A/B/C, BC-102A/B, BC-104A/B, BC-105A/B ,BC-106A/B, BC-111A/B/C/D, BC-110A1/B1, BC-110A/B Installed at CHP-D, CSTPS Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 4.67 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.4 | Supply erection & commissioning of set of internal of spares of stacker reclaimer installed at CHP-D, CSTPS Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 1.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.5 | Supply erection & commissioning of set of internal of spares of Wagon tippler installed at CHP-D, CSTPS Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 2.12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 0.38 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 2 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 2.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
A6 | Supply, Installation & Commissioning of Online Coal Flow Monitoring & Balancing System at Unit-8-9, CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0457 Dt 26.07.2024 | 2024-07-26 | 34.21 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, installation and commissioning of Online Coal flow monitoring and balancing system for U- 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2024-2025/MSPGCL/0457 Dt 26.07.2024 | 2024-07-26 | 34.21 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0457 Dt 26.07.2024 | 2024-07-26 | 0.31 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
A7 | Providing, supplying, laying and commissioning of 1600 mm dia. M.S. Pipe by replacement of existing PSC raw water line from Erai dam to reservoir at CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 40.7945 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing, supplying, laying and commissioning of 1600mm dia. M.S. pipe by replacement of existing PSC raw water line from Erai dam to reservoir at CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 40.7945 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 8.83 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
A8 | Adoption of Ozonization technique for disinfection of Cooling Water System at U # 8 & 9 | MERC/CAPEX/MSPGCL/2023-2024/0467 Dt 02.08.2024 | 2024-08-02 | 67 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Adoption of Ozonization technique for disinfection of Unit 8&9 Cooling Water at CSTPS. | MERC/CAPEX/MSPGCL/2023-2024/0467 Dt 02.08.2024 | 2024-08-02 | 67 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-2024/0467 Dt 02.08.2024 | 2024-08-02 | 2.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (ii) Submitted to MERC |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y1 | Multiple Schemes for Electrical Maintenance Section and Design, Engineering, Manufacturing, Testing, Unloading at site, E&C of 200MVA, 21/420KV Single Phase Generator Transformer for Unit # 8 & 9, CSTPS | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 10MW, 11kV Motor and its recommended spare for Boiler Feed Pump (BFP) | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Replacement of NiCd battery sets installed for UPS of Fire Water Pump House, CMRH & SWAS lab of Unit 8 & 9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Retrofitting of GE make LT Air Circuit Breakers of various current ratings and procurement of their recommended spares for Unit-8&9, CSTPS | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of BHEL make 6.6kV and 11kV Vacuum Circuit Breakers for Unit-8&9, CSTPS Chandrapur | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y5 | Scheme-1: Procurement of assembly of baskets for Air Preheater of type 31.05 VIMT 2000 (72° PA), Scheme-2: Procurement of spares for PRDS station pressure control valves and Desuperheating spray Control valves in Boiler at U-8&9, CSTPS, Chandrapur, Scheme-3: Procurement of complete set of sky climber at U-8&9, CSTPS, Chandrapur. Scheme-4: Supply, erction, commissioning of oil free rotary screw compressors (including all Civil Electrical, C&I, Testing work) for CMRH system at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-1: Procurement of assembly of baskets for Air Preheater of type 31.5 VIMT 2000 (72° PA) at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-2: Procurement of spares for PRDS station pressure control valves and Desuperheating spray control valves in Boiler at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-3: Procurement of complete set of sky climber at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-4: Supply, erection, commissioning of oil free rotary screw compressors (including all Civil Electrical, C&I, Testing work) for CMRH system at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y6 &Y7 | Supply, Erection & commissioning/retrofitting of HT Circuit Breaker with SF6 Contactor at AHP at Unit-8&9 & CHP#D and Supply, Installation and Commissioning of MV VFD panel along with integrated online cell redundancy technology with VFD bypass feature arrangement for conveyors 103 A & B of CHP-B, C.S.T.P.S., Chandrapur & Design, engineering, manufacturing, testing, unloading at site, E&C of Two No of 200 MVA, 21/420 KV Single Phase Generator Transformers for Unit-8&9, CSTPS, Chandrapur. Through OEM | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme 1: Retrofitting of BHEL make HT Circuit Breaker with SF6 contactor at AHP, Unit#8&9, CSTPS. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme 2: Retrofitting of BHEL make HT Circuit Breaker with SF6 contactor at CHP#D, Unit#8&9, CSTPS. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme 3: Supply, Installation and Commissioning of MV VFD panel along with integrated online cell redundancy technology with VFD bypass feature arrangement for conveyors 103 A & B of CHP-B. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, engineering, manufacturing, testing, unloading at site, E&C of Two No of 200 MVA, 21/420 KV Single Phase Generator Transformers for Unit-8&9, CSTPS, Chandrapur. Through OEM | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (iii) Yet to be Submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Boiler Maintenance -III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of Air & Flue gas ducts of Boiler , Blade set and HAD for PA and FD Fan , SCAPH Coil, ID Fan spares at Unit-8&9 CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-1 Procurement of Air & flue gas expansion joints | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-2 :Procurement of Blade Set and 2 sets of HAD of PA Fan. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme -3 Procurement of Blade Set and 2 sets of HAD of FD Fan. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-4 Procurement of SCAPH Coil for unit- 8&9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-5 :Procurement of ID Fan Impeller , Shaft and Blade set at unit-8 & 9, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme 6: Procurment of Coal Fuel pipes for unit -8 &9 , CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of LTSH and economiser for unit-8&9 CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of LTSH Coil assemsblies unit- 8&9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of economiser coil asemblies | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of existing belt type gravimetric coal feeders to gravimetric rotary weigh coal feeders of unit- 8&9, at CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of Quick Erect Aluminum Boiler Scaffolding system or unit- 8 & 9, (2X500MW), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of Quick Erect Aluminum Boiler Scaffolding system or unit- 8 & 9, (2X500MW), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Turbine Maintenance -III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Schemes for Improvement in availability & performance of TG auxiliaries at U-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 1. Procurement of BFP Booster Pump assembly for Unit-8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 2. Procurement of Boiler Feed Pump catridge with CI sealing for Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 3. Procurement of Modulating type Boiler Feed Pump Recirculation valve (06 Nos) assembly for Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 4. Procurement of HP Heater HPH-5B assembly for Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 5. Procurement of MDBFP working oil & lube oil coolers for Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 6. Procurement of TDBFP Turbine rotor K1401-2 at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 7. Procurement of Main TG Jacking oil pumps (2 Nos.) at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 8. Procurement of HP elements of ZR500 Atlas Copco make compressors along with inter & after coolers tube nest at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 9. Procurement of CW & ACW Pump spares at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 10. Procurement of condenser tubes at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 11. Procurement of HPCF Pump at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | DPR for performance improvement of Condenser Cooling water system & improvement in system reliability of auxiliary cooling water system installed at Unit-8&9, 2x500MW, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| DPR for performance improvement of Condenser Cooling water system & improvement in system reliability of auxiliary cooling water system installed at Unit-8&9, 2x500MW, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of main turbine IPT module at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of main turbine IPT module at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Electrical Maintenance -III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Proc of GTR, MDBFP, UPS battery, breakers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, engineering, manufacturing, testing, unloading at site, E&C of 200 MVA, 21/420 KV Single Phase Generator Transformer for Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of MDBFP motor and recommended spares The Fire Water Pump House UPS Battery set of 240V, 40AH Capacity (1.2V X 176 Cells ) Ni Cd Type Make- HBL The UPS Battery Set at SWAS Lab (Outdoor Area), 45AH Capacity (1.2 V X 276 Cells) Ni Cd type Make- HBL for Unit#8&9 The UPS Battery Set at CMRH (Outdoor Area), 69AH Capacity (1.2 V X 280 Cells) Ni Cd type Make- HBL for Unit#8&9 Retrofitting of 415V GE make ACB of various ratings along with allied spares. BHEL make Breakers and spares for 6.6 kV and 11kV panels | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Design, engineering, manufacturing, testing, unloading at site, E&C of 80 MVA, 420/11/6.9 KV three Phase Station Transformer & 25MVA 21/6.9KV Three phase Unit Aux Transformer as a common pool spares for BTPS 500MW, Khaparkheda 500 MW and Unit-8&9, CSTPS, Chandrapur & Supply, installation, commissioning and testing of Station Batteries of Unit-8&9 CSTPS alongwith all outdoor batteries | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, engineering, manufacturing, testing, unloading at site, E&C of 80 MVA, 420/11/6.9 KV three Phase Station Transformer & 25MVA 21/6.9KV Three phase Unit Aux Transformer as a common pool spares for BTPS 500MW, Khaparkheda 500 MW and Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, installation, commissioning and testing of Station Batteries of Unit-8&9 CSTPS alongwith all outdoor batteries | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| I&C -III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Upgradation of Analysis & Diagnostics system (A&D) for VMS and TSI system at Unit-8&9, CSTPS, Chandrapur.& other schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of Analysis & Diagnostics system (A&D) for VMS and TSI system at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Installation of CO analysers at Eco outlet at Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Complete Engineering Retrofitting of Existing 196 NT Controller by DT 9 Controller alongwith HMI units for Unit 8/9 coal feeder system. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of spares for LP bypass system. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of spares for maxDNA DCS system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Upgradation of HMI and hardware of GE make PLCs installed at Unit-8&9, CSTPS, Chandrapur. & other schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of HMI and hardware of GE make PLCs installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of TD-BFP Turbovisory system installed at Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of EWLI system installed at Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of O2 analysers installed at Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Installation of High temperature Camera system at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of HEA igniter system at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of Flue Gas Analysers and Opacity Analysers at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-8, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-8, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Multiple schemes C&I-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Total Mercury (Gaseous) Analyzers along with their online data connectivity & Remote calibration U-3 to 9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Controllers & Com Boxes for Air Compressors of Unit-8&9. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of Steam and Water Analysis System (SWAS) for Unit – 8 & 9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of Servo valve (ST) with proportional valves (PV) for HP bypass system at Unit – 8 & 9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of GEHO pump VFD panels for Unit – 8 & 9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Upgradation of measurement and control system installed at CSTPS Unit 8&9 & Upgradation of Numerical Protection Relay of Alstom / Schnieder make installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of measurement and control system installed at CSTPS Unit 8&9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of Numerical Protection Relay of Alstom / Schnieder make installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| AHP-III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | supply of piston cylinder assembly, diaphragm assembly, Suction and discharge valve housing assembly of GEHO pump (Model- TZPM 1200). & other schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-1 :supply of piston cylinder assembly, diaphragm assembly, Suction and discharge valve housing assembly of GEHO pump (Model- TZPM 1200). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme -2 :Procurement of sub assemblies for conveying air compressor model ZR 275 and instrument air compressor model ZR 110 in Ash handling plant Unit-8&9 (2x500MW) at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme -3 Supply of 10/8 FAH Warman make slurry pump impeller element assembly, Bearing assembly unit, jacket assembly. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply and replacement of 400 NB MSERW pipeline of ash disposal system of unit 8&9 at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 :Supply and replacement of 400 NB MSERW pipeline of ash disposal system of unit 8&9 at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Complete ESP Refurbishment of 1st & 2 nd Row Field of Unit 8&9 at CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 : Complete ESP Refurbishment of 1st & 2 nd Row Field of Unit 8&9 at CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP - D | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Upgradation Of Hydraulic Systems with Safety Mechanism for wagon unloading system at CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply erection & commissioning of wagon tippler, Side Arm Charger, apron feeder and stacker hydraulic drive system with online NAS value monitoring systems. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Wagon stopping mechanism (Safety) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgardation and Capacity Enhancement of Side Arm Charger Apron Feeder and Bunker Conveyors at CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | capacity enhancement to 60 wagons pulling capacity and associated modification of existing side arm charger | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Capacity enhancement , Commissionng of apron feeder drive | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Modification and revamping of Apron Feeder 101,102,103 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply,Installation and Commissioning of double drive Mechanism with Split Case Bearings for Tripper Trolley and bunkering conevyor belts of CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Modification of Fixed Tripper Head Pulley(Z-Point) of BC110A&B at CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Modification, Errection & Commissioning of drive unit capacity enhancement for conveyor at CHP-D, Chandrapur TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Performance Improvement Schemes of CHP-D CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design engineering , supply and installation of modular chutes with weld cast Liners ,flap gates and actuators. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply erection & commissioning of set of internal of spares of Wagon tippler and Side Arm Charger installed at CHP-D, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply erection & commissioning of set of internal of spares of stacker reclaimer installed at CHP-D, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply erection & commissioning of set of internal of spares of Impact crusher installed at CHP-D, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply erection & commissioning of set of internal of spares of wobbler feeder installed at CHP-D, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply erection & commissioning of 1500 TPH capacity Stacker Recliamer sleeving bearing with fastener of CHP-D (U8&9), CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of Gearbox assemblies at CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Structure Strengthening,Modification works of Conveyors at CHP-D CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Design, Installation, testing and commissioning of new conveyor systems of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Installation, testing and commissioning of conveyor system from crusher house to TP-108 of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Engineering, erection and commissioning of one 1500TPH crusher, short conveyors from TP 106 and open space of near Stack yard A pile to Crusher inlet and a telescopic conveyor at the output of crusher to Stack Yard B pile of CHPD Unit 8&9, CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design, Installation and commissioning of conveyor system from rope way of CHP-A to crusher house of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Installation and commissioning of conveyor system from rope way of CHP-A to crusher house of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Infrastructure Development Schemes at CHP-D CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Supply,Installation and Commissioning of EOT Cranes at Wagon Tippler area of CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Belt Tracking systems for Carrying/Return 1400/1600 mm belt width | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Ceramic Lagging by direct bonding on Conveyor Pulleys without Rubber Pad/Rubber Sheets. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Rewamping of crane and hoist of CHP, Unit 8&9, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Material lifting mechanism at Crusher, bunker and Tunnel area of CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping, modification of TunnelAir ventilation system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping, modification of DE and DS system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping, modification of Dewatering and water recirculation system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of New Office Building with Infrastructure ,Interior Development at CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Material Storage Shed Fabrication work at CHP-D CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Electrical schemes for improvement in availability & Reliability of CHP-D,CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design supply installation and commisioning of LED based energy efficient system for illumination at CHPD | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Erection, Commissioning and Testing of 7.2KV SF6 HT Contactor for retrofitting of existing BHEL make Vacuum Circuit Breakers of CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of GE make 90-30 series PLC system installed at stacker rclaimer and wagon tippler at CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Installation of energy efficient air temperature controlling system at various MCC rooms of CHPD, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Alterration, upgradation of tunnel ventilation system of CHPD, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Fabrication, Erection & commissioning of cable support structure along with re-routing & trial of auxiliaries at Crusher PMCC, compressor house & short conveyor area at CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and installation of LT air circuit breakes at CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, supply, installation & commissioning of solar based energy efficient illumination system at CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of HT motors for various auxiliaries at CHP-D, CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & installation of high capacity submersible slurry pump at CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reconditioning of MCC Board feeder panels at CHP-D,U #8&9.CSTPS,Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & installation of anoodized winding magnets along with control panels for installation at various conveyor belts of CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of 69 AH HBL make battery set of CHP-D (U8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of 100 AH Exide make battery banks (2 Set/ 110 Nos battery cells) & battery charge at CHP-D (U8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Alterration, upgradation of tunnel ventilation system of CHPD, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of HT/LT Xmers assy of CHP-D (U8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of HT/LT Xmers assy of CHP-D (U8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | WTP-III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Engineering, installation and commissioning of DM stream capacity of 4800M3/Day for U # 8 & 9 in addition to existing DM stream at WTP, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Engineering, installation and commissioning of DM stream capacity of 4800M3/Day for U # 8 & 9 in addition to existing DM stream at WTP, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Civil - 8&9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work of diversion of peripheral nallah towards ash water recovery pump house alogwith construction of waste wear at ash bund area CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Work of diversion of peripheral nallah towards ash water recovery pump house alogwith construction of waste wear at ash bund area CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Infrastructure development of CHP-D area at U-8, 9, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of platform for unloading of coal near TP-106 upto stack pile A of CHP-D | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of WBM Road for fire fighting arrangement at CHP-D U-8,9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction & Pushing RCC box of size 2mx2m under railway track to drain out the surface water near Rly - A cabin Unit-8,9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of concrete pavement road connecting to reject gate & vinchoda chowk , Y point to ash recovery pump house | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO1 | CHP Improvement Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at CHP-D | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO2 | Developlment & Upgradation of DSM software system for MSPGCL | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Developlment & Upgradation of DSM software system for MSPGCL | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Implementation of Flexible Operation Solutions | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Flexible Operation Solutions | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 |  | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | General asset | 0 | - | 0 | 1.87 | 1.87 | 0 | 0.83962 | 0.83962 |  |  | 0.83962 | 0
2 | Supply, Operation & Maintenance of Mobile Coal Sampling Equipment (MCSE) for coal sampling at loading ends of WCL for Mahagenco | 0 | - | 0 | 0 | 0 | 0 | 3.1648 | 3.1648 |  |  | 3.1648 | 0
3 | ABC Powder Type and Foam Type Composite Fire Extinguisher | 0 | - | 0 | 0 | 0 | 0 | 1.528 | 1.528 |  |  | 1.528 | 0
4 | NON-Detailed Project Report for the Work of Upgradation/Renovation of Crusher House of CHPB of Unit-5, 6&7 at CSTPS Chandrapur (benefit U-8,9 by short conveyor coal stacking in catering emergency) | 0 | - | 0 | 1.4404 | 0 | 1.4404 | 1.4404 | 2.8807 |  |  | 2.8807 | 0
5 | Extention of stacker reclaimer area for improvement in coal stack management at CHP-D CSTPS Chandrapur U-8,9 | 0 | - | 0 | 3.9102 | 0 | 3.9102 | 4.1828 | 0 |  |  | 0 | 8.093
6 | Retrofitting of BHEL make HT Circuit Breaker with SF6 Contactor at CHP-D, Unit-8&9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 405.5782 | 438.6928 | -33.1145 | 74.7693 | 85.3855 | 0 | 0 | 85.3855 | -43.7308
FY 2024-25
A) Approved Add Cap (Case No. 296 of 2019)
1 | Initial Spares | Approved Add Cap (Case No. 296 of 2019)
| Boiler & Auxiliaries | 0 | - | 10.36 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Bevel Helical Gear box KMP-350 for XRP 1043 coal mills at unit-8&9,CSTPS, Chandrapur. | 0 | - | 0 | 7.4087 | 7.4087 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Hydraulic Adjustment (Actuating) Device for PA fan model PAF 19/10.6-2 and FD fan FAF 23/12.5-1 at Unit 8&9, CSTPS, Chandrapur. | 0 | - | 0 | 1.3971 | 1.3971 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Yokogawa make Zirconia Oxygen Analyser spares for C&I-III, Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 0.51933 | 0.51933 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of High pressure valves installed at unit-8&9 ( 2x500 MW),CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Turbine & Aux | 0 | - | 1.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of IMI Norgren Herion make Trip solenoid valves for Main Turbine, MD-BFP & TD-BFP of Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.37354 | 0.37354 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Speed Sensors for 500 MW KWU Turbine for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.038232 | 0.038232 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Position Feedback Transmitters for Starting Device and Speeder Gear of Main Turbine for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.11225 | 0.11225 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for LP bypass system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur on OEM Basis. | 0 | - | 0 | 0.43645 | 0.43645 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of TSE (Turbine Stress Evaluator) temperature elements for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.2073 | 0.20719 | 0.00010699 | 0 | 0 |  |  | 0 | 0.00010699
| Generator and Auxiliries | 0 | - | 0.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of complete set of water cooled bushing for 500MW Generator installed at Unit-8 & 9, CSTPS Chandrapur. | 0 | - | 0 | 0.26409 | 0.26409 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Tushaco make complete AC Jacking Oil Pump for Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.19949 | 0.19949 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of oil filled Neutral Grounding Transformer for AHP Unit-8&9 CSTPS , Chandrapur. | 0 | - | 0 | 0.34775 | 0.34775 | 0 | 0 | 0 |  |  | 0 | 0
| Electrical and Instrumentation | 0 | - | 29.23 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| ‘Procurement of various spares of BHEL make Vacuum Circuit Breakers’ , for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.49498 | 0.49498 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, erection and commissioning of floor mounted 500KW Resistor Load Bank for D.G. sets installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.27536 | 0.27536 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Turbosupervisory system spares of main turbine for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 1.0366 | 1.0366 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Level transmitters for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.15999 | 0.15999 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Level transmitters for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.018125 | 0.018125 | 0 | 0.01448 | 0.01448 |  |  | 0.01448 | 0
| Procurement of Level transmitters for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.046973 | 0.046973 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of GE PLC spares for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.57304 | 0.57304 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for GEHO pumps PLC control panels for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.084378 | 0.084378 | 2.6e-08 | 0 | 0 |  |  | 0 | 2.6e-08
| Procurement of master calibration lab Instruments for C&I-III, Unit 8 & 9,CSTPS,Chandrapur | 0 | - | 0 | 0.30131 | 0.30131 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Coal Feeder panel spares for C&I-III, Unit 8 & 9,CSTPS, Chandrapur | 0 | - | 0 | 0.58701 | 0.58701 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Opacity Monitor (Stack Particulate matter-SPM) spares for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.14051 | 0.14051 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Forbes Marshall Supervisory system spares For Turbine driven boiler feed pumps (TDBFP) of Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.22449 | 0.22449 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for hydraulic panel of CW pumps for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.13862 | 0.1386 | 1.7196e-05 | 0 | 0 |  |  | 0 | 1.7196e-05
| Procurement of H2 Dew point analyzer spares for Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.049938 | 0.049938 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for HP bypass system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.33965 | 0.33965 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Position feedback transmitter for HP bypass system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.0354 | 0.0354 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Atlas Copco make Instrument, Service and Conveying air Compressors for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.22509 | 0.22509 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for HEA Ignitors and Flame Scanners for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.037701 | 0.037701 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for GEHO pumps of Ash Handling System at C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.28861 | 0.28861 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Turbine side control valve spares for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.17974 | 0.17974 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various numerical protection relays for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.12307 | 0.12307 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various numerical protection relays for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.13184 | 0.13184 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various numerical protection relays for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.13863 | 0.13863 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for DB POWER make UPS system installed at HCSD Pump House, Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.064757 | 0.064757 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Fully Automatic Capacitance & Dissipation Factor (Tan- Delta) measuring kit for Unit-8 &9, CSTPS, Chandrapur. | 0 | - | 0 | 0.48288 | 0.48288 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of various VFD spares for ID fans of Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.45626 | 0.45626 | 0 | 0.08974 | 0.08974 |  |  | 0.08974 | 0
| Procurement of DAVR spares installed at Unit -8&9 CSTPS, Chandrapur. | 0 | - | 0 | 0.57179 | 0.57179 | 0 | 0.02271 | 0.02271 |  |  | 0.02271 | 0
| Procurement of 3 phase relay test kit for Unit-8 &9, CSTPS, Chandrapur. | 0 | - | 0 | 0.35388 | 0.35388 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Fast Bus Transfer System (FBTS) installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.37288 | 0.37288 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various spares for battery chargers installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.40022 | 0.40022 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Auto synchronizing Relay (ASR) & Load Shedding Relay (LSR) installed at Unit-8 &9, CSTPS, Chandrapur. | 0 | - | 0 | 0.34973 | 0.34973 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ESP spares i.e. Field Controller, Thyristor and Trigger card for ESP of Unit-8 & 9, CSTPS Chandrapur. | 0 | - | 0 | 0.26745 | 0.26745 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various VFD spares for GEHO pump of Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.54416 | 0.54416 | 0 | 0 | 0 |  |  | 0 | 0
| Design, Supply, Erection & Commissioning of On-Line Dissolved Gas Analyzers for various Transformers installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 3.1775 | 3.1775 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, Erection & Commissioning of On-Line Dissolved Gas Analyzers for Station Transformers -8B, Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.30519 | 0.30519 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘TOROSHIMA’ make 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motor (without pump casing) for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 4.2037 | 4.2037 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 90kVA ESP Rectiformer for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.29878 | 0.29878 | 0 | 0 | 0 |  |  | 0 | 0
| Supply erection & commissioning of Aviation Lighting for NDCT of Unit-8&9, CSTPS Chandrapur | 0 | - | 0 | 0.57261 | 0.57261 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Transformer oil storage tanks of different capacity for Unit-8&9 CSTPS Chandrapur. | 0 | - | 0 | 0.57024 | 0.57024 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 2000kW & 315kW, 6.6 kV HT motors for CW & ACW Pump installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 1.4505 | 1.4505 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 3.25MVA, 6.6/2.3kV VFD Transformers of vector group DY11 for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0.3941 | 0.3941 |  |  | 0.3941 | 0
| Procurement of 3.25MVA, 6.6/2.3kV VFD Transformer of vector group ‘Dd0’ for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0.3905 | 0.3905 |  |  | 0.3905 | 0
| Procurement of ‘MARATHON’ makes HT/LT Induction motors for various Critical auxiliaries installed at Unit-8 &9, CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of 1.2V, Ni-Cd battery cells for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.12496 | 0.12496 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of 1.2V, Ni-Cd battery cells for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.18931 | 0.18931 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘Air Core DC Reactor’ for VFD and ‘NGR’ for UAT/ Station Transformers installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.44368 | 0.44368 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘Air Core DC Reactor’ for VFD and ‘NGR’ for UAT/ Station Transformers installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.12551 | 0.12551 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘BHEL’ make 680 KW, 6.6KV, Coal Mill Motor for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.37913 | 0.37913 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 400kV OIP Condenser Bushing for Generator Transformer & Station Transformer of Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.49064 | 0.49064 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘11kW DC motor with Control Cabinet’ for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0.2242 | 0.2242 |  |  | 0.2242 | 0
| Procurement of 37kW, 415V motors for Primary Water Pump installed at Unit-8 &9, CSTPS Chandrapur. | 0 | - | 0 | 0.0096851 | 0.0096851 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 15 KW, 415V LT Motor for Service Building & TG Building Lift installed at Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.095155 | 0.095155 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 16KW, 415V LT Motor for Boiler Lift installed at Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.044179 | 0.044179 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, Erection, Testing and Commissioning of Hydrastep-Electronic Drum Level Indicator and its associated accessories for Unit-9, CSTPS, Chandrapur | 0 | - | 0 | 0.27376 | 0.27376 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for BHEL make Hydrastep (Electronic Water Level Indicator -BHELVISION 20M) for Unit 8 & 9, CSTPS, Chandrapur on OEM basis. | 0 | - | 0 | 0.084172 | 0.084172 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Electrodes for Hydrastep (Electronic Water Level Indicator -BHELVISION 20M) for Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.10384 | 0.10384 | 0 | 0 | 0 |  |  | 0 | 0
| Engineering & Retrofitting of 196 NT Controller to DT 9 Controller for Unit-8 & 9 Coal Feeder System. | 0 | - | 0 | 0.38076 | 0.38076 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for BHEL make Acoustic steam leak detection system (BHELSONIC) (BS10) for Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.077807 | 0.077807 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of LT Circuit Breaker assemblies for ESP LT Panels (LTMSB & ACP) of Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.25429 | 0.25429 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for BHEL make maxDNA Distributed control system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 1.117 | 1.117 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of Transformer oil BDV test kit DTA 100C and Oil Tan Delta & Resistivity Tester DTL C at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.47598 | 0.47598 | 0 | 0 | 0 |  |  | 0 | 0
| Outdoor Plant ( CHP/AHP/WTP) | 0 | - | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Elecon make KCN-560 type Gearbox for Apron Feeder installed at CHPD, CSTPS. | 0 | - | 0 | 1.6717 | 1.6717 | -6e-08 | 0 | 0 |  |  | 0 | -6e-08
| Procurement of spares of CKB-280,225,200,8180 typ gearbox installed at CHP-D | 0 | - | 0 | 1.0015 | 1.0015 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Gear Box (MAKE: NEW ALLENBERRY) Spares at CHP-D; CSTPS, Chandrapur. | 0 | - | 0 | 0.5177 | 0.5177 | 1.8e-08 | 0 | 0 |  |  | 0 | 1.8e-08
| Procurement of spares for m/s Elecon make Impact Crusher installed at CHP Unit 8&9 CSTPS, Chandrapur | 0 | - | 0 | 0.84103 | 0.84103 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of V belt pulley of rotor for Impact crusher installed at CHP-D, CSTPS | 0 | - | 0 | 0.11864 | 0.11864 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Spares for hydraulic systems installed at CHPD, CSTPS. | 0 | - | 0 | 0.47537 | 0.47537 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Spares for hydraulic systems installed at CHPD, CSTPS. | 0 | - | 0 | 0.028604 | 0.028604 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of drive & non drive pulley for various conveyors installed at CHP D, CSTPS, Chandrapur. | 0 | - | 0 | 0.25792 | 0.25792 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of drive & non drive pulley for various conveyors installed at CHP D, CSTPS, Chandrapur. | 0 | - | 0 | 0.0914 | 0.0914 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Chain links for apron feeder installed at CHP D, CSTPS, Chandrapur. | 0 | - | 0 | 0.40289 | 0.40289 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of internal spares for Elecon make PWD-18, PLB-25 & SCN-180 type Gearbox for Stacker Reclaimer & wobbler feeder installed at CHP D, CSTPS. | 0 | - | 0 | 0.52774 | 0.52774 | 3.1e-08 | 0 | 0 |  |  | 0 | 3.1e-08
| Supply of GE Make Switchgear Spares for GE Make LT Feeders | 0 | - | 0 | 0.12485 | 0.12485 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Fluidomat make scoop coupling installed at CHP–D, CSTPS, Chandrapur | 0 | - | 0 | 0.48355 | 0.48355 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Oil Filtering machine for hydraulic power packs installed at CHPD, CSTPS | 0 | - | 0 | 0.10592 | 0.10592 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of LT Motors at CHP-D (U#8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0.11302 | 0.11302 | 0 | 0 | 0 |  |  | 0 | 0
| Supply and Installation of Oil Cooled Suspended Anodized Winding Magnet & Control Panel at CHP, Unit 8&9, CSTPS, Chandrapur. | 0 | - | 0 | 2.2967 | 2.2967 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of LT power and control cable for CHP-D | 0 | - | 0 | 0.26256 | 0.26256 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of LT power and control cable for CHP-D | 0 | - | 0 | 0.022125 | 0.022125 | 0 | 0.025575 | 0.025575 |  |  | 0.025575 | 0
2 | Capital Spare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| HPT MODULE | 0 | - | 45.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of HP turbine Module along with breach nuts and pipe spool pieces (Type: H30-100-2) for Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 32.332 | 32.332 | 0 | 0 | 0 |  |  | 0 | 0
| LPT ROTOR | 0 | - | 40.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Fully Bladed & Dynamically Balanced LP Rotor (N30-2X10-2) for Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 29.03 | 29.03 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of set of Free Standing Moving Blades for LP Rotor (N30-2X10-2) for Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 4.5629 | 4.5629 | 0 | 0 | 0 |  |  | 0 | 0
| BFP CARTRIDGE ( 2NOS ) | 0 | - | 4.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of cartridge assembly for Boiler Feed Pump model FK-4E-36 (with Four S/H & 2 R/H spray branches) installed at 2X 500MW, CSTPS, Chandrapur. | 0 | - | 0 | 2.515 | 2.5149 | 6e-05 | 0 | 0 |  |  | 0 | 6e-05
| BCW PUMP | 0 | - | 3.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for ‘TOROSHIMA’ make 350KW BCW Pump-Motor installed at Unit-8 &9, CSTPS Chandrapur. | 0 | - | 0 | 1.3283 | 1.3283 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various spares for ‘TOROSHIMA’ make Boiler Circulating Water (BCW) pump-motor installed at Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 2.2326 | 2.2326 | 0 | 0 | 0 |  |  | 0 | 0
| 15 MVA DRY TYPE TRANSFORMER | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spare ‘Cast Resin Dry Type Transformers (CRTs)’ of different ratings for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 6.0213 | 6.0213 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of phase coil limb and spares of Cast Resin Dry Type Transformers of different ratings for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 7.9255 | 7.9255 | 0 | 0 | 0 |  |  | 0 | 0
| BTG+BOP& Other Works | 0 | - | 20.48 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Design, Supply & Installation, Testing & Commissioning of Public Addressing System for tunnels of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 1.1544 | 1.1544 | 0 | 0 | 0 |  |  | 0 | 0
| Work of upgradation, installation and extension of 220VDC control supply to various PMCC of CHPD, CSTPS, Chandrapur. | 0 | - | 0 | 0.68441 | 0.68441 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Apron Feeder in CHP Unit 8&9 (2x500) MW at CHP-D, CSTPS. | 0 | - | 0 | 2.3388 | 2.3388 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of spares for up gradation of rotary parts of travelling conveyor system installed at CHPD, CSTPS, Chandrapur. | 0 | - | 0 | 0.58939 | 0.58939 | 0 | 0 | 0 |  |  | 0 | 0
| The Work of Design, Engineering, Manufacturing, Supply, Erection & Commissioning of Short Conveyor belt from stack yard of CHP of Unit 5,6&7 to Belt Conveyor 104 A/B at CHP of Unit 8&9, CSTPS, Chandrapur | 0 | - | 0 | 5.164 | 5.164 | 0 | 0.51846 | 0.51846 |  |  | 0.51846 | 0
| Work of design, supply, erection, commissioning of overhead cable tray along with removal & re-routing of power and control cables at CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0.51324 | 0.51324 | 0 | 0 | 0 |  |  | 0 | 0
| Work of provision, modification, retrofitting and revamping of lighting system of transfers points, crusher house and bunker area of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 1.0105 | 1.0105 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for M/s. Weir Minerals make (GEHO pump Model TZPM-1200) for Ash Handling Plant Unit# 8 &9 CSTPS Chandrapur. AHP-III | 0 | - | 0 | 2.106 | 2.106 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Gear Box set of internal (MAKE: NEW ALLENBERRY) Spares at CHP-D; CSTPS, Chandrapur. | 0 | - | 0 | 1.6904 | 1.6904 | 0 | 0 | 0 |  |  | 0 | 0
| Supply and Installation of Oil Cooled Suspended Anodized Winding Magnet & Control Panel at CHP, Unit 8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 196 NT Controller by DT 9 Controller alongwith HMI units for Unit- 8&9 coal feeder system | 0 | - | 0 | 2.0774 | 2.0774 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of set of CW Impeller duly fitted with wear rings & ACW Impeller duly fitted with wear rings of Mather & Platt make Pumps installed at Unit-8 & 9,CSTPS,Chandrapur | 0 | - | 0 | 0.70379 | 0.70379 | 0 | 0 | 0 |  |  | 0 | 0
| CHP System U#8 | 0 | - | 0 | 0.05 | 0.05 | 0 | 0 | 0 |  |  | 0 | 0
| ISOLATED PHASE BUS DUCT | 0 | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| SEGREGATED PHASE BUS DUCT U#8 | 0 | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| SEGREGATED PHASE BUS DUCT U#9 | 0 | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| ISOLATED PHASE BUS DUCT U#9 | 0 | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| DTT & UAT U#8 | 0 | - | 0 | 0.03 | 0.03 | 0 | 0 | 0 |  |  | 0 | 0
| DTT & UAT U#9 | 0 | - | 0 | 0.03 | 0.03 | 0 | 0 | 0 |  |  | 0 | 0
| Cranes and hoists U#8 | 0 | - | 0 | 0.03 | 0.03 | 0 | 0 | 0 |  |  | 0 | 0
| RCC Chimney U#8 | 0 | - | 0 | 9.29 | 9.29 | 0 | 0 | 0 |  |  | 0 | 0
| Coal Handling Plant | 0 | - | 0 | 41.79 | 41.79 | 0 | 0 | 0 |  |  | 0 | 0
| Bunker foundation & civil works (Unit 8) U#8 | 0 | - | 0 | 18.58 | 18.58 | 0 | 0 | 0 |  |  | 0 | 0
| Boiler & Auxiliaries U#9 | 0 | - | 0 | 9.2889 | 9.2872 | 0.0017338 | 0 | 0 |  |  | 0 | 0.0017338
| ESP U#9 | 0 | - | 0 | 2.1589 | 2.1589 | 0 | 0 | 0 |  |  | 0 | 0
| ID fan foundations (Unit 9) U#9 | 0 | - | 0 | 1.7489 | 1.7489 | 0 | 0 | 0 |  |  | 0 | 0
| DRY ASH SILO-12M DIA U#8 | 0 | - | 0 | 1.22 | 1.22 | 0 | 0 | 0 |  |  | 0 | 0
| FD fan foundations (Unit 9) U#9 | 0 | - | 0 | 0.62891 | 0.62891 | 0 | 0 | 0 |  |  | 0 | 0
| PA fan foundations (Unit 9) U#9 | 0 | - | 0 | 0.54891 | 0.54891 | 0 | 0 | 0 |  |  | 0 | 0
| Natural Draft cooling tower- Unit 8 U#8 | 0 | - | 0 | 0.32 | 0.32 | 0 | 0 | 0 |  |  | 0 | 0
| Main power house building-Civil Works-Unit no.-9 U | 0 | - | 0 | 0.15 | 0.15 | 0 | 0 | 0 |  |  | 0 | 0
| Structural Steel works for main power house buildi | 0 | - | 0 | 0.15 | 0.15 | 0 | 0 | 0 |  |  | 0 | 0
| Canteen U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Security and time office U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| CARS SCOOTERS AND CYCLE SHED U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Fire Station U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Watch towers U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| First aid station | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Tranformer yard U#8 | 0 | - | 0 | 0.02 | 0.02 | 0 | 0 | 0 |  |  | 0 | 0
| Rain Water Harvesting Scheme U#8&9 | 0 | - | 0 | -0.01 | -0.01 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Advance Multipurpose Fire Tender | 0 | - | 0 | 3.45 | 3.45 | 0 | 0 | 0 |  |  | 0 | 0
| DM Stream | 0 | - | 29.65 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| DM Stream capacity of 100 M3/Hr in addition to existing stream of WTP. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| CIVIL | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Bridge | 0 | - | 4.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Railway, CHP, AHP etc | 0 | - | 152.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| B. G. railway siding Pway works | 0 | - | 0 | 41.5165 | 41.5165 | 0 | 0 | 0 |  |  | 0 | 0
| S & T work for B.G. railway siding | 0 | - | 0 | 0.023574 | 0.023574 | 0 | 0 | 0 |  |  | 0 | 0
| Consultancy services for B. G. railway siding | 0 | - | 0 | 0.035636 | 0.035636 | 0 | 0 | 0 |  |  | 0 | 0
| Ash infra in Railway | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Bunker structure (Unit 8) U#8 | 0 | - | 0 | 18.57 | 18.57 | 0 | 0 | 0 |  |  | 0 | 0
| Coal Mills | 0 | - | 0 | 1.1389 | 1.1389 | 0 | 0 | 0 |  |  | 0 | 0
| Bunker foundation & civil works (Unit 9) U#9 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Bunker structure (Unit 9) U#9 | 0 | - | 0 | 0.11 | 0.11 | 0 | 0 | 0 |  |  | 0 | 0
| HCSS silo-12m dia U#8 | 0 | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| Ash water PH, HCSD PH, Bottom ash slurry PH U#8 | 0 | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| Ash compressor house & Control room U#8 | 0 | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| MILL REJECT SILO U#8 | 0 | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| Fire protection & Detection system U#8 | 0 | - | 0 | 0.71423 | 0.71423 | 0 | 0 | 0 |  |  | 0 | 0
| DM Water Pump room U#8 | 0 | - | 0 | 4.25 | 0 | 4.25 | 0 | 0 |  |  | 0 | 4.25
| Filter water reservoir & pump house U#8 | 0 | - | 0 | 4.29 | 0 | 4.29 | 0 | 0 |  |  | 0 | 4.29
| ACW + RW + Filtered water piping U#8 | 0 | - | 0 | 2.2409 | -0.0096938 | 2.2506 | 0 | 0 |  |  | 0 | 2.2506
| Laboratory Building U#8 | 0 | - | 0 | 0.12 | 0 | 0.12 | 0 | 0 |  |  | 0 | 0.12
3 | Staff quarters | 0 | - | 15.04 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Work of exterior repair, providing painting to A, D & E type residential buildings and Public Buildings and allied civil works in Urjanagar Colony, CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Staff Quarters- Repair and renovation of E type staff quarters to extend the life of buildings at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Staff Quarters - Repair and renovation of 'B' type staff quarters in residential colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair of D type quarters in colony at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair of C type quarters in colony at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Staff Quarters- Repair and renovation of F and NF type staff quarters to extend the life of buildings at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair and replacement of existing drinking water supply pipelines in E & F type area in colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair and replacement of existing sewer lines in E & F type area in colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Work of providing RCC drain along main roads in colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Rerouting and replacement of domestic water supply pipeline from WTP to ESR in colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Additional Contengencies approved vide e BR No. MSPGCL/BM-162/165, Dt.29.10.2016 vide resolution no. 2016/2085 | 0 | - | 7.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Landscaping and plantation work at various locations inside plant area at CSTPS, chandrapur. | 0 | - | 0 | 3.4266 | 3.4266 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of WBM approach road from point- N to Z Area along ash bund periphery at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design, Engineering, Supply and commissioning of ash-bund water recovery system (Phase II) at CSTPS Chandrapur | 0 | - | 27.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, Engineering, Supply and commissioning of ash-bund water recovery system (Phase II) at CSTPS Chandrapur | 0 | - | 0 | 30.0361 | 30.0361 | 0 | 0 | 0 |  |  | 0 | 0
| Providing Consultancy Services for work of Design, Engineering, Supply, Installation & Commissioning of ash bund water recovery system (Phase-II) at CSTPS, Chandrapur (on EPC contract basis). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Providing laying, jointing and commissioning of 1600 mm dia. M.S. Pipe line from Erai dam to one day reservoir of stage II, III & IV at CTPS | 0 | - | 73.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Providing laying, jointing and commissioning of 1600 mm dia. M.S. Pipe line from Erai dam to one day reservoir of stage II, III & IV at CTPS | 0 | - | 0 | 70.5091 | 70.3626 | 0.1465 | 3.1 | 3.2465 |  |  | 3.2465 | 5.7732e-15
| Work of construction of Control Valve rooms on newly laid 1600 mm M.S. Pipeline no. 6 from Erai dam to One day reservoir at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Providing OHE facility for BG Rly siding of proposed Expansion Project at Chandrapur, for Supply of Materials. | 0 | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Providing OHE facility for BG Rly siding of proposed Expansion Project at Chandrapur, for errection of OHE Items. | 0 | - | 2.5 | 0.7 | 0 | 0.7 | 0 | 0 |  |  | 0 | 0.7
9 | Irrigation scheme for landscaping and Plantation work at Chandrapur expansion project chandrapur. | 0 | - | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Asphalting of WBM road from Nagpur gate to Awanda gate. | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Asphalting of WBM road from Nagpur gate to Awanda gate. | 0 | - | 0 | 0.65141 | 0 | 0.65141 | 0 | 0 |  |  | 0 | 0.65141
| Asphalting over WBM Road of ADP line Service road from Nagpur gate opening to Awandha junction gate at CSTPS Chandrapur | 0 | - | 0 | 0.84833 | 0.84833 | 0 | 0 | 0 |  |  | 0 | 0
| Asphalting of WBM road from Nagpur gate to Awandha gate at CSTPS Chandrapur - Asphalting of road from Reject coal gate to Motghat nallah at CSTPS Chandrapur (PHASE - I) | 0 | - | 0 | 0.47941 | 0.47941 | 0 | 0 | 0 |  |  | 0 | 0
11 | Foot Over Bridge | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Work of Providing retaining wall for sand hump at Vivekanand nagar station yard under modification work in wardha end fro 2 x 500 MW Expn. Project at CSTPS, Chandrapur. | 0 | - | 0.3 | 0.25515 | 0.25515 | 0 | 0 | 0 |  |  | 0 | 0
| Additional Capitalization by O & M | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of GE make 4000Amp LT Air Circuit Breakers for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0.9 | 1.0308 | 1.0308 | 0 | 0 | 0 |  |  | 0 | 0
2 | Air Compressor System | 0 | - | 0.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Energy management Sysytem | 0 | - | 0.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, Installation, Testing & Commissioning of Energy Management System for Unit#8 & 9 for CSTPS, Chandrapur. | 0 | - | 0 | 0.20054 | 0.20054 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Tri-vector 0.2s class Digital Energy meter for Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.094872 | 0.094872 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, Installation & Commissioning of 3D Level Scanners to 64 nos. of ESP hoppers at Unit-8&9 (2X500MW), CSTPS, Chandrapur. | 0 | - | 3.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of internal spares for Elecon make PWD-18, PLB-25 ,Pbh-71 type Gearbox for Stacker Reclaimer installed at CHPD, CSTPS. | 0 | - | 0 | 1.1089 | 1.1089 | 0 | 0 | 0 |  |  | 0 | 0
5 | 4000/2500/1800/800 A GE make LT CKT Brkr | 0 | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| LT Air Circuit Breakers for Incomer Feeders at CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 1.4207 | 1.4207 | 0 | 0 | 0 |  |  | 0 | 0
| LT Air Circuit Breakers at CHP, Unit 8&9, CSTPS | 0 | - | 0 | 1.0141 | 1.0141 | 0 | 0 | 0 |  |  | 0 | 0
6 | Replacement of Impact crusher by hammer mill crusher (installed qty.2 No) | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Replacement of wobbler feeder 1&2 by grizzly screen at CHP-D | 0 | - | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Installation of conveyor system from rope way of CHP-A and crusher house of CHP-D | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| PLC based control & instrumentation of 6.6 KV HT motors of 1250 KW of Crusher I & II and 200 KW of BC 108A1 & A2 at CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0.93628 | 0.93628 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Design, Supply, Erection & Commissioning of Complete Electrical Automation for Short Conveyor from stack yard of CHP-D to Belt Conveyor 107 A/B of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0.70095 | 0.70095 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Design, Supply, Erection & Commissioning of Complete Electrical Automation for Short Conveyor from stack yard of CHP-B to Belt Conveyor 104 A/B of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 2.2368 | 2.2368 | 0 | 0 | 0 |  |  | 0 | 0
| WORK OF DESIGN, ENGINEERING, MANUFACTURING, SUPPLY, ERECTION &COMMISSIONING OF SHORT CONVEYOR BELT FROM STACK YARD OF CHP UNIT-8&9 TO CONVEYOR BELT 107A AND B AT CHP UNIT 8&9, CSTPS, CHANDRAPUR. | 0 | - | 0 | 4.6948 | 4.6948 | -2.4e-08 | 0 | 0 |  |  | 0 | -2.4e-08
| Design, Supply, Installation and Commissioning of High Performance Energy Chain System for Side Arm Charger and Stacker Reclaimer of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 3.8916 | 3.8916 | 0 | 0 | 0 |  |  | 0 | 0
| RBF 103 &104,105 & 106, 107 & 108, and 109 & 110 in to modular Y chute | 0 | - | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-103 & RBF-104 with Design, development, Manufacturing, Supply & erection of modular Chute as per site condition in place of RBF using sintered silicon Carbide plate with motorized Flap Gate at CHP-D, CSTPS. | 0 | - | 0 | 1.1741 | 1.1741 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-105 & RBF-106 with Design, development, Manufacturing, Supply & erection of modular Chute as per site condition in place of RBF using sintered silicon Carbide plate with motorized Flap Gate at CHP-D, CSTPS. | 0 | - | 0 | 1.3169 | 1.3169 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-107 & RBF-108 with Design, development, Manufacturing, Supply & erection of modular Chute as per site condition in place of RBF using Tungsten Carbide plate with Flap Gate at CHP-D, CSTPS. | 0 | - | 0 | 1.1529 | 1.1529 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-109 & RBF-110 with design, erection & Installation by trajectory calculation & removal of existing RBF with Y Chute assembly by flow control with Flap Gate arrangement at TP-107 of CHP-D, CSTPS. | 0 | - | 0 | 1.1506 | 1.1506 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurment , Installation and commissioning of Online Insertable Camera systems for Unit-8, 500MW, CSTPS | 0 | - | 8.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, Supply, Installation & Commissioning of Energy efficient system for Illumination at Unit 8&9 CSTPS, Chandrapur. | 0 | - | 0 | 4.9494 | 4.9494 | 0 | 0 | 0 |  |  | 0 | 0
11 | Construction of Chemical godown shed for unit 8 & 9 at CSTPS,Chandrapur. | 0 | - | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of Chemical godown shed for unit 8 & 9 at CSTPS,Chandrapur. | 0 | - | 0 | 0.42946 | 0.42946 | 0 | 0 | 0 |  |  | 0 | 0
| Comprehencive work of installation, erection, testing and commissioning of MVWS spray system/ Fire safety system for new Bulk Chemical storage godown at CSTPS, Unit 8&9 | 0 | - | 0 | 0.27583 | 0.27583 | 0 | 0 | 0 |  |  | 0 | 0
| Work of electrification of godown for bulk chemical storage near FOPH building at Chandrapur project site. | 0 | - | 0 | 0.018322 | 0.018322 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of additional Chemical godown shed for storage of Lube oil at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Construction of RCC retaining wall for approach to RCC Bridge across Irai River, ADPL line at CSTPS | 0 | - | 8.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of RCC retaining wall for approach to RCC Bridge across Irai River, ADPL line at CSTPS | 0 | - | 0 | 4.0482 | 4.0482 | 0 | 0.3 | 0.3 |  |  | 0.3 | 0
| Asphalting of road from Reject coal gate to Motghat nallah at CSTPS Chandrapur (PHASE - II) | 0 | - | 0 | 0.87403 | 0.87403 | 0 | 0 | 0 |  |  | 0 | 0
| Providing extension to approaches of RCC bridge across Erai river by constructing WBM road at CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| UDL | 0 | - | 0 | 4.85 | 4.85 | 0 | 0 | 0 |  |  | 0 | 0
| B) DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (i) In Principally Approved By MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 1 | HMI (Human Machine Interface) Upgradation of ‘SSPA-T3000’ DCS (Distribution Control System), Rockwell make PLC System installed at 3x660MW Unit No. 8, 9 & 10 at Koradi TPS and HMI (Human Machine Interface) Upgradation of MaxDNA DCS System at Unit 8-9, CSTPS, Chandrapur | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 11.08 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 1.1 | Supply: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 10.52 | 0 | 10.5 | -10.5 | 10.52 | 10.52 |  |  | 10.52 | -10.5
HO DPR 1.2 | Works: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.41 | 0 | 0.4 | -0.4 | 0.41 | 0.41 |  |  | 0.41 | -0.4
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
40 | Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M with construction of concrete dam (Waste Weir & Non overflow structure), construction of drain wells, approach to drain wells and raising of ash compartment for ash bund along with renewal of Ash Disposal Pipe Line Service Road with WBM treatment at CSTPS, Chandrapur | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 4.9692 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 34.8665 | 0 | 34.8665 | -34.8665 | 34.8665 | 34.8665 |  |  | 34.8665 | -34.8665
| Construction of New Drain Wells (12 Nos.) along with necessary connection to existing drain wells at CSTPS | 0 | - | 0.58493 | 0 | 0.58493 | -0.58493 | 0.58493 | 0.58493 |  |  | 0.58493 | -0.58493
| Construction of waste weir for raising of ash bund (Waste Weir & Non overflow structure) | 0 | - | 1.4621 | 0 | 1.4621 | -1.4621 | 1.4621 | 1.4621 |  |  | 1.4621 | -1.4621
| Raising of Ash Compartment i.e. Lagoon in Ash Bund | 0 | - | 8.7868 | 0 | 8.7868 | -8.7868 | 8.7868 | 8.7868 |  |  | 8.7868 | -8.7868
| IDC | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 7.634 | 0 | 7.634 | -7.634 | 7.634 | 7.634 |  |  | 7.634 | -7.634
| IDC | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 4.9692 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
39 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 8-9) | MERC/CAPEX/2020-2021/WFH/SBR/21 | 2020-07-24 | 479.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
39.1 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 8-9) | MERC/CAPEX/2020-2021/WFH/SBR/21 | 2020-07-24 | 440.54 | 0 | 0 | 0 | 119.66 | 119.66 |  |  | 119.66 | 0 | 119.66 | 0
| IDC | MERC/CAPEX/2020-2021/WFH/SBR/21 | 2020-07-24 | 38.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41 | CHP Performance Improvement Schemes at Unit 8-9 of CSTPS, Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 26.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.1 | Work of Design engineering , supply and installation of modular chutes with sintered silicon carbide for smooth flow &center feeding in CHP 2x500MW CSTPS | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 9.43 | 0 | 0 | 0 | 4.715 | 4.715 |  |  | 4.715 | 0 | 4.715 | 0
41.2 | Supply erection & commissioning of set of internal of impact crusher spares installed at CHPP-D, CSTPS | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 8.05 | 0 | 0 | 0 | 4.025 | 4.025 |  |  | 4.025 | 0 | 4.025 | 0
41.3 | Scheme for replacement of Scoop coupling/Fluid coupling of conveyor BC-101A/B/C, BC-102A/B, BC-104A/B, BC-105A/B ,BC-106A/B, BC-111A/B/C/D, BC-110A1/B1, BC-110A/B Installed at CHP-D, CSTPS Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 4.67 | 0 | 0 | 0 | 2.335 | 2.335 |  |  | 2.335 | 0 | 2.335 | 0
41.4 | Supply erection & commissioning of set of internal of spares of stacker reclaimer installed at CHP-D, CSTPS Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 1.96 | 0 | 0 | 0 | 0.98 | 0.98 |  |  | 0.98 | 0 | 0.98 | 0
41.5 | Supply erection & commissioning of set of internal of spares of Wagon tippler installed at CHP-D, CSTPS Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 2.12 | 0 | 0 | 0 | 1.06 | 1.06 |  |  | 1.06 | 0 | 1.06 | 0
| IDC | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 0.38 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 2 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 2.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
A6 | Supply, Installation & Commissioning of Online Coal Flow Monitoring & Balancing System at Unit-8-9, CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0457 Dt 26.07.2024 | 2024-07-26 | 34.21 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, installation and commissioning of Online Coal flow monitoring and balancing system for U- 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2024-2025/MSPGCL/0457 Dt 26.07.2024 | 2024-07-26 | 34.21 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0457 Dt 26.07.2024 | 2024-07-26 | 0.31 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
A7 | Providing, supplying, laying and commissioning of 1600 mm dia. M.S. Pipe by replacement of existing PSC raw water line from Erai dam to reservoir at CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 40.7945 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing, supplying, laying and commissioning of 1600mm dia. M.S. pipe by replacement of existing PSC raw water line from Erai dam to reservoir at CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 40.7945 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 8.83 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
A8 | Adoption of Ozonization technique for disinfection of Cooling Water System at U # 8 & 9 | MERC/CAPEX/MSPGCL/2023-2024/0467 Dt 02.08.2024 | 2024-08-02 | 67 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Adoption of Ozonization technique for disinfection of Unit 8&9 Cooling Water at CSTPS. | MERC/CAPEX/MSPGCL/2023-2024/0467 Dt 02.08.2024 | 2024-08-02 | 67 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-2024/0467 Dt 02.08.2024 | 2024-08-02 | 2.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (ii) Submitted to MERC |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y1 | Multiple Schemes for Electrical Maintenance Section and Design, Engineering, Manufacturing, Testing, Unloading at site, E&C of 200MVA, 21/420KV Single Phase Generator Transformer for Unit # 8 & 9, CSTPS | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 10MW, 11kV Motor and its recommended spare for Boiler Feed Pump (BFP) | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Replacement of NiCd battery sets installed for UPS of Fire Water Pump House, CMRH & SWAS lab of Unit 8 & 9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Retrofitting of GE make LT Air Circuit Breakers of various current ratings and procurement of their recommended spares for Unit-8&9, CSTPS | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of BHEL make 6.6kV and 11kV Vacuum Circuit Breakers for Unit-8&9, CSTPS Chandrapur | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y5 | Scheme-1: Procurement of assembly of baskets for Air Preheater of type 31.05 VIMT 2000 (72° PA), Scheme-2: Procurement of spares for PRDS station pressure control valves and Desuperheating spray Control valves in Boiler at U-8&9, CSTPS, Chandrapur, Scheme-3: Procurement of complete set of sky climber at U-8&9, CSTPS, Chandrapur. Scheme-4: Supply, erction, commissioning of oil free rotary screw compressors (including all Civil Electrical, C&I, Testing work) for CMRH system at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-1: Procurement of assembly of baskets for Air Preheater of type 31.5 VIMT 2000 (72° PA) at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-2: Procurement of spares for PRDS station pressure control valves and Desuperheating spray control valves in Boiler at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-3: Procurement of complete set of sky climber at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-4: Supply, erection, commissioning of oil free rotary screw compressors (including all Civil Electrical, C&I, Testing work) for CMRH system at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y6 &Y7 | Supply, Erection & commissioning/retrofitting of HT Circuit Breaker with SF6 Contactor at AHP at Unit-8&9 & CHP#D and Supply, Installation and Commissioning of MV VFD panel along with integrated online cell redundancy technology with VFD bypass feature arrangement for conveyors 103 A & B of CHP-B, C.S.T.P.S., Chandrapur & Design, engineering, manufacturing, testing, unloading at site, E&C of Two No of 200 MVA, 21/420 KV Single Phase Generator Transformers for Unit-8&9, CSTPS, Chandrapur. Through OEM | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme 1: Retrofitting of BHEL make HT Circuit Breaker with SF6 contactor at AHP, Unit#8&9, CSTPS. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme 2: Retrofitting of BHEL make HT Circuit Breaker with SF6 contactor at CHP#D, Unit#8&9, CSTPS. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme 3: Supply, Installation and Commissioning of MV VFD panel along with integrated online cell redundancy technology with VFD bypass feature arrangement for conveyors 103 A & B of CHP-B. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, engineering, manufacturing, testing, unloading at site, E&C of Two No of 200 MVA, 21/420 KV Single Phase Generator Transformers for Unit-8&9, CSTPS, Chandrapur. Through OEM | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (iii) Yet to be Submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Boiler Maintenance -III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of Air & Flue gas ducts of Boiler , Blade set and HAD for PA and FD Fan , SCAPH Coil, ID Fan spares at Unit-8&9 CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-1 Procurement of Air & flue gas expansion joints | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-2 :Procurement of Blade Set and 2 sets of HAD of PA Fan. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme -3 Procurement of Blade Set and 2 sets of HAD of FD Fan. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-4 Procurement of SCAPH Coil for unit- 8&9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-5 :Procurement of ID Fan Impeller , Shaft and Blade set at unit-8 & 9, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme 6: Procurment of Coal Fuel pipes for unit -8 &9 , CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of LTSH and economiser for unit-8&9 CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of LTSH Coil assemsblies unit- 8&9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of economiser coil asemblies | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of existing belt type gravimetric coal feeders to gravimetric rotary weigh coal feeders of unit- 8&9, at CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of Quick Erect Aluminum Boiler Scaffolding system or unit- 8 & 9, (2X500MW), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of Quick Erect Aluminum Boiler Scaffolding system or unit- 8 & 9, (2X500MW), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Turbine Maintenance -III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Schemes for Improvement in availability & performance of TG auxiliaries at U-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 1. Procurement of BFP Booster Pump assembly for Unit-8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 2. Procurement of Boiler Feed Pump catridge with CI sealing for Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 3. Procurement of Modulating type Boiler Feed Pump Recirculation valve (06 Nos) assembly for Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 4. Procurement of HP Heater HPH-5B assembly for Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 5. Procurement of MDBFP working oil & lube oil coolers for Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 6. Procurement of TDBFP Turbine rotor K1401-2 at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 7. Procurement of Main TG Jacking oil pumps (2 Nos.) at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 8. Procurement of HP elements of ZR500 Atlas Copco make compressors along with inter & after coolers tube nest at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 9. Procurement of CW & ACW Pump spares at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 10. Procurement of condenser tubes at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 11. Procurement of HPCF Pump at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | DPR for performance improvement of Condenser Cooling water system & improvement in system reliability of auxiliary cooling water system installed at Unit-8&9, 2x500MW, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| DPR for performance improvement of Condenser Cooling water system & improvement in system reliability of auxiliary cooling water system installed at Unit-8&9, 2x500MW, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of main turbine IPT module at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of main turbine IPT module at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Electrical Maintenance -III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Proc of GTR, MDBFP, UPS battery, breakers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, engineering, manufacturing, testing, unloading at site, E&C of 200 MVA, 21/420 KV Single Phase Generator Transformer for Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of MDBFP motor and recommended spares The Fire Water Pump House UPS Battery set of 240V, 40AH Capacity (1.2V X 176 Cells ) Ni Cd Type Make- HBL The UPS Battery Set at SWAS Lab (Outdoor Area), 45AH Capacity (1.2 V X 276 Cells) Ni Cd type Make- HBL for Unit#8&9 The UPS Battery Set at CMRH (Outdoor Area), 69AH Capacity (1.2 V X 280 Cells) Ni Cd type Make- HBL for Unit#8&9 Retrofitting of 415V GE make ACB of various ratings along with allied spares. BHEL make Breakers and spares for 6.6 kV and 11kV panels | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Design, engineering, manufacturing, testing, unloading at site, E&C of 80 MVA, 420/11/6.9 KV three Phase Station Transformer & 25MVA 21/6.9KV Three phase Unit Aux Transformer as a common pool spares for BTPS 500MW, Khaparkheda 500 MW and Unit-8&9, CSTPS, Chandrapur & Supply, installation, commissioning and testing of Station Batteries of Unit-8&9 CSTPS alongwith all outdoor batteries | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, engineering, manufacturing, testing, unloading at site, E&C of 80 MVA, 420/11/6.9 KV three Phase Station Transformer & 25MVA 21/6.9KV Three phase Unit Aux Transformer as a common pool spares for BTPS 500MW, Khaparkheda 500 MW and Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, installation, commissioning and testing of Station Batteries of Unit-8&9 CSTPS alongwith all outdoor batteries | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| I&C -III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Upgradation of Analysis & Diagnostics system (A&D) for VMS and TSI system at Unit-8&9, CSTPS, Chandrapur.& other schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of Analysis & Diagnostics system (A&D) for VMS and TSI system at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Installation of CO analysers at Eco outlet at Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Complete Engineering Retrofitting of Existing 196 NT Controller by DT 9 Controller alongwith HMI units for Unit 8/9 coal feeder system. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of spares for LP bypass system. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of spares for maxDNA DCS system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Upgradation of HMI and hardware of GE make PLCs installed at Unit-8&9, CSTPS, Chandrapur. & other schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of HMI and hardware of GE make PLCs installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of TD-BFP Turbovisory system installed at Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of EWLI system installed at Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of O2 analysers installed at Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Installation of High temperature Camera system at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of HEA igniter system at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of Flue Gas Analysers and Opacity Analysers at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-8, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-8, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Multiple schemes C&I-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Total Mercury (Gaseous) Analyzers along with their online data connectivity & Remote calibration U-3 to 9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Controllers & Com Boxes for Air Compressors of Unit-8&9. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of Steam and Water Analysis System (SWAS) for Unit – 8 & 9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of Servo valve (ST) with proportional valves (PV) for HP bypass system at Unit – 8 & 9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of GEHO pump VFD panels for Unit – 8 & 9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Upgradation of measurement and control system installed at CSTPS Unit 8&9 & Upgradation of Numerical Protection Relay of Alstom / Schnieder make installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of measurement and control system installed at CSTPS Unit 8&9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of Numerical Protection Relay of Alstom / Schnieder make installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| AHP-III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | supply of piston cylinder assembly, diaphragm assembly, Suction and discharge valve housing assembly of GEHO pump (Model- TZPM 1200). & other schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-1 :supply of piston cylinder assembly, diaphragm assembly, Suction and discharge valve housing assembly of GEHO pump (Model- TZPM 1200). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme -2 :Procurement of sub assemblies for conveying air compressor model ZR 275 and instrument air compressor model ZR 110 in Ash handling plant Unit-8&9 (2x500MW) at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme -3 Supply of 10/8 FAH Warman make slurry pump impeller element assembly, Bearing assembly unit, jacket assembly. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply and replacement of 400 NB MSERW pipeline of ash disposal system of unit 8&9 at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 :Supply and replacement of 400 NB MSERW pipeline of ash disposal system of unit 8&9 at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Complete ESP Refurbishment of 1st & 2 nd Row Field of Unit 8&9 at CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 : Complete ESP Refurbishment of 1st & 2 nd Row Field of Unit 8&9 at CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP - D | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Upgradation Of Hydraulic Systems with Safety Mechanism for wagon unloading system at CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply erection & commissioning of wagon tippler, Side Arm Charger, apron feeder and stacker hydraulic drive system with online NAS value monitoring systems. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Wagon stopping mechanism (Safety) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgardation and Capacity Enhancement of Side Arm Charger Apron Feeder and Bunker Conveyors at CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | capacity enhancement to 60 wagons pulling capacity and associated modification of existing side arm charger | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Capacity enhancement , Commissionng of apron feeder drive | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Modification and revamping of Apron Feeder 101,102,103 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply,Installation and Commissioning of double drive Mechanism with Split Case Bearings for Tripper Trolley and bunkering conevyor belts of CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Modification of Fixed Tripper Head Pulley(Z-Point) of BC110A&B at CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Modification, Errection & Commissioning of drive unit capacity enhancement for conveyor at CHP-D, Chandrapur TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Performance Improvement Schemes of CHP-D CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design engineering , supply and installation of modular chutes with weld cast Liners ,flap gates and actuators. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply erection & commissioning of set of internal of spares of Wagon tippler and Side Arm Charger installed at CHP-D, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply erection & commissioning of set of internal of spares of stacker reclaimer installed at CHP-D, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply erection & commissioning of set of internal of spares of Impact crusher installed at CHP-D, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply erection & commissioning of set of internal of spares of wobbler feeder installed at CHP-D, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply erection & commissioning of 1500 TPH capacity Stacker Recliamer sleeving bearing with fastener of CHP-D (U8&9), CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of Gearbox assemblies at CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Structure Strengthening,Modification works of Conveyors at CHP-D CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Design, Installation, testing and commissioning of new conveyor systems of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Installation, testing and commissioning of conveyor system from crusher house to TP-108 of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Engineering, erection and commissioning of one 1500TPH crusher, short conveyors from TP 106 and open space of near Stack yard A pile to Crusher inlet and a telescopic conveyor at the output of crusher to Stack Yard B pile of CHPD Unit 8&9, CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design, Installation and commissioning of conveyor system from rope way of CHP-A to crusher house of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Installation and commissioning of conveyor system from rope way of CHP-A to crusher house of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Infrastructure Development Schemes at CHP-D CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Supply,Installation and Commissioning of EOT Cranes at Wagon Tippler area of CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Belt Tracking systems for Carrying/Return 1400/1600 mm belt width | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Ceramic Lagging by direct bonding on Conveyor Pulleys without Rubber Pad/Rubber Sheets. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Rewamping of crane and hoist of CHP, Unit 8&9, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Material lifting mechanism at Crusher, bunker and Tunnel area of CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping, modification of TunnelAir ventilation system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping, modification of DE and DS system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping, modification of Dewatering and water recirculation system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of New Office Building with Infrastructure ,Interior Development at CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Material Storage Shed Fabrication work at CHP-D CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Electrical schemes for improvement in availability & Reliability of CHP-D,CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design supply installation and commisioning of LED based energy efficient system for illumination at CHPD | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Erection, Commissioning and Testing of 7.2KV SF6 HT Contactor for retrofitting of existing BHEL make Vacuum Circuit Breakers of CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of GE make 90-30 series PLC system installed at stacker rclaimer and wagon tippler at CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Installation of energy efficient air temperature controlling system at various MCC rooms of CHPD, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Alterration, upgradation of tunnel ventilation system of CHPD, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Fabrication, Erection & commissioning of cable support structure along with re-routing & trial of auxiliaries at Crusher PMCC, compressor house & short conveyor area at CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and installation of LT air circuit breakes at CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, supply, installation & commissioning of solar based energy efficient illumination system at CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of HT motors for various auxiliaries at CHP-D, CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & installation of high capacity submersible slurry pump at CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reconditioning of MCC Board feeder panels at CHP-D,U #8&9.CSTPS,Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & installation of anoodized winding magnets along with control panels for installation at various conveyor belts of CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of 69 AH HBL make battery set of CHP-D (U8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of 100 AH Exide make battery banks (2 Set/ 110 Nos battery cells) & battery charge at CHP-D (U8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Alterration, upgradation of tunnel ventilation system of CHPD, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of HT/LT Xmers assy of CHP-D (U8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of HT/LT Xmers assy of CHP-D (U8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | WTP-III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Engineering, installation and commissioning of DM stream capacity of 4800M3/Day for U # 8 & 9 in addition to existing DM stream at WTP, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Engineering, installation and commissioning of DM stream capacity of 4800M3/Day for U # 8 & 9 in addition to existing DM stream at WTP, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Civil - 8&9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work of diversion of peripheral nallah towards ash water recovery pump house alogwith construction of waste wear at ash bund area CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Work of diversion of peripheral nallah towards ash water recovery pump house alogwith construction of waste wear at ash bund area CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Infrastructure development of CHP-D area at U-8, 9, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of platform for unloading of coal near TP-106 upto stack pile A of CHP-D | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of WBM Road for fire fighting arrangement at CHP-D U-8,9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction & Pushing RCC box of size 2mx2m under railway track to drain out the surface water near Rly - A cabin Unit-8,9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of concrete pavement road connecting to reject gate & vinchoda chowk , Y point to ash recovery pump house | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO1 | CHP Improvement Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at CHP-D | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO2 | Developlment & Upgradation of DSM software system for MSPGCL | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Developlment & Upgradation of DSM software system for MSPGCL | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Implementation of Flexible Operation Solutions | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Flexible Operation Solutions | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 |  | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | General asset | 0 | - | 0 | 2.7096 | 2.7096 | 0 | 0.5 | 0.5 |  |  | 0.5 | 0
2 | Supply, Operation & Maintenance of Mobile Coal Sampling Equipment (MCSE) for coal sampling at loading ends of WCL for Mahagenco | 0 | - | 0 | 3.1648 | 3.1648 | 0 | 0 | 0 |  |  | 0 | 0
3 | ABC Powder Type and Foam Type Composite Fire Extinguisher | 0 | - | 0 | 1.528 | 1.528 | 0 | 0 | 0 |  |  | 0 | 0
4 | NON-Detailed Project Report for the Work of Upgradation/Renovation of Crusher House of CHPB of Unit-5, 6&7 at CSTPS Chandrapur (benefit U-8,9 by short conveyor coal stacking in catering emergency) | 0 | - | 0 | 2.8807 | 2.8807 | 0 | 0 | 0 |  |  | 0 | 0
5 | Extention of stacker reclaimer area for improvement in coal stack management at CHP-D CSTPS Chandrapur U-8,9 | 0 | - | 0 | 8.093 | 0 | 8.093 | 0.36697 | 8.46 |  |  | 8.46 | 0
6 | Retrofitting of BHEL make HT Circuit Breaker with SF6 Contactor at CHP-D, Unit-8&9 | 0 | - | 0 | 0 | 0 | 0 | 4.25 | 4.25 |  |  | 4.25 | 0
| Total |  |  |  | 480.3475 | 524.0783 | -43.7308 | 207.236 | 215.4756 | 0 | 0 | 215.4756 | -51.9704
FY 2025-26
A) Approved Add Cap (Case No. 296 of 2019)
1 | Initial Spares | Approved Add Cap (Case No. 296 of 2019)
| Boiler & Auxiliaries | 0 | - | 10.36 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Bevel Helical Gear box KMP-350 for XRP 1043 coal mills at unit-8&9,CSTPS, Chandrapur. | 0 | - | 0 | 7.4087 | 7.4087 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Hydraulic Adjustment (Actuating) Device for PA fan model PAF 19/10.6-2 and FD fan FAF 23/12.5-1 at Unit 8&9, CSTPS, Chandrapur. | 0 | - | 0 | 1.3971 | 1.3971 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Yokogawa make Zirconia Oxygen Analyser spares for C&I-III, Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 0.51933 | 0.51933 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of High pressure valves installed at unit-8&9 ( 2x500 MW),CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Turbine & Aux | 0 | - | 1.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of IMI Norgren Herion make Trip solenoid valves for Main Turbine, MD-BFP & TD-BFP of Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.37354 | 0.37354 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Speed Sensors for 500 MW KWU Turbine for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.038232 | 0.038232 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Position Feedback Transmitters for Starting Device and Speeder Gear of Main Turbine for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.11225 | 0.11225 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for LP bypass system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur on OEM Basis. | 0 | - | 0 | 0.43645 | 0.43645 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of TSE (Turbine Stress Evaluator) temperature elements for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.2073 | 0.20719 | 0.00010699 | 0 | 0 |  |  | 0 | 0.00010699
| Generator and Auxiliries | 0 | - | 0.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of complete set of water cooled bushing for 500MW Generator installed at Unit-8 & 9, CSTPS Chandrapur. | 0 | - | 0 | 0.26409 | 0.26409 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Tushaco make complete AC Jacking Oil Pump for Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.19949 | 0.19949 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of oil filled Neutral Grounding Transformer for AHP Unit-8&9 CSTPS , Chandrapur. | 0 | - | 0 | 0.34775 | 0.34775 | 0 | 0 | 0 |  |  | 0 | 0
| Electrical and Instrumentation | 0 | - | 29.23 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| ‘Procurement of various spares of BHEL make Vacuum Circuit Breakers’ , for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.49498 | 0.49498 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, erection and commissioning of floor mounted 500KW Resistor Load Bank for D.G. sets installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.27536 | 0.27536 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Turbosupervisory system spares of main turbine for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 1.0366 | 1.0366 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Level transmitters for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.15999 | 0.15999 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Level transmitters for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.032605 | 0.032605 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Level transmitters for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.046973 | 0.046973 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of GE PLC spares for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.57304 | 0.57304 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for GEHO pumps PLC control panels for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.084378 | 0.084378 | 2.6e-08 | 0 | 0 |  |  | 0 | 2.6e-08
| Procurement of master calibration lab Instruments for C&I-III, Unit 8 & 9,CSTPS,Chandrapur | 0 | - | 0 | 0.30131 | 0.30131 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Coal Feeder panel spares for C&I-III, Unit 8 & 9,CSTPS, Chandrapur | 0 | - | 0 | 0.58701 | 0.58701 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Opacity Monitor (Stack Particulate matter-SPM) spares for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.14051 | 0.14051 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Forbes Marshall Supervisory system spares For Turbine driven boiler feed pumps (TDBFP) of Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.22449 | 0.22449 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for hydraulic panel of CW pumps for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.13862 | 0.1386 | 1.7196e-05 | 0 | 0 |  |  | 0 | 1.7196e-05
| Procurement of H2 Dew point analyzer spares for Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.049938 | 0.049938 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for HP bypass system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.33965 | 0.33965 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Position feedback transmitter for HP bypass system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.0354 | 0.0354 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Atlas Copco make Instrument, Service and Conveying air Compressors for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.22509 | 0.22509 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for HEA Ignitors and Flame Scanners for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.037701 | 0.037701 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for GEHO pumps of Ash Handling System at C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.28861 | 0.28861 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Turbine side control valve spares for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.17974 | 0.17974 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various numerical protection relays for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.12307 | 0.12307 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various numerical protection relays for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.13184 | 0.13184 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various numerical protection relays for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.13863 | 0.13863 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for DB POWER make UPS system installed at HCSD Pump House, Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.064757 | 0.064757 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Fully Automatic Capacitance & Dissipation Factor (Tan- Delta) measuring kit for Unit-8 &9, CSTPS, Chandrapur. | 0 | - | 0 | 0.48288 | 0.48288 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of various VFD spares for ID fans of Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.546 | 0.546 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of DAVR spares installed at Unit -8&9 CSTPS, Chandrapur. | 0 | - | 0 | 0.5945 | 0.5945 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 3 phase relay test kit for Unit-8 &9, CSTPS, Chandrapur. | 0 | - | 0 | 0.35388 | 0.35388 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Fast Bus Transfer System (FBTS) installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.37288 | 0.37288 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various spares for battery chargers installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.40022 | 0.40022 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Auto synchronizing Relay (ASR) & Load Shedding Relay (LSR) installed at Unit-8 &9, CSTPS, Chandrapur. | 0 | - | 0 | 0.34973 | 0.34973 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ESP spares i.e. Field Controller, Thyristor and Trigger card for ESP of Unit-8 & 9, CSTPS Chandrapur. | 0 | - | 0 | 0.26745 | 0.26745 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various VFD spares for GEHO pump of Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.54416 | 0.54416 | 0 | 0 | 0 |  |  | 0 | 0
| Design, Supply, Erection & Commissioning of On-Line Dissolved Gas Analyzers for various Transformers installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 3.1775 | 3.1775 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, Erection & Commissioning of On-Line Dissolved Gas Analyzers for Station Transformers -8B, Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.30519 | 0.30519 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘TOROSHIMA’ make 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motor (without pump casing) for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 4.2037 | 4.2037 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 90kVA ESP Rectiformer for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.29878 | 0.29878 | 0 | 0 | 0 |  |  | 0 | 0
| Supply erection & commissioning of Aviation Lighting for NDCT of Unit-8&9, CSTPS Chandrapur | 0 | - | 0 | 0.57261 | 0.57261 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Transformer oil storage tanks of different capacity for Unit-8&9 CSTPS Chandrapur. | 0 | - | 0 | 0.57024 | 0.57024 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 2000kW & 315kW, 6.6 kV HT motors for CW & ACW Pump installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 1.4505 | 1.4505 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 3.25MVA, 6.6/2.3kV VFD Transformers of vector group DY11 for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.3941 | 0.3941 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 3.25MVA, 6.6/2.3kV VFD Transformer of vector group ‘Dd0’ for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.3905 | 0.3905 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘MARATHON’ makes HT/LT Induction motors for various Critical auxiliaries installed at Unit-8 &9, CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of 1.2V, Ni-Cd battery cells for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.12496 | 0.12496 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of 1.2V, Ni-Cd battery cells for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.18931 | 0.18931 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘Air Core DC Reactor’ for VFD and ‘NGR’ for UAT/ Station Transformers installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.44368 | 0.44368 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘Air Core DC Reactor’ for VFD and ‘NGR’ for UAT/ Station Transformers installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.12551 | 0.12551 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘BHEL’ make 680 KW, 6.6KV, Coal Mill Motor for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.37913 | 0.37913 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 400kV OIP Condenser Bushing for Generator Transformer & Station Transformer of Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.49064 | 0.49064 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘11kW DC motor with Control Cabinet’ for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.2242 | 0.2242 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 37kW, 415V motors for Primary Water Pump installed at Unit-8 &9, CSTPS Chandrapur. | 0 | - | 0 | 0.0096851 | 0.0096851 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 15 KW, 415V LT Motor for Service Building & TG Building Lift installed at Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.095155 | 0.095155 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 16KW, 415V LT Motor for Boiler Lift installed at Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.044179 | 0.044179 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, Erection, Testing and Commissioning of Hydrastep-Electronic Drum Level Indicator and its associated accessories for Unit-9, CSTPS, Chandrapur | 0 | - | 0 | 0.27376 | 0.27376 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for BHEL make Hydrastep (Electronic Water Level Indicator -BHELVISION 20M) for Unit 8 & 9, CSTPS, Chandrapur on OEM basis. | 0 | - | 0 | 0.084172 | 0.084172 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Electrodes for Hydrastep (Electronic Water Level Indicator -BHELVISION 20M) for Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.10384 | 0.10384 | 0 | 0 | 0 |  |  | 0 | 0
| Engineering & Retrofitting of 196 NT Controller to DT 9 Controller for Unit-8 & 9 Coal Feeder System. | 0 | - | 0 | 0.38076 | 0.38076 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for BHEL make Acoustic steam leak detection system (BHELSONIC) (BS10) for Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.077807 | 0.077807 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of LT Circuit Breaker assemblies for ESP LT Panels (LTMSB & ACP) of Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.25429 | 0.25429 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for BHEL make maxDNA Distributed control system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 1.117 | 1.117 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of Transformer oil BDV test kit DTA 100C and Oil Tan Delta & Resistivity Tester DTL C at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.47598 | 0.47598 | 0 | 0 | 0 |  |  | 0 | 0
| Outdoor Plant ( CHP/AHP/WTP) | 0 | - | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Elecon make KCN-560 type Gearbox for Apron Feeder installed at CHPD, CSTPS. | 0 | - | 0 | 1.6717 | 1.6717 | -6e-08 | 0 | 0 |  |  | 0 | -6e-08
| Procurement of spares of CKB-280,225,200,8180 typ gearbox installed at CHP-D | 0 | - | 0 | 1.0015 | 1.0015 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Gear Box (MAKE: NEW ALLENBERRY) Spares at CHP-D; CSTPS, Chandrapur. | 0 | - | 0 | 0.5177 | 0.5177 | 1.8e-08 | 0 | 0 |  |  | 0 | 1.8e-08
| Procurement of spares for m/s Elecon make Impact Crusher installed at CHP Unit 8&9 CSTPS, Chandrapur | 0 | - | 0 | 0.84103 | 0.84103 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of V belt pulley of rotor for Impact crusher installed at CHP-D, CSTPS | 0 | - | 0 | 0.11864 | 0.11864 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Spares for hydraulic systems installed at CHPD, CSTPS. | 0 | - | 0 | 0.47537 | 0.47537 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Spares for hydraulic systems installed at CHPD, CSTPS. | 0 | - | 0 | 0.028604 | 0.028604 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of drive & non drive pulley for various conveyors installed at CHP D, CSTPS, Chandrapur. | 0 | - | 0 | 0.25792 | 0.25792 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of drive & non drive pulley for various conveyors installed at CHP D, CSTPS, Chandrapur. | 0 | - | 0 | 0.0914 | 0.0914 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Chain links for apron feeder installed at CHP D, CSTPS, Chandrapur. | 0 | - | 0 | 0.40289 | 0.40289 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of internal spares for Elecon make PWD-18, PLB-25 & SCN-180 type Gearbox for Stacker Reclaimer & wobbler feeder installed at CHP D, CSTPS. | 0 | - | 0 | 0.52774 | 0.52774 | 3.1e-08 | 0 | 0 |  |  | 0 | 3.1e-08
| Supply of GE Make Switchgear Spares for GE Make LT Feeders | 0 | - | 0 | 0.12485 | 0.12485 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Fluidomat make scoop coupling installed at CHP–D, CSTPS, Chandrapur | 0 | - | 0 | 0.48355 | 0.48355 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Oil Filtering machine for hydraulic power packs installed at CHPD, CSTPS | 0 | - | 0 | 0.10592 | 0.10592 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of LT Motors at CHP-D (U#8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0.11302 | 0.11302 | 0 | 0 | 0 |  |  | 0 | 0
| Supply and Installation of Oil Cooled Suspended Anodized Winding Magnet & Control Panel at CHP, Unit 8&9, CSTPS, Chandrapur. | 0 | - | 0 | 2.2967 | 2.2967 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of LT power and control cable for CHP-D | 0 | - | 0 | 0.26256 | 0.26256 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of LT power and control cable for CHP-D | 0 | - | 0 | 0.0477 | 0.0477 | 0 | 0 | 0 |  |  | 0 | 0
2 | Capital Spare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| HPT MODULE | 0 | - | 45.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of HP turbine Module along with breach nuts and pipe spool pieces (Type: H30-100-2) for Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 32.332 | 32.332 | 0 | 0 | 0 |  |  | 0 | 0
| LPT ROTOR | 0 | - | 40.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Fully Bladed & Dynamically Balanced LP Rotor (N30-2X10-2) for Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 29.03 | 29.03 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of set of Free Standing Moving Blades for LP Rotor (N30-2X10-2) for Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 4.5629 | 4.5629 | 0 | 0 | 0 |  |  | 0 | 0
| BFP CARTRIDGE ( 2NOS ) | 0 | - | 4.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of cartridge assembly for Boiler Feed Pump model FK-4E-36 (with Four S/H & 2 R/H spray branches) installed at 2X 500MW, CSTPS, Chandrapur. | 0 | - | 0 | 2.515 | 2.5149 | 6e-05 | 0 | 0 |  |  | 0 | 6e-05
| BCW PUMP | 0 | - | 3.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for ‘TOROSHIMA’ make 350KW BCW Pump-Motor installed at Unit-8 &9, CSTPS Chandrapur. | 0 | - | 0 | 1.3283 | 1.3283 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various spares for ‘TOROSHIMA’ make Boiler Circulating Water (BCW) pump-motor installed at Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 2.2326 | 2.2326 | 0 | 0 | 0 |  |  | 0 | 0
| 15 MVA DRY TYPE TRANSFORMER | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spare ‘Cast Resin Dry Type Transformers (CRTs)’ of different ratings for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 6.0213 | 6.0213 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of phase coil limb and spares of Cast Resin Dry Type Transformers of different ratings for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 7.9255 | 7.9255 | 0 | 0 | 0 |  |  | 0 | 0
| BTG+BOP& Other Works | 0 | - | 20.48 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Design, Supply & Installation, Testing & Commissioning of Public Addressing System for tunnels of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 1.1544 | 1.1544 | 0 | 0 | 0 |  |  | 0 | 0
| Work of upgradation, installation and extension of 220VDC control supply to various PMCC of CHPD, CSTPS, Chandrapur. | 0 | - | 0 | 0.68441 | 0.68441 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Apron Feeder in CHP Unit 8&9 (2x500) MW at CHP-D, CSTPS. | 0 | - | 0 | 2.3388 | 2.3388 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of spares for up gradation of rotary parts of travelling conveyor system installed at CHPD, CSTPS, Chandrapur. | 0 | - | 0 | 0.58939 | 0.58939 | 0 | 0 | 0 |  |  | 0 | 0
| The Work of Design, Engineering, Manufacturing, Supply, Erection & Commissioning of Short Conveyor belt from stack yard of CHP of Unit 5,6&7 to Belt Conveyor 104 A/B at CHP of Unit 8&9, CSTPS, Chandrapur | 0 | - | 0 | 5.6825 | 5.6825 | 0 | 0 | 0 |  |  | 0 | 0
| Work of design, supply, erection, commissioning of overhead cable tray along with removal & re-routing of power and control cables at CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0.51324 | 0.51324 | 0 | 0 | 0 |  |  | 0 | 0
| Work of provision, modification, retrofitting and revamping of lighting system of transfers points, crusher house and bunker area of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 1.0105 | 1.0105 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for M/s. Weir Minerals make (GEHO pump Model TZPM-1200) for Ash Handling Plant Unit# 8 &9 CSTPS Chandrapur. AHP-III | 0 | - | 0 | 2.106 | 2.106 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Gear Box set of internal (MAKE: NEW ALLENBERRY) Spares at CHP-D; CSTPS, Chandrapur. | 0 | - | 0 | 1.6904 | 1.6904 | 0 | 0 | 0 |  |  | 0 | 0
| Supply and Installation of Oil Cooled Suspended Anodized Winding Magnet & Control Panel at CHP, Unit 8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 196 NT Controller by DT 9 Controller alongwith HMI units for Unit- 8&9 coal feeder system | 0 | - | 0 | 2.0774 | 2.0774 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of set of CW Impeller duly fitted with wear rings & ACW Impeller duly fitted with wear rings of Mather & Platt make Pumps installed at Unit-8 & 9,CSTPS,Chandrapur | 0 | - | 0 | 0.70379 | 0.70379 | 0 | 0 | 0 |  |  | 0 | 0
| CHP System U#8 | 0 | - | 0 | 0.05 | 0.05 | 0 | 0 | 0 |  |  | 0 | 0
| ISOLATED PHASE BUS DUCT | 0 | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| SEGREGATED PHASE BUS DUCT U#8 | 0 | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| SEGREGATED PHASE BUS DUCT U#9 | 0 | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| ISOLATED PHASE BUS DUCT U#9 | 0 | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| DTT & UAT U#8 | 0 | - | 0 | 0.03 | 0.03 | 0 | 0 | 0 |  |  | 0 | 0
| DTT & UAT U#9 | 0 | - | 0 | 0.03 | 0.03 | 0 | 0 | 0 |  |  | 0 | 0
| Cranes and hoists U#8 | 0 | - | 0 | 0.03 | 0.03 | 0 | 0 | 0 |  |  | 0 | 0
| RCC Chimney U#8 | 0 | - | 0 | 9.29 | 9.29 | 0 | 0 | 0 |  |  | 0 | 0
| Coal Handling Plant | 0 | - | 0 | 41.79 | 41.79 | 0 | 0 | 0 |  |  | 0 | 0
| Bunker foundation & civil works (Unit 8) U#8 | 0 | - | 0 | 18.58 | 18.58 | 0 | 0 | 0 |  |  | 0 | 0
| Boiler & Auxiliaries U#9 | 0 | - | 0 | 9.2889 | 9.2872 | 0.0017338 | 0 | 0 |  |  | 0 | 0.0017338
| ESP U#9 | 0 | - | 0 | 2.1589 | 2.1589 | 0 | 0 | 0 |  |  | 0 | 0
| ID fan foundations (Unit 9) U#9 | 0 | - | 0 | 1.7489 | 1.7489 | 0 | 0 | 0 |  |  | 0 | 0
| DRY ASH SILO-12M DIA U#8 | 0 | - | 0 | 1.22 | 1.22 | 0 | 0 | 0 |  |  | 0 | 0
| FD fan foundations (Unit 9) U#9 | 0 | - | 0 | 0.62891 | 0.62891 | 0 | 0 | 0 |  |  | 0 | 0
| PA fan foundations (Unit 9) U#9 | 0 | - | 0 | 0.54891 | 0.54891 | 0 | 0 | 0 |  |  | 0 | 0
| Natural Draft cooling tower- Unit 8 U#8 | 0 | - | 0 | 0.32 | 0.32 | 0 | 0 | 0 |  |  | 0 | 0
| Main power house building-Civil Works-Unit no.-9 U | 0 | - | 0 | 0.15 | 0.15 | 0 | 0 | 0 |  |  | 0 | 0
| Structural Steel works for main power house buildi | 0 | - | 0 | 0.15 | 0.15 | 0 | 0 | 0 |  |  | 0 | 0
| Canteen U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Security and time office U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| CARS SCOOTERS AND CYCLE SHED U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Fire Station U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Watch towers U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| First aid station | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Tranformer yard U#8 | 0 | - | 0 | 0.02 | 0.02 | 0 | 0 | 0 |  |  | 0 | 0
| Rain Water Harvesting Scheme U#8&9 | 0 | - | 0 | -0.01 | -0.01 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Advance Multipurpose Fire Tender | 0 | - | 0 | 3.45 | 3.45 | 0 | 0 | 0 |  |  | 0 | 0
| DM Stream | 0 | - | 29.65 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| DM Stream capacity of 100 M3/Hr in addition to existing stream of WTP. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| CIVIL | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Bridge | 0 | - | 4.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Railway, CHP, AHP etc | 0 | - | 152.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| B. G. railway siding Pway works | 0 | - | 0 | 41.5165 | 41.5165 | 0 | 0 | 0 |  |  | 0 | 0
| S & T work for B.G. railway siding | 0 | - | 0 | 0.023574 | 0.023574 | 0 | 0 | 0 |  |  | 0 | 0
| Consultancy services for B. G. railway siding | 0 | - | 0 | 0.035636 | 0.035636 | 0 | 0 | 0 |  |  | 0 | 0
| Ash infra in Railway | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Bunker structure (Unit 8) U#8 | 0 | - | 0 | 18.57 | 18.57 | 0 | 0 | 0 |  |  | 0 | 0
| Coal Mills | 0 | - | 0 | 1.1389 | 1.1389 | 0 | 0 | 0 |  |  | 0 | 0
| Bunker foundation & civil works (Unit 9) U#9 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Bunker structure (Unit 9) U#9 | 0 | - | 0 | 0.11 | 0.11 | 0 | 0 | 0 |  |  | 0 | 0
| HCSS silo-12m dia U#8 | 0 | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| Ash water PH, HCSD PH, Bottom ash slurry PH U#8 | 0 | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| Ash compressor house & Control room U#8 | 0 | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| MILL REJECT SILO U#8 | 0 | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| Fire protection & Detection system U#8 | 0 | - | 0 | 0.71423 | 0.71423 | 0 | 0 | 0 |  |  | 0 | 0
| DM Water Pump room U#8 | 0 | - | 0 | 4.25 | 0 | 4.25 | 0 | 0 |  |  | 0 | 4.25
| Filter water reservoir & pump house U#8 | 0 | - | 0 | 4.29 | 0 | 4.29 | 0 | 0 |  |  | 0 | 4.29
| ACW + RW + Filtered water piping U#8 | 0 | - | 0 | 2.2409 | -0.0096938 | 2.2506 | 0 | 0 |  |  | 0 | 2.2506
| Laboratory Building U#8 | 0 | - | 0 | 0.12 | 0 | 0.12 | 0 | 0 |  |  | 0 | 0.12
3 | Staff quarters | 0 | - | 15.04 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Work of exterior repair, providing painting to A, D & E type residential buildings and Public Buildings and allied civil works in Urjanagar Colony, CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Staff Quarters- Repair and renovation of E type staff quarters to extend the life of buildings at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Staff Quarters - Repair and renovation of 'B' type staff quarters in residential colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair of D type quarters in colony at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair of C type quarters in colony at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Staff Quarters- Repair and renovation of F and NF type staff quarters to extend the life of buildings at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair and replacement of existing drinking water supply pipelines in E & F type area in colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair and replacement of existing sewer lines in E & F type area in colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Work of providing RCC drain along main roads in colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Rerouting and replacement of domestic water supply pipeline from WTP to ESR in colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Additional Contengencies approved vide e BR No. MSPGCL/BM-162/165, Dt.29.10.2016 vide resolution no. 2016/2085 | 0 | - | 7.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Landscaping and plantation work at various locations inside plant area at CSTPS, chandrapur. | 0 | - | 0 | 3.4266 | 3.4266 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of WBM approach road from point- N to Z Area along ash bund periphery at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design, Engineering, Supply and commissioning of ash-bund water recovery system (Phase II) at CSTPS Chandrapur | 0 | - | 27.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, Engineering, Supply and commissioning of ash-bund water recovery system (Phase II) at CSTPS Chandrapur | 0 | - | 0 | 30.0361 | 30.0361 | 0 | 0 | 0 |  |  | 0 | 0
| Providing Consultancy Services for work of Design, Engineering, Supply, Installation & Commissioning of ash bund water recovery system (Phase-II) at CSTPS, Chandrapur (on EPC contract basis). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Providing laying, jointing and commissioning of 1600 mm dia. M.S. Pipe line from Erai dam to one day reservoir of stage II, III & IV at CTPS | 0 | - | 73.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Providing laying, jointing and commissioning of 1600 mm dia. M.S. Pipe line from Erai dam to one day reservoir of stage II, III & IV at CTPS | 0 | - | 0 | 73.6091 | 73.6091 | 0 | 0 | 0 |  |  | 0 | 0
| Work of construction of Control Valve rooms on newly laid 1600 mm M.S. Pipeline no. 6 from Erai dam to One day reservoir at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Providing OHE facility for BG Rly siding of proposed Expansion Project at Chandrapur, for Supply of Materials. | 0 | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Providing OHE facility for BG Rly siding of proposed Expansion Project at Chandrapur, for errection of OHE Items. | 0 | - | 2.5 | 0.7 | 0 | 0.7 | 0 | 0 |  |  | 0 | 0.7
9 | Irrigation scheme for landscaping and Plantation work at Chandrapur expansion project chandrapur. | 0 | - | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Asphalting of WBM road from Nagpur gate to Awanda gate. | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Asphalting of WBM road from Nagpur gate to Awanda gate. | 0 | - | 0 | 0.65141 | 0 | 0.65141 | 0 | 0 |  |  | 0 | 0.65141
| Asphalting over WBM Road of ADP line Service road from Nagpur gate opening to Awandha junction gate at CSTPS Chandrapur | 0 | - | 0 | 0.84833 | 0.84833 | 0 | 0 | 0 |  |  | 0 | 0
| Asphalting of WBM road from Nagpur gate to Awandha gate at CSTPS Chandrapur - Asphalting of road from Reject coal gate to Motghat nallah at CSTPS Chandrapur (PHASE - I) | 0 | - | 0 | 0.47941 | 0.47941 | 0 | 0 | 0 |  |  | 0 | 0
11 | Foot Over Bridge | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Work of Providing retaining wall for sand hump at Vivekanand nagar station yard under modification work in wardha end fro 2 x 500 MW Expn. Project at CSTPS, Chandrapur. | 0 | - | 0.3 | 0.25515 | 0.25515 | 0 | 0 | 0 |  |  | 0 | 0
| Additional Capitalization by O & M | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of GE make 4000Amp LT Air Circuit Breakers for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0.9 | 1.0308 | 1.0308 | 0 | 0 | 0 |  |  | 0 | 0
2 | Air Compressor System | 0 | - | 0.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Energy management Sysytem | 0 | - | 0.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, Installation, Testing & Commissioning of Energy Management System for Unit#8 & 9 for CSTPS, Chandrapur. | 0 | - | 0 | 0.20054 | 0.20054 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Tri-vector 0.2s class Digital Energy meter for Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.094872 | 0.094872 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, Installation & Commissioning of 3D Level Scanners to 64 nos. of ESP hoppers at Unit-8&9 (2X500MW), CSTPS, Chandrapur. | 0 | - | 3.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of internal spares for Elecon make PWD-18, PLB-25 ,Pbh-71 type Gearbox for Stacker Reclaimer installed at CHPD, CSTPS. | 0 | - | 0 | 1.1089 | 1.1089 | 0 | 0 | 0 |  |  | 0 | 0
5 | 4000/2500/1800/800 A GE make LT CKT Brkr | 0 | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| LT Air Circuit Breakers for Incomer Feeders at CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 1.4207 | 1.4207 | 0 | 0 | 0 |  |  | 0 | 0
| LT Air Circuit Breakers at CHP, Unit 8&9, CSTPS | 0 | - | 0 | 1.0141 | 1.0141 | 0 | 0 | 0 |  |  | 0 | 0
6 | Replacement of Impact crusher by hammer mill crusher (installed qty.2 No) | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Replacement of wobbler feeder 1&2 by grizzly screen at CHP-D | 0 | - | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Installation of conveyor system from rope way of CHP-A and crusher house of CHP-D | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| PLC based control & instrumentation of 6.6 KV HT motors of 1250 KW of Crusher I & II and 200 KW of BC 108A1 & A2 at CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0.93628 | 0.93628 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Design, Supply, Erection & Commissioning of Complete Electrical Automation for Short Conveyor from stack yard of CHP-D to Belt Conveyor 107 A/B of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0.70095 | 0.70095 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Design, Supply, Erection & Commissioning of Complete Electrical Automation for Short Conveyor from stack yard of CHP-B to Belt Conveyor 104 A/B of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 2.2368 | 2.2368 | 0 | 0 | 0 |  |  | 0 | 0
| WORK OF DESIGN, ENGINEERING, MANUFACTURING, SUPPLY, ERECTION &COMMISSIONING OF SHORT CONVEYOR BELT FROM STACK YARD OF CHP UNIT-8&9 TO CONVEYOR BELT 107A AND B AT CHP UNIT 8&9, CSTPS, CHANDRAPUR. | 0 | - | 0 | 4.6948 | 4.6948 | -2.4e-08 | 0 | 0 |  |  | 0 | -2.4e-08
| Design, Supply, Installation and Commissioning of High Performance Energy Chain System for Side Arm Charger and Stacker Reclaimer of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 3.8916 | 3.8916 | 0 | 0 | 0 |  |  | 0 | 0
| RBF 103 &104,105 & 106, 107 & 108, and 109 & 110 in to modular Y chute | 0 | - | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-103 & RBF-104 with Design, development, Manufacturing, Supply & erection of modular Chute as per site condition in place of RBF using sintered silicon Carbide plate with motorized Flap Gate at CHP-D, CSTPS. | 0 | - | 0 | 1.1741 | 1.1741 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-105 & RBF-106 with Design, development, Manufacturing, Supply & erection of modular Chute as per site condition in place of RBF using sintered silicon Carbide plate with motorized Flap Gate at CHP-D, CSTPS. | 0 | - | 0 | 1.3169 | 1.3169 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-107 & RBF-108 with Design, development, Manufacturing, Supply & erection of modular Chute as per site condition in place of RBF using Tungsten Carbide plate with Flap Gate at CHP-D, CSTPS. | 0 | - | 0 | 1.1529 | 1.1529 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-109 & RBF-110 with design, erection & Installation by trajectory calculation & removal of existing RBF with Y Chute assembly by flow control with Flap Gate arrangement at TP-107 of CHP-D, CSTPS. | 0 | - | 0 | 1.1506 | 1.1506 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurment , Installation and commissioning of Online Insertable Camera systems for Unit-8, 500MW, CSTPS | 0 | - | 8.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, Supply, Installation & Commissioning of Energy efficient system for Illumination at Unit 8&9 CSTPS, Chandrapur. | 0 | - | 0 | 4.9494 | 4.9494 | 0 | 0 | 0 |  |  | 0 | 0
11 | Construction of Chemical godown shed for unit 8 & 9 at CSTPS,Chandrapur. | 0 | - | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of Chemical godown shed for unit 8 & 9 at CSTPS,Chandrapur. | 0 | - | 0 | 0.42946 | 0.42946 | 0 | 0 | 0 |  |  | 0 | 0
| Comprehencive work of installation, erection, testing and commissioning of MVWS spray system/ Fire safety system for new Bulk Chemical storage godown at CSTPS, Unit 8&9 | 0 | - | 0 | 0.27583 | 0.27583 | 0 | 0 | 0 |  |  | 0 | 0
| Work of electrification of godown for bulk chemical storage near FOPH building at Chandrapur project site. | 0 | - | 0 | 0.018322 | 0.018322 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of additional Chemical godown shed for storage of Lube oil at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Construction of RCC retaining wall for approach to RCC Bridge across Irai River, ADPL line at CSTPS | 0 | - | 8.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of RCC retaining wall for approach to RCC Bridge across Irai River, ADPL line at CSTPS | 0 | - | 0 | 4.3482 | 4.3482 | 0 | 0 | 0 |  |  | 0 | 0
| Asphalting of road from Reject coal gate to Motghat nallah at CSTPS Chandrapur (PHASE - II) | 0 | - | 0 | 0.87403 | 0.87403 | 0 | 0 | 0 |  |  | 0 | 0
| Providing extension to approaches of RCC bridge across Erai river by constructing WBM road at CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| UDL | 0 | - | 0 | 4.85 | 4.85 | 0 | 0 | 0 |  |  | 0 | 0
| B) DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (i) In Principally Approved By MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 1 | HMI (Human Machine Interface) Upgradation of ‘SSPA-T3000’ DCS (Distribution Control System), Rockwell make PLC System installed at 3x660MW Unit No. 8, 9 & 10 at Koradi TPS and HMI (Human Machine Interface) Upgradation of MaxDNA DCS System at Unit 8-9, CSTPS, Chandrapur | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 11.08 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 1.1 | Supply: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 10.52 | 10.52 | 21.02 | -10.5 | 0 | 0 |  |  | 0 | -10.5
HO DPR 1.2 | Works: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.41 | 0.41 | 0.81 | -0.4 | 0 | 0 |  |  | 0 | -0.4
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
40 | Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M with construction of concrete dam (Waste Weir & Non overflow structure), construction of drain wells, approach to drain wells and raising of ash compartment for ash bund along with renewal of Ash Disposal Pipe Line Service Road with WBM treatment at CSTPS, Chandrapur | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 4.9692 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 34.8665 | 34.8665 | 69.733 | -34.8665 | 0 | 0 |  |  | 0 | -34.8665
| Construction of New Drain Wells (12 Nos.) along with necessary connection to existing drain wells at CSTPS | 0 | - | 0.58493 | 0.58493 | 1.1699 | -0.58493 | 0 | 0 |  |  | 0 | -0.58493
| Construction of waste weir for raising of ash bund (Waste Weir & Non overflow structure) | 0 | - | 1.4621 | 1.4621 | 2.9241 | -1.4621 | 0 | 0 |  |  | 0 | -1.4621
| Raising of Ash Compartment i.e. Lagoon in Ash Bund | 0 | - | 8.7868 | 8.7868 | 17.5736 | -8.7868 | 0 | 0 |  |  | 0 | -8.7868
| IDC | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 7.634 | 7.634 | 15.2679 | -7.634 | 0 | 0 |  |  | 0 | -7.634
| IDC | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 4.9692 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
39 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 8-9) | MERC/CAPEX/2020-2021/WFH/SBR/21 | 2020-07-24 | 479.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
39.1 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 8-9) | MERC/CAPEX/2020-2021/WFH/SBR/21 | 2020-07-24 | 440.54 | 119.66 | 119.66 | 0 | 438.74 | 438.74 |  |  | 438.74 | 0 | 320.88 | 117.86
| IDC | MERC/CAPEX/2020-2021/WFH/SBR/21 | 2020-07-24 | 38.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41 | CHP Performance Improvement Schemes at Unit 8-9 of CSTPS, Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 26.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.1 | Work of Design engineering , supply and installation of modular chutes with sintered silicon carbide for smooth flow &center feeding in CHP 2x500MW CSTPS | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 9.43 | 4.715 | 4.715 | 0 | 4.715 | 4.715 |  |  | 4.715 | 0 | 4.715 | 0
41.2 | Supply erection & commissioning of set of internal of impact crusher spares installed at CHPP-D, CSTPS | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 8.05 | 4.025 | 4.025 | 0 | 4.025 | 4.025 |  |  | 4.025 | 0 | 4.025 | 0
41.3 | Scheme for replacement of Scoop coupling/Fluid coupling of conveyor BC-101A/B/C, BC-102A/B, BC-104A/B, BC-105A/B ,BC-106A/B, BC-111A/B/C/D, BC-110A1/B1, BC-110A/B Installed at CHP-D, CSTPS Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 4.67 | 2.335 | 2.335 | 0 | 2.335 | 2.335 |  |  | 2.335 | 0 | 2.335 | 0
41.4 | Supply erection & commissioning of set of internal of spares of stacker reclaimer installed at CHP-D, CSTPS Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 1.96 | 0.98 | 0.98 | 0 | 0.98 | 0.98 |  |  | 0.98 | 0 | 0.98 | 0
41.5 | Supply erection & commissioning of set of internal of spares of Wagon tippler installed at CHP-D, CSTPS Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 2.12 | 1.06 | 1.06 | 0 | 1.06 | 1.06 |  |  | 1.06 | 0 | 1.06 | 0
| IDC | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 0.38 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 2 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 2.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
A6 | Supply, Installation & Commissioning of Online Coal Flow Monitoring & Balancing System at Unit-8-9, CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0457 Dt 26.07.2024 | 2024-07-26 | 34.21 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, installation and commissioning of Online Coal flow monitoring and balancing system for U- 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2024-2025/MSPGCL/0457 Dt 26.07.2024 | 2024-07-26 | 34.21 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0457 Dt 26.07.2024 | 2024-07-26 | 0.31 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
A7 | Providing, supplying, laying and commissioning of 1600 mm dia. M.S. Pipe by replacement of existing PSC raw water line from Erai dam to reservoir at CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 40.7945 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing, supplying, laying and commissioning of 1600mm dia. M.S. pipe by replacement of existing PSC raw water line from Erai dam to reservoir at CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 40.7945 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 8.83 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
A8 | Adoption of Ozonization technique for disinfection of Cooling Water System at U # 8 & 9 | MERC/CAPEX/MSPGCL/2023-2024/0467 Dt 02.08.2024 | 2024-08-02 | 67 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Adoption of Ozonization technique for disinfection of Unit 8&9 Cooling Water at CSTPS. | MERC/CAPEX/MSPGCL/2023-2024/0467 Dt 02.08.2024 | 2024-08-02 | 67 | 0 | 0 | 0 | 33.5 | 33.5 |  |  | 33.5 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-2024/0467 Dt 02.08.2024 | 2024-08-02 | 2.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (ii) Submitted to MERC |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y1 | Multiple Schemes for Electrical Maintenance Section and Design, Engineering, Manufacturing, Testing, Unloading at site, E&C of 200MVA, 21/420KV Single Phase Generator Transformer for Unit # 8 & 9, CSTPS | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 10MW, 11kV Motor and its recommended spare for Boiler Feed Pump (BFP) | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Replacement of NiCd battery sets installed for UPS of Fire Water Pump House, CMRH & SWAS lab of Unit 8 & 9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Retrofitting of GE make LT Air Circuit Breakers of various current ratings and procurement of their recommended spares for Unit-8&9, CSTPS | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of BHEL make 6.6kV and 11kV Vacuum Circuit Breakers for Unit-8&9, CSTPS Chandrapur | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y5 | Scheme-1: Procurement of assembly of baskets for Air Preheater of type 31.05 VIMT 2000 (72° PA), Scheme-2: Procurement of spares for PRDS station pressure control valves and Desuperheating spray Control valves in Boiler at U-8&9, CSTPS, Chandrapur, Scheme-3: Procurement of complete set of sky climber at U-8&9, CSTPS, Chandrapur. Scheme-4: Supply, erction, commissioning of oil free rotary screw compressors (including all Civil Electrical, C&I, Testing work) for CMRH system at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-1: Procurement of assembly of baskets for Air Preheater of type 31.5 VIMT 2000 (72° PA) at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0 | 0 | 0 | 15.78 | 15.78 |  |  | 15.78 | 0
| Scheme-2: Procurement of spares for PRDS station pressure control valves and Desuperheating spray control valves in Boiler at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0 | 0 | 0 | 6.09 | 6.09 |  |  | 6.09 | 0
| Scheme-3: Procurement of complete set of sky climber at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0 | 0 | 0 | 3.16 | 3.16 |  |  | 3.16 | 0
| Scheme-4: Supply, erection, commissioning of oil free rotary screw compressors (including all Civil Electrical, C&I, Testing work) for CMRH system at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0 | 0 | 0 | 8.3 | 8.3 |  |  | 8.3 | 0
| IDC | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y6 &Y7 | Supply, Erection & commissioning/retrofitting of HT Circuit Breaker with SF6 Contactor at AHP at Unit-8&9 & CHP#D and Supply, Installation and Commissioning of MV VFD panel along with integrated online cell redundancy technology with VFD bypass feature arrangement for conveyors 103 A & B of CHP-B, C.S.T.P.S., Chandrapur & Design, engineering, manufacturing, testing, unloading at site, E&C of Two No of 200 MVA, 21/420 KV Single Phase Generator Transformers for Unit-8&9, CSTPS, Chandrapur. Through OEM | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme 1: Retrofitting of BHEL make HT Circuit Breaker with SF6 contactor at AHP, Unit#8&9, CSTPS. | To be resubmitted | - | 0 | 0 | 0 | 0 | 38.33 | 38.33 |  |  | 38.33 | 0
| Scheme 2: Retrofitting of BHEL make HT Circuit Breaker with SF6 contactor at CHP#D, Unit#8&9, CSTPS. | To be resubmitted | - | 0 | 0 | 0 | 0 | 5.64 | 5.64 |  |  | 5.64 | 0
| Scheme 3: Supply, Installation and Commissioning of MV VFD panel along with integrated online cell redundancy technology with VFD bypass feature arrangement for conveyors 103 A & B of CHP-B. | To be resubmitted | - | 0 | 0 | 0 | 0 | 4.03 | 4.03 |  |  | 4.03 | 0
| Design, engineering, manufacturing, testing, unloading at site, E&C of Two No of 200 MVA, 21/420 KV Single Phase Generator Transformers for Unit-8&9, CSTPS, Chandrapur. Through OEM | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (iii) Yet to be Submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Boiler Maintenance -III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of Air & Flue gas ducts of Boiler , Blade set and HAD for PA and FD Fan , SCAPH Coil, ID Fan spares at Unit-8&9 CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-1 Procurement of Air & flue gas expansion joints | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-2 :Procurement of Blade Set and 2 sets of HAD of PA Fan. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme -3 Procurement of Blade Set and 2 sets of HAD of FD Fan. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-4 Procurement of SCAPH Coil for unit- 8&9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-5 :Procurement of ID Fan Impeller , Shaft and Blade set at unit-8 & 9, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme 6: Procurment of Coal Fuel pipes for unit -8 &9 , CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of LTSH and economiser for unit-8&9 CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of LTSH Coil assemsblies unit- 8&9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of economiser coil asemblies | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of existing belt type gravimetric coal feeders to gravimetric rotary weigh coal feeders of unit- 8&9, at CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 10.03 | 10.03 |  |  | 10.03 | 0
3 | Supply of Quick Erect Aluminum Boiler Scaffolding system or unit- 8 & 9, (2X500MW), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of Quick Erect Aluminum Boiler Scaffolding system or unit- 8 & 9, (2X500MW), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 35 | 35 |  |  | 35 | 0
| Turbine Maintenance -III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Schemes for Improvement in availability & performance of TG auxiliaries at U-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 1. Procurement of BFP Booster Pump assembly for Unit-8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 2. Procurement of Boiler Feed Pump catridge with CI sealing for Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 3. Procurement of Modulating type Boiler Feed Pump Recirculation valve (06 Nos) assembly for Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
| 4. Procurement of HP Heater HPH-5B assembly for Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 5. Procurement of MDBFP working oil & lube oil coolers for Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 6. Procurement of TDBFP Turbine rotor K1401-2 at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 7. Procurement of Main TG Jacking oil pumps (2 Nos.) at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0.5 | 0.5 |  |  | 0.5 | 0
| 8. Procurement of HP elements of ZR500 Atlas Copco make compressors along with inter & after coolers tube nest at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
| 9. Procurement of CW & ACW Pump spares at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
| 10. Procurement of condenser tubes at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 11. Procurement of HPCF Pump at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | DPR for performance improvement of Condenser Cooling water system & improvement in system reliability of auxiliary cooling water system installed at Unit-8&9, 2x500MW, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| DPR for performance improvement of Condenser Cooling water system & improvement in system reliability of auxiliary cooling water system installed at Unit-8&9, 2x500MW, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of main turbine IPT module at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of main turbine IPT module at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Electrical Maintenance -III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Proc of GTR, MDBFP, UPS battery, breakers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, engineering, manufacturing, testing, unloading at site, E&C of 200 MVA, 21/420 KV Single Phase Generator Transformer for Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 21.07 | 21.07 |  |  | 21.07 | 0
| Procurement of MDBFP motor and recommended spares The Fire Water Pump House UPS Battery set of 240V, 40AH Capacity (1.2V X 176 Cells ) Ni Cd Type Make- HBL The UPS Battery Set at SWAS Lab (Outdoor Area), 45AH Capacity (1.2 V X 276 Cells) Ni Cd type Make- HBL for Unit#8&9 The UPS Battery Set at CMRH (Outdoor Area), 69AH Capacity (1.2 V X 280 Cells) Ni Cd type Make- HBL for Unit#8&9 Retrofitting of 415V GE make ACB of various ratings along with allied spares. BHEL make Breakers and spares for 6.6 kV and 11kV panels | 0 | - | 0 | 0 | 0 | 0 | 15.07 | 15.07 |  |  | 15.07 | 0
2 | Design, engineering, manufacturing, testing, unloading at site, E&C of 80 MVA, 420/11/6.9 KV three Phase Station Transformer & 25MVA 21/6.9KV Three phase Unit Aux Transformer as a common pool spares for BTPS 500MW, Khaparkheda 500 MW and Unit-8&9, CSTPS, Chandrapur & Supply, installation, commissioning and testing of Station Batteries of Unit-8&9 CSTPS alongwith all outdoor batteries | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, engineering, manufacturing, testing, unloading at site, E&C of 80 MVA, 420/11/6.9 KV three Phase Station Transformer & 25MVA 21/6.9KV Three phase Unit Aux Transformer as a common pool spares for BTPS 500MW, Khaparkheda 500 MW and Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, installation, commissioning and testing of Station Batteries of Unit-8&9 CSTPS alongwith all outdoor batteries | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| I&C -III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Upgradation of Analysis & Diagnostics system (A&D) for VMS and TSI system at Unit-8&9, CSTPS, Chandrapur.& other schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of Analysis & Diagnostics system (A&D) for VMS and TSI system at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 17 | 17 |  |  | 17 | 0
| Installation of CO analysers at Eco outlet at Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
| Complete Engineering Retrofitting of Existing 196 NT Controller by DT 9 Controller alongwith HMI units for Unit 8/9 coal feeder system. | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
| Supply of spares for LP bypass system. | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
| Supply of spares for maxDNA DCS system | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
2 | Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 30 | 30 |  |  | 30 | 0
3 | Upgradation of HMI and hardware of GE make PLCs installed at Unit-8&9, CSTPS, Chandrapur. & other schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of HMI and hardware of GE make PLCs installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of TD-BFP Turbovisory system installed at Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of EWLI system installed at Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of O2 analysers installed at Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Installation of High temperature Camera system at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of HEA igniter system at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of Flue Gas Analysers and Opacity Analysers at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-8, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-8, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Multiple schemes C&I-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Total Mercury (Gaseous) Analyzers along with their online data connectivity & Remote calibration U-3 to 9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Controllers & Com Boxes for Air Compressors of Unit-8&9. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of Steam and Water Analysis System (SWAS) for Unit – 8 & 9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of Servo valve (ST) with proportional valves (PV) for HP bypass system at Unit – 8 & 9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of GEHO pump VFD panels for Unit – 8 & 9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Upgradation of measurement and control system installed at CSTPS Unit 8&9 & Upgradation of Numerical Protection Relay of Alstom / Schnieder make installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of measurement and control system installed at CSTPS Unit 8&9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of Numerical Protection Relay of Alstom / Schnieder make installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| AHP-III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | supply of piston cylinder assembly, diaphragm assembly, Suction and discharge valve housing assembly of GEHO pump (Model- TZPM 1200). & other schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-1 :supply of piston cylinder assembly, diaphragm assembly, Suction and discharge valve housing assembly of GEHO pump (Model- TZPM 1200). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme -2 :Procurement of sub assemblies for conveying air compressor model ZR 275 and instrument air compressor model ZR 110 in Ash handling plant Unit-8&9 (2x500MW) at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme -3 Supply of 10/8 FAH Warman make slurry pump impeller element assembly, Bearing assembly unit, jacket assembly. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply and replacement of 400 NB MSERW pipeline of ash disposal system of unit 8&9 at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 :Supply and replacement of 400 NB MSERW pipeline of ash disposal system of unit 8&9 at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Complete ESP Refurbishment of 1st & 2 nd Row Field of Unit 8&9 at CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 : Complete ESP Refurbishment of 1st & 2 nd Row Field of Unit 8&9 at CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP - D | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Upgradation Of Hydraulic Systems with Safety Mechanism for wagon unloading system at CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply erection & commissioning of wagon tippler, Side Arm Charger, apron feeder and stacker hydraulic drive system with online NAS value monitoring systems. | 0 | - | 0 | 0 | 0 | 0 | 8 | 8 |  |  | 8 | 0
0 | Wagon stopping mechanism (Safety) | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
2 | Upgardation and Capacity Enhancement of Side Arm Charger Apron Feeder and Bunker Conveyors at CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | capacity enhancement to 60 wagons pulling capacity and associated modification of existing side arm charger | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Capacity enhancement , Commissionng of apron feeder drive | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
0 | Modification and revamping of Apron Feeder 101,102,103 | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
0 | Supply,Installation and Commissioning of double drive Mechanism with Split Case Bearings for Tripper Trolley and bunkering conevyor belts of CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Modification of Fixed Tripper Head Pulley(Z-Point) of BC110A&B at CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Modification, Errection & Commissioning of drive unit capacity enhancement for conveyor at CHP-D, Chandrapur TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Performance Improvement Schemes of CHP-D CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design engineering , supply and installation of modular chutes with weld cast Liners ,flap gates and actuators. | 0 | - | 0 | 0 | 0 | 0 | 20 | 20 |  |  | 20 | 0
0 | Supply erection & commissioning of set of internal of spares of Wagon tippler and Side Arm Charger installed at CHP-D, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply erection & commissioning of set of internal of spares of stacker reclaimer installed at CHP-D, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply erection & commissioning of set of internal of spares of Impact crusher installed at CHP-D, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply erection & commissioning of set of internal of spares of wobbler feeder installed at CHP-D, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply erection & commissioning of 1500 TPH capacity Stacker Recliamer sleeving bearing with fastener of CHP-D (U8&9), CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of Gearbox assemblies at CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 7 | 7 |  |  | 7 | 0
0 | Structure Strengthening,Modification works of Conveyors at CHP-D CSTPS | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
4 | Design, Installation, testing and commissioning of new conveyor systems of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Installation, testing and commissioning of conveyor system from crusher house to TP-108 of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Engineering, erection and commissioning of one 1500TPH crusher, short conveyors from TP 106 and open space of near Stack yard A pile to Crusher inlet and a telescopic conveyor at the output of crusher to Stack Yard B pile of CHPD Unit 8&9, CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design, Installation and commissioning of conveyor system from rope way of CHP-A to crusher house of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Installation and commissioning of conveyor system from rope way of CHP-A to crusher house of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Infrastructure Development Schemes at CHP-D CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Supply,Installation and Commissioning of EOT Cranes at Wagon Tippler area of CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Belt Tracking systems for Carrying/Return 1400/1600 mm belt width | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Ceramic Lagging by direct bonding on Conveyor Pulleys without Rubber Pad/Rubber Sheets. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Rewamping of crane and hoist of CHP, Unit 8&9, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
0 | Material lifting mechanism at Crusher, bunker and Tunnel area of CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
0 | Revamping, modification of TunnelAir ventilation system | 0 | - | 0 | 0 | 0 | 0 | 20 | 20 |  |  | 20 | 0
0 | Revamping, modification of DE and DS system | 0 | - | 0 | 0 | 0 | 0 | 30 | 30 |  |  | 30 | 0
0 | Revamping, modification of Dewatering and water recirculation system | 0 | - | 0 | 0 | 0 | 0 | 30 | 30 |  |  | 30 | 0
0 | Provision of New Office Building with Infrastructure ,Interior Development at CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Material Storage Shed Fabrication work at CHP-D CSTPS | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
7 | Electrical schemes for improvement in availability & Reliability of CHP-D,CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design supply installation and commisioning of LED based energy efficient system for illumination at CHPD | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Erection, Commissioning and Testing of 7.2KV SF6 HT Contactor for retrofitting of existing BHEL make Vacuum Circuit Breakers of CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 4 | 4 |  |  | 4 | 0
0 | Upgradation of GE make 90-30 series PLC system installed at stacker rclaimer and wagon tippler at CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
0 | Installation of energy efficient air temperature controlling system at various MCC rooms of CHPD, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Alterration, upgradation of tunnel ventilation system of CHPD, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Fabrication, Erection & commissioning of cable support structure along with re-routing & trial of auxiliaries at Crusher PMCC, compressor house & short conveyor area at CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and installation of LT air circuit breakes at CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, supply, installation & commissioning of solar based energy efficient illumination system at CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of HT motors for various auxiliaries at CHP-D, CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & installation of high capacity submersible slurry pump at CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reconditioning of MCC Board feeder panels at CHP-D,U #8&9.CSTPS,Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & installation of anoodized winding magnets along with control panels for installation at various conveyor belts of CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of 69 AH HBL make battery set of CHP-D (U8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of 100 AH Exide make battery banks (2 Set/ 110 Nos battery cells) & battery charge at CHP-D (U8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Alterration, upgradation of tunnel ventilation system of CHPD, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of HT/LT Xmers assy of CHP-D (U8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of HT/LT Xmers assy of CHP-D (U8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | WTP-III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Engineering, installation and commissioning of DM stream capacity of 4800M3/Day for U # 8 & 9 in addition to existing DM stream at WTP, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Engineering, installation and commissioning of DM stream capacity of 4800M3/Day for U # 8 & 9 in addition to existing DM stream at WTP, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Civil - 8&9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work of diversion of peripheral nallah towards ash water recovery pump house alogwith construction of waste wear at ash bund area CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Work of diversion of peripheral nallah towards ash water recovery pump house alogwith construction of waste wear at ash bund area CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
2 | Infrastructure development of CHP-D area at U-8, 9, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of platform for unloading of coal near TP-106 upto stack pile A of CHP-D | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of WBM Road for fire fighting arrangement at CHP-D U-8,9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction & Pushing RCC box of size 2mx2m under railway track to drain out the surface water near Rly - A cabin Unit-8,9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of concrete pavement road connecting to reject gate & vinchoda chowk , Y point to ash recovery pump house | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO1 | CHP Improvement Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at CHP-D | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO2 | Developlment & Upgradation of DSM software system for MSPGCL | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Developlment & Upgradation of DSM software system for MSPGCL | 0 | - | 0 | 0 | 0 | 0 | 55 | 55 |  |  | 55 | 0
1 | Implementation of Flexible Operation Solutions | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Flexible Operation Solutions | 0 | - | 0 | 0 | 0 | 0 | 34 | 34 |  |  | 34 | 0
0 |  | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | General asset | 0 | - | 0 | 3.2096 | 3.2096 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply, Operation & Maintenance of Mobile Coal Sampling Equipment (MCSE) for coal sampling at loading ends of WCL for Mahagenco | 0 | - | 0 | 3.1648 | 3.1648 | 0 | 0 | 0 |  |  | 0 | 0
3 | ABC Powder Type and Foam Type Composite Fire Extinguisher | 0 | - | 0 | 1.528 | 1.528 | 0 | 0 | 0 |  |  | 0 | 0
4 | NON-Detailed Project Report for the Work of Upgradation/Renovation of Crusher House of CHPB of Unit-5, 6&7 at CSTPS Chandrapur (benefit U-8,9 by short conveyor coal stacking in catering emergency) | 0 | - | 0 | 2.8807 | 2.8807 | 0 | 0 | 0 |  |  | 0 | 0
5 | Extention of stacker reclaimer area for improvement in coal stack management at CHP-D CSTPS Chandrapur U-8,9 | 0 | - | 0 | 8.46 | 8.46 | 0 | 0 | 0 |  |  | 0 | 0
6 | Retrofitting of BHEL make HT Circuit Breaker with SF6 Contactor at CHP-D, Unit-8&9 | 0 | - | 0 | 4.25 | 4.25 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 687.5835 | 739.5539 | -51.9704 | 965.855 | 965.855 | 0 | 0 | 965.855 | -51.9704
FY 2026-27
A) Approved Add Cap (Case No. 296 of 2019)
1 | Initial Spares | Approved Add Cap (Case No. 296 of 2019)
| Boiler & Auxiliaries | 0 | - | 10.36 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Bevel Helical Gear box KMP-350 for XRP 1043 coal mills at unit-8&9,CSTPS, Chandrapur. | 0 | - | 0 | 7.4087 | 7.4087 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Hydraulic Adjustment (Actuating) Device for PA fan model PAF 19/10.6-2 and FD fan FAF 23/12.5-1 at Unit 8&9, CSTPS, Chandrapur. | 0 | - | 0 | 1.3971 | 1.3971 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Yokogawa make Zirconia Oxygen Analyser spares for C&I-III, Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 0.51933 | 0.51933 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of High pressure valves installed at unit-8&9 ( 2x500 MW),CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Turbine & Aux | 0 | - | 1.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of IMI Norgren Herion make Trip solenoid valves for Main Turbine, MD-BFP & TD-BFP of Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.37354 | 0.37354 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Speed Sensors for 500 MW KWU Turbine for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.038232 | 0.038232 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Position Feedback Transmitters for Starting Device and Speeder Gear of Main Turbine for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.11225 | 0.11225 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for LP bypass system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur on OEM Basis. | 0 | - | 0 | 0.43645 | 0.43645 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of TSE (Turbine Stress Evaluator) temperature elements for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.2073 | 0.20719 | 0.00010699 | 0 | 0 |  |  | 0 | 0.00010699
| Generator and Auxiliries | 0 | - | 0.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of complete set of water cooled bushing for 500MW Generator installed at Unit-8 & 9, CSTPS Chandrapur. | 0 | - | 0 | 0.26409 | 0.26409 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Tushaco make complete AC Jacking Oil Pump for Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.19949 | 0.19949 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of oil filled Neutral Grounding Transformer for AHP Unit-8&9 CSTPS , Chandrapur. | 0 | - | 0 | 0.34775 | 0.34775 | 0 | 0 | 0 |  |  | 0 | 0
| Electrical and Instrumentation | 0 | - | 29.23 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| ‘Procurement of various spares of BHEL make Vacuum Circuit Breakers’ , for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.49498 | 0.49498 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, erection and commissioning of floor mounted 500KW Resistor Load Bank for D.G. sets installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.27536 | 0.27536 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Turbosupervisory system spares of main turbine for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 1.0366 | 1.0366 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Level transmitters for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.15999 | 0.15999 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Level transmitters for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.032605 | 0.032605 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Level transmitters for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.046973 | 0.046973 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of GE PLC spares for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.57304 | 0.57304 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for GEHO pumps PLC control panels for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.084378 | 0.084378 | 2.6e-08 | 0 | 0 |  |  | 0 | 2.6e-08
| Procurement of master calibration lab Instruments for C&I-III, Unit 8 & 9,CSTPS,Chandrapur | 0 | - | 0 | 0.30131 | 0.30131 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Coal Feeder panel spares for C&I-III, Unit 8 & 9,CSTPS, Chandrapur | 0 | - | 0 | 0.58701 | 0.58701 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Opacity Monitor (Stack Particulate matter-SPM) spares for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.14051 | 0.14051 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Forbes Marshall Supervisory system spares For Turbine driven boiler feed pumps (TDBFP) of Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.22449 | 0.22449 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for hydraulic panel of CW pumps for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.13862 | 0.1386 | 1.7196e-05 | 0 | 0 |  |  | 0 | 1.7196e-05
| Procurement of H2 Dew point analyzer spares for Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.049938 | 0.049938 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for HP bypass system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.33965 | 0.33965 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Position feedback transmitter for HP bypass system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.0354 | 0.0354 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Atlas Copco make Instrument, Service and Conveying air Compressors for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.22509 | 0.22509 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for HEA Ignitors and Flame Scanners for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.037701 | 0.037701 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for GEHO pumps of Ash Handling System at C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.28861 | 0.28861 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Turbine side control valve spares for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.17974 | 0.17974 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various numerical protection relays for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.12307 | 0.12307 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various numerical protection relays for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.13184 | 0.13184 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various numerical protection relays for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.13863 | 0.13863 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for DB POWER make UPS system installed at HCSD Pump House, Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.064757 | 0.064757 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Fully Automatic Capacitance & Dissipation Factor (Tan- Delta) measuring kit for Unit-8 &9, CSTPS, Chandrapur. | 0 | - | 0 | 0.48288 | 0.48288 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of various VFD spares for ID fans of Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.546 | 0.546 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of DAVR spares installed at Unit -8&9 CSTPS, Chandrapur. | 0 | - | 0 | 0.5945 | 0.5945 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 3 phase relay test kit for Unit-8 &9, CSTPS, Chandrapur. | 0 | - | 0 | 0.35388 | 0.35388 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Fast Bus Transfer System (FBTS) installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.37288 | 0.37288 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various spares for battery chargers installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.40022 | 0.40022 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Auto synchronizing Relay (ASR) & Load Shedding Relay (LSR) installed at Unit-8 &9, CSTPS, Chandrapur. | 0 | - | 0 | 0.34973 | 0.34973 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ESP spares i.e. Field Controller, Thyristor and Trigger card for ESP of Unit-8 & 9, CSTPS Chandrapur. | 0 | - | 0 | 0.26745 | 0.26745 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various VFD spares for GEHO pump of Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.54416 | 0.54416 | 0 | 0 | 0 |  |  | 0 | 0
| Design, Supply, Erection & Commissioning of On-Line Dissolved Gas Analyzers for various Transformers installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 3.1775 | 3.1775 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, Erection & Commissioning of On-Line Dissolved Gas Analyzers for Station Transformers -8B, Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.30519 | 0.30519 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘TOROSHIMA’ make 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motor (without pump casing) for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 4.2037 | 4.2037 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 90kVA ESP Rectiformer for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.29878 | 0.29878 | 0 | 0 | 0 |  |  | 0 | 0
| Supply erection & commissioning of Aviation Lighting for NDCT of Unit-8&9, CSTPS Chandrapur | 0 | - | 0 | 0.57261 | 0.57261 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Transformer oil storage tanks of different capacity for Unit-8&9 CSTPS Chandrapur. | 0 | - | 0 | 0.57024 | 0.57024 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 2000kW & 315kW, 6.6 kV HT motors for CW & ACW Pump installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 1.4505 | 1.4505 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 3.25MVA, 6.6/2.3kV VFD Transformers of vector group DY11 for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.3941 | 0.3941 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 3.25MVA, 6.6/2.3kV VFD Transformer of vector group ‘Dd0’ for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.3905 | 0.3905 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘MARATHON’ makes HT/LT Induction motors for various Critical auxiliaries installed at Unit-8 &9, CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of 1.2V, Ni-Cd battery cells for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.12496 | 0.12496 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of 1.2V, Ni-Cd battery cells for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.18931 | 0.18931 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘Air Core DC Reactor’ for VFD and ‘NGR’ for UAT/ Station Transformers installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.44368 | 0.44368 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘Air Core DC Reactor’ for VFD and ‘NGR’ for UAT/ Station Transformers installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.12551 | 0.12551 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘BHEL’ make 680 KW, 6.6KV, Coal Mill Motor for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.37913 | 0.37913 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 400kV OIP Condenser Bushing for Generator Transformer & Station Transformer of Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.49064 | 0.49064 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘11kW DC motor with Control Cabinet’ for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.2242 | 0.2242 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 37kW, 415V motors for Primary Water Pump installed at Unit-8 &9, CSTPS Chandrapur. | 0 | - | 0 | 0.0096851 | 0.0096851 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 15 KW, 415V LT Motor for Service Building & TG Building Lift installed at Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.095155 | 0.095155 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 16KW, 415V LT Motor for Boiler Lift installed at Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.044179 | 0.044179 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, Erection, Testing and Commissioning of Hydrastep-Electronic Drum Level Indicator and its associated accessories for Unit-9, CSTPS, Chandrapur | 0 | - | 0 | 0.27376 | 0.27376 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for BHEL make Hydrastep (Electronic Water Level Indicator -BHELVISION 20M) for Unit 8 & 9, CSTPS, Chandrapur on OEM basis. | 0 | - | 0 | 0.084172 | 0.084172 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Electrodes for Hydrastep (Electronic Water Level Indicator -BHELVISION 20M) for Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.10384 | 0.10384 | 0 | 0 | 0 |  |  | 0 | 0
| Engineering & Retrofitting of 196 NT Controller to DT 9 Controller for Unit-8 & 9 Coal Feeder System. | 0 | - | 0 | 0.38076 | 0.38076 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for BHEL make Acoustic steam leak detection system (BHELSONIC) (BS10) for Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.077807 | 0.077807 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of LT Circuit Breaker assemblies for ESP LT Panels (LTMSB & ACP) of Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.25429 | 0.25429 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for BHEL make maxDNA Distributed control system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 1.117 | 1.117 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of Transformer oil BDV test kit DTA 100C and Oil Tan Delta & Resistivity Tester DTL C at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.47598 | 0.47598 | 0 | 0 | 0 |  |  | 0 | 0
| Outdoor Plant ( CHP/AHP/WTP) | 0 | - | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Elecon make KCN-560 type Gearbox for Apron Feeder installed at CHPD, CSTPS. | 0 | - | 0 | 1.6717 | 1.6717 | -6e-08 | 0 | 0 |  |  | 0 | -6e-08
| Procurement of spares of CKB-280,225,200,8180 typ gearbox installed at CHP-D | 0 | - | 0 | 1.0015 | 1.0015 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Gear Box (MAKE: NEW ALLENBERRY) Spares at CHP-D; CSTPS, Chandrapur. | 0 | - | 0 | 0.5177 | 0.5177 | 1.8e-08 | 0 | 0 |  |  | 0 | 1.8e-08
| Procurement of spares for m/s Elecon make Impact Crusher installed at CHP Unit 8&9 CSTPS, Chandrapur | 0 | - | 0 | 0.84103 | 0.84103 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of V belt pulley of rotor for Impact crusher installed at CHP-D, CSTPS | 0 | - | 0 | 0.11864 | 0.11864 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Spares for hydraulic systems installed at CHPD, CSTPS. | 0 | - | 0 | 0.47537 | 0.47537 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Spares for hydraulic systems installed at CHPD, CSTPS. | 0 | - | 0 | 0.028604 | 0.028604 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of drive & non drive pulley for various conveyors installed at CHP D, CSTPS, Chandrapur. | 0 | - | 0 | 0.25792 | 0.25792 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of drive & non drive pulley for various conveyors installed at CHP D, CSTPS, Chandrapur. | 0 | - | 0 | 0.0914 | 0.0914 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Chain links for apron feeder installed at CHP D, CSTPS, Chandrapur. | 0 | - | 0 | 0.40289 | 0.40289 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of internal spares for Elecon make PWD-18, PLB-25 & SCN-180 type Gearbox for Stacker Reclaimer & wobbler feeder installed at CHP D, CSTPS. | 0 | - | 0 | 0.52774 | 0.52774 | 3.1e-08 | 0 | 0 |  |  | 0 | 3.1e-08
| Supply of GE Make Switchgear Spares for GE Make LT Feeders | 0 | - | 0 | 0.12485 | 0.12485 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Fluidomat make scoop coupling installed at CHP–D, CSTPS, Chandrapur | 0 | - | 0 | 0.48355 | 0.48355 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Oil Filtering machine for hydraulic power packs installed at CHPD, CSTPS | 0 | - | 0 | 0.10592 | 0.10592 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of LT Motors at CHP-D (U#8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0.11302 | 0.11302 | 0 | 0 | 0 |  |  | 0 | 0
| Supply and Installation of Oil Cooled Suspended Anodized Winding Magnet & Control Panel at CHP, Unit 8&9, CSTPS, Chandrapur. | 0 | - | 0 | 2.2967 | 2.2967 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of LT power and control cable for CHP-D | 0 | - | 0 | 0.26256 | 0.26256 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of LT power and control cable for CHP-D | 0 | - | 0 | 0.0477 | 0.0477 | 0 | 0 | 0 |  |  | 0 | 0
2 | Capital Spare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| HPT MODULE | 0 | - | 45.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of HP turbine Module along with breach nuts and pipe spool pieces (Type: H30-100-2) for Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 32.332 | 32.332 | 0 | 0 | 0 |  |  | 0 | 0
| LPT ROTOR | 0 | - | 40.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Fully Bladed & Dynamically Balanced LP Rotor (N30-2X10-2) for Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 29.03 | 29.03 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of set of Free Standing Moving Blades for LP Rotor (N30-2X10-2) for Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 4.5629 | 4.5629 | 0 | 0 | 0 |  |  | 0 | 0
| BFP CARTRIDGE ( 2NOS ) | 0 | - | 4.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of cartridge assembly for Boiler Feed Pump model FK-4E-36 (with Four S/H & 2 R/H spray branches) installed at 2X 500MW, CSTPS, Chandrapur. | 0 | - | 0 | 2.515 | 2.5149 | 6e-05 | 0 | 0 |  |  | 0 | 6e-05
| BCW PUMP | 0 | - | 3.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for ‘TOROSHIMA’ make 350KW BCW Pump-Motor installed at Unit-8 &9, CSTPS Chandrapur. | 0 | - | 0 | 1.3283 | 1.3283 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various spares for ‘TOROSHIMA’ make Boiler Circulating Water (BCW) pump-motor installed at Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 2.2326 | 2.2326 | 0 | 0 | 0 |  |  | 0 | 0
| 15 MVA DRY TYPE TRANSFORMER | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spare ‘Cast Resin Dry Type Transformers (CRTs)’ of different ratings for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 6.0213 | 6.0213 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of phase coil limb and spares of Cast Resin Dry Type Transformers of different ratings for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 7.9255 | 7.9255 | 0 | 0 | 0 |  |  | 0 | 0
| BTG+BOP& Other Works | 0 | - | 20.48 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Design, Supply & Installation, Testing & Commissioning of Public Addressing System for tunnels of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 1.1544 | 1.1544 | 0 | 0 | 0 |  |  | 0 | 0
| Work of upgradation, installation and extension of 220VDC control supply to various PMCC of CHPD, CSTPS, Chandrapur. | 0 | - | 0 | 0.68441 | 0.68441 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Apron Feeder in CHP Unit 8&9 (2x500) MW at CHP-D, CSTPS. | 0 | - | 0 | 2.3388 | 2.3388 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of spares for up gradation of rotary parts of travelling conveyor system installed at CHPD, CSTPS, Chandrapur. | 0 | - | 0 | 0.58939 | 0.58939 | 0 | 0 | 0 |  |  | 0 | 0
| The Work of Design, Engineering, Manufacturing, Supply, Erection & Commissioning of Short Conveyor belt from stack yard of CHP of Unit 5,6&7 to Belt Conveyor 104 A/B at CHP of Unit 8&9, CSTPS, Chandrapur | 0 | - | 0 | 5.6825 | 5.6825 | 0 | 0 | 0 |  |  | 0 | 0
| Work of design, supply, erection, commissioning of overhead cable tray along with removal & re-routing of power and control cables at CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0.51324 | 0.51324 | 0 | 0 | 0 |  |  | 0 | 0
| Work of provision, modification, retrofitting and revamping of lighting system of transfers points, crusher house and bunker area of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 1.0105 | 1.0105 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for M/s. Weir Minerals make (GEHO pump Model TZPM-1200) for Ash Handling Plant Unit# 8 &9 CSTPS Chandrapur. AHP-III | 0 | - | 0 | 2.106 | 2.106 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Gear Box set of internal (MAKE: NEW ALLENBERRY) Spares at CHP-D; CSTPS, Chandrapur. | 0 | - | 0 | 1.6904 | 1.6904 | 0 | 0 | 0 |  |  | 0 | 0
| Supply and Installation of Oil Cooled Suspended Anodized Winding Magnet & Control Panel at CHP, Unit 8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 196 NT Controller by DT 9 Controller alongwith HMI units for Unit- 8&9 coal feeder system | 0 | - | 0 | 2.0774 | 2.0774 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of set of CW Impeller duly fitted with wear rings & ACW Impeller duly fitted with wear rings of Mather & Platt make Pumps installed at Unit-8 & 9,CSTPS,Chandrapur | 0 | - | 0 | 0.70379 | 0.70379 | 0 | 0 | 0 |  |  | 0 | 0
| CHP System U#8 | 0 | - | 0 | 0.05 | 0.05 | 0 | 0 | 0 |  |  | 0 | 0
| ISOLATED PHASE BUS DUCT | 0 | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| SEGREGATED PHASE BUS DUCT U#8 | 0 | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| SEGREGATED PHASE BUS DUCT U#9 | 0 | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| ISOLATED PHASE BUS DUCT U#9 | 0 | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| DTT & UAT U#8 | 0 | - | 0 | 0.03 | 0.03 | 0 | 0 | 0 |  |  | 0 | 0
| DTT & UAT U#9 | 0 | - | 0 | 0.03 | 0.03 | 0 | 0 | 0 |  |  | 0 | 0
| Cranes and hoists U#8 | 0 | - | 0 | 0.03 | 0.03 | 0 | 0 | 0 |  |  | 0 | 0
| RCC Chimney U#8 | 0 | - | 0 | 9.29 | 9.29 | 0 | 0 | 0 |  |  | 0 | 0
| Coal Handling Plant | 0 | - | 0 | 41.79 | 41.79 | 0 | 0 | 0 |  |  | 0 | 0
| Bunker foundation & civil works (Unit 8) U#8 | 0 | - | 0 | 18.58 | 18.58 | 0 | 0 | 0 |  |  | 0 | 0
| Boiler & Auxiliaries U#9 | 0 | - | 0 | 9.2889 | 9.2872 | 0.0017338 | 0 | 0 |  |  | 0 | 0.0017338
| ESP U#9 | 0 | - | 0 | 2.1589 | 2.1589 | 0 | 0 | 0 |  |  | 0 | 0
| ID fan foundations (Unit 9) U#9 | 0 | - | 0 | 1.7489 | 1.7489 | 0 | 0 | 0 |  |  | 0 | 0
| DRY ASH SILO-12M DIA U#8 | 0 | - | 0 | 1.22 | 1.22 | 0 | 0 | 0 |  |  | 0 | 0
| FD fan foundations (Unit 9) U#9 | 0 | - | 0 | 0.62891 | 0.62891 | 0 | 0 | 0 |  |  | 0 | 0
| PA fan foundations (Unit 9) U#9 | 0 | - | 0 | 0.54891 | 0.54891 | 0 | 0 | 0 |  |  | 0 | 0
| Natural Draft cooling tower- Unit 8 U#8 | 0 | - | 0 | 0.32 | 0.32 | 0 | 0 | 0 |  |  | 0 | 0
| Main power house building-Civil Works-Unit no.-9 U | 0 | - | 0 | 0.15 | 0.15 | 0 | 0 | 0 |  |  | 0 | 0
| Structural Steel works for main power house buildi | 0 | - | 0 | 0.15 | 0.15 | 0 | 0 | 0 |  |  | 0 | 0
| Canteen U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Security and time office U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| CARS SCOOTERS AND CYCLE SHED U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Fire Station U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Watch towers U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| First aid station | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Tranformer yard U#8 | 0 | - | 0 | 0.02 | 0.02 | 0 | 0 | 0 |  |  | 0 | 0
| Rain Water Harvesting Scheme U#8&9 | 0 | - | 0 | -0.01 | -0.01 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Advance Multipurpose Fire Tender | 0 | - | 0 | 3.45 | 3.45 | 0 | 0 | 0 |  |  | 0 | 0
| DM Stream | 0 | - | 29.65 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| DM Stream capacity of 100 M3/Hr in addition to existing stream of WTP. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| CIVIL | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Bridge | 0 | - | 4.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Railway, CHP, AHP etc | 0 | - | 152.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| B. G. railway siding Pway works | 0 | - | 0 | 41.5165 | 41.5165 | 0 | 0 | 0 |  |  | 0 | 0
| S & T work for B.G. railway siding | 0 | - | 0 | 0.023574 | 0.023574 | 0 | 0 | 0 |  |  | 0 | 0
| Consultancy services for B. G. railway siding | 0 | - | 0 | 0.035636 | 0.035636 | 0 | 0 | 0 |  |  | 0 | 0
| Ash infra in Railway | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Bunker structure (Unit 8) U#8 | 0 | - | 0 | 18.57 | 18.57 | 0 | 0 | 0 |  |  | 0 | 0
| Coal Mills | 0 | - | 0 | 1.1389 | 1.1389 | 0 | 0 | 0 |  |  | 0 | 0
| Bunker foundation & civil works (Unit 9) U#9 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Bunker structure (Unit 9) U#9 | 0 | - | 0 | 0.11 | 0.11 | 0 | 0 | 0 |  |  | 0 | 0
| HCSS silo-12m dia U#8 | 0 | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| Ash water PH, HCSD PH, Bottom ash slurry PH U#8 | 0 | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| Ash compressor house & Control room U#8 | 0 | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| MILL REJECT SILO U#8 | 0 | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| Fire protection & Detection system U#8 | 0 | - | 0 | 0.71423 | 0.71423 | 0 | 0 | 0 |  |  | 0 | 0
| DM Water Pump room U#8 | 0 | - | 0 | 4.25 | 0 | 4.25 | 0 | 0 |  |  | 0 | 4.25
| Filter water reservoir & pump house U#8 | 0 | - | 0 | 4.29 | 0 | 4.29 | 0 | 0 |  |  | 0 | 4.29
| ACW + RW + Filtered water piping U#8 | 0 | - | 0 | 2.2409 | -0.0096938 | 2.2506 | 0 | 0 |  |  | 0 | 2.2506
| Laboratory Building U#8 | 0 | - | 0 | 0.12 | 0 | 0.12 | 0 | 0 |  |  | 0 | 0.12
3 | Staff quarters | 0 | - | 15.04 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Work of exterior repair, providing painting to A, D & E type residential buildings and Public Buildings and allied civil works in Urjanagar Colony, CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Staff Quarters- Repair and renovation of E type staff quarters to extend the life of buildings at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Staff Quarters - Repair and renovation of 'B' type staff quarters in residential colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair of D type quarters in colony at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair of C type quarters in colony at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Staff Quarters- Repair and renovation of F and NF type staff quarters to extend the life of buildings at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair and replacement of existing drinking water supply pipelines in E & F type area in colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair and replacement of existing sewer lines in E & F type area in colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Work of providing RCC drain along main roads in colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Rerouting and replacement of domestic water supply pipeline from WTP to ESR in colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Additional Contengencies approved vide e BR No. MSPGCL/BM-162/165, Dt.29.10.2016 vide resolution no. 2016/2085 | 0 | - | 7.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Landscaping and plantation work at various locations inside plant area at CSTPS, chandrapur. | 0 | - | 0 | 3.4266 | 3.4266 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of WBM approach road from point- N to Z Area along ash bund periphery at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design, Engineering, Supply and commissioning of ash-bund water recovery system (Phase II) at CSTPS Chandrapur | 0 | - | 27.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, Engineering, Supply and commissioning of ash-bund water recovery system (Phase II) at CSTPS Chandrapur | 0 | - | 0 | 30.0361 | 30.0361 | 0 | 0 | 0 |  |  | 0 | 0
| Providing Consultancy Services for work of Design, Engineering, Supply, Installation & Commissioning of ash bund water recovery system (Phase-II) at CSTPS, Chandrapur (on EPC contract basis). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Providing laying, jointing and commissioning of 1600 mm dia. M.S. Pipe line from Erai dam to one day reservoir of stage II, III & IV at CTPS | 0 | - | 73.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Providing laying, jointing and commissioning of 1600 mm dia. M.S. Pipe line from Erai dam to one day reservoir of stage II, III & IV at CTPS | 0 | - | 0 | 73.6091 | 73.6091 | 0 | 0 | 0 |  |  | 0 | 0
| Work of construction of Control Valve rooms on newly laid 1600 mm M.S. Pipeline no. 6 from Erai dam to One day reservoir at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Providing OHE facility for BG Rly siding of proposed Expansion Project at Chandrapur, for Supply of Materials. | 0 | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Providing OHE facility for BG Rly siding of proposed Expansion Project at Chandrapur, for errection of OHE Items. | 0 | - | 2.5 | 0.7 | 0 | 0.7 | 0 | 0 |  |  | 0 | 0.7
9 | Irrigation scheme for landscaping and Plantation work at Chandrapur expansion project chandrapur. | 0 | - | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Asphalting of WBM road from Nagpur gate to Awanda gate. | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Asphalting of WBM road from Nagpur gate to Awanda gate. | 0 | - | 0 | 0.65141 | 0 | 0.65141 | 0 | 0 |  |  | 0 | 0.65141
| Asphalting over WBM Road of ADP line Service road from Nagpur gate opening to Awandha junction gate at CSTPS Chandrapur | 0 | - | 0 | 0.84833 | 0.84833 | 0 | 0 | 0 |  |  | 0 | 0
| Asphalting of WBM road from Nagpur gate to Awandha gate at CSTPS Chandrapur - Asphalting of road from Reject coal gate to Motghat nallah at CSTPS Chandrapur (PHASE - I) | 0 | - | 0 | 0.47941 | 0.47941 | 0 | 0 | 0 |  |  | 0 | 0
11 | Foot Over Bridge | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Work of Providing retaining wall for sand hump at Vivekanand nagar station yard under modification work in wardha end fro 2 x 500 MW Expn. Project at CSTPS, Chandrapur. | 0 | - | 0.3 | 0.25515 | 0.25515 | 0 | 0 | 0 |  |  | 0 | 0
| Additional Capitalization by O & M | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of GE make 4000Amp LT Air Circuit Breakers for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0.9 | 1.0308 | 1.0308 | 0 | 0 | 0 |  |  | 0 | 0
2 | Air Compressor System | 0 | - | 0.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Energy management Sysytem | 0 | - | 0.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, Installation, Testing & Commissioning of Energy Management System for Unit#8 & 9 for CSTPS, Chandrapur. | 0 | - | 0 | 0.20054 | 0.20054 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Tri-vector 0.2s class Digital Energy meter for Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.094872 | 0.094872 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, Installation & Commissioning of 3D Level Scanners to 64 nos. of ESP hoppers at Unit-8&9 (2X500MW), CSTPS, Chandrapur. | 0 | - | 3.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of internal spares for Elecon make PWD-18, PLB-25 ,Pbh-71 type Gearbox for Stacker Reclaimer installed at CHPD, CSTPS. | 0 | - | 0 | 1.1089 | 1.1089 | 0 | 0 | 0 |  |  | 0 | 0
5 | 4000/2500/1800/800 A GE make LT CKT Brkr | 0 | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| LT Air Circuit Breakers for Incomer Feeders at CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 1.4207 | 1.4207 | 0 | 0 | 0 |  |  | 0 | 0
| LT Air Circuit Breakers at CHP, Unit 8&9, CSTPS | 0 | - | 0 | 1.0141 | 1.0141 | 0 | 0 | 0 |  |  | 0 | 0
6 | Replacement of Impact crusher by hammer mill crusher (installed qty.2 No) | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Replacement of wobbler feeder 1&2 by grizzly screen at CHP-D | 0 | - | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Installation of conveyor system from rope way of CHP-A and crusher house of CHP-D | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| PLC based control & instrumentation of 6.6 KV HT motors of 1250 KW of Crusher I & II and 200 KW of BC 108A1 & A2 at CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0.93628 | 0.93628 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Design, Supply, Erection & Commissioning of Complete Electrical Automation for Short Conveyor from stack yard of CHP-D to Belt Conveyor 107 A/B of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0.70095 | 0.70095 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Design, Supply, Erection & Commissioning of Complete Electrical Automation for Short Conveyor from stack yard of CHP-B to Belt Conveyor 104 A/B of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 2.2368 | 2.2368 | 0 | 0 | 0 |  |  | 0 | 0
| WORK OF DESIGN, ENGINEERING, MANUFACTURING, SUPPLY, ERECTION &COMMISSIONING OF SHORT CONVEYOR BELT FROM STACK YARD OF CHP UNIT-8&9 TO CONVEYOR BELT 107A AND B AT CHP UNIT 8&9, CSTPS, CHANDRAPUR. | 0 | - | 0 | 4.6948 | 4.6948 | -2.4e-08 | 0 | 0 |  |  | 0 | -2.4e-08
| Design, Supply, Installation and Commissioning of High Performance Energy Chain System for Side Arm Charger and Stacker Reclaimer of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 3.8916 | 3.8916 | 0 | 0 | 0 |  |  | 0 | 0
| RBF 103 &104,105 & 106, 107 & 108, and 109 & 110 in to modular Y chute | 0 | - | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-103 & RBF-104 with Design, development, Manufacturing, Supply & erection of modular Chute as per site condition in place of RBF using sintered silicon Carbide plate with motorized Flap Gate at CHP-D, CSTPS. | 0 | - | 0 | 1.1741 | 1.1741 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-105 & RBF-106 with Design, development, Manufacturing, Supply & erection of modular Chute as per site condition in place of RBF using sintered silicon Carbide plate with motorized Flap Gate at CHP-D, CSTPS. | 0 | - | 0 | 1.3169 | 1.3169 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-107 & RBF-108 with Design, development, Manufacturing, Supply & erection of modular Chute as per site condition in place of RBF using Tungsten Carbide plate with Flap Gate at CHP-D, CSTPS. | 0 | - | 0 | 1.1529 | 1.1529 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-109 & RBF-110 with design, erection & Installation by trajectory calculation & removal of existing RBF with Y Chute assembly by flow control with Flap Gate arrangement at TP-107 of CHP-D, CSTPS. | 0 | - | 0 | 1.1506 | 1.1506 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurment , Installation and commissioning of Online Insertable Camera systems for Unit-8, 500MW, CSTPS | 0 | - | 8.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, Supply, Installation & Commissioning of Energy efficient system for Illumination at Unit 8&9 CSTPS, Chandrapur. | 0 | - | 0 | 4.9494 | 4.9494 | 0 | 0 | 0 |  |  | 0 | 0
11 | Construction of Chemical godown shed for unit 8 & 9 at CSTPS,Chandrapur. | 0 | - | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of Chemical godown shed for unit 8 & 9 at CSTPS,Chandrapur. | 0 | - | 0 | 0.42946 | 0.42946 | 0 | 0 | 0 |  |  | 0 | 0
| Comprehencive work of installation, erection, testing and commissioning of MVWS spray system/ Fire safety system for new Bulk Chemical storage godown at CSTPS, Unit 8&9 | 0 | - | 0 | 0.27583 | 0.27583 | 0 | 0 | 0 |  |  | 0 | 0
| Work of electrification of godown for bulk chemical storage near FOPH building at Chandrapur project site. | 0 | - | 0 | 0.018322 | 0.018322 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of additional Chemical godown shed for storage of Lube oil at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Construction of RCC retaining wall for approach to RCC Bridge across Irai River, ADPL line at CSTPS | 0 | - | 8.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of RCC retaining wall for approach to RCC Bridge across Irai River, ADPL line at CSTPS | 0 | - | 0 | 4.3482 | 4.3482 | 0 | 0 | 0 |  |  | 0 | 0
| Asphalting of road from Reject coal gate to Motghat nallah at CSTPS Chandrapur (PHASE - II) | 0 | - | 0 | 0.87403 | 0.87403 | 0 | 0 | 0 |  |  | 0 | 0
| Providing extension to approaches of RCC bridge across Erai river by constructing WBM road at CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| UDL | 0 | - | 0 | 4.85 | 4.85 | 0 | 0 | 0 |  |  | 0 | 0
| B) DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (i) In Principally Approved By MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 1 | HMI (Human Machine Interface) Upgradation of ‘SSPA-T3000’ DCS (Distribution Control System), Rockwell make PLC System installed at 3x660MW Unit No. 8, 9 & 10 at Koradi TPS and HMI (Human Machine Interface) Upgradation of MaxDNA DCS System at Unit 8-9, CSTPS, Chandrapur | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 11.08 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 1.1 | Supply: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 10.52 | 10.52 | 21.02 | -10.5 | 0 | 0 |  |  | 0 | -10.5
HO DPR 1.2 | Works: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.41 | 0.41 | 0.81 | -0.4 | 0 | 0 |  |  | 0 | -0.4
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
40 | Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M with construction of concrete dam (Waste Weir & Non overflow structure), construction of drain wells, approach to drain wells and raising of ash compartment for ash bund along with renewal of Ash Disposal Pipe Line Service Road with WBM treatment at CSTPS, Chandrapur | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 4.9692 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 34.8665 | 34.8665 | 69.733 | -34.8665 | 0 | 0 |  |  | 0 | -34.8665
| Construction of New Drain Wells (12 Nos.) along with necessary connection to existing drain wells at CSTPS | 0 | - | 0.58493 | 0.58493 | 1.1699 | -0.58493 | 0 | 0 |  |  | 0 | -0.58493
| Construction of waste weir for raising of ash bund (Waste Weir & Non overflow structure) | 0 | - | 1.4621 | 1.4621 | 2.9241 | -1.4621 | 0 | 0 |  |  | 0 | -1.4621
| Raising of Ash Compartment i.e. Lagoon in Ash Bund | 0 | - | 8.7868 | 8.7868 | 17.5736 | -8.7868 | 0 | 0 |  |  | 0 | -8.7868
| IDC | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 7.634 | 7.634 | 15.2679 | -7.634 | 0 | 0 |  |  | 0 | -7.634
| IDC | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 4.9692 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
39 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 8-9) | MERC/CAPEX/2020-2021/WFH/SBR/21 | 2020-07-24 | 479.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
39.1 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 8-9) | MERC/CAPEX/2020-2021/WFH/SBR/21 | 2020-07-24 | 440.54 | 558.4 | 558.4 | 0 | 239.31 | 239.31 |  |  | 239.31 | 0 | 0 | 239.31
| IDC | MERC/CAPEX/2020-2021/WFH/SBR/21 | 2020-07-24 | 38.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41 | CHP Performance Improvement Schemes at Unit 8-9 of CSTPS, Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 26.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.1 | Work of Design engineering , supply and installation of modular chutes with sintered silicon carbide for smooth flow &center feeding in CHP 2x500MW CSTPS | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 9.43 | 9.43 | 9.43 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.2 | Supply erection & commissioning of set of internal of impact crusher spares installed at CHPP-D, CSTPS | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 8.05 | 8.05 | 8.05 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.3 | Scheme for replacement of Scoop coupling/Fluid coupling of conveyor BC-101A/B/C, BC-102A/B, BC-104A/B, BC-105A/B ,BC-106A/B, BC-111A/B/C/D, BC-110A1/B1, BC-110A/B Installed at CHP-D, CSTPS Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 4.67 | 4.67 | 4.67 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.4 | Supply erection & commissioning of set of internal of spares of stacker reclaimer installed at CHP-D, CSTPS Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 1.96 | 1.96 | 1.96 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.5 | Supply erection & commissioning of set of internal of spares of Wagon tippler installed at CHP-D, CSTPS Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 2.12 | 2.12 | 2.12 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 0.38 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 2 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 2.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 27.12 | 27.12 |  |  | 27.12 | 0 | 27.12 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
A6 | Supply, Installation & Commissioning of Online Coal Flow Monitoring & Balancing System at Unit-8-9, CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0457 Dt 26.07.2024 | 2024-07-26 | 34.21 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, installation and commissioning of Online Coal flow monitoring and balancing system for U- 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2024-2025/MSPGCL/0457 Dt 26.07.2024 | 2024-07-26 | 34.21 | 0 | 0 | 0 | 17.105 | 17.105 |  |  | 17.105 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0457 Dt 26.07.2024 | 2024-07-26 | 0.31 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
A7 | Providing, supplying, laying and commissioning of 1600 mm dia. M.S. Pipe by replacement of existing PSC raw water line from Erai dam to reservoir at CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 40.7945 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing, supplying, laying and commissioning of 1600mm dia. M.S. pipe by replacement of existing PSC raw water line from Erai dam to reservoir at CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 40.7945 | 0 | 0 | 0 | 40.7945 | 40.7945 |  |  | 40.7945 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 8.83 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
A8 | Adoption of Ozonization technique for disinfection of Cooling Water System at U # 8 & 9 | MERC/CAPEX/MSPGCL/2023-2024/0467 Dt 02.08.2024 | 2024-08-02 | 67 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Adoption of Ozonization technique for disinfection of Unit 8&9 Cooling Water at CSTPS. | MERC/CAPEX/MSPGCL/2023-2024/0467 Dt 02.08.2024 | 2024-08-02 | 67 | 33.5 | 33.5 | 0 | 33.5 | 33.5 |  |  | 33.5 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-2024/0467 Dt 02.08.2024 | 2024-08-02 | 2.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (ii) Submitted to MERC |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y1 | Multiple Schemes for Electrical Maintenance Section and Design, Engineering, Manufacturing, Testing, Unloading at site, E&C of 200MVA, 21/420KV Single Phase Generator Transformer for Unit # 8 & 9, CSTPS | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 10MW, 11kV Motor and its recommended spare for Boiler Feed Pump (BFP) | To be resubmitted | - | 0 | 0 | 0 | 0 | 4.95 | 4.95 |  |  | 4.95 | 0
| Replacement of NiCd battery sets installed for UPS of Fire Water Pump House, CMRH & SWAS lab of Unit 8 & 9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0.86 | 0.86 |  |  | 0.86 | 0
| Retrofitting of GE make LT Air Circuit Breakers of various current ratings and procurement of their recommended spares for Unit-8&9, CSTPS | To be resubmitted | - | 0 | 0 | 0 | 0 | 4.85 | 4.85 |  |  | 4.85 | 0
| Procurement of BHEL make 6.6kV and 11kV Vacuum Circuit Breakers for Unit-8&9, CSTPS Chandrapur | To be resubmitted | - | 0 | 0 | 0 | 0 | 2.07 | 2.07 |  |  | 2.07 | 0
| IDC | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y5 | Scheme-1: Procurement of assembly of baskets for Air Preheater of type 31.05 VIMT 2000 (72° PA), Scheme-2: Procurement of spares for PRDS station pressure control valves and Desuperheating spray Control valves in Boiler at U-8&9, CSTPS, Chandrapur, Scheme-3: Procurement of complete set of sky climber at U-8&9, CSTPS, Chandrapur. Scheme-4: Supply, erction, commissioning of oil free rotary screw compressors (including all Civil Electrical, C&I, Testing work) for CMRH system at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-1: Procurement of assembly of baskets for Air Preheater of type 31.5 VIMT 2000 (72° PA) at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 15.78 | 15.78 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-2: Procurement of spares for PRDS station pressure control valves and Desuperheating spray control valves in Boiler at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 6.09 | 6.09 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-3: Procurement of complete set of sky climber at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 3.16 | 3.16 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-4: Supply, erection, commissioning of oil free rotary screw compressors (including all Civil Electrical, C&I, Testing work) for CMRH system at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 8.3 | 8.3 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y6 &Y7 | Supply, Erection & commissioning/retrofitting of HT Circuit Breaker with SF6 Contactor at AHP at Unit-8&9 & CHP#D and Supply, Installation and Commissioning of MV VFD panel along with integrated online cell redundancy technology with VFD bypass feature arrangement for conveyors 103 A & B of CHP-B, C.S.T.P.S., Chandrapur & Design, engineering, manufacturing, testing, unloading at site, E&C of Two No of 200 MVA, 21/420 KV Single Phase Generator Transformers for Unit-8&9, CSTPS, Chandrapur. Through OEM | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme 1: Retrofitting of BHEL make HT Circuit Breaker with SF6 contactor at AHP, Unit#8&9, CSTPS. | To be resubmitted | - | 0 | 38.33 | 38.33 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme 2: Retrofitting of BHEL make HT Circuit Breaker with SF6 contactor at CHP#D, Unit#8&9, CSTPS. | To be resubmitted | - | 0 | 5.64 | 5.64 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme 3: Supply, Installation and Commissioning of MV VFD panel along with integrated online cell redundancy technology with VFD bypass feature arrangement for conveyors 103 A & B of CHP-B. | To be resubmitted | - | 0 | 4.03 | 4.03 | 0 | 0 | 0 |  |  | 0 | 0
| Design, engineering, manufacturing, testing, unloading at site, E&C of Two No of 200 MVA, 21/420 KV Single Phase Generator Transformers for Unit-8&9, CSTPS, Chandrapur. Through OEM | To be resubmitted | - | 0 | 0 | 0 | 0 | 21.07 | 21.07 |  |  | 21.07 | 0
| IDC | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (iii) Yet to be Submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Boiler Maintenance -III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of Air & Flue gas ducts of Boiler , Blade set and HAD for PA and FD Fan , SCAPH Coil, ID Fan spares at Unit-8&9 CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-1 Procurement of Air & flue gas expansion joints | 0 | - | 0 | 0 | 0 | 0 | 40 | 40 |  |  | 40 | 0
| Scheme-2 :Procurement of Blade Set and 2 sets of HAD of PA Fan. | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
| Scheme -3 Procurement of Blade Set and 2 sets of HAD of FD Fan. | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
| Scheme-4 Procurement of SCAPH Coil for unit- 8&9 | 0 | - | 0 | 0 | 0 | 0 | 6 | 6 |  |  | 6 | 0
| Scheme-5 :Procurement of ID Fan Impeller , Shaft and Blade set at unit-8 & 9, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 6 | 6 |  |  | 6 | 0
| Scheme 6: Procurment of Coal Fuel pipes for unit -8 &9 , CSTPS | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
2 | Procurement of LTSH and economiser for unit-8&9 CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of LTSH Coil assemsblies unit- 8&9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of economiser coil asemblies | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of existing belt type gravimetric coal feeders to gravimetric rotary weigh coal feeders of unit- 8&9, at CSTPS, Chandrapur | 0 | - | 0 | 10.03 | 10.03 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of Quick Erect Aluminum Boiler Scaffolding system or unit- 8 & 9, (2X500MW), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of Quick Erect Aluminum Boiler Scaffolding system or unit- 8 & 9, (2X500MW), CSTPS, Chandrapur. | 0 | - | 0 | 35 | 35 | 0 | 0 | 0 |  |  | 0 | 0
| Turbine Maintenance -III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Schemes for Improvement in availability & performance of TG auxiliaries at U-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 1. Procurement of BFP Booster Pump assembly for Unit-8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 3.2 | 3.2 |  |  | 3.2 | 0
| 2. Procurement of Boiler Feed Pump catridge with CI sealing for Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 3. Procurement of Modulating type Boiler Feed Pump Recirculation valve (06 Nos) assembly for Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
| 4. Procurement of HP Heater HPH-5B assembly for Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 8 | 8 |  |  | 8 | 0
| 5. Procurement of MDBFP working oil & lube oil coolers for Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 6. Procurement of TDBFP Turbine rotor K1401-2 at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 7.5 | 7.5 |  |  | 7.5 | 0
| 7. Procurement of Main TG Jacking oil pumps (2 Nos.) at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
| 8. Procurement of HP elements of ZR500 Atlas Copco make compressors along with inter & after coolers tube nest at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
| 9. Procurement of CW & ACW Pump spares at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
| 10. Procurement of condenser tubes at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 11. Procurement of HPCF Pump at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | DPR for performance improvement of Condenser Cooling water system & improvement in system reliability of auxiliary cooling water system installed at Unit-8&9, 2x500MW, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| DPR for performance improvement of Condenser Cooling water system & improvement in system reliability of auxiliary cooling water system installed at Unit-8&9, 2x500MW, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 17 | 17 |  |  | 17 | 0
3 | Procurement of main turbine IPT module at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of main turbine IPT module at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Electrical Maintenance -III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Proc of GTR, MDBFP, UPS battery, breakers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, engineering, manufacturing, testing, unloading at site, E&C of 200 MVA, 21/420 KV Single Phase Generator Transformer for Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 21.07 | 21.07 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of MDBFP motor and recommended spares The Fire Water Pump House UPS Battery set of 240V, 40AH Capacity (1.2V X 176 Cells ) Ni Cd Type Make- HBL The UPS Battery Set at SWAS Lab (Outdoor Area), 45AH Capacity (1.2 V X 276 Cells) Ni Cd type Make- HBL for Unit#8&9 The UPS Battery Set at CMRH (Outdoor Area), 69AH Capacity (1.2 V X 280 Cells) Ni Cd type Make- HBL for Unit#8&9 Retrofitting of 415V GE make ACB of various ratings along with allied spares. BHEL make Breakers and spares for 6.6 kV and 11kV panels | 0 | - | 0 | 15.07 | 15.07 | 0 | 0 | 0 |  |  | 0 | 0
2 | Design, engineering, manufacturing, testing, unloading at site, E&C of 80 MVA, 420/11/6.9 KV three Phase Station Transformer & 25MVA 21/6.9KV Three phase Unit Aux Transformer as a common pool spares for BTPS 500MW, Khaparkheda 500 MW and Unit-8&9, CSTPS, Chandrapur & Supply, installation, commissioning and testing of Station Batteries of Unit-8&9 CSTPS alongwith all outdoor batteries | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, engineering, manufacturing, testing, unloading at site, E&C of 80 MVA, 420/11/6.9 KV three Phase Station Transformer & 25MVA 21/6.9KV Three phase Unit Aux Transformer as a common pool spares for BTPS 500MW, Khaparkheda 500 MW and Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 22 | 22 |  |  | 22 | 0
| Supply, installation, commissioning and testing of Station Batteries of Unit-8&9 CSTPS alongwith all outdoor batteries | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| I&C -III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Upgradation of Analysis & Diagnostics system (A&D) for VMS and TSI system at Unit-8&9, CSTPS, Chandrapur.& other schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of Analysis & Diagnostics system (A&D) for VMS and TSI system at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 17 | 17 | 0 | 0 | 0 |  |  | 0 | 0
| Installation of CO analysers at Eco outlet at Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
| Complete Engineering Retrofitting of Existing 196 NT Controller by DT 9 Controller alongwith HMI units for Unit 8/9 coal feeder system. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of spares for LP bypass system. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of spares for maxDNA DCS system | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
2 | Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-9, CSTPS, Chandrapur. | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
3 | Upgradation of HMI and hardware of GE make PLCs installed at Unit-8&9, CSTPS, Chandrapur. & other schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of HMI and hardware of GE make PLCs installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 15 | 15 |  |  | 15 | 0
| Upgradation of TD-BFP Turbovisory system installed at Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
| Upgradation of EWLI system installed at Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
| Upgradation of O2 analysers installed at Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
| Installation of High temperature Camera system at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
| Up-gradation of HEA igniter system at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
| Up-gradation of Flue Gas Analysers and Opacity Analysers at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
4 | Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-8, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-8, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Multiple schemes C&I-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Total Mercury (Gaseous) Analyzers along with their online data connectivity & Remote calibration U-3 to 9 | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
| Procurement of Controllers & Com Boxes for Air Compressors of Unit-8&9. | 0 | - | 0 | 0 | 0 | 0 | 5.5 | 5.5 |  |  | 5.5 | 0
| Up-gradation of Steam and Water Analysis System (SWAS) for Unit – 8 & 9 | 0 | - | 0 | 0 | 0 | 0 | 13 | 13 |  |  | 13 | 0
| Up-gradation of Servo valve (ST) with proportional valves (PV) for HP bypass system at Unit – 8 & 9 | 0 | - | 0 | 0 | 0 | 0 | 6 | 6 |  |  | 6 | 0
| Upgradation of GEHO pump VFD panels for Unit – 8 & 9 | 0 | - | 0 | 0 | 0 | 0 | 9 | 9 |  |  | 9 | 0
6 | Upgradation of measurement and control system installed at CSTPS Unit 8&9 & Upgradation of Numerical Protection Relay of Alstom / Schnieder make installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of measurement and control system installed at CSTPS Unit 8&9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of Numerical Protection Relay of Alstom / Schnieder make installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| AHP-III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | supply of piston cylinder assembly, diaphragm assembly, Suction and discharge valve housing assembly of GEHO pump (Model- TZPM 1200). & other schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-1 :supply of piston cylinder assembly, diaphragm assembly, Suction and discharge valve housing assembly of GEHO pump (Model- TZPM 1200). | 0 | - | 0 | 0 | 0 | 0 | 13 | 13 |  |  | 13 | 0
| Scheme -2 :Procurement of sub assemblies for conveying air compressor model ZR 275 and instrument air compressor model ZR 110 in Ash handling plant Unit-8&9 (2x500MW) at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 18 | 18 |  |  | 18 | 0
| Scheme -3 Supply of 10/8 FAH Warman make slurry pump impeller element assembly, Bearing assembly unit, jacket assembly. | 0 | - | 0 | 0 | 0 | 0 | 12 | 12 |  |  | 12 | 0
2 | Supply and replacement of 400 NB MSERW pipeline of ash disposal system of unit 8&9 at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 :Supply and replacement of 400 NB MSERW pipeline of ash disposal system of unit 8&9 at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Complete ESP Refurbishment of 1st & 2 nd Row Field of Unit 8&9 at CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 : Complete ESP Refurbishment of 1st & 2 nd Row Field of Unit 8&9 at CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP - D | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Upgradation Of Hydraulic Systems with Safety Mechanism for wagon unloading system at CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply erection & commissioning of wagon tippler, Side Arm Charger, apron feeder and stacker hydraulic drive system with online NAS value monitoring systems. | 0 | - | 0 | 8 | 8 | 0 | 8 | 8 |  |  | 8 | 0
0 | Wagon stopping mechanism (Safety) | 0 | - | 0 | 2 | 2 | 0 | 2 | 2 |  |  | 2 | 0
2 | Upgardation and Capacity Enhancement of Side Arm Charger Apron Feeder and Bunker Conveyors at CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | capacity enhancement to 60 wagons pulling capacity and associated modification of existing side arm charger | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
0 | Capacity enhancement , Commissionng of apron feeder drive | 0 | - | 0 | 2 | 2 | 0 | 2 | 2 |  |  | 2 | 0
0 | Modification and revamping of Apron Feeder 101,102,103 | 0 | - | 0 | 5 | 5 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
0 | Supply,Installation and Commissioning of double drive Mechanism with Split Case Bearings for Tripper Trolley and bunkering conevyor belts of CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 15 | 15 |  |  | 15 | 0
0 | Modification of Fixed Tripper Head Pulley(Z-Point) of BC110A&B at CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 8 | 8 |  |  | 8 | 0
0 | Modification, Errection & Commissioning of drive unit capacity enhancement for conveyor at CHP-D, Chandrapur TPS. | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
3 | Performance Improvement Schemes of CHP-D CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design engineering , supply and installation of modular chutes with weld cast Liners ,flap gates and actuators. | 0 | - | 0 | 20 | 20 | 0 | 15 | 15 |  |  | 15 | 0
0 | Supply erection & commissioning of set of internal of spares of Wagon tippler and Side Arm Charger installed at CHP-D, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
0 | Supply erection & commissioning of set of internal of spares of stacker reclaimer installed at CHP-D, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
0 | Supply erection & commissioning of set of internal of spares of Impact crusher installed at CHP-D, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
0 | Supply erection & commissioning of set of internal of spares of wobbler feeder installed at CHP-D, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
0 | Supply erection & commissioning of 1500 TPH capacity Stacker Recliamer sleeving bearing with fastener of CHP-D (U8&9), CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
0 | Supply of Gearbox assemblies at CHP-D CSTPS. | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
0 | Structure Strengthening,Modification works of Conveyors at CHP-D CSTPS | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
4 | Design, Installation, testing and commissioning of new conveyor systems of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Installation, testing and commissioning of conveyor system from crusher house to TP-108 of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 50 | 50 |  |  | 50 | 0
0 | Supply, Engineering, erection and commissioning of one 1500TPH crusher, short conveyors from TP 106 and open space of near Stack yard A pile to Crusher inlet and a telescopic conveyor at the output of crusher to Stack Yard B pile of CHPD Unit 8&9, CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 15 | 15 |  |  | 15 | 0
5 | Design, Installation and commissioning of conveyor system from rope way of CHP-A to crusher house of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Installation and commissioning of conveyor system from rope way of CHP-A to crusher house of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Infrastructure Development Schemes at CHP-D CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Supply,Installation and Commissioning of EOT Cranes at Wagon Tippler area of CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Belt Tracking systems for Carrying/Return 1400/1600 mm belt width | 0 | - | 0 | 0 | 0 | 0 | 1.25 | 1.25 |  |  | 1.25 | 0
0 | Ceramic Lagging by direct bonding on Conveyor Pulleys without Rubber Pad/Rubber Sheets. | 0 | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
0 | Rewamping of crane and hoist of CHP, Unit 8&9, CSTPS, Chandrapur | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Material lifting mechanism at Crusher, bunker and Tunnel area of CHP-D CSTPS. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping, modification of TunnelAir ventilation system | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping, modification of DE and DS system | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping, modification of Dewatering and water recirculation system | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of New Office Building with Infrastructure ,Interior Development at CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Material Storage Shed Fabrication work at CHP-D CSTPS | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
7 | Electrical schemes for improvement in availability & Reliability of CHP-D,CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design supply installation and commisioning of LED based energy efficient system for illumination at CHPD | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
0 | Supply, Erection, Commissioning and Testing of 7.2KV SF6 HT Contactor for retrofitting of existing BHEL make Vacuum Circuit Breakers of CHP-D, CSTPS | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of GE make 90-30 series PLC system installed at stacker rclaimer and wagon tippler at CHP-D, CSTPS | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Installation of energy efficient air temperature controlling system at various MCC rooms of CHPD, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
0 | Alterration, upgradation of tunnel ventilation system of CHPD, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Fabrication, Erection & commissioning of cable support structure along with re-routing & trial of auxiliaries at Crusher PMCC, compressor house & short conveyor area at CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
0 | Supply and installation of LT air circuit breakes at CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, supply, installation & commissioning of solar based energy efficient illumination system at CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
0 | Procurement of HT motors for various auxiliaries at CHP-D, CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & installation of high capacity submersible slurry pump at CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reconditioning of MCC Board feeder panels at CHP-D,U #8&9.CSTPS,Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & installation of anoodized winding magnets along with control panels for installation at various conveyor belts of CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of 69 AH HBL make battery set of CHP-D (U8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of 100 AH Exide make battery banks (2 Set/ 110 Nos battery cells) & battery charge at CHP-D (U8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Alterration, upgradation of tunnel ventilation system of CHPD, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of HT/LT Xmers assy of CHP-D (U8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of HT/LT Xmers assy of CHP-D (U8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | WTP-III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Engineering, installation and commissioning of DM stream capacity of 4800M3/Day for U # 8 & 9 in addition to existing DM stream at WTP, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Engineering, installation and commissioning of DM stream capacity of 4800M3/Day for U # 8 & 9 in addition to existing DM stream at WTP, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 46.4 | 46.4 |  |  | 46.4 | 0
0 | Civil - 8&9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work of diversion of peripheral nallah towards ash water recovery pump house alogwith construction of waste wear at ash bund area CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Work of diversion of peripheral nallah towards ash water recovery pump house alogwith construction of waste wear at ash bund area CSTPS, Chandrapur. | 0 | - | 0 | 10 | 10 | 0 | 25.4 | 25.4 |  |  | 25.4 | 0
2 | Infrastructure development of CHP-D area at U-8, 9, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of platform for unloading of coal near TP-106 upto stack pile A of CHP-D | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of WBM Road for fire fighting arrangement at CHP-D U-8,9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction & Pushing RCC box of size 2mx2m under railway track to drain out the surface water near Rly - A cabin Unit-8,9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of concrete pavement road connecting to reject gate & vinchoda chowk , Y point to ash recovery pump house | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO1 | CHP Improvement Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at CHP-D | 0 | - | 0 | 0 | 0 | 0 | 100 | 100 |  |  | 100 | 0
HO2 | Developlment & Upgradation of DSM software system for MSPGCL | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Developlment & Upgradation of DSM software system for MSPGCL | 0 | - | 0 | 55 | 55 | 0 | 0 | 0 |  |  | 0 | 0
1 | Implementation of Flexible Operation Solutions | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Flexible Operation Solutions | 0 | - | 0 | 34 | 34 | 0 | 0 | 0 |  |  | 0 | 0
0 |  | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | General asset | 0 | - | 0 | 3.2096 | 3.2096 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply, Operation & Maintenance of Mobile Coal Sampling Equipment (MCSE) for coal sampling at loading ends of WCL for Mahagenco | 0 | - | 0 | 3.1648 | 3.1648 | 0 | 0 | 0 |  |  | 0 | 0
3 | ABC Powder Type and Foam Type Composite Fire Extinguisher | 0 | - | 0 | 1.528 | 1.528 | 0 | 0 | 0 |  |  | 0 | 0
4 | NON-Detailed Project Report for the Work of Upgradation/Renovation of Crusher House of CHPB of Unit-5, 6&7 at CSTPS Chandrapur (benefit U-8,9 by short conveyor coal stacking in catering emergency) | 0 | - | 0 | 2.8807 | 2.8807 | 0 | 0 | 0 |  |  | 0 | 0
5 | Extention of stacker reclaimer area for improvement in coal stack management at CHP-D CSTPS Chandrapur U-8,9 | 0 | - | 0 | 8.46 | 8.46 | 0 | 0 | 0 |  |  | 0 | 0
6 | Retrofitting of BHEL make HT Circuit Breaker with SF6 Contactor at CHP-D, Unit-8&9 | 0 | - | 0 | 4.25 | 4.25 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 1653.4385 | 1705.4089 | -51.9704 | 1002.8795 | 1002.8795 | 0 | 0 | 1002.8795 | -51.9704
FY 2027-28
A) Approved Add Cap (Case No. 296 of 2019)
1 | Initial Spares | Approved Add Cap (Case No. 296 of 2019)
| Boiler & Auxiliaries | 0 | - | 10.36 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Bevel Helical Gear box KMP-350 for XRP 1043 coal mills at unit-8&9,CSTPS, Chandrapur. | 0 | - | 0 | 7.4087 | 7.4087 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Hydraulic Adjustment (Actuating) Device for PA fan model PAF 19/10.6-2 and FD fan FAF 23/12.5-1 at Unit 8&9, CSTPS, Chandrapur. | 0 | - | 0 | 1.3971 | 1.3971 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Yokogawa make Zirconia Oxygen Analyser spares for C&I-III, Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 0.51933 | 0.51933 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of High pressure valves installed at unit-8&9 ( 2x500 MW),CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Turbine & Aux | 0 | - | 1.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of IMI Norgren Herion make Trip solenoid valves for Main Turbine, MD-BFP & TD-BFP of Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.37354 | 0.37354 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Speed Sensors for 500 MW KWU Turbine for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.038232 | 0.038232 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Position Feedback Transmitters for Starting Device and Speeder Gear of Main Turbine for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.11225 | 0.11225 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for LP bypass system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur on OEM Basis. | 0 | - | 0 | 0.43645 | 0.43645 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of TSE (Turbine Stress Evaluator) temperature elements for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.2073 | 0.20719 | 0.00010699 | 0 | 0 |  |  | 0 | 0.00010699
| Generator and Auxiliries | 0 | - | 0.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of complete set of water cooled bushing for 500MW Generator installed at Unit-8 & 9, CSTPS Chandrapur. | 0 | - | 0 | 0.26409 | 0.26409 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Tushaco make complete AC Jacking Oil Pump for Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.19949 | 0.19949 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of oil filled Neutral Grounding Transformer for AHP Unit-8&9 CSTPS , Chandrapur. | 0 | - | 0 | 0.34775 | 0.34775 | 0 | 0 | 0 |  |  | 0 | 0
| Electrical and Instrumentation | 0 | - | 29.23 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| ‘Procurement of various spares of BHEL make Vacuum Circuit Breakers’ , for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.49498 | 0.49498 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, erection and commissioning of floor mounted 500KW Resistor Load Bank for D.G. sets installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.27536 | 0.27536 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Turbosupervisory system spares of main turbine for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 1.0366 | 1.0366 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Level transmitters for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.15999 | 0.15999 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Level transmitters for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.032605 | 0.032605 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Level transmitters for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.046973 | 0.046973 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of GE PLC spares for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.57304 | 0.57304 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for GEHO pumps PLC control panels for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.084378 | 0.084378 | 2.6e-08 | 0 | 0 |  |  | 0 | 2.6e-08
| Procurement of master calibration lab Instruments for C&I-III, Unit 8 & 9,CSTPS,Chandrapur | 0 | - | 0 | 0.30131 | 0.30131 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Coal Feeder panel spares for C&I-III, Unit 8 & 9,CSTPS, Chandrapur | 0 | - | 0 | 0.58701 | 0.58701 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Opacity Monitor (Stack Particulate matter-SPM) spares for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.14051 | 0.14051 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Forbes Marshall Supervisory system spares For Turbine driven boiler feed pumps (TDBFP) of Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.22449 | 0.22449 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for hydraulic panel of CW pumps for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.13862 | 0.1386 | 1.7196e-05 | 0 | 0 |  |  | 0 | 1.7196e-05
| Procurement of H2 Dew point analyzer spares for Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.049938 | 0.049938 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for HP bypass system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.33965 | 0.33965 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Position feedback transmitter for HP bypass system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.0354 | 0.0354 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Atlas Copco make Instrument, Service and Conveying air Compressors for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.22509 | 0.22509 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for HEA Ignitors and Flame Scanners for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.037701 | 0.037701 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for GEHO pumps of Ash Handling System at C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.28861 | 0.28861 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Turbine side control valve spares for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.17974 | 0.17974 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various numerical protection relays for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.12307 | 0.12307 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various numerical protection relays for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.13184 | 0.13184 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various numerical protection relays for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.13863 | 0.13863 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for DB POWER make UPS system installed at HCSD Pump House, Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.064757 | 0.064757 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Fully Automatic Capacitance & Dissipation Factor (Tan- Delta) measuring kit for Unit-8 &9, CSTPS, Chandrapur. | 0 | - | 0 | 0.48288 | 0.48288 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of various VFD spares for ID fans of Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.546 | 0.546 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of DAVR spares installed at Unit -8&9 CSTPS, Chandrapur. | 0 | - | 0 | 0.5945 | 0.5945 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 3 phase relay test kit for Unit-8 &9, CSTPS, Chandrapur. | 0 | - | 0 | 0.35388 | 0.35388 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Fast Bus Transfer System (FBTS) installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.37288 | 0.37288 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various spares for battery chargers installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.40022 | 0.40022 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Auto synchronizing Relay (ASR) & Load Shedding Relay (LSR) installed at Unit-8 &9, CSTPS, Chandrapur. | 0 | - | 0 | 0.34973 | 0.34973 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ESP spares i.e. Field Controller, Thyristor and Trigger card for ESP of Unit-8 & 9, CSTPS Chandrapur. | 0 | - | 0 | 0.26745 | 0.26745 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various VFD spares for GEHO pump of Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.54416 | 0.54416 | 0 | 0 | 0 |  |  | 0 | 0
| Design, Supply, Erection & Commissioning of On-Line Dissolved Gas Analyzers for various Transformers installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 3.1775 | 3.1775 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, Erection & Commissioning of On-Line Dissolved Gas Analyzers for Station Transformers -8B, Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.30519 | 0.30519 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘TOROSHIMA’ make 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motor (without pump casing) for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 4.2037 | 4.2037 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 90kVA ESP Rectiformer for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.29878 | 0.29878 | 0 | 0 | 0 |  |  | 0 | 0
| Supply erection & commissioning of Aviation Lighting for NDCT of Unit-8&9, CSTPS Chandrapur | 0 | - | 0 | 0.57261 | 0.57261 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Transformer oil storage tanks of different capacity for Unit-8&9 CSTPS Chandrapur. | 0 | - | 0 | 0.57024 | 0.57024 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 2000kW & 315kW, 6.6 kV HT motors for CW & ACW Pump installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 1.4505 | 1.4505 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 3.25MVA, 6.6/2.3kV VFD Transformers of vector group DY11 for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.3941 | 0.3941 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 3.25MVA, 6.6/2.3kV VFD Transformer of vector group ‘Dd0’ for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.3905 | 0.3905 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘MARATHON’ makes HT/LT Induction motors for various Critical auxiliaries installed at Unit-8 &9, CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of 1.2V, Ni-Cd battery cells for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.12496 | 0.12496 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of 1.2V, Ni-Cd battery cells for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.18931 | 0.18931 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘Air Core DC Reactor’ for VFD and ‘NGR’ for UAT/ Station Transformers installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.44368 | 0.44368 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘Air Core DC Reactor’ for VFD and ‘NGR’ for UAT/ Station Transformers installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.12551 | 0.12551 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘BHEL’ make 680 KW, 6.6KV, Coal Mill Motor for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.37913 | 0.37913 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 400kV OIP Condenser Bushing for Generator Transformer & Station Transformer of Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.49064 | 0.49064 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘11kW DC motor with Control Cabinet’ for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.2242 | 0.2242 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 37kW, 415V motors for Primary Water Pump installed at Unit-8 &9, CSTPS Chandrapur. | 0 | - | 0 | 0.0096851 | 0.0096851 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 15 KW, 415V LT Motor for Service Building & TG Building Lift installed at Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.095155 | 0.095155 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 16KW, 415V LT Motor for Boiler Lift installed at Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.044179 | 0.044179 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, Erection, Testing and Commissioning of Hydrastep-Electronic Drum Level Indicator and its associated accessories for Unit-9, CSTPS, Chandrapur | 0 | - | 0 | 0.27376 | 0.27376 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for BHEL make Hydrastep (Electronic Water Level Indicator -BHELVISION 20M) for Unit 8 & 9, CSTPS, Chandrapur on OEM basis. | 0 | - | 0 | 0.084172 | 0.084172 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Electrodes for Hydrastep (Electronic Water Level Indicator -BHELVISION 20M) for Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.10384 | 0.10384 | 0 | 0 | 0 |  |  | 0 | 0
| Engineering & Retrofitting of 196 NT Controller to DT 9 Controller for Unit-8 & 9 Coal Feeder System. | 0 | - | 0 | 0.38076 | 0.38076 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for BHEL make Acoustic steam leak detection system (BHELSONIC) (BS10) for Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.077807 | 0.077807 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of LT Circuit Breaker assemblies for ESP LT Panels (LTMSB & ACP) of Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.25429 | 0.25429 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for BHEL make maxDNA Distributed control system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 1.117 | 1.117 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of Transformer oil BDV test kit DTA 100C and Oil Tan Delta & Resistivity Tester DTL C at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.47598 | 0.47598 | 0 | 0 | 0 |  |  | 0 | 0
| Outdoor Plant ( CHP/AHP/WTP) | 0 | - | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Elecon make KCN-560 type Gearbox for Apron Feeder installed at CHPD, CSTPS. | 0 | - | 0 | 1.6717 | 1.6717 | -6e-08 | 0 | 0 |  |  | 0 | -6e-08
| Procurement of spares of CKB-280,225,200,8180 typ gearbox installed at CHP-D | 0 | - | 0 | 1.0015 | 1.0015 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Gear Box (MAKE: NEW ALLENBERRY) Spares at CHP-D; CSTPS, Chandrapur. | 0 | - | 0 | 0.5177 | 0.5177 | 1.8e-08 | 0 | 0 |  |  | 0 | 1.8e-08
| Procurement of spares for m/s Elecon make Impact Crusher installed at CHP Unit 8&9 CSTPS, Chandrapur | 0 | - | 0 | 0.84103 | 0.84103 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of V belt pulley of rotor for Impact crusher installed at CHP-D, CSTPS | 0 | - | 0 | 0.11864 | 0.11864 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Spares for hydraulic systems installed at CHPD, CSTPS. | 0 | - | 0 | 0.47537 | 0.47537 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Spares for hydraulic systems installed at CHPD, CSTPS. | 0 | - | 0 | 0.028604 | 0.028604 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of drive & non drive pulley for various conveyors installed at CHP D, CSTPS, Chandrapur. | 0 | - | 0 | 0.25792 | 0.25792 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of drive & non drive pulley for various conveyors installed at CHP D, CSTPS, Chandrapur. | 0 | - | 0 | 0.0914 | 0.0914 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Chain links for apron feeder installed at CHP D, CSTPS, Chandrapur. | 0 | - | 0 | 0.40289 | 0.40289 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of internal spares for Elecon make PWD-18, PLB-25 & SCN-180 type Gearbox for Stacker Reclaimer & wobbler feeder installed at CHP D, CSTPS. | 0 | - | 0 | 0.52774 | 0.52774 | 3.1e-08 | 0 | 0 |  |  | 0 | 3.1e-08
| Supply of GE Make Switchgear Spares for GE Make LT Feeders | 0 | - | 0 | 0.12485 | 0.12485 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Fluidomat make scoop coupling installed at CHP–D, CSTPS, Chandrapur | 0 | - | 0 | 0.48355 | 0.48355 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Oil Filtering machine for hydraulic power packs installed at CHPD, CSTPS | 0 | - | 0 | 0.10592 | 0.10592 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of LT Motors at CHP-D (U#8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0.11302 | 0.11302 | 0 | 0 | 0 |  |  | 0 | 0
| Supply and Installation of Oil Cooled Suspended Anodized Winding Magnet & Control Panel at CHP, Unit 8&9, CSTPS, Chandrapur. | 0 | - | 0 | 2.2967 | 2.2967 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of LT power and control cable for CHP-D | 0 | - | 0 | 0.26256 | 0.26256 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of LT power and control cable for CHP-D | 0 | - | 0 | 0.0477 | 0.0477 | 0 | 0 | 0 |  |  | 0 | 0
2 | Capital Spare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| HPT MODULE | 0 | - | 45.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of HP turbine Module along with breach nuts and pipe spool pieces (Type: H30-100-2) for Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 32.332 | 32.332 | 0 | 0 | 0 |  |  | 0 | 0
| LPT ROTOR | 0 | - | 40.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Fully Bladed & Dynamically Balanced LP Rotor (N30-2X10-2) for Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 29.03 | 29.03 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of set of Free Standing Moving Blades for LP Rotor (N30-2X10-2) for Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 4.5629 | 4.5629 | 0 | 0 | 0 |  |  | 0 | 0
| BFP CARTRIDGE ( 2NOS ) | 0 | - | 4.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of cartridge assembly for Boiler Feed Pump model FK-4E-36 (with Four S/H & 2 R/H spray branches) installed at 2X 500MW, CSTPS, Chandrapur. | 0 | - | 0 | 2.515 | 2.5149 | 6e-05 | 0 | 0 |  |  | 0 | 6e-05
| BCW PUMP | 0 | - | 3.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for ‘TOROSHIMA’ make 350KW BCW Pump-Motor installed at Unit-8 &9, CSTPS Chandrapur. | 0 | - | 0 | 1.3283 | 1.3283 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various spares for ‘TOROSHIMA’ make Boiler Circulating Water (BCW) pump-motor installed at Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 2.2326 | 2.2326 | 0 | 0 | 0 |  |  | 0 | 0
| 15 MVA DRY TYPE TRANSFORMER | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spare ‘Cast Resin Dry Type Transformers (CRTs)’ of different ratings for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 6.0213 | 6.0213 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of phase coil limb and spares of Cast Resin Dry Type Transformers of different ratings for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 7.9255 | 7.9255 | 0 | 0 | 0 |  |  | 0 | 0
| BTG+BOP& Other Works | 0 | - | 20.48 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Design, Supply & Installation, Testing & Commissioning of Public Addressing System for tunnels of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 1.1544 | 1.1544 | 0 | 0 | 0 |  |  | 0 | 0
| Work of upgradation, installation and extension of 220VDC control supply to various PMCC of CHPD, CSTPS, Chandrapur. | 0 | - | 0 | 0.68441 | 0.68441 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Apron Feeder in CHP Unit 8&9 (2x500) MW at CHP-D, CSTPS. | 0 | - | 0 | 2.3388 | 2.3388 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of spares for up gradation of rotary parts of travelling conveyor system installed at CHPD, CSTPS, Chandrapur. | 0 | - | 0 | 0.58939 | 0.58939 | 0 | 0 | 0 |  |  | 0 | 0
| The Work of Design, Engineering, Manufacturing, Supply, Erection & Commissioning of Short Conveyor belt from stack yard of CHP of Unit 5,6&7 to Belt Conveyor 104 A/B at CHP of Unit 8&9, CSTPS, Chandrapur | 0 | - | 0 | 5.6825 | 5.6825 | 0 | 0 | 0 |  |  | 0 | 0
| Work of design, supply, erection, commissioning of overhead cable tray along with removal & re-routing of power and control cables at CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0.51324 | 0.51324 | 0 | 0 | 0 |  |  | 0 | 0
| Work of provision, modification, retrofitting and revamping of lighting system of transfers points, crusher house and bunker area of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 1.0105 | 1.0105 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for M/s. Weir Minerals make (GEHO pump Model TZPM-1200) for Ash Handling Plant Unit# 8 &9 CSTPS Chandrapur. AHP-III | 0 | - | 0 | 2.106 | 2.106 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Gear Box set of internal (MAKE: NEW ALLENBERRY) Spares at CHP-D; CSTPS, Chandrapur. | 0 | - | 0 | 1.6904 | 1.6904 | 0 | 0 | 0 |  |  | 0 | 0
| Supply and Installation of Oil Cooled Suspended Anodized Winding Magnet & Control Panel at CHP, Unit 8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 196 NT Controller by DT 9 Controller alongwith HMI units for Unit- 8&9 coal feeder system | 0 | - | 0 | 2.0774 | 2.0774 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of set of CW Impeller duly fitted with wear rings & ACW Impeller duly fitted with wear rings of Mather & Platt make Pumps installed at Unit-8 & 9,CSTPS,Chandrapur | 0 | - | 0 | 0.70379 | 0.70379 | 0 | 0 | 0 |  |  | 0 | 0
| CHP System U#8 | 0 | - | 0 | 0.05 | 0.05 | 0 | 0 | 0 |  |  | 0 | 0
| ISOLATED PHASE BUS DUCT | 0 | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| SEGREGATED PHASE BUS DUCT U#8 | 0 | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| SEGREGATED PHASE BUS DUCT U#9 | 0 | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| ISOLATED PHASE BUS DUCT U#9 | 0 | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| DTT & UAT U#8 | 0 | - | 0 | 0.03 | 0.03 | 0 | 0 | 0 |  |  | 0 | 0
| DTT & UAT U#9 | 0 | - | 0 | 0.03 | 0.03 | 0 | 0 | 0 |  |  | 0 | 0
| Cranes and hoists U#8 | 0 | - | 0 | 0.03 | 0.03 | 0 | 0 | 0 |  |  | 0 | 0
| RCC Chimney U#8 | 0 | - | 0 | 9.29 | 9.29 | 0 | 0 | 0 |  |  | 0 | 0
| Coal Handling Plant | 0 | - | 0 | 41.79 | 41.79 | 0 | 0 | 0 |  |  | 0 | 0
| Bunker foundation & civil works (Unit 8) U#8 | 0 | - | 0 | 18.58 | 18.58 | 0 | 0 | 0 |  |  | 0 | 0
| Boiler & Auxiliaries U#9 | 0 | - | 0 | 9.2889 | 9.2872 | 0.0017338 | 0 | 0 |  |  | 0 | 0.0017338
| ESP U#9 | 0 | - | 0 | 2.1589 | 2.1589 | 0 | 0 | 0 |  |  | 0 | 0
| ID fan foundations (Unit 9) U#9 | 0 | - | 0 | 1.7489 | 1.7489 | 0 | 0 | 0 |  |  | 0 | 0
| DRY ASH SILO-12M DIA U#8 | 0 | - | 0 | 1.22 | 1.22 | 0 | 0 | 0 |  |  | 0 | 0
| FD fan foundations (Unit 9) U#9 | 0 | - | 0 | 0.62891 | 0.62891 | 0 | 0 | 0 |  |  | 0 | 0
| PA fan foundations (Unit 9) U#9 | 0 | - | 0 | 0.54891 | 0.54891 | 0 | 0 | 0 |  |  | 0 | 0
| Natural Draft cooling tower- Unit 8 U#8 | 0 | - | 0 | 0.32 | 0.32 | 0 | 0 | 0 |  |  | 0 | 0
| Main power house building-Civil Works-Unit no.-9 U | 0 | - | 0 | 0.15 | 0.15 | 0 | 0 | 0 |  |  | 0 | 0
| Structural Steel works for main power house buildi | 0 | - | 0 | 0.15 | 0.15 | 0 | 0 | 0 |  |  | 0 | 0
| Canteen U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Security and time office U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| CARS SCOOTERS AND CYCLE SHED U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Fire Station U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Watch towers U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| First aid station | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Tranformer yard U#8 | 0 | - | 0 | 0.02 | 0.02 | 0 | 0 | 0 |  |  | 0 | 0
| Rain Water Harvesting Scheme U#8&9 | 0 | - | 0 | -0.01 | -0.01 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Advance Multipurpose Fire Tender | 0 | - | 0 | 3.45 | 3.45 | 0 | 0 | 0 |  |  | 0 | 0
| DM Stream | 0 | - | 29.65 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| DM Stream capacity of 100 M3/Hr in addition to existing stream of WTP. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| CIVIL | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Bridge | 0 | - | 4.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Railway, CHP, AHP etc | 0 | - | 152.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| B. G. railway siding Pway works | 0 | - | 0 | 41.5165 | 41.5165 | 0 | 0 | 0 |  |  | 0 | 0
| S & T work for B.G. railway siding | 0 | - | 0 | 0.023574 | 0.023574 | 0 | 0 | 0 |  |  | 0 | 0
| Consultancy services for B. G. railway siding | 0 | - | 0 | 0.035636 | 0.035636 | 0 | 0 | 0 |  |  | 0 | 0
| Ash infra in Railway | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Bunker structure (Unit 8) U#8 | 0 | - | 0 | 18.57 | 18.57 | 0 | 0 | 0 |  |  | 0 | 0
| Coal Mills | 0 | - | 0 | 1.1389 | 1.1389 | 0 | 0 | 0 |  |  | 0 | 0
| Bunker foundation & civil works (Unit 9) U#9 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Bunker structure (Unit 9) U#9 | 0 | - | 0 | 0.11 | 0.11 | 0 | 0 | 0 |  |  | 0 | 0
| HCSS silo-12m dia U#8 | 0 | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| Ash water PH, HCSD PH, Bottom ash slurry PH U#8 | 0 | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| Ash compressor house & Control room U#8 | 0 | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| MILL REJECT SILO U#8 | 0 | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| Fire protection & Detection system U#8 | 0 | - | 0 | 0.71423 | 0.71423 | 0 | 0 | 0 |  |  | 0 | 0
| DM Water Pump room U#8 | 0 | - | 0 | 4.25 | 0 | 4.25 | 0 | 0 |  |  | 0 | 4.25
| Filter water reservoir & pump house U#8 | 0 | - | 0 | 4.29 | 0 | 4.29 | 0 | 0 |  |  | 0 | 4.29
| ACW + RW + Filtered water piping U#8 | 0 | - | 0 | 2.2409 | -0.0096938 | 2.2506 | 0 | 0 |  |  | 0 | 2.2506
| Laboratory Building U#8 | 0 | - | 0 | 0.12 | 0 | 0.12 | 0 | 0 |  |  | 0 | 0.12
3 | Staff quarters | 0 | - | 15.04 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Work of exterior repair, providing painting to A, D & E type residential buildings and Public Buildings and allied civil works in Urjanagar Colony, CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Staff Quarters- Repair and renovation of E type staff quarters to extend the life of buildings at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Staff Quarters - Repair and renovation of 'B' type staff quarters in residential colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair of D type quarters in colony at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair of C type quarters in colony at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Staff Quarters- Repair and renovation of F and NF type staff quarters to extend the life of buildings at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair and replacement of existing drinking water supply pipelines in E & F type area in colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair and replacement of existing sewer lines in E & F type area in colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Work of providing RCC drain along main roads in colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Rerouting and replacement of domestic water supply pipeline from WTP to ESR in colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Additional Contengencies approved vide e BR No. MSPGCL/BM-162/165, Dt.29.10.2016 vide resolution no. 2016/2085 | 0 | - | 7.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Landscaping and plantation work at various locations inside plant area at CSTPS, chandrapur. | 0 | - | 0 | 3.4266 | 3.4266 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of WBM approach road from point- N to Z Area along ash bund periphery at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design, Engineering, Supply and commissioning of ash-bund water recovery system (Phase II) at CSTPS Chandrapur | 0 | - | 27.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, Engineering, Supply and commissioning of ash-bund water recovery system (Phase II) at CSTPS Chandrapur | 0 | - | 0 | 30.0361 | 30.0361 | 0 | 0 | 0 |  |  | 0 | 0
| Providing Consultancy Services for work of Design, Engineering, Supply, Installation & Commissioning of ash bund water recovery system (Phase-II) at CSTPS, Chandrapur (on EPC contract basis). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Providing laying, jointing and commissioning of 1600 mm dia. M.S. Pipe line from Erai dam to one day reservoir of stage II, III & IV at CTPS | 0 | - | 73.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Providing laying, jointing and commissioning of 1600 mm dia. M.S. Pipe line from Erai dam to one day reservoir of stage II, III & IV at CTPS | 0 | - | 0 | 73.6091 | 73.6091 | 0 | 0 | 0 |  |  | 0 | 0
| Work of construction of Control Valve rooms on newly laid 1600 mm M.S. Pipeline no. 6 from Erai dam to One day reservoir at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Providing OHE facility for BG Rly siding of proposed Expansion Project at Chandrapur, for Supply of Materials. | 0 | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Providing OHE facility for BG Rly siding of proposed Expansion Project at Chandrapur, for errection of OHE Items. | 0 | - | 2.5 | 0.7 | 0 | 0.7 | 0 | 0 |  |  | 0 | 0.7
9 | Irrigation scheme for landscaping and Plantation work at Chandrapur expansion project chandrapur. | 0 | - | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Asphalting of WBM road from Nagpur gate to Awanda gate. | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Asphalting of WBM road from Nagpur gate to Awanda gate. | 0 | - | 0 | 0.65141 | 0 | 0.65141 | 0 | 0 |  |  | 0 | 0.65141
| Asphalting over WBM Road of ADP line Service road from Nagpur gate opening to Awandha junction gate at CSTPS Chandrapur | 0 | - | 0 | 0.84833 | 0.84833 | 0 | 0 | 0 |  |  | 0 | 0
| Asphalting of WBM road from Nagpur gate to Awandha gate at CSTPS Chandrapur - Asphalting of road from Reject coal gate to Motghat nallah at CSTPS Chandrapur (PHASE - I) | 0 | - | 0 | 0.47941 | 0.47941 | 0 | 0 | 0 |  |  | 0 | 0
11 | Foot Over Bridge | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Work of Providing retaining wall for sand hump at Vivekanand nagar station yard under modification work in wardha end fro 2 x 500 MW Expn. Project at CSTPS, Chandrapur. | 0 | - | 0.3 | 0.25515 | 0.25515 | 0 | 0 | 0 |  |  | 0 | 0
| Additional Capitalization by O & M | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of GE make 4000Amp LT Air Circuit Breakers for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0.9 | 1.0308 | 1.0308 | 0 | 0 | 0 |  |  | 0 | 0
2 | Air Compressor System | 0 | - | 0.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Energy management Sysytem | 0 | - | 0.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, Installation, Testing & Commissioning of Energy Management System for Unit#8 & 9 for CSTPS, Chandrapur. | 0 | - | 0 | 0.20054 | 0.20054 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Tri-vector 0.2s class Digital Energy meter for Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.094872 | 0.094872 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, Installation & Commissioning of 3D Level Scanners to 64 nos. of ESP hoppers at Unit-8&9 (2X500MW), CSTPS, Chandrapur. | 0 | - | 3.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of internal spares for Elecon make PWD-18, PLB-25 ,Pbh-71 type Gearbox for Stacker Reclaimer installed at CHPD, CSTPS. | 0 | - | 0 | 1.1089 | 1.1089 | 0 | 0 | 0 |  |  | 0 | 0
5 | 4000/2500/1800/800 A GE make LT CKT Brkr | 0 | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| LT Air Circuit Breakers for Incomer Feeders at CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 1.4207 | 1.4207 | 0 | 0 | 0 |  |  | 0 | 0
| LT Air Circuit Breakers at CHP, Unit 8&9, CSTPS | 0 | - | 0 | 1.0141 | 1.0141 | 0 | 0 | 0 |  |  | 0 | 0
6 | Replacement of Impact crusher by hammer mill crusher (installed qty.2 No) | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Replacement of wobbler feeder 1&2 by grizzly screen at CHP-D | 0 | - | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Installation of conveyor system from rope way of CHP-A and crusher house of CHP-D | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| PLC based control & instrumentation of 6.6 KV HT motors of 1250 KW of Crusher I & II and 200 KW of BC 108A1 & A2 at CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0.93628 | 0.93628 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Design, Supply, Erection & Commissioning of Complete Electrical Automation for Short Conveyor from stack yard of CHP-D to Belt Conveyor 107 A/B of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0.70095 | 0.70095 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Design, Supply, Erection & Commissioning of Complete Electrical Automation for Short Conveyor from stack yard of CHP-B to Belt Conveyor 104 A/B of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 2.2368 | 2.2368 | 0 | 0 | 0 |  |  | 0 | 0
| WORK OF DESIGN, ENGINEERING, MANUFACTURING, SUPPLY, ERECTION &COMMISSIONING OF SHORT CONVEYOR BELT FROM STACK YARD OF CHP UNIT-8&9 TO CONVEYOR BELT 107A AND B AT CHP UNIT 8&9, CSTPS, CHANDRAPUR. | 0 | - | 0 | 4.6948 | 4.6948 | -2.4e-08 | 0 | 0 |  |  | 0 | -2.4e-08
| Design, Supply, Installation and Commissioning of High Performance Energy Chain System for Side Arm Charger and Stacker Reclaimer of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 3.8916 | 3.8916 | 0 | 0 | 0 |  |  | 0 | 0
| RBF 103 &104,105 & 106, 107 & 108, and 109 & 110 in to modular Y chute | 0 | - | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-103 & RBF-104 with Design, development, Manufacturing, Supply & erection of modular Chute as per site condition in place of RBF using sintered silicon Carbide plate with motorized Flap Gate at CHP-D, CSTPS. | 0 | - | 0 | 1.1741 | 1.1741 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-105 & RBF-106 with Design, development, Manufacturing, Supply & erection of modular Chute as per site condition in place of RBF using sintered silicon Carbide plate with motorized Flap Gate at CHP-D, CSTPS. | 0 | - | 0 | 1.3169 | 1.3169 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-107 & RBF-108 with Design, development, Manufacturing, Supply & erection of modular Chute as per site condition in place of RBF using Tungsten Carbide plate with Flap Gate at CHP-D, CSTPS. | 0 | - | 0 | 1.1529 | 1.1529 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-109 & RBF-110 with design, erection & Installation by trajectory calculation & removal of existing RBF with Y Chute assembly by flow control with Flap Gate arrangement at TP-107 of CHP-D, CSTPS. | 0 | - | 0 | 1.1506 | 1.1506 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurment , Installation and commissioning of Online Insertable Camera systems for Unit-8, 500MW, CSTPS | 0 | - | 8.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, Supply, Installation & Commissioning of Energy efficient system for Illumination at Unit 8&9 CSTPS, Chandrapur. | 0 | - | 0 | 4.9494 | 4.9494 | 0 | 0 | 0 |  |  | 0 | 0
11 | Construction of Chemical godown shed for unit 8 & 9 at CSTPS,Chandrapur. | 0 | - | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of Chemical godown shed for unit 8 & 9 at CSTPS,Chandrapur. | 0 | - | 0 | 0.42946 | 0.42946 | 0 | 0 | 0 |  |  | 0 | 0
| Comprehencive work of installation, erection, testing and commissioning of MVWS spray system/ Fire safety system for new Bulk Chemical storage godown at CSTPS, Unit 8&9 | 0 | - | 0 | 0.27583 | 0.27583 | 0 | 0 | 0 |  |  | 0 | 0
| Work of electrification of godown for bulk chemical storage near FOPH building at Chandrapur project site. | 0 | - | 0 | 0.018322 | 0.018322 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of additional Chemical godown shed for storage of Lube oil at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Construction of RCC retaining wall for approach to RCC Bridge across Irai River, ADPL line at CSTPS | 0 | - | 8.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of RCC retaining wall for approach to RCC Bridge across Irai River, ADPL line at CSTPS | 0 | - | 0 | 4.3482 | 4.3482 | 0 | 0 | 0 |  |  | 0 | 0
| Asphalting of road from Reject coal gate to Motghat nallah at CSTPS Chandrapur (PHASE - II) | 0 | - | 0 | 0.87403 | 0.87403 | 0 | 0 | 0 |  |  | 0 | 0
| Providing extension to approaches of RCC bridge across Erai river by constructing WBM road at CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| UDL | 0 | - | 0 | 4.85 | 4.85 | 0 | 0 | 0 |  |  | 0 | 0
| B) DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (i) In Principally Approved By MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 1 | HMI (Human Machine Interface) Upgradation of ‘SSPA-T3000’ DCS (Distribution Control System), Rockwell make PLC System installed at 3x660MW Unit No. 8, 9 & 10 at Koradi TPS and HMI (Human Machine Interface) Upgradation of MaxDNA DCS System at Unit 8-9, CSTPS, Chandrapur | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 11.08 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 1.1 | Supply: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 10.52 | 10.52 | 21.02 | -10.5 | 0 | 0 |  |  | 0 | -10.5
HO DPR 1.2 | Works: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.41 | 0.41 | 0.81 | -0.4 | 0 | 0 |  |  | 0 | -0.4
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
40 | Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M with construction of concrete dam (Waste Weir & Non overflow structure), construction of drain wells, approach to drain wells and raising of ash compartment for ash bund along with renewal of Ash Disposal Pipe Line Service Road with WBM treatment at CSTPS, Chandrapur | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 4.9692 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 34.8665 | 34.8665 | 69.733 | -34.8665 | 0 | 0 |  |  | 0 | -34.8665
| Construction of New Drain Wells (12 Nos.) along with necessary connection to existing drain wells at CSTPS | 0 | - | 0.58493 | 0.58493 | 1.1699 | -0.58493 | 0 | 0 |  |  | 0 | -0.58493
| Construction of waste weir for raising of ash bund (Waste Weir & Non overflow structure) | 0 | - | 1.4621 | 1.4621 | 2.9241 | -1.4621 | 0 | 0 |  |  | 0 | -1.4621
| Raising of Ash Compartment i.e. Lagoon in Ash Bund | 0 | - | 8.7868 | 8.7868 | 17.5736 | -8.7868 | 0 | 0 |  |  | 0 | -8.7868
| IDC | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 7.634 | 7.634 | 15.2679 | -7.634 | 0 | 0 |  |  | 0 | -7.634
| IDC | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 4.9692 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
39 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 8-9) | MERC/CAPEX/2020-2021/WFH/SBR/21 | 2020-07-24 | 479.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
39.1 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 8-9) | MERC/CAPEX/2020-2021/WFH/SBR/21 | 2020-07-24 | 440.54 | 797.71 | 797.71 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/2020-2021/WFH/SBR/21 | 2020-07-24 | 38.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41 | CHP Performance Improvement Schemes at Unit 8-9 of CSTPS, Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 26.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.1 | Work of Design engineering , supply and installation of modular chutes with sintered silicon carbide for smooth flow &center feeding in CHP 2x500MW CSTPS | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 9.43 | 9.43 | 9.43 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.2 | Supply erection & commissioning of set of internal of impact crusher spares installed at CHPP-D, CSTPS | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 8.05 | 8.05 | 8.05 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.3 | Scheme for replacement of Scoop coupling/Fluid coupling of conveyor BC-101A/B/C, BC-102A/B, BC-104A/B, BC-105A/B ,BC-106A/B, BC-111A/B/C/D, BC-110A1/B1, BC-110A/B Installed at CHP-D, CSTPS Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 4.67 | 4.67 | 4.67 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.4 | Supply erection & commissioning of set of internal of spares of stacker reclaimer installed at CHP-D, CSTPS Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 1.96 | 1.96 | 1.96 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.5 | Supply erection & commissioning of set of internal of spares of Wagon tippler installed at CHP-D, CSTPS Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 2.12 | 2.12 | 2.12 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 0.38 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 2 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 2.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 27.12 | 27.12 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
A6 | Supply, Installation & Commissioning of Online Coal Flow Monitoring & Balancing System at Unit-8-9, CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0457 Dt 26.07.2024 | 2024-07-26 | 34.21 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, installation and commissioning of Online Coal flow monitoring and balancing system for U- 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2024-2025/MSPGCL/0457 Dt 26.07.2024 | 2024-07-26 | 34.21 | 17.105 | 17.105 | 0 | 17.105 | 17.105 |  |  | 17.105 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0457 Dt 26.07.2024 | 2024-07-26 | 0.31 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
A7 | Providing, supplying, laying and commissioning of 1600 mm dia. M.S. Pipe by replacement of existing PSC raw water line from Erai dam to reservoir at CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 40.7945 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing, supplying, laying and commissioning of 1600mm dia. M.S. pipe by replacement of existing PSC raw water line from Erai dam to reservoir at CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 40.7945 | 40.7945 | 40.7945 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 8.83 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
A8 | Adoption of Ozonization technique for disinfection of Cooling Water System at U # 8 & 9 | MERC/CAPEX/MSPGCL/2023-2024/0467 Dt 02.08.2024 | 2024-08-02 | 67 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Adoption of Ozonization technique for disinfection of Unit 8&9 Cooling Water at CSTPS. | MERC/CAPEX/MSPGCL/2023-2024/0467 Dt 02.08.2024 | 2024-08-02 | 67 | 67 | 67 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-2024/0467 Dt 02.08.2024 | 2024-08-02 | 2.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (ii) Submitted to MERC |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y1 | Multiple Schemes for Electrical Maintenance Section and Design, Engineering, Manufacturing, Testing, Unloading at site, E&C of 200MVA, 21/420KV Single Phase Generator Transformer for Unit # 8 & 9, CSTPS | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 10MW, 11kV Motor and its recommended spare for Boiler Feed Pump (BFP) | To be resubmitted | - | 0 | 4.95 | 4.95 | 0 | 0 | 0 |  |  | 0 | 0
| Replacement of NiCd battery sets installed for UPS of Fire Water Pump House, CMRH & SWAS lab of Unit 8 & 9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0.86 | 0.86 | 0 | 0 | 0 |  |  | 0 | 0
| Retrofitting of GE make LT Air Circuit Breakers of various current ratings and procurement of their recommended spares for Unit-8&9, CSTPS | To be resubmitted | - | 0 | 4.85 | 4.85 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of BHEL make 6.6kV and 11kV Vacuum Circuit Breakers for Unit-8&9, CSTPS Chandrapur | To be resubmitted | - | 0 | 2.07 | 2.07 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y5 | Scheme-1: Procurement of assembly of baskets for Air Preheater of type 31.05 VIMT 2000 (72° PA), Scheme-2: Procurement of spares for PRDS station pressure control valves and Desuperheating spray Control valves in Boiler at U-8&9, CSTPS, Chandrapur, Scheme-3: Procurement of complete set of sky climber at U-8&9, CSTPS, Chandrapur. Scheme-4: Supply, erction, commissioning of oil free rotary screw compressors (including all Civil Electrical, C&I, Testing work) for CMRH system at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-1: Procurement of assembly of baskets for Air Preheater of type 31.5 VIMT 2000 (72° PA) at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 15.78 | 15.78 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-2: Procurement of spares for PRDS station pressure control valves and Desuperheating spray control valves in Boiler at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 6.09 | 6.09 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-3: Procurement of complete set of sky climber at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 3.16 | 3.16 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-4: Supply, erection, commissioning of oil free rotary screw compressors (including all Civil Electrical, C&I, Testing work) for CMRH system at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 8.3 | 8.3 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y6 &Y7 | Supply, Erection & commissioning/retrofitting of HT Circuit Breaker with SF6 Contactor at AHP at Unit-8&9 & CHP#D and Supply, Installation and Commissioning of MV VFD panel along with integrated online cell redundancy technology with VFD bypass feature arrangement for conveyors 103 A & B of CHP-B, C.S.T.P.S., Chandrapur & Design, engineering, manufacturing, testing, unloading at site, E&C of Two No of 200 MVA, 21/420 KV Single Phase Generator Transformers for Unit-8&9, CSTPS, Chandrapur. Through OEM | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme 1: Retrofitting of BHEL make HT Circuit Breaker with SF6 contactor at AHP, Unit#8&9, CSTPS. | To be resubmitted | - | 0 | 38.33 | 38.33 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme 2: Retrofitting of BHEL make HT Circuit Breaker with SF6 contactor at CHP#D, Unit#8&9, CSTPS. | To be resubmitted | - | 0 | 5.64 | 5.64 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme 3: Supply, Installation and Commissioning of MV VFD panel along with integrated online cell redundancy technology with VFD bypass feature arrangement for conveyors 103 A & B of CHP-B. | To be resubmitted | - | 0 | 4.03 | 4.03 | 0 | 0 | 0 |  |  | 0 | 0
| Design, engineering, manufacturing, testing, unloading at site, E&C of Two No of 200 MVA, 21/420 KV Single Phase Generator Transformers for Unit-8&9, CSTPS, Chandrapur. Through OEM | To be resubmitted | - | 0 | 21.07 | 21.07 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (iii) Yet to be Submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Boiler Maintenance -III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of Air & Flue gas ducts of Boiler , Blade set and HAD for PA and FD Fan , SCAPH Coil, ID Fan spares at Unit-8&9 CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-1 Procurement of Air & flue gas expansion joints | 0 | - | 0 | 40 | 40 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-2 :Procurement of Blade Set and 2 sets of HAD of PA Fan. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme -3 Procurement of Blade Set and 2 sets of HAD of FD Fan. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-4 Procurement of SCAPH Coil for unit- 8&9 | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-5 :Procurement of ID Fan Impeller , Shaft and Blade set at unit-8 & 9, CSTPS | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme 6: Procurment of Coal Fuel pipes for unit -8 &9 , CSTPS | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of LTSH and economiser for unit-8&9 CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of LTSH Coil assemsblies unit- 8&9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of economiser coil asemblies | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of existing belt type gravimetric coal feeders to gravimetric rotary weigh coal feeders of unit- 8&9, at CSTPS, Chandrapur | 0 | - | 0 | 10.03 | 10.03 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of Quick Erect Aluminum Boiler Scaffolding system or unit- 8 & 9, (2X500MW), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of Quick Erect Aluminum Boiler Scaffolding system or unit- 8 & 9, (2X500MW), CSTPS, Chandrapur. | 0 | - | 0 | 35 | 35 | 0 | 0 | 0 |  |  | 0 | 0
| Turbine Maintenance -III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Schemes for Improvement in availability & performance of TG auxiliaries at U-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 1. Procurement of BFP Booster Pump assembly for Unit-8 & 9, CSTPS Chandrapur | 0 | - | 0 | 3.2 | 3.2 | 0 | 0 | 0 |  |  | 0 | 0
| 2. Procurement of Boiler Feed Pump catridge with CI sealing for Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 5.2 | 5.2 |  |  | 5.2 | 0
| 3. Procurement of Modulating type Boiler Feed Pump Recirculation valve (06 Nos) assembly for Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
| 4. Procurement of HP Heater HPH-5B assembly for Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
| 5. Procurement of MDBFP working oil & lube oil coolers for Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
| 6. Procurement of TDBFP Turbine rotor K1401-2 at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 7.5 | 7.5 | 0 | 0 | 0 |  |  | 0 | 0
| 7. Procurement of Main TG Jacking oil pumps (2 Nos.) at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
| 8. Procurement of HP elements of ZR500 Atlas Copco make compressors along with inter & after coolers tube nest at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
| 9. Procurement of CW & ACW Pump spares at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
| 10. Procurement of condenser tubes at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 11. Procurement of HPCF Pump at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | DPR for performance improvement of Condenser Cooling water system & improvement in system reliability of auxiliary cooling water system installed at Unit-8&9, 2x500MW, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| DPR for performance improvement of Condenser Cooling water system & improvement in system reliability of auxiliary cooling water system installed at Unit-8&9, 2x500MW, CSTPS, Chandrapur | 0 | - | 0 | 17 | 17 | 0 | 17 | 17 |  |  | 17 | 0
3 | Procurement of main turbine IPT module at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of main turbine IPT module at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Electrical Maintenance -III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Proc of GTR, MDBFP, UPS battery, breakers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, engineering, manufacturing, testing, unloading at site, E&C of 200 MVA, 21/420 KV Single Phase Generator Transformer for Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 21.07 | 21.07 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of MDBFP motor and recommended spares The Fire Water Pump House UPS Battery set of 240V, 40AH Capacity (1.2V X 176 Cells ) Ni Cd Type Make- HBL The UPS Battery Set at SWAS Lab (Outdoor Area), 45AH Capacity (1.2 V X 276 Cells) Ni Cd type Make- HBL for Unit#8&9 The UPS Battery Set at CMRH (Outdoor Area), 69AH Capacity (1.2 V X 280 Cells) Ni Cd type Make- HBL for Unit#8&9 Retrofitting of 415V GE make ACB of various ratings along with allied spares. BHEL make Breakers and spares for 6.6 kV and 11kV panels | 0 | - | 0 | 15.07 | 15.07 | 0 | 0 | 0 |  |  | 0 | 0
2 | Design, engineering, manufacturing, testing, unloading at site, E&C of 80 MVA, 420/11/6.9 KV three Phase Station Transformer & 25MVA 21/6.9KV Three phase Unit Aux Transformer as a common pool spares for BTPS 500MW, Khaparkheda 500 MW and Unit-8&9, CSTPS, Chandrapur & Supply, installation, commissioning and testing of Station Batteries of Unit-8&9 CSTPS alongwith all outdoor batteries | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, engineering, manufacturing, testing, unloading at site, E&C of 80 MVA, 420/11/6.9 KV three Phase Station Transformer & 25MVA 21/6.9KV Three phase Unit Aux Transformer as a common pool spares for BTPS 500MW, Khaparkheda 500 MW and Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 22 | 22 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, installation, commissioning and testing of Station Batteries of Unit-8&9 CSTPS alongwith all outdoor batteries | 0 | - | 0 | 0 | 0 | 0 | 12 | 12 |  |  | 12 | 0
| I&C -III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Upgradation of Analysis & Diagnostics system (A&D) for VMS and TSI system at Unit-8&9, CSTPS, Chandrapur.& other schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of Analysis & Diagnostics system (A&D) for VMS and TSI system at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 17 | 17 | 0 | 0 | 0 |  |  | 0 | 0
| Installation of CO analysers at Eco outlet at Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
| Complete Engineering Retrofitting of Existing 196 NT Controller by DT 9 Controller alongwith HMI units for Unit 8/9 coal feeder system. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of spares for LP bypass system. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of spares for maxDNA DCS system | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
2 | Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-9, CSTPS, Chandrapur. | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
3 | Upgradation of HMI and hardware of GE make PLCs installed at Unit-8&9, CSTPS, Chandrapur. & other schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of HMI and hardware of GE make PLCs installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of TD-BFP Turbovisory system installed at Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of EWLI system installed at Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of O2 analysers installed at Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
| Installation of High temperature Camera system at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of HEA igniter system at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of Flue Gas Analysers and Opacity Analysers at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
4 | Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-8, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-8, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 30 | 30 |  |  | 30 | 0
5 | Multiple schemes C&I-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Total Mercury (Gaseous) Analyzers along with their online data connectivity & Remote calibration U-3 to 9 | 0 | - | 0 | 3 | 3 | 0 | 6 | 6 |  |  | 6 | 0
| Procurement of Controllers & Com Boxes for Air Compressors of Unit-8&9. | 0 | - | 0 | 5.5 | 5.5 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of Steam and Water Analysis System (SWAS) for Unit – 8 & 9 | 0 | - | 0 | 13 | 13 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of Servo valve (ST) with proportional valves (PV) for HP bypass system at Unit – 8 & 9 | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of GEHO pump VFD panels for Unit – 8 & 9 | 0 | - | 0 | 9 | 9 | 0 | 0 | 0 |  |  | 0 | 0
6 | Upgradation of measurement and control system installed at CSTPS Unit 8&9 & Upgradation of Numerical Protection Relay of Alstom / Schnieder make installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of measurement and control system installed at CSTPS Unit 8&9 | 0 | - | 0 | 0 | 0 | 0 | 20 | 20 |  |  | 20 | 0
| Upgradation of Numerical Protection Relay of Alstom / Schnieder make installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
| AHP-III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | supply of piston cylinder assembly, diaphragm assembly, Suction and discharge valve housing assembly of GEHO pump (Model- TZPM 1200). & other schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-1 :supply of piston cylinder assembly, diaphragm assembly, Suction and discharge valve housing assembly of GEHO pump (Model- TZPM 1200). | 0 | - | 0 | 13 | 13 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme -2 :Procurement of sub assemblies for conveying air compressor model ZR 275 and instrument air compressor model ZR 110 in Ash handling plant Unit-8&9 (2x500MW) at CSTPS, Chandrapur. | 0 | - | 0 | 18 | 18 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme -3 Supply of 10/8 FAH Warman make slurry pump impeller element assembly, Bearing assembly unit, jacket assembly. | 0 | - | 0 | 12 | 12 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply and replacement of 400 NB MSERW pipeline of ash disposal system of unit 8&9 at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 :Supply and replacement of 400 NB MSERW pipeline of ash disposal system of unit 8&9 at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 70 | 70 |  |  | 70 | 0
3 | Complete ESP Refurbishment of 1st & 2 nd Row Field of Unit 8&9 at CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 : Complete ESP Refurbishment of 1st & 2 nd Row Field of Unit 8&9 at CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP - D | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Upgradation Of Hydraulic Systems with Safety Mechanism for wagon unloading system at CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply erection & commissioning of wagon tippler, Side Arm Charger, apron feeder and stacker hydraulic drive system with online NAS value monitoring systems. | 0 | - | 0 | 16 | 16 | 0 | 8 | 8 |  |  | 8 | 0
0 | Wagon stopping mechanism (Safety) | 0 | - | 0 | 4 | 4 | 0 | 2 | 2 |  |  | 2 | 0
2 | Upgardation and Capacity Enhancement of Side Arm Charger Apron Feeder and Bunker Conveyors at CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | capacity enhancement to 60 wagons pulling capacity and associated modification of existing side arm charger | 0 | - | 0 | 10 | 10 | 0 | 10 | 10 |  |  | 10 | 0
0 | Capacity enhancement , Commissionng of apron feeder drive | 0 | - | 0 | 4 | 4 | 0 | 2 | 2 |  |  | 2 | 0
0 | Modification and revamping of Apron Feeder 101,102,103 | 0 | - | 0 | 7.5 | 7.5 | 0 | 6 | 6 |  |  | 6 | 0
0 | Supply,Installation and Commissioning of double drive Mechanism with Split Case Bearings for Tripper Trolley and bunkering conevyor belts of CHP-D, CSTPS | 0 | - | 0 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
0 | Modification of Fixed Tripper Head Pulley(Z-Point) of BC110A&B at CHP-D CSTPS. | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
0 | Modification, Errection & Commissioning of drive unit capacity enhancement for conveyor at CHP-D, Chandrapur TPS. | 0 | - | 0 | 3 | 3 | 0 | 3 | 3 |  |  | 3 | 0
3 | Performance Improvement Schemes of CHP-D CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design engineering , supply and installation of modular chutes with weld cast Liners ,flap gates and actuators. | 0 | - | 0 | 35 | 35 | 0 | 15 | 15 |  |  | 15 | 0
0 | Supply erection & commissioning of set of internal of spares of Wagon tippler and Side Arm Charger installed at CHP-D, CSTPS Chandrapur | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply erection & commissioning of set of internal of spares of stacker reclaimer installed at CHP-D, CSTPS Chandrapur | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply erection & commissioning of set of internal of spares of Impact crusher installed at CHP-D, CSTPS Chandrapur | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply erection & commissioning of set of internal of spares of wobbler feeder installed at CHP-D, CSTPS Chandrapur | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply erection & commissioning of 1500 TPH capacity Stacker Recliamer sleeving bearing with fastener of CHP-D (U8&9), CSTPS, Chandrapur | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of Gearbox assemblies at CHP-D CSTPS. | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
0 | Structure Strengthening,Modification works of Conveyors at CHP-D CSTPS | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
4 | Design, Installation, testing and commissioning of new conveyor systems of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Installation, testing and commissioning of conveyor system from crusher house to TP-108 of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 50 | 50 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Engineering, erection and commissioning of one 1500TPH crusher, short conveyors from TP 106 and open space of near Stack yard A pile to Crusher inlet and a telescopic conveyor at the output of crusher to Stack Yard B pile of CHPD Unit 8&9, CSTPS. | 0 | - | 0 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design, Installation and commissioning of conveyor system from rope way of CHP-A to crusher house of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Installation and commissioning of conveyor system from rope way of CHP-A to crusher house of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 50 | 50 |  |  | 50 | 0
6 | Infrastructure Development Schemes at CHP-D CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Supply,Installation and Commissioning of EOT Cranes at Wagon Tippler area of CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 15 | 15 |  |  | 15 | 0
0 | Belt Tracking systems for Carrying/Return 1400/1600 mm belt width | 0 | - | 0 | 1.25 | 1.25 | 0 | 1.25 | 1.25 |  |  | 1.25 | 0
0 | Ceramic Lagging by direct bonding on Conveyor Pulleys without Rubber Pad/Rubber Sheets. | 0 | - | 0 | 1.5 | 1.5 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
0 | Rewamping of crane and hoist of CHP, Unit 8&9, CSTPS, Chandrapur | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Material lifting mechanism at Crusher, bunker and Tunnel area of CHP-D CSTPS. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping, modification of TunnelAir ventilation system | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping, modification of DE and DS system | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping, modification of Dewatering and water recirculation system | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of New Office Building with Infrastructure ,Interior Development at CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
0 | Material Storage Shed Fabrication work at CHP-D CSTPS | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
7 | Electrical schemes for improvement in availability & Reliability of CHP-D,CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design supply installation and commisioning of LED based energy efficient system for illumination at CHPD | 0 | - | 0 | 5 | 5 | 0 | 5 | 5 |  |  | 5 | 0
0 | Supply, Erection, Commissioning and Testing of 7.2KV SF6 HT Contactor for retrofitting of existing BHEL make Vacuum Circuit Breakers of CHP-D, CSTPS | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of GE make 90-30 series PLC system installed at stacker rclaimer and wagon tippler at CHP-D, CSTPS | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Installation of energy efficient air temperature controlling system at various MCC rooms of CHPD, CSTPS | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Alterration, upgradation of tunnel ventilation system of CHPD, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Fabrication, Erection & commissioning of cable support structure along with re-routing & trial of auxiliaries at Crusher PMCC, compressor house & short conveyor area at CHP-D, CSTPS | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and installation of LT air circuit breakes at CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
0 | Design, supply, installation & commissioning of solar based energy efficient illumination system at CHP-D, CSTPS | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of HT motors for various auxiliaries at CHP-D, CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
0 | Supply & installation of high capacity submersible slurry pump at CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reconditioning of MCC Board feeder panels at CHP-D,U #8&9.CSTPS,Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & installation of anoodized winding magnets along with control panels for installation at various conveyor belts of CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of 69 AH HBL make battery set of CHP-D (U8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of 100 AH Exide make battery banks (2 Set/ 110 Nos battery cells) & battery charge at CHP-D (U8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Alterration, upgradation of tunnel ventilation system of CHPD, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of HT/LT Xmers assy of CHP-D (U8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of HT/LT Xmers assy of CHP-D (U8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | WTP-III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Engineering, installation and commissioning of DM stream capacity of 4800M3/Day for U # 8 & 9 in addition to existing DM stream at WTP, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Engineering, installation and commissioning of DM stream capacity of 4800M3/Day for U # 8 & 9 in addition to existing DM stream at WTP, CSTPS, Chandrapur | 0 | - | 0 | 46.4 | 46.4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Civil - 8&9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work of diversion of peripheral nallah towards ash water recovery pump house alogwith construction of waste wear at ash bund area CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Work of diversion of peripheral nallah towards ash water recovery pump house alogwith construction of waste wear at ash bund area CSTPS, Chandrapur. | 0 | - | 0 | 35.4 | 35.4 | 0 | 0 | 0 |  |  | 0 | 0
2 | Infrastructure development of CHP-D area at U-8, 9, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of platform for unloading of coal near TP-106 upto stack pile A of CHP-D | 0 | - | 0 | 0 | 0 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
0 | Provision of WBM Road for fire fighting arrangement at CHP-D U-8,9 | 0 | - | 0 | 0 | 0 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
0 | Construction & Pushing RCC box of size 2mx2m under railway track to drain out the surface water near Rly - A cabin Unit-8,9 | 0 | - | 0 | 0 | 0 | 0 | 6 | 6 |  |  | 6 | 0
0 | Construction of concrete pavement road connecting to reject gate & vinchoda chowk , Y point to ash recovery pump house | 0 | - | 0 | 0 | 0 | 0 | 30 | 30 |  |  | 30 | 0
HO1 | CHP Improvement Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at CHP-D | 0 | - | 0 | 100 | 100 | 0 | 0 | 0 |  |  | 0 | 0
HO2 | Developlment & Upgradation of DSM software system for MSPGCL | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Developlment & Upgradation of DSM software system for MSPGCL | 0 | - | 0 | 55 | 55 | 0 | 0 | 0 |  |  | 0 | 0
1 | Implementation of Flexible Operation Solutions | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Flexible Operation Solutions | 0 | - | 0 | 34 | 34 | 0 | 0 | 0 |  |  | 0 | 0
0 |  | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | General asset | 0 | - | 0 | 3.2096 | 3.2096 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply, Operation & Maintenance of Mobile Coal Sampling Equipment (MCSE) for coal sampling at loading ends of WCL for Mahagenco | 0 | - | 0 | 3.1648 | 3.1648 | 0 | 0 | 0 |  |  | 0 | 0
3 | ABC Powder Type and Foam Type Composite Fire Extinguisher | 0 | - | 0 | 1.528 | 1.528 | 0 | 0 | 0 |  |  | 0 | 0
4 | NON-Detailed Project Report for the Work of Upgradation/Renovation of Crusher House of CHPB of Unit-5, 6&7 at CSTPS Chandrapur (benefit U-8,9 by short conveyor coal stacking in catering emergency) | 0 | - | 0 | 2.8807 | 2.8807 | 0 | 0 | 0 |  |  | 0 | 0
5 | Extention of stacker reclaimer area for improvement in coal stack management at CHP-D CSTPS Chandrapur U-8,9 | 0 | - | 0 | 8.46 | 8.46 | 0 | 0 | 0 |  |  | 0 | 0
6 | Retrofitting of BHEL make HT Circuit Breaker with SF6 Contactor at CHP-D, Unit-8&9 | 0 | - | 0 | 4.25 | 4.25 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 2656.318 | 2708.2884 | -51.9704 | 360.555 | 360.555 | 0 | 0 | 360.555 | -51.9704
FY 2028-29
A) Approved Add Cap (Case No. 296 of 2019)
1 | Initial Spares | Approved Add Cap (Case No. 296 of 2019)
| Boiler & Auxiliaries | 0 | - | 10.36 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Bevel Helical Gear box KMP-350 for XRP 1043 coal mills at unit-8&9,CSTPS, Chandrapur. | 0 | - | 0 | 7.4087 | 7.4087 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Hydraulic Adjustment (Actuating) Device for PA fan model PAF 19/10.6-2 and FD fan FAF 23/12.5-1 at Unit 8&9, CSTPS, Chandrapur. | 0 | - | 0 | 1.3971 | 1.3971 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Yokogawa make Zirconia Oxygen Analyser spares for C&I-III, Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 0.51933 | 0.51933 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of High pressure valves installed at unit-8&9 ( 2x500 MW),CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Turbine & Aux | 0 | - | 1.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of IMI Norgren Herion make Trip solenoid valves for Main Turbine, MD-BFP & TD-BFP of Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.37354 | 0.37354 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Speed Sensors for 500 MW KWU Turbine for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.038232 | 0.038232 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Position Feedback Transmitters for Starting Device and Speeder Gear of Main Turbine for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.11225 | 0.11225 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for LP bypass system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur on OEM Basis. | 0 | - | 0 | 0.43645 | 0.43645 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of TSE (Turbine Stress Evaluator) temperature elements for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.2073 | 0.20719 | 0.00010699 | 0 | 0 |  |  | 0 | 0.00010699
| Generator and Auxiliries | 0 | - | 0.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of complete set of water cooled bushing for 500MW Generator installed at Unit-8 & 9, CSTPS Chandrapur. | 0 | - | 0 | 0.26409 | 0.26409 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Tushaco make complete AC Jacking Oil Pump for Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.19949 | 0.19949 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of oil filled Neutral Grounding Transformer for AHP Unit-8&9 CSTPS , Chandrapur. | 0 | - | 0 | 0.34775 | 0.34775 | 0 | 0 | 0 |  |  | 0 | 0
| Electrical and Instrumentation | 0 | - | 29.23 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| ‘Procurement of various spares of BHEL make Vacuum Circuit Breakers’ , for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.49498 | 0.49498 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, erection and commissioning of floor mounted 500KW Resistor Load Bank for D.G. sets installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.27536 | 0.27536 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Turbosupervisory system spares of main turbine for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 1.0366 | 1.0366 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Level transmitters for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.15999 | 0.15999 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Level transmitters for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.032605 | 0.032605 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Level transmitters for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.046973 | 0.046973 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of GE PLC spares for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.57304 | 0.57304 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for GEHO pumps PLC control panels for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.084378 | 0.084378 | 2.6e-08 | 0 | 0 |  |  | 0 | 2.6e-08
| Procurement of master calibration lab Instruments for C&I-III, Unit 8 & 9,CSTPS,Chandrapur | 0 | - | 0 | 0.30131 | 0.30131 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Coal Feeder panel spares for C&I-III, Unit 8 & 9,CSTPS, Chandrapur | 0 | - | 0 | 0.58701 | 0.58701 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Opacity Monitor (Stack Particulate matter-SPM) spares for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.14051 | 0.14051 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Forbes Marshall Supervisory system spares For Turbine driven boiler feed pumps (TDBFP) of Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.22449 | 0.22449 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for hydraulic panel of CW pumps for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.13862 | 0.1386 | 1.7196e-05 | 0 | 0 |  |  | 0 | 1.7196e-05
| Procurement of H2 Dew point analyzer spares for Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.049938 | 0.049938 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for HP bypass system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.33965 | 0.33965 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Position feedback transmitter for HP bypass system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.0354 | 0.0354 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Atlas Copco make Instrument, Service and Conveying air Compressors for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.22509 | 0.22509 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for HEA Ignitors and Flame Scanners for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.037701 | 0.037701 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for GEHO pumps of Ash Handling System at C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.28861 | 0.28861 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Turbine side control valve spares for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.17974 | 0.17974 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various numerical protection relays for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.12307 | 0.12307 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various numerical protection relays for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.13184 | 0.13184 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various numerical protection relays for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.13863 | 0.13863 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for DB POWER make UPS system installed at HCSD Pump House, Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.064757 | 0.064757 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Fully Automatic Capacitance & Dissipation Factor (Tan- Delta) measuring kit for Unit-8 &9, CSTPS, Chandrapur. | 0 | - | 0 | 0.48288 | 0.48288 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of various VFD spares for ID fans of Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.546 | 0.546 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of DAVR spares installed at Unit -8&9 CSTPS, Chandrapur. | 0 | - | 0 | 0.5945 | 0.5945 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 3 phase relay test kit for Unit-8 &9, CSTPS, Chandrapur. | 0 | - | 0 | 0.35388 | 0.35388 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Fast Bus Transfer System (FBTS) installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.37288 | 0.37288 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various spares for battery chargers installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.40022 | 0.40022 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Auto synchronizing Relay (ASR) & Load Shedding Relay (LSR) installed at Unit-8 &9, CSTPS, Chandrapur. | 0 | - | 0 | 0.34973 | 0.34973 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ESP spares i.e. Field Controller, Thyristor and Trigger card for ESP of Unit-8 & 9, CSTPS Chandrapur. | 0 | - | 0 | 0.26745 | 0.26745 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various VFD spares for GEHO pump of Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.54416 | 0.54416 | 0 | 0 | 0 |  |  | 0 | 0
| Design, Supply, Erection & Commissioning of On-Line Dissolved Gas Analyzers for various Transformers installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 3.1775 | 3.1775 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, Erection & Commissioning of On-Line Dissolved Gas Analyzers for Station Transformers -8B, Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.30519 | 0.30519 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘TOROSHIMA’ make 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motor (without pump casing) for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 4.2037 | 4.2037 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 90kVA ESP Rectiformer for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.29878 | 0.29878 | 0 | 0 | 0 |  |  | 0 | 0
| Supply erection & commissioning of Aviation Lighting for NDCT of Unit-8&9, CSTPS Chandrapur | 0 | - | 0 | 0.57261 | 0.57261 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Transformer oil storage tanks of different capacity for Unit-8&9 CSTPS Chandrapur. | 0 | - | 0 | 0.57024 | 0.57024 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 2000kW & 315kW, 6.6 kV HT motors for CW & ACW Pump installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 1.4505 | 1.4505 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 3.25MVA, 6.6/2.3kV VFD Transformers of vector group DY11 for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.3941 | 0.3941 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 3.25MVA, 6.6/2.3kV VFD Transformer of vector group ‘Dd0’ for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.3905 | 0.3905 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘MARATHON’ makes HT/LT Induction motors for various Critical auxiliaries installed at Unit-8 &9, CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of 1.2V, Ni-Cd battery cells for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.12496 | 0.12496 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of 1.2V, Ni-Cd battery cells for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.18931 | 0.18931 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘Air Core DC Reactor’ for VFD and ‘NGR’ for UAT/ Station Transformers installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.44368 | 0.44368 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘Air Core DC Reactor’ for VFD and ‘NGR’ for UAT/ Station Transformers installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.12551 | 0.12551 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘BHEL’ make 680 KW, 6.6KV, Coal Mill Motor for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.37913 | 0.37913 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 400kV OIP Condenser Bushing for Generator Transformer & Station Transformer of Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.49064 | 0.49064 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘11kW DC motor with Control Cabinet’ for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.2242 | 0.2242 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 37kW, 415V motors for Primary Water Pump installed at Unit-8 &9, CSTPS Chandrapur. | 0 | - | 0 | 0.0096851 | 0.0096851 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 15 KW, 415V LT Motor for Service Building & TG Building Lift installed at Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.095155 | 0.095155 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 16KW, 415V LT Motor for Boiler Lift installed at Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.044179 | 0.044179 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, Erection, Testing and Commissioning of Hydrastep-Electronic Drum Level Indicator and its associated accessories for Unit-9, CSTPS, Chandrapur | 0 | - | 0 | 0.27376 | 0.27376 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for BHEL make Hydrastep (Electronic Water Level Indicator -BHELVISION 20M) for Unit 8 & 9, CSTPS, Chandrapur on OEM basis. | 0 | - | 0 | 0.084172 | 0.084172 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Electrodes for Hydrastep (Electronic Water Level Indicator -BHELVISION 20M) for Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.10384 | 0.10384 | 0 | 0 | 0 |  |  | 0 | 0
| Engineering & Retrofitting of 196 NT Controller to DT 9 Controller for Unit-8 & 9 Coal Feeder System. | 0 | - | 0 | 0.38076 | 0.38076 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for BHEL make Acoustic steam leak detection system (BHELSONIC) (BS10) for Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.077807 | 0.077807 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of LT Circuit Breaker assemblies for ESP LT Panels (LTMSB & ACP) of Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.25429 | 0.25429 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for BHEL make maxDNA Distributed control system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 1.117 | 1.117 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of Transformer oil BDV test kit DTA 100C and Oil Tan Delta & Resistivity Tester DTL C at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.47598 | 0.47598 | 0 | 0 | 0 |  |  | 0 | 0
| Outdoor Plant ( CHP/AHP/WTP) | 0 | - | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Elecon make KCN-560 type Gearbox for Apron Feeder installed at CHPD, CSTPS. | 0 | - | 0 | 1.6717 | 1.6717 | -6e-08 | 0 | 0 |  |  | 0 | -6e-08
| Procurement of spares of CKB-280,225,200,8180 typ gearbox installed at CHP-D | 0 | - | 0 | 1.0015 | 1.0015 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Gear Box (MAKE: NEW ALLENBERRY) Spares at CHP-D; CSTPS, Chandrapur. | 0 | - | 0 | 0.5177 | 0.5177 | 1.8e-08 | 0 | 0 |  |  | 0 | 1.8e-08
| Procurement of spares for m/s Elecon make Impact Crusher installed at CHP Unit 8&9 CSTPS, Chandrapur | 0 | - | 0 | 0.84103 | 0.84103 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of V belt pulley of rotor for Impact crusher installed at CHP-D, CSTPS | 0 | - | 0 | 0.11864 | 0.11864 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Spares for hydraulic systems installed at CHPD, CSTPS. | 0 | - | 0 | 0.47537 | 0.47537 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Spares for hydraulic systems installed at CHPD, CSTPS. | 0 | - | 0 | 0.028604 | 0.028604 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of drive & non drive pulley for various conveyors installed at CHP D, CSTPS, Chandrapur. | 0 | - | 0 | 0.25792 | 0.25792 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of drive & non drive pulley for various conveyors installed at CHP D, CSTPS, Chandrapur. | 0 | - | 0 | 0.0914 | 0.0914 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Chain links for apron feeder installed at CHP D, CSTPS, Chandrapur. | 0 | - | 0 | 0.40289 | 0.40289 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of internal spares for Elecon make PWD-18, PLB-25 & SCN-180 type Gearbox for Stacker Reclaimer & wobbler feeder installed at CHP D, CSTPS. | 0 | - | 0 | 0.52774 | 0.52774 | 3.1e-08 | 0 | 0 |  |  | 0 | 3.1e-08
| Supply of GE Make Switchgear Spares for GE Make LT Feeders | 0 | - | 0 | 0.12485 | 0.12485 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Fluidomat make scoop coupling installed at CHP–D, CSTPS, Chandrapur | 0 | - | 0 | 0.48355 | 0.48355 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Oil Filtering machine for hydraulic power packs installed at CHPD, CSTPS | 0 | - | 0 | 0.10592 | 0.10592 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of LT Motors at CHP-D (U#8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0.11302 | 0.11302 | 0 | 0 | 0 |  |  | 0 | 0
| Supply and Installation of Oil Cooled Suspended Anodized Winding Magnet & Control Panel at CHP, Unit 8&9, CSTPS, Chandrapur. | 0 | - | 0 | 2.2967 | 2.2967 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of LT power and control cable for CHP-D | 0 | - | 0 | 0.26256 | 0.26256 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of LT power and control cable for CHP-D | 0 | - | 0 | 0.0477 | 0.0477 | 0 | 0 | 0 |  |  | 0 | 0
2 | Capital Spare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| HPT MODULE | 0 | - | 45.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of HP turbine Module along with breach nuts and pipe spool pieces (Type: H30-100-2) for Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 32.332 | 32.332 | 0 | 0 | 0 |  |  | 0 | 0
| LPT ROTOR | 0 | - | 40.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Fully Bladed & Dynamically Balanced LP Rotor (N30-2X10-2) for Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 29.03 | 29.03 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of set of Free Standing Moving Blades for LP Rotor (N30-2X10-2) for Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 4.5629 | 4.5629 | 0 | 0 | 0 |  |  | 0 | 0
| BFP CARTRIDGE ( 2NOS ) | 0 | - | 4.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of cartridge assembly for Boiler Feed Pump model FK-4E-36 (with Four S/H & 2 R/H spray branches) installed at 2X 500MW, CSTPS, Chandrapur. | 0 | - | 0 | 2.515 | 2.5149 | 6e-05 | 0 | 0 |  |  | 0 | 6e-05
| BCW PUMP | 0 | - | 3.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for ‘TOROSHIMA’ make 350KW BCW Pump-Motor installed at Unit-8 &9, CSTPS Chandrapur. | 0 | - | 0 | 1.3283 | 1.3283 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various spares for ‘TOROSHIMA’ make Boiler Circulating Water (BCW) pump-motor installed at Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 2.2326 | 2.2326 | 0 | 0 | 0 |  |  | 0 | 0
| 15 MVA DRY TYPE TRANSFORMER | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spare ‘Cast Resin Dry Type Transformers (CRTs)’ of different ratings for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 6.0213 | 6.0213 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of phase coil limb and spares of Cast Resin Dry Type Transformers of different ratings for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 7.9255 | 7.9255 | 0 | 0 | 0 |  |  | 0 | 0
| BTG+BOP& Other Works | 0 | - | 20.48 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Design, Supply & Installation, Testing & Commissioning of Public Addressing System for tunnels of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 1.1544 | 1.1544 | 0 | 0 | 0 |  |  | 0 | 0
| Work of upgradation, installation and extension of 220VDC control supply to various PMCC of CHPD, CSTPS, Chandrapur. | 0 | - | 0 | 0.68441 | 0.68441 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Apron Feeder in CHP Unit 8&9 (2x500) MW at CHP-D, CSTPS. | 0 | - | 0 | 2.3388 | 2.3388 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of spares for up gradation of rotary parts of travelling conveyor system installed at CHPD, CSTPS, Chandrapur. | 0 | - | 0 | 0.58939 | 0.58939 | 0 | 0 | 0 |  |  | 0 | 0
| The Work of Design, Engineering, Manufacturing, Supply, Erection & Commissioning of Short Conveyor belt from stack yard of CHP of Unit 5,6&7 to Belt Conveyor 104 A/B at CHP of Unit 8&9, CSTPS, Chandrapur | 0 | - | 0 | 5.6825 | 5.6825 | 0 | 0 | 0 |  |  | 0 | 0
| Work of design, supply, erection, commissioning of overhead cable tray along with removal & re-routing of power and control cables at CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0.51324 | 0.51324 | 0 | 0 | 0 |  |  | 0 | 0
| Work of provision, modification, retrofitting and revamping of lighting system of transfers points, crusher house and bunker area of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 1.0105 | 1.0105 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for M/s. Weir Minerals make (GEHO pump Model TZPM-1200) for Ash Handling Plant Unit# 8 &9 CSTPS Chandrapur. AHP-III | 0 | - | 0 | 2.106 | 2.106 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Gear Box set of internal (MAKE: NEW ALLENBERRY) Spares at CHP-D; CSTPS, Chandrapur. | 0 | - | 0 | 1.6904 | 1.6904 | 0 | 0 | 0 |  |  | 0 | 0
| Supply and Installation of Oil Cooled Suspended Anodized Winding Magnet & Control Panel at CHP, Unit 8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 196 NT Controller by DT 9 Controller alongwith HMI units for Unit- 8&9 coal feeder system | 0 | - | 0 | 2.0774 | 2.0774 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of set of CW Impeller duly fitted with wear rings & ACW Impeller duly fitted with wear rings of Mather & Platt make Pumps installed at Unit-8 & 9,CSTPS,Chandrapur | 0 | - | 0 | 0.70379 | 0.70379 | 0 | 0 | 0 |  |  | 0 | 0
| CHP System U#8 | 0 | - | 0 | 0.05 | 0.05 | 0 | 0 | 0 |  |  | 0 | 0
| ISOLATED PHASE BUS DUCT | 0 | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| SEGREGATED PHASE BUS DUCT U#8 | 0 | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| SEGREGATED PHASE BUS DUCT U#9 | 0 | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| ISOLATED PHASE BUS DUCT U#9 | 0 | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| DTT & UAT U#8 | 0 | - | 0 | 0.03 | 0.03 | 0 | 0 | 0 |  |  | 0 | 0
| DTT & UAT U#9 | 0 | - | 0 | 0.03 | 0.03 | 0 | 0 | 0 |  |  | 0 | 0
| Cranes and hoists U#8 | 0 | - | 0 | 0.03 | 0.03 | 0 | 0 | 0 |  |  | 0 | 0
| RCC Chimney U#8 | 0 | - | 0 | 9.29 | 9.29 | 0 | 0 | 0 |  |  | 0 | 0
| Coal Handling Plant | 0 | - | 0 | 41.79 | 41.79 | 0 | 0 | 0 |  |  | 0 | 0
| Bunker foundation & civil works (Unit 8) U#8 | 0 | - | 0 | 18.58 | 18.58 | 0 | 0 | 0 |  |  | 0 | 0
| Boiler & Auxiliaries U#9 | 0 | - | 0 | 9.2889 | 9.2872 | 0.0017338 | 0 | 0 |  |  | 0 | 0.0017338
| ESP U#9 | 0 | - | 0 | 2.1589 | 2.1589 | 0 | 0 | 0 |  |  | 0 | 0
| ID fan foundations (Unit 9) U#9 | 0 | - | 0 | 1.7489 | 1.7489 | 0 | 0 | 0 |  |  | 0 | 0
| DRY ASH SILO-12M DIA U#8 | 0 | - | 0 | 1.22 | 1.22 | 0 | 0 | 0 |  |  | 0 | 0
| FD fan foundations (Unit 9) U#9 | 0 | - | 0 | 0.62891 | 0.62891 | 0 | 0 | 0 |  |  | 0 | 0
| PA fan foundations (Unit 9) U#9 | 0 | - | 0 | 0.54891 | 0.54891 | 0 | 0 | 0 |  |  | 0 | 0
| Natural Draft cooling tower- Unit 8 U#8 | 0 | - | 0 | 0.32 | 0.32 | 0 | 0 | 0 |  |  | 0 | 0
| Main power house building-Civil Works-Unit no.-9 U | 0 | - | 0 | 0.15 | 0.15 | 0 | 0 | 0 |  |  | 0 | 0
| Structural Steel works for main power house buildi | 0 | - | 0 | 0.15 | 0.15 | 0 | 0 | 0 |  |  | 0 | 0
| Canteen U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Security and time office U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| CARS SCOOTERS AND CYCLE SHED U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Fire Station U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Watch towers U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| First aid station | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Tranformer yard U#8 | 0 | - | 0 | 0.02 | 0.02 | 0 | 0 | 0 |  |  | 0 | 0
| Rain Water Harvesting Scheme U#8&9 | 0 | - | 0 | -0.01 | -0.01 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Advance Multipurpose Fire Tender | 0 | - | 0 | 3.45 | 3.45 | 0 | 0 | 0 |  |  | 0 | 0
| DM Stream | 0 | - | 29.65 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| DM Stream capacity of 100 M3/Hr in addition to existing stream of WTP. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| CIVIL | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Bridge | 0 | - | 4.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Railway, CHP, AHP etc | 0 | - | 152.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| B. G. railway siding Pway works | 0 | - | 0 | 41.5165 | 41.5165 | 0 | 0 | 0 |  |  | 0 | 0
| S & T work for B.G. railway siding | 0 | - | 0 | 0.023574 | 0.023574 | 0 | 0 | 0 |  |  | 0 | 0
| Consultancy services for B. G. railway siding | 0 | - | 0 | 0.035636 | 0.035636 | 0 | 0 | 0 |  |  | 0 | 0
| Ash infra in Railway | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Bunker structure (Unit 8) U#8 | 0 | - | 0 | 18.57 | 18.57 | 0 | 0 | 0 |  |  | 0 | 0
| Coal Mills | 0 | - | 0 | 1.1389 | 1.1389 | 0 | 0 | 0 |  |  | 0 | 0
| Bunker foundation & civil works (Unit 9) U#9 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Bunker structure (Unit 9) U#9 | 0 | - | 0 | 0.11 | 0.11 | 0 | 0 | 0 |  |  | 0 | 0
| HCSS silo-12m dia U#8 | 0 | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| Ash water PH, HCSD PH, Bottom ash slurry PH U#8 | 0 | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| Ash compressor house & Control room U#8 | 0 | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| MILL REJECT SILO U#8 | 0 | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| Fire protection & Detection system U#8 | 0 | - | 0 | 0.71423 | 0.71423 | 0 | 0 | 0 |  |  | 0 | 0
| DM Water Pump room U#8 | 0 | - | 0 | 4.25 | 0 | 4.25 | 0 | 0 |  |  | 0 | 4.25
| Filter water reservoir & pump house U#8 | 0 | - | 0 | 4.29 | 0 | 4.29 | 0 | 0 |  |  | 0 | 4.29
| ACW + RW + Filtered water piping U#8 | 0 | - | 0 | 2.2409 | -0.0096938 | 2.2506 | 0 | 0 |  |  | 0 | 2.2506
| Laboratory Building U#8 | 0 | - | 0 | 0.12 | 0 | 0.12 | 0 | 0 |  |  | 0 | 0.12
3 | Staff quarters | 0 | - | 15.04 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Work of exterior repair, providing painting to A, D & E type residential buildings and Public Buildings and allied civil works in Urjanagar Colony, CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Staff Quarters- Repair and renovation of E type staff quarters to extend the life of buildings at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Staff Quarters - Repair and renovation of 'B' type staff quarters in residential colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair of D type quarters in colony at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair of C type quarters in colony at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Staff Quarters- Repair and renovation of F and NF type staff quarters to extend the life of buildings at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair and replacement of existing drinking water supply pipelines in E & F type area in colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair and replacement of existing sewer lines in E & F type area in colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Work of providing RCC drain along main roads in colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Rerouting and replacement of domestic water supply pipeline from WTP to ESR in colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Additional Contengencies approved vide e BR No. MSPGCL/BM-162/165, Dt.29.10.2016 vide resolution no. 2016/2085 | 0 | - | 7.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Landscaping and plantation work at various locations inside plant area at CSTPS, chandrapur. | 0 | - | 0 | 3.4266 | 3.4266 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of WBM approach road from point- N to Z Area along ash bund periphery at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design, Engineering, Supply and commissioning of ash-bund water recovery system (Phase II) at CSTPS Chandrapur | 0 | - | 27.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, Engineering, Supply and commissioning of ash-bund water recovery system (Phase II) at CSTPS Chandrapur | 0 | - | 0 | 30.0361 | 30.0361 | 0 | 0 | 0 |  |  | 0 | 0
| Providing Consultancy Services for work of Design, Engineering, Supply, Installation & Commissioning of ash bund water recovery system (Phase-II) at CSTPS, Chandrapur (on EPC contract basis). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Providing laying, jointing and commissioning of 1600 mm dia. M.S. Pipe line from Erai dam to one day reservoir of stage II, III & IV at CTPS | 0 | - | 73.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Providing laying, jointing and commissioning of 1600 mm dia. M.S. Pipe line from Erai dam to one day reservoir of stage II, III & IV at CTPS | 0 | - | 0 | 73.6091 | 73.6091 | 0 | 0 | 0 |  |  | 0 | 0
| Work of construction of Control Valve rooms on newly laid 1600 mm M.S. Pipeline no. 6 from Erai dam to One day reservoir at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Providing OHE facility for BG Rly siding of proposed Expansion Project at Chandrapur, for Supply of Materials. | 0 | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Providing OHE facility for BG Rly siding of proposed Expansion Project at Chandrapur, for errection of OHE Items. | 0 | - | 2.5 | 0.7 | 0 | 0.7 | 0 | 0 |  |  | 0 | 0.7
9 | Irrigation scheme for landscaping and Plantation work at Chandrapur expansion project chandrapur. | 0 | - | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Asphalting of WBM road from Nagpur gate to Awanda gate. | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Asphalting of WBM road from Nagpur gate to Awanda gate. | 0 | - | 0 | 0.65141 | 0 | 0.65141 | 0 | 0 |  |  | 0 | 0.65141
| Asphalting over WBM Road of ADP line Service road from Nagpur gate opening to Awandha junction gate at CSTPS Chandrapur | 0 | - | 0 | 0.84833 | 0.84833 | 0 | 0 | 0 |  |  | 0 | 0
| Asphalting of WBM road from Nagpur gate to Awandha gate at CSTPS Chandrapur - Asphalting of road from Reject coal gate to Motghat nallah at CSTPS Chandrapur (PHASE - I) | 0 | - | 0 | 0.47941 | 0.47941 | 0 | 0 | 0 |  |  | 0 | 0
11 | Foot Over Bridge | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Work of Providing retaining wall for sand hump at Vivekanand nagar station yard under modification work in wardha end fro 2 x 500 MW Expn. Project at CSTPS, Chandrapur. | 0 | - | 0.3 | 0.25515 | 0.25515 | 0 | 0 | 0 |  |  | 0 | 0
| Additional Capitalization by O & M | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of GE make 4000Amp LT Air Circuit Breakers for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0.9 | 1.0308 | 1.0308 | 0 | 0 | 0 |  |  | 0 | 0
2 | Air Compressor System | 0 | - | 0.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Energy management Sysytem | 0 | - | 0.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, Installation, Testing & Commissioning of Energy Management System for Unit#8 & 9 for CSTPS, Chandrapur. | 0 | - | 0 | 0.20054 | 0.20054 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Tri-vector 0.2s class Digital Energy meter for Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.094872 | 0.094872 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, Installation & Commissioning of 3D Level Scanners to 64 nos. of ESP hoppers at Unit-8&9 (2X500MW), CSTPS, Chandrapur. | 0 | - | 3.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of internal spares for Elecon make PWD-18, PLB-25 ,Pbh-71 type Gearbox for Stacker Reclaimer installed at CHPD, CSTPS. | 0 | - | 0 | 1.1089 | 1.1089 | 0 | 0 | 0 |  |  | 0 | 0
5 | 4000/2500/1800/800 A GE make LT CKT Brkr | 0 | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| LT Air Circuit Breakers for Incomer Feeders at CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 1.4207 | 1.4207 | 0 | 0 | 0 |  |  | 0 | 0
| LT Air Circuit Breakers at CHP, Unit 8&9, CSTPS | 0 | - | 0 | 1.0141 | 1.0141 | 0 | 0 | 0 |  |  | 0 | 0
6 | Replacement of Impact crusher by hammer mill crusher (installed qty.2 No) | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Replacement of wobbler feeder 1&2 by grizzly screen at CHP-D | 0 | - | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Installation of conveyor system from rope way of CHP-A and crusher house of CHP-D | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| PLC based control & instrumentation of 6.6 KV HT motors of 1250 KW of Crusher I & II and 200 KW of BC 108A1 & A2 at CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0.93628 | 0.93628 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Design, Supply, Erection & Commissioning of Complete Electrical Automation for Short Conveyor from stack yard of CHP-D to Belt Conveyor 107 A/B of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0.70095 | 0.70095 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Design, Supply, Erection & Commissioning of Complete Electrical Automation for Short Conveyor from stack yard of CHP-B to Belt Conveyor 104 A/B of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 2.2368 | 2.2368 | 0 | 0 | 0 |  |  | 0 | 0
| WORK OF DESIGN, ENGINEERING, MANUFACTURING, SUPPLY, ERECTION &COMMISSIONING OF SHORT CONVEYOR BELT FROM STACK YARD OF CHP UNIT-8&9 TO CONVEYOR BELT 107A AND B AT CHP UNIT 8&9, CSTPS, CHANDRAPUR. | 0 | - | 0 | 4.6948 | 4.6948 | -2.4e-08 | 0 | 0 |  |  | 0 | -2.4e-08
| Design, Supply, Installation and Commissioning of High Performance Energy Chain System for Side Arm Charger and Stacker Reclaimer of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 3.8916 | 3.8916 | 0 | 0 | 0 |  |  | 0 | 0
| RBF 103 &104,105 & 106, 107 & 108, and 109 & 110 in to modular Y chute | 0 | - | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-103 & RBF-104 with Design, development, Manufacturing, Supply & erection of modular Chute as per site condition in place of RBF using sintered silicon Carbide plate with motorized Flap Gate at CHP-D, CSTPS. | 0 | - | 0 | 1.1741 | 1.1741 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-105 & RBF-106 with Design, development, Manufacturing, Supply & erection of modular Chute as per site condition in place of RBF using sintered silicon Carbide plate with motorized Flap Gate at CHP-D, CSTPS. | 0 | - | 0 | 1.3169 | 1.3169 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-107 & RBF-108 with Design, development, Manufacturing, Supply & erection of modular Chute as per site condition in place of RBF using Tungsten Carbide plate with Flap Gate at CHP-D, CSTPS. | 0 | - | 0 | 1.1529 | 1.1529 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-109 & RBF-110 with design, erection & Installation by trajectory calculation & removal of existing RBF with Y Chute assembly by flow control with Flap Gate arrangement at TP-107 of CHP-D, CSTPS. | 0 | - | 0 | 1.1506 | 1.1506 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurment , Installation and commissioning of Online Insertable Camera systems for Unit-8, 500MW, CSTPS | 0 | - | 8.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, Supply, Installation & Commissioning of Energy efficient system for Illumination at Unit 8&9 CSTPS, Chandrapur. | 0 | - | 0 | 4.9494 | 4.9494 | 0 | 0 | 0 |  |  | 0 | 0
11 | Construction of Chemical godown shed for unit 8 & 9 at CSTPS,Chandrapur. | 0 | - | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of Chemical godown shed for unit 8 & 9 at CSTPS,Chandrapur. | 0 | - | 0 | 0.42946 | 0.42946 | 0 | 0 | 0 |  |  | 0 | 0
| Comprehencive work of installation, erection, testing and commissioning of MVWS spray system/ Fire safety system for new Bulk Chemical storage godown at CSTPS, Unit 8&9 | 0 | - | 0 | 0.27583 | 0.27583 | 0 | 0 | 0 |  |  | 0 | 0
| Work of electrification of godown for bulk chemical storage near FOPH building at Chandrapur project site. | 0 | - | 0 | 0.018322 | 0.018322 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of additional Chemical godown shed for storage of Lube oil at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Construction of RCC retaining wall for approach to RCC Bridge across Irai River, ADPL line at CSTPS | 0 | - | 8.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of RCC retaining wall for approach to RCC Bridge across Irai River, ADPL line at CSTPS | 0 | - | 0 | 4.3482 | 4.3482 | 0 | 0 | 0 |  |  | 0 | 0
| Asphalting of road from Reject coal gate to Motghat nallah at CSTPS Chandrapur (PHASE - II) | 0 | - | 0 | 0.87403 | 0.87403 | 0 | 0 | 0 |  |  | 0 | 0
| Providing extension to approaches of RCC bridge across Erai river by constructing WBM road at CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| UDL | 0 | - | 0 | 4.85 | 4.85 | 0 | 0 | 0 |  |  | 0 | 0
| B) DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (i) In Principally Approved By MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 1 | HMI (Human Machine Interface) Upgradation of ‘SSPA-T3000’ DCS (Distribution Control System), Rockwell make PLC System installed at 3x660MW Unit No. 8, 9 & 10 at Koradi TPS and HMI (Human Machine Interface) Upgradation of MaxDNA DCS System at Unit 8-9, CSTPS, Chandrapur | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 11.08 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 1.1 | Supply: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 10.52 | 10.52 | 21.02 | -10.5 | 0 | 0 |  |  | 0 | -10.5
HO DPR 1.2 | Works: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.41 | 0.41 | 0.81 | -0.4 | 0 | 0 |  |  | 0 | -0.4
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
40 | Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M with construction of concrete dam (Waste Weir & Non overflow structure), construction of drain wells, approach to drain wells and raising of ash compartment for ash bund along with renewal of Ash Disposal Pipe Line Service Road with WBM treatment at CSTPS, Chandrapur | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 4.9692 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 34.8665 | 34.8665 | 69.733 | -34.8665 | 0 | 0 |  |  | 0 | -34.8665
| Construction of New Drain Wells (12 Nos.) along with necessary connection to existing drain wells at CSTPS | 0 | - | 0.58493 | 0.58493 | 1.1699 | -0.58493 | 0 | 0 |  |  | 0 | -0.58493
| Construction of waste weir for raising of ash bund (Waste Weir & Non overflow structure) | 0 | - | 1.4621 | 1.4621 | 2.9241 | -1.4621 | 0 | 0 |  |  | 0 | -1.4621
| Raising of Ash Compartment i.e. Lagoon in Ash Bund | 0 | - | 8.7868 | 8.7868 | 17.5736 | -8.7868 | 0 | 0 |  |  | 0 | -8.7868
| IDC | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 7.634 | 7.634 | 15.2679 | -7.634 | 0 | 0 |  |  | 0 | -7.634
| IDC | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 4.9692 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
39 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 8-9) | MERC/CAPEX/2020-2021/WFH/SBR/21 | 2020-07-24 | 479.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
39.1 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 8-9) | MERC/CAPEX/2020-2021/WFH/SBR/21 | 2020-07-24 | 440.54 | 797.71 | 797.71 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/2020-2021/WFH/SBR/21 | 2020-07-24 | 38.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41 | CHP Performance Improvement Schemes at Unit 8-9 of CSTPS, Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 26.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.1 | Work of Design engineering , supply and installation of modular chutes with sintered silicon carbide for smooth flow &center feeding in CHP 2x500MW CSTPS | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 9.43 | 9.43 | 9.43 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.2 | Supply erection & commissioning of set of internal of impact crusher spares installed at CHPP-D, CSTPS | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 8.05 | 8.05 | 8.05 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.3 | Scheme for replacement of Scoop coupling/Fluid coupling of conveyor BC-101A/B/C, BC-102A/B, BC-104A/B, BC-105A/B ,BC-106A/B, BC-111A/B/C/D, BC-110A1/B1, BC-110A/B Installed at CHP-D, CSTPS Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 4.67 | 4.67 | 4.67 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.4 | Supply erection & commissioning of set of internal of spares of stacker reclaimer installed at CHP-D, CSTPS Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 1.96 | 1.96 | 1.96 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.5 | Supply erection & commissioning of set of internal of spares of Wagon tippler installed at CHP-D, CSTPS Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 2.12 | 2.12 | 2.12 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 0.38 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 2 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 2.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 27.12 | 27.12 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
A6 | Supply, Installation & Commissioning of Online Coal Flow Monitoring & Balancing System at Unit-8-9, CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0457 Dt 26.07.2024 | 2024-07-26 | 34.21 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, installation and commissioning of Online Coal flow monitoring and balancing system for U- 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2024-2025/MSPGCL/0457 Dt 26.07.2024 | 2024-07-26 | 34.21 | 34.21 | 34.21 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0457 Dt 26.07.2024 | 2024-07-26 | 0.31 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
A7 | Providing, supplying, laying and commissioning of 1600 mm dia. M.S. Pipe by replacement of existing PSC raw water line from Erai dam to reservoir at CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 40.7945 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing, supplying, laying and commissioning of 1600mm dia. M.S. pipe by replacement of existing PSC raw water line from Erai dam to reservoir at CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 40.7945 | 40.7945 | 40.7945 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 8.83 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
A8 | Adoption of Ozonization technique for disinfection of Cooling Water System at U # 8 & 9 | MERC/CAPEX/MSPGCL/2023-2024/0467 Dt 02.08.2024 | 2024-08-02 | 67 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Adoption of Ozonization technique for disinfection of Unit 8&9 Cooling Water at CSTPS. | MERC/CAPEX/MSPGCL/2023-2024/0467 Dt 02.08.2024 | 2024-08-02 | 67 | 67 | 67 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-2024/0467 Dt 02.08.2024 | 2024-08-02 | 2.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (ii) Submitted to MERC |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y1 | Multiple Schemes for Electrical Maintenance Section and Design, Engineering, Manufacturing, Testing, Unloading at site, E&C of 200MVA, 21/420KV Single Phase Generator Transformer for Unit # 8 & 9, CSTPS | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 10MW, 11kV Motor and its recommended spare for Boiler Feed Pump (BFP) | To be resubmitted | - | 0 | 4.95 | 4.95 | 0 | 0 | 0 |  |  | 0 | 0
| Replacement of NiCd battery sets installed for UPS of Fire Water Pump House, CMRH & SWAS lab of Unit 8 & 9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0.86 | 0.86 | 0 | 0 | 0 |  |  | 0 | 0
| Retrofitting of GE make LT Air Circuit Breakers of various current ratings and procurement of their recommended spares for Unit-8&9, CSTPS | To be resubmitted | - | 0 | 4.85 | 4.85 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of BHEL make 6.6kV and 11kV Vacuum Circuit Breakers for Unit-8&9, CSTPS Chandrapur | To be resubmitted | - | 0 | 2.07 | 2.07 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y5 | Scheme-1: Procurement of assembly of baskets for Air Preheater of type 31.05 VIMT 2000 (72° PA), Scheme-2: Procurement of spares for PRDS station pressure control valves and Desuperheating spray Control valves in Boiler at U-8&9, CSTPS, Chandrapur, Scheme-3: Procurement of complete set of sky climber at U-8&9, CSTPS, Chandrapur. Scheme-4: Supply, erction, commissioning of oil free rotary screw compressors (including all Civil Electrical, C&I, Testing work) for CMRH system at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-1: Procurement of assembly of baskets for Air Preheater of type 31.5 VIMT 2000 (72° PA) at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 15.78 | 15.78 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-2: Procurement of spares for PRDS station pressure control valves and Desuperheating spray control valves in Boiler at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 6.09 | 6.09 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-3: Procurement of complete set of sky climber at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 3.16 | 3.16 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-4: Supply, erection, commissioning of oil free rotary screw compressors (including all Civil Electrical, C&I, Testing work) for CMRH system at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 8.3 | 8.3 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y6 &Y7 | Supply, Erection & commissioning/retrofitting of HT Circuit Breaker with SF6 Contactor at AHP at Unit-8&9 & CHP#D and Supply, Installation and Commissioning of MV VFD panel along with integrated online cell redundancy technology with VFD bypass feature arrangement for conveyors 103 A & B of CHP-B, C.S.T.P.S., Chandrapur & Design, engineering, manufacturing, testing, unloading at site, E&C of Two No of 200 MVA, 21/420 KV Single Phase Generator Transformers for Unit-8&9, CSTPS, Chandrapur. Through OEM | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme 1: Retrofitting of BHEL make HT Circuit Breaker with SF6 contactor at AHP, Unit#8&9, CSTPS. | To be resubmitted | - | 0 | 38.33 | 38.33 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme 2: Retrofitting of BHEL make HT Circuit Breaker with SF6 contactor at CHP#D, Unit#8&9, CSTPS. | To be resubmitted | - | 0 | 5.64 | 5.64 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme 3: Supply, Installation and Commissioning of MV VFD panel along with integrated online cell redundancy technology with VFD bypass feature arrangement for conveyors 103 A & B of CHP-B. | To be resubmitted | - | 0 | 4.03 | 4.03 | 0 | 0 | 0 |  |  | 0 | 0
| Design, engineering, manufacturing, testing, unloading at site, E&C of Two No of 200 MVA, 21/420 KV Single Phase Generator Transformers for Unit-8&9, CSTPS, Chandrapur. Through OEM | To be resubmitted | - | 0 | 21.07 | 21.07 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (iii) Yet to be Submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Boiler Maintenance -III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of Air & Flue gas ducts of Boiler , Blade set and HAD for PA and FD Fan , SCAPH Coil, ID Fan spares at Unit-8&9 CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-1 Procurement of Air & flue gas expansion joints | 0 | - | 0 | 40 | 40 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-2 :Procurement of Blade Set and 2 sets of HAD of PA Fan. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme -3 Procurement of Blade Set and 2 sets of HAD of FD Fan. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-4 Procurement of SCAPH Coil for unit- 8&9 | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-5 :Procurement of ID Fan Impeller , Shaft and Blade set at unit-8 & 9, CSTPS | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme 6: Procurment of Coal Fuel pipes for unit -8 &9 , CSTPS | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of LTSH and economiser for unit-8&9 CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of LTSH Coil assemsblies unit- 8&9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of economiser coil asemblies | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of existing belt type gravimetric coal feeders to gravimetric rotary weigh coal feeders of unit- 8&9, at CSTPS, Chandrapur | 0 | - | 0 | 10.03 | 10.03 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of Quick Erect Aluminum Boiler Scaffolding system or unit- 8 & 9, (2X500MW), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of Quick Erect Aluminum Boiler Scaffolding system or unit- 8 & 9, (2X500MW), CSTPS, Chandrapur. | 0 | - | 0 | 35 | 35 | 0 | 0 | 0 |  |  | 0 | 0
| Turbine Maintenance -III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Schemes for Improvement in availability & performance of TG auxiliaries at U-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 1. Procurement of BFP Booster Pump assembly for Unit-8 & 9, CSTPS Chandrapur | 0 | - | 0 | 3.2 | 3.2 | 0 | 0 | 0 |  |  | 0 | 0
| 2. Procurement of Boiler Feed Pump catridge with CI sealing for Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 5.2 | 5.2 | 0 | 0 | 0 |  |  | 0 | 0
| 3. Procurement of Modulating type Boiler Feed Pump Recirculation valve (06 Nos) assembly for Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
| 4. Procurement of HP Heater HPH-5B assembly for Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
| 5. Procurement of MDBFP working oil & lube oil coolers for Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
| 6. Procurement of TDBFP Turbine rotor K1401-2 at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 7.5 | 7.5 | 0 | 0 | 0 |  |  | 0 | 0
| 7. Procurement of Main TG Jacking oil pumps (2 Nos.) at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
| 8. Procurement of HP elements of ZR500 Atlas Copco make compressors along with inter & after coolers tube nest at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
| 9. Procurement of CW & ACW Pump spares at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
| 10. Procurement of condenser tubes at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
| 11. Procurement of HPCF Pump at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
2 | DPR for performance improvement of Condenser Cooling water system & improvement in system reliability of auxiliary cooling water system installed at Unit-8&9, 2x500MW, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| DPR for performance improvement of Condenser Cooling water system & improvement in system reliability of auxiliary cooling water system installed at Unit-8&9, 2x500MW, CSTPS, Chandrapur | 0 | - | 0 | 34 | 34 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of main turbine IPT module at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of main turbine IPT module at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Electrical Maintenance -III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Proc of GTR, MDBFP, UPS battery, breakers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, engineering, manufacturing, testing, unloading at site, E&C of 200 MVA, 21/420 KV Single Phase Generator Transformer for Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 21.07 | 21.07 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of MDBFP motor and recommended spares The Fire Water Pump House UPS Battery set of 240V, 40AH Capacity (1.2V X 176 Cells ) Ni Cd Type Make- HBL The UPS Battery Set at SWAS Lab (Outdoor Area), 45AH Capacity (1.2 V X 276 Cells) Ni Cd type Make- HBL for Unit#8&9 The UPS Battery Set at CMRH (Outdoor Area), 69AH Capacity (1.2 V X 280 Cells) Ni Cd type Make- HBL for Unit#8&9 Retrofitting of 415V GE make ACB of various ratings along with allied spares. BHEL make Breakers and spares for 6.6 kV and 11kV panels | 0 | - | 0 | 15.07 | 15.07 | 0 | 0 | 0 |  |  | 0 | 0
2 | Design, engineering, manufacturing, testing, unloading at site, E&C of 80 MVA, 420/11/6.9 KV three Phase Station Transformer & 25MVA 21/6.9KV Three phase Unit Aux Transformer as a common pool spares for BTPS 500MW, Khaparkheda 500 MW and Unit-8&9, CSTPS, Chandrapur & Supply, installation, commissioning and testing of Station Batteries of Unit-8&9 CSTPS alongwith all outdoor batteries | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, engineering, manufacturing, testing, unloading at site, E&C of 80 MVA, 420/11/6.9 KV three Phase Station Transformer & 25MVA 21/6.9KV Three phase Unit Aux Transformer as a common pool spares for BTPS 500MW, Khaparkheda 500 MW and Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 22 | 22 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, installation, commissioning and testing of Station Batteries of Unit-8&9 CSTPS alongwith all outdoor batteries | 0 | - | 0 | 12 | 12 | 0 | 0 | 0 |  |  | 0 | 0
| I&C -III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Upgradation of Analysis & Diagnostics system (A&D) for VMS and TSI system at Unit-8&9, CSTPS, Chandrapur.& other schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of Analysis & Diagnostics system (A&D) for VMS and TSI system at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 17 | 17 | 0 | 0 | 0 |  |  | 0 | 0
| Installation of CO analysers at Eco outlet at Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
| Complete Engineering Retrofitting of Existing 196 NT Controller by DT 9 Controller alongwith HMI units for Unit 8/9 coal feeder system. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of spares for LP bypass system. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of spares for maxDNA DCS system | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
2 | Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-9, CSTPS, Chandrapur. | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
3 | Upgradation of HMI and hardware of GE make PLCs installed at Unit-8&9, CSTPS, Chandrapur. & other schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of HMI and hardware of GE make PLCs installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of TD-BFP Turbovisory system installed at Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of EWLI system installed at Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of O2 analysers installed at Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
| Installation of High temperature Camera system at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of HEA igniter system at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of Flue Gas Analysers and Opacity Analysers at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
4 | Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-8, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-8, CSTPS, Chandrapur. | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
5 | Multiple schemes C&I-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Total Mercury (Gaseous) Analyzers along with their online data connectivity & Remote calibration U-3 to 9 | 0 | - | 0 | 9 | 9 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Controllers & Com Boxes for Air Compressors of Unit-8&9. | 0 | - | 0 | 5.5 | 5.5 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of Steam and Water Analysis System (SWAS) for Unit – 8 & 9 | 0 | - | 0 | 13 | 13 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of Servo valve (ST) with proportional valves (PV) for HP bypass system at Unit – 8 & 9 | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of GEHO pump VFD panels for Unit – 8 & 9 | 0 | - | 0 | 9 | 9 | 0 | 0 | 0 |  |  | 0 | 0
6 | Upgradation of measurement and control system installed at CSTPS Unit 8&9 & Upgradation of Numerical Protection Relay of Alstom / Schnieder make installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of measurement and control system installed at CSTPS Unit 8&9 | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of Numerical Protection Relay of Alstom / Schnieder make installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
| AHP-III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | supply of piston cylinder assembly, diaphragm assembly, Suction and discharge valve housing assembly of GEHO pump (Model- TZPM 1200). & other schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-1 :supply of piston cylinder assembly, diaphragm assembly, Suction and discharge valve housing assembly of GEHO pump (Model- TZPM 1200). | 0 | - | 0 | 13 | 13 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme -2 :Procurement of sub assemblies for conveying air compressor model ZR 275 and instrument air compressor model ZR 110 in Ash handling plant Unit-8&9 (2x500MW) at CSTPS, Chandrapur. | 0 | - | 0 | 18 | 18 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme -3 Supply of 10/8 FAH Warman make slurry pump impeller element assembly, Bearing assembly unit, jacket assembly. | 0 | - | 0 | 12 | 12 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply and replacement of 400 NB MSERW pipeline of ash disposal system of unit 8&9 at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 :Supply and replacement of 400 NB MSERW pipeline of ash disposal system of unit 8&9 at CSTPS, Chandrapur. | 0 | - | 0 | 70 | 70 | 0 | 0 | 0 |  |  | 0 | 0
3 | Complete ESP Refurbishment of 1st & 2 nd Row Field of Unit 8&9 at CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 : Complete ESP Refurbishment of 1st & 2 nd Row Field of Unit 8&9 at CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 12.5 | 12.5 |  |  | 12.5 | 0
0 | CHP - D | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Upgradation Of Hydraulic Systems with Safety Mechanism for wagon unloading system at CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply erection & commissioning of wagon tippler, Side Arm Charger, apron feeder and stacker hydraulic drive system with online NAS value monitoring systems. | 0 | - | 0 | 24 | 24 | 0 | 0 | 0 |  |  | 0 | 0
0 | Wagon stopping mechanism (Safety) | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgardation and Capacity Enhancement of Side Arm Charger Apron Feeder and Bunker Conveyors at CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | capacity enhancement to 60 wagons pulling capacity and associated modification of existing side arm charger | 0 | - | 0 | 20 | 20 | 0 | 10 | 10 |  |  | 10 | 0
0 | Capacity enhancement , Commissionng of apron feeder drive | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
0 | Modification and revamping of Apron Feeder 101,102,103 | 0 | - | 0 | 13.5 | 13.5 | 0 | 3 | 3 |  |  | 3 | 0
0 | Supply,Installation and Commissioning of double drive Mechanism with Split Case Bearings for Tripper Trolley and bunkering conevyor belts of CHP-D, CSTPS | 0 | - | 0 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
0 | Modification of Fixed Tripper Head Pulley(Z-Point) of BC110A&B at CHP-D CSTPS. | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
0 | Modification, Errection & Commissioning of drive unit capacity enhancement for conveyor at CHP-D, Chandrapur TPS. | 0 | - | 0 | 6 | 6 | 0 | 3 | 3 |  |  | 3 | 0
3 | Performance Improvement Schemes of CHP-D CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design engineering , supply and installation of modular chutes with weld cast Liners ,flap gates and actuators. | 0 | - | 0 | 50 | 50 | 0 | 20 | 20 |  |  | 20 | 0
0 | Supply erection & commissioning of set of internal of spares of Wagon tippler and Side Arm Charger installed at CHP-D, CSTPS Chandrapur | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply erection & commissioning of set of internal of spares of stacker reclaimer installed at CHP-D, CSTPS Chandrapur | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply erection & commissioning of set of internal of spares of Impact crusher installed at CHP-D, CSTPS Chandrapur | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply erection & commissioning of set of internal of spares of wobbler feeder installed at CHP-D, CSTPS Chandrapur | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply erection & commissioning of 1500 TPH capacity Stacker Recliamer sleeving bearing with fastener of CHP-D (U8&9), CSTPS, Chandrapur | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of Gearbox assemblies at CHP-D CSTPS. | 0 | - | 0 | 7 | 7 | 0 | 7 | 7 |  |  | 7 | 0
0 | Structure Strengthening,Modification works of Conveyors at CHP-D CSTPS | 0 | - | 0 | 3 | 3 | 0 | 3 | 3 |  |  | 3 | 0
4 | Design, Installation, testing and commissioning of new conveyor systems of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Installation, testing and commissioning of conveyor system from crusher house to TP-108 of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 50 | 50 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Engineering, erection and commissioning of one 1500TPH crusher, short conveyors from TP 106 and open space of near Stack yard A pile to Crusher inlet and a telescopic conveyor at the output of crusher to Stack Yard B pile of CHPD Unit 8&9, CSTPS. | 0 | - | 0 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design, Installation and commissioning of conveyor system from rope way of CHP-A to crusher house of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Installation and commissioning of conveyor system from rope way of CHP-A to crusher house of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 50 | 50 | 0 | 0 | 0 |  |  | 0 | 0
6 | Infrastructure Development Schemes at CHP-D CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Supply,Installation and Commissioning of EOT Cranes at Wagon Tippler area of CHP-D CSTPS. | 0 | - | 0 | 15 | 15 | 0 | 7 | 7 |  |  | 7 | 0
0 | Belt Tracking systems for Carrying/Return 1400/1600 mm belt width | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Ceramic Lagging by direct bonding on Conveyor Pulleys without Rubber Pad/Rubber Sheets. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Rewamping of crane and hoist of CHP, Unit 8&9, CSTPS, Chandrapur | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Material lifting mechanism at Crusher, bunker and Tunnel area of CHP-D CSTPS. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping, modification of TunnelAir ventilation system | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping, modification of DE and DS system | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping, modification of Dewatering and water recirculation system | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of New Office Building with Infrastructure ,Interior Development at CHP-D CSTPS. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Material Storage Shed Fabrication work at CHP-D CSTPS | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
7 | Electrical schemes for improvement in availability & Reliability of CHP-D,CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design supply installation and commisioning of LED based energy efficient system for illumination at CHPD | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Erection, Commissioning and Testing of 7.2KV SF6 HT Contactor for retrofitting of existing BHEL make Vacuum Circuit Breakers of CHP-D, CSTPS | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of GE make 90-30 series PLC system installed at stacker rclaimer and wagon tippler at CHP-D, CSTPS | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Installation of energy efficient air temperature controlling system at various MCC rooms of CHPD, CSTPS | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Alterration, upgradation of tunnel ventilation system of CHPD, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Fabrication, Erection & commissioning of cable support structure along with re-routing & trial of auxiliaries at Crusher PMCC, compressor house & short conveyor area at CHP-D, CSTPS | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and installation of LT air circuit breakes at CHP-D, CSTPS | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, supply, installation & commissioning of solar based energy efficient illumination system at CHP-D, CSTPS | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of HT motors for various auxiliaries at CHP-D, CSTPS. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & installation of high capacity submersible slurry pump at CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 7 | 7 |  |  | 7 | 0
0 | Reconditioning of MCC Board feeder panels at CHP-D,U #8&9.CSTPS,Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
0 | Supply & installation of anoodized winding magnets along with control panels for installation at various conveyor belts of CHP-D, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 4 | 4 |  |  | 4 | 0
0 | Supply of 69 AH HBL make battery set of CHP-D (U8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
0 | Supply of 100 AH Exide make battery banks (2 Set/ 110 Nos battery cells) & battery charge at CHP-D (U8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
0 | Alterration, upgradation of tunnel ventilation system of CHPD, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of HT/LT Xmers assy of CHP-D (U8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of HT/LT Xmers assy of CHP-D (U8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | WTP-III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Engineering, installation and commissioning of DM stream capacity of 4800M3/Day for U # 8 & 9 in addition to existing DM stream at WTP, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Engineering, installation and commissioning of DM stream capacity of 4800M3/Day for U # 8 & 9 in addition to existing DM stream at WTP, CSTPS, Chandrapur | 0 | - | 0 | 46.4 | 46.4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Civil - 8&9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work of diversion of peripheral nallah towards ash water recovery pump house alogwith construction of waste wear at ash bund area CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Work of diversion of peripheral nallah towards ash water recovery pump house alogwith construction of waste wear at ash bund area CSTPS, Chandrapur. | 0 | - | 0 | 35.4 | 35.4 | 0 | 0 | 0 |  |  | 0 | 0
2 | Infrastructure development of CHP-D area at U-8, 9, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of platform for unloading of coal near TP-106 upto stack pile A of CHP-D | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of WBM Road for fire fighting arrangement at CHP-D U-8,9 | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction & Pushing RCC box of size 2mx2m under railway track to drain out the surface water near Rly - A cabin Unit-8,9 | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of concrete pavement road connecting to reject gate & vinchoda chowk , Y point to ash recovery pump house | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
HO1 | CHP Improvement Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at CHP-D | 0 | - | 0 | 100 | 100 | 0 | 0 | 0 |  |  | 0 | 0
HO2 | Developlment & Upgradation of DSM software system for MSPGCL | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Developlment & Upgradation of DSM software system for MSPGCL | 0 | - | 0 | 55 | 55 | 0 | 0 | 0 |  |  | 0 | 0
1 | Implementation of Flexible Operation Solutions | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Flexible Operation Solutions | 0 | - | 0 | 34 | 34 | 0 | 0 | 0 |  |  | 0 | 0
0 |  | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | General asset | 0 | - | 0 | 3.2096 | 3.2096 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply, Operation & Maintenance of Mobile Coal Sampling Equipment (MCSE) for coal sampling at loading ends of WCL for Mahagenco | 0 | - | 0 | 3.1648 | 3.1648 | 0 | 0 | 0 |  |  | 0 | 0
3 | ABC Powder Type and Foam Type Composite Fire Extinguisher | 0 | - | 0 | 1.528 | 1.528 | 0 | 0 | 0 |  |  | 0 | 0
4 | NON-Detailed Project Report for the Work of Upgradation/Renovation of Crusher House of CHPB of Unit-5, 6&7 at CSTPS Chandrapur (benefit U-8,9 by short conveyor coal stacking in catering emergency) | 0 | - | 0 | 2.8807 | 2.8807 | 0 | 0 | 0 |  |  | 0 | 0
5 | Extention of stacker reclaimer area for improvement in coal stack management at CHP-D CSTPS Chandrapur U-8,9 | 0 | - | 0 | 8.46 | 8.46 | 0 | 0 | 0 |  |  | 0 | 0
6 | Retrofitting of BHEL make HT Circuit Breaker with SF6 Contactor at CHP-D, Unit-8&9 | 0 | - | 0 | 4.25 | 4.25 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 3016.873 | 3068.8434 | -51.9704 | 107 | 107 | 0 | 0 | 107 | -51.9704
FY 2029-30
A) Approved Add Cap (Case No. 296 of 2019)
1 | Initial Spares | Approved Add Cap (Case No. 296 of 2019)
| Boiler & Auxiliaries | 0 | - | 10.36 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Bevel Helical Gear box KMP-350 for XRP 1043 coal mills at unit-8&9,CSTPS, Chandrapur. | 0 | - | 0 | 7.4087 | 7.4087 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Hydraulic Adjustment (Actuating) Device for PA fan model PAF 19/10.6-2 and FD fan FAF 23/12.5-1 at Unit 8&9, CSTPS, Chandrapur. | 0 | - | 0 | 1.3971 | 1.3971 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Yokogawa make Zirconia Oxygen Analyser spares for C&I-III, Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 0.51933 | 0.51933 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of High pressure valves installed at unit-8&9 ( 2x500 MW),CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Turbine & Aux | 0 | - | 1.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of IMI Norgren Herion make Trip solenoid valves for Main Turbine, MD-BFP & TD-BFP of Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.37354 | 0.37354 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Speed Sensors for 500 MW KWU Turbine for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.038232 | 0.038232 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Position Feedback Transmitters for Starting Device and Speeder Gear of Main Turbine for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.11225 | 0.11225 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for LP bypass system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur on OEM Basis. | 0 | - | 0 | 0.43645 | 0.43645 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of TSE (Turbine Stress Evaluator) temperature elements for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.2073 | 0.20719 | 0.00010699 | 0 | 0 |  |  | 0 | 0.00010699
| Generator and Auxiliries | 0 | - | 0.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of complete set of water cooled bushing for 500MW Generator installed at Unit-8 & 9, CSTPS Chandrapur. | 0 | - | 0 | 0.26409 | 0.26409 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Tushaco make complete AC Jacking Oil Pump for Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.19949 | 0.19949 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of oil filled Neutral Grounding Transformer for AHP Unit-8&9 CSTPS , Chandrapur. | 0 | - | 0 | 0.34775 | 0.34775 | 0 | 0 | 0 |  |  | 0 | 0
| Electrical and Instrumentation | 0 | - | 29.23 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| ‘Procurement of various spares of BHEL make Vacuum Circuit Breakers’ , for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.49498 | 0.49498 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, erection and commissioning of floor mounted 500KW Resistor Load Bank for D.G. sets installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.27536 | 0.27536 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Turbosupervisory system spares of main turbine for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 1.0366 | 1.0366 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Level transmitters for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.15999 | 0.15999 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Level transmitters for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.032605 | 0.032605 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Level transmitters for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.046973 | 0.046973 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of GE PLC spares for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.57304 | 0.57304 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for GEHO pumps PLC control panels for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.084378 | 0.084378 | 2.6e-08 | 0 | 0 |  |  | 0 | 2.6e-08
| Procurement of master calibration lab Instruments for C&I-III, Unit 8 & 9,CSTPS,Chandrapur | 0 | - | 0 | 0.30131 | 0.30131 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Coal Feeder panel spares for C&I-III, Unit 8 & 9,CSTPS, Chandrapur | 0 | - | 0 | 0.58701 | 0.58701 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Opacity Monitor (Stack Particulate matter-SPM) spares for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.14051 | 0.14051 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Forbes Marshall Supervisory system spares For Turbine driven boiler feed pumps (TDBFP) of Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.22449 | 0.22449 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for hydraulic panel of CW pumps for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.13862 | 0.1386 | 1.7196e-05 | 0 | 0 |  |  | 0 | 1.7196e-05
| Procurement of H2 Dew point analyzer spares for Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.049938 | 0.049938 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for HP bypass system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.33965 | 0.33965 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Position feedback transmitter for HP bypass system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.0354 | 0.0354 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Atlas Copco make Instrument, Service and Conveying air Compressors for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.22509 | 0.22509 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for HEA Ignitors and Flame Scanners for C&I-III, Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.037701 | 0.037701 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for GEHO pumps of Ash Handling System at C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.28861 | 0.28861 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Turbine side control valve spares for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.17974 | 0.17974 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various numerical protection relays for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.12307 | 0.12307 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various numerical protection relays for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.13184 | 0.13184 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various numerical protection relays for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.13863 | 0.13863 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for DB POWER make UPS system installed at HCSD Pump House, Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.064757 | 0.064757 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Fully Automatic Capacitance & Dissipation Factor (Tan- Delta) measuring kit for Unit-8 &9, CSTPS, Chandrapur. | 0 | - | 0 | 0.48288 | 0.48288 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of various VFD spares for ID fans of Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.546 | 0.546 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of DAVR spares installed at Unit -8&9 CSTPS, Chandrapur. | 0 | - | 0 | 0.5945 | 0.5945 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 3 phase relay test kit for Unit-8 &9, CSTPS, Chandrapur. | 0 | - | 0 | 0.35388 | 0.35388 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Fast Bus Transfer System (FBTS) installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.37288 | 0.37288 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various spares for battery chargers installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.40022 | 0.40022 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Auto synchronizing Relay (ASR) & Load Shedding Relay (LSR) installed at Unit-8 &9, CSTPS, Chandrapur. | 0 | - | 0 | 0.34973 | 0.34973 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ESP spares i.e. Field Controller, Thyristor and Trigger card for ESP of Unit-8 & 9, CSTPS Chandrapur. | 0 | - | 0 | 0.26745 | 0.26745 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various VFD spares for GEHO pump of Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.54416 | 0.54416 | 0 | 0 | 0 |  |  | 0 | 0
| Design, Supply, Erection & Commissioning of On-Line Dissolved Gas Analyzers for various Transformers installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 3.1775 | 3.1775 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, Erection & Commissioning of On-Line Dissolved Gas Analyzers for Station Transformers -8B, Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.30519 | 0.30519 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘TOROSHIMA’ make 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motor (without pump casing) for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 4.2037 | 4.2037 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 90kVA ESP Rectiformer for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.29878 | 0.29878 | 0 | 0 | 0 |  |  | 0 | 0
| Supply erection & commissioning of Aviation Lighting for NDCT of Unit-8&9, CSTPS Chandrapur | 0 | - | 0 | 0.57261 | 0.57261 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Transformer oil storage tanks of different capacity for Unit-8&9 CSTPS Chandrapur. | 0 | - | 0 | 0.57024 | 0.57024 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 2000kW & 315kW, 6.6 kV HT motors for CW & ACW Pump installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 1.4505 | 1.4505 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 3.25MVA, 6.6/2.3kV VFD Transformers of vector group DY11 for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.3941 | 0.3941 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 3.25MVA, 6.6/2.3kV VFD Transformer of vector group ‘Dd0’ for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.3905 | 0.3905 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘MARATHON’ makes HT/LT Induction motors for various Critical auxiliaries installed at Unit-8 &9, CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of 1.2V, Ni-Cd battery cells for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.12496 | 0.12496 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of 1.2V, Ni-Cd battery cells for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.18931 | 0.18931 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘Air Core DC Reactor’ for VFD and ‘NGR’ for UAT/ Station Transformers installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.44368 | 0.44368 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘Air Core DC Reactor’ for VFD and ‘NGR’ for UAT/ Station Transformers installed at Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.12551 | 0.12551 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘BHEL’ make 680 KW, 6.6KV, Coal Mill Motor for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.37913 | 0.37913 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 400kV OIP Condenser Bushing for Generator Transformer & Station Transformer of Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.49064 | 0.49064 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of ‘11kW DC motor with Control Cabinet’ for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.2242 | 0.2242 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 37kW, 415V motors for Primary Water Pump installed at Unit-8 &9, CSTPS Chandrapur. | 0 | - | 0 | 0.0096851 | 0.0096851 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 15 KW, 415V LT Motor for Service Building & TG Building Lift installed at Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.095155 | 0.095155 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 16KW, 415V LT Motor for Boiler Lift installed at Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 0.044179 | 0.044179 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, Erection, Testing and Commissioning of Hydrastep-Electronic Drum Level Indicator and its associated accessories for Unit-9, CSTPS, Chandrapur | 0 | - | 0 | 0.27376 | 0.27376 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for BHEL make Hydrastep (Electronic Water Level Indicator -BHELVISION 20M) for Unit 8 & 9, CSTPS, Chandrapur on OEM basis. | 0 | - | 0 | 0.084172 | 0.084172 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Electrodes for Hydrastep (Electronic Water Level Indicator -BHELVISION 20M) for Unit 8 & 9, CSTPS, Chandrapur. | 0 | - | 0 | 0.10384 | 0.10384 | 0 | 0 | 0 |  |  | 0 | 0
| Engineering & Retrofitting of 196 NT Controller to DT 9 Controller for Unit-8 & 9 Coal Feeder System. | 0 | - | 0 | 0.38076 | 0.38076 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for BHEL make Acoustic steam leak detection system (BHELSONIC) (BS10) for Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 0.077807 | 0.077807 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of LT Circuit Breaker assemblies for ESP LT Panels (LTMSB & ACP) of Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.25429 | 0.25429 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for BHEL make maxDNA Distributed control system for C&I-III, Unit 8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 1.117 | 1.117 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of Transformer oil BDV test kit DTA 100C and Oil Tan Delta & Resistivity Tester DTL C at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.47598 | 0.47598 | 0 | 0 | 0 |  |  | 0 | 0
| Outdoor Plant ( CHP/AHP/WTP) | 0 | - | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Elecon make KCN-560 type Gearbox for Apron Feeder installed at CHPD, CSTPS. | 0 | - | 0 | 1.6717 | 1.6717 | -6e-08 | 0 | 0 |  |  | 0 | -6e-08
| Procurement of spares of CKB-280,225,200,8180 typ gearbox installed at CHP-D | 0 | - | 0 | 1.0015 | 1.0015 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Gear Box (MAKE: NEW ALLENBERRY) Spares at CHP-D; CSTPS, Chandrapur. | 0 | - | 0 | 0.5177 | 0.5177 | 1.8e-08 | 0 | 0 |  |  | 0 | 1.8e-08
| Procurement of spares for m/s Elecon make Impact Crusher installed at CHP Unit 8&9 CSTPS, Chandrapur | 0 | - | 0 | 0.84103 | 0.84103 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of V belt pulley of rotor for Impact crusher installed at CHP-D, CSTPS | 0 | - | 0 | 0.11864 | 0.11864 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Spares for hydraulic systems installed at CHPD, CSTPS. | 0 | - | 0 | 0.47537 | 0.47537 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Spares for hydraulic systems installed at CHPD, CSTPS. | 0 | - | 0 | 0.028604 | 0.028604 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of drive & non drive pulley for various conveyors installed at CHP D, CSTPS, Chandrapur. | 0 | - | 0 | 0.25792 | 0.25792 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of drive & non drive pulley for various conveyors installed at CHP D, CSTPS, Chandrapur. | 0 | - | 0 | 0.0914 | 0.0914 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Chain links for apron feeder installed at CHP D, CSTPS, Chandrapur. | 0 | - | 0 | 0.40289 | 0.40289 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of internal spares for Elecon make PWD-18, PLB-25 & SCN-180 type Gearbox for Stacker Reclaimer & wobbler feeder installed at CHP D, CSTPS. | 0 | - | 0 | 0.52774 | 0.52774 | 3.1e-08 | 0 | 0 |  |  | 0 | 3.1e-08
| Supply of GE Make Switchgear Spares for GE Make LT Feeders | 0 | - | 0 | 0.12485 | 0.12485 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for Fluidomat make scoop coupling installed at CHP–D, CSTPS, Chandrapur | 0 | - | 0 | 0.48355 | 0.48355 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Oil Filtering machine for hydraulic power packs installed at CHPD, CSTPS | 0 | - | 0 | 0.10592 | 0.10592 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of LT Motors at CHP-D (U#8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0.11302 | 0.11302 | 0 | 0 | 0 |  |  | 0 | 0
| Supply and Installation of Oil Cooled Suspended Anodized Winding Magnet & Control Panel at CHP, Unit 8&9, CSTPS, Chandrapur. | 0 | - | 0 | 2.2967 | 2.2967 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of LT power and control cable for CHP-D | 0 | - | 0 | 0.26256 | 0.26256 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of LT power and control cable for CHP-D | 0 | - | 0 | 0.0477 | 0.0477 | 0 | 0 | 0 |  |  | 0 | 0
2 | Capital Spare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| HPT MODULE | 0 | - | 45.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of HP turbine Module along with breach nuts and pipe spool pieces (Type: H30-100-2) for Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 32.332 | 32.332 | 0 | 0 | 0 |  |  | 0 | 0
| LPT ROTOR | 0 | - | 40.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Fully Bladed & Dynamically Balanced LP Rotor (N30-2X10-2) for Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 29.03 | 29.03 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of set of Free Standing Moving Blades for LP Rotor (N30-2X10-2) for Unit-8 & 9, CSTPS, Chandrapur | 0 | - | 0 | 4.5629 | 4.5629 | 0 | 0 | 0 |  |  | 0 | 0
| BFP CARTRIDGE ( 2NOS ) | 0 | - | 4.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of cartridge assembly for Boiler Feed Pump model FK-4E-36 (with Four S/H & 2 R/H spray branches) installed at 2X 500MW, CSTPS, Chandrapur. | 0 | - | 0 | 2.515 | 2.5149 | 6e-05 | 0 | 0 |  |  | 0 | 6e-05
| BCW PUMP | 0 | - | 3.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for ‘TOROSHIMA’ make 350KW BCW Pump-Motor installed at Unit-8 &9, CSTPS Chandrapur. | 0 | - | 0 | 1.3283 | 1.3283 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of various spares for ‘TOROSHIMA’ make Boiler Circulating Water (BCW) pump-motor installed at Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 2.2326 | 2.2326 | 0 | 0 | 0 |  |  | 0 | 0
| 15 MVA DRY TYPE TRANSFORMER | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spare ‘Cast Resin Dry Type Transformers (CRTs)’ of different ratings for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 6.0213 | 6.0213 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of phase coil limb and spares of Cast Resin Dry Type Transformers of different ratings for Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 7.9255 | 7.9255 | 0 | 0 | 0 |  |  | 0 | 0
| BTG+BOP& Other Works | 0 | - | 20.48 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Design, Supply & Installation, Testing & Commissioning of Public Addressing System for tunnels of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 1.1544 | 1.1544 | 0 | 0 | 0 |  |  | 0 | 0
| Work of upgradation, installation and extension of 220VDC control supply to various PMCC of CHPD, CSTPS, Chandrapur. | 0 | - | 0 | 0.68441 | 0.68441 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Apron Feeder in CHP Unit 8&9 (2x500) MW at CHP-D, CSTPS. | 0 | - | 0 | 2.3388 | 2.3388 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of spares for up gradation of rotary parts of travelling conveyor system installed at CHPD, CSTPS, Chandrapur. | 0 | - | 0 | 0.58939 | 0.58939 | 0 | 0 | 0 |  |  | 0 | 0
| The Work of Design, Engineering, Manufacturing, Supply, Erection & Commissioning of Short Conveyor belt from stack yard of CHP of Unit 5,6&7 to Belt Conveyor 104 A/B at CHP of Unit 8&9, CSTPS, Chandrapur | 0 | - | 0 | 5.6825 | 5.6825 | 0 | 0 | 0 |  |  | 0 | 0
| Work of design, supply, erection, commissioning of overhead cable tray along with removal & re-routing of power and control cables at CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0.51324 | 0.51324 | 0 | 0 | 0 |  |  | 0 | 0
| Work of provision, modification, retrofitting and revamping of lighting system of transfers points, crusher house and bunker area of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 1.0105 | 1.0105 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of spares for M/s. Weir Minerals make (GEHO pump Model TZPM-1200) for Ash Handling Plant Unit# 8 &9 CSTPS Chandrapur. AHP-III | 0 | - | 0 | 2.106 | 2.106 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Gear Box set of internal (MAKE: NEW ALLENBERRY) Spares at CHP-D; CSTPS, Chandrapur. | 0 | - | 0 | 1.6904 | 1.6904 | 0 | 0 | 0 |  |  | 0 | 0
| Supply and Installation of Oil Cooled Suspended Anodized Winding Magnet & Control Panel at CHP, Unit 8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 196 NT Controller by DT 9 Controller alongwith HMI units for Unit- 8&9 coal feeder system | 0 | - | 0 | 2.0774 | 2.0774 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of set of CW Impeller duly fitted with wear rings & ACW Impeller duly fitted with wear rings of Mather & Platt make Pumps installed at Unit-8 & 9,CSTPS,Chandrapur | 0 | - | 0 | 0.70379 | 0.70379 | 0 | 0 | 0 |  |  | 0 | 0
| CHP System U#8 | 0 | - | 0 | 0.05 | 0.05 | 0 | 0 | 0 |  |  | 0 | 0
| ISOLATED PHASE BUS DUCT | 0 | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| SEGREGATED PHASE BUS DUCT U#8 | 0 | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| SEGREGATED PHASE BUS DUCT U#9 | 0 | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| ISOLATED PHASE BUS DUCT U#9 | 0 | - | 0 | 0.04 | 0.04 | 0 | 0 | 0 |  |  | 0 | 0
| DTT & UAT U#8 | 0 | - | 0 | 0.03 | 0.03 | 0 | 0 | 0 |  |  | 0 | 0
| DTT & UAT U#9 | 0 | - | 0 | 0.03 | 0.03 | 0 | 0 | 0 |  |  | 0 | 0
| Cranes and hoists U#8 | 0 | - | 0 | 0.03 | 0.03 | 0 | 0 | 0 |  |  | 0 | 0
| RCC Chimney U#8 | 0 | - | 0 | 9.29 | 9.29 | 0 | 0 | 0 |  |  | 0 | 0
| Coal Handling Plant | 0 | - | 0 | 41.79 | 41.79 | 0 | 0 | 0 |  |  | 0 | 0
| Bunker foundation & civil works (Unit 8) U#8 | 0 | - | 0 | 18.58 | 18.58 | 0 | 0 | 0 |  |  | 0 | 0
| Boiler & Auxiliaries U#9 | 0 | - | 0 | 9.2889 | 9.2872 | 0.0017338 | 0 | 0 |  |  | 0 | 0.0017338
| ESP U#9 | 0 | - | 0 | 2.1589 | 2.1589 | 0 | 0 | 0 |  |  | 0 | 0
| ID fan foundations (Unit 9) U#9 | 0 | - | 0 | 1.7489 | 1.7489 | 0 | 0 | 0 |  |  | 0 | 0
| DRY ASH SILO-12M DIA U#8 | 0 | - | 0 | 1.22 | 1.22 | 0 | 0 | 0 |  |  | 0 | 0
| FD fan foundations (Unit 9) U#9 | 0 | - | 0 | 0.62891 | 0.62891 | 0 | 0 | 0 |  |  | 0 | 0
| PA fan foundations (Unit 9) U#9 | 0 | - | 0 | 0.54891 | 0.54891 | 0 | 0 | 0 |  |  | 0 | 0
| Natural Draft cooling tower- Unit 8 U#8 | 0 | - | 0 | 0.32 | 0.32 | 0 | 0 | 0 |  |  | 0 | 0
| Main power house building-Civil Works-Unit no.-9 U | 0 | - | 0 | 0.15 | 0.15 | 0 | 0 | 0 |  |  | 0 | 0
| Structural Steel works for main power house buildi | 0 | - | 0 | 0.15 | 0.15 | 0 | 0 | 0 |  |  | 0 | 0
| Canteen U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Security and time office U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| CARS SCOOTERS AND CYCLE SHED U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Fire Station U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Watch towers U#8 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| First aid station | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Tranformer yard U#8 | 0 | - | 0 | 0.02 | 0.02 | 0 | 0 | 0 |  |  | 0 | 0
| Rain Water Harvesting Scheme U#8&9 | 0 | - | 0 | -0.01 | -0.01 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Advance Multipurpose Fire Tender | 0 | - | 0 | 3.45 | 3.45 | 0 | 0 | 0 |  |  | 0 | 0
| DM Stream | 0 | - | 29.65 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| DM Stream capacity of 100 M3/Hr in addition to existing stream of WTP. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| CIVIL | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Bridge | 0 | - | 4.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Railway, CHP, AHP etc | 0 | - | 152.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| B. G. railway siding Pway works | 0 | - | 0 | 41.5165 | 41.5165 | 0 | 0 | 0 |  |  | 0 | 0
| S & T work for B.G. railway siding | 0 | - | 0 | 0.023574 | 0.023574 | 0 | 0 | 0 |  |  | 0 | 0
| Consultancy services for B. G. railway siding | 0 | - | 0 | 0.035636 | 0.035636 | 0 | 0 | 0 |  |  | 0 | 0
| Ash infra in Railway | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Bunker structure (Unit 8) U#8 | 0 | - | 0 | 18.57 | 18.57 | 0 | 0 | 0 |  |  | 0 | 0
| Coal Mills | 0 | - | 0 | 1.1389 | 1.1389 | 0 | 0 | 0 |  |  | 0 | 0
| Bunker foundation & civil works (Unit 9) U#9 | 0 | - | 0 | 0.12 | 0.12 | 0 | 0 | 0 |  |  | 0 | 0
| Bunker structure (Unit 9) U#9 | 0 | - | 0 | 0.11 | 0.11 | 0 | 0 | 0 |  |  | 0 | 0
| HCSS silo-12m dia U#8 | 0 | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| Ash water PH, HCSD PH, Bottom ash slurry PH U#8 | 0 | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| Ash compressor house & Control room U#8 | 0 | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| MILL REJECT SILO U#8 | 0 | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
| Fire protection & Detection system U#8 | 0 | - | 0 | 0.71423 | 0.71423 | 0 | 0 | 0 |  |  | 0 | 0
| DM Water Pump room U#8 | 0 | - | 0 | 4.25 | 0 | 4.25 | 0 | 0 |  |  | 0 | 4.25
| Filter water reservoir & pump house U#8 | 0 | - | 0 | 4.29 | 0 | 4.29 | 0 | 0 |  |  | 0 | 4.29
| ACW + RW + Filtered water piping U#8 | 0 | - | 0 | 2.2409 | -0.0096938 | 2.2506 | 0 | 0 |  |  | 0 | 2.2506
| Laboratory Building U#8 | 0 | - | 0 | 0.12 | 0 | 0.12 | 0 | 0 |  |  | 0 | 0.12
3 | Staff quarters | 0 | - | 15.04 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Work of exterior repair, providing painting to A, D & E type residential buildings and Public Buildings and allied civil works in Urjanagar Colony, CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Staff Quarters- Repair and renovation of E type staff quarters to extend the life of buildings at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Staff Quarters - Repair and renovation of 'B' type staff quarters in residential colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair of D type quarters in colony at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair of C type quarters in colony at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Staff Quarters- Repair and renovation of F and NF type staff quarters to extend the life of buildings at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair and replacement of existing drinking water supply pipelines in E & F type area in colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repair and replacement of existing sewer lines in E & F type area in colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Work of providing RCC drain along main roads in colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Rerouting and replacement of domestic water supply pipeline from WTP to ESR in colony at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Additional Contengencies approved vide e BR No. MSPGCL/BM-162/165, Dt.29.10.2016 vide resolution no. 2016/2085 | 0 | - | 7.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Landscaping and plantation work at various locations inside plant area at CSTPS, chandrapur. | 0 | - | 0 | 3.4266 | 3.4266 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of WBM approach road from point- N to Z Area along ash bund periphery at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design, Engineering, Supply and commissioning of ash-bund water recovery system (Phase II) at CSTPS Chandrapur | 0 | - | 27.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, Engineering, Supply and commissioning of ash-bund water recovery system (Phase II) at CSTPS Chandrapur | 0 | - | 0 | 30.0361 | 30.0361 | 0 | 0 | 0 |  |  | 0 | 0
| Providing Consultancy Services for work of Design, Engineering, Supply, Installation & Commissioning of ash bund water recovery system (Phase-II) at CSTPS, Chandrapur (on EPC contract basis). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Providing laying, jointing and commissioning of 1600 mm dia. M.S. Pipe line from Erai dam to one day reservoir of stage II, III & IV at CTPS | 0 | - | 73.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Providing laying, jointing and commissioning of 1600 mm dia. M.S. Pipe line from Erai dam to one day reservoir of stage II, III & IV at CTPS | 0 | - | 0 | 73.6091 | 73.6091 | 0 | 0 | 0 |  |  | 0 | 0
| Work of construction of Control Valve rooms on newly laid 1600 mm M.S. Pipeline no. 6 from Erai dam to One day reservoir at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Providing OHE facility for BG Rly siding of proposed Expansion Project at Chandrapur, for Supply of Materials. | 0 | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Providing OHE facility for BG Rly siding of proposed Expansion Project at Chandrapur, for errection of OHE Items. | 0 | - | 2.5 | 0.7 | 0 | 0.7 | 0 | 0 |  |  | 0 | 0.7
9 | Irrigation scheme for landscaping and Plantation work at Chandrapur expansion project chandrapur. | 0 | - | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Asphalting of WBM road from Nagpur gate to Awanda gate. | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Asphalting of WBM road from Nagpur gate to Awanda gate. | 0 | - | 0 | 0.65141 | 0 | 0.65141 | 0 | 0 |  |  | 0 | 0.65141
| Asphalting over WBM Road of ADP line Service road from Nagpur gate opening to Awandha junction gate at CSTPS Chandrapur | 0 | - | 0 | 0.84833 | 0.84833 | 0 | 0 | 0 |  |  | 0 | 0
| Asphalting of WBM road from Nagpur gate to Awandha gate at CSTPS Chandrapur - Asphalting of road from Reject coal gate to Motghat nallah at CSTPS Chandrapur (PHASE - I) | 0 | - | 0 | 0.47941 | 0.47941 | 0 | 0 | 0 |  |  | 0 | 0
11 | Foot Over Bridge | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Work of Providing retaining wall for sand hump at Vivekanand nagar station yard under modification work in wardha end fro 2 x 500 MW Expn. Project at CSTPS, Chandrapur. | 0 | - | 0.3 | 0.25515 | 0.25515 | 0 | 0 | 0 |  |  | 0 | 0
| Additional Capitalization by O & M | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of GE make 4000Amp LT Air Circuit Breakers for Unit-8 & 9, CSTPS, Chandrapur. | 0 | - | 0.9 | 1.0308 | 1.0308 | 0 | 0 | 0 |  |  | 0 | 0
2 | Air Compressor System | 0 | - | 0.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Energy management Sysytem | 0 | - | 0.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, Installation, Testing & Commissioning of Energy Management System for Unit#8 & 9 for CSTPS, Chandrapur. | 0 | - | 0 | 0.20054 | 0.20054 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Tri-vector 0.2s class Digital Energy meter for Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0.094872 | 0.094872 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, Installation & Commissioning of 3D Level Scanners to 64 nos. of ESP hoppers at Unit-8&9 (2X500MW), CSTPS, Chandrapur. | 0 | - | 3.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of internal spares for Elecon make PWD-18, PLB-25 ,Pbh-71 type Gearbox for Stacker Reclaimer installed at CHPD, CSTPS. | 0 | - | 0 | 1.1089 | 1.1089 | 0 | 0 | 0 |  |  | 0 | 0
5 | 4000/2500/1800/800 A GE make LT CKT Brkr | 0 | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| LT Air Circuit Breakers for Incomer Feeders at CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 1.4207 | 1.4207 | 0 | 0 | 0 |  |  | 0 | 0
| LT Air Circuit Breakers at CHP, Unit 8&9, CSTPS | 0 | - | 0 | 1.0141 | 1.0141 | 0 | 0 | 0 |  |  | 0 | 0
6 | Replacement of Impact crusher by hammer mill crusher (installed qty.2 No) | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Replacement of wobbler feeder 1&2 by grizzly screen at CHP-D | 0 | - | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Installation of conveyor system from rope way of CHP-A and crusher house of CHP-D | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| PLC based control & instrumentation of 6.6 KV HT motors of 1250 KW of Crusher I & II and 200 KW of BC 108A1 & A2 at CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0.93628 | 0.93628 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Design, Supply, Erection & Commissioning of Complete Electrical Automation for Short Conveyor from stack yard of CHP-D to Belt Conveyor 107 A/B of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0.70095 | 0.70095 | 0 | 0 | 0 |  |  | 0 | 0
| Work of Design, Supply, Erection & Commissioning of Complete Electrical Automation for Short Conveyor from stack yard of CHP-B to Belt Conveyor 104 A/B of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 2.2368 | 2.2368 | 0 | 0 | 0 |  |  | 0 | 0
| WORK OF DESIGN, ENGINEERING, MANUFACTURING, SUPPLY, ERECTION &COMMISSIONING OF SHORT CONVEYOR BELT FROM STACK YARD OF CHP UNIT-8&9 TO CONVEYOR BELT 107A AND B AT CHP UNIT 8&9, CSTPS, CHANDRAPUR. | 0 | - | 0 | 4.6948 | 4.6948 | -2.4e-08 | 0 | 0 |  |  | 0 | -2.4e-08
| Design, Supply, Installation and Commissioning of High Performance Energy Chain System for Side Arm Charger and Stacker Reclaimer of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 3.8916 | 3.8916 | 0 | 0 | 0 |  |  | 0 | 0
| RBF 103 &104,105 & 106, 107 & 108, and 109 & 110 in to modular Y chute | 0 | - | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-103 & RBF-104 with Design, development, Manufacturing, Supply & erection of modular Chute as per site condition in place of RBF using sintered silicon Carbide plate with motorized Flap Gate at CHP-D, CSTPS. | 0 | - | 0 | 1.1741 | 1.1741 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-105 & RBF-106 with Design, development, Manufacturing, Supply & erection of modular Chute as per site condition in place of RBF using sintered silicon Carbide plate with motorized Flap Gate at CHP-D, CSTPS. | 0 | - | 0 | 1.3169 | 1.3169 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-107 & RBF-108 with Design, development, Manufacturing, Supply & erection of modular Chute as per site condition in place of RBF using Tungsten Carbide plate with Flap Gate at CHP-D, CSTPS. | 0 | - | 0 | 1.1529 | 1.1529 | 0 | 0 | 0 |  |  | 0 | 0
| RBF-109 & RBF-110 with design, erection & Installation by trajectory calculation & removal of existing RBF with Y Chute assembly by flow control with Flap Gate arrangement at TP-107 of CHP-D, CSTPS. | 0 | - | 0 | 1.1506 | 1.1506 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurment , Installation and commissioning of Online Insertable Camera systems for Unit-8, 500MW, CSTPS | 0 | - | 8.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, Supply, Installation & Commissioning of Energy efficient system for Illumination at Unit 8&9 CSTPS, Chandrapur. | 0 | - | 0 | 4.9494 | 4.9494 | 0 | 0 | 0 |  |  | 0 | 0
11 | Construction of Chemical godown shed for unit 8 & 9 at CSTPS,Chandrapur. | 0 | - | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of Chemical godown shed for unit 8 & 9 at CSTPS,Chandrapur. | 0 | - | 0 | 0.42946 | 0.42946 | 0 | 0 | 0 |  |  | 0 | 0
| Comprehencive work of installation, erection, testing and commissioning of MVWS spray system/ Fire safety system for new Bulk Chemical storage godown at CSTPS, Unit 8&9 | 0 | - | 0 | 0.27583 | 0.27583 | 0 | 0 | 0 |  |  | 0 | 0
| Work of electrification of godown for bulk chemical storage near FOPH building at Chandrapur project site. | 0 | - | 0 | 0.018322 | 0.018322 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of additional Chemical godown shed for storage of Lube oil at CSTPS Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Construction of RCC retaining wall for approach to RCC Bridge across Irai River, ADPL line at CSTPS | 0 | - | 8.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of RCC retaining wall for approach to RCC Bridge across Irai River, ADPL line at CSTPS | 0 | - | 0 | 4.3482 | 4.3482 | 0 | 0 | 0 |  |  | 0 | 0
| Asphalting of road from Reject coal gate to Motghat nallah at CSTPS Chandrapur (PHASE - II) | 0 | - | 0 | 0.87403 | 0.87403 | 0 | 0 | 0 |  |  | 0 | 0
| Providing extension to approaches of RCC bridge across Erai river by constructing WBM road at CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| UDL | 0 | - | 0 | 4.85 | 4.85 | 0 | 0 | 0 |  |  | 0 | 0
| B) DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (i) In Principally Approved By MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 1 | HMI (Human Machine Interface) Upgradation of ‘SSPA-T3000’ DCS (Distribution Control System), Rockwell make PLC System installed at 3x660MW Unit No. 8, 9 & 10 at Koradi TPS and HMI (Human Machine Interface) Upgradation of MaxDNA DCS System at Unit 8-9, CSTPS, Chandrapur | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 11.08 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 1.1 | Supply: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 10.52 | 10.52 | 21.02 | -10.5 | 0 | 0 |  |  | 0 | -10.5
HO DPR 1.2 | Works: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.41 | 0.41 | 0.81 | -0.4 | 0 | 0 |  |  | 0 | -0.4
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
40 | Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M with construction of concrete dam (Waste Weir & Non overflow structure), construction of drain wells, approach to drain wells and raising of ash compartment for ash bund along with renewal of Ash Disposal Pipe Line Service Road with WBM treatment at CSTPS, Chandrapur | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 4.9692 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 34.8665 | 34.8665 | 69.733 | -34.8665 | 0 | 0 |  |  | 0 | -34.8665
| Construction of New Drain Wells (12 Nos.) along with necessary connection to existing drain wells at CSTPS | 0 | - | 0.58493 | 0.58493 | 1.1699 | -0.58493 | 0 | 0 |  |  | 0 | -0.58493
| Construction of waste weir for raising of ash bund (Waste Weir & Non overflow structure) | 0 | - | 1.4621 | 1.4621 | 2.9241 | -1.4621 | 0 | 0 |  |  | 0 | -1.4621
| Raising of Ash Compartment i.e. Lagoon in Ash Bund | 0 | - | 8.7868 | 8.7868 | 17.5736 | -8.7868 | 0 | 0 |  |  | 0 | -8.7868
| IDC | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 7.634 | 7.634 | 15.2679 | -7.634 | 0 | 0 |  |  | 0 | -7.634
| IDC | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 4.9692 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
39 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 8-9) | MERC/CAPEX/2020-2021/WFH/SBR/21 | 2020-07-24 | 479.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
39.1 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 8-9) | MERC/CAPEX/2020-2021/WFH/SBR/21 | 2020-07-24 | 440.54 | 797.71 | 797.71 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/2020-2021/WFH/SBR/21 | 2020-07-24 | 38.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41 | CHP Performance Improvement Schemes at Unit 8-9 of CSTPS, Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 26.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.1 | Work of Design engineering , supply and installation of modular chutes with sintered silicon carbide for smooth flow &center feeding in CHP 2x500MW CSTPS | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 9.43 | 9.43 | 9.43 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.2 | Supply erection & commissioning of set of internal of impact crusher spares installed at CHPP-D, CSTPS | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 8.05 | 8.05 | 8.05 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.3 | Scheme for replacement of Scoop coupling/Fluid coupling of conveyor BC-101A/B/C, BC-102A/B, BC-104A/B, BC-105A/B ,BC-106A/B, BC-111A/B/C/D, BC-110A1/B1, BC-110A/B Installed at CHP-D, CSTPS Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 4.67 | 4.67 | 4.67 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.4 | Supply erection & commissioning of set of internal of spares of stacker reclaimer installed at CHP-D, CSTPS Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 1.96 | 1.96 | 1.96 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.5 | Supply erection & commissioning of set of internal of spares of Wagon tippler installed at CHP-D, CSTPS Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 2.12 | 2.12 | 2.12 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| IDC | MERC/CAPEX/MSPGCL/2023-24/0586 | 2023-11-03 | 0.38 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 2 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 2.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 27.12 | 27.12 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
A6 | Supply, Installation & Commissioning of Online Coal Flow Monitoring & Balancing System at Unit-8-9, CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0457 Dt 26.07.2024 | 2024-07-26 | 34.21 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, installation and commissioning of Online Coal flow monitoring and balancing system for U- 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2024-2025/MSPGCL/0457 Dt 26.07.2024 | 2024-07-26 | 34.21 | 34.21 | 34.21 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0457 Dt 26.07.2024 | 2024-07-26 | 0.31 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
A7 | Providing, supplying, laying and commissioning of 1600 mm dia. M.S. Pipe by replacement of existing PSC raw water line from Erai dam to reservoir at CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 40.7945 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing, supplying, laying and commissioning of 1600mm dia. M.S. pipe by replacement of existing PSC raw water line from Erai dam to reservoir at CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 40.7945 | 40.7945 | 40.7945 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 8.83 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
A8 | Adoption of Ozonization technique for disinfection of Cooling Water System at U # 8 & 9 | MERC/CAPEX/MSPGCL/2023-2024/0467 Dt 02.08.2024 | 2024-08-02 | 67 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Adoption of Ozonization technique for disinfection of Unit 8&9 Cooling Water at CSTPS. | MERC/CAPEX/MSPGCL/2023-2024/0467 Dt 02.08.2024 | 2024-08-02 | 67 | 67 | 67 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-2024/0467 Dt 02.08.2024 | 2024-08-02 | 2.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (ii) Submitted to MERC |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y1 | Multiple Schemes for Electrical Maintenance Section and Design, Engineering, Manufacturing, Testing, Unloading at site, E&C of 200MVA, 21/420KV Single Phase Generator Transformer for Unit # 8 & 9, CSTPS | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of 10MW, 11kV Motor and its recommended spare for Boiler Feed Pump (BFP) | To be resubmitted | - | 0 | 4.95 | 4.95 | 0 | 0 | 0 |  |  | 0 | 0
| Replacement of NiCd battery sets installed for UPS of Fire Water Pump House, CMRH & SWAS lab of Unit 8 & 9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0.86 | 0.86 | 0 | 0 | 0 |  |  | 0 | 0
| Retrofitting of GE make LT Air Circuit Breakers of various current ratings and procurement of their recommended spares for Unit-8&9, CSTPS | To be resubmitted | - | 0 | 4.85 | 4.85 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of BHEL make 6.6kV and 11kV Vacuum Circuit Breakers for Unit-8&9, CSTPS Chandrapur | To be resubmitted | - | 0 | 2.07 | 2.07 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y5 | Scheme-1: Procurement of assembly of baskets for Air Preheater of type 31.05 VIMT 2000 (72° PA), Scheme-2: Procurement of spares for PRDS station pressure control valves and Desuperheating spray Control valves in Boiler at U-8&9, CSTPS, Chandrapur, Scheme-3: Procurement of complete set of sky climber at U-8&9, CSTPS, Chandrapur. Scheme-4: Supply, erction, commissioning of oil free rotary screw compressors (including all Civil Electrical, C&I, Testing work) for CMRH system at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-1: Procurement of assembly of baskets for Air Preheater of type 31.5 VIMT 2000 (72° PA) at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 15.78 | 15.78 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-2: Procurement of spares for PRDS station pressure control valves and Desuperheating spray control valves in Boiler at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 6.09 | 6.09 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-3: Procurement of complete set of sky climber at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 3.16 | 3.16 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-4: Supply, erection, commissioning of oil free rotary screw compressors (including all Civil Electrical, C&I, Testing work) for CMRH system at U-8&9, CSTPS, Chandrapur. | To be resubmitted | - | 0 | 8.3 | 8.3 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y6 &Y7 | Supply, Erection & commissioning/retrofitting of HT Circuit Breaker with SF6 Contactor at AHP at Unit-8&9 & CHP#D and Supply, Installation and Commissioning of MV VFD panel along with integrated online cell redundancy technology with VFD bypass feature arrangement for conveyors 103 A & B of CHP-B, C.S.T.P.S., Chandrapur & Design, engineering, manufacturing, testing, unloading at site, E&C of Two No of 200 MVA, 21/420 KV Single Phase Generator Transformers for Unit-8&9, CSTPS, Chandrapur. Through OEM | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme 1: Retrofitting of BHEL make HT Circuit Breaker with SF6 contactor at AHP, Unit#8&9, CSTPS. | To be resubmitted | - | 0 | 38.33 | 38.33 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme 2: Retrofitting of BHEL make HT Circuit Breaker with SF6 contactor at CHP#D, Unit#8&9, CSTPS. | To be resubmitted | - | 0 | 5.64 | 5.64 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme 3: Supply, Installation and Commissioning of MV VFD panel along with integrated online cell redundancy technology with VFD bypass feature arrangement for conveyors 103 A & B of CHP-B. | To be resubmitted | - | 0 | 4.03 | 4.03 | 0 | 0 | 0 |  |  | 0 | 0
| Design, engineering, manufacturing, testing, unloading at site, E&C of Two No of 200 MVA, 21/420 KV Single Phase Generator Transformers for Unit-8&9, CSTPS, Chandrapur. Through OEM | To be resubmitted | - | 0 | 21.07 | 21.07 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | To be resubmitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (iii) Yet to be Submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Boiler Maintenance -III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of Air & Flue gas ducts of Boiler , Blade set and HAD for PA and FD Fan , SCAPH Coil, ID Fan spares at Unit-8&9 CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-1 Procurement of Air & flue gas expansion joints | 0 | - | 0 | 40 | 40 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-2 :Procurement of Blade Set and 2 sets of HAD of PA Fan. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme -3 Procurement of Blade Set and 2 sets of HAD of FD Fan. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-4 Procurement of SCAPH Coil for unit- 8&9 | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-5 :Procurement of ID Fan Impeller , Shaft and Blade set at unit-8 & 9, CSTPS | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme 6: Procurment of Coal Fuel pipes for unit -8 &9 , CSTPS | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of LTSH and economiser for unit-8&9 CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of LTSH Coil assemsblies unit- 8&9 | 0 | - | 0 | 0 | 0 | 0 | 20 | 20 |  |  | 20 | 0
| Procurement of economiser coil asemblies | 0 | - | 0 | 0 | 0 | 0 | 25 | 25 |  |  | 25 | 0
| Up-gradation of existing belt type gravimetric coal feeders to gravimetric rotary weigh coal feeders of unit- 8&9, at CSTPS, Chandrapur | 0 | - | 0 | 10.03 | 10.03 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of Quick Erect Aluminum Boiler Scaffolding system or unit- 8 & 9, (2X500MW), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of Quick Erect Aluminum Boiler Scaffolding system or unit- 8 & 9, (2X500MW), CSTPS, Chandrapur. | 0 | - | 0 | 35 | 35 | 0 | 0 | 0 |  |  | 0 | 0
| Turbine Maintenance -III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Schemes for Improvement in availability & performance of TG auxiliaries at U-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 1. Procurement of BFP Booster Pump assembly for Unit-8 & 9, CSTPS Chandrapur | 0 | - | 0 | 3.2 | 3.2 | 0 | 0 | 0 |  |  | 0 | 0
| 2. Procurement of Boiler Feed Pump catridge with CI sealing for Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 5.2 | 5.2 | 0 | 0 | 0 |  |  | 0 | 0
| 3. Procurement of Modulating type Boiler Feed Pump Recirculation valve (06 Nos) assembly for Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
| 4. Procurement of HP Heater HPH-5B assembly for Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
| 5. Procurement of MDBFP working oil & lube oil coolers for Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
| 6. Procurement of TDBFP Turbine rotor K1401-2 at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 7.5 | 7.5 | 0 | 0 | 0 |  |  | 0 | 0
| 7. Procurement of Main TG Jacking oil pumps (2 Nos.) at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
| 8. Procurement of HP elements of ZR500 Atlas Copco make compressors along with inter & after coolers tube nest at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
| 9. Procurement of CW & ACW Pump spares at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
| 10. Procurement of condenser tubes at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
| 11. Procurement of HPCF Pump at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
2 | DPR for performance improvement of Condenser Cooling water system & improvement in system reliability of auxiliary cooling water system installed at Unit-8&9, 2x500MW, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| DPR for performance improvement of Condenser Cooling water system & improvement in system reliability of auxiliary cooling water system installed at Unit-8&9, 2x500MW, CSTPS, Chandrapur | 0 | - | 0 | 34 | 34 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of main turbine IPT module at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of main turbine IPT module at Unit- 8 & 9, CSTPS Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 50 | 50 |  |  | 50 | 0
| Electrical Maintenance -III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Proc of GTR, MDBFP, UPS battery, breakers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, engineering, manufacturing, testing, unloading at site, E&C of 200 MVA, 21/420 KV Single Phase Generator Transformer for Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 21.07 | 21.07 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of MDBFP motor and recommended spares The Fire Water Pump House UPS Battery set of 240V, 40AH Capacity (1.2V X 176 Cells ) Ni Cd Type Make- HBL The UPS Battery Set at SWAS Lab (Outdoor Area), 45AH Capacity (1.2 V X 276 Cells) Ni Cd type Make- HBL for Unit#8&9 The UPS Battery Set at CMRH (Outdoor Area), 69AH Capacity (1.2 V X 280 Cells) Ni Cd type Make- HBL for Unit#8&9 Retrofitting of 415V GE make ACB of various ratings along with allied spares. BHEL make Breakers and spares for 6.6 kV and 11kV panels | 0 | - | 0 | 15.07 | 15.07 | 0 | 0 | 0 |  |  | 0 | 0
2 | Design, engineering, manufacturing, testing, unloading at site, E&C of 80 MVA, 420/11/6.9 KV three Phase Station Transformer & 25MVA 21/6.9KV Three phase Unit Aux Transformer as a common pool spares for BTPS 500MW, Khaparkheda 500 MW and Unit-8&9, CSTPS, Chandrapur & Supply, installation, commissioning and testing of Station Batteries of Unit-8&9 CSTPS alongwith all outdoor batteries | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, engineering, manufacturing, testing, unloading at site, E&C of 80 MVA, 420/11/6.9 KV three Phase Station Transformer & 25MVA 21/6.9KV Three phase Unit Aux Transformer as a common pool spares for BTPS 500MW, Khaparkheda 500 MW and Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 22 | 22 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, installation, commissioning and testing of Station Batteries of Unit-8&9 CSTPS alongwith all outdoor batteries | 0 | - | 0 | 12 | 12 | 0 | 0 | 0 |  |  | 0 | 0
| I&C -III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Upgradation of Analysis & Diagnostics system (A&D) for VMS and TSI system at Unit-8&9, CSTPS, Chandrapur.& other schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of Analysis & Diagnostics system (A&D) for VMS and TSI system at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 17 | 17 | 0 | 0 | 0 |  |  | 0 | 0
| Installation of CO analysers at Eco outlet at Unit-8&9, CSTPS Chandrapur. | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
| Complete Engineering Retrofitting of Existing 196 NT Controller by DT 9 Controller alongwith HMI units for Unit 8/9 coal feeder system. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of spares for LP bypass system. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
| Supply of spares for maxDNA DCS system | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
2 | Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-9, CSTPS, Chandrapur. | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
3 | Upgradation of HMI and hardware of GE make PLCs installed at Unit-8&9, CSTPS, Chandrapur. & other schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of HMI and hardware of GE make PLCs installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of TD-BFP Turbovisory system installed at Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of EWLI system installed at Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of O2 analysers installed at Unit-8&9, CSTPS, Chandrapur | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
| Installation of High temperature Camera system at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of HEA igniter system at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of Flue Gas Analysers and Opacity Analysers at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
4 | Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-8, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Implementation of various Upgradations / Modifications to mitigate the requirements of 40% TML operations of Unit-8, CSTPS, Chandrapur. | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
5 | Multiple schemes C&I-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Total Mercury (Gaseous) Analyzers along with their online data connectivity & Remote calibration U-3 to 9 | 0 | - | 0 | 9 | 9 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Controllers & Com Boxes for Air Compressors of Unit-8&9. | 0 | - | 0 | 5.5 | 5.5 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of Steam and Water Analysis System (SWAS) for Unit – 8 & 9 | 0 | - | 0 | 13 | 13 | 0 | 0 | 0 |  |  | 0 | 0
| Up-gradation of Servo valve (ST) with proportional valves (PV) for HP bypass system at Unit – 8 & 9 | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of GEHO pump VFD panels for Unit – 8 & 9 | 0 | - | 0 | 9 | 9 | 0 | 0 | 0 |  |  | 0 | 0
6 | Upgradation of measurement and control system installed at CSTPS Unit 8&9 & Upgradation of Numerical Protection Relay of Alstom / Schnieder make installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of measurement and control system installed at CSTPS Unit 8&9 | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of Numerical Protection Relay of Alstom / Schnieder make installed at Unit-8&9, CSTPS, Chandrapur. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
| AHP-III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | supply of piston cylinder assembly, diaphragm assembly, Suction and discharge valve housing assembly of GEHO pump (Model- TZPM 1200). & other schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-1 :supply of piston cylinder assembly, diaphragm assembly, Suction and discharge valve housing assembly of GEHO pump (Model- TZPM 1200). | 0 | - | 0 | 13 | 13 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme -2 :Procurement of sub assemblies for conveying air compressor model ZR 275 and instrument air compressor model ZR 110 in Ash handling plant Unit-8&9 (2x500MW) at CSTPS, Chandrapur. | 0 | - | 0 | 18 | 18 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme -3 Supply of 10/8 FAH Warman make slurry pump impeller element assembly, Bearing assembly unit, jacket assembly. | 0 | - | 0 | 12 | 12 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply and replacement of 400 NB MSERW pipeline of ash disposal system of unit 8&9 at CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 :Supply and replacement of 400 NB MSERW pipeline of ash disposal system of unit 8&9 at CSTPS, Chandrapur. | 0 | - | 0 | 70 | 70 | 0 | 0 | 0 |  |  | 0 | 0
3 | Complete ESP Refurbishment of 1st & 2 nd Row Field of Unit 8&9 at CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 : Complete ESP Refurbishment of 1st & 2 nd Row Field of Unit 8&9 at CSTPS. | 0 | - | 0 | 12.5 | 12.5 | 0 | 12.5 | 12.5 |  |  | 12.5 | 0
0 | CHP - D | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Upgradation Of Hydraulic Systems with Safety Mechanism for wagon unloading system at CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply erection & commissioning of wagon tippler, Side Arm Charger, apron feeder and stacker hydraulic drive system with online NAS value monitoring systems. | 0 | - | 0 | 24 | 24 | 0 | 0 | 0 |  |  | 0 | 0
0 | Wagon stopping mechanism (Safety) | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgardation and Capacity Enhancement of Side Arm Charger Apron Feeder and Bunker Conveyors at CHP-D CSTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | capacity enhancement to 60 wagons pulling capacity and associated modification of existing side arm charger | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | Capacity enhancement , Commissionng of apron feeder drive | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
0 | Modification and revamping of Apron Feeder 101,102,103 | 0 | - | 0 | 16.5 | 16.5 | 0 | 7 | 7 |  |  | 7 | 0
0 | Supply,Installation and Commissioning of double drive Mechanism with Split Case Bearings for Tripper Trolley and bunkering conevyor belts of CHP-D, CSTPS | 0 | - | 0 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
0 | Modification of Fixed Tripper Head Pulley(Z-Point) of BC110A&B at CHP-D CSTPS. | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
0 | Modification, Errection & Commissioning of drive unit capacity enhancement for conveyor at CHP-D, Chandrapur TPS. | 0 | - | 0 | 9 | 9 | 0 | 3 | 3 |  |  | 3 | 0
3 | Performance Improvement Schemes of CHP-D CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design engineering , supply and installation of modular chutes with weld cast Liners ,flap gates and actuators. | 0 | - | 0 | 70 | 70 | 0 | 15 | 15 |  |  | 15 | 0
0 | Supply erection & commissioning of set of internal of spares of Wagon tippler and Side Arm Charger installed at CHP-D, CSTPS Chandrapur | 0 | - | 0 | 5 | 5 | 0 | 10 | 10 |  |  | 10 | 0
0 | Supply erection & commissioning of set of internal of spares of stacker reclaimer installed at CHP-D, CSTPS Chandrapur | 0 | - | 0 | 10 | 10 | 0 | 10 | 10 |  |  | 10 | 0
0 | Supply erection & commissioning of set of internal of spares of Impact crusher installed at CHP-D, CSTPS Chandrapur | 0 | - | 0 | 10 | 10 | 0 | 10 | 10 |  |  | 10 | 0
0 | Supply erection & commissioning of set of internal of spares of wobbler feeder installed at CHP-D, CSTPS Chandrapur | 0 | - | 0 | 10 | 10 | 0 | 10 | 10 |  |  | 10 | 0
0 | Supply erection & commissioning of 1500 TPH capacity Stacker Recliamer sleeving bearing with fastener of CHP-D (U8&9), CSTPS, Chandrapur | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of Gearbox assemblies at CHP-D CSTPS. | 0 | - | 0 | 14 | 14 | 0 | 0 | 0 |  |  | 0 | 0
0 | Structure Strengthening,Modification works of Conveyors at CHP-D CSTPS | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
4 | Design, Installation, testing and commissioning of new conveyor systems of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Installation, testing and commissioning of conveyor system from crusher house to TP-108 of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 50 | 50 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Engineering, erection and commissioning of one 1500TPH crusher, short conveyors from TP 106 and open space of near Stack yard A pile to Crusher inlet and a telescopic conveyor at the output of crusher to Stack Yard B pile of CHPD Unit 8&9, CSTPS. | 0 | - | 0 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design, Installation and commissioning of conveyor system from rope way of CHP-A to crusher house of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Installation and commissioning of conveyor system from rope way of CHP-A to crusher house of CHP-D, CSTPS, Chandrapur. | 0 | - | 0 | 50 | 50 | 0 | 0 | 0 |  |  | 0 | 0
6 | Infrastructure Development Schemes at CHP-D CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Supply,Installation and Commissioning of EOT Cranes at Wagon Tippler area of CHP-D CSTPS. | 0 | - | 0 | 22 | 22 | 0 | 0 | 0 |  |  | 0 | 0
0 | Belt Tracking systems for Carrying/Return 1400/1600 mm belt width | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Ceramic Lagging by direct bonding on Conveyor Pulleys without Rubber Pad/Rubber Sheets. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Rewamping of crane and hoist of CHP, Unit 8&9, CSTPS, Chandrapur | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Material lifting mechanism at Crusher, bunker and Tunnel area of CHP-D CSTPS. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping, modification of TunnelAir ventilation system | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping, modification of DE and DS system | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping, modification of Dewatering and water recirculation system | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of New Office Building with Infrastructure ,Interior Development at CHP-D CSTPS. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Material Storage Shed Fabrication work at CHP-D CSTPS | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
7 | Electrical schemes for improvement in availability & Reliability of CHP-D,CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design supply installation and commisioning of LED based energy efficient system for illumination at CHPD | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Erection, Commissioning and Testing of 7.2KV SF6 HT Contactor for retrofitting of existing BHEL make Vacuum Circuit Breakers of CHP-D, CSTPS | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of GE make 90-30 series PLC system installed at stacker rclaimer and wagon tippler at CHP-D, CSTPS | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Installation of energy efficient air temperature controlling system at various MCC rooms of CHPD, CSTPS | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Alterration, upgradation of tunnel ventilation system of CHPD, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
0 | Design, Fabrication, Erection & commissioning of cable support structure along with re-routing & trial of auxiliaries at Crusher PMCC, compressor house & short conveyor area at CHP-D, CSTPS | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and installation of LT air circuit breakes at CHP-D, CSTPS | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, supply, installation & commissioning of solar based energy efficient illumination system at CHP-D, CSTPS | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of HT motors for various auxiliaries at CHP-D, CSTPS. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & installation of high capacity submersible slurry pump at CHP-D, CSTPS | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reconditioning of MCC Board feeder panels at CHP-D,U #8&9.CSTPS,Chandrapur. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & installation of anoodized winding magnets along with control panels for installation at various conveyor belts of CHP-D, CSTPS | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of 69 AH HBL make battery set of CHP-D (U8&9), CSTPS, Chandrapur. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of 100 AH Exide make battery banks (2 Set/ 110 Nos battery cells) & battery charge at CHP-D (U8&9), CSTPS, Chandrapur. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Alterration, upgradation of tunnel ventilation system of CHPD, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
0 | Supply of HT/LT Xmers assy of CHP-D (U8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
0 | Supply of HT/LT Xmers assy of CHP-D (U8&9), CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
0 | WTP-III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Engineering, installation and commissioning of DM stream capacity of 4800M3/Day for U # 8 & 9 in addition to existing DM stream at WTP, CSTPS, Chandrapur | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Engineering, installation and commissioning of DM stream capacity of 4800M3/Day for U # 8 & 9 in addition to existing DM stream at WTP, CSTPS, Chandrapur | 0 | - | 0 | 46.4 | 46.4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Civil - 8&9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work of diversion of peripheral nallah towards ash water recovery pump house alogwith construction of waste wear at ash bund area CSTPS, Chandrapur. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Work of diversion of peripheral nallah towards ash water recovery pump house alogwith construction of waste wear at ash bund area CSTPS, Chandrapur. | 0 | - | 0 | 35.4 | 35.4 | 0 | 0 | 0 |  |  | 0 | 0
2 | Infrastructure development of CHP-D area at U-8, 9, CSTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of platform for unloading of coal near TP-106 upto stack pile A of CHP-D | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of WBM Road for fire fighting arrangement at CHP-D U-8,9 | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction & Pushing RCC box of size 2mx2m under railway track to drain out the surface water near Rly - A cabin Unit-8,9 | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of concrete pavement road connecting to reject gate & vinchoda chowk , Y point to ash recovery pump house | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
HO1 | CHP Improvement Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at CHP-D | 0 | - | 0 | 100 | 100 | 0 | 0 | 0 |  |  | 0 | 0
HO2 | Developlment & Upgradation of DSM software system for MSPGCL | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Developlment & Upgradation of DSM software system for MSPGCL | 0 | - | 0 | 55 | 55 | 0 | 0 | 0 |  |  | 0 | 0
1 | Implementation of Flexible Operation Solutions | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Flexible Operation Solutions | 0 | - | 0 | 34 | 34 | 0 | 0 | 0 |  |  | 0 | 0
0 |  | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | General asset | 0 | - | 0 | 3.2096 | 3.2096 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply, Operation & Maintenance of Mobile Coal Sampling Equipment (MCSE) for coal sampling at loading ends of WCL for Mahagenco | 0 | - | 0 | 3.1648 | 3.1648 | 0 | 0 | 0 |  |  | 0 | 0
3 | ABC Powder Type and Foam Type Composite Fire Extinguisher | 0 | - | 0 | 1.528 | 1.528 | 0 | 0 | 0 |  |  | 0 | 0
4 | NON-Detailed Project Report for the Work of Upgradation/Renovation of Crusher House of CHPB of Unit-5, 6&7 at CSTPS Chandrapur (benefit U-8,9 by short conveyor coal stacking in catering emergency) | 0 | - | 0 | 2.8807 | 2.8807 | 0 | 0 | 0 |  |  | 0 | 0
5 | Extention of stacker reclaimer area for improvement in coal stack management at CHP-D CSTPS Chandrapur U-8,9 | 0 | - | 0 | 8.46 | 8.46 | 0 | 0 | 0 |  |  | 0 | 0
6 | Retrofitting of BHEL make HT Circuit Breaker with SF6 Contactor at CHP-D, Unit-8&9 | 0 | - | 0 | 4.25 | 4.25 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 3123.873 | 3175.8434 | -51.9704 | 212.5 | 212.5 | 0 | 0 | 212.5 | -51.9704