## F4
MSPGCL: Khaperkheda U # 1-4
MTR Petition Formats - Generation
Form 4: Summary of Capital Expenditure and Capitalisation
(Rs. Crore)
Sr. No. | Particulars | FY 2022-23 |  |  | FY 2023-24 |  |  | FY 2024-24 |  |  |  |  | Ensuing Years |  |  |  |  | Remarks
|  | MYT Order (227 of 2022) | April-March (Audited ) | True-Up requirement | MYT Order (227 of 2022) | April-March (Audited ) | True-Up requirement | MYT Order (227 of 2022) | Apr-Sep (Estimated) | Oct-Mar (Projected) | April - March (Projected) | Provisional True-Up requirement | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30
|  | (a) | (b) | (c) = (b) - (a) | (d) | (e) | (f) = (e) - (d) | (g) | (h) | (i) | (j) = (h )+ (i) | (k) = (j) - (g) | Projected | Projected | Projected | Projected | Projected
1 | Capital Expenditure |  | 149.912 | 149.912 |  | 354.1796 | 354.1796 |  |  |  | 207.1952 | 207.1952 | 397.1133 | 1102.88 | 777.49 | 214.92 | 180.8
2 | Capitalisation | 45.77 | 43.1643 | -2.6057 | 421.13 | 112.0788 | -309.0512 | 101.01 | 1.27 | 630.27 | 631.5376 | 530.5276 | 626.4118 | 1102.88 | 777.49 | 214.92 | 180.8
3 | IDC |  |  | 0 |  |  | 0 |  |  |  |  | 0
4 | Capitalisation + IDC | 45.77 | 43.1643 | -2.6057 | 421.13 | 112.0788 | -309.0512 | 101.01 | 1.27 | 630.27 | 631.5376 | 530.5276 | 626.4118 | 1102.88 | 777.49 | 214.92 | 180.8
Note: * - Truing Up for FY 2022-23 & FY 2023-24 to be done under MERC MYT Regulations 2019 with reference to amounts approved in the MYT Order for FY 2019-20 to FY 2024-25
Detailed Justification shall be provided for variation in approved capital expenditure and capitalisation vis-a-vis actual capital expenditure and capitalisation

## F4.1
MSPGCL: Khaperkheda U # 1-4
MTR Petition Formats - Generation
| Project Details |  | Form 4.1: Capital Expenditure Plan | [14 empty] | (Rs. Crore)
Sr. No. | Project Code | Project Title | MERC Approval No. | MERC Approval Date | Project Purpose | Project Start Date |  |  | Project Completion date (Scheduled) |  |  | Capital Cost
[6 empty] | Original | Revised | Actual | Original | Revised | Actual | Approved | Actual Capital Cost Incurred | Deviation = Approved - Actual on account of
[14 empty] | Change in Scope of Work (a) | Material Cost (b) | IDC (c) | Others (d) | Total Deviation (a+b+c+d)
A) DPR Schemes
(i) Submitted to MERC
1 | Combustion optimization system | DPR | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 |  | 2010-10-29 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
1.1 | Dynamic coal flow measurement and control (balancing) system (one) | Scheme | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 |  | 2010-10-29 |  | - | - |  | - | 8.17 | 0 |  | 8.17 |  |  | 8.17
1.2 | CO analyser (8 units) | Scheme | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 |  | 2010-10-29 |  | - | - |  | - | 1.19 | 0 |  | 1.19 |  |  | 1.19
1.3 | Oxygen analyser (32 units) | Scheme | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 |  | 2010-10-29 |  | - | - |  | - | 0.783 | 0.75683 |  | 0.02617 |  |  | 0.02617
0 | IDC | IDC | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 |  | 2010-10-29 |  | - | - |  | - | 0.6 | 0 |  | 0.6 |  |  | 0.6
2 | Spare HPT module for Khaparkheda Unit 1 & 2 | DPR | MERC/CAP/DPR/10/2010-11/1466 | 2010-10-26 |  | 2010-10-26 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
2.1 | HPT module 1 No (unit # 1) | Scheme | MERC/CAP/DPR/10/2010-11/1466 | 2010-10-26 |  | 2010-10-26 |  | - | - |  | - | 23.0379 | 23.9074 |  | -0.86952 |  |  | -0.86952
0 | IDC | IDC | MERC/CAP/DPR/10/2010-11/1466 | 2010-10-26 |  | 2010-10-26 |  | - | - |  | - | 3.4211 | 0 |  | 3.4211 |  |  | 3.4211
3 | Economiser Upper Bank & Lower Bank coils for Khaperkheda Unit no. 3 and Unit no. 4 | DPR | MERC/CAP/DPR/10/2010-11/1695 | 2010-12-15 |  | 2010-12-15 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
3.1 | Economiser Upper Bank & Lower Bank coils for Khaperkheda Unit no. 3 and Unit no. 4 | Scheme | MERC/CAP/DPR/10/2010-11/1695 | 2010-12-15 |  | 2010-12-15 |  | - | - |  | - | 26.35 | 11.77 |  | 14.58 |  |  | 14.58
4 | Economiser & LTSH Upper Bank & Lower Bank coils for Khaperkheda Unit no. 1 and Unit no. 2 | DPR | MERC/CAPEX/20112012/01155 | 2011-07-29 |  | 2011-07-29 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
4.1 | Economiser & LTSH Coil for Unit 1 | Scheme | MERC/CAPEX/20112012/01155 | 2011-07-29 |  | 2011-07-29 |  | - | - |  | - | 15.6924 | 15.6924 |  | 0 |  |  | 0
4.2 | Economiser & LTSH Coil for Unit 2 | Scheme | MERC/CAPEX/20112012/01155 | 2011-07-29 |  | 2011-07-29 |  | - | - |  | - | 16.1528 | 16.1528 |  | 0 |  |  | 0
0 | IDC | IDC | MERC/CAPEX/20112012/01155 | 2011-07-29 |  | 2011-07-29 |  | - | - |  | - | 2.9464 | 0 |  | 2.9464 |  |  | 2.9464
5 | Procurement & Replacement of Re-heater Rear Pendant Assembly Coils for 2*210MW Khaperkheda Unit no. 1 and Unit no. 2 | DPR | MERC/CAPEX/20122013/00603 | 2012-06-18 |  | 2012-06-18 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
5.1 | Re-heater coils for unit no. 1 | Scheme | MERC/CAPEX/20122013/00603 | 2012-06-18 |  | 2012-06-18 |  | - | - |  | - | 5.1267 | 5.1267 |  | 0 |  |  | 0
5.2 | Re-heater coils for unit no. 2 | Scheme | MERC/CAPEX/20122013/00603 | 2012-06-18 |  | 2012-06-18 |  | - | - |  | - | 5.1267 | 5.55 |  | -0.42327 |  |  | -0.42327
0 | IDC | IDC | MERC/CAPEX/20122013/00603 | 2012-06-18 |  | 2012-06-18 |  | - | - |  | - | 0.1204 | 0 |  | 0.1204 |  |  | 0.1204
6 | Procurement of HPT module suitable for khaperkheda TPS Unit 3 & 4 | DPR | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 |  | 2014-01-17 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
6.1 | Procurement of HPT module suitable for khaperkheda TPS Unit 3 & 4 | Scheme | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 |  | 2014-01-17 |  | - | - |  | - | 36.2 | 32.4016 |  | 3.7984 |  |  | 3.7984
7 | Procurement Spare GTR, Locomotive & Compactors | DPR | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 |  | 2014-05-20 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
7.1 | 250 MVA Spare GTR | Scheme | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 |  | 2014-05-20 |  | - | - |  | - | 10.3496 | 11.2511 |  | -0.90146 |  |  | -0.90146
7.2 | Procurement of Locomotive 2no’s. | Scheme | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 |  | 2014-05-20 |  | - | - |  | - | 5.9927 | 5.9927 |  | -1.0052e-05 |  |  | -1.0052e-05
7.3 | Procurement of Compactors 2 no’s. | Scheme | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 |  | 2014-05-20 |  | - | - |  | - | 0.42979 | 0.4298 |  | -1.408e-05 |  |  | -1.408e-05
0 | IDC | IDC | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 |  | 2014-05-20 |  | - | - |  | - | 1.68 | 0 |  | 1.68 |  |  | 1.68
8 | Procurement & Replacement of complete set of LTSH coils for Khaperkheda TPS Unit 3&4 | DPR | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 |  | 2014-05-20 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
8.1 | Procurement and replacement of LTSH coils for Khaperkheda TPS at U3 | Scheme | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 |  | 2014-05-20 |  | 2015-04-28 | 2017-05-20 |  | 2016-08-24 | 8.58 | 3.4291 |  | 5.1509 |  |  | 5.1509
8.2 | Procurement and replacement of LTSH coils for Khaperkheda TPS at U4 | Scheme | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 |  | 2014-05-20 |  | 2017-01-21 | 2017-05-20 |  | 2017-09-05 | 8.58 | 3.1809 |  | 5.3991 |  |  | 5.3991
0 | IDC | IDC | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 |  | 2014-05-20 |  | - | - |  | - | 0.65 | 0 |  | 0.65 |  |  | 0.65
9 | Development of Ash Bund (Waregaon) at K'kheda TPS | DPR | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 |  | 2013-07-09 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
9.1 | Construction of 3rd upstream raising of existing ash bund from TBL 299.50 Mtr to 302.50 Mtr at Waregaon, Khaperkheda TPS. | Scheme | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 |  | 2013-07-09 |  | 2015-06-12 | 2016-12-17 |  | 2019-08-05 | 33.8585 | 32.5375 |  | 1.321 |  |  | 1.321
9.2 | Construction of masonary dam (Gabion structure) at Waregaon TPS, Khaperkheda. | Scheme | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 |  | 2013-07-09 |  | 2015-06-12 | 2016-12-17 |  | 2019-08-05 | 1.0561 | 0 |  | 1.0561 |  |  | 1.0561
9.3 | Construction of approach to drain wells and raising height of drain well no. 1,2 & 3 ash bund at Waregaon, Khaperkheda TPS | Scheme | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 |  | 2013-07-09 |  | 2015-06-12 | 2016-12-17 |  | 2019-08-05 | 0.48488 | 0 |  | 0.48488 |  |  | 0.48488
0 | IDC | IDC | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 |  | 2013-07-09 |  | - | - |  | - | 3.3464 | 0 |  | 3.3464 |  |  | 3.3464
10 | Various schemes related to CHP Improvement & Performance Optimization and scheme of conversion of existing Composite OHE to Conventional OHE | DPR | MERC/CAPEX/20152016/00422 | 2016-08-03 |  | 2016-08-03 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
10.1 | Air Cooled Suspension Magnet for Con. 3 & 6 of CHP 210 MW | Scheme | MERC/CAPEX/20152016/00422 | 2016-08-03 |  | 2016-08-03 |  | 2018-03-01 | 2019-08-03 |  | 20/10/19 | 2.18 | 2.2613 |  | -0.081326 |  |  | -0.081326
10.2 | Procurement of Impact crusher motor | Scheme | MERC/CAPEX/20152016/00422 | 2016-08-03 |  | 2016-08-03 |  | 2017-01-02 | 2019-08-03 |  | 2017-08-03 | 0.84 | 0.52579 |  | 0.31421 |  |  | 0.31421
10.3 | Procurement of 360V, 200 AH battery set and 360V 325 AH battery set for U# 1to 4 | Scheme | MERC/CAPEX/20152016/00422 | 2016-08-03 |  | 2016-08-03 |  | 2018-06-14 | 2019-08-03 |  | 18/12/20 | 1.1 | 1.4576 |  | -0.35764 |  |  | -0.35764
10.4 | Procurement of POG Instruments for Unit 1 to 4 | Scheme | MERC/CAPEX/20152016/00422 | 2016-08-03 |  | 2016-08-03 |  | 2017-04-01 | 2019-08-03 |  | 20/03/18 | 0.77 | 0.35015 |  | 0.41985 |  |  | 0.41985
10.5 | Up gradation of safe scan flame scanner system by BHEL scan system in unit no. 1, 3 & 4 | Scheme | MERC/CAPEX/20152016/00422 | 2016-08-03 |  | 2016-08-03 |  | cancelled | 2019-08-03 |  | cancelled | 1.35 | 0 |  | 1.35 |  |  | 1.35
10.6 | Up gradation of old AVR system to DAVR | Scheme | MERC/CAPEX/20152016/00422 | 2016-08-03 |  | 2016-08-03 |  | cancelled | 2019-08-03 |  | cancelled | 1.33 | 0 |  | 1.33 |  |  | 1.33
10.7 | Conversion of existing Composite OHE to Conventional OHE | Scheme | MERC/CAPEX/20152016/00422 | 2016-08-03 |  | 2016-08-03 |  | 2016-08-03 | 2019-08-03 |  | 2017-03-31 | 2.72 | 2.72 |  | 0 |  |  | 0
0 | IDC | IDC | MERC/CAPEX/20152016/00422 | 2016-08-03 |  | 2016-08-03 |  | - | - |  | - | 0.47 | 0 |  | 0.47 |  |  | 0.47
11 | ESP up-gradation for Unit-1 at Khaperkheda TPS | DPR | MERC/CAPEX/20152016/01261 | 2016-01-11 |  | 2016-01-11 |  | - | 2018-03-31 |  | - | 0 | 0 |  | 0 |  |  | 0
11.1 | ESP up-gradation for Unit-1 at Khaperkheda TPS | Scheme | MERC/CAPEX/20152016/01261 | 2016-01-11 |  | 2016-01-11 |  | - | 2018-03-31 |  | - | 32.01 | 0 |  | 32.01 |  |  | 32.01
13 | Procurement, installation and commissioning of Gravimetric Belt / Rotary Type Feeder, VFD for CEP, Up-gradation of BTS system & Environmental schemes at Khaperkheda TPS | DPR | MERC/CAPEX/20162017/01552 | 2017-02-14 |  | 2017-02-14 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
13.1 | Procurement, installation and commissioning of Gravimetric belt/rotary Feeder at U-1 & 2 | Scheme | MERC/CAPEX/20162017/01552 | 2017-02-14 |  | 2017-02-14 |  | 2018-01-20 | 2020-02-14 |  | 2019-09-07 | 5.72 | 4.7418 |  | 0.9782 |  |  | 0.9782
13.2 | Installation of VFD to CEP at U-1 to 4 | Scheme | MERC/CAPEX/20162017/01552 | 2017-02-14 |  | 2017-02-14 |  | 2019-05-21 | 2020-02-14 |  | - | 8.64 | 7.9943 |  | 0.64574 |  |  | 0.64574
13.3 | Installation of BTS system at U-4 | Scheme | MERC/CAPEX/20162017/01552 | 2017-02-14 |  | 2017-02-14 |  | 2018-10-16 | 2020-02-14 |  | 2019-08-11 | 0.98796 | 0.98796 |  | 0 |  |  | 0
13.4 | Replacement of SOx/NOx analyzer at U-1 to 4 | Scheme | MERC/CAPEX/20162017/01552 | 2017-02-14 |  | 2017-02-14 |  | 2018-03-01 | 2020-02-14 |  | 2019-03-31 | 2.42 | 2.3035 |  | 0.11652 |  |  | 0.11652
13.5 | Procurement of TGA,CHNS analyzer and Bomb calorimeter at U-5 | Scheme | MERC/CAPEX/20162017/01552 | 2017-02-14 |  | 2017-02-14 |  | 2017-04-01 | 2020-02-14 |  | 2018-03-31 | 1.71 | 0.2897 |  | 1.4203 |  |  | 1.4203
0 | IDC | IDC | MERC/CAPEX/20162017/01552 | 2017-02-14 |  | 2017-02-14 |  | - | - |  | - | 0.74 | 0 |  | 0.74 |  |  | 0.74
16 | Up gradation of HMI System at Unit No 3 & 4 at Khaperkheda TPS | DPR | MERC/CAPEX/20172018/03946 | 2017-07-19 |  | 2017-07-19 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
16.1 | HMI Up-gradation at U# 3 & 4 | Scheme | MERC/CAPEX/20172018/03946 | 2017-07-19 |  | 2017-07-19 |  | 2018-05-18 | 2019-07-19 |  | - | 12.78 | 12.5611 |  | 0.2189 |  |  | 0.2189
0 | IDC | IDC | MERC/CAPEX/20172018/03946 | 2017-07-19 |  | 2017-07-19 |  | - | - |  | - | 0.61 | 0 |  | 0.61 |  |  | 0.61
21 | Procurement of APH Basket for unit # 1 to 5 and Up-gradation of HT Motor Protection Relay in Unit # 1 to 4 at Khaperkheda TPS | DPR | MERC/CAPEX/2018-2019/105 | 2019-04-05 |  | 2019-04-05 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
21.1 | Procurement of assembly of baskets for air preheater of type bisector APH 27 VI: 1850, 12 sector in unit no. 1 & 2 and bisector APH 27 VI: 2000; 24 sector in unit no. 3 & 4 (210MW x 4) at TPS, Khaperkheda | Scheme | MERC/CAPEX/2018-2019/105 | 2019-04-05 |  | 2019-04-05 |  | 2019-05-23 | 2021-04-05 |  | - | 5.71 | 8.097 |  | -2.387 |  |  | -2.387
21.3 | Up-gradation of H.T. Motor protection relays in Unit 1 to 4 (210MW), Khaperkheda TPS | Scheme | MERC/CAPEX/2018-2019/105 | 2019-04-05 |  | 2019-04-05 |  | 31.12.2020 | 2021-04-05 |  | - | 3.96 | 3.1137 |  | 0.84633 |  |  | 0.84633
0 | IDC | Scheme | MERC/CAPEX/2018-2019/105 | 2019-04-05 |  | 2019-04-05 |  | - | - |  | - | 0.1 | 0 |  | 0.1 |  |  | 0.1
22 | Procurement of LPT rotor suitable for Unit # 3 & 4 of 210 MW at Khaperkheda TPS | DPR | MERC/CAPEX/2018-2019/132 | 2019-05-09 |  | 2019-05-09 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
22.1 | Procurement of LPT rotor suitable for Unit # 3 & 4 of 210 MW at Khaperkheda TPS | Scheme | MERC/CAPEX/2018-2019/132 | 2019-05-09 |  | 2019-05-09 |  | 2020-04-07 | 2021-05-09 |  | - | 26.491 | 10.7515 |  | 15.7395 |  |  | 15.7395
0 | IDC | IDC | MERC/CAPEX/2018-2019/132 | 2019-05-09 |  | 2019-05-09 |  | - | - |  | - | 0.7 | 0 |  | 0.7 |  |  | 0.7
23 | Supply, Erection & commissioning of HT Vacuum circuit Breakers & SF6 contactors at AHP (U#1-4) & CHP (U#1 to 5) and 160 KW VFD Panel with Motor for fire-fighting pumps at U#1 to 4 at Khaperkheda TPS | DPR | MERC/CAPEX/2019-2020/799 | 2019-09-27 |  | 2019-09-27 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
23.1 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at AHP (Unit#1 to 4, 210MW), Khaperkheda T.P.S. | Scheme | MERC/CAPEX/2019-2020/799 | 2019-09-27 |  | 2019-09-27 |  | 2021-01-22 | 2021-09-27 |  | - | 4.17 | 3.4843 |  | 0.68567 |  |  | 0.68567
23.2 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at CHP (Unit#1 to 4, 210MW) and CHP (Unit#5, 500MW) Khaperkheda T.P.S. | Scheme | MERC/CAPEX/2019-2020/799 | 2019-09-27 |  | 2019-09-27 |  | 2021-01-22 | 2021-09-27 |  | - | 3.81 | 4.031 |  | -0.221 |  |  | -0.221
23.3 | Supply, Erection & commissioning of 150 KW VFD Panel with motor for fire-fighting pumps at 210 MW Khaperkheda TPS. | Scheme | MERC/CAPEX/2019-2020/799 | 2019-09-27 |  | 2019-09-27 |  | 2021-09-29 | 2021-09-27 |  | - | 2.34 | 2.0957 |  | 0.24432 |  |  | 0.24432
0 | IDC | IDC | MERC/CAPEX/2019-2020/799 | 2019-09-27 |  | 2019-09-27 |  | - | - |  | - | 0.58 | 0 |  | 0.58 |  |  | 0.58
24 | Augmentation of Waregaon Ash Water Recovery System at TPS Khaperkheda | DPR | MERC/CAPEX/2019-20/732 | 2019-09-16 |  | 2019-09-16 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
24.1 | Augmentation of Waregaon Ash Water Recovery System at TPS Khaperkheda | Scheme | MERC/CAPEX/2019-20/732 | 2019-09-16 |  | 2019-09-16 |  | 2020-07-17 | 2021-09-16 |  | - | 15.7884 | 13.9315 |  | 1.8569 |  |  | 1.8569
0 | IDC | IDC | MERC/CAPEX/2019-20/732 | 2019-09-16 |  | 2019-09-16 |  | - | - |  | - | 1.41 | 0.58812 |  | 0.82188 |  |  | 0.82188
25 | Procurement of VFD with HMI & Controller & Replacing with existing Eddy-current drives of Coal feeders at U# 3 & 4 and Procurement of Various Critical Components of GEHO Pump (Model-TZPM 800) for AHP-1 at Khaperkheda TPS | DPR | MERC/CAPEX/2019-2020/734 | 2019-09-16 |  | 2019-09-16 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
25.1 | Up-gradation of Existing BHEL make 36” Gravimetric Coal Feeders control panel with HMI and croprocessor based Controller with VFD, Motor & Weigh Module at Unit 3 & 4, (210MW) | Scheme | MERC/CAPEX/2019-2020/734 | 2019-09-16 |  | 2019-09-16 |  | - | 2021-09-16 |  | - | 7.4655 | 0 |  | 7.4655 |  |  | 7.4655
25.2 | Procurement of various Critical Components of GEHO Pump (Model-TZPM 800) for AHP-1 (210MW) | Scheme | MERC/CAPEX/2019-2020/734 | 2019-09-16 |  | 2019-09-16 |  | 2020-07-14 | 2021-09-16 |  | 2021-03-04 | 2.698 | 2.6466 |  | 0.051416 |  |  | 0.051416
0 | IDC | IDC | MERC/CAPEX/2019-2020/734 | 2019-09-16 |  | 2019-09-16 |  | - | - |  | - | 0.49 | 0 |  | 0.49 |  |  | 0.49
26 | Procurement, Replacement of Eco Coils U#1&2 210 MW, & Procurement & replacement of foundation Deck Spring assembly for coal mills U#3,4 at Khaperkheda TPS | DPR | MERC/CAPEX/2019-2020/853 | 2019-10-10 |  | 2019-10-10 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
26.1 | Procurement, Replacement of Eco Coils U#1&2 | Scheme | MERC/CAPEX/2019-2020/853 | 2019-10-10 |  | 2019-10-10 |  | 2019-10-16 | 2021-10-10 |  | 2022-01-15 | 7.4996 | 6.6503 |  | 0.84937 |  |  | 0.84937
26.2 | Procurement & replacement of foundation Deck Spring assembly for coal mills U#3,4 | Scheme | MERC/CAPEX/2019-2020/853 | 2019-10-10 |  | 2019-10-10 |  | 2022-03-08 | 2021-10-11 |  | - | 6.679 | 3.006 |  | 3.673 |  |  | 3.673
0 | IDC | IDC | MERC/CAPEX/2019-2020/853 | 2019-10-10 |  | 2019-10-10 |  | - | - |  | - | 1.23 | 0 |  | 1.23 |  |  | 1.23
28 | ESP Upgradation of 5 Nos. of 210/500MW Units at Khaperkheda, Koradi & Chandrapur TPS | DPR | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 |  | 2022-09-29 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
28.1 | ESP Upgradation at Unit #1, Khaperkheda TPS | Scheme | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 |  | 2022-09-29 |  | - | - |  | - | 42.7114 | 41.685 |  | 1.0264 |  |  | 1.0264
28.2 | ESP Upgradation at Unit #2, Khaperkheda TPS | Scheme | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 |  | 2022-09-29 |  | - | - |  | - | 42.7114 | 41.685 |  | 1.0264 |  |  | 1.0264
0 | IDC | IDC | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 |  | 2022-09-29 |  | - | - |  | - | 4.9307 | 0 |  | 4.9307 |  |  | 4.9307
29 | Flue Gas Desulphurisation System for Khaperkheda Unit # 1-4 | DPR | MERC/CAPEX/2021-2022/MSPGCL/097 | 2022-03-14 |  | 2022-03-14 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
29.1 | FGD System for Khaperkheda Unit # 1-4 | Scheme | MERC/CAPEX/2021-2022/MSPGCL/097 | 2022-03-14 |  | 2022-03-14 |  | 2022-03-29 | 2023-05-29 |  | - | 109.15 | 255.58 |  | -146.43 |  |  | -146.43
0 | IDC | IDC | MERC/CAPEX/2021-2022/MSPGCL/097 | 2022-03-14 |  | 2022-03-14 |  | - | - |  | - | 4.3065 | 0 |  | 4.3065 |  |  | 4.3065
HO DPR 4 | Construction of coal platform for Chandrapur TPS, Khaperkheda TPS & Parli TPS | DPR | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 |  | 2013-07-09 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 4.2 | Khaperkheda TPS | Scheme | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 |  | 2013-07-09 |  | - | - |  | - | 5.43 | 3.9936 |  | 1.4364 |  |  | 1.4364
0 | IDC | IDC | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 |  | 2013-07-09 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | DPR | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 |  | 2014-11-25 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 5.4a | 1. Procurement of 6.6 KV,300 KW, P.A.fan motor for U# 1 & 2 2. Procurement of 6.6 KV,425 KW,CM motor for U # 3 & 4 3. Procurement of 6.6 KV,1400KW,CW pump motor for U-1& 2 4. Procurement of 6.6 KV,1400 KW,CW pump motor for U-3&4 | Scheme | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 |  | 2014-11-25 |  | 2016-11-08 | 2016-11-25 |  | 2020-07-14 | 3.82 | 2.5973 |  | 1.2227 |  |  | 1.2227
HO DPR 5.4b | K'kheda: Procurement of HT Motors(GS/HP Water pump)for U-1&2 and Procurement of HT Motors (ACW)for U-3&4 | Scheme | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 |  | 2014-11-25 |  | 2019-08-21 | 2016-11-25 |  | 2021-02-26 | 1 | 0.4 |  | 0.6 |  |  | 0.6
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | DPR | MERC/CAPEX/20162017/00423 | 2016-08-03 |  | 2016-08-03 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 6.2 | KHAPERKHEDA (U-1 to 4) | Scheme | MERC/CAPEX/20162017/00423 | 2016-08-03 |  | 2016-08-03 |  | 2018-05-30 | 2018-03-08 |  | 2021-11-29 | 3.96 | 3.1173 |  | 0.84268 |  |  | 0.84268
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | DPR | MERC/CAPEX/20162017/00774 | 2016-09-30 |  | 2016-09-30 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 7.2 | Khaperkheda TPS | Scheme | MERC/CAPEX/20162017/00774 | 2016-09-30 |  | 2016-09-30 |  | - | - |  | - | 4.0552 | 0 |  | 4.0552 |  |  | 4.0552
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | DPR | MERC/CAPEX/20172018/4653 | 2017-11-13 |  | 2017-11-13 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender for KPKD 1-4 | Scheme | MERC/CAPEX/20172018/4653 | 2017-11-13 |  | 2017-11-13 |  | 2017-11-13 | 2019-11-13 |  | 2021-11-09 | 1.45 | 1.7765 |  | -0.3265 |  |  | -0.3265
HO DPR 8.2 | Normal Multipurpose Fire Tender KPKD 1-4 | Scheme | MERC/CAPEX/20172018/4653 | 2017-11-13 |  | 2017-11-13 |  | 2022-02-03 | 2019-11-13 |  | - | 1.25 | 2.1847 |  | -0.93465 |  |  | -0.93465
0 | IDC | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 |  | 2017-11-13 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 9 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | DPR | MERC/CAPEX/2017-18/0208 | 2018-02-08 |  | 2018-02-08 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 9.1 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | Scheme | MERC/CAPEX/2017-18/0208 | 2018-02-08 |  | 2018-02-08 |  | 2018-08-03 | 2019-11-08 |  | - | 226.3024 | 291.23 |  | -64.9276 |  |  | -64.9276
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | DPR | MERC/CAPEX/20172018/0177 | 2018-02-06 |  | 2018-02-06 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 10.2a | Compond wall (IB recommdation),Plant Patrolling Roads (IB recommdation) TPS KPKD | Scheme | MERC/CAPEX/20172018/0177 | 2018-02-06 |  | 2018-02-06 |  | 2019-02-04 | 2020-12-06 |  | 2020-01-21 | 4.4604 | 3.9506 |  | 0.50976 |  |  | 0.50976
HO DPR 11 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | DPR | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 |  | 2018-07-24 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 11.1 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | Scheme | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 |  | 2018-07-24 |  | 2019-02-25 | 2020-07-24 |  | 2021-11-07 | 9.05 | 13.3057 |  | -4.2557 |  |  | -4.2557
0 | IDC | IDC | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 |  | 2018-07-24 |  | - | - |  | - | 0.18 | 0 |  | 0.18 |  |  | 0.18
HO DPR 15 | Implementation of Water Flow Monitoring system at Chandrapur STPS & Khaperkheda TPS | DPR | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 |  | 2020-10-27 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 15.3 | Electromagnetic Flow meters at various lines & Locations of 210 MW | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 |  | 2020-10-27 |  | - | - |  | - | 3.8515 | 0 |  | 3.8515 |  |  | 3.8515
HO DPR 15.4 | Automation: Centralized SCADA, RTU, MODBUS Cable, Power cable & mandatory spares | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 |  | 2020-10-27 |  | - | - |  | - | 1.324 | 0 |  | 1.324 |  |  | 1.324
0 | IDC | IDC | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 |  | 2020-10-27 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
30 | Supply of spare Generator Rotor for UNIT 1 & 2, 210MW | DPR | MERC/CAPEX/2023-24/0184 | 2024-03-12 |  | 2024-03-12 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
30.1 | Supply of spare Generator Rotor for UNIT 1 & 2, 210MW | Scheme | MERC/CAPEX/2023-24/0184 | 2024-03-12 |  | 2024-03-12 |  | - | - |  | - | 36.7 | 36.7 |  | 0 |  |  | 0
0 | IDC | IDC | MERC/CAPEX/2023-24/0184 | 2024-03-12 |  | 2024-03-12 |  | - | - |  | - | 0.41 | 0 |  | 0.41 |  |  | 0.41
31 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M with raising of drain wells and modification of Masonary Dam (Waste Weir), 4 x210 MW, TPS, Khaperkheda | DPR | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 |  | 2023-10-09 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
31.1 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M at TPS, Khaperkheda. | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 |  | 2023-10-09 |  | - | - |  | - | 31.0231 | 0 |  | 31.0231 |  |  | 31.0231
31.2 | Raising of drain wells of Waregaon Ash Bund TPS, Khaperkheda. | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 |  | 2023-10-09 |  | - | - |  | - | 1.6569 | 0 |  | 1.6569 |  |  | 1.6569
31.3 | Modification of Masonary Dam (Waste Weir) of Waregaon Ash Bund TPS, Khaperkheda. | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 |  | 2023-10-09 |  | - | - |  | - | 10.1857 | 0 |  | 10.1857 |  |  | 10.1857
0 | IDC | IDC | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 |  | 2023-10-09 |  | - | - |  | - | 2.1878 | 0 |  | 2.1878 |  |  | 2.1878
32 | Flue Gas Desulphurisation (FGD) System for Khaperkheda Unit # 1 & 2 | DPR | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 |  | 2023-09-05 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
32.1 | Flue Gas Desulphurisation (FGD) System for Khaperkheda Unit # 1 & 2 | Scheme | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 |  | 2023-09-05 |  | - | - |  | - | 109.8 | 0 |  | 109.8 |  |  | 109.8
0 | IDC | IDC | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 |  | 2023-09-05 |  | - | - |  | - | 5.54 | 0 |  | 5.54 |  |  | 5.54
33 | Upgradation of DDC/DCS system for UNIT 1 & 3 of 210 MWKhaperkheda TPS | DPR | MERC/CAPEX/MSPGCL/2023-24/601 | 2023-11-10 |  | 2023-11-10 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
33.1 | Upgradation of DDC/DCS system for UNIT 1 & 3 of 210 MWKhaperkheda TPS | Scheme | MERC/CAPEX/MSPGCL/2023-24/601 | 2023-11-10 |  | 2023-11-10 |  | - | - |  | - | 38.7 | 0 |  | 38.7 |  |  | 38.7
0 | IDC | IDC | MERC/CAPEX/MSPGCL/2023-24/601 | 2023-11-10 |  | 2023-11-10 |  | - | - |  | - | 0.44 | 0 |  | 0.44 |  |  | 0.44
34 | Supply & commissioning of interconnection conveyor belt, Elecon make complete impact type crusher, Procurement of 4 NOs. Bull Dozer BEML BD-155 and Eco friendly and power efficient chiller system at Khaperkheda TPS | DPR | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 |  | 2024-02-27 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
34.1 | Design, engineering, manufacturing, supply, erection & commissioning of interconnection conveyor belt from 1 X 500MW to 4 X 210MW stack yard at CHP Khaperkheda TPS | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 |  | 2024-02-27 |  | - | - |  | - | 5.43 | 0 |  | 5.43 |  |  | 5.43
34.2 | Supply & installation of Elecon–make complete impact type crusher at CHP-I, Khaperkheda TPS | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 |  | 2024-02-27 |  | - | - |  | - | 4.29 | 0 |  | 4.29 |  |  | 4.29
34.3 | Procurement of 4 NOs. Bull Dozer BEML BD-155 at CHP, Khaperkheda TPS | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 |  | 2024-02-27 |  | - | - |  | - | 5.255 | 0 |  | 5.255 |  |  | 5.255
34.4 | Supply, erection, & commissioning of Eco friendly and power efficient chiller system for khaperkheda TPS Unit 1 to 4, Service Building and WTP in place of present reciprocating type Chiller system | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 |  | 2024-02-27 |  | - | - |  | - | 11.96 | 0 |  | 11.96 |  |  | 11.96
0 | IDC | IDC | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 |  | 2024-02-27 |  | - | - |  | - | 1.385 | 0 |  | 1.385 |  |  | 1.385
35 | 5 Nos. of Boiler Improvement Schemes for Unit No. 1 to 4 | DPR | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 |  | 2024-04-18 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
35.1 | Procurement & replacement of Re-Heater Rear Pendent Assembly Coils for unit no. 3 & 4 (210 MW) | Scheme | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 |  | 2024-04-18 |  | - | - |  | - | 8.86 | 0 |  | 8.86 |  |  | 8.86
35.2 | Procurement Complete Set of Sky Climber For Unit#1 To 5 Boilers. | Scheme | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 |  | 2024-04-18 |  | - | - |  | - | 3.32 | 0 |  | 3.32 |  |  | 3.32
35.3 | Replacement of glasswool insulation and GI/CORRUGATED sheets of boiler and hot air ducts at unit 1to 4 KHAPERKHEDA TPS | Scheme | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 |  | 2024-04-18 |  | - | - |  | - | 2.19 | 0 |  | 2.19 |  |  | 2.19
35.4 | Procurement, design, manufacture, supply & delivery, dismantling, retrofitting, erection, commissioning and testing of gravimetric belt conveyor type coal feeders for unit no. 1 & 2. | Scheme | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 |  | 2024-04-18 |  | - | - |  | - | 6.68 | 0 |  | 6.68 |  |  | 6.68
35.5 | Procurement and Replacement of Air Preheater Baskets for Unit no. 1 to 4 (4x 210MW). | Scheme | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 |  | 2024-04-18 |  | - | - |  | - | 9.05 | 2.7935 |  | 6.2565 |  |  | 6.2565
0 | IDC | IDC | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 |  | 2024-04-18 |  | - | - |  | - | 2.34 | 0 |  | 2.34 |  |  | 2.34
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | DPR | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 |  | 2022-02-12 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | Scheme | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 |  | 2022-02-12 |  | - | - |  | - | 54.24 | 0 |  | 54.24 |  |  | 54.24
0 | IDC | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 |  | 2022-02-12 |  | - | - |  | - | 2.76 | 0 |  | 2.76 |  |  | 2.76
HO DPR 16 | Centralized Monitoring Solution | DPR | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 |  | 2023-11-02 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
1 | Centralized Monitoring Solution | Scheme | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 |  | 2023-11-02 |  | - | - |  | - | 66.009 | 0 |  | 66.009 |  |  | 66.009
0 | IDC | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 |  | 2023-11-02 |  | - | - |  | - | 3.3 | 0 |  | 3.3 |  |  | 3.3
HO DPR-17 | Various DPR Schemes for The work of maintaining the zero discharge condition of Pond No. 2 & Pond No.3 and providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | DPR | MERC/CAPEX/2018-2019/1242 | 2018-09-22 |  | 2018-09-22 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 17.1 | The work of maintaining the zero discharge condition of Pond No.2 & Pond No.3 at KTPS Koradi | Scheme | MERC/CAPEX/2018-2019/1242 | 2018-09-22 |  | 2018-09-22 |  | - | - |  | - | 4.2068 | 0 |  | 4.2068 |  |  | 4.2068
HO DPR 17.2 | Providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | Scheme | MERC/CAPEX/2018-2019/1242 | 2018-09-22 |  | 2018-09-22 |  | - | - |  | - | 11.5375 | 0 |  | 11.5375 |  |  | 11.5375
2 | Scheme of HMI upgradation of unit 5 DCS along with Max Links , HART Scheme , PADO , all BOP PLCs , SWAS system, CO analyser & Coal feeder controller to match with the external aspect , process improvement & Up gradation of Generator Protections Relays in unit 1 to 4 of 210 MW at khaperkheda TPS | 0 | MERC/CAPEX/2024-2025/478 | 2024-08-06 |  | 2024-08-06 |  | - | - |  | - | 33.76 | 0 |  | 33.76 |  |  | 33.76
2.7 | Up-gradation of Generator Protections Relays in Unit 1 to 4 of 210 MW Khaperkheda TPS. | 0 | MERC/CAPEX/2024-2025/478 | 2024-08-06 |  | 2024-08-06 |  | - | - |  | - | 8.31 | 0 |  | 8.31 |  |  | 8.31
0 | IDC | 0 | MERC/CAPEX/2024-2025/478 | - |  | - |  | - | - |  | - | 0.86 | 0 |  | 0.86 |  |  | 0.86
Formulas:
Project Start Date = [MERC Approval Date]

## F4.2
|  |  | MSPGCL: Khaperkheda U # 1-4 | [16 empty] | 2
MTR Petition Formats - Generation
| Project Details |  | Form 4.2: Capitalisation Plan | [18 empty] | (Rs. Crore) | [19 empty] | (Rs. Crore)
Sr. No. | Project Code | DPR | MERC Approval No. | Date of Submission | MERC Approval Date | Cost as per DPR Crs. | MERC Approved Cost | Debt Equity Ratio | Grant Funding | Approved Start Date | Actual Start Date | Approved Date of Completion | Actual Date of Completion | Benefits in Quantified Terms | Capital Expenditure | [12 empty] | Physical Progress (%) | [6 empty] | Capitalisation | [12 empty] | Old Asset retired against capitalised item (in Rs. Cr) | Remarks | Current Status
[15 empty] | Actual Capex till FY 2018-19 | Actual | Actual | Actual | Actual Capex till FY 2021-22 | Actual | Actual | Revised Projected | projected | projected | projected | projected | projected | Actual Progress till FY 2018-19 | Actual | Actual | Actual | Actual | Actual | Revised Projected | Actual Capitalization till FY 2018-19 | Actual | Actual | Actual | Actual Capitalization till FY 2021-22 | Actual | Actual | Revised Projected | projected | projected | projected | projected | projected
[16 empty] | FY 2019-20 | FY 2020-21 | FY 2021-22 |  | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 |  | FY 2019-20 | FY 2020-21 | FY 2021-22 | FY 2022-23 | FY 2023-24 | FY 2024-25 |  | FY 2019-20 | FY 2020-21 | FY 2021-22 |  | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30
[50 empty] | N.A. | DPR | Not Initiated
| A) DPR Schemes | [48 empty] | N.A. | Scheme | WIP
| (i) Submitted to MERC | [48 empty] | N.A. | IDC | Partially Capitalised
1 | Combustion optimization system | DPR | MERC/CAP/DPR/10/2010-11/1491 | 2010-09-13 | 2010-10-29 | 10.743 | 10.743 |  |  | 2010-10-29 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A. | Non-DPR | Capitalised
1.1 | Dynamic coal flow measurement and control (balancing) system (one) | Scheme | MERC/CAP/DPR/10/2010-11/1491 | 2010-09-13 | 2010-10-29 | 8.17 | 8.17 |  |  | 2010-10-29 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | Cancelled |  | Cancelled
1.2 | CO analyser (8 units) | Scheme | MERC/CAP/DPR/10/2010-11/1491 | 2010-09-13 | 2010-10-29 | 1.19 | 1.19 |  |  | 2010-10-29 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | Cancelled |  | To be cancelled
1.3 | Oxygen analyser (32 units) | Scheme | MERC/CAP/DPR/10/2010-11/1491 | 2010-09-13 | 2010-10-29 | 0.783 | 0.783 |  |  | 2010-10-29 |  |  |  |  | 0.75683 |  |  |  | 0.75683 | [15 empty] | 0.75683 |  |  |  | 0.75683 | [10 empty] | Capitalised |  | N.A.
| IDC | IDC | MERC/CAP/DPR/10/2010-11/1491 | 2010-09-13 | 2010-10-29 | 0.6 | 0.6 |  |  | 2010-10-29 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A. |  | To be confirmed
2 | Spare HPT module for Khaparkheda Unit 1 & 2 | DPR | MERC/CAP/DPR/10/2010-11/1466 | 2010-08-18 | 2010-10-26 | 26.459 | 26.459 |  |  | 2010-10-26 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
2.1 | HPT module 1 No (unit # 1) | Scheme | MERC/CAP/DPR/10/2010-11/1466 | 2010-08-18 | 2010-10-26 | 23.0379 | 23.0379 |  |  | 2010-10-26 |  |  |  |  | 23.9074 |  |  |  | 23.9074 | [15 empty] | 23.9074 |  |  |  | 23.9074 | [10 empty] | Capitalised
| IDC | IDC | MERC/CAP/DPR/10/2010-11/1466 | 2010-08-18 | 2010-10-26 | 3.4211 | 3.4211 |  |  | 2010-10-26 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
3 | Economiser Upper Bank & Lower Bank coils for Khaperkheda Unit no. 3 and Unit no. 4 | DPR | MERC/CAP/DPR/10/2010-11/1695 | 2010-11-23 | 2010-12-15 | 26.35 | 26.35 |  |  | 2010-12-15 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
3.1 | Economiser Upper Bank & Lower Bank coils for Khaperkheda Unit no. 3 and Unit no. 4 | Scheme | MERC/CAP/DPR/10/2010-11/1695 | 2010-11-23 | 2010-12-15 | 26.35 | 26.35 |  |  | 2010-12-15 |  |  |  |  | 11.77 |  |  |  | 11.77 | [15 empty] | 11.77 |  |  |  | 11.77 | [10 empty] | Capitalised
4 | Economiser & LTSH Upper Bank & Lower Bank coils for Khaperkheda Unit no. 1 and Unit no. 2 | DPR | MERC/CAPEX/20112012/01155 | 2011-03-28 | 2011-07-29 | 34.7916 | 34.7916 |  |  | 2011-07-29 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
4.1 | Economiser & LTSH Coil for Unit 1 | Scheme | MERC/CAPEX/20112012/01155 | 2011-03-28 | 2011-07-29 | 15.6924 | 15.6924 |  |  | 2011-07-29 |  |  |  |  | 15.6924 |  |  |  | 15.6924 | [15 empty] | 15.6924 |  |  |  | 15.6924 | [10 empty] | Capitalised
4.2 | Economiser & LTSH Coil for Unit 2 | Scheme | MERC/CAPEX/20112012/01155 | 2011-03-28 | 2011-07-29 | 16.1528 | 16.1528 |  |  | 2011-07-29 |  |  |  |  | 16.1528 |  |  |  | 16.1528 | [15 empty] | 16.1528 |  |  |  | 16.1528 | [10 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/20112012/01155 | 2011-03-28 | 2011-07-29 | 2.9464 | 2.9464 |  |  | 2011-07-29 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
5 | Procurement & Replacement of Re-heater Rear Pendant Assembly Coils for 2*210MW Khaperkheda Unit no. 1 and Unit no. 2 | DPR | MERC/CAPEX/20122013/00603 | 2012-01-10 | 2012-06-18 | 10.3738 | 10.3738 |  |  | 2012-06-18 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
5.1 | Re-heater coils for unit no. 1 | Scheme | MERC/CAPEX/20122013/00603 | 2012-01-10 | 2012-06-18 | 5.1267 | 5.1267 |  |  | 2012-06-18 |  |  |  |  | 5.1267 |  |  |  | 5.1267 | [15 empty] | 5.1267 |  |  |  | 5.1267 | [10 empty] | Capitalised
5.2 | Re-heater coils for unit no. 2 | Scheme | MERC/CAPEX/20122013/00603 | 2012-01-10 | 2012-06-18 | 5.1267 | 5.1267 |  |  | 2012-06-18 |  |  |  |  | 5.55 |  |  |  | 5.55 | [15 empty] | 5.55 |  |  |  | 5.55 | [10 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/20122013/00603 | 2012-01-10 | 2012-06-18 | 0.1204 | 0.1204 |  |  | 2012-06-18 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
6 | Procurement of HPT module suitable for khaperkheda TPS Unit 3 & 4 | DPR | MERC/TECH-1/CAPEX/ 20132014/02001 | 2013-06-19 | 2014-01-17 | 36.2 | 36.2 |  |  | 2014-01-17 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
6.1 | Procurement of HPT module suitable for khaperkheda TPS Unit 3 & 4 | Scheme | MERC/TECH-1/CAPEX/ 20132014/02001 | 2013-06-19 | 2014-01-17 | 36.2 | 36.2 |  |  | 2014-01-17 |  |  |  |  | 32.4016 |  |  |  | 32.4016 | [15 empty] | 32.4016 |  |  |  | 32.4016 | [10 empty] | Capitalised
7 | Procurement Spare GTR, Locomotive & Compactors | DPR | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-03-18 | 2014-05-20 | 18.4521 | 18.4521 |  |  | 2014-05-20 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
7.1 | 250 MVA Spare GTR | Scheme | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-03-18 | 2014-05-20 | 10.3496 | 10.3496 |  |  | 2014-05-20 |  |  |  |  | 11.2511 |  |  |  | 11.2511 | [15 empty] | 11.2511 |  |  |  | 11.2511 | [10 empty] | Capitalised
7.2 | Procurement of Locomotive 2no’s. | Scheme | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-03-18 | 2014-05-20 | 5.9927 | 5.9927 |  |  | 2014-05-20 |  |  |  |  | 5.9927 |  |  |  | 5.9927 | [15 empty] | 5.9927 |  |  |  | 5.9927 | [10 empty] | Capitalised
7.3 | Procurement of Compactors 2 no’s. | Scheme | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-03-18 | 2014-05-20 | 0.42979 | 0.42979 |  |  | 2014-05-20 |  |  |  |  | 0.4298 |  |  |  | 0.4298 | [15 empty] | 0.4298 |  |  |  | 0.4298 | [10 empty] | Capitalised
| IDC | IDC | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-03-18 | 2014-05-20 | 1.68 | 1.68 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
8 | Procurement & Replacement of complete set of LTSH coils for Khaperkheda TPS Unit 3&4 | DPR | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-03-12 | 2014-05-20 | 17.81 | 17.81 |  |  | 2014-05-20 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
8.1 | Procurement and replacement of LTSH coils for Khaperkheda TPS at U3 | Scheme | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-03-12 | 2014-05-20 | 8.58 | 8.58 |  |  | 2014-05-20 | 2015-04-28 | 2017-05-20 | 2016-08-24 | 1. Saving in the generation loss of @ 30 MUs per year for both the units. This will increase in PLF from 80.005 % to 80.505 (Percentage loss in generation due to boiler tube failure will be reduced by 0.5% i.e. by 30 MUs per year.) 2. Saving in Fuel oil consumption of @ 64 KL LDO & @54 KL FO for both the units. 3. DM consumption saving @ 324 KL for both the units (due to reduction in BTL). 4. Total tube failure at LTSH zone will be reduced. 5. Concentrated and localized flue gas erosion will be reduced. 6. Perfect alignment and locking of modules of LTSH will be achieved. 7. Uniform flue gas configuration will be achieved at LTSH. | 3.4291 |  |  |  | 3.4291 | [15 empty] | 3.4291 |  |  |  | 3.4291 | [10 empty] | Capitalised
8.2 | Procurement and replacement of LTSH coils for Khaperkheda TPS at U4 | Scheme | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-03-12 | 2014-05-20 | 8.58 | 8.58 |  |  | 2014-05-20 | 2017-01-21 | 2017-05-20 | 2017-09-05 | 1. Saving in the generation loss of @ 30 MUs per year for both the units. This will increase in PLF from 80.005 % to 80.505 (Percentage loss in generation due to boiler tube failure will be reduced by 0.5% i.e. by 30 MUs per year.) 2. Saving in Fuel oil consumption of @ 64 KL LDO & @54 KL FO for both the units. 3. DM consumption saving @ 324 KL for both the units (due to reduction in BTL). 4. Total tube failure at LTSH zone will be reduced. 5. Concentrated and localized flue gas erosion will be reduced. 6. Perfect alignment and locking of modules of LTSH will be achieved. 7. Uniform flue gas configuration will be achieved at LTSH. | 3.1809 |  |  |  | 3.1809 | [15 empty] | 3.1809 |  |  |  | 3.1809 | [10 empty] | Capitalised
| IDC | IDC | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-03-12 | 2014-05-20 | 0.65 | 0.65 |  |  | 2014-05-20 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
9 | Development of Ash Bund (Waregaon) at K'kheda TPS | DPR | MERC/TECH 1/CAPEX/20132014/00823 | 2012-06-14 | 2013-07-09 | 38.7459 | 38.7459 |  |  | 2013-07-09 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
9.1 | Construction of 3rd upstream raising of existing ash bund from TBL 299.50 Mtr to 302.50 Mtr at Waregaon, Khaperkheda TPS. | Scheme | MERC/TECH 1/CAPEX/20132014/00823 | 2012-06-14 | 2013-07-09 | 33.8585 | 33.8585 |  |  | 2013-07-09 | 2015-06-12 | 2016-12-17 | 2019-08-05 | Due to raising of ash bund from 299.50 ml to TBL 302.5, capacity of ash bund to accommodate ash will be enhanced. It would be feasible to store ash for next 5 years approximately. The stability of bund will be maintained, and generation loss due to unavailability of storage space for ash will be avoided. | 30.1381 | 2.3994 |  |  | 32.5375 | [15 empty] | 30.1381 | 2.3994 |  |  | 32.5375 | [10 empty] | Capitalised
9.2 | Construction of masonary dam (Gabion structure) at Waregaon TPS, Khaperkheda. | Scheme | MERC/TECH 1/CAPEX/20132014/00823 | 2012-06-14 | 2013-07-09 | 1.0561 | 1.0561 |  |  | 2013-07-09 | 2015-06-12 | 2016-12-17 | 2019-08-05 | Due to raising of ash bund from 299.50 ml to TBL 302.5, capacity of ash bund to accommodate ash will be enhanced. It would be feasible to store ash for next 5 years approximately. The stability of bund will be maintained, and generation loss due to unavailability of storage space for ash will be avoided. |  |  |  |  | 0 | [19 empty] | 0 | [10 empty] | Capitalised
9.3 | Construction of approach to drain wells and raising height of drain well no. 1,2 & 3 ash bund at Waregaon, Khaperkheda TPS | Scheme | MERC/TECH 1/CAPEX/20132014/00823 | 2012-06-14 | 2013-07-09 | 0.48488 | 0.48488 |  |  |  | 2015-06-12 | 2016-12-17 | 2019-08-05 | Due to raising of ash bund from 299.50 ml to TBL 302.5, capacity of ash bund to accommodate ash will be enhanced. It would be feasible to store ash for next 5 years approximately. The stability of bund will be maintained, and generation loss due to unavailability of storage space for ash will be avoided. |  |  |  |  | 0 | [19 empty] | 0 | [10 empty] | Capitalised
| IDC | IDC | MERC/TECH 1/CAPEX/20132014/00823 | 2012-06-14 | 2013-07-09 | 3.3464 | 3.3464 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
10 | Various schemes related to CHP Improvement & Performance Optimization and scheme of conversion of existing Composite OHE to Conventional OHE | DPR | MERC/CAPEX/20152016/00422 | 2015-09-08 | 2016-08-03 | 11.03 | 10.76 |  |  | 2016-08-03 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
10.1 | Air Cooled Suspension Magnet for Con. 3 & 6 of CHP 210 MW | Scheme | MERC/CAPEX/20152016/00422 | 2015-09-08 | 2016-08-03 | 2.43 | 2.18 |  |  | 2016-08-03 | 2018-03-01 | 2019-08-03 | 20/10/19 | • CHP performance will be improved. • Quality / Service / Reliability Improvement • System availability & reliability will be improved. • Process Efficiency Improvement • Process Efficiency will be improved due to more attracting forces of magnet. • Impact of improvements on plant parameters • Coal mill outage & generation loss can be minimized. | 2.2613 |  |  |  | 2.2613 | [15 empty] | 0 | 2.2613 |  |  | 2.2613 | [9 empty] | Here actual investment is more than aprroved cost due to the rise in rates over a period from actual preparation of estimate while DPR preparation to the actaul PO placement. Impact of GST is also the reason since 18 to 28% GST is came in force w.e.f July'2017 instead of 5% VAT or 15% service tax. | Capitalised
10.2 | Procurement of Impact crusher motor | Scheme | MERC/CAPEX/20152016/00422 | 2015-09-08 | 2016-08-03 | 0.84 | 0.84 |  |  | 2016-08-03 | 2017-01-02 | 2019-08-03 | 2017-08-03 | • Availability of crusher will be improved. • Quality / Service / Reliability Improvement • System availability & reliability will be improved. • Process Efficiency Improvement • Bunkering will improve due to availability of crusher. • Impact of improvements on plant parameters • Generation loss can be minimized. | 0.52579 |  |  |  | 0.52579 | [15 empty] | 0.52579 |  |  |  | 0.52579 | [10 empty] | Capitalised
10.3 | Procurement of 360V, 200 AH battery set and 360V 325 AH battery set for U# 1to 4 | Scheme | MERC/CAPEX/20152016/00422 | 2015-09-08 | 2016-08-03 | 1.1 | 1.1 |  |  | 2016-08-03 | 2018-06-14 | 2019-08-03 | 18/12/20 | The projected benefits by implementation of these schemes are as under: • 100% availability of auxiliaries. • Generation loss incurred due to non-availability of auxiliaries may be avoided. | 1.4109 | 0.046728 |  |  | 1.4576 | [15 empty] | 0 | 1.0473 | 0.41032 |  | 1.4576 | [9 empty] | Here actual investment is more than aprroved cost due to the rise in rates over a period from actual preparation of estimate while DPR preparation to the actaul PO placement. Impact of GST is also the reason since 18 to 28% GST is came in force w.e.f July'2017 instead of 5% VAT or 15% service tax. | Capitalised
10.4 | Procurement of POG Instruments for Unit 1 to 4 | Scheme | MERC/CAPEX/20152016/00422 | 2015-09-08 | 2016-08-03 | 0.77 | 0.77 |  |  | 2016-08-03 | 2017-04-01 | 2019-08-03 | 20/03/18 | The tangible benefit by adopting this practice cannot be worked out, but the instant availability of the analyzer for analysis will be useful for early detection of the fault and avoid further damages to the equipment. The use of such equipment will be also useful for enhancing the analytical analysis capacity among the employee’s. The performance trending of the poor performing equipment can be done which will help in decision making process. A0 & A3 size scanners are helpful for scanning of the technical drawings and manuals & store them in digital soft copy for ready reference of O&M staff & correspondence in electronic form which results in reduction in paper consumption. | 0.35015 |  |  |  | 0.35015 | [15 empty] | 0.35015 |  |  |  | 0.35015 | [9 empty] | Procurement of Digital flow meter and Power Analyser is cancelled | Capitalised
10.5 | Up gradation of safe scan flame scanner system by BHEL scan system in unit no. 1, 3 & 4 | Scheme | MERC/CAPEX/20152016/00422 | 2015-09-08 | 2016-08-03 | 1.35 | 1.35 |  |  |  | cancelled | 2019-08-03 | cancelled | scheme is cancelled | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
10.6 | Up gradation of old AVR system to DAVR | Scheme | MERC/CAPEX/20152016/00422 | 2015-09-08 | 2016-08-03 | 1.33 | 1.33 |  |  |  | cancelled | 2019-08-03 | cancelled | scheme is cancelled | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
10.7 | Conversion of existing Composite OHE to Conventional OHE | Scheme | MERC/CAPEX/20152016/00422 | 2015-09-08 | 2016-08-03 | 2.72 | 2.72 |  |  | 2016-08-03 | 2016-08-03 | 2019-08-03 | 2017-03-31 | Requirement of Railway department | 2.72 |  |  |  | 2.72 | [15 empty] | 2.72 |  |  |  | 2.72 | [10 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/20152016/00422 | 2015-09-08 | 2016-08-03 | 0.49 | 0.47 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
11 | ESP up-gradation for Unit-1 at Khaperkheda TPS | DPR | MERC/CAPEX/20152016/01261 | 2015-10-21 | 2016-01-11 | 32.01 | 32.01 |  |  | 2016-01-11 |  | 2018-03-31 | [6 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
11.1 | ESP up-gradation for Unit-1 at Khaperkheda TPS | Scheme | MERC/CAPEX/20152016/01261 | 2015-10-21 | 2016-01-11 | 32.01 | 32.01 |  |  | 2016-01-11 |  | 2018-03-31 |  |  | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [9 empty] | Short closed by HO.Please be confirm from CE (Works) | Cancelled
13 | Procurement, installation and commissioning of Gravimetric Belt / Rotary Type Feeder, VFD for CEP, Up-gradation of BTS system & Environmental schemes at Khaperkheda TPS | DPR | MERC/CAPEX/20162017/01552 | 2016-11-15 | 2017-02-14 | 20.21 | 20.218 |  |  | 2017-02-14 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
13.1 | Procurement, installation and commissioning of Gravimetric belt/rotary Feeder at U-1 & 2 | Scheme | MERC/CAPEX/20162017/01552 | 2016-11-15 | 2017-02-14 | 5.72 | 5.72 |  |  | 2017-02-14 | 2018-01-20 | 2020-02-14 | 2019-09-07 | The projected benefits by implementation of scheme under Procurement design, manufacture, supply & delivery, dismantling, retrofitting; erection, testing and commissioning of belt conveyor feeders for unit no. 1 & 2 Benefits achieved by implementing proposed scheme are as follows: There will be no chocking in the feeder in case of wet & sticky coal. There is nearly zero breakdown of feeder. The feeders are operating with consistent gravimetric Feed & with the accuracy in feeding. There will be improvement in mill operation giving better and uniform pulverization of coal. Improved combustion and boiler performance will be achieved. Improved Emission due to improvement in combustion will be achieved. Due to high availability of the feeder, the plant will be able to improve PLF. Coal dust leakage from coal feeders will be completely eliminated after installation of these feeders and strategically located observation ports provide excellent unobstructed views of the inside of the feeder. Therefore, it will be easy to carry out the maintenance if required. | 4.7418 |  |  |  | 4.7418 | [15 empty] | 2.37 | 2.3718 |  |  | 4.7418 | [10 empty] | Capitalised
13.2 | Installation of VFD to CEP at U-1 to 4 | Scheme | MERC/CAPEX/20162017/01552 | 2016-11-15 | 2017-02-14 | 8.64 | 8.64 |  |  | 2017-02-14 | 2019-05-21 | 2020-02-14 |  | The projected benefits by implementation of the scheme 1. APC of Khaperkheda TPS in MUs consumed would go down by at least 120 KWH ---Per CEP. 2. The earnings would increase by at least 34.27 Lacs every year (for single 210 MW unit), as guaranteed in offer document. 3. The VFD provides soft start to the pump avoiding starting jerks caused currently. 4. The Power Factor would improve to around 0.95 as against 0.84 as of now. 5. The vibration levels of CEP would go down as the 1X would reduce on reduced RPM. 6. The life of CEP and its motor would increase as the wear and tear of a pump is squarely proportional to the speed of the pump and the pump would always run on lower RPM than earlier. 7. Life of flow control valve, CD 17 and discharge line up to this valve would improve as the pressure would reduce in the piping as well as valve. | 0 | 1.9027 |  |  | 1.9027 | 0.38326 | 5.7082 | 0.76326 | 0.38326 | [11 empty] | 0 |  |  |  | 0 | 2.2949 | 2.4584 | 2.2949 | 2.0918 | [5 empty] | Cost overrun is due to changes in tax slab from 5% VAT/ 15% service tax to 18% GST at the time of actual PO placement compare to approved DPR estimate.Unit 4 Work completed and capitalised in FY 2022-23 ,Unit #2 Work completed and capitalised in FY 2023-24, Unit#3 Work will be completed in FY 2024-25 during scheduled AOH in August 2024.& remaining Unit #1 work will be completed in FY 2025-26 during Unit #1 AOH | Partially Capitalised
13.3 | Installation of BTS system at U-4 | Scheme | MERC/CAPEX/20162017/01552 | 2016-11-15 | 2017-02-14 | 0.98 | 0.98796 |  |  | 2017-02-14 | 2018-10-16 | 2020-02-14 | 2019-08-11 | Technical Improvements: • Improvement in Operational Performance. • Improvement in Process Performance. • Improvement in System reliability. • Improvement in monitoring of continuous Breaker Trip & Close circuits. • The system has standard communication Protocol. • The system has advanced Software tools for virtual testing, transfer event upload & SOE facility. Quality / Service / Reliability Improvement: Quality / Service / Reliability of the system will improve. Process Efficiency Improvement: No direct relation with process efficiency, as per CPRI guidelines latest technology systems need to be installed for improvement in reliability and performance optimization. Also any tripping due to non availability of this system will be avoided. | 0.87172 | 0.11623 |  |  | 0.98796 | [15 empty] | 0 | 0.98796 |  |  | 0.98796 | [10 empty] | Capitalised
13.4 | Replacement of SOx/NOx analyzer at U-1 to 4 | Scheme | MERC/CAPEX/20162017/01552 | 2016-11-15 | 2017-02-14 | 2.42 | 2.42 |  |  | 2017-02-14 | 2018-03-01 | 2020-02-14 | 2019-03-31 | The system provides following Key Advantages: Above scheme is Mandatory for On-Line measurement of SO2 / NOx of Flue Gas as per MPCB Rules of Regulation & Environment Compliance. It helps to monitor Pollutant Emission. To monitor Quality of Combustion. Quality / Service / Reliability Improvement: • It is Mandatory for On-Line measurement of SO2 / NOx of Flue Gas as per MPCB Rules of Regulation & Environment Compliance. Process Efficiency Improvement: • Process Improvement in Operation Procedures & Decision. | 2.3035 |  |  |  | 2.3035 | [15 empty] | 2.3035 |  |  |  | 2.3035 | [10 empty] | Capitalised
13.5 | Procurement of TGA,CHNS analyzer and Bomb calorimeter at U-5 | Scheme | MERC/CAPEX/20162017/01552 | 2016-11-15 | 2017-02-14 | 1.71 | 1.71 |  |  | 2017-02-14 | 2017-04-01 | 2020-02-14 | 2018-03-31 | • More accurate and reliable analysis of proximate and ultimate parameters of received / blended coal • No heat radiation to operator • Simple and convenient operation technology • Reduced analysis time • Achieving better control over process controlling operational parameters • Precise combustion optimization due to pre-intimation of quality of coal. • Useful for process optimization of boiler efficiency. • Indirect improvement in heat rate. • Availability of qualitative and quantitative fuel data bank for evaluation of present and future performance level and gap analysis. • Slagging, fouling and fireside corrosion can be avoided by knowing exact nature of fuel. • Fuel saving by optimizing excess air. • Flawless analysis results will be possible to endure at controversial circumstances. | 0.2897 |  |  |  | 0.2897 | [15 empty] | 0.2897 |  |  |  | 0.2897 | [9 empty] | TGA AND CHNS ANALYSER IS CANCELLED AND BOMB CALORIMETER IS CAPITALISED | Capitalised
| IDC | IDC | MERC/CAPEX/20162017/01552 | 2016-11-15 | 2017-02-14 | 0.74 | 0.74 |  |  | 2017-02-14 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
16 | Up gradation of HMI System at Unit No 3 & 4 at Khaperkheda TPS | DPR | MERC/CAPEX/20172018/03946 | 2017-05-20 | 2017-07-19 | 13.39 | 13.39 |  |  | 2017-07-19 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
16.1 | HMI Up-gradation at U# 3 & 4 | Scheme | MERC/CAPEX/20172018/03946 | 2017-05-20 | 2017-07-19 | 12.78 | 12.78 |  |  | 2017-07-19 | 2018-05-18 | 2019-07-19 |  | The benefits achieved by implementation of above schemes are as follows: • Main two alpha servers will now be replaced by new Intel core 2 Duo or equivalent Processor. • Spares will be available for Servers and Workstations. • Spares will be available for functional keyboards. • Spares will be available for VME rack electronic cards. (Interconnection between DCS and WSPOSE system) | 12.5611 |  |  |  | 12.5611 | [15 empty] | 0 |  | 6.2805 |  | 6.2805 | 6.2805 |  | 0.62 | [6 empty] | Cost overrun is due to changes in tax slab from 5% VAT/ 15% service tax to 18% GST at the time of actual PO placement compare to approved DPR estimate. | Partially Capitalised
| IDC | IDC | MERC/CAPEX/20172018/03946 | 2017-05-20 | 2017-07-19 | 0.61 | 0.61 |  |  | 2017-07-19 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
21 | Procurement of APH Basket for unit # 1 to 5 and Up-gradation of HT Motor Protection Relay in Unit # 1 to 4 at Khaperkheda TPS | DPR | MERC/CAPEX/2018-2019/105 | 2018-08-23 | 2019-04-05 | 9.77 | 9.77 |  |  | 2019-04-05 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
21.1 | Procurement of assembly of baskets for air preheater of type bisector APH 27 VI: 1850, 12 sector in unit no. 1 & 2 and bisector APH 27 VI: 2000; 24 sector in unit no. 3 & 4 (210MW x 4) at TPS, Khaperkheda | Scheme | MERC/CAPEX/2018-2019/105 | 2018-08-23 | 2019-04-05 | 5.71 | 5.71 |  |  | 2019-04-05 | 2019-05-23 | 2021-04-05 |  | *improvement in flue gas temperature & pressure *improvement in boiler efficiency by reducing heat rate by 6 -10Kcal/KWhr *To reduce APC | 0 | 3.35 | 1.7626 |  | 5.1126 | 2.9843 | [14 empty] | 0 | 1.6195 | 1.7277 |  | 3.3472 | 2.1347 | 2.6123 | [8 empty] | Capitalised
21.3 | Up-gradation of H.T. Motor protection relays in Unit 1 to 4 (210MW), Khaperkheda TPS | Scheme | MERC/CAPEX/2018-2019/105 | 2018-08-23 | 2019-04-05 | 3.96 | 3.96 |  |  | 2019-04-05 | 31.12.2020 | 2021-04-05 |  | *To avoid cost of failure of HT motors protection relays. *precise setting can be incorporated to protect HT motors with new relays *The new age motor protection relays will cover all motor protection required for HT/LT motor feeders and give accurate and reliable operation of relay to protect motor for future period. *The new age numerical relays provide easy fault finding solution. It also gives history data for better fault analysis. Hence there is System improvement only | 0 |  |  | 2.9881 | 2.9881 | 0.12555 |  | 0.14 | [12 empty] | 0 |  |  | 2.9881 | 2.9881 | 0.12555 |  | 0.14 | [7 empty] | Partially Capitalised
| IDC | Scheme | MERC/CAPEX/2018-2019/105 | 2018-08-23 | 2019-04-05 | 0.1 | 0.1 |  |  | 2019-04-05 | [8 empty] | 0 | [19 empty] | 0 |  | 0.18424 | [8 empty] | N.A.
22 | Procurement of LPT rotor suitable for Unit # 3 & 4 of 210 MW at Khaperkheda TPS | DPR | MERC/CAPEX/2018-2019/132 | 2018-09-21 | 2019-05-09 | 27.191 | 27.191 |  |  | 2019-05-09 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
22.1 | Procurement of LPT rotor suitable for Unit # 3 & 4 of 210 MW at Khaperkheda TPS | Scheme | MERC/CAPEX/2018-2019/132 | 2018-09-21 | 2019-05-09 | 26.491 | 26.491 |  |  | 2019-05-09 | 2020-04-07 | 2021-05-09 |  | * improvement in heat rate by 10 kcal/kwhr *improvement in PLF *AVAILIBILITY & RELIABILITY of plant increased | 0 |  |  |  | 0 | 10.7515 | [14 empty] | 0 |  |  |  | 0 |  | 10.7515 | [7 empty] | .CAPITALISED IN FY 2023-24 | Capitalised
| IDC | IDC | MERC/CAPEX/2018-2019/132 | 2018-09-21 | 2019-05-09 | 0.7 | 0.7 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
23 | Supply, Erection & commissioning of HT Vacuum circuit Breakers & SF6 contactors at AHP (U#1-4) & CHP (U#1 to 5) and 160 KW VFD Panel with Motor for fire-fighting pumps at U#1 to 4 at Khaperkheda TPS | DPR | MERC/CAPEX/2019-2020/799 | 2019-04-03 | 2019-09-27 | 10.93 | 10.9 |  |  | 2019-09-27 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
23.1 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at AHP (Unit#1 to 4, 210MW), Khaperkheda T.P.S. | Scheme | MERC/CAPEX/2019-2020/799 | 2019-04-03 | 2019-09-27 | 4.17 | 4.17 |  |  | 2019-09-27 | 2021-01-22 | 2021-09-27 |  | 1. Overall reliability of power plant will be increased due to 100% availibility of breakers 2. Life of breaker system will be enhanced. |  |  |  | 3.1199 | 3.1199 | 0.36441 | [18 empty] | 0 | 4.8883 | [9 empty] | Capitalised
23.2 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at CHP (Unit#1 to 4, 210MW) and CHP (Unit#5, 500MW) Khaperkheda T.P.S. | Scheme | MERC/CAPEX/2019-2020/799 | 2019-04-03 | 2019-09-27 | 3.81 | 3.81 |  |  | 2019-09-27 | 2021-01-22 | 2021-09-27 |  | 1. Overall reliability of power plant will be increased due to 100% availibility of breakers 2. Life of breaker system will be enhanced. |  |  |  | 1.2978 | 1.2978 | 2.5244 | 0.20886 | [17 empty] | 0 |  | 2.7332 | [8 empty] | Capitalised
23.3 | Supply, Erection & commissioning of 150 KW VFD Panel with motor for fire-fighting pumps at 210 MW Khaperkheda TPS. | Scheme | MERC/CAPEX/2019-2020/799 | 2019-04-03 | 2019-09-27 | 2.34 | 2.34 |  |  | 2019-09-27 | 2021-09-29 | 2021-09-27 |  | 1. 100% availibility of fie hydrant pumps 2.VFD control the starting high currrent & provide soft starting 3. VFD provides energy saving during flow control by avoiding throttling lossed. 4. Motor & motor coupling life will get enhanced |  |  |  |  | 0 | 1.9968 | 0.09888 | [17 empty] | 0 |  | 2.0957 | [8 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/2019-2020/799 | 2019-04-03 | 2019-09-27 | 0.61 | 0.58 |  |  | 2019-09-27 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
24 | Augmentation of Waregaon Ash Water Recovery System at TPS Khaperkheda | DPR | MERC/CAPEX/2019-20/732 | 2019-05-30 | 2019-09-16 | 14.1258 | 17.1984 |  |  | 2019-09-16 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
24.1 | Augmentation of Waregaon Ash Water Recovery System at TPS Khaperkheda | Scheme | MERC/CAPEX/2019-20/732 | 2019-05-30 | 2019-09-16 | 12.1658 | 15.7884 |  |  | 2019-09-16 | 2020-07-17 | 2021-09-16 |  | 1. Raw water consumption of Kpkd plant will be reduced. 2. MoEFCC norms will be achieved 3. Ash management will be easier due to efficient ash water recovery 4. Recovered water can be reused fot various work within plant |  |  | 1.6297 | 6.4145 | 8.0442 | 5.8872 |  | 1.2672 | [16 empty] | 0 | 13.9315 |  | 1.2672 | [7 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/2019-20/732 | 2019-05-30 | 2019-09-16 | 1.96 | 1.41 | [11 empty] | 0 | 0.58812 | [18 empty] | 0 | 0.58812 | [9 empty] | N.A.
25 | Procurement of VFD with HMI & Controller & Replacing with existing Eddy-current drives of Coal feeders at U# 3 & 4 and Procurement of Various Critical Components of GEHO Pump (Model-TZPM 800) for AHP-1 at Khaperkheda TPS | DPR | MERC/CAPEX/2019-2020/734 | 2019-07-20 | 2019-09-16 | 10.6535 | 10.6535 |  |  | 2019-09-16 |  |  |  | • Improvement in Operational Performance. • Improvement in Process Performance. • Improvement in System availability and reliability. • Reduction in power consumption. |  |  |  |  | 0 | [19 empty] | 0 | [10 empty] | N.A.
25.1 | Up-gradation of Existing BHEL make 36” Gravimetric Coal Feeders control panel with HMI and croprocessor based Controller with VFD, Motor & Weigh Module at Unit 3 & 4, (210MW) | Scheme | MERC/CAPEX/2019-2020/734 | 2019-07-20 | 2019-09-16 | 7.4655 | 7.4655 |  |  | 2019-09-16 |  | 2021-09-16 |  | 1. Maintenance & caliberation time of CF will be reduced 2.Power consumtion will be reduced due to replacing of eddy current drives by VFD controlled drives. 3.CF outages will be reduced & service will be improved. 4.All field & system related data will be available on HMI hence relibility of CF will be increased. 5.Direct improvement in process efficiency as less breakdown will occur and power saving. All field and system related data will be available on HMI. |  |  |  |  | 0 |  |  | 3.85 | 3.85 | [15 empty] | 0 |  |  | 3.85 | 3.85 | [6 empty] | WIP
25.2 | Procurement of various Critical Components of GEHO Pump (Model-TZPM 800) for AHP-1 (210MW) | Scheme | MERC/CAPEX/2019-2020/734 | 2019-07-20 | 2019-09-16 | 2.698 | 2.698 |  |  | 2019-09-16 | 2020-07-14 | 2021-09-16 | 2021-03-04 | 1. Breakdown time will be reduced. 2. Aux. water consumption will be reduced. 3. Periodical overhauls of pump will be possible with out plat outages. 4. Life & service will be enhanced |  |  | 2.6466 |  | 2.6466 | [18 empty] | 2.6466 | 2.6466 | [10 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/2019-2020/734 | 2019-07-20 | 2019-09-16 | 0.49 | 0.49 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
26 | Procurement, Replacement of Eco Coils U#1&2 210 MW, & Procurement & replacement of foundation Deck Spring assembly for coal mills U#3,4 at Khaperkheda TPS | DPR | MERC/CAPEX/2019-2020/853 | 2019-07-24 | 2019-10-10 | 15.4086 | 15.4086 |  |  | 2019-10-10 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
26.1 | Procurement, Replacement of Eco Coils U#1&2 | Scheme | MERC/CAPEX/2019-2020/853 | 2017-01-10 | 2019-10-10 | 7.4996 | 7.4996 |  |  | 2019-10-10 | 2019-10-16 | 2021-10-10 | 2022-01-15 |  |  |  | 2.7255 | 3.9248 | 6.6503 | [18 empty] | 6.6503 | 6.6503 | [10 empty] | Capitalised
26.2 | Procurement & replacement of foundation Deck Spring assembly for coal mills U#3,4 | Scheme | MERC/CAPEX/2019-2020/853 | 2017-01-11 | 2019-10-10 | 6.679 | 6.679 |  |  | 2019-10-10 | 2022-03-08 | 2021-10-11 | [6 empty] | 0 | 3.006 | 0 | 4.0896 | [9 empty] | 45.01% | 8.078% | 0% |  |  |  |  | 0 |  |  | 3.55 | 3.55 |  |  |  |  | 3.006 | Partial capitalisation (50%qty )of scheme will be done in FY 2024-25 & remaining 50% qty work will be done in FY 2025-26 ( PO placed with 50%reduced qty). PO for remaining 50% qty was placed in FY 2024-25 | WIP
| IDC | IDC | MERC/CAPEX/2019-2020/853 | 2017-01-12 | 2019-10-10 | 1.23 | 1.23 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
28 | ESP Upgradation of 5 Nos. of 210/500MW Units at Khaperkheda, Koradi & Chandrapur TPS | DPR | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2021-02-26 | 2022-09-29 | 90.3535 | 90.3535 |  |  | 2022-09-29 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
28.1 | ESP Upgradation at Unit #1, Khaperkheda TPS | Scheme | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2021-02-26 | 2022-09-29 | 42.7114 | 42.7114 |  |  | 2022-09-29 | [7 empty] | 0 | 0 | 5.955 | 35.73 | 17.865 | [16 empty] | 0 | 0 | 0 |  | 54.445 | [5 empty] | Expenditure amount not CORRECTED please take from the CE(P&P) | WIP
28.2 | ESP Upgradation at Unit #2, Khaperkheda TPS | Scheme | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2021-02-26 | 2022-09-29 | 42.7114 | 42.7114 |  |  | 2022-09-29 | [7 empty] | 0 | 0 | 5.955 | 35.73 | 17.865 | [16 empty] | 0 | 0 | 0 |  | 54.445 | [5 empty] | Expenditure amount not CORRECTED please take from the CE(P&P) | WIP
| IDC | IDC | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2021-02-26 | 2022-09-29 | 4.9307 | 4.9307 |  |  | 2022-09-29 | [8 empty] | 0 | [19 empty] | 0 |  |  |  | 16 | [6 empty] | N.A.
29 | Flue Gas Desulphurisation System for Khaperkheda Unit # 1-4 | DPR | MERC/CAPEX/2021-2022/MSPGCL/097 | 2018-01-30 | 2022-03-14 | 226.913 | 113.4565 |  |  | 2022-03-14 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
29.1 | FGD System for Khaperkheda Unit # 1-4 | Scheme | MERC/CAPEX/2021-2022/MSPGCL/097 | 2018-01-30 | 2022-03-14 | 218.3 | 109.15 |  |  | 2022-03-14 | 2022-03-29 | 2023-05-29 | [6 empty] | 0 | 51.12 | 204.46 | [11 empty] | 100% | [5 empty] | 0 |  | 0 | 130.03 | [6 empty] | MERC's Approval is for Unit # 3 & 4 only. Design Engineering & site clearnce in progress. | WIP
| IDC | IDC | MERC/CAPEX/2021-2022/MSPGCL/097 | 2018-01-30 | 2022-03-14 | 8.613 | 4.3065 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
HO DPR 4 | Construction of coal platform for Chandrapur TPS, Khaperkheda TPS & Parli TPS | DPR | MERC/TECH 1/CAPEX/20132014/00827 | 2013-04-18 | 2013-07-09 | 5.43 | 5.43 |  |  | 2013-07-09 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
HO DPR 4.2 | Khaperkheda TPS | Scheme | MERC/TECH 1/CAPEX/20132014/00827 | 2013-04-18 | 2013-07-09 | 5.43 | 5.43 |  |  | 2013-07-09 |  |  |  |  | 3.9936 |  |  |  | 3.9936 | [15 empty] | 3.9936 |  |  |  | 3.9936 | [10 empty] | Capitalised
| IDC | IDC | MERC/TECH 1/CAPEX/20132014/00827 | 2013-04-18 | 2013-07-09 |  |  |  |  | 2013-07-09 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
HO DPR 5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | DPR | MERC/TECH 1/CAPEX/20142015/01218 | 2014-10-01 | 2014-11-25 | 4.82 | 4.82 |  |  | 2014-11-25 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
HO DPR 5.4a | 1. Procurement of 6.6 KV,300 KW, P.A.fan motor for U# 1 & 2 2. Procurement of 6.6 KV,425 KW,CM motor for U # 3 & 4 3. Procurement of 6.6 KV,1400KW,CW pump motor for U-1& 2 4. Procurement of 6.6 KV,1400 KW,CW pump motor for U-3&4 | Scheme | MERC/TECH 1/CAPEX/20142015/01218 | 2014-10-01 | 2014-11-25 | 3.82 | 3.82 |  |  | 2014-11-25 | 2016-11-08 | 2016-11-25 | 2020-07-14 | 1.Reduced failure reduces the yearly expenditure on maintenance and rewinding 2.The present-day motors are of energy efficient construction. 3.Increased efficiency resulting in reduced loading on the old cables and help avoid cable failures/replacements. 4.Reduced noise level and vibrations around the running motor. 4.Considerable generation loss on account of failure of HT motors can be avoided. | 1.6341 | 0.43182 | 0.46233 |  | 2.5283 |  | 0.069 | [13 empty] | 1.6341 |  | 0.88767 | 0.0064768 | 2.5283 |  | 0.069 | [8 empty] | Capitalised
HO DPR 5.4b | K'kheda: Procurement of HT Motors(GS/HP Water pump)for U-1&2 and Procurement of HT Motors (ACW)for U-3&4 | Scheme | MERC/TECH 1/CAPEX/20142015/01218 | 2014-10-01 | 2014-11-25 | 1 | 1 |  |  | 2014-11-25 | 2019-08-21 | 2016-11-25 | 2021-02-26 | 1.Reduced failure reduces the yearly expenditure on maintenance and rewinding 2.The present-day motors are of energy efficient construction. 3.Increased efficiency resulting in reduced loading on the old cables and help avoid cable failures/replacements. 4.Reduced noise level and vibrations around the running motor. 4.Considerable generation loss on account of failure of HT motors can be avoided. | 0 |  | 0.4 |  | 0.4 | [15 empty] | 0 |  | 0.4 |  | 0.4 | [10 empty] | Capitalised
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | DPR | MERC/CAPEX/20162017/00423 | 2016-02-03 | 2016-08-03 | 3.96 | 3.96 |  |  | 2016-08-03 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
HO DPR 6.2 | KHAPERKHEDA (U-1 to 4) | Scheme | MERC/CAPEX/20162017/00423 | 2016-02-03 | 2016-08-03 | 3.96 | 3.96 |  |  | 2016-08-03 | 2018-05-30 | 2018-03-08 | 2021-11-29 |  | 0 |  | 2.8152 |  | 2.8152 | 0.30212 | [14 empty] | 0 |  | 2.8152 |  | 2.8152 | 0.30212 | [9 empty] | Capitalised
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | DPR | MERC/CAPEX/20162017/00774 | 2016-08-26 | 2016-09-30 | 4.0552 | 4.0552 |  |  | 2016-09-30 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
HO DPR 7.2 | Khaperkheda TPS | Scheme | MERC/CAPEX/20162017/00774 | 2016-08-26 | 2016-09-30 | 4.0552 | 4.0552 |  |  | 2016-09-30 |  |  |  |  | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [10 empty] | Not Initiated
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | DPR | MERC/CAPEX/20172018/4653 | 2017-04-19 | 2017-11-13 | 2.7 | 2.7 |  |  | 2017-11-13 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
HO DPR 8.1 | Advance Multipurpose Fire Tender for KPKD 1-4 | Scheme | MERC/CAPEX/20172018/4653 | 2017-04-19 | 2017-11-13 | 1.45 | 1.45 |  |  | 2017-11-13 | 2017-11-13 | 2019-11-13 | 2021-11-09 |  | 0 |  |  | 1.7765 | 1.7765 | [15 empty] | 0 |  |  | 1.7765 | 1.7765 | [10 empty] | Capitalised
HO DPR 8.2 | Normal Multipurpose Fire Tender KPKD 1-4 | Scheme | MERC/CAPEX/20172018/4653 | 2017-04-19 | 2017-11-13 | 1.25 | 1.25 |  |  | 2017-11-13 | 2022-02-03 | 2019-11-13 |  |  | 0 |  |  |  | 0 | 2.1847 | [14 empty] | 0 |  |  |  | 0 | 2.1847 | [9 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/20172018/4653 | 2017-04-19 | 2017-11-13 |  |  |  |  | 2017-11-13 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
HO DPR 9 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | DPR | MERC/CAPEX/2017-18/0208 | 2017-12-13 | 2018-02-08 | 226.3024 | 226.3024 |  |  | 2018-02-08 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
HO DPR 9.1 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | Scheme | MERC/CAPEX/2017-18/0208 | 2017-12-13 | 2018-02-08 | 226.3024 | 226.3024 |  |  | 2018-02-08 | 2018-08-03 | 2019-11-08 |  | The key benefit of this conveying system is as follows: o Lesser cost of transport per Km / Ton. o Social benefit by eliminating congestion of connected road. o Environmentally more friendly. o More reliable, does not depend on vagaries of weather. o Less pilferage. | 23.15 | 97.62 | 66.87 | 41.73 | 229.37 | 37.33 | 24.53 | [6 empty] | 16% | 48% | 70% | 90% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 57.6077 | 273.81 | [6 empty] | Required More capitalisation as per previous discussion with Koradi Project to avoide disallowance against Non DPR capitalised in FY 2023-24.VC done with all concern CE(RCD) on dtd. 01.08.2024 regarding capitalisation of this scheme. | Partially Capitalised
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | DPR | MERC/CAPEX/20172018/0177 | 2018-01-12 | 2018-02-06 | 4.4604 | 4.4604 |  |  | 2018-02-06 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
HO DPR 10.2a | Compond wall (IB recommdation),Plant Patrolling Roads (IB recommdation) TPS KPKD | Scheme | MERC/CAPEX/20172018/0177 | 2018-01-12 | 2018-02-06 | 4.4604 | 4.4604 |  |  | 2018-02-06 | 2019-02-04 | 2020-12-06 | 2020-01-21 |  | 0 | 2.7187 | 1.2081 |  | 3.9268 |  | 0.023832 | [13 empty] | 0 |  |  | 0.64975 | 0.64975 | 3.2771 | 0.023832 | [8 empty] | Capitalised
HO DPR 11 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | DPR | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-04-18 | 2018-07-24 | 9.23 | 9.23 |  |  | 2018-07-24 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
HO DPR 11.1 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | Scheme | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-04-18 | 2018-07-24 | 9.05 | 9.05 |  |  | 2018-07-24 | 2019-02-25 | 2020-07-24 | 2021-11-07 | As per national & state water policy, priority is to be given to drinking use & agricultaral use of water. Mspgcl will be using GOI & GOM policy to use treated sewage water for therma plants to minimize the use of fresh water & to reduce pollutions in rivers of nagpur & gosi khurd dam.Also, to avoid situation to stop thermal plants due to non availibility of water. | 0 | 8.8458 | 3.563 | 0.89686 | 13.3057 | [15 empty] | 0 |  |  | 13.3057 | 13.3057 | [10 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-04-18 | 2018-07-24 | 0.18 | 0.18 |  |  | 2018-07-24 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
HO DPR 15 | Implementation of Water Flow Monitoring system at Chandrapur STPS & Khaperkheda TPS | DPR | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2019-10-14 | 2020-10-27 | 5.1755 | 5.1755 |  |  | 2020-10-27 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
HO DPR 15.3 | Electromagnetic Flow meters at various lines & Locations of 210 MW | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2019-10-14 | 2020-10-27 | 3.8515 | 3.8515 |  |  | 2020-10-27 |  |  |  | Implementation of this flow monitoring system will help in proper utilization of water & water audit. It will help to arrest any leakages occurring in the system. These will together help in billing purpose which MSPGCL pays to irrigation department. |  |  |  |  | 0 |  |  | 3.8515 | [16 empty] | 0 |  |  | 3.8515 | [7 empty] | WIP
HO DPR 15.4 | Automation: Centralized SCADA, RTU, MODBUS Cable, Power cable & mandatory spares | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2019-10-14 | 2020-10-27 | 1.324 | 1.324 |  |  | 2020-10-27 |  |  |  | Implementation of this flow monitoring system will help in proper utilization of water & water audit. It will help to arrest any leakages occurring in the system. These will together help in billing purpose which MSPGCL pays to irrigation department. |  |  |  |  | 0 |  |  | 1.324 | [16 empty] | 0 |  |  | 1.324 | [7 empty] | WIP
| IDC | IDC | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2019-10-14 | 2020-10-27 | 0 | 0 |  |  | 2020-10-27 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
30 | Supply of spare Generator Rotor for UNIT 1 & 2, 210MW | DPR | MERC/CAPEX/2023-24/0184 | 2022-05-30 | 2024-03-12 | 37.11 | 37.11 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
30.1 | Supply of spare Generator Rotor for UNIT 1 & 2, 210MW | Scheme | MERC/CAPEX/2023-24/0184 | 2022-05-30 | 2024-03-12 | 36.7 | 36.7 | [11 empty] | 0 | 11.01 | 25.69 | [17 empty] | 0 |  |  | 36.7 | [7 empty] | WIP
| IDC | IDC | MERC/CAPEX/2023-24/0184 | 2022-05-30 | 2024-03-12 | 0.41 | 0.41 | [11 empty] | 0 | [19 empty] | 0
31 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M with raising of drain wells and modification of Masonary Dam (Waste Weir), 4 x210 MW, TPS, Khaperkheda | DPR | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2022-11-26 | 2023-10-09 | 45.0535 | 45.0535 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
31.1 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M at TPS, Khaperkheda. | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2022-11-26 | 2023-10-09 | 31.0231 | 31.0231 | [6 empty] | 1.The ash filling storage capacity will be imcreased by 3.95 MM3. The ash bund will in service further for next 3 Yrs approx depending upon ash utilisation. 2.Statutary requirement as per MPCB |  |  |  |  | 0 |  |  | 31.22 | [16 empty] | 0 |  |  | 31.22 | [6 empty] | This scheme will be capitalised in FY 24-25 (30% cost considered in 500MW) | WIP
31.2 | Raising of drain wells of Waregaon Ash Bund TPS, Khaperkheda. | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2022-11-26 | 2023-10-09 | 1.6569 | 1.6569 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | WIP
31.3 | Modification of Masonary Dam (Waste Weir) of Waregaon Ash Bund TPS, Khaperkheda. | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2022-11-26 | 2023-10-09 | 10.1857 | 10.1857 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | WIP
| IDC | IDC | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2022-11-26 | 2023-10-09 | 2.1878 | 2.1878 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
32 | Flue Gas Desulphurisation (FGD) System for Khaperkheda Unit # 1 & 2 | DPR | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-03-24 | 2023-09-05 | 115.34 | 115.34 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
32.1 | Flue Gas Desulphurisation (FGD) System for Khaperkheda Unit # 1 & 2 | Scheme | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-03-24 | 2023-09-05 | 109.8 | 109.8 | [11 empty] | 0 | [19 empty] | 0 |  |  | 29.98 | 99.15 | [6 empty] | WIP
| IDC | IDC | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-03-24 | 2023-09-05 | 5.54 | 5.54 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
33 | Upgradation of DDC/DCS system for UNIT 1 & 3 of 210 MWKhaperkheda TPS | DPR | MERC/CAPEX/MSPGCL/2023-24/601 | 2023-03-28 | 2023-11-10 | 39.14 | 39.14 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
33.1 | Upgradation of DDC/DCS system for UNIT 1 & 3 of 210 MWKhaperkheda TPS | Scheme | MERC/CAPEX/MSPGCL/2023-24/601 | 2023-03-28 | 2023-11-10 | 38.7 | 38.7 | [6 empty] | Upgradation of DDC system will result in improving system reliability. Improvement in reliability of control system resulting in safe and optimized operation. |  |  |  |  | 0 |  |  |  | 19.57 | 19.57 | [14 empty] | 0 |  |  |  | 19.57 | 19.57 | [5 empty] | WIP
| IDC | IDC | MERC/CAPEX/MSPGCL/2023-24/601 | 2023-03-28 | 2023-11-10 | 0.44 | 0.44 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | WIP
34 | Supply & commissioning of interconnection conveyor belt, Elecon make complete impact type crusher, Procurement of 4 NOs. Bull Dozer BEML BD-155 and Eco friendly and power efficient chiller system at Khaperkheda TPS | DPR | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2023-07-24 | 2024-02-27 | 28.32 | 28.32 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
34.1 | Design, engineering, manufacturing, supply, erection & commissioning of interconnection conveyor belt from 1 X 500MW to 4 X 210MW stack yard at CHP Khaperkheda TPS | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2023-07-24 | 2024-02-27 | 5.43 | 5.43 | [11 empty] | 0 | [19 empty] | 0 | [9 empty] | This scheme is to be added in 500MW | WIP
34.2 | Supply & installation of Elecon–make complete impact type crusher at CHP-I, Khaperkheda TPS | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2023-07-24 | 2024-02-27 | 4.29 | 4.29 | [6 empty] | 1. Crushers are in service since last 33 years, due to wear & tear availability reduced to 50%. 2. The scheme will benefit to restoration of capacity and availability will be @ 90%. 3. Demurrage charges will be reduced & benefit of 5.35 Crs. can be realized in one year. |  |  |  |  | 0 |  |  | 4.15 | [16 empty] | 0 |  |  | 4.15 | [7 empty] | WIP
34.3 | Procurement of 4 NOs. Bull Dozer BEML BD-155 at CHP, Khaperkheda TPS | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2023-07-24 | 2024-02-27 | 5.255 | 5.255 |  |  | 27.02.2024 |  |  |  | 1. The dozers are utilized for management of stack yard and directly with related with demurrage charges. 2. Availability of dozer will benefit to save the demurrage charges of 5.35 Crs. Can be realized in one year. |  |  |  |  | 0 |  |  | 12.0596 | [16 empty] | 0 |  | 12.0596 | [7 empty] | CPA PROCUREMENT PLEASE TAKE COST OVERRUN REASONS FROM O/O. CE(CPA) | Capitalised
34.4 | Supply, erection, & commissioning of Eco friendly and power efficient chiller system for khaperkheda TPS Unit 1 to 4, Service Building and WTP in place of present reciprocating type Chiller system | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2023-07-24 | 2024-02-27 | 11.96 | 11.96 | [11 empty] | 0 |  |  | 3.78 | 7.67 | [15 empty] | 0 |  |  | 3.78 | 7.67 | [6 empty] | WIP
| IDC | IDC | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2023-07-24 | 2024-02-27 | 1.385 | 1.385 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
35 | 5 Nos. of Boiler Improvement Schemes for Unit No. 1 to 4 | DPR | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2022-11-16 | 2024-04-18 | 32.44 | 32.44 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
35.1 | Procurement & replacement of Re-Heater Rear Pendent Assembly Coils for unit no. 3 & 4 (210 MW) | Scheme | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2022-11-16 | 2024-04-18 | 8.86 | 8.86 | [11 empty] | 0 |  |  |  | 4.68 | 4.68 | [14 empty] | 0 |  |  |  | 4.68 | 4.68 | [5 empty] | WIP
35.2 | Procurement Complete Set of Sky Climber For Unit#1 To 5 Boilers. | Scheme | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2022-11-16 | 2024-04-18 | 3.32 | 3.32 | [11 empty] | 0 |  |  | 2.43 | [16 empty] | 0 |  |  | 2.43 | [7 empty] | WIP
35.3 | Replacement of glasswool insulation and GI/CORRUGATED sheets of boiler and hot air ducts at unit 1to 4 KHAPERKHEDA TPS | Scheme | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2022-11-16 | 2024-04-18 | 2.19 | 2.19 | [11 empty] | 0 |  |  | 1.99 | [16 empty] | 0 |  |  | 1.99 | [7 empty] | WIP
35.4 | Procurement, design, manufacture, supply & delivery, dismantling, retrofitting, erection, commissioning and testing of gravimetric belt conveyor type coal feeders for unit no. 1 & 2. | Scheme | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2022-11-16 | 2024-04-18 | 6.68 | 6.68 | [11 empty] | 0 |  |  |  | 6.77 | [15 empty] | 0 |  |  |  | 6.77 | [6 empty] | WIP
35.5 | Procurement and Replacement of Air Preheater Baskets for Unit no. 1 to 4 (4x 210MW). | Scheme | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2022-11-16 | 2024-04-18 | 9.05 | 9.05 | [11 empty] | 0 |  | 2.7935 | 2.84 | 2.84 |  | 2.9 | [13 empty] | 0 |  | 2.7935 | 2.84 | 2.84 |  | 2.9 |  |  |  |  | Partially Capitalised
| IDC | IDC | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2022-11-16 | 2024-04-18 | 2.34 | 2.34 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | DPR | MERC/CAPEX/2021-2022/MSPGCL/063 | 2018-08-31 | 2022-02-12 | 113.91 | 57 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | Scheme | MERC/CAPEX/2021-2022/MSPGCL/063 | 2018-08-31 | 2022-02-12 | 108.48 | 54.24 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | To be confirmed
| IDC | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2018-08-31 | 2022-02-12 | 5.43 | 2.76 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
HO DPR 16 | Centralized Monitoring Solution | DPR | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-03-28 | 2023-11-02 | 69.309 | 69.309 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
1 | Centralized Monitoring Solution | Scheme | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-03-28 | 2023-11-02 | 66.009 | 66.009 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | To be confirmed
| IDC | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-03-28 | 2023-11-02 | 3.3 | 3.3 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
HO DPR-17 | Various DPR Schemes for The work of maintaining the zero discharge condition of Pond No. 2 & Pond No.3 and providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | DPR | MERC/CAPEX/2018-2019/1242 | 2018-07-10 | 2018-09-22 | 15.7443 | 15.7443 |  |  | 2018-09-22 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
HO DPR 17.1 | The work of maintaining the zero discharge condition of Pond No.2 & Pond No.3 at KTPS Koradi | Scheme | MERC/CAPEX/2018-2019/1242 | 2018-07-10 | 2018-09-22 | 4.2068 | 4.2068 |  |  | 2018-09-22 |  |  |  |  | 0 |  |  |  | 0 | [19 empty] | 0 | [10 empty] | N.A.
HO DPR 17.2 | Providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | Scheme | MERC/CAPEX/2018-2019/1242 | 2018-07-10 | 2018-09-22 | 11.5375 | 11.5375 |  |  | 2018-09-22 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
2 | Scheme of HMI upgradation of unit 5 DCS along with Max Links , HART Scheme , PADO , all BOP PLCs , SWAS system, CO analyser & Coal feeder controller to match with the external aspect , process improvement & Up gradation of Generator Protections Relays in unit 1 to 4 of 210 MW at khaperkheda TPS |  | MERC/CAPEX/2024-2025/478 | 2024-01-31 | 2024-08-06 | 33.76 | 33.76 | [11 empty] | 0 | [19 empty] | 0
2.7 | Up-gradation of Generator Protections Relays in Unit 1 to 4 of 210 MW Khaperkheda TPS. |  | MERC/CAPEX/2024-2025/478 | 2024-01-31 | 2024-08-06 | 8.31 | 8.31 | [6 empty] | Upgraded relays will have better response time, enhanced features which will help in improving quality & reliability of the system. |  |  |  |  | 0 |  |  |  | 4.43 | 4.43 | [14 empty] | 0 |  |  |  | 4.43 | 4.43 | [5 empty] | WIP
| IDC |  | MERC/CAPEX/2024-2025/478 | 2024-01-31 |  | 0.86 | 0.86 | [11 empty] | 0 | [19 empty] | 0
[19 empty] | 0 | [19 empty] | 0
| (ii) Submitted to MERC, Yet to receive approval | [17 empty] | 0 | [19 empty] | 0
1 | DPR on Refurbishment of Spare HPT Module Unit 1 & 2 at TM-I and Procurement of Complete Gear Box Assemblies of Coal Mills XRP 803 ½ HP & XRP 883 for Unit No. 1 to 4 (4x210 MW), Khaperkheda TPS |  | Yet to be approved | 2022-11-16 |  | 25.8728 | 0 | [11 empty] | 0 | [19 empty] | 0
1.1 | Refurbishment of spare HPT module Unit 1 & 2 at TM-I (4X210 MW), KHAPERKHEDA TPS |  | Yet to be approved | 2022-11-16 |  | 11.54 | [7 empty] | 1.Improvement in efficiency of HPT module, this will result in improved cycle efficiency. 2.Reduction in downtime of machine during COH. 3.Decrease in auxiliary consumption 4.Improvement in Heat rate. |  |  |  |  | 0 | [19 empty] | 0 | [9 empty] | Rejected by Hon MERC as per rejection letter No.MERC/CAPEX/2024-2025/494 dtd 08.08.2024.Hence cost not considered for capitalisation in plan | To be confirmed
1.2 | Procurement of Complete Gear Box Assemblies of Coal Mills XRP 883 for Unit-1 to 4 (210MW). |  | Yet to be approved | 2022-11-16 |  | 14.1128 | [7 empty] | 1.To reduce/avoid generation loss on account of Milling issues |  |  |  |  | 0 |  |  |  | 0 | [15 empty] | 0 | [9 empty] | Rejected by Hon MERC as per rejection letter No.MERC/CAPEX/2024-2025/494 dtd 08.08.2024.Hence cost not considered for capitalisation in plan | To be confirmed
| IDC |  | Yet to be approved | 2022-11-16 |  | 0.22 | [12 empty] | 0 | [19 empty] | 0
| (ii) Yet to be submitted to MERC | [17 empty] | 0 | [19 empty] | 0
1 | SUPPLY INSTALLATION TESTING & COMMISSIONING REVAMPING OF FIRE DETECTION & ALARM AND PROTECTION SYSTEM FROM FIRE AND PROVIDING RAPID EXTINGUISHING CLEAN AGENT (CA) SYSTEM AT UNIT -3,4 & 5 ATKPKD TPS | DPR |  |  |  | 29.71 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN | N.A.
1.1 | Supply Installation Testing & Commissioning , Revamping of fire protection and providing rapid extinguishing clean agent (CA) system at unit # 3 ,4 210 MW TPS, KHAPERKHEDA | Scheme |  |  |  | 6.5 | [7 empty] | 1.statutary requirement 2.for safety and reduction in damaged due to any fire incidence. |  |  |  |  | 0 |  |  |  |  | 6.5 | [14 empty] | 0 |  |  |  |  | 6.5 | [5 empty] | Not Initiated
2 | Restoration of various Fire protection system at Khaperkheda TPS | DPR |  |  |  | 60.63 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
2.1 | Restoration of fire hydrant ring and fire water spray Header at Khaperkheda TPS | Scheme |  |  |  | 13.14 | [7 empty] | 1.statutary requirement 2.for safety and reduction in damaged due to any fire incidence. |  |  |  |  | 0 |  |  |  |  | 13.14 | [14 empty] | 0 |  |  |  |  | 13.14 | [5 empty] | Not Initiated
2.2 | Restoration of deluge valve system at CHP-210MW | Scheme |  |  |  | 25.44 | [7 empty] | 1.statutary requirement 2.for safety and reduction in damaged due to any fire incidence. |  |  |  |  | 0 |  |  |  |  | 25.44 | [14 empty] | 0 |  |  |  |  | 25.44 | [5 empty] | Not Initiated
3 | VARIOUS SCHEMES PROPOSED FOR IMPROVEMENT OF CHP-I (4 X 210 MW). | DPR |  |  |  | 33.82 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
3.1 | Design, Manufacturing, Supply, Erection, Commissioning & Testing of Coal Flow Management system for Coal Bunkers in CHP-I (4 X 210MW), Khaperkheda TPS. | Scheme |  |  |  | 12.27 | [7 empty] | 1. Coal flow management system utilized in bunkers for smooth passing of coal to coal feeder by reducing NCF. 2. The scheme will benefit in reducing generation loss. |  |  |  |  | 0 |  |  |  |  | 12.27 | [14 empty] | 0 |  |  |  |  | 12.27 | [5 empty] | Not Initiated
3.2 | Design, engineering, manufacturing, supply, installation and commissioning of Dedusting System for Crusher House and Bunker area in Unit 3 & 4 at CHP-I (4 X 210MW), Khaperkheda TPS. | Scheme |  |  |  | 12.96 | [7 empty] | 1. Dedusting system are utilized for dust removal in coal handling system and will benefit for good health of workers working there. 2. Also statutary requirement of MPCB & CPCB need to fullfil to operate the plant. |  |  |  |  | 0 | [5 empty] | 12.96 | [13 empty] | 0 | [5 empty] | 12.96 |  |  |  |  | Not Initiated
3.3 | Renovation including replacement of Power & Control cables with automation & upgradation of Stacker Reclaimer No. 1 in CHP-I (4 X 210MW), TPS Khaperkheda." | Scheme |  |  |  | 8.59 | [7 empty] | 1. As the plant is 33 years old and in service, the cable replacement is important to avoid any fire incidence and major breakdown. 2. Availability of Stacker/ Reclaimer will benefit to save the demurrage charges of 5.35 Crs. Can be realized in one year. |  |  |  |  | 0 |  |  |  |  | 8.59 | [14 empty] | 0 |  |  |  |  | 8.59 | [5 empty] | Not Initiated
4 | Flue Gas Desulphrisation | DPR |  |  |  | 127.8 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
4.1 | FGD installation of 210MW unit 1 & 2 at Khaperkheda | Scheme | [16 empty] | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [5 empty] | PROJECT SCHEME.Already taken at serial no.32 above. | N.A.
5 | Upgradation of DDC/DCS system for UNIT 2 & 4 of 210 MW Khaperkheda TPS | DPR |  |  |  | 45 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
5.1 | Upgradation of DDC/DCS system for UNIT 2 & 4 of 210 MW Khaperkheda TPS | Scheme | [11 empty] | Upgradation of DDC system will result in improving system reliability. Improvement in reliability of control system resulting in safe and optimized operation. |  |  |  |  | 0 | [5 empty] | 22.5 | 22.5 | [12 empty] | 0 | [5 empty] | 22.5 | 22.5 |  |  |  | Not Initiated
6 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#1 to 4 Khaperkheda TPS & Upgradation of various governing Element for smooth operation for flexible operation of TG set at 40% technical minimum operation. | DPR |  |  |  | 90 | [7 empty] | CEA flexible operation statutory norms |  |  |  |  | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
6.1 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#1 to 4 Khaperkheda TPS. | Scheme |  |  |  | 60 | [7 empty] | CEA flexible operation statutory norms |  |  |  |  | 0 |  |  |  | 15 | 45 | [14 empty] | 0 |  |  |  | 15 | 45 | [5 empty] | Not Initiated
6.2 | Upgradation of various governing Element for smooth operation for flexible operation of TG set at 40% technical minimum operation. | Scheme |  |  |  | 30 | [7 empty] | CEA flexible operation statutory norms |  |  |  |  | 0 |  |  |  |  | 30 | [14 empty] | 0 |  |  |  |  | 30 | [5 empty] | Not Initiated
7 | Upgradation of Battery Charger , UPS system , GEHO PLC and VFD, ID VFD, supply of Efficiency Measuring Instruments and Supply, erection and commissioning of Sox, Nox , CO, Opacity, ETP and Oxygen Analyser for Unit 1 to 4 of 210 MW at Khaperkheda TPS. | DPR |  |  |  | 44.5 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
7.1 | Supply of Efficiency Monitoring Instruments for performance optimization group (POG) at Khaperkheda TPS. | Scheme |  |  |  | 1.5 | [7 empty] | 1. Ultrasonic flow meter enable plants to obtain the information needed to meet their sustainability goals, reduce energy costs, and improve overall performance though plant optimization. 2. Accurate measurement of the fuel gas flow is important for optimizing the combustion process and maximizing the efficiency of the power plant. 3. Boiler feedwater flow measurement is important for optimizing the steam production process and maximizing the efficiency of the power plant. 4. Deviations from expected values in Heat rate on account of flow can be identified and mitigated. |  |  |  |  | 0 |  |  |  |  | 1.5 | [14 empty] | 0 |  |  |  |  | 1.5 | [5 empty] | Not Initiated
7.2 | Upgradation of 220 V, 24 V DC Float cum boost battery charger at Unit#1 to 4 Khaperkheda TPS. | Scheme |  |  |  | 10 | [7 empty] | • Reduce repair & maintenance costs. • Increased reliability & stability of process • Improve system operability and availability. • Safe & reliable operation of battery. |  |  |  |  | 0 |  |  |  |  | 5 | 5 | [13 empty] | 0 |  |  |  |  | 5 | 5 |  |  |  |  | Not Initiated
7.3 | Upgradation of 2X50 KVA UPS at Unit#1 to 4 Khaperkheda TPS. | Scheme |  |  |  | 5 | [7 empty] | • Reduce repair & maintenance costs. • Increased reliability & stability of process • Improve system operability and availability. • Safe & reliable operation of UPS system. |  |  |  |  | 0 |  |  |  |  | 2.5 | 2.5 | [13 empty] | 0 |  |  |  |  | 2.5 | 2.5 |  |  |  |  | Not Initiated
7.4 | Supply, Erection and Commissioning of Sox, Nox , CO, Opacity and ETP Analyser for Unit 1 to 4 of 210 MW at Khaperkheda TPS | Scheme |  |  |  | 5 | [7 empty] | Above scheme is Mandatory for On-Line measurement of SO2 / NOx of Flue Gas as per MPCB Rules of Regulation & Environment Compliance.Statutary requirement. • It helps to monitor Pollutant Emission. • It helps to monitor Quality of Combustion. |  |  |  |  | 0 |  |  |  |  | 5 | [14 empty] | 0 |  |  |  |  | 5 | [5 empty] | Not Initiated
7.5 | Upgradation of GEHO PLC and VFD along with HCSD system Instrumentaion at Unit 3 & 4 Khaperkheda TPS. | Scheme |  |  |  | 5 | [7 empty] | Reduce repair & maintenance costs. • Increased reliability & stability of process • Improve system operability and availability. • Safe & reliable operation of HCSD system. |  |  |  |  | 0 |  |  |  |  | 5 | [14 empty] | 0 |  |  |  |  | 5 | [5 empty] | Not Initiated
7.6 | Supply, Erection & Commissioning of Oxygen Analyzer for combustion optimization for Unit#1 to 5 Khaperkheda TPS. | Scheme |  |  |  | 3 | [7 empty] | Increases boiler efficiency • Reduced fuel consumption inside boiler • Improves heat rate • Reduction in CO & unburnt coal |  |  |  |  | 0 |  |  |  |  | 3 | [14 empty] | 0 |  |  |  |  | 3 | [5 empty] | Not Initiated
7.7 | Upgradation of VFD for ID FAN in Unit# 3 & 4, 210MW khaperkheda TPS. | Scheme |  |  |  | 10 | [7 empty] | Reduce repair & maintenance costs. • Increased reliability & stability of process • Improve system operability and availability. • Safe & reliable operation of ID Fan system. |  |  |  |  | 0 | [5 empty] | 10 | [13 empty] | 0 | [5 empty] | 10 |  |  |  |  | Not Initiated
7.8 | Scheme 8 Supply, erection & commissioning of PLC and SCADA System of Ash Evacuation and Disposal System for UNIT 3 and 4 Of 210 MW Khaperkheda TPS | Scheme |  |  |  | 5 | [7 empty] | Reduce repair & maintenance costs. • Increased reliability & stability of process • Improve system operability and availability. • Safe & reliable operation of ash evacuation & disposal system. |  |  |  |  | 0 |  |  |  |  | 2.5 | 2.5 | [13 empty] | 0 |  |  |  |  | 2.5 | 2.5 |  |  |  |  | Not Initiated
8 | Procurement of LP Rotor for unit 1 and 2 , Supply and installation of air washer unit 1 and 2 and refurbishment of air washer unit for unit 3 and 4 and GEHO Pummp house control room. Supply and installation of diesel engine driven fire fighting pump with engine. Procurement of various control valves for unit No. 1 to 4. | DPR |  |  |  | 50 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
8.1 | Supply and installation of Air washer unit in unit 1 and 2 , 6.6 KV breaker room, Turbine MCC room Battery room Boiler MCC room for cooling of all the Electrical Panels and AHP stage I Pump House control room air washer system | Scheme |  |  |  | 12 | [12 empty] | 0 | [5 empty] | 12 | [13 empty] | 0 | [5 empty] | 12 |  |  |  |  | Not Initiated
8.2 | Refurbishment of Air washer unit of 3 and 4, 6.6 KV breaker room, Turbine MCC room Battery room Boiler MCC room for cooling of all the Electrical Panels and Refurbishment of GEHO pump House and AHP stage II Pump House control room air washer system | Scheme |  |  |  | 8 | [12 empty] | 0 | [5 empty] | 4 | 4 | [12 empty] | 0 | [5 empty] | 4 | 4 |  |  |  | Not Initiated
8.3 | Procurement of Complete LPT rotor for unit 1 and 2 | Scheme |  |  |  | 20 | [12 empty] | 0 | [5 empty] | 20 | [13 empty] | 0 | [5 empty] | 20 |  |  |  |  | Not Initiated
8.4 | Revamping of diesel engine driven fire fighting pump system with engine. | Scheme |  |  |  | 3 | [12 empty] | 0 |  |  |  |  | 3 | [14 empty] | 0 |  |  |  |  | 3 | [5 empty] | Not Initiated
8.5 | Procurement of various control valves for unit No. 1 to 4 | Scheme |  |  |  | 7 | [12 empty] | 0 |  |  |  |  | 7 | [14 empty] | 0 |  |  |  |  | 7 | [5 empty] | Not Initiated
9 | Procurement of IP Rotor and Inner casing for unit 1 and 2. Procurement of IP rotor and inner casing for unit 3 and 4 | DPR |  |  |  | 65 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
9.1 | Procurement of IP Rotor and Inner casing for unit 1 and 2. | Scheme |  |  |  | 22 | [12 empty] | 0 | [5 empty] | 22 | [13 empty] | 0 | [5 empty] | 22 |  |  |  |  | Not Initiated
9.2 | Procurement of IP rotor and inner casing for unit 3 and 4 along with Turbovisory sensors and panel | Scheme |  |  |  | 23 | [12 empty] | 0 | [5 empty] | 23 | [13 empty] | 0 | [5 empty] | 23 |  |  |  |  | Not Initiated
9.3 | Supply and installation of srew compressor for supply of instrument air to unit No. 3 and 4 along with dryer for unit No. 3 & 4. | Scheme |  |  |  | 20 | [12 empty] | 0 | [5 empty] | 10 | 10 | [12 empty] | 0 | [5 empty] | 10 | 10 |  |  |  | Not Initiated
10 | Procurement of LP rotor for unit 3 and 4 and upgradation of BFP cartridge and BFP Booster pump | DPR |  |  |  | 45 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
10.1 | Procurement of of LP rotor for unit 3 and 4 | Scheme |  |  |  | 25 | [12 empty] | 0 | [5 empty] | 25 | [13 empty] | 0 | [5 empty] | 25 |  |  |  |  | Not Initiated
10.2 | Upgradation of BFP cartridge and BFP Booster pump, motorized scoop for hydraulic coupling and drive unit for BFP and modulating BFP RC valve for Unit 3 & 4 | Scheme |  |  |  | 20 | [12 empty] | 0 | [5 empty] | 10 | 10 | [12 empty] | 0 | [5 empty] | 10 | 10 |  |  |  | Not Initiated
11 | Refurbishment of LP rotor of unit 1 and 2 and Refurbishment of HPT module of unit 1 and 2 | DPR |  |  |  | 30 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
11.1 | Refurbishment of LP rotor of unit 1 and 2 | Scheme |  |  |  | 15 | [12 empty] | 0 | [7 empty] | 15 | [11 empty] | 0 | [7 empty] | 15 |  |  | Not Initiated
11.2 | Refurbishment of HPT module of unit 1 and 2 | Scheme |  |  |  | 15 | [12 empty] | 0 | [7 empty] | 15 | [11 empty] | 0 | [7 empty] | 15 |  |  | Not Initiated
12 | Refurbishment of LP rotor for unit 3 and 4 and Refurbishment and re-blading of HPT module of unit 3 and 4 | DPR |  |  |  | 54 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
12.1 | Refurbishment of LP rotors for unit 3 and 4 | Scheme |  |  |  | 18 | [12 empty] | 0 | [7 empty] | 18 | [11 empty] | 0 | [7 empty] | 18 |  |  | Not Initiated
12.2 | Refurbishment of HPT modules of unit 3 and 4 | Scheme |  |  |  | 36 | [12 empty] | 0 | [7 empty] | 36 | [11 empty] | 0 | [7 empty] | 36 |  |  | Not Initiated
13 | SITC OF COMPLETE SOLUTION AND COMPREHENSIVE PROTECTION AND MONITORING PACKAGE ALONG WITH RETROFIT OF ALLIED ACCESSORIES FOR VARIOUS GTs & STs INSTALLED AT 210 MW KHAPERKHEDA TPS. | DPR |  |  |  | 26 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
13.1 | SUPPLY,INSTALLATION, TESTING & COMMISSIONING OF COMPLETE SOLUTION AND COMPREHENSIVE PROTECTION AND MONITORING PACKAGE ALONG WITH RETROFIT OF ALLIED ACCESSORIES FOR VARIOUS GTs & STs INSTALLED AT 210 MW KHAPERKHEDA TPS. | Scheme |  |  |  | 26 | [7 empty] | 1.Induction of new efficient technology. 2.Online DGA will improve the protection of transformer, thereby major faults on account on internal faults in transformer can be avoided. |  |  |  |  | 0 |  |  |  |  | 6.5 | 19.5 | [13 empty] | 0 |  |  |  |  | 6.5 | 19.5 |  |  |  |  | Not Initiated
14 | PLANT PERFORMANCE IMPROVEMENT BY DESIGN, SUPPLY, INSTALLATION & COMMISSIONING OF STATE OF ART HT VACCUM CIRCUIT BREAERS AT UNIT 1 TO 4 OF 210MW KHAPERKHEDA TPS. | DPR |  |  |  | 31.64 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
14.1 | DESIGN, SUPPLY, INSTALLATION, TESTING & COMMISSIONING OF HT VCB AT U # 1 & 2. | Scheme |  |  |  | 15.14 | [7 empty] | 1.Reliability of system will improve thereby improving availability of U # 1 & 2 HT VCB 2.Induction of new efficient technology. 3.Downtime during fault on running breaker will be minimized due to availability of spare breakers. 4.Reliability of system will improve thereby improving availability of U # 3 & 4 HT VCB 5.Downtime during fault on running breaker will be minimized due to availability of spare breakers. |  |  |  |  | 0 |  |  |  | 15.14 | [15 empty] | 0 |  |  |  | 15.14 | [5 empty] | BR RECEIVED IN FY 2024-25 PROCUREMENT UNDER PROCESS AT CE(CPA) | WIP
14.2 | DESIGN, SUPPLY, INSTALLATION, TESTING & COMMISSIONING OF HT VCB AT U # 3 & 4. | Scheme |  |  |  | 16.5 | [7 empty] | 1.Reliability of system will improve thereby improving availability of U # 1 & 2 HT VCB 2.Induction of new efficient technology. 3.Downtime during fault on running breaker will be minimized due to availability of spare breakers. 4.Reliability of system will improve thereby improving availability of U # 3 & 4 HT VCB 5.Downtime during fault on running breaker will be minimized due to availability of spare breakers. |  |  |  |  | 0 |  |  |  | 8.25 | 8.25 | [14 empty] | 0 |  |  |  | 8.25 | 8.25 |  |  |  |  | BR RECEIVED IN FY 2024-25 PROCUREMENT UNDER PROCESS AT CE(CPA) | WIP
15 | DESIGN, SUPPLY, INSTALLATION, TESTING AND COMMISSIONING OF THE VARIOUS LIFTS IN PLACE OF THE EXISTING OLD LIFTS, LIGHTNING PROTECTION SYSTEM, EARTHING SYSTEM, AVIATION LIGHTING SYSTEM INSTALLED AT UNIT # 1 TO 4 OF 210 MW, KHAPERKHEDA TPS ON OEM BASIS. | DPR |  |  |  | 25.46 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
15.1 | DESIGN, SUPPLY, INSTALLATION, TESTING AND COMMISSIONING OF THE VARIOUS LIFTS IN PLACE OF THE EXISTING OLD LIFTS INSTALLED AT UNIT # 1 TO 4 OF 210 MW, KHAPERKHEDA TPS ON OEM BASIS. | Scheme |  |  |  | 10.46 | [7 empty] | 1.Induction of new efficient technology. 2.Availability of lifts will curtail the heavy material transportation time to boiler during shut down/AOH/COH/running plant. 3.Statutory requirement. |  |  |  |  | 0 |  |  |  |  | 10.46 | [14 empty] | 0 |  |  |  |  | 10.46 | [5 empty] | Not Initiated
15.2 | Design, Engineering, Supply, Erection, Testing & Commissioning of lightning protection system at Khaperkheda TPS. | Scheme |  |  |  | 5 | [7 empty] | 1.Statutory requirement. |  |  |  |  | 0 | [5 empty] | 5 | [13 empty] | 0 | [5 empty] | 5 |  |  |  |  | Not Initiated
15.3 | Design, Engineering, Supply, Erection, Testing & Commissioning of Earthing of electrical system & various buildings at Khaperkheda TPS. | Scheme |  |  |  | 5 | [7 empty] | 1.Statutory requirement. |  |  |  |  | 0 |  |  |  |  | 5 | [14 empty] | 0 |  |  |  |  | 5 | [5 empty] | Not Initiated
15.4 | Design, Engineering, Supply, Erection, Testing & Commissioning of Aviation Lighting Syatem at Khaperkheda TPS. | Scheme |  |  |  | 5 | [7 empty] | 1.Statutory requirement. |  |  |  |  | 0 |  |  |  |  | 5 | [14 empty] | 0 |  |  |  |  | 5 | [5 empty] | Not Initiated
16 | SUPPLY OF SPARE GENERATOR ROTOR FOR U#3 &4, 210MW, TPS KHAPERKHEDA. | DPR |  |  |  | 40 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
16.1 | SUPPLY OF SPARE GENERATOR ROTOR FOR U#3 &4, 210MW, TPS KHAPERKHEDA. | Scheme |  |  |  | 40 | [7 empty] | 1.INSURANCE SPARE AVAILABILITY. 2.AVAILABILITY OF UNIT 3 & 4 WILL IMPROVE. 3.DOWNTIME DURING FAULT ON GENERATOR ROTOR WILL BE MINIMIZED. |  |  |  |  | 0 | [5 empty] | 40 | [13 empty] | 0 | [5 empty] | 40 |  |  |  |  | Not Initiated
17 | PROCUREMENT OF ENERGY EFFICIENT MOTORS FOR U # 1 TO 4 OF KHAPERKHEDA TPS. | DPR |  |  |  | 35 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
17.1 | PROCUREMENT OF ENERGY EFFICIENT MOTORS FOR U # 1 & 2 OF KHAPERKHEDA TPS. | Scheme |  |  |  | 11 | [7 empty] | 1.RELIABILITY OF SYSTEM WILL IMPROVE AS ASSETS HAVE COMPLETED USEFUL SERVICE LIFE. 2.Induction of new efficient technology. 3.DOWNTIME DURING FAULT ON MOTOR WILL BE MINIMIZED DUE TO SPARE MOTOR AVAILABILITY. |  |  |  |  | 0 |  |  |  |  | 11 | [14 empty] | 0 |  |  |  |  | 11 | [5 empty] | Not Initiated
17.2 | PROCUREMENT OF ENERGY EFFICIENT MOTORS FOR U # 3 & 4 OF KHAPERKHEDA TPS. | Scheme |  |  |  | 14 | [7 empty] | 1.RELIABILITY OF SYSTEM WILL IMPROVE AS ASSETS HAVE COMPLETED USEFUL SERVICE LIFE & PERFORMANCE HAS DEGRADED. 2.Induction of new efficient technology. 3.DOWNTIME DURING FAULT ON MOTOR WILL BE MINIMIZED DUE TO SPARE MOTOR AVAILABILITY. |  |  |  |  | 0 |  |  |  |  | 14 | [14 empty] | 0 |  |  |  |  | 14 | [5 empty] | Not Initiated
17.3 | Procurement of DC motors for U # 1 & 2 of Khaperkheda TPS. | Scheme |  |  |  | 5 | [7 empty] | 1.RELIABILITY OF SYSTEM WILL IMPROVE AS ASSETS HAVE COMPLETED USEFUL SERVICE LIFE & PERFORMANCE HAS DEGRADED. 2.Induction of new efficient technology. 3.DOWNTIME DURING FAULT ON MOTOR WILL BE MINIMIZED DUE TO SPARE MOTOR AVAILABILITY. |  |  |  |  | 0 |  |  |  |  | 5 | [14 empty] | 0 |  |  |  |  | 5 | [5 empty] | Not Initiated
17.4 | Procurement of DC motors for U # 3 & 4 of Khaperkheda TPS. | Scheme |  |  |  | 5 | [7 empty] | 1.RELIABILITY OF SYSTEM WILL IMPROVE AS ASSETS HAVE COMPLETED USEFUL SERVICE LIFE & PERFORMANCE HAS DEGRADED. 2.Induction of new efficient technology. 3.DOWNTIME DURING FAULT ON MOTOR WILL BE MINIMIZED DUE TO SPARE MOTOR AVAILABILITY. |  |  |  |  | 0 |  |  |  |  | 2.5 | 2.5 | [13 empty] | 0 |  |  |  |  | 2.5 | 2.5 |  |  |  |  | Not Initiated
18 | UPGRADATION OF EXISTING LT MCC PANEL WITH STATE OF ART LT MCC PANEL AT U # 1 TO 4 OF KHAPERKHEDA TPS. | DPR |  |  |  | 35 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
18.1 | UPGRADATION OF EXISTING LT MCC PANEL WITH STATE OF ART LT MCC PANEL AT U # 1 & 2 OF KHAPERKHEDA TPS. | Scheme |  |  |  | 12.5 | [7 empty] | RELIABILITY OF SYSTEM WILL IMPROVE AS ASSETS HAVE COMPLETED USEFUL SERVICE LIFE & PERFORMANCE HAS DEGRADED. |  |  |  |  | 0 |  |  |  |  | 6.25 | 6.25 | [13 empty] | 0 |  |  |  |  | 6.25 | 6.25 |  |  |  |  | Not Initiated
18.2 | UPGRADATION OF EXISTING LT MCC PANEL WITH STATE OF ART LT MCC PANEL AT U # 3 & 4 OF KHAPERKHEDA TPS. | Scheme |  |  |  | 12.5 | [7 empty] | RELIABILITY OF SYSTEM WILL IMPROVE AS ASSETS HAVE COMPLETED USEFUL SERVICE LIFE & PERFORMANCE HAS DEGRADED. |  |  |  |  | 0 | [5 empty] | 6.25 | 6.25 | [12 empty] | 0 | [5 empty] | 6.25 | 6.25 |  |  |  | Not Initiated
18.3 | UPGRADATION OF HT BREAKER PANEL AT WAREGAON ASH BUND OF KHAPERKHEDA TPS. | Scheme |  |  |  | 3 | [7 empty] | RELIABILITY OF SYSTEM WILL IMPROVE AS ASSETS HAVE COMPLETED USEFUL SERVICE LIFE & PERFORMANCE HAS DEGRADED. |  |  |  |  | 0 | [5 empty] | 3 | [13 empty] | 0 | [5 empty] | 3 |  |  |  |  | Not Initiated
18.4 | UPGRADATION OF HT BREAKER PANEL AT OLD PROJECT OFFICE OF KHAPERKHEDA TPS. | Scheme |  |  |  | 2 | [7 empty] | RELIABILITY OF SYSTEM WILL IMPROVE AS ASSETS HAVE COMPLETED USEFUL SERVICE LIFE & PERFORMANCE HAS DEGRADED. |  |  |  |  | 0 | [5 empty] | 2 | [13 empty] | 0 | [5 empty] | 2 |  |  |  |  | Not Initiated
18.5 | Retrofitting of Existing L & T make LT MCC ACB by state or art ACB at U # 1 to 4 of Khaperkheda TPS. | Scheme |  |  |  | 3 | [7 empty] | RELIABILITY OF SYSTEM WILL IMPROVE AS ASSETS HAVE COMPLETED USEFUL SERVICE LIFE & PERFORMANCE HAS DEGRADED. |  |  |  |  | 0 | [5 empty] | 3 | [13 empty] | 0 | [5 empty] | 3 |  |  |  |  | Not Initiated
18.6 | Retrofitting of Existing ABB make LT MCC ACB by state or art ACB at U # 1 to 4 of Khaperkheda TPS. | Scheme |  |  |  | 2 | [7 empty] | 1.RELIABILITY OF SYSTEM WILL IMPROVE AS ASSETS HAVE COMPLETED USEFUL SERVICE LIFE & PERFORMANCE HAS DEGRADED. 2.AVAILABILITY OF ELECTRICAL SYSTEM WILL IMPROVE. |  |  |  |  | 0 | [5 empty] | 2 | [13 empty] | 0 | [5 empty] | 2 |  |  |  |  | Not Initiated
19 | ERECTION & COMMISIONING OF DRY TYPE CAST RESIN TRANSFORMERS FOR U # 1 TO 4 OF KHAPERKHEDA TPS & Design, Engineering, Supply, Erection, Testing & Commissioning of various Battery sets at Unit # 3 & 4 of Khaperkheda TPS. | DPR |  |  |  | 35 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
19.1 | PROCUREMENT OF DRY TYPE CAST RESIN TRANSFORMERS FOR U # 1 & 2 OF KHAPERKHEDA TPS. | Scheme |  |  |  | 4 | [7 empty] | 1.INSURANCE SPARE AVAILABILITY. 2.RELIABILITY OF SYSTEM WILL IMPROVE AS ASSETS HAVE COMPLETED USEFUL SERVICE LIFE & PERFORMANCE HAS DEGRADED. 3.AVAILABILITY OF ELECTRICAL SYSTEM WILL IMPROVE. |  |  |  |  | 0 | [5 empty] | 4 | [13 empty] | 0 | [5 empty] | 4 |  |  |  |  | Not Initiated
19.2 | PROCUREMENT OF DRY TYPE CAST RESIN TRANSFORMERS FOR U # 3 & 4 OF KHAPERKHEDA TPS. | Scheme |  |  |  | 4 | [7 empty] | 1.INSURANCE SPARE AVAILABILITY. 2.RELIABILITY OF SYSTEM WILL IMPROVE AS ASSETS HAVE COMPLETED USEFUL SERVICE LIFE & PERFORMANCE HAS DEGRADED. |  |  |  |  | 0 |  |  |  |  | 4 | [14 empty] | 0 |  |  |  |  | 4 | [5 empty] | Not Initiated
19.3 | PROCUREMENT OF VFD TRANSFORMERS FOR ID FAN MOTOR U#3&4 OF KHAPERKHEDA TPS. | Scheme |  |  |  | 2 | [7 empty] | 1.INSURANCE SPARE AVAILABILITY. 2.RELIABILITY OF SYSTEM WILL IMPROVE AS ASSETS HAVE COMPLETED USEFUL SERVICE LIFE & PERFORMANCE HAS DEGRADED. 3.SAVING OF GENERATION LOSS & DOWNTIME IN EVENT OF FAULT ON RUNNING TRANSFORMER. |  |  |  |  | 0 | [5 empty] | 1 | 1 | [12 empty] | 0 | [5 empty] | 1 | 1 |  |  |  | Not Initiated
19.4 | Design, Engineering, Supply, Erection, Testing & Commissioning of various Battery sets at Unit # 3 & 4 of Khaperkheda TPS. | Scheme |  |  |  | 25 | [7 empty] | 1.RELIABILITY OF DC SYSTEM WILL IMPROVE AS ASSETS HAVE COMPLETED USEFUL SERVICE LIFE & PERFORMANCE HAS DEGRADED. 2.Induction of new efficient technology. |  |  |  |  | 0 |  |  |  |  | 12.5 | 12.5 | [13 empty] | 0 |  |  |  |  | 12.5 | 12.5 |  |  |  |  | Not Initiated
20 | Study, Supply & Refurbishment of HCSD systems, ESP operation, ambience & various pump, & PLC schemes for the improvement of AHP-I at Khaperkheda TPS. | DPR |  |  |  | 28.65 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
20.1 | STUDY. DESIGN & REFURBISHMENT WORKS OF HIGH CONCENTRATION SLURRY DISPOSAL SYSTEM (HCSD SYSTEM) UNITS #3&4 AT AHP-1, TPS KHAPERKHEDA. | Scheme |  |  |  | 9.32 | [7 empty] | 1. To enhance availability of HCSD system . cleanliness of ambience 2. produce highly concentrated slurry hence water requirement is less. 3. Energy efficeient /saving as compare to lean slurry system. 4. Reduce the water and land pollution. 5. improve the reliabilty / MTBF 6. on time evacuationof ESPs due to availability of HCSD (GEHO pumps) |  |  |  |  | 0 |  |  |  |  | 9.32 | [14 empty] | 0 |  |  |  |  | 9.32 |  |  |  |  | Submitted to CE(Works) | Not Initiated
20.2 | STUDY, DESIGN & REFURBISHMENT WORKS OF ARTs AND ASSOCIATED MOUNTINGS & ACCESSORIES OF HCSD SYSTEM FOR AHP-I, TPS KHAPERKHEDA.” | Scheme |  |  |  | 8.96 | [7 empty] | 1. To enhance availability of HCSD system & cleanliness of ambience 2. assisted to produce highly concentrated slurry hence water requirement is less. 3. Energy efficeient /saving of eneergy compare to lean slurry system. 4. Reduce the water and land pollution. 5. improve the reliabilty / MTBF. 6. Enable On time evacuationof ESPs due to availability of HCSD (GEHO pumps) . 7. condition / closed monitoring . 8. Reduce material and maintenanace cost. |  |  |  |  | 0 |  |  |  |  | 8.96 | [14 empty] | 0 |  |  |  |  | 8.96 | [5 empty] | Not Initiated
20.3 | ‘SUPPLY & REFURBISHMENT WORKS OF HCSD ASH SLURRY MIXER SYSTEM AT UNIT #3 &4 OF AHP-I, TPS KHAPERKHEDA’. | Scheme |  |  |  | 2.85 | [7 empty] | 1. Helps to preapre homogenious slurry before GEHO , thus, enhance availability of HCSD system & cleanliness of ambience 2. assisted to produce highly concentrated slurry hence water requirement is less. 3. Energy efficeient /saving of eneergy compare to lean slurry system. 4. Reduce the water and land pollution. 5. improve the reliabilty / MTBF. 6. Enable On time evacuation of ESPs due to availability of HCSD (GEHO pumps) . 7. condition / closed monitoring . 8. Reduce material and maintenanace cost. |  |  |  |  | 0 |  |  |  |  | 2.85 | [14 empty] | 0 |  |  |  |  | 2.85 | [5 empty] | Not Initiated
20.4 | ‘STUDY, SUPPLY, RESTORATIONS & REPLACEMENT OF ALL INTERNAL SPARES OF D6 FIELD & RENOVATION OF D1 FIELD OF U3 DURING AOH FOR AHP-I, TPS KHAPERKHEDA’ | Scheme |  |  |  | 2.92 | [7 empty] | 1. To improve the available of D pasaa. 2. To reduce the Chimney SPM level. 3. To reduce overburden of other passes due to frequent maintenance of ESP internals. 4. To reduce the fly ash evacuation irregularities during operation of costomised station control system. 5. coarse ash collection in first filed thus more time / line chocking issues during unit running conditions |  |  |  |  | 0 |  |  |  |  | 2.92 | [14 empty] | 0 |  |  |  |  | 2.92 | [5 empty] | Not Initiated
20.5 | PROCUREMENT OF VARIOUS PUMPS IN RECYCLE WATER SYSTEM IN ASH HANDLING PLANT 4X210 MW AT KHAPARKHEDA TPS | Scheme |  |  |  | 4.6 | [7 empty] | 1) Water recycled will be used for ash evacuation through systems which is cheaper than raw water. 2) It will aso improve efficiency and reduce APC. |  |  |  |  | 0 |  |  |  |  | 4.6 | [14 empty] | 0 |  |  |  |  | 4.6 | [5 empty] | Not Initiated
21 | Reliability improvement and complete replacement of ABC series with drive unit of ash slurry pipeline of 7 KM of 4*210MW Khaperkheda TPS | DPR |  |  |  | 25 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
21.1 | Procurement and restoration of complete pipeline replacement of ABC series | Scheme |  |  |  | 20 | [7 empty] | 1) It will reduce the patch work of pipeline. 2) Pipeline is worn out and there are frequent leakages of ash slurry in public area through this series which attarcts hefty penalties from Regulators, 3)Also compensation to Farmers due to these leaked ash is burden on MSPGCL. Replacing the complete pipe line will not only save the penalties and compensation but will improve the overall credibility of Plant. |  |  |  |  | 0 |  |  |  |  | 20 | [14 empty] | 0 |  |  |  |  | 20 | [5 empty] | Not Initiated
21.2 | Procurement and restoration of complete drive unit replacement of ABC series | Scheme |  |  |  | 5 | [7 empty] | 1) Replacing Complete drive unit will increase efficiency and will save auxilary power consumption. |  |  |  |  | 0 |  |  |  |  | 5 | [14 empty] | 0 |  |  |  |  | 5 | [5 empty] | Not Initiated
22 | Procurement and restoration of complete Bottom ash hopper replacement including entire structure, Clinker grinder alongwith motor, Feed Gate, Power Cylinder and Pipelines discharge of U3&4 of 4*210MW Khaparkheda TPS. | DPR |  |  |  | 30.2 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
22.1 | Procurement and restoration of complete BAH replacement including entire structure and clinker griender | Scheme |  |  |  | 23 | [7 empty] | 1) No. Of forced shutdowns to attend leakages of BAH and CG will reduce to 20% i.e Shutdown cost for a day= 1.512 crs Total loss1.512 X 15=22.62 crs. Saving by implimenting the scheme=80% x 22.68=18.44 crs 2) BAH area is very critical and prone to accidental. By keeping it restored accidents will be reduced. |  |  |  |  | 0 | [6 empty] | 23 | [12 empty] | 0 | [6 empty] | 23 |  |  |  | Not Initiated
22.2 | Procurement and restoration of complete drive unit of clinker grinder for Unit 1 to 4 | Scheme | [11 empty] | 1) By restoring driving unit availability of CG will increase. Resulting minimum clinker formation. So load reduction to remove clinkers will be minimized. 2)Clinker formation=24/year. Load reduction = 30% minimum, load reduction period= 1.5 hrs. Total loss= 0.6804 crs. Reduction in load loss events= 80%. Total Savings=0.54432 crs |  |  |  |  | 0 |  |  |  |  | 1.6 | 1.6 | [13 empty] | 0 |  |  |  |  | 1.6 | 1.6 |  |  |  |  | Not Initiated
22.3 | Procurement and restoration of discharge pipeline of vertical sump pump | Scheme | [11 empty] | 1) Rep. 8 maintenance cost of pipe rotation and patching will be minimized. |  |  |  |  | 0 | [5 empty] | 4 | [13 empty] | 0 | [5 empty] | 4 |  |  |  |  | Not Initiated
23 | Procurement and restoration of Pipeline garlanding at Waregaon ash Bund of 4*210 MW Khapakheda TPS | DPR |  |  |  | 30 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
23.1 | Pipeline garlanding at Waregaon ash Bund of 4*210 MW Khapakheda TPS | Scheme |  |  |  | 30 | [7 empty] | 1)It will prevent the uneven distribution of ash being deposited in ash bund. 2)It will reduce the chances of breaching which will save penalties being imposed due to breaching. |  |  |  |  | 0 | [5 empty] | 15 | 15 | [12 empty] | 0 | [5 empty] | 15 | 15 |  |  |  | Not Initiated
24 | Upgradation, modification and erection of complete wet fly ash evacuation into dry fly ash evacuation systen for ESP 1 and 2 of 4*210 MW Khapakheda TPS. | DPR |  |  |  | 100 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
24.1 | Upgradation, modification and erection of complete wet fly ash evacuation into dry fly ash evacuation systen for ESP 1 and 2, 4*210 MW Khapakheda TPS | Scheme |  |  |  | 100 | [7 empty] | 1) Wastage of water will be reduced. 2) Fly ash utilization increased drastically. 3) Ash bund loading will be stopped. 4) Fly ash discharge line maintenance reduces drastically. 5) The pump loading reduces drastically resulting in APC. 60 nFly ash emmision via chimney reduces. |  |  |  |  | 0 | [5 empty] | 100 | [13 empty] | 0 | [5 empty] | 100 |  |  |  |  | Not Initiated
25 | Reliability improvement and complete replacement of JKL series with drive unit of ash slurry pipeline of 7 KM of 4*210MW Khaperkheda TPS | DPR |  |  |  | 25 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
25.1 | Procurement and restoration of complete pipeline replacement of JKL series | Scheme |  |  |  | 20 | [7 empty] | 1) It will reduce the patch work of pipeline. 2) Pipeline is worn out and there are frequent leakages of ash slurry in public area through this series which attarcts hefty penalties from Regulators, 3)Also compensation to Farmers due to these leaked ash is burden on MSPGCL. Replacing the complete pipe line will not only save the penalties and compensation but will improve the overall credibility of Plant. |  |  |  |  | 0 | [5 empty] | 20 | [13 empty] | 0 | [5 empty] | 20 |  |  |  |  | Not Initiated
25.2 | Procurement and restoration of complete drive unit replacement of JKL series | Scheme |  |  |  | 5 | [7 empty] | 1) Replacing Complete drive unit will increase efficiency and will save auxilary power consumption. |  |  |  |  | 0 | [5 empty] | 5 | [13 empty] | 0 | [5 empty] | 5 |  |  |  |  | Not Initiated
26 | Study, Supply and Refurbishment of HCSD System | DPR |  |  |  | 40 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
26.1 | Procurement of complete Suction and discharge valve of Geho pump | Scheme |  |  |  | 15 | [7 empty] | 1. To enhance availability of GEHO pumps. thus, Improve the availability of HCSD system. 2. highly concentrated slurry hence low water consumption. 3. Enrgy saving as compare to slurry system. 5. Reduce the frequent water and land pollution. 5. improve the reliabilty and improve the MTBF 6. on time evacuationof ESPs due to availability of HCSD (GEHO pumps) |  |  |  |  | 0 | [7 empty] | 15 | [11 empty] | 0 | [7 empty] | 15 |  |  | Not Initiated
26.2 | Procurement of Subassemblies of Geho pump. | Scheme |  |  |  | 10 | [7 empty] | 1. Helps to preapre homogenious slurry before GEHO 2. assisted to produce highly concentrated slurry hence water requirement is less. 3. Energy efficeient /saving of energy compare to lean slurry system. 4. Reduce the water and land pollution. 5. improve the reliabilty / MTBF. 6. Enable On time evacuation of ESPs due to availability of HCSD (GEHO pumps) . 7. condition / closed monitoring . 8. Reduce material and maintenanace cost. 9.To enhance availability of HCSD system & cleanliness of ambience. |  |  |  |  | 0 | [7 empty] | 10 | [11 empty] | 0 | [7 empty] | 10 |  |  | Not Initiated
26.3 | Upgradation and compressors of dry ash evacutaion system of U#3&4. | Scheme |  |  |  | 5 | [7 empty] | 1. To Ensure 100% the availability of pressurised dry ash evacuation system. 2. on time evacuation 3. Energy efficeient & energy saving compressors 4. Upgardation i.e capacity enhancement will reduce the operational cost 5. improve the reliabilty / improve the MTBF. 6. Enable On time evacuation of ESPs . 7. condition / closed monitoring . 8. Reduce material and maintenanace cost. 9.to enhance availability & cleanliness of ambience. |  |  |  |  | 0 | [6 empty] | 5 | [12 empty] | 0 | [6 empty] | 5 |  |  |  | Not Initiated
26.4 | Procuremenet of complete drive unit and VFD of GEHO pump. | Scheme |  |  |  | 10 | [7 empty] | 1. improve the reliabilty of GEH pumps 2. Energy efficeient / saving of energy compare to lean slurry system. 3. improve the reliabilty / MTBF. 4. Enable On time evacuation of ESPs due to availability of HCSD (GEHO pumps) . 5. Reduce material and frequent maintenanace cost. 6.To enhance availability of HCSD system & cleanliness of ambience. |  |  |  |  | 0 | [6 empty] | 10 | [12 empty] | 0 | [6 empty] | 10 |  |  |  | Not Initiated
27 | RENOVATION OF ESP FIELD INTERNALS FOR UNIT 3 & 4 | DPR |  |  |  | 60 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
27.1 | RENOVATION OF ESP FIELD INTERNALS FOR UNIT 3 & 4 | Scheme |  |  |  | 60 | [7 empty] | 1. To improve the available of D pass. 2. To reduce the overall Chimney SPM level. 3. To reduce overburden / maintenance of ESP internals. 3. clean environment / ambience 4. to Reduce the PCBs pollution related obligations & penalties thereof. 5. improve availabilties / healthiness of ESP 6. to improve oveall Flue gas cycle margin and unit load (MW) capacity. |  |  |  |  | 0 | [6 empty] | 30 | 30 | [11 empty] | 0 | [6 empty] | 30 | 30 |  |  | Not Initiated
28 | R & M OF APH OF UNIT # 1& 2 (2 x 210MW) | DPR |  |  |  | 36.8 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
28.1 | R & M OF APH OF UNIT # 1& 2 (2 x 210MW) OF KHAPERKHEDA TPS FROM MODEL: 27 VI 1850 TO 27 VI 2000 mm. DESIGN, ENGINEERING, SUPPLY, ERECTION & COMMISSIONING OF DOUBLE SEALING | Scheme |  |  |  | 36.8 | [7 empty] | 1. Renovation and modernization for life extension of entire project 2. Improvement In system parameters 3. Increase in Operational efficiency of existing system. |  |  |  |  | 0 | [6 empty] | 18.4 | 18.4 | [11 empty] | 0 | [6 empty] | 18.4 | 18.4 |  |  | Not Initiated
29 | DPR FOR ECONOMISER COILS AND APH GEAR BOX | DPR |  |  |  | 29 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
29.1 | PROCUREMENT AND REPLACEMENT OF COMPLETE SET OF ECONOMISER UPPER BANK & LOWER BANK COILS FOR KHAPERKHEDA TPS UNIT NO.3&4 | Scheme |  |  |  | 22 | [7 empty] | 1. Replacement of entire asset after completion of useful life and which has gone beyond repair. 2. Increase in Operational efficiency of existing system. |  |  |  |  | 0 |  |  |  | 11 | 11 | [14 empty] | 0 |  |  |  | 11 | 11 |  |  |  |  | Submitted to CE(Works) in FY 2022-23 but Data-Gap letter received on 30.11.2022. Reply sent on 6.5.23.Rate Rise is 47% per year. Revised estimation DPR cost only 18Cr. Hence DPR Returned back to TPS vide mail Dt. 19.3.2024 to club with other schemes.This revised DPR will be sent to CE(Works) soon | Not Initiated
29.2 | Procurement of APH gear box in unit no. 1 & 2 | Scheme |  |  |  | 2 | [7 empty] | 1. Reduction in maintenance requirements 2. Replacement of entire asset after completion of useful life and which has gone beyond repair. 3.Reduction in Generation loss due to non availability of Asset |  |  |  |  | 0 |  |  |  | 2 | [15 empty] | 0 |  |  |  | 2 | [5 empty] | Submitted to CE(Works) in FY 2022-23 but Data-Gap letter received on 30.11.2022. Reply sent on 6.5.23.Rate Rise is 47% per year. Revised estimation DPR cost only 18Cr. Hence DPR Returned back to TPS vide mail Dt. 19.3.2024 to club with other schemes.This revised DPR will be sent to CE(Works) soon | Not Initiated
29.3 | Procurement of APH speed reducer gear box in unit no. 3 & 4 | Scheme |  |  |  | 5 | [7 empty] | 1. Reduction in maintenance requirements 2. Replacement of entire asset after completion of useful life and which has gone beyond repair. 3.Reduction in Generation loss due to non availability of Asset |  |  |  |  | 0 |  |  |  | 2.5 | 2.5 | [14 empty] | 0 |  |  |  | 2.5 | 2.5 |  |  |  |  | Submitted to CE(Works) in FY 2022-23 but Data-Gap letter received on 30.11.2022. Reply sent on 6.5.23.Rate Rise is 47% per year. Revised estimation DPR cost only 18Cr. Hence DPR Returned back to TPS vide mail Dt. 19.3.2024 to club with other schemes.This revised DPR will be sent to CE(Works) soon | Not Initiated
30 | DPR FOR LTSH COILS , APH BASKETS & RH OUTLET STUB BENDS | DPR |  |  |  | 32 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
30.1 | Procurement of Air Pre-heater Baskets for unit no. 2 to 4 | Scheme |  |  |  | 11 | [7 empty] | 1.Replacement of entire asset after completion of useful life and which has gone beyond repair. 2. Increase in Operational efficiency of existing system. |  |  |  |  | 0 | [5 empty] | 3.5 | 3.75 | 3.75 | [11 empty] | 0 | [5 empty] | 3.5 | 3.75 | 3.75 |  |  | Not Initiated
30.2 | Procurement of LTSH coils for unit no. 1 & 2 and Procurement of Reheater outlet header stub bends for unit no. 1 to 2 | Scheme |  |  |  | 12 | [7 empty] | 1.Replacement of entire asset after completion of useful life and which has gone beyond repair. 2. Increase in Operational efficiency of existing system. |  |  |  |  | 0 | [6 empty] | 6 | 6 | [11 empty] | 0 | [6 empty] | 6 | 6 |  |  | Not Initiated
30.3 | Procurement of LTSH coils for unit no. 3 & 4 and Procurement of Reheater outlet header stub bends for unit no. 3 to 4 | Scheme |  |  |  | 9 | [7 empty] | 1.Replacement of entire asset after completion of useful life and which has gone beyond repair. 2. Increase in Operational efficiency of existing system. |  |  |  |  | 0 | [7 empty] | 9 | [11 empty] | 0 | [7 empty] | 9 |  |  | Not Initiated
31 | DPR FOR SUPPLY & REPLACMENT OF THERMAL INSULATION OF BOILER AND DUCT AT UNIT 1 TO 4 KHAPERKHEDA TPS | DPR |  |  |  | 40 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
31.1 | SUPPLY & REPLACMENT OF THERMAL INSULATION OF BOILER AND DUCT AT UNIT 1 TO 2KHAPERKHEDA TPS | Scheme |  |  |  | 20 | [7 empty] | 1. Replacement of entire asset after completion of useful life and which has gone beyond repair. 2. Increase in Operational efficiency of existing system. |  |  |  |  | 0 | [5 empty] | 20 | [13 empty] | 0 | [5 empty] | 20 |  |  |  |  | Not Initiated
31.2 | SUPPLY & REPLACMENT OF THERMAL INSULATION OF BOILER AND DUCT AT UNIT 3 TO 4 KHAPERKHEDA TPS | Scheme |  |  |  | 20 | [7 empty] | 1. Replacement of entire asset after completion of useful life and which has gone beyond repair. 2. Increase in Operational efficiency of existing system. |  |  |  |  | 0 | [5 empty] | 10 | 10 | [12 empty] | 0 | [5 empty] | 10 | 10 |  |  |  | Not Initiated
32 | DPR FOR COAL CYCLE IMPROVEMENT IN UNIT NO.1 TO 4 | DPR |  |  |  | 32.86 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
32.1 | Procurement of Complete Journal Assembly for 803 ½ HP Coal Mills of Unit No. 1 To 2 | Scheme |  |  |  | 3 | [7 empty] | 1. Replacement of entire asset after completion of useful life and which has gone beyond repair. 2. Increase in Operational efficiency of existing system. 3. Reduction in maintenance requirements 4. Improvement in power quality and reliability |  |  |  |  | 0 | [5 empty] | 3 | [13 empty] | 0 | [5 empty] | 3 |  |  |  |  | Not Initiated
32.2 | Procurement of Complete Journal Assembly for XRP 883 Coal Mills of Unit No. 3 To 4, | Scheme |  |  |  | 9.86 | [7 empty] | 1. Replacement of entire asset after completion of useful life and which has gone beyond repair. 2. Increase in Operational efficiency of existing system. 3. Reduction in maintenance requirements 4. Improvement in power quality and reliability |  |  |  |  | 0 | [6 empty] | 9.86 | [12 empty] | 0 | [6 empty] | 9.86 |  |  |  | Not Initiated
32.3 | Procurement of assembly of worm shaft & worm wheel with hub for unit no. 3 & 4 | Scheme |  |  |  | 5 | [7 empty] | 1. Reduction in maintenance requirements 2. Improvement in power quality and reliability 3. Improvement in power quality and reliability |  |  |  |  | 0 | [5 empty] | 2.5 | 2.5 | [12 empty] | 0 | [5 empty] | 2.5 | 2.5 |  |  |  | Not Initiated
32.4 | PROCUREMENT OF COMPLETE GEAR BOX ASSEMBLIES OF COAL MILLS XRP 803 ½ HP FOR UNIT # 1 TO 2 AT KHAPERKHEDA TPS | Scheme |  |  |  | 7.5 | [7 empty] | 1. Replacement of entire asset after completion of useful life and which has gone beyond repair. 2. Increase in Operational efficiency of existing system. 3. Reduction in maintenance requirements 4. Improvement in power quality and reliability |  |  |  |  | 0 | [5 empty] | 7.5 | [13 empty] | 0 | [5 empty] | 7.5 |  |  |  |  | Not Initiated
32.5 | PROCUREMENT OF COMPLETE GEAR BOX ASSEMBLIES OF COAL MILLS XRP 883 FOR UNIT # 3 TO 4 AT KHAPERKHEDA TPS | Scheme |  |  |  | 7.5 | [7 empty] | 1. Replacement of entire asset after completion of useful life and which has gone beyond repair. 2. Increase in Operational efficiency of existing system. 3. Reduction in maintenance requirements 4. Improvement in power quality and reliability |  |  |  |  | 0 | [5 empty] | 7.5 | [13 empty] | 0 | [5 empty] | 7.5 |  |  |  |  | Not Initiated
33 | DPR FOR PERFORMANCE IMPROVEMENT OF BOILER PA FAN, ID FAN AND FD FAN IN UNIT NO. 1 TO 4 | DPR |  |  |  | 76.06 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
33.1 | Procurement of PA fan Casings along with Dampers in Unit- 1 & 2, at Khaperkheda TPS | Scheme |  |  |  | 17.75 | [7 empty] | 1. Replacement of the entire asset after completion of Useful Life and which has gone beyond repair. 2. Reduction in maintenance requirements 3. Increase in operational efficiency of existing system |  |  |  |  | 0 | [5 empty] | 17.75 | [13 empty] | 0 | [5 empty] | 17.75 |  |  |  |  | Not Initiated
33.2 | PROCUREMENT OF COMPLETE ROTOR ASSEMBLY ALONG WITH MOTOR FOR NDZV 31 SIDOR IN UNIT NO. 1 & 2 KHAPERKHEDA TPS (ID FAN) | Scheme |  |  |  | 25 | [7 empty] | 1. Replacement of the entire asset after completion of Useful Life and which has gone beyond repair 2. Reduction in maintenance requirements 3. Increase in operational efficiency of existing system |  |  |  |  | 0 | [5 empty] | 25 | [13 empty] | 0 | [5 empty] | 25 |  |  |  |  | Not Initiated
33.3 | PROCUREMENT OF FD FAN (BHEL AP 1-20 / 11) ASSEMBLY ALONG WITH DRIVE UNIT(MOTOR) FOR UNIT 1 & 2 AT KHAPERKHEDA TPS UNDER OEM NATURE ITEMS | Scheme |  |  |  | 10 | [7 empty] | 1. Replacement of entire asset after completion of useful life and which has gone beyond repair. 2. Increase in Operational efficiency of existing system. 3. Increase in the Useful Life of the entire project/scheme/assets 4. Improvement in power quality and reliability |  |  |  |  | 0 | [5 empty] | 10 | [13 empty] | 0 | [5 empty] | 10 |  |  |  |  | Not Initiated
33.4 | PROCUREMENT OF FD FAN (BHEL AP 1-20 / 11) ASSEMBLY ALONG WITH DRIVE UNIT(MOTOR) FOR UNIT 3& 4 AT KHAPERKHEDA TPS UNDER OEM NATURE ITEMS | Scheme |  |  |  | 10 | [7 empty] | 1. Replacement of entire asset after completion of useful life and which has gone beyond repair. 2. Increase in Operational efficiency of existing system. 3. Increase in the Useful Life of the entire project/scheme/assets 4. Improvement in power quality and reliability |  |  |  |  | 0 | [6 empty] | 10 | [12 empty] | 0 | [6 empty] | 10 |  |  |  | Not Initiated
33.5 | NDZV 33 SIDOR ID Fan Impeller Assembly for Unit 3 & 4 at TPS, Khaperkheda | Scheme |  |  |  | 7.28 | [7 empty] | 1. Replacement of entire asset after completion of useful life and which has gone beyond repair. 2. Increase in Operational efficiency of existing system. 3. Increase in the Useful Life of the entire project/scheme/assets 4. Improvement in power quality and reliability |  |  |  |  | 0 | [6 empty] | 7.28 | [12 empty] | 0 | [6 empty] | 7.28 |  |  |  | Not Initiated
33.6 | Design, Engineering, Manufacturing, Supply & Commissioning including civil works for installation of 70 LPM lubricant ystems for PA Fans in unit no. 1&2. | Scheme |  |  |  | 1.38 | [7 empty] | 1. Renovation and Modernisation for life extension of entire project 2. Increase in operational efficiency of existing system |  |  |  |  | 0 | [6 empty] | 1.38 | [12 empty] | 0 | [6 empty] | 1.38 |  |  |  | Not Initiated
33.7 | Supply and installation of ID and PA foundation deck spring for unit no. 3 & 4 | Scheme |  |  |  | 4.65 | [7 empty] | 1. Replacement of entire asset after completion of useful life and which has gone beyond repair. 2. Increase in Operational efficiency of existing system. 3. Increase in the Useful Life of the entire project/scheme/assets 4. Improvement in power quality and reliability |  |  |  |  | 0 | [7 empty] | 4.65 | [11 empty] | 0 | [7 empty] | 4.65 |  |  | Not Initiated
34 | VARIOUS SCHEMES FOR BOILER PERFORMANCE IMPROVEMENT | DPR |  |  |  | 43.28 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
34.1 | SUPPLY OF COAL MILL SEPERATOR & SCRAPPER BODIES FOR XRP-803 1/2 HP COAL MILLS IN UNIT 1 & 2 | Scheme |  |  |  | 17.28 | [7 empty] | 1. Replacement of entire asset after completion of useful life and which has gone beyond repair. 2. Increase in Operational efficiency of existing system. 3. Increase in the Useful Life of the entire project/scheme/assets 4. Improvement in power quality and reliability |  |  |  |  | 0 | [5 empty] | 17.28 | [13 empty] | 0 | [5 empty] | 17.28 |  |  |  |  | Not Initiated
34.2 | MODIFICATION OF EXISTING COAL BUNKER AND COMMISSIONING OF BUNKER CHUTE ASSEMBLY WITH VIBRATING MOTOR TO AVOID BUNKER MOUTH COAL CHOKE UP FOR UNIT 1 & 2AT KHAPERKHEDA TPS. | Scheme |  |  |  | 9 | [7 empty] | 1. Renovation and Modernisation for life extension of entire project 2. Increase in operational efficiency of existing system |  |  |  |  | 0 | [6 empty] | 9 | [12 empty] | 0 | [6 empty] | 9 |  |  |  | Not Initiated
34.3 | MODIFICATION OF EXISTING COAL BUNKER AND COMMISSIONING OF BUNKER CHUTE ASSEMBLY WITH VIBRATING MOTOR TO AVOID BUNKER MOUTH COAL CHOKE UP FOR UNIT 3 & 4 AT KHAPERKHEDA TPS. | Scheme |  |  |  | 9 | [7 empty] | 1. Renovation and Modernisation for life extension of entire project 2. Increase in operational efficiency of existing system |  |  |  |  | 0 | [5 empty] | 9 | [13 empty] | 0 | [5 empty] | 9 |  |  |  |  | Not Initiated
34.4 | DESIGN, DEVELOPMENT, COMMISIONING OF SEAL AIR FAN ASSEMBLIES IN UNIT 1 & 2 | Scheme |  |  |  | 4 | [7 empty] | 1. Renovation and Modernisation for life extension of entire project 2. Increase in operational efficiency of existing system 3. Reduction in maintenance requirements |  |  |  |  | 0 | [5 empty] | 4 | [13 empty] | 0 | [5 empty] | 4 |  |  |  |  | Not Initiated
34.5 | Procurement of sub body assembly of control valve in unit no. 1 & 2 actuating main gear unit part electrical actuator in unit no. 1 to 4 Khaperkheda TPS | Scheme |  |  |  | 4 | [7 empty] | 1. Increase in operational efficiency of existing system 2. Reduction in maintenance requirements |  |  |  |  | 0 | [5 empty] | 4 | [13 empty] | 0 | [5 empty] | 4 |  |  |  |  | Not Initiated
35 | Construction of A, B, C, D & E type stilt + 6 floor buildings at TPS Khaperkheda. | DPR |  |  |  | 180 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
35.1 | Construction of A, B, C, D & E type stilt + 6 floor buildings at TPS Khaperkheda. | Scheme |  |  |  | 180 | [7 empty] | 1. New Infrastructure to meet upcoming load; 2. Increase in operational efficiency of existing system; 3. Replacement of the entire asset after completion of Useful Life and which has gone beyond repair; 4. Reduction in maintenance requirements; 5. Renovation and Modernisation for life extension of entire project; 6.Construction of new Civil infrastructure |  |  |  |  | 0 | [5 empty] | 180 | [13 empty] | 0 | [5 empty] | 180 |  |  |  |  | Not Initiated
36 | Enhancement & Renovation of existing building, Construction of Market building, Construction of club building community hall, Construction of school building, & Enhancement of existing domestic plant providing V wire 3 MLD at Colony TPS Khaperkheda. | DPR |  |  |  | 48 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
36.1 | Enhancement / Renovation & strengthening of existing building & allied works in colony TPS Khaperkhda. | Scheme |  |  |  | 28 | [7 empty] | 1. Increase in operational efficiency of existing system; 2. Replacement of the entire asset after completion of Useful Life and which has gone beyond repair; 3. Reduction in maintenance requirements; 4. Renovation and Modernisation for life extension of entire project; 5.Fulfilment of any statutory compliance requirement; |  |  |  |  | 0 |  |  |  |  | 28 | [14 empty] | 0 |  |  |  |  | 28 | [5 empty] | Not Initiated
36.2 | Construction of Market building including approach road, drainage arrangement & electrification at colony TPS Khaperkheda | Scheme |  |  |  | 6 | [7 empty] | 1. New Infrastructure to meet upcoming load; 2. Increase in operational efficiency of existing system; 3. Replacement of the entire asset after completion of Useful Life and which has gone beyond repair; 4. Reduction in maintenance requirements; 5. Renovation and Modernisation for life extension of entire project; 6.Construction of new Civil infrastructure |  |  |  |  | 0 |  |  |  |  | 6 | [14 empty] | 0 |  |  |  |  | 6 | [5 empty] | Not Initiated
36.3 | Construction of club building / community hall | Scheme |  |  |  | 8 | [7 empty] | 1. New Infrastructure to meet upcoming load; 2. Increase in operational efficiency of existing system; 3. Replacement of the entire asset after completion of Useful Life and which has gone beyond repair; 4. Reduction in maintenance requirements; 5. Renovation and Modernisation for life extension of entire project; 6.Construction of new Civil infrastructure |  |  |  |  | 0 | [5 empty] | 8 | [13 empty] | 0 | [5 empty] | 8 |  |  |  |  | Not Initiated
36.4 | Construction of school building | Scheme |  |  |  | 3 | [7 empty] | 1. New Infrastructure to meet upcoming load; 2. Increase in operational efficiency of existing system; 3. Replacement of the entire asset after completion of Useful Life and which has gone beyond repair; 4. Reduction in maintenance requirements; 5. Renovation and Modernisation for life extension of entire project; 6.Construction of new Civil infrastructure |  |  |  |  | 0 | [5 empty] | 3 | [13 empty] | 0 | [5 empty] | 3 |  |  |  |  | Not Initiated
36.5 | Enhancement of existing domestic plant providing V wire 3 MLD | Scheme |  |  |  | 3 | [7 empty] | 1. New Infrastructure to meet upcoming load; 2. Increase in operational efficiency of existing system; 3. Replacement of the entire asset after completion of Useful Life and which has gone beyond repair; 4. Reduction in maintenance requirements; 5. Renovation and Modernisation for life extension of entire project; 6.Construction of new Civil infrastructure |  |  |  |  | 0 |  |  |  |  | 3 | [14 empty] | 0 |  |  |  |  | 3 | [5 empty] | Not Initiated
37 | Enhancement / Renovation of Saudamini Administrative Building, Construction of VIP Guest House, Construction of roads at Prakashnagar Colony and Providing various civil works related to coal transport railway lines of khaperkheda TPSTPS Khaperkheda. | DPR |  |  |  | 35 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
37.1 | Enhancement / Renovation of Saudamini building | Scheme |  |  |  | 7 | [7 empty] | 1. Increase in operational efficiency of existing system; 2. Replacement of the entire asset after completion of Useful Life and which has gone beyond repair; 3. Reduction in maintenance requirements; 4. Renovation and Modernisation for life extension of entire project; 5.Fulfilment of any statutory compliance requirement; |  |  |  |  | 0 |  |  |  | 7 | [15 empty] | 0 |  |  |  | 7 | [6 empty] | Not Initiated
37.2 | Construction of VIP guest house TPS Khaperkheda. | Scheme |  |  |  | 5 | [7 empty] | 1. New Infrastructure to meet upcoming load; 2. Increase in operational efficiency of existing system; 3. Replacement of the entire asset after completion of Useful Life and which has gone beyond repair; 4. Reduction in maintenance requirements; 5. Renovation and Modernisation for life extension of entire project; 6.Construction of new Civil infrastructure |  |  |  |  | 0 |  |  |  |  | 5 | [14 empty] | 0 |  |  |  |  | 5 | [5 empty] | Not Initiated
37.3 | Construction of Roads | Scheme |  |  |  | 13 | [7 empty] | 1. New Infrastructure to meet upcoming load; 2. Increase in operational efficiency of existing system; 3. Replacement of the entire asset after completion of Useful Life and which has gone beyond repair; 4. Reduction in maintenance requirements; 5. Renovation and Modernisation for life extension of entire project; 6.Construction of new Civil infrastructure |  |  |  |  | 0 |  |  |  |  | 13 | [14 empty] | 0 |  |  |  |  | 13 | [5 empty] | Not Initiated
37.4 | Construction of office building & store for electrical maintenance & Civil at KPKD | Scheme |  |  |  | 2.5 | [7 empty] | 1. New Infrastructure to meet upcoming load; 2. Increase in operational efficiency of existing system; 3. Replacement of the entire asset after completion of Useful Life and which has gone beyond repair; 4. Reduction in maintenance requirements; 5. Renovation and Modernisation for life extension of entire project; 6.Construction of new Civil infrastructure |  |  |  |  | 0 |  |  |  | 2.5 | [15 empty] | 0 |  |  |  | 2.5 | [6 empty] | Not Initiated
37.5 | Providing Special repair & retrofitting work of river bridge no.09 on Khaperkheda - Kalumna railway siding of TPS Khaperkheda. | Scheme |  |  |  | 1.5 | [7 empty] | 1. Increase in operational efficiency of existing system; 2. Replacement of the entire asset after completion of Useful Life and which has gone beyond repair; 3. Reduction in maintenance requirements; 4. Renovation and Modernisation for life extension of entire project; 5.Fulfilment of any statutory compliance requirement; |  |  |  |  | 0 |  |  |  | 1.5 | [15 empty] | 0 |  |  |  | 1.5 | [6 empty] | Not Initiated
37.6 | Construction & repairing of drains & culverts along coal Transporting Railway lines & approach road of TPS Khaperkheda. | Scheme |  |  |  | 2.5 | [7 empty] | 1. Increase in operational efficiency of existing system; 2. Replacement of the entire asset after completion of Useful Life and which has gone beyond repair; 3. Reduction in maintenance requirements; 4. Renovation and Modernisation for life extension of entire project; 5.Fulfilment of any statutory compliance requirement; |  |  |  |  | 0 |  |  |  |  | 2.5 | [14 empty] | 0 |  |  |  |  | 2.5 | [5 empty] | Not Initiated
37.7 | Repairing, providing & applying Epoxy Painting and Structural Steel Works to steel structural bridges on kpkd to Kaluma and kpkd to Saoner railway lines as per recommendation of structural stability report at TPS Khaperkheda. | Scheme |  |  |  | 1 | [7 empty] | 1. Increase in operational efficiency of existing system; 2. Replacement of the entire asset after completion of Useful Life and which has gone beyond repair; 3. Reduction in maintenance requirements; 4. Renovation and Modernisation for life extension of entire project; 5.Fulfilment of any statutory compliance requirement; |  |  |  |  | 0 |  |  |  |  | 1 | [14 empty] | 0 |  |  |  |  | 1 | [5 empty] | Not Initiated
37.8 | Construction of compound wall KPKD Colony | Scheme |  |  |  | 2.5 | [7 empty] | 1. Increase in operational efficiency of existing system; 2. New infrastructure for enhancement of security; 3. Reduction in maintenance requirements; 4. Renovation and Modernisation for life extension of entire project; 5.Fulfilment of any statutory compliance requirement; |  |  |  |  | 0 |  |  |  |  | 2.5 | [14 empty] | 0 |  |  |  |  | 2.5 | [5 empty] | Not Initiated
38 | Work of Strengthening and modification of Main Plant, construction of roads, strengthening of IDCT 1 to 4 in plant area, 4x210 MW, TPS, Khaperkheda. | DPR |  |  |  | 54.01 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
38.1 | Work of attending additional works based on structural report at Induced Draft Cooling Towers(IDCT) unit 1,2,3 & 4 at 4 x 210MW, TPS, Khaperkheda. | Scheme |  |  |  | 1.21 | [7 empty] | 1. Increase in operational efficiency of existing system; 2. Replacement of the entire asset after completion of Useful Life and which has gone beyond repair; 3. Reduction in maintenance requirements; 4. Renovation and Modernisation for life extension of entire project; 5.Fulfilment of any statutory compliance requirement; |  |  |  |  | 0 |  |  |  |  | 1.21 | [14 empty] | 0 |  |  |  |  | 1.21 | [5 empty] | Not Initiated
38.2 | Work of constructon of roadside drains from VIP gate no.3 to IDCT No.1 at 4 x 210MW TPS Khaperkheda. | Scheme |  |  |  | 3.61 | [7 empty] | 1. Increase in operational efficiency of existing system; 2. Replacement of the entire asset after completion of Useful Life and which has gone beyond repair; 3. Reduction in maintenance requirements; 4. Renovation and Modernisation for life extension of entire project; 5.Fulfilment of any statutory compliance requirement; |  |  |  |  | 0 |  |  |  | 3.61 | [15 empty] | 0 |  |  |  | 3.61 | [6 empty] | Not Initiated
38.3 | Construction of bituminous macadam road from Administrative Building to GCR Road near Service Building of 4X210MW TPS Khaperkheda. | Scheme |  |  |  | 2.7 | [7 empty] | 1. Increase in operational efficiency of existing system; 2. Replacement of the entire asset after completion of Useful Life and which has gone beyond repair; 3. Reduction in maintenance requirements; 4. Renovation and Modernisation for life extension of entire project; 5.Fulfilment of any statutory compliance requirement; |  |  |  |  | 0 |  |  |  | 2.7 | [15 empty] | 0 |  |  |  | 2.7 | [6 empty] | Not Initiated
38.4 | Work for Construction of cement concrete road for equipment movement for salt lagoon (WTP-I), FGD(System), H2(cylinders) plant etc. inside plant premises in 4x 210MW, TPS, Khaperkheda. | Scheme |  |  |  | 3.63 | [7 empty] | 1. New Infrastructure to meet upcoming load; 2. Increase in operational efficiency of existing system; 3. Replacement of the entire asset after completion of Useful Life and which has gone beyond repair; 4. Reduction in maintenance requirements; 5. Renovation and Modernisation for life extension of entire project; 6.Construction of new Civil infrastructure |  |  |  |  | 0 |  |  |  | 3.63 | [15 empty] | 0 |  |  |  | 3.63 | [6 empty] | Not Initiated
38.5 | Construction of cement concrete road outside BTG area of Power Plant 4 x 210MW TPS Khaperkheda. | Scheme |  |  |  | 8.92 | [7 empty] | 1. New Infrastructure to meet upcoming load; 2. Increase in operational efficiency of existing system; 3. Replacement of the entire asset after completion of Useful Life and which has gone beyond repair; 4. Reduction in maintenance requirements; 5. Renovation and Modernisation for life extension of entire project; 6.Construction of new Civil infrastructure |  |  |  |  | 0 |  |  |  |  | 8.92 | [14 empty] | 0 |  |  |  |  | 8.92 | [5 empty] | Not Initiated
38.6 | Construction of cement concrete road for material transportation from D-Point CHP to reject coal Dumping yard in 4x 210MW, TPS, Khaperkheda. | Scheme |  |  |  | 5.94 | [7 empty] | 1. New Infrastructure to meet upcoming load; 2. Increase in operational efficiency of existing system; 3. Replacement of the entire asset after completion of Useful Life and which has gone beyond repair; 4. Reduction in maintenance requirements; 5. Renovation and Modernisation for life extension of entire project; 6.Construction of new Civil infrastructure . |  |  |  |  | 0 |  |  |  | 5.94 | [15 empty] | 0 |  |  |  | 5.94 | [6 empty] | Not Initiated
38.7 | Work of Strengthening and modification of Main Plant, Major Stores, Auxiliary in plant area, 4x210 MW, TPS, Khaperkheda. | Scheme |  |  |  | 10 | [7 empty] | 1. Increase in operational efficiency of existing system; 2. Replacement of the entire asset after completion of Useful Life and which has gone beyond repair; 3. Reduction in maintenance requirements; 4. Renovation and Modernisation for life extension of entire project; 5.Fulfilment of any statutory compliance requirement; |  |  |  |  | 0 |  |  |  |  | 10 | [14 empty] | 0 |  |  |  |  | 10 | [5 empty] | Not Initiated
38.8 | Construction of diversion road along with RCC bridge from rejct coal yard CHP-I & CHP-II | Scheme |  |  |  | 15 | [7 empty] | 1. New Infrastructure to meet upcoming load; 2. Increase in operational efficiency of existing system; 3. Replacement of the entire asset after completion of Useful Life and which has gone beyond repair; 4. Reduction in maintenance requirements; 5. Renovation and Modernisation for life extension of entire project; 6.Construction of new Civil infrastructure . |  |  |  |  | 0 |  |  |  |  | 15 | [14 empty] | 0 |  |  |  |  | 15 | [5 empty] | Not Initiated
38.9 | Upgradation of existing ETP plant consist civil works, electrification and pumps. | Scheme |  |  |  | 3 | [7 empty] | 1. New Infrastructure to meet upcoming load; 2. Increase in operational efficiency of existing system; 3. Replacement of the entire asset after completion of Useful Life and which has gone beyond repair; 4. Reduction in maintenance requirements; 5. Renovation and Modernisation for life extension of entire project; 6.Construction of new Civil infrastructure . |  |  |  |  | 0 |  |  |  |  | 3 | [14 empty] | 0 |  |  |  |  | 3 | [5 empty] | Not Initiated
39 | Work of 5th Raising of Waregaon Ash Bund, 4x210 MW, TPS, Khaperkheda. | DPR |  |  |  | 150 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
39.1 | Work of 5th Raising of Waregaon Ash Bund, 4x210 MW, TPS, Khaperkheda. | Scheme |  |  |  | 150 | [7 empty] | 1. New Infrastructure to meet upcoming load; 2. Increase in operational efficiency of existing system; 3. Replacement of the entire asset after completion of Useful Life and which has gone beyond repair; 4. Reduction in maintenance requirements; 5. Renovation and Modernisation for life extension of entire project; 6.Construction of new Civil infrastructure . |  |  |  |  | 0 |  |  |  |  | 150 | [14 empty] | 0 |  |  |  |  | 150 | [5 empty] | Not Initiated
40 | Work of CTR(Complete Track Removal),TTR(TRAIN TRAVLER REGULATOR) and Yard Remoulding incl. misc. works at Mahagenco Khaperkheda Plant. | DPR |  |  |  | 178 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
40.1 | Work of CTR(Complete Track Removal),TTR(TRAIN TRAVLER REGULATOR) and Yard Remoulding incl. misc. works at Mahagenco Khaperkheda Plant. | Scheme | [11 empty] | 1. New Infrastructure to meet upcoming load; 2. Increase in operational efficiency of existing system; 3. Replacement of the entire asset after completion of Useful Life and which has gone beyond repair; 4. Reduction in maintenance requirements; 5. Renovation and Modernisation for life extension of entire project; 6.Construction of new Civil infrastructure . |  |  |  |  | 0 |  |  |  |  | 178 | [14 empty] | 0 |  |  |  |  | 178 | [5 empty] | Not Initiated
41 | Various WTP 210MW improvement schemes i.e. Up-gradation of SWAS SYSTEM UNIT- 1 to 4 at WTP-I 210 MW along with coal sampling lab upgradation, Comissioning of CW Chemical Dosing system etc | DPR |  |  |  | 38.5 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
41.1 | Upgradation of Existing ETP system viz. Plate Settler, Settling tank, Sludge Drying bed, Chemical dosing system etc.)as per MPCB consent condition | Scheme |  |  |  | 5 | [12 empty] | 0 |  |  |  | 5 | [15 empty] | 0 |  |  |  | 5 | [6 empty] | Not Initiated
41.2 | Upgradation of SWAS Lab 3& 4 at WTP-210 MW | Scheme |  |  |  | 9 | [12 empty] | 0 |  |  |  | 9 | [15 empty] | 0 |  |  |  | 9 | [6 empty] | Not Initiated
41.3 | Revamping of Chlorination Plant Stream (A+ B) & Installation, Comissioning of CW Chemical Dosing system (Viz. Scale inhibitor, Scale Dispersant, Biodispersant, Corossion Inhibitor & H2SO4 dosing) and Online CW Chemical parameter monitoring system at KPKD TPS | Scheme |  |  |  | 7 | [12 empty] | 0 |  |  |  |  | 7 | [14 empty] | 0 |  |  |  |  | 7 | [5 empty] | Not Initiated
41.4 | Upgradation of SWAS Lab 1& 2 at WTP-210 MW | Scheme |  |  |  | 9 | [12 empty] | 0 |  |  |  |  | 9 | [14 empty] | 0 |  |  |  |  | 9 | [5 empty] | Not Initiated
41.5 | Upgradation of Water &Coal testing Lab at WTP-210 MW &Procurement of Coal Lab Instruments and upgradation of coal sampling Room & Instruments related to Coal sample Preparation. at WTP-210 MW | Scheme |  |  |  | 8.5 | [12 empty] | 0 | [5 empty] | 8.5 | [13 empty] | 0 | [5 empty] | 8.5 |  |  |  |  | Not Initiated
42 | Work of capacity restoration of unloading stream from Beetle Charger No. 1 to Stacker/Reclaimer No. 1 for perfromance improvement of CHP-I (4 x 210 MW) & Capacity restoration of unloading stream from Beetle Charger No. 1 to Stacker/Reclaimer No. 1 for perfromance improvement of CHP-I (4 x 210 MW). | DPR |  |  |  | 84 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
42.1 | Revamping/ refurbishment, capacity restoration and upgradation for beetle charger No. 1 | Scheme |  |  |  | 3 | [7 empty] | 1. As the plant is 33 years old and in service, the availability of beetle charger system is reduced. 2. Availability of beetle charge will help to increase in wagon unloading and benefit to save the demurrage charges of 5.35 Crs. Can be realized in one year. |  |  |  |  | 0 |  |  |  |  | 3 | [14 empty] | 0 |  |  |  |  | 3 | [5 empty] | Not Initiated
42.2 | Revamping/ refurbishment, capacity restoration and upgradation for Wagon Tippler No. 1 | Scheme |  |  |  | 6 | [7 empty] | 1. As the plant is 33 years old and in service, the availability of wagon tippler is reduced. 2. Availability of wagon tippler will help to increase in wagon unloading and benefit to save the demurrage charges of 5.35 Crs. Can be realized in one year. |  |  |  |  | 0 |  |  |  | 6 | [15 empty] | 0 |  |  |  | 6 | [6 empty] | Not Initiated
42.3 | Revamping/ refurbishment, capacity restoration and upgradation for Apron Feeder No. 1 | Scheme |  |  |  | 3 | [7 empty] | 1. As the plant is 33 years old and in service, the availability of apron feeder is reduced. 2. Availability of apron feeder will benefit to save the demurrage charges of 5.35 Crs. Can be realized in one year. |  |  |  |  | 0 |  |  |  |  | 3 | [14 empty] | 0 |  |  |  |  | 3 | [5 empty] | Not Initiated
42.4 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 2C, 3A, 4A, 8A, 9 | Scheme |  |  |  | 25 | [7 empty] | 1. As the plant is 33 years old and in service, the availability of unloading conveyors are reduced and also reduced the coal carrying capacity. 2. Upgradation of conveyor system will restore the coal carrying capacity. 3. Also benefit to save the demurrage charges of 5.35 Crs. Can be realized in one year. |  |  |  |  | 0 |  |  |  | 25 | [15 empty] | 0 |  |  |  | 25 | [6 empty] | Not Initiated
42.5 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for impact crusher and wobbler feeder No. 1 & 3 | Scheme |  |  |  | 7 | [7 empty] | 1. As the plant is 33 years old and in service, the availability of impact crusher & wobbler feeder is reduced. 2. Upgradation of impact crusher & wobbler feeder will increase the availabilityf of system. 3. Also benefit to save the demurrage charges of 5.35 Crs. Can be realized in one year. |  |  |  |  | 0 |  |  |  |  | 7 | [14 empty] | 0 |  |  |  |  | 7 | [5 empty] | Not Initiated
42.6 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Stacker/Reclaimer No. 1. | Scheme |  |  |  | 10 | [7 empty] | 1. As the plant is 33 years old and in service, the availability of Stacker/Reclaimer is reduced. 2. Upgradation of Stakcer/ Reclaimer will increase the availability of system. 3. Also benefit to save the demurrage charges of 5.35 Crs. Can be realized in one year. |  |  |  |  | 0 |  |  |  | 10 | [15 empty] | 0 |  |  |  | 10 | [6 empty] | Not Initiated
42.7 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv. 3C to 3A, Conv. 3A to 4A, Conv. 4A to 8A and Conv. 9 by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | Scheme |  |  |  | 10 | [7 empty] | 1. As the plant is 33 years old and in service, the most of the chutes are worn out and beyond repair. Hence coal spillage is increase. 2. Replacement of modular chutes will help to avoid the coal spillage and improvement of cleaning. 3. Also benefit to save material & maintenance cost and also the demurrage charges of 5.35 Crs. Can be realized in one year. |  |  |  |  | 0 |  |  |  |  | 10 | [14 empty] | 0 |  |  |  |  | 10 | [5 empty] | Not Initiated
42.8 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of beetle Charger, wagon tippler, apron feeder, covneyors (Conv. 2C, 3A, 4A, 8A, 9), crushers/ wobbler feeder No. 1 & 3 and Stacker/Reclaimer No. 1 in CHP-1 (4 x 210 MW) | Scheme |  |  |  | 20 | [7 empty] | 1. As the plant is 33 years old and in service, the most of the cables, feeder, panels are under capacity and frequent breakdown occurs. 2. Also the spare parts of existing feeders are obsolete and available in market. 3. Upgradation of system will help to increase in availabilty of system. 4. Also benefit to save material & maintenance cost and also the demurrage charges of 5.35 Crs. Can be realized in one year. |  |  |  |  | 0 |  |  |  |  | 20 | [14 empty] | 0 |  |  |  |  | 20 | [5 empty] | Not Initiated
43 | DPR fo Capacity restoration of bunkering stream from Conv. 5A to 7A/B/C/D including shuttle conveyors in CHP-I (4 x 210 MW) | DPR |  |  |  | 45 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
43.1 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 5A, 6B, 7A, 7B, 7C, 7D and Shuttle Conv. 1 to 4 in CHP-I (4 x 210 MW) | Scheme |  |  |  | 25 | [7 empty] | 1. As the plant is 33 years old and in service, the availability of bunkering conveyors are reduced and also reduced the coal carrying capacity. 2. Upgradation of conveyor system will restore the coal carrying capacity. 3. Also benefit to save the generation loss of 32 Crs. and demurrage charges of 5.35 Crs. Can be realized in one year. |  |  |  |  | 0 |  |  |  | 25 | [15 empty] | 0 |  |  |  | 25 | [6 empty] | Not Initiated
43.2 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv.Conv. 4D to 5A/B , 5A to 6B, Conv. 6B to 7A & 7B, Conv. 7B to 7D upto shuttle conveyor, Conv. 7A to 7C upto shuttle conveyor by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | Scheme |  |  |  | 10 | [7 empty] | 1. As the plant is 33 years old and in service, the most of the chutes are worn out and beyond repair. Hence coal spillage is increase. 2. Replacement of modular chutes will help to avoid the coal spillage and improvement of cleaning. 3. Also benefit to save material & maintenance cost, also the generation loss will reduced and demurrage charges of 5.35 Crs. Can be realized in one year. |  |  |  |  | 0 |  |  |  |  | 10 | [14 empty] | 0 |  |  |  |  | 10 | [5 empty] | Not Initiated
43.3 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of covneyors (Conv. 5A, 6B, 7A/B/C/D & Shuttle Conv. 1 to 4 in CHP-1 (4 x 210 MW) | Scheme |  |  |  | 10 | [7 empty] | 1. As the plant is 33 years old and in service, the most of the cables, feeder, panels are under capacity and frequent breakdown occurs. 2. Also the spare parts of existing feeders are obsolete and available in market. 3. Upgradation of system will help to increase in availabilty of system. 4. Also benefit to save material & maintenance cost, also the generation loss will reduced and also the demurrage charges of 5.35 Crs. Can be realized in one year. |  |  |  |  | 0 |  |  |  | 10 | [15 empty] | 0 |  |  |  | 10 | [6 empty] | Not Initiated
44 | Work of capacity restoration of unloading stream from Beetle Charger No. 2 to Stacker/Reclaimer No. 2 for perfromance improvement of CHP-I (4 x 210 MW). | DPR |  |  |  | 74 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
44.1 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for beetle charger No. 2 | Scheme |  |  |  | 3 | [7 empty] | 1. As the plant is 33 years old and in service, the availability of beetle charger system is reduced. 2. Availability of beetle charge will help to increase in wagon unloading and benefit to save the demurrage charges of 5.35 Crs. Can be realized in one year. |  |  |  |  | 0 |  |  |  | 3 | [15 empty] | 0 |  |  |  | 3 | [6 empty] | Not Initiated
44.2 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Wagon Tippler No. 2 | Scheme |  |  |  | 6 | [7 empty] | 1. As the plant is 33 years old and in service, the availability of wagon tippler is reduced. 2. Availability of wagon tippler will help to increase in wagon unloading and benefit to save the demurrage charges of 5.35 Crs. Can be realized in one year. |  |  |  |  | 0 |  |  |  |  | 6 | [14 empty] | 0 |  |  |  |  | 6 | [5 empty] | Not Initiated
44.3 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Apron Feeder No. 2 | Scheme |  |  |  | 3 | [7 empty] | 1. As the plant is 33 years old and in service, the availability of apron feeder is reduced. 2. Availability of apron feeder will benefit to save the demurrage charges of 5.35 Crs. Can be realized in one year. |  |  |  |  | 0 |  |  |  | 3 | [15 empty] | 0 |  |  |  | 3 | [6 empty] | Not Initiated
44.4 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 2D, 3B, 4B, 8B, 10 | Scheme |  |  |  | 25 | [7 empty] | 1. As the plant is 33 years old and in service, the availability of unloading conveyors are reduced and also reduced the coal carrying capacity. 2. Upgradation of conveyor system will restore the coal carrying capacity. 3. Also benefit to save the demurrage charges of 5.35 Crs. Can be realized in one year. |  |  |  |  | 0 |  |  |  |  | 25 | [14 empty] | 0 |  |  |  |  | 25 | [5 empty] | Not Initiated
44.5 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for impact crusher and wobbler feeder No. 2 & 4 | Scheme |  |  |  | 7 | [7 empty] | 1. As the plant is 33 years old and in service, the availability of impact crusher & wobbler feeder is reduced. 2. Upgradation of impact crusher & wobbler feeder will increase the availabilityf of system. 3. Also benefit to save the demurrage charges of 5.35 Crs. Can be realized in one year. |  |  |  |  | 0 |  |  |  |  | 7 | [14 empty] | 0 |  |  |  |  | 7 | [5 empty] | Not Initiated
44.6 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Stacker/Reclaimer No. 2. | Scheme |  |  |  | 10 | [7 empty] | 1. As the plant is 33 years old and in service, the availability of Stacker/Reclaimer is reduced. 2. Upgradation of Stakcer/ Reclaimer will increase the availability of system. 3. Also benefit to save the demurrage charges of 5.35 Crs. Can be realized in one year. |  |  |  |  | 0 |  |  |  |  | 10 | [14 empty] | 0 |  |  |  |  | 10 | [5 empty] | Not Initiated
44.7 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv. 2D to 3B, Conv. 3B to 4B, Conv. 4B to 8B and Conv. 10 by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | Scheme |  |  |  | 10 | [7 empty] | 1. As the plant is 33 years old and in service, the most of the chutes are worn out and beyond repair. Hence coal spillage is increase. 2. Replacement of modular chutes will help to avoid the coal spillage and improvement of cleaning. 3. Also benefit to save material & maintenance cost and also the demurrage charges of 5.35 Crs. Can be realized in one year. |  |  |  |  | 0 |  |  |  |  | 10 | [14 empty] | 0 |  |  |  |  | 10 | [5 empty] | Not Initiated
44.8 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of beetle Charger, wagon tippler, apron feeder, covneyors (Conv. 2D, 3B, 4B, 8B, 10), crushers/ wobbler feeder No. 2 & 4 and Stacker/Reclaimer No. 2 in CHP-1 (4 x 210 MW) | Scheme |  |  |  | 10 | [7 empty] | 1. As the plant is 33 years old and in service, the most of the cables, feeder, panels are under capacity and frequent breakdown occurs. 2. Also the spare parts of existing feeders are obsolete and available in market. 3. Upgradation of system will help to increase in availabilty of system. 4. Also benefit to save material & maintenance cost and also the demurrage charges of 5.35 Crs. Can be realized in one year. |  |  |  |  | 0 |  |  |  |  | 10 | [14 empty] | 0 |  |  |  |  | 10 | [5 empty] | Not Initiated
45 | Work of capacity restoration of bunkering stream from Conv. 1A/B, 2A/B, 5B to 7E/F/G/H including shuttle conveyors in CHP-I (4 x 210 MW) | DPR |  |  |  | 75 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
45.1 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 1A/B, 2A/B, 5B, 6A, 7E, 7F, 7G, 7H and Shuttle Conv. 5 to 8 in CHP-I (4 x 210 MW) | Scheme |  |  |  | 30 | [7 empty] | 1. As the plant is 33 years old and in service, the availability of unloading conveyors are reduced and also reduced the coal carrying capacity. 2. Upgradation of conveyor system will restore the coal carrying capacity. 3. Also benefit to save the generation loss of 32 Crs. and demurrage charges of 5.35 Crs. Can be realized in one year. |  |  |  |  | 0 |  |  |  | 30 | [15 empty] | 0 |  |  |  | 30 | [6 empty] | Not Initiated
45.2 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv. 1A/b to 2A/B,Conv. 4C to 5A/B, Conv. 5B to 6A, Conv. 6A to 7E & 7F, Conv. 7E to 7G upto shuttle conveyor, Conv. 7F to 7H upto shuttle conveyor by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | Scheme |  |  |  | 15 | [7 empty] | 1. As the plant is 33 years old and in service, the most of the chutes are worn out and beyond repair. Hence coal spillage is increase. 2. Replacement of modular chutes will help to avoid the coal spillage and improvement of cleaning. 3. Also benefit to save material & maintenance cost, generation loss will be reduced and the demurrage charges of 5.35 Crs. Can be realized in one year. |  |  |  |  | 0 |  |  |  |  | 15 | [14 empty] | 0 |  |  |  |  | 15 | [5 empty] | Not Initiated
45.3 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of conveyor system from Conv. 1A/B, 2A/B, 5B, 6A, 7E, 7F, 7G, 7H and Shuttle Conv. 5 to 8 in CHP-1 (4 x 210 MW) | Scheme |  |  |  | 20 | [7 empty] | 1. As the plant is 33 years old and in service, the most of the cables, feeder, panels are under capacity and frequent breakdown occurs. 2. Also the spare parts of existing feeders are obsolete and available in market. 3. Upgradation of system will help to increase in availabilty of system. 4. Also benefit to save material & maintenance cost,, generation loss will be reduced and the demurrage charges of 5.35 Crs. Can be realized in one year. |  |  |  |  | 0 |  |  |  | 20 | [15 empty] | 0 |  |  |  | 20 | [6 empty] | Not Initiated
45.4 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Paddel Feeder No. 1 to 4 and truck hopper in CHP-I (4 x 210 MW) | Scheme |  |  |  | 10 | [7 empty] | 1. As the plant is 33 years old and in service, the availability of paddle feeders and track hopper is reduced. 2. Availability of paddle feeders and track hopper will help to increase in wagon unloading and benefit to save the demurrage charges of 5.35 Crs. Can be realized in one year. |  |  |  |  | 0 |  |  |  |  | 10 | [14 empty] | 0 |  |  |  |  | 10 | [5 empty] | Not Initiated
46 | Renovation and upgradation of various electrical system for CHP-I (4 x 210 MW) improvement & Renovation and upgradation of various electrical system for CHP-I (4 x 210 MW) improvement. | DPR |  |  |  | 61 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
46.1 | Design, development and upgradation with circuit breaker VFD of various LT MCC of CHP-I. | Scheme |  |  |  | 17 | [7 empty] | 1. As the plant is 33 years old and in service, the most of the circuit breaker, MCC panels are under capacity and frequent breakdown occurs. 2. Also the spare parts of existing feeders are obsolete and available in market. 3. Upgradation of system will help to increase in availabilty of system. 4. Also benefit to save material & maintenance cost,, generation loss will be reduced and the demurrage charges of 5.35 Crs. Can be realized in one year. |  |  |  |  | 0 |  |  |  |  | 17 | [14 empty] | 0 |  |  |  |  | 17 | [5 empty] | Not Initiated
46.2 | Design, Supply, Installation, Commissioning and Testing of Energy Chain System for Paddle Feeder, Shuttle Conveyor and Stacker/Reclaimers in CHP-1 (4 x 210 MW), Khaperkheda TPS. | Scheme |  |  |  | 10 | [7 empty] | 1. As the plant is 33 years old and in service, the most of the cable carrier system is not working properly and frequent damages to cables & breakdown occurs. 2. Upgradation of system will help to increase in availabilty of system. 3. Also benefit to save material & maintenance cost,, generation loss will be reduced and the demurrage charges of 5.35 Crs. Can be realized in one year. |  |  |  |  | 0 |  |  |  | 10 | [15 empty] | 0 |  |  |  | 10 | [6 empty] | Not Initiated
46.3 | Upgradation of relay logic system with PLC & SCADA in CHP-I control room and Wagon Tipplers in CHP-1 (4 x 210 MW), Khaperkheda TPS. | Scheme |  |  |  | 8 | [7 empty] | 1. As the plant is 33 years old and in service, the existing relay logic based system are under capacity and frequent breakdown occurs. 2. Also the spare parts of existing relay logic based system are obsolete and available in market. 3. Upgradation of system will help to increase in availabilty of system. 4. Also benefit to save material & maintenance cost, generation loss will be reduced and the demurrage charges of 5.35 Crs. Can be realized in one year. |  |  |  |  | 0 |  |  |  |  | 8 | [14 empty] | 0 |  |  |  |  | 8 | [5 empty] | Not Initiated
46.4 | Complete upgradation of conveyor lighting system with energey efficient LED lights for CHP-1 (4 x 210 MW), Khaperkheda TPS. | Scheme |  |  |  | 8 | [7 empty] | 1. As the plant is 33 years old and in service, the existing conveyor lighting system are under capacity and some places fixtures & fittings are missing / damaged, hence poor illumination is conveyor gallary. 2. Upgradation of conveyor lightign system will help to improvement in illumination in conveyor gallary and safe working. 4. Also benefit to avoid accidenet / mishap due to poor illumination, to avoid loss of man / machine, reduced the maintenance & material cost. |  |  |  |  | 0 |  |  |  | 8 | [15 empty] | 0 |  |  |  | 8 | [6 empty] | Not Initiated
46.5 | Providing, installation, testing commissioning, maintenance and operation of explosion proof & weather proof surveillance system at CHP-I (4 X 210 MW), TPS Khaperkheda. | Scheme |  |  |  | 6 | [7 empty] | 1. As the plant is 33 years old and in service, close monitoring of the auxilairies is required. 2. Survelliance system will help to monitor the auxiliaries installed at CHP-I area and reduced the losses of auxiliaries. |  |  |  |  | 0 |  |  |  |  | 6 | [14 empty] | 0 |  |  |  |  | 6 | [5 empty] | Not Initiated
46.6 | Complete revamping/refurbishment, upgradation and modification of various EOT cranes & hoist installed at CHP-I (4 x 210 MW), TPS Khaperkheda. | Scheme |  |  |  | 12 | [7 empty] | 1. As the plant is 33 years old and in service, the existing EOT crane are not working properly and spare part of the EOT crane are not available in market. 2. Upgradation and modification of EOT cranes will help to increase availability. 4. Also benefit to reduced the maintenance & material cost and also reduced the breakdown of the system. |  |  |  |  | 0 |  |  |  |  | 12 | [14 empty] | 0 |  |  |  |  | 12 | [5 empty] | Not Initiated
47 | Procurement of various capacity SAN make locomotives and BEML make loader & bulldozer for CHP-I (4 x 210 MW) | DPR |  |  |  | 25 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
47.1 | Procurement of various capacity SAN make locomotives and BEML make loader & bulldozer for CHP-I (4 x 210 MW) | Scheme |  |  |  | 25 | [7 empty] | 1. As the plant is 33 years old and in service, the existing locomotives, loader & bulldozers are under capacity. 2. Reduction in expenditure as compare to hired locomotives/ dozer. 4. Reduction in maintenance & material cost of locomotives / dozer. 5. Reduction in oil & diesel consumption. |  |  |  |  | 0 |  |  |  | 25 | [15 empty] | 0 |  |  |  | 25 | [6 empty] | Not Initiated
48 | CHP Improvement Schemesfor 4x 210 MW units | DPR |  |  |  | 50 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
48.1 | Design, manufacture, supply and installation of suspended magnet for bunkering belts at CHP-I (4 x 210 MW), TPS Khaperkheda. | Scheme |  |  |  | 4 | [7 empty] | 1. As the plant is 33 years old and in service, the existing suspended magnets are not working properly and unable to trap the foreign materials. 2. Installation of new suspended magnets will be to reduced losses of auxiliaries and coal mills due to foreign material. 3. Also benefit to reduced the maintenance and material cost and to save the generation loss of 32 Crs. can be realized in one year. |  |  |  |  | 0 |  |  |  |  | 4 | [14 empty] | 0 |  |  |  |  | 4 |  |  |  |  | scheme added | Not Initiated
48.2 | Design, manufacture, supply and installation of travel drive system for shuttle conveyors and conveyors at CHP-I (4 x 210 MW), TPS Khaperkheda. | Scheme |  |  |  | 5 | [7 empty] | 1. As the plant is 33 years old and in service, the existing travel drive system for system for shuttle conveyors and conveyors are under capacity . 2. Upgradation will help restore the original capacity. 3. Also benefit to save the generation loss of 32 Crs. and demurrage charges of 5.35 Crs. Can be realized in one year. |  |  |  |  | 0 |  |  |  |  | 5 | [14 empty] | 0 |  |  |  |  | 5 |  |  |  |  | scheme added | Not Initiated
48.3 | Renovation including replacement of Power & Control cables with automation & upgradation of Stacker Reclaimer No. 2 in CHP-I (4 X 210MW), TPS Khaperkheda." | Scheme |  |  |  | 8 | [7 empty] | 1. As the plant is 33 years old and in service, the cable replacement is important to avoid any fire incidence and major breakdown. 2. Availability of Stacker/ Reclaimer will benefit to save the demurrage charges of 5.35 Crs. Can be realized in one year. |  |  |  |  | 0 |  |  |  |  | 8 | [14 empty] | 0 |  |  |  |  | 8 |  |  |  |  | scheme added | Not Initiated
48.4 | Complete reconditionding & upgradation of LT MCC installed at Unit No. 3 & 4 bunker auxiliareis in CHP-I (4 x 210 MW) | Scheme |  |  |  | 7 | [7 empty] | 1. As the plant is 33 years old and in service, the most of LT, MCC panels are under capacity and frequent breakdown occurs. 2. Also the spare parts of existing feeders are obsolete and available in market. 3. Upgradation of system will help to increase in availabilty of system. 4. Also benefit to save material & maintenance cost, generation loss will be reduced. |  |  |  |  | 0 |  |  |  |  | 7 | [14 empty] | 0 |  |  |  |  | 7 |  |  |  |  | scheme added | Not Initiated
48.5 | Complete reconditionding & upgradation of outdoor lighting system in CHP-I (4 x 210 MW) | Scheme |  |  |  | 8 | [7 empty] | 1. As the plant is 33 years old and in service, the existing outdoor lighting system are under capacity and some places fixtures & fittings are missing / damaged, hence poor illumination is conveyor gallary. 2. Upgradation of outdoor lighting system will help to improvement in illumination and safe working. 4. Also benefit to avoid accidenet / mishap due to poor illumination, to avoid loss of man / machine, reduced the maintenance & material cost. |  |  |  |  | 0 |  |  |  |  | 8 | [14 empty] | 0 |  |  |  |  | 8 |  |  |  |  | scheme added | Not Initiated
48.6 | Complete reconditionding & upgradation of HT breaker, control circuits & protection relays in CHP-I (4 x 210 MW) | Scheme |  |  |  | 3 | [7 empty] | 1. As the plant is 33 years old and in service, the most of HT breaker, control circuit & protection relays are under capacity and frequent breakdown occurs. 2. Also the spare parts of existing systems are obsolete and available in market. 3. Upgradation of system will help to increase in availabilty of system. 4. Also benefit to save material & maintenance cost, generation loss will be reduced. |  |  |  |  | 0 |  |  |  |  | 3 | [14 empty] | 0 |  |  |  |  | 3 |  |  |  |  | scheme added | Not Initiated
48.7 | Complete revamping/refurbishment, upgradation and modification of various monorail hoists & winch machine installed at CHP-I (4 x 210 MW), TPS Khaperkheda. | Scheme |  |  |  | 10 | [7 empty] | 1. As the plant is 33 years old and in service, the existing hoists are not working properly and spare part of the hoists are not available in market. 2. Upgradation and modification of hoists will help to increase availability. 4. Also benefit to reduced the maintenance & material cost and also reduced the breakdown of the system. |  |  |  |  | 0 |  |  |  |  | 10 | [14 empty] | 0 |  |  |  |  | 10 |  |  |  |  | scheme added | Not Initiated
48.8 | Procurement of hydra 14 Ton above capacity and heavy vehicles for CHP- I & II. | Scheme |  |  |  | 5 | [7 empty] | 1. As the plant is 33 years old and in service, the existing hydra and heavy vehicles are under capacity. 2. Reduction in expenditure as compare to hired hydra / vehicles. 4. Reduction in maintenance & material cost of locomotives / dozer. 5. Reduction in oil & diesel consumption. |  |  |  |  | 0 |  |  |  |  | 5 | [14 empty] | 0 |  |  |  |  | 5 |  |  |  |  | scheme added | Not Initiated
49 | Installation of Real Time Coal Analyzer at all TPS of Mahagenco | DPR |  |  |  | 31.42 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX ROLLING PLAN
49.1 | Installation of Real time Coal Analyzer at Khaperkheda TPS | Scheme |  |  |  | 31.42 | [12 empty] | 0 |  |  |  |  | 31.42 | [14 empty] | 0 |  |  |  |  | 31.42 | [5 empty] | Not Initiated
50 | Railway expenses for refurbishment of OHE lines at CHP-I (4 x 210 MW) | DPR |  |  |  | 26 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | Newly added DPR
50.1 | Railway expenses for refurbishment of OHE lines at CHP-I (4 x 210 MW) | Scheme |  |  |  | 26 | [7 empty] | 1. Refurbishment of OHE lines charges will be depostied in Railways account. |  |  |  |  | 0 |  |  |  |  | 26 | [14 empty] | 0 |  |  |  |  | 26 |  |  |  |  | scheme added newly | Not Initiated
[19 empty] | 0 | [19 empty] | 0
[19 empty] | 0 | [19 empty] | 0
[19 empty] | 0 | [19 empty] | 0
| B) Non-DPR Schemes | [17 empty] | 0 | [19 empty] | 0
1 | PROCUREMENT COMPLETE Gear BOX ASSEMBLIES FOR 803 1/2 HP & XRP 883 COAL MILLS OF UNIT NO. 1& 2 AT KHAPERKHEDA TPS. | Non-DPR | N.A. |  |  | 4.25 |  |  |  | 2020-12-15 | 2021-07-15 | 2021-12-15 | 2021-02-08 | [5 empty] | 0 | 4.5548 | [18 empty] | 0 | 4.5548 | [8 empty] | approved | Capitalised
2 | Supply Erection and commissioning of Oil Cooled Suspended magnets at Conv 6A & 6B at Khaperkheda TPS. | Non-DPR | N.A. |  |  | 1.15 | [12 empty] | 0 | 1.1484 | [18 empty] | 0 | 1.1484 | [8 empty] | approved | Capitalised
3 | Procurment of new 02 Ambulance Van & 2 Truck for KPKD TPS(Asset Nos. 170100512, 170100513, 170100514, 170100515) | Non-DPR | N.A. | [12 empty] | 0.41055 |  |  | 0.41055 | [16 empty] | 0.41055 |  |  | 0.41055 | [10 empty] | Capitalised
4 | GEHO PUMP (Valve housing assembly) | Non-DPR | N.A. | [15 empty] | 0 |  | 8.7933 | [10 empty] | 100% | 100% | [5 empty] | 0 |  | 8.7933 | [7 empty] | All documents related to this N-DPR scheme Appendix I,WCR etc submitted to O/o. CE(Works) | Capitalised
5 | RESTORATION OF AHP OUTLET TO ESP INLET DUCTS U#1&2(Unit #2 Part only) | Non-DPR | N.A. |  |  | 15.03 | [12 empty] | 0 |  | 7.0042 | [17 empty] | 0 |  | 7.0042 | [7 empty] | UNIT#2 WORK COMPLETED AND CAPITALISED & Unit#1 Work will be completed in next FY 2025-26 during AOH.Proposal for Unit #1 is under process,. | Partially Capitalised
6 | ABC powder type and foam type composite Fire Extinguisher | Non-DPR | N.A. | [15 empty] | 0 |  | 0.714 | [17 empty] | 0 |  | 0.714 | [7 empty] | HO Non DPR & PO Placed by HO capitalised in FY 2023-24 | Capitalised
7 | FFEQUIP HYDRAULIC JACK (BM-I) | Non-DPR | N.A. | [15 empty] | 0 |  | 0.57696 | [17 empty] | 0 |  | 0.57696 | [8 empty] | Capitalised
8 | MOBILE COAL SAMPLING EQUIP-AUGER (FMC) CHP-I | Non-DPR | N.A. | [15 empty] | 0 |  | 1.5824 | [17 empty] | 0 |  | 1.5824 | [7 empty] | CE(FMC) capitalised by Account section as per HO. This scheme is under DPR/Non DPR MPD Khaperklheda not received any details please confirm at your end.Such N-DPR schemes added by HO without MPD Knoledge through N-DPR may leads to disallowance | Capitalised
9 | Replacement of ash slurry disposal pump to improve performance & capacity enhancement of ash slurry disposal system at AHP-1 Khaperkheda TPS | Non-DPR |  |  |  | 4.92 | [12 empty] | 0 |  |  | 4.92 | [16 empty] | 0 |  |  | 4.92 | [6 empty] | admin approval received | WIP
10 | Procurement of Pillow Block Dodge Bearing Assemblies (Expansion & Non-Expansion) for PA fans in Unit- n1 to 4, at Khaperkheda TPS | Non-DPR |  |  |  | 5.11 | [12 empty] | 0 |  |  | 5.11 | [16 empty] | 0 |  |  | 5.11 | [6 empty] | admin approval received | WIP
11 | Replacement of Economizer outlet to APH outlet common duct in unit no. 3 (210MW), Khaperkheda TPS | Non-DPR |  |  |  | 6.24 | [12 empty] | 0 |  |  | 6.24 | [16 empty] | 0 |  |  | 6.24 | [6 empty] | admin approval received | WIP
12 | PROCUREMENT OF OIL COOLED SUSPENSION MAGNET FOR 210MW AND MODIFICATION & REPLACEMENT OF VIBRATING FEEDER WITH VIBRATING TRANSFER CHUTE FOR 210MW | Non-DPR |  |  |  | 3.09 | [12 empty] | 0 |  |  | 3.09 | [16 empty] | 0 |  |  | 3.09 | [6 empty] | admin approval received | WIP
13 | DESIGN,ENGINEERING,MODIFICATION ,ERECTION AND COMMISSIONING OF DRIVE UNIT ARRANGEMENT FOR CONVEYOR 10 AT CHP1 | Non-DPR |  |  |  | 1.65 | [12 empty] | 0 |  |  | 1.65 | [16 empty] | 0 |  |  | 1.65 | [6 empty] | admin approval received | WIP
14 | ENERGY EFFICIENT PLANT LIGHTING AND COLONY LIGHTING MODIFICATIONS | Non-DPR |  |  |  | 21.04 | [12 empty] | 0 |  |  | 21.04 | [16 empty] | 0 |  |  | 21.04 | [6 empty] | admin approval received | WIP
15 | Supply installation testing and commisioning of various battery sets at unit No 1 & 2 of Khaperkheda TPS | Non-DPR |  |  |  | 9.31 | [12 empty] | 0 |  |  | 9.31 | [16 empty] | 0 |  |  | 9.31 | [6 empty] | admin approval received | WIP
16 | Revamping and modification of existing alarm and protection system from fire and provide rapid extinguishing Clean Agent (CA) system at Unit #1 & 2 (210 MW) units, KPKD TPS | Non-DPR |  |  |  | 8.21 | [12 empty] | 0 |  |  | 8.21 | [16 empty] | 0 |  |  | 8.21 | [6 empty] | admin approval received | WIP
17 | Supply of electronic modules for Procontrol DCS system in unit 1 to 4 of 210 MW Khaperkheda TPS | Non-DPR |  |  |  | 1.18 | [12 empty] | 0 |  |  | 1.18 | [16 empty] | 0 |  |  | 1.18 | [6 empty] | admin approval received | WIP
18 | Revamping & UPGRADATION of SWAS system in unit 3 & 4 of 210 MW Khaperkheda TPS | Non-DPR |  |  |  | 8.56 | [12 empty] | 0 |  |  | 8.56 | [16 empty] | 0 |  |  | 8.56 | [6 empty] | admin approval received | WIP
19 | Upgradation of process instrumentation in unit 1 to 2 of 210 MW Khaperkheda TPS | Non-DPR |  |  |  | 4.64 | [12 empty] | 0 |  |  | 4.64 | [16 empty] | 0 |  |  | 4.64 | [6 empty] | admin approval received | WIP
20 | Replacement of flue gas duct from air heater outlet to esp inlet for U 1 & 2 (S+W) | Non-DPR |  |  |  | 8.03 | [12 empty] | 0 |  |  |  | 8.03 | [15 empty] | 0 |  |  |  | 8.03 | [5 empty] | admin approval received | WIP
21 | PROCUREMENT OF COMPLETE ROTOR ASSEMBLY FOR NDZV 31 SIDOR IN UNIT NO. 1 & 2 KHAPERKHEDA TPS (ID FAN). | Non-DPR |  |  |  | 14.52 | [12 empty] | 0 |  |  |  | 14.52 | [15 empty] | 0 |  |  |  | 14.52 | [5 empty] | admin approval received | WIP
22 | UPGRADATION OF BELT CONVEYOR CAPACITY OF 2C &2D AND 8A & 8B AT CHP1 | Non-DPR |  |  |  | 3.94 | [12 empty] | 0 |  |  |  | 3.94 | [15 empty] | 0 |  |  |  | 3.94 | [5 empty] | admin approval received | WIP
23 | WORK OF DESIGN,ENGINEERING,ERECTION AND UPGRADATION OF DRIVE UNITS OF BELT CONVEYOR 3A & 3BAT CHP1 | Non-DPR |  |  |  | 8.34 | [12 empty] | 0 |  |  |  | 8.34 | [15 empty] | 0 |  |  |  | 8.34 | [5 empty] | admin approval received | WIP
24 | Procurement of 1500 KW ID Fan Synchronous Motor at Unit 3 & 4 Khaperkheda TPS. | Non-DPR |  |  |  | 3.12 | [12 empty] | 0 |  |  |  | 3.12 | [15 empty] | 0 |  |  |  | 3.12 | [5 empty] | admin approval received | WIP
25 | Procurement of Steam and Water Analysis System(SWAS) for Unit 1&2 (210MW) KPKD TPS, Khaperkheda. | Non-DPR |  |  |  | 9.65 | [12 empty] | 0 |  |  |  | 9.65 | [15 empty] | 0 |  |  |  | 9.65 | [5 empty] | admin approval received | WIP
26 | Supply and replacement of complete PVC fills of cell of cooling tower of unit 1-4 (210 MW) at Khaperkheda TPS | Non-DPR |  |  |  | 8.52 | [12 empty] | 0 |  |  |  | 8.52 | [15 empty] | 0 |  |  |  | 8.52 | [5 empty] | admin approval received | WIP
27 | PROCUREMENT OF FD FAN (BHEL AP 1-20/11) ASSEMBLY FOR UNIT 1 TO 4 ATKHAPERKHEDA TPS. | Non-DPR |  |  |  | 4.37 | [12 empty] | 0 |  |  | 4.37 | [16 empty] | 0 |  |  | 4.37 | [6 empty] | Not approved speedily approval is required to capitalised in FY 2024-25 | WIP
28 | CHP performance improvement scheme for capacity restoration of drive units installed at CHP-1 (4 x 210 MW), TPS Khaperkheda. | Non-DPR |  |  |  | 14.5 | [12 empty] | 0 |  |  | 14.5 | [16 empty] | 0 |  |  | 14.5 | [6 empty] | Not approved speedily approval is required to capitalised in FY 2024-25 | WIP
29 | Work of Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of belt conveyor 8A & 8B and belt conveyor 2C & 2D at CHP-1 (4 x 210 MW), Khaperkheda TPS. | Non-DPR |  |  |  | 2.15 | [12 empty] | 0 |  |  | 2.15 | [16 empty] | 0 |  |  | 2.15 | [6 empty] | Not approved speedily approval is required to capitalised in FY 2024-25 | WIP
30 | WORK OF DESING,SUPPLY ,ERECTION,COMMISSIONG AND UPGRADATION OF COMPLETE ELECTRICAL SYSTEM FOR DRIVE UNITS OF BELT CONVEYOR 3A & 3B AND BELT CONVEYOR 4A,4B,4C & 4D AT CHP1 Khaperkheda TPS. | Non-DPR |  |  |  | 2.29 | [12 empty] | 0 |  |  | 2.29 | [16 empty] | 0 |  |  | 2.29 | [6 empty] | Not approved speedily approval is required to capitalised in FY 2024-25 | WIP
31 | Supply, Installation, & Commissioning of Instruments at coal Testing Lab, WTP-I, TPS Khaperkheda. | Non-DPR |  |  |  | 0.45 | [12 empty] | 0 |  |  | 0.45 | [16 empty] | 0 |  |  | 0.45 | [6 empty] | Not approved speedily approval is required to capitalised in FY 2024-25 | WIP
32 | Supply, Installation & Commissioning and Refurbishment of asbestos based H2 Generator and compressor to convert it to non-asbestos based H2 Generator for Unit 1 to 5, Khaperkheda TPS. | Non-DPR |  |  |  | 7.65 | [12 empty] | 0 |  |  |  | 7.65 | [15 empty] | 0 |  |  |  | 7.65 | [5 empty] | Not approved | N.A.
33 | construction of bituminous macadam roads at Prakashnagar Colony TPS Khaperkheda | Non-DPR |  |  |  | 5.4 | [12 empty] | 0 |  |  |  | 5.4 | [15 empty] | 0 |  |  |  | 5.4 | [5 empty] | Not approved | N.A.
34 | Work of attending additional works based on structural report at Induced Draft Cooling Towers (IDCT) unit 1,2,3 & 4 at 4 x 210MW, TPS, Khaperkheda | Non-DPR |  |  |  | 1.21 | [12 empty] | 0 |  |  |  | 1.21 | [15 empty] | 0 |  |  |  | 1.21 | [5 empty] | Not approved | N.A.
35 | VIBRATION ANALYSER | Non-DPR |  |  |  | 0.5 | [12 empty] | 0 |  |  |  | 0.5 | [15 empty] | 0 |  |  |  | 0.5 | [5 empty] | Not approved | N.A.
36 | Upgradation of GEHO pump instrumentation for AHP Unit No. 3 & 4 (210 MW) at Khaperkheda TPS | Non-DPR |  |  |  | 1.27 | [12 empty] | 0 |  |  |  | 1.27 | [15 empty] | 0 |  |  |  | 1.27 | [5 empty] | Not approved | N.A.
37 | Refurbishment of HPT module for Unit 1 & 2 | Non-DPR |  |  |  | 5 | [12 empty] | 0 |  |  |  | 5 | [15 empty] | 0 |  |  |  | 5 | [5 empty] | Not approved | N.A.
38 | General Asset Furniture | Non-DPR | N.A. | [12 empty] | 0.55866 | 0.0266 | 0.18348 | 0.76874 | 0.084353 | 0.0086842 | [14 empty] | 0.55866 | 0.0266 | 0.18348 | 0.76874 | 0.084353 | 0.0086842 | [8 empty] | Capitalised
39 | General Asset AC, Fans, Air coolers, water filter etc. | Non-DPR | N.A. | [12 empty] | 0.17023 | 0.18256 | 0.05286 | 0.40564 | 0.009879 | 0.12056 | [14 empty] | 0.17023 | 0.18256 | 0.05286 | 0.40564 | 0.009879 | 0 | [8 empty] | Capitalised
40 | General Asset Computer, scanners, etc. | Non-DPR | N.A. | [12 empty] | 0.17951 | 1.0279 | 0.72842 | 1.9358 | 0.2868 | 0.33717 | [14 empty] | 0.17951 | 1.0279 | 0.72842 | 1.9358 | 0 | 0.0103 | [8 empty] | Capitalised
41 | Land aquired for rly siding | Non-DPR | N.A. | [15 empty] | 0 | 0.4072 | [18 empty] | 0 | 0.4072 | [9 empty] | Capitalised
42 | RCC ROAD FROM ASH SILO TO 'D' POINT FOR BULKER MO | Non-DPR | N.A. | [15 empty] | 0 | 0.95225 | [18 empty] | 0 | 0.95225 | [8 empty] | Ash Utilisation fund | Capitalised
| Total | [13 empty] | 222.5932 | 118.7503 | 85.3201 | 63.1132 | 489.7769 | 149.912 | 354.1796 | 207.1952 | 397.1133 | 1102.88 | 777.49 | 214.92 | 180.8 | [7 empty] | 179.9663 | 12.0062 | 13.7585 | 28.9881 | 234.7191 | 43.1643 | 112.0788 | 631.5376 | 626.4118 | 1102.88 | 777.49 | 214.92 | 180.8 | 3.006
[17 empty] | 0.2 | [19 empty] | 0.2
[17 empty] | Land | [19 empty] | Land |  |  | 7.1568 | 18.6898 | 97.71
Formulas:
Approved Start Date = IF([MERC Approval Date]=0,"-",[MERC Approval Date])
MERC Approval Date = IF([MERC Approval Date, row above]=0,"-",[MERC Approval Date, row above])
MERC Approval Date = [MERC Approval Date, row above]
Date of Submission = [Date of Submission, row above]
Note on M4: SSP-RCD As per the implementation plan submitted in the DPR/ Approved by MERC
Note on P13: RCD-SSP: FY 2013-14 & 2014--15
Note on P16: RCD-SSP: FY 2014-15
Note on P19: RCD-SSP: FY 2011-12; As per HY 17-18, capitalization of 23.47
Note on P26: RCD-SSP: FY 2012-13
Note on P29: SSP-RCD: Capitalised in FY 2015-16
Note on P31: SSP-RCD: Capitalised in FY 15-16
Note on P32: SSP-RCD: Capitalised in FY 14-15
Note on P33: SSP-RCD: Capitalised in FY 14-15
Note on P36: SSP-RCD: Capitalised in FY 16-17
Note on P37: SSP-RCD: Capitalised in FY 17-18
Note on P96: SUSHANT: FY 2014-15
Note on AJ96: SUSHANT: FY 2014-15
Note on G110: SSP-RCD: Total Expenditure is booked on 2 units of kpkd 1-4 & 1 unit of kpkd 5. i.e. 2*210+1*500
Note on H110: SUSHANT: Share of KPKD 1-4 to be confirmed
Note on H114: SUSHANT: Share of kpkd 1-4 to be confirmed
Note on G116: SSP-RCD: Including 18% GST & 2% P&F Charges
Note on G153: SSP-RCD: Share of Koradi 6-7, Kpkd 1-4 & kpkd 5 to be confirmed
Note on H153: SSP-RCD: Share of Koradi 6-7, Kpkd 1-4 & kpkd 5 to be confirmed

## F4.3
MSPGCL: Khaperkheda U # 1-4
MTR Petition Formats - Generation
| Project Details | Form 4.3: Capital Work-in-progress - Project-wise details | [9 empty] | (Rs. Crore)
Sr. No. | Project Code | MERC Approval No. | MERC Approval Date | Approved Project Cost | Cumulative Expenditure Incurred till beginning of the Year | Capital Expenditure Capitalised | Opening CWIP | Investment during the year | Capitalization |  |  |  | Closing CWIP
[9 empty] | Works Capitalised | Interest Capitalised | Expenses Capitalised | Total Capitalisation |  | Allowable Capitalisation | Probable Disallowance
FY 2022-23
a) DPR Schemes
(i) Submitted to MERC
1 | Combustion optimization system | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 | 10.743 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Dynamic coal flow measurement and control (balancing) system (one) | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 | 8.17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | CO analyser (8 units) | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 | 1.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Oxygen analyser (32 units) | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 | 0.783 | 0.75683 | 0.75683 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Spare HPT module for Khaparkheda Unit 1 & 2 | MERC/CAP/DPR/10/2010-11/1466 | 2010-10-26 | 26.459 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | HPT module 1 No (unit # 1) | MERC/CAP/DPR/10/2010-11/1466 | 2010-10-26 | 23.0379 | 23.9074 | 23.9074 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAP/DPR/10/2010-11/1466 | 2010-10-26 | 3.4211 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Economiser Upper Bank & Lower Bank coils for Khaperkheda Unit no. 3 and Unit no. 4 | MERC/CAP/DPR/10/2010-11/1695 | 2010-12-15 | 26.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Economiser Upper Bank & Lower Bank coils for Khaperkheda Unit no. 3 and Unit no. 4 | MERC/CAP/DPR/10/2010-11/1695 | 2010-12-15 | 26.35 | 11.77 | 11.77 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Economiser & LTSH Upper Bank & Lower Bank coils for Khaperkheda Unit no. 1 and Unit no. 2 | MERC/CAPEX/20112012/01155 | 2011-07-29 | 34.7916 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Economiser & LTSH Coil for Unit 1 | MERC/CAPEX/20112012/01155 | 2011-07-29 | 15.6924 | 15.6924 | 15.6924 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Economiser & LTSH Coil for Unit 2 | MERC/CAPEX/20112012/01155 | 2011-07-29 | 16.1528 | 16.1528 | 16.1528 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20112012/01155 | 2011-07-29 | 2.9464 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Procurement & Replacement of Re-heater Rear Pendant Assembly Coils for 2*210MW Khaperkheda Unit no. 1 and Unit no. 2 | MERC/CAPEX/20122013/00603 | 2012-06-18 | 10.3738 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Re-heater coils for unit no. 1 | MERC/CAPEX/20122013/00603 | 2012-06-18 | 5.1267 | 5.1267 | 5.1267 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Re-heater coils for unit no. 2 | MERC/CAPEX/20122013/00603 | 2012-06-18 | 5.1267 | 5.55 | 5.55 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/00603 | 2012-06-18 | 0.1204 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Procurement of HPT module suitable for khaperkheda TPS Unit 3 & 4 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 36.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Procurement of HPT module suitable for khaperkheda TPS Unit 3 & 4 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 36.2 | 32.4016 | 32.4016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7 | Procurement Spare GTR, Locomotive & Compactors | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 18.4521 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | 250 MVA Spare GTR | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 10.3496 | 11.2511 | 11.2511 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.2 | Procurement of Locomotive 2no’s. | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 5.9927 | 5.9927 | 5.9927 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.3 | Procurement of Compactors 2 no’s. | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 0.42979 | 0.4298 | 0.4298 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 1.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Procurement & Replacement of complete set of LTSH coils for Khaperkheda TPS Unit 3&4 | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 17.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement and replacement of LTSH coils for Khaperkheda TPS at U3 | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 8.58 | 3.4291 | 3.4291 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Procurement and replacement of LTSH coils for Khaperkheda TPS at U4 | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 8.58 | 3.1809 | 3.1809 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 0.65 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Development of Ash Bund (Waregaon) at K'kheda TPS | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 38.7459 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Construction of 3rd upstream raising of existing ash bund from TBL 299.50 Mtr to 302.50 Mtr at Waregaon, Khaperkheda TPS. | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 33.8585 | 32.5375 | 32.5375 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.2 | Construction of masonary dam (Gabion structure) at Waregaon TPS, Khaperkheda. | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 1.0561 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.3 | Construction of approach to drain wells and raising height of drain well no. 1,2 & 3 ash bund at Waregaon, Khaperkheda TPS | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 0.48488 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 3.3464 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Various schemes related to CHP Improvement & Performance Optimization and scheme of conversion of existing Composite OHE to Conventional OHE | MERC/CAPEX/20152016/00422 | 2016-08-03 | 10.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Air Cooled Suspension Magnet for Con. 3 & 6 of CHP 210 MW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 2.18 | 2.2613 | 2.2613 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | Procurement of Impact crusher motor | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.84 | 0.52579 | 0.52579 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.3 | Procurement of 360V, 200 AH battery set and 360V 325 AH battery set for U# 1to 4 | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.1 | 1.4576 | 1.4576 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.4 | Procurement of POG Instruments for Unit 1 to 4 | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.77 | 0.35015 | 0.35015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.5 | Up gradation of safe scan flame scanner system by BHEL scan system in unit no. 1, 3 & 4 | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.6 | Up gradation of old AVR system to DAVR | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.7 | Conversion of existing Composite OHE to Conventional OHE | MERC/CAPEX/20152016/00422 | 2016-08-03 | 2.72 | 2.72 | 2.72 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.47 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | ESP up-gradation for Unit-1 at Khaperkheda TPS | MERC/CAPEX/20152016/01261 | 2016-01-11 | 32.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | ESP up-gradation for Unit-1 at Khaperkheda TPS | MERC/CAPEX/20152016/01261 | 2016-01-11 | 32.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Procurement, installation and commissioning of Gravimetric Belt / Rotary Type Feeder, VFD for CEP, Up-gradation of BTS system & Environmental schemes at Khaperkheda TPS | MERC/CAPEX/20162017/01552 | 2017-02-14 | 20.218 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Procurement, installation and commissioning of Gravimetric belt/rotary Feeder at U-1 & 2 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 5.72 | 4.7418 | 4.7418 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Installation of VFD to CEP at U-1 to 4 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 8.64 | 1.9027 | 0 | 1.9027 | 0.38326 | 2.2949 |  |  | 2.2949 | -0.008878 | 2.2949 | 0
13.3 | Installation of BTS system at U-4 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 0.98796 | 0.98796 | 0.98796 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.4 | Replacement of SOx/NOx analyzer at U-1 to 4 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 2.42 | 2.3035 | 2.3035 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.5 | Procurement of TGA,CHNS analyzer and Bomb calorimeter at U-5 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 1.71 | 0.2897 | 0.2897 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01552 | 2017-02-14 | 0.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Up gradation of HMI System at Unit No 3 & 4 at Khaperkheda TPS | MERC/CAPEX/20172018/03946 | 2017-07-19 | 13.39 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | HMI Up-gradation at U# 3 & 4 | MERC/CAPEX/20172018/03946 | 2017-07-19 | 12.78 | 12.5611 | 6.2805 | 6.2805 | 0 | 6.2805 |  |  | 6.2805 | 0 | 6.2805 | 0
0 | IDC | MERC/CAPEX/20172018/03946 | 2017-07-19 | 0.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21 | Procurement of APH Basket for unit # 1 to 5 and Up-gradation of HT Motor Protection Relay in Unit # 1 to 4 at Khaperkheda TPS | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 9.77 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.1 | Procurement of assembly of baskets for air preheater of type bisector APH 27 VI: 1850, 12 sector in unit no. 1 & 2 and bisector APH 27 VI: 2000; 24 sector in unit no. 3 & 4 (210MW x 4) at TPS, Khaperkheda | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 5.71 | 5.1126 | 3.3472 | 1.7655 | 2.9843 | 2.1347 |  |  | 2.1347 | 2.6151 | 2.1347 | 0
21.3 | Up-gradation of H.T. Motor protection relays in Unit 1 to 4 (210MW), Khaperkheda TPS | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 3.96 | 2.9881 | 2.9881 | 0 | 0.12555 | 0.12555 |  |  | 0.12555 | 0 | 0.12555 | 0
0 | IDC | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 0.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22 | Procurement of LPT rotor suitable for Unit # 3 & 4 of 210 MW at Khaperkheda TPS | MERC/CAPEX/2018-2019/132 | 2019-05-09 | 27.191 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.1 | Procurement of LPT rotor suitable for Unit # 3 & 4 of 210 MW at Khaperkheda TPS | MERC/CAPEX/2018-2019/132 | 2019-05-09 | 26.491 | 0 | 0 | 0 | 10.7515 | 0 |  |  | 0 | 10.7515 | 0 | 0
0 | IDC | MERC/CAPEX/2018-2019/132 | 2019-05-09 | 0.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23 | Supply, Erection & commissioning of HT Vacuum circuit Breakers & SF6 contactors at AHP (U#1-4) & CHP (U#1 to 5) and 160 KW VFD Panel with Motor for fire-fighting pumps at U#1 to 4 at Khaperkheda TPS | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 10.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.1 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at AHP (Unit#1 to 4, 210MW), Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 4.17 | 3.1199 | 0 | 3.1199 | 0.36441 | 4.8883 |  |  | 4.8883 | -1.404 | 4.17 | 0.71829
23.2 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at CHP (Unit#1 to 4, 210MW) and CHP (Unit#5, 500MW) Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 3.81 | 1.2978 | 0 | 1.2978 | 2.5244 | 0 |  |  | 0 | 3.8221 | 0 | 0
23.3 | Supply, Erection & commissioning of 150 KW VFD Panel with motor for fire-fighting pumps at 210 MW Khaperkheda TPS. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 2.34 | 0 | 0 | 0 | 1.9968 | 0 |  |  | 0 | 1.9968 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 0.58 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24 | Augmentation of Waregaon Ash Water Recovery System at TPS Khaperkheda | MERC/CAPEX/2019-20/732 | 2019-09-16 | 17.1984 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.1 | Augmentation of Waregaon Ash Water Recovery System at TPS Khaperkheda | MERC/CAPEX/2019-20/732 | 2019-09-16 | 15.7884 | 8.0442 | 0 | 8.0442 | 5.8872 | 13.9315 |  |  | 13.9315 | 0 | 13.9315 | 0
0 | IDC | MERC/CAPEX/2019-20/732 | 2019-09-16 | 1.41 | 0 | 0 | 0 | 0.58812 | 0.58812 |  |  | 0.58812 | 0 | 0.58812 | 0
25 | Procurement of VFD with HMI & Controller & Replacing with existing Eddy-current drives of Coal feeders at U# 3 & 4 and Procurement of Various Critical Components of GEHO Pump (Model-TZPM 800) for AHP-1 at Khaperkheda TPS | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 10.6535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25.1 | Up-gradation of Existing BHEL make 36” Gravimetric Coal Feeders control panel with HMI and croprocessor based Controller with VFD, Motor & Weigh Module at Unit 3 & 4, (210MW) | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 7.4655 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25.2 | Procurement of various Critical Components of GEHO Pump (Model-TZPM 800) for AHP-1 (210MW) | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 2.698 | 2.6466 | 2.6466 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 0.49 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26 | Procurement, Replacement of Eco Coils U#1&2 210 MW, & Procurement & replacement of foundation Deck Spring assembly for coal mills U#3,4 at Khaperkheda TPS | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 15.4086 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26.1 | Procurement, Replacement of Eco Coils U#1&2 | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 7.4996 | 6.6503 | 6.6503 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26.2 | Procurement & replacement of foundation Deck Spring assembly for coal mills U#3,4 | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 6.679 | 0 | 0 | 0 | 3.006 | 0 |  |  | 0 | 3.006 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 1.23 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28 | ESP Upgradation of 5 Nos. of 210/500MW Units at Khaperkheda, Koradi & Chandrapur TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 90.3535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.1 | ESP Upgradation at Unit #1, Khaperkheda TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 42.7114 | 0 | 0 | 0 | 5.955 | 0 |  |  | 0 | 5.955 | 0 | 0
28.2 | ESP Upgradation at Unit #2, Khaperkheda TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 42.7114 | 0 | 0 | 0 | 5.955 | 0 |  |  | 0 | 5.955 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 4.9307 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29 | Flue Gas Desulphurisation System for Khaperkheda Unit # 1-4 | MERC/CAPEX/2021-2022/MSPGCL/097 | 2022-03-14 | 113.4565 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.1 | FGD System for Khaperkheda Unit # 1-4 | MERC/CAPEX/2021-2022/MSPGCL/097 | 2022-03-14 | 109.15 | 0 | 0 | 0 | 51.12 | 0 |  |  | 0 | 51.12 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/097 | 2022-03-14 | 4.3065 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4 | Construction of coal platform for Chandrapur TPS, Khaperkheda TPS & Parli TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 5.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4.2 | Khaperkheda TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 5.43 | 3.9936 | 3.9936 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 4.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.4a | 1. Procurement of 6.6 KV,300 KW, P.A.fan motor for U# 1 & 2 2. Procurement of 6.6 KV,425 KW,CM motor for U # 3 & 4 3. Procurement of 6.6 KV,1400KW,CW pump motor for U-1& 2 4. Procurement of 6.6 KV,1400 KW,CW pump motor for U-3&4 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 3.82 | 2.5283 | 2.5283 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.4b | K'kheda: Procurement of HT Motors(GS/HP Water pump)for U-1&2 and Procurement of HT Motors (ACW)for U-3&4 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 1 | 0.4 | 0.4 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.2 | KHAPERKHEDA (U-1 to 4) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.96 | 2.8152 | 2.8152 | 0 | 0.30212 | 0.30212 |  |  | 0.30212 | 0 | 0.30212 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.2 | Khaperkheda TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender for KPKD 1-4 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 1.7765 | 1.7765 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.2 | Normal Multipurpose Fire Tender KPKD 1-4 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 0 | 0 | 0 | 2.1847 | 2.1847 |  |  | 2.1847 | 0 | 1.25 | 0.93465
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 226.3024 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9.1 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 226.3024 | 229.37 | 0 | 229.37 | 37.33 | 0 |  |  | 0 | 266.7 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 4.4604 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.2a | Compond wall (IB recommdation),Plant Patrolling Roads (IB recommdation) TPS KPKD | MERC/CAPEX/20172018/0177 | 2018-02-06 | 4.4604 | 3.9268 | 0.64975 | 3.2771 | 0 | 3.2771 |  |  | 3.2771 | 0 | 3.2771 | 0
HO DPR 11 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 9.23 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11.1 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 9.05 | 13.3057 | 13.3057 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 0.18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15 | Implementation of Water Flow Monitoring system at Chandrapur STPS & Khaperkheda TPS | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 5.1755 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.3 | Electromagnetic Flow meters at various lines & Locations of 210 MW | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 3.8515 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.4 | Automation: Centralized SCADA, RTU, MODBUS Cable, Power cable & mandatory spares | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 1.324 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30 | Supply of spare Generator Rotor for UNIT 1 & 2, 210MW | MERC/CAPEX/2023-24/0184 | 2024-03-12 | 37.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.1 | Supply of spare Generator Rotor for UNIT 1 & 2, 210MW | MERC/CAPEX/2023-24/0184 | 2024-03-12 | 36.7 | 0 | 0 | 0 | 11.01 | 0 |  |  | 0 | 11.01 | 0 | 0
0 | IDC | MERC/CAPEX/2023-24/0184 | 2024-03-12 | 0.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M with raising of drain wells and modification of Masonary Dam (Waste Weir), 4 x210 MW, TPS, Khaperkheda | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 45.0535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.1 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M at TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 31.0231 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.2 | Raising of drain wells of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 1.6569 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.3 | Modification of Masonary Dam (Waste Weir) of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 10.1857 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 2.1878 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32 | Flue Gas Desulphurisation (FGD) System for Khaperkheda Unit # 1 & 2 | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 115.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.1 | Flue Gas Desulphurisation (FGD) System for Khaperkheda Unit # 1 & 2 | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 109.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 5.54 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33 | Upgradation of DDC/DCS system for UNIT 1 & 3 of 210 MWKhaperkheda TPS | MERC/CAPEX/MSPGCL/2023-24/601 | 2023-11-10 | 39.14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.1 | Upgradation of DDC/DCS system for UNIT 1 & 3 of 210 MWKhaperkheda TPS | MERC/CAPEX/MSPGCL/2023-24/601 | 2023-11-10 | 38.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/601 | 2023-11-10 | 0.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34 | Supply & commissioning of interconnection conveyor belt, Elecon make complete impact type crusher, Procurement of 4 NOs. Bull Dozer BEML BD-155 and Eco friendly and power efficient chiller system at Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 28.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.1 | Design, engineering, manufacturing, supply, erection & commissioning of interconnection conveyor belt from 1 X 500MW to 4 X 210MW stack yard at CHP Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.2 | Supply & installation of Elecon–make complete impact type crusher at CHP-I, Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 4.29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.3 | Procurement of 4 NOs. Bull Dozer BEML BD-155 at CHP, Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.255 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.4 | Supply, erection, & commissioning of Eco friendly and power efficient chiller system for khaperkheda TPS Unit 1 to 4, Service Building and WTP in place of present reciprocating type Chiller system | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 11.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 1.385 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | 5 Nos. of Boiler Improvement Schemes for Unit No. 1 to 4 | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 32.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Procurement & replacement of Re-Heater Rear Pendent Assembly Coils for unit no. 3 & 4 (210 MW) | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 8.86 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.2 | Procurement Complete Set of Sky Climber For Unit#1 To 5 Boilers. | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 3.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.3 | Replacement of glasswool insulation and GI/CORRUGATED sheets of boiler and hot air ducts at unit 1to 4 KHAPERKHEDA TPS | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 2.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.4 | Procurement, design, manufacture, supply & delivery, dismantling, retrofitting, erection, commissioning and testing of gravimetric belt conveyor type coal feeders for unit no. 1 & 2. | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 6.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.5 | Procurement and Replacement of Air Preheater Baskets for Unit no. 1 to 4 (4x 210MW). | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 9.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 2.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR-17 | Various DPR Schemes for The work of maintaining the zero discharge condition of Pond No. 2 & Pond No.3 and providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 15.7443 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | The work of maintaining the zero discharge condition of Pond No.2 & Pond No.3 at KTPS Koradi | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 4.2068 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.2 | Providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 11.5375 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Scheme of HMI upgradation of unit 5 DCS along with Max Links , HART Scheme , PADO , all BOP PLCs , SWAS system, CO analyser & Coal feeder controller to match with the external aspect , process improvement & Up gradation of Generator Protections Relays in unit 1 to 4 of 210 MW at khaperkheda TPS | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 33.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.7 | Up-gradation of Generator Protections Relays in Unit 1 to 4 of 210 MW Khaperkheda TPS. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 8.31 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/478 | - | 0.86 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Submitted to MERC, Yet to receive approval | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR on Refurbishment of Spare HPT Module Unit 1 & 2 at TM-I and Procurement of Complete Gear Box Assemblies of Coal Mills XRP 803 ½ HP & XRP 883 for Unit No. 1 to 4 (4x210 MW), Khaperkheda TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Refurbishment of spare HPT module Unit 1 & 2 at TM-I (4X210 MW), KHAPERKHEDA TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Procurement of Complete Gear Box Assemblies of Coal Mills XRP 883 for Unit-1 to 4 (210MW). | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | SUPPLY INSTALLATION TESTING & COMMISSIONING REVAMPING OF FIRE DETECTION & ALARM AND PROTECTION SYSTEM FROM FIRE AND PROVIDING RAPID EXTINGUISHING CLEAN AGENT (CA) SYSTEM AT UNIT -3,4 & 5 ATKPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Supply Installation Testing & Commissioning , Revamping of fire protection and providing rapid extinguishing clean agent (CA) system at unit # 3 ,4 210 MW TPS, KHAPERKHEDA | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Restoration of various Fire protection system at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Restoration of fire hydrant ring and fire water spray Header at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Restoration of deluge valve system at CHP-210MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | VARIOUS SCHEMES PROPOSED FOR IMPROVEMENT OF CHP-I (4 X 210 MW). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Design, Manufacturing, Supply, Erection, Commissioning & Testing of Coal Flow Management system for Coal Bunkers in CHP-I (4 X 210MW), Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Design, engineering, manufacturing, supply, installation and commissioning of Dedusting System for Crusher House and Bunker area in Unit 3 & 4 at CHP-I (4 X 210MW), Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Renovation including replacement of Power & Control cables with automation & upgradation of Stacker Reclaimer No. 1 in CHP-I (4 X 210MW), TPS Khaperkheda." | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Flue Gas Desulphrisation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | FGD installation of 210MW unit 1 & 2 at Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Upgradation of DDC/DCS system for UNIT 2 & 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Upgradation of DDC/DCS system for UNIT 2 & 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#1 to 4 Khaperkheda TPS & Upgradation of various governing Element for smooth operation for flexible operation of TG set at 40% technical minimum operation. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#1 to 4 Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.2 | Upgradation of various governing Element for smooth operation for flexible operation of TG set at 40% technical minimum operation. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Upgradation of Battery Charger , UPS system , GEHO PLC and VFD, ID VFD, supply of Efficiency Measuring Instruments and Supply, erection and commissioning of Sox, Nox , CO, Opacity, ETP and Oxygen Analyser for Unit 1 to 4 of 210 MW at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Supply of Efficiency Monitoring Instruments for performance optimization group (POG) at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.2 | Upgradation of 220 V, 24 V DC Float cum boost battery charger at Unit#1 to 4 Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.3 | Upgradation of 2X50 KVA UPS at Unit#1 to 4 Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.4 | Supply, Erection and Commissioning of Sox, Nox , CO, Opacity and ETP Analyser for Unit 1 to 4 of 210 MW at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.5 | Upgradation of GEHO PLC and VFD along with HCSD system Instrumentaion at Unit 3 & 4 Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.6 | Supply, Erection & Commissioning of Oxygen Analyzer for combustion optimization for Unit#1 to 5 Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.7 | Upgradation of VFD for ID FAN in Unit# 3 & 4, 210MW khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.8 | Scheme 8 Supply, erection & commissioning of PLC and SCADA System of Ash Evacuation and Disposal System for UNIT 3 and 4 Of 210 MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of LP Rotor for unit 1 and 2 , Supply and installation of air washer unit 1 and 2 and refurbishment of air washer unit for unit 3 and 4 and GEHO Pummp house control room. Supply and installation of diesel engine driven fire fighting pump with engine. Procurement of various control valves for unit No. 1 to 4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.1 | Supply and installation of Air washer unit in unit 1 and 2 , 6.6 KV breaker room, Turbine MCC room Battery room Boiler MCC room for cooling of all the Electrical Panels and AHP stage I Pump House control room air washer system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.2 | Refurbishment of Air washer unit of 3 and 4, 6.6 KV breaker room, Turbine MCC room Battery room Boiler MCC room for cooling of all the Electrical Panels and Refurbishment of GEHO pump House and AHP stage II Pump House control room air washer system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.3 | Procurement of Complete LPT rotor for unit 1 and 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.4 | Revamping of diesel engine driven fire fighting pump system with engine. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.5 | Procurement of various control valves for unit No. 1 to 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of IP Rotor and Inner casing for unit 1 and 2. Procurement of IP rotor and inner casing for unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.1 | Procurement of IP Rotor and Inner casing for unit 1 and 2. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.2 | Procurement of IP rotor and inner casing for unit 3 and 4 along with Turbovisory sensors and panel | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.3 | Supply and installation of srew compressor for supply of instrument air to unit No. 3 and 4 along with dryer for unit No. 3 & 4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of LP rotor for unit 3 and 4 and upgradation of BFP cartridge and BFP Booster pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.1 | Procurement of of LP rotor for unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.2 | Upgradation of BFP cartridge and BFP Booster pump, motorized scoop for hydraulic coupling and drive unit for BFP and modulating BFP RC valve for Unit 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Refurbishment of LP rotor of unit 1 and 2 and Refurbishment of HPT module of unit 1 and 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.1 | Refurbishment of LP rotor of unit 1 and 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.2 | Refurbishment of HPT module of unit 1 and 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Refurbishment of LP rotor for unit 3 and 4 and Refurbishment and re-blading of HPT module of unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.1 | Refurbishment of LP rotors for unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.2 | Refurbishment of HPT modules of unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | SITC OF COMPLETE SOLUTION AND COMPREHENSIVE PROTECTION AND MONITORING PACKAGE ALONG WITH RETROFIT OF ALLIED ACCESSORIES FOR VARIOUS GTs & STs INSTALLED AT 210 MW KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | SUPPLY,INSTALLATION, TESTING & COMMISSIONING OF COMPLETE SOLUTION AND COMPREHENSIVE PROTECTION AND MONITORING PACKAGE ALONG WITH RETROFIT OF ALLIED ACCESSORIES FOR VARIOUS GTs & STs INSTALLED AT 210 MW KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | PLANT PERFORMANCE IMPROVEMENT BY DESIGN, SUPPLY, INSTALLATION & COMMISSIONING OF STATE OF ART HT VACCUM CIRCUIT BREAERS AT UNIT 1 TO 4 OF 210MW KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.1 | DESIGN, SUPPLY, INSTALLATION, TESTING & COMMISSIONING OF HT VCB AT U # 1 & 2. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.2 | DESIGN, SUPPLY, INSTALLATION, TESTING & COMMISSIONING OF HT VCB AT U # 3 & 4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | DESIGN, SUPPLY, INSTALLATION, TESTING AND COMMISSIONING OF THE VARIOUS LIFTS IN PLACE OF THE EXISTING OLD LIFTS, LIGHTNING PROTECTION SYSTEM, EARTHING SYSTEM, AVIATION LIGHTING SYSTEM INSTALLED AT UNIT # 1 TO 4 OF 210 MW, KHAPERKHEDA TPS ON OEM BASIS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | DESIGN, SUPPLY, INSTALLATION, TESTING AND COMMISSIONING OF THE VARIOUS LIFTS IN PLACE OF THE EXISTING OLD LIFTS INSTALLED AT UNIT # 1 TO 4 OF 210 MW, KHAPERKHEDA TPS ON OEM BASIS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Design, Engineering, Supply, Erection, Testing & Commissioning of lightning protection system at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Design, Engineering, Supply, Erection, Testing & Commissioning of Earthing of electrical system & various buildings at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Design, Engineering, Supply, Erection, Testing & Commissioning of Aviation Lighting Syatem at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | SUPPLY OF SPARE GENERATOR ROTOR FOR U#3 &4, 210MW, TPS KHAPERKHEDA. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.1 | SUPPLY OF SPARE GENERATOR ROTOR FOR U#3 &4, 210MW, TPS KHAPERKHEDA. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | PROCUREMENT OF ENERGY EFFICIENT MOTORS FOR U # 1 TO 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.1 | PROCUREMENT OF ENERGY EFFICIENT MOTORS FOR U # 1 & 2 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.2 | PROCUREMENT OF ENERGY EFFICIENT MOTORS FOR U # 3 & 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.3 | Procurement of DC motors for U # 1 & 2 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.4 | Procurement of DC motors for U # 3 & 4 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | UPGRADATION OF EXISTING LT MCC PANEL WITH STATE OF ART LT MCC PANEL AT U # 1 TO 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | UPGRADATION OF EXISTING LT MCC PANEL WITH STATE OF ART LT MCC PANEL AT U # 1 & 2 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.2 | UPGRADATION OF EXISTING LT MCC PANEL WITH STATE OF ART LT MCC PANEL AT U # 3 & 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.3 | UPGRADATION OF HT BREAKER PANEL AT WAREGAON ASH BUND OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | UPGRADATION OF HT BREAKER PANEL AT OLD PROJECT OFFICE OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.5 | Retrofitting of Existing L & T make LT MCC ACB by state or art ACB at U # 1 to 4 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.6 | Retrofitting of Existing ABB make LT MCC ACB by state or art ACB at U # 1 to 4 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | ERECTION & COMMISIONING OF DRY TYPE CAST RESIN TRANSFORMERS FOR U # 1 TO 4 OF KHAPERKHEDA TPS & Design, Engineering, Supply, Erection, Testing & Commissioning of various Battery sets at Unit # 3 & 4 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | PROCUREMENT OF DRY TYPE CAST RESIN TRANSFORMERS FOR U # 1 & 2 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.2 | PROCUREMENT OF DRY TYPE CAST RESIN TRANSFORMERS FOR U # 3 & 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.3 | PROCUREMENT OF VFD TRANSFORMERS FOR ID FAN MOTOR U#3&4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.4 | Design, Engineering, Supply, Erection, Testing & Commissioning of various Battery sets at Unit # 3 & 4 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20 | Study, Supply & Refurbishment of HCSD systems, ESP operation, ambience & various pump, & PLC schemes for the improvement of AHP-I at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.1 | STUDY. DESIGN & REFURBISHMENT WORKS OF HIGH CONCENTRATION SLURRY DISPOSAL SYSTEM (HCSD SYSTEM) UNITS #3&4 AT AHP-1, TPS KHAPERKHEDA. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.2 | STUDY, DESIGN & REFURBISHMENT WORKS OF ARTs AND ASSOCIATED MOUNTINGS & ACCESSORIES OF HCSD SYSTEM FOR AHP-I, TPS KHAPERKHEDA.” | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.3 | ‘SUPPLY & REFURBISHMENT WORKS OF HCSD ASH SLURRY MIXER SYSTEM AT UNIT #3 &4 OF AHP-I, TPS KHAPERKHEDA’. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.4 | ‘STUDY, SUPPLY, RESTORATIONS & REPLACEMENT OF ALL INTERNAL SPARES OF D6 FIELD & RENOVATION OF D1 FIELD OF U3 DURING AOH FOR AHP-I, TPS KHAPERKHEDA’ | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.5 | PROCUREMENT OF VARIOUS PUMPS IN RECYCLE WATER SYSTEM IN ASH HANDLING PLANT 4X210 MW AT KHAPARKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Reliability improvement and complete replacement of ABC series with drive unit of ash slurry pipeline of 7 KM of 4*210MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Procurement and restoration of complete pipeline replacement of ABC series | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.2 | Procurement and restoration of complete drive unit replacement of ABC series | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | Procurement and restoration of complete Bottom ash hopper replacement including entire structure, Clinker grinder alongwith motor, Feed Gate, Power Cylinder and Pipelines discharge of U3&4 of 4*210MW Khaparkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.1 | Procurement and restoration of complete BAH replacement including entire structure and clinker griender | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.2 | Procurement and restoration of complete drive unit of clinker grinder for Unit 1 to 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.3 | Procurement and restoration of discharge pipeline of vertical sump pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Procurement and restoration of Pipeline garlanding at Waregaon ash Bund of 4*210 MW Khapakheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.1 | Pipeline garlanding at Waregaon ash Bund of 4*210 MW Khapakheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Upgradation, modification and erection of complete wet fly ash evacuation into dry fly ash evacuation systen for ESP 1 and 2 of 4*210 MW Khapakheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.1 | Upgradation, modification and erection of complete wet fly ash evacuation into dry fly ash evacuation systen for ESP 1 and 2, 4*210 MW Khapakheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | Reliability improvement and complete replacement of JKL series with drive unit of ash slurry pipeline of 7 KM of 4*210MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.1 | Procurement and restoration of complete pipeline replacement of JKL series | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.2 | Procurement and restoration of complete drive unit replacement of JKL series | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | Study, Supply and Refurbishment of HCSD System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.1 | Procurement of complete Suction and discharge valve of Geho pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.2 | Procurement of Subassemblies of Geho pump. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.3 | Upgradation and compressors of dry ash evacutaion system of U#3&4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.4 | Procuremenet of complete drive unit and VFD of GEHO pump. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | RENOVATION OF ESP FIELD INTERNALS FOR UNIT 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.1 | RENOVATION OF ESP FIELD INTERNALS FOR UNIT 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28 | R & M OF APH OF UNIT # 1& 2 (2 x 210MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28.1 | R & M OF APH OF UNIT # 1& 2 (2 x 210MW) OF KHAPERKHEDA TPS FROM MODEL: 27 VI 1850 TO 27 VI 2000 mm. DESIGN, ENGINEERING, SUPPLY, ERECTION & COMMISSIONING OF DOUBLE SEALING | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29 | DPR FOR ECONOMISER COILS AND APH GEAR BOX | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29.1 | PROCUREMENT AND REPLACEMENT OF COMPLETE SET OF ECONOMISER UPPER BANK & LOWER BANK COILS FOR KHAPERKHEDA TPS UNIT NO.3&4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29.2 | Procurement of APH gear box in unit no. 1 & 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29.3 | Procurement of APH speed reducer gear box in unit no. 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30 | DPR FOR LTSH COILS , APH BASKETS & RH OUTLET STUB BENDS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.1 | Procurement of Air Pre-heater Baskets for unit no. 2 to 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.2 | Procurement of LTSH coils for unit no. 1 & 2 and Procurement of Reheater outlet header stub bends for unit no. 1 to 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.3 | Procurement of LTSH coils for unit no. 3 & 4 and Procurement of Reheater outlet header stub bends for unit no. 3 to 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31 | DPR FOR SUPPLY & REPLACMENT OF THERMAL INSULATION OF BOILER AND DUCT AT UNIT 1 TO 4 KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.1 | SUPPLY & REPLACMENT OF THERMAL INSULATION OF BOILER AND DUCT AT UNIT 1 TO 2KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.2 | SUPPLY & REPLACMENT OF THERMAL INSULATION OF BOILER AND DUCT AT UNIT 3 TO 4 KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32 | DPR FOR COAL CYCLE IMPROVEMENT IN UNIT NO.1 TO 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.1 | Procurement of Complete Journal Assembly for 803 ½ HP Coal Mills of Unit No. 1 To 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.2 | Procurement of Complete Journal Assembly for XRP 883 Coal Mills of Unit No. 3 To 4, | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.3 | Procurement of assembly of worm shaft & worm wheel with hub for unit no. 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.4 | PROCUREMENT OF COMPLETE GEAR BOX ASSEMBLIES OF COAL MILLS XRP 803 ½ HP FOR UNIT # 1 TO 2 AT KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.5 | PROCUREMENT OF COMPLETE GEAR BOX ASSEMBLIES OF COAL MILLS XRP 883 FOR UNIT # 3 TO 4 AT KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33 | DPR FOR PERFORMANCE IMPROVEMENT OF BOILER PA FAN, ID FAN AND FD FAN IN UNIT NO. 1 TO 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.1 | Procurement of PA fan Casings along with Dampers in Unit- 1 & 2, at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.2 | PROCUREMENT OF COMPLETE ROTOR ASSEMBLY ALONG WITH MOTOR FOR NDZV 31 SIDOR IN UNIT NO. 1 & 2 KHAPERKHEDA TPS (ID FAN) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.3 | PROCUREMENT OF FD FAN (BHEL AP 1-20 / 11) ASSEMBLY ALONG WITH DRIVE UNIT(MOTOR) FOR UNIT 1 & 2 AT KHAPERKHEDA TPS UNDER OEM NATURE ITEMS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.4 | PROCUREMENT OF FD FAN (BHEL AP 1-20 / 11) ASSEMBLY ALONG WITH DRIVE UNIT(MOTOR) FOR UNIT 3& 4 AT KHAPERKHEDA TPS UNDER OEM NATURE ITEMS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.5 | NDZV 33 SIDOR ID Fan Impeller Assembly for Unit 3 & 4 at TPS, Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.6 | Design, Engineering, Manufacturing, Supply & Commissioning including civil works for installation of 70 LPM lubricant ystems for PA Fans in unit no. 1&2. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.7 | Supply and installation of ID and PA foundation deck spring for unit no. 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34 | VARIOUS SCHEMES FOR BOILER PERFORMANCE IMPROVEMENT | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.1 | SUPPLY OF COAL MILL SEPERATOR & SCRAPPER BODIES FOR XRP-803 1/2 HP COAL MILLS IN UNIT 1 & 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.2 | MODIFICATION OF EXISTING COAL BUNKER AND COMMISSIONING OF BUNKER CHUTE ASSEMBLY WITH VIBRATING MOTOR TO AVOID BUNKER MOUTH COAL CHOKE UP FOR UNIT 1 & 2AT KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.3 | MODIFICATION OF EXISTING COAL BUNKER AND COMMISSIONING OF BUNKER CHUTE ASSEMBLY WITH VIBRATING MOTOR TO AVOID BUNKER MOUTH COAL CHOKE UP FOR UNIT 3 & 4 AT KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.4 | DESIGN, DEVELOPMENT, COMMISIONING OF SEAL AIR FAN ASSEMBLIES IN UNIT 1 & 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.5 | Procurement of sub body assembly of control valve in unit no. 1 & 2 actuating main gear unit part electrical actuator in unit no. 1 to 4 Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | Construction of A, B, C, D & E type stilt + 6 floor buildings at TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Construction of A, B, C, D & E type stilt + 6 floor buildings at TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36 | Enhancement & Renovation of existing building, Construction of Market building, Construction of club building community hall, Construction of school building, & Enhancement of existing domestic plant providing V wire 3 MLD at Colony TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.1 | Enhancement / Renovation & strengthening of existing building & allied works in colony TPS Khaperkhda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.2 | Construction of Market building including approach road, drainage arrangement & electrification at colony TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.3 | Construction of club building / community hall | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.4 | Construction of school building | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.5 | Enhancement of existing domestic plant providing V wire 3 MLD | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37 | Enhancement / Renovation of Saudamini Administrative Building, Construction of VIP Guest House, Construction of roads at Prakashnagar Colony and Providing various civil works related to coal transport railway lines of khaperkheda TPSTPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.1 | Enhancement / Renovation of Saudamini building | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.2 | Construction of VIP guest house TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.3 | Construction of Roads | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.4 | Construction of office building & store for electrical maintenance & Civil at KPKD | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.5 | Providing Special repair & retrofitting work of river bridge no.09 on Khaperkheda - Kalumna railway siding of TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.6 | Construction & repairing of drains & culverts along coal Transporting Railway lines & approach road of TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.7 | Repairing, providing & applying Epoxy Painting and Structural Steel Works to steel structural bridges on kpkd to Kaluma and kpkd to Saoner railway lines as per recommendation of structural stability report at TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.8 | Construction of compound wall KPKD Colony | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38 | Work of Strengthening and modification of Main Plant, construction of roads, strengthening of IDCT 1 to 4 in plant area, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.1 | Work of attending additional works based on structural report at Induced Draft Cooling Towers(IDCT) unit 1,2,3 & 4 at 4 x 210MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.2 | Work of constructon of roadside drains from VIP gate no.3 to IDCT No.1 at 4 x 210MW TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.3 | Construction of bituminous macadam road from Administrative Building to GCR Road near Service Building of 4X210MW TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.4 | Work for Construction of cement concrete road for equipment movement for salt lagoon (WTP-I), FGD(System), H2(cylinders) plant etc. inside plant premises in 4x 210MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.5 | Construction of cement concrete road outside BTG area of Power Plant 4 x 210MW TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.6 | Construction of cement concrete road for material transportation from D-Point CHP to reject coal Dumping yard in 4x 210MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.7 | Work of Strengthening and modification of Main Plant, Major Stores, Auxiliary in plant area, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.8 | Construction of diversion road along with RCC bridge from rejct coal yard CHP-I & CHP-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.9 | Upgradation of existing ETP plant consist civil works, electrification and pumps. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
39 | Work of 5th Raising of Waregaon Ash Bund, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
39.1 | Work of 5th Raising of Waregaon Ash Bund, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
40 | Work of CTR(Complete Track Removal),TTR(TRAIN TRAVLER REGULATOR) and Yard Remoulding incl. misc. works at Mahagenco Khaperkheda Plant. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
40.1 | Work of CTR(Complete Track Removal),TTR(TRAIN TRAVLER REGULATOR) and Yard Remoulding incl. misc. works at Mahagenco Khaperkheda Plant. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41 | Various WTP 210MW improvement schemes i.e. Up-gradation of SWAS SYSTEM UNIT- 1 to 4 at WTP-I 210 MW along with coal sampling lab upgradation, Comissioning of CW Chemical Dosing system etc | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.1 | Upgradation of Existing ETP system viz. Plate Settler, Settling tank, Sludge Drying bed, Chemical dosing system etc.)as per MPCB consent condition | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.2 | Upgradation of SWAS Lab 3& 4 at WTP-210 MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.3 | Revamping of Chlorination Plant Stream (A+ B) & Installation, Comissioning of CW Chemical Dosing system (Viz. Scale inhibitor, Scale Dispersant, Biodispersant, Corossion Inhibitor & H2SO4 dosing) and Online CW Chemical parameter monitoring system at KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.4 | Upgradation of SWAS Lab 1& 2 at WTP-210 MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.5 | Upgradation of Water &Coal testing Lab at WTP-210 MW &Procurement of Coal Lab Instruments and upgradation of coal sampling Room & Instruments related to Coal sample Preparation. at WTP-210 MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42 | Work of capacity restoration of unloading stream from Beetle Charger No. 1 to Stacker/Reclaimer No. 1 for perfromance improvement of CHP-I (4 x 210 MW) & Capacity restoration of unloading stream from Beetle Charger No. 1 to Stacker/Reclaimer No. 1 for perfromance improvement of CHP-I (4 x 210 MW). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.1 | Revamping/ refurbishment, capacity restoration and upgradation for beetle charger No. 1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.2 | Revamping/ refurbishment, capacity restoration and upgradation for Wagon Tippler No. 1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.3 | Revamping/ refurbishment, capacity restoration and upgradation for Apron Feeder No. 1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.4 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 2C, 3A, 4A, 8A, 9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.5 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for impact crusher and wobbler feeder No. 1 & 3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.6 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Stacker/Reclaimer No. 1. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.7 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv. 3C to 3A, Conv. 3A to 4A, Conv. 4A to 8A and Conv. 9 by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.8 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of beetle Charger, wagon tippler, apron feeder, covneyors (Conv. 2C, 3A, 4A, 8A, 9), crushers/ wobbler feeder No. 1 & 3 and Stacker/Reclaimer No. 1 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
43 | DPR fo Capacity restoration of bunkering stream from Conv. 5A to 7A/B/C/D including shuttle conveyors in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
43.1 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 5A, 6B, 7A, 7B, 7C, 7D and Shuttle Conv. 1 to 4 in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
43.2 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv.Conv. 4D to 5A/B , 5A to 6B, Conv. 6B to 7A & 7B, Conv. 7B to 7D upto shuttle conveyor, Conv. 7A to 7C upto shuttle conveyor by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
43.3 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of covneyors (Conv. 5A, 6B, 7A/B/C/D & Shuttle Conv. 1 to 4 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44 | Work of capacity restoration of unloading stream from Beetle Charger No. 2 to Stacker/Reclaimer No. 2 for perfromance improvement of CHP-I (4 x 210 MW). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.1 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for beetle charger No. 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.2 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Wagon Tippler No. 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.3 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Apron Feeder No. 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.4 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 2D, 3B, 4B, 8B, 10 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.5 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for impact crusher and wobbler feeder No. 2 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.6 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Stacker/Reclaimer No. 2. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.7 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv. 2D to 3B, Conv. 3B to 4B, Conv. 4B to 8B and Conv. 10 by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.8 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of beetle Charger, wagon tippler, apron feeder, covneyors (Conv. 2D, 3B, 4B, 8B, 10), crushers/ wobbler feeder No. 2 & 4 and Stacker/Reclaimer No. 2 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45 | Work of capacity restoration of bunkering stream from Conv. 1A/B, 2A/B, 5B to 7E/F/G/H including shuttle conveyors in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.1 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 1A/B, 2A/B, 5B, 6A, 7E, 7F, 7G, 7H and Shuttle Conv. 5 to 8 in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.2 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv. 1A/b to 2A/B,Conv. 4C to 5A/B, Conv. 5B to 6A, Conv. 6A to 7E & 7F, Conv. 7E to 7G upto shuttle conveyor, Conv. 7F to 7H upto shuttle conveyor by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.3 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of conveyor system from Conv. 1A/B, 2A/B, 5B, 6A, 7E, 7F, 7G, 7H and Shuttle Conv. 5 to 8 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.4 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Paddel Feeder No. 1 to 4 and truck hopper in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46 | Renovation and upgradation of various electrical system for CHP-I (4 x 210 MW) improvement & Renovation and upgradation of various electrical system for CHP-I (4 x 210 MW) improvement. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.1 | Design, development and upgradation with circuit breaker VFD of various LT MCC of CHP-I. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.2 | Design, Supply, Installation, Commissioning and Testing of Energy Chain System for Paddle Feeder, Shuttle Conveyor and Stacker/Reclaimers in CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.3 | Upgradation of relay logic system with PLC & SCADA in CHP-I control room and Wagon Tipplers in CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.4 | Complete upgradation of conveyor lighting system with energey efficient LED lights for CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.5 | Providing, installation, testing commissioning, maintenance and operation of explosion proof & weather proof surveillance system at CHP-I (4 X 210 MW), TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.6 | Complete revamping/refurbishment, upgradation and modification of various EOT cranes & hoist installed at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47 | Procurement of various capacity SAN make locomotives and BEML make loader & bulldozer for CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.1 | Procurement of various capacity SAN make locomotives and BEML make loader & bulldozer for CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48 | CHP Improvement Schemesfor 4x 210 MW units | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.1 | Design, manufacture, supply and installation of suspended magnet for bunkering belts at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.2 | Design, manufacture, supply and installation of travel drive system for shuttle conveyors and conveyors at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.3 | Renovation including replacement of Power & Control cables with automation & upgradation of Stacker Reclaimer No. 2 in CHP-I (4 X 210MW), TPS Khaperkheda." | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.4 | Complete reconditionding & upgradation of LT MCC installed at Unit No. 3 & 4 bunker auxiliareis in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.5 | Complete reconditionding & upgradation of outdoor lighting system in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.6 | Complete reconditionding & upgradation of HT breaker, control circuits & protection relays in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.7 | Complete revamping/refurbishment, upgradation and modification of various monorail hoists & winch machine installed at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.8 | Procurement of hydra 14 Ton above capacity and heavy vehicles for CHP- I & II. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
49 | Installation of Real Time Coal Analyzer at all TPS of Mahagenco | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
49.1 | Installation of Real time Coal Analyzer at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50 | Railway expenses for refurbishment of OHE lines at CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50.1 | Railway expenses for refurbishment of OHE lines at CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | PROCUREMENT COMPLETE Gear BOX ASSEMBLIES FOR 803 1/2 HP & XRP 883 COAL MILLS OF UNIT NO. 1& 2 AT KHAPERKHEDA TPS. | N.A. | - | 0 | 0 | 0 | 0 | 4.5548 | 4.5548 |  |  | 4.5548 | 0
2 | Supply Erection and commissioning of Oil Cooled Suspended magnets at Conv 6A & 6B at Khaperkheda TPS. | N.A. | - | 0 | 0 | 0 | 0 | 1.1484 | 1.1484 |  |  | 1.1484 | 0
3 | Procurment of new 02 Ambulance Van & 2 Truck for KPKD TPS(Asset Nos. 170100512, 170100513, 170100514, 170100515) | N.A. | - | 0 | 0.41055 | 0.41055 | 0 | 0 | 0 |  |  | 0 | 0
4 | GEHO PUMP (Valve housing assembly) | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | RESTORATION OF AHP OUTLET TO ESP INLET DUCTS U#1&2(Unit #2 Part only) | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | ABC powder type and foam type composite Fire Extinguisher | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | FFEQUIP HYDRAULIC JACK (BM-I) | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | MOBILE COAL SAMPLING EQUIP-AUGER (FMC) CHP-I | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Replacement of ash slurry disposal pump to improve performance & capacity enhancement of ash slurry disposal system at AHP-1 Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of Pillow Block Dodge Bearing Assemblies (Expansion & Non-Expansion) for PA fans in Unit- n1 to 4, at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Replacement of Economizer outlet to APH outlet common duct in unit no. 3 (210MW), Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | PROCUREMENT OF OIL COOLED SUSPENSION MAGNET FOR 210MW AND MODIFICATION & REPLACEMENT OF VIBRATING FEEDER WITH VIBRATING TRANSFER CHUTE FOR 210MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | DESIGN,ENGINEERING,MODIFICATION ,ERECTION AND COMMISSIONING OF DRIVE UNIT ARRANGEMENT FOR CONVEYOR 10 AT CHP1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | ENERGY EFFICIENT PLANT LIGHTING AND COLONY LIGHTING MODIFICATIONS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | Supply installation testing and commisioning of various battery sets at unit No 1 & 2 of Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | Revamping and modification of existing alarm and protection system from fire and provide rapid extinguishing Clean Agent (CA) system at Unit #1 & 2 (210 MW) units, KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | Supply of electronic modules for Procontrol DCS system in unit 1 to 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | Revamping & UPGRADATION of SWAS system in unit 3 & 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | Upgradation of process instrumentation in unit 1 to 2 of 210 MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20 | Replacement of flue gas duct from air heater outlet to esp inlet for U 1 & 2 (S+W) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | PROCUREMENT OF COMPLETE ROTOR ASSEMBLY FOR NDZV 31 SIDOR IN UNIT NO. 1 & 2 KHAPERKHEDA TPS (ID FAN). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | UPGRADATION OF BELT CONVEYOR CAPACITY OF 2C &2D AND 8A & 8B AT CHP1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | WORK OF DESIGN,ENGINEERING,ERECTION AND UPGRADATION OF DRIVE UNITS OF BELT CONVEYOR 3A & 3BAT CHP1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Procurement of 1500 KW ID Fan Synchronous Motor at Unit 3 & 4 Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | Procurement of Steam and Water Analysis System(SWAS) for Unit 1&2 (210MW) KPKD TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | Supply and replacement of complete PVC fills of cell of cooling tower of unit 1-4 (210 MW) at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | PROCUREMENT OF FD FAN (BHEL AP 1-20/11) ASSEMBLY FOR UNIT 1 TO 4 ATKHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28 | CHP performance improvement scheme for capacity restoration of drive units installed at CHP-1 (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29 | Work of Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of belt conveyor 8A & 8B and belt conveyor 2C & 2D at CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30 | WORK OF DESING,SUPPLY ,ERECTION,COMMISSIONG AND UPGRADATION OF COMPLETE ELECTRICAL SYSTEM FOR DRIVE UNITS OF BELT CONVEYOR 3A & 3B AND BELT CONVEYOR 4A,4B,4C & 4D AT CHP1 Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31 | Supply, Installation, & Commissioning of Instruments at coal Testing Lab, WTP-I, TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32 | Supply, Installation & Commissioning and Refurbishment of asbestos based H2 Generator and compressor to convert it to non-asbestos based H2 Generator for Unit 1 to 5, Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33 | construction of bituminous macadam roads at Prakashnagar Colony TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34 | Work of attending additional works based on structural report at Induced Draft Cooling Towers (IDCT) unit 1,2,3 & 4 at 4 x 210MW, TPS, Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | VIBRATION ANALYSER | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36 | Upgradation of GEHO pump instrumentation for AHP Unit No. 3 & 4 (210 MW) at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37 | Refurbishment of HPT module for Unit 1 & 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38 | General Asset Furniture | N.A. | - | 0 | 0.76874 | 0.76874 | 0 | 0.084353 | 0.084353 |  |  | 0.084353 | 0
39 | General Asset AC, Fans, Air coolers, water filter etc. | N.A. | - | 0 | 0.40564 | 0.40564 | 0 | 0.009879 | 0.009879 |  |  | 0.009879 | 0
40 | General Asset Computer, scanners, etc. | N.A. | - | 0 | 1.9358 | 1.9358 | 0 | 0.2868 | 0 |  |  | 0 | 0.2868
41 | Land aquired for rly siding | N.A. | - | 0 | 0 | 0 | 0 | 0.4072 | 0.4072 |  |  | 0.4072 | 0
42 | RCC ROAD FROM ASH SILO TO 'D' POINT FOR BULKER MO | N.A. | - | 0 | 0 | 0 | 0 | 0.95225 | 0.95225 |  |  | 0.95225 | 0
| Total |  |  |  | 489.7769 | 234.7191 | 255.0578 | 149.912 | 43.1643 | 0 | 0 | 43.1643 | 361.8055
FY 2023-24
a) DPR Schemes
(i) Submitted to MERC
1 | Combustion optimization system | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 | 10.743 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Dynamic coal flow measurement and control (balancing) system (one) | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 | 8.17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | CO analyser (8 units) | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 | 1.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Oxygen analyser (32 units) | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 | 0.783 | 0.75683 | 0.75683 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Spare HPT module for Khaparkheda Unit 1 & 2 | MERC/CAP/DPR/10/2010-11/1466 | 2010-10-26 | 26.459 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | HPT module 1 No (unit # 1) | MERC/CAP/DPR/10/2010-11/1466 | 2010-10-26 | 23.0379 | 23.9074 | 23.9074 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAP/DPR/10/2010-11/1466 | 2010-10-26 | 3.4211 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Economiser Upper Bank & Lower Bank coils for Khaperkheda Unit no. 3 and Unit no. 4 | MERC/CAP/DPR/10/2010-11/1695 | 2010-12-15 | 26.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Economiser Upper Bank & Lower Bank coils for Khaperkheda Unit no. 3 and Unit no. 4 | MERC/CAP/DPR/10/2010-11/1695 | 2010-12-15 | 26.35 | 11.77 | 11.77 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Economiser & LTSH Upper Bank & Lower Bank coils for Khaperkheda Unit no. 1 and Unit no. 2 | MERC/CAPEX/20112012/01155 | 2011-07-29 | 34.7916 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Economiser & LTSH Coil for Unit 1 | MERC/CAPEX/20112012/01155 | 2011-07-29 | 15.6924 | 15.6924 | 15.6924 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Economiser & LTSH Coil for Unit 2 | MERC/CAPEX/20112012/01155 | 2011-07-29 | 16.1528 | 16.1528 | 16.1528 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20112012/01155 | 2011-07-29 | 2.9464 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Procurement & Replacement of Re-heater Rear Pendant Assembly Coils for 2*210MW Khaperkheda Unit no. 1 and Unit no. 2 | MERC/CAPEX/20122013/00603 | 2012-06-18 | 10.3738 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Re-heater coils for unit no. 1 | MERC/CAPEX/20122013/00603 | 2012-06-18 | 5.1267 | 5.1267 | 5.1267 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Re-heater coils for unit no. 2 | MERC/CAPEX/20122013/00603 | 2012-06-18 | 5.1267 | 5.55 | 5.55 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/00603 | 2012-06-18 | 0.1204 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Procurement of HPT module suitable for khaperkheda TPS Unit 3 & 4 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 36.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Procurement of HPT module suitable for khaperkheda TPS Unit 3 & 4 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 36.2 | 32.4016 | 32.4016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7 | Procurement Spare GTR, Locomotive & Compactors | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 18.4521 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | 250 MVA Spare GTR | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 10.3496 | 11.2511 | 11.2511 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.2 | Procurement of Locomotive 2no’s. | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 5.9927 | 5.9927 | 5.9927 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.3 | Procurement of Compactors 2 no’s. | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 0.42979 | 0.4298 | 0.4298 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 1.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Procurement & Replacement of complete set of LTSH coils for Khaperkheda TPS Unit 3&4 | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 17.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement and replacement of LTSH coils for Khaperkheda TPS at U3 | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 8.58 | 3.4291 | 3.4291 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Procurement and replacement of LTSH coils for Khaperkheda TPS at U4 | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 8.58 | 3.1809 | 3.1809 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 0.65 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Development of Ash Bund (Waregaon) at K'kheda TPS | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 38.7459 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Construction of 3rd upstream raising of existing ash bund from TBL 299.50 Mtr to 302.50 Mtr at Waregaon, Khaperkheda TPS. | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 33.8585 | 32.5375 | 32.5375 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.2 | Construction of masonary dam (Gabion structure) at Waregaon TPS, Khaperkheda. | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 1.0561 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.3 | Construction of approach to drain wells and raising height of drain well no. 1,2 & 3 ash bund at Waregaon, Khaperkheda TPS | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 0.48488 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 3.3464 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Various schemes related to CHP Improvement & Performance Optimization and scheme of conversion of existing Composite OHE to Conventional OHE | MERC/CAPEX/20152016/00422 | 2016-08-03 | 10.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Air Cooled Suspension Magnet for Con. 3 & 6 of CHP 210 MW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 2.18 | 2.2613 | 2.2613 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | Procurement of Impact crusher motor | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.84 | 0.52579 | 0.52579 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.3 | Procurement of 360V, 200 AH battery set and 360V 325 AH battery set for U# 1to 4 | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.1 | 1.4576 | 1.4576 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.4 | Procurement of POG Instruments for Unit 1 to 4 | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.77 | 0.35015 | 0.35015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.5 | Up gradation of safe scan flame scanner system by BHEL scan system in unit no. 1, 3 & 4 | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.6 | Up gradation of old AVR system to DAVR | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.7 | Conversion of existing Composite OHE to Conventional OHE | MERC/CAPEX/20152016/00422 | 2016-08-03 | 2.72 | 2.72 | 2.72 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.47 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | ESP up-gradation for Unit-1 at Khaperkheda TPS | MERC/CAPEX/20152016/01261 | 2016-01-11 | 32.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | ESP up-gradation for Unit-1 at Khaperkheda TPS | MERC/CAPEX/20152016/01261 | 2016-01-11 | 32.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Procurement, installation and commissioning of Gravimetric Belt / Rotary Type Feeder, VFD for CEP, Up-gradation of BTS system & Environmental schemes at Khaperkheda TPS | MERC/CAPEX/20162017/01552 | 2017-02-14 | 20.218 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Procurement, installation and commissioning of Gravimetric belt/rotary Feeder at U-1 & 2 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 5.72 | 4.7418 | 4.7418 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Installation of VFD to CEP at U-1 to 4 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 8.64 | 2.286 | 2.2949 | -0.008878 | 5.7082 | 2.4584 |  |  | 2.4584 | 3.241 | 2.4584 | 0
13.3 | Installation of BTS system at U-4 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 0.98796 | 0.98796 | 0.98796 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.4 | Replacement of SOx/NOx analyzer at U-1 to 4 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 2.42 | 2.3035 | 2.3035 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.5 | Procurement of TGA,CHNS analyzer and Bomb calorimeter at U-5 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 1.71 | 0.2897 | 0.2897 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01552 | 2017-02-14 | 0.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Up gradation of HMI System at Unit No 3 & 4 at Khaperkheda TPS | MERC/CAPEX/20172018/03946 | 2017-07-19 | 13.39 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | HMI Up-gradation at U# 3 & 4 | MERC/CAPEX/20172018/03946 | 2017-07-19 | 12.78 | 12.5611 | 12.5611 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/03946 | 2017-07-19 | 0.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21 | Procurement of APH Basket for unit # 1 to 5 and Up-gradation of HT Motor Protection Relay in Unit # 1 to 4 at Khaperkheda TPS | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 9.77 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.1 | Procurement of assembly of baskets for air preheater of type bisector APH 27 VI: 1850, 12 sector in unit no. 1 & 2 and bisector APH 27 VI: 2000; 24 sector in unit no. 3 & 4 (210MW x 4) at TPS, Khaperkheda | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 5.71 | 8.097 | 5.4819 | 2.6151 | 0 | 2.6123 |  |  | 2.6123 | 0.002845 | 0.22812 | 2.3841
21.3 | Up-gradation of H.T. Motor protection relays in Unit 1 to 4 (210MW), Khaperkheda TPS | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 3.96 | 3.1137 | 3.1137 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 0.1 | 0 | 0 | 0 | 0 | 0.18424 |  |  | 0.18424 | -0.18424 | 0.1 | 0.08424
22 | Procurement of LPT rotor suitable for Unit # 3 & 4 of 210 MW at Khaperkheda TPS | MERC/CAPEX/2018-2019/132 | 2019-05-09 | 27.191 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.1 | Procurement of LPT rotor suitable for Unit # 3 & 4 of 210 MW at Khaperkheda TPS | MERC/CAPEX/2018-2019/132 | 2019-05-09 | 26.491 | 10.7515 | 0 | 10.7515 | 0 | 10.7515 |  |  | 10.7515 | 0 | 10.7515 | 0
0 | IDC | MERC/CAPEX/2018-2019/132 | 2019-05-09 | 0.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23 | Supply, Erection & commissioning of HT Vacuum circuit Breakers & SF6 contactors at AHP (U#1-4) & CHP (U#1 to 5) and 160 KW VFD Panel with Motor for fire-fighting pumps at U#1 to 4 at Khaperkheda TPS | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 10.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.1 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at AHP (Unit#1 to 4, 210MW), Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 4.17 | 3.4843 | 4.8883 | -1.404 | 0 | 0 |  |  | 0 | -1.404 | 0 | 0
23.2 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at CHP (Unit#1 to 4, 210MW) and CHP (Unit#5, 500MW) Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 3.81 | 3.8221 | 0 | 3.8221 | 0.20886 | 2.7332 |  |  | 2.7332 | 1.2978 | 2.7332 | 0
23.3 | Supply, Erection & commissioning of 150 KW VFD Panel with motor for fire-fighting pumps at 210 MW Khaperkheda TPS. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 2.34 | 1.9968 | 0 | 1.9968 | 0.09888 | 2.0957 |  |  | 2.0957 | 0 | 2.0957 | 0
0 | IDC | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 0.58 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24 | Augmentation of Waregaon Ash Water Recovery System at TPS Khaperkheda | MERC/CAPEX/2019-20/732 | 2019-09-16 | 17.1984 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.1 | Augmentation of Waregaon Ash Water Recovery System at TPS Khaperkheda | MERC/CAPEX/2019-20/732 | 2019-09-16 | 15.7884 | 13.9315 | 13.9315 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-20/732 | 2019-09-16 | 1.41 | 0.58812 | 0.58812 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25 | Procurement of VFD with HMI & Controller & Replacing with existing Eddy-current drives of Coal feeders at U# 3 & 4 and Procurement of Various Critical Components of GEHO Pump (Model-TZPM 800) for AHP-1 at Khaperkheda TPS | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 10.6535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25.1 | Up-gradation of Existing BHEL make 36” Gravimetric Coal Feeders control panel with HMI and croprocessor based Controller with VFD, Motor & Weigh Module at Unit 3 & 4, (210MW) | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 7.4655 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25.2 | Procurement of various Critical Components of GEHO Pump (Model-TZPM 800) for AHP-1 (210MW) | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 2.698 | 2.6466 | 2.6466 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 0.49 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26 | Procurement, Replacement of Eco Coils U#1&2 210 MW, & Procurement & replacement of foundation Deck Spring assembly for coal mills U#3,4 at Khaperkheda TPS | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 15.4086 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26.1 | Procurement, Replacement of Eco Coils U#1&2 | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 7.4996 | 6.6503 | 6.6503 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26.2 | Procurement & replacement of foundation Deck Spring assembly for coal mills U#3,4 | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 6.679 | 3.006 | 0 | 3.006 | 0 | 0 |  |  | 0 | 3.006 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 1.23 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28 | ESP Upgradation of 5 Nos. of 210/500MW Units at Khaperkheda, Koradi & Chandrapur TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 90.3535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.1 | ESP Upgradation at Unit #1, Khaperkheda TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 42.7114 | 5.955 | 0 | 5.955 | 35.73 | 0 |  |  | 0 | 41.685 | 0 | 0
28.2 | ESP Upgradation at Unit #2, Khaperkheda TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 42.7114 | 5.955 | 0 | 5.955 | 35.73 | 0 |  |  | 0 | 41.685 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 4.9307 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29 | Flue Gas Desulphurisation System for Khaperkheda Unit # 1-4 | MERC/CAPEX/2021-2022/MSPGCL/097 | 2022-03-14 | 113.4565 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.1 | FGD System for Khaperkheda Unit # 1-4 | MERC/CAPEX/2021-2022/MSPGCL/097 | 2022-03-14 | 109.15 | 51.12 | 0 | 51.12 | 204.46 | 0 |  |  | 0 | 255.58 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/097 | 2022-03-14 | 4.3065 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4 | Construction of coal platform for Chandrapur TPS, Khaperkheda TPS & Parli TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 5.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4.2 | Khaperkheda TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 5.43 | 3.9936 | 3.9936 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 4.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.4a | 1. Procurement of 6.6 KV,300 KW, P.A.fan motor for U# 1 & 2 2. Procurement of 6.6 KV,425 KW,CM motor for U # 3 & 4 3. Procurement of 6.6 KV,1400KW,CW pump motor for U-1& 2 4. Procurement of 6.6 KV,1400 KW,CW pump motor for U-3&4 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 3.82 | 2.5283 | 2.5283 | 0 | 0.069 | 0.069 |  |  | 0.069 | 0 | 0.069 | 0
HO DPR 5.4b | K'kheda: Procurement of HT Motors(GS/HP Water pump)for U-1&2 and Procurement of HT Motors (ACW)for U-3&4 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 1 | 0.4 | 0.4 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.2 | KHAPERKHEDA (U-1 to 4) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.96 | 3.1173 | 3.1173 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.2 | Khaperkheda TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender for KPKD 1-4 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 1.7765 | 1.7765 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.2 | Normal Multipurpose Fire Tender KPKD 1-4 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 2.1847 | 2.1847 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 226.3024 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9.1 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 226.3024 | 266.7 | 0 | 266.7 | 24.53 | 57.6077 |  |  | 57.6077 | 233.6223 | 57.6077 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 4.4604 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.2a | Compond wall (IB recommdation),Plant Patrolling Roads (IB recommdation) TPS KPKD | MERC/CAPEX/20172018/0177 | 2018-02-06 | 4.4604 | 3.9268 | 3.9268 | 0 | 0.023832 | 0.023832 |  |  | 0.023832 | 0 | 0.023832 | 0
HO DPR 11 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 9.23 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11.1 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 9.05 | 13.3057 | 13.3057 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 0.18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15 | Implementation of Water Flow Monitoring system at Chandrapur STPS & Khaperkheda TPS | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 5.1755 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.3 | Electromagnetic Flow meters at various lines & Locations of 210 MW | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 3.8515 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.4 | Automation: Centralized SCADA, RTU, MODBUS Cable, Power cable & mandatory spares | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 1.324 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30 | Supply of spare Generator Rotor for UNIT 1 & 2, 210MW | MERC/CAPEX/2023-24/0184 | 2024-03-12 | 37.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.1 | Supply of spare Generator Rotor for UNIT 1 & 2, 210MW | MERC/CAPEX/2023-24/0184 | 2024-03-12 | 36.7 | 11.01 | 0 | 11.01 | 25.69 | 0 |  |  | 0 | 36.7 | 0 | 0
0 | IDC | MERC/CAPEX/2023-24/0184 | 2024-03-12 | 0.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M with raising of drain wells and modification of Masonary Dam (Waste Weir), 4 x210 MW, TPS, Khaperkheda | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 45.0535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.1 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M at TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 31.0231 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.2 | Raising of drain wells of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 1.6569 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.3 | Modification of Masonary Dam (Waste Weir) of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 10.1857 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 2.1878 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32 | Flue Gas Desulphurisation (FGD) System for Khaperkheda Unit # 1 & 2 | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 115.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.1 | Flue Gas Desulphurisation (FGD) System for Khaperkheda Unit # 1 & 2 | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 109.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 5.54 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33 | Upgradation of DDC/DCS system for UNIT 1 & 3 of 210 MWKhaperkheda TPS | MERC/CAPEX/MSPGCL/2023-24/601 | 2023-11-10 | 39.14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.1 | Upgradation of DDC/DCS system for UNIT 1 & 3 of 210 MWKhaperkheda TPS | MERC/CAPEX/MSPGCL/2023-24/601 | 2023-11-10 | 38.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/601 | 2023-11-10 | 0.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34 | Supply & commissioning of interconnection conveyor belt, Elecon make complete impact type crusher, Procurement of 4 NOs. Bull Dozer BEML BD-155 and Eco friendly and power efficient chiller system at Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 28.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.1 | Design, engineering, manufacturing, supply, erection & commissioning of interconnection conveyor belt from 1 X 500MW to 4 X 210MW stack yard at CHP Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.2 | Supply & installation of Elecon–make complete impact type crusher at CHP-I, Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 4.29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.3 | Procurement of 4 NOs. Bull Dozer BEML BD-155 at CHP, Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.255 | 0 | 0 | 0 | 0 | 12.0596 |  |  | 12.0596 | -12.0596
34.4 | Supply, erection, & commissioning of Eco friendly and power efficient chiller system for khaperkheda TPS Unit 1 to 4, Service Building and WTP in place of present reciprocating type Chiller system | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 11.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 1.385 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | 5 Nos. of Boiler Improvement Schemes for Unit No. 1 to 4 | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 32.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Procurement & replacement of Re-Heater Rear Pendent Assembly Coils for unit no. 3 & 4 (210 MW) | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 8.86 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.2 | Procurement Complete Set of Sky Climber For Unit#1 To 5 Boilers. | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 3.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.3 | Replacement of glasswool insulation and GI/CORRUGATED sheets of boiler and hot air ducts at unit 1to 4 KHAPERKHEDA TPS | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 2.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.4 | Procurement, design, manufacture, supply & delivery, dismantling, retrofitting, erection, commissioning and testing of gravimetric belt conveyor type coal feeders for unit no. 1 & 2. | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 6.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.5 | Procurement and Replacement of Air Preheater Baskets for Unit no. 1 to 4 (4x 210MW). | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 9.05 | 0 | 0 | 0 | 2.7935 | 2.7935 |  |  | 2.7935 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 2.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR-17 | Various DPR Schemes for The work of maintaining the zero discharge condition of Pond No. 2 & Pond No.3 and providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 15.7443 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | The work of maintaining the zero discharge condition of Pond No.2 & Pond No.3 at KTPS Koradi | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 4.2068 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.2 | Providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 11.5375 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Scheme of HMI upgradation of unit 5 DCS along with Max Links , HART Scheme , PADO , all BOP PLCs , SWAS system, CO analyser & Coal feeder controller to match with the external aspect , process improvement & Up gradation of Generator Protections Relays in unit 1 to 4 of 210 MW at khaperkheda TPS | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 33.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.7 | Up-gradation of Generator Protections Relays in Unit 1 to 4 of 210 MW Khaperkheda TPS. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 8.31 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/478 | - | 0.86 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Submitted to MERC, Yet to receive approval | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR on Refurbishment of Spare HPT Module Unit 1 & 2 at TM-I and Procurement of Complete Gear Box Assemblies of Coal Mills XRP 803 ½ HP & XRP 883 for Unit No. 1 to 4 (4x210 MW), Khaperkheda TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Refurbishment of spare HPT module Unit 1 & 2 at TM-I (4X210 MW), KHAPERKHEDA TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Procurement of Complete Gear Box Assemblies of Coal Mills XRP 883 for Unit-1 to 4 (210MW). | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | SUPPLY INSTALLATION TESTING & COMMISSIONING REVAMPING OF FIRE DETECTION & ALARM AND PROTECTION SYSTEM FROM FIRE AND PROVIDING RAPID EXTINGUISHING CLEAN AGENT (CA) SYSTEM AT UNIT -3,4 & 5 ATKPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Supply Installation Testing & Commissioning , Revamping of fire protection and providing rapid extinguishing clean agent (CA) system at unit # 3 ,4 210 MW TPS, KHAPERKHEDA | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Restoration of various Fire protection system at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Restoration of fire hydrant ring and fire water spray Header at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Restoration of deluge valve system at CHP-210MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | VARIOUS SCHEMES PROPOSED FOR IMPROVEMENT OF CHP-I (4 X 210 MW). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Design, Manufacturing, Supply, Erection, Commissioning & Testing of Coal Flow Management system for Coal Bunkers in CHP-I (4 X 210MW), Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Design, engineering, manufacturing, supply, installation and commissioning of Dedusting System for Crusher House and Bunker area in Unit 3 & 4 at CHP-I (4 X 210MW), Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Renovation including replacement of Power & Control cables with automation & upgradation of Stacker Reclaimer No. 1 in CHP-I (4 X 210MW), TPS Khaperkheda." | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Flue Gas Desulphrisation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | FGD installation of 210MW unit 1 & 2 at Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Upgradation of DDC/DCS system for UNIT 2 & 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Upgradation of DDC/DCS system for UNIT 2 & 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#1 to 4 Khaperkheda TPS & Upgradation of various governing Element for smooth operation for flexible operation of TG set at 40% technical minimum operation. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#1 to 4 Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.2 | Upgradation of various governing Element for smooth operation for flexible operation of TG set at 40% technical minimum operation. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Upgradation of Battery Charger , UPS system , GEHO PLC and VFD, ID VFD, supply of Efficiency Measuring Instruments and Supply, erection and commissioning of Sox, Nox , CO, Opacity, ETP and Oxygen Analyser for Unit 1 to 4 of 210 MW at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Supply of Efficiency Monitoring Instruments for performance optimization group (POG) at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.2 | Upgradation of 220 V, 24 V DC Float cum boost battery charger at Unit#1 to 4 Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.3 | Upgradation of 2X50 KVA UPS at Unit#1 to 4 Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.4 | Supply, Erection and Commissioning of Sox, Nox , CO, Opacity and ETP Analyser for Unit 1 to 4 of 210 MW at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.5 | Upgradation of GEHO PLC and VFD along with HCSD system Instrumentaion at Unit 3 & 4 Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.6 | Supply, Erection & Commissioning of Oxygen Analyzer for combustion optimization for Unit#1 to 5 Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.7 | Upgradation of VFD for ID FAN in Unit# 3 & 4, 210MW khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.8 | Scheme 8 Supply, erection & commissioning of PLC and SCADA System of Ash Evacuation and Disposal System for UNIT 3 and 4 Of 210 MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of LP Rotor for unit 1 and 2 , Supply and installation of air washer unit 1 and 2 and refurbishment of air washer unit for unit 3 and 4 and GEHO Pummp house control room. Supply and installation of diesel engine driven fire fighting pump with engine. Procurement of various control valves for unit No. 1 to 4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.1 | Supply and installation of Air washer unit in unit 1 and 2 , 6.6 KV breaker room, Turbine MCC room Battery room Boiler MCC room for cooling of all the Electrical Panels and AHP stage I Pump House control room air washer system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.2 | Refurbishment of Air washer unit of 3 and 4, 6.6 KV breaker room, Turbine MCC room Battery room Boiler MCC room for cooling of all the Electrical Panels and Refurbishment of GEHO pump House and AHP stage II Pump House control room air washer system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.3 | Procurement of Complete LPT rotor for unit 1 and 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.4 | Revamping of diesel engine driven fire fighting pump system with engine. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.5 | Procurement of various control valves for unit No. 1 to 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of IP Rotor and Inner casing for unit 1 and 2. Procurement of IP rotor and inner casing for unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.1 | Procurement of IP Rotor and Inner casing for unit 1 and 2. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.2 | Procurement of IP rotor and inner casing for unit 3 and 4 along with Turbovisory sensors and panel | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.3 | Supply and installation of srew compressor for supply of instrument air to unit No. 3 and 4 along with dryer for unit No. 3 & 4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of LP rotor for unit 3 and 4 and upgradation of BFP cartridge and BFP Booster pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.1 | Procurement of of LP rotor for unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.2 | Upgradation of BFP cartridge and BFP Booster pump, motorized scoop for hydraulic coupling and drive unit for BFP and modulating BFP RC valve for Unit 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Refurbishment of LP rotor of unit 1 and 2 and Refurbishment of HPT module of unit 1 and 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.1 | Refurbishment of LP rotor of unit 1 and 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.2 | Refurbishment of HPT module of unit 1 and 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Refurbishment of LP rotor for unit 3 and 4 and Refurbishment and re-blading of HPT module of unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.1 | Refurbishment of LP rotors for unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.2 | Refurbishment of HPT modules of unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | SITC OF COMPLETE SOLUTION AND COMPREHENSIVE PROTECTION AND MONITORING PACKAGE ALONG WITH RETROFIT OF ALLIED ACCESSORIES FOR VARIOUS GTs & STs INSTALLED AT 210 MW KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | SUPPLY,INSTALLATION, TESTING & COMMISSIONING OF COMPLETE SOLUTION AND COMPREHENSIVE PROTECTION AND MONITORING PACKAGE ALONG WITH RETROFIT OF ALLIED ACCESSORIES FOR VARIOUS GTs & STs INSTALLED AT 210 MW KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | PLANT PERFORMANCE IMPROVEMENT BY DESIGN, SUPPLY, INSTALLATION & COMMISSIONING OF STATE OF ART HT VACCUM CIRCUIT BREAERS AT UNIT 1 TO 4 OF 210MW KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.1 | DESIGN, SUPPLY, INSTALLATION, TESTING & COMMISSIONING OF HT VCB AT U # 1 & 2. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.2 | DESIGN, SUPPLY, INSTALLATION, TESTING & COMMISSIONING OF HT VCB AT U # 3 & 4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | DESIGN, SUPPLY, INSTALLATION, TESTING AND COMMISSIONING OF THE VARIOUS LIFTS IN PLACE OF THE EXISTING OLD LIFTS, LIGHTNING PROTECTION SYSTEM, EARTHING SYSTEM, AVIATION LIGHTING SYSTEM INSTALLED AT UNIT # 1 TO 4 OF 210 MW, KHAPERKHEDA TPS ON OEM BASIS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | DESIGN, SUPPLY, INSTALLATION, TESTING AND COMMISSIONING OF THE VARIOUS LIFTS IN PLACE OF THE EXISTING OLD LIFTS INSTALLED AT UNIT # 1 TO 4 OF 210 MW, KHAPERKHEDA TPS ON OEM BASIS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Design, Engineering, Supply, Erection, Testing & Commissioning of lightning protection system at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Design, Engineering, Supply, Erection, Testing & Commissioning of Earthing of electrical system & various buildings at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Design, Engineering, Supply, Erection, Testing & Commissioning of Aviation Lighting Syatem at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | SUPPLY OF SPARE GENERATOR ROTOR FOR U#3 &4, 210MW, TPS KHAPERKHEDA. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.1 | SUPPLY OF SPARE GENERATOR ROTOR FOR U#3 &4, 210MW, TPS KHAPERKHEDA. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | PROCUREMENT OF ENERGY EFFICIENT MOTORS FOR U # 1 TO 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.1 | PROCUREMENT OF ENERGY EFFICIENT MOTORS FOR U # 1 & 2 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.2 | PROCUREMENT OF ENERGY EFFICIENT MOTORS FOR U # 3 & 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.3 | Procurement of DC motors for U # 1 & 2 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.4 | Procurement of DC motors for U # 3 & 4 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | UPGRADATION OF EXISTING LT MCC PANEL WITH STATE OF ART LT MCC PANEL AT U # 1 TO 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | UPGRADATION OF EXISTING LT MCC PANEL WITH STATE OF ART LT MCC PANEL AT U # 1 & 2 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.2 | UPGRADATION OF EXISTING LT MCC PANEL WITH STATE OF ART LT MCC PANEL AT U # 3 & 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.3 | UPGRADATION OF HT BREAKER PANEL AT WAREGAON ASH BUND OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | UPGRADATION OF HT BREAKER PANEL AT OLD PROJECT OFFICE OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.5 | Retrofitting of Existing L & T make LT MCC ACB by state or art ACB at U # 1 to 4 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.6 | Retrofitting of Existing ABB make LT MCC ACB by state or art ACB at U # 1 to 4 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | ERECTION & COMMISIONING OF DRY TYPE CAST RESIN TRANSFORMERS FOR U # 1 TO 4 OF KHAPERKHEDA TPS & Design, Engineering, Supply, Erection, Testing & Commissioning of various Battery sets at Unit # 3 & 4 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | PROCUREMENT OF DRY TYPE CAST RESIN TRANSFORMERS FOR U # 1 & 2 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.2 | PROCUREMENT OF DRY TYPE CAST RESIN TRANSFORMERS FOR U # 3 & 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.3 | PROCUREMENT OF VFD TRANSFORMERS FOR ID FAN MOTOR U#3&4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.4 | Design, Engineering, Supply, Erection, Testing & Commissioning of various Battery sets at Unit # 3 & 4 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20 | Study, Supply & Refurbishment of HCSD systems, ESP operation, ambience & various pump, & PLC schemes for the improvement of AHP-I at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.1 | STUDY. DESIGN & REFURBISHMENT WORKS OF HIGH CONCENTRATION SLURRY DISPOSAL SYSTEM (HCSD SYSTEM) UNITS #3&4 AT AHP-1, TPS KHAPERKHEDA. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.2 | STUDY, DESIGN & REFURBISHMENT WORKS OF ARTs AND ASSOCIATED MOUNTINGS & ACCESSORIES OF HCSD SYSTEM FOR AHP-I, TPS KHAPERKHEDA.” | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.3 | ‘SUPPLY & REFURBISHMENT WORKS OF HCSD ASH SLURRY MIXER SYSTEM AT UNIT #3 &4 OF AHP-I, TPS KHAPERKHEDA’. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.4 | ‘STUDY, SUPPLY, RESTORATIONS & REPLACEMENT OF ALL INTERNAL SPARES OF D6 FIELD & RENOVATION OF D1 FIELD OF U3 DURING AOH FOR AHP-I, TPS KHAPERKHEDA’ | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.5 | PROCUREMENT OF VARIOUS PUMPS IN RECYCLE WATER SYSTEM IN ASH HANDLING PLANT 4X210 MW AT KHAPARKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Reliability improvement and complete replacement of ABC series with drive unit of ash slurry pipeline of 7 KM of 4*210MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Procurement and restoration of complete pipeline replacement of ABC series | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.2 | Procurement and restoration of complete drive unit replacement of ABC series | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | Procurement and restoration of complete Bottom ash hopper replacement including entire structure, Clinker grinder alongwith motor, Feed Gate, Power Cylinder and Pipelines discharge of U3&4 of 4*210MW Khaparkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.1 | Procurement and restoration of complete BAH replacement including entire structure and clinker griender | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.2 | Procurement and restoration of complete drive unit of clinker grinder for Unit 1 to 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.3 | Procurement and restoration of discharge pipeline of vertical sump pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Procurement and restoration of Pipeline garlanding at Waregaon ash Bund of 4*210 MW Khapakheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.1 | Pipeline garlanding at Waregaon ash Bund of 4*210 MW Khapakheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Upgradation, modification and erection of complete wet fly ash evacuation into dry fly ash evacuation systen for ESP 1 and 2 of 4*210 MW Khapakheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.1 | Upgradation, modification and erection of complete wet fly ash evacuation into dry fly ash evacuation systen for ESP 1 and 2, 4*210 MW Khapakheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | Reliability improvement and complete replacement of JKL series with drive unit of ash slurry pipeline of 7 KM of 4*210MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.1 | Procurement and restoration of complete pipeline replacement of JKL series | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.2 | Procurement and restoration of complete drive unit replacement of JKL series | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | Study, Supply and Refurbishment of HCSD System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.1 | Procurement of complete Suction and discharge valve of Geho pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.2 | Procurement of Subassemblies of Geho pump. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.3 | Upgradation and compressors of dry ash evacutaion system of U#3&4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.4 | Procuremenet of complete drive unit and VFD of GEHO pump. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | RENOVATION OF ESP FIELD INTERNALS FOR UNIT 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.1 | RENOVATION OF ESP FIELD INTERNALS FOR UNIT 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28 | R & M OF APH OF UNIT # 1& 2 (2 x 210MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28.1 | R & M OF APH OF UNIT # 1& 2 (2 x 210MW) OF KHAPERKHEDA TPS FROM MODEL: 27 VI 1850 TO 27 VI 2000 mm. DESIGN, ENGINEERING, SUPPLY, ERECTION & COMMISSIONING OF DOUBLE SEALING | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29 | DPR FOR ECONOMISER COILS AND APH GEAR BOX | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29.1 | PROCUREMENT AND REPLACEMENT OF COMPLETE SET OF ECONOMISER UPPER BANK & LOWER BANK COILS FOR KHAPERKHEDA TPS UNIT NO.3&4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29.2 | Procurement of APH gear box in unit no. 1 & 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29.3 | Procurement of APH speed reducer gear box in unit no. 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30 | DPR FOR LTSH COILS , APH BASKETS & RH OUTLET STUB BENDS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.1 | Procurement of Air Pre-heater Baskets for unit no. 2 to 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.2 | Procurement of LTSH coils for unit no. 1 & 2 and Procurement of Reheater outlet header stub bends for unit no. 1 to 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.3 | Procurement of LTSH coils for unit no. 3 & 4 and Procurement of Reheater outlet header stub bends for unit no. 3 to 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31 | DPR FOR SUPPLY & REPLACMENT OF THERMAL INSULATION OF BOILER AND DUCT AT UNIT 1 TO 4 KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.1 | SUPPLY & REPLACMENT OF THERMAL INSULATION OF BOILER AND DUCT AT UNIT 1 TO 2KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.2 | SUPPLY & REPLACMENT OF THERMAL INSULATION OF BOILER AND DUCT AT UNIT 3 TO 4 KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32 | DPR FOR COAL CYCLE IMPROVEMENT IN UNIT NO.1 TO 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.1 | Procurement of Complete Journal Assembly for 803 ½ HP Coal Mills of Unit No. 1 To 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.2 | Procurement of Complete Journal Assembly for XRP 883 Coal Mills of Unit No. 3 To 4, | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.3 | Procurement of assembly of worm shaft & worm wheel with hub for unit no. 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.4 | PROCUREMENT OF COMPLETE GEAR BOX ASSEMBLIES OF COAL MILLS XRP 803 ½ HP FOR UNIT # 1 TO 2 AT KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.5 | PROCUREMENT OF COMPLETE GEAR BOX ASSEMBLIES OF COAL MILLS XRP 883 FOR UNIT # 3 TO 4 AT KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33 | DPR FOR PERFORMANCE IMPROVEMENT OF BOILER PA FAN, ID FAN AND FD FAN IN UNIT NO. 1 TO 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.1 | Procurement of PA fan Casings along with Dampers in Unit- 1 & 2, at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.2 | PROCUREMENT OF COMPLETE ROTOR ASSEMBLY ALONG WITH MOTOR FOR NDZV 31 SIDOR IN UNIT NO. 1 & 2 KHAPERKHEDA TPS (ID FAN) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.3 | PROCUREMENT OF FD FAN (BHEL AP 1-20 / 11) ASSEMBLY ALONG WITH DRIVE UNIT(MOTOR) FOR UNIT 1 & 2 AT KHAPERKHEDA TPS UNDER OEM NATURE ITEMS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.4 | PROCUREMENT OF FD FAN (BHEL AP 1-20 / 11) ASSEMBLY ALONG WITH DRIVE UNIT(MOTOR) FOR UNIT 3& 4 AT KHAPERKHEDA TPS UNDER OEM NATURE ITEMS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.5 | NDZV 33 SIDOR ID Fan Impeller Assembly for Unit 3 & 4 at TPS, Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.6 | Design, Engineering, Manufacturing, Supply & Commissioning including civil works for installation of 70 LPM lubricant ystems for PA Fans in unit no. 1&2. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.7 | Supply and installation of ID and PA foundation deck spring for unit no. 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34 | VARIOUS SCHEMES FOR BOILER PERFORMANCE IMPROVEMENT | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.1 | SUPPLY OF COAL MILL SEPERATOR & SCRAPPER BODIES FOR XRP-803 1/2 HP COAL MILLS IN UNIT 1 & 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.2 | MODIFICATION OF EXISTING COAL BUNKER AND COMMISSIONING OF BUNKER CHUTE ASSEMBLY WITH VIBRATING MOTOR TO AVOID BUNKER MOUTH COAL CHOKE UP FOR UNIT 1 & 2AT KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.3 | MODIFICATION OF EXISTING COAL BUNKER AND COMMISSIONING OF BUNKER CHUTE ASSEMBLY WITH VIBRATING MOTOR TO AVOID BUNKER MOUTH COAL CHOKE UP FOR UNIT 3 & 4 AT KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.4 | DESIGN, DEVELOPMENT, COMMISIONING OF SEAL AIR FAN ASSEMBLIES IN UNIT 1 & 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.5 | Procurement of sub body assembly of control valve in unit no. 1 & 2 actuating main gear unit part electrical actuator in unit no. 1 to 4 Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | Construction of A, B, C, D & E type stilt + 6 floor buildings at TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Construction of A, B, C, D & E type stilt + 6 floor buildings at TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36 | Enhancement & Renovation of existing building, Construction of Market building, Construction of club building community hall, Construction of school building, & Enhancement of existing domestic plant providing V wire 3 MLD at Colony TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.1 | Enhancement / Renovation & strengthening of existing building & allied works in colony TPS Khaperkhda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.2 | Construction of Market building including approach road, drainage arrangement & electrification at colony TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.3 | Construction of club building / community hall | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.4 | Construction of school building | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.5 | Enhancement of existing domestic plant providing V wire 3 MLD | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37 | Enhancement / Renovation of Saudamini Administrative Building, Construction of VIP Guest House, Construction of roads at Prakashnagar Colony and Providing various civil works related to coal transport railway lines of khaperkheda TPSTPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.1 | Enhancement / Renovation of Saudamini building | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.2 | Construction of VIP guest house TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.3 | Construction of Roads | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.4 | Construction of office building & store for electrical maintenance & Civil at KPKD | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.5 | Providing Special repair & retrofitting work of river bridge no.09 on Khaperkheda - Kalumna railway siding of TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.6 | Construction & repairing of drains & culverts along coal Transporting Railway lines & approach road of TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.7 | Repairing, providing & applying Epoxy Painting and Structural Steel Works to steel structural bridges on kpkd to Kaluma and kpkd to Saoner railway lines as per recommendation of structural stability report at TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.8 | Construction of compound wall KPKD Colony | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38 | Work of Strengthening and modification of Main Plant, construction of roads, strengthening of IDCT 1 to 4 in plant area, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.1 | Work of attending additional works based on structural report at Induced Draft Cooling Towers(IDCT) unit 1,2,3 & 4 at 4 x 210MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.2 | Work of constructon of roadside drains from VIP gate no.3 to IDCT No.1 at 4 x 210MW TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.3 | Construction of bituminous macadam road from Administrative Building to GCR Road near Service Building of 4X210MW TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.4 | Work for Construction of cement concrete road for equipment movement for salt lagoon (WTP-I), FGD(System), H2(cylinders) plant etc. inside plant premises in 4x 210MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.5 | Construction of cement concrete road outside BTG area of Power Plant 4 x 210MW TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.6 | Construction of cement concrete road for material transportation from D-Point CHP to reject coal Dumping yard in 4x 210MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.7 | Work of Strengthening and modification of Main Plant, Major Stores, Auxiliary in plant area, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.8 | Construction of diversion road along with RCC bridge from rejct coal yard CHP-I & CHP-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.9 | Upgradation of existing ETP plant consist civil works, electrification and pumps. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
39 | Work of 5th Raising of Waregaon Ash Bund, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
39.1 | Work of 5th Raising of Waregaon Ash Bund, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
40 | Work of CTR(Complete Track Removal),TTR(TRAIN TRAVLER REGULATOR) and Yard Remoulding incl. misc. works at Mahagenco Khaperkheda Plant. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
40.1 | Work of CTR(Complete Track Removal),TTR(TRAIN TRAVLER REGULATOR) and Yard Remoulding incl. misc. works at Mahagenco Khaperkheda Plant. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41 | Various WTP 210MW improvement schemes i.e. Up-gradation of SWAS SYSTEM UNIT- 1 to 4 at WTP-I 210 MW along with coal sampling lab upgradation, Comissioning of CW Chemical Dosing system etc | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.1 | Upgradation of Existing ETP system viz. Plate Settler, Settling tank, Sludge Drying bed, Chemical dosing system etc.)as per MPCB consent condition | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.2 | Upgradation of SWAS Lab 3& 4 at WTP-210 MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.3 | Revamping of Chlorination Plant Stream (A+ B) & Installation, Comissioning of CW Chemical Dosing system (Viz. Scale inhibitor, Scale Dispersant, Biodispersant, Corossion Inhibitor & H2SO4 dosing) and Online CW Chemical parameter monitoring system at KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.4 | Upgradation of SWAS Lab 1& 2 at WTP-210 MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.5 | Upgradation of Water &Coal testing Lab at WTP-210 MW &Procurement of Coal Lab Instruments and upgradation of coal sampling Room & Instruments related to Coal sample Preparation. at WTP-210 MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42 | Work of capacity restoration of unloading stream from Beetle Charger No. 1 to Stacker/Reclaimer No. 1 for perfromance improvement of CHP-I (4 x 210 MW) & Capacity restoration of unloading stream from Beetle Charger No. 1 to Stacker/Reclaimer No. 1 for perfromance improvement of CHP-I (4 x 210 MW). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.1 | Revamping/ refurbishment, capacity restoration and upgradation for beetle charger No. 1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.2 | Revamping/ refurbishment, capacity restoration and upgradation for Wagon Tippler No. 1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.3 | Revamping/ refurbishment, capacity restoration and upgradation for Apron Feeder No. 1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.4 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 2C, 3A, 4A, 8A, 9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.5 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for impact crusher and wobbler feeder No. 1 & 3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.6 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Stacker/Reclaimer No. 1. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.7 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv. 3C to 3A, Conv. 3A to 4A, Conv. 4A to 8A and Conv. 9 by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.8 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of beetle Charger, wagon tippler, apron feeder, covneyors (Conv. 2C, 3A, 4A, 8A, 9), crushers/ wobbler feeder No. 1 & 3 and Stacker/Reclaimer No. 1 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
43 | DPR fo Capacity restoration of bunkering stream from Conv. 5A to 7A/B/C/D including shuttle conveyors in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
43.1 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 5A, 6B, 7A, 7B, 7C, 7D and Shuttle Conv. 1 to 4 in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
43.2 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv.Conv. 4D to 5A/B , 5A to 6B, Conv. 6B to 7A & 7B, Conv. 7B to 7D upto shuttle conveyor, Conv. 7A to 7C upto shuttle conveyor by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
43.3 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of covneyors (Conv. 5A, 6B, 7A/B/C/D & Shuttle Conv. 1 to 4 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44 | Work of capacity restoration of unloading stream from Beetle Charger No. 2 to Stacker/Reclaimer No. 2 for perfromance improvement of CHP-I (4 x 210 MW). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.1 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for beetle charger No. 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.2 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Wagon Tippler No. 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.3 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Apron Feeder No. 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.4 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 2D, 3B, 4B, 8B, 10 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.5 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for impact crusher and wobbler feeder No. 2 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.6 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Stacker/Reclaimer No. 2. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.7 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv. 2D to 3B, Conv. 3B to 4B, Conv. 4B to 8B and Conv. 10 by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.8 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of beetle Charger, wagon tippler, apron feeder, covneyors (Conv. 2D, 3B, 4B, 8B, 10), crushers/ wobbler feeder No. 2 & 4 and Stacker/Reclaimer No. 2 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45 | Work of capacity restoration of bunkering stream from Conv. 1A/B, 2A/B, 5B to 7E/F/G/H including shuttle conveyors in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.1 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 1A/B, 2A/B, 5B, 6A, 7E, 7F, 7G, 7H and Shuttle Conv. 5 to 8 in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.2 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv. 1A/b to 2A/B,Conv. 4C to 5A/B, Conv. 5B to 6A, Conv. 6A to 7E & 7F, Conv. 7E to 7G upto shuttle conveyor, Conv. 7F to 7H upto shuttle conveyor by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.3 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of conveyor system from Conv. 1A/B, 2A/B, 5B, 6A, 7E, 7F, 7G, 7H and Shuttle Conv. 5 to 8 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.4 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Paddel Feeder No. 1 to 4 and truck hopper in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46 | Renovation and upgradation of various electrical system for CHP-I (4 x 210 MW) improvement & Renovation and upgradation of various electrical system for CHP-I (4 x 210 MW) improvement. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.1 | Design, development and upgradation with circuit breaker VFD of various LT MCC of CHP-I. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.2 | Design, Supply, Installation, Commissioning and Testing of Energy Chain System for Paddle Feeder, Shuttle Conveyor and Stacker/Reclaimers in CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.3 | Upgradation of relay logic system with PLC & SCADA in CHP-I control room and Wagon Tipplers in CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.4 | Complete upgradation of conveyor lighting system with energey efficient LED lights for CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.5 | Providing, installation, testing commissioning, maintenance and operation of explosion proof & weather proof surveillance system at CHP-I (4 X 210 MW), TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.6 | Complete revamping/refurbishment, upgradation and modification of various EOT cranes & hoist installed at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47 | Procurement of various capacity SAN make locomotives and BEML make loader & bulldozer for CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.1 | Procurement of various capacity SAN make locomotives and BEML make loader & bulldozer for CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48 | CHP Improvement Schemesfor 4x 210 MW units | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.1 | Design, manufacture, supply and installation of suspended magnet for bunkering belts at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.2 | Design, manufacture, supply and installation of travel drive system for shuttle conveyors and conveyors at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.3 | Renovation including replacement of Power & Control cables with automation & upgradation of Stacker Reclaimer No. 2 in CHP-I (4 X 210MW), TPS Khaperkheda." | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.4 | Complete reconditionding & upgradation of LT MCC installed at Unit No. 3 & 4 bunker auxiliareis in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.5 | Complete reconditionding & upgradation of outdoor lighting system in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.6 | Complete reconditionding & upgradation of HT breaker, control circuits & protection relays in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.7 | Complete revamping/refurbishment, upgradation and modification of various monorail hoists & winch machine installed at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.8 | Procurement of hydra 14 Ton above capacity and heavy vehicles for CHP- I & II. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
49 | Installation of Real Time Coal Analyzer at all TPS of Mahagenco | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
49.1 | Installation of Real time Coal Analyzer at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50 | Railway expenses for refurbishment of OHE lines at CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50.1 | Railway expenses for refurbishment of OHE lines at CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | PROCUREMENT COMPLETE Gear BOX ASSEMBLIES FOR 803 1/2 HP & XRP 883 COAL MILLS OF UNIT NO. 1& 2 AT KHAPERKHEDA TPS. | N.A. | - | 0 | 4.5548 | 4.5548 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply Erection and commissioning of Oil Cooled Suspended magnets at Conv 6A & 6B at Khaperkheda TPS. | N.A. | - | 0 | 1.1484 | 1.1484 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurment of new 02 Ambulance Van & 2 Truck for KPKD TPS(Asset Nos. 170100512, 170100513, 170100514, 170100515) | N.A. | - | 0 | 0.41055 | 0.41055 | 0 | 0 | 0 |  |  | 0 | 0
4 | GEHO PUMP (Valve housing assembly) | N.A. | - | 0 | 0 | 0 | 0 | 8.7933 | 8.7933 |  |  | 8.7933 | 0
5 | RESTORATION OF AHP OUTLET TO ESP INLET DUCTS U#1&2(Unit #2 Part only) | N.A. | - | 0 | 0 | 0 | 0 | 7.0042 | 7.0042 |  |  | 7.0042 | 0
6 | ABC powder type and foam type composite Fire Extinguisher | N.A. | - | 0 | 0 | 0 | 0 | 0.714 | 0.714 |  |  | 0.714 | 0
7 | FFEQUIP HYDRAULIC JACK (BM-I) | N.A. | - | 0 | 0 | 0 | 0 | 0.57696 | 0.57696 |  |  | 0.57696 | 0
8 | MOBILE COAL SAMPLING EQUIP-AUGER (FMC) CHP-I | N.A. | - | 0 | 0 | 0 | 0 | 1.5824 | 1.5824 |  |  | 1.5824 | 0
9 | Replacement of ash slurry disposal pump to improve performance & capacity enhancement of ash slurry disposal system at AHP-1 Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of Pillow Block Dodge Bearing Assemblies (Expansion & Non-Expansion) for PA fans in Unit- n1 to 4, at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Replacement of Economizer outlet to APH outlet common duct in unit no. 3 (210MW), Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | PROCUREMENT OF OIL COOLED SUSPENSION MAGNET FOR 210MW AND MODIFICATION & REPLACEMENT OF VIBRATING FEEDER WITH VIBRATING TRANSFER CHUTE FOR 210MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | DESIGN,ENGINEERING,MODIFICATION ,ERECTION AND COMMISSIONING OF DRIVE UNIT ARRANGEMENT FOR CONVEYOR 10 AT CHP1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | ENERGY EFFICIENT PLANT LIGHTING AND COLONY LIGHTING MODIFICATIONS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | Supply installation testing and commisioning of various battery sets at unit No 1 & 2 of Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | Revamping and modification of existing alarm and protection system from fire and provide rapid extinguishing Clean Agent (CA) system at Unit #1 & 2 (210 MW) units, KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | Supply of electronic modules for Procontrol DCS system in unit 1 to 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | Revamping & UPGRADATION of SWAS system in unit 3 & 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | Upgradation of process instrumentation in unit 1 to 2 of 210 MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20 | Replacement of flue gas duct from air heater outlet to esp inlet for U 1 & 2 (S+W) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | PROCUREMENT OF COMPLETE ROTOR ASSEMBLY FOR NDZV 31 SIDOR IN UNIT NO. 1 & 2 KHAPERKHEDA TPS (ID FAN). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | UPGRADATION OF BELT CONVEYOR CAPACITY OF 2C &2D AND 8A & 8B AT CHP1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | WORK OF DESIGN,ENGINEERING,ERECTION AND UPGRADATION OF DRIVE UNITS OF BELT CONVEYOR 3A & 3BAT CHP1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Procurement of 1500 KW ID Fan Synchronous Motor at Unit 3 & 4 Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | Procurement of Steam and Water Analysis System(SWAS) for Unit 1&2 (210MW) KPKD TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | Supply and replacement of complete PVC fills of cell of cooling tower of unit 1-4 (210 MW) at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | PROCUREMENT OF FD FAN (BHEL AP 1-20/11) ASSEMBLY FOR UNIT 1 TO 4 ATKHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28 | CHP performance improvement scheme for capacity restoration of drive units installed at CHP-1 (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29 | Work of Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of belt conveyor 8A & 8B and belt conveyor 2C & 2D at CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30 | WORK OF DESING,SUPPLY ,ERECTION,COMMISSIONG AND UPGRADATION OF COMPLETE ELECTRICAL SYSTEM FOR DRIVE UNITS OF BELT CONVEYOR 3A & 3B AND BELT CONVEYOR 4A,4B,4C & 4D AT CHP1 Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31 | Supply, Installation, & Commissioning of Instruments at coal Testing Lab, WTP-I, TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32 | Supply, Installation & Commissioning and Refurbishment of asbestos based H2 Generator and compressor to convert it to non-asbestos based H2 Generator for Unit 1 to 5, Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33 | construction of bituminous macadam roads at Prakashnagar Colony TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34 | Work of attending additional works based on structural report at Induced Draft Cooling Towers (IDCT) unit 1,2,3 & 4 at 4 x 210MW, TPS, Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | VIBRATION ANALYSER | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36 | Upgradation of GEHO pump instrumentation for AHP Unit No. 3 & 4 (210 MW) at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37 | Refurbishment of HPT module for Unit 1 & 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38 | General Asset Furniture | N.A. | - | 0 | 0.85309 | 0.85309 | 0 | 0.0086842 | 0.0086842 |  |  | 0.0086842 | 0
39 | General Asset AC, Fans, Air coolers, water filter etc. | N.A. | - | 0 | 0.41552 | 0.41552 | 0 | 0.12056 | 0 |  |  | 0 | 0.12056
40 | General Asset Computer, scanners, etc. | N.A. | - | 0 | 2.2226 | 1.9358 | 0.2868 | 0.33717 | 0.0103 |  |  | 0.0103 | 0.61367
41 | Land aquired for rly siding | N.A. | - | 0 | 0.4072 | 0.4072 | 0 | 0 | 0 |  |  | 0 | 0
42 | RCC ROAD FROM ASH SILO TO 'D' POINT FOR BULKER MO | N.A. | - | 0 | 0.95225 | 0.95225 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 639.6889 | 277.8834 | 361.8055 | 354.1796 | 112.0788 | 0 | 0 | 112.0788 | 603.9062
FY 2024-25
a) DPR Schemes
(i) Submitted to MERC
1 | Combustion optimization system | [6 empty] | 0 | 0
1.1 | Dynamic coal flow measurement and control (balancing) system (one) | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 | 8.17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | CO analyser (8 units) | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 | 1.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Oxygen analyser (32 units) | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 | 0.783 | 0.75683 | 0.75683 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Spare HPT module for Khaparkheda Unit 1 & 2 | MERC/CAP/DPR/10/2010-11/1466 | 2010-10-26 | 26.459 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | HPT module 1 No (unit # 1) | MERC/CAP/DPR/10/2010-11/1466 | 2010-10-26 | 23.0379 | 23.9074 | 23.9074 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAP/DPR/10/2010-11/1466 | 2010-10-26 | 3.4211 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Economiser Upper Bank & Lower Bank coils for Khaperkheda Unit no. 3 and Unit no. 4 | MERC/CAP/DPR/10/2010-11/1695 | 2010-12-15 | 26.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Economiser Upper Bank & Lower Bank coils for Khaperkheda Unit no. 3 and Unit no. 4 | MERC/CAP/DPR/10/2010-11/1695 | 2010-12-15 | 26.35 | 11.77 | 11.77 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Economiser & LTSH Upper Bank & Lower Bank coils for Khaperkheda Unit no. 1 and Unit no. 2 | MERC/CAPEX/20112012/01155 | 2011-07-29 | 34.7916 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Economiser & LTSH Coil for Unit 1 | MERC/CAPEX/20112012/01155 | 2011-07-29 | 15.6924 | 15.6924 | 15.6924 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Economiser & LTSH Coil for Unit 2 | MERC/CAPEX/20112012/01155 | 2011-07-29 | 16.1528 | 16.1528 | 16.1528 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20112012/01155 | 2011-07-29 | 2.9464 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Procurement & Replacement of Re-heater Rear Pendant Assembly Coils for 2*210MW Khaperkheda Unit no. 1 and Unit no. 2 | MERC/CAPEX/20122013/00603 | 2012-06-18 | 10.3738 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Re-heater coils for unit no. 1 | MERC/CAPEX/20122013/00603 | 2012-06-18 | 5.1267 | 5.1267 | 5.1267 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Re-heater coils for unit no. 2 | MERC/CAPEX/20122013/00603 | 2012-06-18 | 5.1267 | 5.55 | 5.55 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/00603 | 2012-06-18 | 0.1204 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Procurement of HPT module suitable for khaperkheda TPS Unit 3 & 4 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 36.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Procurement of HPT module suitable for khaperkheda TPS Unit 3 & 4 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 36.2 | 32.4016 | 32.4016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7 | Procurement Spare GTR, Locomotive & Compactors | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 18.4521 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | 250 MVA Spare GTR | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 10.3496 | 11.2511 | 11.2511 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.2 | Procurement of Locomotive 2no’s. | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 5.9927 | 5.9927 | 5.9927 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.3 | Procurement of Compactors 2 no’s. | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 0.42979 | 0.4298 | 0.4298 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 1.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Procurement & Replacement of complete set of LTSH coils for Khaperkheda TPS Unit 3&4 | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 17.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement and replacement of LTSH coils for Khaperkheda TPS at U3 | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 8.58 | 3.4291 | 3.4291 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Procurement and replacement of LTSH coils for Khaperkheda TPS at U4 | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 8.58 | 3.1809 | 3.1809 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 0.65 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Development of Ash Bund (Waregaon) at K'kheda TPS | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 38.7459 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Construction of 3rd upstream raising of existing ash bund from TBL 299.50 Mtr to 302.50 Mtr at Waregaon, Khaperkheda TPS. | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 33.8585 | 32.5375 | 32.5375 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.2 | Construction of masonary dam (Gabion structure) at Waregaon TPS, Khaperkheda. | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 1.0561 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.3 | Construction of approach to drain wells and raising height of drain well no. 1,2 & 3 ash bund at Waregaon, Khaperkheda TPS | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 0.48488 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 3.3464 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Various schemes related to CHP Improvement & Performance Optimization and scheme of conversion of existing Composite OHE to Conventional OHE | MERC/CAPEX/20152016/00422 | 2016-08-03 | 10.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Air Cooled Suspension Magnet for Con. 3 & 6 of CHP 210 MW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 2.18 | 2.2613 | 2.2613 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | Procurement of Impact crusher motor | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.84 | 0.52579 | 0.52579 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.3 | Procurement of 360V, 200 AH battery set and 360V 325 AH battery set for U# 1to 4 | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.1 | 1.4576 | 1.4576 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.4 | Procurement of POG Instruments for Unit 1 to 4 | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.77 | 0.35015 | 0.35015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.5 | Up gradation of safe scan flame scanner system by BHEL scan system in unit no. 1, 3 & 4 | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.6 | Up gradation of old AVR system to DAVR | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.7 | Conversion of existing Composite OHE to Conventional OHE | MERC/CAPEX/20152016/00422 | 2016-08-03 | 2.72 | 2.72 | 2.72 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.47 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | ESP up-gradation for Unit-1 at Khaperkheda TPS | MERC/CAPEX/20152016/01261 | 2016-01-11 | 32.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | ESP up-gradation for Unit-1 at Khaperkheda TPS | MERC/CAPEX/20152016/01261 | 2016-01-11 | 32.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Procurement, installation and commissioning of Gravimetric Belt / Rotary Type Feeder, VFD for CEP, Up-gradation of BTS system & Environmental schemes at Khaperkheda TPS | MERC/CAPEX/20162017/01552 | 2017-02-14 | 20.218 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Procurement, installation and commissioning of Gravimetric belt/rotary Feeder at U-1 & 2 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 5.72 | 4.7418 | 4.7418 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Installation of VFD to CEP at U-1 to 4 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 8.64 | 7.9943 | 4.7533 | 3.241 | 0.76326 | 2.2949 |  |  | 2.2949 | 1.7093 | 2.2949 | 0
13.3 | Installation of BTS system at U-4 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 0.98796 | 0.98796 | 0.98796 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.4 | Replacement of SOx/NOx analyzer at U-1 to 4 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 2.42 | 2.3035 | 2.3035 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.5 | Procurement of TGA,CHNS analyzer and Bomb calorimeter at U-5 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 1.71 | 0.2897 | 0.2897 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01552 | 2017-02-14 | 0.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Up gradation of HMI System at Unit No 3 & 4 at Khaperkheda TPS | MERC/CAPEX/20172018/03946 | 2017-07-19 | 13.39 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | HMI Up-gradation at U# 3 & 4 | MERC/CAPEX/20172018/03946 | 2017-07-19 | 12.78 | 12.5611 | 12.5611 | 0 | 0 | 0.62 |  |  | 0.62 | -0.62 | 0.2189 | 0.4011
0 | IDC | MERC/CAPEX/20172018/03946 | 2017-07-19 | 0.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21 | Procurement of APH Basket for unit # 1 to 5 and Up-gradation of HT Motor Protection Relay in Unit # 1 to 4 at Khaperkheda TPS | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 9.77 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.1 | Procurement of assembly of baskets for air preheater of type bisector APH 27 VI: 1850, 12 sector in unit no. 1 & 2 and bisector APH 27 VI: 2000; 24 sector in unit no. 3 & 4 (210MW x 4) at TPS, Khaperkheda | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 5.71 | 8.097 | 8.0941 | 0.002845 | 0 | 0 |  |  | 0 | 0.002845 | 0 | 0
21.3 | Up-gradation of H.T. Motor protection relays in Unit 1 to 4 (210MW), Khaperkheda TPS | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 3.96 | 3.1137 | 3.1137 | 0 | 0.14 | 0.14 |  |  | 0.14 | 0 | 0.14 | 0
0 | IDC | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 0.1 | 0 | 0.18424 | -0.18424 | 0 | 0 |  |  | 0 | -0.18424 | 0 | 0
22 | Procurement of LPT rotor suitable for Unit # 3 & 4 of 210 MW at Khaperkheda TPS | MERC/CAPEX/2018-2019/132 | 2019-05-09 | 27.191 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.1 | Procurement of LPT rotor suitable for Unit # 3 & 4 of 210 MW at Khaperkheda TPS | MERC/CAPEX/2018-2019/132 | 2019-05-09 | 26.491 | 10.7515 | 10.7515 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2018-2019/132 | 2019-05-09 | 0.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23 | Supply, Erection & commissioning of HT Vacuum circuit Breakers & SF6 contactors at AHP (U#1-4) & CHP (U#1 to 5) and 160 KW VFD Panel with Motor for fire-fighting pumps at U#1 to 4 at Khaperkheda TPS | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 10.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.1 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at AHP (Unit#1 to 4, 210MW), Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 4.17 | 3.4843 | 4.8883 | -1.404 | 0 | 0 |  |  | 0 | -1.404 | 0 | 0
23.2 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at CHP (Unit#1 to 4, 210MW) and CHP (Unit#5, 500MW) Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 3.81 | 4.031 | 2.7332 | 1.2978 | 0 | 0 |  |  | 0 | 1.2978 | 0 | 0
23.3 | Supply, Erection & commissioning of 150 KW VFD Panel with motor for fire-fighting pumps at 210 MW Khaperkheda TPS. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 2.34 | 2.0957 | 2.0957 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 0.58 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24 | Augmentation of Waregaon Ash Water Recovery System at TPS Khaperkheda | MERC/CAPEX/2019-20/732 | 2019-09-16 | 17.1984 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.1 | Augmentation of Waregaon Ash Water Recovery System at TPS Khaperkheda | MERC/CAPEX/2019-20/732 | 2019-09-16 | 15.7884 | 13.9315 | 13.9315 | 0 | 1.2672 | 1.2672 |  |  | 1.2672 | 0 | 1.2672 | 0
0 | IDC | MERC/CAPEX/2019-20/732 | 2019-09-16 | 1.41 | 0.58812 | 0.58812 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25 | Procurement of VFD with HMI & Controller & Replacing with existing Eddy-current drives of Coal feeders at U# 3 & 4 and Procurement of Various Critical Components of GEHO Pump (Model-TZPM 800) for AHP-1 at Khaperkheda TPS | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 10.6535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25.1 | Up-gradation of Existing BHEL make 36” Gravimetric Coal Feeders control panel with HMI and croprocessor based Controller with VFD, Motor & Weigh Module at Unit 3 & 4, (210MW) | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 7.4655 | 0 | 0 | 0 | 3.85 | 3.85 |  |  | 3.85 | 0 | 3.85 | 0
25.2 | Procurement of various Critical Components of GEHO Pump (Model-TZPM 800) for AHP-1 (210MW) | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 2.698 | 2.6466 | 2.6466 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 0.49 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26 | Procurement, Replacement of Eco Coils U#1&2 210 MW, & Procurement & replacement of foundation Deck Spring assembly for coal mills U#3,4 at Khaperkheda TPS | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 15.4086 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26.1 | Procurement, Replacement of Eco Coils U#1&2 | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 7.4996 | 6.6503 | 6.6503 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26.2 | Procurement & replacement of foundation Deck Spring assembly for coal mills U#3,4 | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 6.679 | 3.006 | 0 | 3.006 | 4.0896 | 3.55 |  |  | 3.55 | 3.5455 | 3.55 | 0
0 | IDC | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 1.23 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28 | ESP Upgradation of 5 Nos. of 210/500MW Units at Khaperkheda, Koradi & Chandrapur TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 90.3535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.1 | ESP Upgradation at Unit #1, Khaperkheda TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 42.7114 | 41.685 | 0 | 41.685 | 17.865 | 0 |  |  | 0 | 59.55 | 0 | 0
28.2 | ESP Upgradation at Unit #2, Khaperkheda TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 42.7114 | 41.685 | 0 | 41.685 | 17.865 | 0 |  |  | 0 | 59.55 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 4.9307 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29 | Flue Gas Desulphurisation System for Khaperkheda Unit # 1-4 | MERC/CAPEX/2021-2022/MSPGCL/097 | 2022-03-14 | 113.4565 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.1 | FGD System for Khaperkheda Unit # 1-4 | MERC/CAPEX/2021-2022/MSPGCL/097 | 2022-03-14 | 109.15 | 255.58 | 0 | 255.58 | 0 | 130.03 |  |  | 130.03 | 125.55 | 109.15 | 20.88
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/097 | 2022-03-14 | 4.3065 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4 | Construction of coal platform for Chandrapur TPS, Khaperkheda TPS & Parli TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 5.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4.2 | Khaperkheda TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 5.43 | 3.9936 | 3.9936 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 4.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.4a | 1. Procurement of 6.6 KV,300 KW, P.A.fan motor for U# 1 & 2 2. Procurement of 6.6 KV,425 KW,CM motor for U # 3 & 4 3. Procurement of 6.6 KV,1400KW,CW pump motor for U-1& 2 4. Procurement of 6.6 KV,1400 KW,CW pump motor for U-3&4 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 3.82 | 2.5973 | 2.5973 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.4b | K'kheda: Procurement of HT Motors(GS/HP Water pump)for U-1&2 and Procurement of HT Motors (ACW)for U-3&4 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 1 | 0.4 | 0.4 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.2 | KHAPERKHEDA (U-1 to 4) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.96 | 3.1173 | 3.1173 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.2 | Khaperkheda TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender for KPKD 1-4 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 1.7765 | 1.7765 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.2 | Normal Multipurpose Fire Tender KPKD 1-4 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 2.1847 | 2.1847 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 226.3024 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9.1 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 226.3024 | 291.23 | 57.6077 | 233.6223 | 0 | 273.81 |  |  | 273.81 | -40.1877 | 168.6947 | 105.1153
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 4.4604 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.2a | Compond wall (IB recommdation),Plant Patrolling Roads (IB recommdation) TPS KPKD | MERC/CAPEX/20172018/0177 | 2018-02-06 | 4.4604 | 3.9506 | 3.9506 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 9.23 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11.1 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 9.05 | 13.3057 | 13.3057 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 0.18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15 | Implementation of Water Flow Monitoring system at Chandrapur STPS & Khaperkheda TPS | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 5.1755 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.3 | Electromagnetic Flow meters at various lines & Locations of 210 MW | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 3.8515 | 0 | 0 | 0 | 3.8515 | 3.8515 |  |  | 3.8515 | 0 | 3.8515 | 0
HO DPR 15.4 | Automation: Centralized SCADA, RTU, MODBUS Cable, Power cable & mandatory spares | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 1.324 | 0 | 0 | 0 | 1.324 | 1.324 |  |  | 1.324 | 0 | 1.324 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30 | Supply of spare Generator Rotor for UNIT 1 & 2, 210MW | MERC/CAPEX/2023-24/0184 | 2024-03-12 | 37.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.1 | Supply of spare Generator Rotor for UNIT 1 & 2, 210MW | MERC/CAPEX/2023-24/0184 | 2024-03-12 | 36.7 | 36.7 | 0 | 36.7 | 0 | 36.7 |  |  | 36.7 | 0 | 36.7 | 0
0 | IDC | MERC/CAPEX/2023-24/0184 | 2024-03-12 | 0.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M with raising of drain wells and modification of Masonary Dam (Waste Weir), 4 x210 MW, TPS, Khaperkheda | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 45.0535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.1 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M at TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 31.0231 | 0 | 0 | 0 | 31.22 | 31.22 |  |  | 31.22 | 0 | 31.0231 | 0.19692
31.2 | Raising of drain wells of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 1.6569 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.3 | Modification of Masonary Dam (Waste Weir) of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 10.1857 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 2.1878 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
32 | Flue Gas Desulphurisation (FGD) System for Khaperkheda Unit # 1 & 2 | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 115.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.1 | Flue Gas Desulphurisation (FGD) System for Khaperkheda Unit # 1 & 2 | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 109.8 | 0 | 0 | 0 | 0 | 29.98 |  |  | 29.98 | -29.98
0 | IDC | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 5.54 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33 | Upgradation of DDC/DCS system for UNIT 1 & 3 of 210 MWKhaperkheda TPS | MERC/CAPEX/MSPGCL/2023-24/601 | 2023-11-10 | 39.14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.1 | Upgradation of DDC/DCS system for UNIT 1 & 3 of 210 MWKhaperkheda TPS | MERC/CAPEX/MSPGCL/2023-24/601 | 2023-11-10 | 38.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/601 | 2023-11-10 | 0.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34 | Supply & commissioning of interconnection conveyor belt, Elecon make complete impact type crusher, Procurement of 4 NOs. Bull Dozer BEML BD-155 and Eco friendly and power efficient chiller system at Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 28.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.1 | Design, engineering, manufacturing, supply, erection & commissioning of interconnection conveyor belt from 1 X 500MW to 4 X 210MW stack yard at CHP Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.2 | Supply & installation of Elecon–make complete impact type crusher at CHP-I, Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 4.29 | 0 | 0 | 0 | 4.15 | 4.15 |  |  | 4.15 | 0
34.3 | Procurement of 4 NOs. Bull Dozer BEML BD-155 at CHP, Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.255 | 0 | 12.0596 | -12.0596 | 12.0596 | 0 |  |  | 0 | 0
34.4 | Supply, erection, & commissioning of Eco friendly and power efficient chiller system for khaperkheda TPS Unit 1 to 4, Service Building and WTP in place of present reciprocating type Chiller system | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 11.96 | 0 | 0 | 0 | 3.78 | 3.78 |  |  | 3.78 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 1.385 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | 5 Nos. of Boiler Improvement Schemes for Unit No. 1 to 4 | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 32.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Procurement & replacement of Re-Heater Rear Pendent Assembly Coils for unit no. 3 & 4 (210 MW) | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 8.86 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.2 | Procurement Complete Set of Sky Climber For Unit#1 To 5 Boilers. | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 3.32 | 0 | 0 | 0 | 2.43 | 2.43 |  |  | 2.43 | 0
35.3 | Replacement of glasswool insulation and GI/CORRUGATED sheets of boiler and hot air ducts at unit 1to 4 KHAPERKHEDA TPS | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 2.19 | 0 | 0 | 0 | 1.99 | 1.99 |  |  | 1.99 | 0
35.4 | Procurement, design, manufacture, supply & delivery, dismantling, retrofitting, erection, commissioning and testing of gravimetric belt conveyor type coal feeders for unit no. 1 & 2. | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 6.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.5 | Procurement and Replacement of Air Preheater Baskets for Unit no. 1 to 4 (4x 210MW). | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 9.05 | 2.7935 | 2.7935 | 0 | 2.84 | 2.84 |  |  | 2.84 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 2.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR-17 | Various DPR Schemes for The work of maintaining the zero discharge condition of Pond No. 2 & Pond No.3 and providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 15.7443 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | The work of maintaining the zero discharge condition of Pond No.2 & Pond No.3 at KTPS Koradi | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 4.2068 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.2 | Providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 11.5375 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Scheme of HMI upgradation of unit 5 DCS along with Max Links , HART Scheme , PADO , all BOP PLCs , SWAS system, CO analyser & Coal feeder controller to match with the external aspect , process improvement & Up gradation of Generator Protections Relays in unit 1 to 4 of 210 MW at khaperkheda TPS | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 33.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.7 | Up-gradation of Generator Protections Relays in Unit 1 to 4 of 210 MW Khaperkheda TPS. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 8.31 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/478 | - | 0.86 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Submitted to MERC, Yet to receive approval | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR on Refurbishment of Spare HPT Module Unit 1 & 2 at TM-I and Procurement of Complete Gear Box Assemblies of Coal Mills XRP 803 ½ HP & XRP 883 for Unit No. 1 to 4 (4x210 MW), Khaperkheda TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Refurbishment of spare HPT module Unit 1 & 2 at TM-I (4X210 MW), KHAPERKHEDA TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Procurement of Complete Gear Box Assemblies of Coal Mills XRP 883 for Unit-1 to 4 (210MW). | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | SUPPLY INSTALLATION TESTING & COMMISSIONING REVAMPING OF FIRE DETECTION & ALARM AND PROTECTION SYSTEM FROM FIRE AND PROVIDING RAPID EXTINGUISHING CLEAN AGENT (CA) SYSTEM AT UNIT -3,4 & 5 ATKPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Supply Installation Testing & Commissioning , Revamping of fire protection and providing rapid extinguishing clean agent (CA) system at unit # 3 ,4 210 MW TPS, KHAPERKHEDA | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Restoration of various Fire protection system at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Restoration of fire hydrant ring and fire water spray Header at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Restoration of deluge valve system at CHP-210MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | VARIOUS SCHEMES PROPOSED FOR IMPROVEMENT OF CHP-I (4 X 210 MW). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Design, Manufacturing, Supply, Erection, Commissioning & Testing of Coal Flow Management system for Coal Bunkers in CHP-I (4 X 210MW), Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Design, engineering, manufacturing, supply, installation and commissioning of Dedusting System for Crusher House and Bunker area in Unit 3 & 4 at CHP-I (4 X 210MW), Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Renovation including replacement of Power & Control cables with automation & upgradation of Stacker Reclaimer No. 1 in CHP-I (4 X 210MW), TPS Khaperkheda." | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Flue Gas Desulphrisation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | FGD installation of 210MW unit 1 & 2 at Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Upgradation of DDC/DCS system for UNIT 2 & 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Upgradation of DDC/DCS system for UNIT 2 & 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#1 to 4 Khaperkheda TPS & Upgradation of various governing Element for smooth operation for flexible operation of TG set at 40% technical minimum operation. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#1 to 4 Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.2 | Upgradation of various governing Element for smooth operation for flexible operation of TG set at 40% technical minimum operation. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Upgradation of Battery Charger , UPS system , GEHO PLC and VFD, ID VFD, supply of Efficiency Measuring Instruments and Supply, erection and commissioning of Sox, Nox , CO, Opacity, ETP and Oxygen Analyser for Unit 1 to 4 of 210 MW at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Supply of Efficiency Monitoring Instruments for performance optimization group (POG) at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.2 | Upgradation of 220 V, 24 V DC Float cum boost battery charger at Unit#1 to 4 Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.3 | Upgradation of 2X50 KVA UPS at Unit#1 to 4 Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.4 | Supply, Erection and Commissioning of Sox, Nox , CO, Opacity and ETP Analyser for Unit 1 to 4 of 210 MW at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.5 | Upgradation of GEHO PLC and VFD along with HCSD system Instrumentaion at Unit 3 & 4 Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.6 | Supply, Erection & Commissioning of Oxygen Analyzer for combustion optimization for Unit#1 to 5 Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.7 | Upgradation of VFD for ID FAN in Unit# 3 & 4, 210MW khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.8 | Scheme 8 Supply, erection & commissioning of PLC and SCADA System of Ash Evacuation and Disposal System for UNIT 3 and 4 Of 210 MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of LP Rotor for unit 1 and 2 , Supply and installation of air washer unit 1 and 2 and refurbishment of air washer unit for unit 3 and 4 and GEHO Pummp house control room. Supply and installation of diesel engine driven fire fighting pump with engine. Procurement of various control valves for unit No. 1 to 4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.1 | Supply and installation of Air washer unit in unit 1 and 2 , 6.6 KV breaker room, Turbine MCC room Battery room Boiler MCC room for cooling of all the Electrical Panels and AHP stage I Pump House control room air washer system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.2 | Refurbishment of Air washer unit of 3 and 4, 6.6 KV breaker room, Turbine MCC room Battery room Boiler MCC room for cooling of all the Electrical Panels and Refurbishment of GEHO pump House and AHP stage II Pump House control room air washer system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.3 | Procurement of Complete LPT rotor for unit 1 and 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.4 | Revamping of diesel engine driven fire fighting pump system with engine. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.5 | Procurement of various control valves for unit No. 1 to 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of IP Rotor and Inner casing for unit 1 and 2. Procurement of IP rotor and inner casing for unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.1 | Procurement of IP Rotor and Inner casing for unit 1 and 2. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.2 | Procurement of IP rotor and inner casing for unit 3 and 4 along with Turbovisory sensors and panel | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.3 | Supply and installation of srew compressor for supply of instrument air to unit No. 3 and 4 along with dryer for unit No. 3 & 4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of LP rotor for unit 3 and 4 and upgradation of BFP cartridge and BFP Booster pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.1 | Procurement of of LP rotor for unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.2 | Upgradation of BFP cartridge and BFP Booster pump, motorized scoop for hydraulic coupling and drive unit for BFP and modulating BFP RC valve for Unit 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Refurbishment of LP rotor of unit 1 and 2 and Refurbishment of HPT module of unit 1 and 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.1 | Refurbishment of LP rotor of unit 1 and 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.2 | Refurbishment of HPT module of unit 1 and 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Refurbishment of LP rotor for unit 3 and 4 and Refurbishment and re-blading of HPT module of unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.1 | Refurbishment of LP rotors for unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.2 | Refurbishment of HPT modules of unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | SITC OF COMPLETE SOLUTION AND COMPREHENSIVE PROTECTION AND MONITORING PACKAGE ALONG WITH RETROFIT OF ALLIED ACCESSORIES FOR VARIOUS GTs & STs INSTALLED AT 210 MW KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | SUPPLY,INSTALLATION, TESTING & COMMISSIONING OF COMPLETE SOLUTION AND COMPREHENSIVE PROTECTION AND MONITORING PACKAGE ALONG WITH RETROFIT OF ALLIED ACCESSORIES FOR VARIOUS GTs & STs INSTALLED AT 210 MW KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | PLANT PERFORMANCE IMPROVEMENT BY DESIGN, SUPPLY, INSTALLATION & COMMISSIONING OF STATE OF ART HT VACCUM CIRCUIT BREAERS AT UNIT 1 TO 4 OF 210MW KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.1 | DESIGN, SUPPLY, INSTALLATION, TESTING & COMMISSIONING OF HT VCB AT U # 1 & 2. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.2 | DESIGN, SUPPLY, INSTALLATION, TESTING & COMMISSIONING OF HT VCB AT U # 3 & 4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | DESIGN, SUPPLY, INSTALLATION, TESTING AND COMMISSIONING OF THE VARIOUS LIFTS IN PLACE OF THE EXISTING OLD LIFTS, LIGHTNING PROTECTION SYSTEM, EARTHING SYSTEM, AVIATION LIGHTING SYSTEM INSTALLED AT UNIT # 1 TO 4 OF 210 MW, KHAPERKHEDA TPS ON OEM BASIS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | DESIGN, SUPPLY, INSTALLATION, TESTING AND COMMISSIONING OF THE VARIOUS LIFTS IN PLACE OF THE EXISTING OLD LIFTS INSTALLED AT UNIT # 1 TO 4 OF 210 MW, KHAPERKHEDA TPS ON OEM BASIS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Design, Engineering, Supply, Erection, Testing & Commissioning of lightning protection system at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Design, Engineering, Supply, Erection, Testing & Commissioning of Earthing of electrical system & various buildings at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Design, Engineering, Supply, Erection, Testing & Commissioning of Aviation Lighting Syatem at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | SUPPLY OF SPARE GENERATOR ROTOR FOR U#3 &4, 210MW, TPS KHAPERKHEDA. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.1 | SUPPLY OF SPARE GENERATOR ROTOR FOR U#3 &4, 210MW, TPS KHAPERKHEDA. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | PROCUREMENT OF ENERGY EFFICIENT MOTORS FOR U # 1 TO 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.1 | PROCUREMENT OF ENERGY EFFICIENT MOTORS FOR U # 1 & 2 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.2 | PROCUREMENT OF ENERGY EFFICIENT MOTORS FOR U # 3 & 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.3 | Procurement of DC motors for U # 1 & 2 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.4 | Procurement of DC motors for U # 3 & 4 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | UPGRADATION OF EXISTING LT MCC PANEL WITH STATE OF ART LT MCC PANEL AT U # 1 TO 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | UPGRADATION OF EXISTING LT MCC PANEL WITH STATE OF ART LT MCC PANEL AT U # 1 & 2 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.2 | UPGRADATION OF EXISTING LT MCC PANEL WITH STATE OF ART LT MCC PANEL AT U # 3 & 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.3 | UPGRADATION OF HT BREAKER PANEL AT WAREGAON ASH BUND OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | UPGRADATION OF HT BREAKER PANEL AT OLD PROJECT OFFICE OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.5 | Retrofitting of Existing L & T make LT MCC ACB by state or art ACB at U # 1 to 4 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.6 | Retrofitting of Existing ABB make LT MCC ACB by state or art ACB at U # 1 to 4 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | ERECTION & COMMISIONING OF DRY TYPE CAST RESIN TRANSFORMERS FOR U # 1 TO 4 OF KHAPERKHEDA TPS & Design, Engineering, Supply, Erection, Testing & Commissioning of various Battery sets at Unit # 3 & 4 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | PROCUREMENT OF DRY TYPE CAST RESIN TRANSFORMERS FOR U # 1 & 2 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.2 | PROCUREMENT OF DRY TYPE CAST RESIN TRANSFORMERS FOR U # 3 & 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.3 | PROCUREMENT OF VFD TRANSFORMERS FOR ID FAN MOTOR U#3&4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.4 | Design, Engineering, Supply, Erection, Testing & Commissioning of various Battery sets at Unit # 3 & 4 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20 | Study, Supply & Refurbishment of HCSD systems, ESP operation, ambience & various pump, & PLC schemes for the improvement of AHP-I at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.1 | STUDY. DESIGN & REFURBISHMENT WORKS OF HIGH CONCENTRATION SLURRY DISPOSAL SYSTEM (HCSD SYSTEM) UNITS #3&4 AT AHP-1, TPS KHAPERKHEDA. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.2 | STUDY, DESIGN & REFURBISHMENT WORKS OF ARTs AND ASSOCIATED MOUNTINGS & ACCESSORIES OF HCSD SYSTEM FOR AHP-I, TPS KHAPERKHEDA.” | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.3 | ‘SUPPLY & REFURBISHMENT WORKS OF HCSD ASH SLURRY MIXER SYSTEM AT UNIT #3 &4 OF AHP-I, TPS KHAPERKHEDA’. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.4 | ‘STUDY, SUPPLY, RESTORATIONS & REPLACEMENT OF ALL INTERNAL SPARES OF D6 FIELD & RENOVATION OF D1 FIELD OF U3 DURING AOH FOR AHP-I, TPS KHAPERKHEDA’ | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.5 | PROCUREMENT OF VARIOUS PUMPS IN RECYCLE WATER SYSTEM IN ASH HANDLING PLANT 4X210 MW AT KHAPARKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Reliability improvement and complete replacement of ABC series with drive unit of ash slurry pipeline of 7 KM of 4*210MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Procurement and restoration of complete pipeline replacement of ABC series | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.2 | Procurement and restoration of complete drive unit replacement of ABC series | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | Procurement and restoration of complete Bottom ash hopper replacement including entire structure, Clinker grinder alongwith motor, Feed Gate, Power Cylinder and Pipelines discharge of U3&4 of 4*210MW Khaparkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.1 | Procurement and restoration of complete BAH replacement including entire structure and clinker griender | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.2 | Procurement and restoration of complete drive unit of clinker grinder for Unit 1 to 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.3 | Procurement and restoration of discharge pipeline of vertical sump pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Procurement and restoration of Pipeline garlanding at Waregaon ash Bund of 4*210 MW Khapakheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.1 | Pipeline garlanding at Waregaon ash Bund of 4*210 MW Khapakheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Upgradation, modification and erection of complete wet fly ash evacuation into dry fly ash evacuation systen for ESP 1 and 2 of 4*210 MW Khapakheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.1 | Upgradation, modification and erection of complete wet fly ash evacuation into dry fly ash evacuation systen for ESP 1 and 2, 4*210 MW Khapakheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | Reliability improvement and complete replacement of JKL series with drive unit of ash slurry pipeline of 7 KM of 4*210MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.1 | Procurement and restoration of complete pipeline replacement of JKL series | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.2 | Procurement and restoration of complete drive unit replacement of JKL series | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | Study, Supply and Refurbishment of HCSD System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.1 | Procurement of complete Suction and discharge valve of Geho pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.2 | Procurement of Subassemblies of Geho pump. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.3 | Upgradation and compressors of dry ash evacutaion system of U#3&4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.4 | Procuremenet of complete drive unit and VFD of GEHO pump. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | RENOVATION OF ESP FIELD INTERNALS FOR UNIT 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.1 | RENOVATION OF ESP FIELD INTERNALS FOR UNIT 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28 | R & M OF APH OF UNIT # 1& 2 (2 x 210MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28.1 | R & M OF APH OF UNIT # 1& 2 (2 x 210MW) OF KHAPERKHEDA TPS FROM MODEL: 27 VI 1850 TO 27 VI 2000 mm. DESIGN, ENGINEERING, SUPPLY, ERECTION & COMMISSIONING OF DOUBLE SEALING | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29 | DPR FOR ECONOMISER COILS AND APH GEAR BOX | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29.1 | PROCUREMENT AND REPLACEMENT OF COMPLETE SET OF ECONOMISER UPPER BANK & LOWER BANK COILS FOR KHAPERKHEDA TPS UNIT NO.3&4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29.2 | Procurement of APH gear box in unit no. 1 & 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29.3 | Procurement of APH speed reducer gear box in unit no. 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30 | DPR FOR LTSH COILS , APH BASKETS & RH OUTLET STUB BENDS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.1 | Procurement of Air Pre-heater Baskets for unit no. 2 to 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.2 | Procurement of LTSH coils for unit no. 1 & 2 and Procurement of Reheater outlet header stub bends for unit no. 1 to 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.3 | Procurement of LTSH coils for unit no. 3 & 4 and Procurement of Reheater outlet header stub bends for unit no. 3 to 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31 | DPR FOR SUPPLY & REPLACMENT OF THERMAL INSULATION OF BOILER AND DUCT AT UNIT 1 TO 4 KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.1 | SUPPLY & REPLACMENT OF THERMAL INSULATION OF BOILER AND DUCT AT UNIT 1 TO 2KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.2 | SUPPLY & REPLACMENT OF THERMAL INSULATION OF BOILER AND DUCT AT UNIT 3 TO 4 KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32 | DPR FOR COAL CYCLE IMPROVEMENT IN UNIT NO.1 TO 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.1 | Procurement of Complete Journal Assembly for 803 ½ HP Coal Mills of Unit No. 1 To 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.2 | Procurement of Complete Journal Assembly for XRP 883 Coal Mills of Unit No. 3 To 4, | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.3 | Procurement of assembly of worm shaft & worm wheel with hub for unit no. 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.4 | PROCUREMENT OF COMPLETE GEAR BOX ASSEMBLIES OF COAL MILLS XRP 803 ½ HP FOR UNIT # 1 TO 2 AT KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.5 | PROCUREMENT OF COMPLETE GEAR BOX ASSEMBLIES OF COAL MILLS XRP 883 FOR UNIT # 3 TO 4 AT KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33 | DPR FOR PERFORMANCE IMPROVEMENT OF BOILER PA FAN, ID FAN AND FD FAN IN UNIT NO. 1 TO 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.1 | Procurement of PA fan Casings along with Dampers in Unit- 1 & 2, at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.2 | PROCUREMENT OF COMPLETE ROTOR ASSEMBLY ALONG WITH MOTOR FOR NDZV 31 SIDOR IN UNIT NO. 1 & 2 KHAPERKHEDA TPS (ID FAN) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.3 | PROCUREMENT OF FD FAN (BHEL AP 1-20 / 11) ASSEMBLY ALONG WITH DRIVE UNIT(MOTOR) FOR UNIT 1 & 2 AT KHAPERKHEDA TPS UNDER OEM NATURE ITEMS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.4 | PROCUREMENT OF FD FAN (BHEL AP 1-20 / 11) ASSEMBLY ALONG WITH DRIVE UNIT(MOTOR) FOR UNIT 3& 4 AT KHAPERKHEDA TPS UNDER OEM NATURE ITEMS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.5 | NDZV 33 SIDOR ID Fan Impeller Assembly for Unit 3 & 4 at TPS, Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.6 | Design, Engineering, Manufacturing, Supply & Commissioning including civil works for installation of 70 LPM lubricant ystems for PA Fans in unit no. 1&2. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.7 | Supply and installation of ID and PA foundation deck spring for unit no. 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34 | VARIOUS SCHEMES FOR BOILER PERFORMANCE IMPROVEMENT | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.1 | SUPPLY OF COAL MILL SEPERATOR & SCRAPPER BODIES FOR XRP-803 1/2 HP COAL MILLS IN UNIT 1 & 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.2 | MODIFICATION OF EXISTING COAL BUNKER AND COMMISSIONING OF BUNKER CHUTE ASSEMBLY WITH VIBRATING MOTOR TO AVOID BUNKER MOUTH COAL CHOKE UP FOR UNIT 1 & 2AT KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.3 | MODIFICATION OF EXISTING COAL BUNKER AND COMMISSIONING OF BUNKER CHUTE ASSEMBLY WITH VIBRATING MOTOR TO AVOID BUNKER MOUTH COAL CHOKE UP FOR UNIT 3 & 4 AT KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.4 | DESIGN, DEVELOPMENT, COMMISIONING OF SEAL AIR FAN ASSEMBLIES IN UNIT 1 & 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.5 | Procurement of sub body assembly of control valve in unit no. 1 & 2 actuating main gear unit part electrical actuator in unit no. 1 to 4 Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | Construction of A, B, C, D & E type stilt + 6 floor buildings at TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Construction of A, B, C, D & E type stilt + 6 floor buildings at TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36 | Enhancement & Renovation of existing building, Construction of Market building, Construction of club building community hall, Construction of school building, & Enhancement of existing domestic plant providing V wire 3 MLD at Colony TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.1 | Enhancement / Renovation & strengthening of existing building & allied works in colony TPS Khaperkhda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.2 | Construction of Market building including approach road, drainage arrangement & electrification at colony TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.3 | Construction of club building / community hall | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.4 | Construction of school building | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.5 | Enhancement of existing domestic plant providing V wire 3 MLD | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37 | Enhancement / Renovation of Saudamini Administrative Building, Construction of VIP Guest House, Construction of roads at Prakashnagar Colony and Providing various civil works related to coal transport railway lines of khaperkheda TPSTPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.1 | Enhancement / Renovation of Saudamini building | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.2 | Construction of VIP guest house TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.3 | Construction of Roads | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.4 | Construction of office building & store for electrical maintenance & Civil at KPKD | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.5 | Providing Special repair & retrofitting work of river bridge no.09 on Khaperkheda - Kalumna railway siding of TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.6 | Construction & repairing of drains & culverts along coal Transporting Railway lines & approach road of TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.7 | Repairing, providing & applying Epoxy Painting and Structural Steel Works to steel structural bridges on kpkd to Kaluma and kpkd to Saoner railway lines as per recommendation of structural stability report at TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.8 | Construction of compound wall KPKD Colony | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38 | Work of Strengthening and modification of Main Plant, construction of roads, strengthening of IDCT 1 to 4 in plant area, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.1 | Work of attending additional works based on structural report at Induced Draft Cooling Towers(IDCT) unit 1,2,3 & 4 at 4 x 210MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.2 | Work of constructon of roadside drains from VIP gate no.3 to IDCT No.1 at 4 x 210MW TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.3 | Construction of bituminous macadam road from Administrative Building to GCR Road near Service Building of 4X210MW TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.4 | Work for Construction of cement concrete road for equipment movement for salt lagoon (WTP-I), FGD(System), H2(cylinders) plant etc. inside plant premises in 4x 210MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.5 | Construction of cement concrete road outside BTG area of Power Plant 4 x 210MW TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.6 | Construction of cement concrete road for material transportation from D-Point CHP to reject coal Dumping yard in 4x 210MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.7 | Work of Strengthening and modification of Main Plant, Major Stores, Auxiliary in plant area, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.8 | Construction of diversion road along with RCC bridge from rejct coal yard CHP-I & CHP-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.9 | Upgradation of existing ETP plant consist civil works, electrification and pumps. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
39 | Work of 5th Raising of Waregaon Ash Bund, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
39.1 | Work of 5th Raising of Waregaon Ash Bund, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
40 | Work of CTR(Complete Track Removal),TTR(TRAIN TRAVLER REGULATOR) and Yard Remoulding incl. misc. works at Mahagenco Khaperkheda Plant. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
40.1 | Work of CTR(Complete Track Removal),TTR(TRAIN TRAVLER REGULATOR) and Yard Remoulding incl. misc. works at Mahagenco Khaperkheda Plant. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41 | Various WTP 210MW improvement schemes i.e. Up-gradation of SWAS SYSTEM UNIT- 1 to 4 at WTP-I 210 MW along with coal sampling lab upgradation, Comissioning of CW Chemical Dosing system etc | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.1 | Upgradation of Existing ETP system viz. Plate Settler, Settling tank, Sludge Drying bed, Chemical dosing system etc.)as per MPCB consent condition | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.2 | Upgradation of SWAS Lab 3& 4 at WTP-210 MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.3 | Revamping of Chlorination Plant Stream (A+ B) & Installation, Comissioning of CW Chemical Dosing system (Viz. Scale inhibitor, Scale Dispersant, Biodispersant, Corossion Inhibitor & H2SO4 dosing) and Online CW Chemical parameter monitoring system at KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.4 | Upgradation of SWAS Lab 1& 2 at WTP-210 MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.5 | Upgradation of Water &Coal testing Lab at WTP-210 MW &Procurement of Coal Lab Instruments and upgradation of coal sampling Room & Instruments related to Coal sample Preparation. at WTP-210 MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42 | Work of capacity restoration of unloading stream from Beetle Charger No. 1 to Stacker/Reclaimer No. 1 for perfromance improvement of CHP-I (4 x 210 MW) & Capacity restoration of unloading stream from Beetle Charger No. 1 to Stacker/Reclaimer No. 1 for perfromance improvement of CHP-I (4 x 210 MW). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.1 | Revamping/ refurbishment, capacity restoration and upgradation for beetle charger No. 1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.2 | Revamping/ refurbishment, capacity restoration and upgradation for Wagon Tippler No. 1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.3 | Revamping/ refurbishment, capacity restoration and upgradation for Apron Feeder No. 1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.4 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 2C, 3A, 4A, 8A, 9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.5 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for impact crusher and wobbler feeder No. 1 & 3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.6 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Stacker/Reclaimer No. 1. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.7 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv. 3C to 3A, Conv. 3A to 4A, Conv. 4A to 8A and Conv. 9 by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.8 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of beetle Charger, wagon tippler, apron feeder, covneyors (Conv. 2C, 3A, 4A, 8A, 9), crushers/ wobbler feeder No. 1 & 3 and Stacker/Reclaimer No. 1 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
43 | DPR fo Capacity restoration of bunkering stream from Conv. 5A to 7A/B/C/D including shuttle conveyors in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
43.1 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 5A, 6B, 7A, 7B, 7C, 7D and Shuttle Conv. 1 to 4 in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
43.2 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv.Conv. 4D to 5A/B , 5A to 6B, Conv. 6B to 7A & 7B, Conv. 7B to 7D upto shuttle conveyor, Conv. 7A to 7C upto shuttle conveyor by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
43.3 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of covneyors (Conv. 5A, 6B, 7A/B/C/D & Shuttle Conv. 1 to 4 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44 | Work of capacity restoration of unloading stream from Beetle Charger No. 2 to Stacker/Reclaimer No. 2 for perfromance improvement of CHP-I (4 x 210 MW). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.1 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for beetle charger No. 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.2 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Wagon Tippler No. 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.3 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Apron Feeder No. 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.4 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 2D, 3B, 4B, 8B, 10 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.5 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for impact crusher and wobbler feeder No. 2 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.6 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Stacker/Reclaimer No. 2. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.7 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv. 2D to 3B, Conv. 3B to 4B, Conv. 4B to 8B and Conv. 10 by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.8 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of beetle Charger, wagon tippler, apron feeder, covneyors (Conv. 2D, 3B, 4B, 8B, 10), crushers/ wobbler feeder No. 2 & 4 and Stacker/Reclaimer No. 2 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45 | Work of capacity restoration of bunkering stream from Conv. 1A/B, 2A/B, 5B to 7E/F/G/H including shuttle conveyors in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.1 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 1A/B, 2A/B, 5B, 6A, 7E, 7F, 7G, 7H and Shuttle Conv. 5 to 8 in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.2 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv. 1A/b to 2A/B,Conv. 4C to 5A/B, Conv. 5B to 6A, Conv. 6A to 7E & 7F, Conv. 7E to 7G upto shuttle conveyor, Conv. 7F to 7H upto shuttle conveyor by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.3 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of conveyor system from Conv. 1A/B, 2A/B, 5B, 6A, 7E, 7F, 7G, 7H and Shuttle Conv. 5 to 8 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.4 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Paddel Feeder No. 1 to 4 and truck hopper in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46 | Renovation and upgradation of various electrical system for CHP-I (4 x 210 MW) improvement & Renovation and upgradation of various electrical system for CHP-I (4 x 210 MW) improvement. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.1 | Design, development and upgradation with circuit breaker VFD of various LT MCC of CHP-I. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.2 | Design, Supply, Installation, Commissioning and Testing of Energy Chain System for Paddle Feeder, Shuttle Conveyor and Stacker/Reclaimers in CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.3 | Upgradation of relay logic system with PLC & SCADA in CHP-I control room and Wagon Tipplers in CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.4 | Complete upgradation of conveyor lighting system with energey efficient LED lights for CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.5 | Providing, installation, testing commissioning, maintenance and operation of explosion proof & weather proof surveillance system at CHP-I (4 X 210 MW), TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.6 | Complete revamping/refurbishment, upgradation and modification of various EOT cranes & hoist installed at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47 | Procurement of various capacity SAN make locomotives and BEML make loader & bulldozer for CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.1 | Procurement of various capacity SAN make locomotives and BEML make loader & bulldozer for CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48 | CHP Improvement Schemesfor 4x 210 MW units | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.1 | Design, manufacture, supply and installation of suspended magnet for bunkering belts at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.2 | Design, manufacture, supply and installation of travel drive system for shuttle conveyors and conveyors at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.3 | Renovation including replacement of Power & Control cables with automation & upgradation of Stacker Reclaimer No. 2 in CHP-I (4 X 210MW), TPS Khaperkheda." | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.4 | Complete reconditionding & upgradation of LT MCC installed at Unit No. 3 & 4 bunker auxiliareis in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.5 | Complete reconditionding & upgradation of outdoor lighting system in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.6 | Complete reconditionding & upgradation of HT breaker, control circuits & protection relays in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.7 | Complete revamping/refurbishment, upgradation and modification of various monorail hoists & winch machine installed at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.8 | Procurement of hydra 14 Ton above capacity and heavy vehicles for CHP- I & II. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
49 | Installation of Real Time Coal Analyzer at all TPS of Mahagenco | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
49.1 | Installation of Real time Coal Analyzer at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50 | Railway expenses for refurbishment of OHE lines at CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50.1 | Railway expenses for refurbishment of OHE lines at CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | PROCUREMENT COMPLETE Gear BOX ASSEMBLIES FOR 803 1/2 HP & XRP 883 COAL MILLS OF UNIT NO. 1& 2 AT KHAPERKHEDA TPS. | N.A. | - | 0 | 4.5548 | 4.5548 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply Erection and commissioning of Oil Cooled Suspended magnets at Conv 6A & 6B at Khaperkheda TPS. | N.A. | - | 0 | 1.1484 | 1.1484 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurment of new 02 Ambulance Van & 2 Truck for KPKD TPS(Asset Nos. 170100512, 170100513, 170100514, 170100515) | N.A. | - | 0 | 0.41055 | 0.41055 | 0 | 0 | 0 |  |  | 0 | 0
4 | GEHO PUMP (Valve housing assembly) | N.A. | - | 0 | 8.7933 | 8.7933 | 0 | 0 | 0 |  |  | 0 | 0
5 | RESTORATION OF AHP OUTLET TO ESP INLET DUCTS U#1&2(Unit #2 Part only) | N.A. | - | 0 | 7.0042 | 7.0042 | 0 | 0 | 0 |  |  | 0 | 0
6 | ABC powder type and foam type composite Fire Extinguisher | N.A. | - | 0 | 0.714 | 0.714 | 0 | 0 | 0 |  |  | 0 | 0
7 | FFEQUIP HYDRAULIC JACK (BM-I) | N.A. | - | 0 | 0.57696 | 0.57696 | 0 | 0 | 0 |  |  | 0 | 0
8 | MOBILE COAL SAMPLING EQUIP-AUGER (FMC) CHP-I | N.A. | - | 0 | 1.5824 | 1.5824 | 0 | 0 | 0 |  |  | 0 | 0
9 | Replacement of ash slurry disposal pump to improve performance & capacity enhancement of ash slurry disposal system at AHP-1 Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 4.92 | 4.92 |  |  | 4.92 | 0
10 | Procurement of Pillow Block Dodge Bearing Assemblies (Expansion & Non-Expansion) for PA fans in Unit- n1 to 4, at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 5.11 | 5.11 |  |  | 5.11 | 0
11 | Replacement of Economizer outlet to APH outlet common duct in unit no. 3 (210MW), Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 6.24 | 6.24 |  |  | 6.24 | 0
12 | PROCUREMENT OF OIL COOLED SUSPENSION MAGNET FOR 210MW AND MODIFICATION & REPLACEMENT OF VIBRATING FEEDER WITH VIBRATING TRANSFER CHUTE FOR 210MW | 0 | - | 0 | 0 | 0 | 0 | 3.09 | 3.09 |  |  | 3.09 | 0
13 | DESIGN,ENGINEERING,MODIFICATION ,ERECTION AND COMMISSIONING OF DRIVE UNIT ARRANGEMENT FOR CONVEYOR 10 AT CHP1 | 0 | - | 0 | 0 | 0 | 0 | 1.65 | 1.65 |  |  | 1.65 | 0
14 | ENERGY EFFICIENT PLANT LIGHTING AND COLONY LIGHTING MODIFICATIONS | 0 | - | 0 | 0 | 0 | 0 | 21.04 | 21.04 |  |  | 21.04 | 0
15 | Supply installation testing and commisioning of various battery sets at unit No 1 & 2 of Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 9.31 | 9.31 |  |  | 9.31 | 0
16 | Revamping and modification of existing alarm and protection system from fire and provide rapid extinguishing Clean Agent (CA) system at Unit #1 & 2 (210 MW) units, KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 8.21 | 8.21 |  |  | 8.21 | 0
17 | Supply of electronic modules for Procontrol DCS system in unit 1 to 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 1.18 | 1.18 |  |  | 1.18 | 0
18 | Revamping & UPGRADATION of SWAS system in unit 3 & 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 8.56 | 8.56 |  |  | 8.56 | 0
19 | Upgradation of process instrumentation in unit 1 to 2 of 210 MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 4.64 | 4.64 |  |  | 4.64 | 0
20 | Replacement of flue gas duct from air heater outlet to esp inlet for U 1 & 2 (S+W) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | PROCUREMENT OF COMPLETE ROTOR ASSEMBLY FOR NDZV 31 SIDOR IN UNIT NO. 1 & 2 KHAPERKHEDA TPS (ID FAN). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | UPGRADATION OF BELT CONVEYOR CAPACITY OF 2C &2D AND 8A & 8B AT CHP1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | WORK OF DESIGN,ENGINEERING,ERECTION AND UPGRADATION OF DRIVE UNITS OF BELT CONVEYOR 3A & 3BAT CHP1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Procurement of 1500 KW ID Fan Synchronous Motor at Unit 3 & 4 Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | Procurement of Steam and Water Analysis System(SWAS) for Unit 1&2 (210MW) KPKD TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | Supply and replacement of complete PVC fills of cell of cooling tower of unit 1-4 (210 MW) at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | PROCUREMENT OF FD FAN (BHEL AP 1-20/11) ASSEMBLY FOR UNIT 1 TO 4 ATKHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 4.37 | 4.37 |  |  | 4.37 | 0
28 | CHP performance improvement scheme for capacity restoration of drive units installed at CHP-1 (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 14.5 | 14.5 |  |  | 14.5 | 0
29 | Work of Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of belt conveyor 8A & 8B and belt conveyor 2C & 2D at CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 2.15 | 2.15 |  |  | 2.15 | 0
30 | WORK OF DESING,SUPPLY ,ERECTION,COMMISSIONG AND UPGRADATION OF COMPLETE ELECTRICAL SYSTEM FOR DRIVE UNITS OF BELT CONVEYOR 3A & 3B AND BELT CONVEYOR 4A,4B,4C & 4D AT CHP1 Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 2.29 | 2.29 |  |  | 2.29 | 0
31 | Supply, Installation, & Commissioning of Instruments at coal Testing Lab, WTP-I, TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0.45 | 0.45 |  |  | 0.45 | 0
32 | Supply, Installation & Commissioning and Refurbishment of asbestos based H2 Generator and compressor to convert it to non-asbestos based H2 Generator for Unit 1 to 5, Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33 | construction of bituminous macadam roads at Prakashnagar Colony TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34 | Work of attending additional works based on structural report at Induced Draft Cooling Towers (IDCT) unit 1,2,3 & 4 at 4 x 210MW, TPS, Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | VIBRATION ANALYSER | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36 | Upgradation of GEHO pump instrumentation for AHP Unit No. 3 & 4 (210 MW) at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37 | Refurbishment of HPT module for Unit 1 & 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38 | General Asset Furniture | N.A. | - | 0 | 0.86177 | 0.86177 | 0 | 0 | 0 |  |  | 0 | 0
39 | General Asset AC, Fans, Air coolers, water filter etc. | N.A. | - | 0 | 0.53608 | 0.41552 | 0.12056 | 0 | 0 |  |  | 0 | 0.12056
40 | General Asset Computer, scanners, etc. | N.A. | - | 0 | 2.5598 | 1.9461 | 0.61367 | 0 | 0 |  |  | 0 | 0.61367
41 | Land aquired for rly siding | N.A. | - | 0 | 0.4072 | 0.4072 | 0 | 0 | 0 |  |  | 0 | 0
42 | RCC ROAD FROM ASH SILO TO 'D' POINT FOR BULKER MO | N.A. | - | 0 | 0.95225 | 0.95225 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 993.8684 | 389.9622 | 603.9062 | 207.1952 | 631.5376 | 0 | 0 | 631.5376 | 179.5638
FY 2025-26
a) DPR Schemes
(i) Submitted to MERC
| Combustion optimization system | [6 empty] | 0 | 0
1 | Dynamic coal flow measurement and control (balancing) system (one) | [6 empty] | 0 | 0
1.2 | CO analyser (8 units) | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 | 1.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Oxygen analyser (32 units) | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 | 0.783 | 0.75683 | 0.75683 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Spare HPT module for Khaparkheda Unit 1 & 2 | MERC/CAP/DPR/10/2010-11/1466 | 2010-10-26 | 26.459 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | HPT module 1 No (unit # 1) | MERC/CAP/DPR/10/2010-11/1466 | 2010-10-26 | 23.0379 | 23.9074 | 23.9074 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAP/DPR/10/2010-11/1466 | 2010-10-26 | 3.4211 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Economiser Upper Bank & Lower Bank coils for Khaperkheda Unit no. 3 and Unit no. 4 | MERC/CAP/DPR/10/2010-11/1695 | 2010-12-15 | 26.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Economiser Upper Bank & Lower Bank coils for Khaperkheda Unit no. 3 and Unit no. 4 | MERC/CAP/DPR/10/2010-11/1695 | 2010-12-15 | 26.35 | 11.77 | 11.77 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Economiser & LTSH Upper Bank & Lower Bank coils for Khaperkheda Unit no. 1 and Unit no. 2 | MERC/CAPEX/20112012/01155 | 2011-07-29 | 34.7916 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Economiser & LTSH Coil for Unit 1 | MERC/CAPEX/20112012/01155 | 2011-07-29 | 15.6924 | 15.6924 | 15.6924 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Economiser & LTSH Coil for Unit 2 | MERC/CAPEX/20112012/01155 | 2011-07-29 | 16.1528 | 16.1528 | 16.1528 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20112012/01155 | 2011-07-29 | 2.9464 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Procurement & Replacement of Re-heater Rear Pendant Assembly Coils for 2*210MW Khaperkheda Unit no. 1 and Unit no. 2 | MERC/CAPEX/20122013/00603 | 2012-06-18 | 10.3738 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Re-heater coils for unit no. 1 | MERC/CAPEX/20122013/00603 | 2012-06-18 | 5.1267 | 5.1267 | 5.1267 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Re-heater coils for unit no. 2 | MERC/CAPEX/20122013/00603 | 2012-06-18 | 5.1267 | 5.55 | 5.55 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/00603 | 2012-06-18 | 0.1204 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Procurement of HPT module suitable for khaperkheda TPS Unit 3 & 4 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 36.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Procurement of HPT module suitable for khaperkheda TPS Unit 3 & 4 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 36.2 | 32.4016 | 32.4016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7 | Procurement Spare GTR, Locomotive & Compactors | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 18.4521 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | 250 MVA Spare GTR | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 10.3496 | 11.2511 | 11.2511 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.2 | Procurement of Locomotive 2no’s. | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 5.9927 | 5.9927 | 5.9927 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.3 | Procurement of Compactors 2 no’s. | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 0.42979 | 0.4298 | 0.4298 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 1.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Procurement & Replacement of complete set of LTSH coils for Khaperkheda TPS Unit 3&4 | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 17.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement and replacement of LTSH coils for Khaperkheda TPS at U3 | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 8.58 | 3.4291 | 3.4291 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Procurement and replacement of LTSH coils for Khaperkheda TPS at U4 | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 8.58 | 3.1809 | 3.1809 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 0.65 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Development of Ash Bund (Waregaon) at K'kheda TPS | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 38.7459 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Construction of 3rd upstream raising of existing ash bund from TBL 299.50 Mtr to 302.50 Mtr at Waregaon, Khaperkheda TPS. | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 33.8585 | 32.5375 | 32.5375 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.2 | Construction of masonary dam (Gabion structure) at Waregaon TPS, Khaperkheda. | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 1.0561 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.3 | Construction of approach to drain wells and raising height of drain well no. 1,2 & 3 ash bund at Waregaon, Khaperkheda TPS | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 0.48488 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 3.3464 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Various schemes related to CHP Improvement & Performance Optimization and scheme of conversion of existing Composite OHE to Conventional OHE | MERC/CAPEX/20152016/00422 | 2016-08-03 | 10.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Air Cooled Suspension Magnet for Con. 3 & 6 of CHP 210 MW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 2.18 | 2.2613 | 2.2613 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | Procurement of Impact crusher motor | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.84 | 0.52579 | 0.52579 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.3 | Procurement of 360V, 200 AH battery set and 360V 325 AH battery set for U# 1to 4 | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.1 | 1.4576 | 1.4576 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.4 | Procurement of POG Instruments for Unit 1 to 4 | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.77 | 0.35015 | 0.35015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.5 | Up gradation of safe scan flame scanner system by BHEL scan system in unit no. 1, 3 & 4 | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.6 | Up gradation of old AVR system to DAVR | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.7 | Conversion of existing Composite OHE to Conventional OHE | MERC/CAPEX/20152016/00422 | 2016-08-03 | 2.72 | 2.72 | 2.72 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.47 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | ESP up-gradation for Unit-1 at Khaperkheda TPS | MERC/CAPEX/20152016/01261 | 2016-01-11 | 32.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | ESP up-gradation for Unit-1 at Khaperkheda TPS | MERC/CAPEX/20152016/01261 | 2016-01-11 | 32.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Procurement, installation and commissioning of Gravimetric Belt / Rotary Type Feeder, VFD for CEP, Up-gradation of BTS system & Environmental schemes at Khaperkheda TPS | MERC/CAPEX/20162017/01552 | 2017-02-14 | 20.218 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Procurement, installation and commissioning of Gravimetric belt/rotary Feeder at U-1 & 2 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 5.72 | 4.7418 | 4.7418 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Installation of VFD to CEP at U-1 to 4 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 8.64 | 8.7575 | 7.0482 | 1.7093 | 0.38326 | 2.0918 |  |  | 2.0918 | 0.000792 | 1.5918 | 0.5
13.3 | Installation of BTS system at U-4 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 0.98796 | 0.98796 | 0.98796 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.4 | Replacement of SOx/NOx analyzer at U-1 to 4 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 2.42 | 2.3035 | 2.3035 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.5 | Procurement of TGA,CHNS analyzer and Bomb calorimeter at U-5 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 1.71 | 0.2897 | 0.2897 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01552 | 2017-02-14 | 0.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Up gradation of HMI System at Unit No 3 & 4 at Khaperkheda TPS | MERC/CAPEX/20172018/03946 | 2017-07-19 | 13.39 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | HMI Up-gradation at U# 3 & 4 | MERC/CAPEX/20172018/03946 | 2017-07-19 | 12.78 | 12.5611 | 13.1811 | -0.62 | 0 | 0 |  |  | 0 | -0.62 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/03946 | 2017-07-19 | 0.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21 | Procurement of APH Basket for unit # 1 to 5 and Up-gradation of HT Motor Protection Relay in Unit # 1 to 4 at Khaperkheda TPS | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 9.77 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.1 | Procurement of assembly of baskets for air preheater of type bisector APH 27 VI: 1850, 12 sector in unit no. 1 & 2 and bisector APH 27 VI: 2000; 24 sector in unit no. 3 & 4 (210MW x 4) at TPS, Khaperkheda | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 5.71 | 8.097 | 8.0941 | 0.002845 | 0 | 0 |  |  | 0 | 0.002845 | 0 | 0
21.3 | Up-gradation of H.T. Motor protection relays in Unit 1 to 4 (210MW), Khaperkheda TPS | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 3.96 | 3.2537 | 3.2537 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 0.1 | 0 | 0.18424 | -0.18424 | 0 | 0 |  |  | 0 | -0.18424 | 0 | 0
22 | Procurement of LPT rotor suitable for Unit # 3 & 4 of 210 MW at Khaperkheda TPS | MERC/CAPEX/2018-2019/132 | 2019-05-09 | 27.191 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.1 | Procurement of LPT rotor suitable for Unit # 3 & 4 of 210 MW at Khaperkheda TPS | MERC/CAPEX/2018-2019/132 | 2019-05-09 | 26.491 | 10.7515 | 10.7515 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2018-2019/132 | 2019-05-09 | 0.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23 | Supply, Erection & commissioning of HT Vacuum circuit Breakers & SF6 contactors at AHP (U#1-4) & CHP (U#1 to 5) and 160 KW VFD Panel with Motor for fire-fighting pumps at U#1 to 4 at Khaperkheda TPS | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 10.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.1 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at AHP (Unit#1 to 4, 210MW), Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 4.17 | 3.4843 | 4.8883 | -1.404 | 0 | 0 |  |  | 0 | -1.404 | 0 | 0
23.2 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at CHP (Unit#1 to 4, 210MW) and CHP (Unit#5, 500MW) Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 3.81 | 4.031 | 2.7332 | 1.2978 | 0 | 0 |  |  | 0 | 1.2978 | 0 | 0
23.3 | Supply, Erection & commissioning of 150 KW VFD Panel with motor for fire-fighting pumps at 210 MW Khaperkheda TPS. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 2.34 | 2.0957 | 2.0957 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 0.58 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24 | Augmentation of Waregaon Ash Water Recovery System at TPS Khaperkheda | MERC/CAPEX/2019-20/732 | 2019-09-16 | 17.1984 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.1 | Augmentation of Waregaon Ash Water Recovery System at TPS Khaperkheda | MERC/CAPEX/2019-20/732 | 2019-09-16 | 15.7884 | 15.1987 | 15.1987 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-20/732 | 2019-09-16 | 1.41 | 0.58812 | 0.58812 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25 | Procurement of VFD with HMI & Controller & Replacing with existing Eddy-current drives of Coal feeders at U# 3 & 4 and Procurement of Various Critical Components of GEHO Pump (Model-TZPM 800) for AHP-1 at Khaperkheda TPS | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 10.6535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25.1 | Up-gradation of Existing BHEL make 36” Gravimetric Coal Feeders control panel with HMI and croprocessor based Controller with VFD, Motor & Weigh Module at Unit 3 & 4, (210MW) | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 7.4655 | 3.85 | 3.85 | 0 | 3.85 | 3.85 |  |  | 3.85 | 0 | 3.6155 | 0.23446
25.2 | Procurement of various Critical Components of GEHO Pump (Model-TZPM 800) for AHP-1 (210MW) | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 2.698 | 2.6466 | 2.6466 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 0.49 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26 | Procurement, Replacement of Eco Coils U#1&2 210 MW, & Procurement & replacement of foundation Deck Spring assembly for coal mills U#3,4 at Khaperkheda TPS | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 15.4086 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26.1 | Procurement, Replacement of Eco Coils U#1&2 | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 7.4996 | 6.6503 | 6.6503 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26.2 | Procurement & replacement of foundation Deck Spring assembly for coal mills U#3,4 | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 6.679 | 7.0955 | 3.55 | 3.5455 | 0 | 3.55 |  |  | 3.55 | -0.004476 | 3.129 | 0.42102
0 | IDC | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 1.23 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28 | ESP Upgradation of 5 Nos. of 210/500MW Units at Khaperkheda, Koradi & Chandrapur TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 90.3535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.1 | ESP Upgradation at Unit #1, Khaperkheda TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 42.7114 | 59.55 | 0 | 59.55 | 0 | 54.445 |  |  | 54.445 | 5.105 | 42.7114 | 11.7336
28.2 | ESP Upgradation at Unit #2, Khaperkheda TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 42.7114 | 59.55 | 0 | 59.55 | 0 | 54.445 |  |  | 54.445 | 5.105 | 42.7114 | 11.7336
0 | IDC | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 4.9307 | 0 | 0 | 0 | 0 | 16 |  |  | 16 | -16 | 4.9307 | 11.0693
29 | Flue Gas Desulphurisation System for Khaperkheda Unit # 1-4 | MERC/CAPEX/2021-2022/MSPGCL/097 | 2022-03-14 | 113.4565 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.1 | FGD System for Khaperkheda Unit # 1-4 | MERC/CAPEX/2021-2022/MSPGCL/097 | 2022-03-14 | 109.15 | 255.58 | 130.03 | 125.55 | 0 | 0 |  |  | 0 | 125.55 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/097 | 2022-03-14 | 4.3065 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4 | Construction of coal platform for Chandrapur TPS, Khaperkheda TPS & Parli TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 5.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4.2 | Khaperkheda TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 5.43 | 3.9936 | 3.9936 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 4.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.4a | 1. Procurement of 6.6 KV,300 KW, P.A.fan motor for U# 1 & 2 2. Procurement of 6.6 KV,425 KW,CM motor for U # 3 & 4 3. Procurement of 6.6 KV,1400KW,CW pump motor for U-1& 2 4. Procurement of 6.6 KV,1400 KW,CW pump motor for U-3&4 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 3.82 | 2.5973 | 2.5973 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.4b | K'kheda: Procurement of HT Motors(GS/HP Water pump)for U-1&2 and Procurement of HT Motors (ACW)for U-3&4 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 1 | 0.4 | 0.4 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.2 | KHAPERKHEDA (U-1 to 4) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.96 | 3.1173 | 3.1173 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.2 | Khaperkheda TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender for KPKD 1-4 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 1.7765 | 1.7765 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.2 | Normal Multipurpose Fire Tender KPKD 1-4 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 2.1847 | 2.1847 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 226.3024 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9.1 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 226.3024 | 291.23 | 331.4177 | -40.1877 | 0 | 0 |  |  | 0 | -40.1877 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 4.4604 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.2a | Compond wall (IB recommdation),Plant Patrolling Roads (IB recommdation) TPS KPKD | MERC/CAPEX/20172018/0177 | 2018-02-06 | 4.4604 | 3.9506 | 3.9506 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 9.23 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11.1 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 9.05 | 13.3057 | 13.3057 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 0.18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15 | Implementation of Water Flow Monitoring system at Chandrapur STPS & Khaperkheda TPS | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 5.1755 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.3 | Electromagnetic Flow meters at various lines & Locations of 210 MW | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 3.8515 | 3.8515 | 3.8515 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.4 | Automation: Centralized SCADA, RTU, MODBUS Cable, Power cable & mandatory spares | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 1.324 | 1.324 | 1.324 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30 | Supply of spare Generator Rotor for UNIT 1 & 2, 210MW | MERC/CAPEX/2023-24/0184 | 2024-03-12 | 37.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.1 | Supply of spare Generator Rotor for UNIT 1 & 2, 210MW | MERC/CAPEX/2023-24/0184 | 2024-03-12 | 36.7 | 36.7 | 36.7 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2023-24/0184 | 2024-03-12 | 0.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M with raising of drain wells and modification of Masonary Dam (Waste Weir), 4 x210 MW, TPS, Khaperkheda | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 45.0535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.1 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M at TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 31.0231 | 31.22 | 31.22 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.2 | Raising of drain wells of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 1.6569 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.3 | Modification of Masonary Dam (Waste Weir) of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 10.1857 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 2.1878 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
32 | Flue Gas Desulphurisation (FGD) System for Khaperkheda Unit # 1 & 2 | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 115.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
32.1 | Flue Gas Desulphurisation (FGD) System for Khaperkheda Unit # 1 & 2 | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 109.8 | 0 | 29.98 | -29.98 | 0 | 99.15 |  |  | 99.15 | -129.13
0 | IDC | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 5.54 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33 | Upgradation of DDC/DCS system for UNIT 1 & 3 of 210 MWKhaperkheda TPS | MERC/CAPEX/MSPGCL/2023-24/601 | 2023-11-10 | 39.14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.1 | Upgradation of DDC/DCS system for UNIT 1 & 3 of 210 MWKhaperkheda TPS | MERC/CAPEX/MSPGCL/2023-24/601 | 2023-11-10 | 38.7 | 0 | 0 | 0 | 19.57 | 19.57 |  |  | 19.57 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/601 | 2023-11-10 | 0.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34 | Supply & commissioning of interconnection conveyor belt, Elecon make complete impact type crusher, Procurement of 4 NOs. Bull Dozer BEML BD-155 and Eco friendly and power efficient chiller system at Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 28.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.1 | Design, engineering, manufacturing, supply, erection & commissioning of interconnection conveyor belt from 1 X 500MW to 4 X 210MW stack yard at CHP Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.2 | Supply & installation of Elecon–make complete impact type crusher at CHP-I, Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 4.29 | 4.15 | 4.15 | 0 | 0 | 0 |  |  | 0 | 0
34.3 | Procurement of 4 NOs. Bull Dozer BEML BD-155 at CHP, Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.255 | 12.0596 | 12.0596 | 0 | 0 | 0 |  |  | 0 | 0
34.4 | Supply, erection, & commissioning of Eco friendly and power efficient chiller system for khaperkheda TPS Unit 1 to 4, Service Building and WTP in place of present reciprocating type Chiller system | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 11.96 | 3.78 | 3.78 | 0 | 7.67 | 7.67 |  |  | 7.67 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 1.385 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | 5 Nos. of Boiler Improvement Schemes for Unit No. 1 to 4 | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 32.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Procurement & replacement of Re-Heater Rear Pendent Assembly Coils for unit no. 3 & 4 (210 MW) | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 8.86 | 0 | 0 | 0 | 4.68 | 4.68 |  |  | 4.68 | 0
35.2 | Procurement Complete Set of Sky Climber For Unit#1 To 5 Boilers. | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 3.32 | 2.43 | 2.43 | 0 | 0 | 0 |  |  | 0 | 0
35.3 | Replacement of glasswool insulation and GI/CORRUGATED sheets of boiler and hot air ducts at unit 1to 4 KHAPERKHEDA TPS | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 2.19 | 1.99 | 1.99 | 0 | 0 | 0 |  |  | 0 | 0
35.4 | Procurement, design, manufacture, supply & delivery, dismantling, retrofitting, erection, commissioning and testing of gravimetric belt conveyor type coal feeders for unit no. 1 & 2. | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 6.68 | 0 | 0 | 0 | 6.77 | 6.77 |  |  | 6.77 | 0
35.5 | Procurement and Replacement of Air Preheater Baskets for Unit no. 1 to 4 (4x 210MW). | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 9.05 | 5.6335 | 5.6335 | 0 | 2.84 | 2.84 |  |  | 2.84 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 2.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR-17 | Various DPR Schemes for The work of maintaining the zero discharge condition of Pond No. 2 & Pond No.3 and providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 15.7443 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | The work of maintaining the zero discharge condition of Pond No.2 & Pond No.3 at KTPS Koradi | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 4.2068 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.2 | Providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 11.5375 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Scheme of HMI upgradation of unit 5 DCS along with Max Links , HART Scheme , PADO , all BOP PLCs , SWAS system, CO analyser & Coal feeder controller to match with the external aspect , process improvement & Up gradation of Generator Protections Relays in unit 1 to 4 of 210 MW at khaperkheda TPS | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 33.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.7 | Up-gradation of Generator Protections Relays in Unit 1 to 4 of 210 MW Khaperkheda TPS. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 8.31 | 0 | 0 | 0 | 4.43 | 4.43 |  |  | 4.43 | 0
0 | IDC | MERC/CAPEX/2024-2025/478 | - | 0.86 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Submitted to MERC, Yet to receive approval | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR on Refurbishment of Spare HPT Module Unit 1 & 2 at TM-I and Procurement of Complete Gear Box Assemblies of Coal Mills XRP 803 ½ HP & XRP 883 for Unit No. 1 to 4 (4x210 MW), Khaperkheda TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Refurbishment of spare HPT module Unit 1 & 2 at TM-I (4X210 MW), KHAPERKHEDA TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Procurement of Complete Gear Box Assemblies of Coal Mills XRP 883 for Unit-1 to 4 (210MW). | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | SUPPLY INSTALLATION TESTING & COMMISSIONING REVAMPING OF FIRE DETECTION & ALARM AND PROTECTION SYSTEM FROM FIRE AND PROVIDING RAPID EXTINGUISHING CLEAN AGENT (CA) SYSTEM AT UNIT -3,4 & 5 ATKPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Supply Installation Testing & Commissioning , Revamping of fire protection and providing rapid extinguishing clean agent (CA) system at unit # 3 ,4 210 MW TPS, KHAPERKHEDA | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Restoration of various Fire protection system at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Restoration of fire hydrant ring and fire water spray Header at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Restoration of deluge valve system at CHP-210MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | VARIOUS SCHEMES PROPOSED FOR IMPROVEMENT OF CHP-I (4 X 210 MW). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Design, Manufacturing, Supply, Erection, Commissioning & Testing of Coal Flow Management system for Coal Bunkers in CHP-I (4 X 210MW), Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Design, engineering, manufacturing, supply, installation and commissioning of Dedusting System for Crusher House and Bunker area in Unit 3 & 4 at CHP-I (4 X 210MW), Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Renovation including replacement of Power & Control cables with automation & upgradation of Stacker Reclaimer No. 1 in CHP-I (4 X 210MW), TPS Khaperkheda." | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Flue Gas Desulphrisation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | FGD installation of 210MW unit 1 & 2 at Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Upgradation of DDC/DCS system for UNIT 2 & 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Upgradation of DDC/DCS system for UNIT 2 & 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#1 to 4 Khaperkheda TPS & Upgradation of various governing Element for smooth operation for flexible operation of TG set at 40% technical minimum operation. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#1 to 4 Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 15 | 15 |  |  | 15 | 0
6.2 | Upgradation of various governing Element for smooth operation for flexible operation of TG set at 40% technical minimum operation. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Upgradation of Battery Charger , UPS system , GEHO PLC and VFD, ID VFD, supply of Efficiency Measuring Instruments and Supply, erection and commissioning of Sox, Nox , CO, Opacity, ETP and Oxygen Analyser for Unit 1 to 4 of 210 MW at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Supply of Efficiency Monitoring Instruments for performance optimization group (POG) at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.2 | Upgradation of 220 V, 24 V DC Float cum boost battery charger at Unit#1 to 4 Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.3 | Upgradation of 2X50 KVA UPS at Unit#1 to 4 Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.4 | Supply, Erection and Commissioning of Sox, Nox , CO, Opacity and ETP Analyser for Unit 1 to 4 of 210 MW at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.5 | Upgradation of GEHO PLC and VFD along with HCSD system Instrumentaion at Unit 3 & 4 Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.6 | Supply, Erection & Commissioning of Oxygen Analyzer for combustion optimization for Unit#1 to 5 Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.7 | Upgradation of VFD for ID FAN in Unit# 3 & 4, 210MW khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.8 | Scheme 8 Supply, erection & commissioning of PLC and SCADA System of Ash Evacuation and Disposal System for UNIT 3 and 4 Of 210 MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of LP Rotor for unit 1 and 2 , Supply and installation of air washer unit 1 and 2 and refurbishment of air washer unit for unit 3 and 4 and GEHO Pummp house control room. Supply and installation of diesel engine driven fire fighting pump with engine. Procurement of various control valves for unit No. 1 to 4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.1 | Supply and installation of Air washer unit in unit 1 and 2 , 6.6 KV breaker room, Turbine MCC room Battery room Boiler MCC room for cooling of all the Electrical Panels and AHP stage I Pump House control room air washer system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.2 | Refurbishment of Air washer unit of 3 and 4, 6.6 KV breaker room, Turbine MCC room Battery room Boiler MCC room for cooling of all the Electrical Panels and Refurbishment of GEHO pump House and AHP stage II Pump House control room air washer system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.3 | Procurement of Complete LPT rotor for unit 1 and 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.4 | Revamping of diesel engine driven fire fighting pump system with engine. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.5 | Procurement of various control valves for unit No. 1 to 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of IP Rotor and Inner casing for unit 1 and 2. Procurement of IP rotor and inner casing for unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.1 | Procurement of IP Rotor and Inner casing for unit 1 and 2. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.2 | Procurement of IP rotor and inner casing for unit 3 and 4 along with Turbovisory sensors and panel | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.3 | Supply and installation of srew compressor for supply of instrument air to unit No. 3 and 4 along with dryer for unit No. 3 & 4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of LP rotor for unit 3 and 4 and upgradation of BFP cartridge and BFP Booster pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.1 | Procurement of of LP rotor for unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.2 | Upgradation of BFP cartridge and BFP Booster pump, motorized scoop for hydraulic coupling and drive unit for BFP and modulating BFP RC valve for Unit 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Refurbishment of LP rotor of unit 1 and 2 and Refurbishment of HPT module of unit 1 and 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.1 | Refurbishment of LP rotor of unit 1 and 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.2 | Refurbishment of HPT module of unit 1 and 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Refurbishment of LP rotor for unit 3 and 4 and Refurbishment and re-blading of HPT module of unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.1 | Refurbishment of LP rotors for unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.2 | Refurbishment of HPT modules of unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | SITC OF COMPLETE SOLUTION AND COMPREHENSIVE PROTECTION AND MONITORING PACKAGE ALONG WITH RETROFIT OF ALLIED ACCESSORIES FOR VARIOUS GTs & STs INSTALLED AT 210 MW KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | SUPPLY,INSTALLATION, TESTING & COMMISSIONING OF COMPLETE SOLUTION AND COMPREHENSIVE PROTECTION AND MONITORING PACKAGE ALONG WITH RETROFIT OF ALLIED ACCESSORIES FOR VARIOUS GTs & STs INSTALLED AT 210 MW KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | PLANT PERFORMANCE IMPROVEMENT BY DESIGN, SUPPLY, INSTALLATION & COMMISSIONING OF STATE OF ART HT VACCUM CIRCUIT BREAERS AT UNIT 1 TO 4 OF 210MW KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.1 | DESIGN, SUPPLY, INSTALLATION, TESTING & COMMISSIONING OF HT VCB AT U # 1 & 2. | 0 | - | 0 | 0 | 0 | 0 | 15.14 | 15.14 |  |  | 15.14 | 0
14.2 | DESIGN, SUPPLY, INSTALLATION, TESTING & COMMISSIONING OF HT VCB AT U # 3 & 4. | 0 | - | 0 | 0 | 0 | 0 | 8.25 | 8.25 |  |  | 8.25 | 0
15 | DESIGN, SUPPLY, INSTALLATION, TESTING AND COMMISSIONING OF THE VARIOUS LIFTS IN PLACE OF THE EXISTING OLD LIFTS, LIGHTNING PROTECTION SYSTEM, EARTHING SYSTEM, AVIATION LIGHTING SYSTEM INSTALLED AT UNIT # 1 TO 4 OF 210 MW, KHAPERKHEDA TPS ON OEM BASIS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | DESIGN, SUPPLY, INSTALLATION, TESTING AND COMMISSIONING OF THE VARIOUS LIFTS IN PLACE OF THE EXISTING OLD LIFTS INSTALLED AT UNIT # 1 TO 4 OF 210 MW, KHAPERKHEDA TPS ON OEM BASIS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Design, Engineering, Supply, Erection, Testing & Commissioning of lightning protection system at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Design, Engineering, Supply, Erection, Testing & Commissioning of Earthing of electrical system & various buildings at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Design, Engineering, Supply, Erection, Testing & Commissioning of Aviation Lighting Syatem at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | SUPPLY OF SPARE GENERATOR ROTOR FOR U#3 &4, 210MW, TPS KHAPERKHEDA. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.1 | SUPPLY OF SPARE GENERATOR ROTOR FOR U#3 &4, 210MW, TPS KHAPERKHEDA. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | PROCUREMENT OF ENERGY EFFICIENT MOTORS FOR U # 1 TO 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.1 | PROCUREMENT OF ENERGY EFFICIENT MOTORS FOR U # 1 & 2 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.2 | PROCUREMENT OF ENERGY EFFICIENT MOTORS FOR U # 3 & 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.3 | Procurement of DC motors for U # 1 & 2 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.4 | Procurement of DC motors for U # 3 & 4 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | UPGRADATION OF EXISTING LT MCC PANEL WITH STATE OF ART LT MCC PANEL AT U # 1 TO 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | UPGRADATION OF EXISTING LT MCC PANEL WITH STATE OF ART LT MCC PANEL AT U # 1 & 2 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.2 | UPGRADATION OF EXISTING LT MCC PANEL WITH STATE OF ART LT MCC PANEL AT U # 3 & 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.3 | UPGRADATION OF HT BREAKER PANEL AT WAREGAON ASH BUND OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | UPGRADATION OF HT BREAKER PANEL AT OLD PROJECT OFFICE OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.5 | Retrofitting of Existing L & T make LT MCC ACB by state or art ACB at U # 1 to 4 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.6 | Retrofitting of Existing ABB make LT MCC ACB by state or art ACB at U # 1 to 4 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | ERECTION & COMMISIONING OF DRY TYPE CAST RESIN TRANSFORMERS FOR U # 1 TO 4 OF KHAPERKHEDA TPS & Design, Engineering, Supply, Erection, Testing & Commissioning of various Battery sets at Unit # 3 & 4 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | PROCUREMENT OF DRY TYPE CAST RESIN TRANSFORMERS FOR U # 1 & 2 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.2 | PROCUREMENT OF DRY TYPE CAST RESIN TRANSFORMERS FOR U # 3 & 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.3 | PROCUREMENT OF VFD TRANSFORMERS FOR ID FAN MOTOR U#3&4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.4 | Design, Engineering, Supply, Erection, Testing & Commissioning of various Battery sets at Unit # 3 & 4 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20 | Study, Supply & Refurbishment of HCSD systems, ESP operation, ambience & various pump, & PLC schemes for the improvement of AHP-I at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.1 | STUDY. DESIGN & REFURBISHMENT WORKS OF HIGH CONCENTRATION SLURRY DISPOSAL SYSTEM (HCSD SYSTEM) UNITS #3&4 AT AHP-1, TPS KHAPERKHEDA. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.2 | STUDY, DESIGN & REFURBISHMENT WORKS OF ARTs AND ASSOCIATED MOUNTINGS & ACCESSORIES OF HCSD SYSTEM FOR AHP-I, TPS KHAPERKHEDA.” | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.3 | ‘SUPPLY & REFURBISHMENT WORKS OF HCSD ASH SLURRY MIXER SYSTEM AT UNIT #3 &4 OF AHP-I, TPS KHAPERKHEDA’. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.4 | ‘STUDY, SUPPLY, RESTORATIONS & REPLACEMENT OF ALL INTERNAL SPARES OF D6 FIELD & RENOVATION OF D1 FIELD OF U3 DURING AOH FOR AHP-I, TPS KHAPERKHEDA’ | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.5 | PROCUREMENT OF VARIOUS PUMPS IN RECYCLE WATER SYSTEM IN ASH HANDLING PLANT 4X210 MW AT KHAPARKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Reliability improvement and complete replacement of ABC series with drive unit of ash slurry pipeline of 7 KM of 4*210MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Procurement and restoration of complete pipeline replacement of ABC series | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.2 | Procurement and restoration of complete drive unit replacement of ABC series | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | Procurement and restoration of complete Bottom ash hopper replacement including entire structure, Clinker grinder alongwith motor, Feed Gate, Power Cylinder and Pipelines discharge of U3&4 of 4*210MW Khaparkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.1 | Procurement and restoration of complete BAH replacement including entire structure and clinker griender | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.2 | Procurement and restoration of complete drive unit of clinker grinder for Unit 1 to 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.3 | Procurement and restoration of discharge pipeline of vertical sump pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Procurement and restoration of Pipeline garlanding at Waregaon ash Bund of 4*210 MW Khapakheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.1 | Pipeline garlanding at Waregaon ash Bund of 4*210 MW Khapakheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Upgradation, modification and erection of complete wet fly ash evacuation into dry fly ash evacuation systen for ESP 1 and 2 of 4*210 MW Khapakheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.1 | Upgradation, modification and erection of complete wet fly ash evacuation into dry fly ash evacuation systen for ESP 1 and 2, 4*210 MW Khapakheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | Reliability improvement and complete replacement of JKL series with drive unit of ash slurry pipeline of 7 KM of 4*210MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.1 | Procurement and restoration of complete pipeline replacement of JKL series | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.2 | Procurement and restoration of complete drive unit replacement of JKL series | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | Study, Supply and Refurbishment of HCSD System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.1 | Procurement of complete Suction and discharge valve of Geho pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.2 | Procurement of Subassemblies of Geho pump. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.3 | Upgradation and compressors of dry ash evacutaion system of U#3&4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.4 | Procuremenet of complete drive unit and VFD of GEHO pump. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | RENOVATION OF ESP FIELD INTERNALS FOR UNIT 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.1 | RENOVATION OF ESP FIELD INTERNALS FOR UNIT 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28 | R & M OF APH OF UNIT # 1& 2 (2 x 210MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28.1 | R & M OF APH OF UNIT # 1& 2 (2 x 210MW) OF KHAPERKHEDA TPS FROM MODEL: 27 VI 1850 TO 27 VI 2000 mm. DESIGN, ENGINEERING, SUPPLY, ERECTION & COMMISSIONING OF DOUBLE SEALING | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29 | DPR FOR ECONOMISER COILS AND APH GEAR BOX | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29.1 | PROCUREMENT AND REPLACEMENT OF COMPLETE SET OF ECONOMISER UPPER BANK & LOWER BANK COILS FOR KHAPERKHEDA TPS UNIT NO.3&4 | 0 | - | 0 | 0 | 0 | 0 | 11 | 11 |  |  | 11 | 0
29.2 | Procurement of APH gear box in unit no. 1 & 2 | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
29.3 | Procurement of APH speed reducer gear box in unit no. 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
30 | DPR FOR LTSH COILS , APH BASKETS & RH OUTLET STUB BENDS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.1 | Procurement of Air Pre-heater Baskets for unit no. 2 to 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.2 | Procurement of LTSH coils for unit no. 1 & 2 and Procurement of Reheater outlet header stub bends for unit no. 1 to 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.3 | Procurement of LTSH coils for unit no. 3 & 4 and Procurement of Reheater outlet header stub bends for unit no. 3 to 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31 | DPR FOR SUPPLY & REPLACMENT OF THERMAL INSULATION OF BOILER AND DUCT AT UNIT 1 TO 4 KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.1 | SUPPLY & REPLACMENT OF THERMAL INSULATION OF BOILER AND DUCT AT UNIT 1 TO 2KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.2 | SUPPLY & REPLACMENT OF THERMAL INSULATION OF BOILER AND DUCT AT UNIT 3 TO 4 KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32 | DPR FOR COAL CYCLE IMPROVEMENT IN UNIT NO.1 TO 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.1 | Procurement of Complete Journal Assembly for 803 ½ HP Coal Mills of Unit No. 1 To 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.2 | Procurement of Complete Journal Assembly for XRP 883 Coal Mills of Unit No. 3 To 4, | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.3 | Procurement of assembly of worm shaft & worm wheel with hub for unit no. 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.4 | PROCUREMENT OF COMPLETE GEAR BOX ASSEMBLIES OF COAL MILLS XRP 803 ½ HP FOR UNIT # 1 TO 2 AT KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.5 | PROCUREMENT OF COMPLETE GEAR BOX ASSEMBLIES OF COAL MILLS XRP 883 FOR UNIT # 3 TO 4 AT KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33 | DPR FOR PERFORMANCE IMPROVEMENT OF BOILER PA FAN, ID FAN AND FD FAN IN UNIT NO. 1 TO 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.1 | Procurement of PA fan Casings along with Dampers in Unit- 1 & 2, at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.2 | PROCUREMENT OF COMPLETE ROTOR ASSEMBLY ALONG WITH MOTOR FOR NDZV 31 SIDOR IN UNIT NO. 1 & 2 KHAPERKHEDA TPS (ID FAN) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.3 | PROCUREMENT OF FD FAN (BHEL AP 1-20 / 11) ASSEMBLY ALONG WITH DRIVE UNIT(MOTOR) FOR UNIT 1 & 2 AT KHAPERKHEDA TPS UNDER OEM NATURE ITEMS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.4 | PROCUREMENT OF FD FAN (BHEL AP 1-20 / 11) ASSEMBLY ALONG WITH DRIVE UNIT(MOTOR) FOR UNIT 3& 4 AT KHAPERKHEDA TPS UNDER OEM NATURE ITEMS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.5 | NDZV 33 SIDOR ID Fan Impeller Assembly for Unit 3 & 4 at TPS, Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.6 | Design, Engineering, Manufacturing, Supply & Commissioning including civil works for installation of 70 LPM lubricant ystems for PA Fans in unit no. 1&2. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.7 | Supply and installation of ID and PA foundation deck spring for unit no. 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34 | VARIOUS SCHEMES FOR BOILER PERFORMANCE IMPROVEMENT | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.1 | SUPPLY OF COAL MILL SEPERATOR & SCRAPPER BODIES FOR XRP-803 1/2 HP COAL MILLS IN UNIT 1 & 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.2 | MODIFICATION OF EXISTING COAL BUNKER AND COMMISSIONING OF BUNKER CHUTE ASSEMBLY WITH VIBRATING MOTOR TO AVOID BUNKER MOUTH COAL CHOKE UP FOR UNIT 1 & 2AT KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.3 | MODIFICATION OF EXISTING COAL BUNKER AND COMMISSIONING OF BUNKER CHUTE ASSEMBLY WITH VIBRATING MOTOR TO AVOID BUNKER MOUTH COAL CHOKE UP FOR UNIT 3 & 4 AT KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.4 | DESIGN, DEVELOPMENT, COMMISIONING OF SEAL AIR FAN ASSEMBLIES IN UNIT 1 & 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.5 | Procurement of sub body assembly of control valve in unit no. 1 & 2 actuating main gear unit part electrical actuator in unit no. 1 to 4 Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | Construction of A, B, C, D & E type stilt + 6 floor buildings at TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Construction of A, B, C, D & E type stilt + 6 floor buildings at TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36 | Enhancement & Renovation of existing building, Construction of Market building, Construction of club building community hall, Construction of school building, & Enhancement of existing domestic plant providing V wire 3 MLD at Colony TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.1 | Enhancement / Renovation & strengthening of existing building & allied works in colony TPS Khaperkhda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.2 | Construction of Market building including approach road, drainage arrangement & electrification at colony TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.3 | Construction of club building / community hall | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.4 | Construction of school building | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.5 | Enhancement of existing domestic plant providing V wire 3 MLD | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37 | Enhancement / Renovation of Saudamini Administrative Building, Construction of VIP Guest House, Construction of roads at Prakashnagar Colony and Providing various civil works related to coal transport railway lines of khaperkheda TPSTPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.1 | Enhancement / Renovation of Saudamini building | 0 | - | 0 | 0 | 0 | 0 | 7 | 7 |  |  | 7 | 0
37.2 | Construction of VIP guest house TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.3 | Construction of Roads | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.4 | Construction of office building & store for electrical maintenance & Civil at KPKD | 0 | - | 0 | 0 | 0 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
37.5 | Providing Special repair & retrofitting work of river bridge no.09 on Khaperkheda - Kalumna railway siding of TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
37.6 | Construction & repairing of drains & culverts along coal Transporting Railway lines & approach road of TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.7 | Repairing, providing & applying Epoxy Painting and Structural Steel Works to steel structural bridges on kpkd to Kaluma and kpkd to Saoner railway lines as per recommendation of structural stability report at TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.8 | Construction of compound wall KPKD Colony | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38 | Work of Strengthening and modification of Main Plant, construction of roads, strengthening of IDCT 1 to 4 in plant area, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.1 | Work of attending additional works based on structural report at Induced Draft Cooling Towers(IDCT) unit 1,2,3 & 4 at 4 x 210MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.2 | Work of constructon of roadside drains from VIP gate no.3 to IDCT No.1 at 4 x 210MW TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 3.61 | 3.61 |  |  | 3.61 | 0
38.3 | Construction of bituminous macadam road from Administrative Building to GCR Road near Service Building of 4X210MW TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 2.7 | 2.7 |  |  | 2.7 | 0
38.4 | Work for Construction of cement concrete road for equipment movement for salt lagoon (WTP-I), FGD(System), H2(cylinders) plant etc. inside plant premises in 4x 210MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 3.63 | 3.63 |  |  | 3.63 | 0
38.5 | Construction of cement concrete road outside BTG area of Power Plant 4 x 210MW TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.6 | Construction of cement concrete road for material transportation from D-Point CHP to reject coal Dumping yard in 4x 210MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 5.94 | 5.94 |  |  | 5.94 | 0
38.7 | Work of Strengthening and modification of Main Plant, Major Stores, Auxiliary in plant area, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.8 | Construction of diversion road along with RCC bridge from rejct coal yard CHP-I & CHP-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.9 | Upgradation of existing ETP plant consist civil works, electrification and pumps. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
39 | Work of 5th Raising of Waregaon Ash Bund, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
39.1 | Work of 5th Raising of Waregaon Ash Bund, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
40 | Work of CTR(Complete Track Removal),TTR(TRAIN TRAVLER REGULATOR) and Yard Remoulding incl. misc. works at Mahagenco Khaperkheda Plant. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
40.1 | Work of CTR(Complete Track Removal),TTR(TRAIN TRAVLER REGULATOR) and Yard Remoulding incl. misc. works at Mahagenco Khaperkheda Plant. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41 | Various WTP 210MW improvement schemes i.e. Up-gradation of SWAS SYSTEM UNIT- 1 to 4 at WTP-I 210 MW along with coal sampling lab upgradation, Comissioning of CW Chemical Dosing system etc | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.1 | Upgradation of Existing ETP system viz. Plate Settler, Settling tank, Sludge Drying bed, Chemical dosing system etc.)as per MPCB consent condition | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
41.2 | Upgradation of SWAS Lab 3& 4 at WTP-210 MW | 0 | - | 0 | 0 | 0 | 0 | 9 | 9 |  |  | 9 | 0
41.3 | Revamping of Chlorination Plant Stream (A+ B) & Installation, Comissioning of CW Chemical Dosing system (Viz. Scale inhibitor, Scale Dispersant, Biodispersant, Corossion Inhibitor & H2SO4 dosing) and Online CW Chemical parameter monitoring system at KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.4 | Upgradation of SWAS Lab 1& 2 at WTP-210 MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.5 | Upgradation of Water &Coal testing Lab at WTP-210 MW &Procurement of Coal Lab Instruments and upgradation of coal sampling Room & Instruments related to Coal sample Preparation. at WTP-210 MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42 | Work of capacity restoration of unloading stream from Beetle Charger No. 1 to Stacker/Reclaimer No. 1 for perfromance improvement of CHP-I (4 x 210 MW) & Capacity restoration of unloading stream from Beetle Charger No. 1 to Stacker/Reclaimer No. 1 for perfromance improvement of CHP-I (4 x 210 MW). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.1 | Revamping/ refurbishment, capacity restoration and upgradation for beetle charger No. 1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.2 | Revamping/ refurbishment, capacity restoration and upgradation for Wagon Tippler No. 1 | 0 | - | 0 | 0 | 0 | 0 | 6 | 6 |  |  | 6 | 0
42.3 | Revamping/ refurbishment, capacity restoration and upgradation for Apron Feeder No. 1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.4 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 2C, 3A, 4A, 8A, 9 | 0 | - | 0 | 0 | 0 | 0 | 25 | 25 |  |  | 25 | 0
42.5 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for impact crusher and wobbler feeder No. 1 & 3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.6 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Stacker/Reclaimer No. 1. | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
42.7 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv. 3C to 3A, Conv. 3A to 4A, Conv. 4A to 8A and Conv. 9 by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.8 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of beetle Charger, wagon tippler, apron feeder, covneyors (Conv. 2C, 3A, 4A, 8A, 9), crushers/ wobbler feeder No. 1 & 3 and Stacker/Reclaimer No. 1 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
43 | DPR fo Capacity restoration of bunkering stream from Conv. 5A to 7A/B/C/D including shuttle conveyors in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
43.1 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 5A, 6B, 7A, 7B, 7C, 7D and Shuttle Conv. 1 to 4 in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 25 | 25 |  |  | 25 | 0
43.2 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv.Conv. 4D to 5A/B , 5A to 6B, Conv. 6B to 7A & 7B, Conv. 7B to 7D upto shuttle conveyor, Conv. 7A to 7C upto shuttle conveyor by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
43.3 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of covneyors (Conv. 5A, 6B, 7A/B/C/D & Shuttle Conv. 1 to 4 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
44 | Work of capacity restoration of unloading stream from Beetle Charger No. 2 to Stacker/Reclaimer No. 2 for perfromance improvement of CHP-I (4 x 210 MW). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.1 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for beetle charger No. 2 | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
44.2 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Wagon Tippler No. 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.3 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Apron Feeder No. 2 | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
44.4 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 2D, 3B, 4B, 8B, 10 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.5 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for impact crusher and wobbler feeder No. 2 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.6 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Stacker/Reclaimer No. 2. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.7 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv. 2D to 3B, Conv. 3B to 4B, Conv. 4B to 8B and Conv. 10 by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.8 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of beetle Charger, wagon tippler, apron feeder, covneyors (Conv. 2D, 3B, 4B, 8B, 10), crushers/ wobbler feeder No. 2 & 4 and Stacker/Reclaimer No. 2 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45 | Work of capacity restoration of bunkering stream from Conv. 1A/B, 2A/B, 5B to 7E/F/G/H including shuttle conveyors in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.1 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 1A/B, 2A/B, 5B, 6A, 7E, 7F, 7G, 7H and Shuttle Conv. 5 to 8 in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 30 | 30 |  |  | 30 | 0
45.2 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv. 1A/b to 2A/B,Conv. 4C to 5A/B, Conv. 5B to 6A, Conv. 6A to 7E & 7F, Conv. 7E to 7G upto shuttle conveyor, Conv. 7F to 7H upto shuttle conveyor by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.3 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of conveyor system from Conv. 1A/B, 2A/B, 5B, 6A, 7E, 7F, 7G, 7H and Shuttle Conv. 5 to 8 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 20 | 20 |  |  | 20 | 0
45.4 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Paddel Feeder No. 1 to 4 and truck hopper in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46 | Renovation and upgradation of various electrical system for CHP-I (4 x 210 MW) improvement & Renovation and upgradation of various electrical system for CHP-I (4 x 210 MW) improvement. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.1 | Design, development and upgradation with circuit breaker VFD of various LT MCC of CHP-I. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.2 | Design, Supply, Installation, Commissioning and Testing of Energy Chain System for Paddle Feeder, Shuttle Conveyor and Stacker/Reclaimers in CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
46.3 | Upgradation of relay logic system with PLC & SCADA in CHP-I control room and Wagon Tipplers in CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.4 | Complete upgradation of conveyor lighting system with energey efficient LED lights for CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 8 | 8 |  |  | 8 | 0
46.5 | Providing, installation, testing commissioning, maintenance and operation of explosion proof & weather proof surveillance system at CHP-I (4 X 210 MW), TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.6 | Complete revamping/refurbishment, upgradation and modification of various EOT cranes & hoist installed at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47 | Procurement of various capacity SAN make locomotives and BEML make loader & bulldozer for CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.1 | Procurement of various capacity SAN make locomotives and BEML make loader & bulldozer for CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 25 | 25 |  |  | 25 | 0
48 | CHP Improvement Schemesfor 4x 210 MW units | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.1 | Design, manufacture, supply and installation of suspended magnet for bunkering belts at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.2 | Design, manufacture, supply and installation of travel drive system for shuttle conveyors and conveyors at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.3 | Renovation including replacement of Power & Control cables with automation & upgradation of Stacker Reclaimer No. 2 in CHP-I (4 X 210MW), TPS Khaperkheda." | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.4 | Complete reconditionding & upgradation of LT MCC installed at Unit No. 3 & 4 bunker auxiliareis in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.5 | Complete reconditionding & upgradation of outdoor lighting system in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.6 | Complete reconditionding & upgradation of HT breaker, control circuits & protection relays in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.7 | Complete revamping/refurbishment, upgradation and modification of various monorail hoists & winch machine installed at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.8 | Procurement of hydra 14 Ton above capacity and heavy vehicles for CHP- I & II. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
49 | Installation of Real Time Coal Analyzer at all TPS of Mahagenco | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
49.1 | Installation of Real time Coal Analyzer at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50 | Railway expenses for refurbishment of OHE lines at CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50.1 | Railway expenses for refurbishment of OHE lines at CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | PROCUREMENT COMPLETE Gear BOX ASSEMBLIES FOR 803 1/2 HP & XRP 883 COAL MILLS OF UNIT NO. 1& 2 AT KHAPERKHEDA TPS. | N.A. | - | 0 | 4.5548 | 4.5548 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply Erection and commissioning of Oil Cooled Suspended magnets at Conv 6A & 6B at Khaperkheda TPS. | N.A. | - | 0 | 1.1484 | 1.1484 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurment of new 02 Ambulance Van & 2 Truck for KPKD TPS(Asset Nos. 170100512, 170100513, 170100514, 170100515) | N.A. | - | 0 | 0.41055 | 0.41055 | 0 | 0 | 0 |  |  | 0 | 0
4 | GEHO PUMP (Valve housing assembly) | N.A. | - | 0 | 8.7933 | 8.7933 | 0 | 0 | 0 |  |  | 0 | 0
5 | RESTORATION OF AHP OUTLET TO ESP INLET DUCTS U#1&2(Unit #2 Part only) | N.A. | - | 0 | 7.0042 | 7.0042 | 0 | 0 | 0 |  |  | 0 | 0
6 | ABC powder type and foam type composite Fire Extinguisher | N.A. | - | 0 | 0.714 | 0.714 | 0 | 0 | 0 |  |  | 0 | 0
7 | FFEQUIP HYDRAULIC JACK (BM-I) | N.A. | - | 0 | 0.57696 | 0.57696 | 0 | 0 | 0 |  |  | 0 | 0
8 | MOBILE COAL SAMPLING EQUIP-AUGER (FMC) CHP-I | N.A. | - | 0 | 1.5824 | 1.5824 | 0 | 0 | 0 |  |  | 0 | 0
9 | Replacement of ash slurry disposal pump to improve performance & capacity enhancement of ash slurry disposal system at AHP-1 Khaperkheda TPS | 0 | - | 0 | 4.92 | 4.92 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of Pillow Block Dodge Bearing Assemblies (Expansion & Non-Expansion) for PA fans in Unit- n1 to 4, at Khaperkheda TPS | 0 | - | 0 | 5.11 | 5.11 | 0 | 0 | 0 |  |  | 0 | 0
11 | Replacement of Economizer outlet to APH outlet common duct in unit no. 3 (210MW), Khaperkheda TPS | 0 | - | 0 | 6.24 | 6.24 | 0 | 0 | 0 |  |  | 0 | 0
12 | PROCUREMENT OF OIL COOLED SUSPENSION MAGNET FOR 210MW AND MODIFICATION & REPLACEMENT OF VIBRATING FEEDER WITH VIBRATING TRANSFER CHUTE FOR 210MW | 0 | - | 0 | 3.09 | 3.09 | 0 | 0 | 0 |  |  | 0 | 0
13 | DESIGN,ENGINEERING,MODIFICATION ,ERECTION AND COMMISSIONING OF DRIVE UNIT ARRANGEMENT FOR CONVEYOR 10 AT CHP1 | 0 | - | 0 | 1.65 | 1.65 | 0 | 0 | 0 |  |  | 0 | 0
14 | ENERGY EFFICIENT PLANT LIGHTING AND COLONY LIGHTING MODIFICATIONS | 0 | - | 0 | 21.04 | 21.04 | 0 | 0 | 0 |  |  | 0 | 0
15 | Supply installation testing and commisioning of various battery sets at unit No 1 & 2 of Khaperkheda TPS | 0 | - | 0 | 9.31 | 9.31 | 0 | 0 | 0 |  |  | 0 | 0
16 | Revamping and modification of existing alarm and protection system from fire and provide rapid extinguishing Clean Agent (CA) system at Unit #1 & 2 (210 MW) units, KPKD TPS | 0 | - | 0 | 8.21 | 8.21 | 0 | 0 | 0 |  |  | 0 | 0
17 | Supply of electronic modules for Procontrol DCS system in unit 1 to 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 1.18 | 1.18 | 0 | 0 | 0 |  |  | 0 | 0
18 | Revamping & UPGRADATION of SWAS system in unit 3 & 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 8.56 | 8.56 | 0 | 0 | 0 |  |  | 0 | 0
19 | Upgradation of process instrumentation in unit 1 to 2 of 210 MW Khaperkheda TPS | 0 | - | 0 | 4.64 | 4.64 | 0 | 0 | 0 |  |  | 0 | 0
20 | Replacement of flue gas duct from air heater outlet to esp inlet for U 1 & 2 (S+W) | 0 | - | 0 | 0 | 0 | 0 | 8.03 | 8.03 |  |  | 8.03 | 0
21 | PROCUREMENT OF COMPLETE ROTOR ASSEMBLY FOR NDZV 31 SIDOR IN UNIT NO. 1 & 2 KHAPERKHEDA TPS (ID FAN). | 0 | - | 0 | 0 | 0 | 0 | 14.52 | 14.52 |  |  | 14.52 | 0
22 | UPGRADATION OF BELT CONVEYOR CAPACITY OF 2C &2D AND 8A & 8B AT CHP1 | 0 | - | 0 | 0 | 0 | 0 | 3.94 | 3.94 |  |  | 3.94 | 0
23 | WORK OF DESIGN,ENGINEERING,ERECTION AND UPGRADATION OF DRIVE UNITS OF BELT CONVEYOR 3A & 3BAT CHP1 | 0 | - | 0 | 0 | 0 | 0 | 8.34 | 8.34 |  |  | 8.34 | 0
24 | Procurement of 1500 KW ID Fan Synchronous Motor at Unit 3 & 4 Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 3.12 | 3.12 |  |  | 3.12 | 0
25 | Procurement of Steam and Water Analysis System(SWAS) for Unit 1&2 (210MW) KPKD TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 9.65 | 9.65 |  |  | 9.65 | 0
26 | Supply and replacement of complete PVC fills of cell of cooling tower of unit 1-4 (210 MW) at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 8.52 | 8.52 |  |  | 8.52 | 0
27 | PROCUREMENT OF FD FAN (BHEL AP 1-20/11) ASSEMBLY FOR UNIT 1 TO 4 ATKHAPERKHEDA TPS. | 0 | - | 0 | 4.37 | 4.37 | 0 | 0 | 0 |  |  | 0 | 0
28 | CHP performance improvement scheme for capacity restoration of drive units installed at CHP-1 (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 14.5 | 14.5 | 0 | 0 | 0 |  |  | 0 | 0
29 | Work of Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of belt conveyor 8A & 8B and belt conveyor 2C & 2D at CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 2.15 | 2.15 | 0 | 0 | 0 |  |  | 0 | 0
30 | WORK OF DESING,SUPPLY ,ERECTION,COMMISSIONG AND UPGRADATION OF COMPLETE ELECTRICAL SYSTEM FOR DRIVE UNITS OF BELT CONVEYOR 3A & 3B AND BELT CONVEYOR 4A,4B,4C & 4D AT CHP1 Khaperkheda TPS. | 0 | - | 0 | 2.29 | 2.29 | 0 | 0 | 0 |  |  | 0 | 0
31 | Supply, Installation, & Commissioning of Instruments at coal Testing Lab, WTP-I, TPS Khaperkheda. | 0 | - | 0 | 0.45 | 0.45 | 0 | 0 | 0 |  |  | 0 | 0
32 | Supply, Installation & Commissioning and Refurbishment of asbestos based H2 Generator and compressor to convert it to non-asbestos based H2 Generator for Unit 1 to 5, Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 7.65 | 7.65 |  |  | 7.65 | 0
33 | construction of bituminous macadam roads at Prakashnagar Colony TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 5.4 | 5.4 |  |  | 5.4 | 0
34 | Work of attending additional works based on structural report at Induced Draft Cooling Towers (IDCT) unit 1,2,3 & 4 at 4 x 210MW, TPS, Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 1.21 | 1.21 |  |  | 1.21 | 0
35 | VIBRATION ANALYSER | 0 | - | 0 | 0 | 0 | 0 | 0.5 | 0.5 |  |  | 0.5 | 0
36 | Upgradation of GEHO pump instrumentation for AHP Unit No. 3 & 4 (210 MW) at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 1.27 | 1.27 |  |  | 1.27 | 0
37 | Refurbishment of HPT module for Unit 1 & 2 | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
38 | General Asset Furniture | N.A. | - | 0 | 0.86177 | 0.86177 | 0 | 0 | 0 |  |  | 0 | 0
39 | General Asset AC, Fans, Air coolers, water filter etc. | N.A. | - | 0 | 0.53608 | 0.41552 | 0.12056 | 0 | 0 |  |  | 0 | 0.12056
40 | General Asset Computer, scanners, etc. | N.A. | - | 0 | 2.5598 | 1.9461 | 0.61367 | 0 | 0 |  |  | 0 | 0.61367
41 | Land aquired for rly siding | N.A. | - | 0 | 0.4072 | 0.4072 | 0 | 0 | 0 |  |  | 0 | 0
42 | RCC ROAD FROM ASH SILO TO 'D' POINT FOR BULKER MO | N.A. | - | 0 | 0.95225 | 0.95225 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 1201.0636 | 1021.4998 | 179.5638 | 397.1133 | 626.4118 | 0 | 0 | 626.4118 | -49.7348
FY 2026-27
a) DPR Schemes
(i) Submitted to MERC
| Combustion optimization system | [6 empty] | 0 | 0
1 | Dynamic coal flow measurement and control (balancing) system (one) | [6 empty] | 0 | 0
1.2 | CO analyser (8 units) | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 | 1.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Oxygen analyser (32 units) | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 | 0.783 | 0.75683 | 0.75683 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Spare HPT module for Khaparkheda Unit 1 & 2 | MERC/CAP/DPR/10/2010-11/1466 | 2010-10-26 | 26.459 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | HPT module 1 No (unit # 1) | MERC/CAP/DPR/10/2010-11/1466 | 2010-10-26 | 23.0379 | 23.9074 | 23.9074 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAP/DPR/10/2010-11/1466 | 2010-10-26 | 3.4211 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Economiser Upper Bank & Lower Bank coils for Khaperkheda Unit no. 3 and Unit no. 4 | MERC/CAP/DPR/10/2010-11/1695 | 2010-12-15 | 26.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Economiser Upper Bank & Lower Bank coils for Khaperkheda Unit no. 3 and Unit no. 4 | MERC/CAP/DPR/10/2010-11/1695 | 2010-12-15 | 26.35 | 11.77 | 11.77 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Economiser & LTSH Upper Bank & Lower Bank coils for Khaperkheda Unit no. 1 and Unit no. 2 | MERC/CAPEX/20112012/01155 | 2011-07-29 | 34.7916 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Economiser & LTSH Coil for Unit 1 | MERC/CAPEX/20112012/01155 | 2011-07-29 | 15.6924 | 15.6924 | 15.6924 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Economiser & LTSH Coil for Unit 2 | MERC/CAPEX/20112012/01155 | 2011-07-29 | 16.1528 | 16.1528 | 16.1528 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20112012/01155 | 2011-07-29 | 2.9464 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Procurement & Replacement of Re-heater Rear Pendant Assembly Coils for 2*210MW Khaperkheda Unit no. 1 and Unit no. 2 | MERC/CAPEX/20122013/00603 | 2012-06-18 | 10.3738 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Re-heater coils for unit no. 1 | MERC/CAPEX/20122013/00603 | 2012-06-18 | 5.1267 | 5.1267 | 5.1267 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Re-heater coils for unit no. 2 | MERC/CAPEX/20122013/00603 | 2012-06-18 | 5.1267 | 5.55 | 5.55 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/00603 | 2012-06-18 | 0.1204 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Procurement of HPT module suitable for khaperkheda TPS Unit 3 & 4 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 36.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Procurement of HPT module suitable for khaperkheda TPS Unit 3 & 4 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 36.2 | 32.4016 | 32.4016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7 | Procurement Spare GTR, Locomotive & Compactors | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 18.4521 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | 250 MVA Spare GTR | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 10.3496 | 11.2511 | 11.2511 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.2 | Procurement of Locomotive 2no’s. | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 5.9927 | 5.9927 | 5.9927 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.3 | Procurement of Compactors 2 no’s. | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 0.42979 | 0.4298 | 0.4298 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 1.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Procurement & Replacement of complete set of LTSH coils for Khaperkheda TPS Unit 3&4 | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 17.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement and replacement of LTSH coils for Khaperkheda TPS at U3 | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 8.58 | 3.4291 | 3.4291 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Procurement and replacement of LTSH coils for Khaperkheda TPS at U4 | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 8.58 | 3.1809 | 3.1809 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 0.65 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Development of Ash Bund (Waregaon) at K'kheda TPS | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 38.7459 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Construction of 3rd upstream raising of existing ash bund from TBL 299.50 Mtr to 302.50 Mtr at Waregaon, Khaperkheda TPS. | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 33.8585 | 32.5375 | 32.5375 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.2 | Construction of masonary dam (Gabion structure) at Waregaon TPS, Khaperkheda. | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 1.0561 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.3 | Construction of approach to drain wells and raising height of drain well no. 1,2 & 3 ash bund at Waregaon, Khaperkheda TPS | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 0.48488 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 3.3464 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Various schemes related to CHP Improvement & Performance Optimization and scheme of conversion of existing Composite OHE to Conventional OHE | MERC/CAPEX/20152016/00422 | 2016-08-03 | 10.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Air Cooled Suspension Magnet for Con. 3 & 6 of CHP 210 MW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 2.18 | 2.2613 | 2.2613 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | Procurement of Impact crusher motor | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.84 | 0.52579 | 0.52579 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.3 | Procurement of 360V, 200 AH battery set and 360V 325 AH battery set for U# 1to 4 | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.1 | 1.4576 | 1.4576 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.4 | Procurement of POG Instruments for Unit 1 to 4 | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.77 | 0.35015 | 0.35015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.5 | Up gradation of safe scan flame scanner system by BHEL scan system in unit no. 1, 3 & 4 | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.6 | Up gradation of old AVR system to DAVR | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.7 | Conversion of existing Composite OHE to Conventional OHE | MERC/CAPEX/20152016/00422 | 2016-08-03 | 2.72 | 2.72 | 2.72 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.47 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | ESP up-gradation for Unit-1 at Khaperkheda TPS | MERC/CAPEX/20152016/01261 | 2016-01-11 | 32.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | ESP up-gradation for Unit-1 at Khaperkheda TPS | MERC/CAPEX/20152016/01261 | 2016-01-11 | 32.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Procurement, installation and commissioning of Gravimetric Belt / Rotary Type Feeder, VFD for CEP, Up-gradation of BTS system & Environmental schemes at Khaperkheda TPS | MERC/CAPEX/20162017/01552 | 2017-02-14 | 20.218 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Procurement, installation and commissioning of Gravimetric belt/rotary Feeder at U-1 & 2 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 5.72 | 4.7418 | 4.7418 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Installation of VFD to CEP at U-1 to 4 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 8.64 | 9.1408 | 9.14 | 0.000792 | 0 | 0 |  |  | 0 | 0.000792 | 0 | 0
13.3 | Installation of BTS system at U-4 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 0.98796 | 0.98796 | 0.98796 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.4 | Replacement of SOx/NOx analyzer at U-1 to 4 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 2.42 | 2.3035 | 2.3035 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.5 | Procurement of TGA,CHNS analyzer and Bomb calorimeter at U-5 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 1.71 | 0.2897 | 0.2897 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01552 | 2017-02-14 | 0.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Up gradation of HMI System at Unit No 3 & 4 at Khaperkheda TPS | MERC/CAPEX/20172018/03946 | 2017-07-19 | 13.39 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | HMI Up-gradation at U# 3 & 4 | MERC/CAPEX/20172018/03946 | 2017-07-19 | 12.78 | 12.5611 | 13.1811 | -0.62 | 0 | 0 |  |  | 0 | -0.62 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/03946 | 2017-07-19 | 0.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21 | Procurement of APH Basket for unit # 1 to 5 and Up-gradation of HT Motor Protection Relay in Unit # 1 to 4 at Khaperkheda TPS | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 9.77 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.1 | Procurement of assembly of baskets for air preheater of type bisector APH 27 VI: 1850, 12 sector in unit no. 1 & 2 and bisector APH 27 VI: 2000; 24 sector in unit no. 3 & 4 (210MW x 4) at TPS, Khaperkheda | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 5.71 | 8.097 | 8.0941 | 0.002845 | 0 | 0 |  |  | 0 | 0.002845 | 0 | 0
21.3 | Up-gradation of H.T. Motor protection relays in Unit 1 to 4 (210MW), Khaperkheda TPS | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 3.96 | 3.2537 | 3.2537 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 0.1 | 0 | 0.18424 | -0.18424 | 0 | 0 |  |  | 0 | -0.18424 | 0 | 0
22 | Procurement of LPT rotor suitable for Unit # 3 & 4 of 210 MW at Khaperkheda TPS | MERC/CAPEX/2018-2019/132 | 2019-05-09 | 27.191 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.1 | Procurement of LPT rotor suitable for Unit # 3 & 4 of 210 MW at Khaperkheda TPS | MERC/CAPEX/2018-2019/132 | 2019-05-09 | 26.491 | 10.7515 | 10.7515 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2018-2019/132 | 2019-05-09 | 0.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23 | Supply, Erection & commissioning of HT Vacuum circuit Breakers & SF6 contactors at AHP (U#1-4) & CHP (U#1 to 5) and 160 KW VFD Panel with Motor for fire-fighting pumps at U#1 to 4 at Khaperkheda TPS | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 10.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.1 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at AHP (Unit#1 to 4, 210MW), Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 4.17 | 3.4843 | 4.8883 | -1.404 | 0 | 0 |  |  | 0 | -1.404 | 0 | 0
23.2 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at CHP (Unit#1 to 4, 210MW) and CHP (Unit#5, 500MW) Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 3.81 | 4.031 | 2.7332 | 1.2978 | 0 | 0 |  |  | 0 | 1.2978 | 0 | 0
23.3 | Supply, Erection & commissioning of 150 KW VFD Panel with motor for fire-fighting pumps at 210 MW Khaperkheda TPS. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 2.34 | 2.0957 | 2.0957 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 0.58 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24 | Augmentation of Waregaon Ash Water Recovery System at TPS Khaperkheda | MERC/CAPEX/2019-20/732 | 2019-09-16 | 17.1984 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.1 | Augmentation of Waregaon Ash Water Recovery System at TPS Khaperkheda | MERC/CAPEX/2019-20/732 | 2019-09-16 | 15.7884 | 15.1987 | 15.1987 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-20/732 | 2019-09-16 | 1.41 | 0.58812 | 0.58812 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25 | Procurement of VFD with HMI & Controller & Replacing with existing Eddy-current drives of Coal feeders at U# 3 & 4 and Procurement of Various Critical Components of GEHO Pump (Model-TZPM 800) for AHP-1 at Khaperkheda TPS | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 10.6535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25.1 | Up-gradation of Existing BHEL make 36” Gravimetric Coal Feeders control panel with HMI and croprocessor based Controller with VFD, Motor & Weigh Module at Unit 3 & 4, (210MW) | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 7.4655 | 7.7 | 7.7 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25.2 | Procurement of various Critical Components of GEHO Pump (Model-TZPM 800) for AHP-1 (210MW) | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 2.698 | 2.6466 | 2.6466 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 0.49 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26 | Procurement, Replacement of Eco Coils U#1&2 210 MW, & Procurement & replacement of foundation Deck Spring assembly for coal mills U#3,4 at Khaperkheda TPS | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 15.4086 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26.1 | Procurement, Replacement of Eco Coils U#1&2 | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 7.4996 | 6.6503 | 6.6503 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26.2 | Procurement & replacement of foundation Deck Spring assembly for coal mills U#3,4 | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 6.679 | 7.0955 | 7.1 | -0.004476 | 0 | 0 |  |  | 0 | -0.004476 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 1.23 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28 | ESP Upgradation of 5 Nos. of 210/500MW Units at Khaperkheda, Koradi & Chandrapur TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 90.3535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.1 | ESP Upgradation at Unit #1, Khaperkheda TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 42.7114 | 59.55 | 54.445 | 5.105 | 0 | 0 |  |  | 0 | 5.105 | 0 | 0
28.2 | ESP Upgradation at Unit #2, Khaperkheda TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 42.7114 | 59.55 | 54.445 | 5.105 | 0 | 0 |  |  | 0 | 5.105 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 4.9307 | 0 | 16 | -16 | 0 | 0 |  |  | 0 | -16 | 0 | 0
29 | Flue Gas Desulphurisation System for Khaperkheda Unit # 1-4 | MERC/CAPEX/2021-2022/MSPGCL/097 | 2022-03-14 | 113.4565 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.1 | FGD System for Khaperkheda Unit # 1-4 | MERC/CAPEX/2021-2022/MSPGCL/097 | 2022-03-14 | 109.15 | 255.58 | 130.03 | 125.55 | 0 | 0 |  |  | 0 | 125.55 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/097 | 2022-03-14 | 4.3065 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4 | Construction of coal platform for Chandrapur TPS, Khaperkheda TPS & Parli TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 5.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4.2 | Khaperkheda TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 5.43 | 3.9936 | 3.9936 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 4.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.4a | 1. Procurement of 6.6 KV,300 KW, P.A.fan motor for U# 1 & 2 2. Procurement of 6.6 KV,425 KW,CM motor for U # 3 & 4 3. Procurement of 6.6 KV,1400KW,CW pump motor for U-1& 2 4. Procurement of 6.6 KV,1400 KW,CW pump motor for U-3&4 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 3.82 | 2.5973 | 2.5973 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.4b | K'kheda: Procurement of HT Motors(GS/HP Water pump)for U-1&2 and Procurement of HT Motors (ACW)for U-3&4 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 1 | 0.4 | 0.4 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.2 | KHAPERKHEDA (U-1 to 4) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.96 | 3.1173 | 3.1173 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.2 | Khaperkheda TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender for KPKD 1-4 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 1.7765 | 1.7765 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.2 | Normal Multipurpose Fire Tender KPKD 1-4 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 2.1847 | 2.1847 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 226.3024 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9.1 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 226.3024 | 291.23 | 331.4177 | -40.1877 | 0 | 0 |  |  | 0 | -40.1877 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 4.4604 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.2a | Compond wall (IB recommdation),Plant Patrolling Roads (IB recommdation) TPS KPKD | MERC/CAPEX/20172018/0177 | 2018-02-06 | 4.4604 | 3.9506 | 3.9506 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 9.23 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11.1 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 9.05 | 13.3057 | 13.3057 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 0.18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15 | Implementation of Water Flow Monitoring system at Chandrapur STPS & Khaperkheda TPS | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 5.1755 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.3 | Electromagnetic Flow meters at various lines & Locations of 210 MW | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 3.8515 | 3.8515 | 3.8515 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.4 | Automation: Centralized SCADA, RTU, MODBUS Cable, Power cable & mandatory spares | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 1.324 | 1.324 | 1.324 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30 | Supply of spare Generator Rotor for UNIT 1 & 2, 210MW | MERC/CAPEX/2023-24/0184 | 2024-03-12 | 37.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.1 | Supply of spare Generator Rotor for UNIT 1 & 2, 210MW | MERC/CAPEX/2023-24/0184 | 2024-03-12 | 36.7 | 36.7 | 36.7 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2023-24/0184 | 2024-03-12 | 0.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M with raising of drain wells and modification of Masonary Dam (Waste Weir), 4 x210 MW, TPS, Khaperkheda | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 45.0535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.1 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M at TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 31.0231 | 31.22 | 31.22 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.2 | Raising of drain wells of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 1.6569 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.3 | Modification of Masonary Dam (Waste Weir) of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 10.1857 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 2.1878 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
32 | Flue Gas Desulphurisation (FGD) System for Khaperkheda Unit # 1 & 2 | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 115.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
32.1 | Flue Gas Desulphurisation (FGD) System for Khaperkheda Unit # 1 & 2 | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 109.8 | 0 | 129.13 | -129.13 | 0 | 0 |  |  | 0 | -129.13
0 | IDC | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 5.54 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33 | Upgradation of DDC/DCS system for UNIT 1 & 3 of 210 MWKhaperkheda TPS | MERC/CAPEX/MSPGCL/2023-24/601 | 2023-11-10 | 39.14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.1 | Upgradation of DDC/DCS system for UNIT 1 & 3 of 210 MWKhaperkheda TPS | MERC/CAPEX/MSPGCL/2023-24/601 | 2023-11-10 | 38.7 | 19.57 | 19.57 | 0 | 19.57 | 19.57 |  |  | 19.57 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/601 | 2023-11-10 | 0.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34 | Supply & commissioning of interconnection conveyor belt, Elecon make complete impact type crusher, Procurement of 4 NOs. Bull Dozer BEML BD-155 and Eco friendly and power efficient chiller system at Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 28.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.1 | Design, engineering, manufacturing, supply, erection & commissioning of interconnection conveyor belt from 1 X 500MW to 4 X 210MW stack yard at CHP Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.2 | Supply & installation of Elecon–make complete impact type crusher at CHP-I, Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 4.29 | 4.15 | 4.15 | 0 | 0 | 0 |  |  | 0 | 0
34.3 | Procurement of 4 NOs. Bull Dozer BEML BD-155 at CHP, Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.255 | 12.0596 | 12.0596 | 0 | 0 | 0 |  |  | 0 | 0
34.4 | Supply, erection, & commissioning of Eco friendly and power efficient chiller system for khaperkheda TPS Unit 1 to 4, Service Building and WTP in place of present reciprocating type Chiller system | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 11.96 | 11.45 | 11.45 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 1.385 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | 5 Nos. of Boiler Improvement Schemes for Unit No. 1 to 4 | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 32.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Procurement & replacement of Re-Heater Rear Pendent Assembly Coils for unit no. 3 & 4 (210 MW) | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 8.86 | 4.68 | 4.68 | 0 | 4.68 | 4.68 |  |  | 4.68 | 0
35.2 | Procurement Complete Set of Sky Climber For Unit#1 To 5 Boilers. | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 3.32 | 2.43 | 2.43 | 0 | 0 | 0 |  |  | 0 | 0
35.3 | Replacement of glasswool insulation and GI/CORRUGATED sheets of boiler and hot air ducts at unit 1to 4 KHAPERKHEDA TPS | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 2.19 | 1.99 | 1.99 | 0 | 0 | 0 |  |  | 0 | 0
35.4 | Procurement, design, manufacture, supply & delivery, dismantling, retrofitting, erection, commissioning and testing of gravimetric belt conveyor type coal feeders for unit no. 1 & 2. | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 6.68 | 6.77 | 6.77 | 0 | 0 | 0 |  |  | 0 | 0
35.5 | Procurement and Replacement of Air Preheater Baskets for Unit no. 1 to 4 (4x 210MW). | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 9.05 | 8.4735 | 8.4735 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 2.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR-17 | Various DPR Schemes for The work of maintaining the zero discharge condition of Pond No. 2 & Pond No.3 and providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 15.7443 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | The work of maintaining the zero discharge condition of Pond No.2 & Pond No.3 at KTPS Koradi | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 4.2068 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.2 | Providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 11.5375 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Scheme of HMI upgradation of unit 5 DCS along with Max Links , HART Scheme , PADO , all BOP PLCs , SWAS system, CO analyser & Coal feeder controller to match with the external aspect , process improvement & Up gradation of Generator Protections Relays in unit 1 to 4 of 210 MW at khaperkheda TPS | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 33.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.7 | Up-gradation of Generator Protections Relays in Unit 1 to 4 of 210 MW Khaperkheda TPS. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 8.31 | 4.43 | 4.43 | 0 | 4.43 | 4.43 |  |  | 4.43 | 0
0 | IDC | MERC/CAPEX/2024-2025/478 | - | 0.86 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Submitted to MERC, Yet to receive approval | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR on Refurbishment of Spare HPT Module Unit 1 & 2 at TM-I and Procurement of Complete Gear Box Assemblies of Coal Mills XRP 803 ½ HP & XRP 883 for Unit No. 1 to 4 (4x210 MW), Khaperkheda TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Refurbishment of spare HPT module Unit 1 & 2 at TM-I (4X210 MW), KHAPERKHEDA TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Procurement of Complete Gear Box Assemblies of Coal Mills XRP 883 for Unit-1 to 4 (210MW). | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | SUPPLY INSTALLATION TESTING & COMMISSIONING REVAMPING OF FIRE DETECTION & ALARM AND PROTECTION SYSTEM FROM FIRE AND PROVIDING RAPID EXTINGUISHING CLEAN AGENT (CA) SYSTEM AT UNIT -3,4 & 5 ATKPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Supply Installation Testing & Commissioning , Revamping of fire protection and providing rapid extinguishing clean agent (CA) system at unit # 3 ,4 210 MW TPS, KHAPERKHEDA | 0 | - | 0 | 0 | 0 | 0 | 6.5 | 6.5 |  |  | 6.5 | 0
2 | Restoration of various Fire protection system at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Restoration of fire hydrant ring and fire water spray Header at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 13.14 | 13.14 |  |  | 13.14 | 0
2.2 | Restoration of deluge valve system at CHP-210MW | 0 | - | 0 | 0 | 0 | 0 | 25.44 | 25.44 |  |  | 25.44 | 0
3 | VARIOUS SCHEMES PROPOSED FOR IMPROVEMENT OF CHP-I (4 X 210 MW). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Design, Manufacturing, Supply, Erection, Commissioning & Testing of Coal Flow Management system for Coal Bunkers in CHP-I (4 X 210MW), Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 12.27 | 12.27 |  |  | 12.27 | 0
3.2 | Design, engineering, manufacturing, supply, installation and commissioning of Dedusting System for Crusher House and Bunker area in Unit 3 & 4 at CHP-I (4 X 210MW), Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Renovation including replacement of Power & Control cables with automation & upgradation of Stacker Reclaimer No. 1 in CHP-I (4 X 210MW), TPS Khaperkheda." | 0 | - | 0 | 0 | 0 | 0 | 8.59 | 8.59 |  |  | 8.59 | 0
4 | Flue Gas Desulphrisation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | FGD installation of 210MW unit 1 & 2 at Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Upgradation of DDC/DCS system for UNIT 2 & 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Upgradation of DDC/DCS system for UNIT 2 & 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#1 to 4 Khaperkheda TPS & Upgradation of various governing Element for smooth operation for flexible operation of TG set at 40% technical minimum operation. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#1 to 4 Khaperkheda TPS. | 0 | - | 0 | 15 | 15 | 0 | 45 | 45 |  |  | 45 | 0
6.2 | Upgradation of various governing Element for smooth operation for flexible operation of TG set at 40% technical minimum operation. | 0 | - | 0 | 0 | 0 | 0 | 30 | 30 |  |  | 30 | 0
7 | Upgradation of Battery Charger , UPS system , GEHO PLC and VFD, ID VFD, supply of Efficiency Measuring Instruments and Supply, erection and commissioning of Sox, Nox , CO, Opacity, ETP and Oxygen Analyser for Unit 1 to 4 of 210 MW at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Supply of Efficiency Monitoring Instruments for performance optimization group (POG) at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
7.2 | Upgradation of 220 V, 24 V DC Float cum boost battery charger at Unit#1 to 4 Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
7.3 | Upgradation of 2X50 KVA UPS at Unit#1 to 4 Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
7.4 | Supply, Erection and Commissioning of Sox, Nox , CO, Opacity and ETP Analyser for Unit 1 to 4 of 210 MW at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
7.5 | Upgradation of GEHO PLC and VFD along with HCSD system Instrumentaion at Unit 3 & 4 Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
7.6 | Supply, Erection & Commissioning of Oxygen Analyzer for combustion optimization for Unit#1 to 5 Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
7.7 | Upgradation of VFD for ID FAN in Unit# 3 & 4, 210MW khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.8 | Scheme 8 Supply, erection & commissioning of PLC and SCADA System of Ash Evacuation and Disposal System for UNIT 3 and 4 Of 210 MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
8 | Procurement of LP Rotor for unit 1 and 2 , Supply and installation of air washer unit 1 and 2 and refurbishment of air washer unit for unit 3 and 4 and GEHO Pummp house control room. Supply and installation of diesel engine driven fire fighting pump with engine. Procurement of various control valves for unit No. 1 to 4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.1 | Supply and installation of Air washer unit in unit 1 and 2 , 6.6 KV breaker room, Turbine MCC room Battery room Boiler MCC room for cooling of all the Electrical Panels and AHP stage I Pump House control room air washer system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.2 | Refurbishment of Air washer unit of 3 and 4, 6.6 KV breaker room, Turbine MCC room Battery room Boiler MCC room for cooling of all the Electrical Panels and Refurbishment of GEHO pump House and AHP stage II Pump House control room air washer system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.3 | Procurement of Complete LPT rotor for unit 1 and 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.4 | Revamping of diesel engine driven fire fighting pump system with engine. | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
8.5 | Procurement of various control valves for unit No. 1 to 4 | 0 | - | 0 | 0 | 0 | 0 | 7 | 7 |  |  | 7 | 0
9 | Procurement of IP Rotor and Inner casing for unit 1 and 2. Procurement of IP rotor and inner casing for unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.1 | Procurement of IP Rotor and Inner casing for unit 1 and 2. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.2 | Procurement of IP rotor and inner casing for unit 3 and 4 along with Turbovisory sensors and panel | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.3 | Supply and installation of srew compressor for supply of instrument air to unit No. 3 and 4 along with dryer for unit No. 3 & 4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of LP rotor for unit 3 and 4 and upgradation of BFP cartridge and BFP Booster pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.1 | Procurement of of LP rotor for unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.2 | Upgradation of BFP cartridge and BFP Booster pump, motorized scoop for hydraulic coupling and drive unit for BFP and modulating BFP RC valve for Unit 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Refurbishment of LP rotor of unit 1 and 2 and Refurbishment of HPT module of unit 1 and 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.1 | Refurbishment of LP rotor of unit 1 and 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.2 | Refurbishment of HPT module of unit 1 and 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Refurbishment of LP rotor for unit 3 and 4 and Refurbishment and re-blading of HPT module of unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.1 | Refurbishment of LP rotors for unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.2 | Refurbishment of HPT modules of unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | SITC OF COMPLETE SOLUTION AND COMPREHENSIVE PROTECTION AND MONITORING PACKAGE ALONG WITH RETROFIT OF ALLIED ACCESSORIES FOR VARIOUS GTs & STs INSTALLED AT 210 MW KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | SUPPLY,INSTALLATION, TESTING & COMMISSIONING OF COMPLETE SOLUTION AND COMPREHENSIVE PROTECTION AND MONITORING PACKAGE ALONG WITH RETROFIT OF ALLIED ACCESSORIES FOR VARIOUS GTs & STs INSTALLED AT 210 MW KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 6.5 | 6.5 |  |  | 6.5 | 0
14 | PLANT PERFORMANCE IMPROVEMENT BY DESIGN, SUPPLY, INSTALLATION & COMMISSIONING OF STATE OF ART HT VACCUM CIRCUIT BREAERS AT UNIT 1 TO 4 OF 210MW KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.1 | DESIGN, SUPPLY, INSTALLATION, TESTING & COMMISSIONING OF HT VCB AT U # 1 & 2. | 0 | - | 0 | 15.14 | 15.14 | 0 | 0 | 0 |  |  | 0 | 0
14.2 | DESIGN, SUPPLY, INSTALLATION, TESTING & COMMISSIONING OF HT VCB AT U # 3 & 4. | 0 | - | 0 | 8.25 | 8.25 | 0 | 8.25 | 8.25 |  |  | 8.25 | 0
15 | DESIGN, SUPPLY, INSTALLATION, TESTING AND COMMISSIONING OF THE VARIOUS LIFTS IN PLACE OF THE EXISTING OLD LIFTS, LIGHTNING PROTECTION SYSTEM, EARTHING SYSTEM, AVIATION LIGHTING SYSTEM INSTALLED AT UNIT # 1 TO 4 OF 210 MW, KHAPERKHEDA TPS ON OEM BASIS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | DESIGN, SUPPLY, INSTALLATION, TESTING AND COMMISSIONING OF THE VARIOUS LIFTS IN PLACE OF THE EXISTING OLD LIFTS INSTALLED AT UNIT # 1 TO 4 OF 210 MW, KHAPERKHEDA TPS ON OEM BASIS. | 0 | - | 0 | 0 | 0 | 0 | 10.46 | 10.46 |  |  | 10.46 | 0
15.2 | Design, Engineering, Supply, Erection, Testing & Commissioning of lightning protection system at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Design, Engineering, Supply, Erection, Testing & Commissioning of Earthing of electrical system & various buildings at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
15.4 | Design, Engineering, Supply, Erection, Testing & Commissioning of Aviation Lighting Syatem at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
16 | SUPPLY OF SPARE GENERATOR ROTOR FOR U#3 &4, 210MW, TPS KHAPERKHEDA. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.1 | SUPPLY OF SPARE GENERATOR ROTOR FOR U#3 &4, 210MW, TPS KHAPERKHEDA. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | PROCUREMENT OF ENERGY EFFICIENT MOTORS FOR U # 1 TO 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.1 | PROCUREMENT OF ENERGY EFFICIENT MOTORS FOR U # 1 & 2 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 11 | 11 |  |  | 11 | 0
17.2 | PROCUREMENT OF ENERGY EFFICIENT MOTORS FOR U # 3 & 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 14 | 14 |  |  | 14 | 0
17.3 | Procurement of DC motors for U # 1 & 2 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
17.4 | Procurement of DC motors for U # 3 & 4 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
18 | UPGRADATION OF EXISTING LT MCC PANEL WITH STATE OF ART LT MCC PANEL AT U # 1 TO 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | UPGRADATION OF EXISTING LT MCC PANEL WITH STATE OF ART LT MCC PANEL AT U # 1 & 2 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 6.25 | 6.25 |  |  | 6.25 | 0
18.2 | UPGRADATION OF EXISTING LT MCC PANEL WITH STATE OF ART LT MCC PANEL AT U # 3 & 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.3 | UPGRADATION OF HT BREAKER PANEL AT WAREGAON ASH BUND OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | UPGRADATION OF HT BREAKER PANEL AT OLD PROJECT OFFICE OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.5 | Retrofitting of Existing L & T make LT MCC ACB by state or art ACB at U # 1 to 4 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.6 | Retrofitting of Existing ABB make LT MCC ACB by state or art ACB at U # 1 to 4 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | ERECTION & COMMISIONING OF DRY TYPE CAST RESIN TRANSFORMERS FOR U # 1 TO 4 OF KHAPERKHEDA TPS & Design, Engineering, Supply, Erection, Testing & Commissioning of various Battery sets at Unit # 3 & 4 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | PROCUREMENT OF DRY TYPE CAST RESIN TRANSFORMERS FOR U # 1 & 2 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.2 | PROCUREMENT OF DRY TYPE CAST RESIN TRANSFORMERS FOR U # 3 & 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 4 | 4 |  |  | 4 | 0
19.3 | PROCUREMENT OF VFD TRANSFORMERS FOR ID FAN MOTOR U#3&4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.4 | Design, Engineering, Supply, Erection, Testing & Commissioning of various Battery sets at Unit # 3 & 4 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 12.5 | 12.5 |  |  | 12.5 | 0
20 | Study, Supply & Refurbishment of HCSD systems, ESP operation, ambience & various pump, & PLC schemes for the improvement of AHP-I at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.1 | STUDY. DESIGN & REFURBISHMENT WORKS OF HIGH CONCENTRATION SLURRY DISPOSAL SYSTEM (HCSD SYSTEM) UNITS #3&4 AT AHP-1, TPS KHAPERKHEDA. | 0 | - | 0 | 0 | 0 | 0 | 9.32 | 9.32 |  |  | 9.32 | 0
20.2 | STUDY, DESIGN & REFURBISHMENT WORKS OF ARTs AND ASSOCIATED MOUNTINGS & ACCESSORIES OF HCSD SYSTEM FOR AHP-I, TPS KHAPERKHEDA.” | 0 | - | 0 | 0 | 0 | 0 | 8.96 | 8.96 |  |  | 8.96 | 0
20.3 | ‘SUPPLY & REFURBISHMENT WORKS OF HCSD ASH SLURRY MIXER SYSTEM AT UNIT #3 &4 OF AHP-I, TPS KHAPERKHEDA’. | 0 | - | 0 | 0 | 0 | 0 | 2.85 | 2.85 |  |  | 2.85 | 0
20.4 | ‘STUDY, SUPPLY, RESTORATIONS & REPLACEMENT OF ALL INTERNAL SPARES OF D6 FIELD & RENOVATION OF D1 FIELD OF U3 DURING AOH FOR AHP-I, TPS KHAPERKHEDA’ | 0 | - | 0 | 0 | 0 | 0 | 2.92 | 2.92 |  |  | 2.92 | 0
20.5 | PROCUREMENT OF VARIOUS PUMPS IN RECYCLE WATER SYSTEM IN ASH HANDLING PLANT 4X210 MW AT KHAPARKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 4.6 | 4.6 |  |  | 4.6 | 0
21 | Reliability improvement and complete replacement of ABC series with drive unit of ash slurry pipeline of 7 KM of 4*210MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Procurement and restoration of complete pipeline replacement of ABC series | 0 | - | 0 | 0 | 0 | 0 | 20 | 20 |  |  | 20 | 0
21.2 | Procurement and restoration of complete drive unit replacement of ABC series | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
22 | Procurement and restoration of complete Bottom ash hopper replacement including entire structure, Clinker grinder alongwith motor, Feed Gate, Power Cylinder and Pipelines discharge of U3&4 of 4*210MW Khaparkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.1 | Procurement and restoration of complete BAH replacement including entire structure and clinker griender | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.2 | Procurement and restoration of complete drive unit of clinker grinder for Unit 1 to 4 | 0 | - | 0 | 0 | 0 | 0 | 1.6 | 1.6 |  |  | 1.6 | 0
22.3 | Procurement and restoration of discharge pipeline of vertical sump pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Procurement and restoration of Pipeline garlanding at Waregaon ash Bund of 4*210 MW Khapakheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.1 | Pipeline garlanding at Waregaon ash Bund of 4*210 MW Khapakheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Upgradation, modification and erection of complete wet fly ash evacuation into dry fly ash evacuation systen for ESP 1 and 2 of 4*210 MW Khapakheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.1 | Upgradation, modification and erection of complete wet fly ash evacuation into dry fly ash evacuation systen for ESP 1 and 2, 4*210 MW Khapakheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | Reliability improvement and complete replacement of JKL series with drive unit of ash slurry pipeline of 7 KM of 4*210MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.1 | Procurement and restoration of complete pipeline replacement of JKL series | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.2 | Procurement and restoration of complete drive unit replacement of JKL series | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | Study, Supply and Refurbishment of HCSD System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.1 | Procurement of complete Suction and discharge valve of Geho pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.2 | Procurement of Subassemblies of Geho pump. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.3 | Upgradation and compressors of dry ash evacutaion system of U#3&4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.4 | Procuremenet of complete drive unit and VFD of GEHO pump. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | RENOVATION OF ESP FIELD INTERNALS FOR UNIT 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.1 | RENOVATION OF ESP FIELD INTERNALS FOR UNIT 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28 | R & M OF APH OF UNIT # 1& 2 (2 x 210MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28.1 | R & M OF APH OF UNIT # 1& 2 (2 x 210MW) OF KHAPERKHEDA TPS FROM MODEL: 27 VI 1850 TO 27 VI 2000 mm. DESIGN, ENGINEERING, SUPPLY, ERECTION & COMMISSIONING OF DOUBLE SEALING | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29 | DPR FOR ECONOMISER COILS AND APH GEAR BOX | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29.1 | PROCUREMENT AND REPLACEMENT OF COMPLETE SET OF ECONOMISER UPPER BANK & LOWER BANK COILS FOR KHAPERKHEDA TPS UNIT NO.3&4 | 0 | - | 0 | 11 | 11 | 0 | 11 | 11 |  |  | 11 | 0
29.2 | Procurement of APH gear box in unit no. 1 & 2 | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
29.3 | Procurement of APH speed reducer gear box in unit no. 3 & 4 | 0 | - | 0 | 2.5 | 2.5 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
30 | DPR FOR LTSH COILS , APH BASKETS & RH OUTLET STUB BENDS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.1 | Procurement of Air Pre-heater Baskets for unit no. 2 to 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.2 | Procurement of LTSH coils for unit no. 1 & 2 and Procurement of Reheater outlet header stub bends for unit no. 1 to 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.3 | Procurement of LTSH coils for unit no. 3 & 4 and Procurement of Reheater outlet header stub bends for unit no. 3 to 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31 | DPR FOR SUPPLY & REPLACMENT OF THERMAL INSULATION OF BOILER AND DUCT AT UNIT 1 TO 4 KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.1 | SUPPLY & REPLACMENT OF THERMAL INSULATION OF BOILER AND DUCT AT UNIT 1 TO 2KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.2 | SUPPLY & REPLACMENT OF THERMAL INSULATION OF BOILER AND DUCT AT UNIT 3 TO 4 KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32 | DPR FOR COAL CYCLE IMPROVEMENT IN UNIT NO.1 TO 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.1 | Procurement of Complete Journal Assembly for 803 ½ HP Coal Mills of Unit No. 1 To 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.2 | Procurement of Complete Journal Assembly for XRP 883 Coal Mills of Unit No. 3 To 4, | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.3 | Procurement of assembly of worm shaft & worm wheel with hub for unit no. 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.4 | PROCUREMENT OF COMPLETE GEAR BOX ASSEMBLIES OF COAL MILLS XRP 803 ½ HP FOR UNIT # 1 TO 2 AT KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.5 | PROCUREMENT OF COMPLETE GEAR BOX ASSEMBLIES OF COAL MILLS XRP 883 FOR UNIT # 3 TO 4 AT KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33 | DPR FOR PERFORMANCE IMPROVEMENT OF BOILER PA FAN, ID FAN AND FD FAN IN UNIT NO. 1 TO 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.1 | Procurement of PA fan Casings along with Dampers in Unit- 1 & 2, at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.2 | PROCUREMENT OF COMPLETE ROTOR ASSEMBLY ALONG WITH MOTOR FOR NDZV 31 SIDOR IN UNIT NO. 1 & 2 KHAPERKHEDA TPS (ID FAN) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.3 | PROCUREMENT OF FD FAN (BHEL AP 1-20 / 11) ASSEMBLY ALONG WITH DRIVE UNIT(MOTOR) FOR UNIT 1 & 2 AT KHAPERKHEDA TPS UNDER OEM NATURE ITEMS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.4 | PROCUREMENT OF FD FAN (BHEL AP 1-20 / 11) ASSEMBLY ALONG WITH DRIVE UNIT(MOTOR) FOR UNIT 3& 4 AT KHAPERKHEDA TPS UNDER OEM NATURE ITEMS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.5 | NDZV 33 SIDOR ID Fan Impeller Assembly for Unit 3 & 4 at TPS, Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.6 | Design, Engineering, Manufacturing, Supply & Commissioning including civil works for installation of 70 LPM lubricant ystems for PA Fans in unit no. 1&2. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.7 | Supply and installation of ID and PA foundation deck spring for unit no. 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34 | VARIOUS SCHEMES FOR BOILER PERFORMANCE IMPROVEMENT | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.1 | SUPPLY OF COAL MILL SEPERATOR & SCRAPPER BODIES FOR XRP-803 1/2 HP COAL MILLS IN UNIT 1 & 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.2 | MODIFICATION OF EXISTING COAL BUNKER AND COMMISSIONING OF BUNKER CHUTE ASSEMBLY WITH VIBRATING MOTOR TO AVOID BUNKER MOUTH COAL CHOKE UP FOR UNIT 1 & 2AT KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.3 | MODIFICATION OF EXISTING COAL BUNKER AND COMMISSIONING OF BUNKER CHUTE ASSEMBLY WITH VIBRATING MOTOR TO AVOID BUNKER MOUTH COAL CHOKE UP FOR UNIT 3 & 4 AT KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.4 | DESIGN, DEVELOPMENT, COMMISIONING OF SEAL AIR FAN ASSEMBLIES IN UNIT 1 & 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.5 | Procurement of sub body assembly of control valve in unit no. 1 & 2 actuating main gear unit part electrical actuator in unit no. 1 to 4 Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | Construction of A, B, C, D & E type stilt + 6 floor buildings at TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Construction of A, B, C, D & E type stilt + 6 floor buildings at TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36 | Enhancement & Renovation of existing building, Construction of Market building, Construction of club building community hall, Construction of school building, & Enhancement of existing domestic plant providing V wire 3 MLD at Colony TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.1 | Enhancement / Renovation & strengthening of existing building & allied works in colony TPS Khaperkhda. | 0 | - | 0 | 0 | 0 | 0 | 28 | 28 |  |  | 28 | 0
36.2 | Construction of Market building including approach road, drainage arrangement & electrification at colony TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 6 | 6 |  |  | 6 | 0
36.3 | Construction of club building / community hall | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.4 | Construction of school building | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.5 | Enhancement of existing domestic plant providing V wire 3 MLD | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
37 | Enhancement / Renovation of Saudamini Administrative Building, Construction of VIP Guest House, Construction of roads at Prakashnagar Colony and Providing various civil works related to coal transport railway lines of khaperkheda TPSTPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.1 | Enhancement / Renovation of Saudamini building | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
37.2 | Construction of VIP guest house TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
37.3 | Construction of Roads | 0 | - | 0 | 0 | 0 | 0 | 13 | 13 |  |  | 13 | 0
37.4 | Construction of office building & store for electrical maintenance & Civil at KPKD | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
37.5 | Providing Special repair & retrofitting work of river bridge no.09 on Khaperkheda - Kalumna railway siding of TPS Khaperkheda. | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
37.6 | Construction & repairing of drains & culverts along coal Transporting Railway lines & approach road of TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
37.7 | Repairing, providing & applying Epoxy Painting and Structural Steel Works to steel structural bridges on kpkd to Kaluma and kpkd to Saoner railway lines as per recommendation of structural stability report at TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
37.8 | Construction of compound wall KPKD Colony | 0 | - | 0 | 0 | 0 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
38 | Work of Strengthening and modification of Main Plant, construction of roads, strengthening of IDCT 1 to 4 in plant area, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.1 | Work of attending additional works based on structural report at Induced Draft Cooling Towers(IDCT) unit 1,2,3 & 4 at 4 x 210MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 1.21 | 1.21 |  |  | 1.21 | 0
38.2 | Work of constructon of roadside drains from VIP gate no.3 to IDCT No.1 at 4 x 210MW TPS Khaperkheda. | 0 | - | 0 | 3.61 | 3.61 | 0 | 0 | 0 |  |  | 0 | 0
38.3 | Construction of bituminous macadam road from Administrative Building to GCR Road near Service Building of 4X210MW TPS Khaperkheda. | 0 | - | 0 | 2.7 | 2.7 | 0 | 0 | 0 |  |  | 0 | 0
38.4 | Work for Construction of cement concrete road for equipment movement for salt lagoon (WTP-I), FGD(System), H2(cylinders) plant etc. inside plant premises in 4x 210MW, TPS, Khaperkheda. | 0 | - | 0 | 3.63 | 3.63 | 0 | 0 | 0 |  |  | 0 | 0
38.5 | Construction of cement concrete road outside BTG area of Power Plant 4 x 210MW TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 8.92 | 8.92 |  |  | 8.92 | 0
38.6 | Construction of cement concrete road for material transportation from D-Point CHP to reject coal Dumping yard in 4x 210MW, TPS, Khaperkheda. | 0 | - | 0 | 5.94 | 5.94 | 0 | 0 | 0 |  |  | 0 | 0
38.7 | Work of Strengthening and modification of Main Plant, Major Stores, Auxiliary in plant area, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
38.8 | Construction of diversion road along with RCC bridge from rejct coal yard CHP-I & CHP-II | 0 | - | 0 | 0 | 0 | 0 | 15 | 15 |  |  | 15 | 0
38.9 | Upgradation of existing ETP plant consist civil works, electrification and pumps. | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
39 | Work of 5th Raising of Waregaon Ash Bund, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
39.1 | Work of 5th Raising of Waregaon Ash Bund, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 150 | 150 |  |  | 150 | 0
40 | Work of CTR(Complete Track Removal),TTR(TRAIN TRAVLER REGULATOR) and Yard Remoulding incl. misc. works at Mahagenco Khaperkheda Plant. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
40.1 | Work of CTR(Complete Track Removal),TTR(TRAIN TRAVLER REGULATOR) and Yard Remoulding incl. misc. works at Mahagenco Khaperkheda Plant. | 0 | - | 0 | 0 | 0 | 0 | 178 | 178 |  |  | 178 | 0
41 | Various WTP 210MW improvement schemes i.e. Up-gradation of SWAS SYSTEM UNIT- 1 to 4 at WTP-I 210 MW along with coal sampling lab upgradation, Comissioning of CW Chemical Dosing system etc | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.1 | Upgradation of Existing ETP system viz. Plate Settler, Settling tank, Sludge Drying bed, Chemical dosing system etc.)as per MPCB consent condition | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
41.2 | Upgradation of SWAS Lab 3& 4 at WTP-210 MW | 0 | - | 0 | 9 | 9 | 0 | 0 | 0 |  |  | 0 | 0
41.3 | Revamping of Chlorination Plant Stream (A+ B) & Installation, Comissioning of CW Chemical Dosing system (Viz. Scale inhibitor, Scale Dispersant, Biodispersant, Corossion Inhibitor & H2SO4 dosing) and Online CW Chemical parameter monitoring system at KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 7 | 7 |  |  | 7 | 0
41.4 | Upgradation of SWAS Lab 1& 2 at WTP-210 MW | 0 | - | 0 | 0 | 0 | 0 | 9 | 9 |  |  | 9 | 0
41.5 | Upgradation of Water &Coal testing Lab at WTP-210 MW &Procurement of Coal Lab Instruments and upgradation of coal sampling Room & Instruments related to Coal sample Preparation. at WTP-210 MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42 | Work of capacity restoration of unloading stream from Beetle Charger No. 1 to Stacker/Reclaimer No. 1 for perfromance improvement of CHP-I (4 x 210 MW) & Capacity restoration of unloading stream from Beetle Charger No. 1 to Stacker/Reclaimer No. 1 for perfromance improvement of CHP-I (4 x 210 MW). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.1 | Revamping/ refurbishment, capacity restoration and upgradation for beetle charger No. 1 | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
42.2 | Revamping/ refurbishment, capacity restoration and upgradation for Wagon Tippler No. 1 | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
42.3 | Revamping/ refurbishment, capacity restoration and upgradation for Apron Feeder No. 1 | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
42.4 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 2C, 3A, 4A, 8A, 9 | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
42.5 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for impact crusher and wobbler feeder No. 1 & 3 | 0 | - | 0 | 0 | 0 | 0 | 7 | 7 |  |  | 7 | 0
42.6 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Stacker/Reclaimer No. 1. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
42.7 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv. 3C to 3A, Conv. 3A to 4A, Conv. 4A to 8A and Conv. 9 by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
42.8 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of beetle Charger, wagon tippler, apron feeder, covneyors (Conv. 2C, 3A, 4A, 8A, 9), crushers/ wobbler feeder No. 1 & 3 and Stacker/Reclaimer No. 1 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 20 | 20 |  |  | 20 | 0
43 | DPR fo Capacity restoration of bunkering stream from Conv. 5A to 7A/B/C/D including shuttle conveyors in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
43.1 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 5A, 6B, 7A, 7B, 7C, 7D and Shuttle Conv. 1 to 4 in CHP-I (4 x 210 MW) | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
43.2 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv.Conv. 4D to 5A/B , 5A to 6B, Conv. 6B to 7A & 7B, Conv. 7B to 7D upto shuttle conveyor, Conv. 7A to 7C upto shuttle conveyor by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
43.3 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of covneyors (Conv. 5A, 6B, 7A/B/C/D & Shuttle Conv. 1 to 4 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
44 | Work of capacity restoration of unloading stream from Beetle Charger No. 2 to Stacker/Reclaimer No. 2 for perfromance improvement of CHP-I (4 x 210 MW). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.1 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for beetle charger No. 2 | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
44.2 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Wagon Tippler No. 2 | 0 | - | 0 | 0 | 0 | 0 | 6 | 6 |  |  | 6 | 0
44.3 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Apron Feeder No. 2 | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
44.4 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 2D, 3B, 4B, 8B, 10 | 0 | - | 0 | 0 | 0 | 0 | 25 | 25 |  |  | 25 | 0
44.5 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for impact crusher and wobbler feeder No. 2 & 4 | 0 | - | 0 | 0 | 0 | 0 | 7 | 7 |  |  | 7 | 0
44.6 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Stacker/Reclaimer No. 2. | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
44.7 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv. 2D to 3B, Conv. 3B to 4B, Conv. 4B to 8B and Conv. 10 by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
44.8 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of beetle Charger, wagon tippler, apron feeder, covneyors (Conv. 2D, 3B, 4B, 8B, 10), crushers/ wobbler feeder No. 2 & 4 and Stacker/Reclaimer No. 2 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
45 | Work of capacity restoration of bunkering stream from Conv. 1A/B, 2A/B, 5B to 7E/F/G/H including shuttle conveyors in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.1 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 1A/B, 2A/B, 5B, 6A, 7E, 7F, 7G, 7H and Shuttle Conv. 5 to 8 in CHP-I (4 x 210 MW) | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
45.2 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv. 1A/b to 2A/B,Conv. 4C to 5A/B, Conv. 5B to 6A, Conv. 6A to 7E & 7F, Conv. 7E to 7G upto shuttle conveyor, Conv. 7F to 7H upto shuttle conveyor by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 15 | 15 |  |  | 15 | 0
45.3 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of conveyor system from Conv. 1A/B, 2A/B, 5B, 6A, 7E, 7F, 7G, 7H and Shuttle Conv. 5 to 8 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
45.4 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Paddel Feeder No. 1 to 4 and truck hopper in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
46 | Renovation and upgradation of various electrical system for CHP-I (4 x 210 MW) improvement & Renovation and upgradation of various electrical system for CHP-I (4 x 210 MW) improvement. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.1 | Design, development and upgradation with circuit breaker VFD of various LT MCC of CHP-I. | 0 | - | 0 | 0 | 0 | 0 | 17 | 17 |  |  | 17 | 0
46.2 | Design, Supply, Installation, Commissioning and Testing of Energy Chain System for Paddle Feeder, Shuttle Conveyor and Stacker/Reclaimers in CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
46.3 | Upgradation of relay logic system with PLC & SCADA in CHP-I control room and Wagon Tipplers in CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 8 | 8 |  |  | 8 | 0
46.4 | Complete upgradation of conveyor lighting system with energey efficient LED lights for CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
46.5 | Providing, installation, testing commissioning, maintenance and operation of explosion proof & weather proof surveillance system at CHP-I (4 X 210 MW), TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 6 | 6 |  |  | 6 | 0
46.6 | Complete revamping/refurbishment, upgradation and modification of various EOT cranes & hoist installed at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 12 | 12 |  |  | 12 | 0
47 | Procurement of various capacity SAN make locomotives and BEML make loader & bulldozer for CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.1 | Procurement of various capacity SAN make locomotives and BEML make loader & bulldozer for CHP-I (4 x 210 MW) | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
48 | CHP Improvement Schemesfor 4x 210 MW units | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.1 | Design, manufacture, supply and installation of suspended magnet for bunkering belts at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 4 | 4 |  |  | 4 | 0
48.2 | Design, manufacture, supply and installation of travel drive system for shuttle conveyors and conveyors at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
48.3 | Renovation including replacement of Power & Control cables with automation & upgradation of Stacker Reclaimer No. 2 in CHP-I (4 X 210MW), TPS Khaperkheda." | 0 | - | 0 | 0 | 0 | 0 | 8 | 8 |  |  | 8 | 0
48.4 | Complete reconditionding & upgradation of LT MCC installed at Unit No. 3 & 4 bunker auxiliareis in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 7 | 7 |  |  | 7 | 0
48.5 | Complete reconditionding & upgradation of outdoor lighting system in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 8 | 8 |  |  | 8 | 0
48.6 | Complete reconditionding & upgradation of HT breaker, control circuits & protection relays in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
48.7 | Complete revamping/refurbishment, upgradation and modification of various monorail hoists & winch machine installed at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
48.8 | Procurement of hydra 14 Ton above capacity and heavy vehicles for CHP- I & II. | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
49 | Installation of Real Time Coal Analyzer at all TPS of Mahagenco | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
49.1 | Installation of Real time Coal Analyzer at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 31.42 | 31.42 |  |  | 31.42 | 0
50 | Railway expenses for refurbishment of OHE lines at CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50.1 | Railway expenses for refurbishment of OHE lines at CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 26 | 26 |  |  | 26 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | PROCUREMENT COMPLETE Gear BOX ASSEMBLIES FOR 803 1/2 HP & XRP 883 COAL MILLS OF UNIT NO. 1& 2 AT KHAPERKHEDA TPS. | N.A. | - | 0 | 4.5548 | 4.5548 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply Erection and commissioning of Oil Cooled Suspended magnets at Conv 6A & 6B at Khaperkheda TPS. | N.A. | - | 0 | 1.1484 | 1.1484 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurment of new 02 Ambulance Van & 2 Truck for KPKD TPS(Asset Nos. 170100512, 170100513, 170100514, 170100515) | N.A. | - | 0 | 0.41055 | 0.41055 | 0 | 0 | 0 |  |  | 0 | 0
4 | GEHO PUMP (Valve housing assembly) | N.A. | - | 0 | 8.7933 | 8.7933 | 0 | 0 | 0 |  |  | 0 | 0
5 | RESTORATION OF AHP OUTLET TO ESP INLET DUCTS U#1&2(Unit #2 Part only) | N.A. | - | 0 | 7.0042 | 7.0042 | 0 | 0 | 0 |  |  | 0 | 0
6 | ABC powder type and foam type composite Fire Extinguisher | N.A. | - | 0 | 0.714 | 0.714 | 0 | 0 | 0 |  |  | 0 | 0
7 | FFEQUIP HYDRAULIC JACK (BM-I) | N.A. | - | 0 | 0.57696 | 0.57696 | 0 | 0 | 0 |  |  | 0 | 0
8 | MOBILE COAL SAMPLING EQUIP-AUGER (FMC) CHP-I | N.A. | - | 0 | 1.5824 | 1.5824 | 0 | 0 | 0 |  |  | 0 | 0
9 | Replacement of ash slurry disposal pump to improve performance & capacity enhancement of ash slurry disposal system at AHP-1 Khaperkheda TPS | 0 | - | 0 | 4.92 | 4.92 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of Pillow Block Dodge Bearing Assemblies (Expansion & Non-Expansion) for PA fans in Unit- n1 to 4, at Khaperkheda TPS | 0 | - | 0 | 5.11 | 5.11 | 0 | 0 | 0 |  |  | 0 | 0
11 | Replacement of Economizer outlet to APH outlet common duct in unit no. 3 (210MW), Khaperkheda TPS | 0 | - | 0 | 6.24 | 6.24 | 0 | 0 | 0 |  |  | 0 | 0
12 | PROCUREMENT OF OIL COOLED SUSPENSION MAGNET FOR 210MW AND MODIFICATION & REPLACEMENT OF VIBRATING FEEDER WITH VIBRATING TRANSFER CHUTE FOR 210MW | 0 | - | 0 | 3.09 | 3.09 | 0 | 0 | 0 |  |  | 0 | 0
13 | DESIGN,ENGINEERING,MODIFICATION ,ERECTION AND COMMISSIONING OF DRIVE UNIT ARRANGEMENT FOR CONVEYOR 10 AT CHP1 | 0 | - | 0 | 1.65 | 1.65 | 0 | 0 | 0 |  |  | 0 | 0
14 | ENERGY EFFICIENT PLANT LIGHTING AND COLONY LIGHTING MODIFICATIONS | 0 | - | 0 | 21.04 | 21.04 | 0 | 0 | 0 |  |  | 0 | 0
15 | Supply installation testing and commisioning of various battery sets at unit No 1 & 2 of Khaperkheda TPS | 0 | - | 0 | 9.31 | 9.31 | 0 | 0 | 0 |  |  | 0 | 0
16 | Revamping and modification of existing alarm and protection system from fire and provide rapid extinguishing Clean Agent (CA) system at Unit #1 & 2 (210 MW) units, KPKD TPS | 0 | - | 0 | 8.21 | 8.21 | 0 | 0 | 0 |  |  | 0 | 0
17 | Supply of electronic modules for Procontrol DCS system in unit 1 to 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 1.18 | 1.18 | 0 | 0 | 0 |  |  | 0 | 0
18 | Revamping & UPGRADATION of SWAS system in unit 3 & 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 8.56 | 8.56 | 0 | 0 | 0 |  |  | 0 | 0
19 | Upgradation of process instrumentation in unit 1 to 2 of 210 MW Khaperkheda TPS | 0 | - | 0 | 4.64 | 4.64 | 0 | 0 | 0 |  |  | 0 | 0
20 | Replacement of flue gas duct from air heater outlet to esp inlet for U 1 & 2 (S+W) | 0 | - | 0 | 8.03 | 8.03 | 0 | 0 | 0 |  |  | 0 | 0
21 | PROCUREMENT OF COMPLETE ROTOR ASSEMBLY FOR NDZV 31 SIDOR IN UNIT NO. 1 & 2 KHAPERKHEDA TPS (ID FAN). | 0 | - | 0 | 14.52 | 14.52 | 0 | 0 | 0 |  |  | 0 | 0
22 | UPGRADATION OF BELT CONVEYOR CAPACITY OF 2C &2D AND 8A & 8B AT CHP1 | 0 | - | 0 | 3.94 | 3.94 | 0 | 0 | 0 |  |  | 0 | 0
23 | WORK OF DESIGN,ENGINEERING,ERECTION AND UPGRADATION OF DRIVE UNITS OF BELT CONVEYOR 3A & 3BAT CHP1 | 0 | - | 0 | 8.34 | 8.34 | 0 | 0 | 0 |  |  | 0 | 0
24 | Procurement of 1500 KW ID Fan Synchronous Motor at Unit 3 & 4 Khaperkheda TPS. | 0 | - | 0 | 3.12 | 3.12 | 0 | 0 | 0 |  |  | 0 | 0
25 | Procurement of Steam and Water Analysis System(SWAS) for Unit 1&2 (210MW) KPKD TPS, Khaperkheda. | 0 | - | 0 | 9.65 | 9.65 | 0 | 0 | 0 |  |  | 0 | 0
26 | Supply and replacement of complete PVC fills of cell of cooling tower of unit 1-4 (210 MW) at Khaperkheda TPS | 0 | - | 0 | 8.52 | 8.52 | 0 | 0 | 0 |  |  | 0 | 0
27 | PROCUREMENT OF FD FAN (BHEL AP 1-20/11) ASSEMBLY FOR UNIT 1 TO 4 ATKHAPERKHEDA TPS. | 0 | - | 0 | 4.37 | 4.37 | 0 | 0 | 0 |  |  | 0 | 0
28 | CHP performance improvement scheme for capacity restoration of drive units installed at CHP-1 (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 14.5 | 14.5 | 0 | 0 | 0 |  |  | 0 | 0
29 | Work of Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of belt conveyor 8A & 8B and belt conveyor 2C & 2D at CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 2.15 | 2.15 | 0 | 0 | 0 |  |  | 0 | 0
30 | WORK OF DESING,SUPPLY ,ERECTION,COMMISSIONG AND UPGRADATION OF COMPLETE ELECTRICAL SYSTEM FOR DRIVE UNITS OF BELT CONVEYOR 3A & 3B AND BELT CONVEYOR 4A,4B,4C & 4D AT CHP1 Khaperkheda TPS. | 0 | - | 0 | 2.29 | 2.29 | 0 | 0 | 0 |  |  | 0 | 0
31 | Supply, Installation, & Commissioning of Instruments at coal Testing Lab, WTP-I, TPS Khaperkheda. | 0 | - | 0 | 0.45 | 0.45 | 0 | 0 | 0 |  |  | 0 | 0
32 | Supply, Installation & Commissioning and Refurbishment of asbestos based H2 Generator and compressor to convert it to non-asbestos based H2 Generator for Unit 1 to 5, Khaperkheda TPS. | 0 | - | 0 | 7.65 | 7.65 | 0 | 0 | 0 |  |  | 0 | 0
33 | construction of bituminous macadam roads at Prakashnagar Colony TPS Khaperkheda | 0 | - | 0 | 5.4 | 5.4 | 0 | 0 | 0 |  |  | 0 | 0
34 | Work of attending additional works based on structural report at Induced Draft Cooling Towers (IDCT) unit 1,2,3 & 4 at 4 x 210MW, TPS, Khaperkheda | 0 | - | 0 | 1.21 | 1.21 | 0 | 0 | 0 |  |  | 0 | 0
35 | VIBRATION ANALYSER | 0 | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
36 | Upgradation of GEHO pump instrumentation for AHP Unit No. 3 & 4 (210 MW) at Khaperkheda TPS | 0 | - | 0 | 1.27 | 1.27 | 0 | 0 | 0 |  |  | 0 | 0
37 | Refurbishment of HPT module for Unit 1 & 2 | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
38 | General Asset Furniture | N.A. | - | 0 | 0.86177 | 0.86177 | 0 | 0 | 0 |  |  | 0 | 0
39 | General Asset AC, Fans, Air coolers, water filter etc. | N.A. | - | 0 | 0.53608 | 0.41552 | 0.12056 | 0 | 0 |  |  | 0 | 0.12056
40 | General Asset Computer, scanners, etc. | N.A. | - | 0 | 2.5598 | 1.9461 | 0.61367 | 0 | 0 |  |  | 0 | 0.61367
41 | Land aquired for rly siding | N.A. | - | 0 | 0.4072 | 0.4072 | 0 | 0 | 0 |  |  | 0 | 0
42 | RCC ROAD FROM ASH SILO TO 'D' POINT FOR BULKER MO | N.A. | - | 0 | 0.95225 | 0.95225 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 1598.1769 | 1647.9116 | -49.7348 | 1102.88 | 1102.88 | 0 | 0 | 1102.88 | -49.7348
FY 2027-28
a) DPR Schemes
(i) Submitted to MERC
| Combustion optimization system | [6 empty] | 0 | 0
1 | Dynamic coal flow measurement and control (balancing) system (one) | [6 empty] | 0 | 0
1.2 | CO analyser (8 units) | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 | 1.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Oxygen analyser (32 units) | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 | 0.783 | 0.75683 | 0.75683 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Spare HPT module for Khaparkheda Unit 1 & 2 | MERC/CAP/DPR/10/2010-11/1466 | 2010-10-26 | 26.459 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | HPT module 1 No (unit # 1) | MERC/CAP/DPR/10/2010-11/1466 | 2010-10-26 | 23.0379 | 23.9074 | 23.9074 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAP/DPR/10/2010-11/1466 | 2010-10-26 | 3.4211 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Economiser Upper Bank & Lower Bank coils for Khaperkheda Unit no. 3 and Unit no. 4 | MERC/CAP/DPR/10/2010-11/1695 | 2010-12-15 | 26.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Economiser Upper Bank & Lower Bank coils for Khaperkheda Unit no. 3 and Unit no. 4 | MERC/CAP/DPR/10/2010-11/1695 | 2010-12-15 | 26.35 | 11.77 | 11.77 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Economiser & LTSH Upper Bank & Lower Bank coils for Khaperkheda Unit no. 1 and Unit no. 2 | MERC/CAPEX/20112012/01155 | 2011-07-29 | 34.7916 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Economiser & LTSH Coil for Unit 1 | MERC/CAPEX/20112012/01155 | 2011-07-29 | 15.6924 | 15.6924 | 15.6924 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Economiser & LTSH Coil for Unit 2 | MERC/CAPEX/20112012/01155 | 2011-07-29 | 16.1528 | 16.1528 | 16.1528 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20112012/01155 | 2011-07-29 | 2.9464 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Procurement & Replacement of Re-heater Rear Pendant Assembly Coils for 2*210MW Khaperkheda Unit no. 1 and Unit no. 2 | MERC/CAPEX/20122013/00603 | 2012-06-18 | 10.3738 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Re-heater coils for unit no. 1 | MERC/CAPEX/20122013/00603 | 2012-06-18 | 5.1267 | 5.1267 | 5.1267 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Re-heater coils for unit no. 2 | MERC/CAPEX/20122013/00603 | 2012-06-18 | 5.1267 | 5.55 | 5.55 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/00603 | 2012-06-18 | 0.1204 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Procurement of HPT module suitable for khaperkheda TPS Unit 3 & 4 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 36.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Procurement of HPT module suitable for khaperkheda TPS Unit 3 & 4 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 36.2 | 32.4016 | 32.4016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7 | Procurement Spare GTR, Locomotive & Compactors | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 18.4521 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | 250 MVA Spare GTR | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 10.3496 | 11.2511 | 11.2511 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.2 | Procurement of Locomotive 2no’s. | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 5.9927 | 5.9927 | 5.9927 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.3 | Procurement of Compactors 2 no’s. | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 0.42979 | 0.4298 | 0.4298 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 1.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Procurement & Replacement of complete set of LTSH coils for Khaperkheda TPS Unit 3&4 | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 17.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement and replacement of LTSH coils for Khaperkheda TPS at U3 | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 8.58 | 3.4291 | 3.4291 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Procurement and replacement of LTSH coils for Khaperkheda TPS at U4 | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 8.58 | 3.1809 | 3.1809 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 0.65 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Development of Ash Bund (Waregaon) at K'kheda TPS | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 38.7459 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Construction of 3rd upstream raising of existing ash bund from TBL 299.50 Mtr to 302.50 Mtr at Waregaon, Khaperkheda TPS. | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 33.8585 | 32.5375 | 32.5375 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.2 | Construction of masonary dam (Gabion structure) at Waregaon TPS, Khaperkheda. | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 1.0561 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.3 | Construction of approach to drain wells and raising height of drain well no. 1,2 & 3 ash bund at Waregaon, Khaperkheda TPS | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 0.48488 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 3.3464 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Various schemes related to CHP Improvement & Performance Optimization and scheme of conversion of existing Composite OHE to Conventional OHE | MERC/CAPEX/20152016/00422 | 2016-08-03 | 10.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Air Cooled Suspension Magnet for Con. 3 & 6 of CHP 210 MW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 2.18 | 2.2613 | 2.2613 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | Procurement of Impact crusher motor | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.84 | 0.52579 | 0.52579 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.3 | Procurement of 360V, 200 AH battery set and 360V 325 AH battery set for U# 1to 4 | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.1 | 1.4576 | 1.4576 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.4 | Procurement of POG Instruments for Unit 1 to 4 | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.77 | 0.35015 | 0.35015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.5 | Up gradation of safe scan flame scanner system by BHEL scan system in unit no. 1, 3 & 4 | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.6 | Up gradation of old AVR system to DAVR | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.7 | Conversion of existing Composite OHE to Conventional OHE | MERC/CAPEX/20152016/00422 | 2016-08-03 | 2.72 | 2.72 | 2.72 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.47 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | ESP up-gradation for Unit-1 at Khaperkheda TPS | MERC/CAPEX/20152016/01261 | 2016-01-11 | 32.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | ESP up-gradation for Unit-1 at Khaperkheda TPS | MERC/CAPEX/20152016/01261 | 2016-01-11 | 32.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Procurement, installation and commissioning of Gravimetric Belt / Rotary Type Feeder, VFD for CEP, Up-gradation of BTS system & Environmental schemes at Khaperkheda TPS | MERC/CAPEX/20162017/01552 | 2017-02-14 | 20.218 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Procurement, installation and commissioning of Gravimetric belt/rotary Feeder at U-1 & 2 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 5.72 | 4.7418 | 4.7418 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Installation of VFD to CEP at U-1 to 4 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 8.64 | 9.1408 | 9.14 | 0.000792 | 0 | 0 |  |  | 0 | 0.000792 | 0 | 0
13.3 | Installation of BTS system at U-4 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 0.98796 | 0.98796 | 0.98796 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.4 | Replacement of SOx/NOx analyzer at U-1 to 4 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 2.42 | 2.3035 | 2.3035 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.5 | Procurement of TGA,CHNS analyzer and Bomb calorimeter at U-5 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 1.71 | 0.2897 | 0.2897 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01552 | 2017-02-14 | 0.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Up gradation of HMI System at Unit No 3 & 4 at Khaperkheda TPS | MERC/CAPEX/20172018/03946 | 2017-07-19 | 13.39 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | HMI Up-gradation at U# 3 & 4 | MERC/CAPEX/20172018/03946 | 2017-07-19 | 12.78 | 12.5611 | 13.1811 | -0.62 | 0 | 0 |  |  | 0 | -0.62 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/03946 | 2017-07-19 | 0.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21 | Procurement of APH Basket for unit # 1 to 5 and Up-gradation of HT Motor Protection Relay in Unit # 1 to 4 at Khaperkheda TPS | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 9.77 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.1 | Procurement of assembly of baskets for air preheater of type bisector APH 27 VI: 1850, 12 sector in unit no. 1 & 2 and bisector APH 27 VI: 2000; 24 sector in unit no. 3 & 4 (210MW x 4) at TPS, Khaperkheda | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 5.71 | 8.097 | 8.0941 | 0.002845 | 0 | 0 |  |  | 0 | 0.002845 | 0 | 0
21.3 | Up-gradation of H.T. Motor protection relays in Unit 1 to 4 (210MW), Khaperkheda TPS | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 3.96 | 3.2537 | 3.2537 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 0.1 | 0 | 0.18424 | -0.18424 | 0 | 0 |  |  | 0 | -0.18424 | 0 | 0
22 | Procurement of LPT rotor suitable for Unit # 3 & 4 of 210 MW at Khaperkheda TPS | MERC/CAPEX/2018-2019/132 | 2019-05-09 | 27.191 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.1 | Procurement of LPT rotor suitable for Unit # 3 & 4 of 210 MW at Khaperkheda TPS | MERC/CAPEX/2018-2019/132 | 2019-05-09 | 26.491 | 10.7515 | 10.7515 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2018-2019/132 | 2019-05-09 | 0.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23 | Supply, Erection & commissioning of HT Vacuum circuit Breakers & SF6 contactors at AHP (U#1-4) & CHP (U#1 to 5) and 160 KW VFD Panel with Motor for fire-fighting pumps at U#1 to 4 at Khaperkheda TPS | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 10.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.1 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at AHP (Unit#1 to 4, 210MW), Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 4.17 | 3.4843 | 4.8883 | -1.404 | 0 | 0 |  |  | 0 | -1.404 | 0 | 0
23.2 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at CHP (Unit#1 to 4, 210MW) and CHP (Unit#5, 500MW) Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 3.81 | 4.031 | 2.7332 | 1.2978 | 0 | 0 |  |  | 0 | 1.2978 | 0 | 0
23.3 | Supply, Erection & commissioning of 150 KW VFD Panel with motor for fire-fighting pumps at 210 MW Khaperkheda TPS. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 2.34 | 2.0957 | 2.0957 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 0.58 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24 | Augmentation of Waregaon Ash Water Recovery System at TPS Khaperkheda | MERC/CAPEX/2019-20/732 | 2019-09-16 | 17.1984 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.1 | Augmentation of Waregaon Ash Water Recovery System at TPS Khaperkheda | MERC/CAPEX/2019-20/732 | 2019-09-16 | 15.7884 | 15.1987 | 15.1987 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-20/732 | 2019-09-16 | 1.41 | 0.58812 | 0.58812 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25 | Procurement of VFD with HMI & Controller & Replacing with existing Eddy-current drives of Coal feeders at U# 3 & 4 and Procurement of Various Critical Components of GEHO Pump (Model-TZPM 800) for AHP-1 at Khaperkheda TPS | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 10.6535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25.1 | Up-gradation of Existing BHEL make 36” Gravimetric Coal Feeders control panel with HMI and croprocessor based Controller with VFD, Motor & Weigh Module at Unit 3 & 4, (210MW) | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 7.4655 | 7.7 | 7.7 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25.2 | Procurement of various Critical Components of GEHO Pump (Model-TZPM 800) for AHP-1 (210MW) | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 2.698 | 2.6466 | 2.6466 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 0.49 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26 | Procurement, Replacement of Eco Coils U#1&2 210 MW, & Procurement & replacement of foundation Deck Spring assembly for coal mills U#3,4 at Khaperkheda TPS | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 15.4086 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26.1 | Procurement, Replacement of Eco Coils U#1&2 | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 7.4996 | 6.6503 | 6.6503 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26.2 | Procurement & replacement of foundation Deck Spring assembly for coal mills U#3,4 | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 6.679 | 7.0955 | 7.1 | -0.004476 | 0 | 0 |  |  | 0 | -0.004476 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 1.23 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28 | ESP Upgradation of 5 Nos. of 210/500MW Units at Khaperkheda, Koradi & Chandrapur TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 90.3535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.1 | ESP Upgradation at Unit #1, Khaperkheda TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 42.7114 | 59.55 | 54.445 | 5.105 | 0 | 0 |  |  | 0 | 5.105 | 0 | 0
28.2 | ESP Upgradation at Unit #2, Khaperkheda TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 42.7114 | 59.55 | 54.445 | 5.105 | 0 | 0 |  |  | 0 | 5.105 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 4.9307 | 0 | 16 | -16 | 0 | 0 |  |  | 0 | -16 | 0 | 0
29 | Flue Gas Desulphurisation System for Khaperkheda Unit # 1-4 | MERC/CAPEX/2021-2022/MSPGCL/097 | 2022-03-14 | 113.4565 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.1 | FGD System for Khaperkheda Unit # 1-4 | MERC/CAPEX/2021-2022/MSPGCL/097 | 2022-03-14 | 109.15 | 255.58 | 130.03 | 125.55 | 0 | 0 |  |  | 0 | 125.55 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/097 | 2022-03-14 | 4.3065 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4 | Construction of coal platform for Chandrapur TPS, Khaperkheda TPS & Parli TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 5.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4.2 | Khaperkheda TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 5.43 | 3.9936 | 3.9936 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 4.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.4a | 1. Procurement of 6.6 KV,300 KW, P.A.fan motor for U# 1 & 2 2. Procurement of 6.6 KV,425 KW,CM motor for U # 3 & 4 3. Procurement of 6.6 KV,1400KW,CW pump motor for U-1& 2 4. Procurement of 6.6 KV,1400 KW,CW pump motor for U-3&4 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 3.82 | 2.5973 | 2.5973 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.4b | K'kheda: Procurement of HT Motors(GS/HP Water pump)for U-1&2 and Procurement of HT Motors (ACW)for U-3&4 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 1 | 0.4 | 0.4 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.2 | KHAPERKHEDA (U-1 to 4) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.96 | 3.1173 | 3.1173 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.2 | Khaperkheda TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender for KPKD 1-4 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 1.7765 | 1.7765 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.2 | Normal Multipurpose Fire Tender KPKD 1-4 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 2.1847 | 2.1847 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 226.3024 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9.1 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 226.3024 | 291.23 | 331.4177 | -40.1877 | 0 | 0 |  |  | 0 | -40.1877 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 4.4604 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.2a | Compond wall (IB recommdation),Plant Patrolling Roads (IB recommdation) TPS KPKD | MERC/CAPEX/20172018/0177 | 2018-02-06 | 4.4604 | 3.9506 | 3.9506 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 9.23 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11.1 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 9.05 | 13.3057 | 13.3057 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 0.18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15 | Implementation of Water Flow Monitoring system at Chandrapur STPS & Khaperkheda TPS | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 5.1755 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.3 | Electromagnetic Flow meters at various lines & Locations of 210 MW | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 3.8515 | 3.8515 | 3.8515 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.4 | Automation: Centralized SCADA, RTU, MODBUS Cable, Power cable & mandatory spares | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 1.324 | 1.324 | 1.324 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30 | Supply of spare Generator Rotor for UNIT 1 & 2, 210MW | MERC/CAPEX/2023-24/0184 | 2024-03-12 | 37.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.1 | Supply of spare Generator Rotor for UNIT 1 & 2, 210MW | MERC/CAPEX/2023-24/0184 | 2024-03-12 | 36.7 | 36.7 | 36.7 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2023-24/0184 | 2024-03-12 | 0.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M with raising of drain wells and modification of Masonary Dam (Waste Weir), 4 x210 MW, TPS, Khaperkheda | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 45.0535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.1 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M at TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 31.0231 | 31.22 | 31.22 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.2 | Raising of drain wells of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 1.6569 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.3 | Modification of Masonary Dam (Waste Weir) of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 10.1857 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 2.1878 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
32 | Flue Gas Desulphurisation (FGD) System for Khaperkheda Unit # 1 & 2 | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 115.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
32.1 | Flue Gas Desulphurisation (FGD) System for Khaperkheda Unit # 1 & 2 | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 109.8 | 0 | 129.13 | -129.13 | 0 | 0 |  |  | 0 | -129.13
0 | IDC | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 5.54 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33 | Upgradation of DDC/DCS system for UNIT 1 & 3 of 210 MWKhaperkheda TPS | MERC/CAPEX/MSPGCL/2023-24/601 | 2023-11-10 | 39.14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.1 | Upgradation of DDC/DCS system for UNIT 1 & 3 of 210 MWKhaperkheda TPS | MERC/CAPEX/MSPGCL/2023-24/601 | 2023-11-10 | 38.7 | 39.14 | 39.14 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/601 | 2023-11-10 | 0.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34 | Supply & commissioning of interconnection conveyor belt, Elecon make complete impact type crusher, Procurement of 4 NOs. Bull Dozer BEML BD-155 and Eco friendly and power efficient chiller system at Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 28.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.1 | Design, engineering, manufacturing, supply, erection & commissioning of interconnection conveyor belt from 1 X 500MW to 4 X 210MW stack yard at CHP Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.2 | Supply & installation of Elecon–make complete impact type crusher at CHP-I, Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 4.29 | 4.15 | 4.15 | 0 | 0 | 0 |  |  | 0 | 0
34.3 | Procurement of 4 NOs. Bull Dozer BEML BD-155 at CHP, Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.255 | 12.0596 | 12.0596 | 0 | 0 | 0 |  |  | 0 | 0
34.4 | Supply, erection, & commissioning of Eco friendly and power efficient chiller system for khaperkheda TPS Unit 1 to 4, Service Building and WTP in place of present reciprocating type Chiller system | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 11.96 | 11.45 | 11.45 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 1.385 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | 5 Nos. of Boiler Improvement Schemes for Unit No. 1 to 4 | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 32.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Procurement & replacement of Re-Heater Rear Pendent Assembly Coils for unit no. 3 & 4 (210 MW) | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 8.86 | 9.36 | 9.36 | 0 | 0 | 0 |  |  | 0 | 0
35.2 | Procurement Complete Set of Sky Climber For Unit#1 To 5 Boilers. | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 3.32 | 2.43 | 2.43 | 0 | 0 | 0 |  |  | 0 | 0
35.3 | Replacement of glasswool insulation and GI/CORRUGATED sheets of boiler and hot air ducts at unit 1to 4 KHAPERKHEDA TPS | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 2.19 | 1.99 | 1.99 | 0 | 0 | 0 |  |  | 0 | 0
35.4 | Procurement, design, manufacture, supply & delivery, dismantling, retrofitting, erection, commissioning and testing of gravimetric belt conveyor type coal feeders for unit no. 1 & 2. | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 6.68 | 6.77 | 6.77 | 0 | 0 | 0 |  |  | 0 | 0
35.5 | Procurement and Replacement of Air Preheater Baskets for Unit no. 1 to 4 (4x 210MW). | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 9.05 | 8.4735 | 8.4735 | 0 | 2.9 | 2.9 |  |  | 2.9 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 2.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR-17 | Various DPR Schemes for The work of maintaining the zero discharge condition of Pond No. 2 & Pond No.3 and providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 15.7443 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | The work of maintaining the zero discharge condition of Pond No.2 & Pond No.3 at KTPS Koradi | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 4.2068 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.2 | Providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 11.5375 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Scheme of HMI upgradation of unit 5 DCS along with Max Links , HART Scheme , PADO , all BOP PLCs , SWAS system, CO analyser & Coal feeder controller to match with the external aspect , process improvement & Up gradation of Generator Protections Relays in unit 1 to 4 of 210 MW at khaperkheda TPS | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 33.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.7 | Up-gradation of Generator Protections Relays in Unit 1 to 4 of 210 MW Khaperkheda TPS. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 8.31 | 8.86 | 8.86 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/478 | - | 0.86 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Submitted to MERC, Yet to receive approval | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR on Refurbishment of Spare HPT Module Unit 1 & 2 at TM-I and Procurement of Complete Gear Box Assemblies of Coal Mills XRP 803 ½ HP & XRP 883 for Unit No. 1 to 4 (4x210 MW), Khaperkheda TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Refurbishment of spare HPT module Unit 1 & 2 at TM-I (4X210 MW), KHAPERKHEDA TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Procurement of Complete Gear Box Assemblies of Coal Mills XRP 883 for Unit-1 to 4 (210MW). | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | SUPPLY INSTALLATION TESTING & COMMISSIONING REVAMPING OF FIRE DETECTION & ALARM AND PROTECTION SYSTEM FROM FIRE AND PROVIDING RAPID EXTINGUISHING CLEAN AGENT (CA) SYSTEM AT UNIT -3,4 & 5 ATKPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Supply Installation Testing & Commissioning , Revamping of fire protection and providing rapid extinguishing clean agent (CA) system at unit # 3 ,4 210 MW TPS, KHAPERKHEDA | 0 | - | 0 | 6.5 | 6.5 | 0 | 0 | 0 |  |  | 0 | 0
2 | Restoration of various Fire protection system at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Restoration of fire hydrant ring and fire water spray Header at Khaperkheda TPS | 0 | - | 0 | 13.14 | 13.14 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Restoration of deluge valve system at CHP-210MW | 0 | - | 0 | 25.44 | 25.44 | 0 | 0 | 0 |  |  | 0 | 0
3 | VARIOUS SCHEMES PROPOSED FOR IMPROVEMENT OF CHP-I (4 X 210 MW). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Design, Manufacturing, Supply, Erection, Commissioning & Testing of Coal Flow Management system for Coal Bunkers in CHP-I (4 X 210MW), Khaperkheda TPS. | 0 | - | 0 | 12.27 | 12.27 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Design, engineering, manufacturing, supply, installation and commissioning of Dedusting System for Crusher House and Bunker area in Unit 3 & 4 at CHP-I (4 X 210MW), Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 12.96 | 12.96 |  |  | 12.96 | 0
3.3 | Renovation including replacement of Power & Control cables with automation & upgradation of Stacker Reclaimer No. 1 in CHP-I (4 X 210MW), TPS Khaperkheda." | 0 | - | 0 | 8.59 | 8.59 | 0 | 0 | 0 |  |  | 0 | 0
4 | Flue Gas Desulphrisation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | FGD installation of 210MW unit 1 & 2 at Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Upgradation of DDC/DCS system for UNIT 2 & 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Upgradation of DDC/DCS system for UNIT 2 & 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 22.5 | 22.5 |  |  | 22.5 | 0
6 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#1 to 4 Khaperkheda TPS & Upgradation of various governing Element for smooth operation for flexible operation of TG set at 40% technical minimum operation. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#1 to 4 Khaperkheda TPS. | 0 | - | 0 | 60 | 60 | 0 | 0 | 0 |  |  | 0 | 0
6.2 | Upgradation of various governing Element for smooth operation for flexible operation of TG set at 40% technical minimum operation. | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
7 | Upgradation of Battery Charger , UPS system , GEHO PLC and VFD, ID VFD, supply of Efficiency Measuring Instruments and Supply, erection and commissioning of Sox, Nox , CO, Opacity, ETP and Oxygen Analyser for Unit 1 to 4 of 210 MW at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Supply of Efficiency Monitoring Instruments for performance optimization group (POG) at Khaperkheda TPS. | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
7.2 | Upgradation of 220 V, 24 V DC Float cum boost battery charger at Unit#1 to 4 Khaperkheda TPS. | 0 | - | 0 | 5 | 5 | 0 | 5 | 5 |  |  | 5 | 0
7.3 | Upgradation of 2X50 KVA UPS at Unit#1 to 4 Khaperkheda TPS. | 0 | - | 0 | 2.5 | 2.5 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
7.4 | Supply, Erection and Commissioning of Sox, Nox , CO, Opacity and ETP Analyser for Unit 1 to 4 of 210 MW at Khaperkheda TPS | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
7.5 | Upgradation of GEHO PLC and VFD along with HCSD system Instrumentaion at Unit 3 & 4 Khaperkheda TPS. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
7.6 | Supply, Erection & Commissioning of Oxygen Analyzer for combustion optimization for Unit#1 to 5 Khaperkheda TPS. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
7.7 | Upgradation of VFD for ID FAN in Unit# 3 & 4, 210MW khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
7.8 | Scheme 8 Supply, erection & commissioning of PLC and SCADA System of Ash Evacuation and Disposal System for UNIT 3 and 4 Of 210 MW Khaperkheda TPS | 0 | - | 0 | 2.5 | 2.5 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
8 | Procurement of LP Rotor for unit 1 and 2 , Supply and installation of air washer unit 1 and 2 and refurbishment of air washer unit for unit 3 and 4 and GEHO Pummp house control room. Supply and installation of diesel engine driven fire fighting pump with engine. Procurement of various control valves for unit No. 1 to 4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.1 | Supply and installation of Air washer unit in unit 1 and 2 , 6.6 KV breaker room, Turbine MCC room Battery room Boiler MCC room for cooling of all the Electrical Panels and AHP stage I Pump House control room air washer system | 0 | - | 0 | 0 | 0 | 0 | 12 | 12 |  |  | 12 | 0
8.2 | Refurbishment of Air washer unit of 3 and 4, 6.6 KV breaker room, Turbine MCC room Battery room Boiler MCC room for cooling of all the Electrical Panels and Refurbishment of GEHO pump House and AHP stage II Pump House control room air washer system | 0 | - | 0 | 0 | 0 | 0 | 4 | 4 |  |  | 4 | 0
8.3 | Procurement of Complete LPT rotor for unit 1 and 2 | 0 | - | 0 | 0 | 0 | 0 | 20 | 20 |  |  | 20 | 0
8.4 | Revamping of diesel engine driven fire fighting pump system with engine. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
8.5 | Procurement of various control valves for unit No. 1 to 4 | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of IP Rotor and Inner casing for unit 1 and 2. Procurement of IP rotor and inner casing for unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.1 | Procurement of IP Rotor and Inner casing for unit 1 and 2. | 0 | - | 0 | 0 | 0 | 0 | 22 | 22 |  |  | 22 | 0
9.2 | Procurement of IP rotor and inner casing for unit 3 and 4 along with Turbovisory sensors and panel | 0 | - | 0 | 0 | 0 | 0 | 23 | 23 |  |  | 23 | 0
9.3 | Supply and installation of srew compressor for supply of instrument air to unit No. 3 and 4 along with dryer for unit No. 3 & 4. | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
10 | Procurement of LP rotor for unit 3 and 4 and upgradation of BFP cartridge and BFP Booster pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.1 | Procurement of of LP rotor for unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 25 | 25 |  |  | 25 | 0
10.2 | Upgradation of BFP cartridge and BFP Booster pump, motorized scoop for hydraulic coupling and drive unit for BFP and modulating BFP RC valve for Unit 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
11 | Refurbishment of LP rotor of unit 1 and 2 and Refurbishment of HPT module of unit 1 and 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.1 | Refurbishment of LP rotor of unit 1 and 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.2 | Refurbishment of HPT module of unit 1 and 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Refurbishment of LP rotor for unit 3 and 4 and Refurbishment and re-blading of HPT module of unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.1 | Refurbishment of LP rotors for unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.2 | Refurbishment of HPT modules of unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | SITC OF COMPLETE SOLUTION AND COMPREHENSIVE PROTECTION AND MONITORING PACKAGE ALONG WITH RETROFIT OF ALLIED ACCESSORIES FOR VARIOUS GTs & STs INSTALLED AT 210 MW KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | SUPPLY,INSTALLATION, TESTING & COMMISSIONING OF COMPLETE SOLUTION AND COMPREHENSIVE PROTECTION AND MONITORING PACKAGE ALONG WITH RETROFIT OF ALLIED ACCESSORIES FOR VARIOUS GTs & STs INSTALLED AT 210 MW KHAPERKHEDA TPS. | 0 | - | 0 | 6.5 | 6.5 | 0 | 19.5 | 19.5 |  |  | 19.5 | 0
14 | PLANT PERFORMANCE IMPROVEMENT BY DESIGN, SUPPLY, INSTALLATION & COMMISSIONING OF STATE OF ART HT VACCUM CIRCUIT BREAERS AT UNIT 1 TO 4 OF 210MW KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.1 | DESIGN, SUPPLY, INSTALLATION, TESTING & COMMISSIONING OF HT VCB AT U # 1 & 2. | 0 | - | 0 | 15.14 | 15.14 | 0 | 0 | 0 |  |  | 0 | 0
14.2 | DESIGN, SUPPLY, INSTALLATION, TESTING & COMMISSIONING OF HT VCB AT U # 3 & 4. | 0 | - | 0 | 16.5 | 16.5 | 0 | 0 | 0 |  |  | 0 | 0
15 | DESIGN, SUPPLY, INSTALLATION, TESTING AND COMMISSIONING OF THE VARIOUS LIFTS IN PLACE OF THE EXISTING OLD LIFTS, LIGHTNING PROTECTION SYSTEM, EARTHING SYSTEM, AVIATION LIGHTING SYSTEM INSTALLED AT UNIT # 1 TO 4 OF 210 MW, KHAPERKHEDA TPS ON OEM BASIS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | DESIGN, SUPPLY, INSTALLATION, TESTING AND COMMISSIONING OF THE VARIOUS LIFTS IN PLACE OF THE EXISTING OLD LIFTS INSTALLED AT UNIT # 1 TO 4 OF 210 MW, KHAPERKHEDA TPS ON OEM BASIS. | 0 | - | 0 | 10.46 | 10.46 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Design, Engineering, Supply, Erection, Testing & Commissioning of lightning protection system at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
15.3 | Design, Engineering, Supply, Erection, Testing & Commissioning of Earthing of electrical system & various buildings at Khaperkheda TPS. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Design, Engineering, Supply, Erection, Testing & Commissioning of Aviation Lighting Syatem at Khaperkheda TPS. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
16 | SUPPLY OF SPARE GENERATOR ROTOR FOR U#3 &4, 210MW, TPS KHAPERKHEDA. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.1 | SUPPLY OF SPARE GENERATOR ROTOR FOR U#3 &4, 210MW, TPS KHAPERKHEDA. | 0 | - | 0 | 0 | 0 | 0 | 40 | 40 |  |  | 40 | 0
17 | PROCUREMENT OF ENERGY EFFICIENT MOTORS FOR U # 1 TO 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.1 | PROCUREMENT OF ENERGY EFFICIENT MOTORS FOR U # 1 & 2 OF KHAPERKHEDA TPS. | 0 | - | 0 | 11 | 11 | 0 | 0 | 0 |  |  | 0 | 0
17.2 | PROCUREMENT OF ENERGY EFFICIENT MOTORS FOR U # 3 & 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 14 | 14 | 0 | 0 | 0 |  |  | 0 | 0
17.3 | Procurement of DC motors for U # 1 & 2 of Khaperkheda TPS. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
17.4 | Procurement of DC motors for U # 3 & 4 of Khaperkheda TPS. | 0 | - | 0 | 2.5 | 2.5 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
18 | UPGRADATION OF EXISTING LT MCC PANEL WITH STATE OF ART LT MCC PANEL AT U # 1 TO 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | UPGRADATION OF EXISTING LT MCC PANEL WITH STATE OF ART LT MCC PANEL AT U # 1 & 2 OF KHAPERKHEDA TPS. | 0 | - | 0 | 6.25 | 6.25 | 0 | 6.25 | 6.25 |  |  | 6.25 | 0
18.2 | UPGRADATION OF EXISTING LT MCC PANEL WITH STATE OF ART LT MCC PANEL AT U # 3 & 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 6.25 | 6.25 |  |  | 6.25 | 0
18.3 | UPGRADATION OF HT BREAKER PANEL AT WAREGAON ASH BUND OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
18.4 | UPGRADATION OF HT BREAKER PANEL AT OLD PROJECT OFFICE OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
18.5 | Retrofitting of Existing L & T make LT MCC ACB by state or art ACB at U # 1 to 4 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
18.6 | Retrofitting of Existing ABB make LT MCC ACB by state or art ACB at U # 1 to 4 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
19 | ERECTION & COMMISIONING OF DRY TYPE CAST RESIN TRANSFORMERS FOR U # 1 TO 4 OF KHAPERKHEDA TPS & Design, Engineering, Supply, Erection, Testing & Commissioning of various Battery sets at Unit # 3 & 4 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | PROCUREMENT OF DRY TYPE CAST RESIN TRANSFORMERS FOR U # 1 & 2 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 4 | 4 |  |  | 4 | 0
19.2 | PROCUREMENT OF DRY TYPE CAST RESIN TRANSFORMERS FOR U # 3 & 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
19.3 | PROCUREMENT OF VFD TRANSFORMERS FOR ID FAN MOTOR U#3&4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
19.4 | Design, Engineering, Supply, Erection, Testing & Commissioning of various Battery sets at Unit # 3 & 4 of Khaperkheda TPS. | 0 | - | 0 | 12.5 | 12.5 | 0 | 12.5 | 12.5 |  |  | 12.5 | 0
20 | Study, Supply & Refurbishment of HCSD systems, ESP operation, ambience & various pump, & PLC schemes for the improvement of AHP-I at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.1 | STUDY. DESIGN & REFURBISHMENT WORKS OF HIGH CONCENTRATION SLURRY DISPOSAL SYSTEM (HCSD SYSTEM) UNITS #3&4 AT AHP-1, TPS KHAPERKHEDA. | 0 | - | 0 | 9.32 | 9.32 | 0 | 0 | 0 |  |  | 0 | 0
20.2 | STUDY, DESIGN & REFURBISHMENT WORKS OF ARTs AND ASSOCIATED MOUNTINGS & ACCESSORIES OF HCSD SYSTEM FOR AHP-I, TPS KHAPERKHEDA.” | 0 | - | 0 | 8.96 | 8.96 | 0 | 0 | 0 |  |  | 0 | 0
20.3 | ‘SUPPLY & REFURBISHMENT WORKS OF HCSD ASH SLURRY MIXER SYSTEM AT UNIT #3 &4 OF AHP-I, TPS KHAPERKHEDA’. | 0 | - | 0 | 2.85 | 2.85 | 0 | 0 | 0 |  |  | 0 | 0
20.4 | ‘STUDY, SUPPLY, RESTORATIONS & REPLACEMENT OF ALL INTERNAL SPARES OF D6 FIELD & RENOVATION OF D1 FIELD OF U3 DURING AOH FOR AHP-I, TPS KHAPERKHEDA’ | 0 | - | 0 | 2.92 | 2.92 | 0 | 0 | 0 |  |  | 0 | 0
20.5 | PROCUREMENT OF VARIOUS PUMPS IN RECYCLE WATER SYSTEM IN ASH HANDLING PLANT 4X210 MW AT KHAPARKHEDA TPS | 0 | - | 0 | 4.6 | 4.6 | 0 | 0 | 0 |  |  | 0 | 0
21 | Reliability improvement and complete replacement of ABC series with drive unit of ash slurry pipeline of 7 KM of 4*210MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Procurement and restoration of complete pipeline replacement of ABC series | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
21.2 | Procurement and restoration of complete drive unit replacement of ABC series | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
22 | Procurement and restoration of complete Bottom ash hopper replacement including entire structure, Clinker grinder alongwith motor, Feed Gate, Power Cylinder and Pipelines discharge of U3&4 of 4*210MW Khaparkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.1 | Procurement and restoration of complete BAH replacement including entire structure and clinker griender | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.2 | Procurement and restoration of complete drive unit of clinker grinder for Unit 1 to 4 | 0 | - | 0 | 1.6 | 1.6 | 0 | 1.6 | 1.6 |  |  | 1.6 | 0
22.3 | Procurement and restoration of discharge pipeline of vertical sump pump | 0 | - | 0 | 0 | 0 | 0 | 4 | 4 |  |  | 4 | 0
23 | Procurement and restoration of Pipeline garlanding at Waregaon ash Bund of 4*210 MW Khapakheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.1 | Pipeline garlanding at Waregaon ash Bund of 4*210 MW Khapakheda TPS | 0 | - | 0 | 0 | 0 | 0 | 15 | 15 |  |  | 15 | 0
24 | Upgradation, modification and erection of complete wet fly ash evacuation into dry fly ash evacuation systen for ESP 1 and 2 of 4*210 MW Khapakheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.1 | Upgradation, modification and erection of complete wet fly ash evacuation into dry fly ash evacuation systen for ESP 1 and 2, 4*210 MW Khapakheda TPS | 0 | - | 0 | 0 | 0 | 0 | 100 | 100 |  |  | 100 | 0
25 | Reliability improvement and complete replacement of JKL series with drive unit of ash slurry pipeline of 7 KM of 4*210MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.1 | Procurement and restoration of complete pipeline replacement of JKL series | 0 | - | 0 | 0 | 0 | 0 | 20 | 20 |  |  | 20 | 0
25.2 | Procurement and restoration of complete drive unit replacement of JKL series | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
26 | Study, Supply and Refurbishment of HCSD System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.1 | Procurement of complete Suction and discharge valve of Geho pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.2 | Procurement of Subassemblies of Geho pump. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.3 | Upgradation and compressors of dry ash evacutaion system of U#3&4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.4 | Procuremenet of complete drive unit and VFD of GEHO pump. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | RENOVATION OF ESP FIELD INTERNALS FOR UNIT 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.1 | RENOVATION OF ESP FIELD INTERNALS FOR UNIT 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28 | R & M OF APH OF UNIT # 1& 2 (2 x 210MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28.1 | R & M OF APH OF UNIT # 1& 2 (2 x 210MW) OF KHAPERKHEDA TPS FROM MODEL: 27 VI 1850 TO 27 VI 2000 mm. DESIGN, ENGINEERING, SUPPLY, ERECTION & COMMISSIONING OF DOUBLE SEALING | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29 | DPR FOR ECONOMISER COILS AND APH GEAR BOX | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29.1 | PROCUREMENT AND REPLACEMENT OF COMPLETE SET OF ECONOMISER UPPER BANK & LOWER BANK COILS FOR KHAPERKHEDA TPS UNIT NO.3&4 | 0 | - | 0 | 22 | 22 | 0 | 0 | 0 |  |  | 0 | 0
29.2 | Procurement of APH gear box in unit no. 1 & 2 | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
29.3 | Procurement of APH speed reducer gear box in unit no. 3 & 4 | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
30 | DPR FOR LTSH COILS , APH BASKETS & RH OUTLET STUB BENDS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.1 | Procurement of Air Pre-heater Baskets for unit no. 2 to 4 | 0 | - | 0 | 0 | 0 | 0 | 3.5 | 3.5 |  |  | 3.5 | 0
30.2 | Procurement of LTSH coils for unit no. 1 & 2 and Procurement of Reheater outlet header stub bends for unit no. 1 to 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.3 | Procurement of LTSH coils for unit no. 3 & 4 and Procurement of Reheater outlet header stub bends for unit no. 3 to 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31 | DPR FOR SUPPLY & REPLACMENT OF THERMAL INSULATION OF BOILER AND DUCT AT UNIT 1 TO 4 KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.1 | SUPPLY & REPLACMENT OF THERMAL INSULATION OF BOILER AND DUCT AT UNIT 1 TO 2KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 20 | 20 |  |  | 20 | 0
31.2 | SUPPLY & REPLACMENT OF THERMAL INSULATION OF BOILER AND DUCT AT UNIT 3 TO 4 KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
32 | DPR FOR COAL CYCLE IMPROVEMENT IN UNIT NO.1 TO 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.1 | Procurement of Complete Journal Assembly for 803 ½ HP Coal Mills of Unit No. 1 To 2 | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
32.2 | Procurement of Complete Journal Assembly for XRP 883 Coal Mills of Unit No. 3 To 4, | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.3 | Procurement of assembly of worm shaft & worm wheel with hub for unit no. 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
32.4 | PROCUREMENT OF COMPLETE GEAR BOX ASSEMBLIES OF COAL MILLS XRP 803 ½ HP FOR UNIT # 1 TO 2 AT KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 7.5 | 7.5 |  |  | 7.5 | 0
32.5 | PROCUREMENT OF COMPLETE GEAR BOX ASSEMBLIES OF COAL MILLS XRP 883 FOR UNIT # 3 TO 4 AT KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 7.5 | 7.5 |  |  | 7.5 | 0
33 | DPR FOR PERFORMANCE IMPROVEMENT OF BOILER PA FAN, ID FAN AND FD FAN IN UNIT NO. 1 TO 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.1 | Procurement of PA fan Casings along with Dampers in Unit- 1 & 2, at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 17.75 | 17.75 |  |  | 17.75 | 0
33.2 | PROCUREMENT OF COMPLETE ROTOR ASSEMBLY ALONG WITH MOTOR FOR NDZV 31 SIDOR IN UNIT NO. 1 & 2 KHAPERKHEDA TPS (ID FAN) | 0 | - | 0 | 0 | 0 | 0 | 25 | 25 |  |  | 25 | 0
33.3 | PROCUREMENT OF FD FAN (BHEL AP 1-20 / 11) ASSEMBLY ALONG WITH DRIVE UNIT(MOTOR) FOR UNIT 1 & 2 AT KHAPERKHEDA TPS UNDER OEM NATURE ITEMS | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
33.4 | PROCUREMENT OF FD FAN (BHEL AP 1-20 / 11) ASSEMBLY ALONG WITH DRIVE UNIT(MOTOR) FOR UNIT 3& 4 AT KHAPERKHEDA TPS UNDER OEM NATURE ITEMS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.5 | NDZV 33 SIDOR ID Fan Impeller Assembly for Unit 3 & 4 at TPS, Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.6 | Design, Engineering, Manufacturing, Supply & Commissioning including civil works for installation of 70 LPM lubricant ystems for PA Fans in unit no. 1&2. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.7 | Supply and installation of ID and PA foundation deck spring for unit no. 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34 | VARIOUS SCHEMES FOR BOILER PERFORMANCE IMPROVEMENT | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.1 | SUPPLY OF COAL MILL SEPERATOR & SCRAPPER BODIES FOR XRP-803 1/2 HP COAL MILLS IN UNIT 1 & 2 | 0 | - | 0 | 0 | 0 | 0 | 17.28 | 17.28 |  |  | 17.28 | 0
34.2 | MODIFICATION OF EXISTING COAL BUNKER AND COMMISSIONING OF BUNKER CHUTE ASSEMBLY WITH VIBRATING MOTOR TO AVOID BUNKER MOUTH COAL CHOKE UP FOR UNIT 1 & 2AT KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.3 | MODIFICATION OF EXISTING COAL BUNKER AND COMMISSIONING OF BUNKER CHUTE ASSEMBLY WITH VIBRATING MOTOR TO AVOID BUNKER MOUTH COAL CHOKE UP FOR UNIT 3 & 4 AT KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 9 | 9 |  |  | 9 | 0
34.4 | DESIGN, DEVELOPMENT, COMMISIONING OF SEAL AIR FAN ASSEMBLIES IN UNIT 1 & 2 | 0 | - | 0 | 0 | 0 | 0 | 4 | 4 |  |  | 4 | 0
34.5 | Procurement of sub body assembly of control valve in unit no. 1 & 2 actuating main gear unit part electrical actuator in unit no. 1 to 4 Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 4 | 4 |  |  | 4 | 0
35 | Construction of A, B, C, D & E type stilt + 6 floor buildings at TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Construction of A, B, C, D & E type stilt + 6 floor buildings at TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 180 | 180 |  |  | 180 | 0
36 | Enhancement & Renovation of existing building, Construction of Market building, Construction of club building community hall, Construction of school building, & Enhancement of existing domestic plant providing V wire 3 MLD at Colony TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.1 | Enhancement / Renovation & strengthening of existing building & allied works in colony TPS Khaperkhda. | 0 | - | 0 | 28 | 28 | 0 | 0 | 0 |  |  | 0 | 0
36.2 | Construction of Market building including approach road, drainage arrangement & electrification at colony TPS Khaperkheda | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
36.3 | Construction of club building / community hall | 0 | - | 0 | 0 | 0 | 0 | 8 | 8 |  |  | 8 | 0
36.4 | Construction of school building | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
36.5 | Enhancement of existing domestic plant providing V wire 3 MLD | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
37 | Enhancement / Renovation of Saudamini Administrative Building, Construction of VIP Guest House, Construction of roads at Prakashnagar Colony and Providing various civil works related to coal transport railway lines of khaperkheda TPSTPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.1 | Enhancement / Renovation of Saudamini building | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
37.2 | Construction of VIP guest house TPS Khaperkheda. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
37.3 | Construction of Roads | 0 | - | 0 | 13 | 13 | 0 | 0 | 0 |  |  | 0 | 0
37.4 | Construction of office building & store for electrical maintenance & Civil at KPKD | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
37.5 | Providing Special repair & retrofitting work of river bridge no.09 on Khaperkheda - Kalumna railway siding of TPS Khaperkheda. | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
37.6 | Construction & repairing of drains & culverts along coal Transporting Railway lines & approach road of TPS Khaperkheda. | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
37.7 | Repairing, providing & applying Epoxy Painting and Structural Steel Works to steel structural bridges on kpkd to Kaluma and kpkd to Saoner railway lines as per recommendation of structural stability report at TPS Khaperkheda. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
37.8 | Construction of compound wall KPKD Colony | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
38 | Work of Strengthening and modification of Main Plant, construction of roads, strengthening of IDCT 1 to 4 in plant area, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.1 | Work of attending additional works based on structural report at Induced Draft Cooling Towers(IDCT) unit 1,2,3 & 4 at 4 x 210MW, TPS, Khaperkheda. | 0 | - | 0 | 1.21 | 1.21 | 0 | 0 | 0 |  |  | 0 | 0
38.2 | Work of constructon of roadside drains from VIP gate no.3 to IDCT No.1 at 4 x 210MW TPS Khaperkheda. | 0 | - | 0 | 3.61 | 3.61 | 0 | 0 | 0 |  |  | 0 | 0
38.3 | Construction of bituminous macadam road from Administrative Building to GCR Road near Service Building of 4X210MW TPS Khaperkheda. | 0 | - | 0 | 2.7 | 2.7 | 0 | 0 | 0 |  |  | 0 | 0
38.4 | Work for Construction of cement concrete road for equipment movement for salt lagoon (WTP-I), FGD(System), H2(cylinders) plant etc. inside plant premises in 4x 210MW, TPS, Khaperkheda. | 0 | - | 0 | 3.63 | 3.63 | 0 | 0 | 0 |  |  | 0 | 0
38.5 | Construction of cement concrete road outside BTG area of Power Plant 4 x 210MW TPS Khaperkheda. | 0 | - | 0 | 8.92 | 8.92 | 0 | 0 | 0 |  |  | 0 | 0
38.6 | Construction of cement concrete road for material transportation from D-Point CHP to reject coal Dumping yard in 4x 210MW, TPS, Khaperkheda. | 0 | - | 0 | 5.94 | 5.94 | 0 | 0 | 0 |  |  | 0 | 0
38.7 | Work of Strengthening and modification of Main Plant, Major Stores, Auxiliary in plant area, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
38.8 | Construction of diversion road along with RCC bridge from rejct coal yard CHP-I & CHP-II | 0 | - | 0 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
38.9 | Upgradation of existing ETP plant consist civil works, electrification and pumps. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
39 | Work of 5th Raising of Waregaon Ash Bund, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
39.1 | Work of 5th Raising of Waregaon Ash Bund, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 150 | 150 | 0 | 0 | 0 |  |  | 0 | 0
40 | Work of CTR(Complete Track Removal),TTR(TRAIN TRAVLER REGULATOR) and Yard Remoulding incl. misc. works at Mahagenco Khaperkheda Plant. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
40.1 | Work of CTR(Complete Track Removal),TTR(TRAIN TRAVLER REGULATOR) and Yard Remoulding incl. misc. works at Mahagenco Khaperkheda Plant. | 0 | - | 0 | 178 | 178 | 0 | 0 | 0 |  |  | 0 | 0
41 | Various WTP 210MW improvement schemes i.e. Up-gradation of SWAS SYSTEM UNIT- 1 to 4 at WTP-I 210 MW along with coal sampling lab upgradation, Comissioning of CW Chemical Dosing system etc | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.1 | Upgradation of Existing ETP system viz. Plate Settler, Settling tank, Sludge Drying bed, Chemical dosing system etc.)as per MPCB consent condition | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
41.2 | Upgradation of SWAS Lab 3& 4 at WTP-210 MW | 0 | - | 0 | 9 | 9 | 0 | 0 | 0 |  |  | 0 | 0
41.3 | Revamping of Chlorination Plant Stream (A+ B) & Installation, Comissioning of CW Chemical Dosing system (Viz. Scale inhibitor, Scale Dispersant, Biodispersant, Corossion Inhibitor & H2SO4 dosing) and Online CW Chemical parameter monitoring system at KPKD TPS | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
41.4 | Upgradation of SWAS Lab 1& 2 at WTP-210 MW | 0 | - | 0 | 9 | 9 | 0 | 0 | 0 |  |  | 0 | 0
41.5 | Upgradation of Water &Coal testing Lab at WTP-210 MW &Procurement of Coal Lab Instruments and upgradation of coal sampling Room & Instruments related to Coal sample Preparation. at WTP-210 MW | 0 | - | 0 | 0 | 0 | 0 | 8.5 | 8.5 |  |  | 8.5 | 0
42 | Work of capacity restoration of unloading stream from Beetle Charger No. 1 to Stacker/Reclaimer No. 1 for perfromance improvement of CHP-I (4 x 210 MW) & Capacity restoration of unloading stream from Beetle Charger No. 1 to Stacker/Reclaimer No. 1 for perfromance improvement of CHP-I (4 x 210 MW). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.1 | Revamping/ refurbishment, capacity restoration and upgradation for beetle charger No. 1 | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
42.2 | Revamping/ refurbishment, capacity restoration and upgradation for Wagon Tippler No. 1 | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
42.3 | Revamping/ refurbishment, capacity restoration and upgradation for Apron Feeder No. 1 | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
42.4 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 2C, 3A, 4A, 8A, 9 | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
42.5 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for impact crusher and wobbler feeder No. 1 & 3 | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
42.6 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Stacker/Reclaimer No. 1. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
42.7 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv. 3C to 3A, Conv. 3A to 4A, Conv. 4A to 8A and Conv. 9 by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
42.8 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of beetle Charger, wagon tippler, apron feeder, covneyors (Conv. 2C, 3A, 4A, 8A, 9), crushers/ wobbler feeder No. 1 & 3 and Stacker/Reclaimer No. 1 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
43 | DPR fo Capacity restoration of bunkering stream from Conv. 5A to 7A/B/C/D including shuttle conveyors in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
43.1 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 5A, 6B, 7A, 7B, 7C, 7D and Shuttle Conv. 1 to 4 in CHP-I (4 x 210 MW) | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
43.2 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv.Conv. 4D to 5A/B , 5A to 6B, Conv. 6B to 7A & 7B, Conv. 7B to 7D upto shuttle conveyor, Conv. 7A to 7C upto shuttle conveyor by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
43.3 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of covneyors (Conv. 5A, 6B, 7A/B/C/D & Shuttle Conv. 1 to 4 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
44 | Work of capacity restoration of unloading stream from Beetle Charger No. 2 to Stacker/Reclaimer No. 2 for perfromance improvement of CHP-I (4 x 210 MW). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.1 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for beetle charger No. 2 | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
44.2 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Wagon Tippler No. 2 | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
44.3 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Apron Feeder No. 2 | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
44.4 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 2D, 3B, 4B, 8B, 10 | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
44.5 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for impact crusher and wobbler feeder No. 2 & 4 | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
44.6 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Stacker/Reclaimer No. 2. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
44.7 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv. 2D to 3B, Conv. 3B to 4B, Conv. 4B to 8B and Conv. 10 by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
44.8 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of beetle Charger, wagon tippler, apron feeder, covneyors (Conv. 2D, 3B, 4B, 8B, 10), crushers/ wobbler feeder No. 2 & 4 and Stacker/Reclaimer No. 2 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
45 | Work of capacity restoration of bunkering stream from Conv. 1A/B, 2A/B, 5B to 7E/F/G/H including shuttle conveyors in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.1 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 1A/B, 2A/B, 5B, 6A, 7E, 7F, 7G, 7H and Shuttle Conv. 5 to 8 in CHP-I (4 x 210 MW) | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
45.2 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv. 1A/b to 2A/B,Conv. 4C to 5A/B, Conv. 5B to 6A, Conv. 6A to 7E & 7F, Conv. 7E to 7G upto shuttle conveyor, Conv. 7F to 7H upto shuttle conveyor by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
45.3 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of conveyor system from Conv. 1A/B, 2A/B, 5B, 6A, 7E, 7F, 7G, 7H and Shuttle Conv. 5 to 8 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
45.4 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Paddel Feeder No. 1 to 4 and truck hopper in CHP-I (4 x 210 MW) | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
46 | Renovation and upgradation of various electrical system for CHP-I (4 x 210 MW) improvement & Renovation and upgradation of various electrical system for CHP-I (4 x 210 MW) improvement. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.1 | Design, development and upgradation with circuit breaker VFD of various LT MCC of CHP-I. | 0 | - | 0 | 17 | 17 | 0 | 0 | 0 |  |  | 0 | 0
46.2 | Design, Supply, Installation, Commissioning and Testing of Energy Chain System for Paddle Feeder, Shuttle Conveyor and Stacker/Reclaimers in CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
46.3 | Upgradation of relay logic system with PLC & SCADA in CHP-I control room and Wagon Tipplers in CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
46.4 | Complete upgradation of conveyor lighting system with energey efficient LED lights for CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
46.5 | Providing, installation, testing commissioning, maintenance and operation of explosion proof & weather proof surveillance system at CHP-I (4 X 210 MW), TPS Khaperkheda. | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
46.6 | Complete revamping/refurbishment, upgradation and modification of various EOT cranes & hoist installed at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 12 | 12 | 0 | 0 | 0 |  |  | 0 | 0
47 | Procurement of various capacity SAN make locomotives and BEML make loader & bulldozer for CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.1 | Procurement of various capacity SAN make locomotives and BEML make loader & bulldozer for CHP-I (4 x 210 MW) | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
48 | CHP Improvement Schemesfor 4x 210 MW units | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.1 | Design, manufacture, supply and installation of suspended magnet for bunkering belts at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
48.2 | Design, manufacture, supply and installation of travel drive system for shuttle conveyors and conveyors at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
48.3 | Renovation including replacement of Power & Control cables with automation & upgradation of Stacker Reclaimer No. 2 in CHP-I (4 X 210MW), TPS Khaperkheda." | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
48.4 | Complete reconditionding & upgradation of LT MCC installed at Unit No. 3 & 4 bunker auxiliareis in CHP-I (4 x 210 MW) | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
48.5 | Complete reconditionding & upgradation of outdoor lighting system in CHP-I (4 x 210 MW) | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
48.6 | Complete reconditionding & upgradation of HT breaker, control circuits & protection relays in CHP-I (4 x 210 MW) | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
48.7 | Complete revamping/refurbishment, upgradation and modification of various monorail hoists & winch machine installed at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
48.8 | Procurement of hydra 14 Ton above capacity and heavy vehicles for CHP- I & II. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
49 | Installation of Real Time Coal Analyzer at all TPS of Mahagenco | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
49.1 | Installation of Real time Coal Analyzer at Khaperkheda TPS | 0 | - | 0 | 31.42 | 31.42 | 0 | 0 | 0 |  |  | 0 | 0
50 | Railway expenses for refurbishment of OHE lines at CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50.1 | Railway expenses for refurbishment of OHE lines at CHP-I (4 x 210 MW) | 0 | - | 0 | 26 | 26 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | PROCUREMENT COMPLETE Gear BOX ASSEMBLIES FOR 803 1/2 HP & XRP 883 COAL MILLS OF UNIT NO. 1& 2 AT KHAPERKHEDA TPS. | N.A. | - | 0 | 4.5548 | 4.5548 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply Erection and commissioning of Oil Cooled Suspended magnets at Conv 6A & 6B at Khaperkheda TPS. | N.A. | - | 0 | 1.1484 | 1.1484 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurment of new 02 Ambulance Van & 2 Truck for KPKD TPS(Asset Nos. 170100512, 170100513, 170100514, 170100515) | N.A. | - | 0 | 0.41055 | 0.41055 | 0 | 0 | 0 |  |  | 0 | 0
4 | GEHO PUMP (Valve housing assembly) | N.A. | - | 0 | 8.7933 | 8.7933 | 0 | 0 | 0 |  |  | 0 | 0
5 | RESTORATION OF AHP OUTLET TO ESP INLET DUCTS U#1&2(Unit #2 Part only) | N.A. | - | 0 | 7.0042 | 7.0042 | 0 | 0 | 0 |  |  | 0 | 0
6 | ABC powder type and foam type composite Fire Extinguisher | N.A. | - | 0 | 0.714 | 0.714 | 0 | 0 | 0 |  |  | 0 | 0
7 | FFEQUIP HYDRAULIC JACK (BM-I) | N.A. | - | 0 | 0.57696 | 0.57696 | 0 | 0 | 0 |  |  | 0 | 0
8 | MOBILE COAL SAMPLING EQUIP-AUGER (FMC) CHP-I | N.A. | - | 0 | 1.5824 | 1.5824 | 0 | 0 | 0 |  |  | 0 | 0
9 | Replacement of ash slurry disposal pump to improve performance & capacity enhancement of ash slurry disposal system at AHP-1 Khaperkheda TPS | 0 | - | 0 | 4.92 | 4.92 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of Pillow Block Dodge Bearing Assemblies (Expansion & Non-Expansion) for PA fans in Unit- n1 to 4, at Khaperkheda TPS | 0 | - | 0 | 5.11 | 5.11 | 0 | 0 | 0 |  |  | 0 | 0
11 | Replacement of Economizer outlet to APH outlet common duct in unit no. 3 (210MW), Khaperkheda TPS | 0 | - | 0 | 6.24 | 6.24 | 0 | 0 | 0 |  |  | 0 | 0
12 | PROCUREMENT OF OIL COOLED SUSPENSION MAGNET FOR 210MW AND MODIFICATION & REPLACEMENT OF VIBRATING FEEDER WITH VIBRATING TRANSFER CHUTE FOR 210MW | 0 | - | 0 | 3.09 | 3.09 | 0 | 0 | 0 |  |  | 0 | 0
13 | DESIGN,ENGINEERING,MODIFICATION ,ERECTION AND COMMISSIONING OF DRIVE UNIT ARRANGEMENT FOR CONVEYOR 10 AT CHP1 | 0 | - | 0 | 1.65 | 1.65 | 0 | 0 | 0 |  |  | 0 | 0
14 | ENERGY EFFICIENT PLANT LIGHTING AND COLONY LIGHTING MODIFICATIONS | 0 | - | 0 | 21.04 | 21.04 | 0 | 0 | 0 |  |  | 0 | 0
15 | Supply installation testing and commisioning of various battery sets at unit No 1 & 2 of Khaperkheda TPS | 0 | - | 0 | 9.31 | 9.31 | 0 | 0 | 0 |  |  | 0 | 0
16 | Revamping and modification of existing alarm and protection system from fire and provide rapid extinguishing Clean Agent (CA) system at Unit #1 & 2 (210 MW) units, KPKD TPS | 0 | - | 0 | 8.21 | 8.21 | 0 | 0 | 0 |  |  | 0 | 0
17 | Supply of electronic modules for Procontrol DCS system in unit 1 to 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 1.18 | 1.18 | 0 | 0 | 0 |  |  | 0 | 0
18 | Revamping & UPGRADATION of SWAS system in unit 3 & 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 8.56 | 8.56 | 0 | 0 | 0 |  |  | 0 | 0
19 | Upgradation of process instrumentation in unit 1 to 2 of 210 MW Khaperkheda TPS | 0 | - | 0 | 4.64 | 4.64 | 0 | 0 | 0 |  |  | 0 | 0
20 | Replacement of flue gas duct from air heater outlet to esp inlet for U 1 & 2 (S+W) | 0 | - | 0 | 8.03 | 8.03 | 0 | 0 | 0 |  |  | 0 | 0
21 | PROCUREMENT OF COMPLETE ROTOR ASSEMBLY FOR NDZV 31 SIDOR IN UNIT NO. 1 & 2 KHAPERKHEDA TPS (ID FAN). | 0 | - | 0 | 14.52 | 14.52 | 0 | 0 | 0 |  |  | 0 | 0
22 | UPGRADATION OF BELT CONVEYOR CAPACITY OF 2C &2D AND 8A & 8B AT CHP1 | 0 | - | 0 | 3.94 | 3.94 | 0 | 0 | 0 |  |  | 0 | 0
23 | WORK OF DESIGN,ENGINEERING,ERECTION AND UPGRADATION OF DRIVE UNITS OF BELT CONVEYOR 3A & 3BAT CHP1 | 0 | - | 0 | 8.34 | 8.34 | 0 | 0 | 0 |  |  | 0 | 0
24 | Procurement of 1500 KW ID Fan Synchronous Motor at Unit 3 & 4 Khaperkheda TPS. | 0 | - | 0 | 3.12 | 3.12 | 0 | 0 | 0 |  |  | 0 | 0
25 | Procurement of Steam and Water Analysis System(SWAS) for Unit 1&2 (210MW) KPKD TPS, Khaperkheda. | 0 | - | 0 | 9.65 | 9.65 | 0 | 0 | 0 |  |  | 0 | 0
26 | Supply and replacement of complete PVC fills of cell of cooling tower of unit 1-4 (210 MW) at Khaperkheda TPS | 0 | - | 0 | 8.52 | 8.52 | 0 | 0 | 0 |  |  | 0 | 0
27 | PROCUREMENT OF FD FAN (BHEL AP 1-20/11) ASSEMBLY FOR UNIT 1 TO 4 ATKHAPERKHEDA TPS. | 0 | - | 0 | 4.37 | 4.37 | 0 | 0 | 0 |  |  | 0 | 0
28 | CHP performance improvement scheme for capacity restoration of drive units installed at CHP-1 (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 14.5 | 14.5 | 0 | 0 | 0 |  |  | 0 | 0
29 | Work of Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of belt conveyor 8A & 8B and belt conveyor 2C & 2D at CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 2.15 | 2.15 | 0 | 0 | 0 |  |  | 0 | 0
30 | WORK OF DESING,SUPPLY ,ERECTION,COMMISSIONG AND UPGRADATION OF COMPLETE ELECTRICAL SYSTEM FOR DRIVE UNITS OF BELT CONVEYOR 3A & 3B AND BELT CONVEYOR 4A,4B,4C & 4D AT CHP1 Khaperkheda TPS. | 0 | - | 0 | 2.29 | 2.29 | 0 | 0 | 0 |  |  | 0 | 0
31 | Supply, Installation, & Commissioning of Instruments at coal Testing Lab, WTP-I, TPS Khaperkheda. | 0 | - | 0 | 0.45 | 0.45 | 0 | 0 | 0 |  |  | 0 | 0
32 | Supply, Installation & Commissioning and Refurbishment of asbestos based H2 Generator and compressor to convert it to non-asbestos based H2 Generator for Unit 1 to 5, Khaperkheda TPS. | 0 | - | 0 | 7.65 | 7.65 | 0 | 0 | 0 |  |  | 0 | 0
33 | construction of bituminous macadam roads at Prakashnagar Colony TPS Khaperkheda | 0 | - | 0 | 5.4 | 5.4 | 0 | 0 | 0 |  |  | 0 | 0
34 | Work of attending additional works based on structural report at Induced Draft Cooling Towers (IDCT) unit 1,2,3 & 4 at 4 x 210MW, TPS, Khaperkheda | 0 | - | 0 | 1.21 | 1.21 | 0 | 0 | 0 |  |  | 0 | 0
35 | VIBRATION ANALYSER | 0 | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
36 | Upgradation of GEHO pump instrumentation for AHP Unit No. 3 & 4 (210 MW) at Khaperkheda TPS | 0 | - | 0 | 1.27 | 1.27 | 0 | 0 | 0 |  |  | 0 | 0
37 | Refurbishment of HPT module for Unit 1 & 2 | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
38 | General Asset Furniture | N.A. | - | 0 | 0.86177 | 0.86177 | 0 | 0 | 0 |  |  | 0 | 0
39 | General Asset AC, Fans, Air coolers, water filter etc. | N.A. | - | 0 | 0.53608 | 0.41552 | 0.12056 | 0 | 0 |  |  | 0 | 0.12056
40 | General Asset Computer, scanners, etc. | N.A. | - | 0 | 2.5598 | 1.9461 | 0.61367 | 0 | 0 |  |  | 0 | 0.61367
41 | Land aquired for rly siding | N.A. | - | 0 | 0.4072 | 0.4072 | 0 | 0 | 0 |  |  | 0 | 0
42 | RCC ROAD FROM ASH SILO TO 'D' POINT FOR BULKER MO | N.A. | - | 0 | 0.95225 | 0.95225 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 2701.0569 | 2750.7916 | -49.7348 | 777.49 | 777.49 | 0 | 0 | 777.49 | -49.7348
FY 2028-29
a) DPR Schemes
(i) Submitted to MERC
| Combustion optimization system | [6 empty] | 0 | 0
1 | Dynamic coal flow measurement and control (balancing) system (one) | [6 empty] | 0 | 0
1.2 | CO analyser (8 units) | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 | 1.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Oxygen analyser (32 units) | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 | 0.783 | 0.75683 | 0.75683 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Spare HPT module for Khaparkheda Unit 1 & 2 | MERC/CAP/DPR/10/2010-11/1466 | 2010-10-26 | 26.459 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | HPT module 1 No (unit # 1) | MERC/CAP/DPR/10/2010-11/1466 | 2010-10-26 | 23.0379 | 23.9074 | 23.9074 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAP/DPR/10/2010-11/1466 | 2010-10-26 | 3.4211 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Economiser Upper Bank & Lower Bank coils for Khaperkheda Unit no. 3 and Unit no. 4 | MERC/CAP/DPR/10/2010-11/1695 | 2010-12-15 | 26.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Economiser Upper Bank & Lower Bank coils for Khaperkheda Unit no. 3 and Unit no. 4 | MERC/CAP/DPR/10/2010-11/1695 | 2010-12-15 | 26.35 | 11.77 | 11.77 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Economiser & LTSH Upper Bank & Lower Bank coils for Khaperkheda Unit no. 1 and Unit no. 2 | MERC/CAPEX/20112012/01155 | 2011-07-29 | 34.7916 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Economiser & LTSH Coil for Unit 1 | MERC/CAPEX/20112012/01155 | 2011-07-29 | 15.6924 | 15.6924 | 15.6924 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Economiser & LTSH Coil for Unit 2 | MERC/CAPEX/20112012/01155 | 2011-07-29 | 16.1528 | 16.1528 | 16.1528 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20112012/01155 | 2011-07-29 | 2.9464 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Procurement & Replacement of Re-heater Rear Pendant Assembly Coils for 2*210MW Khaperkheda Unit no. 1 and Unit no. 2 | MERC/CAPEX/20122013/00603 | 2012-06-18 | 10.3738 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Re-heater coils for unit no. 1 | MERC/CAPEX/20122013/00603 | 2012-06-18 | 5.1267 | 5.1267 | 5.1267 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Re-heater coils for unit no. 2 | MERC/CAPEX/20122013/00603 | 2012-06-18 | 5.1267 | 5.55 | 5.55 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/00603 | 2012-06-18 | 0.1204 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Procurement of HPT module suitable for khaperkheda TPS Unit 3 & 4 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 36.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Procurement of HPT module suitable for khaperkheda TPS Unit 3 & 4 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 36.2 | 32.4016 | 32.4016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7 | Procurement Spare GTR, Locomotive & Compactors | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 18.4521 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | 250 MVA Spare GTR | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 10.3496 | 11.2511 | 11.2511 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.2 | Procurement of Locomotive 2no’s. | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 5.9927 | 5.9927 | 5.9927 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.3 | Procurement of Compactors 2 no’s. | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 0.42979 | 0.4298 | 0.4298 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 1.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Procurement & Replacement of complete set of LTSH coils for Khaperkheda TPS Unit 3&4 | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 17.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement and replacement of LTSH coils for Khaperkheda TPS at U3 | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 8.58 | 3.4291 | 3.4291 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Procurement and replacement of LTSH coils for Khaperkheda TPS at U4 | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 8.58 | 3.1809 | 3.1809 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 0.65 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Development of Ash Bund (Waregaon) at K'kheda TPS | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 38.7459 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Construction of 3rd upstream raising of existing ash bund from TBL 299.50 Mtr to 302.50 Mtr at Waregaon, Khaperkheda TPS. | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 33.8585 | 32.5375 | 32.5375 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.2 | Construction of masonary dam (Gabion structure) at Waregaon TPS, Khaperkheda. | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 1.0561 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.3 | Construction of approach to drain wells and raising height of drain well no. 1,2 & 3 ash bund at Waregaon, Khaperkheda TPS | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 0.48488 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 3.3464 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Various schemes related to CHP Improvement & Performance Optimization and scheme of conversion of existing Composite OHE to Conventional OHE | MERC/CAPEX/20152016/00422 | 2016-08-03 | 10.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Air Cooled Suspension Magnet for Con. 3 & 6 of CHP 210 MW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 2.18 | 2.2613 | 2.2613 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | Procurement of Impact crusher motor | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.84 | 0.52579 | 0.52579 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.3 | Procurement of 360V, 200 AH battery set and 360V 325 AH battery set for U# 1to 4 | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.1 | 1.4576 | 1.4576 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.4 | Procurement of POG Instruments for Unit 1 to 4 | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.77 | 0.35015 | 0.35015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.5 | Up gradation of safe scan flame scanner system by BHEL scan system in unit no. 1, 3 & 4 | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.6 | Up gradation of old AVR system to DAVR | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.7 | Conversion of existing Composite OHE to Conventional OHE | MERC/CAPEX/20152016/00422 | 2016-08-03 | 2.72 | 2.72 | 2.72 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.47 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | ESP up-gradation for Unit-1 at Khaperkheda TPS | MERC/CAPEX/20152016/01261 | 2016-01-11 | 32.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | ESP up-gradation for Unit-1 at Khaperkheda TPS | MERC/CAPEX/20152016/01261 | 2016-01-11 | 32.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Procurement, installation and commissioning of Gravimetric Belt / Rotary Type Feeder, VFD for CEP, Up-gradation of BTS system & Environmental schemes at Khaperkheda TPS | MERC/CAPEX/20162017/01552 | 2017-02-14 | 20.218 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Procurement, installation and commissioning of Gravimetric belt/rotary Feeder at U-1 & 2 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 5.72 | 4.7418 | 4.7418 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Installation of VFD to CEP at U-1 to 4 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 8.64 | 9.1408 | 9.14 | 0.000792 | 0 | 0 |  |  | 0 | 0.000792 | 0 | 0
13.3 | Installation of BTS system at U-4 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 0.98796 | 0.98796 | 0.98796 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.4 | Replacement of SOx/NOx analyzer at U-1 to 4 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 2.42 | 2.3035 | 2.3035 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.5 | Procurement of TGA,CHNS analyzer and Bomb calorimeter at U-5 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 1.71 | 0.2897 | 0.2897 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01552 | 2017-02-14 | 0.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Up gradation of HMI System at Unit No 3 & 4 at Khaperkheda TPS | MERC/CAPEX/20172018/03946 | 2017-07-19 | 13.39 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | HMI Up-gradation at U# 3 & 4 | MERC/CAPEX/20172018/03946 | 2017-07-19 | 12.78 | 12.5611 | 13.1811 | -0.62 | 0 | 0 |  |  | 0 | -0.62 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/03946 | 2017-07-19 | 0.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21 | Procurement of APH Basket for unit # 1 to 5 and Up-gradation of HT Motor Protection Relay in Unit # 1 to 4 at Khaperkheda TPS | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 9.77 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.1 | Procurement of assembly of baskets for air preheater of type bisector APH 27 VI: 1850, 12 sector in unit no. 1 & 2 and bisector APH 27 VI: 2000; 24 sector in unit no. 3 & 4 (210MW x 4) at TPS, Khaperkheda | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 5.71 | 8.097 | 8.0941 | 0.002845 | 0 | 0 |  |  | 0 | 0.002845 | 0 | 0
21.3 | Up-gradation of H.T. Motor protection relays in Unit 1 to 4 (210MW), Khaperkheda TPS | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 3.96 | 3.2537 | 3.2537 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 0.1 | 0 | 0.18424 | -0.18424 | 0 | 0 |  |  | 0 | -0.18424 | 0 | 0
22 | Procurement of LPT rotor suitable for Unit # 3 & 4 of 210 MW at Khaperkheda TPS | MERC/CAPEX/2018-2019/132 | 2019-05-09 | 27.191 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.1 | Procurement of LPT rotor suitable for Unit # 3 & 4 of 210 MW at Khaperkheda TPS | MERC/CAPEX/2018-2019/132 | 2019-05-09 | 26.491 | 10.7515 | 10.7515 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2018-2019/132 | 2019-05-09 | 0.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23 | Supply, Erection & commissioning of HT Vacuum circuit Breakers & SF6 contactors at AHP (U#1-4) & CHP (U#1 to 5) and 160 KW VFD Panel with Motor for fire-fighting pumps at U#1 to 4 at Khaperkheda TPS | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 10.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.1 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at AHP (Unit#1 to 4, 210MW), Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 4.17 | 3.4843 | 4.8883 | -1.404 | 0 | 0 |  |  | 0 | -1.404 | 0 | 0
23.2 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at CHP (Unit#1 to 4, 210MW) and CHP (Unit#5, 500MW) Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 3.81 | 4.031 | 2.7332 | 1.2978 | 0 | 0 |  |  | 0 | 1.2978 | 0 | 0
23.3 | Supply, Erection & commissioning of 150 KW VFD Panel with motor for fire-fighting pumps at 210 MW Khaperkheda TPS. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 2.34 | 2.0957 | 2.0957 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 0.58 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24 | Augmentation of Waregaon Ash Water Recovery System at TPS Khaperkheda | MERC/CAPEX/2019-20/732 | 2019-09-16 | 17.1984 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.1 | Augmentation of Waregaon Ash Water Recovery System at TPS Khaperkheda | MERC/CAPEX/2019-20/732 | 2019-09-16 | 15.7884 | 15.1987 | 15.1987 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-20/732 | 2019-09-16 | 1.41 | 0.58812 | 0.58812 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25 | Procurement of VFD with HMI & Controller & Replacing with existing Eddy-current drives of Coal feeders at U# 3 & 4 and Procurement of Various Critical Components of GEHO Pump (Model-TZPM 800) for AHP-1 at Khaperkheda TPS | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 10.6535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25.1 | Up-gradation of Existing BHEL make 36” Gravimetric Coal Feeders control panel with HMI and croprocessor based Controller with VFD, Motor & Weigh Module at Unit 3 & 4, (210MW) | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 7.4655 | 7.7 | 7.7 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25.2 | Procurement of various Critical Components of GEHO Pump (Model-TZPM 800) for AHP-1 (210MW) | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 2.698 | 2.6466 | 2.6466 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 0.49 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26 | Procurement, Replacement of Eco Coils U#1&2 210 MW, & Procurement & replacement of foundation Deck Spring assembly for coal mills U#3,4 at Khaperkheda TPS | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 15.4086 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26.1 | Procurement, Replacement of Eco Coils U#1&2 | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 7.4996 | 6.6503 | 6.6503 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26.2 | Procurement & replacement of foundation Deck Spring assembly for coal mills U#3,4 | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 6.679 | 7.0955 | 7.1 | -0.004476 | 0 | 0 |  |  | 0 | -0.004476 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 1.23 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28 | ESP Upgradation of 5 Nos. of 210/500MW Units at Khaperkheda, Koradi & Chandrapur TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 90.3535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.1 | ESP Upgradation at Unit #1, Khaperkheda TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 42.7114 | 59.55 | 54.445 | 5.105 | 0 | 0 |  |  | 0 | 5.105 | 0 | 0
28.2 | ESP Upgradation at Unit #2, Khaperkheda TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 42.7114 | 59.55 | 54.445 | 5.105 | 0 | 0 |  |  | 0 | 5.105 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 4.9307 | 0 | 16 | -16 | 0 | 0 |  |  | 0 | -16 | 0 | 0
29 | Flue Gas Desulphurisation System for Khaperkheda Unit # 1-4 | MERC/CAPEX/2021-2022/MSPGCL/097 | 2022-03-14 | 113.4565 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.1 | FGD System for Khaperkheda Unit # 1-4 | MERC/CAPEX/2021-2022/MSPGCL/097 | 2022-03-14 | 109.15 | 255.58 | 130.03 | 125.55 | 0 | 0 |  |  | 0 | 125.55 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/097 | 2022-03-14 | 4.3065 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4 | Construction of coal platform for Chandrapur TPS, Khaperkheda TPS & Parli TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 5.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4.2 | Khaperkheda TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 5.43 | 3.9936 | 3.9936 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 4.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.4a | 1. Procurement of 6.6 KV,300 KW, P.A.fan motor for U# 1 & 2 2. Procurement of 6.6 KV,425 KW,CM motor for U # 3 & 4 3. Procurement of 6.6 KV,1400KW,CW pump motor for U-1& 2 4. Procurement of 6.6 KV,1400 KW,CW pump motor for U-3&4 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 3.82 | 2.5973 | 2.5973 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.4b | K'kheda: Procurement of HT Motors(GS/HP Water pump)for U-1&2 and Procurement of HT Motors (ACW)for U-3&4 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 1 | 0.4 | 0.4 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.2 | KHAPERKHEDA (U-1 to 4) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.96 | 3.1173 | 3.1173 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.2 | Khaperkheda TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender for KPKD 1-4 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 1.7765 | 1.7765 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.2 | Normal Multipurpose Fire Tender KPKD 1-4 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 2.1847 | 2.1847 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 226.3024 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9.1 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 226.3024 | 291.23 | 331.4177 | -40.1877 | 0 | 0 |  |  | 0 | -40.1877 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 4.4604 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.2a | Compond wall (IB recommdation),Plant Patrolling Roads (IB recommdation) TPS KPKD | MERC/CAPEX/20172018/0177 | 2018-02-06 | 4.4604 | 3.9506 | 3.9506 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 9.23 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11.1 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 9.05 | 13.3057 | 13.3057 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 0.18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15 | Implementation of Water Flow Monitoring system at Chandrapur STPS & Khaperkheda TPS | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 5.1755 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.3 | Electromagnetic Flow meters at various lines & Locations of 210 MW | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 3.8515 | 3.8515 | 3.8515 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.4 | Automation: Centralized SCADA, RTU, MODBUS Cable, Power cable & mandatory spares | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 1.324 | 1.324 | 1.324 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30 | Supply of spare Generator Rotor for UNIT 1 & 2, 210MW | MERC/CAPEX/2023-24/0184 | 2024-03-12 | 37.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.1 | Supply of spare Generator Rotor for UNIT 1 & 2, 210MW | MERC/CAPEX/2023-24/0184 | 2024-03-12 | 36.7 | 36.7 | 36.7 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2023-24/0184 | 2024-03-12 | 0.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M with raising of drain wells and modification of Masonary Dam (Waste Weir), 4 x210 MW, TPS, Khaperkheda | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 45.0535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.1 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M at TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 31.0231 | 31.22 | 31.22 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.2 | Raising of drain wells of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 1.6569 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.3 | Modification of Masonary Dam (Waste Weir) of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 10.1857 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 2.1878 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
32 | Flue Gas Desulphurisation (FGD) System for Khaperkheda Unit # 1 & 2 | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 115.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
32.1 | Flue Gas Desulphurisation (FGD) System for Khaperkheda Unit # 1 & 2 | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 109.8 | 0 | 129.13 | -129.13 | 0 | 0 |  |  | 0 | -129.13
0 | IDC | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 5.54 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33 | Upgradation of DDC/DCS system for UNIT 1 & 3 of 210 MWKhaperkheda TPS | MERC/CAPEX/MSPGCL/2023-24/601 | 2023-11-10 | 39.14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.1 | Upgradation of DDC/DCS system for UNIT 1 & 3 of 210 MWKhaperkheda TPS | MERC/CAPEX/MSPGCL/2023-24/601 | 2023-11-10 | 38.7 | 39.14 | 39.14 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/601 | 2023-11-10 | 0.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34 | Supply & commissioning of interconnection conveyor belt, Elecon make complete impact type crusher, Procurement of 4 NOs. Bull Dozer BEML BD-155 and Eco friendly and power efficient chiller system at Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 28.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.1 | Design, engineering, manufacturing, supply, erection & commissioning of interconnection conveyor belt from 1 X 500MW to 4 X 210MW stack yard at CHP Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.2 | Supply & installation of Elecon–make complete impact type crusher at CHP-I, Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 4.29 | 4.15 | 4.15 | 0 | 0 | 0 |  |  | 0 | 0
34.3 | Procurement of 4 NOs. Bull Dozer BEML BD-155 at CHP, Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.255 | 12.0596 | 12.0596 | 0 | 0 | 0 |  |  | 0 | 0
34.4 | Supply, erection, & commissioning of Eco friendly and power efficient chiller system for khaperkheda TPS Unit 1 to 4, Service Building and WTP in place of present reciprocating type Chiller system | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 11.96 | 11.45 | 11.45 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 1.385 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | 5 Nos. of Boiler Improvement Schemes for Unit No. 1 to 4 | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 32.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Procurement & replacement of Re-Heater Rear Pendent Assembly Coils for unit no. 3 & 4 (210 MW) | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 8.86 | 9.36 | 9.36 | 0 | 0 | 0 |  |  | 0 | 0
35.2 | Procurement Complete Set of Sky Climber For Unit#1 To 5 Boilers. | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 3.32 | 2.43 | 2.43 | 0 | 0 | 0 |  |  | 0 | 0
35.3 | Replacement of glasswool insulation and GI/CORRUGATED sheets of boiler and hot air ducts at unit 1to 4 KHAPERKHEDA TPS | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 2.19 | 1.99 | 1.99 | 0 | 0 | 0 |  |  | 0 | 0
35.4 | Procurement, design, manufacture, supply & delivery, dismantling, retrofitting, erection, commissioning and testing of gravimetric belt conveyor type coal feeders for unit no. 1 & 2. | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 6.68 | 6.77 | 6.77 | 0 | 0 | 0 |  |  | 0 | 0
35.5 | Procurement and Replacement of Air Preheater Baskets for Unit no. 1 to 4 (4x 210MW). | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 9.05 | 11.3735 | 11.3735 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 2.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR-17 | Various DPR Schemes for The work of maintaining the zero discharge condition of Pond No. 2 & Pond No.3 and providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 15.7443 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | The work of maintaining the zero discharge condition of Pond No.2 & Pond No.3 at KTPS Koradi | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 4.2068 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.2 | Providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 11.5375 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Scheme of HMI upgradation of unit 5 DCS along with Max Links , HART Scheme , PADO , all BOP PLCs , SWAS system, CO analyser & Coal feeder controller to match with the external aspect , process improvement & Up gradation of Generator Protections Relays in unit 1 to 4 of 210 MW at khaperkheda TPS | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 33.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.7 | Up-gradation of Generator Protections Relays in Unit 1 to 4 of 210 MW Khaperkheda TPS. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 8.31 | 8.86 | 8.86 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/478 | - | 0.86 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Submitted to MERC, Yet to receive approval | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR on Refurbishment of Spare HPT Module Unit 1 & 2 at TM-I and Procurement of Complete Gear Box Assemblies of Coal Mills XRP 803 ½ HP & XRP 883 for Unit No. 1 to 4 (4x210 MW), Khaperkheda TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Refurbishment of spare HPT module Unit 1 & 2 at TM-I (4X210 MW), KHAPERKHEDA TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Procurement of Complete Gear Box Assemblies of Coal Mills XRP 883 for Unit-1 to 4 (210MW). | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | SUPPLY INSTALLATION TESTING & COMMISSIONING REVAMPING OF FIRE DETECTION & ALARM AND PROTECTION SYSTEM FROM FIRE AND PROVIDING RAPID EXTINGUISHING CLEAN AGENT (CA) SYSTEM AT UNIT -3,4 & 5 ATKPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Supply Installation Testing & Commissioning , Revamping of fire protection and providing rapid extinguishing clean agent (CA) system at unit # 3 ,4 210 MW TPS, KHAPERKHEDA | 0 | - | 0 | 6.5 | 6.5 | 0 | 0 | 0 |  |  | 0 | 0
2 | Restoration of various Fire protection system at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Restoration of fire hydrant ring and fire water spray Header at Khaperkheda TPS | 0 | - | 0 | 13.14 | 13.14 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Restoration of deluge valve system at CHP-210MW | 0 | - | 0 | 25.44 | 25.44 | 0 | 0 | 0 |  |  | 0 | 0
3 | VARIOUS SCHEMES PROPOSED FOR IMPROVEMENT OF CHP-I (4 X 210 MW). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Design, Manufacturing, Supply, Erection, Commissioning & Testing of Coal Flow Management system for Coal Bunkers in CHP-I (4 X 210MW), Khaperkheda TPS. | 0 | - | 0 | 12.27 | 12.27 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Design, engineering, manufacturing, supply, installation and commissioning of Dedusting System for Crusher House and Bunker area in Unit 3 & 4 at CHP-I (4 X 210MW), Khaperkheda TPS. | 0 | - | 0 | 12.96 | 12.96 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Renovation including replacement of Power & Control cables with automation & upgradation of Stacker Reclaimer No. 1 in CHP-I (4 X 210MW), TPS Khaperkheda." | 0 | - | 0 | 8.59 | 8.59 | 0 | 0 | 0 |  |  | 0 | 0
4 | Flue Gas Desulphrisation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | FGD installation of 210MW unit 1 & 2 at Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Upgradation of DDC/DCS system for UNIT 2 & 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Upgradation of DDC/DCS system for UNIT 2 & 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 22.5 | 22.5 | 0 | 22.5 | 22.5 |  |  | 22.5 | 0
6 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#1 to 4 Khaperkheda TPS & Upgradation of various governing Element for smooth operation for flexible operation of TG set at 40% technical minimum operation. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#1 to 4 Khaperkheda TPS. | 0 | - | 0 | 60 | 60 | 0 | 0 | 0 |  |  | 0 | 0
6.2 | Upgradation of various governing Element for smooth operation for flexible operation of TG set at 40% technical minimum operation. | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
7 | Upgradation of Battery Charger , UPS system , GEHO PLC and VFD, ID VFD, supply of Efficiency Measuring Instruments and Supply, erection and commissioning of Sox, Nox , CO, Opacity, ETP and Oxygen Analyser for Unit 1 to 4 of 210 MW at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Supply of Efficiency Monitoring Instruments for performance optimization group (POG) at Khaperkheda TPS. | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
7.2 | Upgradation of 220 V, 24 V DC Float cum boost battery charger at Unit#1 to 4 Khaperkheda TPS. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
7.3 | Upgradation of 2X50 KVA UPS at Unit#1 to 4 Khaperkheda TPS. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
7.4 | Supply, Erection and Commissioning of Sox, Nox , CO, Opacity and ETP Analyser for Unit 1 to 4 of 210 MW at Khaperkheda TPS | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
7.5 | Upgradation of GEHO PLC and VFD along with HCSD system Instrumentaion at Unit 3 & 4 Khaperkheda TPS. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
7.6 | Supply, Erection & Commissioning of Oxygen Analyzer for combustion optimization for Unit#1 to 5 Khaperkheda TPS. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
7.7 | Upgradation of VFD for ID FAN in Unit# 3 & 4, 210MW khaperkheda TPS. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
7.8 | Scheme 8 Supply, erection & commissioning of PLC and SCADA System of Ash Evacuation and Disposal System for UNIT 3 and 4 Of 210 MW Khaperkheda TPS | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of LP Rotor for unit 1 and 2 , Supply and installation of air washer unit 1 and 2 and refurbishment of air washer unit for unit 3 and 4 and GEHO Pummp house control room. Supply and installation of diesel engine driven fire fighting pump with engine. Procurement of various control valves for unit No. 1 to 4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.1 | Supply and installation of Air washer unit in unit 1 and 2 , 6.6 KV breaker room, Turbine MCC room Battery room Boiler MCC room for cooling of all the Electrical Panels and AHP stage I Pump House control room air washer system | 0 | - | 0 | 12 | 12 | 0 | 0 | 0 |  |  | 0 | 0
8.2 | Refurbishment of Air washer unit of 3 and 4, 6.6 KV breaker room, Turbine MCC room Battery room Boiler MCC room for cooling of all the Electrical Panels and Refurbishment of GEHO pump House and AHP stage II Pump House control room air washer system | 0 | - | 0 | 4 | 4 | 0 | 4 | 4 |  |  | 4 | 0
8.3 | Procurement of Complete LPT rotor for unit 1 and 2 | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
8.4 | Revamping of diesel engine driven fire fighting pump system with engine. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
8.5 | Procurement of various control valves for unit No. 1 to 4 | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of IP Rotor and Inner casing for unit 1 and 2. Procurement of IP rotor and inner casing for unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.1 | Procurement of IP Rotor and Inner casing for unit 1 and 2. | 0 | - | 0 | 22 | 22 | 0 | 0 | 0 |  |  | 0 | 0
9.2 | Procurement of IP rotor and inner casing for unit 3 and 4 along with Turbovisory sensors and panel | 0 | - | 0 | 23 | 23 | 0 | 0 | 0 |  |  | 0 | 0
9.3 | Supply and installation of srew compressor for supply of instrument air to unit No. 3 and 4 along with dryer for unit No. 3 & 4. | 0 | - | 0 | 10 | 10 | 0 | 10 | 10 |  |  | 10 | 0
10 | Procurement of LP rotor for unit 3 and 4 and upgradation of BFP cartridge and BFP Booster pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.1 | Procurement of of LP rotor for unit 3 and 4 | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
10.2 | Upgradation of BFP cartridge and BFP Booster pump, motorized scoop for hydraulic coupling and drive unit for BFP and modulating BFP RC valve for Unit 3 & 4 | 0 | - | 0 | 10 | 10 | 0 | 10 | 10 |  |  | 10 | 0
11 | Refurbishment of LP rotor of unit 1 and 2 and Refurbishment of HPT module of unit 1 and 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.1 | Refurbishment of LP rotor of unit 1 and 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.2 | Refurbishment of HPT module of unit 1 and 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Refurbishment of LP rotor for unit 3 and 4 and Refurbishment and re-blading of HPT module of unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.1 | Refurbishment of LP rotors for unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.2 | Refurbishment of HPT modules of unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | SITC OF COMPLETE SOLUTION AND COMPREHENSIVE PROTECTION AND MONITORING PACKAGE ALONG WITH RETROFIT OF ALLIED ACCESSORIES FOR VARIOUS GTs & STs INSTALLED AT 210 MW KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | SUPPLY,INSTALLATION, TESTING & COMMISSIONING OF COMPLETE SOLUTION AND COMPREHENSIVE PROTECTION AND MONITORING PACKAGE ALONG WITH RETROFIT OF ALLIED ACCESSORIES FOR VARIOUS GTs & STs INSTALLED AT 210 MW KHAPERKHEDA TPS. | 0 | - | 0 | 26 | 26 | 0 | 0 | 0 |  |  | 0 | 0
14 | PLANT PERFORMANCE IMPROVEMENT BY DESIGN, SUPPLY, INSTALLATION & COMMISSIONING OF STATE OF ART HT VACCUM CIRCUIT BREAERS AT UNIT 1 TO 4 OF 210MW KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.1 | DESIGN, SUPPLY, INSTALLATION, TESTING & COMMISSIONING OF HT VCB AT U # 1 & 2. | 0 | - | 0 | 15.14 | 15.14 | 0 | 0 | 0 |  |  | 0 | 0
14.2 | DESIGN, SUPPLY, INSTALLATION, TESTING & COMMISSIONING OF HT VCB AT U # 3 & 4. | 0 | - | 0 | 16.5 | 16.5 | 0 | 0 | 0 |  |  | 0 | 0
15 | DESIGN, SUPPLY, INSTALLATION, TESTING AND COMMISSIONING OF THE VARIOUS LIFTS IN PLACE OF THE EXISTING OLD LIFTS, LIGHTNING PROTECTION SYSTEM, EARTHING SYSTEM, AVIATION LIGHTING SYSTEM INSTALLED AT UNIT # 1 TO 4 OF 210 MW, KHAPERKHEDA TPS ON OEM BASIS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | DESIGN, SUPPLY, INSTALLATION, TESTING AND COMMISSIONING OF THE VARIOUS LIFTS IN PLACE OF THE EXISTING OLD LIFTS INSTALLED AT UNIT # 1 TO 4 OF 210 MW, KHAPERKHEDA TPS ON OEM BASIS. | 0 | - | 0 | 10.46 | 10.46 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Design, Engineering, Supply, Erection, Testing & Commissioning of lightning protection system at Khaperkheda TPS. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Design, Engineering, Supply, Erection, Testing & Commissioning of Earthing of electrical system & various buildings at Khaperkheda TPS. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Design, Engineering, Supply, Erection, Testing & Commissioning of Aviation Lighting Syatem at Khaperkheda TPS. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
16 | SUPPLY OF SPARE GENERATOR ROTOR FOR U#3 &4, 210MW, TPS KHAPERKHEDA. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.1 | SUPPLY OF SPARE GENERATOR ROTOR FOR U#3 &4, 210MW, TPS KHAPERKHEDA. | 0 | - | 0 | 40 | 40 | 0 | 0 | 0 |  |  | 0 | 0
17 | PROCUREMENT OF ENERGY EFFICIENT MOTORS FOR U # 1 TO 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.1 | PROCUREMENT OF ENERGY EFFICIENT MOTORS FOR U # 1 & 2 OF KHAPERKHEDA TPS. | 0 | - | 0 | 11 | 11 | 0 | 0 | 0 |  |  | 0 | 0
17.2 | PROCUREMENT OF ENERGY EFFICIENT MOTORS FOR U # 3 & 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 14 | 14 | 0 | 0 | 0 |  |  | 0 | 0
17.3 | Procurement of DC motors for U # 1 & 2 of Khaperkheda TPS. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
17.4 | Procurement of DC motors for U # 3 & 4 of Khaperkheda TPS. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
18 | UPGRADATION OF EXISTING LT MCC PANEL WITH STATE OF ART LT MCC PANEL AT U # 1 TO 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | UPGRADATION OF EXISTING LT MCC PANEL WITH STATE OF ART LT MCC PANEL AT U # 1 & 2 OF KHAPERKHEDA TPS. | 0 | - | 0 | 12.5 | 12.5 | 0 | 0 | 0 |  |  | 0 | 0
18.2 | UPGRADATION OF EXISTING LT MCC PANEL WITH STATE OF ART LT MCC PANEL AT U # 3 & 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 6.25 | 6.25 | 0 | 6.25 | 6.25 |  |  | 6.25 | 0
18.3 | UPGRADATION OF HT BREAKER PANEL AT WAREGAON ASH BUND OF KHAPERKHEDA TPS. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | UPGRADATION OF HT BREAKER PANEL AT OLD PROJECT OFFICE OF KHAPERKHEDA TPS. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
18.5 | Retrofitting of Existing L & T make LT MCC ACB by state or art ACB at U # 1 to 4 of Khaperkheda TPS. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
18.6 | Retrofitting of Existing ABB make LT MCC ACB by state or art ACB at U # 1 to 4 of Khaperkheda TPS. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
19 | ERECTION & COMMISIONING OF DRY TYPE CAST RESIN TRANSFORMERS FOR U # 1 TO 4 OF KHAPERKHEDA TPS & Design, Engineering, Supply, Erection, Testing & Commissioning of various Battery sets at Unit # 3 & 4 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | PROCUREMENT OF DRY TYPE CAST RESIN TRANSFORMERS FOR U # 1 & 2 OF KHAPERKHEDA TPS. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
19.2 | PROCUREMENT OF DRY TYPE CAST RESIN TRANSFORMERS FOR U # 3 & 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
19.3 | PROCUREMENT OF VFD TRANSFORMERS FOR ID FAN MOTOR U#3&4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 1 | 1 | 0 | 1 | 1 |  |  | 1 | 0
19.4 | Design, Engineering, Supply, Erection, Testing & Commissioning of various Battery sets at Unit # 3 & 4 of Khaperkheda TPS. | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
20 | Study, Supply & Refurbishment of HCSD systems, ESP operation, ambience & various pump, & PLC schemes for the improvement of AHP-I at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.1 | STUDY. DESIGN & REFURBISHMENT WORKS OF HIGH CONCENTRATION SLURRY DISPOSAL SYSTEM (HCSD SYSTEM) UNITS #3&4 AT AHP-1, TPS KHAPERKHEDA. | 0 | - | 0 | 9.32 | 9.32 | 0 | 0 | 0 |  |  | 0 | 0
20.2 | STUDY, DESIGN & REFURBISHMENT WORKS OF ARTs AND ASSOCIATED MOUNTINGS & ACCESSORIES OF HCSD SYSTEM FOR AHP-I, TPS KHAPERKHEDA.” | 0 | - | 0 | 8.96 | 8.96 | 0 | 0 | 0 |  |  | 0 | 0
20.3 | ‘SUPPLY & REFURBISHMENT WORKS OF HCSD ASH SLURRY MIXER SYSTEM AT UNIT #3 &4 OF AHP-I, TPS KHAPERKHEDA’. | 0 | - | 0 | 2.85 | 2.85 | 0 | 0 | 0 |  |  | 0 | 0
20.4 | ‘STUDY, SUPPLY, RESTORATIONS & REPLACEMENT OF ALL INTERNAL SPARES OF D6 FIELD & RENOVATION OF D1 FIELD OF U3 DURING AOH FOR AHP-I, TPS KHAPERKHEDA’ | 0 | - | 0 | 2.92 | 2.92 | 0 | 0 | 0 |  |  | 0 | 0
20.5 | PROCUREMENT OF VARIOUS PUMPS IN RECYCLE WATER SYSTEM IN ASH HANDLING PLANT 4X210 MW AT KHAPARKHEDA TPS | 0 | - | 0 | 4.6 | 4.6 | 0 | 0 | 0 |  |  | 0 | 0
21 | Reliability improvement and complete replacement of ABC series with drive unit of ash slurry pipeline of 7 KM of 4*210MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Procurement and restoration of complete pipeline replacement of ABC series | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
21.2 | Procurement and restoration of complete drive unit replacement of ABC series | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
22 | Procurement and restoration of complete Bottom ash hopper replacement including entire structure, Clinker grinder alongwith motor, Feed Gate, Power Cylinder and Pipelines discharge of U3&4 of 4*210MW Khaparkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.1 | Procurement and restoration of complete BAH replacement including entire structure and clinker griender | 0 | - | 0 | 0 | 0 | 0 | 23 | 23 |  |  | 23 | 0
22.2 | Procurement and restoration of complete drive unit of clinker grinder for Unit 1 to 4 | 0 | - | 0 | 3.2 | 3.2 | 0 | 0 | 0 |  |  | 0 | 0
22.3 | Procurement and restoration of discharge pipeline of vertical sump pump | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
23 | Procurement and restoration of Pipeline garlanding at Waregaon ash Bund of 4*210 MW Khapakheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.1 | Pipeline garlanding at Waregaon ash Bund of 4*210 MW Khapakheda TPS | 0 | - | 0 | 15 | 15 | 0 | 15 | 15 |  |  | 15 | 0
24 | Upgradation, modification and erection of complete wet fly ash evacuation into dry fly ash evacuation systen for ESP 1 and 2 of 4*210 MW Khapakheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.1 | Upgradation, modification and erection of complete wet fly ash evacuation into dry fly ash evacuation systen for ESP 1 and 2, 4*210 MW Khapakheda TPS | 0 | - | 0 | 100 | 100 | 0 | 0 | 0 |  |  | 0 | 0
25 | Reliability improvement and complete replacement of JKL series with drive unit of ash slurry pipeline of 7 KM of 4*210MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.1 | Procurement and restoration of complete pipeline replacement of JKL series | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
25.2 | Procurement and restoration of complete drive unit replacement of JKL series | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
26 | Study, Supply and Refurbishment of HCSD System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.1 | Procurement of complete Suction and discharge valve of Geho pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.2 | Procurement of Subassemblies of Geho pump. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.3 | Upgradation and compressors of dry ash evacutaion system of U#3&4. | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
26.4 | Procuremenet of complete drive unit and VFD of GEHO pump. | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
27 | RENOVATION OF ESP FIELD INTERNALS FOR UNIT 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.1 | RENOVATION OF ESP FIELD INTERNALS FOR UNIT 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 30 | 30 |  |  | 30 | 0
28 | R & M OF APH OF UNIT # 1& 2 (2 x 210MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28.1 | R & M OF APH OF UNIT # 1& 2 (2 x 210MW) OF KHAPERKHEDA TPS FROM MODEL: 27 VI 1850 TO 27 VI 2000 mm. DESIGN, ENGINEERING, SUPPLY, ERECTION & COMMISSIONING OF DOUBLE SEALING | 0 | - | 0 | 0 | 0 | 0 | 18.4 | 18.4 |  |  | 18.4 | 0
29 | DPR FOR ECONOMISER COILS AND APH GEAR BOX | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29.1 | PROCUREMENT AND REPLACEMENT OF COMPLETE SET OF ECONOMISER UPPER BANK & LOWER BANK COILS FOR KHAPERKHEDA TPS UNIT NO.3&4 | 0 | - | 0 | 22 | 22 | 0 | 0 | 0 |  |  | 0 | 0
29.2 | Procurement of APH gear box in unit no. 1 & 2 | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
29.3 | Procurement of APH speed reducer gear box in unit no. 3 & 4 | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
30 | DPR FOR LTSH COILS , APH BASKETS & RH OUTLET STUB BENDS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.1 | Procurement of Air Pre-heater Baskets for unit no. 2 to 4 | 0 | - | 0 | 3.5 | 3.5 | 0 | 3.75 | 3.75 |  |  | 3.75 | 0
30.2 | Procurement of LTSH coils for unit no. 1 & 2 and Procurement of Reheater outlet header stub bends for unit no. 1 to 2 | 0 | - | 0 | 0 | 0 | 0 | 6 | 6 |  |  | 6 | 0
30.3 | Procurement of LTSH coils for unit no. 3 & 4 and Procurement of Reheater outlet header stub bends for unit no. 3 to 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31 | DPR FOR SUPPLY & REPLACMENT OF THERMAL INSULATION OF BOILER AND DUCT AT UNIT 1 TO 4 KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.1 | SUPPLY & REPLACMENT OF THERMAL INSULATION OF BOILER AND DUCT AT UNIT 1 TO 2KHAPERKHEDA TPS | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
31.2 | SUPPLY & REPLACMENT OF THERMAL INSULATION OF BOILER AND DUCT AT UNIT 3 TO 4 KHAPERKHEDA TPS | 0 | - | 0 | 10 | 10 | 0 | 10 | 10 |  |  | 10 | 0
32 | DPR FOR COAL CYCLE IMPROVEMENT IN UNIT NO.1 TO 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.1 | Procurement of Complete Journal Assembly for 803 ½ HP Coal Mills of Unit No. 1 To 2 | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
32.2 | Procurement of Complete Journal Assembly for XRP 883 Coal Mills of Unit No. 3 To 4, | 0 | - | 0 | 0 | 0 | 0 | 9.86 | 9.86 |  |  | 9.86 | 0
32.3 | Procurement of assembly of worm shaft & worm wheel with hub for unit no. 3 & 4 | 0 | - | 0 | 2.5 | 2.5 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
32.4 | PROCUREMENT OF COMPLETE GEAR BOX ASSEMBLIES OF COAL MILLS XRP 803 ½ HP FOR UNIT # 1 TO 2 AT KHAPERKHEDA TPS | 0 | - | 0 | 7.5 | 7.5 | 0 | 0 | 0 |  |  | 0 | 0
32.5 | PROCUREMENT OF COMPLETE GEAR BOX ASSEMBLIES OF COAL MILLS XRP 883 FOR UNIT # 3 TO 4 AT KHAPERKHEDA TPS | 0 | - | 0 | 7.5 | 7.5 | 0 | 0 | 0 |  |  | 0 | 0
33 | DPR FOR PERFORMANCE IMPROVEMENT OF BOILER PA FAN, ID FAN AND FD FAN IN UNIT NO. 1 TO 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.1 | Procurement of PA fan Casings along with Dampers in Unit- 1 & 2, at Khaperkheda TPS | 0 | - | 0 | 17.75 | 17.75 | 0 | 0 | 0 |  |  | 0 | 0
33.2 | PROCUREMENT OF COMPLETE ROTOR ASSEMBLY ALONG WITH MOTOR FOR NDZV 31 SIDOR IN UNIT NO. 1 & 2 KHAPERKHEDA TPS (ID FAN) | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
33.3 | PROCUREMENT OF FD FAN (BHEL AP 1-20 / 11) ASSEMBLY ALONG WITH DRIVE UNIT(MOTOR) FOR UNIT 1 & 2 AT KHAPERKHEDA TPS UNDER OEM NATURE ITEMS | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
33.4 | PROCUREMENT OF FD FAN (BHEL AP 1-20 / 11) ASSEMBLY ALONG WITH DRIVE UNIT(MOTOR) FOR UNIT 3& 4 AT KHAPERKHEDA TPS UNDER OEM NATURE ITEMS | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
33.5 | NDZV 33 SIDOR ID Fan Impeller Assembly for Unit 3 & 4 at TPS, Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 7.28 | 7.28 |  |  | 7.28 | 0
33.6 | Design, Engineering, Manufacturing, Supply & Commissioning including civil works for installation of 70 LPM lubricant ystems for PA Fans in unit no. 1&2. | 0 | - | 0 | 0 | 0 | 0 | 1.38 | 1.38 |  |  | 1.38 | 0
33.7 | Supply and installation of ID and PA foundation deck spring for unit no. 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34 | VARIOUS SCHEMES FOR BOILER PERFORMANCE IMPROVEMENT | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.1 | SUPPLY OF COAL MILL SEPERATOR & SCRAPPER BODIES FOR XRP-803 1/2 HP COAL MILLS IN UNIT 1 & 2 | 0 | - | 0 | 17.28 | 17.28 | 0 | 0 | 0 |  |  | 0 | 0
34.2 | MODIFICATION OF EXISTING COAL BUNKER AND COMMISSIONING OF BUNKER CHUTE ASSEMBLY WITH VIBRATING MOTOR TO AVOID BUNKER MOUTH COAL CHOKE UP FOR UNIT 1 & 2AT KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 9 | 9 |  |  | 9 | 0
34.3 | MODIFICATION OF EXISTING COAL BUNKER AND COMMISSIONING OF BUNKER CHUTE ASSEMBLY WITH VIBRATING MOTOR TO AVOID BUNKER MOUTH COAL CHOKE UP FOR UNIT 3 & 4 AT KHAPERKHEDA TPS. | 0 | - | 0 | 9 | 9 | 0 | 0 | 0 |  |  | 0 | 0
34.4 | DESIGN, DEVELOPMENT, COMMISIONING OF SEAL AIR FAN ASSEMBLIES IN UNIT 1 & 2 | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
34.5 | Procurement of sub body assembly of control valve in unit no. 1 & 2 actuating main gear unit part electrical actuator in unit no. 1 to 4 Khaperkheda TPS | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
35 | Construction of A, B, C, D & E type stilt + 6 floor buildings at TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Construction of A, B, C, D & E type stilt + 6 floor buildings at TPS Khaperkheda. | 0 | - | 0 | 180 | 180 | 0 | 0 | 0 |  |  | 0 | 0
36 | Enhancement & Renovation of existing building, Construction of Market building, Construction of club building community hall, Construction of school building, & Enhancement of existing domestic plant providing V wire 3 MLD at Colony TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.1 | Enhancement / Renovation & strengthening of existing building & allied works in colony TPS Khaperkhda. | 0 | - | 0 | 28 | 28 | 0 | 0 | 0 |  |  | 0 | 0
36.2 | Construction of Market building including approach road, drainage arrangement & electrification at colony TPS Khaperkheda | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
36.3 | Construction of club building / community hall | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
36.4 | Construction of school building | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
36.5 | Enhancement of existing domestic plant providing V wire 3 MLD | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
37 | Enhancement / Renovation of Saudamini Administrative Building, Construction of VIP Guest House, Construction of roads at Prakashnagar Colony and Providing various civil works related to coal transport railway lines of khaperkheda TPSTPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.1 | Enhancement / Renovation of Saudamini building | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
37.2 | Construction of VIP guest house TPS Khaperkheda. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
37.3 | Construction of Roads | 0 | - | 0 | 13 | 13 | 0 | 0 | 0 |  |  | 0 | 0
37.4 | Construction of office building & store for electrical maintenance & Civil at KPKD | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
37.5 | Providing Special repair & retrofitting work of river bridge no.09 on Khaperkheda - Kalumna railway siding of TPS Khaperkheda. | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
37.6 | Construction & repairing of drains & culverts along coal Transporting Railway lines & approach road of TPS Khaperkheda. | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
37.7 | Repairing, providing & applying Epoxy Painting and Structural Steel Works to steel structural bridges on kpkd to Kaluma and kpkd to Saoner railway lines as per recommendation of structural stability report at TPS Khaperkheda. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
37.8 | Construction of compound wall KPKD Colony | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
38 | Work of Strengthening and modification of Main Plant, construction of roads, strengthening of IDCT 1 to 4 in plant area, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.1 | Work of attending additional works based on structural report at Induced Draft Cooling Towers(IDCT) unit 1,2,3 & 4 at 4 x 210MW, TPS, Khaperkheda. | 0 | - | 0 | 1.21 | 1.21 | 0 | 0 | 0 |  |  | 0 | 0
38.2 | Work of constructon of roadside drains from VIP gate no.3 to IDCT No.1 at 4 x 210MW TPS Khaperkheda. | 0 | - | 0 | 3.61 | 3.61 | 0 | 0 | 0 |  |  | 0 | 0
38.3 | Construction of bituminous macadam road from Administrative Building to GCR Road near Service Building of 4X210MW TPS Khaperkheda. | 0 | - | 0 | 2.7 | 2.7 | 0 | 0 | 0 |  |  | 0 | 0
38.4 | Work for Construction of cement concrete road for equipment movement for salt lagoon (WTP-I), FGD(System), H2(cylinders) plant etc. inside plant premises in 4x 210MW, TPS, Khaperkheda. | 0 | - | 0 | 3.63 | 3.63 | 0 | 0 | 0 |  |  | 0 | 0
38.5 | Construction of cement concrete road outside BTG area of Power Plant 4 x 210MW TPS Khaperkheda. | 0 | - | 0 | 8.92 | 8.92 | 0 | 0 | 0 |  |  | 0 | 0
38.6 | Construction of cement concrete road for material transportation from D-Point CHP to reject coal Dumping yard in 4x 210MW, TPS, Khaperkheda. | 0 | - | 0 | 5.94 | 5.94 | 0 | 0 | 0 |  |  | 0 | 0
38.7 | Work of Strengthening and modification of Main Plant, Major Stores, Auxiliary in plant area, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
38.8 | Construction of diversion road along with RCC bridge from rejct coal yard CHP-I & CHP-II | 0 | - | 0 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
38.9 | Upgradation of existing ETP plant consist civil works, electrification and pumps. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
39 | Work of 5th Raising of Waregaon Ash Bund, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
39.1 | Work of 5th Raising of Waregaon Ash Bund, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 150 | 150 | 0 | 0 | 0 |  |  | 0 | 0
40 | Work of CTR(Complete Track Removal),TTR(TRAIN TRAVLER REGULATOR) and Yard Remoulding incl. misc. works at Mahagenco Khaperkheda Plant. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
40.1 | Work of CTR(Complete Track Removal),TTR(TRAIN TRAVLER REGULATOR) and Yard Remoulding incl. misc. works at Mahagenco Khaperkheda Plant. | 0 | - | 0 | 178 | 178 | 0 | 0 | 0 |  |  | 0 | 0
41 | Various WTP 210MW improvement schemes i.e. Up-gradation of SWAS SYSTEM UNIT- 1 to 4 at WTP-I 210 MW along with coal sampling lab upgradation, Comissioning of CW Chemical Dosing system etc | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.1 | Upgradation of Existing ETP system viz. Plate Settler, Settling tank, Sludge Drying bed, Chemical dosing system etc.)as per MPCB consent condition | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
41.2 | Upgradation of SWAS Lab 3& 4 at WTP-210 MW | 0 | - | 0 | 9 | 9 | 0 | 0 | 0 |  |  | 0 | 0
41.3 | Revamping of Chlorination Plant Stream (A+ B) & Installation, Comissioning of CW Chemical Dosing system (Viz. Scale inhibitor, Scale Dispersant, Biodispersant, Corossion Inhibitor & H2SO4 dosing) and Online CW Chemical parameter monitoring system at KPKD TPS | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
41.4 | Upgradation of SWAS Lab 1& 2 at WTP-210 MW | 0 | - | 0 | 9 | 9 | 0 | 0 | 0 |  |  | 0 | 0
41.5 | Upgradation of Water &Coal testing Lab at WTP-210 MW &Procurement of Coal Lab Instruments and upgradation of coal sampling Room & Instruments related to Coal sample Preparation. at WTP-210 MW | 0 | - | 0 | 8.5 | 8.5 | 0 | 0 | 0 |  |  | 0 | 0
42 | Work of capacity restoration of unloading stream from Beetle Charger No. 1 to Stacker/Reclaimer No. 1 for perfromance improvement of CHP-I (4 x 210 MW) & Capacity restoration of unloading stream from Beetle Charger No. 1 to Stacker/Reclaimer No. 1 for perfromance improvement of CHP-I (4 x 210 MW). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.1 | Revamping/ refurbishment, capacity restoration and upgradation for beetle charger No. 1 | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
42.2 | Revamping/ refurbishment, capacity restoration and upgradation for Wagon Tippler No. 1 | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
42.3 | Revamping/ refurbishment, capacity restoration and upgradation for Apron Feeder No. 1 | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
42.4 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 2C, 3A, 4A, 8A, 9 | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
42.5 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for impact crusher and wobbler feeder No. 1 & 3 | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
42.6 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Stacker/Reclaimer No. 1. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
42.7 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv. 3C to 3A, Conv. 3A to 4A, Conv. 4A to 8A and Conv. 9 by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
42.8 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of beetle Charger, wagon tippler, apron feeder, covneyors (Conv. 2C, 3A, 4A, 8A, 9), crushers/ wobbler feeder No. 1 & 3 and Stacker/Reclaimer No. 1 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
43 | DPR fo Capacity restoration of bunkering stream from Conv. 5A to 7A/B/C/D including shuttle conveyors in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
43.1 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 5A, 6B, 7A, 7B, 7C, 7D and Shuttle Conv. 1 to 4 in CHP-I (4 x 210 MW) | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
43.2 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv.Conv. 4D to 5A/B , 5A to 6B, Conv. 6B to 7A & 7B, Conv. 7B to 7D upto shuttle conveyor, Conv. 7A to 7C upto shuttle conveyor by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
43.3 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of covneyors (Conv. 5A, 6B, 7A/B/C/D & Shuttle Conv. 1 to 4 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
44 | Work of capacity restoration of unloading stream from Beetle Charger No. 2 to Stacker/Reclaimer No. 2 for perfromance improvement of CHP-I (4 x 210 MW). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.1 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for beetle charger No. 2 | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
44.2 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Wagon Tippler No. 2 | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
44.3 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Apron Feeder No. 2 | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
44.4 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 2D, 3B, 4B, 8B, 10 | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
44.5 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for impact crusher and wobbler feeder No. 2 & 4 | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
44.6 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Stacker/Reclaimer No. 2. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
44.7 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv. 2D to 3B, Conv. 3B to 4B, Conv. 4B to 8B and Conv. 10 by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
44.8 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of beetle Charger, wagon tippler, apron feeder, covneyors (Conv. 2D, 3B, 4B, 8B, 10), crushers/ wobbler feeder No. 2 & 4 and Stacker/Reclaimer No. 2 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
45 | Work of capacity restoration of bunkering stream from Conv. 1A/B, 2A/B, 5B to 7E/F/G/H including shuttle conveyors in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.1 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 1A/B, 2A/B, 5B, 6A, 7E, 7F, 7G, 7H and Shuttle Conv. 5 to 8 in CHP-I (4 x 210 MW) | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
45.2 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv. 1A/b to 2A/B,Conv. 4C to 5A/B, Conv. 5B to 6A, Conv. 6A to 7E & 7F, Conv. 7E to 7G upto shuttle conveyor, Conv. 7F to 7H upto shuttle conveyor by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
45.3 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of conveyor system from Conv. 1A/B, 2A/B, 5B, 6A, 7E, 7F, 7G, 7H and Shuttle Conv. 5 to 8 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
45.4 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Paddel Feeder No. 1 to 4 and truck hopper in CHP-I (4 x 210 MW) | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
46 | Renovation and upgradation of various electrical system for CHP-I (4 x 210 MW) improvement & Renovation and upgradation of various electrical system for CHP-I (4 x 210 MW) improvement. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.1 | Design, development and upgradation with circuit breaker VFD of various LT MCC of CHP-I. | 0 | - | 0 | 17 | 17 | 0 | 0 | 0 |  |  | 0 | 0
46.2 | Design, Supply, Installation, Commissioning and Testing of Energy Chain System for Paddle Feeder, Shuttle Conveyor and Stacker/Reclaimers in CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
46.3 | Upgradation of relay logic system with PLC & SCADA in CHP-I control room and Wagon Tipplers in CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
46.4 | Complete upgradation of conveyor lighting system with energey efficient LED lights for CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
46.5 | Providing, installation, testing commissioning, maintenance and operation of explosion proof & weather proof surveillance system at CHP-I (4 X 210 MW), TPS Khaperkheda. | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
46.6 | Complete revamping/refurbishment, upgradation and modification of various EOT cranes & hoist installed at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 12 | 12 | 0 | 0 | 0 |  |  | 0 | 0
47 | Procurement of various capacity SAN make locomotives and BEML make loader & bulldozer for CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.1 | Procurement of various capacity SAN make locomotives and BEML make loader & bulldozer for CHP-I (4 x 210 MW) | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
48 | CHP Improvement Schemesfor 4x 210 MW units | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.1 | Design, manufacture, supply and installation of suspended magnet for bunkering belts at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
48.2 | Design, manufacture, supply and installation of travel drive system for shuttle conveyors and conveyors at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
48.3 | Renovation including replacement of Power & Control cables with automation & upgradation of Stacker Reclaimer No. 2 in CHP-I (4 X 210MW), TPS Khaperkheda." | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
48.4 | Complete reconditionding & upgradation of LT MCC installed at Unit No. 3 & 4 bunker auxiliareis in CHP-I (4 x 210 MW) | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
48.5 | Complete reconditionding & upgradation of outdoor lighting system in CHP-I (4 x 210 MW) | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
48.6 | Complete reconditionding & upgradation of HT breaker, control circuits & protection relays in CHP-I (4 x 210 MW) | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
48.7 | Complete revamping/refurbishment, upgradation and modification of various monorail hoists & winch machine installed at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
48.8 | Procurement of hydra 14 Ton above capacity and heavy vehicles for CHP- I & II. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
49 | Installation of Real Time Coal Analyzer at all TPS of Mahagenco | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
49.1 | Installation of Real time Coal Analyzer at Khaperkheda TPS | 0 | - | 0 | 31.42 | 31.42 | 0 | 0 | 0 |  |  | 0 | 0
50 | Railway expenses for refurbishment of OHE lines at CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50.1 | Railway expenses for refurbishment of OHE lines at CHP-I (4 x 210 MW) | 0 | - | 0 | 26 | 26 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | PROCUREMENT COMPLETE Gear BOX ASSEMBLIES FOR 803 1/2 HP & XRP 883 COAL MILLS OF UNIT NO. 1& 2 AT KHAPERKHEDA TPS. | N.A. | - | 0 | 4.5548 | 4.5548 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply Erection and commissioning of Oil Cooled Suspended magnets at Conv 6A & 6B at Khaperkheda TPS. | N.A. | - | 0 | 1.1484 | 1.1484 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurment of new 02 Ambulance Van & 2 Truck for KPKD TPS(Asset Nos. 170100512, 170100513, 170100514, 170100515) | N.A. | - | 0 | 0.41055 | 0.41055 | 0 | 0 | 0 |  |  | 0 | 0
4 | GEHO PUMP (Valve housing assembly) | N.A. | - | 0 | 8.7933 | 8.7933 | 0 | 0 | 0 |  |  | 0 | 0
5 | RESTORATION OF AHP OUTLET TO ESP INLET DUCTS U#1&2(Unit #2 Part only) | N.A. | - | 0 | 7.0042 | 7.0042 | 0 | 0 | 0 |  |  | 0 | 0
6 | ABC powder type and foam type composite Fire Extinguisher | N.A. | - | 0 | 0.714 | 0.714 | 0 | 0 | 0 |  |  | 0 | 0
7 | FFEQUIP HYDRAULIC JACK (BM-I) | N.A. | - | 0 | 0.57696 | 0.57696 | 0 | 0 | 0 |  |  | 0 | 0
8 | MOBILE COAL SAMPLING EQUIP-AUGER (FMC) CHP-I | N.A. | - | 0 | 1.5824 | 1.5824 | 0 | 0 | 0 |  |  | 0 | 0
9 | Replacement of ash slurry disposal pump to improve performance & capacity enhancement of ash slurry disposal system at AHP-1 Khaperkheda TPS | 0 | - | 0 | 4.92 | 4.92 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of Pillow Block Dodge Bearing Assemblies (Expansion & Non-Expansion) for PA fans in Unit- n1 to 4, at Khaperkheda TPS | 0 | - | 0 | 5.11 | 5.11 | 0 | 0 | 0 |  |  | 0 | 0
11 | Replacement of Economizer outlet to APH outlet common duct in unit no. 3 (210MW), Khaperkheda TPS | 0 | - | 0 | 6.24 | 6.24 | 0 | 0 | 0 |  |  | 0 | 0
12 | PROCUREMENT OF OIL COOLED SUSPENSION MAGNET FOR 210MW AND MODIFICATION & REPLACEMENT OF VIBRATING FEEDER WITH VIBRATING TRANSFER CHUTE FOR 210MW | 0 | - | 0 | 3.09 | 3.09 | 0 | 0 | 0 |  |  | 0 | 0
13 | DESIGN,ENGINEERING,MODIFICATION ,ERECTION AND COMMISSIONING OF DRIVE UNIT ARRANGEMENT FOR CONVEYOR 10 AT CHP1 | 0 | - | 0 | 1.65 | 1.65 | 0 | 0 | 0 |  |  | 0 | 0
14 | ENERGY EFFICIENT PLANT LIGHTING AND COLONY LIGHTING MODIFICATIONS | 0 | - | 0 | 21.04 | 21.04 | 0 | 0 | 0 |  |  | 0 | 0
15 | Supply installation testing and commisioning of various battery sets at unit No 1 & 2 of Khaperkheda TPS | 0 | - | 0 | 9.31 | 9.31 | 0 | 0 | 0 |  |  | 0 | 0
16 | Revamping and modification of existing alarm and protection system from fire and provide rapid extinguishing Clean Agent (CA) system at Unit #1 & 2 (210 MW) units, KPKD TPS | 0 | - | 0 | 8.21 | 8.21 | 0 | 0 | 0 |  |  | 0 | 0
17 | Supply of electronic modules for Procontrol DCS system in unit 1 to 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 1.18 | 1.18 | 0 | 0 | 0 |  |  | 0 | 0
18 | Revamping & UPGRADATION of SWAS system in unit 3 & 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 8.56 | 8.56 | 0 | 0 | 0 |  |  | 0 | 0
19 | Upgradation of process instrumentation in unit 1 to 2 of 210 MW Khaperkheda TPS | 0 | - | 0 | 4.64 | 4.64 | 0 | 0 | 0 |  |  | 0 | 0
20 | Replacement of flue gas duct from air heater outlet to esp inlet for U 1 & 2 (S+W) | 0 | - | 0 | 8.03 | 8.03 | 0 | 0 | 0 |  |  | 0 | 0
21 | PROCUREMENT OF COMPLETE ROTOR ASSEMBLY FOR NDZV 31 SIDOR IN UNIT NO. 1 & 2 KHAPERKHEDA TPS (ID FAN). | 0 | - | 0 | 14.52 | 14.52 | 0 | 0 | 0 |  |  | 0 | 0
22 | UPGRADATION OF BELT CONVEYOR CAPACITY OF 2C &2D AND 8A & 8B AT CHP1 | 0 | - | 0 | 3.94 | 3.94 | 0 | 0 | 0 |  |  | 0 | 0
23 | WORK OF DESIGN,ENGINEERING,ERECTION AND UPGRADATION OF DRIVE UNITS OF BELT CONVEYOR 3A & 3BAT CHP1 | 0 | - | 0 | 8.34 | 8.34 | 0 | 0 | 0 |  |  | 0 | 0
24 | Procurement of 1500 KW ID Fan Synchronous Motor at Unit 3 & 4 Khaperkheda TPS. | 0 | - | 0 | 3.12 | 3.12 | 0 | 0 | 0 |  |  | 0 | 0
25 | Procurement of Steam and Water Analysis System(SWAS) for Unit 1&2 (210MW) KPKD TPS, Khaperkheda. | 0 | - | 0 | 9.65 | 9.65 | 0 | 0 | 0 |  |  | 0 | 0
26 | Supply and replacement of complete PVC fills of cell of cooling tower of unit 1-4 (210 MW) at Khaperkheda TPS | 0 | - | 0 | 8.52 | 8.52 | 0 | 0 | 0 |  |  | 0 | 0
27 | PROCUREMENT OF FD FAN (BHEL AP 1-20/11) ASSEMBLY FOR UNIT 1 TO 4 ATKHAPERKHEDA TPS. | 0 | - | 0 | 4.37 | 4.37 | 0 | 0 | 0 |  |  | 0 | 0
28 | CHP performance improvement scheme for capacity restoration of drive units installed at CHP-1 (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 14.5 | 14.5 | 0 | 0 | 0 |  |  | 0 | 0
29 | Work of Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of belt conveyor 8A & 8B and belt conveyor 2C & 2D at CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 2.15 | 2.15 | 0 | 0 | 0 |  |  | 0 | 0
30 | WORK OF DESING,SUPPLY ,ERECTION,COMMISSIONG AND UPGRADATION OF COMPLETE ELECTRICAL SYSTEM FOR DRIVE UNITS OF BELT CONVEYOR 3A & 3B AND BELT CONVEYOR 4A,4B,4C & 4D AT CHP1 Khaperkheda TPS. | 0 | - | 0 | 2.29 | 2.29 | 0 | 0 | 0 |  |  | 0 | 0
31 | Supply, Installation, & Commissioning of Instruments at coal Testing Lab, WTP-I, TPS Khaperkheda. | 0 | - | 0 | 0.45 | 0.45 | 0 | 0 | 0 |  |  | 0 | 0
32 | Supply, Installation & Commissioning and Refurbishment of asbestos based H2 Generator and compressor to convert it to non-asbestos based H2 Generator for Unit 1 to 5, Khaperkheda TPS. | 0 | - | 0 | 7.65 | 7.65 | 0 | 0 | 0 |  |  | 0 | 0
33 | construction of bituminous macadam roads at Prakashnagar Colony TPS Khaperkheda | 0 | - | 0 | 5.4 | 5.4 | 0 | 0 | 0 |  |  | 0 | 0
34 | Work of attending additional works based on structural report at Induced Draft Cooling Towers (IDCT) unit 1,2,3 & 4 at 4 x 210MW, TPS, Khaperkheda | 0 | - | 0 | 1.21 | 1.21 | 0 | 0 | 0 |  |  | 0 | 0
35 | VIBRATION ANALYSER | 0 | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
36 | Upgradation of GEHO pump instrumentation for AHP Unit No. 3 & 4 (210 MW) at Khaperkheda TPS | 0 | - | 0 | 1.27 | 1.27 | 0 | 0 | 0 |  |  | 0 | 0
37 | Refurbishment of HPT module for Unit 1 & 2 | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
38 | General Asset Furniture | N.A. | - | 0 | 0.86177 | 0.86177 | 0 | 0 | 0 |  |  | 0 | 0
39 | General Asset AC, Fans, Air coolers, water filter etc. | N.A. | - | 0 | 0.53608 | 0.41552 | 0.12056 | 0 | 0 |  |  | 0 | 0.12056
40 | General Asset Computer, scanners, etc. | N.A. | - | 0 | 2.5598 | 1.9461 | 0.61367 | 0 | 0 |  |  | 0 | 0.61367
41 | Land aquired for rly siding | N.A. | - | 0 | 0.4072 | 0.4072 | 0 | 0 | 0 |  |  | 0 | 0
42 | RCC ROAD FROM ASH SILO TO 'D' POINT FOR BULKER MO | N.A. | - | 0 | 0.95225 | 0.95225 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 3478.5469 | 3528.2816 | -49.7348 | 214.92 | 214.92 | 0 | 0 | 214.92 | -49.7348
FY 2029-30
a) DPR Schemes
(i) Submitted to MERC
| Combustion optimization system | [6 empty] | 0 | 0
1 | Dynamic coal flow measurement and control (balancing) system (one) | [6 empty] | 0 | 0
1.2 | CO analyser (8 units) | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 | 1.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Oxygen analyser (32 units) | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 | 0.783 | 0.75683 | 0.75683 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAP/DPR/10/2010-11/1491 | 2010-10-29 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Spare HPT module for Khaparkheda Unit 1 & 2 | MERC/CAP/DPR/10/2010-11/1466 | 2010-10-26 | 26.459 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | HPT module 1 No (unit # 1) | MERC/CAP/DPR/10/2010-11/1466 | 2010-10-26 | 23.0379 | 23.9074 | 23.9074 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAP/DPR/10/2010-11/1466 | 2010-10-26 | 3.4211 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Economiser Upper Bank & Lower Bank coils for Khaperkheda Unit no. 3 and Unit no. 4 | MERC/CAP/DPR/10/2010-11/1695 | 2010-12-15 | 26.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Economiser Upper Bank & Lower Bank coils for Khaperkheda Unit no. 3 and Unit no. 4 | MERC/CAP/DPR/10/2010-11/1695 | 2010-12-15 | 26.35 | 11.77 | 11.77 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Economiser & LTSH Upper Bank & Lower Bank coils for Khaperkheda Unit no. 1 and Unit no. 2 | MERC/CAPEX/20112012/01155 | 2011-07-29 | 34.7916 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Economiser & LTSH Coil for Unit 1 | MERC/CAPEX/20112012/01155 | 2011-07-29 | 15.6924 | 15.6924 | 15.6924 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Economiser & LTSH Coil for Unit 2 | MERC/CAPEX/20112012/01155 | 2011-07-29 | 16.1528 | 16.1528 | 16.1528 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20112012/01155 | 2011-07-29 | 2.9464 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Procurement & Replacement of Re-heater Rear Pendant Assembly Coils for 2*210MW Khaperkheda Unit no. 1 and Unit no. 2 | MERC/CAPEX/20122013/00603 | 2012-06-18 | 10.3738 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Re-heater coils for unit no. 1 | MERC/CAPEX/20122013/00603 | 2012-06-18 | 5.1267 | 5.1267 | 5.1267 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Re-heater coils for unit no. 2 | MERC/CAPEX/20122013/00603 | 2012-06-18 | 5.1267 | 5.55 | 5.55 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/00603 | 2012-06-18 | 0.1204 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Procurement of HPT module suitable for khaperkheda TPS Unit 3 & 4 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 36.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Procurement of HPT module suitable for khaperkheda TPS Unit 3 & 4 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 36.2 | 32.4016 | 32.4016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7 | Procurement Spare GTR, Locomotive & Compactors | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 18.4521 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | 250 MVA Spare GTR | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 10.3496 | 11.2511 | 11.2511 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.2 | Procurement of Locomotive 2no’s. | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 5.9927 | 5.9927 | 5.9927 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.3 | Procurement of Compactors 2 no’s. | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 0.42979 | 0.4298 | 0.4298 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH-1/CAPEX/ 20142015/00364 | 2014-05-20 | 1.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Procurement & Replacement of complete set of LTSH coils for Khaperkheda TPS Unit 3&4 | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 17.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement and replacement of LTSH coils for Khaperkheda TPS at U3 | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 8.58 | 3.4291 | 3.4291 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Procurement and replacement of LTSH coils for Khaperkheda TPS at U4 | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 8.58 | 3.1809 | 3.1809 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH-1/CAPEX/ 20142015/00363 | 2014-05-20 | 0.65 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Development of Ash Bund (Waregaon) at K'kheda TPS | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 38.7459 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Construction of 3rd upstream raising of existing ash bund from TBL 299.50 Mtr to 302.50 Mtr at Waregaon, Khaperkheda TPS. | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 33.8585 | 32.5375 | 32.5375 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.2 | Construction of masonary dam (Gabion structure) at Waregaon TPS, Khaperkheda. | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 1.0561 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.3 | Construction of approach to drain wells and raising height of drain well no. 1,2 & 3 ash bund at Waregaon, Khaperkheda TPS | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 0.48488 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 3.3464 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Various schemes related to CHP Improvement & Performance Optimization and scheme of conversion of existing Composite OHE to Conventional OHE | MERC/CAPEX/20152016/00422 | 2016-08-03 | 10.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Air Cooled Suspension Magnet for Con. 3 & 6 of CHP 210 MW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 2.18 | 2.2613 | 2.2613 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | Procurement of Impact crusher motor | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.84 | 0.52579 | 0.52579 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.3 | Procurement of 360V, 200 AH battery set and 360V 325 AH battery set for U# 1to 4 | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.1 | 1.4576 | 1.4576 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.4 | Procurement of POG Instruments for Unit 1 to 4 | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.77 | 0.35015 | 0.35015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.5 | Up gradation of safe scan flame scanner system by BHEL scan system in unit no. 1, 3 & 4 | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.6 | Up gradation of old AVR system to DAVR | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.7 | Conversion of existing Composite OHE to Conventional OHE | MERC/CAPEX/20152016/00422 | 2016-08-03 | 2.72 | 2.72 | 2.72 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.47 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | ESP up-gradation for Unit-1 at Khaperkheda TPS | MERC/CAPEX/20152016/01261 | 2016-01-11 | 32.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | ESP up-gradation for Unit-1 at Khaperkheda TPS | MERC/CAPEX/20152016/01261 | 2016-01-11 | 32.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Procurement, installation and commissioning of Gravimetric Belt / Rotary Type Feeder, VFD for CEP, Up-gradation of BTS system & Environmental schemes at Khaperkheda TPS | MERC/CAPEX/20162017/01552 | 2017-02-14 | 20.218 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Procurement, installation and commissioning of Gravimetric belt/rotary Feeder at U-1 & 2 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 5.72 | 4.7418 | 4.7418 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Installation of VFD to CEP at U-1 to 4 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 8.64 | 9.1408 | 9.14 | 0.000792 | 0 | 0 |  |  | 0 | 0.000792 | 0 | 0
13.3 | Installation of BTS system at U-4 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 0.98796 | 0.98796 | 0.98796 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.4 | Replacement of SOx/NOx analyzer at U-1 to 4 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 2.42 | 2.3035 | 2.3035 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.5 | Procurement of TGA,CHNS analyzer and Bomb calorimeter at U-5 | MERC/CAPEX/20162017/01552 | 2017-02-14 | 1.71 | 0.2897 | 0.2897 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01552 | 2017-02-14 | 0.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Up gradation of HMI System at Unit No 3 & 4 at Khaperkheda TPS | MERC/CAPEX/20172018/03946 | 2017-07-19 | 13.39 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | HMI Up-gradation at U# 3 & 4 | MERC/CAPEX/20172018/03946 | 2017-07-19 | 12.78 | 12.5611 | 13.1811 | -0.62 | 0 | 0 |  |  | 0 | -0.62 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/03946 | 2017-07-19 | 0.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21 | Procurement of APH Basket for unit # 1 to 5 and Up-gradation of HT Motor Protection Relay in Unit # 1 to 4 at Khaperkheda TPS | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 9.77 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.1 | Procurement of assembly of baskets for air preheater of type bisector APH 27 VI: 1850, 12 sector in unit no. 1 & 2 and bisector APH 27 VI: 2000; 24 sector in unit no. 3 & 4 (210MW x 4) at TPS, Khaperkheda | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 5.71 | 8.097 | 8.0941 | 0.002845 | 0 | 0 |  |  | 0 | 0.002845 | 0 | 0
21.3 | Up-gradation of H.T. Motor protection relays in Unit 1 to 4 (210MW), Khaperkheda TPS | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 3.96 | 3.2537 | 3.2537 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 0.1 | 0 | 0.18424 | -0.18424 | 0 | 0 |  |  | 0 | -0.18424 | 0 | 0
22 | Procurement of LPT rotor suitable for Unit # 3 & 4 of 210 MW at Khaperkheda TPS | MERC/CAPEX/2018-2019/132 | 2019-05-09 | 27.191 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.1 | Procurement of LPT rotor suitable for Unit # 3 & 4 of 210 MW at Khaperkheda TPS | MERC/CAPEX/2018-2019/132 | 2019-05-09 | 26.491 | 10.7515 | 10.7515 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2018-2019/132 | 2019-05-09 | 0.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23 | Supply, Erection & commissioning of HT Vacuum circuit Breakers & SF6 contactors at AHP (U#1-4) & CHP (U#1 to 5) and 160 KW VFD Panel with Motor for fire-fighting pumps at U#1 to 4 at Khaperkheda TPS | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 10.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.1 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at AHP (Unit#1 to 4, 210MW), Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 4.17 | 3.4843 | 4.8883 | -1.404 | 0 | 0 |  |  | 0 | -1.404 | 0 | 0
23.2 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at CHP (Unit#1 to 4, 210MW) and CHP (Unit#5, 500MW) Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 3.81 | 4.031 | 2.7332 | 1.2978 | 0 | 0 |  |  | 0 | 1.2978 | 0 | 0
23.3 | Supply, Erection & commissioning of 150 KW VFD Panel with motor for fire-fighting pumps at 210 MW Khaperkheda TPS. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 2.34 | 2.0957 | 2.0957 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 0.58 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24 | Augmentation of Waregaon Ash Water Recovery System at TPS Khaperkheda | MERC/CAPEX/2019-20/732 | 2019-09-16 | 17.1984 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.1 | Augmentation of Waregaon Ash Water Recovery System at TPS Khaperkheda | MERC/CAPEX/2019-20/732 | 2019-09-16 | 15.7884 | 15.1987 | 15.1987 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-20/732 | 2019-09-16 | 1.41 | 0.58812 | 0.58812 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25 | Procurement of VFD with HMI & Controller & Replacing with existing Eddy-current drives of Coal feeders at U# 3 & 4 and Procurement of Various Critical Components of GEHO Pump (Model-TZPM 800) for AHP-1 at Khaperkheda TPS | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 10.6535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25.1 | Up-gradation of Existing BHEL make 36” Gravimetric Coal Feeders control panel with HMI and croprocessor based Controller with VFD, Motor & Weigh Module at Unit 3 & 4, (210MW) | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 7.4655 | 7.7 | 7.7 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25.2 | Procurement of various Critical Components of GEHO Pump (Model-TZPM 800) for AHP-1 (210MW) | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 2.698 | 2.6466 | 2.6466 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/734 | 2019-09-16 | 0.49 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26 | Procurement, Replacement of Eco Coils U#1&2 210 MW, & Procurement & replacement of foundation Deck Spring assembly for coal mills U#3,4 at Khaperkheda TPS | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 15.4086 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26.1 | Procurement, Replacement of Eco Coils U#1&2 | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 7.4996 | 6.6503 | 6.6503 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26.2 | Procurement & replacement of foundation Deck Spring assembly for coal mills U#3,4 | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 6.679 | 7.0955 | 7.1 | -0.004476 | 0 | 0 |  |  | 0 | -0.004476 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/853 | 2019-10-10 | 1.23 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28 | ESP Upgradation of 5 Nos. of 210/500MW Units at Khaperkheda, Koradi & Chandrapur TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 90.3535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.1 | ESP Upgradation at Unit #1, Khaperkheda TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 42.7114 | 59.55 | 54.445 | 5.105 | 0 | 0 |  |  | 0 | 5.105 | 0 | 0
28.2 | ESP Upgradation at Unit #2, Khaperkheda TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 42.7114 | 59.55 | 54.445 | 5.105 | 0 | 0 |  |  | 0 | 5.105 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 4.9307 | 0 | 16 | -16 | 0 | 0 |  |  | 0 | -16 | 0 | 0
29 | Flue Gas Desulphurisation System for Khaperkheda Unit # 1-4 | MERC/CAPEX/2021-2022/MSPGCL/097 | 2022-03-14 | 113.4565 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.1 | FGD System for Khaperkheda Unit # 1-4 | MERC/CAPEX/2021-2022/MSPGCL/097 | 2022-03-14 | 109.15 | 255.58 | 130.03 | 125.55 | 0 | 0 |  |  | 0 | 125.55 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/097 | 2022-03-14 | 4.3065 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4 | Construction of coal platform for Chandrapur TPS, Khaperkheda TPS & Parli TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 5.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4.2 | Khaperkheda TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 5.43 | 3.9936 | 3.9936 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 4.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.4a | 1. Procurement of 6.6 KV,300 KW, P.A.fan motor for U# 1 & 2 2. Procurement of 6.6 KV,425 KW,CM motor for U # 3 & 4 3. Procurement of 6.6 KV,1400KW,CW pump motor for U-1& 2 4. Procurement of 6.6 KV,1400 KW,CW pump motor for U-3&4 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 3.82 | 2.5973 | 2.5973 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.4b | K'kheda: Procurement of HT Motors(GS/HP Water pump)for U-1&2 and Procurement of HT Motors (ACW)for U-3&4 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 1 | 0.4 | 0.4 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.2 | KHAPERKHEDA (U-1 to 4) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.96 | 3.1173 | 3.1173 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.2 | Khaperkheda TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 4.0552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender for KPKD 1-4 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 1.7765 | 1.7765 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.2 | Normal Multipurpose Fire Tender KPKD 1-4 | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 2.1847 | 2.1847 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 226.3024 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9.1 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 226.3024 | 291.23 | 331.4177 | -40.1877 | 0 | 0 |  |  | 0 | -40.1877 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 4.4604 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.2a | Compond wall (IB recommdation),Plant Patrolling Roads (IB recommdation) TPS KPKD | MERC/CAPEX/20172018/0177 | 2018-02-06 | 4.4604 | 3.9506 | 3.9506 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 9.23 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11.1 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 9.05 | 13.3057 | 13.3057 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 0.18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15 | Implementation of Water Flow Monitoring system at Chandrapur STPS & Khaperkheda TPS | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 5.1755 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.3 | Electromagnetic Flow meters at various lines & Locations of 210 MW | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 3.8515 | 3.8515 | 3.8515 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.4 | Automation: Centralized SCADA, RTU, MODBUS Cable, Power cable & mandatory spares | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 1.324 | 1.324 | 1.324 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30 | Supply of spare Generator Rotor for UNIT 1 & 2, 210MW | MERC/CAPEX/2023-24/0184 | 2024-03-12 | 37.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.1 | Supply of spare Generator Rotor for UNIT 1 & 2, 210MW | MERC/CAPEX/2023-24/0184 | 2024-03-12 | 36.7 | 36.7 | 36.7 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2023-24/0184 | 2024-03-12 | 0.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M with raising of drain wells and modification of Masonary Dam (Waste Weir), 4 x210 MW, TPS, Khaperkheda | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 45.0535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.1 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M at TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 31.0231 | 31.22 | 31.22 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.2 | Raising of drain wells of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 1.6569 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.3 | Modification of Masonary Dam (Waste Weir) of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 10.1857 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 2.1878 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
32 | Flue Gas Desulphurisation (FGD) System for Khaperkheda Unit # 1 & 2 | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 115.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
32.1 | Flue Gas Desulphurisation (FGD) System for Khaperkheda Unit # 1 & 2 | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 109.8 | 0 | 129.13 | -129.13 | 0 | 0 |  |  | 0 | -129.13
0 | IDC | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 5.54 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33 | Upgradation of DDC/DCS system for UNIT 1 & 3 of 210 MWKhaperkheda TPS | MERC/CAPEX/MSPGCL/2023-24/601 | 2023-11-10 | 39.14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.1 | Upgradation of DDC/DCS system for UNIT 1 & 3 of 210 MWKhaperkheda TPS | MERC/CAPEX/MSPGCL/2023-24/601 | 2023-11-10 | 38.7 | 39.14 | 39.14 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/601 | 2023-11-10 | 0.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34 | Supply & commissioning of interconnection conveyor belt, Elecon make complete impact type crusher, Procurement of 4 NOs. Bull Dozer BEML BD-155 and Eco friendly and power efficient chiller system at Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 28.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.1 | Design, engineering, manufacturing, supply, erection & commissioning of interconnection conveyor belt from 1 X 500MW to 4 X 210MW stack yard at CHP Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.2 | Supply & installation of Elecon–make complete impact type crusher at CHP-I, Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 4.29 | 4.15 | 4.15 | 0 | 0 | 0 |  |  | 0 | 0
34.3 | Procurement of 4 NOs. Bull Dozer BEML BD-155 at CHP, Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.255 | 12.0596 | 12.0596 | 0 | 0 | 0 |  |  | 0 | 0
34.4 | Supply, erection, & commissioning of Eco friendly and power efficient chiller system for khaperkheda TPS Unit 1 to 4, Service Building and WTP in place of present reciprocating type Chiller system | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 11.96 | 11.45 | 11.45 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 1.385 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | 5 Nos. of Boiler Improvement Schemes for Unit No. 1 to 4 | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 32.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Procurement & replacement of Re-Heater Rear Pendent Assembly Coils for unit no. 3 & 4 (210 MW) | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 8.86 | 9.36 | 9.36 | 0 | 0 | 0 |  |  | 0 | 0
35.2 | Procurement Complete Set of Sky Climber For Unit#1 To 5 Boilers. | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 3.32 | 2.43 | 2.43 | 0 | 0 | 0 |  |  | 0 | 0
35.3 | Replacement of glasswool insulation and GI/CORRUGATED sheets of boiler and hot air ducts at unit 1to 4 KHAPERKHEDA TPS | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 2.19 | 1.99 | 1.99 | 0 | 0 | 0 |  |  | 0 | 0
35.4 | Procurement, design, manufacture, supply & delivery, dismantling, retrofitting, erection, commissioning and testing of gravimetric belt conveyor type coal feeders for unit no. 1 & 2. | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 6.68 | 6.77 | 6.77 | 0 | 0 | 0 |  |  | 0 | 0
35.5 | Procurement and Replacement of Air Preheater Baskets for Unit no. 1 to 4 (4x 210MW). | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 9.05 | 11.3735 | 11.3735 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 2.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR-17 | Various DPR Schemes for The work of maintaining the zero discharge condition of Pond No. 2 & Pond No.3 and providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 15.7443 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | The work of maintaining the zero discharge condition of Pond No.2 & Pond No.3 at KTPS Koradi | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 4.2068 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.2 | Providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 11.5375 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Scheme of HMI upgradation of unit 5 DCS along with Max Links , HART Scheme , PADO , all BOP PLCs , SWAS system, CO analyser & Coal feeder controller to match with the external aspect , process improvement & Up gradation of Generator Protections Relays in unit 1 to 4 of 210 MW at khaperkheda TPS | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 33.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.7 | Up-gradation of Generator Protections Relays in Unit 1 to 4 of 210 MW Khaperkheda TPS. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 8.31 | 8.86 | 8.86 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/478 | - | 0.86 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Submitted to MERC, Yet to receive approval | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR on Refurbishment of Spare HPT Module Unit 1 & 2 at TM-I and Procurement of Complete Gear Box Assemblies of Coal Mills XRP 803 ½ HP & XRP 883 for Unit No. 1 to 4 (4x210 MW), Khaperkheda TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Refurbishment of spare HPT module Unit 1 & 2 at TM-I (4X210 MW), KHAPERKHEDA TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Procurement of Complete Gear Box Assemblies of Coal Mills XRP 883 for Unit-1 to 4 (210MW). | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | SUPPLY INSTALLATION TESTING & COMMISSIONING REVAMPING OF FIRE DETECTION & ALARM AND PROTECTION SYSTEM FROM FIRE AND PROVIDING RAPID EXTINGUISHING CLEAN AGENT (CA) SYSTEM AT UNIT -3,4 & 5 ATKPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Supply Installation Testing & Commissioning , Revamping of fire protection and providing rapid extinguishing clean agent (CA) system at unit # 3 ,4 210 MW TPS, KHAPERKHEDA | 0 | - | 0 | 6.5 | 6.5 | 0 | 0 | 0 |  |  | 0 | 0
2 | Restoration of various Fire protection system at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Restoration of fire hydrant ring and fire water spray Header at Khaperkheda TPS | 0 | - | 0 | 13.14 | 13.14 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Restoration of deluge valve system at CHP-210MW | 0 | - | 0 | 25.44 | 25.44 | 0 | 0 | 0 |  |  | 0 | 0
3 | VARIOUS SCHEMES PROPOSED FOR IMPROVEMENT OF CHP-I (4 X 210 MW). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Design, Manufacturing, Supply, Erection, Commissioning & Testing of Coal Flow Management system for Coal Bunkers in CHP-I (4 X 210MW), Khaperkheda TPS. | 0 | - | 0 | 12.27 | 12.27 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Design, engineering, manufacturing, supply, installation and commissioning of Dedusting System for Crusher House and Bunker area in Unit 3 & 4 at CHP-I (4 X 210MW), Khaperkheda TPS. | 0 | - | 0 | 12.96 | 12.96 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Renovation including replacement of Power & Control cables with automation & upgradation of Stacker Reclaimer No. 1 in CHP-I (4 X 210MW), TPS Khaperkheda." | 0 | - | 0 | 8.59 | 8.59 | 0 | 0 | 0 |  |  | 0 | 0
4 | Flue Gas Desulphrisation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | FGD installation of 210MW unit 1 & 2 at Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Upgradation of DDC/DCS system for UNIT 2 & 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Upgradation of DDC/DCS system for UNIT 2 & 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 45 | 45 | 0 | 0 | 0 |  |  | 0 | 0
6 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#1 to 4 Khaperkheda TPS & Upgradation of various governing Element for smooth operation for flexible operation of TG set at 40% technical minimum operation. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#1 to 4 Khaperkheda TPS. | 0 | - | 0 | 60 | 60 | 0 | 0 | 0 |  |  | 0 | 0
6.2 | Upgradation of various governing Element for smooth operation for flexible operation of TG set at 40% technical minimum operation. | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
7 | Upgradation of Battery Charger , UPS system , GEHO PLC and VFD, ID VFD, supply of Efficiency Measuring Instruments and Supply, erection and commissioning of Sox, Nox , CO, Opacity, ETP and Oxygen Analyser for Unit 1 to 4 of 210 MW at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Supply of Efficiency Monitoring Instruments for performance optimization group (POG) at Khaperkheda TPS. | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
7.2 | Upgradation of 220 V, 24 V DC Float cum boost battery charger at Unit#1 to 4 Khaperkheda TPS. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
7.3 | Upgradation of 2X50 KVA UPS at Unit#1 to 4 Khaperkheda TPS. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
7.4 | Supply, Erection and Commissioning of Sox, Nox , CO, Opacity and ETP Analyser for Unit 1 to 4 of 210 MW at Khaperkheda TPS | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
7.5 | Upgradation of GEHO PLC and VFD along with HCSD system Instrumentaion at Unit 3 & 4 Khaperkheda TPS. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
7.6 | Supply, Erection & Commissioning of Oxygen Analyzer for combustion optimization for Unit#1 to 5 Khaperkheda TPS. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
7.7 | Upgradation of VFD for ID FAN in Unit# 3 & 4, 210MW khaperkheda TPS. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
7.8 | Scheme 8 Supply, erection & commissioning of PLC and SCADA System of Ash Evacuation and Disposal System for UNIT 3 and 4 Of 210 MW Khaperkheda TPS | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of LP Rotor for unit 1 and 2 , Supply and installation of air washer unit 1 and 2 and refurbishment of air washer unit for unit 3 and 4 and GEHO Pummp house control room. Supply and installation of diesel engine driven fire fighting pump with engine. Procurement of various control valves for unit No. 1 to 4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.1 | Supply and installation of Air washer unit in unit 1 and 2 , 6.6 KV breaker room, Turbine MCC room Battery room Boiler MCC room for cooling of all the Electrical Panels and AHP stage I Pump House control room air washer system | 0 | - | 0 | 12 | 12 | 0 | 0 | 0 |  |  | 0 | 0
8.2 | Refurbishment of Air washer unit of 3 and 4, 6.6 KV breaker room, Turbine MCC room Battery room Boiler MCC room for cooling of all the Electrical Panels and Refurbishment of GEHO pump House and AHP stage II Pump House control room air washer system | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
8.3 | Procurement of Complete LPT rotor for unit 1 and 2 | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
8.4 | Revamping of diesel engine driven fire fighting pump system with engine. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
8.5 | Procurement of various control valves for unit No. 1 to 4 | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of IP Rotor and Inner casing for unit 1 and 2. Procurement of IP rotor and inner casing for unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.1 | Procurement of IP Rotor and Inner casing for unit 1 and 2. | 0 | - | 0 | 22 | 22 | 0 | 0 | 0 |  |  | 0 | 0
9.2 | Procurement of IP rotor and inner casing for unit 3 and 4 along with Turbovisory sensors and panel | 0 | - | 0 | 23 | 23 | 0 | 0 | 0 |  |  | 0 | 0
9.3 | Supply and installation of srew compressor for supply of instrument air to unit No. 3 and 4 along with dryer for unit No. 3 & 4. | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of LP rotor for unit 3 and 4 and upgradation of BFP cartridge and BFP Booster pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.1 | Procurement of of LP rotor for unit 3 and 4 | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
10.2 | Upgradation of BFP cartridge and BFP Booster pump, motorized scoop for hydraulic coupling and drive unit for BFP and modulating BFP RC valve for Unit 3 & 4 | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
11 | Refurbishment of LP rotor of unit 1 and 2 and Refurbishment of HPT module of unit 1 and 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.1 | Refurbishment of LP rotor of unit 1 and 2 | 0 | - | 0 | 0 | 0 | 0 | 15 | 15 |  |  | 15 | 0
11.2 | Refurbishment of HPT module of unit 1 and 2 | 0 | - | 0 | 0 | 0 | 0 | 15 | 15 |  |  | 15 | 0
12 | Refurbishment of LP rotor for unit 3 and 4 and Refurbishment and re-blading of HPT module of unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.1 | Refurbishment of LP rotors for unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 18 | 18 |  |  | 18 | 0
12.2 | Refurbishment of HPT modules of unit 3 and 4 | 0 | - | 0 | 0 | 0 | 0 | 36 | 36 |  |  | 36 | 0
13 | SITC OF COMPLETE SOLUTION AND COMPREHENSIVE PROTECTION AND MONITORING PACKAGE ALONG WITH RETROFIT OF ALLIED ACCESSORIES FOR VARIOUS GTs & STs INSTALLED AT 210 MW KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | SUPPLY,INSTALLATION, TESTING & COMMISSIONING OF COMPLETE SOLUTION AND COMPREHENSIVE PROTECTION AND MONITORING PACKAGE ALONG WITH RETROFIT OF ALLIED ACCESSORIES FOR VARIOUS GTs & STs INSTALLED AT 210 MW KHAPERKHEDA TPS. | 0 | - | 0 | 26 | 26 | 0 | 0 | 0 |  |  | 0 | 0
14 | PLANT PERFORMANCE IMPROVEMENT BY DESIGN, SUPPLY, INSTALLATION & COMMISSIONING OF STATE OF ART HT VACCUM CIRCUIT BREAERS AT UNIT 1 TO 4 OF 210MW KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.1 | DESIGN, SUPPLY, INSTALLATION, TESTING & COMMISSIONING OF HT VCB AT U # 1 & 2. | 0 | - | 0 | 15.14 | 15.14 | 0 | 0 | 0 |  |  | 0 | 0
14.2 | DESIGN, SUPPLY, INSTALLATION, TESTING & COMMISSIONING OF HT VCB AT U # 3 & 4. | 0 | - | 0 | 16.5 | 16.5 | 0 | 0 | 0 |  |  | 0 | 0
15 | DESIGN, SUPPLY, INSTALLATION, TESTING AND COMMISSIONING OF THE VARIOUS LIFTS IN PLACE OF THE EXISTING OLD LIFTS, LIGHTNING PROTECTION SYSTEM, EARTHING SYSTEM, AVIATION LIGHTING SYSTEM INSTALLED AT UNIT # 1 TO 4 OF 210 MW, KHAPERKHEDA TPS ON OEM BASIS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | DESIGN, SUPPLY, INSTALLATION, TESTING AND COMMISSIONING OF THE VARIOUS LIFTS IN PLACE OF THE EXISTING OLD LIFTS INSTALLED AT UNIT # 1 TO 4 OF 210 MW, KHAPERKHEDA TPS ON OEM BASIS. | 0 | - | 0 | 10.46 | 10.46 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Design, Engineering, Supply, Erection, Testing & Commissioning of lightning protection system at Khaperkheda TPS. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Design, Engineering, Supply, Erection, Testing & Commissioning of Earthing of electrical system & various buildings at Khaperkheda TPS. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Design, Engineering, Supply, Erection, Testing & Commissioning of Aviation Lighting Syatem at Khaperkheda TPS. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
16 | SUPPLY OF SPARE GENERATOR ROTOR FOR U#3 &4, 210MW, TPS KHAPERKHEDA. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.1 | SUPPLY OF SPARE GENERATOR ROTOR FOR U#3 &4, 210MW, TPS KHAPERKHEDA. | 0 | - | 0 | 40 | 40 | 0 | 0 | 0 |  |  | 0 | 0
17 | PROCUREMENT OF ENERGY EFFICIENT MOTORS FOR U # 1 TO 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.1 | PROCUREMENT OF ENERGY EFFICIENT MOTORS FOR U # 1 & 2 OF KHAPERKHEDA TPS. | 0 | - | 0 | 11 | 11 | 0 | 0 | 0 |  |  | 0 | 0
17.2 | PROCUREMENT OF ENERGY EFFICIENT MOTORS FOR U # 3 & 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 14 | 14 | 0 | 0 | 0 |  |  | 0 | 0
17.3 | Procurement of DC motors for U # 1 & 2 of Khaperkheda TPS. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
17.4 | Procurement of DC motors for U # 3 & 4 of Khaperkheda TPS. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
18 | UPGRADATION OF EXISTING LT MCC PANEL WITH STATE OF ART LT MCC PANEL AT U # 1 TO 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | UPGRADATION OF EXISTING LT MCC PANEL WITH STATE OF ART LT MCC PANEL AT U # 1 & 2 OF KHAPERKHEDA TPS. | 0 | - | 0 | 12.5 | 12.5 | 0 | 0 | 0 |  |  | 0 | 0
18.2 | UPGRADATION OF EXISTING LT MCC PANEL WITH STATE OF ART LT MCC PANEL AT U # 3 & 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 12.5 | 12.5 | 0 | 0 | 0 |  |  | 0 | 0
18.3 | UPGRADATION OF HT BREAKER PANEL AT WAREGAON ASH BUND OF KHAPERKHEDA TPS. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | UPGRADATION OF HT BREAKER PANEL AT OLD PROJECT OFFICE OF KHAPERKHEDA TPS. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
18.5 | Retrofitting of Existing L & T make LT MCC ACB by state or art ACB at U # 1 to 4 of Khaperkheda TPS. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
18.6 | Retrofitting of Existing ABB make LT MCC ACB by state or art ACB at U # 1 to 4 of Khaperkheda TPS. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
19 | ERECTION & COMMISIONING OF DRY TYPE CAST RESIN TRANSFORMERS FOR U # 1 TO 4 OF KHAPERKHEDA TPS & Design, Engineering, Supply, Erection, Testing & Commissioning of various Battery sets at Unit # 3 & 4 of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | PROCUREMENT OF DRY TYPE CAST RESIN TRANSFORMERS FOR U # 1 & 2 OF KHAPERKHEDA TPS. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
19.2 | PROCUREMENT OF DRY TYPE CAST RESIN TRANSFORMERS FOR U # 3 & 4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
19.3 | PROCUREMENT OF VFD TRANSFORMERS FOR ID FAN MOTOR U#3&4 OF KHAPERKHEDA TPS. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
19.4 | Design, Engineering, Supply, Erection, Testing & Commissioning of various Battery sets at Unit # 3 & 4 of Khaperkheda TPS. | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
20 | Study, Supply & Refurbishment of HCSD systems, ESP operation, ambience & various pump, & PLC schemes for the improvement of AHP-I at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.1 | STUDY. DESIGN & REFURBISHMENT WORKS OF HIGH CONCENTRATION SLURRY DISPOSAL SYSTEM (HCSD SYSTEM) UNITS #3&4 AT AHP-1, TPS KHAPERKHEDA. | 0 | - | 0 | 9.32 | 9.32 | 0 | 0 | 0 |  |  | 0 | 0
20.2 | STUDY, DESIGN & REFURBISHMENT WORKS OF ARTs AND ASSOCIATED MOUNTINGS & ACCESSORIES OF HCSD SYSTEM FOR AHP-I, TPS KHAPERKHEDA.” | 0 | - | 0 | 8.96 | 8.96 | 0 | 0 | 0 |  |  | 0 | 0
20.3 | ‘SUPPLY & REFURBISHMENT WORKS OF HCSD ASH SLURRY MIXER SYSTEM AT UNIT #3 &4 OF AHP-I, TPS KHAPERKHEDA’. | 0 | - | 0 | 2.85 | 2.85 | 0 | 0 | 0 |  |  | 0 | 0
20.4 | ‘STUDY, SUPPLY, RESTORATIONS & REPLACEMENT OF ALL INTERNAL SPARES OF D6 FIELD & RENOVATION OF D1 FIELD OF U3 DURING AOH FOR AHP-I, TPS KHAPERKHEDA’ | 0 | - | 0 | 2.92 | 2.92 | 0 | 0 | 0 |  |  | 0 | 0
20.5 | PROCUREMENT OF VARIOUS PUMPS IN RECYCLE WATER SYSTEM IN ASH HANDLING PLANT 4X210 MW AT KHAPARKHEDA TPS | 0 | - | 0 | 4.6 | 4.6 | 0 | 0 | 0 |  |  | 0 | 0
21 | Reliability improvement and complete replacement of ABC series with drive unit of ash slurry pipeline of 7 KM of 4*210MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Procurement and restoration of complete pipeline replacement of ABC series | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
21.2 | Procurement and restoration of complete drive unit replacement of ABC series | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
22 | Procurement and restoration of complete Bottom ash hopper replacement including entire structure, Clinker grinder alongwith motor, Feed Gate, Power Cylinder and Pipelines discharge of U3&4 of 4*210MW Khaparkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.1 | Procurement and restoration of complete BAH replacement including entire structure and clinker griender | 0 | - | 0 | 23 | 23 | 0 | 0 | 0 |  |  | 0 | 0
22.2 | Procurement and restoration of complete drive unit of clinker grinder for Unit 1 to 4 | 0 | - | 0 | 3.2 | 3.2 | 0 | 0 | 0 |  |  | 0 | 0
22.3 | Procurement and restoration of discharge pipeline of vertical sump pump | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
23 | Procurement and restoration of Pipeline garlanding at Waregaon ash Bund of 4*210 MW Khapakheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.1 | Pipeline garlanding at Waregaon ash Bund of 4*210 MW Khapakheda TPS | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
24 | Upgradation, modification and erection of complete wet fly ash evacuation into dry fly ash evacuation systen for ESP 1 and 2 of 4*210 MW Khapakheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.1 | Upgradation, modification and erection of complete wet fly ash evacuation into dry fly ash evacuation systen for ESP 1 and 2, 4*210 MW Khapakheda TPS | 0 | - | 0 | 100 | 100 | 0 | 0 | 0 |  |  | 0 | 0
25 | Reliability improvement and complete replacement of JKL series with drive unit of ash slurry pipeline of 7 KM of 4*210MW Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.1 | Procurement and restoration of complete pipeline replacement of JKL series | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
25.2 | Procurement and restoration of complete drive unit replacement of JKL series | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
26 | Study, Supply and Refurbishment of HCSD System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.1 | Procurement of complete Suction and discharge valve of Geho pump | 0 | - | 0 | 0 | 0 | 0 | 15 | 15 |  |  | 15 | 0
26.2 | Procurement of Subassemblies of Geho pump. | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
26.3 | Upgradation and compressors of dry ash evacutaion system of U#3&4. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
26.4 | Procuremenet of complete drive unit and VFD of GEHO pump. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
27 | RENOVATION OF ESP FIELD INTERNALS FOR UNIT 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.1 | RENOVATION OF ESP FIELD INTERNALS FOR UNIT 3 & 4 | 0 | - | 0 | 30 | 30 | 0 | 30 | 30 |  |  | 30 | 0
28 | R & M OF APH OF UNIT # 1& 2 (2 x 210MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28.1 | R & M OF APH OF UNIT # 1& 2 (2 x 210MW) OF KHAPERKHEDA TPS FROM MODEL: 27 VI 1850 TO 27 VI 2000 mm. DESIGN, ENGINEERING, SUPPLY, ERECTION & COMMISSIONING OF DOUBLE SEALING | 0 | - | 0 | 18.4 | 18.4 | 0 | 18.4 | 18.4 |  |  | 18.4 | 0
29 | DPR FOR ECONOMISER COILS AND APH GEAR BOX | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29.1 | PROCUREMENT AND REPLACEMENT OF COMPLETE SET OF ECONOMISER UPPER BANK & LOWER BANK COILS FOR KHAPERKHEDA TPS UNIT NO.3&4 | 0 | - | 0 | 22 | 22 | 0 | 0 | 0 |  |  | 0 | 0
29.2 | Procurement of APH gear box in unit no. 1 & 2 | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
29.3 | Procurement of APH speed reducer gear box in unit no. 3 & 4 | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
30 | DPR FOR LTSH COILS , APH BASKETS & RH OUTLET STUB BENDS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.1 | Procurement of Air Pre-heater Baskets for unit no. 2 to 4 | 0 | - | 0 | 7.25 | 7.25 | 0 | 3.75 | 3.75 |  |  | 3.75 | 0
30.2 | Procurement of LTSH coils for unit no. 1 & 2 and Procurement of Reheater outlet header stub bends for unit no. 1 to 2 | 0 | - | 0 | 6 | 6 | 0 | 6 | 6 |  |  | 6 | 0
30.3 | Procurement of LTSH coils for unit no. 3 & 4 and Procurement of Reheater outlet header stub bends for unit no. 3 to 4 | 0 | - | 0 | 0 | 0 | 0 | 9 | 9 |  |  | 9 | 0
31 | DPR FOR SUPPLY & REPLACMENT OF THERMAL INSULATION OF BOILER AND DUCT AT UNIT 1 TO 4 KHAPERKHEDA TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.1 | SUPPLY & REPLACMENT OF THERMAL INSULATION OF BOILER AND DUCT AT UNIT 1 TO 2KHAPERKHEDA TPS | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
31.2 | SUPPLY & REPLACMENT OF THERMAL INSULATION OF BOILER AND DUCT AT UNIT 3 TO 4 KHAPERKHEDA TPS | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
32 | DPR FOR COAL CYCLE IMPROVEMENT IN UNIT NO.1 TO 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.1 | Procurement of Complete Journal Assembly for 803 ½ HP Coal Mills of Unit No. 1 To 2 | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
32.2 | Procurement of Complete Journal Assembly for XRP 883 Coal Mills of Unit No. 3 To 4, | 0 | - | 0 | 9.86 | 9.86 | 0 | 0 | 0 |  |  | 0 | 0
32.3 | Procurement of assembly of worm shaft & worm wheel with hub for unit no. 3 & 4 | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
32.4 | PROCUREMENT OF COMPLETE GEAR BOX ASSEMBLIES OF COAL MILLS XRP 803 ½ HP FOR UNIT # 1 TO 2 AT KHAPERKHEDA TPS | 0 | - | 0 | 7.5 | 7.5 | 0 | 0 | 0 |  |  | 0 | 0
32.5 | PROCUREMENT OF COMPLETE GEAR BOX ASSEMBLIES OF COAL MILLS XRP 883 FOR UNIT # 3 TO 4 AT KHAPERKHEDA TPS | 0 | - | 0 | 7.5 | 7.5 | 0 | 0 | 0 |  |  | 0 | 0
33 | DPR FOR PERFORMANCE IMPROVEMENT OF BOILER PA FAN, ID FAN AND FD FAN IN UNIT NO. 1 TO 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.1 | Procurement of PA fan Casings along with Dampers in Unit- 1 & 2, at Khaperkheda TPS | 0 | - | 0 | 17.75 | 17.75 | 0 | 0 | 0 |  |  | 0 | 0
33.2 | PROCUREMENT OF COMPLETE ROTOR ASSEMBLY ALONG WITH MOTOR FOR NDZV 31 SIDOR IN UNIT NO. 1 & 2 KHAPERKHEDA TPS (ID FAN) | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
33.3 | PROCUREMENT OF FD FAN (BHEL AP 1-20 / 11) ASSEMBLY ALONG WITH DRIVE UNIT(MOTOR) FOR UNIT 1 & 2 AT KHAPERKHEDA TPS UNDER OEM NATURE ITEMS | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
33.4 | PROCUREMENT OF FD FAN (BHEL AP 1-20 / 11) ASSEMBLY ALONG WITH DRIVE UNIT(MOTOR) FOR UNIT 3& 4 AT KHAPERKHEDA TPS UNDER OEM NATURE ITEMS | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
33.5 | NDZV 33 SIDOR ID Fan Impeller Assembly for Unit 3 & 4 at TPS, Khaperkheda | 0 | - | 0 | 7.28 | 7.28 | 0 | 0 | 0 |  |  | 0 | 0
33.6 | Design, Engineering, Manufacturing, Supply & Commissioning including civil works for installation of 70 LPM lubricant ystems for PA Fans in unit no. 1&2. | 0 | - | 0 | 1.38 | 1.38 | 0 | 0 | 0 |  |  | 0 | 0
33.7 | Supply and installation of ID and PA foundation deck spring for unit no. 3 & 4 | 0 | - | 0 | 0 | 0 | 0 | 4.65 | 4.65 |  |  | 4.65 | 0
34 | VARIOUS SCHEMES FOR BOILER PERFORMANCE IMPROVEMENT | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.1 | SUPPLY OF COAL MILL SEPERATOR & SCRAPPER BODIES FOR XRP-803 1/2 HP COAL MILLS IN UNIT 1 & 2 | 0 | - | 0 | 17.28 | 17.28 | 0 | 0 | 0 |  |  | 0 | 0
34.2 | MODIFICATION OF EXISTING COAL BUNKER AND COMMISSIONING OF BUNKER CHUTE ASSEMBLY WITH VIBRATING MOTOR TO AVOID BUNKER MOUTH COAL CHOKE UP FOR UNIT 1 & 2AT KHAPERKHEDA TPS. | 0 | - | 0 | 9 | 9 | 0 | 0 | 0 |  |  | 0 | 0
34.3 | MODIFICATION OF EXISTING COAL BUNKER AND COMMISSIONING OF BUNKER CHUTE ASSEMBLY WITH VIBRATING MOTOR TO AVOID BUNKER MOUTH COAL CHOKE UP FOR UNIT 3 & 4 AT KHAPERKHEDA TPS. | 0 | - | 0 | 9 | 9 | 0 | 0 | 0 |  |  | 0 | 0
34.4 | DESIGN, DEVELOPMENT, COMMISIONING OF SEAL AIR FAN ASSEMBLIES IN UNIT 1 & 2 | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
34.5 | Procurement of sub body assembly of control valve in unit no. 1 & 2 actuating main gear unit part electrical actuator in unit no. 1 to 4 Khaperkheda TPS | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
35 | Construction of A, B, C, D & E type stilt + 6 floor buildings at TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Construction of A, B, C, D & E type stilt + 6 floor buildings at TPS Khaperkheda. | 0 | - | 0 | 180 | 180 | 0 | 0 | 0 |  |  | 0 | 0
36 | Enhancement & Renovation of existing building, Construction of Market building, Construction of club building community hall, Construction of school building, & Enhancement of existing domestic plant providing V wire 3 MLD at Colony TPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.1 | Enhancement / Renovation & strengthening of existing building & allied works in colony TPS Khaperkhda. | 0 | - | 0 | 28 | 28 | 0 | 0 | 0 |  |  | 0 | 0
36.2 | Construction of Market building including approach road, drainage arrangement & electrification at colony TPS Khaperkheda | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
36.3 | Construction of club building / community hall | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
36.4 | Construction of school building | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
36.5 | Enhancement of existing domestic plant providing V wire 3 MLD | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
37 | Enhancement / Renovation of Saudamini Administrative Building, Construction of VIP Guest House, Construction of roads at Prakashnagar Colony and Providing various civil works related to coal transport railway lines of khaperkheda TPSTPS Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.1 | Enhancement / Renovation of Saudamini building | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
37.2 | Construction of VIP guest house TPS Khaperkheda. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
37.3 | Construction of Roads | 0 | - | 0 | 13 | 13 | 0 | 0 | 0 |  |  | 0 | 0
37.4 | Construction of office building & store for electrical maintenance & Civil at KPKD | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
37.5 | Providing Special repair & retrofitting work of river bridge no.09 on Khaperkheda - Kalumna railway siding of TPS Khaperkheda. | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
37.6 | Construction & repairing of drains & culverts along coal Transporting Railway lines & approach road of TPS Khaperkheda. | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
37.7 | Repairing, providing & applying Epoxy Painting and Structural Steel Works to steel structural bridges on kpkd to Kaluma and kpkd to Saoner railway lines as per recommendation of structural stability report at TPS Khaperkheda. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
37.8 | Construction of compound wall KPKD Colony | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
38 | Work of Strengthening and modification of Main Plant, construction of roads, strengthening of IDCT 1 to 4 in plant area, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.1 | Work of attending additional works based on structural report at Induced Draft Cooling Towers(IDCT) unit 1,2,3 & 4 at 4 x 210MW, TPS, Khaperkheda. | 0 | - | 0 | 1.21 | 1.21 | 0 | 0 | 0 |  |  | 0 | 0
38.2 | Work of constructon of roadside drains from VIP gate no.3 to IDCT No.1 at 4 x 210MW TPS Khaperkheda. | 0 | - | 0 | 3.61 | 3.61 | 0 | 0 | 0 |  |  | 0 | 0
38.3 | Construction of bituminous macadam road from Administrative Building to GCR Road near Service Building of 4X210MW TPS Khaperkheda. | 0 | - | 0 | 2.7 | 2.7 | 0 | 0 | 0 |  |  | 0 | 0
38.4 | Work for Construction of cement concrete road for equipment movement for salt lagoon (WTP-I), FGD(System), H2(cylinders) plant etc. inside plant premises in 4x 210MW, TPS, Khaperkheda. | 0 | - | 0 | 3.63 | 3.63 | 0 | 0 | 0 |  |  | 0 | 0
38.5 | Construction of cement concrete road outside BTG area of Power Plant 4 x 210MW TPS Khaperkheda. | 0 | - | 0 | 8.92 | 8.92 | 0 | 0 | 0 |  |  | 0 | 0
38.6 | Construction of cement concrete road for material transportation from D-Point CHP to reject coal Dumping yard in 4x 210MW, TPS, Khaperkheda. | 0 | - | 0 | 5.94 | 5.94 | 0 | 0 | 0 |  |  | 0 | 0
38.7 | Work of Strengthening and modification of Main Plant, Major Stores, Auxiliary in plant area, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
38.8 | Construction of diversion road along with RCC bridge from rejct coal yard CHP-I & CHP-II | 0 | - | 0 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
38.9 | Upgradation of existing ETP plant consist civil works, electrification and pumps. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
39 | Work of 5th Raising of Waregaon Ash Bund, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
39.1 | Work of 5th Raising of Waregaon Ash Bund, 4x210 MW, TPS, Khaperkheda. | 0 | - | 0 | 150 | 150 | 0 | 0 | 0 |  |  | 0 | 0
40 | Work of CTR(Complete Track Removal),TTR(TRAIN TRAVLER REGULATOR) and Yard Remoulding incl. misc. works at Mahagenco Khaperkheda Plant. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
40.1 | Work of CTR(Complete Track Removal),TTR(TRAIN TRAVLER REGULATOR) and Yard Remoulding incl. misc. works at Mahagenco Khaperkheda Plant. | 0 | - | 0 | 178 | 178 | 0 | 0 | 0 |  |  | 0 | 0
41 | Various WTP 210MW improvement schemes i.e. Up-gradation of SWAS SYSTEM UNIT- 1 to 4 at WTP-I 210 MW along with coal sampling lab upgradation, Comissioning of CW Chemical Dosing system etc | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.1 | Upgradation of Existing ETP system viz. Plate Settler, Settling tank, Sludge Drying bed, Chemical dosing system etc.)as per MPCB consent condition | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
41.2 | Upgradation of SWAS Lab 3& 4 at WTP-210 MW | 0 | - | 0 | 9 | 9 | 0 | 0 | 0 |  |  | 0 | 0
41.3 | Revamping of Chlorination Plant Stream (A+ B) & Installation, Comissioning of CW Chemical Dosing system (Viz. Scale inhibitor, Scale Dispersant, Biodispersant, Corossion Inhibitor & H2SO4 dosing) and Online CW Chemical parameter monitoring system at KPKD TPS | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
41.4 | Upgradation of SWAS Lab 1& 2 at WTP-210 MW | 0 | - | 0 | 9 | 9 | 0 | 0 | 0 |  |  | 0 | 0
41.5 | Upgradation of Water &Coal testing Lab at WTP-210 MW &Procurement of Coal Lab Instruments and upgradation of coal sampling Room & Instruments related to Coal sample Preparation. at WTP-210 MW | 0 | - | 0 | 8.5 | 8.5 | 0 | 0 | 0 |  |  | 0 | 0
42 | Work of capacity restoration of unloading stream from Beetle Charger No. 1 to Stacker/Reclaimer No. 1 for perfromance improvement of CHP-I (4 x 210 MW) & Capacity restoration of unloading stream from Beetle Charger No. 1 to Stacker/Reclaimer No. 1 for perfromance improvement of CHP-I (4 x 210 MW). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.1 | Revamping/ refurbishment, capacity restoration and upgradation for beetle charger No. 1 | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
42.2 | Revamping/ refurbishment, capacity restoration and upgradation for Wagon Tippler No. 1 | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
42.3 | Revamping/ refurbishment, capacity restoration and upgradation for Apron Feeder No. 1 | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
42.4 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 2C, 3A, 4A, 8A, 9 | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
42.5 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for impact crusher and wobbler feeder No. 1 & 3 | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
42.6 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Stacker/Reclaimer No. 1. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
42.7 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv. 3C to 3A, Conv. 3A to 4A, Conv. 4A to 8A and Conv. 9 by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
42.8 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of beetle Charger, wagon tippler, apron feeder, covneyors (Conv. 2C, 3A, 4A, 8A, 9), crushers/ wobbler feeder No. 1 & 3 and Stacker/Reclaimer No. 1 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
43 | DPR fo Capacity restoration of bunkering stream from Conv. 5A to 7A/B/C/D including shuttle conveyors in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
43.1 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 5A, 6B, 7A, 7B, 7C, 7D and Shuttle Conv. 1 to 4 in CHP-I (4 x 210 MW) | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
43.2 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv.Conv. 4D to 5A/B , 5A to 6B, Conv. 6B to 7A & 7B, Conv. 7B to 7D upto shuttle conveyor, Conv. 7A to 7C upto shuttle conveyor by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
43.3 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of covneyors (Conv. 5A, 6B, 7A/B/C/D & Shuttle Conv. 1 to 4 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
44 | Work of capacity restoration of unloading stream from Beetle Charger No. 2 to Stacker/Reclaimer No. 2 for perfromance improvement of CHP-I (4 x 210 MW). | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.1 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for beetle charger No. 2 | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
44.2 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Wagon Tippler No. 2 | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
44.3 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Apron Feeder No. 2 | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
44.4 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 2D, 3B, 4B, 8B, 10 | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
44.5 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for impact crusher and wobbler feeder No. 2 & 4 | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
44.6 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Stacker/Reclaimer No. 2. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
44.7 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv. 2D to 3B, Conv. 3B to 4B, Conv. 4B to 8B and Conv. 10 by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
44.8 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of beetle Charger, wagon tippler, apron feeder, covneyors (Conv. 2D, 3B, 4B, 8B, 10), crushers/ wobbler feeder No. 2 & 4 and Stacker/Reclaimer No. 2 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
45 | Work of capacity restoration of bunkering stream from Conv. 1A/B, 2A/B, 5B to 7E/F/G/H including shuttle conveyors in CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.1 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for conveyor system from Conv. 1A/B, 2A/B, 5B, 6A, 7E, 7F, 7G, 7H and Shuttle Conv. 5 to 8 in CHP-I (4 x 210 MW) | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
45.2 | Design, development, modification, manufacturing, supply, erection and commissioning of modular chutes for Conv. 1A/b to 2A/B,Conv. 4C to 5A/B, Conv. 5B to 6A, Conv. 6A to 7E & 7F, Conv. 7E to 7G upto shuttle conveyor, Conv. 7F to 7H upto shuttle conveyor by using Anti-wear Tungsten Carbide Plates in CHP-I (4 x 210 MW), TPS Khaperkheda | 0 | - | 0 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
45.3 | Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of conveyor system from Conv. 1A/B, 2A/B, 5B, 6A, 7E, 7F, 7G, 7H and Shuttle Conv. 5 to 8 in CHP-1 (4 x 210 MW) | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
45.4 | Work of complete revamping/ refurbishment, capacity restoration and upgradation for Paddel Feeder No. 1 to 4 and truck hopper in CHP-I (4 x 210 MW) | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
46 | Renovation and upgradation of various electrical system for CHP-I (4 x 210 MW) improvement & Renovation and upgradation of various electrical system for CHP-I (4 x 210 MW) improvement. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.1 | Design, development and upgradation with circuit breaker VFD of various LT MCC of CHP-I. | 0 | - | 0 | 17 | 17 | 0 | 0 | 0 |  |  | 0 | 0
46.2 | Design, Supply, Installation, Commissioning and Testing of Energy Chain System for Paddle Feeder, Shuttle Conveyor and Stacker/Reclaimers in CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
46.3 | Upgradation of relay logic system with PLC & SCADA in CHP-I control room and Wagon Tipplers in CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
46.4 | Complete upgradation of conveyor lighting system with energey efficient LED lights for CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
46.5 | Providing, installation, testing commissioning, maintenance and operation of explosion proof & weather proof surveillance system at CHP-I (4 X 210 MW), TPS Khaperkheda. | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
46.6 | Complete revamping/refurbishment, upgradation and modification of various EOT cranes & hoist installed at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 12 | 12 | 0 | 0 | 0 |  |  | 0 | 0
47 | Procurement of various capacity SAN make locomotives and BEML make loader & bulldozer for CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.1 | Procurement of various capacity SAN make locomotives and BEML make loader & bulldozer for CHP-I (4 x 210 MW) | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
48 | CHP Improvement Schemesfor 4x 210 MW units | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.1 | Design, manufacture, supply and installation of suspended magnet for bunkering belts at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
48.2 | Design, manufacture, supply and installation of travel drive system for shuttle conveyors and conveyors at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
48.3 | Renovation including replacement of Power & Control cables with automation & upgradation of Stacker Reclaimer No. 2 in CHP-I (4 X 210MW), TPS Khaperkheda." | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
48.4 | Complete reconditionding & upgradation of LT MCC installed at Unit No. 3 & 4 bunker auxiliareis in CHP-I (4 x 210 MW) | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
48.5 | Complete reconditionding & upgradation of outdoor lighting system in CHP-I (4 x 210 MW) | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
48.6 | Complete reconditionding & upgradation of HT breaker, control circuits & protection relays in CHP-I (4 x 210 MW) | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
48.7 | Complete revamping/refurbishment, upgradation and modification of various monorail hoists & winch machine installed at CHP-I (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
48.8 | Procurement of hydra 14 Ton above capacity and heavy vehicles for CHP- I & II. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
49 | Installation of Real Time Coal Analyzer at all TPS of Mahagenco | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
49.1 | Installation of Real time Coal Analyzer at Khaperkheda TPS | 0 | - | 0 | 31.42 | 31.42 | 0 | 0 | 0 |  |  | 0 | 0
50 | Railway expenses for refurbishment of OHE lines at CHP-I (4 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50.1 | Railway expenses for refurbishment of OHE lines at CHP-I (4 x 210 MW) | 0 | - | 0 | 26 | 26 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | PROCUREMENT COMPLETE Gear BOX ASSEMBLIES FOR 803 1/2 HP & XRP 883 COAL MILLS OF UNIT NO. 1& 2 AT KHAPERKHEDA TPS. | N.A. | - | 0 | 4.5548 | 4.5548 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply Erection and commissioning of Oil Cooled Suspended magnets at Conv 6A & 6B at Khaperkheda TPS. | N.A. | - | 0 | 1.1484 | 1.1484 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurment of new 02 Ambulance Van & 2 Truck for KPKD TPS(Asset Nos. 170100512, 170100513, 170100514, 170100515) | N.A. | - | 0 | 0.41055 | 0.41055 | 0 | 0 | 0 |  |  | 0 | 0
4 | GEHO PUMP (Valve housing assembly) | N.A. | - | 0 | 8.7933 | 8.7933 | 0 | 0 | 0 |  |  | 0 | 0
5 | RESTORATION OF AHP OUTLET TO ESP INLET DUCTS U#1&2(Unit #2 Part only) | N.A. | - | 0 | 7.0042 | 7.0042 | 0 | 0 | 0 |  |  | 0 | 0
6 | ABC powder type and foam type composite Fire Extinguisher | N.A. | - | 0 | 0.714 | 0.714 | 0 | 0 | 0 |  |  | 0 | 0
7 | FFEQUIP HYDRAULIC JACK (BM-I) | N.A. | - | 0 | 0.57696 | 0.57696 | 0 | 0 | 0 |  |  | 0 | 0
8 | MOBILE COAL SAMPLING EQUIP-AUGER (FMC) CHP-I | N.A. | - | 0 | 1.5824 | 1.5824 | 0 | 0 | 0 |  |  | 0 | 0
9 | Replacement of ash slurry disposal pump to improve performance & capacity enhancement of ash slurry disposal system at AHP-1 Khaperkheda TPS | 0 | - | 0 | 4.92 | 4.92 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of Pillow Block Dodge Bearing Assemblies (Expansion & Non-Expansion) for PA fans in Unit- n1 to 4, at Khaperkheda TPS | 0 | - | 0 | 5.11 | 5.11 | 0 | 0 | 0 |  |  | 0 | 0
11 | Replacement of Economizer outlet to APH outlet common duct in unit no. 3 (210MW), Khaperkheda TPS | 0 | - | 0 | 6.24 | 6.24 | 0 | 0 | 0 |  |  | 0 | 0
12 | PROCUREMENT OF OIL COOLED SUSPENSION MAGNET FOR 210MW AND MODIFICATION & REPLACEMENT OF VIBRATING FEEDER WITH VIBRATING TRANSFER CHUTE FOR 210MW | 0 | - | 0 | 3.09 | 3.09 | 0 | 0 | 0 |  |  | 0 | 0
13 | DESIGN,ENGINEERING,MODIFICATION ,ERECTION AND COMMISSIONING OF DRIVE UNIT ARRANGEMENT FOR CONVEYOR 10 AT CHP1 | 0 | - | 0 | 1.65 | 1.65 | 0 | 0 | 0 |  |  | 0 | 0
14 | ENERGY EFFICIENT PLANT LIGHTING AND COLONY LIGHTING MODIFICATIONS | 0 | - | 0 | 21.04 | 21.04 | 0 | 0 | 0 |  |  | 0 | 0
15 | Supply installation testing and commisioning of various battery sets at unit No 1 & 2 of Khaperkheda TPS | 0 | - | 0 | 9.31 | 9.31 | 0 | 0 | 0 |  |  | 0 | 0
16 | Revamping and modification of existing alarm and protection system from fire and provide rapid extinguishing Clean Agent (CA) system at Unit #1 & 2 (210 MW) units, KPKD TPS | 0 | - | 0 | 8.21 | 8.21 | 0 | 0 | 0 |  |  | 0 | 0
17 | Supply of electronic modules for Procontrol DCS system in unit 1 to 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 1.18 | 1.18 | 0 | 0 | 0 |  |  | 0 | 0
18 | Revamping & UPGRADATION of SWAS system in unit 3 & 4 of 210 MW Khaperkheda TPS | 0 | - | 0 | 8.56 | 8.56 | 0 | 0 | 0 |  |  | 0 | 0
19 | Upgradation of process instrumentation in unit 1 to 2 of 210 MW Khaperkheda TPS | 0 | - | 0 | 4.64 | 4.64 | 0 | 0 | 0 |  |  | 0 | 0
20 | Replacement of flue gas duct from air heater outlet to esp inlet for U 1 & 2 (S+W) | 0 | - | 0 | 8.03 | 8.03 | 0 | 0 | 0 |  |  | 0 | 0
21 | PROCUREMENT OF COMPLETE ROTOR ASSEMBLY FOR NDZV 31 SIDOR IN UNIT NO. 1 & 2 KHAPERKHEDA TPS (ID FAN). | 0 | - | 0 | 14.52 | 14.52 | 0 | 0 | 0 |  |  | 0 | 0
22 | UPGRADATION OF BELT CONVEYOR CAPACITY OF 2C &2D AND 8A & 8B AT CHP1 | 0 | - | 0 | 3.94 | 3.94 | 0 | 0 | 0 |  |  | 0 | 0
23 | WORK OF DESIGN,ENGINEERING,ERECTION AND UPGRADATION OF DRIVE UNITS OF BELT CONVEYOR 3A & 3BAT CHP1 | 0 | - | 0 | 8.34 | 8.34 | 0 | 0 | 0 |  |  | 0 | 0
24 | Procurement of 1500 KW ID Fan Synchronous Motor at Unit 3 & 4 Khaperkheda TPS. | 0 | - | 0 | 3.12 | 3.12 | 0 | 0 | 0 |  |  | 0 | 0
25 | Procurement of Steam and Water Analysis System(SWAS) for Unit 1&2 (210MW) KPKD TPS, Khaperkheda. | 0 | - | 0 | 9.65 | 9.65 | 0 | 0 | 0 |  |  | 0 | 0
26 | Supply and replacement of complete PVC fills of cell of cooling tower of unit 1-4 (210 MW) at Khaperkheda TPS | 0 | - | 0 | 8.52 | 8.52 | 0 | 0 | 0 |  |  | 0 | 0
27 | PROCUREMENT OF FD FAN (BHEL AP 1-20/11) ASSEMBLY FOR UNIT 1 TO 4 ATKHAPERKHEDA TPS. | 0 | - | 0 | 4.37 | 4.37 | 0 | 0 | 0 |  |  | 0 | 0
28 | CHP performance improvement scheme for capacity restoration of drive units installed at CHP-1 (4 x 210 MW), TPS Khaperkheda. | 0 | - | 0 | 14.5 | 14.5 | 0 | 0 | 0 |  |  | 0 | 0
29 | Work of Design, Supply, Erection, Commissioning and Upgradation of complete electrical system for drive units of belt conveyor 8A & 8B and belt conveyor 2C & 2D at CHP-1 (4 x 210 MW), Khaperkheda TPS. | 0 | - | 0 | 2.15 | 2.15 | 0 | 0 | 0 |  |  | 0 | 0
30 | WORK OF DESING,SUPPLY ,ERECTION,COMMISSIONG AND UPGRADATION OF COMPLETE ELECTRICAL SYSTEM FOR DRIVE UNITS OF BELT CONVEYOR 3A & 3B AND BELT CONVEYOR 4A,4B,4C & 4D AT CHP1 Khaperkheda TPS. | 0 | - | 0 | 2.29 | 2.29 | 0 | 0 | 0 |  |  | 0 | 0
31 | Supply, Installation, & Commissioning of Instruments at coal Testing Lab, WTP-I, TPS Khaperkheda. | 0 | - | 0 | 0.45 | 0.45 | 0 | 0 | 0 |  |  | 0 | 0
32 | Supply, Installation & Commissioning and Refurbishment of asbestos based H2 Generator and compressor to convert it to non-asbestos based H2 Generator for Unit 1 to 5, Khaperkheda TPS. | 0 | - | 0 | 7.65 | 7.65 | 0 | 0 | 0 |  |  | 0 | 0
33 | construction of bituminous macadam roads at Prakashnagar Colony TPS Khaperkheda | 0 | - | 0 | 5.4 | 5.4 | 0 | 0 | 0 |  |  | 0 | 0
34 | Work of attending additional works based on structural report at Induced Draft Cooling Towers (IDCT) unit 1,2,3 & 4 at 4 x 210MW, TPS, Khaperkheda | 0 | - | 0 | 1.21 | 1.21 | 0 | 0 | 0 |  |  | 0 | 0
35 | VIBRATION ANALYSER | 0 | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
36 | Upgradation of GEHO pump instrumentation for AHP Unit No. 3 & 4 (210 MW) at Khaperkheda TPS | 0 | - | 0 | 1.27 | 1.27 | 0 | 0 | 0 |  |  | 0 | 0
37 | Refurbishment of HPT module for Unit 1 & 2 | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
38 | General Asset Furniture | N.A. | - | 0 | 0.86177 | 0.86177 | 0 | 0 | 0 |  |  | 0 | 0
39 | General Asset AC, Fans, Air coolers, water filter etc. | N.A. | - | 0 | 0.53608 | 0.41552 | 0.12056 | 0 | 0 |  |  | 0 | 0.12056
40 | General Asset Computer, scanners, etc. | N.A. | - | 0 | 2.5598 | 1.9461 | 0.61367 | 0 | 0 |  |  | 0 | 0.61367
41 | Land aquired for rly siding | N.A. | - | 0 | 0.4072 | 0.4072 | 0 | 0 | 0 |  |  | 0 | 0
42 | RCC ROAD FROM ASH SILO TO 'D' POINT FOR BULKER MO | N.A. | - | 0 | 0.95225 | 0.95225 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 3693.4669 | 3743.2016 | -49.7348 | 180.8 | 180.8 | 0 | 0 | 180.8 | -49.7348
`