## F4
MSPGCL-Paras U # 3-4
MTR Petition Formats - Generation
Form 4: Summary of Capital Expenditure and Capitalisation
(Rs. Crore)
Sr. No. | Particulars | FY 2022-23 |  |  | FY 2023-24 |  |  | FY 2024-25 |  |  |  |  | Ensuing Years |  |  |  |  | Remarks
|  | MYT Order (227 of 2022) | April-March (Audited ) | True-Up requirement | MYT Order (227 of 2022) | April-March (Audited ) | True-Up requirement | MYT Order (227 of 2022) | Apr-Sep (Estimated) | Oct-Mar (Projected) | April - March (Projected) | Provisional True-Up requirement | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30
|  | (a) | (b) | (c) = (b) - (a) | (d) | (e) | (f) = (e) - (d) | (g) | (h) | (i) | (j) = (h )+ (i) | (k) = (j) - (g) | Projected | Projected | Projected | Projected | Projected
1 | Capital Expenditure |  | 50.5713 | 50.5713 |  | 134.3751 | 134.3751 |  |  |  | 263.6406 | 263.6406 | 267.3423 | 203.184 | 201.61 | 59.45 | 46.55
2 | Capitalisation | 82.56 | 78.5823 | -3.9777 | 44.95 | 26.7271 | -18.2229 | 381.66 | 36.79 | 249.74 | 286.5317 | -95.1283 | 379.5305 | 264.684 | 209.81 | 70.25 | 55.25
3 | IDC |  |  | 0 |  |  | 0 |  |  |  |  | 0
4 | Capitalisation + IDC | 82.56 | 78.5823 | -3.9777 | 44.95 | 26.7271 | -18.2229 | 381.66 | 36.79 | 249.74 | 286.5317 | -95.1283 | 379.5305 | 264.684 | 209.81 | 70.25 | 55.25
Note: * - Truing Up for FY 2022-23 & FY 2023-24 to be done under MERC MYT Regulations 2019 with reference to amounts approved in the MYT Order for FY 2020-21 to FY 2024-25
Detailed Justification shall be provided for variation in approved capital expenditure and capitalisation vis-a-vis actual capital expenditure and capitalisation

## F4.1
MSPGCL-Paras U # 3-4
MTR Petition Formats - Generation
| Project Details |  | Form 4.1: Capital Expenditure Plan | [14 empty] | (Rs. Crore)
Sr. No. | Project Code | Project Title | MERC Approval No. | MERC Approval Date | Project Purpose | Project Start Date |  |  | Project Completion date (Scheduled) |  |  | Capital Cost
[6 empty] | Original | Revised | Actual | Original | Revised | Actual | Approved | Actual Capital Cost Incurred | Deviation = Approved - Actual on account of
[14 empty] | Change in Scope of Work (a) | Material Cost (b) | IDC (c) | Others (d) | Total Deviation (a+b+c+d)
A) DPR Schemes
(i) Submitted to MERC
1 | Power supply arrangement at colony & separate 25 KV OHE supply feeding arrangement to BESG siding & provision of Passenger elevators | DPR | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 |  | 2014-04-02 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
1.1 | Provision of separate 25 KV OHE supply feeding arrangement to BESG siding at Paras TPS | Scheme | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 |  | 2014-04-02 |  | 2013-04-13 | 2015-11-30 |  | 2015-01-04 | 0.3715 | 0.37148 |  | 2.17e-05 |  |  | 2.17e-05
1.2 | Arrangement of power supply for Paras TPS colony from 250 MW units with stepping down 6.6 KV supply to 3.3 KV. | Scheme | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 |  | 2014-04-02 |  | 2014-12-23 | 2015-09-27 |  | 2015-09-27 | 3.6334 | 1.9509 |  | 1.6825 |  |  | 1.6825
1.3 | Supply & installation of Total 12 nos. passenger elevators at `D’ & `E’ type quarters & administrative building of Paras TPS | Scheme | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 |  | 2014-04-02 |  | 2017-01-17 | 2018-03-30 |  | 2020-01-02 | 3.15 | 1.6426 |  | 1.5074 |  |  | 1.5074
2 | Ash Handling Plant augmentation scheme at Paras TPS Unit 3 & 4 | DPR | MERC/TECH 1/CAPEX/20142015/01160 | 2014-11-17 |  | 2014-11-17 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
2.1 | Ash Handling Plant augmentation scheme at Paras TPS Unit 3 & 4 | Scheme | MERC/TECH 1/CAPEX/20142015/01160 | 2014-11-17 |  | 2014-11-17 |  | 2018-02-06 | 2018-02-06 |  | 2021-07-29 | 34.6889 | 58.676 |  | -23.987 |  |  | -23.987
0 | IDC | IDC | MERC/TECH 1/CAPEX/20142015/01160 | 2014-11-17 |  | 2014-11-17 |  | - | - |  | - | 3.41 | 0.99854 |  | 2.4115 |  |  | 2.4115
3 | 3rd raising of Ash bund from TBL 273.63 mtr. to 276.63 mtr. with construction of masonry dam | DPR | MERC/MSPGCL/CAPEX/20142015/01648 | 2015-02-26 |  | 2015-02-26 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
3.1 | 3rd raising of Ash bund from TBL 273.63 mtr. to 276.63 mtr. with construction of masonry dam | Scheme | MERC/MSPGCL/CAPEX/20142015/01648 | 2015-02-26 |  | 2015-02-26 |  | 2015-06-30 | 2016-08-20 |  | 2017-07-30 | 8.2519 | 3.3121 |  | 4.9398 |  |  | 4.9398
0 | IDC | IDC | MERC/MSPGCL/CAPEX/20142015/01648 | 2015-02-26 |  | 2015-02-26 |  | - | - |  | - | 0.95855 | 0 |  | 0.95855 |  |  | 0.95855
4 | Various schemes related to CHP Improvement and Stack Management & Coal Mill Performance Improvement schemes | DPR | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 |  | 2016-11-29 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
4.1 | Procurement of apron feeder system, pan & chain Assembly (2 no.’s) | Scheme | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 |  | 2016-11-29 |  | 2017-01-05 | 2017-11-30 |  | 2021-07-15 | 7.44 | 7.521 |  | -0.081032 |  |  | -0.081032
4.2 | Procurement of Assembly of Impact Crusher complete set with Beater Arm & Head.(1 no.) | Scheme | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 |  | 2016-11-29 |  | 2014-06-24 | 2017-11-30 |  | 2017-18 | 1.57 | 1.6013 |  | -0.031342 |  |  | -0.031342
4.3 | Procurement of Slewing Bearing of Stacker Reclaimer. (1 no.) | Scheme | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 |  | 2016-11-29 |  | 2014-06-21 | 2017-11-30 |  | 2017-18 | 1.45 | 1.4676 |  | -0.017625 |  |  | -0.017625
4.4 | Capacity Enhancement of Wagon Tippler at Old CHP. | Scheme | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 |  | 2016-11-29 |  | 2014-08-07 | 2017-11-30 |  | 2017-18 | 2.86 | 2.9502 |  | -0.090208 |  |  | -0.090208
4.5 | Procurement of Bulldozer BD-155 for CHP(1 no.) | Scheme | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 |  | 2016-11-29 |  | 2014-01-09 | 2017-11-30 |  | 2017-18 | 1.7 | 2.1022 |  | -0.4022 |  |  | -0.4022
4.6 | Procurement of Girth Gear and Pinion for BBD 4772 coal mills of 250 MW (1 set) | Scheme | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 |  | 2016-11-29 |  | 2014-06-16 | 2017-11-30 |  | 2017-18 | 1.6 | 1.6943 |  | -0.094306 |  |  | -0.094306
0 | IDC | IDC | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 |  | 2016-11-29 |  | - | - |  | - | 1.12 | 0 |  | 1.12 |  |  | 1.12
5 | Procurement of Two Cartridge assembly for Boiler Feed Pump (Type: FK-3B-40) of 250MW Set | DPR | MERC/MSPGCL/CAPEX/20162017/04228 | 2017-09-22 |  | 2017-09-22 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
5.1 | Procurement of Two Cartridge assembly for Boiler Feed Pump (Type: FK-3B-40) of 250MW Set | Scheme | MERC/MSPGCL/CAPEX/20162017/04228 | 2017-09-22 |  | 2017-09-22 |  | 2018-05-25 | 2019-03-30 |  | 2017-18 | 13.88 | 14.0416 |  | -0.16156 |  |  | -0.16156
6 | Replacement of battery bank set, replacement of two complete set of air pre-heater baskets & coal compartment assemblies for 250MW Unit 4 at Paras TPS | DPR | MERC/CAPEX/2019-2020/0137 | 2019-05-15 |  | 2019-05-15 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
6.1 | Replacement of battery bank set to enhance process reliability of 250 MW Unit-4 at Paras TPS. | Scheme | MERC/CAPEX/2019-2020/0137 | 2019-05-15 |  | 2019-05-15 |  | 2019-01-07 | 2020-01-08 |  | 2021-05-30 | 7.54 | 8.4214 |  | -0.88136 |  |  | -0.88136
6.2 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-4, Paras TPS. | Scheme | MERC/CAPEX/2019-2020/0137 | 2019-05-15 |  | 2019-05-15 |  | 2019-01-01 | 2019-01-12 |  | 2019-01-10 | 1.78 | 2.45 |  | -0.67 |  |  | -0.67
6.3 | Procurement & Replacement of Coal Compartment Assemblies Baskets at 250 MW Unit-4, Paras TPS. | Scheme | MERC/CAPEX/2019-2020/0137 | 2019-05-15 |  | 2019-05-15 |  | 2019-01-08 | 2019-01-12 |  | 2022-10-19 | 0.75 | 0.56974 |  | 0.18026 |  |  | 0.18026
0 | IDC | IDC | MERC/CAPEX/2019-2020/0137 | 2019-05-15 |  | 2019-05-15 |  | - | - |  | - | 0.04 | 0.25586 |  | -0.21586 |  |  | -0.21586
7 | Procurement & Replacement of complete set of Economizer and LTSH upper & lower coils at Unit-3, Paras TPS | DPR | MERC/CAPEX/2019-2020/2 | 2019-05-24 |  | 2019-05-24 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
7.1 | Replacement of complete set of economizer (upper & lower) coil assemblies & LTSH (upper & lower) coil assemblies for Unit-3. | Scheme | MERC/CAPEX/2019-2020/2 | 2019-05-24 |  | 2019-05-24 |  | 2019-01-08 | 2020-01-12 |  | WIP | 10.6 | 8.8 |  | 1.8 |  |  | 1.8
0 | IDC | IDC | MERC/CAPEX/2019-2020/2 | 2019-05-24 |  | 2019-05-24 |  | - | - |  | - | 0.22 | 1.8345 |  | -1.6145 |  |  | -1.6145
8 | HMI (Human Machine Interface) up gradation of DCS UNIT-3 & 4, WTP (Water Treatment Plant unit-3 & 4 combined PLC system) & AHP (Ash Handling Plant Unit-3 & 4 PLC System), Procurement of girth gear & pinion for optimum availability of auxiliary at Paras TPS | DPR | MERC/CAPEX/2019-2020/644 | 2019-08-26 |  | 2019-08-26 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
8.1 | Up-gradation of Existing Max-DNA System (HMI) at Paras TPS (U# 3 & 4). | Scheme | MERC/CAPEX/2019-2020/644 | 2019-08-26 |  | 2019-08-26 |  | 2019-01-08 | 2020-01-12 |  | WIP | 7.12 | 8.4417 |  | -1.3217 |  |  | -1.3217
8.2 | Up-gradation of GE IP (GE-Fanuc) make PLC system (HMI) installed at WTP at Paras TPS (Combined for U# 3 & 4). | Scheme | MERC/CAPEX/2019-2020/644 | 2019-08-26 |  | 2019-08-26 |  | 2019-01-08 | 2020-01-12 |  | 2021-12-02 | 0.38 | 0.36789 |  | 0.01211 |  |  | 0.01211
8.3 | Up-gradation of GE IP (GE-Fanuc) make PLC system (HMI) installed at AHP Unit - 4 at Paras TPS. | Scheme | MERC/CAPEX/2019-2020/644 | 2019-08-26 |  | 2019-08-26 |  | 2019-01-08 | 2020-01-12 |  | 2021-02-03 | 0.48 | 0.45873 |  | 0.021268 |  |  | 0.021268
8.4 | Up-gradation of Existing Schneider make PLC (HMI + PLC hardware) installed at AHP Unit - 3 at Paras TPS. | Scheme | MERC/CAPEX/2019-2020/644 | 2019-08-26 |  | 2019-08-26 |  | 2019-01-08 | 2020-01-12 |  | WIP | 0.9 | 0.7788 |  | 0.1212 |  |  | 0.1212
8.5 | Procurement & installation of Girth Gear & Pinion for coal mill BBD-4772. | Scheme | MERC/CAPEX/2019-2020/644 | 2019-08-26 |  | 2019-08-26 |  | 2019-01-08 | 2020-01-12 |  | 2021-03-31 | 2.26 | 2.1171 |  | 0.14288 |  |  | 0.14288
0 | IDC | IDC | MERC/CAPEX/2019-2020/644 | 2019-08-26 |  | 2019-08-26 |  | - | - |  | - | 0 | 0.45004 |  | -0.45004 |  |  | -0.45004
9 | Complete Track Renewal at Paras TPS | DPR | MERC/CAPEX/2019-2020/479 | 2019-08-02 |  | 2019-08-02 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
9.1 | Complete Track Renewal at Paras TPS | Scheme | MERC/CAPEX/2019-2020/479 | 2019-08-02 |  | 2019-08-02 |  | 2019-01-08 | 2020-01-12 |  | WIP | 12.05 | 7.5378 |  | 4.5122 |  |  | 4.5122
0 | IDC | IDC | MERC/CAPEX/2019-2020/479 | 2019-08-02 |  | 2019-08-02 |  | - | - |  | - | 0.72 | 0.078332 |  | 0.64167 |  |  | 0.64167
10 | Procurement & Replacement of water wall panels in Unit#4 & Installation of VFD to existing eddy current drive driven coal feeders at 2x250 MW at Paras TPS | DPR | MERC/CAPEX/2019-2020/664 | 2019-08-28 |  | 2019-08-28 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
10.1 | Replacement of water wall panel in Unit-4 Boiler at 2 X 250 MW, PTPS | Scheme | MERC/CAPEX/2019-2020/664 | 2019-08-28 |  | 2019-08-28 |  | 2019-01-08 | 2020-01-08 |  | WIP | 6.49 | 2.7423 |  | 3.7477 |  |  | 3.7477
10.2 | Installation of VFD with controller over existing eddy current drives with controller at 2 X 250 MW, PTPS. | Scheme | MERC/CAPEX/2019-2020/664 | 2019-08-28 |  | 2019-08-28 |  | 2019-01-08 | 2020-01-08 |  | WIP | 6.23 | 6.1732 |  | 0.056806 |  |  | 0.056806
0 | IDC | IDC | MERC/CAPEX/2019-2020/664 | 2019-08-28 |  | 2019-08-28 |  | - | - |  | - | 0 | 1.0135 |  | -1.0135 |  |  | -1.0135
11 | Reinforcement & Capacity Enhancement of Old CHP Coal Conveyor Belt Structure from (200 TPH to 360 TPH) at old CHP Paras TPS & Procurement of One No. of Bulldozer & Diesel Hydraulic Locomotive at Paras TPS | DPR | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 |  | 2021-11-09 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
11.1 | Capacity Enhancement of Old CHP Conveyor belt from 200 TPH to 360 TPH at Old CHP, Paras TPS. | Scheme | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 |  | 2021-11-09 |  | 2021-01-12 | - |  | WIP | 2.94 | 0 |  | 2.94 |  |  | 2.94
11.2 | Reinforcement of Belt Conveyor structure at Old CHP, Paras TPS. | Scheme | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 |  | 2021-11-09 |  | 2021-01-12 | - |  | WIP | 2.66 | 0 |  | 2.66 |  |  | 2.66
11.3 | Procurement of Bulldozer at CHP, Paras TPS. | Scheme | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 |  | 2021-11-09 |  | 2021-01-12 | 2021-22 |  | 2021-22 | 2.31 | 2.4909 |  | -0.18089 |  |  | -0.18089
11.4 | Procurement of Diesel Hydraulic Locomotive at CHP, Paras TPS. | Scheme | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 |  | 2021-11-09 |  | 2021-01-12 | - |  | WIP | 3.6 | 3.2208 |  | 0.37919 |  |  | 0.37919
0 | IDC | IDC | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 |  | 2021-11-09 |  | - | - |  | - | 0.9 | 0 |  | 0.9 |  |  | 0.9
12 | Flue Gas Desulpherization (FGD) System for Paras Unit No. 3 & 4 | DPR | MERC/CAPEX/2020-2021/WFH/SBR/42 | 2020-12-14 |  | 2020-12-14 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
12.1 | Flue Gas Desulpherization (FGD) System for Paras Unit No. 3 & 4 | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/42 | 2020-12-14 |  | 2020-12-14 |  | 2022-05-19 | - |  | 2024-10-19 | 347.02 | 115.2387 |  | 231.7813 |  |  | 231.7813
0 | IDC | IDC | MERC/CAPEX/2020-2021/WFH/SBR/42 | 2020-12-14 |  | 2020-12-14 |  | - | - |  | - | 29.04 | 0 |  | 29.04 |  |  | 29.04
13 | Procurement & Installation of complete assembly of Elecon make Gear Boxes, Wagon Tippler Assembly; Design, Supply, Installation, Commissioning & Successful Trial of Link Conveyor from Stackyard to C-2 Conveyor Belt at CHP; Procurement of Bucket Wheel of Stacker Reclaimer for CHP at Paras TPS | DPR | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 |  | 2024-05-30 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
13.1 | Procurement & Installation of complete assembly of Elecon make Gear Boxes, Wagon Tippler Assembly; Design, Supply, Installation, Commissioning & Successful Trial of Link Conveyor from Stackyard to C-2 Conveyor Belt at CHP; Procurement of Bucket Wheel of Stacker Reclaimer for CHP at Paras TPS | Scheme | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 |  | 2024-05-30 |  | - | - |  | - | 32.78 | 0 |  | 32.78 |  |  | 32.78
13.2 | Procurement of Wagon Tippler Assembly & Installation of the same at CHP at Paras TPS | Scheme | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 |  | 2024-05-30 |  | - | - |  | - | 13.9 | 0 |  | 13.9 |  |  | 13.9
13.3 | Design, supply, installation, commissioning & successful trial of Link Conveyor from Stackyard to C-2 conveyor belt at CHP, Paras TPS | Scheme | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 |  | 2024-05-30 |  | - | - |  | - | 5.93 | 0 |  | 5.93 |  |  | 5.93
13.4 | Procurement of bucket wheel of stacker reclaimer for CHP 250MW Paras TPS | Scheme | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 |  | 2024-05-30 |  | - | - |  | - | 1.07 | 0 |  | 1.07 |  |  | 1.07
0 | IDC | IDC | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 |  | 2024-05-30 |  | - | - |  | - | 1.3 | 0 |  | 1.3 |  |  | 1.3
HO DPR 5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | DPR | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 |  | 2014-11-25 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 5.6 | Paras: Procurement of HT Motors(CEP/ACW Motors-I Phase and CW/CHP Motors-II Phase)for U-3&4 | Scheme | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 |  | 2014-11-25 |  | 2017-01-05 | 2017-03-30 |  | 2022-23 | 3.6 | 2.0958 |  | 1.5042 |  |  | 1.5042
0 | IDC | IDC | 0 | - |  | - |  | - | - |  | - | 0 | 1.235 |  | -1.235 |  |  | -1.235
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | DPR | MERC/CAPEX/20162017/00423 | 2016-08-03 |  | 2016-08-03 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 6.1 | PARAS(U-3 & 4) | Scheme | MERC/CAPEX/20162017/00423 | 2016-08-03 |  | 2016-08-03 |  | 2017-01-01 | 2016-09-30 |  | 2019-01-09 | 3.9773 | 3.8456 |  | 0.13166 |  |  | 0.13166
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | DPR | MERC/CAPEX/20162017/00774 | 2016-09-30 |  | 2016-09-30 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 7.1 | Paras TPS | Scheme | MERC/CAPEX/20162017/00774 | 2016-09-30 |  | 2016-09-30 |  | - | - |  | - | 2.0276 | 0 |  | 2.0276 |  |  | 2.0276
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | DPR | MERC/CAPEX/20172018/4653 | 2017-11-13 |  | 2017-11-13 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender at Paras TPS | Scheme | MERC/CAPEX/20172018/4653 | 2017-11-13 |  | 2017-11-13 |  | 2018-01-01 | 2018-19 |  | 2021-22 | 1.45 | 2.9191 |  | -1.4691 |  |  | -1.4691
HO DPR 8.2 | Normal Multipurpose Fire Tender at Paras TPS | Scheme | MERC/CAPEX/20172018/4653 | 2017-11-13 |  | 2017-11-13 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
0 | IDC | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 |  | 2017-11-13 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | DPR | MERC/CAPEX/20172018/0177 | 2018-02-06 |  | 2018-02-06 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 10.1 | TPS Paras | Scheme | MERC/CAPEX/20172018/0177 | 2018-02-06 |  | 2018-02-06 |  | 2018-01-08 | 2019-20 |  | 2022-03-31 | 2.0768 | 1.6142 |  | 0.46263 |  |  | 0.46263
HO DPR 11 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | DPR | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 |  | 2022-02-12 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 11.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | Scheme | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 |  | 2022-02-12 |  | - | - |  | - | 54.24 | 0 |  | 54.24 |  |  | 54.24
0 | IDC | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 |  | 2022-02-12 |  | - | - |  | - | 2.76 | 0 |  | 2.76 |  |  | 2.76
HO DPR 12 | Centralized Monitoring Solution | DPR | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 |  | 2023-11-02 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 12.1 | Centralized Monitoring Solution | Scheme | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 |  | 2023-11-02 |  | - | - |  | - | 66.009 | 0 |  | 66.009 |  |  | 66.009
0 | IDC | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 |  | 2023-11-02 |  | - | - |  | - | 3.3 | 0 |  | 3.3 |  |  | 3.3
Formulas:
Project Start Date = [MERC Approval Date]

## F4.2
MSPGCL-Paras U # 3-4
MTR Petition Formats - Generation
| Project Details |  | Form 4.2: Capitalisation Plan | [18 empty] | (Rs. Crore) | [24 empty] | (Rs. Crore)
Sr. No. | Project Code | DPR | MERC Approval No. | Date of Submission | MERC Approval Date | Cost as per DPR Crs. | MERC Approved Cost | Debt Equity Ratio | Grant Funding | Approved Start Date | Actual Start Date | Approved Date of Completion | Actual Date of Completion | Benefits in Quantified Terms | Capital Expenditure | [12 empty] | Physical Progress (%) | [11 empty] | Capitalisation | [12 empty] | Old Asset retired against capitalised item (in Rs. Cr) | Remarks | Current Status
[15 empty] | Actual Capex till FY 2018-19 | Actual | Actual | Actual | Actual Capex till FY 2021-22 | Actual | Actual | Revised Projected | Projected | Projected | Projected | Projected | Projected | Actual Progress till FY 2018-19 | Actual | Actual | Actual | Actual | Actual | Revised Projected | Projected | Projected | Projected | Projected | Projected | Actual Capitalization till FY 2018-19 | Actual | Actual | Actual | Actual Capitalization till FY 2021-22 | Actual | Actual | Revised Projected | Projected | Projected | Projected | Projected | Projected
[16 empty] | FY 2019-20 | FY 2020-21 | FY 2021-22 |  | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 |  | FY 2019-20 | FY 2020-21 | FY 2021-22 | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 |  | FY 2019-20 | FY 2020-21 | FY 2021-22 |  | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30
[55 empty] | N.A. | DPR | Not Initiated
| A) DPR Schemes | [53 empty] | N.A. | Scheme | WIP
| (i) Submitted to MERC | [53 empty] | N.A. | IDC | Partially Capitalised
1 | Power supply arrangement at colony & separate 25 KV OHE supply feeding arrangement to BESG siding & provision of Passenger elevators | DPR | MERC/TECH 1/CAPEX/20132014/00030 | 2013-12-30 | 2014-04-02 | 7.1549 | 7.1549 |  |  | 2014-04-02 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A. | Non-DPR | Capitalised
1.1 | Provision of separate 25 KV OHE supply feeding arrangement to BESG siding at Paras TPS | Scheme | MERC/TECH 1/CAPEX/20132014/00030 | 2013-12-30 | 2014-04-02 | 0.3715 | 0.3715 |  |  | 2014-04-02 | 2013-04-13 | 2015-11-30 | 2015-01-04 | The schemes of DPR do not affect the plant parameters and hence calculation for cost benefits is not possible | 0.37148 | 0 | 0 | 0 | 0.37148 | 0 | 0 | 0 | [5 empty] | 100% | - | - | - | - | - | - | [5 empty] | 0.37148 | 0 | 0 | 0 | 0.37148 | 0 | 0 | 0 | [7 empty] | Capitalised |  | Cancelled
1.2 | Arrangement of power supply for Paras TPS colony from 250 MW units with stepping down 6.6 KV supply to 3.3 KV. | Scheme | MERC/TECH 1/CAPEX/20132014/00030 | 2013-12-30 | 2014-04-02 | 3.6334 | 3.6334 |  |  | 2014-04-02 | 2014-12-23 | 2015-09-27 | 2015-09-27 | The schemes of DPR do not affect the plant parameters and hence calculation for cost benefits is not possible. | 1.9509 | 0 | 0 | 0 | 1.9509 | 0 | 0 | 0 | [5 empty] | 100% | - | - | - | - | - | - | [5 empty] | 1.9509 | 0 | 0 | 0 | 1.9509 | 0 | 0 | 0 | [7 empty] | Capitalised |  | To be cancelled
1.3 | Supply & installation of Total 12 nos. passenger elevators at `D’ & `E’ type quarters & administrative building of Paras TPS | Scheme | MERC/TECH 1/CAPEX/20132014/00030 | 2013-12-30 | 2014-04-02 | 3.15 | 3.15 |  |  | 2014-04-02 | 2017-01-17 | 2018-03-30 | 2020-01-02 | The schemes of DPR do not affect the plant parameters and hence calculation for cost benefits is not possible. | 1.5069 | 0.1357 | 0 | 0 | 1.6426 | 0 | 0 | 0.13204 | [5 empty] | 30% | 70% | 100% | - | - | - | - | [5 empty] | 1.5069 | 0.1357 | 0 | 0 | 1.6426 | 0 | 0 | 0.13204 | [6 empty] | PO placed vide No.- 4370000919 , Work Completed on 21-01-2020. Capitalization done in FY 2019-20. Two Year AMC work completed as per PO & biil awaited from vendor. | Capitalised |  | N.A.
2 | Ash Handling Plant augmentation scheme at Paras TPS Unit 3 & 4 | DPR | MERC/TECH 1/CAPEX/20142015/01160 | 2014-08-25 | 2014-11-17 | 38.0989 | 38.0989 |  |  | 2014-11-17 | [8 empty] | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | N.A.
2.1 | Ash Handling Plant augmentation scheme at Paras TPS Unit 3 & 4 | Scheme | MERC/TECH 1/CAPEX/20142015/01160 | 2014-08-25 | 2014-11-17 | 34.6889 | 34.6889 |  |  | 2014-11-17 | 2018-02-06 | 2018-02-06 | 2021-07-29 | Investment for AHP Augmentation scheme i.e. extension of Ash Slurry pipe lines and Pumping Scheme is the requirement of system. As such there is no alternate arrangement to dispose the ash and hence cost benefit cannot be quantified | 38.0721 | 13.7427 | 3.7239 | 3.1373 | 58.676 | 0 |  | 2.35 | [6 empty] | 30% | 70% | 100% | - | - | - | [5 empty] | 0 | 0 | 0 | 0 | 0 | 44.7505 | 13.9255 | 2.3525 | [6 empty] | Rs. 44.75 Cr. capitalized in FY22-23. Balance 14.92 with IDC is capitalized during FY-23-24. Time Overun- * GST implication * Government impose restrictions due to Covid-19 * As plant in running condition it was difficult to give work front. Cost Overrun- * Highly undulating terrain/geography of existing land * Quantities of pipe culverts, Box culverts & Retaining wall increased due to execution of the work in submergence area of Paras Barrage * Change in the alignment of ash pipeline corridor & service road * The garlanding work of ash Pipeline at Gazipur ash bund * Additional work of concrete Approach Road towards crematorium at Satargaon Village. * Details for cost overrun submitted by P&P is attached herewith. *15 Th Final bill ,bill of quntity variation and PV bill of Rs.2.35 cr as per civil-3 office note no.00279 dt 16.10.2024 will be capitalised in fy 24-25. | Partially Capitalised
| IDC | IDC | MERC/TECH 1/CAPEX/20142015/01160 | 2014-08-25 | 2014-11-17 | 3.41 | 3.41 |  |  | 2014-11-17 | [8 empty] | 0 | 0.99854 | [23 empty] | 0 |  | 0.99854 | [8 empty] | N.A.
3 | 3rd raising of Ash bund from TBL 273.63 mtr. to 276.63 mtr. with construction of masonry dam | DPR | MERC/MSPGCL/CAPEX/20142015/01648 | 2014-12-19 | 2015-02-26 | 9.2104 | 9.2104 |  |  | 2015-02-26 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
3.1 | 3rd raising of Ash bund from TBL 273.63 mtr. to 276.63 mtr. with construction of masonry dam | Scheme | MERC/MSPGCL/CAPEX/20142015/01648 | 2014-12-19 | 2015-02-26 | 8.2519 | 8.2519 |  |  | 2015-02-26 | 2015-06-30 | 2016-08-20 | 2017-07-30 | Cost benefit of work cannot be measured in trems of amount. Ash bund is necessary for deposition of ash generated due to burning of coal. It is inevitable process of generation of electricity. Power plant cannot be run without arrangement for deposition of ash. However, ash generated can be utilized in manufacturing of ash bricks, cement etc.,in contruction work of ash bund,concrete road etc. | 3.3121 |  |  |  | 3.3121 | [8 empty] | 100% | [11 empty] | 3.3121 |  |  |  | 3.3121 | [10 empty] | Capitalised
| IDC | IDC | MERC/MSPGCL/CAPEX/20142015/01648 | 2014-12-19 | 2015-02-26 | 0.95855 | 0.95855 |  |  | 2015-02-26 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
4 | Various schemes related to CHP Improvement and Stack Management & Coal Mill Performance Improvement schemes | DPR | MERC/MSPGCL/CAPEX/20152016/00907 | 2015-10-28 | 2016-11-29 | 17.74 | 17.74 |  |  | 2016-11-29 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
4.1 | Procurement of apron feeder system, pan & chain Assembly (2 no.’s) | Scheme | MERC/MSPGCL/CAPEX/20152016/00907 | 2015-10-28 | 2016-11-29 | 7.44 | 7.44 |  |  | 2016-11-29 | 2017-01-05 | 2017-11-30 | 2021-07-15 | By maintaining the availability of major parts of the Apron Feeder the auxiliary down time will be reduced. The Apron Feeder availability will be improved. | 0 | 5.4137 | 2.1073 |  | 7.521 | [9 empty] | 50% | 70% | 100% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 7.521 | [8 empty] | PO placed vide No-4385000047.Capitalized in FY 2022-23. Reason for Cost Overun:- Cost Overrun is due to change in taxation from S-Tax to GST | Capitalised
4.2 | Procurement of Assembly of Impact Crusher complete set with Beater Arm & Head.(1 no.) | Scheme | MERC/MSPGCL/CAPEX/20152016/00907 | 2015-10-28 | 2016-11-29 | 1.57 | 1.57 |  |  | 2016-11-29 | 2014-06-24 | 2017-11-30 | 2017-18 |  | 1.6013 |  |  |  | 1.6013 | [8 empty] | 100% | [11 empty] | 1.6013 |  |  |  | 1.6013 | [9 empty] | Scheme completed. | Capitalised
4.3 | Procurement of Slewing Bearing of Stacker Reclaimer. (1 no.) | Scheme | MERC/MSPGCL/CAPEX/20152016/00907 | 2015-10-28 | 2016-11-29 | 1.45 | 1.45 |  |  | 2016-11-29 | 2014-06-21 | 2017-11-30 | 2017-18 |  | 1.4676 |  |  |  | 1.4676 | [8 empty] | 100% | [11 empty] | 1.4676 |  |  |  | 1.4676 | [9 empty] | Scheme completed. | Capitalised
4.4 | Capacity Enhancement of Wagon Tippler at Old CHP. | Scheme | MERC/MSPGCL/CAPEX/20152016/00907 | 2015-10-28 | 2016-11-29 | 2.86 | 2.86 |  |  | 2016-11-29 | 2014-08-07 | 2017-11-30 | 2017-18 |  | 2.9502 |  |  |  | 2.9502 | [8 empty] | 100% | [11 empty] | 2.9502 |  |  |  | 2.9502 | [9 empty] | Scheme completed. | Capitalised
4.5 | Procurement of Bulldozer BD-155 for CHP(1 no.) | Scheme | MERC/MSPGCL/CAPEX/20152016/00907 | 2015-10-28 | 2016-11-29 | 1.7 | 1.7 |  |  | 2016-11-29 | 2014-01-09 | 2017-11-30 | 2017-18 | Maximum dozer required in monsoon for reclaim any coal and stacking of wet coal on ground. In case of non-availability of bulldozers, coal bunkering affects generation loss consequently demurrage charges increase. | 2.1022 |  |  |  | 2.1022 | [8 empty] | 100% | [11 empty] | 2.1022 |  |  |  | 2.1022 | [9 empty] | Scheme completed. | Capitalised
4.6 | Procurement of Girth Gear and Pinion for BBD 4772 coal mills of 250 MW (1 set) | Scheme | MERC/MSPGCL/CAPEX/20152016/00907 | 2015-10-28 | 2016-11-29 | 1.6 | 1.6 |  |  | 2016-11-29 | 2014-06-16 | 2017-11-30 | 2017-18 | At present Paras TPS do not have Girth Gear and Pinion in stack. If any problem arises in existing Girth Gear and Pinion, then one coal mill with two coal feeders will be out of service, Due to non availability of one coal mill, Oil consumption may increase. Also preventative maintenance schedule may get disturbed. | 1.6943 |  |  |  | 1.6943 | [8 empty] | 100% | [11 empty] | 1.6943 |  |  |  | 1.6943 | [9 empty] | Scheme completed. | Capitalised
| IDC | IDC | MERC/MSPGCL/CAPEX/20152016/00907 | 2015-10-28 | 2016-11-29 | 1.12 | 1.12 |  |  | 2016-11-29 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
5 | Procurement of Two Cartridge assembly for Boiler Feed Pump (Type: FK-3B-40) of 250MW Set | DPR | MERC/MSPGCL/CAPEX/20162017/04228 | 2017-01-31 | 2017-09-22 | 13.88 | 13.88 |  |  | 2017-09-22 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
5.1 | Procurement of Two Cartridge assembly for Boiler Feed Pump (Type: FK-3B-40) of 250MW Set | Scheme | MERC/MSPGCL/CAPEX/20162017/04228 | 2017-01-31 | 2017-09-22 | 13.88 | 13.88 |  |  | 2017-09-22 | 2018-05-25 | 2019-03-30 | 2017-18 | Availability of new spare BFP cartridge will avoid any emergency & generation loss due to it. Subsequently, the auxiliary power consumption of plant will be reduced subsequentially. This will result in considerable savings. | 14.0416 |  |  |  | 14.0416 | [8 empty] | 100% | [11 empty] | 14.0416 |  |  |  | 14.0416 | [10 empty] | Capitalised
6 | Replacement of battery bank set, replacement of two complete set of air pre-heater baskets & coal compartment assemblies for 250MW Unit 4 at Paras TPS | DPR | MERC/CAPEX/2019-2020/0137 | 2018-09-21 | 2019-05-15 | 10.11 | 10.11 |  |  | 2019-05-15 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
6.1 | Replacement of battery bank set to enhance process reliability of 250 MW Unit-4 at Paras TPS. | Scheme | MERC/CAPEX/2019-2020/0137 | 2018-09-21 | 2019-05-15 | 7.54 | 7.54 |  |  | 2019-05-15 | 2019-01-07 | 2020-01-08 | 2021-05-30 | • Availability & Reliability of Unit get Increased. | 0 | 0 | 8.0644 | 0.35695 | 8.4214 | 0 | 0 | 0 | [6 empty] | 70% | 90% | 100% | - | - | - | [5 empty] | 0 | 0 | 0 | 8.4214 | 8.4214 | 0 | 0 | 0 | [5 empty] | 0 | Scheme completed / As estimated cost was not included Packing & Freight Charges Hence, Cost Increased by 2% Packing & 2% Freight Charges PO.4385000111 Intrest Amounting of Rs.2183872 has been capitalized in 22-23. | Capitalised
6.2 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-4, Paras TPS. | Scheme | MERC/CAPEX/2019-2020/0137 | 2018-09-21 | 2019-05-15 | 1.78 | 1.78 |  |  | 2019-05-15 | 2019-01-01 | 2019-01-12 | 2019-01-10 | Net improvement in unit heat rate. | 0 | 2.45 | 0 | 0 | 2.45 | 0 | 0 | 0 | [5 empty] | 70% | 100% | - | - | - | - | - | [5 empty] | 0 | 2.45 | 0 | 0 | 2.45 | 0 | 0 | 0 | [5 empty] | 0 | Scheme completed. / justification for cost overrun .please confirm from CPA. Amounting of Rs 20010/- Intrest has been capitalized in fy 22-23. | Capitalised
6.3 | Procurement & Replacement of Coal Compartment Assemblies Baskets at 250 MW Unit-4, Paras TPS. | Scheme | MERC/CAPEX/2019-2020/0137 | 2018-09-21 | 2019-05-15 | 0.75 | 0.75 |  |  | 2019-05-15 | 2019-01-08 | 2019-01-12 | 2022-10-19 | • Optimal fuel consumption. • Reduction in fuel consumption. • Reduction in aux. Consumption | 0 | 0 | 0 | 0.46586 | 0.46586 | 0.10388 | 0 | 0 | [5 empty] | 30% | 70% | 80% | 90% | 100% | - | - | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.56974 | 0 | 0 | [5 empty] | 0 | Supply PO-HO/4370002640 dated 30-03-2021 +IDC 3,75,388.00 Works PO-PTPS/4385000610/No.4746 dated 12-09-2022. Work completed on 19-10-2022. capitalized in FY 2022-23. 46,58,640.00+9,049.33+10,29,743.52 | Capitalised
| IDC | IDC | MERC/CAPEX/2019-2020/0137 | 2018-09-21 | 2019-05-15 | 0.04 | 0.04 |  |  | 2019-05-15 | [8 empty] | 0 | 0.25586 | [23 empty] | 0 | 0.25786 | [9 empty] | N.A.
7 | Procurement & Replacement of complete set of Economizer and LTSH upper & lower coils at Unit-3, Paras TPS | DPR | MERC/CAPEX/2019-2020/2 | 2019-01-15 | 2019-05-24 | 10.82 | 10.82 |  |  | 2019-05-24 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
7.1 | Replacement of complete set of economizer (upper & lower) coil assemblies & LTSH (upper & lower) coil assemblies for Unit-3. | Scheme | MERC/CAPEX/2019-2020/2 | 2019-01-15 | 2019-05-24 | 10.6 | 10.6 |  |  | 2019-05-24 | 2019-01-08 | 2020-01-12 | WIP | Due to implementation of this scheme, Reliability of power plant will increase, heat rate will improve and the units are expected to achieve their design parameter. After implementation of this scheme, Boiler efficiency will improve. Quality/service will be improved as requirement of fuel will be reduce as boiler efficiency is going to increase. | 0 | 0 | 0 | 8.8 | 8.8 | 0 | 0 | 3.0971 | [5 empty] | 20% | 20% | 40% | 60% | 80% | 80% | 100% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | - | 11.8971 | [5 empty] | 0 | Supply POs:- * LTSH (Upper+Lower)- -HO/4370002563/No. 5167 dated 05-11-2020. Material received on 14.01.2022. * ECO Coil-HO/4370002567/No. 5168 dated 05-11-2020- Material received on 25-10-2021. Works POs:- LTSH LHS- PO No-4385000682(Rs. 1.07 Cr) LTSH RHS-PO No- 4385000681(Rs. 1,07 Cr) ECO LHS-PO No-4385000685 ( Rs. 0.67 Cr.) ECO RHS-PO No-4385000683 (Rs. 0. 67 Cr.) (Total Work portion- 3,48,38,845.17) PO placed. Work is completed in COH U-3 in FY 2024-25.(July-2024) Intrest expenditure in FY 22-23 details as per po Rs.4628211-PO 4370002563&Rs.3733221-PO 4370002567 and Rs. 8736229 Interest expenditure in FY 2023-24 | Capitalised
| IDC | IDC | MERC/CAPEX/2019-2020/2 | 2019-01-15 | 2019-05-24 | 0.22 | 0.22 |  |  | 2019-05-24 | [8 empty] | 0 | 0.96092 | 0.87362 | [22 empty] | 0 |  |  | 1.8345 | [7 empty] | N.A.
8 | HMI (Human Machine Interface) up gradation of DCS UNIT-3 & 4, WTP (Water Treatment Plant unit-3 & 4 combined PLC system) & AHP (Ash Handling Plant Unit-3 & 4 PLC System), Procurement of girth gear & pinion for optimum availability of auxiliary at Paras TPS | DPR | MERC/CAPEX/2019-2020/644 | 2019-01-19 | 2019-08-26 | 11.5 | 11.14 |  |  | 2019-08-26 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
8.1 | Up-gradation of Existing Max-DNA System (HMI) at Paras TPS (U# 3 & 4). | Scheme | MERC/CAPEX/2019-2020/644 | 2019-01-19 | 2019-08-26 | 7.12 | 7.12 |  |  | 2019-08-26 | 2019-01-08 | 2020-01-12 | WIP | Scheme involves measures to improve the reliability of existing DCS system it is indirect effect on improvement in performance of Power plant.If availability of the new spares is not ensured within the life span, then there can be possibility of auxiliary performance declination & finally breakdown,resulting huge generation loss. | 0 | 0 | 0 | 0 | 0 | 0 | 8.4417 | 0.39472 | [5 empty] | - | 20% | 40% | 60% | 80% | 80% | 100% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.8364 | [5 empty] | 0 | PO-SAP PO No. 4385000588- placed on M/s. BHEL BANGLORE. Material Received on 31-03-2023. U-3 DCS Work is completed in COH of U-3 in FY 2024-25 (July-2024) & U-4 DCS work is completed in Short shudown in June2024-25. | Capitalised
8.2 | Up-gradation of GE IP (GE-Fanuc) make PLC system (HMI) installed at WTP at Paras TPS (Combined for U# 3 & 4). | Scheme | MERC/CAPEX/2019-2020/644 | 2019-01-19 | 2019-08-26 | 0.38 | 0.38 |  |  | 2019-08-26 | 2019-01-08 | 2020-01-12 | 2021-12-02 | HMI Up-gradation empowers the plant operator and engineers to make informed decisions and thereby improved and reliable operation of the plant | 0 | 0 | 0.36789 | 0 | 0.36789 | 0 | 0 | 0 | [5 empty] | - | 20% | 100% | [9 empty] | 0 | 0 | 0.36789 | 0 | 0.36789 | 0 | 0 | 0 | [5 empty] | 0 | Scheme completed. | Capitalised
8.3 | Up-gradation of GE IP (GE-Fanuc) make PLC system (HMI) installed at AHP Unit - 4 at Paras TPS. | Scheme | MERC/CAPEX/2019-2020/644 | 2019-01-19 | 2019-08-26 | 0.48 | 0.48 |  |  | 2019-08-26 | 2019-01-08 | 2020-01-12 | 2021-02-03 | This new system will be more stable than existing one for bug removal. The possibilities of catastrophic failures are minimum. Microsoft will support for operating system for maximum life cycle. | 0 | 0 | 0.45873 | 0 | 0.45873 | 0 | 0 | 0 | [5 empty] | - | 20% | 100% | [9 empty] | 0 |  | 0.45873 | 0 | 0.45873 | 0 | 0 | 0 | [5 empty] | 0 | Scheme completed | Capitalised
8.4 | Up-gradation of Existing Schneider make PLC (HMI + PLC hardware) installed at AHP Unit - 3 at Paras TPS. | Scheme | MERC/CAPEX/2019-2020/644 | 2019-01-19 | 2019-08-26 | 0.9 | 0.9 |  |  | 2019-08-26 | 2019-01-08 | 2020-01-12 | WIP | HMI Up-gradation empowers the plant operator and engineers to make informed decisions and thereby improved and reliable operation of the plant | 0 | 0 | 0 | 0.7788 | 0.7788 | 0 | 0 | 0.10384 | [5 empty] | - | 20% | 40% | 60% | 80% | 80% | 100% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.88264 | [5 empty] | 0 | PO placed vide No. 4385000263- placed on M/s Schneider Electric System India. Material Received on 30-03-2022. Work is completed in COH of U-3 in FY 2024-25. (July-2024) | WIP
8.5 | Procurement & installation of Girth Gear & Pinion for coal mill BBD-4772. | Scheme | MERC/CAPEX/2019-2020/644 | 2019-01-19 | 2019-08-26 | 2.26 | 2.26 |  |  | 2019-08-26 | 2019-01-08 | 2020-01-12 | 2021-03-31 | This scheme ensure the availability of high cost coal mill spares. Readily availability of Girth Gear will reduce auxiliary down time which in turn reduce possible oil consumption. The availability of Girth gear also ensures minimum auxiliary down time | 0 | 0 | 1.9266 | 0.1905 | 2.1171 | 0 | 0 | 0 | [5 empty] | - | 20% | 50% | 100% | - | - | - | [5 empty] | 0 | 0 | 0 | 2.1171 | 2.1171 | 0 | 0 | 0 | [5 empty] | 0 | Scheme completed. | Capitalised
| IDC | IDC | MERC/CAPEX/2019-2020/644 | 2019-01-19 | 2019-08-26 | 0.36 | 0 |  |  | 2019-08-26 | [8 empty] | 0 |  | 0.45004 | [22 empty] | 0 |  |  | 0.45004 | [7 empty] | N.A.
9 | Complete Track Renewal at Paras TPS | DPR | MERC/CAPEX/2019-2020/479 | 2019-02-08 | 2019-08-02 | 12.77 | 12.77 |  |  | 2019-08-02 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
9.1 | Complete Track Renewal at Paras TPS | Scheme | MERC/CAPEX/2019-2020/479 | 2019-02-08 | 2019-08-02 | 12.05 | 12.05 |  |  | 2019-08-02 | 2019-01-08 | 2020-01-12 | WIP | cheme involves replacement of old chp complete track, reliability of track will be improve. technical benefits which are expected to improve after implementing scheme cannot be quantified.It will only ensure safe and uninturrupted coal stack movement in old CHP. | 0 | 0 | 0 | 0 | 0 | 0 | 7.5378 | 8.858 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 30% | 100% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.3958 | [6 empty] | PO No. HO / 4370003189 /CE(C )/Gen III/ 2148 Dt. 22-09-2023.Work completion period is 12 Month. {Work order placed vide CE(C)-III/Paras/CTR /1254/No-5262 dated 07-06-2023}. Supply 100% completed. Total 65% work completed. Reason for Cost overun- Cancellation & refloating of E-tender:  Due to Covid-19, Economic Measures Circular Dt. 22.06.2020 was issued and only necessary CAPEX schemes were to be taken up. Hence, there was a delay in opening of Price-Bid. After opening of Price-bid, on consultation with RITES, the Consultant mentioned rate justification for 14.19% above. Subsequently, M/s SC Gupta offered rebate of 2.5 % below i.e 17.23% above the estimated rate in February 2021. However, due to Director (F) Circular, no new W.O were to be issued pertaining to Civil. Therefore there was a delay. Paras TPS on 11.01.2022 gave justification for necessity and urgency for taking up the work and cited that Railway Authorities have certified that track needs to renovated as early as possible to avoid derailment, etc. In meeting with agency on 25.02.2022, the agency refused to work with rebated rate citing various reasons such as price-escalation due to Covid-19, inflation, shortage of man-power.  Competent Authority vide office-note no. CE(C)-III/Paras/CTR/546 Dt.08.03.2022 accorded approval for i) refloating the tender with revised estimate as per current rate ii) approval for Consultant for revised remuneration as per revised estimated amount.  Consultant furnished revised estimate as per current rate as follows: a) Rs. 13.37 Crs. (excl. GST) – (Supply of Material-5.04 Crs, Execution of Civil & P-way works- 5.10 Crs, Supply of Rails 60 kg – Rs. 3.21 Crs) b) RITES fees @ 7.5 % of total cost – 1.00 Crs. c) Total Cost excluding GST- Rs. 14.55 Crs. | WIP
| IDC | IDC | MERC/CAPEX/2019-2020/479 | 2019-02-08 | 2019-08-02 | 0.72 | 0.72 |  |  | 2019-08-02 | [8 empty] | 0 |  | 0.078332 | [22 empty] | 0 |  |  | 0.078332 | [7 empty] | N.A.
10 | Procurement & Replacement of water wall panels in Unit#4 & Installation of VFD to existing eddy current drive driven coal feeders at 2x250 MW at Paras TPS | DPR | MERC/CAPEX/2019-2020/664 | 2019-05-20 | 2019-08-28 | 12.72 | 12.72 |  |  | 2019-08-28 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
10.1 | Replacement of water wall panel in Unit-4 Boiler at 2 X 250 MW, PTPS | Scheme | MERC/CAPEX/2019-2020/664 | 2019-05-20 | 2019-08-28 | 6.49 | 6.49 |  |  | 2019-08-28 | 2019-01-08 | 2020-01-08 | WIP | • Improvement in heat transfer in water wall zone. • Increased availability & reliability of the unit. • Improved Fireball Position in furnace due to proper alignment & fitting in the all 4 corners. • Saving in Fuel oil consumption due to reduced BTL • Reduction in outages.. | 0 | 0 | 0 | 2.7423 | 2.7423 | 0 | 0 | [10 empty] | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6.2823 | [5 empty] | * Supply PO-SAP PO No. 4370002364- placed on M/s. Bajaj Power Equipments Pvt. Ltd. Material Received on 30-03-2021. Work will be completed in AOH/COH of U-4 in FY 2025-26. | WIP
10.2 | Installation of VFD with controller over existing eddy current drives with controller at 2 X 250 MW, PTPS. | Scheme | MERC/CAPEX/2019-2020/664 | 2019-05-20 | 2019-08-28 | 6.23 | 6.23 |  |  | 2019-08-28 | 2019-01-08 | 2020-01-08 | WIP | • Improvement in availability. • Smooth control over the variable load. | 0 | 0 | 0 | 0 | 0 | 6.1732 | 0 | 0.29396 | [9 empty] | 80% | 90% | 100% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.4672 | [6 empty] | PO NO.4385000529 placed on M/s. Encon System. Material received on 15-11-2022. Installation completed on 30-04-2024. | Capitalised
| IDC | IDC | MERC/CAPEX/2019-2020/664 | 2019-05-20 | 2019-08-28 | 0 | 0 |  |  | 2019-08-28 | [8 empty] | 0 |  | 1.0135 | [22 empty] | 0 |  |  | 1.0135 | [7 empty] | N.A.
11 | Reinforcement & Capacity Enhancement of Old CHP Coal Conveyor Belt Structure from (200 TPH to 360 TPH) at old CHP Paras TPS & Procurement of One No. of Bulldozer & Diesel Hydraulic Locomotive at Paras TPS | DPR | MERC/CAPEX/2021-22/SBR/20 | 2019-12-31 | 2021-11-09 | 12.41 | 12.41 |  |  | 2021-11-09 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
11.1 | Capacity Enhancement of Old CHP Conveyor belt from 200 TPH to 360 TPH at Old CHP, Paras TPS. | Scheme | MERC/CAPEX/2021-22/SBR/20 | 2019-12-31 | 2021-11-09 | 2.94 | 2.94 |  |  | 2021-11-09 | 2021-01-12 | - | WIP | Improvement in Loadability of Old CHP Coal Conveyor System which results into reduction in running hours which in turn reduce the auxiliary consumption in account of Coal Handling Plant. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 |  |  | 0 | 0 | 0 | 0 |  | 2.9382 | [5 empty] | HO Approval is received to PR No 1100128266. Tender Stage. Revised QR is sent to HO for approval on dated 04-05-2023. Query reply sent on 20-07-2023. Query-2 received on 05-12-2023. Reply sent on 01-01-2023. Mail sent to HO for approval on dtd.12.02.2024 | WIP
11.2 | Reinforcement of Belt Conveyor structure at Old CHP, Paras TPS. | Scheme | MERC/CAPEX/2021-22/SBR/20 | 2019-12-31 | 2021-11-09 | 2.66 | 2.66 |  |  | 2021-11-09 | 2021-01-12 | - | WIP | reduce the auxiliary consumption in account of Coal Handling Plant & Reduction of unloading time which in turn reduces the Demurrage hours & Demurrage charges which claims by Railway. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9137 | [9 empty] | 0% | 0% | 100% | [5 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 2.9137 | [6 empty] | HO Approval is received to PR No 1100127806. Draft PO 4385000692 is sent to HO for approval on 13-10-2023. Query reply given on 23-11-2023. PO approval received from HO vide ltr No-00615 dtd 16-01-2024. PO dispatched vide PRSTPS/4385000692/No.1074 dated 16-02-2024. Work is in progress. | WIP
11.3 | Procurement of Bulldozer at CHP, Paras TPS. | Scheme | MERC/CAPEX/2021-22/SBR/20 | 2019-12-31 | 2021-11-09 | 2.31 | 2.31 |  |  | 2021-11-09 | 2021-01-12 | 2021-22 | 2021-22 | Maximum dozer required in monsoon for reclaim any coal and stacking of wet coal on ground. In case of non-availability of bulldozers, coal bunkering affects generation loss consequently demurrage charges increase. | 0 | 0 | 0 | 2.4909 | 2.4909 | 0 | 0 | 0 | [8 empty] | 100% | [8 empty] | 0 |  |  | 2.4909 | 2.4909 | 0 | 0 | 0 | [6 empty] | Scheme completed. | Capitalised
11.4 | Procurement of Diesel Hydraulic Locomotive at CHP, Paras TPS. | Scheme | MERC/CAPEX/2021-22/SBR/20 | 2019-12-31 | 2021-11-09 | 3.6 | 3.6 |  |  | 2021-11-09 | 2021-01-12 | - | WIP | Reduction in outage hours in account of Locomotives will get reduced, hence improvement in availability & reliability of Locomotives. Coal wagon movement can be possible more rapidly & efficiently. | 0 | 0 | 0 | 0 | 0 | 3.057 | 0.16377 | 0 | [9 empty] | 100% | [7 empty] | 0 |  |  | 0 | 0 | 3.057 | 0.16377 | 0 | [6 empty] | PO placed vide No. 4370002825, Material/LOCO received on 31-03-2024. Scheme completed & Capitalized in FY 2022-23. As per CPA, HO letter No.CE(CPA)/Gr-IV-A/SAN LOCO/Amendment-1/No.9213 dated 30-08-2023, PO is amended for GST 12% to 18%. GST difference is paid & Capitalized in FY 2023-24. | Capitalised
| IDC | IDC | MERC/CAPEX/2021-22/SBR/20 | 2019-12-31 | 2021-11-09 | 0.9 | 0.9 |  |  | 2021-11-09 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
12 | Flue Gas Desulpherization (FGD) System for Paras Unit No. 3 & 4 | DPR | MERC/CAPEX/2020-2021/WFH/SBR/42 | 2020-05-28 | 2020-12-14 | 391.06 | 376.06 |  |  | 2020-12-14 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
12.1 | Flue Gas Desulpherization (FGD) System for Paras Unit No. 3 & 4 | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/42 | 2020-05-28 | 2020-12-14 | 346.06 | 347.02 |  |  | 2020-12-14 | 2022-05-19 |  | 2024-10-19 |  | 0 | 0 | 0 | 0 | 0 | 20.35 | 94.8887 | 244 | 119.3423 |  |  |  |  | 0% | 0% | 0% | 0% | 20% | 70% | 80% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211.99 | 211.3 | 52.3 |  |  |  |  | Design Engineering & site clearnce in progress. PO 4300001736/1735 ,4300001718,4300001720. Pertains to CE-P&P and CE-Project Bhusawal 660MW. As per CE(Bhusawal Project) Letter No. CE(P)/BSL/Proj./AHP/Paras-FGD/09/No.01750 dated 02-08-2024, scheme will be completed & Capitalized in FY 2025-26. | WIP
| IDC | IDC | MERC/CAPEX/2020-2021/WFH/SBR/42 | 2020-05-28 | 2020-12-14 | 45 | 29.04 |  |  | 2020-12-14 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
13 | Procurement & Installation of complete assembly of Elecon make Gear Boxes, Wagon Tippler Assembly; Design, Supply, Installation, Commissioning & Successful Trial of Link Conveyor from Stackyard to C-2 Conveyor Belt at CHP; Procurement of Bucket Wheel of Stacker Reclaimer for CHP at Paras TPS | DPR | MERC/CAPEX/MSPGCL/2024-25/0325 | 2023-10-31 | 2024-05-30 | 54.98 | 54.98 | [11 empty] | 0 | [24 empty] | 0
13.1 | Procurement & Installation of complete assembly of Elecon make Gear Boxes, Wagon Tippler Assembly; Design, Supply, Installation, Commissioning & Successful Trial of Link Conveyor from Stackyard to C-2 Conveyor Belt at CHP; Procurement of Bucket Wheel of Stacker Reclaimer for CHP at Paras TPS | Scheme | MERC/CAPEX/MSPGCL/2024-25/0325 | 2023-10-31 | 2024-05-30 | 32.78 | 32.78 | [11 empty] | 0 |  |  |  | 11.88 | [11 empty] | 100% | [8 empty] | 0 |  |  |  | 11.88 | [5 empty] | Mail sent to HO for PO approval 01.08.2024 | WIP
13.2 | Procurement of Wagon Tippler Assembly & Installation of the same at CHP at Paras TPS | Scheme | MERC/CAPEX/MSPGCL/2024-25/0325 | 2023-10-31 | 2024-05-30 | 13.9 | 13.9 | [6 empty] | Saving in cost of Generation Loss |  |  |  |  | 0 |  |  |  | 13.9 | [11 empty] | 100% | [8 empty] | 0 |  |  |  | 13.9 | [5 empty] | PO Dispatched 4385000772/No.5244 dated 17-08-2024. | WIP
13.3 | Design, supply, installation, commissioning & successful trial of Link Conveyor from Stackyard to C-2 conveyor belt at CHP, Paras TPS | Scheme | MERC/CAPEX/MSPGCL/2024-25/0325 | 2023-10-31 | 2024-05-30 | 5.93 | 5.93 | [6 empty] | Saving in cost of Generation Loss |  |  |  |  | 0 |  |  |  | 5.93 | [11 empty] | 100% | [8 empty] | 0 |  |  |  | 5.93 | [5 empty] | for PB open 26.08.2024, for PO creation 27.08.2024. PO 4385000783 created & submitted to HO for approval. | WIP
13.4 | Procurement of bucket wheel of stacker reclaimer for CHP 250MW Paras TPS | Scheme | MERC/CAPEX/MSPGCL/2024-25/0325 | 2023-10-31 | 2024-05-30 | 1.07 | 1.07 | [6 empty] | Saving in cost of Generation Loss |  |  |  |  | 0 |  |  |  | 1.07 | [11 empty] | 100% | [8 empty] | 0 |  |  |  | 1.07 | [5 empty] | PO Dispatched 4385000772/No.5243 dated 17-08-2024. | WIP
| IDC | IDC | MERC/CAPEX/MSPGCL/2024-25/0325 | 2023-10-31 | 2024-05-30 | 1.3 | 1.3 | [11 empty] | 0 | [24 empty] | 0
HO DPR 5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | DPR | MERC/TECH 1/CAPEX/20142015/01218 | 2014-10-01 | 2014-11-25 | 3.6 | 3.6 |  |  | 2014-11-25 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
HO DPR 5.6 | Paras: Procurement of HT Motors(CEP/ACW Motors-I Phase and CW/CHP Motors-II Phase)for U-3&4 | Scheme | MERC/TECH 1/CAPEX/20142015/01218 | 2014-10-01 | 2014-11-25 | 3.6 | 3.6 |  |  | 2014-11-25 | 2017-01-05 | 2017-03-30 | 2022-23 | Improvement in Spare motor availability | 0 | 0 | 0.88198 | 1.2139 | 2.0958 | [9 empty] | 30% | 70% | 90% | 100% | [7 empty] | 0 | 0 | 0.49553 | 0.86636 | 1.3619 | 0.73396 | 0 | 0 | [5 empty] | 0 | HO PO-4370001604,4370001605,4370001606. | Capitalised
| IDC | IDC | [16 empty] | 0 | 1.235 | [23 empty] | 0 | 1.235
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | DPR | MERC/CAPEX/20162017/00423 | 2016-02-03 | 2016-08-03 | 3.9773 | 3.9773 |  |  | 2016-08-03 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
HO DPR 6.1 | PARAS(U-3 & 4) | Scheme | MERC/CAPEX/20162017/00423 | 2016-02-03 | 2016-08-03 | 3.9773 | 3.9773 |  |  | 2016-08-03 | 2017-01-01 | 2016-09-30 | 2019-01-09 | • The CAAQMS scheme is statutory requirement for MPCB & environment Compliance. Therefore, through the cost benefit analysis of such scheme can’t be calculate, for complying MPCB norms implementation of these schemes is very essential | 3.7536 | 0 | 0 | 0 | 3.7536 | 0 | 0.092 | 0 | [5 empty] | 50% | 100% | [10 empty] | 0 | 3.7536 | 0 | 0 | 3.7536 | 0 | 0.092 | 0 | [5 empty] | 0 | HO PO-4370001152 dtd.30.05.2018. Work Completed on 04-09-2019.WCR submitted on 26-09-2019. Capitalization done of Rs.3.75 Cr. Scheme completed/Work bill is delay submitted by vendor. | Capitalised
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | DPR | MERC/CAPEX/20162017/00774 | 2016-08-26 | 2016-09-30 | 2.0276 | 2.0276 |  |  | 2016-09-30 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
HO DPR 7.1 | Paras TPS | Scheme | MERC/CAPEX/20162017/00774 | 2016-08-26 | 2016-09-30 | 2.0276 | 2.0276 |  |  | 2016-09-30 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 |  |  |  | 2.31 | [6 empty] | Not Initiated
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | DPR | MERC/CAPEX/20172018/4653 | 2017-04-19 | 2017-11-13 | 1.45 | 1.45 |  |  | 2017-11-13 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
HO DPR 8.1 | Advance Multipurpose Fire Tender at Paras TPS | Scheme | MERC/CAPEX/20172018/4653 | 2017-04-19 | 2017-11-13 | 1.45 | 1.45 |  |  | 2017-11-13 | 2018-01-01 | 2018-19 | 2021-22 | Advance MFT is one of the statutory requirement for life and property saving of the organization.cost benefit analysis of such scheme cant be directly calculated. | 0 | 0 | 0 | 1.7765 | 1.7765 | 1.1426 | 0 | 0 | [8 empty] | 100% | [8 empty] | 0 | 0 | 0 | 1.7765 | 1.7765 | 1.1426 | 0 | 0 | [5 empty] | 0 | 1.PO No-4370001800, Capitalized in FY 2021-22 Scheme completed / DUE TO CHANGES IN TAXATION S-TAX TO GST 2. Amounting of Rs 11,426,251.00/- has been capitalized by HO in our business area in fy 22-23. | Capitalised
HO DPR 8.2 | Normal Multipurpose Fire Tender at Paras TPS | Scheme | MERC/CAPEX/20172018/4653 | 2017-04-19 | 2017-11-13 | 0 | 0 |  |  | 2017-11-13 | [8 empty] | 0 | [24 empty] | 0 | [9 empty] | QTY IS NIL FOR PARAS TPS. | N.A.
| IDC | IDC | MERC/CAPEX/20172018/4653 | 2017-04-19 | 2017-11-13 |  |  |  |  | 2017-11-13 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | DPR | MERC/CAPEX/20172018/0177 | 2018-01-12 | 2018-02-06 | 2.0768 | 2.0768 |  |  | 2018-02-06 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
HO DPR 10.1 | TPS Paras | Scheme | MERC/CAPEX/20172018/0177 | 2018-01-12 | 2018-02-06 | 2.0768 | 2.0768 |  |  | 2018-02-06 | 2018-01-08 | 2019-20 | 2022-03-31 | The safety is statutary requirement for IB norms.Therefore though the cost benefit analysis of such scheme can't be calculated, for complying IB norm , implentation of these scheme is very essential. | 0.44241 | 0.45047 | 0.25492 | 0.46637 | 1.6142 | 0 | 0 | 0 | [5 empty] | 10% | 30% | 70% | 100% | [8 empty] | 0 | 0 | 0 | 1.6142 | 1.6142 | [9 empty] | Scheme completed. 4370001578 | Capitalised
HO DPR 11 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | DPR | MERC/CAPEX/2021-2022/MSPGCL/063 | 2018-08-31 | 2022-02-12 | 113.91 | 57 | [11 empty] | 0 | [24 empty] | 0 | [10 empty] | WIP
HO DPR 11.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | Scheme | MERC/CAPEX/2021-2022/MSPGCL/063 | 2018-08-31 | 2022-02-12 | 108.48 | 54.24 | [11 empty] | 0 | [24 empty] | 0 | [10 empty] | WIP
| IDC | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2018-08-31 | 2022-02-12 | 5.43 | 2.76 | [11 empty] | 0 | [24 empty] | 0 | [10 empty] | WIP
HO DPR 12 | Centralized Monitoring Solution | DPR | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-03-28 | 2023-11-02 | 69.309 | 69.309 | [11 empty] | 0 | [24 empty] | 0 | [10 empty] | WIP
HO DPR 12.1 | Centralized Monitoring Solution | Scheme | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-03-28 | 2023-11-02 | 66.009 | 66.009 | [11 empty] | 0 | [24 empty] | 0 | [10 empty] | WIP
| IDC | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-03-28 | 2023-11-02 | 3.3 | 3.3 | [11 empty] | 0 | [24 empty] | 0
[19 empty] | 0 | [24 empty] | 0
| (ii) Yet to be submitted to MERC | [17 empty] | 0 | [24 empty] | 0
[19 empty] | 0 | [24 empty] | 0
1 | Enhancing process reliability at U-3 & U-4 at 2X250MW Paras TPS | DPR |  |  |  | 77.96 | [12 empty] | 0 | [24 empty] | 0
1.1 | Procurement & replacement of complete set of Economiser (upper & lower) coil assemblies & LTSH (upper & lower) coil assemblies in Unit-4 (250mw) at Paras TPS. | Scheme |  |  |  | 14.18 | [7 empty] | • Station Heat Rate Improvement: The total expected heat rate improvement to be achieved due to the implementation of above scheme is 12.0 Kcal/kwh |  |  |  |  | 0 |  |  |  | 14.18 | [11 empty] | 100% | [8 empty] | 0 |  |  |  | 14.18
1.2 | Procurement & installation of complete discharge assembly of coal mill BBD 4772 In Unit-3&4 at Paras TPS | Scheme |  |  |  | 22.51 | [7 empty] | * Huge Generation loss on account of non-availability of coal mill will be reduced. * This scheme results in improvement in availability of coal mill, quantity, availability and load ability |  |  |  |  | 0 |  |  |  | 22.51 | [11 empty] | 100% | [8 empty] | 0 |  |  |  | 22.51
1.3 | Supply, replacement, erection and installation of foundation deck spring of coal mill BBD 4772 for Unit-3&4 at 250 MW at Paras TPS | Scheme |  |  |  | 3.36 | [7 empty] | *This scheme results in increase availability of coal mill * Partial/half load will occur if one coal mill will be out (out of two running mills) i.e., loss of 125 MW. |  |  |  |  | 0 |  |  |  | 3.36 | [11 empty] | 100% | [8 empty] | 0 |  |  |  | 3.36
1.4 | Procurement & Replacement of Coal Compartment Assemblies at 250 MW for Unit-3&4, Paras TPS | Scheme |  |  |  | 1.77 | [7 empty] | * Expected heat rate of improvement as 5.0 Kcal/Kwh |  |  |  |  | 0 |  |  |  | 1.77 | [11 empty] | 100% | [8 empty] | 0 |  |  |  | 1.77
1.5 | Procurement & Replacement of Girth gear and pinion Assemblies at 250 MW Unit-3,4, Paras TPS | Scheme |  |  |  | 9.22 | [7 empty] | * Huge Generation loss on account of non-availability of coal mill will be reduced |  |  |  |  | 0 |  |  |  | 9.22 | [11 empty] | 100% | [8 empty] | 0 |  |  |  | 9.22
1.6 | Procurement & Replacement of Coal Mill drive shaft Assemblies at 250 MW Unit-3&4 Paras TPS. | Scheme |  |  |  | 7.67 | [7 empty] | • Reduction in generation loss on account of coal mill • Increase in Coal mill loadability • Reduction in Auxiliary down time. • Availability & Reliability of coal mill get Increased. • Reduction in oil consumption |  |  |  |  | 0 |  |  |  | 7.67 | [11 empty] | 100% | [8 empty] | 0 |  |  |  | 7.67
1.7 | Procurement & Replacement of Air Pre Heater speed reducer gear box set of internals (assembly) for Unit-3&4. | Scheme |  |  |  | 1.33 | [7 empty] | • Improvement in performance of Air Pre-heater. • Improvement in reliability of Air Pre-heater. • Air Pre-heater availability will be increased. • Reduction in Air Pre-heater down time. • Reduction in generation loss and oil consumption on account of abrupt failure APH gearbox. |  |  |  |  | 0 |  |  |  | 1.33 | [11 empty] | 100% | [8 empty] | 0 |  |  |  | 1.33
1.8 | Procurement & Replacement of foundation deck spring assembly (vibration isolation system) for ID fan for Unit 3&4 at Paras TPS. | Scheme |  |  |  | 2.31 | [7 empty] | • Reduction in generation loss on account of ID fan. • Reduction in Auxiliary down time. • Availability & Reliability of ID fan get Increased. • Reduction in oil consumption |  |  |  |  | 0 |  |  |  | 2.31 | [11 empty] | 100% | [8 empty] | 0 |  |  |  | 2.31
1.9 | Procurement of CW Pump module with mandatory spares for TM section | Scheme |  |  |  | 15.61 | [7 empty] | 1.Availability of spare CW pump may avoid generation loss during any emergency. 2.Replacement of new pump with old one will reduce auxiliary power consumption (~20 Amps.) 3.Availability of CW pump may reduce the down time in case of any unforeseen emergency. |  |  |  |  | 0 |  |  |  | 15.61 | [11 empty] | 100% | [8 empty] | 0 |  |  |  | 15.61
2 | DPR for Ash Evacuation System Rehabilitation and improvement of performance & efficiency of Ash Handling System | DPR |  |  |  | 34.71 | [12 empty] | 0 | [24 empty] | 0
2.1 | Replacement of old 300NB ash slurry disposal pipeline with new 300NB MSERW pipeline from slurry pump house to surface drain pump house at Paras TPS. | Scheme |  |  |  | 6.66 | [7 empty] | * Availability of slurry disposal system increases. * Flowing of slurry in farms avoided. |  |  |  |  | 0 |  |  |  |  | 6.66 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 6.66
2.2 | Replacement of old 200nb bottom ash, coarse ash, fly ash conveying pipeline with new 200 NB MSERW pipeline from ash hoppers to slurry tank & SILO AT PTPS. | Scheme |  |  |  | 4.7 | [7 empty] | * Availability of wet ash evacuation system increases. * Maintenance of downtime decrease. |  |  |  |  | 0 |  |  |  |  | 4.7 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 4.7
2.3 | Procurement of complete assembly of air compressors (T-BTD-JM (4NOS) AND T-BD-QL (6NOS.)) in ash evacuation system in AHP, Paras TPS. | Scheme |  |  |  | 3.99 | [7 empty] | * Efficiency of fly ash sytem increases. * Operating pressure increases which reduces fly ash evacuation timing. |  |  |  |  | 0 |  |  |  |  | 3.99 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 3.99
2.4 | Procurement of complete assembly of SAM make ar-150/510 Pumps (9 nos) for replacement of ash slurry pumps of bottom ash slurry disposal from slurry tank to ash bund in slurry pump house. | Scheme |  |  |  | 2.15 | [7 empty] | * Availability of slurry disposal system increases & wet ash evacuation increses. *Reduces wet ash evacuation timing hence reduce auxiliary power consumption, water consumption. * Generation loss avoided due to non-availability of wet ash system. |  |  |  |  | 0 |  |  |  |  | 2.15 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 2.15
2.5 | Procurement of complete assembly of SAM MAKE ZM-II 530/03 (4 NOS) for replacement of HP pumps of bottom ash & coarse ash evacuation from BA/CA hoppers to slurry tank in ash water pump house. | Scheme |  |  |  | 0.89 | [7 empty] | * Availability of slurry disposal system increases & wet ash evacuation increses. *Reduces wet ash evacuation timing hence reduce auxiliary power consumption, water consumption. * Generation loss avoided due to non-availability of wet ash system. |  |  |  |  | 0 |  |  |  |  | 0.89 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 0.89
2.6 | Procurement of major internal assemblies of weir make GEHO pumps installed at AHP, Paras TPS. | Scheme |  |  |  | 13.4 | [7 empty] | * Availability of silo HCSD system increases. *Avoid generation loss due to non-availability of fly ash evacuation system i.e HCSD system. * Increases efficiency of HCSD sytem |  |  |  |  | 0 |  |  |  |  | 13.4 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 13.4
2.7 | Procurement of critical transmission drive systems and fluid couplings internal assemblies for slurry pumps and silo HCSD system installed at AHP, Paras TPS. | Scheme |  |  |  | 2.92 | [7 empty] | * Availability of silo HCSD system increases. *Avoid generation loss due to non-availability of fly ash evacuation system i.e HCSD system. * Increases efficiency of HCSD sytem |  |  |  |  | 0 |  |  |  |  | 2.92 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 2.92
3 | Augmentaion/Modification of U-3 & U-4 ESP | DPR |  |  |  | 50 | [12 empty] | 0 | [24 empty] | 0
3.1 | Restoration of ESP Fields of Unit- 3 & 4 Paras TPS | Scheme |  |  |  | 50 | [7 empty] | * Stack emission reduction. * Meet MPCB norms. |  |  |  |  | 0 | [5 empty] | 50 | [11 empty] | 100% | [6 empty] | 0 | [5 empty] | 50
4 | Performance & Capacity enhancement of Ash handling plant | DPR |  |  |  | 26 | [12 empty] | 0 | [24 empty] | 0
4.1 | Procurement & Replacement of existing ash slurry disposal pump assembly by higher efficient pump assembly in AHP of Paras TPS | Scheme |  |  |  | 12 | [7 empty] | * Availability of slurry disposal system increases & wet ash evacuation increses. *Reduces wet ash evacuation timing hence reduce auxiliary power consumption, water consumption. * Generation loss avoided due to non-availability of wet ash system. |  |  |  |  | 0 |  |  |  |  | 12 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 12
4.2 | Procurement of higher capacity vacuum pumps along with motors to improve availability & performance of fly ash system of AHP Paras TPS | Scheme |  |  |  | 3 | [7 empty] | * Efficiency of fly ash sytem increases. * Increases availability & performance of fly ash evacuation timing. |  |  |  |  | 0 |  |  |  |  | 3 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 3
4.3 | Modification & Replacement of air drier at AHP Paras TPS | Scheme |  |  |  | 2 | [7 empty] | * Efficiency of fly ash sytem increases. |  |  |  |  | 0 |  |  |  |  | 2 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 2
4.4 | Procurement & Replacement of existing HT Motors by energy efficient HT Motors In AHP of Paras TPS | Scheme |  |  |  | 4 | [7 empty] | * Reduce auxiliary power consumption. |  |  |  |  | 0 |  |  |  |  | 4 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 4
4.5 | Procurement & Replacement of ash handling plant auxiliaries & systems of Paras TPS | Scheme |  |  |  | 5 | [7 empty] | * Availability of system increases. *Avoid generation loss due to non-availability of fly ash evacuation system * Increases efficiency sytem. |  |  |  |  | 0 |  |  |  |  | 5 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 5
5 | Procurement & Replacement of DRC Pipeline of fly ash evacuation system of AHP Paras for Availability improvement | DPR |  |  |  | 40 | [12 empty] | 0 | [24 empty] | 0
5.1 | Procurement & Replacement of DRC Pipeline of fly ash evacuation system of AHP Paras TPS | Scheme |  |  |  | 40 | [7 empty] | * Availability of wet ash evacuation system increases. * Maintenance of downtime decrease. |  |  |  |  | 0 | [5 empty] | 40 | [11 empty] | 100% | [6 empty] | 0 | [5 empty] | 40
6 | Structure strengthening of AHP | DPR |  |  |  | 25 | [12 empty] | 0 | [24 empty] | 0
6.1 | Work of anticorrosive Painting & Structure strengthening of Ash Handling Plant structures | Scheme |  |  |  | 25 | [7 empty] | * Life of AHP structure increses. * Accident or Generation loss due to collapse of structure |  |  |  |  | 0 |  |  |  |  | 25 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 25
7 | U-3 Boiler Effyciency & Performance improvement schemes | DPR |  |  |  | 31.66 | [12 empty] | 0 | [24 empty] | 0
7.1 | CAVT & CFD for unit-3 | Scheme |  |  |  | 1.2 | [7 empty] | 1) To avoid the BTL due to flue gas erosion. 2) Non uniform flow and higher velocity of flue gas also affects the performance of ESP and affecting stack emission. 3) Duct erosion due to uneven flue gas velocities will increase in ID Fan loading due to air ingress from flue gas duct leakages. |  |  |  |  | 0 |  |  |  |  | 1.2 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 1.2
7.2 | Procurement of sky climber assembly for Paras TPS | Scheme |  |  |  | 2 | [7 empty] | Delay in BTL attending work, which leads to heavy generation loss |  |  |  |  | 0 |  |  |  |  | 2 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 2
7.3 | Procurement & replacement of PA fan NDV22 BAB2 rotor assembly with impeller and cone & blade assembly of IGV with rod end assly for IGV control for unit-3. | Scheme |  |  |  | 1.51 | [7 empty] | Non avaibality of PA fan NDV22 BAB2 rotor assembly with impeller and cone & blade assembly of IGV with rod end assly may lead to heavy generation loss. |  |  |  |  | 0 |  |  |  |  | 1.51 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 1.51
7.4 | Procurement & replacement Dampers, shutoff gate assemblies for series 5,6,7 & 8 dampers, ID fan inlet gate, APH flue gas dampers I/L & O/L, APH PA I/L & O/L dampers, APH SA I/L & O/L dampers along with actuators, SADC dampers at wind box with actuators for unit-3 | Scheme |  |  |  | 2.5 | [7 empty] | To avoid hot air loss due to air leakages. |  |  |  |  | 0 |  |  |  |  | 2.5 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 2.5
7.5 | Procurement & replacement of critical high pressure valves, safety valves & control valves for unit-3. | Scheme |  |  |  | 2 | [7 empty] | To avoid generation loss & smooth running of boiler |  |  |  |  | 0 |  |  |  |  | 2 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 2
7.6 | Supply and Replacement of Thermal Insulation of Boiler, Ducts & Steam Pipelines for unit-3 | Scheme |  |  |  | 1.5 | [7 empty] | To avoid heat dissipation in the atmosphere & to improve boiler efficiency. |  |  |  |  | 0 |  |  |  |  | 1.5 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 1.5
7.7 | Procurement and replacement of HP and B&S Lub oil pumps of coal mills BBD-4772 installed at Paras TPS | Scheme |  |  |  | 0 | [7 empty] | * Availability of Coal mill increses. |  |  |  |  | 0 |  |  |  |  | 1.8 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 1.8
7.8 | Procurement & replacement of complete Coal compartment assly for unit-3. | Scheme |  |  |  | 1.3 | [7 empty] | 1) Better combustion due to healthy burner arrangement. 2) Net effect on unit heat rate will be improved. 3) Availability and Reliability of unit will be increased. 4) Reduction in BTL due to coal particle erosion 5) Improvement in boiler efficiency |  |  |  |  | 0 | [6 empty] | 1.3 | [11 empty] | 100% | [5 empty] | 0 | [6 empty] | 1.3
7.9 | Procurement & replacement of complete APH baskets, HE & CE sector plate, diapharm plate, rotor spool piece, grating assly, all type seals, rack pinion for unit-3. | Scheme |  |  |  | 5.5 | [7 empty] | 1) Reduction in flue gas outlet temperature. 2) Improvement in performance of APH 3) The heat rate of unit will be improved. 4) Improvement in boiler efficiency |  |  |  |  | 0 | [6 empty] | 5.5 | [11 empty] | 100% | [5 empty] | 0 | [6 empty] | 5.5
7.1 | Procurement & replacement of complete set of Final super heater coil assembly for unit-3. | Scheme |  |  |  | 12 | [7 empty] | 1) Heat rate of unit will be improved. 2) Reduction in BTL in FSH 3) Improvement in boiler efficiency. 4) Availability and Reliability of unit will be increased. 5) Reduction in the Maintenance cost on account of BTL. |  |  |  |  | 0 | [6 empty] | 12 | [11 empty] | 100% | [5 empty] | 0 | [6 empty] | 12
7.11 | Procurement & replacement of complete rotor assembly of FD fan including shaft with brg assly, impeller with oil hydraulic blade adjustment device with blades & coupling for unit-3. | Scheme |  |  |  | 2.15 | [7 empty] | 1) improvement in boiler efficiency. 2) Relaibility will be improved 3) Reduction in maintainance cost. |  |  |  |  | 0 | [6 empty] | 2.15 | [11 empty] | 100% | [5 empty] | 0 | [6 empty] | 2.15
8 | U-3 & U-4 Boiler Effyciency, Performance & reliability improvement schemes | DPR |  |  |  | 43 | [12 empty] | 0 | [24 empty] | 0
8.1 | Procurement & replacement of Coal compartment assly for unit-4. | Scheme |  |  |  | 1.1 | [7 empty] | 1) Better combustion due to healthy burner arrangement. 2) Net effect on unit heat rate will be improved. 3) Availability and Reliability of unit will be increased. 4) Reduction in BTL due to coal particle erosion 5) Improvement in boiler efficiency |  |  |  |  | 0 | [5 empty] | 1.1 | [11 empty] | 100% | [6 empty] | 0 | [5 empty] | 1.1
8.2 | Supply and Replacement of Thermal Insulation of Boiler, Ducts & Steam Pipelines for unit-4 | Scheme |  |  |  | 1.5 | [7 empty] | To avoid heat dissipation in the atmosphere & to improve boiler efficiency. |  |  |  |  | 0 | [5 empty] | 1.5 | [11 empty] | 100% | [6 empty] | 0 | [5 empty] | 1.5
8.3 | Procurement & replacement of critical high pressure valves, safety valves & control valves for unit-4. | Scheme |  |  |  | 2 | [7 empty] | To avoid generation loss & smooth running of boiler |  |  |  |  | 0 | [5 empty] | 2 | [11 empty] | 100% | [6 empty] | 0 | [5 empty] | 2
8.4 | CAVT & CFD for unit-4 | Scheme |  |  |  | 1.2 | [7 empty] | 1) To avoid the BTL due to flue gas erosion. 2) Non uniform flow and higher velocity of flue gas also affects the performance of ESP and affecting stack emission. 3) Duct erosion due to uneven flue gas velocities will increase in ID Fan loading due to air ingress from flue gas duct leakages. |  |  |  |  | 0 | [5 empty] | 1.2 | [11 empty] | 100% | [6 empty] | 0 | [5 empty] | 1.2
8.5 | Procurement & replacement Dampers, shutoff gate assemblies for series 5,6,7 & 8 dampers, ID fan inlet gate, APH flue gas dampers I/L & O/L, APH PA I/L & O/L dampers, APH SA I/L & O/L dampers along with actuators, SADC dampers at wind box with actuators for unit-4 | Scheme |  |  |  | 2.5 | [7 empty] | To avoid hot air loss due to air leakages. |  |  |  |  | 0 | [5 empty] | 2.5 | [11 empty] | 100% | [6 empty] | 0 | [5 empty] | 2.5
8.6 | Procurement & replacement of complete seal air fan assembly of coal mill BBD-4772 (without Motor) installed at Paras TPS | Scheme |  |  |  | 1 | [7 empty] | 1) Improvement in boiler efficiency. 2) Availability and Reliability of unit will be increased. |  |  |  |  | 0 | [5 empty] | 1 | [11 empty] | 100% | [6 empty] | 0 | [5 empty] | 1
8.7 | Procurement & replacement of complete set of Final super heater coil assembly for unit-4 | Scheme |  |  |  | 12.5 | [7 empty] | 1) Heat rate of unit will be improved. 2) Reduction in BTL in FSH 3) Improvement in boiler efficiency. 4) Availability and Reliability of unit will be increased. 5) Reduction in the Maintenance cost on account of BTL. |  |  |  |  | 0 | [7 empty] | 12.5 | [11 empty] | 100% |  |  |  |  | 0 | [7 empty] | 12.5
8.8 | Procurement & replacement of complete Coal compartment assly for unit-4 | Scheme |  |  |  | 1.3 | [7 empty] | 1) Better combustion due to healthy burner arrangement. 2) Net effect on unit heat rate will be improved. 3) Availability and Reliability of unit will be increased. 4) Reduction in BTL due to coal particle erosion 5) Improvement in boiler efficiency |  |  |  |  | 0 | [7 empty] | 1.3 | [11 empty] | 100% |  |  |  |  | 0 | [7 empty] | 1.3
8.9 | Procurement & replacement of complete APH baskets, HE & CE sector plate, diapharm plate, rotor spool piece, grating assly, all type seals, rack pinion for unit-4. | Scheme |  |  |  | 6 | [7 empty] | 1) Reduction in flue gas outlet temperature. 2) Improvement in performance of APH 3) The heat rate of unit will be improved. 4) Improvement in boiler efficiency |  |  |  |  | 0 | [7 empty] | 6 | [11 empty] | 100% |  |  |  |  | 0 | [7 empty] | 6
8.1 | Procurement & replacement of complete Coal compartment assly for unit-3 | Scheme |  |  |  | 1.4 | [7 empty] | 1) Better combustion due to healthy burner arrangement. 2) Net effect on unit heat rate will be improved. 3) Availability and Reliability of unit will be increased. 4) Reduction in BTL due to coal particle erosion 5) Improvement in boiler efficiency |  |  |  |  | 0 | [6 empty] | 1.4 | [11 empty] | 100% | [5 empty] | 0 | [6 empty] | 1.4
8.11 | Procurement & replacement of complete set of Re-heater coil (HRH & CRH) assembly for unit-3 | Scheme |  |  |  | 12.5 | [7 empty] | 1) Heat rate of unit will be improved. 2) Reduction in BTL in RH 3) Improvement in boiler efficiency. 4) Availability and Reliability of unit will be increased Reduction in the 5) Maintenance cost on account of BTL. |  |  |  |  | 0 | [6 empty] | 12.5 | [11 empty] | 100% | [5 empty] | 0 | [6 empty] | 12.5
9 | ODP plant Process reliability improvement schemes | DPR |  |  |  | 32.2 | [12 empty] | 0 | [24 empty] | 0
9.1 | Revamping of WT Plant Auxilliaries. | Scheme |  |  |  | 25 | [7 empty] | * Process realibility improvement. |  |  |  |  | 0 |  |  |  |  | 10 | 15 | [10 empty] | 100% | 100% | [6 empty] | 0 |  |  |  |  | 10 | 15
9.2 | Renovation of NDCT FILL at 2X250MW Units, Paras TPS | Scheme |  |  |  | 6 | [7 empty] | * Process realibility improvement. |  |  |  |  | 0 | [5 empty] | 6 | [11 empty] | 100% | [6 empty] | 0 | [5 empty] | 6
9.3 | Design, engineering, manufacturing, supply , erection and commissioning of degasser unit at Paras TPS | Scheme |  |  |  | 1.2 | [7 empty] | * Process realibility improvement. |  |  |  |  | 0 |  |  |  |  | 1.2 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 1.2
10 | Performance improvement of compressors, compressored air drier system & Modification in Air ventilation system at 2x250MW Paras TPS | DPR |  |  |  | 36.3 | [12 empty] | 0 | [24 empty] | 0
10.1 | Revamping, modification of outdoor ducting of Air ventilation system at 2X250 MW, Paras TPS. | Scheme |  |  |  | 16 | [7 empty] | * Process realibility improvement. |  |  |  |  | 0 |  |  |  |  | 16 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 16
10.2 | Performance improvement of compressors in Unit No.3, Paras TPS. | Scheme |  |  |  | 10.3 | [7 empty] | * Performance improvement & Process realibility improvement. |  |  |  |  | 0 |  |  |  |  | 10.3 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 10.3
10.3 | Renovation of Compressed Air Refrigerated Dryer System for 2X250MW Unit, Paras TPS | Scheme |  |  |  | 10 | [7 empty] | * Process realibility improvement. |  |  |  |  | 0 |  |  |  |  | 10 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 10
11 | Procurement of LP Turbine blades, control fluid pump, AOP, JOP & HP valves for Turbine & its Auxiliaries efficiency improvement | DPR |  |  |  | 25.51 | [12 empty] | 0 | [24 empty] | 0
11.1 | Procurement of Control Fluid Pumps & AOP of 250MW Unit No. 3 & 4 Paras TPS | Scheme |  |  |  | 12 | [7 empty] | * Process realibility improvement. |  |  |  |  | 0 | [5 empty] | 12 | [11 empty] | 100% | [6 empty] | 0 | [5 empty] | 12
11.2 | Moving blades for LPT-2L, 2R, 3L, 3R | Scheme |  |  |  | 13.51 | [7 empty] | * Process realibility improvement. |  |  |  |  | 0 | [5 empty] | 13.51 | [11 empty] | 100% | [6 empty] | 0 | [5 empty] | 13.51
11.3 | Replacement of valves – Main Steam Valves, Extraction Valves, BFP Recirculation Valves, etc. | Scheme |  |  |  | 5 | [7 empty] | * Process realibility improvement. |  |  |  |  | 0 | [6 empty] | 5 | [11 empty] | 100% | [5 empty] | 0 | [6 empty] | 5
12 | Various schemes for reliability & performance improvement of Electrical & Control system | DPR |  |  |  | 32.814 | [12 empty] | 0 | [24 empty] | 0
12.1 | Implementation of Water Flow monitoring system of various Location flowmeter at U3&4 Paras TPS | Scheme |  |  |  | 5.5 | [7 empty] | 1. CGM (E&S) has communicated to all TPS regarding the optimum use of water has become necessary as Ministry Of Environment Forest & Climate Change and MPCB are imposing stringent conditions for the usage of water. In view of the above the scheme is taken up for monitoring and measure the quantity of water processed at various points in TPS. 2. After installation of flow meters water consumption can be monitored. & proper record can be submitted to Irrigation dept. AS per the irrigatin department, if water recovery is more than 25 % then Paras TPS will be eligible for 25 % waive off in billing as per the Maharashtra Water Regulatory Resource Authority. |  |  |  |  | 0 |  |  |  |  | 5.5 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 5.5
12.2 | Upgradation of HMI and PLC hardware of Emerson (Former GE IP) make PLC system installed at Main Plant compressor Unit-4(PLC hardware and HMI), Condensate Polishing Unit Unit-3&4(HMI and PLC hardware), Pre-Treatment Plant Unit-4(HMI and PLC hardware) Water Treatment Plant (PLC hardware Unit-3&4) Ash Handling Plant Unit-4(PLC hardware), at Paras TPS. | Scheme |  |  |  | 9 | [7 empty] | 1. HMI plays a crucial role in the control and monitoring of PLC in Ash Handling Plant, Compressor Plant and Condensate Polishing Unit. HMI upgradation empowers the plant operator and engineers to make informed decisions and thereby improving the reliable operation of the plant. 2. Report generation and event logger will come in new format as software of upgraded PLC system is newly designed, this will help to represent the plant parameters in proper format to calculate efficiency. 3. Also, as GE IP (GE FANUC) has designed this PLC system with latest software, considering all the malware and bugs, the reliability has been improved itself as compare to the existing GE IP (GE FANUC) PLC software. |  |  |  |  | 0 |  |  |  |  | 9 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 9
12.3 | Upgradation of Vibration Monitoring System server make Baker & Hughes (Former Bently Nevada) installed at Unit-3&4 Paras TPS. | Scheme |  |  |  | 3 | [7 empty] | 1. VMS extremely dense data sets both static and dynamic. 2. Rich set of plotting formats for analyzing machine health issues. 3. HMI plays a crucial role in the control and monitoring of performance as part of overall condition monitoring platform, helps monitor asset performance and efficiency and enables performance diagnostics for better maintenance strategies. |  |  |  |  | 0 |  |  |  |  | 3 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 3
12.4 | Revamping and Upgradation of PLC hardware of ABB make Online Condenser Tube Cleaning System installed at Unit-3&4 Paras TPS. | Scheme |  |  |  | 2 | [7 empty] | 1. Reduces turbine back pressure and improves heat rate. 2. Aids in preventing micro-fouling of condensers and heat exchangers. 3. Extends condenser tube life by reducing fouling that can lead to surface pitting and under deposit corrosion. 4. Reduces operating differential across condenser from fouling accumulation. 5. HMI plays a crucial role in the control and monitoring of PLC in Online condenser Tube cleaning system. It empowers the plant operators and engineers with critical data for better control. 6. Emergencies can be avoided by smooth operation of station by HMI upgradation. |  |  |  |  | 0 | [5 empty] | 2 | [11 empty] | 100% | [6 empty] | 0 | [5 empty] | 2
12.5 | Upgradation of carbon monoxide system in Air Preheater flue gas path at Unit-3&4 Paras TPS | Scheme |  |  |  | 3 | [7 empty] | 1. Increased reliability & stability of process and increase Availability and loadability of Plant. 3. CO monitoring will give accurate air fuel ratio for combustion. 4. Carbon monoxide analyzer improves combustion efficiency resulting in heat rate improvement. |  |  |  |  | 0 | [5 empty] | 3 | [11 empty] | 100% | [6 empty] | 0 | [5 empty] | 3
12.6 | Supply, erection, commissioning and testing of 24 V 2X2250Ah, 360V 650AH UPS main plant, 360V 100Ah AHP UPS, 220V 125 Ah RWPH Battery at Paras TPS | Scheme |  |  |  | 3.671 | [7 empty] | * Avoid generation loss. |  |  |  |  | 0 |  |  |  |  | 3.671 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 3.671
12.7 | Upgradation of existing FBTS sytem installed at Paras TPS | Scheme |  |  |  | 4.456 | [7 empty] | 1. Improvement in Operational, Process Performance and System reliability. 2. Improvement in monitoring of continuous Breaker Trip & Close circuits. 3. The system has standard communication Protocol. 4. The system has advanced Software tools for virtual testing, transfer event upload & SOE facility 5. Smooth changeover of supply will take place which will avoid tripping of the Units due to grid disturbance and generation loss thereof. |  |  |  |  | 0 |  |  |  |  | 4.456 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 4.456
12.8 | Procurement and Installation of Aviation Obstruction lighting system of Chimney and Cooling Towers at Paras TPS | Scheme |  |  |  | 2.187 | [7 empty] | 1. The Scheme is not related to plant efficiency and performance, but it is mandatory and statutory requirement as per FAA and ICAO. According to international regulations, such high structures should be noticeable using aircraft warning lights. These are high-intensity, medium intensity lighting devices which are normally attached to high structures. 2. Aircraft warning lights are also utilized as collision prevention measures. These devices make structures more noticeable to passing aircraft and are typically operated at night – however, they can be also used during the day. |  |  |  |  | 0 |  |  |  |  | 2.187 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 2.187
13 | Schemes related to Reduction in auxiliary Power consumption and upgradation of Valves & Instruments of C&I | DPR |  |  |  | 50.5 | [12 empty] | 0 | [24 empty] | 0
13.1 | Renovation and Modification of Colony Electric Supply System to improve availability and reliability of supply system at Paras TPS colony | Scheme |  |  |  | 3 | [7 empty] | * Improve availability and reliability of supply system at Paras TPS colony |  |  |  |  | 0 |  |  |  |  | 3 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 3
13.2 | Supply installation of VFD to CEP motors installed at paras TPS. | Scheme |  |  |  | 10 | [7 empty] | * Reduction in auxiliary Power consumption |  |  |  |  | 0 | [5 empty] | 10 | [11 empty] | 100% | [6 empty] | 0 | [5 empty] | 10
13.3 | Mid life overhauling of GCB installed at Paras TPS. | Scheme |  |  |  | 6 | [7 empty] | * Improve availability and reliability of GCB |  |  |  |  | 0 | [5 empty] | 6 | [11 empty] | 100% | [6 empty] | 0 | [5 empty] | 6
13.4 | Supply, installation testig and comissioning of VFD to PA fan motoras installed at Paras TPS. | Scheme |  |  |  | 10 | [7 empty] | * Reduction in auxiliary Power consumption |  |  |  |  | 0 | [6 empty] | 10 | [11 empty] | 100% | [5 empty] | 0 | [6 empty] | 10
13.5 | Upgradation of ID fan VFD installed at Paras TPS | Scheme |  |  |  | 15 | [7 empty] | * Reduction in auxiliary Power consumption |  |  |  |  | 0 | [7 empty] | 15 | [11 empty] | 100% |  |  |  |  | 0 | [7 empty] | 15
13.6 | Scheme-1-Upgradation of all pneumatic control valve with smart positioner at Unit-3&4 Paras TPS | Scheme |  |  |  | 2 | [7 empty] | 1. To avoid the sluggishness of pneumatic control valve. 2. The resistance to water & heat so sturdy operation |  |  |  |  | 0 | [6 empty] | 2 | [11 empty] | 100% | [5 empty] | 0 | [6 empty] | 2
13.7 | Scheme-2-Upgradation of HFO mass flow meters at Unit-3&4 Paras TPS | Scheme |  |  |  | 1.5 | [7 empty] | 1. For accurate Oil level measurement and monitoring of oil consumption. |  |  |  |  | 0 | [7 empty] | 1.5 | [11 empty] | 100% |  |  |  |  | 0 | [7 empty] | 1.5
13.8 | Scheme-3-Upgradation of O2 measurement system in Air Preheater inlet /outlet flue gas path and chimney inlet path at Unit-3&4 Paras TPS | Scheme |  |  |  | 1 | [7 empty] | 1. O2 measurement for proper burning of coal. 2. To identify the air ingress. |  |  |  |  | 0 | [7 empty] | 1 | [11 empty] | 100% |  |  |  |  | 0 | [7 empty] | 1
13.9 | Scheme-4-Upgradation of Steam Leak Detecting BHELSONIC system at Unit-3&4 Paras TPS | Scheme |  |  |  | 2 | [7 empty] | 1. For identify the early tube leakage and avoid secondary damages. 2. Identifying the steam leaks promptly not only improves efficiency but also contributes to safety and cost savings. |  |  |  |  | 0 | [7 empty] | 2 | [11 empty] | 100% |  |  |  |  | 0 | [7 empty] | 2
14 | Various Civil schemes for Paras TPS Colony | DPR |  |  |  | 25.5 | [12 empty] | 0 | [24 empty] | 0
14.1 | Attendning internal leakages of residential bulding in colony area at TPS Paras. | Scheme |  |  |  | 8.2 | [7 empty] | * Cost benefits for such a scheme cannot be directly quantified but it is essential for residential purposes |  |  |  |  | 0 |  |  |  |  | 8.2 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 8.2
14.2 | Providing Terrace waterproofing to various buildings in colony area at TPS Paras. | Scheme |  |  |  | 2 | [7 empty] | * Cost benefits for such a scheme cannot be directly quantified but it is essential for residential purposes |  |  |  |  | 0 |  |  |  |  | 2 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 2
14.3 | Providing and laying M.S. pipe line from new STP to WTP at TPS Paras. | Scheme |  |  |  | 0.8 | [7 empty] | * Cost benefits for such a scheme cannot be directly quantified but it is essential for residential purposes |  |  |  |  | 0 |  |  |  |  | 0.8 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 0.8
14.4 | Replacement of Water Supply GI Pipe line in colony area at TPS Paras | Scheme |  |  |  | 0.9 | [7 empty] | * Cost benefits for such a scheme cannot be directly quantified but it is essential for residential purposes |  |  |  |  | 0 |  |  |  |  | 0.9 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 0.9
14.5 | Repairing of Colony Internal roads by BT at TPS Paras | Scheme |  |  |  | 3 | [7 empty] | * Cost benefits for such a scheme cannot be directly quantified but it is essential for residential purposes |  |  |  |  | 0 |  |  |  |  | 3 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 3
14.6 | Providing alluminium window to NF,NE,ND & Repairing of existing alluminium window and cupboard of resendial buildings in colony area at TPS Paras. | Scheme |  |  |  | 2.7 | [7 empty] | * Cost benefits for such a scheme cannot be directly quantified but it is essential for residential purposes |  |  |  |  | 0 | [5 empty] | 2.7 | [11 empty] | 100% | [6 empty] | 0 | [5 empty] | 2.7
14.7 | Providing External Painting to Resenditial buildings in colony area at TPS Paras. | Scheme |  |  |  | 2.9 | [7 empty] | * Cost benefits for such a scheme cannot be directly quantified but it is essential for residential purposes |  |  |  |  | 0 | [5 empty] | 2.9 | [11 empty] | 100% | [6 empty] | 0 | [5 empty] | 2.9
14.8 | Construction of Hospital Bulding in colony area at TPS Paras | Scheme |  |  |  | 1 | [7 empty] | * Cost benefits for such a scheme cannot be directly quantified but it is essential for residential purposes |  |  |  |  | 0 | [6 empty] | 1 | [11 empty] | 100% | [5 empty] | 0 | [6 empty] | 1
14.9 | Construction of Community Hall in colony area at TPS Paras | Scheme |  |  |  | 1.1 | [7 empty] | * Cost benefits for such a scheme cannot be directly quantified but it is essential for residential purposes |  |  |  |  | 0 | [6 empty] | 1.1 | [11 empty] | 100% | [5 empty] | 0 | [6 empty] | 1.1
14.1 | Development of Play Ground with Stage in colony area at TPS Paras | Scheme |  |  |  | 0.4 | [7 empty] | * Cost benefits for such a scheme cannot be directly quantified but it is essential for residential purposes |  |  |  |  | 0 | [6 empty] | 0.4 | [11 empty] | 100% | [5 empty] | 0 | [6 empty] | 0.4
14.11 | Beutification of colony area by providing Gardens and plantation in colony area at TPS Paras. | Scheme |  |  |  | 0.2 | [7 empty] | * Cost benefits for such a scheme cannot be directly quantified but it is essential for residential purposes |  |  |  |  | 0 | [7 empty] | 0.2 | [11 empty] | 100% |  |  |  |  | 0 | [7 empty] | 0.2
14.12 | Construction of drain along internal roads in colony area at TPS Paras | Scheme |  |  |  | 2.3 | [7 empty] | * Cost benefits for such a scheme cannot be directly quantified but it is essential for residential purposes |  |  |  |  | 0 | [7 empty] | 2.3 | [11 empty] | 100% |  |  |  |  | 0 | [7 empty] | 2.3
15 | Various Civil schemes related to Plant area of Paras TPS | DPR |  |  |  | 25.4 | [12 empty] | 0 | [24 empty] | 0
15.1 | Providing waterproofing to terrace of various buildings in plant area at TPS Paras. | Scheme |  |  |  | 3.9 | [7 empty] | * Cost benefits for such a scheme cannot be directly quantified but it is essential for plant machinery. |  |  |  |  | 0 |  |  |  |  | 3.9 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 3.9
15.2 | Attedning internal leakages and modification of Toilets in Plant area at TPS Paras. | Scheme |  |  |  | 1.6 | [7 empty] | * Cost benefits for such a scheme cannot be directly quantified but it is essential for plant machinery. |  |  |  |  | 0 |  |  |  |  | 1.6 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 1.6
15.3 | Retrofitting and carben rapping of cooling tower coloumn at TPS Paras | Scheme |  |  |  | 0.5 | [7 empty] | * Cost benefits for such a scheme cannot be directly quantified . |  |  |  |  | 0 |  |  |  |  | 0.5 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 0.5
15.4 | Attendning internal leakages of Parasdeep building along with renovatation of Toilets at TPS Paras. | Scheme |  |  |  | 0.25 | [7 empty] | * Cost benefits for such a scheme cannot be directly quantified . |  |  |  |  | 0 |  |  |  |  | 0.25 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 0.25
15.5 | Replacement of water supply pipe lines in plant area at TPS Paras. | Scheme |  |  |  | 0.9 | [7 empty] | * Cost benefits for such a scheme cannot be directly quantified . |  |  |  |  | 0 |  |  |  |  | 0.9 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 0.9
15.6 | Providing External Painting to various buildings in plant area at TPS Paras. | Scheme |  |  |  | 0.6 | [7 empty] | * Cost benefits for such a scheme cannot be directly quantified . |  |  |  |  | 0 |  |  |  |  | 0.6 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 0.6
15.7 | Construction of Walk Way from Plant Gate to Service Building at TPS Paras | Scheme |  |  |  | 0.4 | [7 empty] | * Cost benefits for such a scheme cannot be directly quantified . |  |  |  |  | 0 |  |  |  |  | 0.4 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 0.4
15.8 | Providing & fixing modular kitchen (Trolleys) in B Type, CM Type, DM Type and EM Type quarters at TPS Paras. | Scheme |  |  |  | 3.5 | [7 empty] | * Cost benefits for such a scheme cannot be directly quantified . |  |  |  |  | 0 |  |  |  |  | 3.5 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 3.5
15.9 | Construction of drain with Footpath from CE Bunglow to Main Road at TPS Paras | Scheme |  |  |  | 2.5 | [7 empty] | * Cost benefits for such a scheme cannot be directly quantified . |  |  |  |  | 0 | [5 empty] | 2.5 | [11 empty] | 100% | [6 empty] | 0 | [5 empty] | 2.5
15.1 | Construction of drain with Footpath from colony gate to Chummery Building at TPS Paras | Scheme |  |  |  | 1.6 | [7 empty] | * Cost benefits for such a scheme cannot be directly quantified . |  |  |  |  | 0 | [5 empty] | 1.6 | [11 empty] | 100% | [6 empty] | 0 | [5 empty] | 1.6
15.11 | Providing Internal Painting to Resenditial buildings in colony area at TPS Paras. | Scheme |  |  |  | 1 | [7 empty] | * Cost benefits for such a scheme cannot be directly quantified . |  |  |  |  | 0 | [6 empty] | 1 | [11 empty] | 100% | [5 empty] | 0 | [6 empty] | 1
15.12 | Renovation of Entrance road from T point to Colony Gate at TPS Paras. | Scheme |  |  |  | 4 | [7 empty] | * Cost benefits for such a scheme cannot be directly quantified . |  |  |  |  | 0 | [6 empty] | 4 | [11 empty] | 100% | [5 empty] | 0 | [6 empty] | 4
15.13 | Repairing of Plant Internal roads by BT at TPS Paras | Scheme |  |  |  | 4.65 | [7 empty] | * Cost benefits for such a scheme cannot be directly quantified . |  |  |  |  | 0 | [7 empty] | 4.65 | [11 empty] | 100% |  |  |  |  | 0 | [7 empty] | 4.65
16 | IB recommendation at TPS Paras | DPR |  |  |  | 7.16 | [12 empty] | 0 | [24 empty] | 0
16.1 | “Construction of RCC Compound wall as per IB recommendation at Paras TPS.” | Scheme |  |  |  | 4.86 | [7 empty] | * IB recommendation. * Cost benefits for such a scheme cannot be directly quantified . |  |  |  |  | 0 |  |  |  | 4.86 | [11 empty] | 100% | [8 empty] | 0 |  |  |  | 4.86
16.2 | “Construction of Watch towers along periphery compound wall as per IB recommendation at TPS Paras.” | Scheme |  |  |  | 2.3 | [7 empty] | * IB recommendation. * Cost benefits for such a scheme cannot be directly quantified . |  |  |  |  | 0 |  |  |  | 2.3 | [11 empty] | 100% | [8 empty] | 0 |  |  |  | 2.3
17 | CHP Improvement Schemes at 2 x 250 MW Paras TPS | DPR |  |  |  | 25 | [12 empty] | 0 | [24 empty] | 0
17.1 | CHP Improvement Schemes at 2 x 250 MW Paras TPS | Scheme |  |  |  | 25 | [7 empty] | CHP performance will be incresed |  |  |  |  | 0 | [5 empty] | 25 | [11 empty] | 100% | [6 empty] | 0 | [5 empty] | 25
18 | FGMO related Capex scheme | DPR |  |  |  | 30 | [12 empty] | 0 | [24 empty] | 0
18.1 | FGMO related Capex scheme | Scheme |  |  |  | 30 | [12 empty] | 0 |  |  |  | 30 | [11 empty] | 100% | [8 empty] | 0 |  |  |  | 30 | [5 empty] | Yet to be prepared | N.A.
[19 empty] | 0 | [24 empty] | 0
| Covid-19 Pandemic Related Work | [17 empty] | 0 | [24 empty] | 0
1 | Medical Oxygen Gen. & Bottling Plant |  | N.A. | [14 empty] | 2.6741 | 2.6741 | [11 empty] | 100% | [11 empty] | 2.6741 | 2.6741 | [10 empty] | Capitalised
2 | Empty Std size Medical Gr. Oxygen Cyl. |  | N.A. | [14 empty] | 0.41133 | 0.41133 | [11 empty] | 100% | [11 empty] | 0.41133 | 0.41133 | [10 empty] | Capitalised
3 | Oxy Installation&Commissioning of Plant |  | N.A. | [14 empty] | 0.079772 | 0.079772 | [11 empty] | 100% | [11 empty] | 0.079772 | 0.079772 | [10 empty] | Capitalised
[19 empty] | 0 | [24 empty] | 0
| Asset Transfer from Paras Project | [17 empty] | 0 | [24 empty] | 0
4 | Boiler Plant and Equipment Single Drum |  | N.A. | [14 empty] | 4.9843 | 4.9843 | [11 empty] | 100% | [11 empty] | 4.9843 | 4.9843 | [9 empty] | Balance payment to BHEL After reconciliation | Capitalised
| LAND |  | N.A. | [12 empty] | 1.2533 | 1.836 | 1.0788 | 4.1681 | 11.2307 | 8.4063 | [19 empty] | 1.2533 | 1.836 | 1.0788 | 4.1681 | 11.2307 | 8.4063 | 10.5 | 8.5 | 9 | 8 | 8.5 | 8.5
| B) Non-DPR Schemes | [17 empty] | 0 | [24 empty] | 0
1 | Installation of portable crusher alongwith conveying system at 250 MW CHP, Paras TPS.-(CHP) | Non-DPR | N.A. | [7 empty] | 2019-11-29 | - | 2019-20 | IMPROVEMENT OF PERFORMANCE & EFFICIENCY OF CHP | 0.99445 | 0.99445 | 0 | 0 | 1.9889 | 0 | [8 empty] | 100% | [11 empty] | 1.9889 | 0 | 0 | 1.9889 | 0 | [8 empty] | Scheme completed | Capitalised
2 | Providing & Applying Epoxy Painting upto all height to structural steel work in power house area at TPS, Paras-(CIVIL) | Non-DPR | N.A. | [7 empty] | 2022-23 | - | 2020-21 | To arrest deterioration,Avoid catastrophic failure,Increase availability of plant & equipment Preservation of Asse,To increase the life of structures | 0 | 5.5619 | 0.11846 | 0 | 5.6803 | 0 | [9 empty] | 100% | [10 empty] | 0 | 5.6803 | 0 | 5.6803 | 0 | [8 empty] | Scheme completed | Capitalised
3 | Material Handling Equipments | [15 empty] | 0.033747 |  | 0.033747 | [22 empty] | 0.033747 |  | 0.033747
5 | Scheme for supply, erection, commissioning & testing of 7.2 KV SF6 contactor for retrofitting of existing BHEL make VM-12 type 6.6 KV HT circuit breakers of CHP Paras TPS.-(CHP) | Non-DPR | N.A. | [7 empty] | 2022-23 | - | - | This scheme leads to process improvement, Improvement in availability of Single steam coal conveyor system. The cost of spars as well as labor cost toward maintenance of HT breaker will be reduced over long period. | 0 | 0 | 0 | 2.0947 | 2.0947 | 0.11054 | 0 | 0.1652 | [9 empty] | 100% | [8 empty] | 0 | 0 | 0 | 0 | 2.2053 |  | 0.1652 | [6 empty] | PO No-4385000155.IDC-11,05,361.00 Scheme completed & Capitalized in FY 22-23, Work portion still to be capitalized.Expected in FY 2024-25. | Partially Capitalised
6 | SWAS Lab improvement -(C&I) | Non-DPR | N.A. | [7 empty] | 2022-23 | - | - | All the SWAS system analyzers will be in service resulting in complete monitoring of system enabling fewer damages to boiler, turbine and BFPs. | 0 | 0 | 0 | 0 | 0 | 2.2951 | [11 empty] | 100% | [8 empty] | 0 | 0 | 0 | 0 | 2.2951 | [8 empty] | PO No-4385000556. Scheme completed & Capitalized in FY 22-23, | Capitalised
7 | Design, supply, installation and commissioning of High performance energy chain system for Side Arm Charger at CHP 2 X 250 MW Unit 3 & 4 -(CHP) | Non-DPR | N.A. | [7 empty] | 2022-23 | - | - | IMPROVEMENT OF PERFORMANCE & EFFICIENCY OF WAGON TIPPLER | 0 | 0 | 0 | 0.92548 | 0.92548 | 0.12437 | [11 empty] | 100% | [8 empty] | 0 | 0 | 0 | 0 | 1.0499 | [8 empty] | PO No-4385000507. IDC=7,24,518.00 Scheme completed & Capitalized in FY 22-23, | Capitalised
8 | Design, Manufacturing, supply, fabricate & erection of coal chutes with extra life weir reistatnce plates -(CHP) | Non-DPR | N.A. | [7 empty] | 2022-23 | - | - | System availability will increase. Repetitive maintenances of chute will reduce, Chute life will increase, Coal leakages at transfer point will be reduce drastically, therefore cleaning and housekeeping problems will reduce. | 0 | 0 | 0 | 0 | 0 | 2.3522 | [11 empty] | 100% | [8 empty] | 0 | 0 | 0 | 0 | 2.3522 | [8 empty] | PO No-4385000490.IDC-12,19,808.00 Scheme completed & Capitalized in FY 22-23, | Capitalised
9 | Procurement and installation of set of internals of reducer gear box of coall mill BBD4772 @ Paras TPS -(BM) | Non-DPR | N.A. | [7 empty] | 2022-23 | - | - | Reduction in generation loss on account of non availability of coal mill & improvement in availability of coal mill , quantity, availability and loadability. | 0 | 0 | 0 | 0 | 0 | 0 | 1.788 | [11 empty] | 100% | [7 empty] | 0 | 0 | 0 | 0 |  | 1.788 | [7 empty] | PO No-4550015189, 4385000666 Scheme completed & Capitalized in FY 23-24, | Capitalised
10 | NON DPR scheme of procurement and installation of spares of non standard gridflex and gearflex couplings for coal mill BBD 4772 at Paras TPS 2x250MW -(BM) | Non-DPR | N.A. | [7 empty] | 2023-24 | - | - | Reduction in generation loss on account of non availability of coal mill & improvement in availability of coal mill , quantity, availability and loadability. | 0 | 0 | 0 | 0 | 0 |  | 0.88434 | 0.024426 | [10 empty] | 100% | [7 empty] | 0 | 0 | 0 | 0 |  | 0.60584 | 0.30292 | [6 empty] | PO No-4385000632, 4385000654 Partialy Capitalized in FY 23-24. 3 rd set is installed in June-2024. | Capitalised
11 | HO Non-DPR-Procurement of ABC powder Type & Foam type composite Fire Extnguisher for Paras TPS | Non-DPR | N.A. | [7 empty] | 2023-24 | - | - | [5 empty] | 0 |  | 0.5712 | [11 empty] | 100% | [10 empty] | 0 |  | 0.5712 | [7 empty] | PO No-4500128925 Scheme completed & Capitalized in FY 23-24, | Capitalised
12 | Supply & replacement of APH baskets at Unit-3 | Non-DPR | N.A. | [7 empty] | 2024-25 | - | - | [5 empty] | 0 |  | 3.1799 | 0.26786 | [21 empty] | 0 |  |  | 3.45 | [6 empty] | PO NO placed vide HO/4370003146 dated 26.05.2023. Delivery Period is 4 month after drawing Approval. Material received on 05-10-2023. Work PO dispatched. 4385000690 Work completed in COH U-3 (FY 2024-25) | Capitalised
13 | Battery Bank 220VDC , 2140Ah for Unit -3 | Non-DPR | N.A. | [7 empty] | 2024-25 | - | - | [5 empty] | 0 |  | 5.83 | [22 empty] | 0 |  |  | 5.83 | [6 empty] | PO No-4385000664 placed on M/s. Shree Enterprises - Parli Vaijanath on dated 17-07-2023. Material received on 12-09-2023. Installation work completed. | Capitalised
[19 empty] | 0 | [24 empty] | 0
| General Assets | [9 empty] | 2023-24 | - | - | [5 empty] | 0 | [24 empty] | 0
10 | Furniture & Fixtures | Non-DPR | N.A. | [12 empty] | 0.32215 | 0.1442 | 0.12929 | 0.59564 | 0.059711 | 0.016874 | 0.043673 | [9 empty] | 100% | [8 empty] | 0.32215 | 0.1442 | 0.12929 | 0.59564 | 0.059711 | 0.016874 | 0.043673 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  |  | Capitalised
11 | Office Equipment | Non-DPR | N.A. | [12 empty] | 0.52 | 1.0508 | 0.30708 | 1.8779 | 0.12174 | 0.082568 | 0.04328 | [9 empty] | 100% | [8 empty] | 0.52 | 1.0508 | 0.30708 | 1.8779 | 0.12174 | 0.082568 | 0.04328 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  | Rs 32950 actual capitalization fy 24-25 | Capitalised
12 | RCC Approach Road for CHP at Paras TPS | Non-DPR | N.A. | [13 empty] | 1.7158 |  | 1.7158 |  | 0.076522 | [10 empty] | 100% | [9 empty] | 1.7158 |  | 1.7158 |  | 0.076522 | [8 empty] | Capitalised
13 | Vehicles | Non-DPR | N.A. | [12 empty] | 0.34653 |  |  | 0.34653 |  |  | 0.4043 | [9 empty] | 100% | [8 empty] | 0.34653 |  |  | 0.34653 | 0 | 0 | 0.4043 | [7 empty] | Capitalised
14 | I.T. Equipment | [17 empty] | 0 |  |  | 0.54853 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | [16 empty] | 0 |  |  | 0.54853 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
15 | Building | [17 empty] | 0 | [24 empty] | 0 | [6 empty] | 2.1
| Total | [13 empty] | 74.261 | 31.1909 | 22.6849 | 35.1042 | 163.241 | 50.5713 | 134.3751 | 263.6406 | 267.3423 | 203.184 | 201.61 | 59.45 | 46.55 | [12 empty] | 30.9985 | 10.7702 | 11.7831 | 26.951 | 80.5028 | 78.5823 | 26.7271 | 286.5317 | 379.5305 | 264.684 | 209.81 | 70.25 | 55.25 | 0 | 0 | 0
[45 empty] | 8.0839 | 3.141 | 10.7879
[45 empty] | 19.3145 | 11.5473 | 21.2879 | 8.8 | 9.3 | 8.3 | 10.9 | 8.8
Formulas:
Approved Start Date = IF([MERC Approval Date]=0,"-",[MERC Approval Date])
Date of Submission = [Date of Submission, row above]
MERC Approval Date = IF([MERC Approval Date, row above]=0,"-",[MERC Approval Date, row above])
MERC Approval Date = [MERC Approval Date, row above]
Note on M4: SSP-RCD As per the implementation plan submitted in the DPR/ Approved by MERC
Note on G35: RCD-SSP: 29.51 As per financial model. 26.20 as per BR & initial submission.
Note on G37: SSP: In initial submission, the IDC was wrongly submitted as Rs. 0.04 Cr.

## F4.3
MSPGCL-Paras U # 3-4
MTR Petition Formats - Generation
| Project Details | Form 4.3: Capital Work-in-progress - Project-wise details | [9 empty] | (Rs. Crore)
Sr. No. | Project Code | MERC Approval No. | MERC Approval Date | Approved Project Cost | Cumulative Expenditure Incurred till beginning of the Year | Capital Expenditure Capitalised | Opening CWIP | Investment during the year | Capitalization |  |  |  | Closing CWIP
[9 empty] | Works Capitalised | Interest Capitalised | Expenses Capitalised | Total Capitalisation |  | Allowable Capitalisation | Probable Disallowance
FY 2022-23
a) DPR Schemes
(i) Submitted to MERC
1 | Power supply arrangement at colony & separate 25 KV OHE supply feeding arrangement to BESG siding & provision of Passenger elevators | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 7.1549 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Provision of separate 25 KV OHE supply feeding arrangement to BESG siding at Paras TPS | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 0.3715 | 0.37148 | 0.37148 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | Arrangement of power supply for Paras TPS colony from 250 MW units with stepping down 6.6 KV supply to 3.3 KV. | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 3.6334 | 1.9509 | 1.9509 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Supply & installation of Total 12 nos. passenger elevators at `D’ & `E’ type quarters & administrative building of Paras TPS | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 3.15 | 1.6426 | 1.6426 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Ash Handling Plant augmentation scheme at Paras TPS Unit 3 & 4 | MERC/TECH 1/CAPEX/20142015/01160 | 2014-11-17 | 38.0989 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Ash Handling Plant augmentation scheme at Paras TPS Unit 3 & 4 | MERC/TECH 1/CAPEX/20142015/01160 | 2014-11-17 | 34.6889 | 58.676 | 0 | 58.676 | 0 | 44.7505 |  |  | 44.7505 | 13.9255 | 34.6889 | 10.0616
0 | IDC | MERC/TECH 1/CAPEX/20142015/01160 | 2014-11-17 | 3.41 | 0 | 0 | 0 | 0.99854 | 0 |  |  | 0 | 0.99854 | 0 | 0
3 | 3rd raising of Ash bund from TBL 273.63 mtr. to 276.63 mtr. with construction of masonry dam | MERC/MSPGCL/CAPEX/20142015/01648 | 2015-02-26 | 9.2104 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | 3rd raising of Ash bund from TBL 273.63 mtr. to 276.63 mtr. with construction of masonry dam | MERC/MSPGCL/CAPEX/20142015/01648 | 2015-02-26 | 8.2519 | 3.3121 | 3.3121 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/CAPEX/20142015/01648 | 2015-02-26 | 0.95855 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Various schemes related to CHP Improvement and Stack Management & Coal Mill Performance Improvement schemes | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 17.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Procurement of apron feeder system, pan & chain Assembly (2 no.’s) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 7.44 | 7.521 | 0 | 7.521 | 0 | 7.521 |  |  | 7.521 | 0 | 7.44 | 0.081032
4.2 | Procurement of Assembly of Impact Crusher complete set with Beater Arm & Head.(1 no.) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.57 | 1.6013 | 1.6013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.3 | Procurement of Slewing Bearing of Stacker Reclaimer. (1 no.) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.45 | 1.4676 | 1.4676 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.4 | Capacity Enhancement of Wagon Tippler at Old CHP. | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 2.86 | 2.9502 | 2.9502 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.5 | Procurement of Bulldozer BD-155 for CHP(1 no.) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.7 | 2.1022 | 2.1022 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.6 | Procurement of Girth Gear and Pinion for BBD 4772 coal mills of 250 MW (1 set) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.6 | 1.6943 | 1.6943 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Procurement of Two Cartridge assembly for Boiler Feed Pump (Type: FK-3B-40) of 250MW Set | MERC/MSPGCL/CAPEX/20162017/04228 | 2017-09-22 | 13.88 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Procurement of Two Cartridge assembly for Boiler Feed Pump (Type: FK-3B-40) of 250MW Set | MERC/MSPGCL/CAPEX/20162017/04228 | 2017-09-22 | 13.88 | 14.0416 | 14.0416 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Replacement of battery bank set, replacement of two complete set of air pre-heater baskets & coal compartment assemblies for 250MW Unit 4 at Paras TPS | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 10.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Replacement of battery bank set to enhance process reliability of 250 MW Unit-4 at Paras TPS. | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 7.54 | 8.4214 | 8.4214 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.2 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-4, Paras TPS. | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 1.78 | 2.45 | 2.45 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.3 | Procurement & Replacement of Coal Compartment Assemblies Baskets at 250 MW Unit-4, Paras TPS. | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 0.75 | 0.46586 | 0 | 0.46586 | 0.10388 | 0.56974 |  |  | 0.56974 | 0 | 0.56974 | 0
0 | IDC | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 0.04 | 0 | 0 | 0 | 0.25586 | 0.25786 |  |  | 0.25786 | -0.002001 | 0.04 | 0.21786
7 | Procurement & Replacement of complete set of Economizer and LTSH upper & lower coils at Unit-3, Paras TPS | MERC/CAPEX/2019-2020/2 | 2019-05-24 | 10.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Replacement of complete set of economizer (upper & lower) coil assemblies & LTSH (upper & lower) coil assemblies for Unit-3. | MERC/CAPEX/2019-2020/2 | 2019-05-24 | 10.6 | 8.8 | 0 | 8.8 | 0 | 0 |  |  | 0 | 8.8 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/2 | 2019-05-24 | 0.22 | 0 | 0 | 0 | 0.96092 | 0 |  |  | 0 | 0.96092 | 0 | 0
8 | HMI (Human Machine Interface) up gradation of DCS UNIT-3 & 4, WTP (Water Treatment Plant unit-3 & 4 combined PLC system) & AHP (Ash Handling Plant Unit-3 & 4 PLC System), Procurement of girth gear & pinion for optimum availability of auxiliary at Paras TPS | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 11.14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Up-gradation of Existing Max-DNA System (HMI) at Paras TPS (U# 3 & 4). | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 7.12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Up-gradation of GE IP (GE-Fanuc) make PLC system (HMI) installed at WTP at Paras TPS (Combined for U# 3 & 4). | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0.38 | 0.36789 | 0.36789 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.3 | Up-gradation of GE IP (GE-Fanuc) make PLC system (HMI) installed at AHP Unit - 4 at Paras TPS. | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0.48 | 0.45873 | 0.45873 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.4 | Up-gradation of Existing Schneider make PLC (HMI + PLC hardware) installed at AHP Unit - 3 at Paras TPS. | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0.9 | 0.7788 | 0 | 0.7788 | 0 | 0 |  |  | 0 | 0.7788 | 0 | 0
8.5 | Procurement & installation of Girth Gear & Pinion for coal mill BBD-4772. | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 2.26 | 2.1171 | 2.1171 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Complete Track Renewal at Paras TPS | MERC/CAPEX/2019-2020/479 | 2019-08-02 | 12.77 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Complete Track Renewal at Paras TPS | MERC/CAPEX/2019-2020/479 | 2019-08-02 | 12.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/479 | 2019-08-02 | 0.72 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Procurement & Replacement of water wall panels in Unit#4 & Installation of VFD to existing eddy current drive driven coal feeders at 2x250 MW at Paras TPS | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 12.72 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Replacement of water wall panel in Unit-4 Boiler at 2 X 250 MW, PTPS | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 6.49 | 2.7423 | 0 | 2.7423 | 0 | 0 |  |  | 0 | 2.7423 | 0 | 0
10.2 | Installation of VFD with controller over existing eddy current drives with controller at 2 X 250 MW, PTPS. | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 6.23 | 0 | 0 | 0 | 6.1732 | 0 |  |  | 0 | 6.1732 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Reinforcement & Capacity Enhancement of Old CHP Coal Conveyor Belt Structure from (200 TPH to 360 TPH) at old CHP Paras TPS & Procurement of One No. of Bulldozer & Diesel Hydraulic Locomotive at Paras TPS | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 12.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Capacity Enhancement of Old CHP Conveyor belt from 200 TPH to 360 TPH at Old CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 2.94 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Reinforcement of Belt Conveyor structure at Old CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 2.66 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.3 | Procurement of Bulldozer at CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 2.31 | 2.4909 | 2.4909 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.4 | Procurement of Diesel Hydraulic Locomotive at CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 3.6 | 0 | 0 | 0 | 3.057 | 3.057 |  |  | 3.057 | 0 | 3.057 | 0
0 | IDC | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 0.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Flue Gas Desulpherization (FGD) System for Paras Unit No. 3 & 4 | MERC/CAPEX/2020-2021/WFH/SBR/42 | 2020-12-14 | 376.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Flue Gas Desulpherization (FGD) System for Paras Unit No. 3 & 4 | MERC/CAPEX/2020-2021/WFH/SBR/42 | 2020-12-14 | 347.02 | 0 | 0 | 0 | 20.35 | 0 |  |  | 0 | 20.35 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/42 | 2020-12-14 | 29.04 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Procurement & Installation of complete assembly of Elecon make Gear Boxes, Wagon Tippler Assembly; Design, Supply, Installation, Commissioning & Successful Trial of Link Conveyor from Stackyard to C-2 Conveyor Belt at CHP; Procurement of Bucket Wheel of Stacker Reclaimer for CHP at Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 54.98 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Procurement & Installation of complete assembly of Elecon make Gear Boxes, Wagon Tippler Assembly; Design, Supply, Installation, Commissioning & Successful Trial of Link Conveyor from Stackyard to C-2 Conveyor Belt at CHP; Procurement of Bucket Wheel of Stacker Reclaimer for CHP at Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 32.78 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Procurement of Wagon Tippler Assembly & Installation of the same at CHP at Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 13.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.3 | Design, supply, installation, commissioning & successful trial of Link Conveyor from Stackyard to C-2 conveyor belt at CHP, Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 5.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.4 | Procurement of bucket wheel of stacker reclaimer for CHP 250MW Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 1.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 1.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 3.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.6 | Paras: Procurement of HT Motors(CEP/ACW Motors-I Phase and CW/CHP Motors-II Phase)for U-3&4 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 3.6 | 2.0958 | 1.3619 | 0.73396 | 0 | 0.73396 |  |  | 0.73396 | 0 | 0.73396 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 1.235 | 1.235 |  |  | 1.235 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.1 | PARAS(U-3 & 4) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 3.7536 | 3.7536 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 2.0276 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.1 | Paras TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 2.0276 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender at Paras TPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 1.7765 | 1.7765 | 0 | 1.1426 | 1.1426 |  |  | 1.1426 | 0 | 0 | 1.1426
HO DPR 8.2 | Normal Multipurpose Fire Tender at Paras TPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.0768 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.1 | TPS Paras | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.0768 | 1.6142 | 1.6142 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 11.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 12 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 12.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Enhancing process reliability at U-3 & U-4 at 2X250MW Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement & replacement of complete set of Economiser (upper & lower) coil assemblies & LTSH (upper & lower) coil assemblies in Unit-4 (250mw) at Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement & installation of complete discharge assembly of coal mill BBD 4772 In Unit-3&4 at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, replacement, erection and installation of foundation deck spring of coal mill BBD 4772 for Unit-3&4 at 250 MW at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement & Replacement of Coal Compartment Assemblies at 250 MW for Unit-3&4, Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement & Replacement of Girth gear and pinion Assemblies at 250 MW Unit-3,4, Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement & Replacement of Coal Mill drive shaft Assemblies at 250 MW Unit-3&4 Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement & Replacement of Air Pre Heater speed reducer gear box set of internals (assembly) for Unit-3&4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement & Replacement of foundation deck spring assembly (vibration isolation system) for ID fan for Unit 3&4 at Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of CW Pump module with mandatory spares for TM section | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| DPR for Ash Evacuation System Rehabilitation and improvement of performance & efficiency of Ash Handling System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Replacement of old 300NB ash slurry disposal pipeline with new 300NB MSERW pipeline from slurry pump house to surface drain pump house at Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Replacement of old 200nb bottom ash, coarse ash, fly ash conveying pipeline with new 200 NB MSERW pipeline from ash hoppers to slurry tank & SILO AT PTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of complete assembly of air compressors (T-BTD-JM (4NOS) AND T-BD-QL (6NOS.)) in ash evacuation system in AHP, Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of complete assembly of SAM make ar-150/510 Pumps (9 nos) for replacement of ash slurry pumps of bottom ash slurry disposal from slurry tank to ash bund in slurry pump house. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of complete assembly of SAM MAKE ZM-II 530/03 (4 NOS) for replacement of HP pumps of bottom ash & coarse ash evacuation from BA/CA hoppers to slurry tank in ash water pump house. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of major internal assemblies of weir make GEHO pumps installed at AHP, Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of critical transmission drive systems and fluid couplings internal assemblies for slurry pumps and silo HCSD system installed at AHP, Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Augmentaion/Modification of U-3 & U-4 ESP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Restoration of ESP Fields of Unit- 3 & 4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Performance & Capacity enhancement of Ash handling plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement & Replacement of existing ash slurry disposal pump assembly by higher efficient pump assembly in AHP of Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of higher capacity vacuum pumps along with motors to improve availability & performance of fly ash system of AHP Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Modification & Replacement of air drier at AHP Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement & Replacement of existing HT Motors by energy efficient HT Motors In AHP of Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement & Replacement of ash handling plant auxiliaries & systems of Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement & Replacement of DRC Pipeline of fly ash evacuation system of AHP Paras for Availability improvement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement & Replacement of DRC Pipeline of fly ash evacuation system of AHP Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Structure strengthening of AHP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Work of anticorrosive Painting & Structure strengthening of Ash Handling Plant structures | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| U-3 Boiler Effyciency & Performance improvement schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| CAVT & CFD for unit-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of sky climber assembly for Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement & replacement of PA fan NDV22 BAB2 rotor assembly with impeller and cone & blade assembly of IGV with rod end assly for IGV control for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement & replacement Dampers, shutoff gate assemblies for series 5,6,7 & 8 dampers, ID fan inlet gate, APH flue gas dampers I/L & O/L, APH PA I/L & O/L dampers, APH SA I/L & O/L dampers along with actuators, SADC dampers at wind box with actuators for unit-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement & replacement of critical high pressure valves, safety valves & control valves for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply and Replacement of Thermal Insulation of Boiler, Ducts & Steam Pipelines for unit-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement and replacement of HP and B&S Lub oil pumps of coal mills BBD-4772 installed at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement & replacement of complete Coal compartment assly for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement & replacement of complete APH baskets, HE & CE sector plate, diapharm plate, rotor spool piece, grating assly, all type seals, rack pinion for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement & replacement of complete set of Final super heater coil assembly for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement & replacement of complete rotor assembly of FD fan including shaft with brg assly, impeller with oil hydraulic blade adjustment device with blades & coupling for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| U-3 & U-4 Boiler Effyciency, Performance & reliability improvement schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement & replacement of Coal compartment assly for unit-4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply and Replacement of Thermal Insulation of Boiler, Ducts & Steam Pipelines for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement & replacement of critical high pressure valves, safety valves & control valves for unit-4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| CAVT & CFD for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement & replacement Dampers, shutoff gate assemblies for series 5,6,7 & 8 dampers, ID fan inlet gate, APH flue gas dampers I/L & O/L, APH PA I/L & O/L dampers, APH SA I/L & O/L dampers along with actuators, SADC dampers at wind box with actuators for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement & replacement of complete seal air fan assembly of coal mill BBD-4772 (without Motor) installed at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement & replacement of complete set of Final super heater coil assembly for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement & replacement of complete Coal compartment assly for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement & replacement of complete APH baskets, HE & CE sector plate, diapharm plate, rotor spool piece, grating assly, all type seals, rack pinion for unit-4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement & replacement of complete Coal compartment assly for unit-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement & replacement of complete set of Re-heater coil (HRH & CRH) assembly for unit-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| ODP plant Process reliability improvement schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Revamping of WT Plant Auxilliaries. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Renovation of NDCT FILL at 2X250MW Units, Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Design, engineering, manufacturing, supply , erection and commissioning of degasser unit at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Performance improvement of compressors, compressored air drier system & Modification in Air ventilation system at 2x250MW Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Revamping, modification of outdoor ducting of Air ventilation system at 2X250 MW, Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Performance improvement of compressors in Unit No.3, Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Renovation of Compressed Air Refrigerated Dryer System for 2X250MW Unit, Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of LP Turbine blades, control fluid pump, AOP, JOP & HP valves for Turbine & its Auxiliaries efficiency improvement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement of Control Fluid Pumps & AOP of 250MW Unit No. 3 & 4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Moving blades for LPT-2L, 2R, 3L, 3R | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Replacement of valves – Main Steam Valves, Extraction Valves, BFP Recirculation Valves, etc. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Various schemes for reliability & performance improvement of Electrical & Control system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Implementation of Water Flow monitoring system of various Location flowmeter at U3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of HMI and PLC hardware of Emerson (Former GE IP) make PLC system installed at Main Plant compressor Unit-4(PLC hardware and HMI), Condensate Polishing Unit Unit-3&4(HMI and PLC hardware), Pre-Treatment Plant Unit-4(HMI and PLC hardware) Water Treatment Plant (PLC hardware Unit-3&4) Ash Handling Plant Unit-4(PLC hardware), at Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of Vibration Monitoring System server make Baker & Hughes (Former Bently Nevada) installed at Unit-3&4 Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Revamping and Upgradation of PLC hardware of ABB make Online Condenser Tube Cleaning System installed at Unit-3&4 Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of carbon monoxide system in Air Preheater flue gas path at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, erection, commissioning and testing of 24 V 2X2250Ah, 360V 650AH UPS main plant, 360V 100Ah AHP UPS, 220V 125 Ah RWPH Battery at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of existing FBTS sytem installed at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Procurement and Installation of Aviation Obstruction lighting system of Chimney and Cooling Towers at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Schemes related to Reduction in auxiliary Power consumption and upgradation of Valves & Instruments of C&I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Renovation and Modification of Colony Electric Supply System to improve availability and reliability of supply system at Paras TPS colony | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply installation of VFD to CEP motors installed at paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Mid life overhauling of GCB installed at Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply, installation testig and comissioning of VFD to PA fan motoras installed at Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Upgradation of ID fan VFD installed at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-1-Upgradation of all pneumatic control valve with smart positioner at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-2-Upgradation of HFO mass flow meters at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-3-Upgradation of O2 measurement system in Air Preheater inlet /outlet flue gas path and chimney inlet path at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme-4-Upgradation of Steam Leak Detecting BHELSONIC system at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Various Civil schemes for Paras TPS Colony | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Attendning internal leakages of residential bulding in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Providing Terrace waterproofing to various buildings in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Providing and laying M.S. pipe line from new STP to WTP at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Replacement of Water Supply GI Pipe line in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repairing of Colony Internal roads by BT at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Providing alluminium window to NF,NE,ND & Repairing of existing alluminium window and cupboard of resendial buildings in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Providing External Painting to Resenditial buildings in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of Hospital Bulding in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of Community Hall in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Development of Play Ground with Stage in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Beutification of colony area by providing Gardens and plantation in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of drain along internal roads in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Various Civil schemes related to Plant area of Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Providing waterproofing to terrace of various buildings in plant area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Attedning internal leakages and modification of Toilets in Plant area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Retrofitting and carben rapping of cooling tower coloumn at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Attendning internal leakages of Parasdeep building along with renovatation of Toilets at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Replacement of water supply pipe lines in plant area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Providing External Painting to various buildings in plant area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of Walk Way from Plant Gate to Service Building at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Providing & fixing modular kitchen (Trolleys) in B Type, CM Type, DM Type and EM Type quarters at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of drain with Footpath from CE Bunglow to Main Road at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Construction of drain with Footpath from colony gate to Chummery Building at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Providing Internal Painting to Resenditial buildings in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Renovation of Entrance road from T point to Colony Gate at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Repairing of Plant Internal roads by BT at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| IB recommendation at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| “Construction of RCC Compound wall as per IB recommendation at Paras TPS.” | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| “Construction of Watch towers along periphery compound wall as per IB recommendation at TPS Paras.” | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| CHP Improvement Schemes at 2 x 250 MW Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| CHP Improvement Schemes at 2 x 250 MW Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| FGMO related Capex scheme | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| FGMO related Capex scheme | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Covid-19 Pandemic Related Work | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Medical Oxygen Gen. & Bottling Plant | N.A. | - | 0 | 2.6741 | 2.6741 | 0 | 0 | 0 |  |  | 0 | 0
| Empty Std size Medical Gr. Oxygen Cyl. | N.A. | - | 0 | 0.41133 | 0.41133 | 0 | 0 | 0 |  |  | 0 | 0
| Oxy Installation&Commissioning of Plant | N.A. | - | 0 | 0.079772 | 0.079772 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Asset Transfer from Paras Project | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Boiler Plant and Equipment Single Drum | N.A. | - | 0 | 4.9843 | 4.9843 | 0 | 0 | 0 |  |  | 0 | 0
| LAND | N.A. | - | 0 | 4.1681 | 4.1681 | 0 | 11.2307 | 11.2307 |  |  | 11.2307 | 0
| B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Installation of portable crusher alongwith conveying system at 250 MW CHP, Paras TPS.-(CHP) | N.A. | - | 0 | 1.9889 | 1.9889 | 0 | 0 | 0 |  |  | 0 | 0
| Providing & Applying Epoxy Painting upto all height to structural steel work in power house area at TPS, Paras-(CIVIL) | N.A. | - | 0 | 5.6803 | 5.6803 | 0 | 0 | 0 |  |  | 0 | 0
| Material Handling Equipments | 0 | - | 0 | 0.033747 | 0.033747 | 0 | 0 | 0 |  |  | 0 | 0
| Scheme for supply, erection, commissioning & testing of 7.2 KV SF6 contactor for retrofitting of existing BHEL make VM-12 type 6.6 KV HT circuit breakers of CHP Paras TPS.-(CHP) | N.A. | - | 0 | 2.0947 | 0 | 2.0947 | 0.11054 | 2.2053 |  |  | 2.2053 | 0
| SWAS Lab improvement -(C&I) | N.A. | - | 0 | 0 | 0 | 0 | 2.2951 | 2.2951 |  |  | 2.2951 | 0
| Design, supply, installation and commissioning of High performance energy chain system for Side Arm Charger at CHP 2 X 250 MW Unit 3 & 4 -(CHP) | N.A. | - | 0 | 0.92548 | 0 | 0.92548 | 0.12437 | 1.0499 |  |  | 1.0499 | 0
| Design, Manufacturing, supply, fabricate & erection of coal chutes with extra life weir reistatnce plates -(CHP) | N.A. | - | 0 | 0 | 0 | 0 | 2.3522 | 2.3522 |  |  | 2.3522 | 0
| Procurement and installation of set of internals of reducer gear box of coall mill BBD4772 @ Paras TPS -(BM) | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| NON DPR scheme of procurement and installation of spares of non standard gridflex and gearflex couplings for coal mill BBD 4772 at Paras TPS 2x250MW -(BM) | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| HO Non-DPR-Procurement of ABC powder Type & Foam type composite Fire Extnguisher for Paras TPS | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Supply & replacement of APH baskets at Unit-3 | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Battery Bank 220VDC , 2140Ah for Unit -3 | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| General Assets | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Furniture & Fixtures | N.A. | - | 0 | 0.59564 | 0.59564 | 0 | 0.059711 | 0.059711 |  |  | 0.059711 | 0
| Office Equipment | N.A. | - | 0 | 1.8779 | 1.8779 | 0 | 0.12174 | 0.12174 |  |  | 0.12174 | 0
| RCC Approach Road for CHP at Paras TPS | N.A. | - | 0 | 1.7158 | 1.7158 | 0 | 0 | 0 |  |  | 0 | 0
| Vehicles | N.A. | - | 0 | 0.34653 | 0.34653 | 0 | 0 | 0 |  |  | 0 | 0
| I.T. Equipment | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Building | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 163.241 | 80.5028 | 82.7382 | 50.5713 | 78.5823 | 0 | 0 | 78.5823 | 54.7272
FY 2023-24
a) DPR Schemes
(i) Submitted to MERC
1 | Power supply arrangement at colony & separate 25 KV OHE supply feeding arrangement to BESG siding & provision of Passenger elevators | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 7.1549 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Provision of separate 25 KV OHE supply feeding arrangement to BESG siding at Paras TPS | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 0.3715 | 0.37148 | 0.37148 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | Arrangement of power supply for Paras TPS colony from 250 MW units with stepping down 6.6 KV supply to 3.3 KV. | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 3.6334 | 1.9509 | 1.9509 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Supply & installation of Total 12 nos. passenger elevators at `D’ & `E’ type quarters & administrative building of Paras TPS | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 3.15 | 1.6426 | 1.6426 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Ash Handling Plant augmentation scheme at Paras TPS Unit 3 & 4 | MERC/TECH 1/CAPEX/20142015/01160 | 2014-11-17 | 38.0989 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Ash Handling Plant augmentation scheme at Paras TPS Unit 3 & 4 | MERC/TECH 1/CAPEX/20142015/01160 | 2014-11-17 | 34.6889 | 58.676 | 44.7505 | 13.9255 | 2.35 | 13.9255 |  |  | 13.9255 | 2.35 | 0 | 13.9255
0 | IDC | MERC/TECH 1/CAPEX/20142015/01160 | 2014-11-17 | 3.41 | 0.99854 | 0 | 0.99854 | 0 | 0.99854 |  |  | 0.99854 | 0 | 0.99854 | 0
3 | 3rd raising of Ash bund from TBL 273.63 mtr. to 276.63 mtr. with construction of masonry dam | MERC/MSPGCL/CAPEX/20142015/01648 | 2015-02-26 | 9.2104 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | 3rd raising of Ash bund from TBL 273.63 mtr. to 276.63 mtr. with construction of masonry dam | MERC/MSPGCL/CAPEX/20142015/01648 | 2015-02-26 | 8.2519 | 3.3121 | 3.3121 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/CAPEX/20142015/01648 | 2015-02-26 | 0.95855 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Various schemes related to CHP Improvement and Stack Management & Coal Mill Performance Improvement schemes | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 17.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Procurement of apron feeder system, pan & chain Assembly (2 no.’s) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 7.44 | 7.521 | 7.521 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Procurement of Assembly of Impact Crusher complete set with Beater Arm & Head.(1 no.) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.57 | 1.6013 | 1.6013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.3 | Procurement of Slewing Bearing of Stacker Reclaimer. (1 no.) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.45 | 1.4676 | 1.4676 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.4 | Capacity Enhancement of Wagon Tippler at Old CHP. | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 2.86 | 2.9502 | 2.9502 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.5 | Procurement of Bulldozer BD-155 for CHP(1 no.) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.7 | 2.1022 | 2.1022 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.6 | Procurement of Girth Gear and Pinion for BBD 4772 coal mills of 250 MW (1 set) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.6 | 1.6943 | 1.6943 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Procurement of Two Cartridge assembly for Boiler Feed Pump (Type: FK-3B-40) of 250MW Set | MERC/MSPGCL/CAPEX/20162017/04228 | 2017-09-22 | 13.88 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Procurement of Two Cartridge assembly for Boiler Feed Pump (Type: FK-3B-40) of 250MW Set | MERC/MSPGCL/CAPEX/20162017/04228 | 2017-09-22 | 13.88 | 14.0416 | 14.0416 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Replacement of battery bank set, replacement of two complete set of air pre-heater baskets & coal compartment assemblies for 250MW Unit 4 at Paras TPS | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 10.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Replacement of battery bank set to enhance process reliability of 250 MW Unit-4 at Paras TPS. | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 7.54 | 8.4214 | 8.4214 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.2 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-4, Paras TPS. | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 1.78 | 2.45 | 2.45 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.3 | Procurement & Replacement of Coal Compartment Assemblies Baskets at 250 MW Unit-4, Paras TPS. | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 0.75 | 0.56974 | 0.56974 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 0.04 | 0.25586 | 0.25786 | -0.002001 | 0 | 0 |  |  | 0 | -0.002001 | 0 | 0
7 | Procurement & Replacement of complete set of Economizer and LTSH upper & lower coils at Unit-3, Paras TPS | MERC/CAPEX/2019-2020/2 | 2019-05-24 | 10.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Replacement of complete set of economizer (upper & lower) coil assemblies & LTSH (upper & lower) coil assemblies for Unit-3. | MERC/CAPEX/2019-2020/2 | 2019-05-24 | 10.6 | 8.8 | 0 | 8.8 | 0 | - |  |  | 0 | 8.8 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/2 | 2019-05-24 | 0.22 | 0.96092 | 0 | 0.96092 | 0.87362 | 0 |  |  | 0 | 1.8345 | 0 | 0
8 | HMI (Human Machine Interface) up gradation of DCS UNIT-3 & 4, WTP (Water Treatment Plant unit-3 & 4 combined PLC system) & AHP (Ash Handling Plant Unit-3 & 4 PLC System), Procurement of girth gear & pinion for optimum availability of auxiliary at Paras TPS | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 11.14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Up-gradation of Existing Max-DNA System (HMI) at Paras TPS (U# 3 & 4). | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 7.12 | 0 | 0 | 0 | 8.4417 | 0 |  |  | 0 | 8.4417 | 0 | 0
8.2 | Up-gradation of GE IP (GE-Fanuc) make PLC system (HMI) installed at WTP at Paras TPS (Combined for U# 3 & 4). | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0.38 | 0.36789 | 0.36789 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.3 | Up-gradation of GE IP (GE-Fanuc) make PLC system (HMI) installed at AHP Unit - 4 at Paras TPS. | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0.48 | 0.45873 | 0.45873 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.4 | Up-gradation of Existing Schneider make PLC (HMI + PLC hardware) installed at AHP Unit - 3 at Paras TPS. | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0.9 | 0.7788 | 0 | 0.7788 | 0 | 0 |  |  | 0 | 0.7788 | 0 | 0
8.5 | Procurement & installation of Girth Gear & Pinion for coal mill BBD-4772. | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 2.26 | 2.1171 | 2.1171 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0 | 0 | 0 | 0 | 0.45004 | 0 |  |  | 0 | 0.45004 | 0 | 0
9 | Complete Track Renewal at Paras TPS | MERC/CAPEX/2019-2020/479 | 2019-08-02 | 12.77 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Complete Track Renewal at Paras TPS | MERC/CAPEX/2019-2020/479 | 2019-08-02 | 12.05 | 0 | 0 | 0 | 7.5378 | 0 |  |  | 0 | 7.5378 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/479 | 2019-08-02 | 0.72 | 0 | 0 | 0 | 0.078332 | 0 |  |  | 0 | 0.078332 | 0 | 0
10 | Procurement & Replacement of water wall panels in Unit#4 & Installation of VFD to existing eddy current drive driven coal feeders at 2x250 MW at Paras TPS | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 12.72 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Replacement of water wall panel in Unit-4 Boiler at 2 X 250 MW, PTPS | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 6.49 | 2.7423 | 0 | 2.7423 | 0 | 0 |  |  | 0 | 2.7423 | 0 | 0
10.2 | Installation of VFD with controller over existing eddy current drives with controller at 2 X 250 MW, PTPS. | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 6.23 | 6.1732 | 0 | 6.1732 | 0 | 0 |  |  | 0 | 6.1732 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 0 | 0 | 0 | 0 | 1.0135 | 0 |  |  | 0 | 1.0135 | 0 | 0
11 | Reinforcement & Capacity Enhancement of Old CHP Coal Conveyor Belt Structure from (200 TPH to 360 TPH) at old CHP Paras TPS & Procurement of One No. of Bulldozer & Diesel Hydraulic Locomotive at Paras TPS | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 12.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Capacity Enhancement of Old CHP Conveyor belt from 200 TPH to 360 TPH at Old CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 2.94 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Reinforcement of Belt Conveyor structure at Old CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 2.66 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.3 | Procurement of Bulldozer at CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 2.31 | 2.4909 | 2.4909 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.4 | Procurement of Diesel Hydraulic Locomotive at CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 3.6 | 3.057 | 3.057 | 0 | 0.16377 | 0.16377 |  |  | 0.16377 | 0 | 0.16377 | 0
0 | IDC | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 0.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Flue Gas Desulpherization (FGD) System for Paras Unit No. 3 & 4 | MERC/CAPEX/2020-2021/WFH/SBR/42 | 2020-12-14 | 376.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Flue Gas Desulpherization (FGD) System for Paras Unit No. 3 & 4 | MERC/CAPEX/2020-2021/WFH/SBR/42 | 2020-12-14 | 347.02 | 20.35 | 0 | 20.35 | 94.8887 | 0 |  |  | 0 | 115.2387 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/42 | 2020-12-14 | 29.04 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Procurement & Installation of complete assembly of Elecon make Gear Boxes, Wagon Tippler Assembly; Design, Supply, Installation, Commissioning & Successful Trial of Link Conveyor from Stackyard to C-2 Conveyor Belt at CHP; Procurement of Bucket Wheel of Stacker Reclaimer for CHP at Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 54.98 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Procurement & Installation of complete assembly of Elecon make Gear Boxes, Wagon Tippler Assembly; Design, Supply, Installation, Commissioning & Successful Trial of Link Conveyor from Stackyard to C-2 Conveyor Belt at CHP; Procurement of Bucket Wheel of Stacker Reclaimer for CHP at Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 32.78 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Procurement of Wagon Tippler Assembly & Installation of the same at CHP at Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 13.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.3 | Design, supply, installation, commissioning & successful trial of Link Conveyor from Stackyard to C-2 conveyor belt at CHP, Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 5.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.4 | Procurement of bucket wheel of stacker reclaimer for CHP 250MW Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 1.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 1.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 3.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.6 | Paras: Procurement of HT Motors(CEP/ACW Motors-I Phase and CW/CHP Motors-II Phase)for U-3&4 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 3.6 | 2.0958 | 2.0958 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 1.235 | 1.235 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.1 | PARAS(U-3 & 4) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 3.7536 | 3.7536 | 0 | 0.092 | 0.092 |  |  | 0.092 | 0 | 0.092 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 2.0276 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.1 | Paras TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 2.0276 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender at Paras TPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 2.9191 | 2.9191 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.2 | Normal Multipurpose Fire Tender at Paras TPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.0768 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.1 | TPS Paras | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.0768 | 1.6142 | 1.6142 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 12 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 12.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Enhancing process reliability at U-3 & U-4 at 2X250MW Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete set of Economiser (upper & lower) coil assemblies & LTSH (upper & lower) coil assemblies in Unit-4 (250mw) at Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & installation of complete discharge assembly of coal mill BBD 4772 In Unit-3&4 at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, replacement, erection and installation of foundation deck spring of coal mill BBD 4772 for Unit-3&4 at 250 MW at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of Coal Compartment Assemblies at 250 MW for Unit-3&4, Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of Girth gear and pinion Assemblies at 250 MW Unit-3,4, Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of Coal Mill drive shaft Assemblies at 250 MW Unit-3&4 Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of Air Pre Heater speed reducer gear box set of internals (assembly) for Unit-3&4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of foundation deck spring assembly (vibration isolation system) for ID fan for Unit 3&4 at Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of CW Pump module with mandatory spares for TM section | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Ash Evacuation System Rehabilitation and improvement of performance & efficiency of Ash Handling System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of old 300NB ash slurry disposal pipeline with new 300NB MSERW pipeline from slurry pump house to surface drain pump house at Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of old 200nb bottom ash, coarse ash, fly ash conveying pipeline with new 200 NB MSERW pipeline from ash hoppers to slurry tank & SILO AT PTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of complete assembly of air compressors (T-BTD-JM (4NOS) AND T-BD-QL (6NOS.)) in ash evacuation system in AHP, Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of complete assembly of SAM make ar-150/510 Pumps (9 nos) for replacement of ash slurry pumps of bottom ash slurry disposal from slurry tank to ash bund in slurry pump house. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of complete assembly of SAM MAKE ZM-II 530/03 (4 NOS) for replacement of HP pumps of bottom ash & coarse ash evacuation from BA/CA hoppers to slurry tank in ash water pump house. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of major internal assemblies of weir make GEHO pumps installed at AHP, Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of critical transmission drive systems and fluid couplings internal assemblies for slurry pumps and silo HCSD system installed at AHP, Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Augmentaion/Modification of U-3 & U-4 ESP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Restoration of ESP Fields of Unit- 3 & 4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Performance & Capacity enhancement of Ash handling plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of existing ash slurry disposal pump assembly by higher efficient pump assembly in AHP of Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of higher capacity vacuum pumps along with motors to improve availability & performance of fly ash system of AHP Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Modification & Replacement of air drier at AHP Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of existing HT Motors by energy efficient HT Motors In AHP of Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of ash handling plant auxiliaries & systems of Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of DRC Pipeline of fly ash evacuation system of AHP Paras for Availability improvement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of DRC Pipeline of fly ash evacuation system of AHP Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Structure strengthening of AHP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Work of anticorrosive Painting & Structure strengthening of Ash Handling Plant structures | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | U-3 Boiler Effyciency & Performance improvement schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CAVT & CFD for unit-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of sky climber assembly for Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of PA fan NDV22 BAB2 rotor assembly with impeller and cone & blade assembly of IGV with rod end assly for IGV control for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement Dampers, shutoff gate assemblies for series 5,6,7 & 8 dampers, ID fan inlet gate, APH flue gas dampers I/L & O/L, APH PA I/L & O/L dampers, APH SA I/L & O/L dampers along with actuators, SADC dampers at wind box with actuators for unit-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of critical high pressure valves, safety valves & control valves for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and Replacement of Thermal Insulation of Boiler, Ducts & Steam Pipelines for unit-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement and replacement of HP and B&S Lub oil pumps of coal mills BBD-4772 installed at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete Coal compartment assly for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete APH baskets, HE & CE sector plate, diapharm plate, rotor spool piece, grating assly, all type seals, rack pinion for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete set of Final super heater coil assembly for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete rotor assembly of FD fan including shaft with brg assly, impeller with oil hydraulic blade adjustment device with blades & coupling for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | U-3 & U-4 Boiler Effyciency, Performance & reliability improvement schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of Coal compartment assly for unit-4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and Replacement of Thermal Insulation of Boiler, Ducts & Steam Pipelines for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of critical high pressure valves, safety valves & control valves for unit-4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CAVT & CFD for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement Dampers, shutoff gate assemblies for series 5,6,7 & 8 dampers, ID fan inlet gate, APH flue gas dampers I/L & O/L, APH PA I/L & O/L dampers, APH SA I/L & O/L dampers along with actuators, SADC dampers at wind box with actuators for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete seal air fan assembly of coal mill BBD-4772 (without Motor) installed at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete set of Final super heater coil assembly for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete Coal compartment assly for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete APH baskets, HE & CE sector plate, diapharm plate, rotor spool piece, grating assly, all type seals, rack pinion for unit-4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete Coal compartment assly for unit-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete set of Re-heater coil (HRH & CRH) assembly for unit-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | ODP plant Process reliability improvement schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping of WT Plant Auxilliaries. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation of NDCT FILL at 2X250MW Units, Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, engineering, manufacturing, supply , erection and commissioning of degasser unit at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Performance improvement of compressors, compressored air drier system & Modification in Air ventilation system at 2x250MW Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping, modification of outdoor ducting of Air ventilation system at 2X250 MW, Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Performance improvement of compressors in Unit No.3, Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation of Compressed Air Refrigerated Dryer System for 2X250MW Unit, Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of LP Turbine blades, control fluid pump, AOP, JOP & HP valves for Turbine & its Auxiliaries efficiency improvement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Control Fluid Pumps & AOP of 250MW Unit No. 3 & 4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Moving blades for LPT-2L, 2R, 3L, 3R | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of valves – Main Steam Valves, Extraction Valves, BFP Recirculation Valves, etc. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Various schemes for reliability & performance improvement of Electrical & Control system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Water Flow monitoring system of various Location flowmeter at U3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of HMI and PLC hardware of Emerson (Former GE IP) make PLC system installed at Main Plant compressor Unit-4(PLC hardware and HMI), Condensate Polishing Unit Unit-3&4(HMI and PLC hardware), Pre-Treatment Plant Unit-4(HMI and PLC hardware) Water Treatment Plant (PLC hardware Unit-3&4) Ash Handling Plant Unit-4(PLC hardware), at Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Vibration Monitoring System server make Baker & Hughes (Former Bently Nevada) installed at Unit-3&4 Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping and Upgradation of PLC hardware of ABB make Online Condenser Tube Cleaning System installed at Unit-3&4 Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of carbon monoxide system in Air Preheater flue gas path at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, erection, commissioning and testing of 24 V 2X2250Ah, 360V 650AH UPS main plant, 360V 100Ah AHP UPS, 220V 125 Ah RWPH Battery at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of existing FBTS sytem installed at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement and Installation of Aviation Obstruction lighting system of Chimney and Cooling Towers at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Schemes related to Reduction in auxiliary Power consumption and upgradation of Valves & Instruments of C&I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation and Modification of Colony Electric Supply System to improve availability and reliability of supply system at Paras TPS colony | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply installation of VFD to CEP motors installed at paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Mid life overhauling of GCB installed at Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, installation testig and comissioning of VFD to PA fan motoras installed at Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of ID fan VFD installed at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1-Upgradation of all pneumatic control valve with smart positioner at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2-Upgradation of HFO mass flow meters at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3-Upgradation of O2 measurement system in Air Preheater inlet /outlet flue gas path and chimney inlet path at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-4-Upgradation of Steam Leak Detecting BHELSONIC system at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Various Civil schemes for Paras TPS Colony | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Attendning internal leakages of residential bulding in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing Terrace waterproofing to various buildings in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing and laying M.S. pipe line from new STP to WTP at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Water Supply GI Pipe line in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing of Colony Internal roads by BT at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing alluminium window to NF,NE,ND & Repairing of existing alluminium window and cupboard of resendial buildings in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing External Painting to Resenditial buildings in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Hospital Bulding in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Community Hall in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Development of Play Ground with Stage in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Beutification of colony area by providing Gardens and plantation in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of drain along internal roads in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Various Civil schemes related to Plant area of Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing waterproofing to terrace of various buildings in plant area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Attedning internal leakages and modification of Toilets in Plant area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting and carben rapping of cooling tower coloumn at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Attendning internal leakages of Parasdeep building along with renovatation of Toilets at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of water supply pipe lines in plant area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing External Painting to various buildings in plant area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Walk Way from Plant Gate to Service Building at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing & fixing modular kitchen (Trolleys) in B Type, CM Type, DM Type and EM Type quarters at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of drain with Footpath from CE Bunglow to Main Road at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of drain with Footpath from colony gate to Chummery Building at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing Internal Painting to Resenditial buildings in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation of Entrance road from T point to Colony Gate at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing of Plant Internal roads by BT at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IB recommendation at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | “Construction of RCC Compound wall as per IB recommendation at Paras TPS.” | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | “Construction of Watch towers along periphery compound wall as per IB recommendation at TPS Paras.” | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at 2 x 250 MW Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at 2 x 250 MW Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FGMO related Capex scheme | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FGMO related Capex scheme | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Covid-19 Pandemic Related Work | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Medical Oxygen Gen. & Bottling Plant | N.A. | - | 0 | 2.6741 | 2.6741 | 0 | 0 | 0 |  |  | 0 | 0
0 | Empty Std size Medical Gr. Oxygen Cyl. | N.A. | - | 0 | 0.41133 | 0.41133 | 0 | 0 | 0 |  |  | 0 | 0
0 | Oxy Installation&Commissioning of Plant | N.A. | - | 0 | 0.079772 | 0.079772 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Asset Transfer from Paras Project | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Boiler Plant and Equipment Single Drum | N.A. | - | 0 | 4.9843 | 4.9843 | 0 | 0 | 0 |  |  | 0 | 0
0 | LAND | N.A. | - | 0 | 15.3988 | 15.3988 | 0 | 8.4063 | 8.4063 |  |  | 8.4063 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Installation of portable crusher alongwith conveying system at 250 MW CHP, Paras TPS.-(CHP) | N.A. | - | 0 | 1.9889 | 1.9889 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing & Applying Epoxy Painting upto all height to structural steel work in power house area at TPS, Paras-(CIVIL) | N.A. | - | 0 | 5.6803 | 5.6803 | 0 | 0 | 0 |  |  | 0 | 0
0 | Material Handling Equipments | 0 | - | 0 | 0.033747 | 0.033747 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme for supply, erection, commissioning & testing of 7.2 KV SF6 contactor for retrofitting of existing BHEL make VM-12 type 6.6 KV HT circuit breakers of CHP Paras TPS.-(CHP) | N.A. | - | 0 | 2.2053 | 2.2053 | 0 | 0 | 0 |  |  | 0 | 0
0 | SWAS Lab improvement -(C&I) | N.A. | - | 0 | 2.2951 | 2.2951 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, supply, installation and commissioning of High performance energy chain system for Side Arm Charger at CHP 2 X 250 MW Unit 3 & 4 -(CHP) | N.A. | - | 0 | 1.0499 | 1.0499 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Manufacturing, supply, fabricate & erection of coal chutes with extra life weir reistatnce plates -(CHP) | N.A. | - | 0 | 2.3522 | 2.3522 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement and installation of set of internals of reducer gear box of coall mill BBD4772 @ Paras TPS -(BM) | N.A. | - | 0 | 0 | 0 | 0 | 1.788 | 1.788 |  |  | 1.788 | 0
0 | NON DPR scheme of procurement and installation of spares of non standard gridflex and gearflex couplings for coal mill BBD 4772 at Paras TPS 2x250MW -(BM) | N.A. | - | 0 | 0 | 0 | 0 | 0.88434 | 0.60584 |  |  | 0.60584 | 0.27849
0 | HO Non-DPR-Procurement of ABC powder Type & Foam type composite Fire Extnguisher for Paras TPS | N.A. | - | 0 | 0 | 0 | 0 | 0.5712 | 0.5712 |  |  | 0.5712 | 0
0 | Supply & replacement of APH baskets at Unit-3 | N.A. | - | 0 | 0 | 0 | 0 | 3.1799 | 0 |  |  | 0 | 3.1799
0 | Battery Bank 220VDC , 2140Ah for Unit -3 | N.A. | - | 0 | 0 | 0 | 0 | 5.83 | 0 |  |  | 0 | 5.83
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | General Assets | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Furniture & Fixtures | N.A. | - | 0 | 0.65535 | 0.65535 | 0 | 0.016874 | 0.016874 |  |  | 0.016874 | 0
0 | Office Equipment | N.A. | - | 0 | 1.9996 | 1.9996 | 0 | 0.082568 | 0.082568 |  |  | 0.082568 | 0
0 | RCC Approach Road for CHP at Paras TPS | N.A. | - | 0 | 1.7158 | 1.7158 | 0 | 0.076522 | 0.076522 |  |  | 0.076522 | 0
0 | Vehicles | N.A. | - | 0 | 0.34653 | 0.34653 | 0 | 0 | 0 |  |  | 0 | 0
0 | I.T. Equipment | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Building | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 213.8124 | 159.0851 | 54.7272 | 136.7251 | 26.7271 | 0 | 0 | 26.7271 | 164.7253
FY 2024-25
a) DPR Schemes
(i) Submitted to MERC
1 | Power supply arrangement at colony & separate 25 KV OHE supply feeding arrangement to BESG siding & provision of Passenger elevators | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 7.1549 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Provision of separate 25 KV OHE supply feeding arrangement to BESG siding at Paras TPS | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 0.3715 | 0.37148 | 0.37148 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | Arrangement of power supply for Paras TPS colony from 250 MW units with stepping down 6.6 KV supply to 3.3 KV. | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 3.6334 | 1.9509 | 1.9509 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Supply & installation of Total 12 nos. passenger elevators at `D’ & `E’ type quarters & administrative building of Paras TPS | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 3.15 | 1.6426 | 1.6426 | 0 | 0.13204 | 0.13204 |  |  | 0.13204 | 0 | 0.13204 | 0
2 | Ash Handling Plant augmentation scheme at Paras TPS Unit 3 & 4 | MERC/TECH 1/CAPEX/20142015/01160 | 2014-11-17 | 38.0989 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Ash Handling Plant augmentation scheme at Paras TPS Unit 3 & 4 | MERC/TECH 1/CAPEX/20142015/01160 | 2014-11-17 | 34.6889 | 61.026 | 58.676 | 2.35 | 2.35 | 2.3525 |  |  | 2.3525 | 2.3475 | 0 | 2.3525
0 | IDC | MERC/TECH 1/CAPEX/20142015/01160 | 2014-11-17 | 3.41 | 0.99854 | 0.99854 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | 3rd raising of Ash bund from TBL 273.63 mtr. to 276.63 mtr. with construction of masonry dam | MERC/MSPGCL/CAPEX/20142015/01648 | 2015-02-26 | 9.2104 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | 3rd raising of Ash bund from TBL 273.63 mtr. to 276.63 mtr. with construction of masonry dam | MERC/MSPGCL/CAPEX/20142015/01648 | 2015-02-26 | 8.2519 | 3.3121 | 3.3121 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/CAPEX/20142015/01648 | 2015-02-26 | 0.95855 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Various schemes related to CHP Improvement and Stack Management & Coal Mill Performance Improvement schemes | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 17.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Procurement of apron feeder system, pan & chain Assembly (2 no.’s) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 7.44 | 7.521 | 7.521 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Procurement of Assembly of Impact Crusher complete set with Beater Arm & Head.(1 no.) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.57 | 1.6013 | 1.6013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.3 | Procurement of Slewing Bearing of Stacker Reclaimer. (1 no.) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.45 | 1.4676 | 1.4676 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.4 | Capacity Enhancement of Wagon Tippler at Old CHP. | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 2.86 | 2.9502 | 2.9502 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.5 | Procurement of Bulldozer BD-155 for CHP(1 no.) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.7 | 2.1022 | 2.1022 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.6 | Procurement of Girth Gear and Pinion for BBD 4772 coal mills of 250 MW (1 set) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.6 | 1.6943 | 1.6943 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Procurement of Two Cartridge assembly for Boiler Feed Pump (Type: FK-3B-40) of 250MW Set | MERC/MSPGCL/CAPEX/20162017/04228 | 2017-09-22 | 13.88 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Procurement of Two Cartridge assembly for Boiler Feed Pump (Type: FK-3B-40) of 250MW Set | MERC/MSPGCL/CAPEX/20162017/04228 | 2017-09-22 | 13.88 | 14.0416 | 14.0416 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Replacement of battery bank set, replacement of two complete set of air pre-heater baskets & coal compartment assemblies for 250MW Unit 4 at Paras TPS | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 10.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Replacement of battery bank set to enhance process reliability of 250 MW Unit-4 at Paras TPS. | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 7.54 | 8.4214 | 8.4214 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.2 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-4, Paras TPS. | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 1.78 | 2.45 | 2.45 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.3 | Procurement & Replacement of Coal Compartment Assemblies Baskets at 250 MW Unit-4, Paras TPS. | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 0.75 | 0.56974 | 0.56974 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 0.04 | 0.25586 | 0.25786 | -0.002001 | 0 | 0 |  |  | 0 | -0.002001 | 0 | 0
7 | Procurement & Replacement of complete set of Economizer and LTSH upper & lower coils at Unit-3, Paras TPS | MERC/CAPEX/2019-2020/2 | 2019-05-24 | 10.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Replacement of complete set of economizer (upper & lower) coil assemblies & LTSH (upper & lower) coil assemblies for Unit-3. | MERC/CAPEX/2019-2020/2 | 2019-05-24 | 10.6 | 8.8 | 0 | 8.8 | 3.0971 | 11.8971 |  |  | 11.8971 | 0 | 10.6 | 1.2971
0 | IDC | MERC/CAPEX/2019-2020/2 | 2019-05-24 | 0.22 | 1.8345 | 0 | 1.8345 | 0 | 1.8345 |  |  | 1.8345 | 0 | 0.22 | 1.6145
8 | HMI (Human Machine Interface) up gradation of DCS UNIT-3 & 4, WTP (Water Treatment Plant unit-3 & 4 combined PLC system) & AHP (Ash Handling Plant Unit-3 & 4 PLC System), Procurement of girth gear & pinion for optimum availability of auxiliary at Paras TPS | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 11.14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Up-gradation of Existing Max-DNA System (HMI) at Paras TPS (U# 3 & 4). | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 7.12 | 8.4417 | 0 | 8.4417 | 0.39472 | 8.8364 |  |  | 8.8364 | 0 | 7.12 | 1.7164
8.2 | Up-gradation of GE IP (GE-Fanuc) make PLC system (HMI) installed at WTP at Paras TPS (Combined for U# 3 & 4). | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0.38 | 0.36789 | 0.36789 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.3 | Up-gradation of GE IP (GE-Fanuc) make PLC system (HMI) installed at AHP Unit - 4 at Paras TPS. | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0.48 | 0.45873 | 0.45873 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.4 | Up-gradation of Existing Schneider make PLC (HMI + PLC hardware) installed at AHP Unit - 3 at Paras TPS. | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0.9 | 0.7788 | 0 | 0.7788 | 0.10384 | 0.88264 |  |  | 0.88264 | 0 | 0.88264 | 0
8.5 | Procurement & installation of Girth Gear & Pinion for coal mill BBD-4772. | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 2.26 | 2.1171 | 2.1171 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0 | 0.45004 | 0 | 0.45004 | 0 | 0.45004 |  |  | 0.45004 | 0 | 0 | 0.45004
9 | Complete Track Renewal at Paras TPS | MERC/CAPEX/2019-2020/479 | 2019-08-02 | 12.77 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Complete Track Renewal at Paras TPS | MERC/CAPEX/2019-2020/479 | 2019-08-02 | 12.05 | 7.5378 | 0 | 7.5378 | 8.858 | 16.3958 |  |  | 16.3958 | 0 | 12.05 | 4.3458
0 | IDC | MERC/CAPEX/2019-2020/479 | 2019-08-02 | 0.72 | 0.078332 | 0 | 0.078332 | 0 | 0.078332 |  |  | 0.078332 | 0 | 0.078332 | 0
10 | Procurement & Replacement of water wall panels in Unit#4 & Installation of VFD to existing eddy current drive driven coal feeders at 2x250 MW at Paras TPS | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 12.72 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Replacement of water wall panel in Unit-4 Boiler at 2 X 250 MW, PTPS | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 6.49 | 2.7423 | 0 | 2.7423 | 0 | 0 |  |  | 0 | 2.7423 | 0 | 0
10.2 | Installation of VFD with controller over existing eddy current drives with controller at 2 X 250 MW, PTPS. | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 6.23 | 6.1732 | 0 | 6.1732 | 0.29396 | 6.4672 |  |  | 6.4672 | 0 | 6.23 | 0.23716
0 | IDC | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 0 | 1.0135 | 0 | 1.0135 | 0 | 1.0135 |  |  | 1.0135 | 0 | 0 | 1.0135
11 | Reinforcement & Capacity Enhancement of Old CHP Coal Conveyor Belt Structure from (200 TPH to 360 TPH) at old CHP Paras TPS & Procurement of One No. of Bulldozer & Diesel Hydraulic Locomotive at Paras TPS | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 12.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Capacity Enhancement of Old CHP Conveyor belt from 200 TPH to 360 TPH at Old CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 2.94 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Reinforcement of Belt Conveyor structure at Old CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 2.66 | 0 | 0 | 0 | 2.9137 | 2.9137 |  |  | 2.9137 | 0 | 2.66 | 0.25369
11.3 | Procurement of Bulldozer at CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 2.31 | 2.4909 | 2.4909 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.4 | Procurement of Diesel Hydraulic Locomotive at CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 3.6 | 3.2208 | 3.2208 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 0.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Flue Gas Desulpherization (FGD) System for Paras Unit No. 3 & 4 | MERC/CAPEX/2020-2021/WFH/SBR/42 | 2020-12-14 | 376.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Flue Gas Desulpherization (FGD) System for Paras Unit No. 3 & 4 | MERC/CAPEX/2020-2021/WFH/SBR/42 | 2020-12-14 | 347.02 | 115.2387 | 0 | 115.2387 | 244 | 211.99 |  |  | 211.99 | 147.2487 | 211.99 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/42 | 2020-12-14 | 29.04 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Procurement & Installation of complete assembly of Elecon make Gear Boxes, Wagon Tippler Assembly; Design, Supply, Installation, Commissioning & Successful Trial of Link Conveyor from Stackyard to C-2 Conveyor Belt at CHP; Procurement of Bucket Wheel of Stacker Reclaimer for CHP at Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 54.98 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Procurement & Installation of complete assembly of Elecon make Gear Boxes, Wagon Tippler Assembly; Design, Supply, Installation, Commissioning & Successful Trial of Link Conveyor from Stackyard to C-2 Conveyor Belt at CHP; Procurement of Bucket Wheel of Stacker Reclaimer for CHP at Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 32.78 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Procurement of Wagon Tippler Assembly & Installation of the same at CHP at Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 13.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.3 | Design, supply, installation, commissioning & successful trial of Link Conveyor from Stackyard to C-2 conveyor belt at CHP, Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 5.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.4 | Procurement of bucket wheel of stacker reclaimer for CHP 250MW Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 1.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 1.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 3.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.6 | Paras: Procurement of HT Motors(CEP/ACW Motors-I Phase and CW/CHP Motors-II Phase)for U-3&4 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 3.6 | 2.0958 | 2.0958 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 1.235 | 1.235 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.1 | PARAS(U-3 & 4) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 3.8456 | 3.8456 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 2.0276 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.1 | Paras TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 2.0276 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender at Paras TPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 2.9191 | 2.9191 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.2 | Normal Multipurpose Fire Tender at Paras TPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.0768 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.1 | TPS Paras | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.0768 | 1.6142 | 1.6142 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 12 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 12.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Enhancing process reliability at U-3 & U-4 at 2X250MW Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete set of Economiser (upper & lower) coil assemblies & LTSH (upper & lower) coil assemblies in Unit-4 (250mw) at Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & installation of complete discharge assembly of coal mill BBD 4772 In Unit-3&4 at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, replacement, erection and installation of foundation deck spring of coal mill BBD 4772 for Unit-3&4 at 250 MW at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of Coal Compartment Assemblies at 250 MW for Unit-3&4, Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of Girth gear and pinion Assemblies at 250 MW Unit-3,4, Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of Coal Mill drive shaft Assemblies at 250 MW Unit-3&4 Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of Air Pre Heater speed reducer gear box set of internals (assembly) for Unit-3&4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of foundation deck spring assembly (vibration isolation system) for ID fan for Unit 3&4 at Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of CW Pump module with mandatory spares for TM section | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Ash Evacuation System Rehabilitation and improvement of performance & efficiency of Ash Handling System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of old 300NB ash slurry disposal pipeline with new 300NB MSERW pipeline from slurry pump house to surface drain pump house at Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of old 200nb bottom ash, coarse ash, fly ash conveying pipeline with new 200 NB MSERW pipeline from ash hoppers to slurry tank & SILO AT PTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of complete assembly of air compressors (T-BTD-JM (4NOS) AND T-BD-QL (6NOS.)) in ash evacuation system in AHP, Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of complete assembly of SAM make ar-150/510 Pumps (9 nos) for replacement of ash slurry pumps of bottom ash slurry disposal from slurry tank to ash bund in slurry pump house. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of complete assembly of SAM MAKE ZM-II 530/03 (4 NOS) for replacement of HP pumps of bottom ash & coarse ash evacuation from BA/CA hoppers to slurry tank in ash water pump house. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of major internal assemblies of weir make GEHO pumps installed at AHP, Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of critical transmission drive systems and fluid couplings internal assemblies for slurry pumps and silo HCSD system installed at AHP, Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Augmentaion/Modification of U-3 & U-4 ESP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Restoration of ESP Fields of Unit- 3 & 4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Performance & Capacity enhancement of Ash handling plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of existing ash slurry disposal pump assembly by higher efficient pump assembly in AHP of Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of higher capacity vacuum pumps along with motors to improve availability & performance of fly ash system of AHP Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Modification & Replacement of air drier at AHP Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of existing HT Motors by energy efficient HT Motors In AHP of Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of ash handling plant auxiliaries & systems of Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of DRC Pipeline of fly ash evacuation system of AHP Paras for Availability improvement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of DRC Pipeline of fly ash evacuation system of AHP Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Structure strengthening of AHP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Work of anticorrosive Painting & Structure strengthening of Ash Handling Plant structures | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | U-3 Boiler Effyciency & Performance improvement schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CAVT & CFD for unit-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of sky climber assembly for Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of PA fan NDV22 BAB2 rotor assembly with impeller and cone & blade assembly of IGV with rod end assly for IGV control for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement Dampers, shutoff gate assemblies for series 5,6,7 & 8 dampers, ID fan inlet gate, APH flue gas dampers I/L & O/L, APH PA I/L & O/L dampers, APH SA I/L & O/L dampers along with actuators, SADC dampers at wind box with actuators for unit-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of critical high pressure valves, safety valves & control valves for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and Replacement of Thermal Insulation of Boiler, Ducts & Steam Pipelines for unit-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement and replacement of HP and B&S Lub oil pumps of coal mills BBD-4772 installed at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete Coal compartment assly for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete APH baskets, HE & CE sector plate, diapharm plate, rotor spool piece, grating assly, all type seals, rack pinion for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete set of Final super heater coil assembly for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete rotor assembly of FD fan including shaft with brg assly, impeller with oil hydraulic blade adjustment device with blades & coupling for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | U-3 & U-4 Boiler Effyciency, Performance & reliability improvement schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of Coal compartment assly for unit-4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and Replacement of Thermal Insulation of Boiler, Ducts & Steam Pipelines for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of critical high pressure valves, safety valves & control valves for unit-4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CAVT & CFD for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement Dampers, shutoff gate assemblies for series 5,6,7 & 8 dampers, ID fan inlet gate, APH flue gas dampers I/L & O/L, APH PA I/L & O/L dampers, APH SA I/L & O/L dampers along with actuators, SADC dampers at wind box with actuators for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete seal air fan assembly of coal mill BBD-4772 (without Motor) installed at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete set of Final super heater coil assembly for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete Coal compartment assly for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete APH baskets, HE & CE sector plate, diapharm plate, rotor spool piece, grating assly, all type seals, rack pinion for unit-4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete Coal compartment assly for unit-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete set of Re-heater coil (HRH & CRH) assembly for unit-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | ODP plant Process reliability improvement schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping of WT Plant Auxilliaries. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation of NDCT FILL at 2X250MW Units, Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, engineering, manufacturing, supply , erection and commissioning of degasser unit at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Performance improvement of compressors, compressored air drier system & Modification in Air ventilation system at 2x250MW Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping, modification of outdoor ducting of Air ventilation system at 2X250 MW, Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Performance improvement of compressors in Unit No.3, Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation of Compressed Air Refrigerated Dryer System for 2X250MW Unit, Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of LP Turbine blades, control fluid pump, AOP, JOP & HP valves for Turbine & its Auxiliaries efficiency improvement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Control Fluid Pumps & AOP of 250MW Unit No. 3 & 4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Moving blades for LPT-2L, 2R, 3L, 3R | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of valves – Main Steam Valves, Extraction Valves, BFP Recirculation Valves, etc. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Various schemes for reliability & performance improvement of Electrical & Control system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Water Flow monitoring system of various Location flowmeter at U3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of HMI and PLC hardware of Emerson (Former GE IP) make PLC system installed at Main Plant compressor Unit-4(PLC hardware and HMI), Condensate Polishing Unit Unit-3&4(HMI and PLC hardware), Pre-Treatment Plant Unit-4(HMI and PLC hardware) Water Treatment Plant (PLC hardware Unit-3&4) Ash Handling Plant Unit-4(PLC hardware), at Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Vibration Monitoring System server make Baker & Hughes (Former Bently Nevada) installed at Unit-3&4 Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping and Upgradation of PLC hardware of ABB make Online Condenser Tube Cleaning System installed at Unit-3&4 Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of carbon monoxide system in Air Preheater flue gas path at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, erection, commissioning and testing of 24 V 2X2250Ah, 360V 650AH UPS main plant, 360V 100Ah AHP UPS, 220V 125 Ah RWPH Battery at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of existing FBTS sytem installed at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement and Installation of Aviation Obstruction lighting system of Chimney and Cooling Towers at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Schemes related to Reduction in auxiliary Power consumption and upgradation of Valves & Instruments of C&I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation and Modification of Colony Electric Supply System to improve availability and reliability of supply system at Paras TPS colony | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply installation of VFD to CEP motors installed at paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Mid life overhauling of GCB installed at Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, installation testig and comissioning of VFD to PA fan motoras installed at Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of ID fan VFD installed at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1-Upgradation of all pneumatic control valve with smart positioner at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2-Upgradation of HFO mass flow meters at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3-Upgradation of O2 measurement system in Air Preheater inlet /outlet flue gas path and chimney inlet path at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-4-Upgradation of Steam Leak Detecting BHELSONIC system at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Various Civil schemes for Paras TPS Colony | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Attendning internal leakages of residential bulding in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing Terrace waterproofing to various buildings in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing and laying M.S. pipe line from new STP to WTP at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Water Supply GI Pipe line in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing of Colony Internal roads by BT at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing alluminium window to NF,NE,ND & Repairing of existing alluminium window and cupboard of resendial buildings in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing External Painting to Resenditial buildings in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Hospital Bulding in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Community Hall in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Development of Play Ground with Stage in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Beutification of colony area by providing Gardens and plantation in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of drain along internal roads in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Various Civil schemes related to Plant area of Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing waterproofing to terrace of various buildings in plant area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Attedning internal leakages and modification of Toilets in Plant area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting and carben rapping of cooling tower coloumn at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Attendning internal leakages of Parasdeep building along with renovatation of Toilets at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of water supply pipe lines in plant area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing External Painting to various buildings in plant area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Walk Way from Plant Gate to Service Building at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing & fixing modular kitchen (Trolleys) in B Type, CM Type, DM Type and EM Type quarters at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of drain with Footpath from CE Bunglow to Main Road at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of drain with Footpath from colony gate to Chummery Building at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing Internal Painting to Resenditial buildings in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation of Entrance road from T point to Colony Gate at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing of Plant Internal roads by BT at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IB recommendation at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | “Construction of RCC Compound wall as per IB recommendation at Paras TPS.” | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | “Construction of Watch towers along periphery compound wall as per IB recommendation at TPS Paras.” | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at 2 x 250 MW Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at 2 x 250 MW Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FGMO related Capex scheme | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FGMO related Capex scheme | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Covid-19 Pandemic Related Work | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Medical Oxygen Gen. & Bottling Plant | N.A. | - | 0 | 2.6741 | 2.6741 | 0 | 0 | 0 |  |  | 0 | 0
0 | Empty Std size Medical Gr. Oxygen Cyl. | N.A. | - | 0 | 0.41133 | 0.41133 | 0 | 0 | 0 |  |  | 0 | 0
0 | Oxy Installation&Commissioning of Plant | N.A. | - | 0 | 0.079772 | 0.079772 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Asset Transfer from Paras Project | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Boiler Plant and Equipment Single Drum | N.A. | - | 0 | 4.9843 | 4.9843 | 0 | 0 | 0 |  |  | 0 | 0
0 | LAND | N.A. | - | 0 | 23.8051 | 23.8051 | 0 | 0 | 10.5 |  |  | 10.5 | -10.5
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Installation of portable crusher alongwith conveying system at 250 MW CHP, Paras TPS.-(CHP) | N.A. | - | 0 | 1.9889 | 1.9889 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing & Applying Epoxy Painting upto all height to structural steel work in power house area at TPS, Paras-(CIVIL) | N.A. | - | 0 | 5.6803 | 5.6803 | 0 | 0 | 0 |  |  | 0 | 0
0 | Material Handling Equipments | 0 | - | 0 | 0.033747 | 0.033747 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme for supply, erection, commissioning & testing of 7.2 KV SF6 contactor for retrofitting of existing BHEL make VM-12 type 6.6 KV HT circuit breakers of CHP Paras TPS.-(CHP) | N.A. | - | 0 | 2.2053 | 2.2053 | 0 | 0.1652 | 0.1652 |  |  | 0.1652 | 0
0 | SWAS Lab improvement -(C&I) | N.A. | - | 0 | 2.2951 | 2.2951 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, supply, installation and commissioning of High performance energy chain system for Side Arm Charger at CHP 2 X 250 MW Unit 3 & 4 -(CHP) | N.A. | - | 0 | 1.0499 | 1.0499 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Manufacturing, supply, fabricate & erection of coal chutes with extra life weir reistatnce plates -(CHP) | N.A. | - | 0 | 2.3522 | 2.3522 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement and installation of set of internals of reducer gear box of coall mill BBD4772 @ Paras TPS -(BM) | N.A. | - | 0 | 1.788 | 1.788 | 0 | 0 | 0 |  |  | 0 | 0
0 | NON DPR scheme of procurement and installation of spares of non standard gridflex and gearflex couplings for coal mill BBD 4772 at Paras TPS 2x250MW -(BM) | N.A. | - | 0 | 0.88434 | 0.60584 | 0.27849 | 0.024426 | 0.30292 |  |  | 0.30292 | 0
0 | HO Non-DPR-Procurement of ABC powder Type & Foam type composite Fire Extnguisher for Paras TPS | N.A. | - | 0 | 0.5712 | 0.5712 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & replacement of APH baskets at Unit-3 | N.A. | - | 0 | 3.1799 | 0 | 3.1799 | 0.26786 | 3.45 |  |  | 3.45 | -0.0022658
0 | Battery Bank 220VDC , 2140Ah for Unit -3 | N.A. | - | 0 | 5.83 | 0 | 5.83 | 0 | 5.83 |  |  | 5.83 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | General Assets | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Furniture & Fixtures | N.A. | - | 0 | 0.67222 | 0.67222 | 0 | 0.043673 | 0.043673 |  |  | 0.043673 | 0
0 | Office Equipment | N.A. | - | 0 | 2.0822 | 2.0822 | 0 | 0.04328 | 0.04328 |  |  | 0.04328 | 0
0 | RCC Approach Road for CHP at Paras TPS | N.A. | - | 0 | 1.7924 | 1.7924 | 0 | 0 | 0 |  |  | 0 | 0
0 | Vehicles | N.A. | - | 0 | 0.34653 | 0.34653 | 0 | 0.4043 | 0.4043 |  |  | 0.4043 | 0
0 | I.T. Equipment | 0 | - | 0 | 0 | 0 | 0 | 0.54853 | 0.54853 |  |  | 0.54853 | 0
0 | Building | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 350.5375 | 185.8122 | 164.7253 | 263.6406 | 286.5317 | 0 | 0 | 286.5317 | 141.8342
FY 2025-26
a) DPR Schemes
(i) Submitted to MERC
1 | Power supply arrangement at colony & separate 25 KV OHE supply feeding arrangement to BESG siding & provision of Passenger elevators | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 7.1549 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Provision of separate 25 KV OHE supply feeding arrangement to BESG siding at Paras TPS | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 0.3715 | 0.37148 | 0.37148 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | Arrangement of power supply for Paras TPS colony from 250 MW units with stepping down 6.6 KV supply to 3.3 KV. | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 3.6334 | 1.9509 | 1.9509 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Supply & installation of Total 12 nos. passenger elevators at `D’ & `E’ type quarters & administrative building of Paras TPS | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 3.15 | 1.7746 | 1.7746 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Ash Handling Plant augmentation scheme at Paras TPS Unit 3 & 4 | MERC/TECH 1/CAPEX/20142015/01160 | 2014-11-17 | 38.0989 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Ash Handling Plant augmentation scheme at Paras TPS Unit 3 & 4 | MERC/TECH 1/CAPEX/20142015/01160 | 2014-11-17 | 34.6889 | 63.376 | 61.0285 | 2.3475 | 0 | 0 |  |  | 0 | 2.3475 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/01160 | 2014-11-17 | 3.41 | 0.99854 | 0.99854 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | 3rd raising of Ash bund from TBL 273.63 mtr. to 276.63 mtr. with construction of masonry dam | MERC/MSPGCL/CAPEX/20142015/01648 | 2015-02-26 | 9.2104 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | 3rd raising of Ash bund from TBL 273.63 mtr. to 276.63 mtr. with construction of masonry dam | MERC/MSPGCL/CAPEX/20142015/01648 | 2015-02-26 | 8.2519 | 3.3121 | 3.3121 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/CAPEX/20142015/01648 | 2015-02-26 | 0.95855 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Various schemes related to CHP Improvement and Stack Management & Coal Mill Performance Improvement schemes | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 17.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Procurement of apron feeder system, pan & chain Assembly (2 no.’s) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 7.44 | 7.521 | 7.521 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Procurement of Assembly of Impact Crusher complete set with Beater Arm & Head.(1 no.) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.57 | 1.6013 | 1.6013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.3 | Procurement of Slewing Bearing of Stacker Reclaimer. (1 no.) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.45 | 1.4676 | 1.4676 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.4 | Capacity Enhancement of Wagon Tippler at Old CHP. | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 2.86 | 2.9502 | 2.9502 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.5 | Procurement of Bulldozer BD-155 for CHP(1 no.) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.7 | 2.1022 | 2.1022 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.6 | Procurement of Girth Gear and Pinion for BBD 4772 coal mills of 250 MW (1 set) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.6 | 1.6943 | 1.6943 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Procurement of Two Cartridge assembly for Boiler Feed Pump (Type: FK-3B-40) of 250MW Set | MERC/MSPGCL/CAPEX/20162017/04228 | 2017-09-22 | 13.88 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Procurement of Two Cartridge assembly for Boiler Feed Pump (Type: FK-3B-40) of 250MW Set | MERC/MSPGCL/CAPEX/20162017/04228 | 2017-09-22 | 13.88 | 14.0416 | 14.0416 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Replacement of battery bank set, replacement of two complete set of air pre-heater baskets & coal compartment assemblies for 250MW Unit 4 at Paras TPS | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 10.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Replacement of battery bank set to enhance process reliability of 250 MW Unit-4 at Paras TPS. | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 7.54 | 8.4214 | 8.4214 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.2 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-4, Paras TPS. | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 1.78 | 2.45 | 2.45 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.3 | Procurement & Replacement of Coal Compartment Assemblies Baskets at 250 MW Unit-4, Paras TPS. | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 0.75 | 0.56974 | 0.56974 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 0.04 | 0.25586 | 0.25786 | -0.002001 | 0 | 0 |  |  | 0 | -0.002001 | 0 | 0
7 | Procurement & Replacement of complete set of Economizer and LTSH upper & lower coils at Unit-3, Paras TPS | MERC/CAPEX/2019-2020/2 | 2019-05-24 | 10.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Replacement of complete set of economizer (upper & lower) coil assemblies & LTSH (upper & lower) coil assemblies for Unit-3. | MERC/CAPEX/2019-2020/2 | 2019-05-24 | 10.6 | 11.8971 | 11.8971 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/2 | 2019-05-24 | 0.22 | 1.8345 | 1.8345 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | HMI (Human Machine Interface) up gradation of DCS UNIT-3 & 4, WTP (Water Treatment Plant unit-3 & 4 combined PLC system) & AHP (Ash Handling Plant Unit-3 & 4 PLC System), Procurement of girth gear & pinion for optimum availability of auxiliary at Paras TPS | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 11.14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Up-gradation of Existing Max-DNA System (HMI) at Paras TPS (U# 3 & 4). | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 7.12 | 8.8364 | 8.8364 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Up-gradation of GE IP (GE-Fanuc) make PLC system (HMI) installed at WTP at Paras TPS (Combined for U# 3 & 4). | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0.38 | 0.36789 | 0.36789 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.3 | Up-gradation of GE IP (GE-Fanuc) make PLC system (HMI) installed at AHP Unit - 4 at Paras TPS. | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0.48 | 0.45873 | 0.45873 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.4 | Up-gradation of Existing Schneider make PLC (HMI + PLC hardware) installed at AHP Unit - 3 at Paras TPS. | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0.9 | 0.88264 | 0.88264 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.5 | Procurement & installation of Girth Gear & Pinion for coal mill BBD-4772. | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 2.26 | 2.1171 | 2.1171 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0 | 0.45004 | 0.45004 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Complete Track Renewal at Paras TPS | MERC/CAPEX/2019-2020/479 | 2019-08-02 | 12.77 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Complete Track Renewal at Paras TPS | MERC/CAPEX/2019-2020/479 | 2019-08-02 | 12.05 | 16.3958 | 16.3958 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/479 | 2019-08-02 | 0.72 | 0.078332 | 0.078332 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Procurement & Replacement of water wall panels in Unit#4 & Installation of VFD to existing eddy current drive driven coal feeders at 2x250 MW at Paras TPS | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 12.72 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Replacement of water wall panel in Unit-4 Boiler at 2 X 250 MW, PTPS | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 6.49 | 2.7423 | 0 | 2.7423 | 0 | 6.2823 |  |  | 6.2823 | -3.54 | 6.2823 | 0
10.2 | Installation of VFD with controller over existing eddy current drives with controller at 2 X 250 MW, PTPS. | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 6.23 | 6.4672 | 6.4672 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 0 | 1.0135 | 1.0135 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Reinforcement & Capacity Enhancement of Old CHP Coal Conveyor Belt Structure from (200 TPH to 360 TPH) at old CHP Paras TPS & Procurement of One No. of Bulldozer & Diesel Hydraulic Locomotive at Paras TPS | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 12.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Capacity Enhancement of Old CHP Conveyor belt from 200 TPH to 360 TPH at Old CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 2.94 | 0 | 0 | 0 | 0 | 2.9382 |  |  | 2.9382 | -2.9382 | 2.9382 | 0
11.2 | Reinforcement of Belt Conveyor structure at Old CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 2.66 | 2.9137 | 2.9137 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.3 | Procurement of Bulldozer at CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 2.31 | 2.4909 | 2.4909 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.4 | Procurement of Diesel Hydraulic Locomotive at CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 3.6 | 3.2208 | 3.2208 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 0.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Flue Gas Desulpherization (FGD) System for Paras Unit No. 3 & 4 | MERC/CAPEX/2020-2021/WFH/SBR/42 | 2020-12-14 | 376.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Flue Gas Desulpherization (FGD) System for Paras Unit No. 3 & 4 | MERC/CAPEX/2020-2021/WFH/SBR/42 | 2020-12-14 | 347.02 | 359.2387 | 211.99 | 147.2487 | 119.3423 | 211.3 |  |  | 211.3 | 55.291 | 135.03 | 76.27
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/42 | 2020-12-14 | 29.04 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Procurement & Installation of complete assembly of Elecon make Gear Boxes, Wagon Tippler Assembly; Design, Supply, Installation, Commissioning & Successful Trial of Link Conveyor from Stackyard to C-2 Conveyor Belt at CHP; Procurement of Bucket Wheel of Stacker Reclaimer for CHP at Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 54.98 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Procurement & Installation of complete assembly of Elecon make Gear Boxes, Wagon Tippler Assembly; Design, Supply, Installation, Commissioning & Successful Trial of Link Conveyor from Stackyard to C-2 Conveyor Belt at CHP; Procurement of Bucket Wheel of Stacker Reclaimer for CHP at Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 32.78 | 0 | 0 | 0 | 11.88 | 11.88 |  |  | 11.88 | 0 | 11.88 | 0
13.2 | Procurement of Wagon Tippler Assembly & Installation of the same at CHP at Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 13.9 | 0 | 0 | 0 | 13.9 | 13.9 |  |  | 13.9 | 0
13.3 | Design, supply, installation, commissioning & successful trial of Link Conveyor from Stackyard to C-2 conveyor belt at CHP, Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 5.93 | 0 | 0 | 0 | 5.93 | 5.93 |  |  | 5.93 | 0
13.4 | Procurement of bucket wheel of stacker reclaimer for CHP 250MW Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 1.07 | 0 | 0 | 0 | 1.07 | 1.07 |  |  | 1.07 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 1.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 3.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.6 | Paras: Procurement of HT Motors(CEP/ACW Motors-I Phase and CW/CHP Motors-II Phase)for U-3&4 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 3.6 | 2.0958 | 2.0958 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 1.235 | 1.235 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.1 | PARAS(U-3 & 4) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 3.8456 | 3.8456 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 2.0276 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.1 | Paras TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 2.0276 | 0 | 0 | 0 | 0 | 2.31 |  |  | 2.31 | -2.31 | 2.0276 | 0.2824
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender at Paras TPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 2.9191 | 2.9191 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.2 | Normal Multipurpose Fire Tender at Paras TPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.0768 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.1 | TPS Paras | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.0768 | 1.6142 | 1.6142 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 12 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 12.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Enhancing process reliability at U-3 & U-4 at 2X250MW Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete set of Economiser (upper & lower) coil assemblies & LTSH (upper & lower) coil assemblies in Unit-4 (250mw) at Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 14.18 | 14.18 |  |  | 14.18 | 0
0 | Procurement & installation of complete discharge assembly of coal mill BBD 4772 In Unit-3&4 at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 22.51 | 22.51 |  |  | 22.51 | 0
0 | Supply, replacement, erection and installation of foundation deck spring of coal mill BBD 4772 for Unit-3&4 at 250 MW at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 3.36 | 3.36 |  |  | 3.36 | 0
0 | Procurement & Replacement of Coal Compartment Assemblies at 250 MW for Unit-3&4, Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 1.77 | 1.77 |  |  | 1.77 | 0
0 | Procurement & Replacement of Girth gear and pinion Assemblies at 250 MW Unit-3,4, Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 9.22 | 9.22 |  |  | 9.22 | 0
0 | Procurement & Replacement of Coal Mill drive shaft Assemblies at 250 MW Unit-3&4 Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 7.67 | 7.67 |  |  | 7.67 | 0
0 | Procurement & Replacement of Air Pre Heater speed reducer gear box set of internals (assembly) for Unit-3&4. | 0 | - | 0 | 0 | 0 | 0 | 1.33 | 1.33 |  |  | 1.33 | 0
0 | Procurement & Replacement of foundation deck spring assembly (vibration isolation system) for ID fan for Unit 3&4 at Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 2.31 | 2.31 |  |  | 2.31 | 0
0 | Procurement of CW Pump module with mandatory spares for TM section | 0 | - | 0 | 0 | 0 | 0 | 15.61 | 15.61 |  |  | 15.61 | 0
0 | DPR for Ash Evacuation System Rehabilitation and improvement of performance & efficiency of Ash Handling System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of old 300NB ash slurry disposal pipeline with new 300NB MSERW pipeline from slurry pump house to surface drain pump house at Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of old 200nb bottom ash, coarse ash, fly ash conveying pipeline with new 200 NB MSERW pipeline from ash hoppers to slurry tank & SILO AT PTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of complete assembly of air compressors (T-BTD-JM (4NOS) AND T-BD-QL (6NOS.)) in ash evacuation system in AHP, Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of complete assembly of SAM make ar-150/510 Pumps (9 nos) for replacement of ash slurry pumps of bottom ash slurry disposal from slurry tank to ash bund in slurry pump house. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of complete assembly of SAM MAKE ZM-II 530/03 (4 NOS) for replacement of HP pumps of bottom ash & coarse ash evacuation from BA/CA hoppers to slurry tank in ash water pump house. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of major internal assemblies of weir make GEHO pumps installed at AHP, Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of critical transmission drive systems and fluid couplings internal assemblies for slurry pumps and silo HCSD system installed at AHP, Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Augmentaion/Modification of U-3 & U-4 ESP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Restoration of ESP Fields of Unit- 3 & 4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Performance & Capacity enhancement of Ash handling plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of existing ash slurry disposal pump assembly by higher efficient pump assembly in AHP of Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of higher capacity vacuum pumps along with motors to improve availability & performance of fly ash system of AHP Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Modification & Replacement of air drier at AHP Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of existing HT Motors by energy efficient HT Motors In AHP of Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of ash handling plant auxiliaries & systems of Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of DRC Pipeline of fly ash evacuation system of AHP Paras for Availability improvement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of DRC Pipeline of fly ash evacuation system of AHP Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Structure strengthening of AHP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Work of anticorrosive Painting & Structure strengthening of Ash Handling Plant structures | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | U-3 Boiler Effyciency & Performance improvement schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CAVT & CFD for unit-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of sky climber assembly for Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of PA fan NDV22 BAB2 rotor assembly with impeller and cone & blade assembly of IGV with rod end assly for IGV control for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement Dampers, shutoff gate assemblies for series 5,6,7 & 8 dampers, ID fan inlet gate, APH flue gas dampers I/L & O/L, APH PA I/L & O/L dampers, APH SA I/L & O/L dampers along with actuators, SADC dampers at wind box with actuators for unit-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of critical high pressure valves, safety valves & control valves for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and Replacement of Thermal Insulation of Boiler, Ducts & Steam Pipelines for unit-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement and replacement of HP and B&S Lub oil pumps of coal mills BBD-4772 installed at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete Coal compartment assly for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete APH baskets, HE & CE sector plate, diapharm plate, rotor spool piece, grating assly, all type seals, rack pinion for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete set of Final super heater coil assembly for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete rotor assembly of FD fan including shaft with brg assly, impeller with oil hydraulic blade adjustment device with blades & coupling for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | U-3 & U-4 Boiler Effyciency, Performance & reliability improvement schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of Coal compartment assly for unit-4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and Replacement of Thermal Insulation of Boiler, Ducts & Steam Pipelines for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of critical high pressure valves, safety valves & control valves for unit-4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CAVT & CFD for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement Dampers, shutoff gate assemblies for series 5,6,7 & 8 dampers, ID fan inlet gate, APH flue gas dampers I/L & O/L, APH PA I/L & O/L dampers, APH SA I/L & O/L dampers along with actuators, SADC dampers at wind box with actuators for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete seal air fan assembly of coal mill BBD-4772 (without Motor) installed at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete set of Final super heater coil assembly for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete Coal compartment assly for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete APH baskets, HE & CE sector plate, diapharm plate, rotor spool piece, grating assly, all type seals, rack pinion for unit-4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete Coal compartment assly for unit-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete set of Re-heater coil (HRH & CRH) assembly for unit-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | ODP plant Process reliability improvement schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping of WT Plant Auxilliaries. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation of NDCT FILL at 2X250MW Units, Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, engineering, manufacturing, supply , erection and commissioning of degasser unit at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Performance improvement of compressors, compressored air drier system & Modification in Air ventilation system at 2x250MW Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping, modification of outdoor ducting of Air ventilation system at 2X250 MW, Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Performance improvement of compressors in Unit No.3, Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation of Compressed Air Refrigerated Dryer System for 2X250MW Unit, Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of LP Turbine blades, control fluid pump, AOP, JOP & HP valves for Turbine & its Auxiliaries efficiency improvement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Control Fluid Pumps & AOP of 250MW Unit No. 3 & 4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Moving blades for LPT-2L, 2R, 3L, 3R | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of valves – Main Steam Valves, Extraction Valves, BFP Recirculation Valves, etc. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Various schemes for reliability & performance improvement of Electrical & Control system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Water Flow monitoring system of various Location flowmeter at U3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of HMI and PLC hardware of Emerson (Former GE IP) make PLC system installed at Main Plant compressor Unit-4(PLC hardware and HMI), Condensate Polishing Unit Unit-3&4(HMI and PLC hardware), Pre-Treatment Plant Unit-4(HMI and PLC hardware) Water Treatment Plant (PLC hardware Unit-3&4) Ash Handling Plant Unit-4(PLC hardware), at Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Vibration Monitoring System server make Baker & Hughes (Former Bently Nevada) installed at Unit-3&4 Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping and Upgradation of PLC hardware of ABB make Online Condenser Tube Cleaning System installed at Unit-3&4 Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of carbon monoxide system in Air Preheater flue gas path at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, erection, commissioning and testing of 24 V 2X2250Ah, 360V 650AH UPS main plant, 360V 100Ah AHP UPS, 220V 125 Ah RWPH Battery at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of existing FBTS sytem installed at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement and Installation of Aviation Obstruction lighting system of Chimney and Cooling Towers at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Schemes related to Reduction in auxiliary Power consumption and upgradation of Valves & Instruments of C&I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation and Modification of Colony Electric Supply System to improve availability and reliability of supply system at Paras TPS colony | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply installation of VFD to CEP motors installed at paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Mid life overhauling of GCB installed at Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, installation testig and comissioning of VFD to PA fan motoras installed at Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of ID fan VFD installed at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1-Upgradation of all pneumatic control valve with smart positioner at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2-Upgradation of HFO mass flow meters at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3-Upgradation of O2 measurement system in Air Preheater inlet /outlet flue gas path and chimney inlet path at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-4-Upgradation of Steam Leak Detecting BHELSONIC system at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Various Civil schemes for Paras TPS Colony | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Attendning internal leakages of residential bulding in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing Terrace waterproofing to various buildings in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing and laying M.S. pipe line from new STP to WTP at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Water Supply GI Pipe line in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing of Colony Internal roads by BT at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing alluminium window to NF,NE,ND & Repairing of existing alluminium window and cupboard of resendial buildings in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing External Painting to Resenditial buildings in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Hospital Bulding in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Community Hall in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Development of Play Ground with Stage in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Beutification of colony area by providing Gardens and plantation in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of drain along internal roads in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Various Civil schemes related to Plant area of Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing waterproofing to terrace of various buildings in plant area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Attedning internal leakages and modification of Toilets in Plant area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting and carben rapping of cooling tower coloumn at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Attendning internal leakages of Parasdeep building along with renovatation of Toilets at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of water supply pipe lines in plant area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing External Painting to various buildings in plant area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Walk Way from Plant Gate to Service Building at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing & fixing modular kitchen (Trolleys) in B Type, CM Type, DM Type and EM Type quarters at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of drain with Footpath from CE Bunglow to Main Road at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of drain with Footpath from colony gate to Chummery Building at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing Internal Painting to Resenditial buildings in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation of Entrance road from T point to Colony Gate at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing of Plant Internal roads by BT at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IB recommendation at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | “Construction of RCC Compound wall as per IB recommendation at Paras TPS.” | 0 | - | 0 | 0 | 0 | 0 | 4.86 | 4.86 |  |  | 4.86 | 0
0 | “Construction of Watch towers along periphery compound wall as per IB recommendation at TPS Paras.” | 0 | - | 0 | 0 | 0 | 0 | 2.3 | 2.3 |  |  | 2.3 | 0
0 | CHP Improvement Schemes at 2 x 250 MW Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at 2 x 250 MW Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FGMO related Capex scheme | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FGMO related Capex scheme | 0 | - | 0 | 0 | 0 | 0 | 30 | 30 |  |  | 30 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Covid-19 Pandemic Related Work | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Medical Oxygen Gen. & Bottling Plant | N.A. | - | 0 | 2.6741 | 2.6741 | 0 | 0 | 0 |  |  | 0 | 0
0 | Empty Std size Medical Gr. Oxygen Cyl. | N.A. | - | 0 | 0.41133 | 0.41133 | 0 | 0 | 0 |  |  | 0 | 0
0 | Oxy Installation&Commissioning of Plant | N.A. | - | 0 | 0.079772 | 0.079772 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Asset Transfer from Paras Project | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Boiler Plant and Equipment Single Drum | N.A. | - | 0 | 4.9843 | 4.9843 | 0 | 0 | 0 |  |  | 0 | 0
0 | LAND | N.A. | - | 0 | 23.8051 | 34.3051 | -10.5 | 0 | 8.5 |  |  | 8.5 | -19
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Installation of portable crusher alongwith conveying system at 250 MW CHP, Paras TPS.-(CHP) | N.A. | - | 0 | 1.9889 | 1.9889 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing & Applying Epoxy Painting upto all height to structural steel work in power house area at TPS, Paras-(CIVIL) | N.A. | - | 0 | 5.6803 | 5.6803 | 0 | 0 | 0 |  |  | 0 | 0
0 | Material Handling Equipments | 0 | - | 0 | 0.033747 | 0.033747 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme for supply, erection, commissioning & testing of 7.2 KV SF6 contactor for retrofitting of existing BHEL make VM-12 type 6.6 KV HT circuit breakers of CHP Paras TPS.-(CHP) | N.A. | - | 0 | 2.3705 | 2.3705 | 0 | 0 | 0 |  |  | 0 | 0
0 | SWAS Lab improvement -(C&I) | N.A. | - | 0 | 2.2951 | 2.2951 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, supply, installation and commissioning of High performance energy chain system for Side Arm Charger at CHP 2 X 250 MW Unit 3 & 4 -(CHP) | N.A. | - | 0 | 1.0499 | 1.0499 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Manufacturing, supply, fabricate & erection of coal chutes with extra life weir reistatnce plates -(CHP) | N.A. | - | 0 | 2.3522 | 2.3522 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement and installation of set of internals of reducer gear box of coall mill BBD4772 @ Paras TPS -(BM) | N.A. | - | 0 | 1.788 | 1.788 | 0 | 0 | 0 |  |  | 0 | 0
0 | NON DPR scheme of procurement and installation of spares of non standard gridflex and gearflex couplings for coal mill BBD 4772 at Paras TPS 2x250MW -(BM) | N.A. | - | 0 | 0.90876 | 0.90876 | 0 | 0 | 0 |  |  | 0 | 0
0 | HO Non-DPR-Procurement of ABC powder Type & Foam type composite Fire Extnguisher for Paras TPS | N.A. | - | 0 | 0.5712 | 0.5712 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & replacement of APH baskets at Unit-3 | N.A. | - | 0 | 3.4477 | 3.45 | -0.0022658 | 0 | 0 |  |  | 0 | -0.0022658
0 | Battery Bank 220VDC , 2140Ah for Unit -3 | N.A. | - | 0 | 5.83 | 5.83 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | General Assets | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Furniture & Fixtures | N.A. | - | 0 | 0.71589 | 0.71589 | 0 | 0 | 0.1 |  |  | 0.1 | -0.1
0 | Office Equipment | N.A. | - | 0 | 2.1255 | 2.1255 | 0 | 0 | 0.1 |  |  | 0.1 | -0.1
0 | RCC Approach Road for CHP at Paras TPS | N.A. | - | 0 | 1.7924 | 1.7924 | 0 | 0 | 0 |  |  | 0 | 0
0 | Vehicles | N.A. | - | 0 | 0.75083 | 0.75083 | 0 | 0 | 0 |  |  | 0 | 0
0 | I.T. Equipment | 0 | - | 0 | 0.54853 | 0.54853 | 0 | 0.1 | 0.1 |  |  | 0.1 | 0
0 | Building | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 614.1781 | 472.3439 | 141.8342 | 267.3423 | 379.5305 | 0 | 0 | 379.5305 | 29.646
FY 2026-27
a) DPR Schemes
(i) Submitted to MERC
1 | Power supply arrangement at colony & separate 25 KV OHE supply feeding arrangement to BESG siding & provision of Passenger elevators | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 7.1549 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Provision of separate 25 KV OHE supply feeding arrangement to BESG siding at Paras TPS | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 0.3715 | 0.37148 | 0.37148 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | Arrangement of power supply for Paras TPS colony from 250 MW units with stepping down 6.6 KV supply to 3.3 KV. | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 3.6334 | 1.9509 | 1.9509 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Supply & installation of Total 12 nos. passenger elevators at `D’ & `E’ type quarters & administrative building of Paras TPS | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 3.15 | 1.7746 | 1.7746 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Ash Handling Plant augmentation scheme at Paras TPS Unit 3 & 4 | MERC/TECH 1/CAPEX/20142015/01160 | 2014-11-17 | 38.0989 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Ash Handling Plant augmentation scheme at Paras TPS Unit 3 & 4 | MERC/TECH 1/CAPEX/20142015/01160 | 2014-11-17 | 34.6889 | 63.376 | 61.0285 | 2.3475 | 0 | 0 |  |  | 0 | 2.3475 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/01160 | 2014-11-17 | 3.41 | 0.99854 | 0.99854 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | 3rd raising of Ash bund from TBL 273.63 mtr. to 276.63 mtr. with construction of masonry dam | MERC/MSPGCL/CAPEX/20142015/01648 | 2015-02-26 | 9.2104 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | 3rd raising of Ash bund from TBL 273.63 mtr. to 276.63 mtr. with construction of masonry dam | MERC/MSPGCL/CAPEX/20142015/01648 | 2015-02-26 | 8.2519 | 3.3121 | 3.3121 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/CAPEX/20142015/01648 | 2015-02-26 | 0.95855 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Various schemes related to CHP Improvement and Stack Management & Coal Mill Performance Improvement schemes | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 17.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Procurement of apron feeder system, pan & chain Assembly (2 no.’s) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 7.44 | 7.521 | 7.521 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Procurement of Assembly of Impact Crusher complete set with Beater Arm & Head.(1 no.) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.57 | 1.6013 | 1.6013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.3 | Procurement of Slewing Bearing of Stacker Reclaimer. (1 no.) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.45 | 1.4676 | 1.4676 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.4 | Capacity Enhancement of Wagon Tippler at Old CHP. | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 2.86 | 2.9502 | 2.9502 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.5 | Procurement of Bulldozer BD-155 for CHP(1 no.) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.7 | 2.1022 | 2.1022 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.6 | Procurement of Girth Gear and Pinion for BBD 4772 coal mills of 250 MW (1 set) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.6 | 1.6943 | 1.6943 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Procurement of Two Cartridge assembly for Boiler Feed Pump (Type: FK-3B-40) of 250MW Set | MERC/MSPGCL/CAPEX/20162017/04228 | 2017-09-22 | 13.88 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Procurement of Two Cartridge assembly for Boiler Feed Pump (Type: FK-3B-40) of 250MW Set | MERC/MSPGCL/CAPEX/20162017/04228 | 2017-09-22 | 13.88 | 14.0416 | 14.0416 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Replacement of battery bank set, replacement of two complete set of air pre-heater baskets & coal compartment assemblies for 250MW Unit 4 at Paras TPS | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 10.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Replacement of battery bank set to enhance process reliability of 250 MW Unit-4 at Paras TPS. | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 7.54 | 8.4214 | 8.4214 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.2 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-4, Paras TPS. | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 1.78 | 2.45 | 2.45 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.3 | Procurement & Replacement of Coal Compartment Assemblies Baskets at 250 MW Unit-4, Paras TPS. | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 0.75 | 0.56974 | 0.56974 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 0.04 | 0.25586 | 0.25786 | -0.002001 | 0 | 0 |  |  | 0 | -0.002001 | 0 | 0
7 | Procurement & Replacement of complete set of Economizer and LTSH upper & lower coils at Unit-3, Paras TPS | MERC/CAPEX/2019-2020/2 | 2019-05-24 | 10.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Replacement of complete set of economizer (upper & lower) coil assemblies & LTSH (upper & lower) coil assemblies for Unit-3. | MERC/CAPEX/2019-2020/2 | 2019-05-24 | 10.6 | 11.8971 | 11.8971 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/2 | 2019-05-24 | 0.22 | 1.8345 | 1.8345 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | HMI (Human Machine Interface) up gradation of DCS UNIT-3 & 4, WTP (Water Treatment Plant unit-3 & 4 combined PLC system) & AHP (Ash Handling Plant Unit-3 & 4 PLC System), Procurement of girth gear & pinion for optimum availability of auxiliary at Paras TPS | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 11.14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Up-gradation of Existing Max-DNA System (HMI) at Paras TPS (U# 3 & 4). | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 7.12 | 8.8364 | 8.8364 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Up-gradation of GE IP (GE-Fanuc) make PLC system (HMI) installed at WTP at Paras TPS (Combined for U# 3 & 4). | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0.38 | 0.36789 | 0.36789 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.3 | Up-gradation of GE IP (GE-Fanuc) make PLC system (HMI) installed at AHP Unit - 4 at Paras TPS. | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0.48 | 0.45873 | 0.45873 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.4 | Up-gradation of Existing Schneider make PLC (HMI + PLC hardware) installed at AHP Unit - 3 at Paras TPS. | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0.9 | 0.88264 | 0.88264 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.5 | Procurement & installation of Girth Gear & Pinion for coal mill BBD-4772. | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 2.26 | 2.1171 | 2.1171 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0 | 0.45004 | 0.45004 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Complete Track Renewal at Paras TPS | MERC/CAPEX/2019-2020/479 | 2019-08-02 | 12.77 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Complete Track Renewal at Paras TPS | MERC/CAPEX/2019-2020/479 | 2019-08-02 | 12.05 | 16.3958 | 16.3958 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/479 | 2019-08-02 | 0.72 | 0.078332 | 0.078332 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Procurement & Replacement of water wall panels in Unit#4 & Installation of VFD to existing eddy current drive driven coal feeders at 2x250 MW at Paras TPS | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 12.72 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Replacement of water wall panel in Unit-4 Boiler at 2 X 250 MW, PTPS | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 6.49 | 2.7423 | 6.2823 | -3.54 | 0 | 0 |  |  | 0 | -3.54 | 0 | 0
10.2 | Installation of VFD with controller over existing eddy current drives with controller at 2 X 250 MW, PTPS. | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 6.23 | 6.4672 | 6.4672 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 0 | 1.0135 | 1.0135 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Reinforcement & Capacity Enhancement of Old CHP Coal Conveyor Belt Structure from (200 TPH to 360 TPH) at old CHP Paras TPS & Procurement of One No. of Bulldozer & Diesel Hydraulic Locomotive at Paras TPS | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 12.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Capacity Enhancement of Old CHP Conveyor belt from 200 TPH to 360 TPH at Old CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 2.94 | 0 | 2.9382 | -2.9382 | 0 | 0 |  |  | 0 | -2.9382 | 0 | 0
11.2 | Reinforcement of Belt Conveyor structure at Old CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 2.66 | 2.9137 | 2.9137 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.3 | Procurement of Bulldozer at CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 2.31 | 2.4909 | 2.4909 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.4 | Procurement of Diesel Hydraulic Locomotive at CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 3.6 | 3.2208 | 3.2208 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 0.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Flue Gas Desulpherization (FGD) System for Paras Unit No. 3 & 4 | MERC/CAPEX/2020-2021/WFH/SBR/42 | 2020-12-14 | 376.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Flue Gas Desulpherization (FGD) System for Paras Unit No. 3 & 4 | MERC/CAPEX/2020-2021/WFH/SBR/42 | 2020-12-14 | 347.02 | 478.581 | 423.29 | 55.291 | 0 | 52.3 |  |  | 52.3 | 2.991 | 0 | 52.3
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/42 | 2020-12-14 | 29.04 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Procurement & Installation of complete assembly of Elecon make Gear Boxes, Wagon Tippler Assembly; Design, Supply, Installation, Commissioning & Successful Trial of Link Conveyor from Stackyard to C-2 Conveyor Belt at CHP; Procurement of Bucket Wheel of Stacker Reclaimer for CHP at Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 54.98 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Procurement & Installation of complete assembly of Elecon make Gear Boxes, Wagon Tippler Assembly; Design, Supply, Installation, Commissioning & Successful Trial of Link Conveyor from Stackyard to C-2 Conveyor Belt at CHP; Procurement of Bucket Wheel of Stacker Reclaimer for CHP at Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 32.78 | 11.88 | 11.88 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Procurement of Wagon Tippler Assembly & Installation of the same at CHP at Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 13.9 | 13.9 | 13.9 | 0 | 0 | 0 |  |  | 0 | 0
13.3 | Design, supply, installation, commissioning & successful trial of Link Conveyor from Stackyard to C-2 conveyor belt at CHP, Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 5.93 | 5.93 | 5.93 | 0 | 0 | 0 |  |  | 0 | 0
13.4 | Procurement of bucket wheel of stacker reclaimer for CHP 250MW Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 1.07 | 1.07 | 1.07 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 1.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 3.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.6 | Paras: Procurement of HT Motors(CEP/ACW Motors-I Phase and CW/CHP Motors-II Phase)for U-3&4 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 3.6 | 2.0958 | 2.0958 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 1.235 | 1.235 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.1 | PARAS(U-3 & 4) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 3.8456 | 3.8456 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 2.0276 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.1 | Paras TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 2.0276 | 0 | 2.31 | -2.31 | 0 | 0 |  |  | 0 | -2.31 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender at Paras TPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 2.9191 | 2.9191 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.2 | Normal Multipurpose Fire Tender at Paras TPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.0768 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.1 | TPS Paras | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.0768 | 1.6142 | 1.6142 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 12 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 12.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Enhancing process reliability at U-3 & U-4 at 2X250MW Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete set of Economiser (upper & lower) coil assemblies & LTSH (upper & lower) coil assemblies in Unit-4 (250mw) at Paras TPS. | 0 | - | 0 | 14.18 | 14.18 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & installation of complete discharge assembly of coal mill BBD 4772 In Unit-3&4 at Paras TPS | 0 | - | 0 | 22.51 | 22.51 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, replacement, erection and installation of foundation deck spring of coal mill BBD 4772 for Unit-3&4 at 250 MW at Paras TPS | 0 | - | 0 | 3.36 | 3.36 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of Coal Compartment Assemblies at 250 MW for Unit-3&4, Paras TPS | 0 | - | 0 | 1.77 | 1.77 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of Girth gear and pinion Assemblies at 250 MW Unit-3,4, Paras TPS | 0 | - | 0 | 9.22 | 9.22 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of Coal Mill drive shaft Assemblies at 250 MW Unit-3&4 Paras TPS. | 0 | - | 0 | 7.67 | 7.67 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of Air Pre Heater speed reducer gear box set of internals (assembly) for Unit-3&4. | 0 | - | 0 | 1.33 | 1.33 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of foundation deck spring assembly (vibration isolation system) for ID fan for Unit 3&4 at Paras TPS. | 0 | - | 0 | 2.31 | 2.31 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of CW Pump module with mandatory spares for TM section | 0 | - | 0 | 15.61 | 15.61 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Ash Evacuation System Rehabilitation and improvement of performance & efficiency of Ash Handling System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of old 300NB ash slurry disposal pipeline with new 300NB MSERW pipeline from slurry pump house to surface drain pump house at Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 6.66 | 6.66 |  |  | 6.66 | 0
0 | Replacement of old 200nb bottom ash, coarse ash, fly ash conveying pipeline with new 200 NB MSERW pipeline from ash hoppers to slurry tank & SILO AT PTPS. | 0 | - | 0 | 0 | 0 | 0 | 4.7 | 4.7 |  |  | 4.7 | 0
0 | Procurement of complete assembly of air compressors (T-BTD-JM (4NOS) AND T-BD-QL (6NOS.)) in ash evacuation system in AHP, Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 3.99 | 3.99 |  |  | 3.99 | 0
0 | Procurement of complete assembly of SAM make ar-150/510 Pumps (9 nos) for replacement of ash slurry pumps of bottom ash slurry disposal from slurry tank to ash bund in slurry pump house. | 0 | - | 0 | 0 | 0 | 0 | 2.15 | 2.15 |  |  | 2.15 | 0
0 | Procurement of complete assembly of SAM MAKE ZM-II 530/03 (4 NOS) for replacement of HP pumps of bottom ash & coarse ash evacuation from BA/CA hoppers to slurry tank in ash water pump house. | 0 | - | 0 | 0 | 0 | 0 | 0.89 | 0.89 |  |  | 0.89 | 0
0 | Procurement of major internal assemblies of weir make GEHO pumps installed at AHP, Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 13.4 | 13.4 |  |  | 13.4 | 0
0 | Procurement of critical transmission drive systems and fluid couplings internal assemblies for slurry pumps and silo HCSD system installed at AHP, Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 2.92 | 2.92 |  |  | 2.92 | 0
0 | Augmentaion/Modification of U-3 & U-4 ESP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Restoration of ESP Fields of Unit- 3 & 4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Performance & Capacity enhancement of Ash handling plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of existing ash slurry disposal pump assembly by higher efficient pump assembly in AHP of Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 12 | 12 |  |  | 12 | 0
0 | Procurement of higher capacity vacuum pumps along with motors to improve availability & performance of fly ash system of AHP Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
0 | Modification & Replacement of air drier at AHP Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
0 | Procurement & Replacement of existing HT Motors by energy efficient HT Motors In AHP of Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 4 | 4 |  |  | 4 | 0
0 | Procurement & Replacement of ash handling plant auxiliaries & systems of Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
0 | Procurement & Replacement of DRC Pipeline of fly ash evacuation system of AHP Paras for Availability improvement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of DRC Pipeline of fly ash evacuation system of AHP Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Structure strengthening of AHP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Work of anticorrosive Painting & Structure strengthening of Ash Handling Plant structures | 0 | - | 0 | 0 | 0 | 0 | 25 | 25 |  |  | 25 | 0
0 | U-3 Boiler Effyciency & Performance improvement schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CAVT & CFD for unit-3 | 0 | - | 0 | 0 | 0 | 0 | 1.2 | 1.2 |  |  | 1.2 | 0
0 | Procurement of sky climber assembly for Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
0 | Procurement & replacement of PA fan NDV22 BAB2 rotor assembly with impeller and cone & blade assembly of IGV with rod end assly for IGV control for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 1.51 | 1.51 |  |  | 1.51 | 0
0 | Procurement & replacement Dampers, shutoff gate assemblies for series 5,6,7 & 8 dampers, ID fan inlet gate, APH flue gas dampers I/L & O/L, APH PA I/L & O/L dampers, APH SA I/L & O/L dampers along with actuators, SADC dampers at wind box with actuators for unit-3 | 0 | - | 0 | 0 | 0 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
0 | Procurement & replacement of critical high pressure valves, safety valves & control valves for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
0 | Supply and Replacement of Thermal Insulation of Boiler, Ducts & Steam Pipelines for unit-3 | 0 | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
0 | Procurement and replacement of HP and B&S Lub oil pumps of coal mills BBD-4772 installed at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 1.8 | 1.8 |  |  | 1.8 | 0
0 | Procurement & replacement of complete Coal compartment assly for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete APH baskets, HE & CE sector plate, diapharm plate, rotor spool piece, grating assly, all type seals, rack pinion for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete set of Final super heater coil assembly for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete rotor assembly of FD fan including shaft with brg assly, impeller with oil hydraulic blade adjustment device with blades & coupling for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | U-3 & U-4 Boiler Effyciency, Performance & reliability improvement schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of Coal compartment assly for unit-4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and Replacement of Thermal Insulation of Boiler, Ducts & Steam Pipelines for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of critical high pressure valves, safety valves & control valves for unit-4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CAVT & CFD for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement Dampers, shutoff gate assemblies for series 5,6,7 & 8 dampers, ID fan inlet gate, APH flue gas dampers I/L & O/L, APH PA I/L & O/L dampers, APH SA I/L & O/L dampers along with actuators, SADC dampers at wind box with actuators for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete seal air fan assembly of coal mill BBD-4772 (without Motor) installed at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete set of Final super heater coil assembly for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete Coal compartment assly for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete APH baskets, HE & CE sector plate, diapharm plate, rotor spool piece, grating assly, all type seals, rack pinion for unit-4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete Coal compartment assly for unit-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete set of Re-heater coil (HRH & CRH) assembly for unit-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | ODP plant Process reliability improvement schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping of WT Plant Auxilliaries. | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
0 | Renovation of NDCT FILL at 2X250MW Units, Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, engineering, manufacturing, supply , erection and commissioning of degasser unit at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 1.2 | 1.2 |  |  | 1.2 | 0
0 | Performance improvement of compressors, compressored air drier system & Modification in Air ventilation system at 2x250MW Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping, modification of outdoor ducting of Air ventilation system at 2X250 MW, Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 16 | 16 |  |  | 16 | 0
0 | Performance improvement of compressors in Unit No.3, Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 10.3 | 10.3 |  |  | 10.3 | 0
0 | Renovation of Compressed Air Refrigerated Dryer System for 2X250MW Unit, Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
0 | Procurement of LP Turbine blades, control fluid pump, AOP, JOP & HP valves for Turbine & its Auxiliaries efficiency improvement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Control Fluid Pumps & AOP of 250MW Unit No. 3 & 4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Moving blades for LPT-2L, 2R, 3L, 3R | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of valves – Main Steam Valves, Extraction Valves, BFP Recirculation Valves, etc. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Various schemes for reliability & performance improvement of Electrical & Control system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Water Flow monitoring system of various Location flowmeter at U3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 5.5 | 5.5 |  |  | 5.5 | 0
0 | Upgradation of HMI and PLC hardware of Emerson (Former GE IP) make PLC system installed at Main Plant compressor Unit-4(PLC hardware and HMI), Condensate Polishing Unit Unit-3&4(HMI and PLC hardware), Pre-Treatment Plant Unit-4(HMI and PLC hardware) Water Treatment Plant (PLC hardware Unit-3&4) Ash Handling Plant Unit-4(PLC hardware), at Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 9 | 9 |  |  | 9 | 0
0 | Upgradation of Vibration Monitoring System server make Baker & Hughes (Former Bently Nevada) installed at Unit-3&4 Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
0 | Revamping and Upgradation of PLC hardware of ABB make Online Condenser Tube Cleaning System installed at Unit-3&4 Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of carbon monoxide system in Air Preheater flue gas path at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, erection, commissioning and testing of 24 V 2X2250Ah, 360V 650AH UPS main plant, 360V 100Ah AHP UPS, 220V 125 Ah RWPH Battery at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 3.671 | 3.671 |  |  | 3.671 | 0
0 | Upgradation of existing FBTS sytem installed at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 4.456 | 4.456 |  |  | 4.456 | 0
0 | Procurement and Installation of Aviation Obstruction lighting system of Chimney and Cooling Towers at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 2.187 | 2.187 |  |  | 2.187 | 0
0 | Schemes related to Reduction in auxiliary Power consumption and upgradation of Valves & Instruments of C&I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation and Modification of Colony Electric Supply System to improve availability and reliability of supply system at Paras TPS colony | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
0 | Supply installation of VFD to CEP motors installed at paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Mid life overhauling of GCB installed at Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, installation testig and comissioning of VFD to PA fan motoras installed at Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of ID fan VFD installed at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1-Upgradation of all pneumatic control valve with smart positioner at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2-Upgradation of HFO mass flow meters at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3-Upgradation of O2 measurement system in Air Preheater inlet /outlet flue gas path and chimney inlet path at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-4-Upgradation of Steam Leak Detecting BHELSONIC system at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Various Civil schemes for Paras TPS Colony | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Attendning internal leakages of residential bulding in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 8.2 | 8.2 |  |  | 8.2 | 0
0 | Providing Terrace waterproofing to various buildings in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
0 | Providing and laying M.S. pipe line from new STP to WTP at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0.8 | 0.8 |  |  | 0.8 | 0
0 | Replacement of Water Supply GI Pipe line in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0.9 | 0.9 |  |  | 0.9 | 0
0 | Repairing of Colony Internal roads by BT at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
0 | Providing alluminium window to NF,NE,ND & Repairing of existing alluminium window and cupboard of resendial buildings in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing External Painting to Resenditial buildings in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Hospital Bulding in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Community Hall in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Development of Play Ground with Stage in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Beutification of colony area by providing Gardens and plantation in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of drain along internal roads in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Various Civil schemes related to Plant area of Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing waterproofing to terrace of various buildings in plant area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 3.9 | 3.9 |  |  | 3.9 | 0
0 | Attedning internal leakages and modification of Toilets in Plant area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 1.6 | 1.6 |  |  | 1.6 | 0
0 | Retrofitting and carben rapping of cooling tower coloumn at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0.5 | 0.5 |  |  | 0.5 | 0
0 | Attendning internal leakages of Parasdeep building along with renovatation of Toilets at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0.25 | 0.25 |  |  | 0.25 | 0
0 | Replacement of water supply pipe lines in plant area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0.9 | 0.9 |  |  | 0.9 | 0
0 | Providing External Painting to various buildings in plant area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0.6 | 0.6 |  |  | 0.6 | 0
0 | Construction of Walk Way from Plant Gate to Service Building at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0.4 | 0.4 |  |  | 0.4 | 0
0 | Providing & fixing modular kitchen (Trolleys) in B Type, CM Type, DM Type and EM Type quarters at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 3.5 | 3.5 |  |  | 3.5 | 0
0 | Construction of drain with Footpath from CE Bunglow to Main Road at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of drain with Footpath from colony gate to Chummery Building at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing Internal Painting to Resenditial buildings in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation of Entrance road from T point to Colony Gate at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing of Plant Internal roads by BT at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IB recommendation at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | “Construction of RCC Compound wall as per IB recommendation at Paras TPS.” | 0 | - | 0 | 4.86 | 4.86 | 0 | 0 | 0 |  |  | 0 | 0
0 | “Construction of Watch towers along periphery compound wall as per IB recommendation at TPS Paras.” | 0 | - | 0 | 2.3 | 2.3 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at 2 x 250 MW Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at 2 x 250 MW Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FGMO related Capex scheme | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FGMO related Capex scheme | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Covid-19 Pandemic Related Work | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Medical Oxygen Gen. & Bottling Plant | N.A. | - | 0 | 2.6741 | 2.6741 | 0 | 0 | 0 |  |  | 0 | 0
0 | Empty Std size Medical Gr. Oxygen Cyl. | N.A. | - | 0 | 0.41133 | 0.41133 | 0 | 0 | 0 |  |  | 0 | 0
0 | Oxy Installation&Commissioning of Plant | N.A. | - | 0 | 0.079772 | 0.079772 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Asset Transfer from Paras Project | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Boiler Plant and Equipment Single Drum | N.A. | - | 0 | 4.9843 | 4.9843 | 0 | 0 | 0 |  |  | 0 | 0
0 | LAND | N.A. | - | 0 | 23.8051 | 42.8051 | -19 | 0 | 9 |  |  | 9 | -28
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Installation of portable crusher alongwith conveying system at 250 MW CHP, Paras TPS.-(CHP) | N.A. | - | 0 | 1.9889 | 1.9889 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing & Applying Epoxy Painting upto all height to structural steel work in power house area at TPS, Paras-(CIVIL) | N.A. | - | 0 | 5.6803 | 5.6803 | 0 | 0 | 0 |  |  | 0 | 0
0 | Material Handling Equipments | 0 | - | 0 | 0.033747 | 0.033747 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme for supply, erection, commissioning & testing of 7.2 KV SF6 contactor for retrofitting of existing BHEL make VM-12 type 6.6 KV HT circuit breakers of CHP Paras TPS.-(CHP) | N.A. | - | 0 | 2.3705 | 2.3705 | 0 | 0 | 0 |  |  | 0 | 0
0 | SWAS Lab improvement -(C&I) | N.A. | - | 0 | 2.2951 | 2.2951 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, supply, installation and commissioning of High performance energy chain system for Side Arm Charger at CHP 2 X 250 MW Unit 3 & 4 -(CHP) | N.A. | - | 0 | 1.0499 | 1.0499 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Manufacturing, supply, fabricate & erection of coal chutes with extra life weir reistatnce plates -(CHP) | N.A. | - | 0 | 2.3522 | 2.3522 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement and installation of set of internals of reducer gear box of coall mill BBD4772 @ Paras TPS -(BM) | N.A. | - | 0 | 1.788 | 1.788 | 0 | 0 | 0 |  |  | 0 | 0
0 | NON DPR scheme of procurement and installation of spares of non standard gridflex and gearflex couplings for coal mill BBD 4772 at Paras TPS 2x250MW -(BM) | N.A. | - | 0 | 0.90876 | 0.90876 | 0 | 0 | 0 |  |  | 0 | 0
0 | HO Non-DPR-Procurement of ABC powder Type & Foam type composite Fire Extnguisher for Paras TPS | N.A. | - | 0 | 0.5712 | 0.5712 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & replacement of APH baskets at Unit-3 | N.A. | - | 0 | 3.4477 | 3.45 | -0.0022658 | 0 | 0 |  |  | 0 | -0.0022658
0 | Battery Bank 220VDC , 2140Ah for Unit -3 | N.A. | - | 0 | 5.83 | 5.83 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | General Assets | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Furniture & Fixtures | N.A. | - | 0 | 0.71589 | 0.81589 | -0.1 | 0 | 0.1 |  |  | 0.1 | -0.2
0 | Office Equipment | N.A. | - | 0 | 2.1255 | 2.2255 | -0.1 | 0 | 0.1 |  |  | 0.1 | -0.2
0 | RCC Approach Road for CHP at Paras TPS | N.A. | - | 0 | 1.7924 | 1.7924 | 0 | 0 | 0 |  |  | 0 | 0
0 | Vehicles | N.A. | - | 0 | 0.75083 | 0.75083 | 0 | 0 | 0 |  |  | 0 | 0
0 | I.T. Equipment | 0 | - | 0 | 0.64853 | 0.64853 | 0 | 0.1 | 0.1 |  |  | 0.1 | 0
0 | Building | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 881.5204 | 851.8744 | 29.646 | 203.184 | 264.684 | 0 | 0 | 264.684 | -31.854
FY 2027-28
a) DPR Schemes
(i) Submitted to MERC
1 | Power supply arrangement at colony & separate 25 KV OHE supply feeding arrangement to BESG siding & provision of Passenger elevators | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 7.1549 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Provision of separate 25 KV OHE supply feeding arrangement to BESG siding at Paras TPS | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 0.3715 | 0.37148 | 0.37148 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | Arrangement of power supply for Paras TPS colony from 250 MW units with stepping down 6.6 KV supply to 3.3 KV. | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 3.6334 | 1.9509 | 1.9509 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Supply & installation of Total 12 nos. passenger elevators at `D’ & `E’ type quarters & administrative building of Paras TPS | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 3.15 | 1.7746 | 1.7746 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Ash Handling Plant augmentation scheme at Paras TPS Unit 3 & 4 | MERC/TECH 1/CAPEX/20142015/01160 | 2014-11-17 | 38.0989 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Ash Handling Plant augmentation scheme at Paras TPS Unit 3 & 4 | MERC/TECH 1/CAPEX/20142015/01160 | 2014-11-17 | 34.6889 | 63.376 | 61.0285 | 2.3475 | 0 | 0 |  |  | 0 | 2.3475 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/01160 | 2014-11-17 | 3.41 | 0.99854 | 0.99854 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | 3rd raising of Ash bund from TBL 273.63 mtr. to 276.63 mtr. with construction of masonry dam | MERC/MSPGCL/CAPEX/20142015/01648 | 2015-02-26 | 9.2104 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | 3rd raising of Ash bund from TBL 273.63 mtr. to 276.63 mtr. with construction of masonry dam | MERC/MSPGCL/CAPEX/20142015/01648 | 2015-02-26 | 8.2519 | 3.3121 | 3.3121 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/CAPEX/20142015/01648 | 2015-02-26 | 0.95855 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Various schemes related to CHP Improvement and Stack Management & Coal Mill Performance Improvement schemes | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 17.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Procurement of apron feeder system, pan & chain Assembly (2 no.’s) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 7.44 | 7.521 | 7.521 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Procurement of Assembly of Impact Crusher complete set with Beater Arm & Head.(1 no.) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.57 | 1.6013 | 1.6013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.3 | Procurement of Slewing Bearing of Stacker Reclaimer. (1 no.) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.45 | 1.4676 | 1.4676 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.4 | Capacity Enhancement of Wagon Tippler at Old CHP. | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 2.86 | 2.9502 | 2.9502 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.5 | Procurement of Bulldozer BD-155 for CHP(1 no.) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.7 | 2.1022 | 2.1022 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.6 | Procurement of Girth Gear and Pinion for BBD 4772 coal mills of 250 MW (1 set) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.6 | 1.6943 | 1.6943 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Procurement of Two Cartridge assembly for Boiler Feed Pump (Type: FK-3B-40) of 250MW Set | MERC/MSPGCL/CAPEX/20162017/04228 | 2017-09-22 | 13.88 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Procurement of Two Cartridge assembly for Boiler Feed Pump (Type: FK-3B-40) of 250MW Set | MERC/MSPGCL/CAPEX/20162017/04228 | 2017-09-22 | 13.88 | 14.0416 | 14.0416 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Replacement of battery bank set, replacement of two complete set of air pre-heater baskets & coal compartment assemblies for 250MW Unit 4 at Paras TPS | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 10.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Replacement of battery bank set to enhance process reliability of 250 MW Unit-4 at Paras TPS. | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 7.54 | 8.4214 | 8.4214 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.2 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-4, Paras TPS. | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 1.78 | 2.45 | 2.45 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.3 | Procurement & Replacement of Coal Compartment Assemblies Baskets at 250 MW Unit-4, Paras TPS. | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 0.75 | 0.56974 | 0.56974 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 0.04 | 0.25586 | 0.25786 | -0.002001 | 0 | 0 |  |  | 0 | -0.002001 | 0 | 0
7 | Procurement & Replacement of complete set of Economizer and LTSH upper & lower coils at Unit-3, Paras TPS | MERC/CAPEX/2019-2020/2 | 2019-05-24 | 10.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Replacement of complete set of economizer (upper & lower) coil assemblies & LTSH (upper & lower) coil assemblies for Unit-3. | MERC/CAPEX/2019-2020/2 | 2019-05-24 | 10.6 | 11.8971 | 11.8971 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/2 | 2019-05-24 | 0.22 | 1.8345 | 1.8345 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | HMI (Human Machine Interface) up gradation of DCS UNIT-3 & 4, WTP (Water Treatment Plant unit-3 & 4 combined PLC system) & AHP (Ash Handling Plant Unit-3 & 4 PLC System), Procurement of girth gear & pinion for optimum availability of auxiliary at Paras TPS | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 11.14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Up-gradation of Existing Max-DNA System (HMI) at Paras TPS (U# 3 & 4). | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 7.12 | 8.8364 | 8.8364 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Up-gradation of GE IP (GE-Fanuc) make PLC system (HMI) installed at WTP at Paras TPS (Combined for U# 3 & 4). | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0.38 | 0.36789 | 0.36789 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.3 | Up-gradation of GE IP (GE-Fanuc) make PLC system (HMI) installed at AHP Unit - 4 at Paras TPS. | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0.48 | 0.45873 | 0.45873 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.4 | Up-gradation of Existing Schneider make PLC (HMI + PLC hardware) installed at AHP Unit - 3 at Paras TPS. | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0.9 | 0.88264 | 0.88264 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.5 | Procurement & installation of Girth Gear & Pinion for coal mill BBD-4772. | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 2.26 | 2.1171 | 2.1171 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0 | 0.45004 | 0.45004 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Complete Track Renewal at Paras TPS | MERC/CAPEX/2019-2020/479 | 2019-08-02 | 12.77 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Complete Track Renewal at Paras TPS | MERC/CAPEX/2019-2020/479 | 2019-08-02 | 12.05 | 16.3958 | 16.3958 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/479 | 2019-08-02 | 0.72 | 0.078332 | 0.078332 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Procurement & Replacement of water wall panels in Unit#4 & Installation of VFD to existing eddy current drive driven coal feeders at 2x250 MW at Paras TPS | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 12.72 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Replacement of water wall panel in Unit-4 Boiler at 2 X 250 MW, PTPS | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 6.49 | 2.7423 | 6.2823 | -3.54 | 0 | 0 |  |  | 0 | -3.54 | 0 | 0
10.2 | Installation of VFD with controller over existing eddy current drives with controller at 2 X 250 MW, PTPS. | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 6.23 | 6.4672 | 6.4672 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 0 | 1.0135 | 1.0135 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Reinforcement & Capacity Enhancement of Old CHP Coal Conveyor Belt Structure from (200 TPH to 360 TPH) at old CHP Paras TPS & Procurement of One No. of Bulldozer & Diesel Hydraulic Locomotive at Paras TPS | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 12.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Capacity Enhancement of Old CHP Conveyor belt from 200 TPH to 360 TPH at Old CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 2.94 | 0 | 2.9382 | -2.9382 | 0 | 0 |  |  | 0 | -2.9382 | 0 | 0
11.2 | Reinforcement of Belt Conveyor structure at Old CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 2.66 | 2.9137 | 2.9137 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.3 | Procurement of Bulldozer at CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 2.31 | 2.4909 | 2.4909 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.4 | Procurement of Diesel Hydraulic Locomotive at CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 3.6 | 3.2208 | 3.2208 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 0.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Flue Gas Desulpherization (FGD) System for Paras Unit No. 3 & 4 | MERC/CAPEX/2020-2021/WFH/SBR/42 | 2020-12-14 | 376.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Flue Gas Desulpherization (FGD) System for Paras Unit No. 3 & 4 | MERC/CAPEX/2020-2021/WFH/SBR/42 | 2020-12-14 | 347.02 | 478.581 | 475.59 | 2.991 | 0 | 0 |  |  | 0 | 2.991 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/42 | 2020-12-14 | 29.04 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Procurement & Installation of complete assembly of Elecon make Gear Boxes, Wagon Tippler Assembly; Design, Supply, Installation, Commissioning & Successful Trial of Link Conveyor from Stackyard to C-2 Conveyor Belt at CHP; Procurement of Bucket Wheel of Stacker Reclaimer for CHP at Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 54.98 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Procurement & Installation of complete assembly of Elecon make Gear Boxes, Wagon Tippler Assembly; Design, Supply, Installation, Commissioning & Successful Trial of Link Conveyor from Stackyard to C-2 Conveyor Belt at CHP; Procurement of Bucket Wheel of Stacker Reclaimer for CHP at Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 32.78 | 11.88 | 11.88 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Procurement of Wagon Tippler Assembly & Installation of the same at CHP at Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 13.9 | 13.9 | 13.9 | 0 | 0 | 0 |  |  | 0 | 0
13.3 | Design, supply, installation, commissioning & successful trial of Link Conveyor from Stackyard to C-2 conveyor belt at CHP, Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 5.93 | 5.93 | 5.93 | 0 | 0 | 0 |  |  | 0 | 0
13.4 | Procurement of bucket wheel of stacker reclaimer for CHP 250MW Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 1.07 | 1.07 | 1.07 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 1.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 3.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.6 | Paras: Procurement of HT Motors(CEP/ACW Motors-I Phase and CW/CHP Motors-II Phase)for U-3&4 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 3.6 | 2.0958 | 2.0958 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 1.235 | 1.235 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.1 | PARAS(U-3 & 4) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 3.8456 | 3.8456 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 2.0276 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.1 | Paras TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 2.0276 | 0 | 2.31 | -2.31 | 0 | 0 |  |  | 0 | -2.31 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender at Paras TPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 2.9191 | 2.9191 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.2 | Normal Multipurpose Fire Tender at Paras TPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.0768 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.1 | TPS Paras | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.0768 | 1.6142 | 1.6142 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 12 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 12.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Enhancing process reliability at U-3 & U-4 at 2X250MW Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete set of Economiser (upper & lower) coil assemblies & LTSH (upper & lower) coil assemblies in Unit-4 (250mw) at Paras TPS. | 0 | - | 0 | 14.18 | 14.18 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & installation of complete discharge assembly of coal mill BBD 4772 In Unit-3&4 at Paras TPS | 0 | - | 0 | 22.51 | 22.51 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, replacement, erection and installation of foundation deck spring of coal mill BBD 4772 for Unit-3&4 at 250 MW at Paras TPS | 0 | - | 0 | 3.36 | 3.36 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of Coal Compartment Assemblies at 250 MW for Unit-3&4, Paras TPS | 0 | - | 0 | 1.77 | 1.77 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of Girth gear and pinion Assemblies at 250 MW Unit-3,4, Paras TPS | 0 | - | 0 | 9.22 | 9.22 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of Coal Mill drive shaft Assemblies at 250 MW Unit-3&4 Paras TPS. | 0 | - | 0 | 7.67 | 7.67 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of Air Pre Heater speed reducer gear box set of internals (assembly) for Unit-3&4. | 0 | - | 0 | 1.33 | 1.33 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of foundation deck spring assembly (vibration isolation system) for ID fan for Unit 3&4 at Paras TPS. | 0 | - | 0 | 2.31 | 2.31 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of CW Pump module with mandatory spares for TM section | 0 | - | 0 | 15.61 | 15.61 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Ash Evacuation System Rehabilitation and improvement of performance & efficiency of Ash Handling System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of old 300NB ash slurry disposal pipeline with new 300NB MSERW pipeline from slurry pump house to surface drain pump house at Paras TPS. | 0 | - | 0 | 6.66 | 6.66 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of old 200nb bottom ash, coarse ash, fly ash conveying pipeline with new 200 NB MSERW pipeline from ash hoppers to slurry tank & SILO AT PTPS. | 0 | - | 0 | 4.7 | 4.7 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of complete assembly of air compressors (T-BTD-JM (4NOS) AND T-BD-QL (6NOS.)) in ash evacuation system in AHP, Paras TPS. | 0 | - | 0 | 3.99 | 3.99 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of complete assembly of SAM make ar-150/510 Pumps (9 nos) for replacement of ash slurry pumps of bottom ash slurry disposal from slurry tank to ash bund in slurry pump house. | 0 | - | 0 | 2.15 | 2.15 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of complete assembly of SAM MAKE ZM-II 530/03 (4 NOS) for replacement of HP pumps of bottom ash & coarse ash evacuation from BA/CA hoppers to slurry tank in ash water pump house. | 0 | - | 0 | 0.89 | 0.89 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of major internal assemblies of weir make GEHO pumps installed at AHP, Paras TPS. | 0 | - | 0 | 13.4 | 13.4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of critical transmission drive systems and fluid couplings internal assemblies for slurry pumps and silo HCSD system installed at AHP, Paras TPS. | 0 | - | 0 | 2.92 | 2.92 | 0 | 0 | 0 |  |  | 0 | 0
0 | Augmentaion/Modification of U-3 & U-4 ESP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Restoration of ESP Fields of Unit- 3 & 4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 50 | 50 |  |  | 50 | 0
0 | Performance & Capacity enhancement of Ash handling plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of existing ash slurry disposal pump assembly by higher efficient pump assembly in AHP of Paras TPS | 0 | - | 0 | 12 | 12 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of higher capacity vacuum pumps along with motors to improve availability & performance of fly ash system of AHP Paras TPS | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Modification & Replacement of air drier at AHP Paras TPS | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of existing HT Motors by energy efficient HT Motors In AHP of Paras TPS | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of ash handling plant auxiliaries & systems of Paras TPS | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of DRC Pipeline of fly ash evacuation system of AHP Paras for Availability improvement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of DRC Pipeline of fly ash evacuation system of AHP Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 40 | 40 |  |  | 40 | 0
0 | Structure strengthening of AHP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Work of anticorrosive Painting & Structure strengthening of Ash Handling Plant structures | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
0 | U-3 Boiler Effyciency & Performance improvement schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CAVT & CFD for unit-3 | 0 | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of sky climber assembly for Paras TPS | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of PA fan NDV22 BAB2 rotor assembly with impeller and cone & blade assembly of IGV with rod end assly for IGV control for unit-3. | 0 | - | 0 | 1.51 | 1.51 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement Dampers, shutoff gate assemblies for series 5,6,7 & 8 dampers, ID fan inlet gate, APH flue gas dampers I/L & O/L, APH PA I/L & O/L dampers, APH SA I/L & O/L dampers along with actuators, SADC dampers at wind box with actuators for unit-3 | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of critical high pressure valves, safety valves & control valves for unit-3. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and Replacement of Thermal Insulation of Boiler, Ducts & Steam Pipelines for unit-3 | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement and replacement of HP and B&S Lub oil pumps of coal mills BBD-4772 installed at Paras TPS | 0 | - | 0 | 1.8 | 1.8 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete Coal compartment assly for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete APH baskets, HE & CE sector plate, diapharm plate, rotor spool piece, grating assly, all type seals, rack pinion for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete set of Final super heater coil assembly for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete rotor assembly of FD fan including shaft with brg assly, impeller with oil hydraulic blade adjustment device with blades & coupling for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | U-3 & U-4 Boiler Effyciency, Performance & reliability improvement schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of Coal compartment assly for unit-4. | 0 | - | 0 | 0 | 0 | 0 | 1.1 | 1.1 |  |  | 1.1 | 0
0 | Supply and Replacement of Thermal Insulation of Boiler, Ducts & Steam Pipelines for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
0 | Procurement & replacement of critical high pressure valves, safety valves & control valves for unit-4. | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
0 | CAVT & CFD for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 1.2 | 1.2 |  |  | 1.2 | 0
0 | Procurement & replacement Dampers, shutoff gate assemblies for series 5,6,7 & 8 dampers, ID fan inlet gate, APH flue gas dampers I/L & O/L, APH PA I/L & O/L dampers, APH SA I/L & O/L dampers along with actuators, SADC dampers at wind box with actuators for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
0 | Procurement & replacement of complete seal air fan assembly of coal mill BBD-4772 (without Motor) installed at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
0 | Procurement & replacement of complete set of Final super heater coil assembly for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete Coal compartment assly for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete APH baskets, HE & CE sector plate, diapharm plate, rotor spool piece, grating assly, all type seals, rack pinion for unit-4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete Coal compartment assly for unit-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete set of Re-heater coil (HRH & CRH) assembly for unit-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | ODP plant Process reliability improvement schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping of WT Plant Auxilliaries. | 0 | - | 0 | 10 | 10 | 0 | 15 | 15 |  |  | 15 | 0
0 | Renovation of NDCT FILL at 2X250MW Units, Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 6 | 6 |  |  | 6 | 0
0 | Design, engineering, manufacturing, supply , erection and commissioning of degasser unit at Paras TPS | 0 | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Performance improvement of compressors, compressored air drier system & Modification in Air ventilation system at 2x250MW Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping, modification of outdoor ducting of Air ventilation system at 2X250 MW, Paras TPS. | 0 | - | 0 | 16 | 16 | 0 | 0 | 0 |  |  | 0 | 0
0 | Performance improvement of compressors in Unit No.3, Paras TPS. | 0 | - | 0 | 10.3 | 10.3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation of Compressed Air Refrigerated Dryer System for 2X250MW Unit, Paras TPS | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of LP Turbine blades, control fluid pump, AOP, JOP & HP valves for Turbine & its Auxiliaries efficiency improvement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Control Fluid Pumps & AOP of 250MW Unit No. 3 & 4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 12 | 12 |  |  | 12 | 0
0 | Moving blades for LPT-2L, 2R, 3L, 3R | 0 | - | 0 | 0 | 0 | 0 | 13.51 | 13.51 |  |  | 13.51 | 0
0 | Replacement of valves – Main Steam Valves, Extraction Valves, BFP Recirculation Valves, etc. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Various schemes for reliability & performance improvement of Electrical & Control system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Water Flow monitoring system of various Location flowmeter at U3&4 Paras TPS | 0 | - | 0 | 5.5 | 5.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of HMI and PLC hardware of Emerson (Former GE IP) make PLC system installed at Main Plant compressor Unit-4(PLC hardware and HMI), Condensate Polishing Unit Unit-3&4(HMI and PLC hardware), Pre-Treatment Plant Unit-4(HMI and PLC hardware) Water Treatment Plant (PLC hardware Unit-3&4) Ash Handling Plant Unit-4(PLC hardware), at Paras TPS. | 0 | - | 0 | 9 | 9 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Vibration Monitoring System server make Baker & Hughes (Former Bently Nevada) installed at Unit-3&4 Paras TPS. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping and Upgradation of PLC hardware of ABB make Online Condenser Tube Cleaning System installed at Unit-3&4 Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
0 | Upgradation of carbon monoxide system in Air Preheater flue gas path at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
0 | Supply, erection, commissioning and testing of 24 V 2X2250Ah, 360V 650AH UPS main plant, 360V 100Ah AHP UPS, 220V 125 Ah RWPH Battery at Paras TPS | 0 | - | 0 | 3.671 | 3.671 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of existing FBTS sytem installed at Paras TPS | 0 | - | 0 | 4.456 | 4.456 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement and Installation of Aviation Obstruction lighting system of Chimney and Cooling Towers at Paras TPS | 0 | - | 0 | 2.187 | 2.187 | 0 | 0 | 0 |  |  | 0 | 0
0 | Schemes related to Reduction in auxiliary Power consumption and upgradation of Valves & Instruments of C&I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation and Modification of Colony Electric Supply System to improve availability and reliability of supply system at Paras TPS colony | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply installation of VFD to CEP motors installed at paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
0 | Mid life overhauling of GCB installed at Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 6 | 6 |  |  | 6 | 0
0 | Supply, installation testig and comissioning of VFD to PA fan motoras installed at Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of ID fan VFD installed at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1-Upgradation of all pneumatic control valve with smart positioner at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2-Upgradation of HFO mass flow meters at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3-Upgradation of O2 measurement system in Air Preheater inlet /outlet flue gas path and chimney inlet path at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-4-Upgradation of Steam Leak Detecting BHELSONIC system at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Various Civil schemes for Paras TPS Colony | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Attendning internal leakages of residential bulding in colony area at TPS Paras. | 0 | - | 0 | 8.2 | 8.2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing Terrace waterproofing to various buildings in colony area at TPS Paras. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing and laying M.S. pipe line from new STP to WTP at TPS Paras. | 0 | - | 0 | 0.8 | 0.8 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Water Supply GI Pipe line in colony area at TPS Paras | 0 | - | 0 | 0.9 | 0.9 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing of Colony Internal roads by BT at TPS Paras | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing alluminium window to NF,NE,ND & Repairing of existing alluminium window and cupboard of resendial buildings in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 2.7 | 2.7 |  |  | 2.7 | 0
0 | Providing External Painting to Resenditial buildings in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 2.9 | 2.9 |  |  | 2.9 | 0
0 | Construction of Hospital Bulding in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Community Hall in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Development of Play Ground with Stage in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Beutification of colony area by providing Gardens and plantation in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of drain along internal roads in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Various Civil schemes related to Plant area of Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing waterproofing to terrace of various buildings in plant area at TPS Paras. | 0 | - | 0 | 3.9 | 3.9 | 0 | 0 | 0 |  |  | 0 | 0
0 | Attedning internal leakages and modification of Toilets in Plant area at TPS Paras. | 0 | - | 0 | 1.6 | 1.6 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting and carben rapping of cooling tower coloumn at TPS Paras | 0 | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Attendning internal leakages of Parasdeep building along with renovatation of Toilets at TPS Paras. | 0 | - | 0 | 0.25 | 0.25 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of water supply pipe lines in plant area at TPS Paras. | 0 | - | 0 | 0.9 | 0.9 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing External Painting to various buildings in plant area at TPS Paras. | 0 | - | 0 | 0.6 | 0.6 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Walk Way from Plant Gate to Service Building at TPS Paras | 0 | - | 0 | 0.4 | 0.4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing & fixing modular kitchen (Trolleys) in B Type, CM Type, DM Type and EM Type quarters at TPS Paras. | 0 | - | 0 | 3.5 | 3.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of drain with Footpath from CE Bunglow to Main Road at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
0 | Construction of drain with Footpath from colony gate to Chummery Building at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 1.6 | 1.6 |  |  | 1.6 | 0
0 | Providing Internal Painting to Resenditial buildings in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation of Entrance road from T point to Colony Gate at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing of Plant Internal roads by BT at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IB recommendation at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | “Construction of RCC Compound wall as per IB recommendation at Paras TPS.” | 0 | - | 0 | 4.86 | 4.86 | 0 | 0 | 0 |  |  | 0 | 0
0 | “Construction of Watch towers along periphery compound wall as per IB recommendation at TPS Paras.” | 0 | - | 0 | 2.3 | 2.3 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at 2 x 250 MW Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at 2 x 250 MW Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 25 | 25 |  |  | 25 | 0
0 | FGMO related Capex scheme | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FGMO related Capex scheme | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Covid-19 Pandemic Related Work | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Medical Oxygen Gen. & Bottling Plant | N.A. | - | 0 | 2.6741 | 2.6741 | 0 | 0 | 0 |  |  | 0 | 0
0 | Empty Std size Medical Gr. Oxygen Cyl. | N.A. | - | 0 | 0.41133 | 0.41133 | 0 | 0 | 0 |  |  | 0 | 0
0 | Oxy Installation&Commissioning of Plant | N.A. | - | 0 | 0.079772 | 0.079772 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Asset Transfer from Paras Project | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Boiler Plant and Equipment Single Drum | N.A. | - | 0 | 4.9843 | 4.9843 | 0 | 0 | 0 |  |  | 0 | 0
0 | LAND | N.A. | - | 0 | 23.8051 | 51.8051 | -28 | 0 | 8 |  |  | 8 | -36
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Installation of portable crusher alongwith conveying system at 250 MW CHP, Paras TPS.-(CHP) | N.A. | - | 0 | 1.9889 | 1.9889 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing & Applying Epoxy Painting upto all height to structural steel work in power house area at TPS, Paras-(CIVIL) | N.A. | - | 0 | 5.6803 | 5.6803 | 0 | 0 | 0 |  |  | 0 | 0
0 | Material Handling Equipments | 0 | - | 0 | 0.033747 | 0.033747 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme for supply, erection, commissioning & testing of 7.2 KV SF6 contactor for retrofitting of existing BHEL make VM-12 type 6.6 KV HT circuit breakers of CHP Paras TPS.-(CHP) | N.A. | - | 0 | 2.3705 | 2.3705 | 0 | 0 | 0 |  |  | 0 | 0
0 | SWAS Lab improvement -(C&I) | N.A. | - | 0 | 2.2951 | 2.2951 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, supply, installation and commissioning of High performance energy chain system for Side Arm Charger at CHP 2 X 250 MW Unit 3 & 4 -(CHP) | N.A. | - | 0 | 1.0499 | 1.0499 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Manufacturing, supply, fabricate & erection of coal chutes with extra life weir reistatnce plates -(CHP) | N.A. | - | 0 | 2.3522 | 2.3522 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement and installation of set of internals of reducer gear box of coall mill BBD4772 @ Paras TPS -(BM) | N.A. | - | 0 | 1.788 | 1.788 | 0 | 0 | 0 |  |  | 0 | 0
0 | NON DPR scheme of procurement and installation of spares of non standard gridflex and gearflex couplings for coal mill BBD 4772 at Paras TPS 2x250MW -(BM) | N.A. | - | 0 | 0.90876 | 0.90876 | 0 | 0 | 0 |  |  | 0 | 0
0 | HO Non-DPR-Procurement of ABC powder Type & Foam type composite Fire Extnguisher for Paras TPS | N.A. | - | 0 | 0.5712 | 0.5712 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & replacement of APH baskets at Unit-3 | N.A. | - | 0 | 3.4477 | 3.45 | -0.0022658 | 0 | 0 |  |  | 0 | -0.0022658
0 | Battery Bank 220VDC , 2140Ah for Unit -3 | N.A. | - | 0 | 5.83 | 5.83 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | General Assets | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Furniture & Fixtures | N.A. | - | 0 | 0.71589 | 0.91589 | -0.2 | 0 | 0.1 |  |  | 0.1 | -0.3
0 | Office Equipment | N.A. | - | 0 | 2.1255 | 2.3255 | -0.2 | 0 | 0.1 |  |  | 0.1 | -0.3
0 | RCC Approach Road for CHP at Paras TPS | N.A. | - | 0 | 1.7924 | 1.7924 | 0 | 0 | 0 |  |  | 0 | 0
0 | Vehicles | N.A. | - | 0 | 0.75083 | 0.75083 | 0 | 0 | 0 |  |  | 0 | 0
0 | I.T. Equipment | 0 | - | 0 | 0.74853 | 0.74853 | 0 | 0.1 | 0.1 |  |  | 0.1 | 0
0 | Building | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 1084.7044 | 1116.5584 | -31.854 | 201.61 | 209.81 | 0 | 0 | 209.81 | -40.054
FY 2028-29
a) DPR Schemes
(i) Submitted to MERC
1 | Power supply arrangement at colony & separate 25 KV OHE supply feeding arrangement to BESG siding & provision of Passenger elevators | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 7.1549 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Provision of separate 25 KV OHE supply feeding arrangement to BESG siding at Paras TPS | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 0.3715 | 0.37148 | 0.37148 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | Arrangement of power supply for Paras TPS colony from 250 MW units with stepping down 6.6 KV supply to 3.3 KV. | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 3.6334 | 1.9509 | 1.9509 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Supply & installation of Total 12 nos. passenger elevators at `D’ & `E’ type quarters & administrative building of Paras TPS | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 3.15 | 1.7746 | 1.7746 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Ash Handling Plant augmentation scheme at Paras TPS Unit 3 & 4 | MERC/TECH 1/CAPEX/20142015/01160 | 2014-11-17 | 38.0989 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Ash Handling Plant augmentation scheme at Paras TPS Unit 3 & 4 | MERC/TECH 1/CAPEX/20142015/01160 | 2014-11-17 | 34.6889 | 63.376 | 61.0285 | 2.3475 | 0 | 0 |  |  | 0 | 2.3475 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/01160 | 2014-11-17 | 3.41 | 0.99854 | 0.99854 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | 3rd raising of Ash bund from TBL 273.63 mtr. to 276.63 mtr. with construction of masonry dam | MERC/MSPGCL/CAPEX/20142015/01648 | 2015-02-26 | 9.2104 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | 3rd raising of Ash bund from TBL 273.63 mtr. to 276.63 mtr. with construction of masonry dam | MERC/MSPGCL/CAPEX/20142015/01648 | 2015-02-26 | 8.2519 | 3.3121 | 3.3121 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/CAPEX/20142015/01648 | 2015-02-26 | 0.95855 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Various schemes related to CHP Improvement and Stack Management & Coal Mill Performance Improvement schemes | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 17.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Procurement of apron feeder system, pan & chain Assembly (2 no.’s) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 7.44 | 7.521 | 7.521 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Procurement of Assembly of Impact Crusher complete set with Beater Arm & Head.(1 no.) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.57 | 1.6013 | 1.6013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.3 | Procurement of Slewing Bearing of Stacker Reclaimer. (1 no.) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.45 | 1.4676 | 1.4676 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.4 | Capacity Enhancement of Wagon Tippler at Old CHP. | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 2.86 | 2.9502 | 2.9502 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.5 | Procurement of Bulldozer BD-155 for CHP(1 no.) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.7 | 2.1022 | 2.1022 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.6 | Procurement of Girth Gear and Pinion for BBD 4772 coal mills of 250 MW (1 set) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.6 | 1.6943 | 1.6943 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Procurement of Two Cartridge assembly for Boiler Feed Pump (Type: FK-3B-40) of 250MW Set | MERC/MSPGCL/CAPEX/20162017/04228 | 2017-09-22 | 13.88 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Procurement of Two Cartridge assembly for Boiler Feed Pump (Type: FK-3B-40) of 250MW Set | MERC/MSPGCL/CAPEX/20162017/04228 | 2017-09-22 | 13.88 | 14.0416 | 14.0416 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Replacement of battery bank set, replacement of two complete set of air pre-heater baskets & coal compartment assemblies for 250MW Unit 4 at Paras TPS | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 10.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Replacement of battery bank set to enhance process reliability of 250 MW Unit-4 at Paras TPS. | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 7.54 | 8.4214 | 8.4214 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.2 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-4, Paras TPS. | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 1.78 | 2.45 | 2.45 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.3 | Procurement & Replacement of Coal Compartment Assemblies Baskets at 250 MW Unit-4, Paras TPS. | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 0.75 | 0.56974 | 0.56974 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 0.04 | 0.25586 | 0.25786 | -0.002001 | 0 | 0 |  |  | 0 | -0.002001 | 0 | 0
7 | Procurement & Replacement of complete set of Economizer and LTSH upper & lower coils at Unit-3, Paras TPS | MERC/CAPEX/2019-2020/2 | 2019-05-24 | 10.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Replacement of complete set of economizer (upper & lower) coil assemblies & LTSH (upper & lower) coil assemblies for Unit-3. | MERC/CAPEX/2019-2020/2 | 2019-05-24 | 10.6 | 11.8971 | 11.8971 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/2 | 2019-05-24 | 0.22 | 1.8345 | 1.8345 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | HMI (Human Machine Interface) up gradation of DCS UNIT-3 & 4, WTP (Water Treatment Plant unit-3 & 4 combined PLC system) & AHP (Ash Handling Plant Unit-3 & 4 PLC System), Procurement of girth gear & pinion for optimum availability of auxiliary at Paras TPS | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 11.14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Up-gradation of Existing Max-DNA System (HMI) at Paras TPS (U# 3 & 4). | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 7.12 | 8.8364 | 8.8364 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Up-gradation of GE IP (GE-Fanuc) make PLC system (HMI) installed at WTP at Paras TPS (Combined for U# 3 & 4). | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0.38 | 0.36789 | 0.36789 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.3 | Up-gradation of GE IP (GE-Fanuc) make PLC system (HMI) installed at AHP Unit - 4 at Paras TPS. | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0.48 | 0.45873 | 0.45873 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.4 | Up-gradation of Existing Schneider make PLC (HMI + PLC hardware) installed at AHP Unit - 3 at Paras TPS. | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0.9 | 0.88264 | 0.88264 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.5 | Procurement & installation of Girth Gear & Pinion for coal mill BBD-4772. | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 2.26 | 2.1171 | 2.1171 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0 | 0.45004 | 0.45004 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Complete Track Renewal at Paras TPS | MERC/CAPEX/2019-2020/479 | 2019-08-02 | 12.77 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Complete Track Renewal at Paras TPS | MERC/CAPEX/2019-2020/479 | 2019-08-02 | 12.05 | 16.3958 | 16.3958 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/479 | 2019-08-02 | 0.72 | 0.078332 | 0.078332 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Procurement & Replacement of water wall panels in Unit#4 & Installation of VFD to existing eddy current drive driven coal feeders at 2x250 MW at Paras TPS | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 12.72 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Replacement of water wall panel in Unit-4 Boiler at 2 X 250 MW, PTPS | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 6.49 | 2.7423 | 6.2823 | -3.54 | 0 | 0 |  |  | 0 | -3.54 | 0 | 0
10.2 | Installation of VFD with controller over existing eddy current drives with controller at 2 X 250 MW, PTPS. | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 6.23 | 6.4672 | 6.4672 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 0 | 1.0135 | 1.0135 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Reinforcement & Capacity Enhancement of Old CHP Coal Conveyor Belt Structure from (200 TPH to 360 TPH) at old CHP Paras TPS & Procurement of One No. of Bulldozer & Diesel Hydraulic Locomotive at Paras TPS | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 12.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Capacity Enhancement of Old CHP Conveyor belt from 200 TPH to 360 TPH at Old CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 2.94 | 0 | 2.9382 | -2.9382 | 0 | 0 |  |  | 0 | -2.9382 | 0 | 0
11.2 | Reinforcement of Belt Conveyor structure at Old CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 2.66 | 2.9137 | 2.9137 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.3 | Procurement of Bulldozer at CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 2.31 | 2.4909 | 2.4909 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.4 | Procurement of Diesel Hydraulic Locomotive at CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 3.6 | 3.2208 | 3.2208 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 0.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Flue Gas Desulpherization (FGD) System for Paras Unit No. 3 & 4 | MERC/CAPEX/2020-2021/WFH/SBR/42 | 2020-12-14 | 376.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Flue Gas Desulpherization (FGD) System for Paras Unit No. 3 & 4 | MERC/CAPEX/2020-2021/WFH/SBR/42 | 2020-12-14 | 347.02 | 478.581 | 475.59 | 2.991 | 0 | 0 |  |  | 0 | 2.991 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/42 | 2020-12-14 | 29.04 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Procurement & Installation of complete assembly of Elecon make Gear Boxes, Wagon Tippler Assembly; Design, Supply, Installation, Commissioning & Successful Trial of Link Conveyor from Stackyard to C-2 Conveyor Belt at CHP; Procurement of Bucket Wheel of Stacker Reclaimer for CHP at Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 54.98 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Procurement & Installation of complete assembly of Elecon make Gear Boxes, Wagon Tippler Assembly; Design, Supply, Installation, Commissioning & Successful Trial of Link Conveyor from Stackyard to C-2 Conveyor Belt at CHP; Procurement of Bucket Wheel of Stacker Reclaimer for CHP at Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 32.78 | 11.88 | 11.88 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Procurement of Wagon Tippler Assembly & Installation of the same at CHP at Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 13.9 | 13.9 | 13.9 | 0 | 0 | 0 |  |  | 0 | 0
13.3 | Design, supply, installation, commissioning & successful trial of Link Conveyor from Stackyard to C-2 conveyor belt at CHP, Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 5.93 | 5.93 | 5.93 | 0 | 0 | 0 |  |  | 0 | 0
13.4 | Procurement of bucket wheel of stacker reclaimer for CHP 250MW Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 1.07 | 1.07 | 1.07 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 1.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 3.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.6 | Paras: Procurement of HT Motors(CEP/ACW Motors-I Phase and CW/CHP Motors-II Phase)for U-3&4 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 3.6 | 2.0958 | 2.0958 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 1.235 | 1.235 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.1 | PARAS(U-3 & 4) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 3.8456 | 3.8456 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 2.0276 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.1 | Paras TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 2.0276 | 0 | 2.31 | -2.31 | 0 | 0 |  |  | 0 | -2.31 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender at Paras TPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 2.9191 | 2.9191 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.2 | Normal Multipurpose Fire Tender at Paras TPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.0768 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.1 | TPS Paras | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.0768 | 1.6142 | 1.6142 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 12 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 12.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Enhancing process reliability at U-3 & U-4 at 2X250MW Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete set of Economiser (upper & lower) coil assemblies & LTSH (upper & lower) coil assemblies in Unit-4 (250mw) at Paras TPS. | 0 | - | 0 | 14.18 | 14.18 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & installation of complete discharge assembly of coal mill BBD 4772 In Unit-3&4 at Paras TPS | 0 | - | 0 | 22.51 | 22.51 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, replacement, erection and installation of foundation deck spring of coal mill BBD 4772 for Unit-3&4 at 250 MW at Paras TPS | 0 | - | 0 | 3.36 | 3.36 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of Coal Compartment Assemblies at 250 MW for Unit-3&4, Paras TPS | 0 | - | 0 | 1.77 | 1.77 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of Girth gear and pinion Assemblies at 250 MW Unit-3,4, Paras TPS | 0 | - | 0 | 9.22 | 9.22 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of Coal Mill drive shaft Assemblies at 250 MW Unit-3&4 Paras TPS. | 0 | - | 0 | 7.67 | 7.67 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of Air Pre Heater speed reducer gear box set of internals (assembly) for Unit-3&4. | 0 | - | 0 | 1.33 | 1.33 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of foundation deck spring assembly (vibration isolation system) for ID fan for Unit 3&4 at Paras TPS. | 0 | - | 0 | 2.31 | 2.31 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of CW Pump module with mandatory spares for TM section | 0 | - | 0 | 15.61 | 15.61 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Ash Evacuation System Rehabilitation and improvement of performance & efficiency of Ash Handling System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of old 300NB ash slurry disposal pipeline with new 300NB MSERW pipeline from slurry pump house to surface drain pump house at Paras TPS. | 0 | - | 0 | 6.66 | 6.66 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of old 200nb bottom ash, coarse ash, fly ash conveying pipeline with new 200 NB MSERW pipeline from ash hoppers to slurry tank & SILO AT PTPS. | 0 | - | 0 | 4.7 | 4.7 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of complete assembly of air compressors (T-BTD-JM (4NOS) AND T-BD-QL (6NOS.)) in ash evacuation system in AHP, Paras TPS. | 0 | - | 0 | 3.99 | 3.99 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of complete assembly of SAM make ar-150/510 Pumps (9 nos) for replacement of ash slurry pumps of bottom ash slurry disposal from slurry tank to ash bund in slurry pump house. | 0 | - | 0 | 2.15 | 2.15 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of complete assembly of SAM MAKE ZM-II 530/03 (4 NOS) for replacement of HP pumps of bottom ash & coarse ash evacuation from BA/CA hoppers to slurry tank in ash water pump house. | 0 | - | 0 | 0.89 | 0.89 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of major internal assemblies of weir make GEHO pumps installed at AHP, Paras TPS. | 0 | - | 0 | 13.4 | 13.4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of critical transmission drive systems and fluid couplings internal assemblies for slurry pumps and silo HCSD system installed at AHP, Paras TPS. | 0 | - | 0 | 2.92 | 2.92 | 0 | 0 | 0 |  |  | 0 | 0
0 | Augmentaion/Modification of U-3 & U-4 ESP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Restoration of ESP Fields of Unit- 3 & 4 Paras TPS | 0 | - | 0 | 50 | 50 | 0 | 0 | 0 |  |  | 0 | 0
0 | Performance & Capacity enhancement of Ash handling plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of existing ash slurry disposal pump assembly by higher efficient pump assembly in AHP of Paras TPS | 0 | - | 0 | 12 | 12 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of higher capacity vacuum pumps along with motors to improve availability & performance of fly ash system of AHP Paras TPS | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Modification & Replacement of air drier at AHP Paras TPS | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of existing HT Motors by energy efficient HT Motors In AHP of Paras TPS | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of ash handling plant auxiliaries & systems of Paras TPS | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of DRC Pipeline of fly ash evacuation system of AHP Paras for Availability improvement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of DRC Pipeline of fly ash evacuation system of AHP Paras TPS | 0 | - | 0 | 40 | 40 | 0 | 0 | 0 |  |  | 0 | 0
0 | Structure strengthening of AHP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Work of anticorrosive Painting & Structure strengthening of Ash Handling Plant structures | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
0 | U-3 Boiler Effyciency & Performance improvement schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CAVT & CFD for unit-3 | 0 | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of sky climber assembly for Paras TPS | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of PA fan NDV22 BAB2 rotor assembly with impeller and cone & blade assembly of IGV with rod end assly for IGV control for unit-3. | 0 | - | 0 | 1.51 | 1.51 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement Dampers, shutoff gate assemblies for series 5,6,7 & 8 dampers, ID fan inlet gate, APH flue gas dampers I/L & O/L, APH PA I/L & O/L dampers, APH SA I/L & O/L dampers along with actuators, SADC dampers at wind box with actuators for unit-3 | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of critical high pressure valves, safety valves & control valves for unit-3. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and Replacement of Thermal Insulation of Boiler, Ducts & Steam Pipelines for unit-3 | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement and replacement of HP and B&S Lub oil pumps of coal mills BBD-4772 installed at Paras TPS | 0 | - | 0 | 1.8 | 1.8 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete Coal compartment assly for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 1.3 | 1.3 |  |  | 1.3 | 0
0 | Procurement & replacement of complete APH baskets, HE & CE sector plate, diapharm plate, rotor spool piece, grating assly, all type seals, rack pinion for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 5.5 | 5.5 |  |  | 5.5 | 0
0 | Procurement & replacement of complete set of Final super heater coil assembly for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 12 | 12 |  |  | 12 | 0
0 | Procurement & replacement of complete rotor assembly of FD fan including shaft with brg assly, impeller with oil hydraulic blade adjustment device with blades & coupling for unit-3. | 0 | - | 0 | 0 | 0 | 0 | 2.15 | 2.15 |  |  | 2.15 | 0
0 | U-3 & U-4 Boiler Effyciency, Performance & reliability improvement schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of Coal compartment assly for unit-4. | 0 | - | 0 | 1.1 | 1.1 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and Replacement of Thermal Insulation of Boiler, Ducts & Steam Pipelines for unit-4 | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of critical high pressure valves, safety valves & control valves for unit-4. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | CAVT & CFD for unit-4 | 0 | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement Dampers, shutoff gate assemblies for series 5,6,7 & 8 dampers, ID fan inlet gate, APH flue gas dampers I/L & O/L, APH PA I/L & O/L dampers, APH SA I/L & O/L dampers along with actuators, SADC dampers at wind box with actuators for unit-4 | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete seal air fan assembly of coal mill BBD-4772 (without Motor) installed at Paras TPS | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete set of Final super heater coil assembly for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete Coal compartment assly for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete APH baskets, HE & CE sector plate, diapharm plate, rotor spool piece, grating assly, all type seals, rack pinion for unit-4. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete Coal compartment assly for unit-3 | 0 | - | 0 | 0 | 0 | 0 | 1.4 | 1.4 |  |  | 1.4 | 0
0 | Procurement & replacement of complete set of Re-heater coil (HRH & CRH) assembly for unit-3 | 0 | - | 0 | 0 | 0 | 0 | 12.5 | 12.5 |  |  | 12.5 | 0
0 | ODP plant Process reliability improvement schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping of WT Plant Auxilliaries. | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation of NDCT FILL at 2X250MW Units, Paras TPS | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, engineering, manufacturing, supply , erection and commissioning of degasser unit at Paras TPS | 0 | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Performance improvement of compressors, compressored air drier system & Modification in Air ventilation system at 2x250MW Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping, modification of outdoor ducting of Air ventilation system at 2X250 MW, Paras TPS. | 0 | - | 0 | 16 | 16 | 0 | 0 | 0 |  |  | 0 | 0
0 | Performance improvement of compressors in Unit No.3, Paras TPS. | 0 | - | 0 | 10.3 | 10.3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation of Compressed Air Refrigerated Dryer System for 2X250MW Unit, Paras TPS | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of LP Turbine blades, control fluid pump, AOP, JOP & HP valves for Turbine & its Auxiliaries efficiency improvement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Control Fluid Pumps & AOP of 250MW Unit No. 3 & 4 Paras TPS | 0 | - | 0 | 12 | 12 | 0 | 0 | 0 |  |  | 0 | 0
0 | Moving blades for LPT-2L, 2R, 3L, 3R | 0 | - | 0 | 13.51 | 13.51 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of valves – Main Steam Valves, Extraction Valves, BFP Recirculation Valves, etc. | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
0 | Various schemes for reliability & performance improvement of Electrical & Control system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Water Flow monitoring system of various Location flowmeter at U3&4 Paras TPS | 0 | - | 0 | 5.5 | 5.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of HMI and PLC hardware of Emerson (Former GE IP) make PLC system installed at Main Plant compressor Unit-4(PLC hardware and HMI), Condensate Polishing Unit Unit-3&4(HMI and PLC hardware), Pre-Treatment Plant Unit-4(HMI and PLC hardware) Water Treatment Plant (PLC hardware Unit-3&4) Ash Handling Plant Unit-4(PLC hardware), at Paras TPS. | 0 | - | 0 | 9 | 9 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Vibration Monitoring System server make Baker & Hughes (Former Bently Nevada) installed at Unit-3&4 Paras TPS. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping and Upgradation of PLC hardware of ABB make Online Condenser Tube Cleaning System installed at Unit-3&4 Paras TPS. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of carbon monoxide system in Air Preheater flue gas path at Unit-3&4 Paras TPS | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, erection, commissioning and testing of 24 V 2X2250Ah, 360V 650AH UPS main plant, 360V 100Ah AHP UPS, 220V 125 Ah RWPH Battery at Paras TPS | 0 | - | 0 | 3.671 | 3.671 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of existing FBTS sytem installed at Paras TPS | 0 | - | 0 | 4.456 | 4.456 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement and Installation of Aviation Obstruction lighting system of Chimney and Cooling Towers at Paras TPS | 0 | - | 0 | 2.187 | 2.187 | 0 | 0 | 0 |  |  | 0 | 0
0 | Schemes related to Reduction in auxiliary Power consumption and upgradation of Valves & Instruments of C&I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation and Modification of Colony Electric Supply System to improve availability and reliability of supply system at Paras TPS colony | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply installation of VFD to CEP motors installed at paras TPS. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Mid life overhauling of GCB installed at Paras TPS. | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, installation testig and comissioning of VFD to PA fan motoras installed at Paras TPS. | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
0 | Upgradation of ID fan VFD installed at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1-Upgradation of all pneumatic control valve with smart positioner at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
0 | Scheme-2-Upgradation of HFO mass flow meters at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3-Upgradation of O2 measurement system in Air Preheater inlet /outlet flue gas path and chimney inlet path at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-4-Upgradation of Steam Leak Detecting BHELSONIC system at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Various Civil schemes for Paras TPS Colony | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Attendning internal leakages of residential bulding in colony area at TPS Paras. | 0 | - | 0 | 8.2 | 8.2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing Terrace waterproofing to various buildings in colony area at TPS Paras. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing and laying M.S. pipe line from new STP to WTP at TPS Paras. | 0 | - | 0 | 0.8 | 0.8 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Water Supply GI Pipe line in colony area at TPS Paras | 0 | - | 0 | 0.9 | 0.9 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing of Colony Internal roads by BT at TPS Paras | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing alluminium window to NF,NE,ND & Repairing of existing alluminium window and cupboard of resendial buildings in colony area at TPS Paras. | 0 | - | 0 | 2.7 | 2.7 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing External Painting to Resenditial buildings in colony area at TPS Paras. | 0 | - | 0 | 2.9 | 2.9 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Hospital Bulding in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
0 | Construction of Community Hall in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 1.1 | 1.1 |  |  | 1.1 | 0
0 | Development of Play Ground with Stage in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0.4 | 0.4 |  |  | 0.4 | 0
0 | Beutification of colony area by providing Gardens and plantation in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of drain along internal roads in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Various Civil schemes related to Plant area of Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing waterproofing to terrace of various buildings in plant area at TPS Paras. | 0 | - | 0 | 3.9 | 3.9 | 0 | 0 | 0 |  |  | 0 | 0
0 | Attedning internal leakages and modification of Toilets in Plant area at TPS Paras. | 0 | - | 0 | 1.6 | 1.6 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting and carben rapping of cooling tower coloumn at TPS Paras | 0 | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Attendning internal leakages of Parasdeep building along with renovatation of Toilets at TPS Paras. | 0 | - | 0 | 0.25 | 0.25 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of water supply pipe lines in plant area at TPS Paras. | 0 | - | 0 | 0.9 | 0.9 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing External Painting to various buildings in plant area at TPS Paras. | 0 | - | 0 | 0.6 | 0.6 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Walk Way from Plant Gate to Service Building at TPS Paras | 0 | - | 0 | 0.4 | 0.4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing & fixing modular kitchen (Trolleys) in B Type, CM Type, DM Type and EM Type quarters at TPS Paras. | 0 | - | 0 | 3.5 | 3.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of drain with Footpath from CE Bunglow to Main Road at TPS Paras | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of drain with Footpath from colony gate to Chummery Building at TPS Paras | 0 | - | 0 | 1.6 | 1.6 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing Internal Painting to Resenditial buildings in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
0 | Renovation of Entrance road from T point to Colony Gate at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 4 | 4 |  |  | 4 | 0
0 | Repairing of Plant Internal roads by BT at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IB recommendation at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | “Construction of RCC Compound wall as per IB recommendation at Paras TPS.” | 0 | - | 0 | 4.86 | 4.86 | 0 | 0 | 0 |  |  | 0 | 0
0 | “Construction of Watch towers along periphery compound wall as per IB recommendation at TPS Paras.” | 0 | - | 0 | 2.3 | 2.3 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at 2 x 250 MW Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at 2 x 250 MW Paras TPS | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
0 | FGMO related Capex scheme | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FGMO related Capex scheme | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Covid-19 Pandemic Related Work | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Medical Oxygen Gen. & Bottling Plant | N.A. | - | 0 | 2.6741 | 2.6741 | 0 | 0 | 0 |  |  | 0 | 0
0 | Empty Std size Medical Gr. Oxygen Cyl. | N.A. | - | 0 | 0.41133 | 0.41133 | 0 | 0 | 0 |  |  | 0 | 0
0 | Oxy Installation&Commissioning of Plant | N.A. | - | 0 | 0.079772 | 0.079772 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Asset Transfer from Paras Project | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Boiler Plant and Equipment Single Drum | N.A. | - | 0 | 4.9843 | 4.9843 | 0 | 0 | 0 |  |  | 0 | 0
0 | LAND | N.A. | - | 0 | 23.8051 | 59.8051 | -36 | 0 | 8.5 |  |  | 8.5 | -44.5
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Installation of portable crusher alongwith conveying system at 250 MW CHP, Paras TPS.-(CHP) | N.A. | - | 0 | 1.9889 | 1.9889 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing & Applying Epoxy Painting upto all height to structural steel work in power house area at TPS, Paras-(CIVIL) | N.A. | - | 0 | 5.6803 | 5.6803 | 0 | 0 | 0 |  |  | 0 | 0
0 | Material Handling Equipments | 0 | - | 0 | 0.033747 | 0.033747 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme for supply, erection, commissioning & testing of 7.2 KV SF6 contactor for retrofitting of existing BHEL make VM-12 type 6.6 KV HT circuit breakers of CHP Paras TPS.-(CHP) | N.A. | - | 0 | 2.3705 | 2.3705 | 0 | 0 | 0 |  |  | 0 | 0
0 | SWAS Lab improvement -(C&I) | N.A. | - | 0 | 2.2951 | 2.2951 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, supply, installation and commissioning of High performance energy chain system for Side Arm Charger at CHP 2 X 250 MW Unit 3 & 4 -(CHP) | N.A. | - | 0 | 1.0499 | 1.0499 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Manufacturing, supply, fabricate & erection of coal chutes with extra life weir reistatnce plates -(CHP) | N.A. | - | 0 | 2.3522 | 2.3522 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement and installation of set of internals of reducer gear box of coall mill BBD4772 @ Paras TPS -(BM) | N.A. | - | 0 | 1.788 | 1.788 | 0 | 0 | 0 |  |  | 0 | 0
0 | NON DPR scheme of procurement and installation of spares of non standard gridflex and gearflex couplings for coal mill BBD 4772 at Paras TPS 2x250MW -(BM) | N.A. | - | 0 | 0.90876 | 0.90876 | 0 | 0 | 0 |  |  | 0 | 0
0 | HO Non-DPR-Procurement of ABC powder Type & Foam type composite Fire Extnguisher for Paras TPS | N.A. | - | 0 | 0.5712 | 0.5712 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & replacement of APH baskets at Unit-3 | N.A. | - | 0 | 3.4477 | 3.45 | -0.0022658 | 0 | 0 |  |  | 0 | -0.0022658
0 | Battery Bank 220VDC , 2140Ah for Unit -3 | N.A. | - | 0 | 5.83 | 5.83 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | General Assets | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Furniture & Fixtures | N.A. | - | 0 | 0.71589 | 1.0159 | -0.3 | 0 | 0.1 |  |  | 0.1 | -0.4
0 | Office Equipment | N.A. | - | 0 | 2.1255 | 2.4255 | -0.3 | 0 | 0.1 |  |  | 0.1 | -0.4
0 | RCC Approach Road for CHP at Paras TPS | N.A. | - | 0 | 1.7924 | 1.7924 | 0 | 0 | 0 |  |  | 0 | 0
0 | Vehicles | N.A. | - | 0 | 0.75083 | 0.75083 | 0 | 0 | 0 |  |  | 0 | 0
0 | I.T. Equipment | 0 | - | 0 | 0.84853 | 0.84853 | 0 | 0.1 | 0.1 |  |  | 0.1 | 0
0 | Building | 0 | - | 0 | 0 | 0 | 0 | 0 | 2.1 |  |  | 2.1 | -2.1
| Total |  |  |  | 1286.3144 | 1326.3684 | -40.054 | 59.45 | 70.25 | 0 | 0 | 70.25 | -50.854
FY 2029-30
a) DPR Schemes
(i) Submitted to MERC
1 | Power supply arrangement at colony & separate 25 KV OHE supply feeding arrangement to BESG siding & provision of Passenger elevators | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 7.1549 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Provision of separate 25 KV OHE supply feeding arrangement to BESG siding at Paras TPS | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 0.3715 | 0.37148 | 0.37148 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | Arrangement of power supply for Paras TPS colony from 250 MW units with stepping down 6.6 KV supply to 3.3 KV. | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 3.6334 | 1.9509 | 1.9509 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Supply & installation of Total 12 nos. passenger elevators at `D’ & `E’ type quarters & administrative building of Paras TPS | MERC/TECH 1/CAPEX/20132014/00030 | 2014-04-02 | 3.15 | 1.7746 | 1.7746 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Ash Handling Plant augmentation scheme at Paras TPS Unit 3 & 4 | MERC/TECH 1/CAPEX/20142015/01160 | 2014-11-17 | 38.0989 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Ash Handling Plant augmentation scheme at Paras TPS Unit 3 & 4 | MERC/TECH 1/CAPEX/20142015/01160 | 2014-11-17 | 34.6889 | 63.376 | 61.0285 | 2.3475 | 0 | 0 |  |  | 0 | 2.3475 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/01160 | 2014-11-17 | 3.41 | 0.99854 | 0.99854 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | 3rd raising of Ash bund from TBL 273.63 mtr. to 276.63 mtr. with construction of masonry dam | MERC/MSPGCL/CAPEX/20142015/01648 | 2015-02-26 | 9.2104 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | 3rd raising of Ash bund from TBL 273.63 mtr. to 276.63 mtr. with construction of masonry dam | MERC/MSPGCL/CAPEX/20142015/01648 | 2015-02-26 | 8.2519 | 3.3121 | 3.3121 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/CAPEX/20142015/01648 | 2015-02-26 | 0.95855 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Various schemes related to CHP Improvement and Stack Management & Coal Mill Performance Improvement schemes | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 17.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Procurement of apron feeder system, pan & chain Assembly (2 no.’s) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 7.44 | 7.521 | 7.521 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Procurement of Assembly of Impact Crusher complete set with Beater Arm & Head.(1 no.) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.57 | 1.6013 | 1.6013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.3 | Procurement of Slewing Bearing of Stacker Reclaimer. (1 no.) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.45 | 1.4676 | 1.4676 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.4 | Capacity Enhancement of Wagon Tippler at Old CHP. | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 2.86 | 2.9502 | 2.9502 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.5 | Procurement of Bulldozer BD-155 for CHP(1 no.) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.7 | 2.1022 | 2.1022 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.6 | Procurement of Girth Gear and Pinion for BBD 4772 coal mills of 250 MW (1 set) | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.6 | 1.6943 | 1.6943 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/CAPEX/20152016/00907 | 2016-11-29 | 1.12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Procurement of Two Cartridge assembly for Boiler Feed Pump (Type: FK-3B-40) of 250MW Set | MERC/MSPGCL/CAPEX/20162017/04228 | 2017-09-22 | 13.88 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Procurement of Two Cartridge assembly for Boiler Feed Pump (Type: FK-3B-40) of 250MW Set | MERC/MSPGCL/CAPEX/20162017/04228 | 2017-09-22 | 13.88 | 14.0416 | 14.0416 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Replacement of battery bank set, replacement of two complete set of air pre-heater baskets & coal compartment assemblies for 250MW Unit 4 at Paras TPS | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 10.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Replacement of battery bank set to enhance process reliability of 250 MW Unit-4 at Paras TPS. | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 7.54 | 8.4214 | 8.4214 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.2 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-4, Paras TPS. | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 1.78 | 2.45 | 2.45 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.3 | Procurement & Replacement of Coal Compartment Assemblies Baskets at 250 MW Unit-4, Paras TPS. | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 0.75 | 0.56974 | 0.56974 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/0137 | 2019-05-15 | 0.04 | 0.25586 | 0.25786 | -0.002001 | 0 | 0 |  |  | 0 | -0.002001 | 0 | 0
7 | Procurement & Replacement of complete set of Economizer and LTSH upper & lower coils at Unit-3, Paras TPS | MERC/CAPEX/2019-2020/2 | 2019-05-24 | 10.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Replacement of complete set of economizer (upper & lower) coil assemblies & LTSH (upper & lower) coil assemblies for Unit-3. | MERC/CAPEX/2019-2020/2 | 2019-05-24 | 10.6 | 11.8971 | 11.8971 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/2 | 2019-05-24 | 0.22 | 1.8345 | 1.8345 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | HMI (Human Machine Interface) up gradation of DCS UNIT-3 & 4, WTP (Water Treatment Plant unit-3 & 4 combined PLC system) & AHP (Ash Handling Plant Unit-3 & 4 PLC System), Procurement of girth gear & pinion for optimum availability of auxiliary at Paras TPS | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 11.14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Up-gradation of Existing Max-DNA System (HMI) at Paras TPS (U# 3 & 4). | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 7.12 | 8.8364 | 8.8364 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Up-gradation of GE IP (GE-Fanuc) make PLC system (HMI) installed at WTP at Paras TPS (Combined for U# 3 & 4). | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0.38 | 0.36789 | 0.36789 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.3 | Up-gradation of GE IP (GE-Fanuc) make PLC system (HMI) installed at AHP Unit - 4 at Paras TPS. | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0.48 | 0.45873 | 0.45873 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.4 | Up-gradation of Existing Schneider make PLC (HMI + PLC hardware) installed at AHP Unit - 3 at Paras TPS. | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0.9 | 0.88264 | 0.88264 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.5 | Procurement & installation of Girth Gear & Pinion for coal mill BBD-4772. | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 2.26 | 2.1171 | 2.1171 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/644 | 2019-08-26 | 0 | 0.45004 | 0.45004 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Complete Track Renewal at Paras TPS | MERC/CAPEX/2019-2020/479 | 2019-08-02 | 12.77 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Complete Track Renewal at Paras TPS | MERC/CAPEX/2019-2020/479 | 2019-08-02 | 12.05 | 16.3958 | 16.3958 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/479 | 2019-08-02 | 0.72 | 0.078332 | 0.078332 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Procurement & Replacement of water wall panels in Unit#4 & Installation of VFD to existing eddy current drive driven coal feeders at 2x250 MW at Paras TPS | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 12.72 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Replacement of water wall panel in Unit-4 Boiler at 2 X 250 MW, PTPS | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 6.49 | 2.7423 | 6.2823 | -3.54 | 0 | 0 |  |  | 0 | -3.54 | 0 | 0
10.2 | Installation of VFD with controller over existing eddy current drives with controller at 2 X 250 MW, PTPS. | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 6.23 | 6.4672 | 6.4672 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/664 | 2019-08-28 | 0 | 1.0135 | 1.0135 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Reinforcement & Capacity Enhancement of Old CHP Coal Conveyor Belt Structure from (200 TPH to 360 TPH) at old CHP Paras TPS & Procurement of One No. of Bulldozer & Diesel Hydraulic Locomotive at Paras TPS | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 12.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Capacity Enhancement of Old CHP Conveyor belt from 200 TPH to 360 TPH at Old CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 2.94 | 0 | 2.9382 | -2.9382 | 0 | 0 |  |  | 0 | -2.9382 | 0 | 0
11.2 | Reinforcement of Belt Conveyor structure at Old CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 2.66 | 2.9137 | 2.9137 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.3 | Procurement of Bulldozer at CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 2.31 | 2.4909 | 2.4909 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.4 | Procurement of Diesel Hydraulic Locomotive at CHP, Paras TPS. | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 3.6 | 3.2208 | 3.2208 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-22/SBR/20 | 2021-11-09 | 0.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Flue Gas Desulpherization (FGD) System for Paras Unit No. 3 & 4 | MERC/CAPEX/2020-2021/WFH/SBR/42 | 2020-12-14 | 376.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Flue Gas Desulpherization (FGD) System for Paras Unit No. 3 & 4 | MERC/CAPEX/2020-2021/WFH/SBR/42 | 2020-12-14 | 347.02 | 478.581 | 475.59 | 2.991 | 0 | 0 |  |  | 0 | 2.991 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/42 | 2020-12-14 | 29.04 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Procurement & Installation of complete assembly of Elecon make Gear Boxes, Wagon Tippler Assembly; Design, Supply, Installation, Commissioning & Successful Trial of Link Conveyor from Stackyard to C-2 Conveyor Belt at CHP; Procurement of Bucket Wheel of Stacker Reclaimer for CHP at Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 54.98 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Procurement & Installation of complete assembly of Elecon make Gear Boxes, Wagon Tippler Assembly; Design, Supply, Installation, Commissioning & Successful Trial of Link Conveyor from Stackyard to C-2 Conveyor Belt at CHP; Procurement of Bucket Wheel of Stacker Reclaimer for CHP at Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 32.78 | 11.88 | 11.88 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Procurement of Wagon Tippler Assembly & Installation of the same at CHP at Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 13.9 | 13.9 | 13.9 | 0 | 0 | 0 |  |  | 0 | 0
13.3 | Design, supply, installation, commissioning & successful trial of Link Conveyor from Stackyard to C-2 conveyor belt at CHP, Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 5.93 | 5.93 | 5.93 | 0 | 0 | 0 |  |  | 0 | 0
13.4 | Procurement of bucket wheel of stacker reclaimer for CHP 250MW Paras TPS | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 1.07 | 1.07 | 1.07 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2024-25/0325 | 2024-05-30 | 1.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 3.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.6 | Paras: Procurement of HT Motors(CEP/ACW Motors-I Phase and CW/CHP Motors-II Phase)for U-3&4 | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 3.6 | 2.0958 | 2.0958 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 1.235 | 1.235 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.1 | PARAS(U-3 & 4) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 3.9773 | 3.8456 | 3.8456 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 2.0276 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.1 | Paras TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 2.0276 | 0 | 2.31 | -2.31 | 0 | 0 |  |  | 0 | -2.31 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender at Paras TPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 2.9191 | 2.9191 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.2 | Normal Multipurpose Fire Tender at Paras TPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.0768 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.1 | TPS Paras | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.0768 | 1.6142 | 1.6142 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 12 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 12.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Enhancing process reliability at U-3 & U-4 at 2X250MW Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete set of Economiser (upper & lower) coil assemblies & LTSH (upper & lower) coil assemblies in Unit-4 (250mw) at Paras TPS. | 0 | - | 0 | 14.18 | 14.18 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & installation of complete discharge assembly of coal mill BBD 4772 In Unit-3&4 at Paras TPS | 0 | - | 0 | 22.51 | 22.51 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, replacement, erection and installation of foundation deck spring of coal mill BBD 4772 for Unit-3&4 at 250 MW at Paras TPS | 0 | - | 0 | 3.36 | 3.36 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of Coal Compartment Assemblies at 250 MW for Unit-3&4, Paras TPS | 0 | - | 0 | 1.77 | 1.77 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of Girth gear and pinion Assemblies at 250 MW Unit-3,4, Paras TPS | 0 | - | 0 | 9.22 | 9.22 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of Coal Mill drive shaft Assemblies at 250 MW Unit-3&4 Paras TPS. | 0 | - | 0 | 7.67 | 7.67 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of Air Pre Heater speed reducer gear box set of internals (assembly) for Unit-3&4. | 0 | - | 0 | 1.33 | 1.33 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of foundation deck spring assembly (vibration isolation system) for ID fan for Unit 3&4 at Paras TPS. | 0 | - | 0 | 2.31 | 2.31 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of CW Pump module with mandatory spares for TM section | 0 | - | 0 | 15.61 | 15.61 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Ash Evacuation System Rehabilitation and improvement of performance & efficiency of Ash Handling System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of old 300NB ash slurry disposal pipeline with new 300NB MSERW pipeline from slurry pump house to surface drain pump house at Paras TPS. | 0 | - | 0 | 6.66 | 6.66 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of old 200nb bottom ash, coarse ash, fly ash conveying pipeline with new 200 NB MSERW pipeline from ash hoppers to slurry tank & SILO AT PTPS. | 0 | - | 0 | 4.7 | 4.7 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of complete assembly of air compressors (T-BTD-JM (4NOS) AND T-BD-QL (6NOS.)) in ash evacuation system in AHP, Paras TPS. | 0 | - | 0 | 3.99 | 3.99 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of complete assembly of SAM make ar-150/510 Pumps (9 nos) for replacement of ash slurry pumps of bottom ash slurry disposal from slurry tank to ash bund in slurry pump house. | 0 | - | 0 | 2.15 | 2.15 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of complete assembly of SAM MAKE ZM-II 530/03 (4 NOS) for replacement of HP pumps of bottom ash & coarse ash evacuation from BA/CA hoppers to slurry tank in ash water pump house. | 0 | - | 0 | 0.89 | 0.89 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of major internal assemblies of weir make GEHO pumps installed at AHP, Paras TPS. | 0 | - | 0 | 13.4 | 13.4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of critical transmission drive systems and fluid couplings internal assemblies for slurry pumps and silo HCSD system installed at AHP, Paras TPS. | 0 | - | 0 | 2.92 | 2.92 | 0 | 0 | 0 |  |  | 0 | 0
0 | Augmentaion/Modification of U-3 & U-4 ESP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Restoration of ESP Fields of Unit- 3 & 4 Paras TPS | 0 | - | 0 | 50 | 50 | 0 | 0 | 0 |  |  | 0 | 0
0 | Performance & Capacity enhancement of Ash handling plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of existing ash slurry disposal pump assembly by higher efficient pump assembly in AHP of Paras TPS | 0 | - | 0 | 12 | 12 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of higher capacity vacuum pumps along with motors to improve availability & performance of fly ash system of AHP Paras TPS | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Modification & Replacement of air drier at AHP Paras TPS | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of existing HT Motors by energy efficient HT Motors In AHP of Paras TPS | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of ash handling plant auxiliaries & systems of Paras TPS | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of DRC Pipeline of fly ash evacuation system of AHP Paras for Availability improvement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & Replacement of DRC Pipeline of fly ash evacuation system of AHP Paras TPS | 0 | - | 0 | 40 | 40 | 0 | 0 | 0 |  |  | 0 | 0
0 | Structure strengthening of AHP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Work of anticorrosive Painting & Structure strengthening of Ash Handling Plant structures | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
0 | U-3 Boiler Effyciency & Performance improvement schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CAVT & CFD for unit-3 | 0 | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of sky climber assembly for Paras TPS | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of PA fan NDV22 BAB2 rotor assembly with impeller and cone & blade assembly of IGV with rod end assly for IGV control for unit-3. | 0 | - | 0 | 1.51 | 1.51 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement Dampers, shutoff gate assemblies for series 5,6,7 & 8 dampers, ID fan inlet gate, APH flue gas dampers I/L & O/L, APH PA I/L & O/L dampers, APH SA I/L & O/L dampers along with actuators, SADC dampers at wind box with actuators for unit-3 | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of critical high pressure valves, safety valves & control valves for unit-3. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and Replacement of Thermal Insulation of Boiler, Ducts & Steam Pipelines for unit-3 | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement and replacement of HP and B&S Lub oil pumps of coal mills BBD-4772 installed at Paras TPS | 0 | - | 0 | 1.8 | 1.8 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete Coal compartment assly for unit-3. | 0 | - | 0 | 1.3 | 1.3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete APH baskets, HE & CE sector plate, diapharm plate, rotor spool piece, grating assly, all type seals, rack pinion for unit-3. | 0 | - | 0 | 5.5 | 5.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete set of Final super heater coil assembly for unit-3. | 0 | - | 0 | 12 | 12 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete rotor assembly of FD fan including shaft with brg assly, impeller with oil hydraulic blade adjustment device with blades & coupling for unit-3. | 0 | - | 0 | 2.15 | 2.15 | 0 | 0 | 0 |  |  | 0 | 0
0 | U-3 & U-4 Boiler Effyciency, Performance & reliability improvement schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of Coal compartment assly for unit-4. | 0 | - | 0 | 1.1 | 1.1 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and Replacement of Thermal Insulation of Boiler, Ducts & Steam Pipelines for unit-4 | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of critical high pressure valves, safety valves & control valves for unit-4. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | CAVT & CFD for unit-4 | 0 | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement Dampers, shutoff gate assemblies for series 5,6,7 & 8 dampers, ID fan inlet gate, APH flue gas dampers I/L & O/L, APH PA I/L & O/L dampers, APH SA I/L & O/L dampers along with actuators, SADC dampers at wind box with actuators for unit-4 | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete seal air fan assembly of coal mill BBD-4772 (without Motor) installed at Paras TPS | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete set of Final super heater coil assembly for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 12.5 | 12.5 |  |  | 12.5 | 0
0 | Procurement & replacement of complete Coal compartment assly for unit-4 | 0 | - | 0 | 0 | 0 | 0 | 1.3 | 1.3 |  |  | 1.3 | 0
0 | Procurement & replacement of complete APH baskets, HE & CE sector plate, diapharm plate, rotor spool piece, grating assly, all type seals, rack pinion for unit-4. | 0 | - | 0 | 0 | 0 | 0 | 6 | 6 |  |  | 6 | 0
0 | Procurement & replacement of complete Coal compartment assly for unit-3 | 0 | - | 0 | 1.4 | 1.4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete set of Re-heater coil (HRH & CRH) assembly for unit-3 | 0 | - | 0 | 12.5 | 12.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | ODP plant Process reliability improvement schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping of WT Plant Auxilliaries. | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation of NDCT FILL at 2X250MW Units, Paras TPS | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, engineering, manufacturing, supply , erection and commissioning of degasser unit at Paras TPS | 0 | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Performance improvement of compressors, compressored air drier system & Modification in Air ventilation system at 2x250MW Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping, modification of outdoor ducting of Air ventilation system at 2X250 MW, Paras TPS. | 0 | - | 0 | 16 | 16 | 0 | 0 | 0 |  |  | 0 | 0
0 | Performance improvement of compressors in Unit No.3, Paras TPS. | 0 | - | 0 | 10.3 | 10.3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation of Compressed Air Refrigerated Dryer System for 2X250MW Unit, Paras TPS | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of LP Turbine blades, control fluid pump, AOP, JOP & HP valves for Turbine & its Auxiliaries efficiency improvement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Control Fluid Pumps & AOP of 250MW Unit No. 3 & 4 Paras TPS | 0 | - | 0 | 12 | 12 | 0 | 0 | 0 |  |  | 0 | 0
0 | Moving blades for LPT-2L, 2R, 3L, 3R | 0 | - | 0 | 13.51 | 13.51 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of valves – Main Steam Valves, Extraction Valves, BFP Recirculation Valves, etc. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Various schemes for reliability & performance improvement of Electrical & Control system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Water Flow monitoring system of various Location flowmeter at U3&4 Paras TPS | 0 | - | 0 | 5.5 | 5.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of HMI and PLC hardware of Emerson (Former GE IP) make PLC system installed at Main Plant compressor Unit-4(PLC hardware and HMI), Condensate Polishing Unit Unit-3&4(HMI and PLC hardware), Pre-Treatment Plant Unit-4(HMI and PLC hardware) Water Treatment Plant (PLC hardware Unit-3&4) Ash Handling Plant Unit-4(PLC hardware), at Paras TPS. | 0 | - | 0 | 9 | 9 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Vibration Monitoring System server make Baker & Hughes (Former Bently Nevada) installed at Unit-3&4 Paras TPS. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping and Upgradation of PLC hardware of ABB make Online Condenser Tube Cleaning System installed at Unit-3&4 Paras TPS. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of carbon monoxide system in Air Preheater flue gas path at Unit-3&4 Paras TPS | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, erection, commissioning and testing of 24 V 2X2250Ah, 360V 650AH UPS main plant, 360V 100Ah AHP UPS, 220V 125 Ah RWPH Battery at Paras TPS | 0 | - | 0 | 3.671 | 3.671 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of existing FBTS sytem installed at Paras TPS | 0 | - | 0 | 4.456 | 4.456 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement and Installation of Aviation Obstruction lighting system of Chimney and Cooling Towers at Paras TPS | 0 | - | 0 | 2.187 | 2.187 | 0 | 0 | 0 |  |  | 0 | 0
0 | Schemes related to Reduction in auxiliary Power consumption and upgradation of Valves & Instruments of C&I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation and Modification of Colony Electric Supply System to improve availability and reliability of supply system at Paras TPS colony | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply installation of VFD to CEP motors installed at paras TPS. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Mid life overhauling of GCB installed at Paras TPS. | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, installation testig and comissioning of VFD to PA fan motoras installed at Paras TPS. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of ID fan VFD installed at Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 15 | 15 |  |  | 15 | 0
0 | Scheme-1-Upgradation of all pneumatic control valve with smart positioner at Unit-3&4 Paras TPS | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2-Upgradation of HFO mass flow meters at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
0 | Scheme-3-Upgradation of O2 measurement system in Air Preheater inlet /outlet flue gas path and chimney inlet path at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
0 | Scheme-4-Upgradation of Steam Leak Detecting BHELSONIC system at Unit-3&4 Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
0 | Various Civil schemes for Paras TPS Colony | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Attendning internal leakages of residential bulding in colony area at TPS Paras. | 0 | - | 0 | 8.2 | 8.2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing Terrace waterproofing to various buildings in colony area at TPS Paras. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing and laying M.S. pipe line from new STP to WTP at TPS Paras. | 0 | - | 0 | 0.8 | 0.8 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Water Supply GI Pipe line in colony area at TPS Paras | 0 | - | 0 | 0.9 | 0.9 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing of Colony Internal roads by BT at TPS Paras | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing alluminium window to NF,NE,ND & Repairing of existing alluminium window and cupboard of resendial buildings in colony area at TPS Paras. | 0 | - | 0 | 2.7 | 2.7 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing External Painting to Resenditial buildings in colony area at TPS Paras. | 0 | - | 0 | 2.9 | 2.9 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Hospital Bulding in colony area at TPS Paras | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Community Hall in colony area at TPS Paras | 0 | - | 0 | 1.1 | 1.1 | 0 | 0 | 0 |  |  | 0 | 0
0 | Development of Play Ground with Stage in colony area at TPS Paras | 0 | - | 0 | 0.4 | 0.4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Beutification of colony area by providing Gardens and plantation in colony area at TPS Paras. | 0 | - | 0 | 0 | 0 | 0 | 0.2 | 0.2 |  |  | 0.2 | 0
0 | Construction of drain along internal roads in colony area at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 2.3 | 2.3 |  |  | 2.3 | 0
0 | Various Civil schemes related to Plant area of Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing waterproofing to terrace of various buildings in plant area at TPS Paras. | 0 | - | 0 | 3.9 | 3.9 | 0 | 0 | 0 |  |  | 0 | 0
0 | Attedning internal leakages and modification of Toilets in Plant area at TPS Paras. | 0 | - | 0 | 1.6 | 1.6 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting and carben rapping of cooling tower coloumn at TPS Paras | 0 | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Attendning internal leakages of Parasdeep building along with renovatation of Toilets at TPS Paras. | 0 | - | 0 | 0.25 | 0.25 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of water supply pipe lines in plant area at TPS Paras. | 0 | - | 0 | 0.9 | 0.9 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing External Painting to various buildings in plant area at TPS Paras. | 0 | - | 0 | 0.6 | 0.6 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Walk Way from Plant Gate to Service Building at TPS Paras | 0 | - | 0 | 0.4 | 0.4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing & fixing modular kitchen (Trolleys) in B Type, CM Type, DM Type and EM Type quarters at TPS Paras. | 0 | - | 0 | 3.5 | 3.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of drain with Footpath from CE Bunglow to Main Road at TPS Paras | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of drain with Footpath from colony gate to Chummery Building at TPS Paras | 0 | - | 0 | 1.6 | 1.6 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing Internal Painting to Resenditial buildings in colony area at TPS Paras. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation of Entrance road from T point to Colony Gate at TPS Paras. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing of Plant Internal roads by BT at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 4.65 | 4.65 |  |  | 4.65 | 0
0 | IB recommendation at TPS Paras | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | “Construction of RCC Compound wall as per IB recommendation at Paras TPS.” | 0 | - | 0 | 4.86 | 4.86 | 0 | 0 | 0 |  |  | 0 | 0
0 | “Construction of Watch towers along periphery compound wall as per IB recommendation at TPS Paras.” | 0 | - | 0 | 2.3 | 2.3 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at 2 x 250 MW Paras TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at 2 x 250 MW Paras TPS | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
0 | FGMO related Capex scheme | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | FGMO related Capex scheme | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Covid-19 Pandemic Related Work | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Medical Oxygen Gen. & Bottling Plant | N.A. | - | 0 | 2.6741 | 2.6741 | 0 | 0 | 0 |  |  | 0 | 0
0 | Empty Std size Medical Gr. Oxygen Cyl. | N.A. | - | 0 | 0.41133 | 0.41133 | 0 | 0 | 0 |  |  | 0 | 0
0 | Oxy Installation&Commissioning of Plant | N.A. | - | 0 | 0.079772 | 0.079772 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Asset Transfer from Paras Project | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Boiler Plant and Equipment Single Drum | N.A. | - | 0 | 4.9843 | 4.9843 | 0 | 0 | 0 |  |  | 0 | 0
0 | LAND | N.A. | - | 0 | 23.8051 | 68.3051 | -44.5 | 0 | 8.5 |  |  | 8.5 | -53
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Installation of portable crusher alongwith conveying system at 250 MW CHP, Paras TPS.-(CHP) | N.A. | - | 0 | 1.9889 | 1.9889 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing & Applying Epoxy Painting upto all height to structural steel work in power house area at TPS, Paras-(CIVIL) | N.A. | - | 0 | 5.6803 | 5.6803 | 0 | 0 | 0 |  |  | 0 | 0
0 | Material Handling Equipments | 0 | - | 0 | 0.033747 | 0.033747 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme for supply, erection, commissioning & testing of 7.2 KV SF6 contactor for retrofitting of existing BHEL make VM-12 type 6.6 KV HT circuit breakers of CHP Paras TPS.-(CHP) | N.A. | - | 0 | 2.3705 | 2.3705 | 0 | 0 | 0 |  |  | 0 | 0
0 | SWAS Lab improvement -(C&I) | N.A. | - | 0 | 2.2951 | 2.2951 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, supply, installation and commissioning of High performance energy chain system for Side Arm Charger at CHP 2 X 250 MW Unit 3 & 4 -(CHP) | N.A. | - | 0 | 1.0499 | 1.0499 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Manufacturing, supply, fabricate & erection of coal chutes with extra life weir reistatnce plates -(CHP) | N.A. | - | 0 | 2.3522 | 2.3522 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement and installation of set of internals of reducer gear box of coall mill BBD4772 @ Paras TPS -(BM) | N.A. | - | 0 | 1.788 | 1.788 | 0 | 0 | 0 |  |  | 0 | 0
0 | NON DPR scheme of procurement and installation of spares of non standard gridflex and gearflex couplings for coal mill BBD 4772 at Paras TPS 2x250MW -(BM) | N.A. | - | 0 | 0.90876 | 0.90876 | 0 | 0 | 0 |  |  | 0 | 0
0 | HO Non-DPR-Procurement of ABC powder Type & Foam type composite Fire Extnguisher for Paras TPS | N.A. | - | 0 | 0.5712 | 0.5712 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & replacement of APH baskets at Unit-3 | N.A. | - | 0 | 3.4477 | 3.45 | -0.0022658 | 0 | 0 |  |  | 0 | -0.0022658
0 | Battery Bank 220VDC , 2140Ah for Unit -3 | N.A. | - | 0 | 5.83 | 5.83 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | General Assets | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Furniture & Fixtures | N.A. | - | 0 | 0.71589 | 1.1159 | -0.4 | 0 | 0.1 |  |  | 0.1 | -0.5
0 | Office Equipment | N.A. | - | 0 | 2.1255 | 2.5255 | -0.4 | 0 | 0.1 |  |  | 0.1 | -0.5
0 | RCC Approach Road for CHP at Paras TPS | N.A. | - | 0 | 1.7924 | 1.7924 | 0 | 0 | 0 |  |  | 0 | 0
0 | Vehicles | N.A. | - | 0 | 0.75083 | 0.75083 | 0 | 0 | 0 |  |  | 0 | 0
0 | I.T. Equipment | 0 | - | 0 | 0.94853 | 0.94853 | 0 | 0.1 | 0.1 |  |  | 0.1 | 0
0 | Building | 0 | - | 0 | 0 | 2.1 | -2.1 | 0 | 0 |  |  | 0 | -2.1
| Total |  |  |  | 1345.7644 | 1396.6184 | -50.854 | 46.55 | 55.25 | 0 | 0 | 55.25 | -59.554