## F4
MSPGCL: Parli 8
MTR Petition Formats - Generation
Form 4: Summary of Capital Expenditure and Capitalisation
(Rs. Crore)
Sr. No. | Particulars | FY 2022-23 |  |  | FY 2023-24 |  |  | FY 2024-25 |  |  |  |  | Ensuing Years |  |  |  |  | Remarks
|  | MYT Order (227 of 2022) | April-March (Audited ) | True-Up requirement | MYT Order (227 of 2022) | April-March (Audited ) | True-Up requirement | MYT Order (227 of 2022) | Apr-Sep (Estimated) | Oct-Mar (Projected) | April - March (Projected) | Provisional True-Up requirement | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30
|  | (a) | (b) | (c) = (b) - (a) | (d) | (e) | (f) = (e) - (d) | (g) | (h) | (i) | (j) = (h )+ (i) | (k) = (j) - (g) | Projected | Projected | Projected | Projected | Projected
1 | Capital Expenditure |  | 20.1701 | 20.1701 |  | 28.2934 | 28.2934 |  | 0 | 113.29 | 108.28 | 108.28 | 214.42 | 195.37 | 161.54 | 11.79 | 65.29
2 | Capitalisation | 103.66 | 12.8049 | -90.8551 | 7.57 | 78.8337 | 71.2637 | 89.24 | 0 | 93.31 | 93.31 | 4.07 | 239.08 | 203.37 | 161.54 | 11.79 | 65.29
3 | IDC |  |  | 0 |  |  | 0 |  | 0 |  |  | 0
4 | Capitalisation + IDC | 103.66 | 12.8049 | -90.8551 | 7.57 | 78.8337 | 71.2637 | 89.24 | 0 | 93.31 | 93.31 | 4.07 | 239.08 | 203.37 | 161.54 | 11.79 | 65.29 | 0
Note: * - Truing Up for FY 2022-23 & FY 2023-24 to be done under MERC MYT Regulations 2019 with reference to amounts approved in the MYT Order for FY 2020-21 to FY 2024-25
Detailed Justification shall be provided for variation in approved capital expenditure and capitalisation vis-a-vis actual capital expenditure and capitalisation

## F4.1
MSPGCL: Parli 8
MTR Petition Formats - Generation
| Project Details |  | Form 4.1: Capital Expenditure Plan | [14 empty] | (Rs. Crore)
Sr. No. | Project Code | Project Title | MERC Approval No. | MERC Approval Date | Project Purpose | Project Start Date |  |  | Project Completion date (Scheduled) |  |  | Capital Cost
[6 empty] | Original | Revised | Actual | Original | Revised | Actual | Approved | Actual Capital Cost Incurred | Deviation = Approved - Actual on account of
[14 empty] | Change in Scope of Work (a) | Material Cost (b) | IDC (c) | Others (d) | Total Deviation (a+b+c+d)
22 | FGD at Parli Unit # 8 | DPR | MERC/CAPEX/2021-2022/0284 | 2022-06-27 | 0 | 2022-06-27 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
22.1 | FGD at Parli Unit # 8 | Scheme | MERC/CAPEX/2021-2022/0284 | 2022-06-27 | 0 | 2022-06-27 |  | - | - |  | - | 85.2 | 4.1 |  | 81.1 |  |  | 81.1
0 | IDC | IDC | MERC/CAPEX/2021-2022/0284 | 2022-06-27 | 0 | 2022-06-27 |  | - | - |  | - | 4.04 | 0.49 |  | 3.55 |  |  | 3.55
HO DPR 16 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | DPR | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 0 | 2022-02-12 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 16.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | Scheme | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 0 | 2022-02-12 |  | - | - |  | - | 54.24 | 0 |  | 54.24 |  |  | 54.24
0 | IDC | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 0 | 2022-02-12 |  | - | - |  | - | 2.76 | 0 |  | 2.76 |  |  | 2.76
HO DPR 17 | Centralized Monitoring Solution | DPR | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 0 | 2023-11-02 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 17.1 | Centralized Monitoring Solution | Scheme | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 0 | 2023-11-02 |  | - | - |  | - | 66.009 | 0 |  | 66.009 |  |  | 66.009
0 | IDC | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 0 | 2023-11-02 |  | - | - |  | - | 3.3 | 0 |  | 3.3 |  |  | 3.3
Formulas:
Project Start Date = [MERC Approval Date]

## F4.2
|  |  | MSPGCL: Parli 8 | [54 empty] | DPR | Not Initiated
|  |  | MTR Petition Formats - Generation | [54 empty] | Scheme | WIP
| Project Details |  | Form 4.2: Capitalisation Plan | [18 empty] | (Rs. Crore) | [24 empty] | (Rs. Crore) | [8 empty] | 10000000 |  | IDC | Partially Capitalized
Sr. No. | Project Code | DPR | MERC Approval No. | Date of Submission | MERC Approval Date | Cost as per DPR Crs. | MERC Approved Cost | Debt Equity Ratio | Grant Funding | Approved Start Date | Actual Start Date | Approved Date of Completion | Actual Date of Completion | Benefits in Quantified Terms | Capital Expenditure | [12 empty] | Physical Progress (%) | [11 empty] | Capitalisation | [12 empty] | Old Asset retired against capitalised item (in Rs. Cr) | Remarks | Current Status | PO.NO |  | Non-DPR | Capitalised
[15 empty] | Actual Capex till FY 2018-19 | Actual | Actual | Actual | Actual Capex till FY 2021-22 | Actual | Actual | Revised Projected | Projected | Projected | Projected | Projected | Projected | Actual Progress till FY 2018-19 | Actual | Actual | Actual | Actual | Actual | Revised Projected | Projected | Projected | Projected | Projected | Projected | Actual Capitalization till FY 2018-19 | Actual | Actual | Actual | Actual Capitalization till FY 2021-22 | Actual | Actual | Revised Projected | Projected | Projected | Projected | Projected | Projected | [6 empty] | Cancelled
[16 empty] | FY 2019-20 | FY 2020-21 | FY 2021-22 |  | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 |  | FY 2019-20 | FY 2020-21 | FY 2021-22 | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 |  | FY 2019-20 | FY 2020-21 | FY 2021-22 |  | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 |  |  |  |  | Asset No | DATE OF COMMISSION OF ASSET | To be cancelled
| Add Cap (As per 296 of 2019) | [53 empty] | N.A. |  |  |  | To be confirmed
A | Initial spares |  | Add Cap (As per 296 of 2019) | [6 empty] | -
1 | Boiler and Auxiliaries | Scheme | Add Cap (As per 296 of 2019) | N.A |  |  | 7.2 |  |  | -
1 | Procurement of Coal Mill XRP-903 Gear Box Type KMP-280 Spares of Unit # 8 at BM-NPTPS Parli-Vaijnath | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 28/07/2020 | 31.03.2022 | N.A. | Coal Mill XRP-903 is having planetary gear box as drive unit, which is having various spares. Availability of these sparts are very much essential to avoid outages of Coal Mill and hence to avoid generation loss. Currently no stock of any spares is available at Parli TPS and at other TPS’s. | 0 | 0 | 0 | 0 | 0 | 1.35 | 0 | 0 | [5 empty] | 0% | 0% | 20% | 40% | 100% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 1.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO dispatch 18/11; Material received. | Capitalised | 4385000438
2 | Supply of Labyrinth Seal Rings with replaceable Inner liners for Coal Mill XRP-903 required for BM Unit-8, NPTPS, Parli-V. | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 15/09/2020 | 31.03.2022 | 12.03.2021 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0.33134 | 0 | 0.33134 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 100% | 0% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0.33134 | 0 | 0.33134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HO app recd 25/9; PO dis 3/12; material received 12/03; | Capitalised | 4370002552 | 1501008371 | 12.03.2021
3 | Supply and Installation of coal mill liners(weld overlay) of XRP-903 Coal Mill in BM U-8, NPTPS,Parli-V. | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 30/07/2020 | 31.03.2022 | 12.06.2021 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 0.33134 | 0.33134 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 20% | 100% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0.33134 | 0.33134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Dispatch 07/04; Material received | Capitalised | 4385000408 | 1501008519 | 12.06.2021
4 | Procurement of Coal Mill XRP-903 Bowl & Bowl Hub of Unit # 8 at BM-NPTPS Parli-Vaijnath | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 2020-10-09 | 31.03.2022 | 13.11.2021 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 0.73326 | 0.73326 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 20% | 100% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0.73326 | 0.73326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO dispatch; Material received | Capitalised | 4385000483 | 1501008572 | 13.11.2021
5 | Supply of impeller assembly for ID fan | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 28/10/2020 | 31.03.2022 |  | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 0 | 0 | 0.5233 | 0 | 0 | [5 empty] | 0% | 0% | 20% | 40% | 100% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.5233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO Dispatch 01/06/21; Material RECEIVED | Capitalised | 4385000384
6 | Procurement of Primary Air Fan & Forced Draught Fan Drive Coupling on OEM basis required at BM U-8, NPTPS, Parli-V | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 28/10/2020 | 31.03.2022 |  | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 0 | 0 | 0.1941 | 0 | 0 | [5 empty] | 0% | 0% | 20% | 20% | 100% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.1941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO dispatch 15/04/22; Material received. | Capitalised | 4385000569
7 | Procurement of Primary Air Fan PAF 17/11.8-2 Hydraulic Adjustment Device on OEM basis required at BM U-8 NPTPS Parli-V | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 28/10/2020 | 31.03.2022 | 14.08.2021 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 0.53521 | 0.53521 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 20% | 100% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0.53521 | 0.53521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO Dispatch 23/06/21;Material received. | Capitalised | 4385000383 | 1501008573 | 14.08.2021
8 | Proc of spares for fabric expansion joints required at BM U-8, NPTPS, Parli-V. | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 2020-10-11 | 31.03.2022 | 12.02.2021 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0.56972 | 0 | 0.56972 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 10% | 0% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0.56972 | 0 | 0.56972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO Placed 11/02 material received at site; | Capitalised | 4370002571 | 1501008372 | 12.02.2021
9 | Proc of separator body and seperator top spares for coal mill XRP-903 at BM U-8, NPTPS Parli-V. | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 2020-12-11 | 31.03.2022 | 26.04.2021 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 0.42569 | 0.42569 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 40% |  | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0.42569 | 0.42569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO Dispatch 30/03; Material received; | Capitalised | 4385000389 | 1501008520 | 26.04.2021
10 | Proc of scrapper area & reject system spares for coal mill XRP-903 at BM U-8, NPTPS Parli-V. | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 2020-10-11 | 31.03.2022 | 31.03.2021 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0.27833 | 0 | 0.27833 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 100% | 0% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0.27833 | 0 | 0.27833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO Dispatch 30/03; Material received | Capitalised | 4385000387 | 1501008369 | 31.03.2021
11 | Proc of seal air fan spares at BM-8 NPTPS, Parli-V. | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 2020-05-12 | 31.03.2022 | 31.03.2021 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0.26432 | 0 | 0.26432 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 100% | 0% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0.26432 | 0 | 0.26432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO Dispatch 30/03; Material received; | Capitalised | 4385000404 | 1501008370 | 31.03.2021
12 | Procurement of FD Fan Type FAF 17/9.5-1 Drive Coupling required at BM U-8 NPTPS Parli-V | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 2021-08-02 | 31.03.2022 |  | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 40% |  | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | New PR No.1100131599; DO is in process. | WIP | _
13 | Procurement of complete planatary gear box-KMP -280/300 for coal mill XRP-903 at BM U-8 NPTPS Parli-V | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - |  | 31.03.2022 |  | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0% |  |  |  | 100% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | _ | WIP
2 | Turbine and Auxiliaries | Scheme | Add Cap (As per 296 of 2019) | N.A |  |  | 4.3 |  |  | - |  | 31.03.2022 | [6 empty] | 0 | [24 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
1 | Procurement of spares for Equipment Cooling Water Pumps (Make-FLOWMORE) of model FIG-5824 (SG Side) and FIG-5822 (TG side) at Unit-8 NPTPS Parli-V | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 31/03/2021 | 31.03.2022 | 11.06.2021 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 0.51812 | 0.51812 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 20% |  | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0.51812 | 0.51812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO dispatch 16/4; Material received | Capitalised | 4500114242 | 1501008517 | 11.06.2021
2 | Supply of spars for recovery & FF Pumps along with work at U#8 | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 2020-08-10 | 31.03.2022 | 27.07.2021 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 0.37713 | 0.37713 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 40% |  | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0.37713 | 0.37713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | new PR 1100115195 -; PO placed material received | Capitalised | 4385000340 | 1501008613 | 27.07.2021
3 | Supply of seal oil vacuum pump in unit 08 | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 16/12/2020 | 31.03.2022 | 25.03.2021 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0.27502 | 0 | 0.27502 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 100% | 0% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0.27502 | 0 | 0.27502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO Placed 12/03; material received; | Capitalised | 4385000390 | 1501008385 | 25.03.2021
4 | Procurement of AC pressure pipes (235MM OD, 200MM ID, 4.5M Length) for NDCT hot spray water distribution system in Unit-8 NPTPS Parli-Vaijnath | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 2021-01-01 | 31.03.2022 | 31.03.2021 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0.42522 | 0 | 0.42522 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 100% | 0% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0.42522 | 0 | 0.42522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO Dispatch 25/02; Material received, | Capitalised | 4385000354 | 130100798 | 31.03.2021
5 | Supply of M/s Summits make Instrument Air Dryer & spares at U # 8 TM, Parli-V | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 16/01/2021 | 31.03.2022 | 05.07.2021 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 0.54787 | 0.54787 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 40% | 100% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0.54787 | 0.54787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO dis 22/3/21; material received | Capitalised | 4550008448 | 1501008601 | 05.07.2021
6 | Supply of PVC fills for NDCTs at U # 8 TM, Parli-V | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 20/01/2021 | 31.03.2022 | 14.05.2021/ 03.04.2021 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0.20386 | 0.37859 | 0.58245 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 40% | 100% | 0% | 0% | 0% | [5 empty] | 0 |  |  | 0.58245 | 0.58245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO dis 24/3;Material received; | Capitalised | 4550008409 /4550008410 | 130100801/ 130100802 | 14.05.2021/ 03.04.2021
7 | Procurement of NB 600MM Gate valves for ACW self cleaning strainers in U#8 TM NPTPS Parli-V | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 15/01/2021 | 31.03.2022 | 15.06.2021 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 0.42338 | 0.42338 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 40% | 100% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0.42338 | 0.42338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO dis 17/3; material received | Capitalised | 4550008413 | 1501008518 | 15.06.2021
8 | Procurement of Mechanical seals ( Make Leak-Proof) for various pumps in TM Unit-8 NPTPS Parli. | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 2020-12-12 | 31.03.2022 | 05.05.2021 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 0.49233 | 0.49233 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 40% | 100% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0.49233 | 0.49233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO placed 26/03 material received | Capitalised | 4550008451 | 1501008602 | 05.05.2021
9 | Supply of SS 304 pipes & others at U # 8 TM, Parli-V. | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 28/01/2021 | 31.03.2022 | 01.04.2021 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 0.52905 | 0.52905 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 40% | 100% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0.52905 | 0.52905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO placed 22/03/21 material received | Capitalised | 4550008396 | 1501008600 | 01.04.2021
3 | Electrical and Instrumentation | Scheme | Add Cap (As per 296 of 2019) | N.A |  |  | 6.1 |  |  | - |  | 31.03.2022 | [6 empty] | 0 | [24 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
1 | Supply of Instrumentation Spares of LP Bypass System at Unit-8. | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 2020-04-08 | 31.03.2022 | 30.03.2022 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 1.9615 | 1.9615 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 20% | 100% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 1.9615 | 1.9615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO dispatch 08/12; Material received | Capitalised | 4385000495 | 1501008607 | 30.03.2022
2 | Procurement of Schneider MICOM Numerical Relays for GRP and STPR swithcgear at NPTPS Unit-8 Testing | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 17/08/2020 | 31.03.2022 | 26.03.2022 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 0.47613 | 0.47613 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 20% | 100% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0.47613 | 0.47613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO dispatch 27/01; Material received | Capitalised | 4385000511 | 1501008604 | 26.03.2022
3 | Procurement of 220V DC Chloride make (formally caldyne) make battery chargers Spre of Unit 8 NPTPS Parli-V | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 27/08/2020 | 31.03.2022 | 22.02.2022 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 0.23365 | 0.23365 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 20% | 100% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0.23365 | 0.23365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO dispatch 02/11;Material received | Capitalised | 4385000459 | 1501008605 | 22.02.2022
4 | Procurement of 24V DC Chhabi make make battery chargers Spare of Unit 8 NPTPS Parli-V | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 18/08/2020 | 31.03.2022 | 21.12.2021 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 0.16465 | 0.16465 | 0.06 | 0 | 0 | [5 empty] | 0% | 0% | 20% | 100% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0.16465 | 0.16465 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO Dispatch 1/5/21; Material received | Capitalised | 4385000345 | 1501008611 | 21.12.2021
5 | Procurement of Spare for Hitachi Hi-Rel make UPS systems installed at Unit-8 NPTPS Parli Vaijnath. | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 14/08/2020 | 31.03.2022 | 17.09.2021 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 0.19186 | 0.19186 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 20% | 100% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0.19186 | 0.19186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO dispatch 19/4; Material received | Capitalised | 4385000352 | 1501008547 | 17.09.2021
6 | Procurement of various test kit for testing U#8 such as energy meter calibration kit, DC earth faulth locator kit, promary current injection kit, breaker time measurement kit, numeric relay test kit and other testing instruments. | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 18/08/2020 | 31.03.2022 | 06.04.2021/ 14.07.2021 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 0.67345 | 0.67345 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 40% | 100% | 0% | 0% | 0% | [5 empty] | 0 |  |  | 0.67345 | 0.67345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.4385000351 PO Placed 18/03 Material received; 2.114125: Dis 26/03; material received | Capitalised | 4385000351/4385000385 | 1501008513/ 1501008514 | 06.04.2021/ 14.07.2021
7 | Procurement of Energymeter Caliberation Software Module and hardware for upgrading Numeric Relay Test kit at Unit -8 Testing. | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 2021-04-08 | 31.03.2022 | 26.03.2022 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 0.11863 | 0.11863 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 20% | 100% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0.11863 | 0.11863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO Dis 31/01; Material received | Capitalised | 4385000534 | 1501008603 | 26.03.2022
8 | Procurement of H T Motors. | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 2020-07-09 | 31.03.2022 |  | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 20% | 20% |  | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PR To section obs 14/12; Budgetary offer validity which was given at the time of estimate of PR expired.Then account asked to provide new budgetary offer with extended vality but agency not provided budgetary offers.so further processing pending. | To be cancelled | _
9 | Procurement of critical L T Motors | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 2020-10-09 | 31.03.2022 |  | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 20% | 20% |  | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PR To section obs 14/12; Budgetary offer validity which was given at the time of estimate of PR expired.Then account asked to provide new budgetary offer with extended vality but agency not provided budgetary offers.so further processing pending. | To be cancelled | _
10 | Procurement of ESP Hopper heaters (As a initial spares) Installed at EM U-8, NPTPS, Parli-Vaijnath under add cap scheme. | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 23/04/2021 | 31.03.2022 | 24.11.2021 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 0.38586 | 0.38586 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 0% | 100% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0.38586 | 0.38586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO dispatch 22/07/21; Material received | Capitalised | 4385000471 | 1501008566 | 24.11.2021
4 | Outdoor Plant(CHP/AHP/WTP) | Scheme | Add Cap (As per 296 of 2019) | N.A |  |  | 6.64 |  |  | - |  | 31.03.2022 | [6 empty] | 0 | [24 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
1 | Supply of Apron Feeder spares installed at CHP NPTPS Parli-V | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 14/01/2020 | 31.03.2022 | 16.10.2021 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 1.6233 | 1.6233 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 20% | 100% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 1.6233 | 1.6233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO Dispatch 8/6/21; Material received; | Capitalised | 4385000415 | 1501008510 | 16.10.2021
2 | Supply of various drive and non drive pulleys for CHP U-8. | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 13/01/2020 | 31.03.2022 | 06.08.2021/ 09.11.2021 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 0.54529 | 0.54529 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 40% | 100% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0.54529 | 0.54529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO Placed 27/03; material received | Capitalised | 4385000402 /4385000403 | 1501008509/ 1501008656 | 06.08.2021/ 09.11.2021
3 | Supply and installation of clamp pads & resting pads for Side Beam of Wagon Tippler for CHP U-8 | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 14/01/2020 | 31.03.2022 | 15.04.2021 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0.54802 | -4e-08 | 0.54802 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 40% | 100% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0.54802 | 0.54802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO Dis 9/2;Material received; | Capitalised | 4385000347 | 1501008516 | 15.04.2021
4 | Supply of unbalance motorozied vibrating feeder for S/R of U-7/8 CHP NPTPS Parli-V. | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 16/01/2020 | 31.03.2022 | 07.09.2021 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 0.3958 | 0.3958 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 20% | 100% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0.3958 | 0.3958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | T.C.3000011773. PO dis 12/4; material received; | Capitalised | 4385000417 | 1501008512 | 07.09.2021
5 | Procurement of conveying and Instrument air compressor spares at AHP U#8 | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 2020-01-08 | 31.03.2022 | 16.03.2022 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 1.7575 | 1.7575 | 0.012459 | 0 | 0 | [5 empty] | 0% | 0% | 20% | 95% | 100% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 1.7575 | 1.7575 | 0.012459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO dispatch 27/11; Material received | Capitalised | 4385000477 | 1501008615 | 16.03.2022
6 | Procurement of vacuum pump spares at AHP U#8 | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 21/01/2021 | 31.03.2022 | 12.08.2021 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 0.2291 | 0.2291 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 20% | 100% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0.2291 | 0.2291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO Dispatch 12/4; Material received | Capitalised | 4385000411 | 1501008506 | 12.08.2021
7 | Procurement of fluidizing blower spares at AHP U#8 | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 31/12/2020 | 31.03.2022 | 09.09.2021 | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 0.11796 | 0.11796 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 20% | 100% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0.11796 | 0.11796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO Dispatch 12/4; material received | Capitalised | 4385000407 | 1501008608 | 09.09.2021
8 | Procurement of slurry pump spares at AHP U#8 | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 29/09/2020 | 31.03.2022 | N.A | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 20% | 20% | 100% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO stage | WIP | _
9 | Procurement of Clinker grinder spares at AHP U#8 | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 2020-10-12 | 31.03.2022 |  | Availability of auxiliaries will improve which finally avoid emergency & generation loss. | 0 | 0 | 0 | 0 | 0 | 0.12334 | 0 | 0 | [5 empty] | 0% | 0% | 20% | 40% | 100% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.12334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PO Dispatch 19/05; Material received | Capitalised | 4385000432
[10 empty] | - | [8 empty] | 0 | [13 empty] | 0% | 0% | [9 empty] | 0
B | Reassessment of remaining BOP work after insolvency of M/s Sunil Hi-Tech | [8 empty] | - | [8 empty] | 0 | [13 empty] | 0% | 0% | [9 empty] | 0
| Project balance E&M and procurement of mandetory spares | Scheme | MERC CAPEX Approval in MTR Order 296 of 2019 | N.A | Order 296 of 2019 | 41.4534 | 41.4534 |  |  |  |  | 31.03.2022 | [6 empty] | 0 | [24 empty] | 0 | [9 empty] | Approved Cost of BR is Rs.35.13 Crs, Excluding taxes.
1 | Work order for Contract of Supply and application of Fire Stop Mortar Seal and Fire Retardant Cable Coating Compound at NPTP U-8 Parli Project | Scheme | MERC CAPEX Approval in MTR Order 296 of 2019 |  |  | 3.48 | [5 empty] | 31.03.2022 |  |  | 0 | 0 | 3.4589 | 0 | 3.4589 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 100% | 0% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 3.4589 | 0 | 3.4589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Supply & Work completed | Capitalised
2 | Work order for contract for Supply Installaion Testing & Commissioning Smoke Detection & alaram system | Scheme | MERC CAPEX Approval in MTR Order 296 of 2019 |  |  | 2.9736 | [5 empty] | 31.03.2022 |  |  | 0 | 0 | 2.5606 | 0 | 2.5606 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 100% | 0% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 2.5606 | 0 | 2.5606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Supply & Work completed | Capitalised
3 | Work order for contract for Supply Installaion Testing & Commissioning of Balance Fire Fighting System at NPTP U-8 Parli Project | Scheme | MERC CAPEX Approval in MTR Order 296 of 2019 |  |  | 1.2272 | [5 empty] | 31.03.2022 |  |  | 0 | 0 | 1.0502 | 0 | 1.0502 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 100% | 0% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 1.0502 | 0 | 1.0502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Supply & Work completed | Capitalised
4 | Supply, Errection, testing & commissioning works of RWP, PT potable chlorination system, ETP system control panel, automation of LDO, HFO tank foam system Hose boxes with RRL hoses and branch pipe and allied system at NPTP | Scheme | MERC CAPEX Approval in MTR Order 296 of 2019 |  |  | 0.8614 | [5 empty] | 31.03.2022 |  |  | 0 | 0 | 0.8496 | 0 | 0.8496 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 100% | 0% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0.8496 | 0 | 0.8496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Supply & Work completed | Capitalised
5 | Work Order contract for supply, installation Testing & Commissioning of telephone exchange (EPBAX) & Telephone System at NPTP U-8 Parli project | Scheme | MERC CAPEX Approval in MTR Order 296 of 2019 |  |  | 0.9322 | [5 empty] | 31.03.2022 |  |  | 0 | 0 | 0.91256 | 0 | 0.91256 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 100% | 0% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0.91256 | 0 | 0.91256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Supply & Work completed | Capitalised
6 | Balance Supply of Electrical Lab Equipment at NPTP parli-V | Scheme | MERC CAPEX Approval in MTR Order 296 of 2019 |  |  | 0.767 | [5 empty] | 31.03.2022 |  |  | 0 | 0 | 0.60826 | 0 | 0.60826 | 0 | 0 | 0 | [5 empty] | 0% | 0% | 100% | 0% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0.60826 | 0 | 0.60826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Supply & Work completed | Capitalised
7 | Work order for contract for Supply Installaion Testing & Commissioning with required material to complete Balance CHP work at NPTP U-8 Parli Project | Scheme | MERC CAPEX Approval in MTR Order 296 of 2019 |  |  | 0.5192 | [5 empty] | 31.03.2022 |  |  | 0 | 0 | 0 | 0 | 0 | 0.41 | 0 | 0 | [5 empty] | 0% | 0% | 0% | 0% | 100% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Supply & Work completed | Capitalised
8 | Supply, Errection, testing & commissioning of Interconnecting Conveyor no.9 & 10 from U-8 to U-6&7 of CHP at NPTP U-8, Parli-V | Scheme | MERC CAPEX Approval in MTR Order 296 of 2019 |  |  | 3.5872 | [5 empty] | 31.03.2022 |  |  | 0 | 0 | 0 | 2.6267 | 2.6267 | 0.95521 | 0 | 0 | [5 empty] | 0% | 0% | 0% | 0% | 100% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 3.5814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Suply completed, work completed | Capitalised
9 | SUPPLY ,INSTA,TEST ,COMM ELECTRICAL SYS | Scheme | MERC CAPEX Approval in MTR Order 296 of 2019 |  |  | 3.2214 | [5 empty] | 31.03.2022 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.75 | 0 | [5 empty] | 0% | 0% | 0% | 0% | 100% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1.7448 | 0 | 0 | 0 | 0 | 0 | 0 |  | work completed | Capitalised
10 | SUPPLY,INSTAL,TEST,COMM OF CRANS&HOIST | Scheme | MERC CAPEX Approval in MTR Order 296 of 2019 |  |  | 2.1594 | [5 empty] | 31.03.2022 |  |  | 0 | 0 | 0 | 0 | 0 | 1.3805 | 0 | 0 | [5 empty] | 0% | 0% | 0% | 0% | 100% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 1.3805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Suply completed,work completed | Capitalised
11 | Supply, Errection, testing & commissioning of Dust Extraction system at NPTP U-8, Parli-V | Scheme | MERC CAPEX Approval in MTR Order 296 of 2019 |  |  | 2.2656 | [5 empty] | 31.03.2022 |  |  | 0 | 0 | 0 | 1.8061 | 1.8061 | 0 | 0.43 | 0 | [5 empty] | 0% | 0% | 0% | 0% | 100% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2.2418 | 0 | 0 | 0 | 0 | 0 | 0 |  | Suply completed, work completed | Capitalised
12 | Supply, Errection, testing & commissioning of DSS & DFDS at NPTP U-8, Parli-V | Scheme | MERC CAPEX Approval in MTR Order 296 of 2019 |  |  | 4.3424 | [5 empty] | 31.03.2022 |  |  | 0 | 0 | 0 | 2.8091 | 2.8091 | 0 | 0 | 1.53 | [5 empty] | 0% | 0% | 0% | 0% | 100% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.34 | 0 | 0 | 0 | 0 | 0 |  | Suply completed, work completed | WIP
13 | Supply, Errection, testing & commissioning of Monorail at NPTP U-8, Parli-V | Scheme | MERC CAPEX Approval in MTR Order 296 of 2019 |  |  | 1.652 | [5 empty] | 31.03.2022 |  |  | 0 | 0 | 0 | 0.8011 | 0.8011 | 0.38808 | 0 | 0 | [5 empty] | 0% | 0% | 0% | 0% | 100% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 1.1891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Suply completed, work completed | Capitalised
14 | Supply, Errection, testing & commissioning of various Control & Instrumentation equipments at NPTP U-8, Parli-V | Scheme | MERC CAPEX Approval in MTR Order 296 of 2019 |  |  | 0.8378 | [5 empty] | 31.03.2022 |  |  | 0 | 0 | 0 | 0 | 0 | 0.72225 | 0 | 0 | [5 empty] | 0% | 0% | 0% | 0% | 100% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.72225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Work completed | Capitalised
15 | Supply, Errection, testing & commissioning of Air Conditioning System at NPTP U-8, Parli-V | Scheme | MERC CAPEX Approval in MTR Order 296 of 2019 |  |  | 0.7788 | [5 empty] | 31.03.2022 |  |  | 0 | 0 | 0 | 0 | 0 | 0.15304 | 0 | 0 | [5 empty] | 0% | 0% | 0% | 0% | 100% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.44729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Work completed | Capitalised
16 | Supply, Errection, testing & commissioning of Ventilation System at NPTP U-8, Parli-V | Scheme | MERC CAPEX Approval in MTR Order 296 of 2019 |  |  | 2.183 | [5 empty] | 31.03.2022 |  |  | 0 | 0 | 0 | 0.86893 | 0.86893 | 0.33467 | 0 | 0 | [5 empty] | 0% | 0% | 0% | 0% | 100% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 1.2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Supply completed, work completed | Capitalised
17 | Supply, Errection, testing & commissioning of Elevator works. | Scheme | MERC CAPEX Approval in MTR Order 296 of 2019 |  |  | 0.9204 | [5 empty] | 31.03.2022 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0.91 | 0 | [5 empty] | 0% | 0% | 0% | 0% | 100% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.91 | 0 | 0 | 0 | 0 | 0 |  | Supply completed, work 50% completed | WIP
18 | Work contract for dismentaling, supply, erection & commissioning of MRHS | Scheme | MERC CAPEX Approval in MTR Order 296 of 2019 |  |  | 3.5164 | [5 empty] | 31.03.2022 |  |  | 0 | 0 | 0 |  | 0 | 0 | 3.5173 | 0 | [5 empty] | 0% | 0% | 0% | 0% | 100% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 3.5173 | 0 | 0 | 0 | 0 | 0 | 0 |  | Supply completed, work completed | Capitalised
19 | Supply, Errection, testing & commissioning of FF System, Smoke detection & Fire stop mortar & Fire retradant cable coating for conveyor 09 & 10 | Scheme | MERC CAPEX Approval in MTR Order 296 of 2019 |  |  | 2.2302 | [5 empty] | 31.03.2022 |  |  | 0 | 0 | 0 |  | 0 | 0 | 2.2335 | 0 | [5 empty] | 0% | 0% | 0% | 0% | 100% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2.2335 | 0 | 0 | 0 | 0 | 0 | 0 |  | Supply completed, work completed | Capitalised
20 | Supply, Errection, testing & commissioning of Chimney Elevator | Scheme | MERC CAPEX Approval in MTR Order 296 of 2019 |  |  | 0.2242 | [5 empty] | 31.03.2022 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0.22171 | 0 | [5 empty] | 0% | 0% | 0% | 0% | 100% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0.51866 | 0 | 0 | 0 | 0 | 0 | 0 |  | Supply completed, work completed | Capitalised
21 | Supply, Errection, testing & commissioning work of GEHO Pumps. | Scheme | MERC CAPEX Approval in MTR Order 296 of 2019 |  |  | 1.062 | [5 empty] | 31.03.2022 |  |  | 0 | 0 | 0 |  | 0 | 0 | 1.0608 | 0 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 100% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.06 | 0 | 0 | 0 | 0 | 0 |  | 90% WORK COMPLETED | WIP
22 | Procurement of various Mandetory spares of BOP packages | Scheme | MERC CAPEX Approval in MTR Order 296 of 2019 |  |  | 6.5136 | [5 empty] | 31.03.2022 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 5.47 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 100% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 6.54 | 0 | 0 | 0 | 0 | 0 |  | PROPOSAL IS IN PROCESS | WIP
| Balance civil work of BOP scope at 250 MW Parli-V |  | MERC CAPEX Approval in MTR Order 296 of 2019 |  |  | 49.09 | 45.3238 |  |  |  |  | 31.03.2022 | [6 empty] | 0 | [24 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | Approved Cost of BR is Rs.38.41 Crs, Excluding taxes. 1) The work of BOP was awarded to M/s SHEL vide Order No DG/PARLI-8/BOP/SUPPLY DT. 01.01.2010 AND Order No DG/PARLI-8/BOP/ERECTION/2 DT. 01.01.2010. M/s SHEL has not carried out the work completely and M/s SHEL approached to Arbitration, Due to this work of BOP held up and so in the interest of MSPGCL Hon. Managiing Director, MSPGCL issued the BR No 48 dt. 15.02.2019 for RS 73.54 Crores for Risk and Cost against Encashment of BGs already deposited by M/s SHEL RS. 83 Crores 2) Therefore Bal Civil work of BOP Scope at 1*250 MW parli was undertaken and Order No. CE[C]/II/KRD TECH/t-68/1376 dt. 20.08.2019 issued to M/s Mitcon for RS. 49.08 Crores inclusive of Taxes. 3) The SHEL completed the work of Rs. 116 crores Civil order No 2 against W.O value Rs. 133 Crores(incl. of taxes) and balance work Rs. 16.50 was incomplete, after Technical inspection and scrutiny the work by Competent Authorities the remained work was decided to complete in all respect, so that the revised Estimate of Balance work prepared for RS. 36.21 Crores package wise and approved by HO and Hon. MD and BR NO. MSPGCL/CS/CIR RES/48 DT. 15.02.2019 issued for RS. 38.41 Crores exclusive of Taxes. 4) The work of BOP civil stopped by SHEL and therefore New Order of Rs. 49.08 (incl. taxes) issued to M/s Mitcon to complete the work, in the mean period the costs has been increased of Cement, Steel and other civil equipment hence the Rates are taken as per New Govt. DSR for the respective year and revised estimates of RS. 36.21 crores packages wise prepared and approved by HO. 5) The order Value has also increased due to higher rate quoated by M/S Mitcon by RS. 14.89% above the estimated cost of RS. 36.21 crores hence the amount of Rs. 5.39 Crores increased 6) Now the Work of BOP Civil has been completed to the values of RS. 37.41 Crores against Total Order of Rs. 49.08 Crores i.e. 76% and balance work is in progress and total work is estimated to be completed in 2022-23. 7) Therefore the reasons for increased costs against civil work order due to- i) Delay in completion of work by SHEL. ii) Prize Hike in Material and Equipments during the mean time. iii) Higher Prize quoted by Agency M/S Mitcon. iv) Taxes increase in due period.
1 | Area grading | Scheme | MERC CAPEX Approval in MTR Order 296 of 2019 |  |  | 7.16 | [5 empty] | 31.03.2022 |  |  |  |  | 4.61 |  | 4.61 | 1.9929 | 0.55712 | 0 | [9 empty] | 100% | 0% | 0% | [9 empty] | 0 | 0 | 16.72 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Capitalised
2 | CMD | Scheme | MERC CAPEX Approval in MTR Order 296 of 2019 |  |  | 1.15 | [5 empty] | 31.03.2022 |  |  |  |  | 0.52 | 0.07 | 0.59 | 0.17624 | 0.38376 | 0 | [9 empty] | 100% | 0% | 0% | [9 empty] | 0 | 0 | 0.89 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Capitalised
3 | Conveyor 09, 10 & TP 06 | Scheme | MERC CAPEX Approval in MTR Order 296 of 2019 |  |  | 11.08 | [5 empty] | 31.03.2022 |  |  |  |  | 9.72 | 0.37 | 10.09 | 0.51517 | 0.47483 | 0 | [9 empty] | 100% | 0% | 0% | [9 empty] | 0 | 0 | 1.3549 | 2.03 | 0 | 0 | 0 | 0 | 0 |  |  | WIP
4 | Finishing item | Scheme | MERC CAPEX Approval in MTR Order 296 of 2019 |  |  | 11.75 | [5 empty] | 31.03.2022 |  |  |  |  | 2.44 | 2.03 | 4.47 | 1.6746 | 3.9554 | 0 | [9 empty] | 100% | 0% | 0% | [9 empty] | 0 | 0 | 10.1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Capitalised
5 | Drain & nala | Scheme | MERC CAPEX Approval in MTR Order 296 of 2019 |  |  | 4.65 | [5 empty] | 31.03.2022 |  |  |  |  | 1.3 | 0.42 | 1.72 | 0.98966 | 1.9403 | 0 | [9 empty] | 100% | 0% | 0% | [9 empty] | 0 | 0 | 4.6506 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Capitalised
6 | Internal roads | Scheme | MERC CAPEX Approval in MTR Order 296 of 2019 |  |  | 11.79 | [5 empty] | 31.03.2022 |  |  |  |  | 6.7 | 1.21 | 7.91 | 1.5048 | 2.3752 | 0 | [9 empty] | 100% | 0% | 0% | [9 empty] | 0 | 0 | 11.79 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Capitalised
7 | Stacker & reclaimer | Scheme | MERC CAPEX Approval in MTR Order 296 of 2019 |  |  | 1.5 | [5 empty] | 31.03.2022 |  |  |  |  | 0.81 | 0.19 | 1 | 0.16268 | 0.33732 | 0 | [9 empty] | 100% | 0% | 0% | [9 empty] | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Capitalised
| Other Add Cap | [17 empty] | 0 | [24 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | N.A.
| Laboratory set up | Scheme | Add Cap (As per 296 of 2019) | N.A |  | 0 |  |  |  | - |  | 31.03.2022 |  | Quality control of fuel,water, bulk chemicals, lub oils etc.Moniters heatrate, fuel consumption,chemical consumption etc. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | N.A.
1 | Supply of Analytical Instruments for condition monitoring Laboratory for 1X250 MW of NPTPS, Parli-V. | Scheme | Add Cap (As per 296 of 2019) | N.A |  | 0.5 | 0.5 |  |  | - | 2019-03-03 | 31.03.2022 | 25.11.2020 | Quality control of fuel,water, bulk chemicals, lub oils etc.Moniters heatrate, fuel consumption,chemical consumption etc. | 0 | 0 | 0.49655 | 0 | 0.49655 | 0 | 0 | 0 | [5 empty] | 20% | 20% | 100% | 0% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0.49655 | 0 | 0.49655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Material received. | Capitalised | 4385000174 | 1501008295 | 25.11.2020
2 | Supply of Analytical Instruments for Water Analysis Laboratory for 1X250 MW of NPTPS, Parli-V | Scheme | Add Cap (As per 296 of 2019) | N.A |  | 1.23 | 1.23 |  |  | - | 2019-06-03 | 31.03.2022 | 17.06.2021/ 08.09.2021 | Quality control of fuel,water, bulk chemicals, lub oils etc.Moniters heatrate, fuel consumption,chemical consumption etc. | 0 | 0 | 0 | 0.29847 | 0.29847 | 0 | 0 | 0 | [5 empty] | 20% | 20% | 40% | 0% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0.29847 | 0.29847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Material received. | Capitalised | 4385000392 /4385000393 | 1501008556/ 1501008555 | 17.06.2021/ 08.09.2021
3 | Supply of Analytical Instruments for Environment Laboratory for 1 x 250 MW, NPTPS, Parli-V. | Scheme | Add Cap (As per 296 of 2019) | N.A |  | 0.39 | 0.39 |  |  | - | 2019-06-03 | 31.03.2022 | 08.02.2020 | Quality control of fuel,water, bulk chemicals, lub oils etc.Moniters heatrate, fuel consumption,chemical consumption etc. | 0 | 0.3658 | 0 | 0 | 0.3658 | 0 | 0 | 0 | [5 empty] | 20% | 40% | 0% | 0% | 0% | 0% | 0% | [5 empty] | 0 | 0.3658 | 0 | 0 | 0.3658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Material received. | Capitalised | 4385000073/4385000074 | 1501008201 | 08.02.2020
4 | Supply of Analytical Instruments for Precision Laboratory for 1 x 250 MW, NPTPS, Parli-V. | Scheme | Add Cap (As per 296 of 2019) | N.A |  | 1 | 1 |  |  | - | 2019-06-03 | 31.03.2022 |  | Quality control of fuel,water, bulk chemicals, lub oils etc.Moniters heatrate, fuel consumption,chemical consumption etc. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 20% | 20% | 20% | 20% |  | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | ADDCAP Proposal No.1100098925 is returned back as per SE Chemist remark.Office note dated 16.12.2020 remark by Suptd.Cemist(FM)ref N.CE/Suptdg chem/CPA/Inst/1038 dated 16.12.2020. | To be cancelled | N.A.
5 | Supply of Analytical Instruments for General Laboratory of Water Treatment Plant of 1 x 250 MW, NPTPS, Parli-V. | Scheme | Add Cap (As per 296 of 2019) | N.A |  | 0.93 | 0.93 |  |  | - | 2019-06-03 | 31.03.2022 |  | Quality control of fuel,water, bulk chemicals, lub oils etc.Moniters heatrate, fuel consumption,chemical consumption etc. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 20% | 20% | 20% | 20% |  | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | ADDCAP Proposal No.1100098925 is returned back as per SE Chemist remark.Office note dated 16.12.2020 remark by Suptd.Cemist(FM)ref N.CE/Suptdg chem/CPA/Inst/1038 dated 16.12.2020. | To be cancelled | N.A.
6 | Supply of Corrosion Monitor/Meter, Corrosion Coupon & Coupon Rack for 1X250 MW of NPTPS, Parli-V. | Scheme | Add Cap (As per 296 of 2019) | N.A |  | 0.34 | 0.34 |  |  | - | 2019-06-03 | 31.03.2022 | 10.10.2019 | Quality control of fuel,water, bulk chemicals, lub oils etc.Moniters heatrate, fuel consumption,chemical consumption etc. | 0 | 0.34736 | 0 | 0 | 0.34736 | 0 | 0 | 0 | [5 empty] | 20% | 40% |  |  |  | 0% | 0% | [5 empty] | 0 | 0.34736 | 0 | 0 | 0.34736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Material received. | Capitalised | 4385000075 | 1501008202 | 10.10.2019
7 | Supply of Analytical Instruments for Coal Analysis Laboratory for 1X250 MW of NPTPS, Parli-V | Scheme | Add Cap (As per 296 of 2019) | N.A |  | 1.65 | 1.65 |  |  | - | 2019-07-03 | 31.03.2022 | 31.12.2021 | Quality control of fuel,water, bulk chemicals, lub oils etc.Moniters heatrate, fuel consumption,chemical consumption etc. | 0 | 0 | 0 | 0.39444 | 0.39444 | 0 | 0 | 0 | [5 empty] | 20% | 20% | 20% | 100% | 0% | 0% | 0% | [5 empty] | 0 |  |  | 0.39444 | 0.39444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Material received. | Capitalised | 4385000460 / 4385000461 | 1501008564 | 31.12.2021
9 | Grade slab (WTP Area) | Scheme | Add Cap (As per 296 of 2019) | N.A |  | 1 | 1 |  |  | - | N.A | 31.03.2022 | 30.11.2019/ 05.01.2020 |  | 0 | 0.59508 | 0.40245 | 0 | 0.99752 | 0 | 0 | 0 | [5 empty] | 20% | 100% | 0% | 0% | 0% | 0% | 0% | [5 empty] | 0 | 0.59508 | 0.40245 | 0 | 0.99752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Work completed | Capitalised | 4370001852 | 120201366/ 120201392 | 30.11.2019/ 05.01.2020
10 | Grade slab (Near AHP Building) | Scheme | Add Cap (As per 296 of 2019) | N.A |  | 0.75 | 0.75 |  |  |  | N.A | 31.03.2022 | 15.12.2019 |  | 0 | 0.74556 | 0 | 0 | 0.74556 | 0 | 0 | 0 | [5 empty] | 20% | 100% | 0% | 0% | 0% | 0% | 0% | [5 empty] | 0 | 0.74556 | 0 | 0 | 0.74556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Work completed | Capitalised | 4370001851 | 120201362 | 15.12.2019
11 | Temporary shed for empty barrles & filled barrles | Scheme | Add Cap (As per 296 of 2019) | N.A |  | 0.5 | 0.5 |  |  | - | N.A | 31.03.2022 | 17.05.2020 | For reduced the pollustion and healthy working enviroment | 0 | 0 | 0 | 0.45635 | 0.45635 | 0 | 0 | 0 | [5 empty] | 20% | 40% | 100% | 0% | 0% | 0% | 0% | [5 empty] | 0 | 0 |  | 0.45635 | 0.45635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Work completed | Capitalised | 4370001867 | 120201412 | 17.05.2020
12 | Cabins for operators at TP. | Scheme | Add Cap (As per 296 of 2019) | N.A |  | 0.2 | 0.2 |  |  | - | N.A | 31.03.2022 | 10.02.2020 | Provide healthy working enviroment to the operator | 0 | 0.18583 | 0 | 0 | 0.18583 | 0 | 0 | 0 | [5 empty] | 20% | 100% | 0% | 0% | 0% | 0% | 0% | [5 empty] | 0 | 0.18583 | 0 | 0 | 0.18583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Work completed | Capitalised | 4370001850 | 120201367 | 10.02.2020
13 | Compound wall for isolation of administrative building. | Scheme | Add Cap (As per 296 of 2019) | N.A |  | 0.5 | 0.5 |  |  | - | N.A | 31.03.2022 | N.A. | Provde safety to admine building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 40% | 80% | 80% | 100% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Constrution of admin building near NPTPS premises pending. hence Site yet not handed over to agency. Pertains to Civil-iii | To be confirmed | 4370001854
14 | Work of providing/ fixing of internal partitions of aluminium/Nova palm/glass/wooden for Unit 8 service building & other allied builings in the premises. | Scheme | Add Cap (As per 296 of 2019) | N.A |  | 0.7 | 0.7 |  |  | - | N.A | 31.03.2022 | 05.01.2020 |  | 0 | 0.67356 | 0 | 0 | 0.67356 | 0 | 0 | 0 | [5 empty] | 20% | 100% | 0% | 0% | 0% | 0% | 0% | [5 empty] | 0 | 0.67356 |  |  | 0.67356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Work completed | Capitalised | 4370001853 | 120201365 | 05.01.2020
15 | Provision of DM and softening water line interconnection from u-6,7 to u-8 & Provision of recovery of waste water from sandava pump house,NDCT. | Scheme | Add Cap (As per 296 of 2019) | N.A |  | 3 | 3 |  |  | - | 26/02/2019 | 31.03.2022 | 20.05.2019 | Water conservation | 0 | 1.0266 | 0 | 0 | 1.0266 | 0 | 0 | 0 | [5 empty] | 20% | 100% | 0% | 0% | 0% | 0% | 0% | [5 empty] | 0 | 1.0266 | 0 | 0 | 1.0266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Work completed | Capitalised | 4370001958 | 130100793 | 20.05.2019
|  | Scheme | Add Cap (As per 296 of 2019) | N.A | [5 empty] | - | 31/08/2019 | 31.03.2022 | 09.01.2020 | Water conservation | 0 | 1.8371 | 0 | 0 | 1.8371 | 0 | 0 | 0 | [5 empty] | 0% | 100% | 0% | 0% | 0% | 0% | 0% | [5 empty] | 0 | 1.8371 | 0 | 0 | 1.8371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Work completed | Capitalised | 4370002184 | 130100795 | 09.01.2020
16 | Hydraulic drive system modification. | Scheme | Add Cap (As per 296 of 2019) | N.A |  | 2.5 | 2.5 |  |  | - | 2019-07-02 | 31.03.2022 | 26.08.2021 |  | 0 | 0 | 0 | 2.4384 | 2.4384 | 0 | 0 | 0 | [5 empty] | 20% | 20% | 40% | 100% | 0% | 0% | 0% | [6 empty] | 0 | 0 | 2.4384 | 2.4384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Work completed, Scheme capitalized | Capitalised | 4385000201 | 1501008565 | 26.08.2021
17 | Link conveyor from Con-2 of U-6/7 to Con.-2AB of U-8. | Scheme | Add Cap (As per 296 of 2019) | N.A |  | 3.7 | 3.7 |  |  | - | 2019-05-02 | 31.03.2022 | 10.01.2022 | Better utilisation of coal feeding system for all the units | 0 | 0 | 1.9217 | 1.9217 | 3.8434 | 0 | 0 | 0 | [5 empty] | 20% | 20% | 40% | 100% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 3.8434 | 3.8434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Work completed, Scheme capitalized | Capitalised | 4385000280 | 1501008657 | 10.01.2022
18 | Ozone plant for Unit -8 | Scheme | Add Cap (As per 296 of 2019) | N.A |  | 20 | 20 |  |  | - | P&P HO | 31.03.2022 | P&P HO | controls bio growth in cooling water system & helps in reducing of fouling of condenser. Helps in improving NDCT performance. |  |  | 4.4556 | 8.4491 | 12.9047 | 5 | 0.8 | 0 | [5 empty] | 0% |  |  |  |  | 0% | 0% | [9 empty] | 0 | 0 | 18.8129 | 0 | 0 | 0 | 0 | 0 | 0 |  | Work completed. | Capitalised | P&P Project
| IDC | [17 empty] | 0 |  | 2.19 | 0 | [10 empty] | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2.1929 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 2.1929 | 0 | 0 | 0 | 0 | 0 | 0
19 | Water management system | Scheme | Add Cap (As per 296 of 2019) | N.A |  | 2 | 2 |  |  | - | 20/02/2019 | 31.03.2022 |  | To measure consumed water at various locations to optimise water consumption. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 20% | 20% | 20% | 20% |  | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Proposal returened back as per CE CPA letterCE(CPA)/Gr.IVB/NPTPS/ADDCAP Return No.5296 Dtd. 13.06.2022 | To be cancelled | N.A.
8, 20 | Procurement & Installation of EMS system at Unit-8 NPTPS Parli-Vaijnath | Scheme | Add Cap (As per 296 of 2019) | N.A |  | 1 | 1 |  |  | - | 26/02/2019 | 31.03.2022 | 14.10.2021 | 1. Improved availability of EMS System will help in APC Calculation Fulfillment norms of PAT Mandatory Audit. 2. Availability of EMS will help in reducing APC as APC will be monitored precisely. Hence it will go with planning for achieving zero disallowance mission. | 0 | 0 | 0 | 0.14417 | 0.14417 | 0 | 0 | 0 | [5 empty] | 20% | 20% | 40% | 100% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0.14417 | 0.14417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Work completed, Scheme capitalized | Capitalised | 4385000281 | 1501008546 | 14.10.2021
21 | Conveyor-5 of stacking/reclaiming belt double drive arrangement. | Scheme | Add Cap (As per 296 of 2019) | N.A |  | 2 | 2 |  |  | - | 2019-07-02 | 31.03.2022 | 10.06.2021 | for coal stacking | 0 | 0 | 0.81727 | 1.2259 | 2.0432 | 0 | 0 | 0 | [5 empty] | 20% | 20% | 40% | 100% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 2.0432 | 2.0432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Work completed, Scheme capitalized | Capitalised | 4385000195 | 1501008515 | 10.06.2021
22 | Chemical lab building | Scheme | Add Cap (As per 296 of 2019) | N.A |  | 1.5 | 1.5 |  |  | - | N.A | 31.03.2022 | N.A. |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 40% | 40% | 40% | 100% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | To be confirmed from Civil-III, Fresh DPR preparation in progress | To be confirmed | N.A.
23 | Chemical store | Scheme | Add Cap (As per 296 of 2019) | N.A |  | 2.5 | 2.5 |  |  | - | N.A | 31.03.2022 | N.A. | for provide safe storage to the chemical. | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 40% | 40% | 40% | 100% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | To be confirmed from Civil-III, Fresh DPR preparation in progress | To be confirmed | N.A.
24 | Lawn development around NDCT. | Scheme | Add Cap (As per 296 of 2019) | N.A |  | 0.75 | 0.75 |  |  | - | N.A | 31.03.2022 | N.A. | For reduced the pollustion and healthy working enviroment | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 20% | 40% | 40% | 100% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | To be confirmed from Civil-III, Fresh DPR preparation in progress | To be confirmed | N.A.
25 | Tree plantation & greenery along road side. | Scheme | Add Cap (As per 296 of 2019) | N.A |  | 0.5 | 0.5 |  |  | - | N.A | 31.03.2022 | N.A. | For reduced the pollustion and healthy working enviroment | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 20% | 40% | 40% | 100% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | To be confirmed from Civil-III, Fresh DPR preparation in progress | To be confirmed | N.A.
26 | Greenery development in area between WTP & main plant. | Scheme | Add Cap (As per 296 of 2019) | N.A |  | 1.25 | 1.25 |  |  | - | N.A | 31.03.2022 | N.A. | For reduced the pollustion and healthy working enviroment | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 20% | 40% | 40% | 100% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | To be confirmed from Civil-III, Fresh DPR preparation in progress | To be confirmed | N.A.
27 | Construction of staff rooms & store for CHP maint.. | Scheme | Add Cap (As per 296 of 2019) | N.A |  | 1 | 1 |  |  | - | N.A | 31.03.2022 | 31.12.2021 | Provide healthy working enviroment to the staffs | 0 | 0 | 0.31031 | 0.59672 | 0.90703 | 0 | 0 | 0 | [5 empty] | 20% | 40% | 60% | 100% | 0% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0.90703 | 0.90703 | 0 | 0 | 0 | [6 empty] | Work completed | Capitalised | 4370001991 | 120100260 | 31.12.2021
28 | Dsludg filteration for raw water | Scheme | Add Cap (As per 296 of 2019) | N.A |  | 17 | 17 |  |  | - | 20/02/2019 | 31.03.2022 | N.A. | Removes sediments & bio growth drom water .Minimises accumulation of sludge in pond. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 20% | 20% | 20% | 20% |  | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Proposal returened back as per CE CPA letterCE(CPA)/Gr.IVB/NPTPS/ADDCAP Return No.5296 Dtd. 13.06.2022 | To be cancelled | N.A.
29 | PLC/UPS system upgradation | Scheme | Add Cap (As per 296 of 2019) | N.A |  | 0.5 | 0.5 |  |  | - | 2020-07-11 | 31.03.2022 | N.A. |  | 0 | 0 | 0 | 0 | 0 | 0.40149 | 0 | 0 | [5 empty] | 0% | 0% | 20% | 40% | 100% | 0% | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.40149 | 0 | 0 | [6 empty] | Order placed, Material received work completed. | Capitalised | 4385000381
| DPR Schemes | [8 empty] | - | [8 empty] | 0 | [24 empty] | 0
22 | FGD at Parli Unit # 8 | DPR | MERC/CAPEX/2021-2022/0284 | 2021-04-19 | 2022-06-27 | 89.24 | 89.24 |  |  | 2022-06-27 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
22.1 | FGD at Parli Unit # 8 | Scheme | MERC/CAPEX/2021-2022/0284 | 2021-04-19 | 2022-06-27 | 85.2 | 85.2 |  |  | 2022-06-27 | [8 empty] | 0 |  | 4.1 | 94.72 | [11 empty] | 100% | [9 empty] | 0 |  |  | 76.2 | 32.66 | [5 empty] | Work in progress | WIP
| IDC | IDC | MERC/CAPEX/2021-2022/0284 | 2021-04-19 | 2022-06-27 | 4.04 | 4.04 |  |  | 2022-06-27 | [8 empty] | 0 |  | 0.49 | 4.04 | [11 empty] | 100% | [9 empty] | 0 | [10 empty] | N.A.
HO DPR 16 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | DPR | MERC/CAPEX/2021-2022/MSPGCL/063 | 2018-08-31 | 2022-02-12 | 113.91 | 57 | [11 empty] | 0 | [24 empty] | 0
HO DPR 16.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | Scheme | MERC/CAPEX/2021-2022/MSPGCL/063 | 2018-08-31 | 2022-02-12 | 108.48 | 54.24 | [11 empty] | 0 | [24 empty] | 0
| IDC | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2018-08-31 | 2022-02-12 | 5.43 | 2.76 | [11 empty] | 0 | [24 empty] | 0
HO DPR 17 | Centralized Monitoring Solution | DPR | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-03-28 | 2023-11-02 | 69.309 | 69.309 | [11 empty] | 0 | [24 empty] | 0
HO DPR 17.1 | Centralized Monitoring Solution | Scheme | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-03-28 | 2023-11-02 | 66.009 | 66.009 | [11 empty] | 0 |  |  | 2.23 | [21 empty] | 0 |  |  | 2.23 | [6 empty] | HO initiated DPR SCHEME. | WIP
| IDC | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-03-28 | 2023-11-02 | 3.3 | 3.3 | [11 empty] | 0 | [24 empty] | 0
| (ii) Yet to be submitted to MERC | [8 empty] | - | [8 empty] | 0 | [24 empty] | 0
1 | Detailed Project Report on Boiler plant performance improvement and availability improvement schemes at Boiler Maintenance 1x250MW Unit-8 TPS Parli-V | DPR | Yet to be approved | [15 empty] | 0 | [24 empty] | 0 | [9 empty] | Board approval RECEIVED, DPR submitted to MERC. | WIP
1.1 | Procurement & Replacement of Complete Economizer Upper & Lower Bank Coil Assemblies at Unit-8, NPTPS Parli-V | Scheme | Yet to be approved |  |  | 5.68 | [7 empty] | 1.Reduced number of tube leakages in Economizer area will increase reliability of boiler operation. 2.Generation loss due to boiler tube leakages will be avoided. 3.Better operating efficiency of Economizer will help in recovering heat from flue gas to heat feed water and hence heat rate will improve. 4. Decrease in repair and outage cost of boiler due to tube leakages in Economizer area. 5. Better heat transfer area will be available as currently 17 numbers of coils are in bypass condition. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.68 | 0 | 0 | 0 | 0 | [7 empty] | 100% | [8 empty] | 0 |  |  |  | 5.68 | [5 empty] | Board approval RECEIVED, DPR submitted to MERC, PR sent to HO for approval 21.10.2024 | WIP
1.2 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-8, Parli TPS. | Scheme | Yet to be approved |  |  | 4.5 | [7 empty] | 1. Reduction in flue gas outlet temp. 2.Reduction in DP across APH. 3.Reduction in loss due to Dry flue gas. 4.Improvement in performance of APH & Improvement in boiler efficiency. 5.Heat rate of unit will be improved. 6.Reduction in the Fuel consumption. 7.Reduction in the Maintenance cost on account of APH Overhaul. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 0 | 0 | 0 | 0 | [7 empty] | 100% | [8 empty] | 0 |  |  |  | 4.5 | [5 empty] | Board approval RECEIVED, DPR submitted to MERC | WIP
1.3 | Procurement & replacement of PA Fan PAF 17/11.8-2 and FD Fan FAF 17/9.5-1 Complete Blade set required at BM U-8 NPTPS Parli-V. | Scheme | Yet to be approved |  |  | 5.45 | [7 empty] |  Better and stable operation of both fans.  No variation in PA header pressure and furnace draft hence aavailability and Reliability of unit will be increased.  Better response and control over the air output of both fans.  Reduction in fuel (HFO) consumption due to better availability of fans.  Improvement in overall plant efficiency. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.45 | 0 | 0 | 0 | 0 | [7 empty] | 100% | [8 empty] | 0 |  |  |  | 5.45 | [5 empty] | Board approval RECEIVED, DPR submitted to MERC, PR at Pre-audit stage | WIP
1.4 | Procurement & Replacement of Coal Mill Gear Box Type KMP 280 at 250 MW Unit-8, Parli TPS. | Scheme | Yet to be approved |  |  | 7.43 | [7 empty] |  Better availability of coal mills.  Decrease in generation loss due to outage of coal mills.  Availability and Reliability of unit will be increased.  Reduction in fuel (HFO) consumption due to better availability of coal mills.  Improvement in overall milling plant efficiency. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.43 | 0 | 0 | 0 | 0 | [7 empty] | 100% | [8 empty] | 0 |  |  |  | 7.43 | [5 empty] | Board approval RECEIVED, DPR submitted to MERC, PR at Pre-audit stage | WIP
1.5 | Procurement & replacement of Bowl & Bowl Hub Assembly of Coal Mill XRP-903 required at BM U-8 NPTPS Parli-V. | Scheme | Yet to be approved |  |  | 3.1 | [7 empty] |  Since this scheme involves complete replacement of bowl and bowl hub assembly of coal mill, it will be very beneficial in view of the coal mill availability and to avoid generation loss. Major tangible aspects in this regard have been considered as below.  Better availability of coal mills.  Decrease in generation loss due to lesser outage of coal mills for labyrinth seal leakage.  Availability and Reliability of unit will be increased.  Reduction in fuel (HFO) consumption due to better availability of coal mills.  Improvement in overall milling plant efficiency. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1 | 0 | 0 | 0 | 0 | [7 empty] | 100% | [8 empty] | 0 |  |  |  | 3.1 | [5 empty] | Board approval RECEIVED, DPR submitted to MERC, PR sent to HO for approval 25.10.2024 | WIP
1.6 | Procurement of Complete Journal Assembly without Grinding roll for Coal Mill XRP-903 required at BM U-8 NPTPS Parli-V | Scheme | Yet to be approved |  |  | 1.29 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.29 | 0 | 0 | 0 | 0 | [7 empty] | 100% | [8 empty] | 0 |  |  |  | 1.29 | [5 empty] | Board approval RECEIVED, DPR submitted to MERC, PR at Pre-audit stage | WIP
1.7 | Procurement of Hydraulic Adjustment Device for FD Fan FAF 17/9.5-1 at BM U-8 NPTPS Parli-V. | Scheme | Yet to be approved |  |  | 1.4 | [7 empty] |  Better response and accuracy in operation of FD fan.  Sustainable provision of secondary air for combustion without any fluctuations.  Availability and Reliability of unit will be increased. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4 | 0 | 0 | 0 | 0 | [7 empty] | 100% | [8 empty] | 0 |  |  |  | 1.4 | [5 empty] | Board approval RECEIVED, DPR submitted to MERC, PR at Pre-audit stage | WIP
1.8 | SWAS upgradation at U#8 | Scheme | Yet to be approved |  |  | 4 | [7 empty] | • Online real time analysis of Water & Steam parameters and stringent quality monitoring thereof. • Achieving better control over process controlling operational parameters. • Precise Boiler water chemical parameters optimization. • Control over chemical corrosion of boiler and other related piping. • Stringent control over steam quality and purity. • Decrease in heat rate. • Reduction in CBD losses. • Reduction in boiler tube leakages. • Availability of qualitative and quantitative Boiler Drum water chemical parameter data bank for evaluation of present and future performance level and gap analysis. • Analysis of Generation loss through CBD, Deterioration & Chemical losses in terms of quality. • Boiler Tube Leakage and turbine blades deterioration and corrosion can be avoided by knowing exact nature of steam Quality. • DM water saving by optimizing process control. • Reduction in outages. • Quick, on- line, real time sampling by reducing manual error, thereby precision in analysis. • Measurement of critical chemical parameters at normal room temperature. • Control over other related parameters like temperature and pressure of samples. • fast and real time analysis and action to be taken in case, if any abnormality is observed in the parameters | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.8 | 0 | 0 | 0 | 0 | [7 empty] | 100% | [8 empty] | 0 |  |  |  | 4.8 | [5 empty] | Board approval RECEIVED, DPR submitted to MERC | WIP
| (ii) Yet to be submitted to MERC | [8 empty] | - | [8 empty] | 0 | [24 empty] | 0
2 | Procurement & Replacement of Complete Platen super heater coils Coil Assemblies at Unit-8, TPS Parli-V, Procurement & Replacement of Complete LTSH upper & lower bank Coil Assemblies at Unit-8, TPS Parli-V & Procurement & Replacement of Coal Mill Gear Box Type KMP 280 at 250 MW Unit-8, Parli TPS. | DPR | Yet to be approved | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0% | [9 empty] | DPR under preparation | Not Initiated
2.1 | Procurement & Replacement of Complete Platen super heater coils Coil Assemblies at Unit-8, TPS Parli-V | Scheme | Yet to be approved |  |  | 12 | [7 empty] | 1) Increased Reliability of platen superheater operation.2) Gain in heat rate due to improvement in heat absoption. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | [8 empty] | 100% | [7 empty] | 0% |  |  |  |  | 12 |  |  |  |  | DPR under preparation | Not Initiated
2.2 | Procurement & Replacement of Complete LTSH upper & lower bank Coil Assemblies at Unit-8, TPS Parli-V | Scheme | Yet to be approved |  |  | 9.35 | [7 empty] | 1) Avoid outages due to tube leakage in LTSH. 2) Imporove in heat rate. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.35 | 0 | 0 | 0 | [8 empty] | 100% | [7 empty] | 0% |  |  |  |  | 9.35 |  |  |  |  | DPR under preparation | Not Initiated
2.3 | Procurement & Replacement of Coal Mill Gear Box Type KMP 280 at 250 MW Unit-8, Parli TPS. | Scheme | Yet to be approved |  |  | 7.8 | [7 empty] | 1) Increased availability and loadability of mills. 2) Avoiding generation loss on account of mills due to longer outages caused by PGB failure. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.8 | 0 | 0 | 0 | [8 empty] | 100% | [7 empty] | 0% |  |  |  |  | 7.8 |  |  |  |  | DPR under preparation | Not Initiated
3 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-8, Parli TPS Procurement & replacement of PA & FD fan rotar hub assembly at Unit-8 TPS Parli-V | DPR | Yet to be approved | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0% | [9 empty] | DPR under preparation | Not Initiated
3.1 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-8, Parli TPS. | Scheme | Yet to be approved |  |  | 6 | [7 empty] | 1) Improvement in heat rate. 2) Improvement in waste heat recovery from flue gas towards primary and secondary air. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | [11 empty] | 100% |  |  |  |  | 0% | [7 empty] | 6 |  | DPR under preparation | Not Initiated
3.2 | Procurement & replacement of PA & FD fan rotar hub assembly at Unit-8 TPS Parli-V | Scheme | Yet to be approved |  |  | 10 | [7 empty] | 1) Better and stable operation of both fans. 2) Availability and Reliability of unit will be increase. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | [9 empty] | 100% | [6 empty] | 0% | [5 empty] | 10 |  |  |  | DPR under preparation | Not Initiated
4 | DPR on Refurbishment of TG Governing system at Unit-8, PTPS, Parli V. | DPR | Yet to be approved | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0% | [9 empty] | DPR under preparation | Not Initiated
4.1 | Refurbishment of TG Governing system at Unit-8, PTPS, Parli V. | Scheme | Yet to be approved |  |  | 25 | [7 empty] | 1. Reduced time of rolling and synchronisation. Hence oil consumption of reduced. 2. Precise functioning of sub-assemblies of Governing unit, malfunctioning of system avoided. 3. Accurate operation of protection devices which saves major damage to TG unit and avoids permanant deformations in turbine 4. Enhancement in Unit operational service life 5. Availabality of unit ensured. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | [7 empty] | 100% | [8 empty] | 0 |  |  |  | 25 | [5 empty] | DPR under preparation | Not Initiated
5 | DPR on Performance improvement of Natural Draft Cooling Tower (NDCT) at Unit-8, PTPS, Parli V. | DPR | Yet to be approved | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [16 empty] | 0 | [9 empty] | DPR under preparation | Not Initiated
5.1 | Performance improvement of Natural Draft Cooling Tower (NDCT) by replacement of PVC fills, AC cement pipes, strengthening of Hot water distribution system, replacement of beams, columns, support structures, etc. at Unit-8, PTPS, Parli V. | Scheme | Yet to be approved |  |  | 25 | [7 empty] | 1. NDCT and condenser efficiency improved. 2. Cost efficient elecricity generation ensured 3. Unit PLF, Heat rate and availability improved 4 Maintenance cost per year reduced | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | [7 empty] | 100% | [8 empty] | 0 |  |  |  | 25 | [5 empty] | DPR under preparation | Not Initiated
6 | DPR on Procurement of ACW & CW pump along with mandatory spares at Unit-8, PTPS, Parli V. | DPR | Yet to be approved | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [16 empty] | 0 | [9 empty] | DPR under preparation | Not Initiated
6.1 | DPR on Procurement of ACW & CW pump along with mandatory spares at Unit-8, PTPS, Parli V. | Scheme | Yet to be approved |  |  | 35 | [7 empty] | 1. Auxiliary power consumption reduced due to improved performance of pumps 2 . Availability of unit ensured 3. Maintenance cost on pumps reduced due to improved reliability. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | [7 empty] | 100% | [8 empty] | 0 |  |  |  | 35 | [5 empty] | DPR under preparation | Not Initiated
7 | DPR on Procurement of CEP pump and BFP Booster pump along with mandatory spares at Unit-8, PTPS, Parli V and Procurement of Energy Efficient Cartridges of Boiler Feed Pump at Unit-8, PTPS, Parli V. | DPR | Yet to be approved | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [16 empty] | 0 | [9 empty] | DPR under preparation | Not Initiated
7.1 | Procurement of CEP pump and BFP Booster pump along with mandatory spares at Unit-8, PTPS, Parli | Scheme | Yet to be approved |  |  | 30 | [7 empty] | Availability of unit ensured 2 Maintenance cost on pumps reduced due to improved reliability. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | [7 empty] | 100% | [8 empty] | 0 |  |  |  | 30 | [5 empty] | DPR under preparation | Not Initiated
7.2 | Procurement of Energy Efficient Cartridges of Boiler Feed Pump at Unit-8, PTPS, Parli V. | Scheme | Yet to be approved |  |  | 10 | [7 empty] | 3. Auxiliary power consumption reduced due to improved performance of pumps 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | [7 empty] | 100% | [8 empty] | 0 |  |  |  | 10 | [5 empty] | DPR under preparation | Not Initiated
8 | DPR on Procurement of turbine blades of HP, IP & LP rotor in Unit-8, PTPS, Parli V. | DPR | Yet to be approved | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 | [9 empty] | DPR under preparation | Not Initiated
8.1 | DPR on Procurement of turbine blades of HP, IP & LP rotor in Unit-8, PTPS, Parli V. | Scheme | Yet to be approved |  |  | 35 | [7 empty] | 1. HP, IP and LP turbine thermal and overall effiency improved 2 Major deformation in turbine avoided due to use of worn out blades 3 Heat rate improved 4 Improved service life of unit 5. Efficient electricity generation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | [8 empty] | 100% | [7 empty] | 0 |  |  |  |  | 35 |  |  |  |  | DPR under preparation | Not Initiated
9 | DPR on Repair & Reconditioning of Water treatment plant at Unit-8, PTPS, Parli V and Performance improvement of centralised AC plant at Unit-8, PTPS, Parli V. | DPR | Yet to be approved | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 | [9 empty] | DPR under preparation | Not Initiated
9.1 | Reconditioning of Acid and Alkali Unloading and storage system at Unit-8, PTPS, Parli V. | Scheme | Yet to be approved |  |  | 10 | [7 empty] | 1. Timely unloading and efficient utilisation of Acid and alkali. 2. Accident due to acid and alkali avoided. 3 Wastage of costly acid and alkali minimised. 4. Environmental damaged avoided. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | [8 empty] | 100% | [7 empty] | 0 |  |  |  |  | 10 |  |  |  |  | DPR under preparation | Not Initiated
9.2 | Reconditioning & repairing of WTP DM Plant regeneration system at Unit-8, PTPS, Parli V. | Scheme | Yet to be approved |  |  | 20 | [7 empty] | 1 Unintrrupted supply of DM and service water for unit 2. Better perfomance of DM plant. 3. Cost of raisin procurement reduced | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | [8 empty] | 100% | [7 empty] | 0 |  |  |  |  | 20 |  |  |  |  | DPR under preparation | Not Initiated
9.3 | Performance improvement of centralised AC plant by reconditioning of cooling tower, various pumps, heat exchangers, etc. at Unit-8, PTPS, Parli V. | Scheme | Yet to be approved |  |  | 10 | [7 empty] | 1. Malfunctioning of instrumentation system avoided, hence unit tripping avoided 2. Service life of instrumentation logic cards improved 3 availability of unit ensured | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | [8 empty] | 100% | [7 empty] | 0 |  |  |  |  | 10 |  |  |  |  | DPR under preparation | Not Initiated
10 | DPR on Procurement of Control Fluid (HPCF) pump, Lube Oil pump, Emergency Oil pump, Jacking Oil pump, Seal oil pump at Unit-8, PTPS, Parli V. | DPR | Yet to be approved | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 | [9 empty] | DPR under preparation | Not Initiated
10.1 | DPR on Procurement of Control Fluid (HPCF) pump, Lube Oil pump, Emergency Oil pump, Jacking Oil pump, Seal oil pump at Unit-8, PTPS, Parli V. | Scheme | Yet to be approved |  |  | 25 | [7 empty] | 1 TG unit lube oil, seal oil and governing system functional reliabilty improved. 2 Reduced APC due to energy efficient and improved performance of pumps 3. Unit availability and reliabilty ensured. 4. Operational life of Unit improved. 5. Major deformation in TG unit avoided due to failure of these auxiliaries. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | [8 empty] | 100% | [7 empty] | 0 |  |  |  |  | 25 |  |  |  |  | DPR under preparation | Not Initiated
11 | DPR on Procurement of H2 cooler, BFP coolers, generator exciter cooler, Seal and Lube oil coolers at Unit-8, PTPS, Parli V. | DPR | Yet to be approved | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 | [9 empty] | DPR under preparation | Not Initiated
11.1 | DPR on Procurement of H2 cooler, BFP coolers, generator exciter cooler, Seal and Lube oil coolers at Unit-8, PTPS, Parli V. | Scheme | Yet to be approved |  |  | 30 | [7 empty] | 1 Better heat dessipation gnerated in system during electricity generation. 2. Improved service life of various systems like seal oil and lube oil system 3. Major accident due to higher oil temperatures avoided. 4 Unit availability improved. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | [9 empty] | 100% | [6 empty] | 0 | [5 empty] | 30 |  |  |  | DPR under preparation | Not Initiated
12 | Supply, installation & commissioning of 220V 2140AH,24V 830AH & 710AH, 360V 570AH Mains UPS,110V 110AH AHP PLC , 110V , 103 AH DM plant battery set for unit 8 , NPTPS Parli-V & Procurement of HT motors at U#8 | DPR | Yet to be approved | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [16 empty] | 0 | [9 empty] | DPR under preparation | Not Initiated
12.1 | Supply, installation & commissioning of 220V 2140AH,24V 830AH & 710AH, 360V 570AH Mains UPS,110V 110AH AHP PLC , 110V , 103 AH DM plant battery set for unit 8 , NPTPS Parli-V | Scheme | Yet to be approved |  |  | 15 | [7 empty] | Station Batteries are the heart of power plant required for the reliabikity of supply in case of AC failure, as it feed supply to DC auxilaries, Also 24 V and UPS batteries gives uninterpted supply to DCS. failure of DC supply due battery life lead to direct generation loss and secondary damge to turbine bearing and Rotor. Hencefinancial quantification can not be derived | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | [9 empty] | 100% | [6 empty] | 0 | [5 empty] | 15 |  |  |  | DPR under preparation | Not Initiated
12.2 | Procurement of HT motors at U#8 | Scheme | Yet to be approved |  |  | 10 | [7 empty] | 1. The existing motors have been repaired / rewound several times during this period. The motors are in dilapidated condition with increased internal losses, mechanical deterioration etc. Replacement of such motors will definitely result in to reduced failures and ready availability of spare motors for replacement. 2. The availability of spare motors will enable periodical overhaul of motors irrespective of unit overhauls as the spare motors can be kept overhauled and replaced even in short outage of units.  For example, in case of failure of any HT motor of 250 MW unit, the common pool motor is to be brought from other power station which involved transportation. Thus, for restoration of normalcy considerable period is required. If such motor is readily available, the work involved would only be removal and replacement of failed motor. Early restoration of normalcy will add to generation as the unit is brought on bars earlier than what used to be without spare motor.  Reduced failures will reduce the yearly expenditure on maintenance and rewinding.  The present-day motors are of energy efficient construction.  Increased efficiency will result in reduced loading on the old cables and help avoid cable failures/replacements.  Reduced noise level and vibrations around the running motor.  Considerable generation loss on account of failure of Coal mill HT motors will be avoided.  There is considerable saving in auxiliary consumption due to energy efficient HT Motor. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | [7 empty] | 100% | [8 empty] | 0 |  |  |  | 10 | [5 empty] | DPR under preparation | Not Initiated
13 | DPR on various instrumentation & control schemes at U#8 | DPR | Yet to be approved | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [16 empty] | 0 | [9 empty] | DPR under preparation | Not Initiated
13.1 | Upgradation of MAX-DNA DCS system at U#8 (HMI upgradation) | Scheme | Yet to be approved |  |  | 6.81 | [7 empty] | 1.To improve reliability of MAX-DNA DCS system. 2.To avoid any outage due MAX DNA DCS System. 3.For better and stable operation of DCS system. 4.To avoid any generation loss due to DCS system. 5 .New versions of hardware & software will be available which will be useful to operate plant with greater flexibility & reliability | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.81 | 0 | 0 | 0 | 0 | [7 empty] | 100% | [8 empty] | 0 |  |  |  | 6.81 | [5 empty] | DPR under preparation | Not Initiated
13.2 | Upgradation of existing Pcal system with plant performance analysis diagnostic and optimization system (PADO) at Unit 8 New Parli TPS | Scheme | Yet to be approved |  |  | 1.4 | [7 empty] | 1.To improve reliability of PCAL system. 2.For better and stable operation of PCAL system. . 5 .New versions of hardware & software will be available which will be useful to operate plant with greater flexibility & reliability | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4 | 0 | 0 | 0 | 0 | [7 empty] | 100% | [8 empty] | 0 |  |  |  | 1.4 | [5 empty] | DPR under preparation | Not Initiated
13.3 | Upgradation of coal feeder for I&C Unit8 PTPS Parli V. | Scheme | Yet to be approved |  |  | 1.5 | [7 empty] | 1.To improve reliability of Coal feeder 2.To avoid any outage due to coal feeder 3.For better and stable operation of coal feeder. 4.To avoid any generation loss due to coal feeder. 5 .New versions of hardware & software will be available which will be useful to operate plant with greater flexibility & reliability | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.5 | 0 | 0 | 0 | [8 empty] | 100% | [7 empty] | 0 |  |  |  |  | 1.5 |  |  |  |  | DPR under preparation | Not Initiated
13.4 | Procurement of smart control positioner at I&C Unit8 PTPS Parli V. | Scheme | Yet to be approved |  |  | 0.95 | [7 empty] | 1.To improve reliability of control valve & dampers . 2.To avoid any outage due valve & dampers. 3.For better and stable operation of valve & dampers. 4.To avoid any generation loss due tovalve & dampers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.95 | 0 | 0 | 0 | [8 empty] | 100% | [7 empty] | 0 |  |  |  |  | 0.95 |  |  |  |  | DPR under preparation | Not Initiated
13.5 | Upgradation Electronic control drive for I&C Unit8 PTPS Parli V. | Scheme | Yet to be approved |  |  | 3.05 | [7 empty] | 1.To improve reliability of Electric control drive system. 2.To avoid any outage due Electric control drive System. 3.For better and stable operation ofElectric control drive system. 4.To avoid any generation loss due to Electric control drive system. 5 .New versions of hardware & software will be available which will be useful to operate plant with greater flexibility & reliability | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3.05 | 0 | 0 | 0 | [8 empty] | 100% | [7 empty] | 0 |  |  |  |  | 3.05 |  |  |  |  | DPR under preparation | Not Initiated
13.6 | Upgradation of turbovisory & vibration monitoring system control panel. |  | Yet to be approved |  |  | 2 | [7 empty] | 1.To improve reliability of turbovisory & vibration monitoring system. 2.To avoid any outage dueturbovisory & vibration monitoring System. 3.For better and stable operation of turbovisory & vibration monitoring system. 4.To avoid any generation loss due toturbovisory & vibration monitoring system. 5 .New versions of hardware & software will be available which will be useful to operate plant with greater flexibility & reliability |  |  |  |  | 0 |  |  |  |  | 2 | [11 empty] | 100% | [7 empty] | 0 |  |  |  |  | 2 |  |  |  |  | DPR under preparation
14 | Performance improvement by system up gradation at CHP & DPR for normalization and stabilization of coal handling plant performance at Parli TPS | DPR | Yet to be approved | [10 empty] | 1.To improve reliability of turbovisory & vibration monitoring system. 2.To avoid any outage dueturbovisory & vibration monitoring System. 3.For better and stable operation of turbovisory & vibration monitoring system. 4.To avoid any generation loss due toturbovisory & vibration monitoring system. 5 .New versions of hardware & software will be available which will be useful to operate plant with greater flexibility & reliability | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | [16 empty] | 0 | [9 empty] | DPR under preparation | Not Initiated
14.1 | Supply and Commissioning of Energy Efficient Evaporative Cooling System for Control Panel & Breaker room of CHP Unit-8 For PARLI TPS | Scheme | Yet to be approved |  |  | 1.38 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.38 | 0 | 0 | 0 | 0 | [7 empty] | 100% | [8 empty] | 0 |  |  |  | 1.38 | [5 empty] | DPR under preparation | Not Initiated
14.2 | Supply and commissioning of Suspended Magnets for U-8 CHP NPTPS | Scheme | Yet to be approved |  |  | 3.3 | [7 empty] | 1. Improved availability of conveyor system thus healthy bunker levels & help to improve generation. 2. Reductions in Operation and Maintenance cost of HT/LT switchgear equipments.. 3. Reduction in breakdowns of HT/LT breakers.. 4. Availability of motors will be maximized so that scheduled preventive maintenance will be followed. 5. Less energy consumption 6. Reduction in CO2 emission | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3 | 0 | 0 | 0 | 0 | [7 empty] | 100% | [8 empty] | 0 |  |  |  | 3.3 | [5 empty] | DPR under preparation | Not Initiated
14.3 | Stacker-reclaimer Bucket wheel drive modification work of U- 8 CHP | Scheme | Yet to be approved |  |  | 3.32 | [7 empty] | 1. Smooth and uninterrupted operation of CHP. 2. Maximize the utilization and availability of the CHP. 3. Reduction in maintenance and belt failure cost of conveyors. Increase in coal wagon unloading rate. 4. Improved coal mill availability. 5. Improved conveyor belt availability. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.32 | 0 | 0 | 0 | 0 | [7 empty] | 100% | [8 empty] | 0 |  |  |  | 3.32 | [5 empty] | DPR under preparation | Not Initiated
14.4 | Apron feeder drive modification from Hydraulic to Electro-Mechanical at CHP U-8 NPTPS | Scheme | Yet to be approved |  |  | 4.02 | [7 empty] | 1. Smooth and uninterrupted operation of CHP. 2. Maximize the utilization and availability of the CHP. 3. Reduction in maintenance & Failure cost of Stacker-reclaimer. Improved coal mill availability 4. Improved Bucket wheel availability. 5. Utilization of rated capacity of Bucket wheelBetter management of Coal stack yard. 6. Better house keeping at Coal stack yard. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.02 | 0 | 0 | 0 | 0 | [7 empty] | 100% | [8 empty] | 0 |  |  |  | 4.02 | [5 empty] | DPR under preparation | Not Initiated
14.5 | Procurement of U-8 W/T Major spares | Scheme | Yet to be approved |  |  | 10 | [7 empty] | 1.Smooth and uninterrupted operation of CHP. 2. Maximize the utilization and availability of the CHP. 3. Reduction in maintenance & Failure cost of Apron feeder 4. Improved Apron feeder wheel availability. 5. Utilization of rated capacity of Apron feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | [8 empty] | 100% | [7 empty] | 0 |  |  |  |  | 10 |  |  |  |  | DPR under preparation | Not Initiated
14.6 | Provision of Soft starter / VFD for Various conveyor | Scheme | Yet to be approved |  |  | 8 | [7 empty] | Since commissioning these Wagon Tipplers are incontinoues service. Major spares like planatory gearbox, Wagon Tippler / Side Arm Charger racks and pinion, clamps, motors etc parts are detoriated hence replacement is essential to avoid major breakdown and non avaiability of Wagon Tippler / SAC. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | [8 empty] | 100% | [7 empty] | 0 |  |  |  |  | 8 |  |  |  |  | DPR under preparation | Not Initiated
14.7 | TP-3 chute modification at U-8 CHP. | Scheme | Yet to be approved |  |  | 3 | [7 empty] | 1. Maximum Coal Handling Plant availability 2. Faster coal wagon Unloading 3. Reduction in maintenance and operational cost. 4. Utilization of rated capacity of conveyor belts 5. Reduction in auxiliary consumption 6. Reduction in breakdown time | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | [8 empty] | 100% | [7 empty] | 0 |  |  |  |  | 3 |  |  |  |  | DPR under preparation | Not Initiated
14.8 | Design, supply and commissioning of solar operated lighting system in CHP U-8. | Scheme | Yet to be approved |  |  | 15 | [7 empty] | 1. Maximum Coal Handling Plant availability 2. Faster coal wagon Unloading 3. Reduction in maintenance and operational cost. 4. Utilization of rated capacity of conveyor belts 5. Reduction in auxiliary consumption 6. Reduction in breakdown time | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | [8 empty] | 100% | [7 empty] | 0 |  |  |  |  | 15 |  |  |  |  | DPR under preparation | Not Initiated
14.9 | Installation of CCTV survillance system alongwith all conveyors. | Scheme | Yet to be approved |  |  | 4 | [7 empty] | 1. Use of renewable energy and reduction in auxilary consumption. 2. Reduction in Carbon emission. 3. Ambience improvement by providing sufficient lighting during night hours. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | [8 empty] | 100% | [7 empty] | 0 |  |  |  |  | 4 |  |  |  |  | DPR under preparation | Not Initiated
15 | DPR for maximiation of Coal Handling Plant efficiency & DPR on life enhancement of Coal Handling Plant | DPR | Yet to be approved | [10 empty] | 1. Proper survillence of man and machine. 2. Survillence will reduce downtime of auxilaries. 3. As a safety and security will improve. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 | [9 empty] | DPR under preparation | Not Initiated
15.1 | W/T control room & bunker house battery & UPS upgradation | Scheme | Yet to be approved |  |  | 3 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | [9 empty] | 100% | [6 empty] | 0 | [5 empty] | 3 |  |  |  | DPR under preparation | Not Initiated
15.2 | Refurbishment of conveyor no. 2 A/B & 6 A/B drive system of CHP U-8 TPS Parli. | Scheme | Yet to be approved |  |  | 8 | [7 empty] | 1. Smooth and uninterrupted operation of CHP. 2. Uninterrupted power supply to PLC panels. 3. Reduction in maintenance of electronic cards and program software. 4. Improved CHP auxilaries availability. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | [9 empty] | 100% | [6 empty] | 0 | [5 empty] | 8 |  |  |  | DPR under preparation | Not Initiated
15.3 | Provision of Soft starter / VFD for Various conveyor | Scheme | Yet to be approved |  |  | 8 | [7 empty] | 1. Maximum Coal Handling Plant availability 2. Faster coal wagon Unloading 3. Reduction in maintenance and operational cost. 4. Utilization of rated capacity of conveyor belts 5. Reduction in auxiliary consumption 6. Reduction in breakdown time | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | [9 empty] | 100% | [6 empty] | 0 | [5 empty] | 8 |  |  |  | DPR under preparation | Not Initiated
15.4 | Procurement & installation of Belt tear detection system | Scheme | Yet to be approved |  |  | 4.5 | [7 empty] | 1. Maximum Coal Handling Plant availability 2. Faster coal wagon Unloading 3. Reduction in maintenance and operational cost. 4. Utilization of rated capacity of conveyor belts 5. Reduction in auxiliary consumption 6. Reduction in breakdown time | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 0 | [10 empty] | 100% | [5 empty] | 0 | [6 empty] | 4.5 |  |  | DPR under preparation | Not Initiated
15.5 | Conveyor gravity takeup infrastructure strengthening work | Scheme | Yet to be approved |  |  | 3 | [7 empty] | 1. Maximum Coal Handling Plant availability 2. Faster coal wagon Unloading 3. Reduction in maintenance and operational cost. 4. Utilization of rated capacity of conveyor belts 5. Reduction in auxiliary consumption 6. Reduction in breakdown time 7. Spare cost on account of LT switch gear panel will reduce. 8. Break down due to belt snapping will reduce. 9. Conveyor availability will improve by strengthening gravity take insfrastructure work. 10. Faster unloading due to replacement of VF-1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | [10 empty] | 100% | [5 empty] | 0 | [6 empty] | 3 |  |  | DPR under preparation | Not Initiated
15.6 | U-8 CHP apron feeder-I to Conveyor 1 A/B chute modification work . | Scheme | Yet to be approved |  |  | 4 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | [10 empty] | 100% | [5 empty] | 0 | [6 empty] | 4 |  |  | DPR under preparation | Not Initiated
16 | DPR for stabiliazation of Coal Handling Performance. | DPR | Yet to be approved | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 | [9 empty] | DPR under preparation | Not Initiated
16.1 | Drive modification of Stacker Reclaimer slewing system. | Scheme | Yet to be approved |  |  | 5 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | [11 empty] | 100% |  |  |  |  | 0 | [7 empty] | 5 |  | DPR under preparation | Not Initiated
16.2 | Retrofitting of Side Arm Charger-I & II at CHP U-8 | Scheme | Yet to be approved |  |  | 10 | [7 empty] | 1. Maximum Coal Handling Plant availability 2. Faster coal wagon Unloading 3. Reduction in maintenance and operational cost. 4. Utilization of rated capacity of conveyor belts 5. Reduction in auxiliary consumption 6. Reduction in breakdown time 7. Break down due to belt snapping will reduce. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | [11 empty] | 100% |  |  |  |  | 0 | [7 empty] | 10 |  | DPR under preparation | Not Initiated
16.3 | Upgradation of GE/Schineder make PLC system atU-8 CHP. | Scheme | Yet to be approved |  |  | 10 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | [11 empty] | 100% |  |  |  |  | 0 | [7 empty] | 10 |  | DPR under preparation | Not Initiated
16.4 | Refurbishment of Apron Feeder at CHP U-8. | Scheme | Yet to be approved |  |  | 12 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | [11 empty] | 100% |  |  |  |  | 0 | [7 empty] | 12 |  | DPR under preparation | Not Initiated
16.5 | Provision of moveable stacker and crusher in CHP coal stack yard at CHP U-8. | Scheme | Yet to be approved |  |  | 10 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | [11 empty] | 100% |  |  |  |  | 0 | [7 empty] | 10 |  | DPR under preparation | Not Initiated
16.6 | Procurement of Loco & Bulldozer at CHP U-8. | Scheme | Yet to be approved |  |  | 12 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | [11 empty] | 100% |  |  |  |  | 0 | [7 empty] | 12 |  | DPR under preparation | Not Initiated
17 | DPR on dry fly ash utilisation improvement scheme for AHP U-8 NPTPS Parli-V. | DPR | Yet to be approved | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 | [9 empty] | DPR under preparation | Not Initiated
17.1 | Design, supply, erection, installation & comissioning of intermediate silo with sub system at AHP U-8. | Scheme | Yet to be approved |  |  | 38 | [7 empty] | 1) Increases dry fly ash evacuation & conveying. 2) Generates additional revenue from ash utilisation. 3) Reduces auxillary power consumption. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 0 | [9 empty] | 100% | [6 empty] | 0 | [5 empty] | 38 |  |  |  | DPR under preparation | Not Initiated
18 | DPR on ash handling plant improvement scheme for AHP U-8 NPTPS Parli-V. | DPR | Yet to be approved | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 | [9 empty] | DPR under preparation | Not Initiated
18.1 | Design, supply, erection & comissioning of weigh bridge for silo at AHP U-8. | Scheme | Yet to be approved |  |  | 0.5 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | [7 empty] | 100% | [8 empty] | 0 |  |  |  | 0.5 | [5 empty] | DPR under preparation | Not Initiated
18.2 | Supply, installation & comissioning of energy efficient air compressor at AHP U-8. | Scheme | Yet to be approved |  |  | 6 | [7 empty] | 1) Reduction in electrical power consumption. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | [7 empty] | 100% | [8 empty] | 0 |  |  |  | 6 | [5 empty] | DPR under preparation | Not Initiated
18.3 | PROCUREMENT OF COMPLETE ASSEMBLY OF SAM MAKE AR-150/510 PUMPS (2 NOS) FOR REPLACEMENT OF ASH SLURRY PUMPS OF BOTTOM ASH SLURRY DISPOSAL FROM SLURRY TANK TO ASH BUND IN SLURRY PUMP HOUSE. | Scheme | Yet to be approved |  |  | 0.5 | [7 empty] | 1) Increases wet coarse ash evacuation & conveying. 2) Generates additional revenue from ash utilisation. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | [7 empty] | 100% | [8 empty] | 0 |  |  |  | 0.5 | [5 empty] | DPR under preparation | Not Initiated
18.4 | PROCUREMENT OF COMPLETE ASSEMBLY OF SAM MAKE ZM-II 530/02 (2 NOS) FOR REPLACEMENT OF HP PUMPS OF BOTTOM ASH & COARSE ASH EVACUATION FROM BA/CA HOPPERS TO SLURRY TANK IN ASH WATER PUMP HOUSE. 0.75 0.89 | Scheme | Yet to be approved |  |  | 0.4 | [7 empty] | 1) Increases wet coarse ash evacuation & conveying. 2) Generates additional revenue from ash utilisation. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0 | 0 | 0 | 0 | [7 empty] | 100% | [8 empty] | 0 |  |  |  | 0.4 | [5 empty] | DPR under preparation | Not Initiated
18.5 | Procurement of vacuum pumps complete assembly for AHP U-8 NPTPS Parli-V. | Scheme | Yet to be approved |  |  | 1.5 | [7 empty] | 1) Increases dry fly ash evacuation. 2) Generates additional revenue from ash utilisation. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | [7 empty] | 100% | [8 empty] | 0 |  |  |  | 1.5 | [5 empty] | DPR under preparation | Not Initiated
18.6 | Procurement of vacuum pumps complete assembly for AHP U-8 NPTPS Parli-V. | Scheme | Yet to be approved |  |  | 2 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | [7 empty] | 100% | [8 empty] | 0 |  |  |  | 2 | [5 empty] | DPR under preparation | Not Initiated
18.7 | Procurement of Feed Gate Complete Assembly along with modified metallurgy to enhance the life of Clinker Grinder. | Scheme | Yet to be approved |  |  | 1 | [7 empty] | 1) Increases wet coarse ash evacuation & conveying. 2) Generates additional revenue from ash utilisation. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | [7 empty] | 100% | [8 empty] | 0 |  |  |  | 1 | [5 empty] | DPR under preparation | Not Initiated
18.8 | Procurement of Double Roll Clinker Grinder Complete Assembly with Drive Unit installed at AHP | Scheme | Yet to be approved |  |  | 1.25 | [7 empty] | 1) Increases wet coarse ash evacuation & conveying. 2) Generates additional revenue from ash utilisation. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.25 | 0 | 0 | 0 | 0 | [7 empty] | 100% | [8 empty] | 0 |  |  |  | 1.25 | [5 empty] | DPR under preparation | Not Initiated
18.9 | Procurement of Instrument Air Dryers assembly for performance improvement | Scheme | Yet to be approved |  |  | 0.5 | [7 empty] | 1) Increases wet coarse & dry fly ash evacuation & conveying. 2) Generates additional revenue from ash utilisation. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | [7 empty] | 100% | [8 empty] | 0 |  |  |  | 0.5 | [5 empty] | DPR under preparation | Not Initiated
18.1 | Procurement of various types of Isolation Valves assembly, Dome Valves assembly, Root Valve Assembly & Expansion Bellows Assembly for Dry Ash Conveing performance improvement | Scheme | Yet to be approved |  |  | 3.6 | [7 empty] | 1) Increases dry fly ash evacuation & conveying. 2) Generates additional revenue from ash utilisation. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | [7 empty] | 100% | [8 empty] | 0 |  |  |  | 3.6 | [5 empty] | DPR under preparation | Not Initiated
19 | DPR on ash handling plant improvement scheme for AHP U-8 NPTPS Parli-V. | DPR | Yet to be approved | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 | [9 empty] | DPR under preparation | Not Initiated
19.1 | Design, supply, erection, installation & comissioning of DM water close loop cooling system for air compressors at AHP U-8. | Scheme | Yet to be approved |  |  | 3 | [7 empty] | 1) Enhance IAC & CAC air compressor performance. 2) Reduces maintenance time & O&M expenditure. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | [8 empty] | 100% | [7 empty] | 0 |  |  |  |  | 3 |  |  |  |  | DPR under preparation | Not Initiated
19.2 | Up-gradation of Existing Schneider make PLC (HMI + PLC hardware) installed at AHP Unit -8 at Parli TPS. | Scheme | Yet to be approved |  |  | 1.5 | [7 empty] | 1) Un-interrupted & smooth dry and wet coarse ash evacuation & conveying system. 2) Reduces breakdown maintenance work. 3) Updated software and hardware, ensured support from OEM for software & hardware. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | [8 empty] | 100% | [7 empty] | 0 |  |  |  |  | 1.5 |  |  |  |  | DPR under preparation | Not Initiated
19.3 | Procurement of HT motors for AHP U-8 Parli TPS. | Scheme | Yet to be approved |  |  | 2.3 | [7 empty] | 1) Reduces breakdown maintenance time. 2) Availability of HT motors enhances dry fly & wet coarse ash evacuation system. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3 | 0 | 0 | 0 | [8 empty] | 100% | [7 empty] | 0 |  |  |  |  | 2.3 |  |  |  |  | DPR under preparation | Not Initiated
19.4 | PROCUREMENT OF CRITICAL GEARBOXES AND FLUID COUPLINGS INTERNAL ASSEMBLIES FOR SLURRY PUMPS AND SILO HCSD SYSTEM INSTALLED AT AHP, PARLI TPS. | Scheme | Yet to be approved |  |  | 1.2 | [7 empty] | 1) Reduces breakdown maintenance time. 2) Availability of gearboxes enhances dry fly & wet coarse ash evacuation system. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 0 | 0 | [8 empty] | 100% | [7 empty] | 0 |  |  |  |  | 1.2 |  |  |  |  | DPR under preparation | Not Initiated
19.5 | Procurement of Atlas Copco Make Instrument Air Compressors Critical/Non-Critical Spares sub-assembly for performance improvement | Scheme | Yet to be approved |  |  | 6 | [7 empty] | 1) Reduces breakdown time. 2) Reduction in electrical power consumption. 3) Ensures un-interrupted dry fly ash evacution & conveying system. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | [8 empty] | 100% | [7 empty] | 0 |  |  |  |  | 6 |  |  |  |  | DPR under preparation | Not Initiated
19.6 | Upgradation and improvement in Hopper Temperature monitoring system by providing Rf Type Hopper Level Sensors for performance improvement of conveying of Dry ash evacuation system. | Scheme | Yet to be approved |  |  | 1.2 | [7 empty] | 1) Enhances max dry fly ash evacuation. 2) Generates additional revenue through ash utilisation. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 0 | 0 | [8 empty] | 100% | [7 empty] | 0 |  |  |  |  | 1.2 |  |  |  |  | DPR under preparation | Not Initiated
20 | DPR on ash handling plant improvement scheme for AHP U-8 NPTPS Parli-V. | DPR | Yet to be approved | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 | [9 empty] | DPR under preparation | Not Initiated
20.1 | Design, supply, erection, installation & comissioning ESP 1st & 2nd field dry fly ash evacuation & conveying system at AHP U-8. | Scheme | Yet to be approved |  |  | 21.25 | [7 empty] | 1) Max dry fly ash evacuation & utilisation will generate additional revenue. 2) Enhance dry fly ash evacuation, minimise running hours of vacuum pumps which may decrease energy consumption. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.25 | 0 | 0 | [9 empty] | 100% | [6 empty] | 0 | [5 empty] | 21.25 |  |  |  | DPR under preparation | Not Initiated
20.2 | Design, supply, erection, installation & comissioning of dry ash evacuation & conveying system for APH & Economiser ash hoppers at AHP U-8. | Scheme | Yet to be approved |  |  | 3 | [7 empty] | 1) Max dry fly ash evacuation & utilisation will generate additional revenue. 2) Reduction in wet coarse ash evacuation & conveying, minimise water consumption & ash slurry pump running hours, reduce energy consumption. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | [9 empty] | 100% | [6 empty] | 0 | [5 empty] | 3 |  |  |  | DPR under preparation | Not Initiated
21 | Verious Civil schemes in Unit 8 NPTPS Parli V. | DPR | Yet to be approved | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 | [9 empty] | DPR under preparation | Not Initiated
21.1 | Construction of chemical laboratory building at Unit 8, NPTPS, Parli V. | Scheme | Yet to be approved |  |  | 3.78 | [7 empty] | for provide safe storage to the chemical. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 1.28 | 0 | 0 | 0 | [8 empty] | 100% | [7 empty] | 0 |  |  |  |  | 3.78 |  |  |  |  | DPR under preparation | Not Initiated
21.2 | Construction of Alum/salt storage area at Unit No.8 (1X250MW) NPTPS Parli Vaijnath. | Scheme | Yet to be approved |  |  | 3.46 | [7 empty] | for provide safe storage to the chemical. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0.96 | 0 | 0 | 0 | [8 empty] | 100% | [7 empty] | 0 |  |  |  |  | 3.46 |  |  |  |  | DPR under preparation | Not Initiated
21.3 | Construction of Fire Fighting station at Unit-8, NPTPS Parli V. | Scheme | Yet to be approved |  |  | 1.86 | [7 empty] | Provide healthy working enviroment to the staffs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0.36 | 0 | 0 | 0 | [8 empty] | 100% | [7 empty] | 0 |  |  |  |  | 1.86 |  |  |  |  | DPR under preparation | Not Initiated
21.4 | Construction of workshop building at Unit-8, NPTPS Parli V. | Scheme | Yet to be approved |  |  | 2.13 | [7 empty] | For provide machines and workshop building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0.63 | 0 | 0 | 0 | [8 empty] | 100% | [7 empty] | 0 |  |  |  |  | 2.13 |  |  |  |  | DPR under preparation | Not Initiated
22 | CHP improvement scheme at 250 MW | [17 empty] | 0 |  |  | 0 | [21 empty] | 0
22.1 | CHP improvement scheme at 250 MW | [17 empty] | 0 | [5 empty] | 25 | [18 empty] | 0 | [5 empty] | 25
| B) Non-DPR | [17 empty] | 0 | [24 empty] | 0
[19 empty] | 0 | [24 empty] | 0
| B) GA | [17 empty] | 0 | 0.34312 | 0.56615 |  | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 | [16 empty] | 0 | 0.40371 | 0.56615 |  | 0.29 | 0.29 | 0.29 | 0.29 | 0.29
[19 empty] | 0 |  |  | 0.29 | [21 empty] | 0 |  |  | 0
| C) Asset received from Project U#8 | [17 empty] | 0 | [24 empty] | 0 | [9 empty] | Categorise (Works deferred for execution Regu.No.24.1 (ii).
1 | Asset Recived From Civil-U#8-Land-10101 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.0031293 | 0 | 0.0031293 | 0 | 0 | [22 empty] | 0% |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.0031293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 110100101 | 19.11.2016
2 | Asset Recived From Civil-U#8-T.G. Building-10201 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.010038 | 0 | 0.010038 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.010038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 120100249 | 19.11.2016
3 | Asset Recived From Civil-U#8-T.G. Building(BC)bay&control room-10201 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.0045784 | 0 | 0.0045784 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.0045784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 120100250 | 19.11.2016
4 | Asset Recived From Civil-U#8-StructuralSteelWorks4TGBldgA2EBays-10201 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.0013976 | 0 | 0.0013976 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.0013976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 120100251 | 19.11.2016
5 | Asset Recived From Civil-U#8-WTP Building-10201 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.00011482 | 0 | 0.00011482 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.00011482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 120100252 | 19.11.2016
6 | Asset Recived From Civil-U#8-DG SET ROOM CUM AIR COMP. HOUSE-10201 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.00010598 | 0 | 0.00010598 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.00010598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 120100253 | 19.11.2016
7 | Asset Recived From Civil-U#8-WTP-Raw/Fire water pump House-10233 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.00069019 | 0 | 0.00069019 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.00069019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 120200937 | 19.11.2016
8 | Asset Recived From Civil-U#8-SERVICE BUILDING -10211 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.00055144 | 0 | 0.00055144 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.00055144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 120200938 | 19.11.2016
9 | Asset Recived From Civil-U#8-Canteen -10233 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.00072491 | 0 | 0.00072491 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.00072491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 120200939 | 19.11.2016
10 | Asset Recived From Civil-U#8-PARKING SHED -10233 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 6.111e-06 | 0 | 6.111e-06 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 6.111e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 120200940 | 19.11.2016
11 | Asset Recived From Civil-U#8-Time Security Building -10233 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 3.595e-05 | 0 | 3.595e-05 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 3.595e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 120200941 | 19.11.2016
12 | Asset Recived From Civil-U#8-Misc.Building/structure/Watchtower-10233 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.00017243 | 0 | 0.00017243 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Other than BTG & BOP. |  | 0 | 0 | 0.00017243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Other than BTG & BOP. | 120200942 | 19.11.2016
13 | Asset Recived From Civil-U#8-Boundry compound wall Mall-10233 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.15766 | 0 | 0.15766 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Other than BTG & BOP. |  | 0 | 0 | 0.15766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Other than BTG & BOP. | 120200943 | 19.11.2016
14 | Asset Recived From Civil-U#8-Workshop civil work-10233 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 4.188e-05 | 0 | 4.188e-05 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Other than BTG & BOP. |  | 0 | 0 | 4.188e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Other than BTG & BOP. | 120200944 | 19.11.2016
15 | Asset Recived From Civil-U#8-Interior Work for CEC-I Office-10233 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 5.6438e-05 | 0 | 5.6438e-05 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Other than BTG & BOP. |  | 0 | 0 | 5.6438e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Other than BTG & BOP. | 120200945 | 19.11.2016
16 | Asset Recived From Civil-U#8-WTP-Raw water reservoir -10305 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.0012248 | 0 | 0.0012248 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.0012248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 130100760 | 19.11.2016
17 | Asset Recived From Civil-U#8-WTP-Clarifier -10305 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.0011652 | 0 | 0.0011652 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.0011652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 130100761 | 19.11.2016
18 | Asset Recived From Civil-U#8-WTP-Clarifier Water Storage Tank-10305 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.00019514 | 0 | 0.00019514 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.00019514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 130100762 | 19.11.2016
19 | Asset Recived From Civil-U#8-C.W. pump house & forebay-10310 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.00052946 | 0 | 0.00052946 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.00052946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 130100763 | 19.11.2016
20 | Asset Recived From Civil-U#8-Construction of STP for Colony-10322 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.00017966 | 0 | 0.00017966 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Other than BTG & BOP. |  | 0 | 0 | 0.00017966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Other than BTG & BOP. | 130100764 | 19.11.2016
21 | Asset Recived From Civil-U#8-Cooling Towers-10311 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.37628 | 0 | 0.37628 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Other than BTG & BOP. |  | 0 | 0 | 0.37628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Other than BTG & BOP. | 130100765 | 19.11.2016
22 | Asset Recived From Civil-U#8-Railway sidings-10412 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.13615 | 0 | 0.13615 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.13615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 140100483 | 19.11.2016
23 | Asset Recived From Civil-U#8-In plant Roads -10401 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.0009103 | 0 | 0.0009103 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.0009103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 140200326 | 19.11.2016
24 | Asset Recived From Civil-U#8-Pipe Rack -10419 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.00041823 | 0 | 0.00041823 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.00041823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 140200327 | 19.11.2016
25 | Asset Recived From Civil-U#8-Transformar yard area -10541 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.00053169 | 0 | 0.00053169 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.00053169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006753 | 19.11.2016
26 | Asset Recived From Civil-U#8-BA-Boiler and Auxilary foundation-10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.0061116 | 0 | 0.0061116 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.0061116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006754 | 19.11.2016
27 | Asset Recived From Civil-U#8-BA-FD FAN FOUNDATIONS -10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.00011166 | 0 | 0.00011166 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.00011166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006755 | 19.11.2016
28 | Asset Recived From Civil-U#8-BA-PA FAN FOUNDATION -10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.00011166 | 0 | 0.00011166 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.00011166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006756 | 19.11.2016
29 | Asset Recived From Civil-U#8-BA-I.D. Fan foundation -10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.00022332 | 0 | 0.00022332 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.00022332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006757 | 19.11.2016
30 | Asset Recived From Civil-U#8-BA-MILL FOUNDATION-10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.00019826 | 0 | 0.00019826 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.00019826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006758 | 19.11.2016
31 | Asset Recived From Civil-U#8-BA-BUNKER FOUNDATION & STRUCTURE-10515 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.0013925 | 0 | 0.0013925 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.0013925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006759 | 19.11.2016
32 | Asset Recived From Civil-U#8-ESP-10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.00070722 | 0 | 0.00070722 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.00070722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006760 | 19.11.2016
33 | Asset Recived From Civil-U#8-ESP Control Room-10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.00042763 | 0 | 0.00042763 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.00042763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006761 | 19.11.2016
34 | Asset Recived From Civil-U#8-RCC Chimney -10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.0046127 | 0 | 0.0046127 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.0046127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006762 | 19.11.2016
35 | Asset Recived From Civil-U#8-WTP-D.M.Plant equipment fdn. etc.-10509 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 6.3898e-05 | 0 | 6.3898e-05 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 6.3898e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006763 | 19.11.2016
36 | Asset Recived From Civil-U#8-CHP-Wagon Tippler-10515 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.00094041 | 0 | 0.00094041 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.00094041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006764 | 19.11.2016
37 | Asset Recived From Civil-U#8-CHP-Crusher House -10515 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.00074704 | 0 | 0.00074704 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.00074704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006765 | 19.11.2016
38 | Asset Recived From Civil-U#8-CHP-Stacker Reclaimer -10515 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.00028485 | 0 | 0.00028485 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.00028485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006766 | 19.11.2016
39 | Asset Recived From Civil-U#8-CHP-Stock Yard-10515 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.00015851 | 0 | 0.00015851 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.00015851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006767 | 19.11.2016
40 | Asset Recived From Civil-U#8-CHP-ConveyorPedetals&TransferPoint-10515 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.00055408 | 0 | 0.00055408 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.00055408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006768 | 19.11.2016
41 | Asset Recived From Civil-U#8-CHP-MCC ROOM -10515 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.00026945 | 0 | 0.00026945 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.00026945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006769 | 19.11.2016
42 | Asset Recived From Civil-U#8-AHP-RCC Ash Silo -10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.00016423 | 0 | 0.00016423 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.00016423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006770 | 19.11.2016
43 | Asset Recived From Civil-U#8-AHP-Staicase near Silo-10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 1.7302e-05 | 0 | 1.7302e-05 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 1.7302e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006771 | 19.11.2016
44 | Asset Recived From Civil-U#8-AHP-Drain sump in Silo Area -10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 8.551e-06 | 0 | 8.551e-06 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 8.551e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006772 | 19.11.2016
45 | Asset Recived From Civil-U#8-AHP-Slurry Mixing Tank Fdn.-10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 1.6923e-05 | 0 | 1.6923e-05 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 1.6923e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006773 | 19.11.2016
46 | Asset Recived From Civil-U#8-AHP-HCSD PUMP HOUSE-10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 5.8934e-05 | 0 | 5.8934e-05 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 5.8934e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006774 | 19.11.2016
47 | Asset Recived From Civil-U#8-AHP-Ash Slurry Pump House -10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.00014947 | 0 | 0.00014947 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.00014947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006775 | 19.11.2016
48 | Asset Recived From Civil-U#8-AHP-Ash Slurry Sump-10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 4.5159e-05 | 0 | 4.5159e-05 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 4.5159e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006776 | 19.11.2016
49 | Asset Recived From Civil-U#8-AHP-Ash Water Tank-10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 3.422e-05 | 0 | 3.422e-05 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 3.422e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006777 | 19.11.2016
50 | Asset Recived From Civil-U#8-AHP-Bottom Ash Hopper-10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 4.409e-05 | 0 | 4.409e-05 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 4.409e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006778 | 19.11.2016
51 | Asset Recived From Civil-U#8-AHP-Drain sump in BAH Area -10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 8.575e-06 | 0 | 8.575e-06 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 8.575e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006779 | 19.11.2016
52 | Asset Recived From Civil-U#8-Ash Slurry Pipe Line AHP-Pedestals-10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.00013846 | 0 | 0.00013846 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.00013846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006780 | 19.11.2016
53 | Asset Recived From Civil-U#8-AHP-Buffer Hopper Foundation-10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 3.5628e-05 | 0 | 3.5628e-05 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 3.5628e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006781 | 19.11.2016
54 | Asset Recived From Civil-U#8-AHP-Mill reject hopper foundation-10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 1.7814e-05 | 0 | 1.7814e-05 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 1.7814e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006782 | 19.11.2016
55 | Asset Recived From Civil-U#8-FHP-Fuel Oil pump house-10516 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.00065769 | 0 | 0.00065769 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.00065769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006783 | 19.11.2016
56 | Asset Recived From Civil-U#8-FHP-DYKE AREA -10516 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 1.9339e-05 | 0 | 1.9339e-05 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 1.9339e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006784 | 19.11.2016
57 | Asset Recived From Civil-U#8-Effulent Treatment Plant -10509 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.00014135 | 0 | 0.00014135 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.00014135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006785 | 19.11.2016
58 | Asset Recived From Project-U#8-Boiler Pressure parts-10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0 | 0.06549 | 0 | 0.06549 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work after COD within original scope |  | 0 | 0 | 0.06549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work after COD within original scope | 1501006802 | 19.11.2016
59 | Asset Recived From Project-U#8-Mandatory Spares from BHEL–Trichy |  | N.A. | [9 empty] | 08.01.2021 |  | 0 | 0 | 0.0074619 | 0 | 0.0074619 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work after COD within original scope |  | 0 | 0 | 0.0074619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work after COD within original scope | 1501008425 | 08.01.2021
60 | Asset Recived From Civil-U#8-Coal mill reject trench at coal mill D&E |  | N.A. | [9 empty] | 18.10.2019 |  | 0 | 0 | 0.04661 | 0 | 0.04661 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0 | 0.04661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501008440 | 18.10.2019
61 | Asset Recived From Project-U#8-Canteen Equipments & kitchen Utensils |  | N.A. | [9 empty] | 05.11.2020 |  | 0 | 0 | 0.21888 | 0 | 0.21888 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Other than BTG & BOP. |  | 0 | 0 | 0.21888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Other than BTG & BOP. | 180104305 | 05.11.2020
62 | Asset Recived From Project-U#8-Supply & Erection of ACW system-10310 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.00083684 | 0 | 0 | 0.00083684 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.00083684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 130100766 | 19.11.2016
63 | Asset Recived From Project-U#8-SUPPLY & ERECTION OF CCW SYSTEM-10310 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.004856 | 0 | 0 | 0.004856 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.004856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 130100767 | 19.11.2016
64 | Asset Recived From Project-U#8-TG set & its auxilleries-HP/LPFeedWate |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.016842 | 0 | 0 | 0.016842 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.016842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 130100768 | 19.11.2016
65 | Asset Recived From Project-U#8-TG set and its auxilleries- Boilerfeed |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.018479 | 0 | 0 | 0.018479 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.018479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 130100769 | 19.11.2016
66 | Asset Recived From Project-U#8-Air Conditioning-MandatorySpares-10576 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 1.7256e-05 | 0 | 0 | 1.7256e-05 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Work after 19.11.2016 (COD) within original scope |  | 0 | 1.7256e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Work after 19.11.2016 (COD) within original scope | 1501006786 | 19.11.2016
67 | Asset Recived From Project-U#8-Air Conditioning system-10576 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0013446 | 0 | 0 | 0.0013446 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Work after 19.11.2016 (COD) within original scope |  | 0 | 0.0013446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Work after 19.11.2016 (COD) within original scope | 1501006787 | 19.11.2016
68 | Asset Recived From Project-U#8-AHP-FLY ASH & HCSD-SYSTEM-10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0021652 | 0 | 0 | 0.0021652 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.0021652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006788 | 19.11.2016
69 | Asset Recived From Project-U#8-AHP-FLYASH&HCSD-SYSTEMBOUGHT OUT-10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0070969 | 0 | 0 | 0.0070969 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.0070969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006789 | 19.11.2016
70 | Asset Recived From Project-U#8-AHP-BOTTOM ASH SYSTEM-10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.012126 | 0 | 0 | 0.012126 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.012126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006790 | 19.11.2016
71 | Asset Recived From Project-U#8-AHP-ELECTRICAL C & I-10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.004053 | 0 | 0 | 0.004053 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.004053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006791 | 19.11.2016
72 | Asset Recived From Project-U#8-AHP-GEHO PUMP-10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0095128 | 0 | 0 | 0.0095128 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.0095128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006792 | 19.11.2016
73 | Asset Recived FromProject-U#8-Boiler&Aux -Power Cycle Piping-10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.041005 | 0 | 0 | 0.041005 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.041005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006793 | 19.11.2016
74 | Asset Recived From Project-U#8-Boiler&Aux-SUIT BLOWER & PIPING-10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.083837 | 0 | 0 | 0.083837 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.083837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006794 | 19.11.2016
75 | Asset Recived From Project-U#8-Boiler & Auxillaries - PA FAN-10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0010226 | 0 | 0 | 0.0010226 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.0010226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006795 | 19.11.2016
76 | Asset Recived From Project-U#8-Boiler&Aux-Air Preheaters-10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.013281 | 0 | 0 | 0.013281 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.013281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006796 | 19.11.2016
77 | Asset Recived From Project-U#8-Boiler & Auxillaries -COAL MILL-10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.051244 | 0 | 0 | 0.051244 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.051244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006797 | 19.11.2016
78 | Asset Recived From Project-U#8-Boiler & Auxillaries -FD FAN-10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0006817 | 0 | 0 | 0.0006817 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.0006817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006798 | 19.11.2016
79 | Asset Recived From Project-U#8-Boiler & Auxillaries- ID FAN-10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0017043 | 0 | 0 | 0.0017043 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.0017043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006799 | 19.11.2016
80 | Asset Recived From Project-U#8-Boiler&Aux-Mandatory Spares-10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0097935 | 0 | 0 | 0.0097935 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.0097935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006800 | 19.11.2016
81 | Asset Recived From Project-U#8-Boiler&Aux-PLATFORM,STAIRS,GRATINGS, |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.030596 | 0 | 0 | 0.030596 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.030596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006801 | 19.11.2016
82 | Asset Recived From Project-U#8-Boiler Pressure parts-10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.17807 | 0 | 0 | 0.17807 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.17807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006802 | 19.11.2016
83 | Asset Recived From Project-U#8-220V-BATTERY+CHARGERS-MAIN PLANT-10563 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0020848 | 0 | 0 | 0.0020848 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.0020848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006803 | 19.11.2016
84 | Asset Recived From Project-U#8-220V -BATTERY WITH CHARGERS(CHP)-10563 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.00020745 | 0 | 0 | 0.00020745 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.00020745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006804 | 19.11.2016
85 | Asset Recived From Project-U#8-220V-BATTERY+CHARG-WAGON TRIP-2N-10563 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 8.4674e-05 | 0 | 0 | 8.4674e-05 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 8.4674e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006805 | 19.11.2016
86 | Asset Recived From Project-U#8-BOP-OTHER C& i INSTRUMENTS-10509 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0013441 | 0 | 0 | 0.0013441 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.0013441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006806 | 19.11.2016
87 | Asset Recived From Project-U#8-CHP-CONVEYOR SYSTEM-10515 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.015409 | 0 | 0 | 0.015409 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.015409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006807 | 19.11.2016
88 | Asset Recived From Project-U#8-CHP-WOBLER FEEDER-10515 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.00054613 | 0 | 0 | 0.00054613 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.00054613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006808 | 19.11.2016
89 | Asset Recived From Project-U#8-CHP-APRON FEEDER-10515 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0028149 | 0 | 0 | 0.0028149 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.0028149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006809 | 19.11.2016
90 | Asset Recived From Project-U#8-CHP-ILMS,METAL DETECTOR,BELT WEIGHER |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0011704 | 0 | 0 | 0.0011704 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.0011704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006810 | 19.11.2016
91 | Asset Recived From Project-U#8-CHP-IMPACT CRUSHER-10515 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0020638 | 0 | 0 | 0.0020638 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.0020638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006811 | 19.11.2016
92 | Project-U#8-CHP-STRACKER CUM RECLAIMER-10515 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0082014 | 0 | 0 | 0.0082014 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.0082014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006812 | 19.11.2016
93 | Project-U#8-CHP-SIDE DISCHARGE TYPE WAGON TRIPPLER |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0077836 | 0 | 0 | 0.0077836 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.0077836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006813 | 19.11.2016
94 | Project-U#8-Coal Handling Plant-M.S.-10515 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.00034267 | 0 | 0 | 0.00034267 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.00034267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006814 | 19.11.2016
95 | Project-U#8-communication system-10572 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0019253 | 0 | 0 | 0.0019253 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Work after 19.11.2016 (COD) within original scope |  | 0 | 0.0019253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Work after 19.11.2016 (COD) within original scope | 1501006815 | 19.11.2016
96 | Project-U#8-UPS INVERTORS-10563 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.00051465 | 0 | 0 | 0.00051465 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.00051465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006816 | 19.11.2016
97 | Project-U#8-UPS ACDS-10563 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 8.9956e-05 | 0 | 0 | 8.9956e-05 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 8.9956e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006817 | 19.11.2016
98 | Project-U#8-UPS BATTERIRERS-10563 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.00051465 | 0 | 0 | 0.00051465 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.00051465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006818 | 19.11.2016
99 | Project-U#8-24V BATTERY CHARGERS (SGTG)-10563 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.00022873 | 0 | 0 | 0.00022873 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.00022873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006819 | 19.11.2016
100 | Project-U#8-24V BATTERY CHARGERS (BOP)-10563 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.00022873 | 0 | 0 | 0.00022873 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.00022873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006820 | 19.11.2016
101 | Project-U#8-BATTERIS FOR (SGTG)-10563 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.00022873 | 0 | 0 | 0.00022873 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.00022873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006821 | 19.11.2016
102 | Project-U#8-BATTERIS FOR (BOP)-10563 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.00022873 | 0 | 0 | 0.00022873 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.00022873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006822 | 19.11.2016
103 | Project-U#8-DCDB(SGTG)-10563 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 5.7183e-05 | 0 | 0 | 5.7183e-05 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 5.7183e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006823 | 19.11.2016
104 | Project-U#8-DCDB(BOP)-10563 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 5.7183e-05 | 0 | 0 | 5.7183e-05 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 5.7183e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006824 | 19.11.2016
105 | Project-U#8-Controls & Instru. for Main Plant(BTG) |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.044292 | 0 | 0 | 0.044292 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.044292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006825 | 19.11.2016
106 | Project-U#8-CW Chlorination system-10509 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0011974 | 0 | 0 | 0.0011974 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.0011974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006826 | 19.11.2016
107 | Project-U#8-D.G.SET-10509 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 3.7894e-05 | 0 | 0 | 3.7894e-05 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 3.7894e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006827 | 19.11.2016
108 | Project-U#8-D.M.Water System-10509 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.005785 | 0 | 0 | 0.005785 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.005785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006828 | 19.11.2016
109 | Project-U#8-DG set- Manadatory Spares-10509 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.00025004 | 0 | 0 | 0.00025004 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.00025004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006829 | 19.11.2016
110 | Project-U#8-DG Set Room cum Air Compressor House |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0055794 | 0 | 0 | 0.0055794 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.0055794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006830 | 19.11.2016
111 | Project-U#8-Steel for TechnologicalStructure-10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.14836 | 0 | 0 | 0.14836 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.14836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006831 | 19.11.2016
112 | Project-U#8-Electrical Package for BOP-10509 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0024904 | 0 | 0 | 0.0024904 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.0024904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006832 | 19.11.2016
113 | Project-U#8-Electrical CHARGES-10509 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 4.1155e-05 | 0 | 0 | 4.1155e-05 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 4.1155e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006833 | 19.11.2016
114 | Project-U#8-Electrical Package for BOP-Mandatory |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0002757 | 0 | 0 | 0.0002757 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.0002757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006834 | 19.11.2016
115 | Project-U#8-Fire Protection, Alarm & Detection |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0071788 | 0 | 0 | 0.0071788 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.0071788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006835 | 19.11.2016
116 | Project-U#8-Fuel Oil Pump House-10516 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0040925 | 0 | 0 | 0.0040925 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.0040925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006836 | 19.11.2016
117 | Project-U#8-Generator Transformer-10541 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.012655 | 0 | 0 | 0.012655 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.012655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006837 | 19.11.2016
118 | Project-U#8-Generator/Transformer protection |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.00024539 | 0 | 0 | 0.00024539 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.00024539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006838 | 19.11.2016
119 | Project-U#8-H.T.Switchgear for main plant-10561 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.025188 | 0 | 0 | 0.025188 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.025188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006839 | 19.11.2016
120 | Project-U#8-Indoor & Outdoor plant lighting-10599 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0004077 | 0 | 0 | 0.0004077 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.0004077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006840 | 19.11.2016
121 | Project-U#8-L.P.Piping including valves-10509 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0038246 | 0 | 0 | 0.0038246 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.0038246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006841 | 19.11.2016
122 | Project-U#8-L.T. Electrical for main plant.-10561 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 8.7067e-05 | 0 | 0 | 8.7067e-05 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 8.7067e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006842 | 19.11.2016
123 | Project-U#8-Laying&Termination of HT cables-10561 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0008231 | 0 | 0 | 0.0008231 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.0008231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006843 | 19.11.2016
124 | Project-U#8-MainBoiler Structure&foundations-10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.09941 | 0 | 0 | 0.09941 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.09941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006844 | 19.11.2016
125 | Project-U#8-Mandatory Spares for Ash HandlingPlant |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0015616 | 0 | 0 | 0.0015616 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.0015616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006845 | 19.11.2016
126 | Project-U#8-Mandatory spares for C&I of Main Plant |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0050295 | 0 | 0 | 0.0050295 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.0050295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006846 | 19.11.2016
127 | Project-U#8-Mandatory Spares for Electrical MainPa |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.015601 | 0 | 0 | 0.015601 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.015601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006847 | 19.11.2016
128 | Project-U#8-Mandatory Spares For TG & Auxilliaries |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0062588 | 0 | 0 | 0.0062588 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.0062588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006848 | 19.11.2016
129 | Project-U#8-Misc. Cranes & hoists-10553 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0023537 | 0 | 0 | 0.0023537 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.0023537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006849 | 19.11.2016
130 | Project-U#8-Miscellaneous Pumps -10599 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0015672 | 0 | 0 | 0.0015672 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Work after 19.11.2016 (COD) within original scope |  | 0 | 0.0015672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Work after 19.11.2016 (COD) within original scope | 1501006850 | 19.11.2016
131 | Project-U#8-Passanger lift for TG Building-10599 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0016358 | 0 | 0 | 0.0016358 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Work after 19.11.2016 (COD) within original scope |  | 0 | 0.0016358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Work after 19.11.2016 (COD) within original scope | 1501006851 | 19.11.2016
132 | Project-U#8-Passanger/Material Lift at boiler side |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.00084731 | 0 | 0 | 0.00084731 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work after COD within original scope |  | 0 | 0.00084731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work after COD within original scope | 1501006852 | 19.11.2016
133 | Project-U#8-Chemical Laboratory -10509 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0011648 | 0 | 0 | 0.0011648 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.0011648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006853 | 19.11.2016
134 | Project-U#8-Sewage Treatment Plant-10509 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0019006 | 0 | 0 | 0.0019006 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Other than BTG & BOP. |  | 0 | 0.0019006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Other than BTG & BOP. | 1501006854 | 19.11.2016
135 | Project-U#8-Station Transformer-10541 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.026576 | 0 | 0 | 0.026576 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.026576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006855 | 19.11.2016
136 | Project-U#8-Steam Turbine set-10503 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.13864 | 0 | 0 | 0.13864 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.13864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006856 | 19.11.2016
137 | Project-U#8-TG set and its auxilleries- Condensor |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.012703 | 0 | 0 | 0.012703 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.012703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006857 | 19.11.2016
138 | Project-U#8-TG set and its auxilleries -Generator |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.032545 | 0 | 0 | 0.032545 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.032545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006858 | 19.11.2016
139 | Project-U#8-TG set and its auxilleries-Condensor |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.029273 | 0 | 0 | 0.029273 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.029273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006859 | 19.11.2016
140 | Project-U#8-TG set & its auxilleries-Derator-10503 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.002758 | 0 | 0 | 0.002758 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.002758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006860 | 19.11.2016
141 | Project-U#8-TG set and its auxilleries-DMMakeUpSys |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0010491 | 0 | 0 | 0.0010491 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.0010491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006861 | 19.11.2016
142 | Project-U#8-TG set and its auxilleries-Gas System |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0056178 | 0 | 0 | 0.0056178 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.0056178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006862 | 19.11.2016
143 | Project-U#8-TG set and its auxilleries-GoveringSys |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 4.9466e-05 | 0 | 0 | 4.9466e-05 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 4.9466e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006863 | 19.11.2016
144 | Project-U#8-TG set and its auxilleries-HP/LP By-pa |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.010752 | 0 | 0 | 0.010752 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.010752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006864 | 19.11.2016
145 | Project-U#8-TG set and its auxilleries-HP/LP Dozin |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.00039941 | 0 | 0 | 0.00039941 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.00039941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006865 | 19.11.2016
146 | Project-U#8-TG set and its auxilleries-SealOilPump |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 9.8566e-05 | 0 | 0 | 9.8566e-05 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 9.8566e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006866 | 19.11.2016
147 | Project-U#8-TG set and its auxilleries-Vaccum Syst |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.010304 | 0 | 0 | 0.010304 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.010304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006867 | 19.11.2016
148 | Project-U#8-Turbine Lub. Oil System With Purifier |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0022364 | 0 | 0 | 0.0022364 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.0022364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501006868 | 19.11.2016
149 | Project-U#8-Ventillation system-10599 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0014389 | 0 | 0 | 0.0014389 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Work after 19.11.2016 (COD) within original scope |  | 0 | 0.0014389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Work after 19.11.2016 (COD) within original scope | 1501006869 | 19.11.2016
150 | Asset Recived From Project-U#8-M.SPARE_Ventillation system-10599 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 8.5482e-05 | 0 | 0 | 8.5482e-05 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Work after 19.11.2016 (COD) within original scope |  | 0 | 8.5482e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Work after 19.11.2016 (COD) within original scope | 1501006870 | 19.11.2016
151 | Asset Recived From Project-U#8-Water Treatment Plant-10509 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0042384 | 0 | 0 | 0.0042384 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 0.0042384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501006871 | 19.11.2016
152 | Asset Recived From Project-U#8-WORK SHOP MAD_SPARE-10565 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.00030445 | 0 | 0 | 0.00030445 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Other than BTG & BOP. |  | 0 | 0.00030445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Other than BTG & BOP. | 1501006872 | 19.11.2016
153 | Asset Recived From Project-U#8-Workshop-10565 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0013286 | 0 | 0 | 0.0013286 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Other than BTG & BOP. |  | 0 | 0.0013286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Other than BTG & BOP. | 1501006873 | 19.11.2016
154 | Asset Recived From Project-U#8-CMR SYSTEM-10501 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.0020736 | 0 | 0 | 0.0020736 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Other than BTG & BOP. |  | 0 | 0.0020736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Other than BTG & BOP. | 1501006874 | 19.11.2016
155 | Asset Recived From Project-U#8-MandatorySpares-WTP-10.509 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 8.1517e-05 | 0 | 0 | 8.1517e-05 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Works before 19.11.2016 (COD) within Original Scope |  | 0 | 8.1517e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Works before 19.11.2016 (COD) within Original Scope | 1501007958 | 19.11.2016
156 | Asset Recived From Project-U#8-E.1.07_MandSpar 4 C&I MS 4MeasuringIns E.1.07_M S for C&I_ MS For Measuring Ins |  | N.A. | [9 empty] | 29.04.2019 |  | 0 | 0.078697 | 0 | 0 | 0.078697 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.078697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 1501008285 | 29.04.2019
157 | Asset Recived From Project-U#8-BOP_ELECTRICAL-10612 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.01637 | 0 | 0 | 0.01637 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BOP Work after 19.11.2016 (COD) within original scope |  | 0 | 0.01637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOP Work after 19.11.2016 (COD) within original scope | 160100270 | 19.11.2016
158 | Asset Recived From Project-U#8-Bus Ducts-10612 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.012548 | 0 | 0 | 0.012548 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.012548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 160100271 | 19.11.2016
159 | Asset Recived From Project-U#8-Cable trays & supports-10612 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.00036009 | 0 | 0 | 0.00036009 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | BTG Work before COD within original scope |  | 0 | 0.00036009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BTG Work before COD within original scope | 160100272 | 19.11.2016
160 | Project-U#8-PCR FURNITURE-10810 |  | N.A. | [9 empty] | 19.11.2016 |  | 0 | 0.00030684 | 0 | 0 | 0.00030684 | 0 | 0 | 0 | [21 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Other than BTG & BOP. |  | 0 | 0.00030684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Other than BTG & BOP. | 180102383 | 19.11.2016
161 | Project-U#8 Server Intel QUAD CORE 02No. HP Office Server |  | N.A. | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0.11918 | 0 | 0 | [10 empty] | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.11918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0.11918 | 0 | 0 | 0 | 0 | 0 | 0 | 0
162 | Supply Erection testing and commissining of 1000 m3 ETP Civil works |  | N.A. | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0.68324 | 0 | 0 | [10 empty] | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.68324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0.68324 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | [24 empty] | 0
| Total | [13 empty] | 0 | 7.1026 | 47.8937 | 43.2938 | 98.2901 | 20.1701 | 28.2934 | 108.28 | 214.42 | 195.37 | 161.54 | 11.79 | 65.29 | [12 empty] | 0 | 5.777 | 12.4831 | 25.444 | 43.704 | 12.8049 | 78.8337 | 93.31 | 239.08 | 203.37 | 161.54 | 11.79 | 65.29 | 0
[45 empty] | 0.40371 | 0.56615 | 0
Formulas:
Approved Start Date = IF([MERC Approval Date]=0,"-",[MERC Approval Date])
Note on M4: SSP-RCD As per the implementation plan submitted in the DPR/ Approved by MERC

## F4.3
MSPGCL: Parli 8
MTR Petition Formats - Generation
| Project Details | Form 4.3: Capital Work-in-progress - Project-wise details | [9 empty] | (Rs. Crore)
Sr. No. | Project Code | MERC Approval No. | MERC Approval Date | Approved Project Cost | Cumulative Expenditure Incurred till beginning of the Year | Capital Expenditure Capitalised | Opening CWIP | Investment during the year | Capitalization |  |  |  | Closing CWIP
[9 empty] | Works Capitalised | Interest Capitalised | Expenses Capitalised | Total Capitalisation
FY 2022-23
0 | Add Cap (As per 296 of 2019) | 0 | - | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0
A | Initial spares | Add Cap (As per 296 of 2019) | - | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0
1 | Boiler and Auxiliaries | Add Cap (As per 296 of 2019) | - | 7.2 |  |  | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of Coal Mill XRP-903 Gear Box Type KMP-280 Spares of Unit # 8 at BM-NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 1.35 | 1.35 |  |  | 1.35 | 0
2 | Supply of Labyrinth Seal Rings with replaceable Inner liners for Coal Mill XRP-903 required for BM Unit-8, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.33134 | 0.33134 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply and Installation of coal mill liners(weld overlay) of XRP-903 Coal Mill in BM U-8, NPTPS,Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.33134 | 0.33134 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of Coal Mill XRP-903 Bowl & Bowl Hub of Unit # 8 at BM-NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 0 | 0.73326 | 0.73326 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply of impeller assembly for ID fan | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0.5233 | 0.5233 |  |  | 0.5233 | 0
6 | Procurement of Primary Air Fan & Forced Draught Fan Drive Coupling on OEM basis required at BM U-8, NPTPS, Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0.1941 | 0.1941 |  |  | 0.1941 | 0
7 | Procurement of Primary Air Fan PAF 17/11.8-2 Hydraulic Adjustment Device on OEM basis required at BM U-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.53521 | 0.53521 | 0 | 0 | 0 |  |  | 0 | 0
8 | Proc of spares for fabric expansion joints required at BM U-8, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.56972 | 0.56972 | 0 | 0 | 0 |  |  | 0 | 0
9 | Proc of separator body and seperator top spares for coal mill XRP-903 at BM U-8, NPTPS Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.42569 | 0.42569 | 0 | 0 | 0 |  |  | 0 | 0
10 | Proc of scrapper area & reject system spares for coal mill XRP-903 at BM U-8, NPTPS Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.27833 | 0.27833 | 0 | 0 | 0 |  |  | 0 | 0
11 | Proc of seal air fan spares at BM-8 NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.26432 | 0.26432 | 0 | 0 | 0 |  |  | 0 | 0
12 | Procurement of FD Fan Type FAF 17/9.5-1 Drive Coupling required at BM U-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | Procurement of complete planatary gear box-KMP -280/300 for coal mill XRP-903 at BM U-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Turbine and Auxiliaries | Add Cap (As per 296 of 2019) | - | 4.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of spares for Equipment Cooling Water Pumps (Make-FLOWMORE) of model FIG-5824 (SG Side) and FIG-5822 (TG side) at Unit-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.51812 | 0.51812 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply of spars for recovery & FF Pumps along with work at U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0.37713 | 0.37713 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of seal oil vacuum pump in unit 08 | Add Cap (As per 296 of 2019) | - | 0 | 0.27502 | 0.27502 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of AC pressure pipes (235MM OD, 200MM ID, 4.5M Length) for NDCT hot spray water distribution system in Unit-8 NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 0 | 0.42522 | 0.42522 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply of M/s Summits make Instrument Air Dryer & spares at U # 8 TM, Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.54787 | 0.54787 | 0 | 0 | 0 |  |  | 0 | 0
6 | Supply of PVC fills for NDCTs at U # 8 TM, Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.58245 | 0.58245 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of NB 600MM Gate valves for ACW self cleaning strainers in U#8 TM NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.42338 | 0.42338 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of Mechanical seals ( Make Leak-Proof) for various pumps in TM Unit-8 NPTPS Parli. | Add Cap (As per 296 of 2019) | - | 0 | 0.49233 | 0.49233 | 0 | 0 | 0 |  |  | 0 | 0
9 | Supply of SS 304 pipes & others at U # 8 TM, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.52905 | 0.52905 | 0 | 0 | 0 |  |  | 0 | 0
3 | Electrical and Instrumentation | Add Cap (As per 296 of 2019) | - | 6.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of Instrumentation Spares of LP Bypass System at Unit-8. | Add Cap (As per 296 of 2019) | - | 0 | 1.9615 | 1.9615 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of Schneider MICOM Numerical Relays for GRP and STPR swithcgear at NPTPS Unit-8 Testing | Add Cap (As per 296 of 2019) | - | 0 | 0.47613 | 0.47613 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of 220V DC Chloride make (formally caldyne) make battery chargers Spre of Unit 8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.23365 | 0.23365 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of 24V DC Chhabi make make battery chargers Spare of Unit 8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.16465 | 0.16465 | 0 | 0.06 | 0.06 |  |  | 0.06 | 0
5 | Procurement of Spare for Hitachi Hi-Rel make UPS systems installed at Unit-8 NPTPS Parli Vaijnath. | Add Cap (As per 296 of 2019) | - | 0 | 0.19186 | 0.19186 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of various test kit for testing U#8 such as energy meter calibration kit, DC earth faulth locator kit, promary current injection kit, breaker time measurement kit, numeric relay test kit and other testing instruments. | Add Cap (As per 296 of 2019) | - | 0 | 0.67345 | 0.67345 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of Energymeter Caliberation Software Module and hardware for upgrading Numeric Relay Test kit at Unit -8 Testing. | Add Cap (As per 296 of 2019) | - | 0 | 0.11863 | 0.11863 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of H T Motors. | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of critical L T Motors | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of ESP Hopper heaters (As a initial spares) Installed at EM U-8, NPTPS, Parli-Vaijnath under add cap scheme. | Add Cap (As per 296 of 2019) | - | 0 | 0.38586 | 0.38586 | 0 | 0 | 0 |  |  | 0 | 0
4 | Outdoor Plant(CHP/AHP/WTP) | Add Cap (As per 296 of 2019) | - | 6.64 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of Apron Feeder spares installed at CHP NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 1.6233 | 1.6233 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply of various drive and non drive pulleys for CHP U-8. | Add Cap (As per 296 of 2019) | - | 0 | 0.54529 | 0.54529 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply and installation of clamp pads & resting pads for Side Beam of Wagon Tippler for CHP U-8 | Add Cap (As per 296 of 2019) | - | 0 | 0.54802 | 0.54802 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply of unbalance motorozied vibrating feeder for S/R of U-7/8 CHP NPTPS Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.3958 | 0.3958 | 0 | 0 | 0 |  |  | 0 | 0
5 | Procurement of conveying and Instrument air compressor spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 1.7575 | 1.7575 | 0 | 0.012459 | 0.012459 |  |  | 0.012459 | 0
6 | Procurement of vacuum pump spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0.2291 | 0.2291 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of fluidizing blower spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0.11796 | 0.11796 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of slurry pump spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of Clinker grinder spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0.12334 | 0.12334 |  |  | 0.12334 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B | Reassessment of remaining BOP work after insolvency of M/s Sunil Hi-Tech | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Project balance E&M and procurement of mandetory spares | MERC CAPEX Approval in MTR Order 296 of 2019 | Order 296 of 2019 | 41.4534 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work order for Contract of Supply and application of Fire Stop Mortar Seal and Fire Retardant Cable Coating Compound at NPTP U-8 Parli Project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 3.4589 | 3.4589 | 0 | 0 | 0 |  |  | 0 | 0
2 | Work order for contract for Supply Installaion Testing & Commissioning Smoke Detection & alaram system | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 2.5606 | 2.5606 | 0 | 0 | 0 |  |  | 0 | 0
3 | Work order for contract for Supply Installaion Testing & Commissioning of Balance Fire Fighting System at NPTP U-8 Parli Project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.0502 | 1.0502 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, Errection, testing & commissioning works of RWP, PT potable chlorination system, ETP system control panel, automation of LDO, HFO tank foam system Hose boxes with RRL hoses and branch pipe and allied system at NPTP | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.8496 | 0.8496 | 0 | 0 | 0 |  |  | 0 | 0
5 | Work Order contract for supply, installation Testing & Commissioning of telephone exchange (EPBAX) & Telephone System at NPTP U-8 Parli project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.91256 | 0.91256 | 0 | 0 | 0 |  |  | 0 | 0
6 | Balance Supply of Electrical Lab Equipment at NPTP parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.60826 | 0.60826 | 0 | 0 | 0 |  |  | 0 | 0
7 | Work order for contract for Supply Installaion Testing & Commissioning with required material to complete Balance CHP work at NPTP U-8 Parli Project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0 | 0 | 0 | 0.41 | 0.41 |  |  | 0.41 | 0
8 | Supply, Errection, testing & commissioning of Interconnecting Conveyor no.9 & 10 from U-8 to U-6&7 of CHP at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 2.6267 | 0 | 2.6267 | 0.95521 | 3.5814 |  |  | 3.5814 | 0.0005
9 | SUPPLY ,INSTA,TEST ,COMM ELECTRICAL SYS | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | SUPPLY,INSTAL,TEST,COMM OF CRANS&HOIST | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0 | 0 | 0 | 1.3805 | 1.3805 |  |  | 1.3805 | 0
11 | Supply, Errection, testing & commissioning of Dust Extraction system at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.8061 | 0 | 1.8061 | 0 | 0 |  |  | 0 | 1.8061
12 | Supply, Errection, testing & commissioning of DSS & DFDS at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 2.8091 | 0 | 2.8091 | 0 | 0 |  |  | 0 | 2.8091
13 | Supply, Errection, testing & commissioning of Monorail at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.8011 | 0 | 0.8011 | 0.38808 | 1.1891 |  |  | 1.1891 | 7.77e-05
14 | Supply, Errection, testing & commissioning of various Control & Instrumentation equipments at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0 | 0 | 0 | 0.72225 | 0.72225 |  |  | 0.72225 | 0
15 | Supply, Errection, testing & commissioning of Air Conditioning System at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0 | 0 | 0 | 0.15304 | 0.44729 |  |  | 0.44729 | -0.29425
16 | Supply, Errection, testing & commissioning of Ventilation System at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.86893 | 0 | 0.86893 | 0.33467 | 1.2036 |  |  | 1.2036 | 0
17 | Supply, Errection, testing & commissioning of Elevator works. | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | Work contract for dismentaling, supply, erection & commissioning of MRHS | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | Supply, Errection, testing & commissioning of FF System, Smoke detection & Fire stop mortar & Fire retradant cable coating for conveyor 09 & 10 | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20 | Supply, Errection, testing & commissioning of Chimney Elevator | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Supply, Errection, testing & commissioning work of GEHO Pumps. | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | Procurement of various Mandetory spares of BOP packages | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Balance civil work of BOP scope at 250 MW Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 45.3238 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Area grading | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 4.61 | 0 | 4.61 | 1.9929 | 0 |  |  | 0 | 6.6029
2 | CMD | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.59 | 0 | 0.59 | 0.17624 | 0 |  |  | 0 | 0.76624
3 | Conveyor 09, 10 & TP 06 | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 10.09 | 0 | 10.09 | 0.51517 | 0 |  |  | 0 | 10.6052
4 | Finishing item | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 4.47 | 0 | 4.47 | 1.6746 | 0 |  |  | 0 | 6.1446
5 | Drain & nala | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.72 | 0 | 1.72 | 0.98966 | 0 |  |  | 0 | 2.7097
6 | Internal roads | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 7.91 | 0 | 7.91 | 1.5048 | 0 |  |  | 0 | 9.4148
7 | Stacker & reclaimer | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1 | 0 | 1 | 0.16268 | 0 |  |  | 0 | 1.1627
0 | Other Add Cap | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Laboratory set up | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of Analytical Instruments for condition monitoring Laboratory for 1X250 MW of NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.5 | 0.49655 | 0.49655 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply of Analytical Instruments for Water Analysis Laboratory for 1X250 MW of NPTPS, Parli-V | Add Cap (As per 296 of 2019) | - | 1.23 | 0.29847 | 0.29847 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of Analytical Instruments for Environment Laboratory for 1 x 250 MW, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.39 | 0.3658 | 0.3658 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply of Analytical Instruments for Precision Laboratory for 1 x 250 MW, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply of Analytical Instruments for General Laboratory of Water Treatment Plant of 1 x 250 MW, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Supply of Corrosion Monitor/Meter, Corrosion Coupon & Coupon Rack for 1X250 MW of NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.34 | 0.34736 | 0.34736 | 0 | 0 | 0 |  |  | 0 | 0
7 | Supply of Analytical Instruments for Coal Analysis Laboratory for 1X250 MW of NPTPS, Parli-V | Add Cap (As per 296 of 2019) | - | 1.65 | 0.39444 | 0.39444 | 0 | 0 | 0 |  |  | 0 | 0
9 | Grade slab (WTP Area) | Add Cap (As per 296 of 2019) | - | 1 | 0.99752 | 0.99752 | 0 | 0 | 0 |  |  | 0 | 0
10 | Grade slab (Near AHP Building) | Add Cap (As per 296 of 2019) | - | 0.75 | 0.74556 | 0.74556 | 0 | 0 | 0 |  |  | 0 | 0
11 | Temporary shed for empty barrles & filled barrles | Add Cap (As per 296 of 2019) | - | 0.5 | 0.45635 | 0.45635 | 0 | 0 | 0 |  |  | 0 | 0
12 | Cabins for operators at TP. | Add Cap (As per 296 of 2019) | - | 0.2 | 0.18583 | 0.18583 | 0 | 0 | 0 |  |  | 0 | 0
13 | Compound wall for isolation of administrative building. | Add Cap (As per 296 of 2019) | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Work of providing/ fixing of internal partitions of aluminium/Nova palm/glass/wooden for Unit 8 service building & other allied builings in the premises. | Add Cap (As per 296 of 2019) | - | 0.7 | 0.67356 | 0.67356 | 0 | 0 | 0 |  |  | 0 | 0
15 | Provision of DM and softening water line interconnection from u-6,7 to u-8 & Provision of recovery of waste water from sandava pump house,NDCT. | Add Cap (As per 296 of 2019) | - | 3 | 1.0266 | 1.0266 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | Add Cap (As per 296 of 2019) | - | 0 | 1.8371 | 1.8371 | 0 | 0 | 0 |  |  | 0 | 0
16 | Hydraulic drive system modification. | Add Cap (As per 296 of 2019) | - | 2.5 | 2.4384 | 2.4384 | 0 | 0 | 0 |  |  | 0 | 0
17 | Link conveyor from Con-2 of U-6/7 to Con.-2AB of U-8. | Add Cap (As per 296 of 2019) | - | 3.7 | 3.8434 | 3.8434 | 0 | 0 | 0 |  |  | 0 | 0
18 | Ozone plant for Unit -8 | Add Cap (As per 296 of 2019) | - | 20 | 12.9047 | 0 | 12.9047 | 5 | 0 |  |  | 0 | 17.9047
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | Water management system | Add Cap (As per 296 of 2019) | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8, 20 | Procurement & Installation of EMS system at Unit-8 NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 1 | 0.14417 | 0.14417 | 0 | 0 | 0 |  |  | 0 | 0
21 | Conveyor-5 of stacking/reclaiming belt double drive arrangement. | Add Cap (As per 296 of 2019) | - | 2 | 2.0432 | 2.0432 | 0 | 0 | 0 |  |  | 0 | 0
22 | Chemical lab building | Add Cap (As per 296 of 2019) | - | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Chemical store | Add Cap (As per 296 of 2019) | - | 2.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Lawn development around NDCT. | Add Cap (As per 296 of 2019) | - | 0.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | Tree plantation & greenery along road side. | Add Cap (As per 296 of 2019) | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | Greenery development in area between WTP & main plant. | Add Cap (As per 296 of 2019) | - | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | Construction of staff rooms & store for CHP maint.. | Add Cap (As per 296 of 2019) | - | 1 | 0.90703 | 0.90703 | 0 | 0 | 0 |  |  | 0 | 0
28 | Dsludg filteration for raw water | Add Cap (As per 296 of 2019) | - | 17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29 | PLC/UPS system upgradation | Add Cap (As per 296 of 2019) | - | 0.5 | 0 | 0 | 0 | 0.40149 | 0.40149 |  |  | 0.40149 | 0
0 | DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | FGD at Parli Unit # 8 | MERC/CAPEX/2021-2022/0284 | 2022-06-27 | 89.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.1 | FGD at Parli Unit # 8 | MERC/CAPEX/2021-2022/0284 | 2022-06-27 | 85.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/0284 | 2022-06-27 | 4.04 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Detailed Project Report on Boiler plant performance improvement and availability improvement schemes at Boiler Maintenance 1x250MW Unit-8 TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Procurement & Replacement of Complete Economizer Upper & Lower Bank Coil Assemblies at Unit-8, NPTPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.3 | Procurement & replacement of PA Fan PAF 17/11.8-2 and FD Fan FAF 17/9.5-1 Complete Blade set required at BM U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.4 | Procurement & Replacement of Coal Mill Gear Box Type KMP 280 at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.5 | Procurement & replacement of Bowl & Bowl Hub Assembly of Coal Mill XRP-903 required at BM U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.6 | Procurement of Complete Journal Assembly without Grinding roll for Coal Mill XRP-903 required at BM U-8 NPTPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.7 | Procurement of Hydraulic Adjustment Device for FD Fan FAF 17/9.5-1 at BM U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.8 | SWAS upgradation at U#8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement & Replacement of Complete Platen super heater coils Coil Assemblies at Unit-8, TPS Parli-V, Procurement & Replacement of Complete LTSH upper & lower bank Coil Assemblies at Unit-8, TPS Parli-V & Procurement & Replacement of Coal Mill Gear Box Type KMP 280 at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Procurement & Replacement of Complete Platen super heater coils Coil Assemblies at Unit-8, TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Procurement & Replacement of Complete LTSH upper & lower bank Coil Assemblies at Unit-8, TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Procurement & Replacement of Coal Mill Gear Box Type KMP 280 at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-8, Parli TPS Procurement & replacement of PA & FD fan rotar hub assembly at Unit-8 TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Procurement & replacement of PA & FD fan rotar hub assembly at Unit-8 TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | DPR on Refurbishment of TG Governing system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Refurbishment of TG Governing system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | DPR on Performance improvement of Natural Draft Cooling Tower (NDCT) at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Performance improvement of Natural Draft Cooling Tower (NDCT) by replacement of PVC fills, AC cement pipes, strengthening of Hot water distribution system, replacement of beams, columns, support structures, etc. at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | DPR on Procurement of ACW & CW pump along with mandatory spares at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | DPR on Procurement of ACW & CW pump along with mandatory spares at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | DPR on Procurement of CEP pump and BFP Booster pump along with mandatory spares at Unit-8, PTPS, Parli V and Procurement of Energy Efficient Cartridges of Boiler Feed Pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Procurement of CEP pump and BFP Booster pump along with mandatory spares at Unit-8, PTPS, Parli | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.2 | Procurement of Energy Efficient Cartridges of Boiler Feed Pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | DPR on Procurement of turbine blades of HP, IP & LP rotor in Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.1 | DPR on Procurement of turbine blades of HP, IP & LP rotor in Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | DPR on Repair & Reconditioning of Water treatment plant at Unit-8, PTPS, Parli V and Performance improvement of centralised AC plant at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.1 | Reconditioning of Acid and Alkali Unloading and storage system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.2 | Reconditioning & repairing of WTP DM Plant regeneration system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.3 | Performance improvement of centralised AC plant by reconditioning of cooling tower, various pumps, heat exchangers, etc. at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | DPR on Procurement of Control Fluid (HPCF) pump, Lube Oil pump, Emergency Oil pump, Jacking Oil pump, Seal oil pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.1 | DPR on Procurement of Control Fluid (HPCF) pump, Lube Oil pump, Emergency Oil pump, Jacking Oil pump, Seal oil pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | DPR on Procurement of H2 cooler, BFP coolers, generator exciter cooler, Seal and Lube oil coolers at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.1 | DPR on Procurement of H2 cooler, BFP coolers, generator exciter cooler, Seal and Lube oil coolers at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Supply, installation & commissioning of 220V 2140AH,24V 830AH & 710AH, 360V 570AH Mains UPS,110V 110AH AHP PLC , 110V , 103 AH DM plant battery set for unit 8 , NPTPS Parli-V & Procurement of HT motors at U#8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.1 | Supply, installation & commissioning of 220V 2140AH,24V 830AH & 710AH, 360V 570AH Mains UPS,110V 110AH AHP PLC , 110V , 103 AH DM plant battery set for unit 8 , NPTPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.2 | Procurement of HT motors at U#8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | DPR on various instrumentation & control schemes at U#8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | Upgradation of MAX-DNA DCS system at U#8 (HMI upgradation) | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.2 | Upgradation of existing Pcal system with plant performance analysis diagnostic and optimization system (PADO) at Unit 8 New Parli TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.3 | Upgradation of coal feeder for I&C Unit8 PTPS Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.4 | Procurement of smart control positioner at I&C Unit8 PTPS Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.5 | Upgradation Electronic control drive for I&C Unit8 PTPS Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.6 | Upgradation of turbovisory & vibration monitoring system control panel. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Performance improvement by system up gradation at CHP & DPR for normalization and stabilization of coal handling plant performance at Parli TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.1 | Supply and Commissioning of Energy Efficient Evaporative Cooling System for Control Panel & Breaker room of CHP Unit-8 For PARLI TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.2 | Supply and commissioning of Suspended Magnets for U-8 CHP NPTPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.3 | Stacker-reclaimer Bucket wheel drive modification work of U- 8 CHP | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.4 | Apron feeder drive modification from Hydraulic to Electro-Mechanical at CHP U-8 NPTPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.5 | Procurement of U-8 W/T Major spares | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.6 | Provision of Soft starter / VFD for Various conveyor | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.7 | TP-3 chute modification at U-8 CHP. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.8 | Design, supply and commissioning of solar operated lighting system in CHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.9 | Installation of CCTV survillance system alongwith all conveyors. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | DPR for maximiation of Coal Handling Plant efficiency & DPR on life enhancement of Coal Handling Plant | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | W/T control room & bunker house battery & UPS upgradation | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Refurbishment of conveyor no. 2 A/B & 6 A/B drive system of CHP U-8 TPS Parli. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Provision of Soft starter / VFD for Various conveyor | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Procurement & installation of Belt tear detection system | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.5 | Conveyor gravity takeup infrastructure strengthening work | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.6 | U-8 CHP apron feeder-I to Conveyor 1 A/B chute modification work . | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | DPR for stabiliazation of Coal Handling Performance. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.1 | Drive modification of Stacker Reclaimer slewing system. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.2 | Retrofitting of Side Arm Charger-I & II at CHP U-8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.3 | Upgradation of GE/Schineder make PLC system atU-8 CHP. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.4 | Refurbishment of Apron Feeder at CHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.5 | Provision of moveable stacker and crusher in CHP coal stack yard at CHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.6 | Procurement of Loco & Bulldozer at CHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | DPR on dry fly ash utilisation improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.1 | Design, supply, erection, installation & comissioning of intermediate silo with sub system at AHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | DPR on ash handling plant improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | Design, supply, erection & comissioning of weigh bridge for silo at AHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.2 | Supply, installation & comissioning of energy efficient air compressor at AHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.3 | PROCUREMENT OF COMPLETE ASSEMBLY OF SAM MAKE AR-150/510 PUMPS (2 NOS) FOR REPLACEMENT OF ASH SLURRY PUMPS OF BOTTOM ASH SLURRY DISPOSAL FROM SLURRY TANK TO ASH BUND IN SLURRY PUMP HOUSE. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | PROCUREMENT OF COMPLETE ASSEMBLY OF SAM MAKE ZM-II 530/02 (2 NOS) FOR REPLACEMENT OF HP PUMPS OF BOTTOM ASH & COARSE ASH EVACUATION FROM BA/CA HOPPERS TO SLURRY TANK IN ASH WATER PUMP HOUSE. 0.75 0.89 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.5 | Procurement of vacuum pumps complete assembly for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.6 | Procurement of vacuum pumps complete assembly for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.7 | Procurement of Feed Gate Complete Assembly along with modified metallurgy to enhance the life of Clinker Grinder. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.8 | Procurement of Double Roll Clinker Grinder Complete Assembly with Drive Unit installed at AHP | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.9 | Procurement of Instrument Air Dryers assembly for performance improvement | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | Procurement of various types of Isolation Valves assembly, Dome Valves assembly, Root Valve Assembly & Expansion Bellows Assembly for Dry Ash Conveing performance improvement | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | DPR on ash handling plant improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | Design, supply, erection, installation & comissioning of DM water close loop cooling system for air compressors at AHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.2 | Up-gradation of Existing Schneider make PLC (HMI + PLC hardware) installed at AHP Unit -8 at Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.3 | Procurement of HT motors for AHP U-8 Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.4 | PROCUREMENT OF CRITICAL GEARBOXES AND FLUID COUPLINGS INTERNAL ASSEMBLIES FOR SLURRY PUMPS AND SILO HCSD SYSTEM INSTALLED AT AHP, PARLI TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.5 | Procurement of Atlas Copco Make Instrument Air Compressors Critical/Non-Critical Spares sub-assembly for performance improvement | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.6 | Upgradation and improvement in Hopper Temperature monitoring system by providing Rf Type Hopper Level Sensors for performance improvement of conveying of Dry ash evacuation system. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20 | DPR on ash handling plant improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.1 | Design, supply, erection, installation & comissioning ESP 1st & 2nd field dry fly ash evacuation & conveying system at AHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.2 | Design, supply, erection, installation & comissioning of dry ash evacuation & conveying system for APH & Economiser ash hoppers at AHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Verious Civil schemes in Unit 8 NPTPS Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Construction of chemical laboratory building at Unit 8, NPTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.2 | Construction of Alum/salt storage area at Unit No.8 (1X250MW) NPTPS Parli Vaijnath. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.3 | Construction of Fire Fighting station at Unit-8, NPTPS Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.4 | Construction of workshop building at Unit-8, NPTPS Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | CHP improvement scheme at 250 MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.1 | CHP improvement scheme at 250 MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) GA | 0 | - | 0 | 0 | 0 | 0 | 0.34312 | 0.40371 |  |  | 0.40371 | -0.060588
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | C) Asset received from Project U#8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Asset Recived From Civil-U#8-Land-10101 | N.A. | - | 0 | 0.0031293 | 0 | 0.0031293 | 0 | 0 |  |  | 0 | 0.0031293
2 | Asset Recived From Civil-U#8-T.G. Building-10201 | N.A. | - | 0 | 0.010038 | 0 | 0.010038 | 0 | 0 |  |  | 0 | 0.010038
3 | Asset Recived From Civil-U#8-T.G. Building(BC)bay&control room-10201 | N.A. | - | 0 | 0.0045784 | 0 | 0.0045784 | 0 | 0 |  |  | 0 | 0.0045784
4 | Asset Recived From Civil-U#8-StructuralSteelWorks4TGBldgA2EBays-10201 | N.A. | - | 0 | 0.0013976 | 0 | 0.0013976 | 0 | 0 |  |  | 0 | 0.0013976
5 | Asset Recived From Civil-U#8-WTP Building-10201 | N.A. | - | 0 | 0.00011482 | 0 | 0.00011482 | 0 | 0 |  |  | 0 | 0.00011482
6 | Asset Recived From Civil-U#8-DG SET ROOM CUM AIR COMP. HOUSE-10201 | N.A. | - | 0 | 0.00010598 | 0 | 0.00010598 | 0 | 0 |  |  | 0 | 0.00010598
7 | Asset Recived From Civil-U#8-WTP-Raw/Fire water pump House-10233 | N.A. | - | 0 | 0.00069019 | 0 | 0.00069019 | 0 | 0 |  |  | 0 | 0.00069019
8 | Asset Recived From Civil-U#8-SERVICE BUILDING -10211 | N.A. | - | 0 | 0.00055144 | 0 | 0.00055144 | 0 | 0 |  |  | 0 | 0.00055144
9 | Asset Recived From Civil-U#8-Canteen -10233 | N.A. | - | 0 | 0.00072491 | 0 | 0.00072491 | 0 | 0 |  |  | 0 | 0.00072491
10 | Asset Recived From Civil-U#8-PARKING SHED -10233 | N.A. | - | 0 | 6.111e-06 | 0 | 6.111e-06 | 0 | 0 |  |  | 0 | 6.111e-06
11 | Asset Recived From Civil-U#8-Time Security Building -10233 | N.A. | - | 0 | 3.595e-05 | 0 | 3.595e-05 | 0 | 0 |  |  | 0 | 3.595e-05
12 | Asset Recived From Civil-U#8-Misc.Building/structure/Watchtower-10233 | N.A. | - | 0 | 0.00017243 | 0 | 0.00017243 | 0 | 0 |  |  | 0 | 0.00017243
13 | Asset Recived From Civil-U#8-Boundry compound wall Mall-10233 | N.A. | - | 0 | 0.15766 | 0 | 0.15766 | 0 | 0 |  |  | 0 | 0.15766
14 | Asset Recived From Civil-U#8-Workshop civil work-10233 | N.A. | - | 0 | 4.188e-05 | 0 | 4.188e-05 | 0 | 0 |  |  | 0 | 4.188e-05
15 | Asset Recived From Civil-U#8-Interior Work for CEC-I Office-10233 | N.A. | - | 0 | 5.6438e-05 | 0 | 5.6438e-05 | 0 | 0 |  |  | 0 | 5.6438e-05
16 | Asset Recived From Civil-U#8-WTP-Raw water reservoir -10305 | N.A. | - | 0 | 0.0012248 | 0 | 0.0012248 | 0 | 0 |  |  | 0 | 0.0012248
17 | Asset Recived From Civil-U#8-WTP-Clarifier -10305 | N.A. | - | 0 | 0.0011652 | 0 | 0.0011652 | 0 | 0 |  |  | 0 | 0.0011652
18 | Asset Recived From Civil-U#8-WTP-Clarifier Water Storage Tank-10305 | N.A. | - | 0 | 0.00019514 | 0 | 0.00019514 | 0 | 0 |  |  | 0 | 0.00019514
19 | Asset Recived From Civil-U#8-C.W. pump house & forebay-10310 | N.A. | - | 0 | 0.00052946 | 0 | 0.00052946 | 0 | 0 |  |  | 0 | 0.00052946
20 | Asset Recived From Civil-U#8-Construction of STP for Colony-10322 | N.A. | - | 0 | 0.00017966 | 0 | 0.00017966 | 0 | 0 |  |  | 0 | 0.00017966
21 | Asset Recived From Civil-U#8-Cooling Towers-10311 | N.A. | - | 0 | 0.37628 | 0 | 0.37628 | 0 | 0 |  |  | 0 | 0.37628
22 | Asset Recived From Civil-U#8-Railway sidings-10412 | N.A. | - | 0 | 0.13615 | 0 | 0.13615 | 0 | 0 |  |  | 0 | 0.13615
23 | Asset Recived From Civil-U#8-In plant Roads -10401 | N.A. | - | 0 | 0.0009103 | 0 | 0.0009103 | 0 | 0 |  |  | 0 | 0.0009103
24 | Asset Recived From Civil-U#8-Pipe Rack -10419 | N.A. | - | 0 | 0.00041823 | 0 | 0.00041823 | 0 | 0 |  |  | 0 | 0.00041823
25 | Asset Recived From Civil-U#8-Transformar yard area -10541 | N.A. | - | 0 | 0.00053169 | 0 | 0.00053169 | 0 | 0 |  |  | 0 | 0.00053169
26 | Asset Recived From Civil-U#8-BA-Boiler and Auxilary foundation-10501 | N.A. | - | 0 | 0.0061116 | 0 | 0.0061116 | 0 | 0 |  |  | 0 | 0.0061116
27 | Asset Recived From Civil-U#8-BA-FD FAN FOUNDATIONS -10501 | N.A. | - | 0 | 0.00011166 | 0 | 0.00011166 | 0 | 0 |  |  | 0 | 0.00011166
28 | Asset Recived From Civil-U#8-BA-PA FAN FOUNDATION -10501 | N.A. | - | 0 | 0.00011166 | 0 | 0.00011166 | 0 | 0 |  |  | 0 | 0.00011166
29 | Asset Recived From Civil-U#8-BA-I.D. Fan foundation -10501 | N.A. | - | 0 | 0.00022332 | 0 | 0.00022332 | 0 | 0 |  |  | 0 | 0.00022332
30 | Asset Recived From Civil-U#8-BA-MILL FOUNDATION-10501 | N.A. | - | 0 | 0.00019826 | 0 | 0.00019826 | 0 | 0 |  |  | 0 | 0.00019826
31 | Asset Recived From Civil-U#8-BA-BUNKER FOUNDATION & STRUCTURE-10515 | N.A. | - | 0 | 0.0013925 | 0 | 0.0013925 | 0 | 0 |  |  | 0 | 0.0013925
32 | Asset Recived From Civil-U#8-ESP-10501 | N.A. | - | 0 | 0.00070722 | 0 | 0.00070722 | 0 | 0 |  |  | 0 | 0.00070722
33 | Asset Recived From Civil-U#8-ESP Control Room-10501 | N.A. | - | 0 | 0.00042763 | 0 | 0.00042763 | 0 | 0 |  |  | 0 | 0.00042763
34 | Asset Recived From Civil-U#8-RCC Chimney -10501 | N.A. | - | 0 | 0.0046127 | 0 | 0.0046127 | 0 | 0 |  |  | 0 | 0.0046127
35 | Asset Recived From Civil-U#8-WTP-D.M.Plant equipment fdn. etc.-10509 | N.A. | - | 0 | 6.3898e-05 | 0 | 6.3898e-05 | 0 | 0 |  |  | 0 | 6.3898e-05
36 | Asset Recived From Civil-U#8-CHP-Wagon Tippler-10515 | N.A. | - | 0 | 0.00094041 | 0 | 0.00094041 | 0 | 0 |  |  | 0 | 0.00094041
37 | Asset Recived From Civil-U#8-CHP-Crusher House -10515 | N.A. | - | 0 | 0.00074704 | 0 | 0.00074704 | 0 | 0 |  |  | 0 | 0.00074704
38 | Asset Recived From Civil-U#8-CHP-Stacker Reclaimer -10515 | N.A. | - | 0 | 0.00028485 | 0 | 0.00028485 | 0 | 0 |  |  | 0 | 0.00028485
39 | Asset Recived From Civil-U#8-CHP-Stock Yard-10515 | N.A. | - | 0 | 0.00015851 | 0 | 0.00015851 | 0 | 0 |  |  | 0 | 0.00015851
40 | Asset Recived From Civil-U#8-CHP-ConveyorPedetals&TransferPoint-10515 | N.A. | - | 0 | 0.00055408 | 0 | 0.00055408 | 0 | 0 |  |  | 0 | 0.00055408
41 | Asset Recived From Civil-U#8-CHP-MCC ROOM -10515 | N.A. | - | 0 | 0.00026945 | 0 | 0.00026945 | 0 | 0 |  |  | 0 | 0.00026945
42 | Asset Recived From Civil-U#8-AHP-RCC Ash Silo -10501 | N.A. | - | 0 | 0.00016423 | 0 | 0.00016423 | 0 | 0 |  |  | 0 | 0.00016423
43 | Asset Recived From Civil-U#8-AHP-Staicase near Silo-10501 | N.A. | - | 0 | 1.7302e-05 | 0 | 1.7302e-05 | 0 | 0 |  |  | 0 | 1.7302e-05
44 | Asset Recived From Civil-U#8-AHP-Drain sump in Silo Area -10501 | N.A. | - | 0 | 8.551e-06 | 0 | 8.551e-06 | 0 | 0 |  |  | 0 | 8.551e-06
45 | Asset Recived From Civil-U#8-AHP-Slurry Mixing Tank Fdn.-10501 | N.A. | - | 0 | 1.6923e-05 | 0 | 1.6923e-05 | 0 | 0 |  |  | 0 | 1.6923e-05
46 | Asset Recived From Civil-U#8-AHP-HCSD PUMP HOUSE-10501 | N.A. | - | 0 | 5.8934e-05 | 0 | 5.8934e-05 | 0 | 0 |  |  | 0 | 5.8934e-05
47 | Asset Recived From Civil-U#8-AHP-Ash Slurry Pump House -10501 | N.A. | - | 0 | 0.00014947 | 0 | 0.00014947 | 0 | 0 |  |  | 0 | 0.00014947
48 | Asset Recived From Civil-U#8-AHP-Ash Slurry Sump-10501 | N.A. | - | 0 | 4.5159e-05 | 0 | 4.5159e-05 | 0 | 0 |  |  | 0 | 4.5159e-05
49 | Asset Recived From Civil-U#8-AHP-Ash Water Tank-10501 | N.A. | - | 0 | 3.422e-05 | 0 | 3.422e-05 | 0 | 0 |  |  | 0 | 3.422e-05
50 | Asset Recived From Civil-U#8-AHP-Bottom Ash Hopper-10501 | N.A. | - | 0 | 4.409e-05 | 0 | 4.409e-05 | 0 | 0 |  |  | 0 | 4.409e-05
51 | Asset Recived From Civil-U#8-AHP-Drain sump in BAH Area -10501 | N.A. | - | 0 | 8.575e-06 | 0 | 8.575e-06 | 0 | 0 |  |  | 0 | 8.575e-06
52 | Asset Recived From Civil-U#8-Ash Slurry Pipe Line AHP-Pedestals-10501 | N.A. | - | 0 | 0.00013846 | 0 | 0.00013846 | 0 | 0 |  |  | 0 | 0.00013846
53 | Asset Recived From Civil-U#8-AHP-Buffer Hopper Foundation-10501 | N.A. | - | 0 | 3.5628e-05 | 0 | 3.5628e-05 | 0 | 0 |  |  | 0 | 3.5628e-05
54 | Asset Recived From Civil-U#8-AHP-Mill reject hopper foundation-10501 | N.A. | - | 0 | 1.7814e-05 | 0 | 1.7814e-05 | 0 | 0 |  |  | 0 | 1.7814e-05
55 | Asset Recived From Civil-U#8-FHP-Fuel Oil pump house-10516 | N.A. | - | 0 | 0.00065769 | 0 | 0.00065769 | 0 | 0 |  |  | 0 | 0.00065769
56 | Asset Recived From Civil-U#8-FHP-DYKE AREA -10516 | N.A. | - | 0 | 1.9339e-05 | 0 | 1.9339e-05 | 0 | 0 |  |  | 0 | 1.9339e-05
57 | Asset Recived From Civil-U#8-Effulent Treatment Plant -10509 | N.A. | - | 0 | 0.00014135 | 0 | 0.00014135 | 0 | 0 |  |  | 0 | 0.00014135
58 | Asset Recived From Project-U#8-Boiler Pressure parts-10501 | N.A. | - | 0 | 0.06549 | 0 | 0.06549 | 0 | 0 |  |  | 0 | 0.06549
59 | Asset Recived From Project-U#8-Mandatory Spares from BHEL–Trichy | N.A. | - | 0 | 0.0074619 | 0 | 0.0074619 | 0 | 0 |  |  | 0 | 0.0074619
60 | Asset Recived From Civil-U#8-Coal mill reject trench at coal mill D&E | N.A. | - | 0 | 0.04661 | 0 | 0.04661 | 0 | 0 |  |  | 0 | 0.04661
61 | Asset Recived From Project-U#8-Canteen Equipments & kitchen Utensils | N.A. | - | 0 | 0.21888 | 0 | 0.21888 | 0 | 0 |  |  | 0 | 0.21888
62 | Asset Recived From Project-U#8-Supply & Erection of ACW system-10310 | N.A. | - | 0 | 0.00083684 | 0 | 0.00083684 | 0 | 0 |  |  | 0 | 0.00083684
63 | Asset Recived From Project-U#8-SUPPLY & ERECTION OF CCW SYSTEM-10310 | N.A. | - | 0 | 0.004856 | 0 | 0.004856 | 0 | 0 |  |  | 0 | 0.004856
64 | Asset Recived From Project-U#8-TG set & its auxilleries-HP/LPFeedWate | N.A. | - | 0 | 0.016842 | 0 | 0.016842 | 0 | 0 |  |  | 0 | 0.016842
65 | Asset Recived From Project-U#8-TG set and its auxilleries- Boilerfeed | N.A. | - | 0 | 0.018479 | 0 | 0.018479 | 0 | 0 |  |  | 0 | 0.018479
66 | Asset Recived From Project-U#8-Air Conditioning-MandatorySpares-10576 | N.A. | - | 0 | 1.7256e-05 | 0 | 1.7256e-05 | 0 | 0 |  |  | 0 | 1.7256e-05
67 | Asset Recived From Project-U#8-Air Conditioning system-10576 | N.A. | - | 0 | 0.0013446 | 0 | 0.0013446 | 0 | 0 |  |  | 0 | 0.0013446
68 | Asset Recived From Project-U#8-AHP-FLY ASH & HCSD-SYSTEM-10501 | N.A. | - | 0 | 0.0021652 | 0 | 0.0021652 | 0 | 0 |  |  | 0 | 0.0021652
69 | Asset Recived From Project-U#8-AHP-FLYASH&HCSD-SYSTEMBOUGHT OUT-10501 | N.A. | - | 0 | 0.0070969 | 0 | 0.0070969 | 0 | 0 |  |  | 0 | 0.0070969
70 | Asset Recived From Project-U#8-AHP-BOTTOM ASH SYSTEM-10501 | N.A. | - | 0 | 0.012126 | 0 | 0.012126 | 0 | 0 |  |  | 0 | 0.012126
71 | Asset Recived From Project-U#8-AHP-ELECTRICAL C & I-10501 | N.A. | - | 0 | 0.004053 | 0 | 0.004053 | 0 | 0 |  |  | 0 | 0.004053
72 | Asset Recived From Project-U#8-AHP-GEHO PUMP-10501 | N.A. | - | 0 | 0.0095128 | 0 | 0.0095128 | 0 | 0 |  |  | 0 | 0.0095128
73 | Asset Recived FromProject-U#8-Boiler&Aux -Power Cycle Piping-10501 | N.A. | - | 0 | 0.041005 | 0 | 0.041005 | 0 | 0 |  |  | 0 | 0.041005
74 | Asset Recived From Project-U#8-Boiler&Aux-SUIT BLOWER & PIPING-10501 | N.A. | - | 0 | 0.083837 | 0 | 0.083837 | 0 | 0 |  |  | 0 | 0.083837
75 | Asset Recived From Project-U#8-Boiler & Auxillaries - PA FAN-10501 | N.A. | - | 0 | 0.0010226 | 0 | 0.0010226 | 0 | 0 |  |  | 0 | 0.0010226
76 | Asset Recived From Project-U#8-Boiler&Aux-Air Preheaters-10501 | N.A. | - | 0 | 0.013281 | 0 | 0.013281 | 0 | 0 |  |  | 0 | 0.013281
77 | Asset Recived From Project-U#8-Boiler & Auxillaries -COAL MILL-10501 | N.A. | - | 0 | 0.051244 | 0 | 0.051244 | 0 | 0 |  |  | 0 | 0.051244
78 | Asset Recived From Project-U#8-Boiler & Auxillaries -FD FAN-10501 | N.A. | - | 0 | 0.0006817 | 0 | 0.0006817 | 0 | 0 |  |  | 0 | 0.0006817
79 | Asset Recived From Project-U#8-Boiler & Auxillaries- ID FAN-10501 | N.A. | - | 0 | 0.0017043 | 0 | 0.0017043 | 0 | 0 |  |  | 0 | 0.0017043
80 | Asset Recived From Project-U#8-Boiler&Aux-Mandatory Spares-10501 | N.A. | - | 0 | 0.0097935 | 0 | 0.0097935 | 0 | 0 |  |  | 0 | 0.0097935
81 | Asset Recived From Project-U#8-Boiler&Aux-PLATFORM,STAIRS,GRATINGS, | N.A. | - | 0 | 0.030596 | 0 | 0.030596 | 0 | 0 |  |  | 0 | 0.030596
82 | Asset Recived From Project-U#8-Boiler Pressure parts-10501 | N.A. | - | 0 | 0.17807 | 0 | 0.17807 | 0 | 0 |  |  | 0 | 0.17807
83 | Asset Recived From Project-U#8-220V-BATTERY+CHARGERS-MAIN PLANT-10563 | N.A. | - | 0 | 0.0020848 | 0 | 0.0020848 | 0 | 0 |  |  | 0 | 0.0020848
84 | Asset Recived From Project-U#8-220V -BATTERY WITH CHARGERS(CHP)-10563 | N.A. | - | 0 | 0.00020745 | 0 | 0.00020745 | 0 | 0 |  |  | 0 | 0.00020745
85 | Asset Recived From Project-U#8-220V-BATTERY+CHARG-WAGON TRIP-2N-10563 | N.A. | - | 0 | 8.4674e-05 | 0 | 8.4674e-05 | 0 | 0 |  |  | 0 | 8.4674e-05
86 | Asset Recived From Project-U#8-BOP-OTHER C& i INSTRUMENTS-10509 | N.A. | - | 0 | 0.0013441 | 0 | 0.0013441 | 0 | 0 |  |  | 0 | 0.0013441
87 | Asset Recived From Project-U#8-CHP-CONVEYOR SYSTEM-10515 | N.A. | - | 0 | 0.015409 | 0 | 0.015409 | 0 | 0 |  |  | 0 | 0.015409
88 | Asset Recived From Project-U#8-CHP-WOBLER FEEDER-10515 | N.A. | - | 0 | 0.00054613 | 0 | 0.00054613 | 0 | 0 |  |  | 0 | 0.00054613
89 | Asset Recived From Project-U#8-CHP-APRON FEEDER-10515 | N.A. | - | 0 | 0.0028149 | 0 | 0.0028149 | 0 | 0 |  |  | 0 | 0.0028149
90 | Asset Recived From Project-U#8-CHP-ILMS,METAL DETECTOR,BELT WEIGHER | N.A. | - | 0 | 0.0011704 | 0 | 0.0011704 | 0 | 0 |  |  | 0 | 0.0011704
91 | Asset Recived From Project-U#8-CHP-IMPACT CRUSHER-10515 | N.A. | - | 0 | 0.0020638 | 0 | 0.0020638 | 0 | 0 |  |  | 0 | 0.0020638
92 | Project-U#8-CHP-STRACKER CUM RECLAIMER-10515 | N.A. | - | 0 | 0.0082014 | 0 | 0.0082014 | 0 | 0 |  |  | 0 | 0.0082014
93 | Project-U#8-CHP-SIDE DISCHARGE TYPE WAGON TRIPPLER | N.A. | - | 0 | 0.0077836 | 0 | 0.0077836 | 0 | 0 |  |  | 0 | 0.0077836
94 | Project-U#8-Coal Handling Plant-M.S.-10515 | N.A. | - | 0 | 0.00034267 | 0 | 0.00034267 | 0 | 0 |  |  | 0 | 0.00034267
95 | Project-U#8-communication system-10572 | N.A. | - | 0 | 0.0019253 | 0 | 0.0019253 | 0 | 0 |  |  | 0 | 0.0019253
96 | Project-U#8-UPS INVERTORS-10563 | N.A. | - | 0 | 0.00051465 | 0 | 0.00051465 | 0 | 0 |  |  | 0 | 0.00051465
97 | Project-U#8-UPS ACDS-10563 | N.A. | - | 0 | 8.9956e-05 | 0 | 8.9956e-05 | 0 | 0 |  |  | 0 | 8.9956e-05
98 | Project-U#8-UPS BATTERIRERS-10563 | N.A. | - | 0 | 0.00051465 | 0 | 0.00051465 | 0 | 0 |  |  | 0 | 0.00051465
99 | Project-U#8-24V BATTERY CHARGERS (SGTG)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
100 | Project-U#8-24V BATTERY CHARGERS (BOP)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
101 | Project-U#8-BATTERIS FOR (SGTG)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
102 | Project-U#8-BATTERIS FOR (BOP)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
103 | Project-U#8-DCDB(SGTG)-10563 | N.A. | - | 0 | 5.7183e-05 | 0 | 5.7183e-05 | 0 | 0 |  |  | 0 | 5.7183e-05
104 | Project-U#8-DCDB(BOP)-10563 | N.A. | - | 0 | 5.7183e-05 | 0 | 5.7183e-05 | 0 | 0 |  |  | 0 | 5.7183e-05
105 | Project-U#8-Controls & Instru. for Main Plant(BTG) | N.A. | - | 0 | 0.044292 | 0 | 0.044292 | 0 | 0 |  |  | 0 | 0.044292
106 | Project-U#8-CW Chlorination system-10509 | N.A. | - | 0 | 0.0011974 | 0 | 0.0011974 | 0 | 0 |  |  | 0 | 0.0011974
107 | Project-U#8-D.G.SET-10509 | N.A. | - | 0 | 3.7894e-05 | 0 | 3.7894e-05 | 0 | 0 |  |  | 0 | 3.7894e-05
108 | Project-U#8-D.M.Water System-10509 | N.A. | - | 0 | 0.005785 | 0 | 0.005785 | 0 | 0 |  |  | 0 | 0.005785
109 | Project-U#8-DG set- Manadatory Spares-10509 | N.A. | - | 0 | 0.00025004 | 0 | 0.00025004 | 0 | 0 |  |  | 0 | 0.00025004
110 | Project-U#8-DG Set Room cum Air Compressor House | N.A. | - | 0 | 0.0055794 | 0 | 0.0055794 | 0 | 0 |  |  | 0 | 0.0055794
111 | Project-U#8-Steel for TechnologicalStructure-10501 | N.A. | - | 0 | 0.14836 | 0 | 0.14836 | 0 | 0 |  |  | 0 | 0.14836
112 | Project-U#8-Electrical Package for BOP-10509 | N.A. | - | 0 | 0.0024904 | 0 | 0.0024904 | 0 | 0 |  |  | 0 | 0.0024904
113 | Project-U#8-Electrical CHARGES-10509 | N.A. | - | 0 | 4.1155e-05 | 0 | 4.1155e-05 | 0 | 0 |  |  | 0 | 4.1155e-05
114 | Project-U#8-Electrical Package for BOP-Mandatory | N.A. | - | 0 | 0.0002757 | 0 | 0.0002757 | 0 | 0 |  |  | 0 | 0.0002757
115 | Project-U#8-Fire Protection, Alarm & Detection | N.A. | - | 0 | 0.0071788 | 0 | 0.0071788 | 0 | 0 |  |  | 0 | 0.0071788
116 | Project-U#8-Fuel Oil Pump House-10516 | N.A. | - | 0 | 0.0040925 | 0 | 0.0040925 | 0 | 0 |  |  | 0 | 0.0040925
117 | Project-U#8-Generator Transformer-10541 | N.A. | - | 0 | 0.012655 | 0 | 0.012655 | 0 | 0 |  |  | 0 | 0.012655
118 | Project-U#8-Generator/Transformer protection | N.A. | - | 0 | 0.00024539 | 0 | 0.00024539 | 0 | 0 |  |  | 0 | 0.00024539
119 | Project-U#8-H.T.Switchgear for main plant-10561 | N.A. | - | 0 | 0.025188 | 0 | 0.025188 | 0 | 0 |  |  | 0 | 0.025188
120 | Project-U#8-Indoor & Outdoor plant lighting-10599 | N.A. | - | 0 | 0.0004077 | 0 | 0.0004077 | 0 | 0 |  |  | 0 | 0.0004077
121 | Project-U#8-L.P.Piping including valves-10509 | N.A. | - | 0 | 0.0038246 | 0 | 0.0038246 | 0 | 0 |  |  | 0 | 0.0038246
122 | Project-U#8-L.T. Electrical for main plant.-10561 | N.A. | - | 0 | 8.7067e-05 | 0 | 8.7067e-05 | 0 | 0 |  |  | 0 | 8.7067e-05
123 | Project-U#8-Laying&Termination of HT cables-10561 | N.A. | - | 0 | 0.0008231 | 0 | 0.0008231 | 0 | 0 |  |  | 0 | 0.0008231
124 | Project-U#8-MainBoiler Structure&foundations-10501 | N.A. | - | 0 | 0.09941 | 0 | 0.09941 | 0 | 0 |  |  | 0 | 0.09941
125 | Project-U#8-Mandatory Spares for Ash HandlingPlant | N.A. | - | 0 | 0.0015616 | 0 | 0.0015616 | 0 | 0 |  |  | 0 | 0.0015616
126 | Project-U#8-Mandatory spares for C&I of Main Plant | N.A. | - | 0 | 0.0050295 | 0 | 0.0050295 | 0 | 0 |  |  | 0 | 0.0050295
127 | Project-U#8-Mandatory Spares for Electrical MainPa | N.A. | - | 0 | 0.015601 | 0 | 0.015601 | 0 | 0 |  |  | 0 | 0.015601
128 | Project-U#8-Mandatory Spares For TG & Auxilliaries | N.A. | - | 0 | 0.0062588 | 0 | 0.0062588 | 0 | 0 |  |  | 0 | 0.0062588
129 | Project-U#8-Misc. Cranes & hoists-10553 | N.A. | - | 0 | 0.0023537 | 0 | 0.0023537 | 0 | 0 |  |  | 0 | 0.0023537
130 | Project-U#8-Miscellaneous Pumps -10599 | N.A. | - | 0 | 0.0015672 | 0 | 0.0015672 | 0 | 0 |  |  | 0 | 0.0015672
131 | Project-U#8-Passanger lift for TG Building-10599 | N.A. | - | 0 | 0.0016358 | 0 | 0.0016358 | 0 | 0 |  |  | 0 | 0.0016358
132 | Project-U#8-Passanger/Material Lift at boiler side | N.A. | - | 0 | 0.00084731 | 0 | 0.00084731 | 0 | 0 |  |  | 0 | 0.00084731
133 | Project-U#8-Chemical Laboratory -10509 | N.A. | - | 0 | 0.0011648 | 0 | 0.0011648 | 0 | 0 |  |  | 0 | 0.0011648
134 | Project-U#8-Sewage Treatment Plant-10509 | N.A. | - | 0 | 0.0019006 | 0 | 0.0019006 | 0 | 0 |  |  | 0 | 0.0019006
135 | Project-U#8-Station Transformer-10541 | N.A. | - | 0 | 0.026576 | 0 | 0.026576 | 0 | 0 |  |  | 0 | 0.026576
136 | Project-U#8-Steam Turbine set-10503 | N.A. | - | 0 | 0.13864 | 0 | 0.13864 | 0 | 0 |  |  | 0 | 0.13864
137 | Project-U#8-TG set and its auxilleries- Condensor | N.A. | - | 0 | 0.012703 | 0 | 0.012703 | 0 | 0 |  |  | 0 | 0.012703
138 | Project-U#8-TG set and its auxilleries -Generator | N.A. | - | 0 | 0.032545 | 0 | 0.032545 | 0 | 0 |  |  | 0 | 0.032545
139 | Project-U#8-TG set and its auxilleries-Condensor | N.A. | - | 0 | 0.029273 | 0 | 0.029273 | 0 | 0 |  |  | 0 | 0.029273
140 | Project-U#8-TG set & its auxilleries-Derator-10503 | N.A. | - | 0 | 0.002758 | 0 | 0.002758 | 0 | 0 |  |  | 0 | 0.002758
141 | Project-U#8-TG set and its auxilleries-DMMakeUpSys | N.A. | - | 0 | 0.0010491 | 0 | 0.0010491 | 0 | 0 |  |  | 0 | 0.0010491
142 | Project-U#8-TG set and its auxilleries-Gas System | N.A. | - | 0 | 0.0056178 | 0 | 0.0056178 | 0 | 0 |  |  | 0 | 0.0056178
143 | Project-U#8-TG set and its auxilleries-GoveringSys | N.A. | - | 0 | 4.9466e-05 | 0 | 4.9466e-05 | 0 | 0 |  |  | 0 | 4.9466e-05
144 | Project-U#8-TG set and its auxilleries-HP/LP By-pa | N.A. | - | 0 | 0.010752 | 0 | 0.010752 | 0 | 0 |  |  | 0 | 0.010752
145 | Project-U#8-TG set and its auxilleries-HP/LP Dozin | N.A. | - | 0 | 0.00039941 | 0 | 0.00039941 | 0 | 0 |  |  | 0 | 0.00039941
146 | Project-U#8-TG set and its auxilleries-SealOilPump | N.A. | - | 0 | 9.8566e-05 | 0 | 9.8566e-05 | 0 | 0 |  |  | 0 | 9.8566e-05
147 | Project-U#8-TG set and its auxilleries-Vaccum Syst | N.A. | - | 0 | 0.010304 | 0 | 0.010304 | 0 | 0 |  |  | 0 | 0.010304
148 | Project-U#8-Turbine Lub. Oil System With Purifier | N.A. | - | 0 | 0.0022364 | 0 | 0.0022364 | 0 | 0 |  |  | 0 | 0.0022364
149 | Project-U#8-Ventillation system-10599 | N.A. | - | 0 | 0.0014389 | 0 | 0.0014389 | 0 | 0 |  |  | 0 | 0.0014389
150 | Asset Recived From Project-U#8-M.SPARE_Ventillation system-10599 | N.A. | - | 0 | 8.5482e-05 | 0 | 8.5482e-05 | 0 | 0 |  |  | 0 | 8.5482e-05
151 | Asset Recived From Project-U#8-Water Treatment Plant-10509 | N.A. | - | 0 | 0.0042384 | 0 | 0.0042384 | 0 | 0 |  |  | 0 | 0.0042384
152 | Asset Recived From Project-U#8-WORK SHOP MAD_SPARE-10565 | N.A. | - | 0 | 0.00030445 | 0 | 0.00030445 | 0 | 0 |  |  | 0 | 0.00030445
153 | Asset Recived From Project-U#8-Workshop-10565 | N.A. | - | 0 | 0.0013286 | 0 | 0.0013286 | 0 | 0 |  |  | 0 | 0.0013286
154 | Asset Recived From Project-U#8-CMR SYSTEM-10501 | N.A. | - | 0 | 0.0020736 | 0 | 0.0020736 | 0 | 0 |  |  | 0 | 0.0020736
155 | Asset Recived From Project-U#8-MandatorySpares-WTP-10.509 | N.A. | - | 0 | 8.1517e-05 | 0 | 8.1517e-05 | 0 | 0 |  |  | 0 | 8.1517e-05
156 | Asset Recived From Project-U#8-E.1.07_MandSpar 4 C&I MS 4MeasuringIns E.1.07_M S for C&I_ MS For Measuring Ins | N.A. | - | 0 | 0.078697 | 0 | 0.078697 | 0 | 0 |  |  | 0 | 0.078697
157 | Asset Recived From Project-U#8-BOP_ELECTRICAL-10612 | N.A. | - | 0 | 0.01637 | 0 | 0.01637 | 0 | 0 |  |  | 0 | 0.01637
158 | Asset Recived From Project-U#8-Bus Ducts-10612 | N.A. | - | 0 | 0.012548 | 0 | 0.012548 | 0 | 0 |  |  | 0 | 0.012548
159 | Asset Recived From Project-U#8-Cable trays & supports-10612 | N.A. | - | 0 | 0.00036009 | 0 | 0.00036009 | 0 | 0 |  |  | 0 | 0.00036009
160 | Project-U#8-PCR FURNITURE-10810 | N.A. | - | 0 | 0.00030684 | 0 | 0.00030684 | 0 | 0 |  |  | 0 | 0.00030684
161 | Project-U#8 Server Intel QUAD CORE 02No. HP Office Server | N.A. | - | 0 | 0 | 0 | 0 | 0.11918 | 0.11918 |  |  | 0.11918 | 0
162 | Supply Erection testing and commissining of 1000 m3 ETP Civil works | N.A. | - | 0 | 0 | 0 | 0 | 0.68324 | 0.68324 |  |  | 0.68324 | 0
| Total | 0 |  |  | 98.2901 | 43.704 | 54.5861 | 20.1701 | 12.8049 |  |  | 12.8049 | 61.9512
FY 2023-24
0 | Add Cap (As per 296 of 2019) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
A | Initial spares | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Boiler and Auxiliaries | Add Cap (As per 296 of 2019) | - | 7.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of Coal Mill XRP-903 Gear Box Type KMP-280 Spares of Unit # 8 at BM-NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 0 | 1.35 | 1.35 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply of Labyrinth Seal Rings with replaceable Inner liners for Coal Mill XRP-903 required for BM Unit-8, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.33134 | 0.33134 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply and Installation of coal mill liners(weld overlay) of XRP-903 Coal Mill in BM U-8, NPTPS,Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.33134 | 0.33134 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of Coal Mill XRP-903 Bowl & Bowl Hub of Unit # 8 at BM-NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 0 | 0.73326 | 0.73326 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply of impeller assembly for ID fan | Add Cap (As per 296 of 2019) | - | 0 | 0.5233 | 0.5233 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of Primary Air Fan & Forced Draught Fan Drive Coupling on OEM basis required at BM U-8, NPTPS, Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.1941 | 0.1941 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of Primary Air Fan PAF 17/11.8-2 Hydraulic Adjustment Device on OEM basis required at BM U-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.53521 | 0.53521 | 0 | 0 | 0 |  |  | 0 | 0
8 | Proc of spares for fabric expansion joints required at BM U-8, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.56972 | 0.56972 | 0 | 0 | 0 |  |  | 0 | 0
9 | Proc of separator body and seperator top spares for coal mill XRP-903 at BM U-8, NPTPS Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.42569 | 0.42569 | 0 | 0 | 0 |  |  | 0 | 0
10 | Proc of scrapper area & reject system spares for coal mill XRP-903 at BM U-8, NPTPS Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.27833 | 0.27833 | 0 | 0 | 0 |  |  | 0 | 0
11 | Proc of seal air fan spares at BM-8 NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.26432 | 0.26432 | 0 | 0 | 0 |  |  | 0 | 0
12 | Procurement of FD Fan Type FAF 17/9.5-1 Drive Coupling required at BM U-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | Procurement of complete planatary gear box-KMP -280/300 for coal mill XRP-903 at BM U-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Turbine and Auxiliaries | Add Cap (As per 296 of 2019) | - | 4.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of spares for Equipment Cooling Water Pumps (Make-FLOWMORE) of model FIG-5824 (SG Side) and FIG-5822 (TG side) at Unit-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.51812 | 0.51812 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply of spars for recovery & FF Pumps along with work at U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0.37713 | 0.37713 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of seal oil vacuum pump in unit 08 | Add Cap (As per 296 of 2019) | - | 0 | 0.27502 | 0.27502 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of AC pressure pipes (235MM OD, 200MM ID, 4.5M Length) for NDCT hot spray water distribution system in Unit-8 NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 0 | 0.42522 | 0.42522 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply of M/s Summits make Instrument Air Dryer & spares at U # 8 TM, Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.54787 | 0.54787 | 0 | 0 | 0 |  |  | 0 | 0
6 | Supply of PVC fills for NDCTs at U # 8 TM, Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.58245 | 0.58245 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of NB 600MM Gate valves for ACW self cleaning strainers in U#8 TM NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.42338 | 0.42338 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of Mechanical seals ( Make Leak-Proof) for various pumps in TM Unit-8 NPTPS Parli. | Add Cap (As per 296 of 2019) | - | 0 | 0.49233 | 0.49233 | 0 | 0 | 0 |  |  | 0 | 0
9 | Supply of SS 304 pipes & others at U # 8 TM, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.52905 | 0.52905 | 0 | 0 | 0 |  |  | 0 | 0
3 | Electrical and Instrumentation | Add Cap (As per 296 of 2019) | - | 6.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of Instrumentation Spares of LP Bypass System at Unit-8. | Add Cap (As per 296 of 2019) | - | 0 | 1.9615 | 1.9615 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of Schneider MICOM Numerical Relays for GRP and STPR swithcgear at NPTPS Unit-8 Testing | Add Cap (As per 296 of 2019) | - | 0 | 0.47613 | 0.47613 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of 220V DC Chloride make (formally caldyne) make battery chargers Spre of Unit 8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.23365 | 0.23365 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of 24V DC Chhabi make make battery chargers Spare of Unit 8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.22465 | 0.22465 | 0 | 0 | 0 |  |  | 0 | 0
5 | Procurement of Spare for Hitachi Hi-Rel make UPS systems installed at Unit-8 NPTPS Parli Vaijnath. | Add Cap (As per 296 of 2019) | - | 0 | 0.19186 | 0.19186 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of various test kit for testing U#8 such as energy meter calibration kit, DC earth faulth locator kit, promary current injection kit, breaker time measurement kit, numeric relay test kit and other testing instruments. | Add Cap (As per 296 of 2019) | - | 0 | 0.67345 | 0.67345 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of Energymeter Caliberation Software Module and hardware for upgrading Numeric Relay Test kit at Unit -8 Testing. | Add Cap (As per 296 of 2019) | - | 0 | 0.11863 | 0.11863 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of H T Motors. | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of critical L T Motors | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of ESP Hopper heaters (As a initial spares) Installed at EM U-8, NPTPS, Parli-Vaijnath under add cap scheme. | Add Cap (As per 296 of 2019) | - | 0 | 0.38586 | 0.38586 | 0 | 0 | 0 |  |  | 0 | 0
4 | Outdoor Plant(CHP/AHP/WTP) | Add Cap (As per 296 of 2019) | - | 6.64 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of Apron Feeder spares installed at CHP NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 1.6233 | 1.6233 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply of various drive and non drive pulleys for CHP U-8. | Add Cap (As per 296 of 2019) | - | 0 | 0.54529 | 0.54529 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply and installation of clamp pads & resting pads for Side Beam of Wagon Tippler for CHP U-8 | Add Cap (As per 296 of 2019) | - | 0 | 0.54802 | 0.54802 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply of unbalance motorozied vibrating feeder for S/R of U-7/8 CHP NPTPS Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.3958 | 0.3958 | 0 | 0 | 0 |  |  | 0 | 0
5 | Procurement of conveying and Instrument air compressor spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 1.77 | 1.77 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of vacuum pump spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0.2291 | 0.2291 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of fluidizing blower spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0.11796 | 0.11796 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of slurry pump spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of Clinker grinder spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0.12334 | 0.12334 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B | Reassessment of remaining BOP work after insolvency of M/s Sunil Hi-Tech | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Project balance E&M and procurement of mandetory spares | MERC CAPEX Approval in MTR Order 296 of 2019 | Order 296 of 2019 | 41.4534 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work order for Contract of Supply and application of Fire Stop Mortar Seal and Fire Retardant Cable Coating Compound at NPTP U-8 Parli Project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 3.4589 | 3.4589 | 0 | 0 | 0 |  |  | 0 | 0
2 | Work order for contract for Supply Installaion Testing & Commissioning Smoke Detection & alaram system | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 2.5606 | 2.5606 | 0 | 0 | 0 |  |  | 0 | 0
3 | Work order for contract for Supply Installaion Testing & Commissioning of Balance Fire Fighting System at NPTP U-8 Parli Project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.0502 | 1.0502 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, Errection, testing & commissioning works of RWP, PT potable chlorination system, ETP system control panel, automation of LDO, HFO tank foam system Hose boxes with RRL hoses and branch pipe and allied system at NPTP | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.8496 | 0.8496 | 0 | 0 | 0 |  |  | 0 | 0
5 | Work Order contract for supply, installation Testing & Commissioning of telephone exchange (EPBAX) & Telephone System at NPTP U-8 Parli project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.91256 | 0.91256 | 0 | 0 | 0 |  |  | 0 | 0
6 | Balance Supply of Electrical Lab Equipment at NPTP parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.60826 | 0.60826 | 0 | 0 | 0 |  |  | 0 | 0
7 | Work order for contract for Supply Installaion Testing & Commissioning with required material to complete Balance CHP work at NPTP U-8 Parli Project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.41 | 0.41 | 0 | 0 | 0 |  |  | 0 | 0
8 | Supply, Errection, testing & commissioning of Interconnecting Conveyor no.9 & 10 from U-8 to U-6&7 of CHP at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 3.5819 | 3.5814 | 0.0005 | 1.75 | 1.7448 |  |  | 1.7448 | 0.0056593
9 | SUPPLY ,INSTA,TEST ,COMM ELECTRICAL SYS | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | SUPPLY,INSTAL,TEST,COMM OF CRANS&HOIST | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.3805 | 1.3805 | 0 | 0.43 | 2.2418 |  |  | 2.2418 | -1.8118
11 | Supply, Errection, testing & commissioning of Dust Extraction system at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.8061 | 0 | 1.8061 | 0 | 0 |  |  | 0 | 1.8061
12 | Supply, Errection, testing & commissioning of DSS & DFDS at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 2.8091 | 0 | 2.8091 | 0 | 0 |  |  | 0 | 2.8091
13 | Supply, Errection, testing & commissioning of Monorail at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.1892 | 1.1891 | 7.77e-05 | 0 | 0 |  |  | 0 | 7.77e-05
14 | Supply, Errection, testing & commissioning of various Control & Instrumentation equipments at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.72225 | 0.72225 | 0 | 0 | 0 |  |  | 0 | 0
15 | Supply, Errection, testing & commissioning of Air Conditioning System at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.15304 | 0.44729 | -0.29425 | 0 | 0 |  |  | 0 | -0.29425
16 | Supply, Errection, testing & commissioning of Ventilation System at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.2036 | 1.2036 | 0 | 0.91 | 0 |  |  | 0 | 0.91
17 | Supply, Errection, testing & commissioning of Elevator works. | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0 | 0 | 0 | 3.5173 | 3.5173 |  |  | 3.5173 | 0
18 | Work contract for dismentaling, supply, erection & commissioning of MRHS | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0 | 0 | 0 | 2.2335 | 2.2335 |  |  | 2.2335 | 0
19 | Supply, Errection, testing & commissioning of FF System, Smoke detection & Fire stop mortar & Fire retradant cable coating for conveyor 09 & 10 | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0 | 0 | 0 | 0.22171 | 0.51866 |  |  | 0.51866 | -0.29696
20 | Supply, Errection, testing & commissioning of Chimney Elevator | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0 | 0 | 0 | 1.0608 | 0 |  |  | 0 | 1.0608
21 | Supply, Errection, testing & commissioning work of GEHO Pumps. | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | Procurement of various Mandetory spares of BOP packages | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Balance civil work of BOP scope at 250 MW Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 45.3238 | 0 | 0 | 0 | 0.55712 | 16.72 |  |  | 16.72 | -16.1629
1 | Area grading | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 6.6029 | 0 | 6.6029 | 0.38376 | 0.89 |  |  | 0.89 | 6.0966
2 | CMD | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.76624 | 0 | 0.76624 | 0.47483 | 1.3549 |  |  | 1.3549 | -0.11383
3 | Conveyor 09, 10 & TP 06 | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 10.6052 | 0 | 10.6052 | 3.9554 | 10.1 |  |  | 10.1 | 4.4605
4 | Finishing item | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 6.1446 | 0 | 6.1446 | 1.9403 | 4.6506 |  |  | 4.6506 | 3.4344
5 | Drain & nala | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 2.7097 | 0 | 2.7097 | 2.3752 | 11.79 |  |  | 11.79 | -6.7052
6 | Internal roads | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 9.4148 | 0 | 9.4148 | 0.33732 | 1.5 |  |  | 1.5 | 8.2521
7 | Stacker & reclaimer | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.1627 | 0 | 1.1627 | 0 | 0 |  |  | 0 | 1.1627
0 | Other Add Cap | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Laboratory set up | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of Analytical Instruments for condition monitoring Laboratory for 1X250 MW of NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.5 | 0.49655 | 0.49655 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply of Analytical Instruments for Water Analysis Laboratory for 1X250 MW of NPTPS, Parli-V | Add Cap (As per 296 of 2019) | - | 1.23 | 0.29847 | 0.29847 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of Analytical Instruments for Environment Laboratory for 1 x 250 MW, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.39 | 0.3658 | 0.3658 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply of Analytical Instruments for Precision Laboratory for 1 x 250 MW, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply of Analytical Instruments for General Laboratory of Water Treatment Plant of 1 x 250 MW, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Supply of Corrosion Monitor/Meter, Corrosion Coupon & Coupon Rack for 1X250 MW of NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.34 | 0.34736 | 0.34736 | 0 | 0 | 0 |  |  | 0 | 0
7 | Supply of Analytical Instruments for Coal Analysis Laboratory for 1X250 MW of NPTPS, Parli-V | Add Cap (As per 296 of 2019) | - | 1.65 | 0.39444 | 0.39444 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Grade slab (WTP Area) | Add Cap (As per 296 of 2019) | - | 1 | 0.99752 | 0.99752 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Grade slab (Near AHP Building) | Add Cap (As per 296 of 2019) | - | 0.75 | 0.74556 | 0.74556 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Temporary shed for empty barrles & filled barrles | Add Cap (As per 296 of 2019) | - | 0.5 | 0.45635 | 0.45635 | 0 | 0 | 0 |  |  | 0 | 0
12 | Cabins for operators at TP. | Add Cap (As per 296 of 2019) | - | 0.2 | 0.18583 | 0.18583 | 0 | 0 | 0 |  |  | 0 | 0
13 | Compound wall for isolation of administrative building. | Add Cap (As per 296 of 2019) | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Work of providing/ fixing of internal partitions of aluminium/Nova palm/glass/wooden for Unit 8 service building & other allied builings in the premises. | Add Cap (As per 296 of 2019) | - | 0.7 | 0.67356 | 0.67356 | 0 | 0 | 0 |  |  | 0 | 0
15 | Provision of DM and softening water line interconnection from u-6,7 to u-8 & Provision of recovery of waste water from sandava pump house,NDCT. | Add Cap (As per 296 of 2019) | - | 3 | 1.0266 | 1.0266 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | Add Cap (As per 296 of 2019) | - | 0 | 1.8371 | 1.8371 | 0 | 0 | 0 |  |  | 0 | 0
16 | Hydraulic drive system modification. | Add Cap (As per 296 of 2019) | - | 2.5 | 2.4384 | 2.4384 | 0 | 0 | 0 |  |  | 0 | 0
17 | Link conveyor from Con-2 of U-6/7 to Con.-2AB of U-8. | Add Cap (As per 296 of 2019) | - | 3.7 | 3.8434 | 3.8434 | 0 | 0.8 | 18.8129 |  |  | 18.8129 | -18.0129
18 | Ozone plant for Unit -8 | Add Cap (As per 296 of 2019) | - | 20 | 17.9047 | 0 | 17.9047 | 2.19 | 2.1929 |  |  | 2.1929 | 17.9018
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | Water management system | Add Cap (As per 296 of 2019) | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8, 20 | Procurement & Installation of EMS system at Unit-8 NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 1 | 0.14417 | 0.14417 | 0 | 0 | 0 |  |  | 0 | 0
21 | Conveyor-5 of stacking/reclaiming belt double drive arrangement. | Add Cap (As per 296 of 2019) | - | 2 | 2.0432 | 2.0432 | 0 | 0 | 0 |  |  | 0 | 0
22 | Chemical lab building | Add Cap (As per 296 of 2019) | - | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Chemical store | Add Cap (As per 296 of 2019) | - | 2.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Lawn development around NDCT. | Add Cap (As per 296 of 2019) | - | 0.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | Tree plantation & greenery along road side. | Add Cap (As per 296 of 2019) | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | Greenery development in area between WTP & main plant. | Add Cap (As per 296 of 2019) | - | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | Construction of staff rooms & store for CHP maint.. | Add Cap (As per 296 of 2019) | - | 1 | 0.90703 | 0.90703 | 0 | 0 | 0 |  |  | 0 | 0
28 | Dsludg filteration for raw water | Add Cap (As per 296 of 2019) | - | 17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29 | PLC/UPS system upgradation | Add Cap (As per 296 of 2019) | - | 0.5 | 0.40149 | 0.40149 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | FGD at Parli Unit # 8 | MERC/CAPEX/2021-2022/0284 | 2022-06-27 | 89.24 | 0 | 0 | 0 | 4.1 | 0 |  |  | 0 | 4.1
22.1 | FGD at Parli Unit # 8 | MERC/CAPEX/2021-2022/0284 | 2022-06-27 | 85.2 | 0 | 0 | 0 | 0.49 | 0 |  |  | 0 | 0.49
0 | IDC | MERC/CAPEX/2021-2022/0284 | 2022-06-27 | 4.04 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Detailed Project Report on Boiler plant performance improvement and availability improvement schemes at Boiler Maintenance 1x250MW Unit-8 TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Procurement & Replacement of Complete Economizer Upper & Lower Bank Coil Assemblies at Unit-8, NPTPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.3 | Procurement & replacement of PA Fan PAF 17/11.8-2 and FD Fan FAF 17/9.5-1 Complete Blade set required at BM U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.4 | Procurement & Replacement of Coal Mill Gear Box Type KMP 280 at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.5 | Procurement & replacement of Bowl & Bowl Hub Assembly of Coal Mill XRP-903 required at BM U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.6 | Procurement of Complete Journal Assembly without Grinding roll for Coal Mill XRP-903 required at BM U-8 NPTPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.7 | Procurement of Hydraulic Adjustment Device for FD Fan FAF 17/9.5-1 at BM U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.8 | SWAS upgradation at U#8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement & Replacement of Complete Platen super heater coils Coil Assemblies at Unit-8, TPS Parli-V, Procurement & Replacement of Complete LTSH upper & lower bank Coil Assemblies at Unit-8, TPS Parli-V & Procurement & Replacement of Coal Mill Gear Box Type KMP 280 at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Procurement & Replacement of Complete Platen super heater coils Coil Assemblies at Unit-8, TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Procurement & Replacement of Complete LTSH upper & lower bank Coil Assemblies at Unit-8, TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Procurement & Replacement of Coal Mill Gear Box Type KMP 280 at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-8, Parli TPS Procurement & replacement of PA & FD fan rotar hub assembly at Unit-8 TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Procurement & replacement of PA & FD fan rotar hub assembly at Unit-8 TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | DPR on Refurbishment of TG Governing system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Refurbishment of TG Governing system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | DPR on Performance improvement of Natural Draft Cooling Tower (NDCT) at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Performance improvement of Natural Draft Cooling Tower (NDCT) by replacement of PVC fills, AC cement pipes, strengthening of Hot water distribution system, replacement of beams, columns, support structures, etc. at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | DPR on Procurement of ACW & CW pump along with mandatory spares at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | DPR on Procurement of ACW & CW pump along with mandatory spares at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | DPR on Procurement of CEP pump and BFP Booster pump along with mandatory spares at Unit-8, PTPS, Parli V and Procurement of Energy Efficient Cartridges of Boiler Feed Pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Procurement of CEP pump and BFP Booster pump along with mandatory spares at Unit-8, PTPS, Parli | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.2 | Procurement of Energy Efficient Cartridges of Boiler Feed Pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | DPR on Procurement of turbine blades of HP, IP & LP rotor in Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.1 | DPR on Procurement of turbine blades of HP, IP & LP rotor in Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | DPR on Repair & Reconditioning of Water treatment plant at Unit-8, PTPS, Parli V and Performance improvement of centralised AC plant at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.1 | Reconditioning of Acid and Alkali Unloading and storage system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.2 | Reconditioning & repairing of WTP DM Plant regeneration system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.3 | Performance improvement of centralised AC plant by reconditioning of cooling tower, various pumps, heat exchangers, etc. at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | DPR on Procurement of Control Fluid (HPCF) pump, Lube Oil pump, Emergency Oil pump, Jacking Oil pump, Seal oil pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.1 | DPR on Procurement of Control Fluid (HPCF) pump, Lube Oil pump, Emergency Oil pump, Jacking Oil pump, Seal oil pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | DPR on Procurement of H2 cooler, BFP coolers, generator exciter cooler, Seal and Lube oil coolers at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.1 | DPR on Procurement of H2 cooler, BFP coolers, generator exciter cooler, Seal and Lube oil coolers at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Supply, installation & commissioning of 220V 2140AH,24V 830AH & 710AH, 360V 570AH Mains UPS,110V 110AH AHP PLC , 110V , 103 AH DM plant battery set for unit 8 , NPTPS Parli-V & Procurement of HT motors at U#8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.1 | Supply, installation & commissioning of 220V 2140AH,24V 830AH & 710AH, 360V 570AH Mains UPS,110V 110AH AHP PLC , 110V , 103 AH DM plant battery set for unit 8 , NPTPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.2 | Procurement of HT motors at U#8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | DPR on various instrumentation & control schemes at U#8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | Upgradation of MAX-DNA DCS system at U#8 (HMI upgradation) | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.2 | Upgradation of existing Pcal system with plant performance analysis diagnostic and optimization system (PADO) at Unit 8 New Parli TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.3 | Upgradation of coal feeder for I&C Unit8 PTPS Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.4 | Procurement of smart control positioner at I&C Unit8 PTPS Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.5 | Upgradation Electronic control drive for I&C Unit8 PTPS Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.6 | Upgradation of turbovisory & vibration monitoring system control panel. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Performance improvement by system up gradation at CHP & DPR for normalization and stabilization of coal handling plant performance at Parli TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.1 | Supply and Commissioning of Energy Efficient Evaporative Cooling System for Control Panel & Breaker room of CHP Unit-8 For PARLI TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.2 | Supply and commissioning of Suspended Magnets for U-8 CHP NPTPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.3 | Stacker-reclaimer Bucket wheel drive modification work of U- 8 CHP | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.4 | Apron feeder drive modification from Hydraulic to Electro-Mechanical at CHP U-8 NPTPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.5 | Procurement of U-8 W/T Major spares | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.6 | Provision of Soft starter / VFD for Various conveyor | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.7 | TP-3 chute modification at U-8 CHP. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.8 | Design, supply and commissioning of solar operated lighting system in CHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.9 | Installation of CCTV survillance system alongwith all conveyors. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | DPR for maximiation of Coal Handling Plant efficiency & DPR on life enhancement of Coal Handling Plant | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | W/T control room & bunker house battery & UPS upgradation | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Refurbishment of conveyor no. 2 A/B & 6 A/B drive system of CHP U-8 TPS Parli. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Provision of Soft starter / VFD for Various conveyor | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Procurement & installation of Belt tear detection system | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.5 | Conveyor gravity takeup infrastructure strengthening work | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.6 | U-8 CHP apron feeder-I to Conveyor 1 A/B chute modification work . | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | DPR for stabiliazation of Coal Handling Performance. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.1 | Drive modification of Stacker Reclaimer slewing system. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.2 | Retrofitting of Side Arm Charger-I & II at CHP U-8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.3 | Upgradation of GE/Schineder make PLC system atU-8 CHP. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.4 | Refurbishment of Apron Feeder at CHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.5 | Provision of moveable stacker and crusher in CHP coal stack yard at CHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.6 | Procurement of Loco & Bulldozer at CHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | DPR on dry fly ash utilisation improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.1 | Design, supply, erection, installation & comissioning of intermediate silo with sub system at AHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | DPR on ash handling plant improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | Design, supply, erection & comissioning of weigh bridge for silo at AHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.2 | Supply, installation & comissioning of energy efficient air compressor at AHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.3 | PROCUREMENT OF COMPLETE ASSEMBLY OF SAM MAKE AR-150/510 PUMPS (2 NOS) FOR REPLACEMENT OF ASH SLURRY PUMPS OF BOTTOM ASH SLURRY DISPOSAL FROM SLURRY TANK TO ASH BUND IN SLURRY PUMP HOUSE. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | PROCUREMENT OF COMPLETE ASSEMBLY OF SAM MAKE ZM-II 530/02 (2 NOS) FOR REPLACEMENT OF HP PUMPS OF BOTTOM ASH & COARSE ASH EVACUATION FROM BA/CA HOPPERS TO SLURRY TANK IN ASH WATER PUMP HOUSE. 0.75 0.89 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.5 | Procurement of vacuum pumps complete assembly for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.6 | Procurement of vacuum pumps complete assembly for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.7 | Procurement of Feed Gate Complete Assembly along with modified metallurgy to enhance the life of Clinker Grinder. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.8 | Procurement of Double Roll Clinker Grinder Complete Assembly with Drive Unit installed at AHP | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.9 | Procurement of Instrument Air Dryers assembly for performance improvement | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | Procurement of various types of Isolation Valves assembly, Dome Valves assembly, Root Valve Assembly & Expansion Bellows Assembly for Dry Ash Conveing performance improvement | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | DPR on ash handling plant improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | Design, supply, erection, installation & comissioning of DM water close loop cooling system for air compressors at AHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.2 | Up-gradation of Existing Schneider make PLC (HMI + PLC hardware) installed at AHP Unit -8 at Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.3 | Procurement of HT motors for AHP U-8 Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.4 | PROCUREMENT OF CRITICAL GEARBOXES AND FLUID COUPLINGS INTERNAL ASSEMBLIES FOR SLURRY PUMPS AND SILO HCSD SYSTEM INSTALLED AT AHP, PARLI TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.5 | Procurement of Atlas Copco Make Instrument Air Compressors Critical/Non-Critical Spares sub-assembly for performance improvement | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.6 | Upgradation and improvement in Hopper Temperature monitoring system by providing Rf Type Hopper Level Sensors for performance improvement of conveying of Dry ash evacuation system. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20 | DPR on ash handling plant improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.1 | Design, supply, erection, installation & comissioning ESP 1st & 2nd field dry fly ash evacuation & conveying system at AHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.2 | Design, supply, erection, installation & comissioning of dry ash evacuation & conveying system for APH & Economiser ash hoppers at AHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Verious Civil schemes in Unit 8 NPTPS Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Construction of chemical laboratory building at Unit 8, NPTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.2 | Construction of Alum/salt storage area at Unit No.8 (1X250MW) NPTPS Parli Vaijnath. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.3 | Construction of Fire Fighting station at Unit-8, NPTPS Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.4 | Construction of workshop building at Unit-8, NPTPS Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | CHP improvement scheme at 250 MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.1 | CHP improvement scheme at 250 MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0.56615 | 0.56615 |  |  | 0.56615 | 0
0 | B) GA | 0 | - | 0 | 0.34312 | 0.40371 | -0.060588 | 0 | 0 |  |  | 0 | -0.060588
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | C) Asset received from Project U#8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Asset Recived From Civil-U#8-Land-10101 | N.A. | - | 0 | 0.0031293 | 0 | 0.0031293 | 0 | 0 |  |  | 0 | 0.0031293
2 | Asset Recived From Civil-U#8-T.G. Building-10201 | N.A. | - | 0 | 0.010038 | 0 | 0.010038 | 0 | 0 |  |  | 0 | 0.010038
3 | Asset Recived From Civil-U#8-T.G. Building(BC)bay&control room-10201 | N.A. | - | 0 | 0.0045784 | 0 | 0.0045784 | 0 | 0 |  |  | 0 | 0.0045784
4 | Asset Recived From Civil-U#8-StructuralSteelWorks4TGBldgA2EBays-10201 | N.A. | - | 0 | 0.0013976 | 0 | 0.0013976 | 0 | 0 |  |  | 0 | 0.0013976
5 | Asset Recived From Civil-U#8-WTP Building-10201 | N.A. | - | 0 | 0.00011482 | 0 | 0.00011482 | 0 | 0 |  |  | 0 | 0.00011482
6 | Asset Recived From Civil-U#8-DG SET ROOM CUM AIR COMP. HOUSE-10201 | N.A. | - | 0 | 0.00010598 | 0 | 0.00010598 | 0 | 0 |  |  | 0 | 0.00010598
7 | Asset Recived From Civil-U#8-WTP-Raw/Fire water pump House-10233 | N.A. | - | 0 | 0.00069019 | 0 | 0.00069019 | 0 | 0 |  |  | 0 | 0.00069019
8 | Asset Recived From Civil-U#8-SERVICE BUILDING -10211 | N.A. | - | 0 | 0.00055144 | 0 | 0.00055144 | 0 | 0 |  |  | 0 | 0.00055144
9 | Asset Recived From Civil-U#8-Canteen -10233 | N.A. | - | 0 | 0.00072491 | 0 | 0.00072491 | 0 | 0 |  |  | 0 | 0.00072491
10 | Asset Recived From Civil-U#8-PARKING SHED -10233 | N.A. | - | 0 | 6.111e-06 | 0 | 6.111e-06 | 0 | 0 |  |  | 0 | 6.111e-06
11 | Asset Recived From Civil-U#8-Time Security Building -10233 | N.A. | - | 0 | 3.595e-05 | 0 | 3.595e-05 | 0 | 0 |  |  | 0 | 3.595e-05
12 | Asset Recived From Civil-U#8-Misc.Building/structure/Watchtower-10233 | N.A. | - | 0 | 0.00017243 | 0 | 0.00017243 | 0 | 0 |  |  | 0 | 0.00017243
13 | Asset Recived From Civil-U#8-Boundry compound wall Mall-10233 | N.A. | - | 0 | 0.15766 | 0 | 0.15766 | 0 | 0 |  |  | 0 | 0.15766
14 | Asset Recived From Civil-U#8-Workshop civil work-10233 | N.A. | - | 0 | 4.188e-05 | 0 | 4.188e-05 | 0 | 0 |  |  | 0 | 4.188e-05
15 | Asset Recived From Civil-U#8-Interior Work for CEC-I Office-10233 | N.A. | - | 0 | 5.6438e-05 | 0 | 5.6438e-05 | 0 | 0 |  |  | 0 | 5.6438e-05
16 | Asset Recived From Civil-U#8-WTP-Raw water reservoir -10305 | N.A. | - | 0 | 0.0012248 | 0 | 0.0012248 | 0 | 0 |  |  | 0 | 0.0012248
17 | Asset Recived From Civil-U#8-WTP-Clarifier -10305 | N.A. | - | 0 | 0.0011652 | 0 | 0.0011652 | 0 | 0 |  |  | 0 | 0.0011652
18 | Asset Recived From Civil-U#8-WTP-Clarifier Water Storage Tank-10305 | N.A. | - | 0 | 0.00019514 | 0 | 0.00019514 | 0 | 0 |  |  | 0 | 0.00019514
19 | Asset Recived From Civil-U#8-C.W. pump house & forebay-10310 | N.A. | - | 0 | 0.00052946 | 0 | 0.00052946 | 0 | 0 |  |  | 0 | 0.00052946
20 | Asset Recived From Civil-U#8-Construction of STP for Colony-10322 | N.A. | - | 0 | 0.00017966 | 0 | 0.00017966 | 0 | 0 |  |  | 0 | 0.00017966
21 | Asset Recived From Civil-U#8-Cooling Towers-10311 | N.A. | - | 0 | 0.37628 | 0 | 0.37628 | 0 | 0 |  |  | 0 | 0.37628
22 | Asset Recived From Civil-U#8-Railway sidings-10412 | N.A. | - | 0 | 0.13615 | 0 | 0.13615 | 0 | 0 |  |  | 0 | 0.13615
23 | Asset Recived From Civil-U#8-In plant Roads -10401 | N.A. | - | 0 | 0.0009103 | 0 | 0.0009103 | 0 | 0 |  |  | 0 | 0.0009103
24 | Asset Recived From Civil-U#8-Pipe Rack -10419 | N.A. | - | 0 | 0.00041823 | 0 | 0.00041823 | 0 | 0 |  |  | 0 | 0.00041823
25 | Asset Recived From Civil-U#8-Transformar yard area -10541 | N.A. | - | 0 | 0.00053169 | 0 | 0.00053169 | 0 | 0 |  |  | 0 | 0.00053169
26 | Asset Recived From Civil-U#8-BA-Boiler and Auxilary foundation-10501 | N.A. | - | 0 | 0.0061116 | 0 | 0.0061116 | 0 | 0 |  |  | 0 | 0.0061116
27 | Asset Recived From Civil-U#8-BA-FD FAN FOUNDATIONS -10501 | N.A. | - | 0 | 0.00011166 | 0 | 0.00011166 | 0 | 0 |  |  | 0 | 0.00011166
28 | Asset Recived From Civil-U#8-BA-PA FAN FOUNDATION -10501 | N.A. | - | 0 | 0.00011166 | 0 | 0.00011166 | 0 | 0 |  |  | 0 | 0.00011166
29 | Asset Recived From Civil-U#8-BA-I.D. Fan foundation -10501 | N.A. | - | 0 | 0.00022332 | 0 | 0.00022332 | 0 | 0 |  |  | 0 | 0.00022332
30 | Asset Recived From Civil-U#8-BA-MILL FOUNDATION-10501 | N.A. | - | 0 | 0.00019826 | 0 | 0.00019826 | 0 | 0 |  |  | 0 | 0.00019826
31 | Asset Recived From Civil-U#8-BA-BUNKER FOUNDATION & STRUCTURE-10515 | N.A. | - | 0 | 0.0013925 | 0 | 0.0013925 | 0 | 0 |  |  | 0 | 0.0013925
32 | Asset Recived From Civil-U#8-ESP-10501 | N.A. | - | 0 | 0.00070722 | 0 | 0.00070722 | 0 | 0 |  |  | 0 | 0.00070722
33 | Asset Recived From Civil-U#8-ESP Control Room-10501 | N.A. | - | 0 | 0.00042763 | 0 | 0.00042763 | 0 | 0 |  |  | 0 | 0.00042763
34 | Asset Recived From Civil-U#8-RCC Chimney -10501 | N.A. | - | 0 | 0.0046127 | 0 | 0.0046127 | 0 | 0 |  |  | 0 | 0.0046127
35 | Asset Recived From Civil-U#8-WTP-D.M.Plant equipment fdn. etc.-10509 | N.A. | - | 0 | 6.3898e-05 | 0 | 6.3898e-05 | 0 | 0 |  |  | 0 | 6.3898e-05
36 | Asset Recived From Civil-U#8-CHP-Wagon Tippler-10515 | N.A. | - | 0 | 0.00094041 | 0 | 0.00094041 | 0 | 0 |  |  | 0 | 0.00094041
37 | Asset Recived From Civil-U#8-CHP-Crusher House -10515 | N.A. | - | 0 | 0.00074704 | 0 | 0.00074704 | 0 | 0 |  |  | 0 | 0.00074704
38 | Asset Recived From Civil-U#8-CHP-Stacker Reclaimer -10515 | N.A. | - | 0 | 0.00028485 | 0 | 0.00028485 | 0 | 0 |  |  | 0 | 0.00028485
39 | Asset Recived From Civil-U#8-CHP-Stock Yard-10515 | N.A. | - | 0 | 0.00015851 | 0 | 0.00015851 | 0 | 0 |  |  | 0 | 0.00015851
40 | Asset Recived From Civil-U#8-CHP-ConveyorPedetals&TransferPoint-10515 | N.A. | - | 0 | 0.00055408 | 0 | 0.00055408 | 0 | 0 |  |  | 0 | 0.00055408
41 | Asset Recived From Civil-U#8-CHP-MCC ROOM -10515 | N.A. | - | 0 | 0.00026945 | 0 | 0.00026945 | 0 | 0 |  |  | 0 | 0.00026945
42 | Asset Recived From Civil-U#8-AHP-RCC Ash Silo -10501 | N.A. | - | 0 | 0.00016423 | 0 | 0.00016423 | 0 | 0 |  |  | 0 | 0.00016423
43 | Asset Recived From Civil-U#8-AHP-Staicase near Silo-10501 | N.A. | - | 0 | 1.7302e-05 | 0 | 1.7302e-05 | 0 | 0 |  |  | 0 | 1.7302e-05
44 | Asset Recived From Civil-U#8-AHP-Drain sump in Silo Area -10501 | N.A. | - | 0 | 8.551e-06 | 0 | 8.551e-06 | 0 | 0 |  |  | 0 | 8.551e-06
45 | Asset Recived From Civil-U#8-AHP-Slurry Mixing Tank Fdn.-10501 | N.A. | - | 0 | 1.6923e-05 | 0 | 1.6923e-05 | 0 | 0 |  |  | 0 | 1.6923e-05
46 | Asset Recived From Civil-U#8-AHP-HCSD PUMP HOUSE-10501 | N.A. | - | 0 | 5.8934e-05 | 0 | 5.8934e-05 | 0 | 0 |  |  | 0 | 5.8934e-05
47 | Asset Recived From Civil-U#8-AHP-Ash Slurry Pump House -10501 | N.A. | - | 0 | 0.00014947 | 0 | 0.00014947 | 0 | 0 |  |  | 0 | 0.00014947
48 | Asset Recived From Civil-U#8-AHP-Ash Slurry Sump-10501 | N.A. | - | 0 | 4.5159e-05 | 0 | 4.5159e-05 | 0 | 0 |  |  | 0 | 4.5159e-05
49 | Asset Recived From Civil-U#8-AHP-Ash Water Tank-10501 | N.A. | - | 0 | 3.422e-05 | 0 | 3.422e-05 | 0 | 0 |  |  | 0 | 3.422e-05
50 | Asset Recived From Civil-U#8-AHP-Bottom Ash Hopper-10501 | N.A. | - | 0 | 4.409e-05 | 0 | 4.409e-05 | 0 | 0 |  |  | 0 | 4.409e-05
51 | Asset Recived From Civil-U#8-AHP-Drain sump in BAH Area -10501 | N.A. | - | 0 | 8.575e-06 | 0 | 8.575e-06 | 0 | 0 |  |  | 0 | 8.575e-06
52 | Asset Recived From Civil-U#8-Ash Slurry Pipe Line AHP-Pedestals-10501 | N.A. | - | 0 | 0.00013846 | 0 | 0.00013846 | 0 | 0 |  |  | 0 | 0.00013846
53 | Asset Recived From Civil-U#8-AHP-Buffer Hopper Foundation-10501 | N.A. | - | 0 | 3.5628e-05 | 0 | 3.5628e-05 | 0 | 0 |  |  | 0 | 3.5628e-05
54 | Asset Recived From Civil-U#8-AHP-Mill reject hopper foundation-10501 | N.A. | - | 0 | 1.7814e-05 | 0 | 1.7814e-05 | 0 | 0 |  |  | 0 | 1.7814e-05
55 | Asset Recived From Civil-U#8-FHP-Fuel Oil pump house-10516 | N.A. | - | 0 | 0.00065769 | 0 | 0.00065769 | 0 | 0 |  |  | 0 | 0.00065769
56 | Asset Recived From Civil-U#8-FHP-DYKE AREA -10516 | N.A. | - | 0 | 1.9339e-05 | 0 | 1.9339e-05 | 0 | 0 |  |  | 0 | 1.9339e-05
57 | Asset Recived From Civil-U#8-Effulent Treatment Plant -10509 | N.A. | - | 0 | 0.00014135 | 0 | 0.00014135 | 0 | 0 |  |  | 0 | 0.00014135
58 | Asset Recived From Project-U#8-Boiler Pressure parts-10501 | N.A. | - | 0 | 0.06549 | 0 | 0.06549 | 0 | 0 |  |  | 0 | 0.06549
59 | Asset Recived From Project-U#8-Mandatory Spares from BHEL–Trichy | N.A. | - | 0 | 0.0074619 | 0 | 0.0074619 | 0 | 0 |  |  | 0 | 0.0074619
60 | Asset Recived From Civil-U#8-Coal mill reject trench at coal mill D&E | N.A. | - | 0 | 0.04661 | 0 | 0.04661 | 0 | 0 |  |  | 0 | 0.04661
61 | Asset Recived From Project-U#8-Canteen Equipments & kitchen Utensils | N.A. | - | 0 | 0.21888 | 0 | 0.21888 | 0 | 0 |  |  | 0 | 0.21888
62 | Asset Recived From Project-U#8-Supply & Erection of ACW system-10310 | N.A. | - | 0 | 0.00083684 | 0 | 0.00083684 | 0 | 0 |  |  | 0 | 0.00083684
63 | Asset Recived From Project-U#8-SUPPLY & ERECTION OF CCW SYSTEM-10310 | N.A. | - | 0 | 0.004856 | 0 | 0.004856 | 0 | 0 |  |  | 0 | 0.004856
64 | Asset Recived From Project-U#8-TG set & its auxilleries-HP/LPFeedWate | N.A. | - | 0 | 0.016842 | 0 | 0.016842 | 0 | 0 |  |  | 0 | 0.016842
65 | Asset Recived From Project-U#8-TG set and its auxilleries- Boilerfeed | N.A. | - | 0 | 0.018479 | 0 | 0.018479 | 0 | 0 |  |  | 0 | 0.018479
66 | Asset Recived From Project-U#8-Air Conditioning-MandatorySpares-10576 | N.A. | - | 0 | 1.7256e-05 | 0 | 1.7256e-05 | 0 | 0 |  |  | 0 | 1.7256e-05
67 | Asset Recived From Project-U#8-Air Conditioning system-10576 | N.A. | - | 0 | 0.0013446 | 0 | 0.0013446 | 0 | 0 |  |  | 0 | 0.0013446
68 | Asset Recived From Project-U#8-AHP-FLY ASH & HCSD-SYSTEM-10501 | N.A. | - | 0 | 0.0021652 | 0 | 0.0021652 | 0 | 0 |  |  | 0 | 0.0021652
69 | Asset Recived From Project-U#8-AHP-FLYASH&HCSD-SYSTEMBOUGHT OUT-10501 | N.A. | - | 0 | 0.0070969 | 0 | 0.0070969 | 0 | 0 |  |  | 0 | 0.0070969
70 | Asset Recived From Project-U#8-AHP-BOTTOM ASH SYSTEM-10501 | N.A. | - | 0 | 0.012126 | 0 | 0.012126 | 0 | 0 |  |  | 0 | 0.012126
71 | Asset Recived From Project-U#8-AHP-ELECTRICAL C & I-10501 | N.A. | - | 0 | 0.004053 | 0 | 0.004053 | 0 | 0 |  |  | 0 | 0.004053
72 | Asset Recived From Project-U#8-AHP-GEHO PUMP-10501 | N.A. | - | 0 | 0.0095128 | 0 | 0.0095128 | 0 | 0 |  |  | 0 | 0.0095128
73 | Asset Recived FromProject-U#8-Boiler&Aux -Power Cycle Piping-10501 | N.A. | - | 0 | 0.041005 | 0 | 0.041005 | 0 | 0 |  |  | 0 | 0.041005
74 | Asset Recived From Project-U#8-Boiler&Aux-SUIT BLOWER & PIPING-10501 | N.A. | - | 0 | 0.083837 | 0 | 0.083837 | 0 | 0 |  |  | 0 | 0.083837
75 | Asset Recived From Project-U#8-Boiler & Auxillaries - PA FAN-10501 | N.A. | - | 0 | 0.0010226 | 0 | 0.0010226 | 0 | 0 |  |  | 0 | 0.0010226
76 | Asset Recived From Project-U#8-Boiler&Aux-Air Preheaters-10501 | N.A. | - | 0 | 0.013281 | 0 | 0.013281 | 0 | 0 |  |  | 0 | 0.013281
77 | Asset Recived From Project-U#8-Boiler & Auxillaries -COAL MILL-10501 | N.A. | - | 0 | 0.051244 | 0 | 0.051244 | 0 | 0 |  |  | 0 | 0.051244
78 | Asset Recived From Project-U#8-Boiler & Auxillaries -FD FAN-10501 | N.A. | - | 0 | 0.0006817 | 0 | 0.0006817 | 0 | 0 |  |  | 0 | 0.0006817
79 | Asset Recived From Project-U#8-Boiler & Auxillaries- ID FAN-10501 | N.A. | - | 0 | 0.0017043 | 0 | 0.0017043 | 0 | 0 |  |  | 0 | 0.0017043
80 | Asset Recived From Project-U#8-Boiler&Aux-Mandatory Spares-10501 | N.A. | - | 0 | 0.0097935 | 0 | 0.0097935 | 0 | 0 |  |  | 0 | 0.0097935
81 | Asset Recived From Project-U#8-Boiler&Aux-PLATFORM,STAIRS,GRATINGS, | N.A. | - | 0 | 0.030596 | 0 | 0.030596 | 0 | 0 |  |  | 0 | 0.030596
82 | Asset Recived From Project-U#8-Boiler Pressure parts-10501 | N.A. | - | 0 | 0.17807 | 0 | 0.17807 | 0 | 0 |  |  | 0 | 0.17807
83 | Asset Recived From Project-U#8-220V-BATTERY+CHARGERS-MAIN PLANT-10563 | N.A. | - | 0 | 0.0020848 | 0 | 0.0020848 | 0 | 0 |  |  | 0 | 0.0020848
84 | Asset Recived From Project-U#8-220V -BATTERY WITH CHARGERS(CHP)-10563 | N.A. | - | 0 | 0.00020745 | 0 | 0.00020745 | 0 | 0 |  |  | 0 | 0.00020745
85 | Asset Recived From Project-U#8-220V-BATTERY+CHARG-WAGON TRIP-2N-10563 | N.A. | - | 0 | 8.4674e-05 | 0 | 8.4674e-05 | 0 | 0 |  |  | 0 | 8.4674e-05
86 | Asset Recived From Project-U#8-BOP-OTHER C& i INSTRUMENTS-10509 | N.A. | - | 0 | 0.0013441 | 0 | 0.0013441 | 0 | 0 |  |  | 0 | 0.0013441
87 | Asset Recived From Project-U#8-CHP-CONVEYOR SYSTEM-10515 | N.A. | - | 0 | 0.015409 | 0 | 0.015409 | 0 | 0 |  |  | 0 | 0.015409
88 | Asset Recived From Project-U#8-CHP-WOBLER FEEDER-10515 | N.A. | - | 0 | 0.00054613 | 0 | 0.00054613 | 0 | 0 |  |  | 0 | 0.00054613
89 | Asset Recived From Project-U#8-CHP-APRON FEEDER-10515 | N.A. | - | 0 | 0.0028149 | 0 | 0.0028149 | 0 | 0 |  |  | 0 | 0.0028149
90 | Asset Recived From Project-U#8-CHP-ILMS,METAL DETECTOR,BELT WEIGHER | N.A. | - | 0 | 0.0011704 | 0 | 0.0011704 | 0 | 0 |  |  | 0 | 0.0011704
91 | Asset Recived From Project-U#8-CHP-IMPACT CRUSHER-10515 | N.A. | - | 0 | 0.0020638 | 0 | 0.0020638 | 0 | 0 |  |  | 0 | 0.0020638
92 | Project-U#8-CHP-STRACKER CUM RECLAIMER-10515 | N.A. | - | 0 | 0.0082014 | 0 | 0.0082014 | 0 | 0 |  |  | 0 | 0.0082014
93 | Project-U#8-CHP-SIDE DISCHARGE TYPE WAGON TRIPPLER | N.A. | - | 0 | 0.0077836 | 0 | 0.0077836 | 0 | 0 |  |  | 0 | 0.0077836
94 | Project-U#8-Coal Handling Plant-M.S.-10515 | N.A. | - | 0 | 0.00034267 | 0 | 0.00034267 | 0 | 0 |  |  | 0 | 0.00034267
95 | Project-U#8-communication system-10572 | N.A. | - | 0 | 0.0019253 | 0 | 0.0019253 | 0 | 0 |  |  | 0 | 0.0019253
96 | Project-U#8-UPS INVERTORS-10563 | N.A. | - | 0 | 0.00051465 | 0 | 0.00051465 | 0 | 0 |  |  | 0 | 0.00051465
97 | Project-U#8-UPS ACDS-10563 | N.A. | - | 0 | 8.9956e-05 | 0 | 8.9956e-05 | 0 | 0 |  |  | 0 | 8.9956e-05
98 | Project-U#8-UPS BATTERIRERS-10563 | N.A. | - | 0 | 0.00051465 | 0 | 0.00051465 | 0 | 0 |  |  | 0 | 0.00051465
99 | Project-U#8-24V BATTERY CHARGERS (SGTG)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
100 | Project-U#8-24V BATTERY CHARGERS (BOP)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
101 | Project-U#8-BATTERIS FOR (SGTG)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
102 | Project-U#8-BATTERIS FOR (BOP)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
103 | Project-U#8-DCDB(SGTG)-10563 | N.A. | - | 0 | 5.7183e-05 | 0 | 5.7183e-05 | 0 | 0 |  |  | 0 | 5.7183e-05
104 | Project-U#8-DCDB(BOP)-10563 | N.A. | - | 0 | 5.7183e-05 | 0 | 5.7183e-05 | 0 | 0 |  |  | 0 | 5.7183e-05
105 | Project-U#8-Controls & Instru. for Main Plant(BTG) | N.A. | - | 0 | 0.044292 | 0 | 0.044292 | 0 | 0 |  |  | 0 | 0.044292
106 | Project-U#8-CW Chlorination system-10509 | N.A. | - | 0 | 0.0011974 | 0 | 0.0011974 | 0 | 0 |  |  | 0 | 0.0011974
107 | Project-U#8-D.G.SET-10509 | N.A. | - | 0 | 3.7894e-05 | 0 | 3.7894e-05 | 0 | 0 |  |  | 0 | 3.7894e-05
108 | Project-U#8-D.M.Water System-10509 | N.A. | - | 0 | 0.005785 | 0 | 0.005785 | 0 | 0 |  |  | 0 | 0.005785
109 | Project-U#8-DG set- Manadatory Spares-10509 | N.A. | - | 0 | 0.00025004 | 0 | 0.00025004 | 0 | 0 |  |  | 0 | 0.00025004
110 | Project-U#8-DG Set Room cum Air Compressor House | N.A. | - | 0 | 0.0055794 | 0 | 0.0055794 | 0 | 0 |  |  | 0 | 0.0055794
111 | Project-U#8-Steel for TechnologicalStructure-10501 | N.A. | - | 0 | 0.14836 | 0 | 0.14836 | 0 | 0 |  |  | 0 | 0.14836
112 | Project-U#8-Electrical Package for BOP-10509 | N.A. | - | 0 | 0.0024904 | 0 | 0.0024904 | 0 | 0 |  |  | 0 | 0.0024904
113 | Project-U#8-Electrical CHARGES-10509 | N.A. | - | 0 | 4.1155e-05 | 0 | 4.1155e-05 | 0 | 0 |  |  | 0 | 4.1155e-05
114 | Project-U#8-Electrical Package for BOP-Mandatory | N.A. | - | 0 | 0.0002757 | 0 | 0.0002757 | 0 | 0 |  |  | 0 | 0.0002757
115 | Project-U#8-Fire Protection, Alarm & Detection | N.A. | - | 0 | 0.0071788 | 0 | 0.0071788 | 0 | 0 |  |  | 0 | 0.0071788
116 | Project-U#8-Fuel Oil Pump House-10516 | N.A. | - | 0 | 0.0040925 | 0 | 0.0040925 | 0 | 0 |  |  | 0 | 0.0040925
117 | Project-U#8-Generator Transformer-10541 | N.A. | - | 0 | 0.012655 | 0 | 0.012655 | 0 | 0 |  |  | 0 | 0.012655
118 | Project-U#8-Generator/Transformer protection | N.A. | - | 0 | 0.00024539 | 0 | 0.00024539 | 0 | 0 |  |  | 0 | 0.00024539
119 | Project-U#8-H.T.Switchgear for main plant-10561 | N.A. | - | 0 | 0.025188 | 0 | 0.025188 | 0 | 0 |  |  | 0 | 0.025188
120 | Project-U#8-Indoor & Outdoor plant lighting-10599 | N.A. | - | 0 | 0.0004077 | 0 | 0.0004077 | 0 | 0 |  |  | 0 | 0.0004077
121 | Project-U#8-L.P.Piping including valves-10509 | N.A. | - | 0 | 0.0038246 | 0 | 0.0038246 | 0 | 0 |  |  | 0 | 0.0038246
122 | Project-U#8-L.T. Electrical for main plant.-10561 | N.A. | - | 0 | 8.7067e-05 | 0 | 8.7067e-05 | 0 | 0 |  |  | 0 | 8.7067e-05
123 | Project-U#8-Laying&Termination of HT cables-10561 | N.A. | - | 0 | 0.0008231 | 0 | 0.0008231 | 0 | 0 |  |  | 0 | 0.0008231
124 | Project-U#8-MainBoiler Structure&foundations-10501 | N.A. | - | 0 | 0.09941 | 0 | 0.09941 | 0 | 0 |  |  | 0 | 0.09941
125 | Project-U#8-Mandatory Spares for Ash HandlingPlant | N.A. | - | 0 | 0.0015616 | 0 | 0.0015616 | 0 | 0 |  |  | 0 | 0.0015616
126 | Project-U#8-Mandatory spares for C&I of Main Plant | N.A. | - | 0 | 0.0050295 | 0 | 0.0050295 | 0 | 0 |  |  | 0 | 0.0050295
127 | Project-U#8-Mandatory Spares for Electrical MainPa | N.A. | - | 0 | 0.015601 | 0 | 0.015601 | 0 | 0 |  |  | 0 | 0.015601
128 | Project-U#8-Mandatory Spares For TG & Auxilliaries | N.A. | - | 0 | 0.0062588 | 0 | 0.0062588 | 0 | 0 |  |  | 0 | 0.0062588
129 | Project-U#8-Misc. Cranes & hoists-10553 | N.A. | - | 0 | 0.0023537 | 0 | 0.0023537 | 0 | 0 |  |  | 0 | 0.0023537
130 | Project-U#8-Miscellaneous Pumps -10599 | N.A. | - | 0 | 0.0015672 | 0 | 0.0015672 | 0 | 0 |  |  | 0 | 0.0015672
131 | Project-U#8-Passanger lift for TG Building-10599 | N.A. | - | 0 | 0.0016358 | 0 | 0.0016358 | 0 | 0 |  |  | 0 | 0.0016358
132 | Project-U#8-Passanger/Material Lift at boiler side | N.A. | - | 0 | 0.00084731 | 0 | 0.00084731 | 0 | 0 |  |  | 0 | 0.00084731
133 | Project-U#8-Chemical Laboratory -10509 | N.A. | - | 0 | 0.0011648 | 0 | 0.0011648 | 0 | 0 |  |  | 0 | 0.0011648
134 | Project-U#8-Sewage Treatment Plant-10509 | N.A. | - | 0 | 0.0019006 | 0 | 0.0019006 | 0 | 0 |  |  | 0 | 0.0019006
135 | Project-U#8-Station Transformer-10541 | N.A. | - | 0 | 0.026576 | 0 | 0.026576 | 0 | 0 |  |  | 0 | 0.026576
136 | Project-U#8-Steam Turbine set-10503 | N.A. | - | 0 | 0.13864 | 0 | 0.13864 | 0 | 0 |  |  | 0 | 0.13864
137 | Project-U#8-TG set and its auxilleries- Condensor | N.A. | - | 0 | 0.012703 | 0 | 0.012703 | 0 | 0 |  |  | 0 | 0.012703
138 | Project-U#8-TG set and its auxilleries -Generator | N.A. | - | 0 | 0.032545 | 0 | 0.032545 | 0 | 0 |  |  | 0 | 0.032545
139 | Project-U#8-TG set and its auxilleries-Condensor | N.A. | - | 0 | 0.029273 | 0 | 0.029273 | 0 | 0 |  |  | 0 | 0.029273
140 | Project-U#8-TG set & its auxilleries-Derator-10503 | N.A. | - | 0 | 0.002758 | 0 | 0.002758 | 0 | 0 |  |  | 0 | 0.002758
141 | Project-U#8-TG set and its auxilleries-DMMakeUpSys | N.A. | - | 0 | 0.0010491 | 0 | 0.0010491 | 0 | 0 |  |  | 0 | 0.0010491
142 | Project-U#8-TG set and its auxilleries-Gas System | N.A. | - | 0 | 0.0056178 | 0 | 0.0056178 | 0 | 0 |  |  | 0 | 0.0056178
143 | Project-U#8-TG set and its auxilleries-GoveringSys | N.A. | - | 0 | 4.9466e-05 | 0 | 4.9466e-05 | 0 | 0 |  |  | 0 | 4.9466e-05
144 | Project-U#8-TG set and its auxilleries-HP/LP By-pa | N.A. | - | 0 | 0.010752 | 0 | 0.010752 | 0 | 0 |  |  | 0 | 0.010752
145 | Project-U#8-TG set and its auxilleries-HP/LP Dozin | N.A. | - | 0 | 0.00039941 | 0 | 0.00039941 | 0 | 0 |  |  | 0 | 0.00039941
146 | Project-U#8-TG set and its auxilleries-SealOilPump | N.A. | - | 0 | 9.8566e-05 | 0 | 9.8566e-05 | 0 | 0 |  |  | 0 | 9.8566e-05
147 | Project-U#8-TG set and its auxilleries-Vaccum Syst | N.A. | - | 0 | 0.010304 | 0 | 0.010304 | 0 | 0 |  |  | 0 | 0.010304
148 | Project-U#8-Turbine Lub. Oil System With Purifier | N.A. | - | 0 | 0.0022364 | 0 | 0.0022364 | 0 | 0 |  |  | 0 | 0.0022364
149 | Project-U#8-Ventillation system-10599 | N.A. | - | 0 | 0.0014389 | 0 | 0.0014389 | 0 | 0 |  |  | 0 | 0.0014389
150 | Asset Recived From Project-U#8-M.SPARE_Ventillation system-10599 | N.A. | - | 0 | 8.5482e-05 | 0 | 8.5482e-05 | 0 | 0 |  |  | 0 | 8.5482e-05
151 | Asset Recived From Project-U#8-Water Treatment Plant-10509 | N.A. | - | 0 | 0.0042384 | 0 | 0.0042384 | 0 | 0 |  |  | 0 | 0.0042384
152 | Asset Recived From Project-U#8-WORK SHOP MAD_SPARE-10565 | N.A. | - | 0 | 0.00030445 | 0 | 0.00030445 | 0 | 0 |  |  | 0 | 0.00030445
153 | Asset Recived From Project-U#8-Workshop-10565 | N.A. | - | 0 | 0.0013286 | 0 | 0.0013286 | 0 | 0 |  |  | 0 | 0.0013286
154 | Asset Recived From Project-U#8-CMR SYSTEM-10501 | N.A. | - | 0 | 0.0020736 | 0 | 0.0020736 | 0 | 0 |  |  | 0 | 0.0020736
155 | Asset Recived From Project-U#8-MandatorySpares-WTP-10.509 | N.A. | - | 0 | 8.1517e-05 | 0 | 8.1517e-05 | 0 | 0 |  |  | 0 | 8.1517e-05
156 | Asset Recived From Project-U#8-E.1.07_MandSpar 4 C&I MS 4MeasuringIns E.1.07_M S for C&I_ MS For Measuring Ins | N.A. | - | 0 | 0.078697 | 0 | 0.078697 | 0 | 0 |  |  | 0 | 0.078697
157 | Asset Recived From Project-U#8-BOP_ELECTRICAL-10612 | N.A. | - | 0 | 0.01637 | 0 | 0.01637 | 0 | 0 |  |  | 0 | 0.01637
158 | Asset Recived From Project-U#8-Bus Ducts-10612 | N.A. | - | 0 | 0.012548 | 0 | 0.012548 | 0 | 0 |  |  | 0 | 0.012548
159 | Asset Recived From Project-U#8-Cable trays & supports-10612 | N.A. | - | 0 | 0.00036009 | 0 | 0.00036009 | 0 | 0 |  |  | 0 | 0.00036009
160 | Project-U#8-PCR FURNITURE-10810 | N.A. | - | 0 | 0.00030684 | 0 | 0.00030684 | 0 | 0 |  |  | 0 | 0.00030684
161 | Project-U#8 Server Intel QUAD CORE 02No. HP Office Server | N.A. | - | 0 | 0.11918 | 0.11918 | 0 | 0 | 0 |  |  | 0 | 0
162 | Supply Erection testing and commissining of 1000 m3 ETP Civil works | N.A. | - | 0 | 0.68324 | 0.68324 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 118.4602 | 56.509 | 61.9512 | 28.2934 | 78.8337 | 0 | 0 | 78.8337 | 11.4109
FY 2024-25
0 | Add Cap (As per 296 of 2019)
A | Initial spares | Add Cap (As per 296 of 2019) | - | 0
1 | Boiler and Auxiliaries | Add Cap (As per 296 of 2019) | - | 7.2
1 | Procurement of Coal Mill XRP-903 Gear Box Type KMP-280 Spares of Unit # 8 at BM-NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 0 | 1.35 | 1.35 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply of Labyrinth Seal Rings with replaceable Inner liners for Coal Mill XRP-903 required for BM Unit-8, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.33134 | 0.33134 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply and Installation of coal mill liners(weld overlay) of XRP-903 Coal Mill in BM U-8, NPTPS,Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.33134 | 0.33134 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of Coal Mill XRP-903 Bowl & Bowl Hub of Unit # 8 at BM-NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 0 | 0.73326 | 0.73326 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply of impeller assembly for ID fan | Add Cap (As per 296 of 2019) | - | 0 | 0.5233 | 0.5233 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of Primary Air Fan & Forced Draught Fan Drive Coupling on OEM basis required at BM U-8, NPTPS, Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.1941 | 0.1941 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of Primary Air Fan PAF 17/11.8-2 Hydraulic Adjustment Device on OEM basis required at BM U-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.53521 | 0.53521 | 0 | 0 | 0 |  |  | 0 | 0
8 | Proc of spares for fabric expansion joints required at BM U-8, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.56972 | 0.56972 | 0 | 0 | 0 |  |  | 0 | 0
9 | Proc of separator body and seperator top spares for coal mill XRP-903 at BM U-8, NPTPS Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.42569 | 0.42569 | 0 | 0 | 0 |  |  | 0 | 0
10 | Proc of scrapper area & reject system spares for coal mill XRP-903 at BM U-8, NPTPS Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.27833 | 0.27833 | 0 | 0 | 0 |  |  | 0 | 0
11 | Proc of seal air fan spares at BM-8 NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.26432 | 0.26432 | 0 | 0 | 0 |  |  | 0 | 0
12 | Procurement of FD Fan Type FAF 17/9.5-1 Drive Coupling required at BM U-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | Procurement of complete planatary gear box-KMP -280/300 for coal mill XRP-903 at BM U-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Turbine and Auxiliaries | Add Cap (As per 296 of 2019) | - | 4.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of spares for Equipment Cooling Water Pumps (Make-FLOWMORE) of model FIG-5824 (SG Side) and FIG-5822 (TG side) at Unit-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.51812 | 0.51812 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply of spars for recovery & FF Pumps along with work at U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0.37713 | 0.37713 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of seal oil vacuum pump in unit 08 | Add Cap (As per 296 of 2019) | - | 0 | 0.27502 | 0.27502 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of AC pressure pipes (235MM OD, 200MM ID, 4.5M Length) for NDCT hot spray water distribution system in Unit-8 NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 0 | 0.42522 | 0.42522 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply of M/s Summits make Instrument Air Dryer & spares at U # 8 TM, Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.54787 | 0.54787 | 0 | 0 | 0 |  |  | 0 | 0
6 | Supply of PVC fills for NDCTs at U # 8 TM, Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.58245 | 0.58245 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of NB 600MM Gate valves for ACW self cleaning strainers in U#8 TM NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.42338 | 0.42338 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of Mechanical seals ( Make Leak-Proof) for various pumps in TM Unit-8 NPTPS Parli. | Add Cap (As per 296 of 2019) | - | 0 | 0.49233 | 0.49233 | 0 | 0 | 0 |  |  | 0 | 0
9 | Supply of SS 304 pipes & others at U # 8 TM, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.52905 | 0.52905 | 0 | 0 | 0 |  |  | 0 | 0
3 | Electrical and Instrumentation | Add Cap (As per 296 of 2019) | - | 6.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of Instrumentation Spares of LP Bypass System at Unit-8. | Add Cap (As per 296 of 2019) | - | 0 | 1.9615 | 1.9615 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of Schneider MICOM Numerical Relays for GRP and STPR swithcgear at NPTPS Unit-8 Testing | Add Cap (As per 296 of 2019) | - | 0 | 0.47613 | 0.47613 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of 220V DC Chloride make (formally caldyne) make battery chargers Spre of Unit 8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.23365 | 0.23365 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of 24V DC Chhabi make make battery chargers Spare of Unit 8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.22465 | 0.22465 | 0 | 0 | 0 |  |  | 0 | 0
5 | Procurement of Spare for Hitachi Hi-Rel make UPS systems installed at Unit-8 NPTPS Parli Vaijnath. | Add Cap (As per 296 of 2019) | - | 0 | 0.19186 | 0.19186 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of various test kit for testing U#8 such as energy meter calibration kit, DC earth faulth locator kit, promary current injection kit, breaker time measurement kit, numeric relay test kit and other testing instruments. | Add Cap (As per 296 of 2019) | - | 0 | 0.67345 | 0.67345 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of Energymeter Caliberation Software Module and hardware for upgrading Numeric Relay Test kit at Unit -8 Testing. | Add Cap (As per 296 of 2019) | - | 0 | 0.11863 | 0.11863 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of H T Motors. | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of critical L T Motors | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of ESP Hopper heaters (As a initial spares) Installed at EM U-8, NPTPS, Parli-Vaijnath under add cap scheme. | Add Cap (As per 296 of 2019) | - | 0 | 0.38586 | 0.38586 | 0 | 0 | 0 |  |  | 0 | 0
4 | Outdoor Plant(CHP/AHP/WTP) | Add Cap (As per 296 of 2019) | - | 6.64 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of Apron Feeder spares installed at CHP NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 1.6233 | 1.6233 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply of various drive and non drive pulleys for CHP U-8. | Add Cap (As per 296 of 2019) | - | 0 | 0.54529 | 0.54529 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply and installation of clamp pads & resting pads for Side Beam of Wagon Tippler for CHP U-8 | Add Cap (As per 296 of 2019) | - | 0 | 0.54802 | 0.54802 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply of unbalance motorozied vibrating feeder for S/R of U-7/8 CHP NPTPS Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.3958 | 0.3958 | 0 | 0 | 0 |  |  | 0 | 0
5 | Procurement of conveying and Instrument air compressor spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 1.77 | 1.77 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of vacuum pump spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0.2291 | 0.2291 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of fluidizing blower spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0.11796 | 0.11796 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of slurry pump spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of Clinker grinder spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0.12334 | 0.12334 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B | Reassessment of remaining BOP work after insolvency of M/s Sunil Hi-Tech | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Project balance E&M and procurement of mandetory spares | MERC CAPEX Approval in MTR Order 296 of 2019 | Order 296 of 2019 | 41.4534 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work order for Contract of Supply and application of Fire Stop Mortar Seal and Fire Retardant Cable Coating Compound at NPTP U-8 Parli Project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 3.4589 | 3.4589 | 0 | 0 | 0 |  |  | 0 | 0
2 | Work order for contract for Supply Installaion Testing & Commissioning Smoke Detection & alaram system | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 2.5606 | 2.5606 | 0 | 0 | 0 |  |  | 0 | 0
3 | Work order for contract for Supply Installaion Testing & Commissioning of Balance Fire Fighting System at NPTP U-8 Parli Project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.0502 | 1.0502 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, Errection, testing & commissioning works of RWP, PT potable chlorination system, ETP system control panel, automation of LDO, HFO tank foam system Hose boxes with RRL hoses and branch pipe and allied system at NPTP | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.8496 | 0.8496 | 0 | 0 | 0 |  |  | 0 | 0
5 | Work Order contract for supply, installation Testing & Commissioning of telephone exchange (EPBAX) & Telephone System at NPTP U-8 Parli project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.91256 | 0.91256 | 0 | 0 | 0 |  |  | 0 | 0
6 | Balance Supply of Electrical Lab Equipment at NPTP parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.60826 | 0.60826 | 0 | 0 | 0 |  |  | 0 | 0
7 | Work order for contract for Supply Installaion Testing & Commissioning with required material to complete Balance CHP work at NPTP U-8 Parli Project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.41 | 0.41 | 0 | 0 | 0 |  |  | 0 | 0
8 | Supply, Errection, testing & commissioning of Interconnecting Conveyor no.9 & 10 from U-8 to U-6&7 of CHP at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 5.3319 | 5.3262 | 0.0056593 | 0 | 0 |  |  | 0 | 0.0056593
9 | SUPPLY ,INSTA,TEST ,COMM ELECTRICAL SYS | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | SUPPLY,INSTAL,TEST,COMM OF CRANS&HOIST | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.8105 | 3.6223 | -1.8118 | 0 | 0 |  |  | 0 | -1.8118
11 | Supply, Errection, testing & commissioning of Dust Extraction system at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.8061 | 0 | 1.8061 | 0 | 0 |  |  | 0 | 1.8061
12 | Supply, Errection, testing & commissioning of DSS & DFDS at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 2.8091 | 0 | 2.8091 | 1.53 | 4.34 |  |  | 4.34 | -0.0008856
13 | Supply, Errection, testing & commissioning of Monorail at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.1892 | 1.1891 | 7.77e-05 | 0 | 0 |  |  | 0 | 7.77e-05
14 | Supply, Errection, testing & commissioning of various Control & Instrumentation equipments at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.72225 | 0.72225 | 0 | 0 | 0 |  |  | 0 | 0
15 | Supply, Errection, testing & commissioning of Air Conditioning System at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.15304 | 0.44729 | -0.29425 | 0 | 0 |  |  | 0 | -0.29425
16 | Supply, Errection, testing & commissioning of Ventilation System at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 2.1136 | 1.2036 | 0.91 | 0 | 0 |  |  | 0 | 0.91
17 | Supply, Errection, testing & commissioning of Elevator works. | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 3.5173 | 3.5173 | 0 | 0 | 0.91 |  |  | 0.91 | -0.91
18 | Work contract for dismentaling, supply, erection & commissioning of MRHS | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 2.2335 | 2.2335 | 0 | 0 | 0 |  |  | 0 | 0
19 | Supply, Errection, testing & commissioning of FF System, Smoke detection & Fire stop mortar & Fire retradant cable coating for conveyor 09 & 10 | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.22171 | 0.51866 | -0.29696 | 0 | 0 |  |  | 0 | -0.29696
20 | Supply, Errection, testing & commissioning of Chimney Elevator | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.0608 | 0 | 1.0608 | 0 | 0 |  |  | 0 | 1.0608
21 | Supply, Errection, testing & commissioning work of GEHO Pumps. | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0 | 0 | 0 | 0 | 1.06 |  |  | 1.06 | -1.06
22 | Procurement of various Mandetory spares of BOP packages | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0 | 0 | 0 | 5.47 | 6.54 |  |  | 6.54 | -1.07
0 | Balance civil work of BOP scope at 250 MW Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 45.3238 | 0.55712 | 16.72 | -16.1629 | 0 | 0 |  |  | 0 | -16.1629
1 | Area grading | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 6.9866 | 0.89 | 6.0966 | 0 | 0 |  |  | 0 | 6.0966
2 | CMD | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.2411 | 1.3549 | -0.11383 | 0 | 0 |  |  | 0 | -0.11383
3 | Conveyor 09, 10 & TP 06 | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 14.5605 | 10.1 | 4.4605 | 0 | 2.03 |  |  | 2.03 | 2.4305
4 | Finishing item | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 8.085 | 4.6506 | 3.4344 | 0 | 0 |  |  | 0 | 3.4344
5 | Drain & nala | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 5.0848 | 11.79 | -6.7052 | 0 | 0 |  |  | 0 | -6.7052
6 | Internal roads | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 9.7521 | 1.5 | 8.2521 | 0 | 0 |  |  | 0 | 8.2521
7 | Stacker & reclaimer | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.1627 | 0 | 1.1627 | 0 | 0 |  |  | 0 | 1.1627
0 | Other Add Cap | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Laboratory set up | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of Analytical Instruments for condition monitoring Laboratory for 1X250 MW of NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.5 | 0.49655 | 0.49655 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply of Analytical Instruments for Water Analysis Laboratory for 1X250 MW of NPTPS, Parli-V | Add Cap (As per 296 of 2019) | - | 1.23 | 0.29847 | 0.29847 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of Analytical Instruments for Environment Laboratory for 1 x 250 MW, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.39 | 0.3658 | 0.3658 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply of Analytical Instruments for Precision Laboratory for 1 x 250 MW, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply of Analytical Instruments for General Laboratory of Water Treatment Plant of 1 x 250 MW, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Supply of Corrosion Monitor/Meter, Corrosion Coupon & Coupon Rack for 1X250 MW of NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.34 | 0.34736 | 0.34736 | 0 | 0 | 0 |  |  | 0 | 0
7 | Supply of Analytical Instruments for Coal Analysis Laboratory for 1X250 MW of NPTPS, Parli-V | Add Cap (As per 296 of 2019) | - | 1.65 | 0.39444 | 0.39444 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Grade slab (WTP Area) | Add Cap (As per 296 of 2019) | - | 1 | 0.99752 | 0.99752 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Grade slab (Near AHP Building) | Add Cap (As per 296 of 2019) | - | 0.75 | 0.74556 | 0.74556 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Temporary shed for empty barrles & filled barrles | Add Cap (As per 296 of 2019) | - | 0.5 | 0.45635 | 0.45635 | 0 | 0 | 0 |  |  | 0 | 0
12 | Cabins for operators at TP. | Add Cap (As per 296 of 2019) | - | 0.2 | 0.18583 | 0.18583 | 0 | 0 | 0 |  |  | 0 | 0
13 | Compound wall for isolation of administrative building. | Add Cap (As per 296 of 2019) | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Work of providing/ fixing of internal partitions of aluminium/Nova palm/glass/wooden for Unit 8 service building & other allied builings in the premises. | Add Cap (As per 296 of 2019) | - | 0.7 | 0.67356 | 0.67356 | 0 | 0 | 0 |  |  | 0 | 0
15 | Provision of DM and softening water line interconnection from u-6,7 to u-8 & Provision of recovery of waste water from sandava pump house,NDCT. | Add Cap (As per 296 of 2019) | - | 3 | 1.0266 | 1.0266 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | Add Cap (As per 296 of 2019) | - | 0 | 1.8371 | 1.8371 | 0 | 0 | 0 |  |  | 0 | 0
16 | Hydraulic drive system modification. | Add Cap (As per 296 of 2019) | - | 2.5 | 2.4384 | 2.4384 | 0 | 0 | 0 |  |  | 0 | 0
17 | Link conveyor from Con-2 of U-6/7 to Con.-2AB of U-8. | Add Cap (As per 296 of 2019) | - | 3.7 | 4.6434 | 22.6564 | -18.0129 | 0 | 0 |  |  | 0 | -18.0129
18 | Ozone plant for Unit -8 | Add Cap (As per 296 of 2019) | - | 20 | 20.0947 | 2.1929 | 17.9018 | 0 | 0 |  |  | 0 | 17.9018
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | Water management system | Add Cap (As per 296 of 2019) | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8, 20 | Procurement & Installation of EMS system at Unit-8 NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 1 | 0.14417 | 0.14417 | 0 | 0 | 0 |  |  | 0 | 0
21 | Conveyor-5 of stacking/reclaiming belt double drive arrangement. | Add Cap (As per 296 of 2019) | - | 2 | 2.0432 | 2.0432 | 0 | 0 | 0 |  |  | 0 | 0
22 | Chemical lab building | Add Cap (As per 296 of 2019) | - | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Chemical store | Add Cap (As per 296 of 2019) | - | 2.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Lawn development around NDCT. | Add Cap (As per 296 of 2019) | - | 0.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | Tree plantation & greenery along road side. | Add Cap (As per 296 of 2019) | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | Greenery development in area between WTP & main plant. | Add Cap (As per 296 of 2019) | - | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | Construction of staff rooms & store for CHP maint.. | Add Cap (As per 296 of 2019) | - | 1 | 0.90703 | 0.90703 | 0 | 0 | 0 |  |  | 0 | 0
28 | Dsludg filteration for raw water | Add Cap (As per 296 of 2019) | - | 17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29 | PLC/UPS system upgradation | Add Cap (As per 296 of 2019) | - | 0.5 | 0.40149 | 0.40149 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | FGD at Parli Unit # 8 | MERC/CAPEX/2021-2022/0284 | 2022-06-27 | 89.24 | 4.1 | 0 | 4.1 | 0 | 0 |  |  | 0 | 4.1
22.1 | FGD at Parli Unit # 8 | MERC/CAPEX/2021-2022/0284 | 2022-06-27 | 85.2 | 0.49 | 0 | 0.49 | 94.72 | 76.2 |  |  | 76.2 | 19.01
0 | IDC | MERC/CAPEX/2021-2022/0284 | 2022-06-27 | 4.04 | 0 | 0 | 0 | 4.04 | 0 |  |  | 0 | 4.04
HO DPR 16 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 2.23 | 2.23 |  |  | 2.23 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Detailed Project Report on Boiler plant performance improvement and availability improvement schemes at Boiler Maintenance 1x250MW Unit-8 TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Procurement & Replacement of Complete Economizer Upper & Lower Bank Coil Assemblies at Unit-8, NPTPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.3 | Procurement & replacement of PA Fan PAF 17/11.8-2 and FD Fan FAF 17/9.5-1 Complete Blade set required at BM U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.4 | Procurement & Replacement of Coal Mill Gear Box Type KMP 280 at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.5 | Procurement & replacement of Bowl & Bowl Hub Assembly of Coal Mill XRP-903 required at BM U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.6 | Procurement of Complete Journal Assembly without Grinding roll for Coal Mill XRP-903 required at BM U-8 NPTPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.7 | Procurement of Hydraulic Adjustment Device for FD Fan FAF 17/9.5-1 at BM U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.8 | SWAS upgradation at U#8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement & Replacement of Complete Platen super heater coils Coil Assemblies at Unit-8, TPS Parli-V, Procurement & Replacement of Complete LTSH upper & lower bank Coil Assemblies at Unit-8, TPS Parli-V & Procurement & Replacement of Coal Mill Gear Box Type KMP 280 at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Procurement & Replacement of Complete Platen super heater coils Coil Assemblies at Unit-8, TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Procurement & Replacement of Complete LTSH upper & lower bank Coil Assemblies at Unit-8, TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Procurement & Replacement of Coal Mill Gear Box Type KMP 280 at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-8, Parli TPS Procurement & replacement of PA & FD fan rotar hub assembly at Unit-8 TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Procurement & replacement of PA & FD fan rotar hub assembly at Unit-8 TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | DPR on Refurbishment of TG Governing system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Refurbishment of TG Governing system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | DPR on Performance improvement of Natural Draft Cooling Tower (NDCT) at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Performance improvement of Natural Draft Cooling Tower (NDCT) by replacement of PVC fills, AC cement pipes, strengthening of Hot water distribution system, replacement of beams, columns, support structures, etc. at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | DPR on Procurement of ACW & CW pump along with mandatory spares at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | DPR on Procurement of ACW & CW pump along with mandatory spares at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | DPR on Procurement of CEP pump and BFP Booster pump along with mandatory spares at Unit-8, PTPS, Parli V and Procurement of Energy Efficient Cartridges of Boiler Feed Pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Procurement of CEP pump and BFP Booster pump along with mandatory spares at Unit-8, PTPS, Parli | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.2 | Procurement of Energy Efficient Cartridges of Boiler Feed Pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | DPR on Procurement of turbine blades of HP, IP & LP rotor in Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.1 | DPR on Procurement of turbine blades of HP, IP & LP rotor in Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | DPR on Repair & Reconditioning of Water treatment plant at Unit-8, PTPS, Parli V and Performance improvement of centralised AC plant at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.1 | Reconditioning of Acid and Alkali Unloading and storage system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.2 | Reconditioning & repairing of WTP DM Plant regeneration system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.3 | Performance improvement of centralised AC plant by reconditioning of cooling tower, various pumps, heat exchangers, etc. at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | DPR on Procurement of Control Fluid (HPCF) pump, Lube Oil pump, Emergency Oil pump, Jacking Oil pump, Seal oil pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.1 | DPR on Procurement of Control Fluid (HPCF) pump, Lube Oil pump, Emergency Oil pump, Jacking Oil pump, Seal oil pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | DPR on Procurement of H2 cooler, BFP coolers, generator exciter cooler, Seal and Lube oil coolers at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.1 | DPR on Procurement of H2 cooler, BFP coolers, generator exciter cooler, Seal and Lube oil coolers at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Supply, installation & commissioning of 220V 2140AH,24V 830AH & 710AH, 360V 570AH Mains UPS,110V 110AH AHP PLC , 110V , 103 AH DM plant battery set for unit 8 , NPTPS Parli-V & Procurement of HT motors at U#8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.1 | Supply, installation & commissioning of 220V 2140AH,24V 830AH & 710AH, 360V 570AH Mains UPS,110V 110AH AHP PLC , 110V , 103 AH DM plant battery set for unit 8 , NPTPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.2 | Procurement of HT motors at U#8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | DPR on various instrumentation & control schemes at U#8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | Upgradation of MAX-DNA DCS system at U#8 (HMI upgradation) | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.2 | Upgradation of existing Pcal system with plant performance analysis diagnostic and optimization system (PADO) at Unit 8 New Parli TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.3 | Upgradation of coal feeder for I&C Unit8 PTPS Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.4 | Procurement of smart control positioner at I&C Unit8 PTPS Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.5 | Upgradation Electronic control drive for I&C Unit8 PTPS Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.6 | Upgradation of turbovisory & vibration monitoring system control panel. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Performance improvement by system up gradation at CHP & DPR for normalization and stabilization of coal handling plant performance at Parli TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.1 | Supply and Commissioning of Energy Efficient Evaporative Cooling System for Control Panel & Breaker room of CHP Unit-8 For PARLI TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.2 | Supply and commissioning of Suspended Magnets for U-8 CHP NPTPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.3 | Stacker-reclaimer Bucket wheel drive modification work of U- 8 CHP | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.4 | Apron feeder drive modification from Hydraulic to Electro-Mechanical at CHP U-8 NPTPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.5 | Procurement of U-8 W/T Major spares | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.6 | Provision of Soft starter / VFD for Various conveyor | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.7 | TP-3 chute modification at U-8 CHP. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.8 | Design, supply and commissioning of solar operated lighting system in CHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.9 | Installation of CCTV survillance system alongwith all conveyors. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | DPR for maximiation of Coal Handling Plant efficiency & DPR on life enhancement of Coal Handling Plant | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | W/T control room & bunker house battery & UPS upgradation | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Refurbishment of conveyor no. 2 A/B & 6 A/B drive system of CHP U-8 TPS Parli. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Provision of Soft starter / VFD for Various conveyor | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Procurement & installation of Belt tear detection system | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.5 | Conveyor gravity takeup infrastructure strengthening work | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.6 | U-8 CHP apron feeder-I to Conveyor 1 A/B chute modification work . | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | DPR for stabiliazation of Coal Handling Performance. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.1 | Drive modification of Stacker Reclaimer slewing system. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.2 | Retrofitting of Side Arm Charger-I & II at CHP U-8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.3 | Upgradation of GE/Schineder make PLC system atU-8 CHP. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.4 | Refurbishment of Apron Feeder at CHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.5 | Provision of moveable stacker and crusher in CHP coal stack yard at CHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.6 | Procurement of Loco & Bulldozer at CHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | DPR on dry fly ash utilisation improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.1 | Design, supply, erection, installation & comissioning of intermediate silo with sub system at AHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | DPR on ash handling plant improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | Design, supply, erection & comissioning of weigh bridge for silo at AHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.2 | Supply, installation & comissioning of energy efficient air compressor at AHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.3 | PROCUREMENT OF COMPLETE ASSEMBLY OF SAM MAKE AR-150/510 PUMPS (2 NOS) FOR REPLACEMENT OF ASH SLURRY PUMPS OF BOTTOM ASH SLURRY DISPOSAL FROM SLURRY TANK TO ASH BUND IN SLURRY PUMP HOUSE. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | PROCUREMENT OF COMPLETE ASSEMBLY OF SAM MAKE ZM-II 530/02 (2 NOS) FOR REPLACEMENT OF HP PUMPS OF BOTTOM ASH & COARSE ASH EVACUATION FROM BA/CA HOPPERS TO SLURRY TANK IN ASH WATER PUMP HOUSE. 0.75 0.89 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.5 | Procurement of vacuum pumps complete assembly for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.6 | Procurement of vacuum pumps complete assembly for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.7 | Procurement of Feed Gate Complete Assembly along with modified metallurgy to enhance the life of Clinker Grinder. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.8 | Procurement of Double Roll Clinker Grinder Complete Assembly with Drive Unit installed at AHP | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.9 | Procurement of Instrument Air Dryers assembly for performance improvement | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | Procurement of various types of Isolation Valves assembly, Dome Valves assembly, Root Valve Assembly & Expansion Bellows Assembly for Dry Ash Conveing performance improvement | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | DPR on ash handling plant improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | Design, supply, erection, installation & comissioning of DM water close loop cooling system for air compressors at AHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.2 | Up-gradation of Existing Schneider make PLC (HMI + PLC hardware) installed at AHP Unit -8 at Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.3 | Procurement of HT motors for AHP U-8 Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.4 | PROCUREMENT OF CRITICAL GEARBOXES AND FLUID COUPLINGS INTERNAL ASSEMBLIES FOR SLURRY PUMPS AND SILO HCSD SYSTEM INSTALLED AT AHP, PARLI TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.5 | Procurement of Atlas Copco Make Instrument Air Compressors Critical/Non-Critical Spares sub-assembly for performance improvement | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.6 | Upgradation and improvement in Hopper Temperature monitoring system by providing Rf Type Hopper Level Sensors for performance improvement of conveying of Dry ash evacuation system. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20 | DPR on ash handling plant improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.1 | Design, supply, erection, installation & comissioning ESP 1st & 2nd field dry fly ash evacuation & conveying system at AHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.2 | Design, supply, erection, installation & comissioning of dry ash evacuation & conveying system for APH & Economiser ash hoppers at AHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Verious Civil schemes in Unit 8 NPTPS Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Construction of chemical laboratory building at Unit 8, NPTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.2 | Construction of Alum/salt storage area at Unit No.8 (1X250MW) NPTPS Parli Vaijnath. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.3 | Construction of Fire Fighting station at Unit-8, NPTPS Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.4 | Construction of workshop building at Unit-8, NPTPS Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | CHP improvement scheme at 250 MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.1 | CHP improvement scheme at 250 MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0.56615 | 0.56615 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) GA | 0 | - | 0 | 0.34312 | 0.40371 | -0.060588 | 0 | 0 |  |  | 0 | -0.060588
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0.29 | 0 |  |  | 0 | 0.29
0 | C) Asset received from Project U#8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Asset Recived From Civil-U#8-Land-10101 | N.A. | - | 0 | 0.0031293 | 0 | 0.0031293 | 0 | 0 |  |  | 0 | 0.0031293
2 | Asset Recived From Civil-U#8-T.G. Building-10201 | N.A. | - | 0 | 0.010038 | 0 | 0.010038 | 0 | 0 |  |  | 0 | 0.010038
3 | Asset Recived From Civil-U#8-T.G. Building(BC)bay&control room-10201 | N.A. | - | 0 | 0.0045784 | 0 | 0.0045784 | 0 | 0 |  |  | 0 | 0.0045784
4 | Asset Recived From Civil-U#8-StructuralSteelWorks4TGBldgA2EBays-10201 | N.A. | - | 0 | 0.0013976 | 0 | 0.0013976 | 0 | 0 |  |  | 0 | 0.0013976
5 | Asset Recived From Civil-U#8-WTP Building-10201 | N.A. | - | 0 | 0.00011482 | 0 | 0.00011482 | 0 | 0 |  |  | 0 | 0.00011482
6 | Asset Recived From Civil-U#8-DG SET ROOM CUM AIR COMP. HOUSE-10201 | N.A. | - | 0 | 0.00010598 | 0 | 0.00010598 | 0 | 0 |  |  | 0 | 0.00010598
7 | Asset Recived From Civil-U#8-WTP-Raw/Fire water pump House-10233 | N.A. | - | 0 | 0.00069019 | 0 | 0.00069019 | 0 | 0 |  |  | 0 | 0.00069019
8 | Asset Recived From Civil-U#8-SERVICE BUILDING -10211 | N.A. | - | 0 | 0.00055144 | 0 | 0.00055144 | 0 | 0 |  |  | 0 | 0.00055144
9 | Asset Recived From Civil-U#8-Canteen -10233 | N.A. | - | 0 | 0.00072491 | 0 | 0.00072491 | 0 | 0 |  |  | 0 | 0.00072491
10 | Asset Recived From Civil-U#8-PARKING SHED -10233 | N.A. | - | 0 | 6.111e-06 | 0 | 6.111e-06 | 0 | 0 |  |  | 0 | 6.111e-06
11 | Asset Recived From Civil-U#8-Time Security Building -10233 | N.A. | - | 0 | 3.595e-05 | 0 | 3.595e-05 | 0 | 0 |  |  | 0 | 3.595e-05
12 | Asset Recived From Civil-U#8-Misc.Building/structure/Watchtower-10233 | N.A. | - | 0 | 0.00017243 | 0 | 0.00017243 | 0 | 0 |  |  | 0 | 0.00017243
13 | Asset Recived From Civil-U#8-Boundry compound wall Mall-10233 | N.A. | - | 0 | 0.15766 | 0 | 0.15766 | 0 | 0 |  |  | 0 | 0.15766
14 | Asset Recived From Civil-U#8-Workshop civil work-10233 | N.A. | - | 0 | 4.188e-05 | 0 | 4.188e-05 | 0 | 0 |  |  | 0 | 4.188e-05
15 | Asset Recived From Civil-U#8-Interior Work for CEC-I Office-10233 | N.A. | - | 0 | 5.6438e-05 | 0 | 5.6438e-05 | 0 | 0 |  |  | 0 | 5.6438e-05
16 | Asset Recived From Civil-U#8-WTP-Raw water reservoir -10305 | N.A. | - | 0 | 0.0012248 | 0 | 0.0012248 | 0 | 0 |  |  | 0 | 0.0012248
17 | Asset Recived From Civil-U#8-WTP-Clarifier -10305 | N.A. | - | 0 | 0.0011652 | 0 | 0.0011652 | 0 | 0 |  |  | 0 | 0.0011652
18 | Asset Recived From Civil-U#8-WTP-Clarifier Water Storage Tank-10305 | N.A. | - | 0 | 0.00019514 | 0 | 0.00019514 | 0 | 0 |  |  | 0 | 0.00019514
19 | Asset Recived From Civil-U#8-C.W. pump house & forebay-10310 | N.A. | - | 0 | 0.00052946 | 0 | 0.00052946 | 0 | 0 |  |  | 0 | 0.00052946
20 | Asset Recived From Civil-U#8-Construction of STP for Colony-10322 | N.A. | - | 0 | 0.00017966 | 0 | 0.00017966 | 0 | 0 |  |  | 0 | 0.00017966
21 | Asset Recived From Civil-U#8-Cooling Towers-10311 | N.A. | - | 0 | 0.37628 | 0 | 0.37628 | 0 | 0 |  |  | 0 | 0.37628
22 | Asset Recived From Civil-U#8-Railway sidings-10412 | N.A. | - | 0 | 0.13615 | 0 | 0.13615 | 0 | 0 |  |  | 0 | 0.13615
23 | Asset Recived From Civil-U#8-In plant Roads -10401 | N.A. | - | 0 | 0.0009103 | 0 | 0.0009103 | 0 | 0 |  |  | 0 | 0.0009103
24 | Asset Recived From Civil-U#8-Pipe Rack -10419 | N.A. | - | 0 | 0.00041823 | 0 | 0.00041823 | 0 | 0 |  |  | 0 | 0.00041823
25 | Asset Recived From Civil-U#8-Transformar yard area -10541 | N.A. | - | 0 | 0.00053169 | 0 | 0.00053169 | 0 | 0 |  |  | 0 | 0.00053169
26 | Asset Recived From Civil-U#8-BA-Boiler and Auxilary foundation-10501 | N.A. | - | 0 | 0.0061116 | 0 | 0.0061116 | 0 | 0 |  |  | 0 | 0.0061116
27 | Asset Recived From Civil-U#8-BA-FD FAN FOUNDATIONS -10501 | N.A. | - | 0 | 0.00011166 | 0 | 0.00011166 | 0 | 0 |  |  | 0 | 0.00011166
28 | Asset Recived From Civil-U#8-BA-PA FAN FOUNDATION -10501 | N.A. | - | 0 | 0.00011166 | 0 | 0.00011166 | 0 | 0 |  |  | 0 | 0.00011166
29 | Asset Recived From Civil-U#8-BA-I.D. Fan foundation -10501 | N.A. | - | 0 | 0.00022332 | 0 | 0.00022332 | 0 | 0 |  |  | 0 | 0.00022332
30 | Asset Recived From Civil-U#8-BA-MILL FOUNDATION-10501 | N.A. | - | 0 | 0.00019826 | 0 | 0.00019826 | 0 | 0 |  |  | 0 | 0.00019826
31 | Asset Recived From Civil-U#8-BA-BUNKER FOUNDATION & STRUCTURE-10515 | N.A. | - | 0 | 0.0013925 | 0 | 0.0013925 | 0 | 0 |  |  | 0 | 0.0013925
32 | Asset Recived From Civil-U#8-ESP-10501 | N.A. | - | 0 | 0.00070722 | 0 | 0.00070722 | 0 | 0 |  |  | 0 | 0.00070722
33 | Asset Recived From Civil-U#8-ESP Control Room-10501 | N.A. | - | 0 | 0.00042763 | 0 | 0.00042763 | 0 | 0 |  |  | 0 | 0.00042763
34 | Asset Recived From Civil-U#8-RCC Chimney -10501 | N.A. | - | 0 | 0.0046127 | 0 | 0.0046127 | 0 | 0 |  |  | 0 | 0.0046127
35 | Asset Recived From Civil-U#8-WTP-D.M.Plant equipment fdn. etc.-10509 | N.A. | - | 0 | 6.3898e-05 | 0 | 6.3898e-05 | 0 | 0 |  |  | 0 | 6.3898e-05
36 | Asset Recived From Civil-U#8-CHP-Wagon Tippler-10515 | N.A. | - | 0 | 0.00094041 | 0 | 0.00094041 | 0 | 0 |  |  | 0 | 0.00094041
37 | Asset Recived From Civil-U#8-CHP-Crusher House -10515 | N.A. | - | 0 | 0.00074704 | 0 | 0.00074704 | 0 | 0 |  |  | 0 | 0.00074704
38 | Asset Recived From Civil-U#8-CHP-Stacker Reclaimer -10515 | N.A. | - | 0 | 0.00028485 | 0 | 0.00028485 | 0 | 0 |  |  | 0 | 0.00028485
39 | Asset Recived From Civil-U#8-CHP-Stock Yard-10515 | N.A. | - | 0 | 0.00015851 | 0 | 0.00015851 | 0 | 0 |  |  | 0 | 0.00015851
40 | Asset Recived From Civil-U#8-CHP-ConveyorPedetals&TransferPoint-10515 | N.A. | - | 0 | 0.00055408 | 0 | 0.00055408 | 0 | 0 |  |  | 0 | 0.00055408
41 | Asset Recived From Civil-U#8-CHP-MCC ROOM -10515 | N.A. | - | 0 | 0.00026945 | 0 | 0.00026945 | 0 | 0 |  |  | 0 | 0.00026945
42 | Asset Recived From Civil-U#8-AHP-RCC Ash Silo -10501 | N.A. | - | 0 | 0.00016423 | 0 | 0.00016423 | 0 | 0 |  |  | 0 | 0.00016423
43 | Asset Recived From Civil-U#8-AHP-Staicase near Silo-10501 | N.A. | - | 0 | 1.7302e-05 | 0 | 1.7302e-05 | 0 | 0 |  |  | 0 | 1.7302e-05
44 | Asset Recived From Civil-U#8-AHP-Drain sump in Silo Area -10501 | N.A. | - | 0 | 8.551e-06 | 0 | 8.551e-06 | 0 | 0 |  |  | 0 | 8.551e-06
45 | Asset Recived From Civil-U#8-AHP-Slurry Mixing Tank Fdn.-10501 | N.A. | - | 0 | 1.6923e-05 | 0 | 1.6923e-05 | 0 | 0 |  |  | 0 | 1.6923e-05
46 | Asset Recived From Civil-U#8-AHP-HCSD PUMP HOUSE-10501 | N.A. | - | 0 | 5.8934e-05 | 0 | 5.8934e-05 | 0 | 0 |  |  | 0 | 5.8934e-05
47 | Asset Recived From Civil-U#8-AHP-Ash Slurry Pump House -10501 | N.A. | - | 0 | 0.00014947 | 0 | 0.00014947 | 0 | 0 |  |  | 0 | 0.00014947
48 | Asset Recived From Civil-U#8-AHP-Ash Slurry Sump-10501 | N.A. | - | 0 | 4.5159e-05 | 0 | 4.5159e-05 | 0 | 0 |  |  | 0 | 4.5159e-05
49 | Asset Recived From Civil-U#8-AHP-Ash Water Tank-10501 | N.A. | - | 0 | 3.422e-05 | 0 | 3.422e-05 | 0 | 0 |  |  | 0 | 3.422e-05
50 | Asset Recived From Civil-U#8-AHP-Bottom Ash Hopper-10501 | N.A. | - | 0 | 4.409e-05 | 0 | 4.409e-05 | 0 | 0 |  |  | 0 | 4.409e-05
51 | Asset Recived From Civil-U#8-AHP-Drain sump in BAH Area -10501 | N.A. | - | 0 | 8.575e-06 | 0 | 8.575e-06 | 0 | 0 |  |  | 0 | 8.575e-06
52 | Asset Recived From Civil-U#8-Ash Slurry Pipe Line AHP-Pedestals-10501 | N.A. | - | 0 | 0.00013846 | 0 | 0.00013846 | 0 | 0 |  |  | 0 | 0.00013846
53 | Asset Recived From Civil-U#8-AHP-Buffer Hopper Foundation-10501 | N.A. | - | 0 | 3.5628e-05 | 0 | 3.5628e-05 | 0 | 0 |  |  | 0 | 3.5628e-05
54 | Asset Recived From Civil-U#8-AHP-Mill reject hopper foundation-10501 | N.A. | - | 0 | 1.7814e-05 | 0 | 1.7814e-05 | 0 | 0 |  |  | 0 | 1.7814e-05
55 | Asset Recived From Civil-U#8-FHP-Fuel Oil pump house-10516 | N.A. | - | 0 | 0.00065769 | 0 | 0.00065769 | 0 | 0 |  |  | 0 | 0.00065769
56 | Asset Recived From Civil-U#8-FHP-DYKE AREA -10516 | N.A. | - | 0 | 1.9339e-05 | 0 | 1.9339e-05 | 0 | 0 |  |  | 0 | 1.9339e-05
57 | Asset Recived From Civil-U#8-Effulent Treatment Plant -10509 | N.A. | - | 0 | 0.00014135 | 0 | 0.00014135 | 0 | 0 |  |  | 0 | 0.00014135
58 | Asset Recived From Project-U#8-Boiler Pressure parts-10501 | N.A. | - | 0 | 0.06549 | 0 | 0.06549 | 0 | 0 |  |  | 0 | 0.06549
59 | Asset Recived From Project-U#8-Mandatory Spares from BHEL–Trichy | N.A. | - | 0 | 0.0074619 | 0 | 0.0074619 | 0 | 0 |  |  | 0 | 0.0074619
60 | Asset Recived From Civil-U#8-Coal mill reject trench at coal mill D&E | N.A. | - | 0 | 0.04661 | 0 | 0.04661 | 0 | 0 |  |  | 0 | 0.04661
61 | Asset Recived From Project-U#8-Canteen Equipments & kitchen Utensils | N.A. | - | 0 | 0.21888 | 0 | 0.21888 | 0 | 0 |  |  | 0 | 0.21888
62 | Asset Recived From Project-U#8-Supply & Erection of ACW system-10310 | N.A. | - | 0 | 0.00083684 | 0 | 0.00083684 | 0 | 0 |  |  | 0 | 0.00083684
63 | Asset Recived From Project-U#8-SUPPLY & ERECTION OF CCW SYSTEM-10310 | N.A. | - | 0 | 0.004856 | 0 | 0.004856 | 0 | 0 |  |  | 0 | 0.004856
64 | Asset Recived From Project-U#8-TG set & its auxilleries-HP/LPFeedWate | N.A. | - | 0 | 0.016842 | 0 | 0.016842 | 0 | 0 |  |  | 0 | 0.016842
65 | Asset Recived From Project-U#8-TG set and its auxilleries- Boilerfeed | N.A. | - | 0 | 0.018479 | 0 | 0.018479 | 0 | 0 |  |  | 0 | 0.018479
66 | Asset Recived From Project-U#8-Air Conditioning-MandatorySpares-10576 | N.A. | - | 0 | 1.7256e-05 | 0 | 1.7256e-05 | 0 | 0 |  |  | 0 | 1.7256e-05
67 | Asset Recived From Project-U#8-Air Conditioning system-10576 | N.A. | - | 0 | 0.0013446 | 0 | 0.0013446 | 0 | 0 |  |  | 0 | 0.0013446
68 | Asset Recived From Project-U#8-AHP-FLY ASH & HCSD-SYSTEM-10501 | N.A. | - | 0 | 0.0021652 | 0 | 0.0021652 | 0 | 0 |  |  | 0 | 0.0021652
69 | Asset Recived From Project-U#8-AHP-FLYASH&HCSD-SYSTEMBOUGHT OUT-10501 | N.A. | - | 0 | 0.0070969 | 0 | 0.0070969 | 0 | 0 |  |  | 0 | 0.0070969
70 | Asset Recived From Project-U#8-AHP-BOTTOM ASH SYSTEM-10501 | N.A. | - | 0 | 0.012126 | 0 | 0.012126 | 0 | 0 |  |  | 0 | 0.012126
71 | Asset Recived From Project-U#8-AHP-ELECTRICAL C & I-10501 | N.A. | - | 0 | 0.004053 | 0 | 0.004053 | 0 | 0 |  |  | 0 | 0.004053
72 | Asset Recived From Project-U#8-AHP-GEHO PUMP-10501 | N.A. | - | 0 | 0.0095128 | 0 | 0.0095128 | 0 | 0 |  |  | 0 | 0.0095128
73 | Asset Recived FromProject-U#8-Boiler&Aux -Power Cycle Piping-10501 | N.A. | - | 0 | 0.041005 | 0 | 0.041005 | 0 | 0 |  |  | 0 | 0.041005
74 | Asset Recived From Project-U#8-Boiler&Aux-SUIT BLOWER & PIPING-10501 | N.A. | - | 0 | 0.083837 | 0 | 0.083837 | 0 | 0 |  |  | 0 | 0.083837
75 | Asset Recived From Project-U#8-Boiler & Auxillaries - PA FAN-10501 | N.A. | - | 0 | 0.0010226 | 0 | 0.0010226 | 0 | 0 |  |  | 0 | 0.0010226
76 | Asset Recived From Project-U#8-Boiler&Aux-Air Preheaters-10501 | N.A. | - | 0 | 0.013281 | 0 | 0.013281 | 0 | 0 |  |  | 0 | 0.013281
77 | Asset Recived From Project-U#8-Boiler & Auxillaries -COAL MILL-10501 | N.A. | - | 0 | 0.051244 | 0 | 0.051244 | 0 | 0 |  |  | 0 | 0.051244
78 | Asset Recived From Project-U#8-Boiler & Auxillaries -FD FAN-10501 | N.A. | - | 0 | 0.0006817 | 0 | 0.0006817 | 0 | 0 |  |  | 0 | 0.0006817
79 | Asset Recived From Project-U#8-Boiler & Auxillaries- ID FAN-10501 | N.A. | - | 0 | 0.0017043 | 0 | 0.0017043 | 0 | 0 |  |  | 0 | 0.0017043
80 | Asset Recived From Project-U#8-Boiler&Aux-Mandatory Spares-10501 | N.A. | - | 0 | 0.0097935 | 0 | 0.0097935 | 0 | 0 |  |  | 0 | 0.0097935
81 | Asset Recived From Project-U#8-Boiler&Aux-PLATFORM,STAIRS,GRATINGS, | N.A. | - | 0 | 0.030596 | 0 | 0.030596 | 0 | 0 |  |  | 0 | 0.030596
82 | Asset Recived From Project-U#8-Boiler Pressure parts-10501 | N.A. | - | 0 | 0.17807 | 0 | 0.17807 | 0 | 0 |  |  | 0 | 0.17807
83 | Asset Recived From Project-U#8-220V-BATTERY+CHARGERS-MAIN PLANT-10563 | N.A. | - | 0 | 0.0020848 | 0 | 0.0020848 | 0 | 0 |  |  | 0 | 0.0020848
84 | Asset Recived From Project-U#8-220V -BATTERY WITH CHARGERS(CHP)-10563 | N.A. | - | 0 | 0.00020745 | 0 | 0.00020745 | 0 | 0 |  |  | 0 | 0.00020745
85 | Asset Recived From Project-U#8-220V-BATTERY+CHARG-WAGON TRIP-2N-10563 | N.A. | - | 0 | 8.4674e-05 | 0 | 8.4674e-05 | 0 | 0 |  |  | 0 | 8.4674e-05
86 | Asset Recived From Project-U#8-BOP-OTHER C& i INSTRUMENTS-10509 | N.A. | - | 0 | 0.0013441 | 0 | 0.0013441 | 0 | 0 |  |  | 0 | 0.0013441
87 | Asset Recived From Project-U#8-CHP-CONVEYOR SYSTEM-10515 | N.A. | - | 0 | 0.015409 | 0 | 0.015409 | 0 | 0 |  |  | 0 | 0.015409
88 | Asset Recived From Project-U#8-CHP-WOBLER FEEDER-10515 | N.A. | - | 0 | 0.00054613 | 0 | 0.00054613 | 0 | 0 |  |  | 0 | 0.00054613
89 | Asset Recived From Project-U#8-CHP-APRON FEEDER-10515 | N.A. | - | 0 | 0.0028149 | 0 | 0.0028149 | 0 | 0 |  |  | 0 | 0.0028149
90 | Asset Recived From Project-U#8-CHP-ILMS,METAL DETECTOR,BELT WEIGHER | N.A. | - | 0 | 0.0011704 | 0 | 0.0011704 | 0 | 0 |  |  | 0 | 0.0011704
91 | Asset Recived From Project-U#8-CHP-IMPACT CRUSHER-10515 | N.A. | - | 0 | 0.0020638 | 0 | 0.0020638 | 0 | 0 |  |  | 0 | 0.0020638
92 | Project-U#8-CHP-STRACKER CUM RECLAIMER-10515 | N.A. | - | 0 | 0.0082014 | 0 | 0.0082014 | 0 | 0 |  |  | 0 | 0.0082014
93 | Project-U#8-CHP-SIDE DISCHARGE TYPE WAGON TRIPPLER | N.A. | - | 0 | 0.0077836 | 0 | 0.0077836 | 0 | 0 |  |  | 0 | 0.0077836
94 | Project-U#8-Coal Handling Plant-M.S.-10515 | N.A. | - | 0 | 0.00034267 | 0 | 0.00034267 | 0 | 0 |  |  | 0 | 0.00034267
95 | Project-U#8-communication system-10572 | N.A. | - | 0 | 0.0019253 | 0 | 0.0019253 | 0 | 0 |  |  | 0 | 0.0019253
96 | Project-U#8-UPS INVERTORS-10563 | N.A. | - | 0 | 0.00051465 | 0 | 0.00051465 | 0 | 0 |  |  | 0 | 0.00051465
97 | Project-U#8-UPS ACDS-10563 | N.A. | - | 0 | 8.9956e-05 | 0 | 8.9956e-05 | 0 | 0 |  |  | 0 | 8.9956e-05
98 | Project-U#8-UPS BATTERIRERS-10563 | N.A. | - | 0 | 0.00051465 | 0 | 0.00051465 | 0 | 0 |  |  | 0 | 0.00051465
99 | Project-U#8-24V BATTERY CHARGERS (SGTG)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
100 | Project-U#8-24V BATTERY CHARGERS (BOP)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
101 | Project-U#8-BATTERIS FOR (SGTG)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
102 | Project-U#8-BATTERIS FOR (BOP)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
103 | Project-U#8-DCDB(SGTG)-10563 | N.A. | - | 0 | 5.7183e-05 | 0 | 5.7183e-05 | 0 | 0 |  |  | 0 | 5.7183e-05
104 | Project-U#8-DCDB(BOP)-10563 | N.A. | - | 0 | 5.7183e-05 | 0 | 5.7183e-05 | 0 | 0 |  |  | 0 | 5.7183e-05
105 | Project-U#8-Controls & Instru. for Main Plant(BTG) | N.A. | - | 0 | 0.044292 | 0 | 0.044292 | 0 | 0 |  |  | 0 | 0.044292
106 | Project-U#8-CW Chlorination system-10509 | N.A. | - | 0 | 0.0011974 | 0 | 0.0011974 | 0 | 0 |  |  | 0 | 0.0011974
107 | Project-U#8-D.G.SET-10509 | N.A. | - | 0 | 3.7894e-05 | 0 | 3.7894e-05 | 0 | 0 |  |  | 0 | 3.7894e-05
108 | Project-U#8-D.M.Water System-10509 | N.A. | - | 0 | 0.005785 | 0 | 0.005785 | 0 | 0 |  |  | 0 | 0.005785
109 | Project-U#8-DG set- Manadatory Spares-10509 | N.A. | - | 0 | 0.00025004 | 0 | 0.00025004 | 0 | 0 |  |  | 0 | 0.00025004
110 | Project-U#8-DG Set Room cum Air Compressor House | N.A. | - | 0 | 0.0055794 | 0 | 0.0055794 | 0 | 0 |  |  | 0 | 0.0055794
111 | Project-U#8-Steel for TechnologicalStructure-10501 | N.A. | - | 0 | 0.14836 | 0 | 0.14836 | 0 | 0 |  |  | 0 | 0.14836
112 | Project-U#8-Electrical Package for BOP-10509 | N.A. | - | 0 | 0.0024904 | 0 | 0.0024904 | 0 | 0 |  |  | 0 | 0.0024904
113 | Project-U#8-Electrical CHARGES-10509 | N.A. | - | 0 | 4.1155e-05 | 0 | 4.1155e-05 | 0 | 0 |  |  | 0 | 4.1155e-05
114 | Project-U#8-Electrical Package for BOP-Mandatory | N.A. | - | 0 | 0.0002757 | 0 | 0.0002757 | 0 | 0 |  |  | 0 | 0.0002757
115 | Project-U#8-Fire Protection, Alarm & Detection | N.A. | - | 0 | 0.0071788 | 0 | 0.0071788 | 0 | 0 |  |  | 0 | 0.0071788
116 | Project-U#8-Fuel Oil Pump House-10516 | N.A. | - | 0 | 0.0040925 | 0 | 0.0040925 | 0 | 0 |  |  | 0 | 0.0040925
117 | Project-U#8-Generator Transformer-10541 | N.A. | - | 0 | 0.012655 | 0 | 0.012655 | 0 | 0 |  |  | 0 | 0.012655
118 | Project-U#8-Generator/Transformer protection | N.A. | - | 0 | 0.00024539 | 0 | 0.00024539 | 0 | 0 |  |  | 0 | 0.00024539
119 | Project-U#8-H.T.Switchgear for main plant-10561 | N.A. | - | 0 | 0.025188 | 0 | 0.025188 | 0 | 0 |  |  | 0 | 0.025188
120 | Project-U#8-Indoor & Outdoor plant lighting-10599 | N.A. | - | 0 | 0.0004077 | 0 | 0.0004077 | 0 | 0 |  |  | 0 | 0.0004077
121 | Project-U#8-L.P.Piping including valves-10509 | N.A. | - | 0 | 0.0038246 | 0 | 0.0038246 | 0 | 0 |  |  | 0 | 0.0038246
122 | Project-U#8-L.T. Electrical for main plant.-10561 | N.A. | - | 0 | 8.7067e-05 | 0 | 8.7067e-05 | 0 | 0 |  |  | 0 | 8.7067e-05
123 | Project-U#8-Laying&Termination of HT cables-10561 | N.A. | - | 0 | 0.0008231 | 0 | 0.0008231 | 0 | 0 |  |  | 0 | 0.0008231
124 | Project-U#8-MainBoiler Structure&foundations-10501 | N.A. | - | 0 | 0.09941 | 0 | 0.09941 | 0 | 0 |  |  | 0 | 0.09941
125 | Project-U#8-Mandatory Spares for Ash HandlingPlant | N.A. | - | 0 | 0.0015616 | 0 | 0.0015616 | 0 | 0 |  |  | 0 | 0.0015616
126 | Project-U#8-Mandatory spares for C&I of Main Plant | N.A. | - | 0 | 0.0050295 | 0 | 0.0050295 | 0 | 0 |  |  | 0 | 0.0050295
127 | Project-U#8-Mandatory Spares for Electrical MainPa | N.A. | - | 0 | 0.015601 | 0 | 0.015601 | 0 | 0 |  |  | 0 | 0.015601
128 | Project-U#8-Mandatory Spares For TG & Auxilliaries | N.A. | - | 0 | 0.0062588 | 0 | 0.0062588 | 0 | 0 |  |  | 0 | 0.0062588
129 | Project-U#8-Misc. Cranes & hoists-10553 | N.A. | - | 0 | 0.0023537 | 0 | 0.0023537 | 0 | 0 |  |  | 0 | 0.0023537
130 | Project-U#8-Miscellaneous Pumps -10599 | N.A. | - | 0 | 0.0015672 | 0 | 0.0015672 | 0 | 0 |  |  | 0 | 0.0015672
131 | Project-U#8-Passanger lift for TG Building-10599 | N.A. | - | 0 | 0.0016358 | 0 | 0.0016358 | 0 | 0 |  |  | 0 | 0.0016358
132 | Project-U#8-Passanger/Material Lift at boiler side | N.A. | - | 0 | 0.00084731 | 0 | 0.00084731 | 0 | 0 |  |  | 0 | 0.00084731
133 | Project-U#8-Chemical Laboratory -10509 | N.A. | - | 0 | 0.0011648 | 0 | 0.0011648 | 0 | 0 |  |  | 0 | 0.0011648
134 | Project-U#8-Sewage Treatment Plant-10509 | N.A. | - | 0 | 0.0019006 | 0 | 0.0019006 | 0 | 0 |  |  | 0 | 0.0019006
135 | Project-U#8-Station Transformer-10541 | N.A. | - | 0 | 0.026576 | 0 | 0.026576 | 0 | 0 |  |  | 0 | 0.026576
136 | Project-U#8-Steam Turbine set-10503 | N.A. | - | 0 | 0.13864 | 0 | 0.13864 | 0 | 0 |  |  | 0 | 0.13864
137 | Project-U#8-TG set and its auxilleries- Condensor | N.A. | - | 0 | 0.012703 | 0 | 0.012703 | 0 | 0 |  |  | 0 | 0.012703
138 | Project-U#8-TG set and its auxilleries -Generator | N.A. | - | 0 | 0.032545 | 0 | 0.032545 | 0 | 0 |  |  | 0 | 0.032545
139 | Project-U#8-TG set and its auxilleries-Condensor | N.A. | - | 0 | 0.029273 | 0 | 0.029273 | 0 | 0 |  |  | 0 | 0.029273
140 | Project-U#8-TG set & its auxilleries-Derator-10503 | N.A. | - | 0 | 0.002758 | 0 | 0.002758 | 0 | 0 |  |  | 0 | 0.002758
141 | Project-U#8-TG set and its auxilleries-DMMakeUpSys | N.A. | - | 0 | 0.0010491 | 0 | 0.0010491 | 0 | 0 |  |  | 0 | 0.0010491
142 | Project-U#8-TG set and its auxilleries-Gas System | N.A. | - | 0 | 0.0056178 | 0 | 0.0056178 | 0 | 0 |  |  | 0 | 0.0056178
143 | Project-U#8-TG set and its auxilleries-GoveringSys | N.A. | - | 0 | 4.9466e-05 | 0 | 4.9466e-05 | 0 | 0 |  |  | 0 | 4.9466e-05
144 | Project-U#8-TG set and its auxilleries-HP/LP By-pa | N.A. | - | 0 | 0.010752 | 0 | 0.010752 | 0 | 0 |  |  | 0 | 0.010752
145 | Project-U#8-TG set and its auxilleries-HP/LP Dozin | N.A. | - | 0 | 0.00039941 | 0 | 0.00039941 | 0 | 0 |  |  | 0 | 0.00039941
146 | Project-U#8-TG set and its auxilleries-SealOilPump | N.A. | - | 0 | 9.8566e-05 | 0 | 9.8566e-05 | 0 | 0 |  |  | 0 | 9.8566e-05
147 | Project-U#8-TG set and its auxilleries-Vaccum Syst | N.A. | - | 0 | 0.010304 | 0 | 0.010304 | 0 | 0 |  |  | 0 | 0.010304
148 | Project-U#8-Turbine Lub. Oil System With Purifier | N.A. | - | 0 | 0.0022364 | 0 | 0.0022364 | 0 | 0 |  |  | 0 | 0.0022364
149 | Project-U#8-Ventillation system-10599 | N.A. | - | 0 | 0.0014389 | 0 | 0.0014389 | 0 | 0 |  |  | 0 | 0.0014389
150 | Asset Recived From Project-U#8-M.SPARE_Ventillation system-10599 | N.A. | - | 0 | 8.5482e-05 | 0 | 8.5482e-05 | 0 | 0 |  |  | 0 | 8.5482e-05
151 | Asset Recived From Project-U#8-Water Treatment Plant-10509 | N.A. | - | 0 | 0.0042384 | 0 | 0.0042384 | 0 | 0 |  |  | 0 | 0.0042384
152 | Asset Recived From Project-U#8-WORK SHOP MAD_SPARE-10565 | N.A. | - | 0 | 0.00030445 | 0 | 0.00030445 | 0 | 0 |  |  | 0 | 0.00030445
153 | Asset Recived From Project-U#8-Workshop-10565 | N.A. | - | 0 | 0.0013286 | 0 | 0.0013286 | 0 | 0 |  |  | 0 | 0.0013286
154 | Asset Recived From Project-U#8-CMR SYSTEM-10501 | N.A. | - | 0 | 0.0020736 | 0 | 0.0020736 | 0 | 0 |  |  | 0 | 0.0020736
155 | Asset Recived From Project-U#8-MandatorySpares-WTP-10.509 | N.A. | - | 0 | 8.1517e-05 | 0 | 8.1517e-05 | 0 | 0 |  |  | 0 | 8.1517e-05
156 | Asset Recived From Project-U#8-E.1.07_MandSpar 4 C&I MS 4MeasuringIns E.1.07_M S for C&I_ MS For Measuring Ins | N.A. | - | 0 | 0.078697 | 0 | 0.078697 | 0 | 0 |  |  | 0 | 0.078697
157 | Asset Recived From Project-U#8-BOP_ELECTRICAL-10612 | N.A. | - | 0 | 0.01637 | 0 | 0.01637 | 0 | 0 |  |  | 0 | 0.01637
158 | Asset Recived From Project-U#8-Bus Ducts-10612 | N.A. | - | 0 | 0.012548 | 0 | 0.012548 | 0 | 0 |  |  | 0 | 0.012548
159 | Asset Recived From Project-U#8-Cable trays & supports-10612 | N.A. | - | 0 | 0.00036009 | 0 | 0.00036009 | 0 | 0 |  |  | 0 | 0.00036009
160 | Project-U#8-PCR FURNITURE-10810 | N.A. | - | 0 | 0.00030684 | 0 | 0.00030684 | 0 | 0 |  |  | 0 | 0.00030684
161 | Project-U#8 Server Intel QUAD CORE 02No. HP Office Server | N.A. | - | 0 | 0.11918 | 0.11918 | 0 | 0 | 0 |  |  | 0 | 0
162 | Supply Erection testing and commissining of 1000 m3 ETP Civil works | N.A. | - | 0 | 0.68324 | 0.68324 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 146.7535 | 135.3426 | 11.4109 | 108.28 | 93.31 | 0 | 0 | 93.31 | 26.3809
FY 2025-26
0 | Add Cap (As per 296 of 2019)
A | Initial spares | Add Cap (As per 296 of 2019) | - | 0
1 | Boiler and Auxiliaries | Add Cap (As per 296 of 2019) | - | 7.2
1 | Procurement of Coal Mill XRP-903 Gear Box Type KMP-280 Spares of Unit # 8 at BM-NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 0 | 1.35 | 1.35 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply of Labyrinth Seal Rings with replaceable Inner liners for Coal Mill XRP-903 required for BM Unit-8, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.33134 | 0.33134 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply and Installation of coal mill liners(weld overlay) of XRP-903 Coal Mill in BM U-8, NPTPS,Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.33134 | 0.33134 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of Coal Mill XRP-903 Bowl & Bowl Hub of Unit # 8 at BM-NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 0 | 0.73326 | 0.73326 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply of impeller assembly for ID fan | Add Cap (As per 296 of 2019) | - | 0 | 0.5233 | 0.5233 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of Primary Air Fan & Forced Draught Fan Drive Coupling on OEM basis required at BM U-8, NPTPS, Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.1941 | 0.1941 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of Primary Air Fan PAF 17/11.8-2 Hydraulic Adjustment Device on OEM basis required at BM U-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.53521 | 0.53521 | 0 | 0 | 0 |  |  | 0 | 0
8 | Proc of spares for fabric expansion joints required at BM U-8, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.56972 | 0.56972 | 0 | 0 | 0 |  |  | 0 | 0
9 | Proc of separator body and seperator top spares for coal mill XRP-903 at BM U-8, NPTPS Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.42569 | 0.42569 | 0 | 0 | 0 |  |  | 0 | 0
10 | Proc of scrapper area & reject system spares for coal mill XRP-903 at BM U-8, NPTPS Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.27833 | 0.27833 | 0 | 0 | 0 |  |  | 0 | 0
11 | Proc of seal air fan spares at BM-8 NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.26432 | 0.26432 | 0 | 0 | 0 |  |  | 0 | 0
12 | Procurement of FD Fan Type FAF 17/9.5-1 Drive Coupling required at BM U-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | Procurement of complete planatary gear box-KMP -280/300 for coal mill XRP-903 at BM U-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Turbine and Auxiliaries | Add Cap (As per 296 of 2019) | - | 4.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of spares for Equipment Cooling Water Pumps (Make-FLOWMORE) of model FIG-5824 (SG Side) and FIG-5822 (TG side) at Unit-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.51812 | 0.51812 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply of spars for recovery & FF Pumps along with work at U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0.37713 | 0.37713 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of seal oil vacuum pump in unit 08 | Add Cap (As per 296 of 2019) | - | 0 | 0.27502 | 0.27502 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of AC pressure pipes (235MM OD, 200MM ID, 4.5M Length) for NDCT hot spray water distribution system in Unit-8 NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 0 | 0.42522 | 0.42522 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply of M/s Summits make Instrument Air Dryer & spares at U # 8 TM, Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.54787 | 0.54787 | 0 | 0 | 0 |  |  | 0 | 0
6 | Supply of PVC fills for NDCTs at U # 8 TM, Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.58245 | 0.58245 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of NB 600MM Gate valves for ACW self cleaning strainers in U#8 TM NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.42338 | 0.42338 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of Mechanical seals ( Make Leak-Proof) for various pumps in TM Unit-8 NPTPS Parli. | Add Cap (As per 296 of 2019) | - | 0 | 0.49233 | 0.49233 | 0 | 0 | 0 |  |  | 0 | 0
9 | Supply of SS 304 pipes & others at U # 8 TM, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.52905 | 0.52905 | 0 | 0 | 0 |  |  | 0 | 0
3 | Electrical and Instrumentation | Add Cap (As per 296 of 2019) | - | 6.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of Instrumentation Spares of LP Bypass System at Unit-8. | Add Cap (As per 296 of 2019) | - | 0 | 1.9615 | 1.9615 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of Schneider MICOM Numerical Relays for GRP and STPR swithcgear at NPTPS Unit-8 Testing | Add Cap (As per 296 of 2019) | - | 0 | 0.47613 | 0.47613 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of 220V DC Chloride make (formally caldyne) make battery chargers Spre of Unit 8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.23365 | 0.23365 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of 24V DC Chhabi make make battery chargers Spare of Unit 8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.22465 | 0.22465 | 0 | 0 | 0 |  |  | 0 | 0
5 | Procurement of Spare for Hitachi Hi-Rel make UPS systems installed at Unit-8 NPTPS Parli Vaijnath. | Add Cap (As per 296 of 2019) | - | 0 | 0.19186 | 0.19186 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of various test kit for testing U#8 such as energy meter calibration kit, DC earth faulth locator kit, promary current injection kit, breaker time measurement kit, numeric relay test kit and other testing instruments. | Add Cap (As per 296 of 2019) | - | 0 | 0.67345 | 0.67345 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of Energymeter Caliberation Software Module and hardware for upgrading Numeric Relay Test kit at Unit -8 Testing. | Add Cap (As per 296 of 2019) | - | 0 | 0.11863 | 0.11863 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of H T Motors. | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of critical L T Motors | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of ESP Hopper heaters (As a initial spares) Installed at EM U-8, NPTPS, Parli-Vaijnath under add cap scheme. | Add Cap (As per 296 of 2019) | - | 0 | 0.38586 | 0.38586 | 0 | 0 | 0 |  |  | 0 | 0
4 | Outdoor Plant(CHP/AHP/WTP) | Add Cap (As per 296 of 2019) | - | 6.64 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of Apron Feeder spares installed at CHP NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 1.6233 | 1.6233 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply of various drive and non drive pulleys for CHP U-8. | Add Cap (As per 296 of 2019) | - | 0 | 0.54529 | 0.54529 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply and installation of clamp pads & resting pads for Side Beam of Wagon Tippler for CHP U-8 | Add Cap (As per 296 of 2019) | - | 0 | 0.54802 | 0.54802 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply of unbalance motorozied vibrating feeder for S/R of U-7/8 CHP NPTPS Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.3958 | 0.3958 | 0 | 0 | 0 |  |  | 0 | 0
5 | Procurement of conveying and Instrument air compressor spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 1.77 | 1.77 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of vacuum pump spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0.2291 | 0.2291 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of fluidizing blower spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0.11796 | 0.11796 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of slurry pump spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of Clinker grinder spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0.12334 | 0.12334 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B | Reassessment of remaining BOP work after insolvency of M/s Sunil Hi-Tech | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Project balance E&M and procurement of mandetory spares | MERC CAPEX Approval in MTR Order 296 of 2019 | Order 296 of 2019 | 41.4534 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work order for Contract of Supply and application of Fire Stop Mortar Seal and Fire Retardant Cable Coating Compound at NPTP U-8 Parli Project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 3.4589 | 3.4589 | 0 | 0 | 0 |  |  | 0 | 0
2 | Work order for contract for Supply Installaion Testing & Commissioning Smoke Detection & alaram system | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 2.5606 | 2.5606 | 0 | 0 | 0 |  |  | 0 | 0
3 | Work order for contract for Supply Installaion Testing & Commissioning of Balance Fire Fighting System at NPTP U-8 Parli Project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.0502 | 1.0502 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, Errection, testing & commissioning works of RWP, PT potable chlorination system, ETP system control panel, automation of LDO, HFO tank foam system Hose boxes with RRL hoses and branch pipe and allied system at NPTP | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.8496 | 0.8496 | 0 | 0 | 0 |  |  | 0 | 0
5 | Work Order contract for supply, installation Testing & Commissioning of telephone exchange (EPBAX) & Telephone System at NPTP U-8 Parli project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.91256 | 0.91256 | 0 | 0 | 0 |  |  | 0 | 0
6 | Balance Supply of Electrical Lab Equipment at NPTP parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.60826 | 0.60826 | 0 | 0 | 0 |  |  | 0 | 0
7 | Work order for contract for Supply Installaion Testing & Commissioning with required material to complete Balance CHP work at NPTP U-8 Parli Project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.41 | 0.41 | 0 | 0 | 0 |  |  | 0 | 0
8 | Supply, Errection, testing & commissioning of Interconnecting Conveyor no.9 & 10 from U-8 to U-6&7 of CHP at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 5.3319 | 5.3262 | 0.0056593 | 0 | 0 |  |  | 0 | 0.0056593
9 | SUPPLY ,INSTA,TEST ,COMM ELECTRICAL SYS | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | SUPPLY,INSTAL,TEST,COMM OF CRANS&HOIST | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.8105 | 3.6223 | -1.8118 | 0 | 0 |  |  | 0 | -1.8118
11 | Supply, Errection, testing & commissioning of Dust Extraction system at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.8061 | 0 | 1.8061 | 0 | 0 |  |  | 0 | 1.8061
12 | Supply, Errection, testing & commissioning of DSS & DFDS at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 4.3391 | 4.34 | -0.0008856 | 0 | 0 |  |  | 0 | -0.0008856
13 | Supply, Errection, testing & commissioning of Monorail at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.1892 | 1.1891 | 7.77e-05 | 0 | 0 |  |  | 0 | 7.77e-05
14 | Supply, Errection, testing & commissioning of various Control & Instrumentation equipments at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.72225 | 0.72225 | 0 | 0 | 0 |  |  | 0 | 0
15 | Supply, Errection, testing & commissioning of Air Conditioning System at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.15304 | 0.44729 | -0.29425 | 0 | 0 |  |  | 0 | -0.29425
16 | Supply, Errection, testing & commissioning of Ventilation System at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 2.1136 | 1.2036 | 0.91 | 0 | 0 |  |  | 0 | 0.91
17 | Supply, Errection, testing & commissioning of Elevator works. | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 3.5173 | 4.4273 | -0.91 | 0 | 0 |  |  | 0 | -0.91
18 | Work contract for dismentaling, supply, erection & commissioning of MRHS | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 2.2335 | 2.2335 | 0 | 0 | 0 |  |  | 0 | 0
19 | Supply, Errection, testing & commissioning of FF System, Smoke detection & Fire stop mortar & Fire retradant cable coating for conveyor 09 & 10 | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.22171 | 0.51866 | -0.29696 | 0 | 0 |  |  | 0 | -0.29696
20 | Supply, Errection, testing & commissioning of Chimney Elevator | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.0608 | 0 | 1.0608 | 0 | 0 |  |  | 0 | 1.0608
21 | Supply, Errection, testing & commissioning work of GEHO Pumps. | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0 | 1.06 | -1.06 | 0 | 0 |  |  | 0 | -1.06
22 | Procurement of various Mandetory spares of BOP packages | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 5.47 | 6.54 | -1.07 | 0 | 0 |  |  | 0 | -1.07
0 | Balance civil work of BOP scope at 250 MW Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 45.3238 | 0.55712 | 16.72 | -16.1629 | 0 | 0 |  |  | 0 | -16.1629
1 | Area grading | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 6.9866 | 0.89 | 6.0966 | 0 | 0 |  |  | 0 | 6.0966
2 | CMD | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.2411 | 1.3549 | -0.11383 | 0 | 0 |  |  | 0 | -0.11383
3 | Conveyor 09, 10 & TP 06 | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 14.5605 | 12.13 | 2.4305 | 0 | 0 |  |  | 0 | 2.4305
4 | Finishing item | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 8.085 | 4.6506 | 3.4344 | 0 | 0 |  |  | 0 | 3.4344
5 | Drain & nala | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 5.0848 | 11.79 | -6.7052 | 0 | 0 |  |  | 0 | -6.7052
6 | Internal roads | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 9.7521 | 1.5 | 8.2521 | 0 | 0 |  |  | 0 | 8.2521
7 | Stacker & reclaimer | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.1627 | 0 | 1.1627 | 0 | 0 |  |  | 0 | 1.1627
0 | Other Add Cap | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Laboratory set up | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of Analytical Instruments for condition monitoring Laboratory for 1X250 MW of NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.5 | 0.49655 | 0.49655 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply of Analytical Instruments for Water Analysis Laboratory for 1X250 MW of NPTPS, Parli-V | Add Cap (As per 296 of 2019) | - | 1.23 | 0.29847 | 0.29847 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of Analytical Instruments for Environment Laboratory for 1 x 250 MW, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.39 | 0.3658 | 0.3658 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply of Analytical Instruments for Precision Laboratory for 1 x 250 MW, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply of Analytical Instruments for General Laboratory of Water Treatment Plant of 1 x 250 MW, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Supply of Corrosion Monitor/Meter, Corrosion Coupon & Coupon Rack for 1X250 MW of NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.34 | 0.34736 | 0.34736 | 0 | 0 | 0 |  |  | 0 | 0
7 | Supply of Analytical Instruments for Coal Analysis Laboratory for 1X250 MW of NPTPS, Parli-V | Add Cap (As per 296 of 2019) | - | 1.65 | 0.39444 | 0.39444 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Grade slab (WTP Area) | Add Cap (As per 296 of 2019) | - | 1 | 0.99752 | 0.99752 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Grade slab (Near AHP Building) | Add Cap (As per 296 of 2019) | - | 0.75 | 0.74556 | 0.74556 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Temporary shed for empty barrles & filled barrles | Add Cap (As per 296 of 2019) | - | 0.5 | 0.45635 | 0.45635 | 0 | 0 | 0 |  |  | 0 | 0
12 | Cabins for operators at TP. | Add Cap (As per 296 of 2019) | - | 0.2 | 0.18583 | 0.18583 | 0 | 0 | 0 |  |  | 0 | 0
13 | Compound wall for isolation of administrative building. | Add Cap (As per 296 of 2019) | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Work of providing/ fixing of internal partitions of aluminium/Nova palm/glass/wooden for Unit 8 service building & other allied builings in the premises. | Add Cap (As per 296 of 2019) | - | 0.7 | 0.67356 | 0.67356 | 0 | 0 | 0 |  |  | 0 | 0
15 | Provision of DM and softening water line interconnection from u-6,7 to u-8 & Provision of recovery of waste water from sandava pump house,NDCT. | Add Cap (As per 296 of 2019) | - | 3 | 1.0266 | 1.0266 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | Add Cap (As per 296 of 2019) | - | 0 | 1.8371 | 1.8371 | 0 | 0 | 0 |  |  | 0 | 0
16 | Hydraulic drive system modification. | Add Cap (As per 296 of 2019) | - | 2.5 | 2.4384 | 2.4384 | 0 | 0 | 0 |  |  | 0 | 0
17 | Link conveyor from Con-2 of U-6/7 to Con.-2AB of U-8. | Add Cap (As per 296 of 2019) | - | 3.7 | 4.6434 | 22.6564 | -18.0129 | 0 | 0 |  |  | 0 | -18.0129
18 | Ozone plant for Unit -8 | Add Cap (As per 296 of 2019) | - | 20 | 20.0947 | 2.1929 | 17.9018 | 0 | 0 |  |  | 0 | 17.9018
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | Water management system | Add Cap (As per 296 of 2019) | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8, 20 | Procurement & Installation of EMS system at Unit-8 NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 1 | 0.14417 | 0.14417 | 0 | 0 | 0 |  |  | 0 | 0
21 | Conveyor-5 of stacking/reclaiming belt double drive arrangement. | Add Cap (As per 296 of 2019) | - | 2 | 2.0432 | 2.0432 | 0 | 0 | 0 |  |  | 0 | 0
22 | Chemical lab building | Add Cap (As per 296 of 2019) | - | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Chemical store | Add Cap (As per 296 of 2019) | - | 2.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Lawn development around NDCT. | Add Cap (As per 296 of 2019) | - | 0.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | Tree plantation & greenery along road side. | Add Cap (As per 296 of 2019) | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | Greenery development in area between WTP & main plant. | Add Cap (As per 296 of 2019) | - | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | Construction of staff rooms & store for CHP maint.. | Add Cap (As per 296 of 2019) | - | 1 | 0.90703 | 0.90703 | 0 | 0 | 0 |  |  | 0 | 0
28 | Dsludg filteration for raw water | Add Cap (As per 296 of 2019) | - | 17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29 | PLC/UPS system upgradation | Add Cap (As per 296 of 2019) | - | 0.5 | 0.40149 | 0.40149 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | FGD at Parli Unit # 8 | MERC/CAPEX/2021-2022/0284 | 2022-06-27 | 89.24 | 4.1 | 0 | 4.1 | 0 | 0 |  |  | 0 | 4.1
22.1 | FGD at Parli Unit # 8 | MERC/CAPEX/2021-2022/0284 | 2022-06-27 | 85.2 | 95.21 | 76.2 | 19.01 | 0 | 32.66 |  |  | 32.66 | -13.65
0 | IDC | MERC/CAPEX/2021-2022/0284 | 2022-06-27 | 4.04 | 4.04 | 0 | 4.04 | 0 | 0 |  |  | 0 | 4.04
HO DPR 16 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 2.23 | 2.23 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Detailed Project Report on Boiler plant performance improvement and availability improvement schemes at Boiler Maintenance 1x250MW Unit-8 TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Procurement & Replacement of Complete Economizer Upper & Lower Bank Coil Assemblies at Unit-8, NPTPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 5.68 | 5.68 |  |  | 5.68 | 0
1.2 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 4.5 | 4.5 |  |  | 4.5 | 0
1.3 | Procurement & replacement of PA Fan PAF 17/11.8-2 and FD Fan FAF 17/9.5-1 Complete Blade set required at BM U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 5.45 | 5.45 |  |  | 5.45 | 0
1.4 | Procurement & Replacement of Coal Mill Gear Box Type KMP 280 at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 7.43 | 7.43 |  |  | 7.43 | 0
1.5 | Procurement & replacement of Bowl & Bowl Hub Assembly of Coal Mill XRP-903 required at BM U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 3.1 | 3.1 |  |  | 3.1 | 0
1.6 | Procurement of Complete Journal Assembly without Grinding roll for Coal Mill XRP-903 required at BM U-8 NPTPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 1.29 | 1.29 |  |  | 1.29 | 0
1.7 | Procurement of Hydraulic Adjustment Device for FD Fan FAF 17/9.5-1 at BM U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 1.4 | 1.4 |  |  | 1.4 | 0
1.8 | SWAS upgradation at U#8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 4.8 | 4.8 |  |  | 4.8 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement & Replacement of Complete Platen super heater coils Coil Assemblies at Unit-8, TPS Parli-V, Procurement & Replacement of Complete LTSH upper & lower bank Coil Assemblies at Unit-8, TPS Parli-V & Procurement & Replacement of Coal Mill Gear Box Type KMP 280 at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Procurement & Replacement of Complete Platen super heater coils Coil Assemblies at Unit-8, TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Procurement & Replacement of Complete LTSH upper & lower bank Coil Assemblies at Unit-8, TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Procurement & Replacement of Coal Mill Gear Box Type KMP 280 at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-8, Parli TPS Procurement & replacement of PA & FD fan rotar hub assembly at Unit-8 TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Procurement & replacement of PA & FD fan rotar hub assembly at Unit-8 TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | DPR on Refurbishment of TG Governing system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Refurbishment of TG Governing system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 25 | 25 |  |  | 25 | 0
5 | DPR on Performance improvement of Natural Draft Cooling Tower (NDCT) at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Performance improvement of Natural Draft Cooling Tower (NDCT) by replacement of PVC fills, AC cement pipes, strengthening of Hot water distribution system, replacement of beams, columns, support structures, etc. at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 25 | 25 |  |  | 25 | 0
6 | DPR on Procurement of ACW & CW pump along with mandatory spares at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | DPR on Procurement of ACW & CW pump along with mandatory spares at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 35 | 35 |  |  | 35 | 0
7 | DPR on Procurement of CEP pump and BFP Booster pump along with mandatory spares at Unit-8, PTPS, Parli V and Procurement of Energy Efficient Cartridges of Boiler Feed Pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Procurement of CEP pump and BFP Booster pump along with mandatory spares at Unit-8, PTPS, Parli | Yet to be approved | - | 0 | 0 | 0 | 0 | 30 | 30 |  |  | 30 | 0
7.2 | Procurement of Energy Efficient Cartridges of Boiler Feed Pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
8 | DPR on Procurement of turbine blades of HP, IP & LP rotor in Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.1 | DPR on Procurement of turbine blades of HP, IP & LP rotor in Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | DPR on Repair & Reconditioning of Water treatment plant at Unit-8, PTPS, Parli V and Performance improvement of centralised AC plant at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.1 | Reconditioning of Acid and Alkali Unloading and storage system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.2 | Reconditioning & repairing of WTP DM Plant regeneration system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.3 | Performance improvement of centralised AC plant by reconditioning of cooling tower, various pumps, heat exchangers, etc. at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | DPR on Procurement of Control Fluid (HPCF) pump, Lube Oil pump, Emergency Oil pump, Jacking Oil pump, Seal oil pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.1 | DPR on Procurement of Control Fluid (HPCF) pump, Lube Oil pump, Emergency Oil pump, Jacking Oil pump, Seal oil pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | DPR on Procurement of H2 cooler, BFP coolers, generator exciter cooler, Seal and Lube oil coolers at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.1 | DPR on Procurement of H2 cooler, BFP coolers, generator exciter cooler, Seal and Lube oil coolers at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Supply, installation & commissioning of 220V 2140AH,24V 830AH & 710AH, 360V 570AH Mains UPS,110V 110AH AHP PLC , 110V , 103 AH DM plant battery set for unit 8 , NPTPS Parli-V & Procurement of HT motors at U#8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.1 | Supply, installation & commissioning of 220V 2140AH,24V 830AH & 710AH, 360V 570AH Mains UPS,110V 110AH AHP PLC , 110V , 103 AH DM plant battery set for unit 8 , NPTPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.2 | Procurement of HT motors at U#8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
13 | DPR on various instrumentation & control schemes at U#8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | Upgradation of MAX-DNA DCS system at U#8 (HMI upgradation) | Yet to be approved | - | 0 | 0 | 0 | 0 | 6.81 | 6.81 |  |  | 6.81 | 0
13.2 | Upgradation of existing Pcal system with plant performance analysis diagnostic and optimization system (PADO) at Unit 8 New Parli TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 1.4 | 1.4 |  |  | 1.4 | 0
13.3 | Upgradation of coal feeder for I&C Unit8 PTPS Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.4 | Procurement of smart control positioner at I&C Unit8 PTPS Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.5 | Upgradation Electronic control drive for I&C Unit8 PTPS Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.6 | Upgradation of turbovisory & vibration monitoring system control panel. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Performance improvement by system up gradation at CHP & DPR for normalization and stabilization of coal handling plant performance at Parli TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.1 | Supply and Commissioning of Energy Efficient Evaporative Cooling System for Control Panel & Breaker room of CHP Unit-8 For PARLI TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 1.38 | 1.38 |  |  | 1.38 | 0
14.2 | Supply and commissioning of Suspended Magnets for U-8 CHP NPTPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 3.3 | 3.3 |  |  | 3.3 | 0
14.3 | Stacker-reclaimer Bucket wheel drive modification work of U- 8 CHP | Yet to be approved | - | 0 | 0 | 0 | 0 | 3.32 | 3.32 |  |  | 3.32 | 0
14.4 | Apron feeder drive modification from Hydraulic to Electro-Mechanical at CHP U-8 NPTPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 4.02 | 4.02 |  |  | 4.02 | 0
14.5 | Procurement of U-8 W/T Major spares | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.6 | Provision of Soft starter / VFD for Various conveyor | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.7 | TP-3 chute modification at U-8 CHP. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.8 | Design, supply and commissioning of solar operated lighting system in CHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.9 | Installation of CCTV survillance system alongwith all conveyors. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | DPR for maximiation of Coal Handling Plant efficiency & DPR on life enhancement of Coal Handling Plant | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | W/T control room & bunker house battery & UPS upgradation | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Refurbishment of conveyor no. 2 A/B & 6 A/B drive system of CHP U-8 TPS Parli. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Provision of Soft starter / VFD for Various conveyor | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Procurement & installation of Belt tear detection system | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.5 | Conveyor gravity takeup infrastructure strengthening work | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.6 | U-8 CHP apron feeder-I to Conveyor 1 A/B chute modification work . | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | DPR for stabiliazation of Coal Handling Performance. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.1 | Drive modification of Stacker Reclaimer slewing system. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.2 | Retrofitting of Side Arm Charger-I & II at CHP U-8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.3 | Upgradation of GE/Schineder make PLC system atU-8 CHP. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.4 | Refurbishment of Apron Feeder at CHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.5 | Provision of moveable stacker and crusher in CHP coal stack yard at CHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.6 | Procurement of Loco & Bulldozer at CHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | DPR on dry fly ash utilisation improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.1 | Design, supply, erection, installation & comissioning of intermediate silo with sub system at AHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | DPR on ash handling plant improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | Design, supply, erection & comissioning of weigh bridge for silo at AHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0.5 | 0.5 |  |  | 0.5 | 0
18.2 | Supply, installation & comissioning of energy efficient air compressor at AHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 6 | 6 |  |  | 6 | 0
18.3 | PROCUREMENT OF COMPLETE ASSEMBLY OF SAM MAKE AR-150/510 PUMPS (2 NOS) FOR REPLACEMENT OF ASH SLURRY PUMPS OF BOTTOM ASH SLURRY DISPOSAL FROM SLURRY TANK TO ASH BUND IN SLURRY PUMP HOUSE. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0.5 | 0.5 |  |  | 0.5 | 0
18.4 | PROCUREMENT OF COMPLETE ASSEMBLY OF SAM MAKE ZM-II 530/02 (2 NOS) FOR REPLACEMENT OF HP PUMPS OF BOTTOM ASH & COARSE ASH EVACUATION FROM BA/CA HOPPERS TO SLURRY TANK IN ASH WATER PUMP HOUSE. 0.75 0.89 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0.4 | 0.4 |  |  | 0.4 | 0
18.5 | Procurement of vacuum pumps complete assembly for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
18.6 | Procurement of vacuum pumps complete assembly for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
18.7 | Procurement of Feed Gate Complete Assembly along with modified metallurgy to enhance the life of Clinker Grinder. | Yet to be approved | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
18.8 | Procurement of Double Roll Clinker Grinder Complete Assembly with Drive Unit installed at AHP | Yet to be approved | - | 0 | 0 | 0 | 0 | 1.25 | 1.25 |  |  | 1.25 | 0
18.9 | Procurement of Instrument Air Dryers assembly for performance improvement | Yet to be approved | - | 0 | 0 | 0 | 0 | 0.5 | 0.5 |  |  | 0.5 | 0
18.1 | Procurement of various types of Isolation Valves assembly, Dome Valves assembly, Root Valve Assembly & Expansion Bellows Assembly for Dry Ash Conveing performance improvement | Yet to be approved | - | 0 | 0 | 0 | 0 | 3.6 | 3.6 |  |  | 3.6 | 0
19 | DPR on ash handling plant improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | Design, supply, erection, installation & comissioning of DM water close loop cooling system for air compressors at AHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.2 | Up-gradation of Existing Schneider make PLC (HMI + PLC hardware) installed at AHP Unit -8 at Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.3 | Procurement of HT motors for AHP U-8 Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.4 | PROCUREMENT OF CRITICAL GEARBOXES AND FLUID COUPLINGS INTERNAL ASSEMBLIES FOR SLURRY PUMPS AND SILO HCSD SYSTEM INSTALLED AT AHP, PARLI TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.5 | Procurement of Atlas Copco Make Instrument Air Compressors Critical/Non-Critical Spares sub-assembly for performance improvement | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.6 | Upgradation and improvement in Hopper Temperature monitoring system by providing Rf Type Hopper Level Sensors for performance improvement of conveying of Dry ash evacuation system. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20 | DPR on ash handling plant improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.1 | Design, supply, erection, installation & comissioning ESP 1st & 2nd field dry fly ash evacuation & conveying system at AHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.2 | Design, supply, erection, installation & comissioning of dry ash evacuation & conveying system for APH & Economiser ash hoppers at AHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Verious Civil schemes in Unit 8 NPTPS Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Construction of chemical laboratory building at Unit 8, NPTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 2.5 | 0 |  |  | 0 | 2.5
21.2 | Construction of Alum/salt storage area at Unit No.8 (1X250MW) NPTPS Parli Vaijnath. | Yet to be approved | - | 0 | 0 | 0 | 0 | 2.5 | 0 |  |  | 0 | 2.5
21.3 | Construction of Fire Fighting station at Unit-8, NPTPS Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 1.5 | 0 |  |  | 0 | 1.5
21.4 | Construction of workshop building at Unit-8, NPTPS Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 1.5 | 0 |  |  | 0 | 1.5
22 | CHP improvement scheme at 250 MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.1 | CHP improvement scheme at 250 MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0.56615 | 0.56615 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) GA | 0 | - | 0 | 0.34312 | 0.40371 | -0.060588 | 0.29 | 0.29 |  |  | 0.29 | -0.060588
0 | 0 | 0 | - | 0 | 0.29 | 0 | 0.29 | 0 | 0 |  |  | 0 | 0.29
0 | C) Asset received from Project U#8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Asset Recived From Civil-U#8-Land-10101 | N.A. | - | 0 | 0.0031293 | 0 | 0.0031293 | 0 | 0 |  |  | 0 | 0.0031293
2 | Asset Recived From Civil-U#8-T.G. Building-10201 | N.A. | - | 0 | 0.010038 | 0 | 0.010038 | 0 | 0 |  |  | 0 | 0.010038
3 | Asset Recived From Civil-U#8-T.G. Building(BC)bay&control room-10201 | N.A. | - | 0 | 0.0045784 | 0 | 0.0045784 | 0 | 0 |  |  | 0 | 0.0045784
4 | Asset Recived From Civil-U#8-StructuralSteelWorks4TGBldgA2EBays-10201 | N.A. | - | 0 | 0.0013976 | 0 | 0.0013976 | 0 | 0 |  |  | 0 | 0.0013976
5 | Asset Recived From Civil-U#8-WTP Building-10201 | N.A. | - | 0 | 0.00011482 | 0 | 0.00011482 | 0 | 0 |  |  | 0 | 0.00011482
6 | Asset Recived From Civil-U#8-DG SET ROOM CUM AIR COMP. HOUSE-10201 | N.A. | - | 0 | 0.00010598 | 0 | 0.00010598 | 0 | 0 |  |  | 0 | 0.00010598
7 | Asset Recived From Civil-U#8-WTP-Raw/Fire water pump House-10233 | N.A. | - | 0 | 0.00069019 | 0 | 0.00069019 | 0 | 0 |  |  | 0 | 0.00069019
8 | Asset Recived From Civil-U#8-SERVICE BUILDING -10211 | N.A. | - | 0 | 0.00055144 | 0 | 0.00055144 | 0 | 0 |  |  | 0 | 0.00055144
9 | Asset Recived From Civil-U#8-Canteen -10233 | N.A. | - | 0 | 0.00072491 | 0 | 0.00072491 | 0 | 0 |  |  | 0 | 0.00072491
10 | Asset Recived From Civil-U#8-PARKING SHED -10233 | N.A. | - | 0 | 6.111e-06 | 0 | 6.111e-06 | 0 | 0 |  |  | 0 | 6.111e-06
11 | Asset Recived From Civil-U#8-Time Security Building -10233 | N.A. | - | 0 | 3.595e-05 | 0 | 3.595e-05 | 0 | 0 |  |  | 0 | 3.595e-05
12 | Asset Recived From Civil-U#8-Misc.Building/structure/Watchtower-10233 | N.A. | - | 0 | 0.00017243 | 0 | 0.00017243 | 0 | 0 |  |  | 0 | 0.00017243
13 | Asset Recived From Civil-U#8-Boundry compound wall Mall-10233 | N.A. | - | 0 | 0.15766 | 0 | 0.15766 | 0 | 0 |  |  | 0 | 0.15766
14 | Asset Recived From Civil-U#8-Workshop civil work-10233 | N.A. | - | 0 | 4.188e-05 | 0 | 4.188e-05 | 0 | 0 |  |  | 0 | 4.188e-05
15 | Asset Recived From Civil-U#8-Interior Work for CEC-I Office-10233 | N.A. | - | 0 | 5.6438e-05 | 0 | 5.6438e-05 | 0 | 0 |  |  | 0 | 5.6438e-05
16 | Asset Recived From Civil-U#8-WTP-Raw water reservoir -10305 | N.A. | - | 0 | 0.0012248 | 0 | 0.0012248 | 0 | 0 |  |  | 0 | 0.0012248
17 | Asset Recived From Civil-U#8-WTP-Clarifier -10305 | N.A. | - | 0 | 0.0011652 | 0 | 0.0011652 | 0 | 0 |  |  | 0 | 0.0011652
18 | Asset Recived From Civil-U#8-WTP-Clarifier Water Storage Tank-10305 | N.A. | - | 0 | 0.00019514 | 0 | 0.00019514 | 0 | 0 |  |  | 0 | 0.00019514
19 | Asset Recived From Civil-U#8-C.W. pump house & forebay-10310 | N.A. | - | 0 | 0.00052946 | 0 | 0.00052946 | 0 | 0 |  |  | 0 | 0.00052946
20 | Asset Recived From Civil-U#8-Construction of STP for Colony-10322 | N.A. | - | 0 | 0.00017966 | 0 | 0.00017966 | 0 | 0 |  |  | 0 | 0.00017966
21 | Asset Recived From Civil-U#8-Cooling Towers-10311 | N.A. | - | 0 | 0.37628 | 0 | 0.37628 | 0 | 0 |  |  | 0 | 0.37628
22 | Asset Recived From Civil-U#8-Railway sidings-10412 | N.A. | - | 0 | 0.13615 | 0 | 0.13615 | 0 | 0 |  |  | 0 | 0.13615
23 | Asset Recived From Civil-U#8-In plant Roads -10401 | N.A. | - | 0 | 0.0009103 | 0 | 0.0009103 | 0 | 0 |  |  | 0 | 0.0009103
24 | Asset Recived From Civil-U#8-Pipe Rack -10419 | N.A. | - | 0 | 0.00041823 | 0 | 0.00041823 | 0 | 0 |  |  | 0 | 0.00041823
25 | Asset Recived From Civil-U#8-Transformar yard area -10541 | N.A. | - | 0 | 0.00053169 | 0 | 0.00053169 | 0 | 0 |  |  | 0 | 0.00053169
26 | Asset Recived From Civil-U#8-BA-Boiler and Auxilary foundation-10501 | N.A. | - | 0 | 0.0061116 | 0 | 0.0061116 | 0 | 0 |  |  | 0 | 0.0061116
27 | Asset Recived From Civil-U#8-BA-FD FAN FOUNDATIONS -10501 | N.A. | - | 0 | 0.00011166 | 0 | 0.00011166 | 0 | 0 |  |  | 0 | 0.00011166
28 | Asset Recived From Civil-U#8-BA-PA FAN FOUNDATION -10501 | N.A. | - | 0 | 0.00011166 | 0 | 0.00011166 | 0 | 0 |  |  | 0 | 0.00011166
29 | Asset Recived From Civil-U#8-BA-I.D. Fan foundation -10501 | N.A. | - | 0 | 0.00022332 | 0 | 0.00022332 | 0 | 0 |  |  | 0 | 0.00022332
30 | Asset Recived From Civil-U#8-BA-MILL FOUNDATION-10501 | N.A. | - | 0 | 0.00019826 | 0 | 0.00019826 | 0 | 0 |  |  | 0 | 0.00019826
31 | Asset Recived From Civil-U#8-BA-BUNKER FOUNDATION & STRUCTURE-10515 | N.A. | - | 0 | 0.0013925 | 0 | 0.0013925 | 0 | 0 |  |  | 0 | 0.0013925
32 | Asset Recived From Civil-U#8-ESP-10501 | N.A. | - | 0 | 0.00070722 | 0 | 0.00070722 | 0 | 0 |  |  | 0 | 0.00070722
33 | Asset Recived From Civil-U#8-ESP Control Room-10501 | N.A. | - | 0 | 0.00042763 | 0 | 0.00042763 | 0 | 0 |  |  | 0 | 0.00042763
34 | Asset Recived From Civil-U#8-RCC Chimney -10501 | N.A. | - | 0 | 0.0046127 | 0 | 0.0046127 | 0 | 0 |  |  | 0 | 0.0046127
35 | Asset Recived From Civil-U#8-WTP-D.M.Plant equipment fdn. etc.-10509 | N.A. | - | 0 | 6.3898e-05 | 0 | 6.3898e-05 | 0 | 0 |  |  | 0 | 6.3898e-05
36 | Asset Recived From Civil-U#8-CHP-Wagon Tippler-10515 | N.A. | - | 0 | 0.00094041 | 0 | 0.00094041 | 0 | 0 |  |  | 0 | 0.00094041
37 | Asset Recived From Civil-U#8-CHP-Crusher House -10515 | N.A. | - | 0 | 0.00074704 | 0 | 0.00074704 | 0 | 0 |  |  | 0 | 0.00074704
38 | Asset Recived From Civil-U#8-CHP-Stacker Reclaimer -10515 | N.A. | - | 0 | 0.00028485 | 0 | 0.00028485 | 0 | 0 |  |  | 0 | 0.00028485
39 | Asset Recived From Civil-U#8-CHP-Stock Yard-10515 | N.A. | - | 0 | 0.00015851 | 0 | 0.00015851 | 0 | 0 |  |  | 0 | 0.00015851
40 | Asset Recived From Civil-U#8-CHP-ConveyorPedetals&TransferPoint-10515 | N.A. | - | 0 | 0.00055408 | 0 | 0.00055408 | 0 | 0 |  |  | 0 | 0.00055408
41 | Asset Recived From Civil-U#8-CHP-MCC ROOM -10515 | N.A. | - | 0 | 0.00026945 | 0 | 0.00026945 | 0 | 0 |  |  | 0 | 0.00026945
42 | Asset Recived From Civil-U#8-AHP-RCC Ash Silo -10501 | N.A. | - | 0 | 0.00016423 | 0 | 0.00016423 | 0 | 0 |  |  | 0 | 0.00016423
43 | Asset Recived From Civil-U#8-AHP-Staicase near Silo-10501 | N.A. | - | 0 | 1.7302e-05 | 0 | 1.7302e-05 | 0 | 0 |  |  | 0 | 1.7302e-05
44 | Asset Recived From Civil-U#8-AHP-Drain sump in Silo Area -10501 | N.A. | - | 0 | 8.551e-06 | 0 | 8.551e-06 | 0 | 0 |  |  | 0 | 8.551e-06
45 | Asset Recived From Civil-U#8-AHP-Slurry Mixing Tank Fdn.-10501 | N.A. | - | 0 | 1.6923e-05 | 0 | 1.6923e-05 | 0 | 0 |  |  | 0 | 1.6923e-05
46 | Asset Recived From Civil-U#8-AHP-HCSD PUMP HOUSE-10501 | N.A. | - | 0 | 5.8934e-05 | 0 | 5.8934e-05 | 0 | 0 |  |  | 0 | 5.8934e-05
47 | Asset Recived From Civil-U#8-AHP-Ash Slurry Pump House -10501 | N.A. | - | 0 | 0.00014947 | 0 | 0.00014947 | 0 | 0 |  |  | 0 | 0.00014947
48 | Asset Recived From Civil-U#8-AHP-Ash Slurry Sump-10501 | N.A. | - | 0 | 4.5159e-05 | 0 | 4.5159e-05 | 0 | 0 |  |  | 0 | 4.5159e-05
49 | Asset Recived From Civil-U#8-AHP-Ash Water Tank-10501 | N.A. | - | 0 | 3.422e-05 | 0 | 3.422e-05 | 0 | 0 |  |  | 0 | 3.422e-05
50 | Asset Recived From Civil-U#8-AHP-Bottom Ash Hopper-10501 | N.A. | - | 0 | 4.409e-05 | 0 | 4.409e-05 | 0 | 0 |  |  | 0 | 4.409e-05
51 | Asset Recived From Civil-U#8-AHP-Drain sump in BAH Area -10501 | N.A. | - | 0 | 8.575e-06 | 0 | 8.575e-06 | 0 | 0 |  |  | 0 | 8.575e-06
52 | Asset Recived From Civil-U#8-Ash Slurry Pipe Line AHP-Pedestals-10501 | N.A. | - | 0 | 0.00013846 | 0 | 0.00013846 | 0 | 0 |  |  | 0 | 0.00013846
53 | Asset Recived From Civil-U#8-AHP-Buffer Hopper Foundation-10501 | N.A. | - | 0 | 3.5628e-05 | 0 | 3.5628e-05 | 0 | 0 |  |  | 0 | 3.5628e-05
54 | Asset Recived From Civil-U#8-AHP-Mill reject hopper foundation-10501 | N.A. | - | 0 | 1.7814e-05 | 0 | 1.7814e-05 | 0 | 0 |  |  | 0 | 1.7814e-05
55 | Asset Recived From Civil-U#8-FHP-Fuel Oil pump house-10516 | N.A. | - | 0 | 0.00065769 | 0 | 0.00065769 | 0 | 0 |  |  | 0 | 0.00065769
56 | Asset Recived From Civil-U#8-FHP-DYKE AREA -10516 | N.A. | - | 0 | 1.9339e-05 | 0 | 1.9339e-05 | 0 | 0 |  |  | 0 | 1.9339e-05
57 | Asset Recived From Civil-U#8-Effulent Treatment Plant -10509 | N.A. | - | 0 | 0.00014135 | 0 | 0.00014135 | 0 | 0 |  |  | 0 | 0.00014135
58 | Asset Recived From Project-U#8-Boiler Pressure parts-10501 | N.A. | - | 0 | 0.06549 | 0 | 0.06549 | 0 | 0 |  |  | 0 | 0.06549
59 | Asset Recived From Project-U#8-Mandatory Spares from BHEL–Trichy | N.A. | - | 0 | 0.0074619 | 0 | 0.0074619 | 0 | 0 |  |  | 0 | 0.0074619
60 | Asset Recived From Civil-U#8-Coal mill reject trench at coal mill D&E | N.A. | - | 0 | 0.04661 | 0 | 0.04661 | 0 | 0 |  |  | 0 | 0.04661
61 | Asset Recived From Project-U#8-Canteen Equipments & kitchen Utensils | N.A. | - | 0 | 0.21888 | 0 | 0.21888 | 0 | 0 |  |  | 0 | 0.21888
62 | Asset Recived From Project-U#8-Supply & Erection of ACW system-10310 | N.A. | - | 0 | 0.00083684 | 0 | 0.00083684 | 0 | 0 |  |  | 0 | 0.00083684
63 | Asset Recived From Project-U#8-SUPPLY & ERECTION OF CCW SYSTEM-10310 | N.A. | - | 0 | 0.004856 | 0 | 0.004856 | 0 | 0 |  |  | 0 | 0.004856
64 | Asset Recived From Project-U#8-TG set & its auxilleries-HP/LPFeedWate | N.A. | - | 0 | 0.016842 | 0 | 0.016842 | 0 | 0 |  |  | 0 | 0.016842
65 | Asset Recived From Project-U#8-TG set and its auxilleries- Boilerfeed | N.A. | - | 0 | 0.018479 | 0 | 0.018479 | 0 | 0 |  |  | 0 | 0.018479
66 | Asset Recived From Project-U#8-Air Conditioning-MandatorySpares-10576 | N.A. | - | 0 | 1.7256e-05 | 0 | 1.7256e-05 | 0 | 0 |  |  | 0 | 1.7256e-05
67 | Asset Recived From Project-U#8-Air Conditioning system-10576 | N.A. | - | 0 | 0.0013446 | 0 | 0.0013446 | 0 | 0 |  |  | 0 | 0.0013446
68 | Asset Recived From Project-U#8-AHP-FLY ASH & HCSD-SYSTEM-10501 | N.A. | - | 0 | 0.0021652 | 0 | 0.0021652 | 0 | 0 |  |  | 0 | 0.0021652
69 | Asset Recived From Project-U#8-AHP-FLYASH&HCSD-SYSTEMBOUGHT OUT-10501 | N.A. | - | 0 | 0.0070969 | 0 | 0.0070969 | 0 | 0 |  |  | 0 | 0.0070969
70 | Asset Recived From Project-U#8-AHP-BOTTOM ASH SYSTEM-10501 | N.A. | - | 0 | 0.012126 | 0 | 0.012126 | 0 | 0 |  |  | 0 | 0.012126
71 | Asset Recived From Project-U#8-AHP-ELECTRICAL C & I-10501 | N.A. | - | 0 | 0.004053 | 0 | 0.004053 | 0 | 0 |  |  | 0 | 0.004053
72 | Asset Recived From Project-U#8-AHP-GEHO PUMP-10501 | N.A. | - | 0 | 0.0095128 | 0 | 0.0095128 | 0 | 0 |  |  | 0 | 0.0095128
73 | Asset Recived FromProject-U#8-Boiler&Aux -Power Cycle Piping-10501 | N.A. | - | 0 | 0.041005 | 0 | 0.041005 | 0 | 0 |  |  | 0 | 0.041005
74 | Asset Recived From Project-U#8-Boiler&Aux-SUIT BLOWER & PIPING-10501 | N.A. | - | 0 | 0.083837 | 0 | 0.083837 | 0 | 0 |  |  | 0 | 0.083837
75 | Asset Recived From Project-U#8-Boiler & Auxillaries - PA FAN-10501 | N.A. | - | 0 | 0.0010226 | 0 | 0.0010226 | 0 | 0 |  |  | 0 | 0.0010226
76 | Asset Recived From Project-U#8-Boiler&Aux-Air Preheaters-10501 | N.A. | - | 0 | 0.013281 | 0 | 0.013281 | 0 | 0 |  |  | 0 | 0.013281
77 | Asset Recived From Project-U#8-Boiler & Auxillaries -COAL MILL-10501 | N.A. | - | 0 | 0.051244 | 0 | 0.051244 | 0 | 0 |  |  | 0 | 0.051244
78 | Asset Recived From Project-U#8-Boiler & Auxillaries -FD FAN-10501 | N.A. | - | 0 | 0.0006817 | 0 | 0.0006817 | 0 | 0 |  |  | 0 | 0.0006817
79 | Asset Recived From Project-U#8-Boiler & Auxillaries- ID FAN-10501 | N.A. | - | 0 | 0.0017043 | 0 | 0.0017043 | 0 | 0 |  |  | 0 | 0.0017043
80 | Asset Recived From Project-U#8-Boiler&Aux-Mandatory Spares-10501 | N.A. | - | 0 | 0.0097935 | 0 | 0.0097935 | 0 | 0 |  |  | 0 | 0.0097935
81 | Asset Recived From Project-U#8-Boiler&Aux-PLATFORM,STAIRS,GRATINGS, | N.A. | - | 0 | 0.030596 | 0 | 0.030596 | 0 | 0 |  |  | 0 | 0.030596
82 | Asset Recived From Project-U#8-Boiler Pressure parts-10501 | N.A. | - | 0 | 0.17807 | 0 | 0.17807 | 0 | 0 |  |  | 0 | 0.17807
83 | Asset Recived From Project-U#8-220V-BATTERY+CHARGERS-MAIN PLANT-10563 | N.A. | - | 0 | 0.0020848 | 0 | 0.0020848 | 0 | 0 |  |  | 0 | 0.0020848
84 | Asset Recived From Project-U#8-220V -BATTERY WITH CHARGERS(CHP)-10563 | N.A. | - | 0 | 0.00020745 | 0 | 0.00020745 | 0 | 0 |  |  | 0 | 0.00020745
85 | Asset Recived From Project-U#8-220V-BATTERY+CHARG-WAGON TRIP-2N-10563 | N.A. | - | 0 | 8.4674e-05 | 0 | 8.4674e-05 | 0 | 0 |  |  | 0 | 8.4674e-05
86 | Asset Recived From Project-U#8-BOP-OTHER C& i INSTRUMENTS-10509 | N.A. | - | 0 | 0.0013441 | 0 | 0.0013441 | 0 | 0 |  |  | 0 | 0.0013441
87 | Asset Recived From Project-U#8-CHP-CONVEYOR SYSTEM-10515 | N.A. | - | 0 | 0.015409 | 0 | 0.015409 | 0 | 0 |  |  | 0 | 0.015409
88 | Asset Recived From Project-U#8-CHP-WOBLER FEEDER-10515 | N.A. | - | 0 | 0.00054613 | 0 | 0.00054613 | 0 | 0 |  |  | 0 | 0.00054613
89 | Asset Recived From Project-U#8-CHP-APRON FEEDER-10515 | N.A. | - | 0 | 0.0028149 | 0 | 0.0028149 | 0 | 0 |  |  | 0 | 0.0028149
90 | Asset Recived From Project-U#8-CHP-ILMS,METAL DETECTOR,BELT WEIGHER | N.A. | - | 0 | 0.0011704 | 0 | 0.0011704 | 0 | 0 |  |  | 0 | 0.0011704
91 | Asset Recived From Project-U#8-CHP-IMPACT CRUSHER-10515 | N.A. | - | 0 | 0.0020638 | 0 | 0.0020638 | 0 | 0 |  |  | 0 | 0.0020638
92 | Project-U#8-CHP-STRACKER CUM RECLAIMER-10515 | N.A. | - | 0 | 0.0082014 | 0 | 0.0082014 | 0 | 0 |  |  | 0 | 0.0082014
93 | Project-U#8-CHP-SIDE DISCHARGE TYPE WAGON TRIPPLER | N.A. | - | 0 | 0.0077836 | 0 | 0.0077836 | 0 | 0 |  |  | 0 | 0.0077836
94 | Project-U#8-Coal Handling Plant-M.S.-10515 | N.A. | - | 0 | 0.00034267 | 0 | 0.00034267 | 0 | 0 |  |  | 0 | 0.00034267
95 | Project-U#8-communication system-10572 | N.A. | - | 0 | 0.0019253 | 0 | 0.0019253 | 0 | 0 |  |  | 0 | 0.0019253
96 | Project-U#8-UPS INVERTORS-10563 | N.A. | - | 0 | 0.00051465 | 0 | 0.00051465 | 0 | 0 |  |  | 0 | 0.00051465
97 | Project-U#8-UPS ACDS-10563 | N.A. | - | 0 | 8.9956e-05 | 0 | 8.9956e-05 | 0 | 0 |  |  | 0 | 8.9956e-05
98 | Project-U#8-UPS BATTERIRERS-10563 | N.A. | - | 0 | 0.00051465 | 0 | 0.00051465 | 0 | 0 |  |  | 0 | 0.00051465
99 | Project-U#8-24V BATTERY CHARGERS (SGTG)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
100 | Project-U#8-24V BATTERY CHARGERS (BOP)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
101 | Project-U#8-BATTERIS FOR (SGTG)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
102 | Project-U#8-BATTERIS FOR (BOP)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
103 | Project-U#8-DCDB(SGTG)-10563 | N.A. | - | 0 | 5.7183e-05 | 0 | 5.7183e-05 | 0 | 0 |  |  | 0 | 5.7183e-05
104 | Project-U#8-DCDB(BOP)-10563 | N.A. | - | 0 | 5.7183e-05 | 0 | 5.7183e-05 | 0 | 0 |  |  | 0 | 5.7183e-05
105 | Project-U#8-Controls & Instru. for Main Plant(BTG) | N.A. | - | 0 | 0.044292 | 0 | 0.044292 | 0 | 0 |  |  | 0 | 0.044292
106 | Project-U#8-CW Chlorination system-10509 | N.A. | - | 0 | 0.0011974 | 0 | 0.0011974 | 0 | 0 |  |  | 0 | 0.0011974
107 | Project-U#8-D.G.SET-10509 | N.A. | - | 0 | 3.7894e-05 | 0 | 3.7894e-05 | 0 | 0 |  |  | 0 | 3.7894e-05
108 | Project-U#8-D.M.Water System-10509 | N.A. | - | 0 | 0.005785 | 0 | 0.005785 | 0 | 0 |  |  | 0 | 0.005785
109 | Project-U#8-DG set- Manadatory Spares-10509 | N.A. | - | 0 | 0.00025004 | 0 | 0.00025004 | 0 | 0 |  |  | 0 | 0.00025004
110 | Project-U#8-DG Set Room cum Air Compressor House | N.A. | - | 0 | 0.0055794 | 0 | 0.0055794 | 0 | 0 |  |  | 0 | 0.0055794
111 | Project-U#8-Steel for TechnologicalStructure-10501 | N.A. | - | 0 | 0.14836 | 0 | 0.14836 | 0 | 0 |  |  | 0 | 0.14836
112 | Project-U#8-Electrical Package for BOP-10509 | N.A. | - | 0 | 0.0024904 | 0 | 0.0024904 | 0 | 0 |  |  | 0 | 0.0024904
113 | Project-U#8-Electrical CHARGES-10509 | N.A. | - | 0 | 4.1155e-05 | 0 | 4.1155e-05 | 0 | 0 |  |  | 0 | 4.1155e-05
114 | Project-U#8-Electrical Package for BOP-Mandatory | N.A. | - | 0 | 0.0002757 | 0 | 0.0002757 | 0 | 0 |  |  | 0 | 0.0002757
115 | Project-U#8-Fire Protection, Alarm & Detection | N.A. | - | 0 | 0.0071788 | 0 | 0.0071788 | 0 | 0 |  |  | 0 | 0.0071788
116 | Project-U#8-Fuel Oil Pump House-10516 | N.A. | - | 0 | 0.0040925 | 0 | 0.0040925 | 0 | 0 |  |  | 0 | 0.0040925
117 | Project-U#8-Generator Transformer-10541 | N.A. | - | 0 | 0.012655 | 0 | 0.012655 | 0 | 0 |  |  | 0 | 0.012655
118 | Project-U#8-Generator/Transformer protection | N.A. | - | 0 | 0.00024539 | 0 | 0.00024539 | 0 | 0 |  |  | 0 | 0.00024539
119 | Project-U#8-H.T.Switchgear for main plant-10561 | N.A. | - | 0 | 0.025188 | 0 | 0.025188 | 0 | 0 |  |  | 0 | 0.025188
120 | Project-U#8-Indoor & Outdoor plant lighting-10599 | N.A. | - | 0 | 0.0004077 | 0 | 0.0004077 | 0 | 0 |  |  | 0 | 0.0004077
121 | Project-U#8-L.P.Piping including valves-10509 | N.A. | - | 0 | 0.0038246 | 0 | 0.0038246 | 0 | 0 |  |  | 0 | 0.0038246
122 | Project-U#8-L.T. Electrical for main plant.-10561 | N.A. | - | 0 | 8.7067e-05 | 0 | 8.7067e-05 | 0 | 0 |  |  | 0 | 8.7067e-05
123 | Project-U#8-Laying&Termination of HT cables-10561 | N.A. | - | 0 | 0.0008231 | 0 | 0.0008231 | 0 | 0 |  |  | 0 | 0.0008231
124 | Project-U#8-MainBoiler Structure&foundations-10501 | N.A. | - | 0 | 0.09941 | 0 | 0.09941 | 0 | 0 |  |  | 0 | 0.09941
125 | Project-U#8-Mandatory Spares for Ash HandlingPlant | N.A. | - | 0 | 0.0015616 | 0 | 0.0015616 | 0 | 0 |  |  | 0 | 0.0015616
126 | Project-U#8-Mandatory spares for C&I of Main Plant | N.A. | - | 0 | 0.0050295 | 0 | 0.0050295 | 0 | 0 |  |  | 0 | 0.0050295
127 | Project-U#8-Mandatory Spares for Electrical MainPa | N.A. | - | 0 | 0.015601 | 0 | 0.015601 | 0 | 0 |  |  | 0 | 0.015601
128 | Project-U#8-Mandatory Spares For TG & Auxilliaries | N.A. | - | 0 | 0.0062588 | 0 | 0.0062588 | 0 | 0 |  |  | 0 | 0.0062588
129 | Project-U#8-Misc. Cranes & hoists-10553 | N.A. | - | 0 | 0.0023537 | 0 | 0.0023537 | 0 | 0 |  |  | 0 | 0.0023537
130 | Project-U#8-Miscellaneous Pumps -10599 | N.A. | - | 0 | 0.0015672 | 0 | 0.0015672 | 0 | 0 |  |  | 0 | 0.0015672
131 | Project-U#8-Passanger lift for TG Building-10599 | N.A. | - | 0 | 0.0016358 | 0 | 0.0016358 | 0 | 0 |  |  | 0 | 0.0016358
132 | Project-U#8-Passanger/Material Lift at boiler side | N.A. | - | 0 | 0.00084731 | 0 | 0.00084731 | 0 | 0 |  |  | 0 | 0.00084731
133 | Project-U#8-Chemical Laboratory -10509 | N.A. | - | 0 | 0.0011648 | 0 | 0.0011648 | 0 | 0 |  |  | 0 | 0.0011648
134 | Project-U#8-Sewage Treatment Plant-10509 | N.A. | - | 0 | 0.0019006 | 0 | 0.0019006 | 0 | 0 |  |  | 0 | 0.0019006
135 | Project-U#8-Station Transformer-10541 | N.A. | - | 0 | 0.026576 | 0 | 0.026576 | 0 | 0 |  |  | 0 | 0.026576
136 | Project-U#8-Steam Turbine set-10503 | N.A. | - | 0 | 0.13864 | 0 | 0.13864 | 0 | 0 |  |  | 0 | 0.13864
137 | Project-U#8-TG set and its auxilleries- Condensor | N.A. | - | 0 | 0.012703 | 0 | 0.012703 | 0 | 0 |  |  | 0 | 0.012703
138 | Project-U#8-TG set and its auxilleries -Generator | N.A. | - | 0 | 0.032545 | 0 | 0.032545 | 0 | 0 |  |  | 0 | 0.032545
139 | Project-U#8-TG set and its auxilleries-Condensor | N.A. | - | 0 | 0.029273 | 0 | 0.029273 | 0 | 0 |  |  | 0 | 0.029273
140 | Project-U#8-TG set & its auxilleries-Derator-10503 | N.A. | - | 0 | 0.002758 | 0 | 0.002758 | 0 | 0 |  |  | 0 | 0.002758
141 | Project-U#8-TG set and its auxilleries-DMMakeUpSys | N.A. | - | 0 | 0.0010491 | 0 | 0.0010491 | 0 | 0 |  |  | 0 | 0.0010491
142 | Project-U#8-TG set and its auxilleries-Gas System | N.A. | - | 0 | 0.0056178 | 0 | 0.0056178 | 0 | 0 |  |  | 0 | 0.0056178
143 | Project-U#8-TG set and its auxilleries-GoveringSys | N.A. | - | 0 | 4.9466e-05 | 0 | 4.9466e-05 | 0 | 0 |  |  | 0 | 4.9466e-05
144 | Project-U#8-TG set and its auxilleries-HP/LP By-pa | N.A. | - | 0 | 0.010752 | 0 | 0.010752 | 0 | 0 |  |  | 0 | 0.010752
145 | Project-U#8-TG set and its auxilleries-HP/LP Dozin | N.A. | - | 0 | 0.00039941 | 0 | 0.00039941 | 0 | 0 |  |  | 0 | 0.00039941
146 | Project-U#8-TG set and its auxilleries-SealOilPump | N.A. | - | 0 | 9.8566e-05 | 0 | 9.8566e-05 | 0 | 0 |  |  | 0 | 9.8566e-05
147 | Project-U#8-TG set and its auxilleries-Vaccum Syst | N.A. | - | 0 | 0.010304 | 0 | 0.010304 | 0 | 0 |  |  | 0 | 0.010304
148 | Project-U#8-Turbine Lub. Oil System With Purifier | N.A. | - | 0 | 0.0022364 | 0 | 0.0022364 | 0 | 0 |  |  | 0 | 0.0022364
149 | Project-U#8-Ventillation system-10599 | N.A. | - | 0 | 0.0014389 | 0 | 0.0014389 | 0 | 0 |  |  | 0 | 0.0014389
150 | Asset Recived From Project-U#8-M.SPARE_Ventillation system-10599 | N.A. | - | 0 | 8.5482e-05 | 0 | 8.5482e-05 | 0 | 0 |  |  | 0 | 8.5482e-05
151 | Asset Recived From Project-U#8-Water Treatment Plant-10509 | N.A. | - | 0 | 0.0042384 | 0 | 0.0042384 | 0 | 0 |  |  | 0 | 0.0042384
152 | Asset Recived From Project-U#8-WORK SHOP MAD_SPARE-10565 | N.A. | - | 0 | 0.00030445 | 0 | 0.00030445 | 0 | 0 |  |  | 0 | 0.00030445
153 | Asset Recived From Project-U#8-Workshop-10565 | N.A. | - | 0 | 0.0013286 | 0 | 0.0013286 | 0 | 0 |  |  | 0 | 0.0013286
154 | Asset Recived From Project-U#8-CMR SYSTEM-10501 | N.A. | - | 0 | 0.0020736 | 0 | 0.0020736 | 0 | 0 |  |  | 0 | 0.0020736
155 | Asset Recived From Project-U#8-MandatorySpares-WTP-10.509 | N.A. | - | 0 | 8.1517e-05 | 0 | 8.1517e-05 | 0 | 0 |  |  | 0 | 8.1517e-05
156 | Asset Recived From Project-U#8-E.1.07_MandSpar 4 C&I MS 4MeasuringIns E.1.07_M S for C&I_ MS For Measuring Ins | N.A. | - | 0 | 0.078697 | 0 | 0.078697 | 0 | 0 |  |  | 0 | 0.078697
157 | Asset Recived From Project-U#8-BOP_ELECTRICAL-10612 | N.A. | - | 0 | 0.01637 | 0 | 0.01637 | 0 | 0 |  |  | 0 | 0.01637
158 | Asset Recived From Project-U#8-Bus Ducts-10612 | N.A. | - | 0 | 0.012548 | 0 | 0.012548 | 0 | 0 |  |  | 0 | 0.012548
159 | Asset Recived From Project-U#8-Cable trays & supports-10612 | N.A. | - | 0 | 0.00036009 | 0 | 0.00036009 | 0 | 0 |  |  | 0 | 0.00036009
160 | Project-U#8-PCR FURNITURE-10810 | N.A. | - | 0 | 0.00030684 | 0 | 0.00030684 | 0 | 0 |  |  | 0 | 0.00030684
161 | Project-U#8 Server Intel QUAD CORE 02No. HP Office Server | N.A. | - | 0 | 0.11918 | 0.11918 | 0 | 0 | 0 |  |  | 0 | 0
162 | Supply Erection testing and commissining of 1000 m3 ETP Civil works | N.A. | - | 0 | 0.68324 | 0.68324 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 255.0335 | 228.6526 | 26.3809 | 214.42 | 239.08 | 0 | 0 | 239.08 | 1.7209
FY 2026-27
0 | Add Cap (As per 296 of 2019)
A | Initial spares | Add Cap (As per 296 of 2019) | - | 0
1 | Boiler and Auxiliaries | Add Cap (As per 296 of 2019) | - | 7.2
1 | Procurement of Coal Mill XRP-903 Gear Box Type KMP-280 Spares of Unit # 8 at BM-NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 0 | 1.35 | 1.35 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply of Labyrinth Seal Rings with replaceable Inner liners for Coal Mill XRP-903 required for BM Unit-8, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.33134 | 0.33134 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply and Installation of coal mill liners(weld overlay) of XRP-903 Coal Mill in BM U-8, NPTPS,Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.33134 | 0.33134 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of Coal Mill XRP-903 Bowl & Bowl Hub of Unit # 8 at BM-NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 0 | 0.73326 | 0.73326 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply of impeller assembly for ID fan | Add Cap (As per 296 of 2019) | - | 0 | 0.5233 | 0.5233 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of Primary Air Fan & Forced Draught Fan Drive Coupling on OEM basis required at BM U-8, NPTPS, Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.1941 | 0.1941 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of Primary Air Fan PAF 17/11.8-2 Hydraulic Adjustment Device on OEM basis required at BM U-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.53521 | 0.53521 | 0 | 0 | 0 |  |  | 0 | 0
8 | Proc of spares for fabric expansion joints required at BM U-8, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.56972 | 0.56972 | 0 | 0 | 0 |  |  | 0 | 0
9 | Proc of separator body and seperator top spares for coal mill XRP-903 at BM U-8, NPTPS Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.42569 | 0.42569 | 0 | 0 | 0 |  |  | 0 | 0
10 | Proc of scrapper area & reject system spares for coal mill XRP-903 at BM U-8, NPTPS Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.27833 | 0.27833 | 0 | 0 | 0 |  |  | 0 | 0
11 | Proc of seal air fan spares at BM-8 NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.26432 | 0.26432 | 0 | 0 | 0 |  |  | 0 | 0
12 | Procurement of FD Fan Type FAF 17/9.5-1 Drive Coupling required at BM U-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | Procurement of complete planatary gear box-KMP -280/300 for coal mill XRP-903 at BM U-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Turbine and Auxiliaries | Add Cap (As per 296 of 2019) | - | 4.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of spares for Equipment Cooling Water Pumps (Make-FLOWMORE) of model FIG-5824 (SG Side) and FIG-5822 (TG side) at Unit-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.51812 | 0.51812 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply of spars for recovery & FF Pumps along with work at U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0.37713 | 0.37713 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of seal oil vacuum pump in unit 08 | Add Cap (As per 296 of 2019) | - | 0 | 0.27502 | 0.27502 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of AC pressure pipes (235MM OD, 200MM ID, 4.5M Length) for NDCT hot spray water distribution system in Unit-8 NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 0 | 0.42522 | 0.42522 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply of M/s Summits make Instrument Air Dryer & spares at U # 8 TM, Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.54787 | 0.54787 | 0 | 0 | 0 |  |  | 0 | 0
6 | Supply of PVC fills for NDCTs at U # 8 TM, Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.58245 | 0.58245 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of NB 600MM Gate valves for ACW self cleaning strainers in U#8 TM NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.42338 | 0.42338 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of Mechanical seals ( Make Leak-Proof) for various pumps in TM Unit-8 NPTPS Parli. | Add Cap (As per 296 of 2019) | - | 0 | 0.49233 | 0.49233 | 0 | 0 | 0 |  |  | 0 | 0
9 | Supply of SS 304 pipes & others at U # 8 TM, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.52905 | 0.52905 | 0 | 0 | 0 |  |  | 0 | 0
3 | Electrical and Instrumentation | Add Cap (As per 296 of 2019) | - | 6.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of Instrumentation Spares of LP Bypass System at Unit-8. | Add Cap (As per 296 of 2019) | - | 0 | 1.9615 | 1.9615 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of Schneider MICOM Numerical Relays for GRP and STPR swithcgear at NPTPS Unit-8 Testing | Add Cap (As per 296 of 2019) | - | 0 | 0.47613 | 0.47613 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of 220V DC Chloride make (formally caldyne) make battery chargers Spre of Unit 8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.23365 | 0.23365 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of 24V DC Chhabi make make battery chargers Spare of Unit 8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.22465 | 0.22465 | 0 | 0 | 0 |  |  | 0 | 0
5 | Procurement of Spare for Hitachi Hi-Rel make UPS systems installed at Unit-8 NPTPS Parli Vaijnath. | Add Cap (As per 296 of 2019) | - | 0 | 0.19186 | 0.19186 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of various test kit for testing U#8 such as energy meter calibration kit, DC earth faulth locator kit, promary current injection kit, breaker time measurement kit, numeric relay test kit and other testing instruments. | Add Cap (As per 296 of 2019) | - | 0 | 0.67345 | 0.67345 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of Energymeter Caliberation Software Module and hardware for upgrading Numeric Relay Test kit at Unit -8 Testing. | Add Cap (As per 296 of 2019) | - | 0 | 0.11863 | 0.11863 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of H T Motors. | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of critical L T Motors | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of ESP Hopper heaters (As a initial spares) Installed at EM U-8, NPTPS, Parli-Vaijnath under add cap scheme. | Add Cap (As per 296 of 2019) | - | 0 | 0.38586 | 0.38586 | 0 | 0 | 0 |  |  | 0 | 0
4 | Outdoor Plant(CHP/AHP/WTP) | Add Cap (As per 296 of 2019) | - | 6.64 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of Apron Feeder spares installed at CHP NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 1.6233 | 1.6233 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply of various drive and non drive pulleys for CHP U-8. | Add Cap (As per 296 of 2019) | - | 0 | 0.54529 | 0.54529 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply and installation of clamp pads & resting pads for Side Beam of Wagon Tippler for CHP U-8 | Add Cap (As per 296 of 2019) | - | 0 | 0.54802 | 0.54802 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply of unbalance motorozied vibrating feeder for S/R of U-7/8 CHP NPTPS Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.3958 | 0.3958 | 0 | 0 | 0 |  |  | 0 | 0
5 | Procurement of conveying and Instrument air compressor spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 1.77 | 1.77 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of vacuum pump spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0.2291 | 0.2291 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of fluidizing blower spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0.11796 | 0.11796 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of slurry pump spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of Clinker grinder spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0.12334 | 0.12334 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B | Reassessment of remaining BOP work after insolvency of M/s Sunil Hi-Tech | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Project balance E&M and procurement of mandetory spares | MERC CAPEX Approval in MTR Order 296 of 2019 | Order 296 of 2019 | 41.4534 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work order for Contract of Supply and application of Fire Stop Mortar Seal and Fire Retardant Cable Coating Compound at NPTP U-8 Parli Project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 3.4589 | 3.4589 | 0 | 0 | 0 |  |  | 0 | 0
2 | Work order for contract for Supply Installaion Testing & Commissioning Smoke Detection & alaram system | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 2.5606 | 2.5606 | 0 | 0 | 0 |  |  | 0 | 0
3 | Work order for contract for Supply Installaion Testing & Commissioning of Balance Fire Fighting System at NPTP U-8 Parli Project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.0502 | 1.0502 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, Errection, testing & commissioning works of RWP, PT potable chlorination system, ETP system control panel, automation of LDO, HFO tank foam system Hose boxes with RRL hoses and branch pipe and allied system at NPTP | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.8496 | 0.8496 | 0 | 0 | 0 |  |  | 0 | 0
5 | Work Order contract for supply, installation Testing & Commissioning of telephone exchange (EPBAX) & Telephone System at NPTP U-8 Parli project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.91256 | 0.91256 | 0 | 0 | 0 |  |  | 0 | 0
6 | Balance Supply of Electrical Lab Equipment at NPTP parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.60826 | 0.60826 | 0 | 0 | 0 |  |  | 0 | 0
7 | Work order for contract for Supply Installaion Testing & Commissioning with required material to complete Balance CHP work at NPTP U-8 Parli Project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.41 | 0.41 | 0 | 0 | 0 |  |  | 0 | 0
8 | Supply, Errection, testing & commissioning of Interconnecting Conveyor no.9 & 10 from U-8 to U-6&7 of CHP at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 5.3319 | 5.3262 | 0.0056593 | 0 | 0 |  |  | 0 | 0.0056593
9 | SUPPLY ,INSTA,TEST ,COMM ELECTRICAL SYS | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | SUPPLY,INSTAL,TEST,COMM OF CRANS&HOIST | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.8105 | 3.6223 | -1.8118 | 0 | 0 |  |  | 0 | -1.8118
11 | Supply, Errection, testing & commissioning of Dust Extraction system at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.8061 | 0 | 1.8061 | 0 | 0 |  |  | 0 | 1.8061
12 | Supply, Errection, testing & commissioning of DSS & DFDS at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 4.3391 | 4.34 | -0.0008856 | 0 | 0 |  |  | 0 | -0.0008856
13 | Supply, Errection, testing & commissioning of Monorail at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.1892 | 1.1891 | 7.77e-05 | 0 | 0 |  |  | 0 | 7.77e-05
14 | Supply, Errection, testing & commissioning of various Control & Instrumentation equipments at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.72225 | 0.72225 | 0 | 0 | 0 |  |  | 0 | 0
15 | Supply, Errection, testing & commissioning of Air Conditioning System at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.15304 | 0.44729 | -0.29425 | 0 | 0 |  |  | 0 | -0.29425
16 | Supply, Errection, testing & commissioning of Ventilation System at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 2.1136 | 1.2036 | 0.91 | 0 | 0 |  |  | 0 | 0.91
17 | Supply, Errection, testing & commissioning of Elevator works. | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 3.5173 | 4.4273 | -0.91 | 0 | 0 |  |  | 0 | -0.91
18 | Work contract for dismentaling, supply, erection & commissioning of MRHS | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 2.2335 | 2.2335 | 0 | 0 | 0 |  |  | 0 | 0
19 | Supply, Errection, testing & commissioning of FF System, Smoke detection & Fire stop mortar & Fire retradant cable coating for conveyor 09 & 10 | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.22171 | 0.51866 | -0.29696 | 0 | 0 |  |  | 0 | -0.29696
20 | Supply, Errection, testing & commissioning of Chimney Elevator | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.0608 | 0 | 1.0608 | 0 | 0 |  |  | 0 | 1.0608
21 | Supply, Errection, testing & commissioning work of GEHO Pumps. | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0 | 1.06 | -1.06 | 0 | 0 |  |  | 0 | -1.06
22 | Procurement of various Mandetory spares of BOP packages | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 5.47 | 6.54 | -1.07 | 0 | 0 |  |  | 0 | -1.07
0 | Balance civil work of BOP scope at 250 MW Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 45.3238 | 0.55712 | 16.72 | -16.1629 | 0 | 0 |  |  | 0 | -16.1629
1 | Area grading | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 6.9866 | 0.89 | 6.0966 | 0 | 0 |  |  | 0 | 6.0966
2 | CMD | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.2411 | 1.3549 | -0.11383 | 0 | 0 |  |  | 0 | -0.11383
3 | Conveyor 09, 10 & TP 06 | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 14.5605 | 12.13 | 2.4305 | 0 | 0 |  |  | 0 | 2.4305
4 | Finishing item | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 8.085 | 4.6506 | 3.4344 | 0 | 0 |  |  | 0 | 3.4344
5 | Drain & nala | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 5.0848 | 11.79 | -6.7052 | 0 | 0 |  |  | 0 | -6.7052
6 | Internal roads | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 9.7521 | 1.5 | 8.2521 | 0 | 0 |  |  | 0 | 8.2521
7 | Stacker & reclaimer | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.1627 | 0 | 1.1627 | 0 | 0 |  |  | 0 | 1.1627
0 | Other Add Cap | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Laboratory set up | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of Analytical Instruments for condition monitoring Laboratory for 1X250 MW of NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.5 | 0.49655 | 0.49655 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply of Analytical Instruments for Water Analysis Laboratory for 1X250 MW of NPTPS, Parli-V | Add Cap (As per 296 of 2019) | - | 1.23 | 0.29847 | 0.29847 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of Analytical Instruments for Environment Laboratory for 1 x 250 MW, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.39 | 0.3658 | 0.3658 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply of Analytical Instruments for Precision Laboratory for 1 x 250 MW, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply of Analytical Instruments for General Laboratory of Water Treatment Plant of 1 x 250 MW, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Supply of Corrosion Monitor/Meter, Corrosion Coupon & Coupon Rack for 1X250 MW of NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.34 | 0.34736 | 0.34736 | 0 | 0 | 0 |  |  | 0 | 0
7 | Supply of Analytical Instruments for Coal Analysis Laboratory for 1X250 MW of NPTPS, Parli-V | Add Cap (As per 296 of 2019) | - | 1.65 | 0.39444 | 0.39444 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Grade slab (WTP Area) | Add Cap (As per 296 of 2019) | - | 1 | 0.99752 | 0.99752 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Grade slab (Near AHP Building) | Add Cap (As per 296 of 2019) | - | 0.75 | 0.74556 | 0.74556 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Temporary shed for empty barrles & filled barrles | Add Cap (As per 296 of 2019) | - | 0.5 | 0.45635 | 0.45635 | 0 | 0 | 0 |  |  | 0 | 0
12 | Cabins for operators at TP. | Add Cap (As per 296 of 2019) | - | 0.2 | 0.18583 | 0.18583 | 0 | 0 | 0 |  |  | 0 | 0
13 | Compound wall for isolation of administrative building. | Add Cap (As per 296 of 2019) | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Work of providing/ fixing of internal partitions of aluminium/Nova palm/glass/wooden for Unit 8 service building & other allied builings in the premises. | Add Cap (As per 296 of 2019) | - | 0.7 | 0.67356 | 0.67356 | 0 | 0 | 0 |  |  | 0 | 0
15 | Provision of DM and softening water line interconnection from u-6,7 to u-8 & Provision of recovery of waste water from sandava pump house,NDCT. | Add Cap (As per 296 of 2019) | - | 3 | 1.0266 | 1.0266 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | Add Cap (As per 296 of 2019) | - | 0 | 1.8371 | 1.8371 | 0 | 0 | 0 |  |  | 0 | 0
16 | Hydraulic drive system modification. | Add Cap (As per 296 of 2019) | - | 2.5 | 2.4384 | 2.4384 | 0 | 0 | 0 |  |  | 0 | 0
17 | Link conveyor from Con-2 of U-6/7 to Con.-2AB of U-8. | Add Cap (As per 296 of 2019) | - | 3.7 | 4.6434 | 22.6564 | -18.0129 | 0 | 0 |  |  | 0 | -18.0129
18 | Ozone plant for Unit -8 | Add Cap (As per 296 of 2019) | - | 20 | 20.0947 | 2.1929 | 17.9018 | 0 | 0 |  |  | 0 | 17.9018
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | Water management system | Add Cap (As per 296 of 2019) | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8, 20 | Procurement & Installation of EMS system at Unit-8 NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 1 | 0.14417 | 0.14417 | 0 | 0 | 0 |  |  | 0 | 0
21 | Conveyor-5 of stacking/reclaiming belt double drive arrangement. | Add Cap (As per 296 of 2019) | - | 2 | 2.0432 | 2.0432 | 0 | 0 | 0 |  |  | 0 | 0
22 | Chemical lab building | Add Cap (As per 296 of 2019) | - | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Chemical store | Add Cap (As per 296 of 2019) | - | 2.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Lawn development around NDCT. | Add Cap (As per 296 of 2019) | - | 0.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | Tree plantation & greenery along road side. | Add Cap (As per 296 of 2019) | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | Greenery development in area between WTP & main plant. | Add Cap (As per 296 of 2019) | - | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | Construction of staff rooms & store for CHP maint.. | Add Cap (As per 296 of 2019) | - | 1 | 0.90703 | 0.90703 | 0 | 0 | 0 |  |  | 0 | 0
28 | Dsludg filteration for raw water | Add Cap (As per 296 of 2019) | - | 17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29 | PLC/UPS system upgradation | Add Cap (As per 296 of 2019) | - | 0.5 | 0.40149 | 0.40149 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | FGD at Parli Unit # 8 | MERC/CAPEX/2021-2022/0284 | 2022-06-27 | 89.24 | 4.1 | 0 | 4.1 | 0 | 0 |  |  | 0 | 4.1
22.1 | FGD at Parli Unit # 8 | MERC/CAPEX/2021-2022/0284 | 2022-06-27 | 85.2 | 95.21 | 108.86 | -13.65 | 0 | 0 |  |  | 0 | -13.65
0 | IDC | MERC/CAPEX/2021-2022/0284 | 2022-06-27 | 4.04 | 4.04 | 0 | 4.04 | 0 | 0 |  |  | 0 | 4.04
HO DPR 16 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 2.23 | 2.23 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Detailed Project Report on Boiler plant performance improvement and availability improvement schemes at Boiler Maintenance 1x250MW Unit-8 TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Procurement & Replacement of Complete Economizer Upper & Lower Bank Coil Assemblies at Unit-8, NPTPS Parli-V | Yet to be approved | - | 0 | 5.68 | 5.68 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 4.5 | 4.5 | 0 | 0 | 0 |  |  | 0 | 0
1.3 | Procurement & replacement of PA Fan PAF 17/11.8-2 and FD Fan FAF 17/9.5-1 Complete Blade set required at BM U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 5.45 | 5.45 | 0 | 0 | 0 |  |  | 0 | 0
1.4 | Procurement & Replacement of Coal Mill Gear Box Type KMP 280 at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 7.43 | 7.43 | 0 | 0 | 0 |  |  | 0 | 0
1.5 | Procurement & replacement of Bowl & Bowl Hub Assembly of Coal Mill XRP-903 required at BM U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 3.1 | 3.1 | 0 | 0 | 0 |  |  | 0 | 0
1.6 | Procurement of Complete Journal Assembly without Grinding roll for Coal Mill XRP-903 required at BM U-8 NPTPS Parli-V | Yet to be approved | - | 0 | 1.29 | 1.29 | 0 | 0 | 0 |  |  | 0 | 0
1.7 | Procurement of Hydraulic Adjustment Device for FD Fan FAF 17/9.5-1 at BM U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 1.4 | 1.4 | 0 | 0 | 0 |  |  | 0 | 0
1.8 | SWAS upgradation at U#8 | Yet to be approved | - | 0 | 4.8 | 4.8 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement & Replacement of Complete Platen super heater coils Coil Assemblies at Unit-8, TPS Parli-V, Procurement & Replacement of Complete LTSH upper & lower bank Coil Assemblies at Unit-8, TPS Parli-V & Procurement & Replacement of Coal Mill Gear Box Type KMP 280 at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Procurement & Replacement of Complete Platen super heater coils Coil Assemblies at Unit-8, TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 12 | 12 |  |  | 12 | 0
2.2 | Procurement & Replacement of Complete LTSH upper & lower bank Coil Assemblies at Unit-8, TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 9.35 | 9.35 |  |  | 9.35 | 0
2.3 | Procurement & Replacement of Coal Mill Gear Box Type KMP 280 at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 7.8 | 7.8 |  |  | 7.8 | 0
3 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-8, Parli TPS Procurement & replacement of PA & FD fan rotar hub assembly at Unit-8 TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Procurement & replacement of PA & FD fan rotar hub assembly at Unit-8 TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | DPR on Refurbishment of TG Governing system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Refurbishment of TG Governing system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
5 | DPR on Performance improvement of Natural Draft Cooling Tower (NDCT) at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Performance improvement of Natural Draft Cooling Tower (NDCT) by replacement of PVC fills, AC cement pipes, strengthening of Hot water distribution system, replacement of beams, columns, support structures, etc. at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
6 | DPR on Procurement of ACW & CW pump along with mandatory spares at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | DPR on Procurement of ACW & CW pump along with mandatory spares at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 35 | 35 | 0 | 0 | 0 |  |  | 0 | 0
7 | DPR on Procurement of CEP pump and BFP Booster pump along with mandatory spares at Unit-8, PTPS, Parli V and Procurement of Energy Efficient Cartridges of Boiler Feed Pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Procurement of CEP pump and BFP Booster pump along with mandatory spares at Unit-8, PTPS, Parli | Yet to be approved | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
7.2 | Procurement of Energy Efficient Cartridges of Boiler Feed Pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
8 | DPR on Procurement of turbine blades of HP, IP & LP rotor in Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.1 | DPR on Procurement of turbine blades of HP, IP & LP rotor in Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 35 | 35 |  |  | 35 | 0
9 | DPR on Repair & Reconditioning of Water treatment plant at Unit-8, PTPS, Parli V and Performance improvement of centralised AC plant at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.1 | Reconditioning of Acid and Alkali Unloading and storage system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
9.2 | Reconditioning & repairing of WTP DM Plant regeneration system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 20 | 20 |  |  | 20 | 0
9.3 | Performance improvement of centralised AC plant by reconditioning of cooling tower, various pumps, heat exchangers, etc. at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
10 | DPR on Procurement of Control Fluid (HPCF) pump, Lube Oil pump, Emergency Oil pump, Jacking Oil pump, Seal oil pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.1 | DPR on Procurement of Control Fluid (HPCF) pump, Lube Oil pump, Emergency Oil pump, Jacking Oil pump, Seal oil pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 25 | 25 |  |  | 25 | 0
11 | DPR on Procurement of H2 cooler, BFP coolers, generator exciter cooler, Seal and Lube oil coolers at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.1 | DPR on Procurement of H2 cooler, BFP coolers, generator exciter cooler, Seal and Lube oil coolers at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Supply, installation & commissioning of 220V 2140AH,24V 830AH & 710AH, 360V 570AH Mains UPS,110V 110AH AHP PLC , 110V , 103 AH DM plant battery set for unit 8 , NPTPS Parli-V & Procurement of HT motors at U#8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.1 | Supply, installation & commissioning of 220V 2140AH,24V 830AH & 710AH, 360V 570AH Mains UPS,110V 110AH AHP PLC , 110V , 103 AH DM plant battery set for unit 8 , NPTPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.2 | Procurement of HT motors at U#8 | Yet to be approved | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
13 | DPR on various instrumentation & control schemes at U#8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | Upgradation of MAX-DNA DCS system at U#8 (HMI upgradation) | Yet to be approved | - | 0 | 6.81 | 6.81 | 0 | 0 | 0 |  |  | 0 | 0
13.2 | Upgradation of existing Pcal system with plant performance analysis diagnostic and optimization system (PADO) at Unit 8 New Parli TPS | Yet to be approved | - | 0 | 1.4 | 1.4 | 0 | 0 | 0 |  |  | 0 | 0
13.3 | Upgradation of coal feeder for I&C Unit8 PTPS Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
13.4 | Procurement of smart control positioner at I&C Unit8 PTPS Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0.95 | 0.95 |  |  | 0.95 | 0
13.5 | Upgradation Electronic control drive for I&C Unit8 PTPS Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 3.05 | 3.05 |  |  | 3.05 | 0
13.6 | Upgradation of turbovisory & vibration monitoring system control panel. | Yet to be approved | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
14 | Performance improvement by system up gradation at CHP & DPR for normalization and stabilization of coal handling plant performance at Parli TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.1 | Supply and Commissioning of Energy Efficient Evaporative Cooling System for Control Panel & Breaker room of CHP Unit-8 For PARLI TPS | Yet to be approved | - | 0 | 1.38 | 1.38 | 0 | 0 | 0 |  |  | 0 | 0
14.2 | Supply and commissioning of Suspended Magnets for U-8 CHP NPTPS | Yet to be approved | - | 0 | 3.3 | 3.3 | 0 | 0 | 0 |  |  | 0 | 0
14.3 | Stacker-reclaimer Bucket wheel drive modification work of U- 8 CHP | Yet to be approved | - | 0 | 3.32 | 3.32 | 0 | 0 | 0 |  |  | 0 | 0
14.4 | Apron feeder drive modification from Hydraulic to Electro-Mechanical at CHP U-8 NPTPS | Yet to be approved | - | 0 | 4.02 | 4.02 | 0 | 0 | 0 |  |  | 0 | 0
14.5 | Procurement of U-8 W/T Major spares | Yet to be approved | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
14.6 | Provision of Soft starter / VFD for Various conveyor | Yet to be approved | - | 0 | 0 | 0 | 0 | 8 | 8 |  |  | 8 | 0
14.7 | TP-3 chute modification at U-8 CHP. | Yet to be approved | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
14.8 | Design, supply and commissioning of solar operated lighting system in CHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 15 | 15 |  |  | 15 | 0
14.9 | Installation of CCTV survillance system alongwith all conveyors. | Yet to be approved | - | 0 | 0 | 0 | 0 | 4 | 4 |  |  | 4 | 0
15 | DPR for maximiation of Coal Handling Plant efficiency & DPR on life enhancement of Coal Handling Plant | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | W/T control room & bunker house battery & UPS upgradation | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Refurbishment of conveyor no. 2 A/B & 6 A/B drive system of CHP U-8 TPS Parli. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Provision of Soft starter / VFD for Various conveyor | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Procurement & installation of Belt tear detection system | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.5 | Conveyor gravity takeup infrastructure strengthening work | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.6 | U-8 CHP apron feeder-I to Conveyor 1 A/B chute modification work . | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | DPR for stabiliazation of Coal Handling Performance. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.1 | Drive modification of Stacker Reclaimer slewing system. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.2 | Retrofitting of Side Arm Charger-I & II at CHP U-8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.3 | Upgradation of GE/Schineder make PLC system atU-8 CHP. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.4 | Refurbishment of Apron Feeder at CHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.5 | Provision of moveable stacker and crusher in CHP coal stack yard at CHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.6 | Procurement of Loco & Bulldozer at CHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | DPR on dry fly ash utilisation improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.1 | Design, supply, erection, installation & comissioning of intermediate silo with sub system at AHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | DPR on ash handling plant improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | Design, supply, erection & comissioning of weigh bridge for silo at AHP U-8. | Yet to be approved | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
18.2 | Supply, installation & comissioning of energy efficient air compressor at AHP U-8. | Yet to be approved | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
18.3 | PROCUREMENT OF COMPLETE ASSEMBLY OF SAM MAKE AR-150/510 PUMPS (2 NOS) FOR REPLACEMENT OF ASH SLURRY PUMPS OF BOTTOM ASH SLURRY DISPOSAL FROM SLURRY TANK TO ASH BUND IN SLURRY PUMP HOUSE. | Yet to be approved | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | PROCUREMENT OF COMPLETE ASSEMBLY OF SAM MAKE ZM-II 530/02 (2 NOS) FOR REPLACEMENT OF HP PUMPS OF BOTTOM ASH & COARSE ASH EVACUATION FROM BA/CA HOPPERS TO SLURRY TANK IN ASH WATER PUMP HOUSE. 0.75 0.89 | Yet to be approved | - | 0 | 0.4 | 0.4 | 0 | 0 | 0 |  |  | 0 | 0
18.5 | Procurement of vacuum pumps complete assembly for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
18.6 | Procurement of vacuum pumps complete assembly for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
18.7 | Procurement of Feed Gate Complete Assembly along with modified metallurgy to enhance the life of Clinker Grinder. | Yet to be approved | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
18.8 | Procurement of Double Roll Clinker Grinder Complete Assembly with Drive Unit installed at AHP | Yet to be approved | - | 0 | 1.25 | 1.25 | 0 | 0 | 0 |  |  | 0 | 0
18.9 | Procurement of Instrument Air Dryers assembly for performance improvement | Yet to be approved | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | Procurement of various types of Isolation Valves assembly, Dome Valves assembly, Root Valve Assembly & Expansion Bellows Assembly for Dry Ash Conveing performance improvement | Yet to be approved | - | 0 | 3.6 | 3.6 | 0 | 0 | 0 |  |  | 0 | 0
19 | DPR on ash handling plant improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | Design, supply, erection, installation & comissioning of DM water close loop cooling system for air compressors at AHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
19.2 | Up-gradation of Existing Schneider make PLC (HMI + PLC hardware) installed at AHP Unit -8 at Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
19.3 | Procurement of HT motors for AHP U-8 Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 2.3 | 2.3 |  |  | 2.3 | 0
19.4 | PROCUREMENT OF CRITICAL GEARBOXES AND FLUID COUPLINGS INTERNAL ASSEMBLIES FOR SLURRY PUMPS AND SILO HCSD SYSTEM INSTALLED AT AHP, PARLI TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 1.2 | 1.2 |  |  | 1.2 | 0
19.5 | Procurement of Atlas Copco Make Instrument Air Compressors Critical/Non-Critical Spares sub-assembly for performance improvement | Yet to be approved | - | 0 | 0 | 0 | 0 | 6 | 6 |  |  | 6 | 0
19.6 | Upgradation and improvement in Hopper Temperature monitoring system by providing Rf Type Hopper Level Sensors for performance improvement of conveying of Dry ash evacuation system. | Yet to be approved | - | 0 | 0 | 0 | 0 | 1.2 | 1.2 |  |  | 1.2 | 0
20 | DPR on ash handling plant improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.1 | Design, supply, erection, installation & comissioning ESP 1st & 2nd field dry fly ash evacuation & conveying system at AHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.2 | Design, supply, erection, installation & comissioning of dry ash evacuation & conveying system for APH & Economiser ash hoppers at AHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Verious Civil schemes in Unit 8 NPTPS Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Construction of chemical laboratory building at Unit 8, NPTPS, Parli V. | Yet to be approved | - | 0 | 2.5 | 0 | 2.5 | 1.28 | 3.78 |  |  | 3.78 | 0
21.2 | Construction of Alum/salt storage area at Unit No.8 (1X250MW) NPTPS Parli Vaijnath. | Yet to be approved | - | 0 | 2.5 | 0 | 2.5 | 0.96 | 3.46 |  |  | 3.46 | 0
21.3 | Construction of Fire Fighting station at Unit-8, NPTPS Parli V. | Yet to be approved | - | 0 | 1.5 | 0 | 1.5 | 0.36 | 1.86 |  |  | 1.86 | 0
21.4 | Construction of workshop building at Unit-8, NPTPS Parli V. | Yet to be approved | - | 0 | 1.5 | 0 | 1.5 | 0.63 | 2.13 |  |  | 2.13 | 0
22 | CHP improvement scheme at 250 MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.1 | CHP improvement scheme at 250 MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0.56615 | 0.56615 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) GA | 0 | - | 0 | 0.63312 | 0.69371 | -0.060588 | 0.29 | 0.29 |  |  | 0.29 | -0.060588
0 | 0 | 0 | - | 0 | 0.29 | 0 | 0.29 | 0 | 0 |  |  | 0 | 0.29
0 | C) Asset received from Project U#8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Asset Recived From Civil-U#8-Land-10101 | N.A. | - | 0 | 0.0031293 | 0 | 0.0031293 | 0 | 0 |  |  | 0 | 0.0031293
2 | Asset Recived From Civil-U#8-T.G. Building-10201 | N.A. | - | 0 | 0.010038 | 0 | 0.010038 | 0 | 0 |  |  | 0 | 0.010038
3 | Asset Recived From Civil-U#8-T.G. Building(BC)bay&control room-10201 | N.A. | - | 0 | 0.0045784 | 0 | 0.0045784 | 0 | 0 |  |  | 0 | 0.0045784
4 | Asset Recived From Civil-U#8-StructuralSteelWorks4TGBldgA2EBays-10201 | N.A. | - | 0 | 0.0013976 | 0 | 0.0013976 | 0 | 0 |  |  | 0 | 0.0013976
5 | Asset Recived From Civil-U#8-WTP Building-10201 | N.A. | - | 0 | 0.00011482 | 0 | 0.00011482 | 0 | 0 |  |  | 0 | 0.00011482
6 | Asset Recived From Civil-U#8-DG SET ROOM CUM AIR COMP. HOUSE-10201 | N.A. | - | 0 | 0.00010598 | 0 | 0.00010598 | 0 | 0 |  |  | 0 | 0.00010598
7 | Asset Recived From Civil-U#8-WTP-Raw/Fire water pump House-10233 | N.A. | - | 0 | 0.00069019 | 0 | 0.00069019 | 0 | 0 |  |  | 0 | 0.00069019
8 | Asset Recived From Civil-U#8-SERVICE BUILDING -10211 | N.A. | - | 0 | 0.00055144 | 0 | 0.00055144 | 0 | 0 |  |  | 0 | 0.00055144
9 | Asset Recived From Civil-U#8-Canteen -10233 | N.A. | - | 0 | 0.00072491 | 0 | 0.00072491 | 0 | 0 |  |  | 0 | 0.00072491
10 | Asset Recived From Civil-U#8-PARKING SHED -10233 | N.A. | - | 0 | 6.111e-06 | 0 | 6.111e-06 | 0 | 0 |  |  | 0 | 6.111e-06
11 | Asset Recived From Civil-U#8-Time Security Building -10233 | N.A. | - | 0 | 3.595e-05 | 0 | 3.595e-05 | 0 | 0 |  |  | 0 | 3.595e-05
12 | Asset Recived From Civil-U#8-Misc.Building/structure/Watchtower-10233 | N.A. | - | 0 | 0.00017243 | 0 | 0.00017243 | 0 | 0 |  |  | 0 | 0.00017243
13 | Asset Recived From Civil-U#8-Boundry compound wall Mall-10233 | N.A. | - | 0 | 0.15766 | 0 | 0.15766 | 0 | 0 |  |  | 0 | 0.15766
14 | Asset Recived From Civil-U#8-Workshop civil work-10233 | N.A. | - | 0 | 4.188e-05 | 0 | 4.188e-05 | 0 | 0 |  |  | 0 | 4.188e-05
15 | Asset Recived From Civil-U#8-Interior Work for CEC-I Office-10233 | N.A. | - | 0 | 5.6438e-05 | 0 | 5.6438e-05 | 0 | 0 |  |  | 0 | 5.6438e-05
16 | Asset Recived From Civil-U#8-WTP-Raw water reservoir -10305 | N.A. | - | 0 | 0.0012248 | 0 | 0.0012248 | 0 | 0 |  |  | 0 | 0.0012248
17 | Asset Recived From Civil-U#8-WTP-Clarifier -10305 | N.A. | - | 0 | 0.0011652 | 0 | 0.0011652 | 0 | 0 |  |  | 0 | 0.0011652
18 | Asset Recived From Civil-U#8-WTP-Clarifier Water Storage Tank-10305 | N.A. | - | 0 | 0.00019514 | 0 | 0.00019514 | 0 | 0 |  |  | 0 | 0.00019514
19 | Asset Recived From Civil-U#8-C.W. pump house & forebay-10310 | N.A. | - | 0 | 0.00052946 | 0 | 0.00052946 | 0 | 0 |  |  | 0 | 0.00052946
20 | Asset Recived From Civil-U#8-Construction of STP for Colony-10322 | N.A. | - | 0 | 0.00017966 | 0 | 0.00017966 | 0 | 0 |  |  | 0 | 0.00017966
21 | Asset Recived From Civil-U#8-Cooling Towers-10311 | N.A. | - | 0 | 0.37628 | 0 | 0.37628 | 0 | 0 |  |  | 0 | 0.37628
22 | Asset Recived From Civil-U#8-Railway sidings-10412 | N.A. | - | 0 | 0.13615 | 0 | 0.13615 | 0 | 0 |  |  | 0 | 0.13615
23 | Asset Recived From Civil-U#8-In plant Roads -10401 | N.A. | - | 0 | 0.0009103 | 0 | 0.0009103 | 0 | 0 |  |  | 0 | 0.0009103
24 | Asset Recived From Civil-U#8-Pipe Rack -10419 | N.A. | - | 0 | 0.00041823 | 0 | 0.00041823 | 0 | 0 |  |  | 0 | 0.00041823
25 | Asset Recived From Civil-U#8-Transformar yard area -10541 | N.A. | - | 0 | 0.00053169 | 0 | 0.00053169 | 0 | 0 |  |  | 0 | 0.00053169
26 | Asset Recived From Civil-U#8-BA-Boiler and Auxilary foundation-10501 | N.A. | - | 0 | 0.0061116 | 0 | 0.0061116 | 0 | 0 |  |  | 0 | 0.0061116
27 | Asset Recived From Civil-U#8-BA-FD FAN FOUNDATIONS -10501 | N.A. | - | 0 | 0.00011166 | 0 | 0.00011166 | 0 | 0 |  |  | 0 | 0.00011166
28 | Asset Recived From Civil-U#8-BA-PA FAN FOUNDATION -10501 | N.A. | - | 0 | 0.00011166 | 0 | 0.00011166 | 0 | 0 |  |  | 0 | 0.00011166
29 | Asset Recived From Civil-U#8-BA-I.D. Fan foundation -10501 | N.A. | - | 0 | 0.00022332 | 0 | 0.00022332 | 0 | 0 |  |  | 0 | 0.00022332
30 | Asset Recived From Civil-U#8-BA-MILL FOUNDATION-10501 | N.A. | - | 0 | 0.00019826 | 0 | 0.00019826 | 0 | 0 |  |  | 0 | 0.00019826
31 | Asset Recived From Civil-U#8-BA-BUNKER FOUNDATION & STRUCTURE-10515 | N.A. | - | 0 | 0.0013925 | 0 | 0.0013925 | 0 | 0 |  |  | 0 | 0.0013925
32 | Asset Recived From Civil-U#8-ESP-10501 | N.A. | - | 0 | 0.00070722 | 0 | 0.00070722 | 0 | 0 |  |  | 0 | 0.00070722
33 | Asset Recived From Civil-U#8-ESP Control Room-10501 | N.A. | - | 0 | 0.00042763 | 0 | 0.00042763 | 0 | 0 |  |  | 0 | 0.00042763
34 | Asset Recived From Civil-U#8-RCC Chimney -10501 | N.A. | - | 0 | 0.0046127 | 0 | 0.0046127 | 0 | 0 |  |  | 0 | 0.0046127
35 | Asset Recived From Civil-U#8-WTP-D.M.Plant equipment fdn. etc.-10509 | N.A. | - | 0 | 6.3898e-05 | 0 | 6.3898e-05 | 0 | 0 |  |  | 0 | 6.3898e-05
36 | Asset Recived From Civil-U#8-CHP-Wagon Tippler-10515 | N.A. | - | 0 | 0.00094041 | 0 | 0.00094041 | 0 | 0 |  |  | 0 | 0.00094041
37 | Asset Recived From Civil-U#8-CHP-Crusher House -10515 | N.A. | - | 0 | 0.00074704 | 0 | 0.00074704 | 0 | 0 |  |  | 0 | 0.00074704
38 | Asset Recived From Civil-U#8-CHP-Stacker Reclaimer -10515 | N.A. | - | 0 | 0.00028485 | 0 | 0.00028485 | 0 | 0 |  |  | 0 | 0.00028485
39 | Asset Recived From Civil-U#8-CHP-Stock Yard-10515 | N.A. | - | 0 | 0.00015851 | 0 | 0.00015851 | 0 | 0 |  |  | 0 | 0.00015851
40 | Asset Recived From Civil-U#8-CHP-ConveyorPedetals&TransferPoint-10515 | N.A. | - | 0 | 0.00055408 | 0 | 0.00055408 | 0 | 0 |  |  | 0 | 0.00055408
41 | Asset Recived From Civil-U#8-CHP-MCC ROOM -10515 | N.A. | - | 0 | 0.00026945 | 0 | 0.00026945 | 0 | 0 |  |  | 0 | 0.00026945
42 | Asset Recived From Civil-U#8-AHP-RCC Ash Silo -10501 | N.A. | - | 0 | 0.00016423 | 0 | 0.00016423 | 0 | 0 |  |  | 0 | 0.00016423
43 | Asset Recived From Civil-U#8-AHP-Staicase near Silo-10501 | N.A. | - | 0 | 1.7302e-05 | 0 | 1.7302e-05 | 0 | 0 |  |  | 0 | 1.7302e-05
44 | Asset Recived From Civil-U#8-AHP-Drain sump in Silo Area -10501 | N.A. | - | 0 | 8.551e-06 | 0 | 8.551e-06 | 0 | 0 |  |  | 0 | 8.551e-06
45 | Asset Recived From Civil-U#8-AHP-Slurry Mixing Tank Fdn.-10501 | N.A. | - | 0 | 1.6923e-05 | 0 | 1.6923e-05 | 0 | 0 |  |  | 0 | 1.6923e-05
46 | Asset Recived From Civil-U#8-AHP-HCSD PUMP HOUSE-10501 | N.A. | - | 0 | 5.8934e-05 | 0 | 5.8934e-05 | 0 | 0 |  |  | 0 | 5.8934e-05
47 | Asset Recived From Civil-U#8-AHP-Ash Slurry Pump House -10501 | N.A. | - | 0 | 0.00014947 | 0 | 0.00014947 | 0 | 0 |  |  | 0 | 0.00014947
48 | Asset Recived From Civil-U#8-AHP-Ash Slurry Sump-10501 | N.A. | - | 0 | 4.5159e-05 | 0 | 4.5159e-05 | 0 | 0 |  |  | 0 | 4.5159e-05
49 | Asset Recived From Civil-U#8-AHP-Ash Water Tank-10501 | N.A. | - | 0 | 3.422e-05 | 0 | 3.422e-05 | 0 | 0 |  |  | 0 | 3.422e-05
50 | Asset Recived From Civil-U#8-AHP-Bottom Ash Hopper-10501 | N.A. | - | 0 | 4.409e-05 | 0 | 4.409e-05 | 0 | 0 |  |  | 0 | 4.409e-05
51 | Asset Recived From Civil-U#8-AHP-Drain sump in BAH Area -10501 | N.A. | - | 0 | 8.575e-06 | 0 | 8.575e-06 | 0 | 0 |  |  | 0 | 8.575e-06
52 | Asset Recived From Civil-U#8-Ash Slurry Pipe Line AHP-Pedestals-10501 | N.A. | - | 0 | 0.00013846 | 0 | 0.00013846 | 0 | 0 |  |  | 0 | 0.00013846
53 | Asset Recived From Civil-U#8-AHP-Buffer Hopper Foundation-10501 | N.A. | - | 0 | 3.5628e-05 | 0 | 3.5628e-05 | 0 | 0 |  |  | 0 | 3.5628e-05
54 | Asset Recived From Civil-U#8-AHP-Mill reject hopper foundation-10501 | N.A. | - | 0 | 1.7814e-05 | 0 | 1.7814e-05 | 0 | 0 |  |  | 0 | 1.7814e-05
55 | Asset Recived From Civil-U#8-FHP-Fuel Oil pump house-10516 | N.A. | - | 0 | 0.00065769 | 0 | 0.00065769 | 0 | 0 |  |  | 0 | 0.00065769
56 | Asset Recived From Civil-U#8-FHP-DYKE AREA -10516 | N.A. | - | 0 | 1.9339e-05 | 0 | 1.9339e-05 | 0 | 0 |  |  | 0 | 1.9339e-05
57 | Asset Recived From Civil-U#8-Effulent Treatment Plant -10509 | N.A. | - | 0 | 0.00014135 | 0 | 0.00014135 | 0 | 0 |  |  | 0 | 0.00014135
58 | Asset Recived From Project-U#8-Boiler Pressure parts-10501 | N.A. | - | 0 | 0.06549 | 0 | 0.06549 | 0 | 0 |  |  | 0 | 0.06549
59 | Asset Recived From Project-U#8-Mandatory Spares from BHEL–Trichy | N.A. | - | 0 | 0.0074619 | 0 | 0.0074619 | 0 | 0 |  |  | 0 | 0.0074619
60 | Asset Recived From Civil-U#8-Coal mill reject trench at coal mill D&E | N.A. | - | 0 | 0.04661 | 0 | 0.04661 | 0 | 0 |  |  | 0 | 0.04661
61 | Asset Recived From Project-U#8-Canteen Equipments & kitchen Utensils | N.A. | - | 0 | 0.21888 | 0 | 0.21888 | 0 | 0 |  |  | 0 | 0.21888
62 | Asset Recived From Project-U#8-Supply & Erection of ACW system-10310 | N.A. | - | 0 | 0.00083684 | 0 | 0.00083684 | 0 | 0 |  |  | 0 | 0.00083684
63 | Asset Recived From Project-U#8-SUPPLY & ERECTION OF CCW SYSTEM-10310 | N.A. | - | 0 | 0.004856 | 0 | 0.004856 | 0 | 0 |  |  | 0 | 0.004856
64 | Asset Recived From Project-U#8-TG set & its auxilleries-HP/LPFeedWate | N.A. | - | 0 | 0.016842 | 0 | 0.016842 | 0 | 0 |  |  | 0 | 0.016842
65 | Asset Recived From Project-U#8-TG set and its auxilleries- Boilerfeed | N.A. | - | 0 | 0.018479 | 0 | 0.018479 | 0 | 0 |  |  | 0 | 0.018479
66 | Asset Recived From Project-U#8-Air Conditioning-MandatorySpares-10576 | N.A. | - | 0 | 1.7256e-05 | 0 | 1.7256e-05 | 0 | 0 |  |  | 0 | 1.7256e-05
67 | Asset Recived From Project-U#8-Air Conditioning system-10576 | N.A. | - | 0 | 0.0013446 | 0 | 0.0013446 | 0 | 0 |  |  | 0 | 0.0013446
68 | Asset Recived From Project-U#8-AHP-FLY ASH & HCSD-SYSTEM-10501 | N.A. | - | 0 | 0.0021652 | 0 | 0.0021652 | 0 | 0 |  |  | 0 | 0.0021652
69 | Asset Recived From Project-U#8-AHP-FLYASH&HCSD-SYSTEMBOUGHT OUT-10501 | N.A. | - | 0 | 0.0070969 | 0 | 0.0070969 | 0 | 0 |  |  | 0 | 0.0070969
70 | Asset Recived From Project-U#8-AHP-BOTTOM ASH SYSTEM-10501 | N.A. | - | 0 | 0.012126 | 0 | 0.012126 | 0 | 0 |  |  | 0 | 0.012126
71 | Asset Recived From Project-U#8-AHP-ELECTRICAL C & I-10501 | N.A. | - | 0 | 0.004053 | 0 | 0.004053 | 0 | 0 |  |  | 0 | 0.004053
72 | Asset Recived From Project-U#8-AHP-GEHO PUMP-10501 | N.A. | - | 0 | 0.0095128 | 0 | 0.0095128 | 0 | 0 |  |  | 0 | 0.0095128
73 | Asset Recived FromProject-U#8-Boiler&Aux -Power Cycle Piping-10501 | N.A. | - | 0 | 0.041005 | 0 | 0.041005 | 0 | 0 |  |  | 0 | 0.041005
74 | Asset Recived From Project-U#8-Boiler&Aux-SUIT BLOWER & PIPING-10501 | N.A. | - | 0 | 0.083837 | 0 | 0.083837 | 0 | 0 |  |  | 0 | 0.083837
75 | Asset Recived From Project-U#8-Boiler & Auxillaries - PA FAN-10501 | N.A. | - | 0 | 0.0010226 | 0 | 0.0010226 | 0 | 0 |  |  | 0 | 0.0010226
76 | Asset Recived From Project-U#8-Boiler&Aux-Air Preheaters-10501 | N.A. | - | 0 | 0.013281 | 0 | 0.013281 | 0 | 0 |  |  | 0 | 0.013281
77 | Asset Recived From Project-U#8-Boiler & Auxillaries -COAL MILL-10501 | N.A. | - | 0 | 0.051244 | 0 | 0.051244 | 0 | 0 |  |  | 0 | 0.051244
78 | Asset Recived From Project-U#8-Boiler & Auxillaries -FD FAN-10501 | N.A. | - | 0 | 0.0006817 | 0 | 0.0006817 | 0 | 0 |  |  | 0 | 0.0006817
79 | Asset Recived From Project-U#8-Boiler & Auxillaries- ID FAN-10501 | N.A. | - | 0 | 0.0017043 | 0 | 0.0017043 | 0 | 0 |  |  | 0 | 0.0017043
80 | Asset Recived From Project-U#8-Boiler&Aux-Mandatory Spares-10501 | N.A. | - | 0 | 0.0097935 | 0 | 0.0097935 | 0 | 0 |  |  | 0 | 0.0097935
81 | Asset Recived From Project-U#8-Boiler&Aux-PLATFORM,STAIRS,GRATINGS, | N.A. | - | 0 | 0.030596 | 0 | 0.030596 | 0 | 0 |  |  | 0 | 0.030596
82 | Asset Recived From Project-U#8-Boiler Pressure parts-10501 | N.A. | - | 0 | 0.17807 | 0 | 0.17807 | 0 | 0 |  |  | 0 | 0.17807
83 | Asset Recived From Project-U#8-220V-BATTERY+CHARGERS-MAIN PLANT-10563 | N.A. | - | 0 | 0.0020848 | 0 | 0.0020848 | 0 | 0 |  |  | 0 | 0.0020848
84 | Asset Recived From Project-U#8-220V -BATTERY WITH CHARGERS(CHP)-10563 | N.A. | - | 0 | 0.00020745 | 0 | 0.00020745 | 0 | 0 |  |  | 0 | 0.00020745
85 | Asset Recived From Project-U#8-220V-BATTERY+CHARG-WAGON TRIP-2N-10563 | N.A. | - | 0 | 8.4674e-05 | 0 | 8.4674e-05 | 0 | 0 |  |  | 0 | 8.4674e-05
86 | Asset Recived From Project-U#8-BOP-OTHER C& i INSTRUMENTS-10509 | N.A. | - | 0 | 0.0013441 | 0 | 0.0013441 | 0 | 0 |  |  | 0 | 0.0013441
87 | Asset Recived From Project-U#8-CHP-CONVEYOR SYSTEM-10515 | N.A. | - | 0 | 0.015409 | 0 | 0.015409 | 0 | 0 |  |  | 0 | 0.015409
88 | Asset Recived From Project-U#8-CHP-WOBLER FEEDER-10515 | N.A. | - | 0 | 0.00054613 | 0 | 0.00054613 | 0 | 0 |  |  | 0 | 0.00054613
89 | Asset Recived From Project-U#8-CHP-APRON FEEDER-10515 | N.A. | - | 0 | 0.0028149 | 0 | 0.0028149 | 0 | 0 |  |  | 0 | 0.0028149
90 | Asset Recived From Project-U#8-CHP-ILMS,METAL DETECTOR,BELT WEIGHER | N.A. | - | 0 | 0.0011704 | 0 | 0.0011704 | 0 | 0 |  |  | 0 | 0.0011704
91 | Asset Recived From Project-U#8-CHP-IMPACT CRUSHER-10515 | N.A. | - | 0 | 0.0020638 | 0 | 0.0020638 | 0 | 0 |  |  | 0 | 0.0020638
92 | Project-U#8-CHP-STRACKER CUM RECLAIMER-10515 | N.A. | - | 0 | 0.0082014 | 0 | 0.0082014 | 0 | 0 |  |  | 0 | 0.0082014
93 | Project-U#8-CHP-SIDE DISCHARGE TYPE WAGON TRIPPLER | N.A. | - | 0 | 0.0077836 | 0 | 0.0077836 | 0 | 0 |  |  | 0 | 0.0077836
94 | Project-U#8-Coal Handling Plant-M.S.-10515 | N.A. | - | 0 | 0.00034267 | 0 | 0.00034267 | 0 | 0 |  |  | 0 | 0.00034267
95 | Project-U#8-communication system-10572 | N.A. | - | 0 | 0.0019253 | 0 | 0.0019253 | 0 | 0 |  |  | 0 | 0.0019253
96 | Project-U#8-UPS INVERTORS-10563 | N.A. | - | 0 | 0.00051465 | 0 | 0.00051465 | 0 | 0 |  |  | 0 | 0.00051465
97 | Project-U#8-UPS ACDS-10563 | N.A. | - | 0 | 8.9956e-05 | 0 | 8.9956e-05 | 0 | 0 |  |  | 0 | 8.9956e-05
98 | Project-U#8-UPS BATTERIRERS-10563 | N.A. | - | 0 | 0.00051465 | 0 | 0.00051465 | 0 | 0 |  |  | 0 | 0.00051465
99 | Project-U#8-24V BATTERY CHARGERS (SGTG)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
100 | Project-U#8-24V BATTERY CHARGERS (BOP)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
101 | Project-U#8-BATTERIS FOR (SGTG)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
102 | Project-U#8-BATTERIS FOR (BOP)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
103 | Project-U#8-DCDB(SGTG)-10563 | N.A. | - | 0 | 5.7183e-05 | 0 | 5.7183e-05 | 0 | 0 |  |  | 0 | 5.7183e-05
104 | Project-U#8-DCDB(BOP)-10563 | N.A. | - | 0 | 5.7183e-05 | 0 | 5.7183e-05 | 0 | 0 |  |  | 0 | 5.7183e-05
105 | Project-U#8-Controls & Instru. for Main Plant(BTG) | N.A. | - | 0 | 0.044292 | 0 | 0.044292 | 0 | 0 |  |  | 0 | 0.044292
106 | Project-U#8-CW Chlorination system-10509 | N.A. | - | 0 | 0.0011974 | 0 | 0.0011974 | 0 | 0 |  |  | 0 | 0.0011974
107 | Project-U#8-D.G.SET-10509 | N.A. | - | 0 | 3.7894e-05 | 0 | 3.7894e-05 | 0 | 0 |  |  | 0 | 3.7894e-05
108 | Project-U#8-D.M.Water System-10509 | N.A. | - | 0 | 0.005785 | 0 | 0.005785 | 0 | 0 |  |  | 0 | 0.005785
109 | Project-U#8-DG set- Manadatory Spares-10509 | N.A. | - | 0 | 0.00025004 | 0 | 0.00025004 | 0 | 0 |  |  | 0 | 0.00025004
110 | Project-U#8-DG Set Room cum Air Compressor House | N.A. | - | 0 | 0.0055794 | 0 | 0.0055794 | 0 | 0 |  |  | 0 | 0.0055794
111 | Project-U#8-Steel for TechnologicalStructure-10501 | N.A. | - | 0 | 0.14836 | 0 | 0.14836 | 0 | 0 |  |  | 0 | 0.14836
112 | Project-U#8-Electrical Package for BOP-10509 | N.A. | - | 0 | 0.0024904 | 0 | 0.0024904 | 0 | 0 |  |  | 0 | 0.0024904
113 | Project-U#8-Electrical CHARGES-10509 | N.A. | - | 0 | 4.1155e-05 | 0 | 4.1155e-05 | 0 | 0 |  |  | 0 | 4.1155e-05
114 | Project-U#8-Electrical Package for BOP-Mandatory | N.A. | - | 0 | 0.0002757 | 0 | 0.0002757 | 0 | 0 |  |  | 0 | 0.0002757
115 | Project-U#8-Fire Protection, Alarm & Detection | N.A. | - | 0 | 0.0071788 | 0 | 0.0071788 | 0 | 0 |  |  | 0 | 0.0071788
116 | Project-U#8-Fuel Oil Pump House-10516 | N.A. | - | 0 | 0.0040925 | 0 | 0.0040925 | 0 | 0 |  |  | 0 | 0.0040925
117 | Project-U#8-Generator Transformer-10541 | N.A. | - | 0 | 0.012655 | 0 | 0.012655 | 0 | 0 |  |  | 0 | 0.012655
118 | Project-U#8-Generator/Transformer protection | N.A. | - | 0 | 0.00024539 | 0 | 0.00024539 | 0 | 0 |  |  | 0 | 0.00024539
119 | Project-U#8-H.T.Switchgear for main plant-10561 | N.A. | - | 0 | 0.025188 | 0 | 0.025188 | 0 | 0 |  |  | 0 | 0.025188
120 | Project-U#8-Indoor & Outdoor plant lighting-10599 | N.A. | - | 0 | 0.0004077 | 0 | 0.0004077 | 0 | 0 |  |  | 0 | 0.0004077
121 | Project-U#8-L.P.Piping including valves-10509 | N.A. | - | 0 | 0.0038246 | 0 | 0.0038246 | 0 | 0 |  |  | 0 | 0.0038246
122 | Project-U#8-L.T. Electrical for main plant.-10561 | N.A. | - | 0 | 8.7067e-05 | 0 | 8.7067e-05 | 0 | 0 |  |  | 0 | 8.7067e-05
123 | Project-U#8-Laying&Termination of HT cables-10561 | N.A. | - | 0 | 0.0008231 | 0 | 0.0008231 | 0 | 0 |  |  | 0 | 0.0008231
124 | Project-U#8-MainBoiler Structure&foundations-10501 | N.A. | - | 0 | 0.09941 | 0 | 0.09941 | 0 | 0 |  |  | 0 | 0.09941
125 | Project-U#8-Mandatory Spares for Ash HandlingPlant | N.A. | - | 0 | 0.0015616 | 0 | 0.0015616 | 0 | 0 |  |  | 0 | 0.0015616
126 | Project-U#8-Mandatory spares for C&I of Main Plant | N.A. | - | 0 | 0.0050295 | 0 | 0.0050295 | 0 | 0 |  |  | 0 | 0.0050295
127 | Project-U#8-Mandatory Spares for Electrical MainPa | N.A. | - | 0 | 0.015601 | 0 | 0.015601 | 0 | 0 |  |  | 0 | 0.015601
128 | Project-U#8-Mandatory Spares For TG & Auxilliaries | N.A. | - | 0 | 0.0062588 | 0 | 0.0062588 | 0 | 0 |  |  | 0 | 0.0062588
129 | Project-U#8-Misc. Cranes & hoists-10553 | N.A. | - | 0 | 0.0023537 | 0 | 0.0023537 | 0 | 0 |  |  | 0 | 0.0023537
130 | Project-U#8-Miscellaneous Pumps -10599 | N.A. | - | 0 | 0.0015672 | 0 | 0.0015672 | 0 | 0 |  |  | 0 | 0.0015672
131 | Project-U#8-Passanger lift for TG Building-10599 | N.A. | - | 0 | 0.0016358 | 0 | 0.0016358 | 0 | 0 |  |  | 0 | 0.0016358
132 | Project-U#8-Passanger/Material Lift at boiler side | N.A. | - | 0 | 0.00084731 | 0 | 0.00084731 | 0 | 0 |  |  | 0 | 0.00084731
133 | Project-U#8-Chemical Laboratory -10509 | N.A. | - | 0 | 0.0011648 | 0 | 0.0011648 | 0 | 0 |  |  | 0 | 0.0011648
134 | Project-U#8-Sewage Treatment Plant-10509 | N.A. | - | 0 | 0.0019006 | 0 | 0.0019006 | 0 | 0 |  |  | 0 | 0.0019006
135 | Project-U#8-Station Transformer-10541 | N.A. | - | 0 | 0.026576 | 0 | 0.026576 | 0 | 0 |  |  | 0 | 0.026576
136 | Project-U#8-Steam Turbine set-10503 | N.A. | - | 0 | 0.13864 | 0 | 0.13864 | 0 | 0 |  |  | 0 | 0.13864
137 | Project-U#8-TG set and its auxilleries- Condensor | N.A. | - | 0 | 0.012703 | 0 | 0.012703 | 0 | 0 |  |  | 0 | 0.012703
138 | Project-U#8-TG set and its auxilleries -Generator | N.A. | - | 0 | 0.032545 | 0 | 0.032545 | 0 | 0 |  |  | 0 | 0.032545
139 | Project-U#8-TG set and its auxilleries-Condensor | N.A. | - | 0 | 0.029273 | 0 | 0.029273 | 0 | 0 |  |  | 0 | 0.029273
140 | Project-U#8-TG set & its auxilleries-Derator-10503 | N.A. | - | 0 | 0.002758 | 0 | 0.002758 | 0 | 0 |  |  | 0 | 0.002758
141 | Project-U#8-TG set and its auxilleries-DMMakeUpSys | N.A. | - | 0 | 0.0010491 | 0 | 0.0010491 | 0 | 0 |  |  | 0 | 0.0010491
142 | Project-U#8-TG set and its auxilleries-Gas System | N.A. | - | 0 | 0.0056178 | 0 | 0.0056178 | 0 | 0 |  |  | 0 | 0.0056178
143 | Project-U#8-TG set and its auxilleries-GoveringSys | N.A. | - | 0 | 4.9466e-05 | 0 | 4.9466e-05 | 0 | 0 |  |  | 0 | 4.9466e-05
144 | Project-U#8-TG set and its auxilleries-HP/LP By-pa | N.A. | - | 0 | 0.010752 | 0 | 0.010752 | 0 | 0 |  |  | 0 | 0.010752
145 | Project-U#8-TG set and its auxilleries-HP/LP Dozin | N.A. | - | 0 | 0.00039941 | 0 | 0.00039941 | 0 | 0 |  |  | 0 | 0.00039941
146 | Project-U#8-TG set and its auxilleries-SealOilPump | N.A. | - | 0 | 9.8566e-05 | 0 | 9.8566e-05 | 0 | 0 |  |  | 0 | 9.8566e-05
147 | Project-U#8-TG set and its auxilleries-Vaccum Syst | N.A. | - | 0 | 0.010304 | 0 | 0.010304 | 0 | 0 |  |  | 0 | 0.010304
148 | Project-U#8-Turbine Lub. Oil System With Purifier | N.A. | - | 0 | 0.0022364 | 0 | 0.0022364 | 0 | 0 |  |  | 0 | 0.0022364
149 | Project-U#8-Ventillation system-10599 | N.A. | - | 0 | 0.0014389 | 0 | 0.0014389 | 0 | 0 |  |  | 0 | 0.0014389
150 | Asset Recived From Project-U#8-M.SPARE_Ventillation system-10599 | N.A. | - | 0 | 8.5482e-05 | 0 | 8.5482e-05 | 0 | 0 |  |  | 0 | 8.5482e-05
151 | Asset Recived From Project-U#8-Water Treatment Plant-10509 | N.A. | - | 0 | 0.0042384 | 0 | 0.0042384 | 0 | 0 |  |  | 0 | 0.0042384
152 | Asset Recived From Project-U#8-WORK SHOP MAD_SPARE-10565 | N.A. | - | 0 | 0.00030445 | 0 | 0.00030445 | 0 | 0 |  |  | 0 | 0.00030445
153 | Asset Recived From Project-U#8-Workshop-10565 | N.A. | - | 0 | 0.0013286 | 0 | 0.0013286 | 0 | 0 |  |  | 0 | 0.0013286
154 | Asset Recived From Project-U#8-CMR SYSTEM-10501 | N.A. | - | 0 | 0.0020736 | 0 | 0.0020736 | 0 | 0 |  |  | 0 | 0.0020736
155 | Asset Recived From Project-U#8-MandatorySpares-WTP-10.509 | N.A. | - | 0 | 8.1517e-05 | 0 | 8.1517e-05 | 0 | 0 |  |  | 0 | 8.1517e-05
156 | Asset Recived From Project-U#8-E.1.07_MandSpar 4 C&I MS 4MeasuringIns E.1.07_M S for C&I_ MS For Measuring Ins | N.A. | - | 0 | 0.078697 | 0 | 0.078697 | 0 | 0 |  |  | 0 | 0.078697
157 | Asset Recived From Project-U#8-BOP_ELECTRICAL-10612 | N.A. | - | 0 | 0.01637 | 0 | 0.01637 | 0 | 0 |  |  | 0 | 0.01637
158 | Asset Recived From Project-U#8-Bus Ducts-10612 | N.A. | - | 0 | 0.012548 | 0 | 0.012548 | 0 | 0 |  |  | 0 | 0.012548
159 | Asset Recived From Project-U#8-Cable trays & supports-10612 | N.A. | - | 0 | 0.00036009 | 0 | 0.00036009 | 0 | 0 |  |  | 0 | 0.00036009
160 | Project-U#8-PCR FURNITURE-10810 | N.A. | - | 0 | 0.00030684 | 0 | 0.00030684 | 0 | 0 |  |  | 0 | 0.00030684
161 | Project-U#8 Server Intel QUAD CORE 02No. HP Office Server | N.A. | - | 0 | 0.11918 | 0.11918 | 0 | 0 | 0 |  |  | 0 | 0
162 | Supply Erection testing and commissining of 1000 m3 ETP Civil works | N.A. | - | 0 | 0.68324 | 0.68324 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 469.4535 | 467.7326 | 1.7209 | 195.37 | 203.37 | 0 | 0 | 203.37 | -6.2791
FY 2027-28
0 | Add Cap (As per 296 of 2019)
A | Initial spares | Add Cap (As per 296 of 2019) | - | 0
1 | Boiler and Auxiliaries | Add Cap (As per 296 of 2019) | - | 7.2
1 | Procurement of Coal Mill XRP-903 Gear Box Type KMP-280 Spares of Unit # 8 at BM-NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 0 | 1.35 | 1.35 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply of Labyrinth Seal Rings with replaceable Inner liners for Coal Mill XRP-903 required for BM Unit-8, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.33134 | 0.33134 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply and Installation of coal mill liners(weld overlay) of XRP-903 Coal Mill in BM U-8, NPTPS,Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.33134 | 0.33134 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of Coal Mill XRP-903 Bowl & Bowl Hub of Unit # 8 at BM-NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 0 | 0.73326 | 0.73326 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply of impeller assembly for ID fan | Add Cap (As per 296 of 2019) | - | 0 | 0.5233 | 0.5233 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of Primary Air Fan & Forced Draught Fan Drive Coupling on OEM basis required at BM U-8, NPTPS, Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.1941 | 0.1941 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of Primary Air Fan PAF 17/11.8-2 Hydraulic Adjustment Device on OEM basis required at BM U-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.53521 | 0.53521 | 0 | 0 | 0 |  |  | 0 | 0
8 | Proc of spares for fabric expansion joints required at BM U-8, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.56972 | 0.56972 | 0 | 0 | 0 |  |  | 0 | 0
9 | Proc of separator body and seperator top spares for coal mill XRP-903 at BM U-8, NPTPS Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.42569 | 0.42569 | 0 | 0 | 0 |  |  | 0 | 0
10 | Proc of scrapper area & reject system spares for coal mill XRP-903 at BM U-8, NPTPS Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.27833 | 0.27833 | 0 | 0 | 0 |  |  | 0 | 0
11 | Proc of seal air fan spares at BM-8 NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.26432 | 0.26432 | 0 | 0 | 0 |  |  | 0 | 0
12 | Procurement of FD Fan Type FAF 17/9.5-1 Drive Coupling required at BM U-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | Procurement of complete planatary gear box-KMP -280/300 for coal mill XRP-903 at BM U-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Turbine and Auxiliaries | Add Cap (As per 296 of 2019) | - | 4.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of spares for Equipment Cooling Water Pumps (Make-FLOWMORE) of model FIG-5824 (SG Side) and FIG-5822 (TG side) at Unit-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.51812 | 0.51812 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply of spars for recovery & FF Pumps along with work at U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0.37713 | 0.37713 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of seal oil vacuum pump in unit 08 | Add Cap (As per 296 of 2019) | - | 0 | 0.27502 | 0.27502 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of AC pressure pipes (235MM OD, 200MM ID, 4.5M Length) for NDCT hot spray water distribution system in Unit-8 NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 0 | 0.42522 | 0.42522 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply of M/s Summits make Instrument Air Dryer & spares at U # 8 TM, Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.54787 | 0.54787 | 0 | 0 | 0 |  |  | 0 | 0
6 | Supply of PVC fills for NDCTs at U # 8 TM, Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.58245 | 0.58245 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of NB 600MM Gate valves for ACW self cleaning strainers in U#8 TM NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.42338 | 0.42338 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of Mechanical seals ( Make Leak-Proof) for various pumps in TM Unit-8 NPTPS Parli. | Add Cap (As per 296 of 2019) | - | 0 | 0.49233 | 0.49233 | 0 | 0 | 0 |  |  | 0 | 0
9 | Supply of SS 304 pipes & others at U # 8 TM, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.52905 | 0.52905 | 0 | 0 | 0 |  |  | 0 | 0
3 | Electrical and Instrumentation | Add Cap (As per 296 of 2019) | - | 6.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of Instrumentation Spares of LP Bypass System at Unit-8. | Add Cap (As per 296 of 2019) | - | 0 | 1.9615 | 1.9615 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of Schneider MICOM Numerical Relays for GRP and STPR swithcgear at NPTPS Unit-8 Testing | Add Cap (As per 296 of 2019) | - | 0 | 0.47613 | 0.47613 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of 220V DC Chloride make (formally caldyne) make battery chargers Spre of Unit 8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.23365 | 0.23365 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of 24V DC Chhabi make make battery chargers Spare of Unit 8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.22465 | 0.22465 | 0 | 0 | 0 |  |  | 0 | 0
5 | Procurement of Spare for Hitachi Hi-Rel make UPS systems installed at Unit-8 NPTPS Parli Vaijnath. | Add Cap (As per 296 of 2019) | - | 0 | 0.19186 | 0.19186 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of various test kit for testing U#8 such as energy meter calibration kit, DC earth faulth locator kit, promary current injection kit, breaker time measurement kit, numeric relay test kit and other testing instruments. | Add Cap (As per 296 of 2019) | - | 0 | 0.67345 | 0.67345 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of Energymeter Caliberation Software Module and hardware for upgrading Numeric Relay Test kit at Unit -8 Testing. | Add Cap (As per 296 of 2019) | - | 0 | 0.11863 | 0.11863 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of H T Motors. | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of critical L T Motors | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of ESP Hopper heaters (As a initial spares) Installed at EM U-8, NPTPS, Parli-Vaijnath under add cap scheme. | Add Cap (As per 296 of 2019) | - | 0 | 0.38586 | 0.38586 | 0 | 0 | 0 |  |  | 0 | 0
4 | Outdoor Plant(CHP/AHP/WTP) | Add Cap (As per 296 of 2019) | - | 6.64 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of Apron Feeder spares installed at CHP NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 1.6233 | 1.6233 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply of various drive and non drive pulleys for CHP U-8. | Add Cap (As per 296 of 2019) | - | 0 | 0.54529 | 0.54529 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply and installation of clamp pads & resting pads for Side Beam of Wagon Tippler for CHP U-8 | Add Cap (As per 296 of 2019) | - | 0 | 0.54802 | 0.54802 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply of unbalance motorozied vibrating feeder for S/R of U-7/8 CHP NPTPS Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.3958 | 0.3958 | 0 | 0 | 0 |  |  | 0 | 0
5 | Procurement of conveying and Instrument air compressor spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 1.77 | 1.77 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of vacuum pump spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0.2291 | 0.2291 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of fluidizing blower spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0.11796 | 0.11796 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of slurry pump spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of Clinker grinder spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0.12334 | 0.12334 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B | Reassessment of remaining BOP work after insolvency of M/s Sunil Hi-Tech | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Project balance E&M and procurement of mandetory spares | MERC CAPEX Approval in MTR Order 296 of 2019 | Order 296 of 2019 | 41.4534 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work order for Contract of Supply and application of Fire Stop Mortar Seal and Fire Retardant Cable Coating Compound at NPTP U-8 Parli Project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 3.4589 | 3.4589 | 0 | 0 | 0 |  |  | 0 | 0
2 | Work order for contract for Supply Installaion Testing & Commissioning Smoke Detection & alaram system | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 2.5606 | 2.5606 | 0 | 0 | 0 |  |  | 0 | 0
3 | Work order for contract for Supply Installaion Testing & Commissioning of Balance Fire Fighting System at NPTP U-8 Parli Project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.0502 | 1.0502 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, Errection, testing & commissioning works of RWP, PT potable chlorination system, ETP system control panel, automation of LDO, HFO tank foam system Hose boxes with RRL hoses and branch pipe and allied system at NPTP | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.8496 | 0.8496 | 0 | 0 | 0 |  |  | 0 | 0
5 | Work Order contract for supply, installation Testing & Commissioning of telephone exchange (EPBAX) & Telephone System at NPTP U-8 Parli project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.91256 | 0.91256 | 0 | 0 | 0 |  |  | 0 | 0
6 | Balance Supply of Electrical Lab Equipment at NPTP parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.60826 | 0.60826 | 0 | 0 | 0 |  |  | 0 | 0
7 | Work order for contract for Supply Installaion Testing & Commissioning with required material to complete Balance CHP work at NPTP U-8 Parli Project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.41 | 0.41 | 0 | 0 | 0 |  |  | 0 | 0
8 | Supply, Errection, testing & commissioning of Interconnecting Conveyor no.9 & 10 from U-8 to U-6&7 of CHP at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 5.3319 | 5.3262 | 0.0056593 | 0 | 0 |  |  | 0 | 0.0056593
9 | SUPPLY ,INSTA,TEST ,COMM ELECTRICAL SYS | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | SUPPLY,INSTAL,TEST,COMM OF CRANS&HOIST | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.8105 | 3.6223 | -1.8118 | 0 | 0 |  |  | 0 | -1.8118
11 | Supply, Errection, testing & commissioning of Dust Extraction system at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.8061 | 0 | 1.8061 | 0 | 0 |  |  | 0 | 1.8061
12 | Supply, Errection, testing & commissioning of DSS & DFDS at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 4.3391 | 4.34 | -0.0008856 | 0 | 0 |  |  | 0 | -0.0008856
13 | Supply, Errection, testing & commissioning of Monorail at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.1892 | 1.1891 | 7.77e-05 | 0 | 0 |  |  | 0 | 7.77e-05
14 | Supply, Errection, testing & commissioning of various Control & Instrumentation equipments at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.72225 | 0.72225 | 0 | 0 | 0 |  |  | 0 | 0
15 | Supply, Errection, testing & commissioning of Air Conditioning System at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.15304 | 0.44729 | -0.29425 | 0 | 0 |  |  | 0 | -0.29425
16 | Supply, Errection, testing & commissioning of Ventilation System at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 2.1136 | 1.2036 | 0.91 | 0 | 0 |  |  | 0 | 0.91
17 | Supply, Errection, testing & commissioning of Elevator works. | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 3.5173 | 4.4273 | -0.91 | 0 | 0 |  |  | 0 | -0.91
18 | Work contract for dismentaling, supply, erection & commissioning of MRHS | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 2.2335 | 2.2335 | 0 | 0 | 0 |  |  | 0 | 0
19 | Supply, Errection, testing & commissioning of FF System, Smoke detection & Fire stop mortar & Fire retradant cable coating for conveyor 09 & 10 | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.22171 | 0.51866 | -0.29696 | 0 | 0 |  |  | 0 | -0.29696
20 | Supply, Errection, testing & commissioning of Chimney Elevator | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.0608 | 0 | 1.0608 | 0 | 0 |  |  | 0 | 1.0608
21 | Supply, Errection, testing & commissioning work of GEHO Pumps. | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0 | 1.06 | -1.06 | 0 | 0 |  |  | 0 | -1.06
22 | Procurement of various Mandetory spares of BOP packages | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 5.47 | 6.54 | -1.07 | 0 | 0 |  |  | 0 | -1.07
0 | Balance civil work of BOP scope at 250 MW Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 45.3238 | 0.55712 | 16.72 | -16.1629 | 0 | 0 |  |  | 0 | -16.1629
1 | Area grading | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 6.9866 | 0.89 | 6.0966 | 0 | 0 |  |  | 0 | 6.0966
2 | CMD | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.2411 | 1.3549 | -0.11383 | 0 | 0 |  |  | 0 | -0.11383
3 | Conveyor 09, 10 & TP 06 | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 14.5605 | 12.13 | 2.4305 | 0 | 0 |  |  | 0 | 2.4305
4 | Finishing item | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 8.085 | 4.6506 | 3.4344 | 0 | 0 |  |  | 0 | 3.4344
5 | Drain & nala | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 5.0848 | 11.79 | -6.7052 | 0 | 0 |  |  | 0 | -6.7052
6 | Internal roads | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 9.7521 | 1.5 | 8.2521 | 0 | 0 |  |  | 0 | 8.2521
7 | Stacker & reclaimer | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.1627 | 0 | 1.1627 | 0 | 0 |  |  | 0 | 1.1627
0 | Other Add Cap | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Laboratory set up | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of Analytical Instruments for condition monitoring Laboratory for 1X250 MW of NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.5 | 0.49655 | 0.49655 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply of Analytical Instruments for Water Analysis Laboratory for 1X250 MW of NPTPS, Parli-V | Add Cap (As per 296 of 2019) | - | 1.23 | 0.29847 | 0.29847 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of Analytical Instruments for Environment Laboratory for 1 x 250 MW, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.39 | 0.3658 | 0.3658 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply of Analytical Instruments for Precision Laboratory for 1 x 250 MW, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply of Analytical Instruments for General Laboratory of Water Treatment Plant of 1 x 250 MW, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Supply of Corrosion Monitor/Meter, Corrosion Coupon & Coupon Rack for 1X250 MW of NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.34 | 0.34736 | 0.34736 | 0 | 0 | 0 |  |  | 0 | 0
7 | Supply of Analytical Instruments for Coal Analysis Laboratory for 1X250 MW of NPTPS, Parli-V | Add Cap (As per 296 of 2019) | - | 1.65 | 0.39444 | 0.39444 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Grade slab (WTP Area) | Add Cap (As per 296 of 2019) | - | 1 | 0.99752 | 0.99752 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Grade slab (Near AHP Building) | Add Cap (As per 296 of 2019) | - | 0.75 | 0.74556 | 0.74556 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Temporary shed for empty barrles & filled barrles | Add Cap (As per 296 of 2019) | - | 0.5 | 0.45635 | 0.45635 | 0 | 0 | 0 |  |  | 0 | 0
12 | Cabins for operators at TP. | Add Cap (As per 296 of 2019) | - | 0.2 | 0.18583 | 0.18583 | 0 | 0 | 0 |  |  | 0 | 0
13 | Compound wall for isolation of administrative building. | Add Cap (As per 296 of 2019) | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Work of providing/ fixing of internal partitions of aluminium/Nova palm/glass/wooden for Unit 8 service building & other allied builings in the premises. | Add Cap (As per 296 of 2019) | - | 0.7 | 0.67356 | 0.67356 | 0 | 0 | 0 |  |  | 0 | 0
15 | Provision of DM and softening water line interconnection from u-6,7 to u-8 & Provision of recovery of waste water from sandava pump house,NDCT. | Add Cap (As per 296 of 2019) | - | 3 | 1.0266 | 1.0266 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | Add Cap (As per 296 of 2019) | - | 0 | 1.8371 | 1.8371 | 0 | 0 | 0 |  |  | 0 | 0
16 | Hydraulic drive system modification. | Add Cap (As per 296 of 2019) | - | 2.5 | 2.4384 | 2.4384 | 0 | 0 | 0 |  |  | 0 | 0
17 | Link conveyor from Con-2 of U-6/7 to Con.-2AB of U-8. | Add Cap (As per 296 of 2019) | - | 3.7 | 4.6434 | 22.6564 | -18.0129 | 0 | 0 |  |  | 0 | -18.0129
18 | Ozone plant for Unit -8 | Add Cap (As per 296 of 2019) | - | 20 | 20.0947 | 2.1929 | 17.9018 | 0 | 0 |  |  | 0 | 17.9018
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | Water management system | Add Cap (As per 296 of 2019) | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8, 20 | Procurement & Installation of EMS system at Unit-8 NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 1 | 0.14417 | 0.14417 | 0 | 0 | 0 |  |  | 0 | 0
21 | Conveyor-5 of stacking/reclaiming belt double drive arrangement. | Add Cap (As per 296 of 2019) | - | 2 | 2.0432 | 2.0432 | 0 | 0 | 0 |  |  | 0 | 0
22 | Chemical lab building | Add Cap (As per 296 of 2019) | - | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Chemical store | Add Cap (As per 296 of 2019) | - | 2.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Lawn development around NDCT. | Add Cap (As per 296 of 2019) | - | 0.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | Tree plantation & greenery along road side. | Add Cap (As per 296 of 2019) | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | Greenery development in area between WTP & main plant. | Add Cap (As per 296 of 2019) | - | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | Construction of staff rooms & store for CHP maint.. | Add Cap (As per 296 of 2019) | - | 1 | 0.90703 | 0.90703 | 0 | 0 | 0 |  |  | 0 | 0
28 | Dsludg filteration for raw water | Add Cap (As per 296 of 2019) | - | 17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29 | PLC/UPS system upgradation | Add Cap (As per 296 of 2019) | - | 0.5 | 0.40149 | 0.40149 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | FGD at Parli Unit # 8 | MERC/CAPEX/2021-2022/0284 | 2022-06-27 | 89.24 | 4.1 | 0 | 4.1 | 0 | 0 |  |  | 0 | 4.1
22.1 | FGD at Parli Unit # 8 | MERC/CAPEX/2021-2022/0284 | 2022-06-27 | 85.2 | 95.21 | 108.86 | -13.65 | 0 | 0 |  |  | 0 | -13.65
0 | IDC | MERC/CAPEX/2021-2022/0284 | 2022-06-27 | 4.04 | 4.04 | 0 | 4.04 | 0 | 0 |  |  | 0 | 4.04
HO DPR 16 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 2.23 | 2.23 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Detailed Project Report on Boiler plant performance improvement and availability improvement schemes at Boiler Maintenance 1x250MW Unit-8 TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Procurement & Replacement of Complete Economizer Upper & Lower Bank Coil Assemblies at Unit-8, NPTPS Parli-V | Yet to be approved | - | 0 | 5.68 | 5.68 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 4.5 | 4.5 | 0 | 0 | 0 |  |  | 0 | 0
1.3 | Procurement & replacement of PA Fan PAF 17/11.8-2 and FD Fan FAF 17/9.5-1 Complete Blade set required at BM U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 5.45 | 5.45 | 0 | 0 | 0 |  |  | 0 | 0
1.4 | Procurement & Replacement of Coal Mill Gear Box Type KMP 280 at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 7.43 | 7.43 | 0 | 0 | 0 |  |  | 0 | 0
1.5 | Procurement & replacement of Bowl & Bowl Hub Assembly of Coal Mill XRP-903 required at BM U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 3.1 | 3.1 | 0 | 0 | 0 |  |  | 0 | 0
1.6 | Procurement of Complete Journal Assembly without Grinding roll for Coal Mill XRP-903 required at BM U-8 NPTPS Parli-V | Yet to be approved | - | 0 | 1.29 | 1.29 | 0 | 0 | 0 |  |  | 0 | 0
1.7 | Procurement of Hydraulic Adjustment Device for FD Fan FAF 17/9.5-1 at BM U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 1.4 | 1.4 | 0 | 0 | 0 |  |  | 0 | 0
1.8 | SWAS upgradation at U#8 | Yet to be approved | - | 0 | 4.8 | 4.8 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement & Replacement of Complete Platen super heater coils Coil Assemblies at Unit-8, TPS Parli-V, Procurement & Replacement of Complete LTSH upper & lower bank Coil Assemblies at Unit-8, TPS Parli-V & Procurement & Replacement of Coal Mill Gear Box Type KMP 280 at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Procurement & Replacement of Complete Platen super heater coils Coil Assemblies at Unit-8, TPS Parli-V | Yet to be approved | - | 0 | 12 | 12 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Procurement & Replacement of Complete LTSH upper & lower bank Coil Assemblies at Unit-8, TPS Parli-V | Yet to be approved | - | 0 | 9.35 | 9.35 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Procurement & Replacement of Coal Mill Gear Box Type KMP 280 at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 7.8 | 7.8 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-8, Parli TPS Procurement & replacement of PA & FD fan rotar hub assembly at Unit-8 TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Procurement & replacement of PA & FD fan rotar hub assembly at Unit-8 TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
4 | DPR on Refurbishment of TG Governing system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Refurbishment of TG Governing system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
5 | DPR on Performance improvement of Natural Draft Cooling Tower (NDCT) at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Performance improvement of Natural Draft Cooling Tower (NDCT) by replacement of PVC fills, AC cement pipes, strengthening of Hot water distribution system, replacement of beams, columns, support structures, etc. at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
6 | DPR on Procurement of ACW & CW pump along with mandatory spares at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | DPR on Procurement of ACW & CW pump along with mandatory spares at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 35 | 35 | 0 | 0 | 0 |  |  | 0 | 0
7 | DPR on Procurement of CEP pump and BFP Booster pump along with mandatory spares at Unit-8, PTPS, Parli V and Procurement of Energy Efficient Cartridges of Boiler Feed Pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Procurement of CEP pump and BFP Booster pump along with mandatory spares at Unit-8, PTPS, Parli | Yet to be approved | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
7.2 | Procurement of Energy Efficient Cartridges of Boiler Feed Pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
8 | DPR on Procurement of turbine blades of HP, IP & LP rotor in Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.1 | DPR on Procurement of turbine blades of HP, IP & LP rotor in Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 35 | 35 | 0 | 0 | 0 |  |  | 0 | 0
9 | DPR on Repair & Reconditioning of Water treatment plant at Unit-8, PTPS, Parli V and Performance improvement of centralised AC plant at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.1 | Reconditioning of Acid and Alkali Unloading and storage system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
9.2 | Reconditioning & repairing of WTP DM Plant regeneration system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
9.3 | Performance improvement of centralised AC plant by reconditioning of cooling tower, various pumps, heat exchangers, etc. at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
10 | DPR on Procurement of Control Fluid (HPCF) pump, Lube Oil pump, Emergency Oil pump, Jacking Oil pump, Seal oil pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.1 | DPR on Procurement of Control Fluid (HPCF) pump, Lube Oil pump, Emergency Oil pump, Jacking Oil pump, Seal oil pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
11 | DPR on Procurement of H2 cooler, BFP coolers, generator exciter cooler, Seal and Lube oil coolers at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.1 | DPR on Procurement of H2 cooler, BFP coolers, generator exciter cooler, Seal and Lube oil coolers at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 30 | 30 |  |  | 30 | 0
12 | Supply, installation & commissioning of 220V 2140AH,24V 830AH & 710AH, 360V 570AH Mains UPS,110V 110AH AHP PLC , 110V , 103 AH DM plant battery set for unit 8 , NPTPS Parli-V & Procurement of HT motors at U#8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.1 | Supply, installation & commissioning of 220V 2140AH,24V 830AH & 710AH, 360V 570AH Mains UPS,110V 110AH AHP PLC , 110V , 103 AH DM plant battery set for unit 8 , NPTPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 15 | 15 |  |  | 15 | 0
12.2 | Procurement of HT motors at U#8 | Yet to be approved | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
13 | DPR on various instrumentation & control schemes at U#8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | Upgradation of MAX-DNA DCS system at U#8 (HMI upgradation) | Yet to be approved | - | 0 | 6.81 | 6.81 | 0 | 0 | 0 |  |  | 0 | 0
13.2 | Upgradation of existing Pcal system with plant performance analysis diagnostic and optimization system (PADO) at Unit 8 New Parli TPS | Yet to be approved | - | 0 | 1.4 | 1.4 | 0 | 0 | 0 |  |  | 0 | 0
13.3 | Upgradation of coal feeder for I&C Unit8 PTPS Parli V. | Yet to be approved | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
13.4 | Procurement of smart control positioner at I&C Unit8 PTPS Parli V. | Yet to be approved | - | 0 | 0.95 | 0.95 | 0 | 0 | 0 |  |  | 0 | 0
13.5 | Upgradation Electronic control drive for I&C Unit8 PTPS Parli V. | Yet to be approved | - | 0 | 3.05 | 3.05 | 0 | 0 | 0 |  |  | 0 | 0
13.6 | Upgradation of turbovisory & vibration monitoring system control panel. | Yet to be approved | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
14 | Performance improvement by system up gradation at CHP & DPR for normalization and stabilization of coal handling plant performance at Parli TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.1 | Supply and Commissioning of Energy Efficient Evaporative Cooling System for Control Panel & Breaker room of CHP Unit-8 For PARLI TPS | Yet to be approved | - | 0 | 1.38 | 1.38 | 0 | 0 | 0 |  |  | 0 | 0
14.2 | Supply and commissioning of Suspended Magnets for U-8 CHP NPTPS | Yet to be approved | - | 0 | 3.3 | 3.3 | 0 | 0 | 0 |  |  | 0 | 0
14.3 | Stacker-reclaimer Bucket wheel drive modification work of U- 8 CHP | Yet to be approved | - | 0 | 3.32 | 3.32 | 0 | 0 | 0 |  |  | 0 | 0
14.4 | Apron feeder drive modification from Hydraulic to Electro-Mechanical at CHP U-8 NPTPS | Yet to be approved | - | 0 | 4.02 | 4.02 | 0 | 0 | 0 |  |  | 0 | 0
14.5 | Procurement of U-8 W/T Major spares | Yet to be approved | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
14.6 | Provision of Soft starter / VFD for Various conveyor | Yet to be approved | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
14.7 | TP-3 chute modification at U-8 CHP. | Yet to be approved | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
14.8 | Design, supply and commissioning of solar operated lighting system in CHP U-8. | Yet to be approved | - | 0 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
14.9 | Installation of CCTV survillance system alongwith all conveyors. | Yet to be approved | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
15 | DPR for maximiation of Coal Handling Plant efficiency & DPR on life enhancement of Coal Handling Plant | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | W/T control room & bunker house battery & UPS upgradation | Yet to be approved | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
15.2 | Refurbishment of conveyor no. 2 A/B & 6 A/B drive system of CHP U-8 TPS Parli. | Yet to be approved | - | 0 | 0 | 0 | 0 | 8 | 8 |  |  | 8 | 0
15.3 | Provision of Soft starter / VFD for Various conveyor | Yet to be approved | - | 0 | 0 | 0 | 0 | 8 | 8 |  |  | 8 | 0
15.4 | Procurement & installation of Belt tear detection system | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.5 | Conveyor gravity takeup infrastructure strengthening work | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.6 | U-8 CHP apron feeder-I to Conveyor 1 A/B chute modification work . | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | DPR for stabiliazation of Coal Handling Performance. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.1 | Drive modification of Stacker Reclaimer slewing system. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.2 | Retrofitting of Side Arm Charger-I & II at CHP U-8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.3 | Upgradation of GE/Schineder make PLC system atU-8 CHP. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.4 | Refurbishment of Apron Feeder at CHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.5 | Provision of moveable stacker and crusher in CHP coal stack yard at CHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.6 | Procurement of Loco & Bulldozer at CHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | DPR on dry fly ash utilisation improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.1 | Design, supply, erection, installation & comissioning of intermediate silo with sub system at AHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 38 | 38 |  |  | 38 | 0
18 | DPR on ash handling plant improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | Design, supply, erection & comissioning of weigh bridge for silo at AHP U-8. | Yet to be approved | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
18.2 | Supply, installation & comissioning of energy efficient air compressor at AHP U-8. | Yet to be approved | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
18.3 | PROCUREMENT OF COMPLETE ASSEMBLY OF SAM MAKE AR-150/510 PUMPS (2 NOS) FOR REPLACEMENT OF ASH SLURRY PUMPS OF BOTTOM ASH SLURRY DISPOSAL FROM SLURRY TANK TO ASH BUND IN SLURRY PUMP HOUSE. | Yet to be approved | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | PROCUREMENT OF COMPLETE ASSEMBLY OF SAM MAKE ZM-II 530/02 (2 NOS) FOR REPLACEMENT OF HP PUMPS OF BOTTOM ASH & COARSE ASH EVACUATION FROM BA/CA HOPPERS TO SLURRY TANK IN ASH WATER PUMP HOUSE. 0.75 0.89 | Yet to be approved | - | 0 | 0.4 | 0.4 | 0 | 0 | 0 |  |  | 0 | 0
18.5 | Procurement of vacuum pumps complete assembly for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
18.6 | Procurement of vacuum pumps complete assembly for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
18.7 | Procurement of Feed Gate Complete Assembly along with modified metallurgy to enhance the life of Clinker Grinder. | Yet to be approved | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
18.8 | Procurement of Double Roll Clinker Grinder Complete Assembly with Drive Unit installed at AHP | Yet to be approved | - | 0 | 1.25 | 1.25 | 0 | 0 | 0 |  |  | 0 | 0
18.9 | Procurement of Instrument Air Dryers assembly for performance improvement | Yet to be approved | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | Procurement of various types of Isolation Valves assembly, Dome Valves assembly, Root Valve Assembly & Expansion Bellows Assembly for Dry Ash Conveing performance improvement | Yet to be approved | - | 0 | 3.6 | 3.6 | 0 | 0 | 0 |  |  | 0 | 0
19 | DPR on ash handling plant improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | Design, supply, erection, installation & comissioning of DM water close loop cooling system for air compressors at AHP U-8. | Yet to be approved | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
19.2 | Up-gradation of Existing Schneider make PLC (HMI + PLC hardware) installed at AHP Unit -8 at Parli TPS. | Yet to be approved | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
19.3 | Procurement of HT motors for AHP U-8 Parli TPS. | Yet to be approved | - | 0 | 2.3 | 2.3 | 0 | 0 | 0 |  |  | 0 | 0
19.4 | PROCUREMENT OF CRITICAL GEARBOXES AND FLUID COUPLINGS INTERNAL ASSEMBLIES FOR SLURRY PUMPS AND SILO HCSD SYSTEM INSTALLED AT AHP, PARLI TPS. | Yet to be approved | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
19.5 | Procurement of Atlas Copco Make Instrument Air Compressors Critical/Non-Critical Spares sub-assembly for performance improvement | Yet to be approved | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
19.6 | Upgradation and improvement in Hopper Temperature monitoring system by providing Rf Type Hopper Level Sensors for performance improvement of conveying of Dry ash evacuation system. | Yet to be approved | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
20 | DPR on ash handling plant improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.1 | Design, supply, erection, installation & comissioning ESP 1st & 2nd field dry fly ash evacuation & conveying system at AHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 21.25 | 21.25 |  |  | 21.25 | 0
20.2 | Design, supply, erection, installation & comissioning of dry ash evacuation & conveying system for APH & Economiser ash hoppers at AHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
21 | Verious Civil schemes in Unit 8 NPTPS Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Construction of chemical laboratory building at Unit 8, NPTPS, Parli V. | Yet to be approved | - | 0 | 3.78 | 3.78 | 0 | 0 | 0 |  |  | 0 | 0
21.2 | Construction of Alum/salt storage area at Unit No.8 (1X250MW) NPTPS Parli Vaijnath. | Yet to be approved | - | 0 | 3.46 | 3.46 | 0 | 0 | 0 |  |  | 0 | 0
21.3 | Construction of Fire Fighting station at Unit-8, NPTPS Parli V. | Yet to be approved | - | 0 | 1.86 | 1.86 | 0 | 0 | 0 |  |  | 0 | 0
21.4 | Construction of workshop building at Unit-8, NPTPS Parli V. | Yet to be approved | - | 0 | 2.13 | 2.13 | 0 | 0 | 0 |  |  | 0 | 0
22 | CHP improvement scheme at 250 MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.1 | CHP improvement scheme at 250 MW | 0 | - | 0 | 0 | 0 | 0 | 25 | 25 |  |  | 25 | 0
0 | B) Non-DPR | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0.56615 | 0.56615 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) GA | 0 | - | 0 | 0.92312 | 0.98371 | -0.060588 | 0.29 | 0.29 |  |  | 0.29 | -0.060588
0 | 0 | 0 | - | 0 | 0.29 | 0 | 0.29 | 0 | 0 |  |  | 0 | 0.29
0 | C) Asset received from Project U#8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Asset Recived From Civil-U#8-Land-10101 | N.A. | - | 0 | 0.0031293 | 0 | 0.0031293 | 0 | 0 |  |  | 0 | 0.0031293
2 | Asset Recived From Civil-U#8-T.G. Building-10201 | N.A. | - | 0 | 0.010038 | 0 | 0.010038 | 0 | 0 |  |  | 0 | 0.010038
3 | Asset Recived From Civil-U#8-T.G. Building(BC)bay&control room-10201 | N.A. | - | 0 | 0.0045784 | 0 | 0.0045784 | 0 | 0 |  |  | 0 | 0.0045784
4 | Asset Recived From Civil-U#8-StructuralSteelWorks4TGBldgA2EBays-10201 | N.A. | - | 0 | 0.0013976 | 0 | 0.0013976 | 0 | 0 |  |  | 0 | 0.0013976
5 | Asset Recived From Civil-U#8-WTP Building-10201 | N.A. | - | 0 | 0.00011482 | 0 | 0.00011482 | 0 | 0 |  |  | 0 | 0.00011482
6 | Asset Recived From Civil-U#8-DG SET ROOM CUM AIR COMP. HOUSE-10201 | N.A. | - | 0 | 0.00010598 | 0 | 0.00010598 | 0 | 0 |  |  | 0 | 0.00010598
7 | Asset Recived From Civil-U#8-WTP-Raw/Fire water pump House-10233 | N.A. | - | 0 | 0.00069019 | 0 | 0.00069019 | 0 | 0 |  |  | 0 | 0.00069019
8 | Asset Recived From Civil-U#8-SERVICE BUILDING -10211 | N.A. | - | 0 | 0.00055144 | 0 | 0.00055144 | 0 | 0 |  |  | 0 | 0.00055144
9 | Asset Recived From Civil-U#8-Canteen -10233 | N.A. | - | 0 | 0.00072491 | 0 | 0.00072491 | 0 | 0 |  |  | 0 | 0.00072491
10 | Asset Recived From Civil-U#8-PARKING SHED -10233 | N.A. | - | 0 | 6.111e-06 | 0 | 6.111e-06 | 0 | 0 |  |  | 0 | 6.111e-06
11 | Asset Recived From Civil-U#8-Time Security Building -10233 | N.A. | - | 0 | 3.595e-05 | 0 | 3.595e-05 | 0 | 0 |  |  | 0 | 3.595e-05
12 | Asset Recived From Civil-U#8-Misc.Building/structure/Watchtower-10233 | N.A. | - | 0 | 0.00017243 | 0 | 0.00017243 | 0 | 0 |  |  | 0 | 0.00017243
13 | Asset Recived From Civil-U#8-Boundry compound wall Mall-10233 | N.A. | - | 0 | 0.15766 | 0 | 0.15766 | 0 | 0 |  |  | 0 | 0.15766
14 | Asset Recived From Civil-U#8-Workshop civil work-10233 | N.A. | - | 0 | 4.188e-05 | 0 | 4.188e-05 | 0 | 0 |  |  | 0 | 4.188e-05
15 | Asset Recived From Civil-U#8-Interior Work for CEC-I Office-10233 | N.A. | - | 0 | 5.6438e-05 | 0 | 5.6438e-05 | 0 | 0 |  |  | 0 | 5.6438e-05
16 | Asset Recived From Civil-U#8-WTP-Raw water reservoir -10305 | N.A. | - | 0 | 0.0012248 | 0 | 0.0012248 | 0 | 0 |  |  | 0 | 0.0012248
17 | Asset Recived From Civil-U#8-WTP-Clarifier -10305 | N.A. | - | 0 | 0.0011652 | 0 | 0.0011652 | 0 | 0 |  |  | 0 | 0.0011652
18 | Asset Recived From Civil-U#8-WTP-Clarifier Water Storage Tank-10305 | N.A. | - | 0 | 0.00019514 | 0 | 0.00019514 | 0 | 0 |  |  | 0 | 0.00019514
19 | Asset Recived From Civil-U#8-C.W. pump house & forebay-10310 | N.A. | - | 0 | 0.00052946 | 0 | 0.00052946 | 0 | 0 |  |  | 0 | 0.00052946
20 | Asset Recived From Civil-U#8-Construction of STP for Colony-10322 | N.A. | - | 0 | 0.00017966 | 0 | 0.00017966 | 0 | 0 |  |  | 0 | 0.00017966
21 | Asset Recived From Civil-U#8-Cooling Towers-10311 | N.A. | - | 0 | 0.37628 | 0 | 0.37628 | 0 | 0 |  |  | 0 | 0.37628
22 | Asset Recived From Civil-U#8-Railway sidings-10412 | N.A. | - | 0 | 0.13615 | 0 | 0.13615 | 0 | 0 |  |  | 0 | 0.13615
23 | Asset Recived From Civil-U#8-In plant Roads -10401 | N.A. | - | 0 | 0.0009103 | 0 | 0.0009103 | 0 | 0 |  |  | 0 | 0.0009103
24 | Asset Recived From Civil-U#8-Pipe Rack -10419 | N.A. | - | 0 | 0.00041823 | 0 | 0.00041823 | 0 | 0 |  |  | 0 | 0.00041823
25 | Asset Recived From Civil-U#8-Transformar yard area -10541 | N.A. | - | 0 | 0.00053169 | 0 | 0.00053169 | 0 | 0 |  |  | 0 | 0.00053169
26 | Asset Recived From Civil-U#8-BA-Boiler and Auxilary foundation-10501 | N.A. | - | 0 | 0.0061116 | 0 | 0.0061116 | 0 | 0 |  |  | 0 | 0.0061116
27 | Asset Recived From Civil-U#8-BA-FD FAN FOUNDATIONS -10501 | N.A. | - | 0 | 0.00011166 | 0 | 0.00011166 | 0 | 0 |  |  | 0 | 0.00011166
28 | Asset Recived From Civil-U#8-BA-PA FAN FOUNDATION -10501 | N.A. | - | 0 | 0.00011166 | 0 | 0.00011166 | 0 | 0 |  |  | 0 | 0.00011166
29 | Asset Recived From Civil-U#8-BA-I.D. Fan foundation -10501 | N.A. | - | 0 | 0.00022332 | 0 | 0.00022332 | 0 | 0 |  |  | 0 | 0.00022332
30 | Asset Recived From Civil-U#8-BA-MILL FOUNDATION-10501 | N.A. | - | 0 | 0.00019826 | 0 | 0.00019826 | 0 | 0 |  |  | 0 | 0.00019826
31 | Asset Recived From Civil-U#8-BA-BUNKER FOUNDATION & STRUCTURE-10515 | N.A. | - | 0 | 0.0013925 | 0 | 0.0013925 | 0 | 0 |  |  | 0 | 0.0013925
32 | Asset Recived From Civil-U#8-ESP-10501 | N.A. | - | 0 | 0.00070722 | 0 | 0.00070722 | 0 | 0 |  |  | 0 | 0.00070722
33 | Asset Recived From Civil-U#8-ESP Control Room-10501 | N.A. | - | 0 | 0.00042763 | 0 | 0.00042763 | 0 | 0 |  |  | 0 | 0.00042763
34 | Asset Recived From Civil-U#8-RCC Chimney -10501 | N.A. | - | 0 | 0.0046127 | 0 | 0.0046127 | 0 | 0 |  |  | 0 | 0.0046127
35 | Asset Recived From Civil-U#8-WTP-D.M.Plant equipment fdn. etc.-10509 | N.A. | - | 0 | 6.3898e-05 | 0 | 6.3898e-05 | 0 | 0 |  |  | 0 | 6.3898e-05
36 | Asset Recived From Civil-U#8-CHP-Wagon Tippler-10515 | N.A. | - | 0 | 0.00094041 | 0 | 0.00094041 | 0 | 0 |  |  | 0 | 0.00094041
37 | Asset Recived From Civil-U#8-CHP-Crusher House -10515 | N.A. | - | 0 | 0.00074704 | 0 | 0.00074704 | 0 | 0 |  |  | 0 | 0.00074704
38 | Asset Recived From Civil-U#8-CHP-Stacker Reclaimer -10515 | N.A. | - | 0 | 0.00028485 | 0 | 0.00028485 | 0 | 0 |  |  | 0 | 0.00028485
39 | Asset Recived From Civil-U#8-CHP-Stock Yard-10515 | N.A. | - | 0 | 0.00015851 | 0 | 0.00015851 | 0 | 0 |  |  | 0 | 0.00015851
40 | Asset Recived From Civil-U#8-CHP-ConveyorPedetals&TransferPoint-10515 | N.A. | - | 0 | 0.00055408 | 0 | 0.00055408 | 0 | 0 |  |  | 0 | 0.00055408
41 | Asset Recived From Civil-U#8-CHP-MCC ROOM -10515 | N.A. | - | 0 | 0.00026945 | 0 | 0.00026945 | 0 | 0 |  |  | 0 | 0.00026945
42 | Asset Recived From Civil-U#8-AHP-RCC Ash Silo -10501 | N.A. | - | 0 | 0.00016423 | 0 | 0.00016423 | 0 | 0 |  |  | 0 | 0.00016423
43 | Asset Recived From Civil-U#8-AHP-Staicase near Silo-10501 | N.A. | - | 0 | 1.7302e-05 | 0 | 1.7302e-05 | 0 | 0 |  |  | 0 | 1.7302e-05
44 | Asset Recived From Civil-U#8-AHP-Drain sump in Silo Area -10501 | N.A. | - | 0 | 8.551e-06 | 0 | 8.551e-06 | 0 | 0 |  |  | 0 | 8.551e-06
45 | Asset Recived From Civil-U#8-AHP-Slurry Mixing Tank Fdn.-10501 | N.A. | - | 0 | 1.6923e-05 | 0 | 1.6923e-05 | 0 | 0 |  |  | 0 | 1.6923e-05
46 | Asset Recived From Civil-U#8-AHP-HCSD PUMP HOUSE-10501 | N.A. | - | 0 | 5.8934e-05 | 0 | 5.8934e-05 | 0 | 0 |  |  | 0 | 5.8934e-05
47 | Asset Recived From Civil-U#8-AHP-Ash Slurry Pump House -10501 | N.A. | - | 0 | 0.00014947 | 0 | 0.00014947 | 0 | 0 |  |  | 0 | 0.00014947
48 | Asset Recived From Civil-U#8-AHP-Ash Slurry Sump-10501 | N.A. | - | 0 | 4.5159e-05 | 0 | 4.5159e-05 | 0 | 0 |  |  | 0 | 4.5159e-05
49 | Asset Recived From Civil-U#8-AHP-Ash Water Tank-10501 | N.A. | - | 0 | 3.422e-05 | 0 | 3.422e-05 | 0 | 0 |  |  | 0 | 3.422e-05
50 | Asset Recived From Civil-U#8-AHP-Bottom Ash Hopper-10501 | N.A. | - | 0 | 4.409e-05 | 0 | 4.409e-05 | 0 | 0 |  |  | 0 | 4.409e-05
51 | Asset Recived From Civil-U#8-AHP-Drain sump in BAH Area -10501 | N.A. | - | 0 | 8.575e-06 | 0 | 8.575e-06 | 0 | 0 |  |  | 0 | 8.575e-06
52 | Asset Recived From Civil-U#8-Ash Slurry Pipe Line AHP-Pedestals-10501 | N.A. | - | 0 | 0.00013846 | 0 | 0.00013846 | 0 | 0 |  |  | 0 | 0.00013846
53 | Asset Recived From Civil-U#8-AHP-Buffer Hopper Foundation-10501 | N.A. | - | 0 | 3.5628e-05 | 0 | 3.5628e-05 | 0 | 0 |  |  | 0 | 3.5628e-05
54 | Asset Recived From Civil-U#8-AHP-Mill reject hopper foundation-10501 | N.A. | - | 0 | 1.7814e-05 | 0 | 1.7814e-05 | 0 | 0 |  |  | 0 | 1.7814e-05
55 | Asset Recived From Civil-U#8-FHP-Fuel Oil pump house-10516 | N.A. | - | 0 | 0.00065769 | 0 | 0.00065769 | 0 | 0 |  |  | 0 | 0.00065769
56 | Asset Recived From Civil-U#8-FHP-DYKE AREA -10516 | N.A. | - | 0 | 1.9339e-05 | 0 | 1.9339e-05 | 0 | 0 |  |  | 0 | 1.9339e-05
57 | Asset Recived From Civil-U#8-Effulent Treatment Plant -10509 | N.A. | - | 0 | 0.00014135 | 0 | 0.00014135 | 0 | 0 |  |  | 0 | 0.00014135
58 | Asset Recived From Project-U#8-Boiler Pressure parts-10501 | N.A. | - | 0 | 0.06549 | 0 | 0.06549 | 0 | 0 |  |  | 0 | 0.06549
59 | Asset Recived From Project-U#8-Mandatory Spares from BHEL–Trichy | N.A. | - | 0 | 0.0074619 | 0 | 0.0074619 | 0 | 0 |  |  | 0 | 0.0074619
60 | Asset Recived From Civil-U#8-Coal mill reject trench at coal mill D&E | N.A. | - | 0 | 0.04661 | 0 | 0.04661 | 0 | 0 |  |  | 0 | 0.04661
61 | Asset Recived From Project-U#8-Canteen Equipments & kitchen Utensils | N.A. | - | 0 | 0.21888 | 0 | 0.21888 | 0 | 0 |  |  | 0 | 0.21888
62 | Asset Recived From Project-U#8-Supply & Erection of ACW system-10310 | N.A. | - | 0 | 0.00083684 | 0 | 0.00083684 | 0 | 0 |  |  | 0 | 0.00083684
63 | Asset Recived From Project-U#8-SUPPLY & ERECTION OF CCW SYSTEM-10310 | N.A. | - | 0 | 0.004856 | 0 | 0.004856 | 0 | 0 |  |  | 0 | 0.004856
64 | Asset Recived From Project-U#8-TG set & its auxilleries-HP/LPFeedWate | N.A. | - | 0 | 0.016842 | 0 | 0.016842 | 0 | 0 |  |  | 0 | 0.016842
65 | Asset Recived From Project-U#8-TG set and its auxilleries- Boilerfeed | N.A. | - | 0 | 0.018479 | 0 | 0.018479 | 0 | 0 |  |  | 0 | 0.018479
66 | Asset Recived From Project-U#8-Air Conditioning-MandatorySpares-10576 | N.A. | - | 0 | 1.7256e-05 | 0 | 1.7256e-05 | 0 | 0 |  |  | 0 | 1.7256e-05
67 | Asset Recived From Project-U#8-Air Conditioning system-10576 | N.A. | - | 0 | 0.0013446 | 0 | 0.0013446 | 0 | 0 |  |  | 0 | 0.0013446
68 | Asset Recived From Project-U#8-AHP-FLY ASH & HCSD-SYSTEM-10501 | N.A. | - | 0 | 0.0021652 | 0 | 0.0021652 | 0 | 0 |  |  | 0 | 0.0021652
69 | Asset Recived From Project-U#8-AHP-FLYASH&HCSD-SYSTEMBOUGHT OUT-10501 | N.A. | - | 0 | 0.0070969 | 0 | 0.0070969 | 0 | 0 |  |  | 0 | 0.0070969
70 | Asset Recived From Project-U#8-AHP-BOTTOM ASH SYSTEM-10501 | N.A. | - | 0 | 0.012126 | 0 | 0.012126 | 0 | 0 |  |  | 0 | 0.012126
71 | Asset Recived From Project-U#8-AHP-ELECTRICAL C & I-10501 | N.A. | - | 0 | 0.004053 | 0 | 0.004053 | 0 | 0 |  |  | 0 | 0.004053
72 | Asset Recived From Project-U#8-AHP-GEHO PUMP-10501 | N.A. | - | 0 | 0.0095128 | 0 | 0.0095128 | 0 | 0 |  |  | 0 | 0.0095128
73 | Asset Recived FromProject-U#8-Boiler&Aux -Power Cycle Piping-10501 | N.A. | - | 0 | 0.041005 | 0 | 0.041005 | 0 | 0 |  |  | 0 | 0.041005
74 | Asset Recived From Project-U#8-Boiler&Aux-SUIT BLOWER & PIPING-10501 | N.A. | - | 0 | 0.083837 | 0 | 0.083837 | 0 | 0 |  |  | 0 | 0.083837
75 | Asset Recived From Project-U#8-Boiler & Auxillaries - PA FAN-10501 | N.A. | - | 0 | 0.0010226 | 0 | 0.0010226 | 0 | 0 |  |  | 0 | 0.0010226
76 | Asset Recived From Project-U#8-Boiler&Aux-Air Preheaters-10501 | N.A. | - | 0 | 0.013281 | 0 | 0.013281 | 0 | 0 |  |  | 0 | 0.013281
77 | Asset Recived From Project-U#8-Boiler & Auxillaries -COAL MILL-10501 | N.A. | - | 0 | 0.051244 | 0 | 0.051244 | 0 | 0 |  |  | 0 | 0.051244
78 | Asset Recived From Project-U#8-Boiler & Auxillaries -FD FAN-10501 | N.A. | - | 0 | 0.0006817 | 0 | 0.0006817 | 0 | 0 |  |  | 0 | 0.0006817
79 | Asset Recived From Project-U#8-Boiler & Auxillaries- ID FAN-10501 | N.A. | - | 0 | 0.0017043 | 0 | 0.0017043 | 0 | 0 |  |  | 0 | 0.0017043
80 | Asset Recived From Project-U#8-Boiler&Aux-Mandatory Spares-10501 | N.A. | - | 0 | 0.0097935 | 0 | 0.0097935 | 0 | 0 |  |  | 0 | 0.0097935
81 | Asset Recived From Project-U#8-Boiler&Aux-PLATFORM,STAIRS,GRATINGS, | N.A. | - | 0 | 0.030596 | 0 | 0.030596 | 0 | 0 |  |  | 0 | 0.030596
82 | Asset Recived From Project-U#8-Boiler Pressure parts-10501 | N.A. | - | 0 | 0.17807 | 0 | 0.17807 | 0 | 0 |  |  | 0 | 0.17807
83 | Asset Recived From Project-U#8-220V-BATTERY+CHARGERS-MAIN PLANT-10563 | N.A. | - | 0 | 0.0020848 | 0 | 0.0020848 | 0 | 0 |  |  | 0 | 0.0020848
84 | Asset Recived From Project-U#8-220V -BATTERY WITH CHARGERS(CHP)-10563 | N.A. | - | 0 | 0.00020745 | 0 | 0.00020745 | 0 | 0 |  |  | 0 | 0.00020745
85 | Asset Recived From Project-U#8-220V-BATTERY+CHARG-WAGON TRIP-2N-10563 | N.A. | - | 0 | 8.4674e-05 | 0 | 8.4674e-05 | 0 | 0 |  |  | 0 | 8.4674e-05
86 | Asset Recived From Project-U#8-BOP-OTHER C& i INSTRUMENTS-10509 | N.A. | - | 0 | 0.0013441 | 0 | 0.0013441 | 0 | 0 |  |  | 0 | 0.0013441
87 | Asset Recived From Project-U#8-CHP-CONVEYOR SYSTEM-10515 | N.A. | - | 0 | 0.015409 | 0 | 0.015409 | 0 | 0 |  |  | 0 | 0.015409
88 | Asset Recived From Project-U#8-CHP-WOBLER FEEDER-10515 | N.A. | - | 0 | 0.00054613 | 0 | 0.00054613 | 0 | 0 |  |  | 0 | 0.00054613
89 | Asset Recived From Project-U#8-CHP-APRON FEEDER-10515 | N.A. | - | 0 | 0.0028149 | 0 | 0.0028149 | 0 | 0 |  |  | 0 | 0.0028149
90 | Asset Recived From Project-U#8-CHP-ILMS,METAL DETECTOR,BELT WEIGHER | N.A. | - | 0 | 0.0011704 | 0 | 0.0011704 | 0 | 0 |  |  | 0 | 0.0011704
91 | Asset Recived From Project-U#8-CHP-IMPACT CRUSHER-10515 | N.A. | - | 0 | 0.0020638 | 0 | 0.0020638 | 0 | 0 |  |  | 0 | 0.0020638
92 | Project-U#8-CHP-STRACKER CUM RECLAIMER-10515 | N.A. | - | 0 | 0.0082014 | 0 | 0.0082014 | 0 | 0 |  |  | 0 | 0.0082014
93 | Project-U#8-CHP-SIDE DISCHARGE TYPE WAGON TRIPPLER | N.A. | - | 0 | 0.0077836 | 0 | 0.0077836 | 0 | 0 |  |  | 0 | 0.0077836
94 | Project-U#8-Coal Handling Plant-M.S.-10515 | N.A. | - | 0 | 0.00034267 | 0 | 0.00034267 | 0 | 0 |  |  | 0 | 0.00034267
95 | Project-U#8-communication system-10572 | N.A. | - | 0 | 0.0019253 | 0 | 0.0019253 | 0 | 0 |  |  | 0 | 0.0019253
96 | Project-U#8-UPS INVERTORS-10563 | N.A. | - | 0 | 0.00051465 | 0 | 0.00051465 | 0 | 0 |  |  | 0 | 0.00051465
97 | Project-U#8-UPS ACDS-10563 | N.A. | - | 0 | 8.9956e-05 | 0 | 8.9956e-05 | 0 | 0 |  |  | 0 | 8.9956e-05
98 | Project-U#8-UPS BATTERIRERS-10563 | N.A. | - | 0 | 0.00051465 | 0 | 0.00051465 | 0 | 0 |  |  | 0 | 0.00051465
99 | Project-U#8-24V BATTERY CHARGERS (SGTG)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
100 | Project-U#8-24V BATTERY CHARGERS (BOP)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
101 | Project-U#8-BATTERIS FOR (SGTG)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
102 | Project-U#8-BATTERIS FOR (BOP)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
103 | Project-U#8-DCDB(SGTG)-10563 | N.A. | - | 0 | 5.7183e-05 | 0 | 5.7183e-05 | 0 | 0 |  |  | 0 | 5.7183e-05
104 | Project-U#8-DCDB(BOP)-10563 | N.A. | - | 0 | 5.7183e-05 | 0 | 5.7183e-05 | 0 | 0 |  |  | 0 | 5.7183e-05
105 | Project-U#8-Controls & Instru. for Main Plant(BTG) | N.A. | - | 0 | 0.044292 | 0 | 0.044292 | 0 | 0 |  |  | 0 | 0.044292
106 | Project-U#8-CW Chlorination system-10509 | N.A. | - | 0 | 0.0011974 | 0 | 0.0011974 | 0 | 0 |  |  | 0 | 0.0011974
107 | Project-U#8-D.G.SET-10509 | N.A. | - | 0 | 3.7894e-05 | 0 | 3.7894e-05 | 0 | 0 |  |  | 0 | 3.7894e-05
108 | Project-U#8-D.M.Water System-10509 | N.A. | - | 0 | 0.005785 | 0 | 0.005785 | 0 | 0 |  |  | 0 | 0.005785
109 | Project-U#8-DG set- Manadatory Spares-10509 | N.A. | - | 0 | 0.00025004 | 0 | 0.00025004 | 0 | 0 |  |  | 0 | 0.00025004
110 | Project-U#8-DG Set Room cum Air Compressor House | N.A. | - | 0 | 0.0055794 | 0 | 0.0055794 | 0 | 0 |  |  | 0 | 0.0055794
111 | Project-U#8-Steel for TechnologicalStructure-10501 | N.A. | - | 0 | 0.14836 | 0 | 0.14836 | 0 | 0 |  |  | 0 | 0.14836
112 | Project-U#8-Electrical Package for BOP-10509 | N.A. | - | 0 | 0.0024904 | 0 | 0.0024904 | 0 | 0 |  |  | 0 | 0.0024904
113 | Project-U#8-Electrical CHARGES-10509 | N.A. | - | 0 | 4.1155e-05 | 0 | 4.1155e-05 | 0 | 0 |  |  | 0 | 4.1155e-05
114 | Project-U#8-Electrical Package for BOP-Mandatory | N.A. | - | 0 | 0.0002757 | 0 | 0.0002757 | 0 | 0 |  |  | 0 | 0.0002757
115 | Project-U#8-Fire Protection, Alarm & Detection | N.A. | - | 0 | 0.0071788 | 0 | 0.0071788 | 0 | 0 |  |  | 0 | 0.0071788
116 | Project-U#8-Fuel Oil Pump House-10516 | N.A. | - | 0 | 0.0040925 | 0 | 0.0040925 | 0 | 0 |  |  | 0 | 0.0040925
117 | Project-U#8-Generator Transformer-10541 | N.A. | - | 0 | 0.012655 | 0 | 0.012655 | 0 | 0 |  |  | 0 | 0.012655
118 | Project-U#8-Generator/Transformer protection | N.A. | - | 0 | 0.00024539 | 0 | 0.00024539 | 0 | 0 |  |  | 0 | 0.00024539
119 | Project-U#8-H.T.Switchgear for main plant-10561 | N.A. | - | 0 | 0.025188 | 0 | 0.025188 | 0 | 0 |  |  | 0 | 0.025188
120 | Project-U#8-Indoor & Outdoor plant lighting-10599 | N.A. | - | 0 | 0.0004077 | 0 | 0.0004077 | 0 | 0 |  |  | 0 | 0.0004077
121 | Project-U#8-L.P.Piping including valves-10509 | N.A. | - | 0 | 0.0038246 | 0 | 0.0038246 | 0 | 0 |  |  | 0 | 0.0038246
122 | Project-U#8-L.T. Electrical for main plant.-10561 | N.A. | - | 0 | 8.7067e-05 | 0 | 8.7067e-05 | 0 | 0 |  |  | 0 | 8.7067e-05
123 | Project-U#8-Laying&Termination of HT cables-10561 | N.A. | - | 0 | 0.0008231 | 0 | 0.0008231 | 0 | 0 |  |  | 0 | 0.0008231
124 | Project-U#8-MainBoiler Structure&foundations-10501 | N.A. | - | 0 | 0.09941 | 0 | 0.09941 | 0 | 0 |  |  | 0 | 0.09941
125 | Project-U#8-Mandatory Spares for Ash HandlingPlant | N.A. | - | 0 | 0.0015616 | 0 | 0.0015616 | 0 | 0 |  |  | 0 | 0.0015616
126 | Project-U#8-Mandatory spares for C&I of Main Plant | N.A. | - | 0 | 0.0050295 | 0 | 0.0050295 | 0 | 0 |  |  | 0 | 0.0050295
127 | Project-U#8-Mandatory Spares for Electrical MainPa | N.A. | - | 0 | 0.015601 | 0 | 0.015601 | 0 | 0 |  |  | 0 | 0.015601
128 | Project-U#8-Mandatory Spares For TG & Auxilliaries | N.A. | - | 0 | 0.0062588 | 0 | 0.0062588 | 0 | 0 |  |  | 0 | 0.0062588
129 | Project-U#8-Misc. Cranes & hoists-10553 | N.A. | - | 0 | 0.0023537 | 0 | 0.0023537 | 0 | 0 |  |  | 0 | 0.0023537
130 | Project-U#8-Miscellaneous Pumps -10599 | N.A. | - | 0 | 0.0015672 | 0 | 0.0015672 | 0 | 0 |  |  | 0 | 0.0015672
131 | Project-U#8-Passanger lift for TG Building-10599 | N.A. | - | 0 | 0.0016358 | 0 | 0.0016358 | 0 | 0 |  |  | 0 | 0.0016358
132 | Project-U#8-Passanger/Material Lift at boiler side | N.A. | - | 0 | 0.00084731 | 0 | 0.00084731 | 0 | 0 |  |  | 0 | 0.00084731
133 | Project-U#8-Chemical Laboratory -10509 | N.A. | - | 0 | 0.0011648 | 0 | 0.0011648 | 0 | 0 |  |  | 0 | 0.0011648
134 | Project-U#8-Sewage Treatment Plant-10509 | N.A. | - | 0 | 0.0019006 | 0 | 0.0019006 | 0 | 0 |  |  | 0 | 0.0019006
135 | Project-U#8-Station Transformer-10541 | N.A. | - | 0 | 0.026576 | 0 | 0.026576 | 0 | 0 |  |  | 0 | 0.026576
136 | Project-U#8-Steam Turbine set-10503 | N.A. | - | 0 | 0.13864 | 0 | 0.13864 | 0 | 0 |  |  | 0 | 0.13864
137 | Project-U#8-TG set and its auxilleries- Condensor | N.A. | - | 0 | 0.012703 | 0 | 0.012703 | 0 | 0 |  |  | 0 | 0.012703
138 | Project-U#8-TG set and its auxilleries -Generator | N.A. | - | 0 | 0.032545 | 0 | 0.032545 | 0 | 0 |  |  | 0 | 0.032545
139 | Project-U#8-TG set and its auxilleries-Condensor | N.A. | - | 0 | 0.029273 | 0 | 0.029273 | 0 | 0 |  |  | 0 | 0.029273
140 | Project-U#8-TG set & its auxilleries-Derator-10503 | N.A. | - | 0 | 0.002758 | 0 | 0.002758 | 0 | 0 |  |  | 0 | 0.002758
141 | Project-U#8-TG set and its auxilleries-DMMakeUpSys | N.A. | - | 0 | 0.0010491 | 0 | 0.0010491 | 0 | 0 |  |  | 0 | 0.0010491
142 | Project-U#8-TG set and its auxilleries-Gas System | N.A. | - | 0 | 0.0056178 | 0 | 0.0056178 | 0 | 0 |  |  | 0 | 0.0056178
143 | Project-U#8-TG set and its auxilleries-GoveringSys | N.A. | - | 0 | 4.9466e-05 | 0 | 4.9466e-05 | 0 | 0 |  |  | 0 | 4.9466e-05
144 | Project-U#8-TG set and its auxilleries-HP/LP By-pa | N.A. | - | 0 | 0.010752 | 0 | 0.010752 | 0 | 0 |  |  | 0 | 0.010752
145 | Project-U#8-TG set and its auxilleries-HP/LP Dozin | N.A. | - | 0 | 0.00039941 | 0 | 0.00039941 | 0 | 0 |  |  | 0 | 0.00039941
146 | Project-U#8-TG set and its auxilleries-SealOilPump | N.A. | - | 0 | 9.8566e-05 | 0 | 9.8566e-05 | 0 | 0 |  |  | 0 | 9.8566e-05
147 | Project-U#8-TG set and its auxilleries-Vaccum Syst | N.A. | - | 0 | 0.010304 | 0 | 0.010304 | 0 | 0 |  |  | 0 | 0.010304
148 | Project-U#8-Turbine Lub. Oil System With Purifier | N.A. | - | 0 | 0.0022364 | 0 | 0.0022364 | 0 | 0 |  |  | 0 | 0.0022364
149 | Project-U#8-Ventillation system-10599 | N.A. | - | 0 | 0.0014389 | 0 | 0.0014389 | 0 | 0 |  |  | 0 | 0.0014389
150 | Asset Recived From Project-U#8-M.SPARE_Ventillation system-10599 | N.A. | - | 0 | 8.5482e-05 | 0 | 8.5482e-05 | 0 | 0 |  |  | 0 | 8.5482e-05
151 | Asset Recived From Project-U#8-Water Treatment Plant-10509 | N.A. | - | 0 | 0.0042384 | 0 | 0.0042384 | 0 | 0 |  |  | 0 | 0.0042384
152 | Asset Recived From Project-U#8-WORK SHOP MAD_SPARE-10565 | N.A. | - | 0 | 0.00030445 | 0 | 0.00030445 | 0 | 0 |  |  | 0 | 0.00030445
153 | Asset Recived From Project-U#8-Workshop-10565 | N.A. | - | 0 | 0.0013286 | 0 | 0.0013286 | 0 | 0 |  |  | 0 | 0.0013286
154 | Asset Recived From Project-U#8-CMR SYSTEM-10501 | N.A. | - | 0 | 0.0020736 | 0 | 0.0020736 | 0 | 0 |  |  | 0 | 0.0020736
155 | Asset Recived From Project-U#8-MandatorySpares-WTP-10.509 | N.A. | - | 0 | 8.1517e-05 | 0 | 8.1517e-05 | 0 | 0 |  |  | 0 | 8.1517e-05
156 | Asset Recived From Project-U#8-E.1.07_MandSpar 4 C&I MS 4MeasuringIns E.1.07_M S for C&I_ MS For Measuring Ins | N.A. | - | 0 | 0.078697 | 0 | 0.078697 | 0 | 0 |  |  | 0 | 0.078697
157 | Asset Recived From Project-U#8-BOP_ELECTRICAL-10612 | N.A. | - | 0 | 0.01637 | 0 | 0.01637 | 0 | 0 |  |  | 0 | 0.01637
158 | Asset Recived From Project-U#8-Bus Ducts-10612 | N.A. | - | 0 | 0.012548 | 0 | 0.012548 | 0 | 0 |  |  | 0 | 0.012548
159 | Asset Recived From Project-U#8-Cable trays & supports-10612 | N.A. | - | 0 | 0.00036009 | 0 | 0.00036009 | 0 | 0 |  |  | 0 | 0.00036009
160 | Project-U#8-PCR FURNITURE-10810 | N.A. | - | 0 | 0.00030684 | 0 | 0.00030684 | 0 | 0 |  |  | 0 | 0.00030684
161 | Project-U#8 Server Intel QUAD CORE 02No. HP Office Server | N.A. | - | 0 | 0.11918 | 0.11918 | 0 | 0 | 0 |  |  | 0 | 0
162 | Supply Erection testing and commissining of 1000 m3 ETP Civil works | N.A. | - | 0 | 0.68324 | 0.68324 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 664.8235 | 671.1026 | -6.2791 | 161.54 | 161.54 | 0 | 0 | 161.54 | -6.2791
FY 2028-29
0 | Add Cap (As per 296 of 2019)
A | Initial spares | Add Cap (As per 296 of 2019) | - | 0
1 | Boiler and Auxiliaries | Add Cap (As per 296 of 2019) | - | 7.2
1 | Procurement of Coal Mill XRP-903 Gear Box Type KMP-280 Spares of Unit # 8 at BM-NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 0 | 1.35 | 1.35 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply of Labyrinth Seal Rings with replaceable Inner liners for Coal Mill XRP-903 required for BM Unit-8, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.33134 | 0.33134 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply and Installation of coal mill liners(weld overlay) of XRP-903 Coal Mill in BM U-8, NPTPS,Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.33134 | 0.33134 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of Coal Mill XRP-903 Bowl & Bowl Hub of Unit # 8 at BM-NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 0 | 0.73326 | 0.73326 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply of impeller assembly for ID fan | Add Cap (As per 296 of 2019) | - | 0 | 0.5233 | 0.5233 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of Primary Air Fan & Forced Draught Fan Drive Coupling on OEM basis required at BM U-8, NPTPS, Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.1941 | 0.1941 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of Primary Air Fan PAF 17/11.8-2 Hydraulic Adjustment Device on OEM basis required at BM U-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.53521 | 0.53521 | 0 | 0 | 0 |  |  | 0 | 0
8 | Proc of spares for fabric expansion joints required at BM U-8, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.56972 | 0.56972 | 0 | 0 | 0 |  |  | 0 | 0
9 | Proc of separator body and seperator top spares for coal mill XRP-903 at BM U-8, NPTPS Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.42569 | 0.42569 | 0 | 0 | 0 |  |  | 0 | 0
10 | Proc of scrapper area & reject system spares for coal mill XRP-903 at BM U-8, NPTPS Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.27833 | 0.27833 | 0 | 0 | 0 |  |  | 0 | 0
11 | Proc of seal air fan spares at BM-8 NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.26432 | 0.26432 | 0 | 0 | 0 |  |  | 0 | 0
12 | Procurement of FD Fan Type FAF 17/9.5-1 Drive Coupling required at BM U-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | Procurement of complete planatary gear box-KMP -280/300 for coal mill XRP-903 at BM U-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Turbine and Auxiliaries | Add Cap (As per 296 of 2019) | - | 4.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of spares for Equipment Cooling Water Pumps (Make-FLOWMORE) of model FIG-5824 (SG Side) and FIG-5822 (TG side) at Unit-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.51812 | 0.51812 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply of spars for recovery & FF Pumps along with work at U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0.37713 | 0.37713 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of seal oil vacuum pump in unit 08 | Add Cap (As per 296 of 2019) | - | 0 | 0.27502 | 0.27502 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of AC pressure pipes (235MM OD, 200MM ID, 4.5M Length) for NDCT hot spray water distribution system in Unit-8 NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 0 | 0.42522 | 0.42522 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply of M/s Summits make Instrument Air Dryer & spares at U # 8 TM, Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.54787 | 0.54787 | 0 | 0 | 0 |  |  | 0 | 0
6 | Supply of PVC fills for NDCTs at U # 8 TM, Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.58245 | 0.58245 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of NB 600MM Gate valves for ACW self cleaning strainers in U#8 TM NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.42338 | 0.42338 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of Mechanical seals ( Make Leak-Proof) for various pumps in TM Unit-8 NPTPS Parli. | Add Cap (As per 296 of 2019) | - | 0 | 0.49233 | 0.49233 | 0 | 0 | 0 |  |  | 0 | 0
9 | Supply of SS 304 pipes & others at U # 8 TM, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.52905 | 0.52905 | 0 | 0 | 0 |  |  | 0 | 0
3 | Electrical and Instrumentation | Add Cap (As per 296 of 2019) | - | 6.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of Instrumentation Spares of LP Bypass System at Unit-8. | Add Cap (As per 296 of 2019) | - | 0 | 1.9615 | 1.9615 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of Schneider MICOM Numerical Relays for GRP and STPR swithcgear at NPTPS Unit-8 Testing | Add Cap (As per 296 of 2019) | - | 0 | 0.47613 | 0.47613 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of 220V DC Chloride make (formally caldyne) make battery chargers Spre of Unit 8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.23365 | 0.23365 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of 24V DC Chhabi make make battery chargers Spare of Unit 8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.22465 | 0.22465 | 0 | 0 | 0 |  |  | 0 | 0
5 | Procurement of Spare for Hitachi Hi-Rel make UPS systems installed at Unit-8 NPTPS Parli Vaijnath. | Add Cap (As per 296 of 2019) | - | 0 | 0.19186 | 0.19186 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of various test kit for testing U#8 such as energy meter calibration kit, DC earth faulth locator kit, promary current injection kit, breaker time measurement kit, numeric relay test kit and other testing instruments. | Add Cap (As per 296 of 2019) | - | 0 | 0.67345 | 0.67345 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of Energymeter Caliberation Software Module and hardware for upgrading Numeric Relay Test kit at Unit -8 Testing. | Add Cap (As per 296 of 2019) | - | 0 | 0.11863 | 0.11863 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of H T Motors. | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of critical L T Motors | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of ESP Hopper heaters (As a initial spares) Installed at EM U-8, NPTPS, Parli-Vaijnath under add cap scheme. | Add Cap (As per 296 of 2019) | - | 0 | 0.38586 | 0.38586 | 0 | 0 | 0 |  |  | 0 | 0
4 | Outdoor Plant(CHP/AHP/WTP) | Add Cap (As per 296 of 2019) | - | 6.64 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of Apron Feeder spares installed at CHP NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 1.6233 | 1.6233 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply of various drive and non drive pulleys for CHP U-8. | Add Cap (As per 296 of 2019) | - | 0 | 0.54529 | 0.54529 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply and installation of clamp pads & resting pads for Side Beam of Wagon Tippler for CHP U-8 | Add Cap (As per 296 of 2019) | - | 0 | 0.54802 | 0.54802 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply of unbalance motorozied vibrating feeder for S/R of U-7/8 CHP NPTPS Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.3958 | 0.3958 | 0 | 0 | 0 |  |  | 0 | 0
5 | Procurement of conveying and Instrument air compressor spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 1.77 | 1.77 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of vacuum pump spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0.2291 | 0.2291 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of fluidizing blower spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0.11796 | 0.11796 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of slurry pump spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of Clinker grinder spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0.12334 | 0.12334 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B | Reassessment of remaining BOP work after insolvency of M/s Sunil Hi-Tech | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Project balance E&M and procurement of mandetory spares | MERC CAPEX Approval in MTR Order 296 of 2019 | Order 296 of 2019 | 41.4534 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work order for Contract of Supply and application of Fire Stop Mortar Seal and Fire Retardant Cable Coating Compound at NPTP U-8 Parli Project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 3.4589 | 3.4589 | 0 | 0 | 0 |  |  | 0 | 0
2 | Work order for contract for Supply Installaion Testing & Commissioning Smoke Detection & alaram system | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 2.5606 | 2.5606 | 0 | 0 | 0 |  |  | 0 | 0
3 | Work order for contract for Supply Installaion Testing & Commissioning of Balance Fire Fighting System at NPTP U-8 Parli Project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.0502 | 1.0502 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, Errection, testing & commissioning works of RWP, PT potable chlorination system, ETP system control panel, automation of LDO, HFO tank foam system Hose boxes with RRL hoses and branch pipe and allied system at NPTP | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.8496 | 0.8496 | 0 | 0 | 0 |  |  | 0 | 0
5 | Work Order contract for supply, installation Testing & Commissioning of telephone exchange (EPBAX) & Telephone System at NPTP U-8 Parli project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.91256 | 0.91256 | 0 | 0 | 0 |  |  | 0 | 0
6 | Balance Supply of Electrical Lab Equipment at NPTP parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.60826 | 0.60826 | 0 | 0 | 0 |  |  | 0 | 0
7 | Work order for contract for Supply Installaion Testing & Commissioning with required material to complete Balance CHP work at NPTP U-8 Parli Project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.41 | 0.41 | 0 | 0 | 0 |  |  | 0 | 0
8 | Supply, Errection, testing & commissioning of Interconnecting Conveyor no.9 & 10 from U-8 to U-6&7 of CHP at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 5.3319 | 5.3262 | 0.0056593 | 0 | 0 |  |  | 0 | 0.0056593
9 | SUPPLY ,INSTA,TEST ,COMM ELECTRICAL SYS | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | SUPPLY,INSTAL,TEST,COMM OF CRANS&HOIST | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.8105 | 3.6223 | -1.8118 | 0 | 0 |  |  | 0 | -1.8118
11 | Supply, Errection, testing & commissioning of Dust Extraction system at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.8061 | 0 | 1.8061 | 0 | 0 |  |  | 0 | 1.8061
12 | Supply, Errection, testing & commissioning of DSS & DFDS at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 4.3391 | 4.34 | -0.0008856 | 0 | 0 |  |  | 0 | -0.0008856
13 | Supply, Errection, testing & commissioning of Monorail at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.1892 | 1.1891 | 7.77e-05 | 0 | 0 |  |  | 0 | 7.77e-05
14 | Supply, Errection, testing & commissioning of various Control & Instrumentation equipments at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.72225 | 0.72225 | 0 | 0 | 0 |  |  | 0 | 0
15 | Supply, Errection, testing & commissioning of Air Conditioning System at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.15304 | 0.44729 | -0.29425 | 0 | 0 |  |  | 0 | -0.29425
16 | Supply, Errection, testing & commissioning of Ventilation System at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 2.1136 | 1.2036 | 0.91 | 0 | 0 |  |  | 0 | 0.91
17 | Supply, Errection, testing & commissioning of Elevator works. | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 3.5173 | 4.4273 | -0.91 | 0 | 0 |  |  | 0 | -0.91
18 | Work contract for dismentaling, supply, erection & commissioning of MRHS | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 2.2335 | 2.2335 | 0 | 0 | 0 |  |  | 0 | 0
19 | Supply, Errection, testing & commissioning of FF System, Smoke detection & Fire stop mortar & Fire retradant cable coating for conveyor 09 & 10 | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.22171 | 0.51866 | -0.29696 | 0 | 0 |  |  | 0 | -0.29696
20 | Supply, Errection, testing & commissioning of Chimney Elevator | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.0608 | 0 | 1.0608 | 0 | 0 |  |  | 0 | 1.0608
21 | Supply, Errection, testing & commissioning work of GEHO Pumps. | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0 | 1.06 | -1.06 | 0 | 0 |  |  | 0 | -1.06
22 | Procurement of various Mandetory spares of BOP packages | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 5.47 | 6.54 | -1.07 | 0 | 0 |  |  | 0 | -1.07
0 | Balance civil work of BOP scope at 250 MW Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 45.3238 | 0.55712 | 16.72 | -16.1629 | 0 | 0 |  |  | 0 | -16.1629
1 | Area grading | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 6.9866 | 0.89 | 6.0966 | 0 | 0 |  |  | 0 | 6.0966
2 | CMD | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.2411 | 1.3549 | -0.11383 | 0 | 0 |  |  | 0 | -0.11383
3 | Conveyor 09, 10 & TP 06 | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 14.5605 | 12.13 | 2.4305 | 0 | 0 |  |  | 0 | 2.4305
4 | Finishing item | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 8.085 | 4.6506 | 3.4344 | 0 | 0 |  |  | 0 | 3.4344
5 | Drain & nala | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 5.0848 | 11.79 | -6.7052 | 0 | 0 |  |  | 0 | -6.7052
6 | Internal roads | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 9.7521 | 1.5 | 8.2521 | 0 | 0 |  |  | 0 | 8.2521
7 | Stacker & reclaimer | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.1627 | 0 | 1.1627 | 0 | 0 |  |  | 0 | 1.1627
0 | Other Add Cap | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Laboratory set up | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of Analytical Instruments for condition monitoring Laboratory for 1X250 MW of NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.5 | 0.49655 | 0.49655 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply of Analytical Instruments for Water Analysis Laboratory for 1X250 MW of NPTPS, Parli-V | Add Cap (As per 296 of 2019) | - | 1.23 | 0.29847 | 0.29847 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of Analytical Instruments for Environment Laboratory for 1 x 250 MW, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.39 | 0.3658 | 0.3658 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply of Analytical Instruments for Precision Laboratory for 1 x 250 MW, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply of Analytical Instruments for General Laboratory of Water Treatment Plant of 1 x 250 MW, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Supply of Corrosion Monitor/Meter, Corrosion Coupon & Coupon Rack for 1X250 MW of NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.34 | 0.34736 | 0.34736 | 0 | 0 | 0 |  |  | 0 | 0
7 | Supply of Analytical Instruments for Coal Analysis Laboratory for 1X250 MW of NPTPS, Parli-V | Add Cap (As per 296 of 2019) | - | 1.65 | 0.39444 | 0.39444 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Grade slab (WTP Area) | Add Cap (As per 296 of 2019) | - | 1 | 0.99752 | 0.99752 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Grade slab (Near AHP Building) | Add Cap (As per 296 of 2019) | - | 0.75 | 0.74556 | 0.74556 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Temporary shed for empty barrles & filled barrles | Add Cap (As per 296 of 2019) | - | 0.5 | 0.45635 | 0.45635 | 0 | 0 | 0 |  |  | 0 | 0
12 | Cabins for operators at TP. | Add Cap (As per 296 of 2019) | - | 0.2 | 0.18583 | 0.18583 | 0 | 0 | 0 |  |  | 0 | 0
13 | Compound wall for isolation of administrative building. | Add Cap (As per 296 of 2019) | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Work of providing/ fixing of internal partitions of aluminium/Nova palm/glass/wooden for Unit 8 service building & other allied builings in the premises. | Add Cap (As per 296 of 2019) | - | 0.7 | 0.67356 | 0.67356 | 0 | 0 | 0 |  |  | 0 | 0
15 | Provision of DM and softening water line interconnection from u-6,7 to u-8 & Provision of recovery of waste water from sandava pump house,NDCT. | Add Cap (As per 296 of 2019) | - | 3 | 1.0266 | 1.0266 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | Add Cap (As per 296 of 2019) | - | 0 | 1.8371 | 1.8371 | 0 | 0 | 0 |  |  | 0 | 0
16 | Hydraulic drive system modification. | Add Cap (As per 296 of 2019) | - | 2.5 | 2.4384 | 2.4384 | 0 | 0 | 0 |  |  | 0 | 0
17 | Link conveyor from Con-2 of U-6/7 to Con.-2AB of U-8. | Add Cap (As per 296 of 2019) | - | 3.7 | 4.6434 | 22.6564 | -18.0129 | 0 | 0 |  |  | 0 | -18.0129
18 | Ozone plant for Unit -8 | Add Cap (As per 296 of 2019) | - | 20 | 20.0947 | 2.1929 | 17.9018 | 0 | 0 |  |  | 0 | 17.9018
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | Water management system | Add Cap (As per 296 of 2019) | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8, 20 | Procurement & Installation of EMS system at Unit-8 NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 1 | 0.14417 | 0.14417 | 0 | 0 | 0 |  |  | 0 | 0
21 | Conveyor-5 of stacking/reclaiming belt double drive arrangement. | Add Cap (As per 296 of 2019) | - | 2 | 2.0432 | 2.0432 | 0 | 0 | 0 |  |  | 0 | 0
22 | Chemical lab building | Add Cap (As per 296 of 2019) | - | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Chemical store | Add Cap (As per 296 of 2019) | - | 2.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Lawn development around NDCT. | Add Cap (As per 296 of 2019) | - | 0.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | Tree plantation & greenery along road side. | Add Cap (As per 296 of 2019) | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | Greenery development in area between WTP & main plant. | Add Cap (As per 296 of 2019) | - | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | Construction of staff rooms & store for CHP maint.. | Add Cap (As per 296 of 2019) | - | 1 | 0.90703 | 0.90703 | 0 | 0 | 0 |  |  | 0 | 0
28 | Dsludg filteration for raw water | Add Cap (As per 296 of 2019) | - | 17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29 | PLC/UPS system upgradation | Add Cap (As per 296 of 2019) | - | 0.5 | 0.40149 | 0.40149 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | FGD at Parli Unit # 8 | MERC/CAPEX/2021-2022/0284 | 2022-06-27 | 89.24 | 4.1 | 0 | 4.1 | 0 | 0 |  |  | 0 | 4.1
22.1 | FGD at Parli Unit # 8 | MERC/CAPEX/2021-2022/0284 | 2022-06-27 | 85.2 | 95.21 | 108.86 | -13.65 | 0 | 0 |  |  | 0 | -13.65
0 | IDC | MERC/CAPEX/2021-2022/0284 | 2022-06-27 | 4.04 | 4.04 | 0 | 4.04 | 0 | 0 |  |  | 0 | 4.04
HO DPR 16 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 2.23 | 2.23 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Detailed Project Report on Boiler plant performance improvement and availability improvement schemes at Boiler Maintenance 1x250MW Unit-8 TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Procurement & Replacement of Complete Economizer Upper & Lower Bank Coil Assemblies at Unit-8, NPTPS Parli-V | Yet to be approved | - | 0 | 5.68 | 5.68 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 4.5 | 4.5 | 0 | 0 | 0 |  |  | 0 | 0
1.3 | Procurement & replacement of PA Fan PAF 17/11.8-2 and FD Fan FAF 17/9.5-1 Complete Blade set required at BM U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 5.45 | 5.45 | 0 | 0 | 0 |  |  | 0 | 0
1.4 | Procurement & Replacement of Coal Mill Gear Box Type KMP 280 at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 7.43 | 7.43 | 0 | 0 | 0 |  |  | 0 | 0
1.5 | Procurement & replacement of Bowl & Bowl Hub Assembly of Coal Mill XRP-903 required at BM U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 3.1 | 3.1 | 0 | 0 | 0 |  |  | 0 | 0
1.6 | Procurement of Complete Journal Assembly without Grinding roll for Coal Mill XRP-903 required at BM U-8 NPTPS Parli-V | Yet to be approved | - | 0 | 1.29 | 1.29 | 0 | 0 | 0 |  |  | 0 | 0
1.7 | Procurement of Hydraulic Adjustment Device for FD Fan FAF 17/9.5-1 at BM U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 1.4 | 1.4 | 0 | 0 | 0 |  |  | 0 | 0
1.8 | SWAS upgradation at U#8 | Yet to be approved | - | 0 | 4.8 | 4.8 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement & Replacement of Complete Platen super heater coils Coil Assemblies at Unit-8, TPS Parli-V, Procurement & Replacement of Complete LTSH upper & lower bank Coil Assemblies at Unit-8, TPS Parli-V & Procurement & Replacement of Coal Mill Gear Box Type KMP 280 at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Procurement & Replacement of Complete Platen super heater coils Coil Assemblies at Unit-8, TPS Parli-V | Yet to be approved | - | 0 | 12 | 12 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Procurement & Replacement of Complete LTSH upper & lower bank Coil Assemblies at Unit-8, TPS Parli-V | Yet to be approved | - | 0 | 9.35 | 9.35 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Procurement & Replacement of Coal Mill Gear Box Type KMP 280 at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 7.8 | 7.8 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-8, Parli TPS Procurement & replacement of PA & FD fan rotar hub assembly at Unit-8 TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Procurement & replacement of PA & FD fan rotar hub assembly at Unit-8 TPS Parli-V | Yet to be approved | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
4 | DPR on Refurbishment of TG Governing system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Refurbishment of TG Governing system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
5 | DPR on Performance improvement of Natural Draft Cooling Tower (NDCT) at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Performance improvement of Natural Draft Cooling Tower (NDCT) by replacement of PVC fills, AC cement pipes, strengthening of Hot water distribution system, replacement of beams, columns, support structures, etc. at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
6 | DPR on Procurement of ACW & CW pump along with mandatory spares at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | DPR on Procurement of ACW & CW pump along with mandatory spares at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 35 | 35 | 0 | 0 | 0 |  |  | 0 | 0
7 | DPR on Procurement of CEP pump and BFP Booster pump along with mandatory spares at Unit-8, PTPS, Parli V and Procurement of Energy Efficient Cartridges of Boiler Feed Pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Procurement of CEP pump and BFP Booster pump along with mandatory spares at Unit-8, PTPS, Parli | Yet to be approved | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
7.2 | Procurement of Energy Efficient Cartridges of Boiler Feed Pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
8 | DPR on Procurement of turbine blades of HP, IP & LP rotor in Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.1 | DPR on Procurement of turbine blades of HP, IP & LP rotor in Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 35 | 35 | 0 | 0 | 0 |  |  | 0 | 0
9 | DPR on Repair & Reconditioning of Water treatment plant at Unit-8, PTPS, Parli V and Performance improvement of centralised AC plant at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.1 | Reconditioning of Acid and Alkali Unloading and storage system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
9.2 | Reconditioning & repairing of WTP DM Plant regeneration system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
9.3 | Performance improvement of centralised AC plant by reconditioning of cooling tower, various pumps, heat exchangers, etc. at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
10 | DPR on Procurement of Control Fluid (HPCF) pump, Lube Oil pump, Emergency Oil pump, Jacking Oil pump, Seal oil pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.1 | DPR on Procurement of Control Fluid (HPCF) pump, Lube Oil pump, Emergency Oil pump, Jacking Oil pump, Seal oil pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
11 | DPR on Procurement of H2 cooler, BFP coolers, generator exciter cooler, Seal and Lube oil coolers at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.1 | DPR on Procurement of H2 cooler, BFP coolers, generator exciter cooler, Seal and Lube oil coolers at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
12 | Supply, installation & commissioning of 220V 2140AH,24V 830AH & 710AH, 360V 570AH Mains UPS,110V 110AH AHP PLC , 110V , 103 AH DM plant battery set for unit 8 , NPTPS Parli-V & Procurement of HT motors at U#8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.1 | Supply, installation & commissioning of 220V 2140AH,24V 830AH & 710AH, 360V 570AH Mains UPS,110V 110AH AHP PLC , 110V , 103 AH DM plant battery set for unit 8 , NPTPS Parli-V | Yet to be approved | - | 0 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
12.2 | Procurement of HT motors at U#8 | Yet to be approved | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
13 | DPR on various instrumentation & control schemes at U#8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | Upgradation of MAX-DNA DCS system at U#8 (HMI upgradation) | Yet to be approved | - | 0 | 6.81 | 6.81 | 0 | 0 | 0 |  |  | 0 | 0
13.2 | Upgradation of existing Pcal system with plant performance analysis diagnostic and optimization system (PADO) at Unit 8 New Parli TPS | Yet to be approved | - | 0 | 1.4 | 1.4 | 0 | 0 | 0 |  |  | 0 | 0
13.3 | Upgradation of coal feeder for I&C Unit8 PTPS Parli V. | Yet to be approved | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
13.4 | Procurement of smart control positioner at I&C Unit8 PTPS Parli V. | Yet to be approved | - | 0 | 0.95 | 0.95 | 0 | 0 | 0 |  |  | 0 | 0
13.5 | Upgradation Electronic control drive for I&C Unit8 PTPS Parli V. | Yet to be approved | - | 0 | 3.05 | 3.05 | 0 | 0 | 0 |  |  | 0 | 0
13.6 | Upgradation of turbovisory & vibration monitoring system control panel. | Yet to be approved | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
14 | Performance improvement by system up gradation at CHP & DPR for normalization and stabilization of coal handling plant performance at Parli TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.1 | Supply and Commissioning of Energy Efficient Evaporative Cooling System for Control Panel & Breaker room of CHP Unit-8 For PARLI TPS | Yet to be approved | - | 0 | 1.38 | 1.38 | 0 | 0 | 0 |  |  | 0 | 0
14.2 | Supply and commissioning of Suspended Magnets for U-8 CHP NPTPS | Yet to be approved | - | 0 | 3.3 | 3.3 | 0 | 0 | 0 |  |  | 0 | 0
14.3 | Stacker-reclaimer Bucket wheel drive modification work of U- 8 CHP | Yet to be approved | - | 0 | 3.32 | 3.32 | 0 | 0 | 0 |  |  | 0 | 0
14.4 | Apron feeder drive modification from Hydraulic to Electro-Mechanical at CHP U-8 NPTPS | Yet to be approved | - | 0 | 4.02 | 4.02 | 0 | 0 | 0 |  |  | 0 | 0
14.5 | Procurement of U-8 W/T Major spares | Yet to be approved | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
14.6 | Provision of Soft starter / VFD for Various conveyor | Yet to be approved | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
14.7 | TP-3 chute modification at U-8 CHP. | Yet to be approved | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
14.8 | Design, supply and commissioning of solar operated lighting system in CHP U-8. | Yet to be approved | - | 0 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
14.9 | Installation of CCTV survillance system alongwith all conveyors. | Yet to be approved | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
15 | DPR for maximiation of Coal Handling Plant efficiency & DPR on life enhancement of Coal Handling Plant | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | W/T control room & bunker house battery & UPS upgradation | Yet to be approved | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Refurbishment of conveyor no. 2 A/B & 6 A/B drive system of CHP U-8 TPS Parli. | Yet to be approved | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Provision of Soft starter / VFD for Various conveyor | Yet to be approved | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Procurement & installation of Belt tear detection system | Yet to be approved | - | 0 | 0 | 0 | 0 | 4.5 | 4.5 |  |  | 4.5 | 0
15.5 | Conveyor gravity takeup infrastructure strengthening work | Yet to be approved | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
15.6 | U-8 CHP apron feeder-I to Conveyor 1 A/B chute modification work . | Yet to be approved | - | 0 | 0 | 0 | 0 | 4 | 4 |  |  | 4 | 0
16 | DPR for stabiliazation of Coal Handling Performance. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.1 | Drive modification of Stacker Reclaimer slewing system. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.2 | Retrofitting of Side Arm Charger-I & II at CHP U-8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.3 | Upgradation of GE/Schineder make PLC system atU-8 CHP. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.4 | Refurbishment of Apron Feeder at CHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.5 | Provision of moveable stacker and crusher in CHP coal stack yard at CHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.6 | Procurement of Loco & Bulldozer at CHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | DPR on dry fly ash utilisation improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.1 | Design, supply, erection, installation & comissioning of intermediate silo with sub system at AHP U-8. | Yet to be approved | - | 0 | 38 | 38 | 0 | 0 | 0 |  |  | 0 | 0
18 | DPR on ash handling plant improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | Design, supply, erection & comissioning of weigh bridge for silo at AHP U-8. | Yet to be approved | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
18.2 | Supply, installation & comissioning of energy efficient air compressor at AHP U-8. | Yet to be approved | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
18.3 | PROCUREMENT OF COMPLETE ASSEMBLY OF SAM MAKE AR-150/510 PUMPS (2 NOS) FOR REPLACEMENT OF ASH SLURRY PUMPS OF BOTTOM ASH SLURRY DISPOSAL FROM SLURRY TANK TO ASH BUND IN SLURRY PUMP HOUSE. | Yet to be approved | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | PROCUREMENT OF COMPLETE ASSEMBLY OF SAM MAKE ZM-II 530/02 (2 NOS) FOR REPLACEMENT OF HP PUMPS OF BOTTOM ASH & COARSE ASH EVACUATION FROM BA/CA HOPPERS TO SLURRY TANK IN ASH WATER PUMP HOUSE. 0.75 0.89 | Yet to be approved | - | 0 | 0.4 | 0.4 | 0 | 0 | 0 |  |  | 0 | 0
18.5 | Procurement of vacuum pumps complete assembly for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
18.6 | Procurement of vacuum pumps complete assembly for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
18.7 | Procurement of Feed Gate Complete Assembly along with modified metallurgy to enhance the life of Clinker Grinder. | Yet to be approved | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
18.8 | Procurement of Double Roll Clinker Grinder Complete Assembly with Drive Unit installed at AHP | Yet to be approved | - | 0 | 1.25 | 1.25 | 0 | 0 | 0 |  |  | 0 | 0
18.9 | Procurement of Instrument Air Dryers assembly for performance improvement | Yet to be approved | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | Procurement of various types of Isolation Valves assembly, Dome Valves assembly, Root Valve Assembly & Expansion Bellows Assembly for Dry Ash Conveing performance improvement | Yet to be approved | - | 0 | 3.6 | 3.6 | 0 | 0 | 0 |  |  | 0 | 0
19 | DPR on ash handling plant improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | Design, supply, erection, installation & comissioning of DM water close loop cooling system for air compressors at AHP U-8. | Yet to be approved | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
19.2 | Up-gradation of Existing Schneider make PLC (HMI + PLC hardware) installed at AHP Unit -8 at Parli TPS. | Yet to be approved | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
19.3 | Procurement of HT motors for AHP U-8 Parli TPS. | Yet to be approved | - | 0 | 2.3 | 2.3 | 0 | 0 | 0 |  |  | 0 | 0
19.4 | PROCUREMENT OF CRITICAL GEARBOXES AND FLUID COUPLINGS INTERNAL ASSEMBLIES FOR SLURRY PUMPS AND SILO HCSD SYSTEM INSTALLED AT AHP, PARLI TPS. | Yet to be approved | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
19.5 | Procurement of Atlas Copco Make Instrument Air Compressors Critical/Non-Critical Spares sub-assembly for performance improvement | Yet to be approved | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
19.6 | Upgradation and improvement in Hopper Temperature monitoring system by providing Rf Type Hopper Level Sensors for performance improvement of conveying of Dry ash evacuation system. | Yet to be approved | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
20 | DPR on ash handling plant improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.1 | Design, supply, erection, installation & comissioning ESP 1st & 2nd field dry fly ash evacuation & conveying system at AHP U-8. | Yet to be approved | - | 0 | 21.25 | 21.25 | 0 | 0 | 0 |  |  | 0 | 0
20.2 | Design, supply, erection, installation & comissioning of dry ash evacuation & conveying system for APH & Economiser ash hoppers at AHP U-8. | Yet to be approved | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
21 | Verious Civil schemes in Unit 8 NPTPS Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Construction of chemical laboratory building at Unit 8, NPTPS, Parli V. | Yet to be approved | - | 0 | 3.78 | 3.78 | 0 | 0 | 0 |  |  | 0 | 0
21.2 | Construction of Alum/salt storage area at Unit No.8 (1X250MW) NPTPS Parli Vaijnath. | Yet to be approved | - | 0 | 3.46 | 3.46 | 0 | 0 | 0 |  |  | 0 | 0
21.3 | Construction of Fire Fighting station at Unit-8, NPTPS Parli V. | Yet to be approved | - | 0 | 1.86 | 1.86 | 0 | 0 | 0 |  |  | 0 | 0
21.4 | Construction of workshop building at Unit-8, NPTPS Parli V. | Yet to be approved | - | 0 | 2.13 | 2.13 | 0 | 0 | 0 |  |  | 0 | 0
22 | CHP improvement scheme at 250 MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.1 | CHP improvement scheme at 250 MW | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0.56615 | 0.56615 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) GA | 0 | - | 0 | 1.2131 | 1.2737 | -0.060588 | 0.29 | 0.29 |  |  | 0.29 | -0.060588
0 | 0 | 0 | - | 0 | 0.29 | 0 | 0.29 | 0 | 0 |  |  | 0 | 0.29
0 | C) Asset received from Project U#8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Asset Recived From Civil-U#8-Land-10101 | N.A. | - | 0 | 0.0031293 | 0 | 0.0031293 | 0 | 0 |  |  | 0 | 0.0031293
2 | Asset Recived From Civil-U#8-T.G. Building-10201 | N.A. | - | 0 | 0.010038 | 0 | 0.010038 | 0 | 0 |  |  | 0 | 0.010038
3 | Asset Recived From Civil-U#8-T.G. Building(BC)bay&control room-10201 | N.A. | - | 0 | 0.0045784 | 0 | 0.0045784 | 0 | 0 |  |  | 0 | 0.0045784
4 | Asset Recived From Civil-U#8-StructuralSteelWorks4TGBldgA2EBays-10201 | N.A. | - | 0 | 0.0013976 | 0 | 0.0013976 | 0 | 0 |  |  | 0 | 0.0013976
5 | Asset Recived From Civil-U#8-WTP Building-10201 | N.A. | - | 0 | 0.00011482 | 0 | 0.00011482 | 0 | 0 |  |  | 0 | 0.00011482
6 | Asset Recived From Civil-U#8-DG SET ROOM CUM AIR COMP. HOUSE-10201 | N.A. | - | 0 | 0.00010598 | 0 | 0.00010598 | 0 | 0 |  |  | 0 | 0.00010598
7 | Asset Recived From Civil-U#8-WTP-Raw/Fire water pump House-10233 | N.A. | - | 0 | 0.00069019 | 0 | 0.00069019 | 0 | 0 |  |  | 0 | 0.00069019
8 | Asset Recived From Civil-U#8-SERVICE BUILDING -10211 | N.A. | - | 0 | 0.00055144 | 0 | 0.00055144 | 0 | 0 |  |  | 0 | 0.00055144
9 | Asset Recived From Civil-U#8-Canteen -10233 | N.A. | - | 0 | 0.00072491 | 0 | 0.00072491 | 0 | 0 |  |  | 0 | 0.00072491
10 | Asset Recived From Civil-U#8-PARKING SHED -10233 | N.A. | - | 0 | 6.111e-06 | 0 | 6.111e-06 | 0 | 0 |  |  | 0 | 6.111e-06
11 | Asset Recived From Civil-U#8-Time Security Building -10233 | N.A. | - | 0 | 3.595e-05 | 0 | 3.595e-05 | 0 | 0 |  |  | 0 | 3.595e-05
12 | Asset Recived From Civil-U#8-Misc.Building/structure/Watchtower-10233 | N.A. | - | 0 | 0.00017243 | 0 | 0.00017243 | 0 | 0 |  |  | 0 | 0.00017243
13 | Asset Recived From Civil-U#8-Boundry compound wall Mall-10233 | N.A. | - | 0 | 0.15766 | 0 | 0.15766 | 0 | 0 |  |  | 0 | 0.15766
14 | Asset Recived From Civil-U#8-Workshop civil work-10233 | N.A. | - | 0 | 4.188e-05 | 0 | 4.188e-05 | 0 | 0 |  |  | 0 | 4.188e-05
15 | Asset Recived From Civil-U#8-Interior Work for CEC-I Office-10233 | N.A. | - | 0 | 5.6438e-05 | 0 | 5.6438e-05 | 0 | 0 |  |  | 0 | 5.6438e-05
16 | Asset Recived From Civil-U#8-WTP-Raw water reservoir -10305 | N.A. | - | 0 | 0.0012248 | 0 | 0.0012248 | 0 | 0 |  |  | 0 | 0.0012248
17 | Asset Recived From Civil-U#8-WTP-Clarifier -10305 | N.A. | - | 0 | 0.0011652 | 0 | 0.0011652 | 0 | 0 |  |  | 0 | 0.0011652
18 | Asset Recived From Civil-U#8-WTP-Clarifier Water Storage Tank-10305 | N.A. | - | 0 | 0.00019514 | 0 | 0.00019514 | 0 | 0 |  |  | 0 | 0.00019514
19 | Asset Recived From Civil-U#8-C.W. pump house & forebay-10310 | N.A. | - | 0 | 0.00052946 | 0 | 0.00052946 | 0 | 0 |  |  | 0 | 0.00052946
20 | Asset Recived From Civil-U#8-Construction of STP for Colony-10322 | N.A. | - | 0 | 0.00017966 | 0 | 0.00017966 | 0 | 0 |  |  | 0 | 0.00017966
21 | Asset Recived From Civil-U#8-Cooling Towers-10311 | N.A. | - | 0 | 0.37628 | 0 | 0.37628 | 0 | 0 |  |  | 0 | 0.37628
22 | Asset Recived From Civil-U#8-Railway sidings-10412 | N.A. | - | 0 | 0.13615 | 0 | 0.13615 | 0 | 0 |  |  | 0 | 0.13615
23 | Asset Recived From Civil-U#8-In plant Roads -10401 | N.A. | - | 0 | 0.0009103 | 0 | 0.0009103 | 0 | 0 |  |  | 0 | 0.0009103
24 | Asset Recived From Civil-U#8-Pipe Rack -10419 | N.A. | - | 0 | 0.00041823 | 0 | 0.00041823 | 0 | 0 |  |  | 0 | 0.00041823
25 | Asset Recived From Civil-U#8-Transformar yard area -10541 | N.A. | - | 0 | 0.00053169 | 0 | 0.00053169 | 0 | 0 |  |  | 0 | 0.00053169
26 | Asset Recived From Civil-U#8-BA-Boiler and Auxilary foundation-10501 | N.A. | - | 0 | 0.0061116 | 0 | 0.0061116 | 0 | 0 |  |  | 0 | 0.0061116
27 | Asset Recived From Civil-U#8-BA-FD FAN FOUNDATIONS -10501 | N.A. | - | 0 | 0.00011166 | 0 | 0.00011166 | 0 | 0 |  |  | 0 | 0.00011166
28 | Asset Recived From Civil-U#8-BA-PA FAN FOUNDATION -10501 | N.A. | - | 0 | 0.00011166 | 0 | 0.00011166 | 0 | 0 |  |  | 0 | 0.00011166
29 | Asset Recived From Civil-U#8-BA-I.D. Fan foundation -10501 | N.A. | - | 0 | 0.00022332 | 0 | 0.00022332 | 0 | 0 |  |  | 0 | 0.00022332
30 | Asset Recived From Civil-U#8-BA-MILL FOUNDATION-10501 | N.A. | - | 0 | 0.00019826 | 0 | 0.00019826 | 0 | 0 |  |  | 0 | 0.00019826
31 | Asset Recived From Civil-U#8-BA-BUNKER FOUNDATION & STRUCTURE-10515 | N.A. | - | 0 | 0.0013925 | 0 | 0.0013925 | 0 | 0 |  |  | 0 | 0.0013925
32 | Asset Recived From Civil-U#8-ESP-10501 | N.A. | - | 0 | 0.00070722 | 0 | 0.00070722 | 0 | 0 |  |  | 0 | 0.00070722
33 | Asset Recived From Civil-U#8-ESP Control Room-10501 | N.A. | - | 0 | 0.00042763 | 0 | 0.00042763 | 0 | 0 |  |  | 0 | 0.00042763
34 | Asset Recived From Civil-U#8-RCC Chimney -10501 | N.A. | - | 0 | 0.0046127 | 0 | 0.0046127 | 0 | 0 |  |  | 0 | 0.0046127
35 | Asset Recived From Civil-U#8-WTP-D.M.Plant equipment fdn. etc.-10509 | N.A. | - | 0 | 6.3898e-05 | 0 | 6.3898e-05 | 0 | 0 |  |  | 0 | 6.3898e-05
36 | Asset Recived From Civil-U#8-CHP-Wagon Tippler-10515 | N.A. | - | 0 | 0.00094041 | 0 | 0.00094041 | 0 | 0 |  |  | 0 | 0.00094041
37 | Asset Recived From Civil-U#8-CHP-Crusher House -10515 | N.A. | - | 0 | 0.00074704 | 0 | 0.00074704 | 0 | 0 |  |  | 0 | 0.00074704
38 | Asset Recived From Civil-U#8-CHP-Stacker Reclaimer -10515 | N.A. | - | 0 | 0.00028485 | 0 | 0.00028485 | 0 | 0 |  |  | 0 | 0.00028485
39 | Asset Recived From Civil-U#8-CHP-Stock Yard-10515 | N.A. | - | 0 | 0.00015851 | 0 | 0.00015851 | 0 | 0 |  |  | 0 | 0.00015851
40 | Asset Recived From Civil-U#8-CHP-ConveyorPedetals&TransferPoint-10515 | N.A. | - | 0 | 0.00055408 | 0 | 0.00055408 | 0 | 0 |  |  | 0 | 0.00055408
41 | Asset Recived From Civil-U#8-CHP-MCC ROOM -10515 | N.A. | - | 0 | 0.00026945 | 0 | 0.00026945 | 0 | 0 |  |  | 0 | 0.00026945
42 | Asset Recived From Civil-U#8-AHP-RCC Ash Silo -10501 | N.A. | - | 0 | 0.00016423 | 0 | 0.00016423 | 0 | 0 |  |  | 0 | 0.00016423
43 | Asset Recived From Civil-U#8-AHP-Staicase near Silo-10501 | N.A. | - | 0 | 1.7302e-05 | 0 | 1.7302e-05 | 0 | 0 |  |  | 0 | 1.7302e-05
44 | Asset Recived From Civil-U#8-AHP-Drain sump in Silo Area -10501 | N.A. | - | 0 | 8.551e-06 | 0 | 8.551e-06 | 0 | 0 |  |  | 0 | 8.551e-06
45 | Asset Recived From Civil-U#8-AHP-Slurry Mixing Tank Fdn.-10501 | N.A. | - | 0 | 1.6923e-05 | 0 | 1.6923e-05 | 0 | 0 |  |  | 0 | 1.6923e-05
46 | Asset Recived From Civil-U#8-AHP-HCSD PUMP HOUSE-10501 | N.A. | - | 0 | 5.8934e-05 | 0 | 5.8934e-05 | 0 | 0 |  |  | 0 | 5.8934e-05
47 | Asset Recived From Civil-U#8-AHP-Ash Slurry Pump House -10501 | N.A. | - | 0 | 0.00014947 | 0 | 0.00014947 | 0 | 0 |  |  | 0 | 0.00014947
48 | Asset Recived From Civil-U#8-AHP-Ash Slurry Sump-10501 | N.A. | - | 0 | 4.5159e-05 | 0 | 4.5159e-05 | 0 | 0 |  |  | 0 | 4.5159e-05
49 | Asset Recived From Civil-U#8-AHP-Ash Water Tank-10501 | N.A. | - | 0 | 3.422e-05 | 0 | 3.422e-05 | 0 | 0 |  |  | 0 | 3.422e-05
50 | Asset Recived From Civil-U#8-AHP-Bottom Ash Hopper-10501 | N.A. | - | 0 | 4.409e-05 | 0 | 4.409e-05 | 0 | 0 |  |  | 0 | 4.409e-05
51 | Asset Recived From Civil-U#8-AHP-Drain sump in BAH Area -10501 | N.A. | - | 0 | 8.575e-06 | 0 | 8.575e-06 | 0 | 0 |  |  | 0 | 8.575e-06
52 | Asset Recived From Civil-U#8-Ash Slurry Pipe Line AHP-Pedestals-10501 | N.A. | - | 0 | 0.00013846 | 0 | 0.00013846 | 0 | 0 |  |  | 0 | 0.00013846
53 | Asset Recived From Civil-U#8-AHP-Buffer Hopper Foundation-10501 | N.A. | - | 0 | 3.5628e-05 | 0 | 3.5628e-05 | 0 | 0 |  |  | 0 | 3.5628e-05
54 | Asset Recived From Civil-U#8-AHP-Mill reject hopper foundation-10501 | N.A. | - | 0 | 1.7814e-05 | 0 | 1.7814e-05 | 0 | 0 |  |  | 0 | 1.7814e-05
55 | Asset Recived From Civil-U#8-FHP-Fuel Oil pump house-10516 | N.A. | - | 0 | 0.00065769 | 0 | 0.00065769 | 0 | 0 |  |  | 0 | 0.00065769
56 | Asset Recived From Civil-U#8-FHP-DYKE AREA -10516 | N.A. | - | 0 | 1.9339e-05 | 0 | 1.9339e-05 | 0 | 0 |  |  | 0 | 1.9339e-05
57 | Asset Recived From Civil-U#8-Effulent Treatment Plant -10509 | N.A. | - | 0 | 0.00014135 | 0 | 0.00014135 | 0 | 0 |  |  | 0 | 0.00014135
58 | Asset Recived From Project-U#8-Boiler Pressure parts-10501 | N.A. | - | 0 | 0.06549 | 0 | 0.06549 | 0 | 0 |  |  | 0 | 0.06549
59 | Asset Recived From Project-U#8-Mandatory Spares from BHEL–Trichy | N.A. | - | 0 | 0.0074619 | 0 | 0.0074619 | 0 | 0 |  |  | 0 | 0.0074619
60 | Asset Recived From Civil-U#8-Coal mill reject trench at coal mill D&E | N.A. | - | 0 | 0.04661 | 0 | 0.04661 | 0 | 0 |  |  | 0 | 0.04661
61 | Asset Recived From Project-U#8-Canteen Equipments & kitchen Utensils | N.A. | - | 0 | 0.21888 | 0 | 0.21888 | 0 | 0 |  |  | 0 | 0.21888
62 | Asset Recived From Project-U#8-Supply & Erection of ACW system-10310 | N.A. | - | 0 | 0.00083684 | 0 | 0.00083684 | 0 | 0 |  |  | 0 | 0.00083684
63 | Asset Recived From Project-U#8-SUPPLY & ERECTION OF CCW SYSTEM-10310 | N.A. | - | 0 | 0.004856 | 0 | 0.004856 | 0 | 0 |  |  | 0 | 0.004856
64 | Asset Recived From Project-U#8-TG set & its auxilleries-HP/LPFeedWate | N.A. | - | 0 | 0.016842 | 0 | 0.016842 | 0 | 0 |  |  | 0 | 0.016842
65 | Asset Recived From Project-U#8-TG set and its auxilleries- Boilerfeed | N.A. | - | 0 | 0.018479 | 0 | 0.018479 | 0 | 0 |  |  | 0 | 0.018479
66 | Asset Recived From Project-U#8-Air Conditioning-MandatorySpares-10576 | N.A. | - | 0 | 1.7256e-05 | 0 | 1.7256e-05 | 0 | 0 |  |  | 0 | 1.7256e-05
67 | Asset Recived From Project-U#8-Air Conditioning system-10576 | N.A. | - | 0 | 0.0013446 | 0 | 0.0013446 | 0 | 0 |  |  | 0 | 0.0013446
68 | Asset Recived From Project-U#8-AHP-FLY ASH & HCSD-SYSTEM-10501 | N.A. | - | 0 | 0.0021652 | 0 | 0.0021652 | 0 | 0 |  |  | 0 | 0.0021652
69 | Asset Recived From Project-U#8-AHP-FLYASH&HCSD-SYSTEMBOUGHT OUT-10501 | N.A. | - | 0 | 0.0070969 | 0 | 0.0070969 | 0 | 0 |  |  | 0 | 0.0070969
70 | Asset Recived From Project-U#8-AHP-BOTTOM ASH SYSTEM-10501 | N.A. | - | 0 | 0.012126 | 0 | 0.012126 | 0 | 0 |  |  | 0 | 0.012126
71 | Asset Recived From Project-U#8-AHP-ELECTRICAL C & I-10501 | N.A. | - | 0 | 0.004053 | 0 | 0.004053 | 0 | 0 |  |  | 0 | 0.004053
72 | Asset Recived From Project-U#8-AHP-GEHO PUMP-10501 | N.A. | - | 0 | 0.0095128 | 0 | 0.0095128 | 0 | 0 |  |  | 0 | 0.0095128
73 | Asset Recived FromProject-U#8-Boiler&Aux -Power Cycle Piping-10501 | N.A. | - | 0 | 0.041005 | 0 | 0.041005 | 0 | 0 |  |  | 0 | 0.041005
74 | Asset Recived From Project-U#8-Boiler&Aux-SUIT BLOWER & PIPING-10501 | N.A. | - | 0 | 0.083837 | 0 | 0.083837 | 0 | 0 |  |  | 0 | 0.083837
75 | Asset Recived From Project-U#8-Boiler & Auxillaries - PA FAN-10501 | N.A. | - | 0 | 0.0010226 | 0 | 0.0010226 | 0 | 0 |  |  | 0 | 0.0010226
76 | Asset Recived From Project-U#8-Boiler&Aux-Air Preheaters-10501 | N.A. | - | 0 | 0.013281 | 0 | 0.013281 | 0 | 0 |  |  | 0 | 0.013281
77 | Asset Recived From Project-U#8-Boiler & Auxillaries -COAL MILL-10501 | N.A. | - | 0 | 0.051244 | 0 | 0.051244 | 0 | 0 |  |  | 0 | 0.051244
78 | Asset Recived From Project-U#8-Boiler & Auxillaries -FD FAN-10501 | N.A. | - | 0 | 0.0006817 | 0 | 0.0006817 | 0 | 0 |  |  | 0 | 0.0006817
79 | Asset Recived From Project-U#8-Boiler & Auxillaries- ID FAN-10501 | N.A. | - | 0 | 0.0017043 | 0 | 0.0017043 | 0 | 0 |  |  | 0 | 0.0017043
80 | Asset Recived From Project-U#8-Boiler&Aux-Mandatory Spares-10501 | N.A. | - | 0 | 0.0097935 | 0 | 0.0097935 | 0 | 0 |  |  | 0 | 0.0097935
81 | Asset Recived From Project-U#8-Boiler&Aux-PLATFORM,STAIRS,GRATINGS, | N.A. | - | 0 | 0.030596 | 0 | 0.030596 | 0 | 0 |  |  | 0 | 0.030596
82 | Asset Recived From Project-U#8-Boiler Pressure parts-10501 | N.A. | - | 0 | 0.17807 | 0 | 0.17807 | 0 | 0 |  |  | 0 | 0.17807
83 | Asset Recived From Project-U#8-220V-BATTERY+CHARGERS-MAIN PLANT-10563 | N.A. | - | 0 | 0.0020848 | 0 | 0.0020848 | 0 | 0 |  |  | 0 | 0.0020848
84 | Asset Recived From Project-U#8-220V -BATTERY WITH CHARGERS(CHP)-10563 | N.A. | - | 0 | 0.00020745 | 0 | 0.00020745 | 0 | 0 |  |  | 0 | 0.00020745
85 | Asset Recived From Project-U#8-220V-BATTERY+CHARG-WAGON TRIP-2N-10563 | N.A. | - | 0 | 8.4674e-05 | 0 | 8.4674e-05 | 0 | 0 |  |  | 0 | 8.4674e-05
86 | Asset Recived From Project-U#8-BOP-OTHER C& i INSTRUMENTS-10509 | N.A. | - | 0 | 0.0013441 | 0 | 0.0013441 | 0 | 0 |  |  | 0 | 0.0013441
87 | Asset Recived From Project-U#8-CHP-CONVEYOR SYSTEM-10515 | N.A. | - | 0 | 0.015409 | 0 | 0.015409 | 0 | 0 |  |  | 0 | 0.015409
88 | Asset Recived From Project-U#8-CHP-WOBLER FEEDER-10515 | N.A. | - | 0 | 0.00054613 | 0 | 0.00054613 | 0 | 0 |  |  | 0 | 0.00054613
89 | Asset Recived From Project-U#8-CHP-APRON FEEDER-10515 | N.A. | - | 0 | 0.0028149 | 0 | 0.0028149 | 0 | 0 |  |  | 0 | 0.0028149
90 | Asset Recived From Project-U#8-CHP-ILMS,METAL DETECTOR,BELT WEIGHER | N.A. | - | 0 | 0.0011704 | 0 | 0.0011704 | 0 | 0 |  |  | 0 | 0.0011704
91 | Asset Recived From Project-U#8-CHP-IMPACT CRUSHER-10515 | N.A. | - | 0 | 0.0020638 | 0 | 0.0020638 | 0 | 0 |  |  | 0 | 0.0020638
92 | Project-U#8-CHP-STRACKER CUM RECLAIMER-10515 | N.A. | - | 0 | 0.0082014 | 0 | 0.0082014 | 0 | 0 |  |  | 0 | 0.0082014
93 | Project-U#8-CHP-SIDE DISCHARGE TYPE WAGON TRIPPLER | N.A. | - | 0 | 0.0077836 | 0 | 0.0077836 | 0 | 0 |  |  | 0 | 0.0077836
94 | Project-U#8-Coal Handling Plant-M.S.-10515 | N.A. | - | 0 | 0.00034267 | 0 | 0.00034267 | 0 | 0 |  |  | 0 | 0.00034267
95 | Project-U#8-communication system-10572 | N.A. | - | 0 | 0.0019253 | 0 | 0.0019253 | 0 | 0 |  |  | 0 | 0.0019253
96 | Project-U#8-UPS INVERTORS-10563 | N.A. | - | 0 | 0.00051465 | 0 | 0.00051465 | 0 | 0 |  |  | 0 | 0.00051465
97 | Project-U#8-UPS ACDS-10563 | N.A. | - | 0 | 8.9956e-05 | 0 | 8.9956e-05 | 0 | 0 |  |  | 0 | 8.9956e-05
98 | Project-U#8-UPS BATTERIRERS-10563 | N.A. | - | 0 | 0.00051465 | 0 | 0.00051465 | 0 | 0 |  |  | 0 | 0.00051465
99 | Project-U#8-24V BATTERY CHARGERS (SGTG)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
100 | Project-U#8-24V BATTERY CHARGERS (BOP)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
101 | Project-U#8-BATTERIS FOR (SGTG)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
102 | Project-U#8-BATTERIS FOR (BOP)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
103 | Project-U#8-DCDB(SGTG)-10563 | N.A. | - | 0 | 5.7183e-05 | 0 | 5.7183e-05 | 0 | 0 |  |  | 0 | 5.7183e-05
104 | Project-U#8-DCDB(BOP)-10563 | N.A. | - | 0 | 5.7183e-05 | 0 | 5.7183e-05 | 0 | 0 |  |  | 0 | 5.7183e-05
105 | Project-U#8-Controls & Instru. for Main Plant(BTG) | N.A. | - | 0 | 0.044292 | 0 | 0.044292 | 0 | 0 |  |  | 0 | 0.044292
106 | Project-U#8-CW Chlorination system-10509 | N.A. | - | 0 | 0.0011974 | 0 | 0.0011974 | 0 | 0 |  |  | 0 | 0.0011974
107 | Project-U#8-D.G.SET-10509 | N.A. | - | 0 | 3.7894e-05 | 0 | 3.7894e-05 | 0 | 0 |  |  | 0 | 3.7894e-05
108 | Project-U#8-D.M.Water System-10509 | N.A. | - | 0 | 0.005785 | 0 | 0.005785 | 0 | 0 |  |  | 0 | 0.005785
109 | Project-U#8-DG set- Manadatory Spares-10509 | N.A. | - | 0 | 0.00025004 | 0 | 0.00025004 | 0 | 0 |  |  | 0 | 0.00025004
110 | Project-U#8-DG Set Room cum Air Compressor House | N.A. | - | 0 | 0.0055794 | 0 | 0.0055794 | 0 | 0 |  |  | 0 | 0.0055794
111 | Project-U#8-Steel for TechnologicalStructure-10501 | N.A. | - | 0 | 0.14836 | 0 | 0.14836 | 0 | 0 |  |  | 0 | 0.14836
112 | Project-U#8-Electrical Package for BOP-10509 | N.A. | - | 0 | 0.0024904 | 0 | 0.0024904 | 0 | 0 |  |  | 0 | 0.0024904
113 | Project-U#8-Electrical CHARGES-10509 | N.A. | - | 0 | 4.1155e-05 | 0 | 4.1155e-05 | 0 | 0 |  |  | 0 | 4.1155e-05
114 | Project-U#8-Electrical Package for BOP-Mandatory | N.A. | - | 0 | 0.0002757 | 0 | 0.0002757 | 0 | 0 |  |  | 0 | 0.0002757
115 | Project-U#8-Fire Protection, Alarm & Detection | N.A. | - | 0 | 0.0071788 | 0 | 0.0071788 | 0 | 0 |  |  | 0 | 0.0071788
116 | Project-U#8-Fuel Oil Pump House-10516 | N.A. | - | 0 | 0.0040925 | 0 | 0.0040925 | 0 | 0 |  |  | 0 | 0.0040925
117 | Project-U#8-Generator Transformer-10541 | N.A. | - | 0 | 0.012655 | 0 | 0.012655 | 0 | 0 |  |  | 0 | 0.012655
118 | Project-U#8-Generator/Transformer protection | N.A. | - | 0 | 0.00024539 | 0 | 0.00024539 | 0 | 0 |  |  | 0 | 0.00024539
119 | Project-U#8-H.T.Switchgear for main plant-10561 | N.A. | - | 0 | 0.025188 | 0 | 0.025188 | 0 | 0 |  |  | 0 | 0.025188
120 | Project-U#8-Indoor & Outdoor plant lighting-10599 | N.A. | - | 0 | 0.0004077 | 0 | 0.0004077 | 0 | 0 |  |  | 0 | 0.0004077
121 | Project-U#8-L.P.Piping including valves-10509 | N.A. | - | 0 | 0.0038246 | 0 | 0.0038246 | 0 | 0 |  |  | 0 | 0.0038246
122 | Project-U#8-L.T. Electrical for main plant.-10561 | N.A. | - | 0 | 8.7067e-05 | 0 | 8.7067e-05 | 0 | 0 |  |  | 0 | 8.7067e-05
123 | Project-U#8-Laying&Termination of HT cables-10561 | N.A. | - | 0 | 0.0008231 | 0 | 0.0008231 | 0 | 0 |  |  | 0 | 0.0008231
124 | Project-U#8-MainBoiler Structure&foundations-10501 | N.A. | - | 0 | 0.09941 | 0 | 0.09941 | 0 | 0 |  |  | 0 | 0.09941
125 | Project-U#8-Mandatory Spares for Ash HandlingPlant | N.A. | - | 0 | 0.0015616 | 0 | 0.0015616 | 0 | 0 |  |  | 0 | 0.0015616
126 | Project-U#8-Mandatory spares for C&I of Main Plant | N.A. | - | 0 | 0.0050295 | 0 | 0.0050295 | 0 | 0 |  |  | 0 | 0.0050295
127 | Project-U#8-Mandatory Spares for Electrical MainPa | N.A. | - | 0 | 0.015601 | 0 | 0.015601 | 0 | 0 |  |  | 0 | 0.015601
128 | Project-U#8-Mandatory Spares For TG & Auxilliaries | N.A. | - | 0 | 0.0062588 | 0 | 0.0062588 | 0 | 0 |  |  | 0 | 0.0062588
129 | Project-U#8-Misc. Cranes & hoists-10553 | N.A. | - | 0 | 0.0023537 | 0 | 0.0023537 | 0 | 0 |  |  | 0 | 0.0023537
130 | Project-U#8-Miscellaneous Pumps -10599 | N.A. | - | 0 | 0.0015672 | 0 | 0.0015672 | 0 | 0 |  |  | 0 | 0.0015672
131 | Project-U#8-Passanger lift for TG Building-10599 | N.A. | - | 0 | 0.0016358 | 0 | 0.0016358 | 0 | 0 |  |  | 0 | 0.0016358
132 | Project-U#8-Passanger/Material Lift at boiler side | N.A. | - | 0 | 0.00084731 | 0 | 0.00084731 | 0 | 0 |  |  | 0 | 0.00084731
133 | Project-U#8-Chemical Laboratory -10509 | N.A. | - | 0 | 0.0011648 | 0 | 0.0011648 | 0 | 0 |  |  | 0 | 0.0011648
134 | Project-U#8-Sewage Treatment Plant-10509 | N.A. | - | 0 | 0.0019006 | 0 | 0.0019006 | 0 | 0 |  |  | 0 | 0.0019006
135 | Project-U#8-Station Transformer-10541 | N.A. | - | 0 | 0.026576 | 0 | 0.026576 | 0 | 0 |  |  | 0 | 0.026576
136 | Project-U#8-Steam Turbine set-10503 | N.A. | - | 0 | 0.13864 | 0 | 0.13864 | 0 | 0 |  |  | 0 | 0.13864
137 | Project-U#8-TG set and its auxilleries- Condensor | N.A. | - | 0 | 0.012703 | 0 | 0.012703 | 0 | 0 |  |  | 0 | 0.012703
138 | Project-U#8-TG set and its auxilleries -Generator | N.A. | - | 0 | 0.032545 | 0 | 0.032545 | 0 | 0 |  |  | 0 | 0.032545
139 | Project-U#8-TG set and its auxilleries-Condensor | N.A. | - | 0 | 0.029273 | 0 | 0.029273 | 0 | 0 |  |  | 0 | 0.029273
140 | Project-U#8-TG set & its auxilleries-Derator-10503 | N.A. | - | 0 | 0.002758 | 0 | 0.002758 | 0 | 0 |  |  | 0 | 0.002758
141 | Project-U#8-TG set and its auxilleries-DMMakeUpSys | N.A. | - | 0 | 0.0010491 | 0 | 0.0010491 | 0 | 0 |  |  | 0 | 0.0010491
142 | Project-U#8-TG set and its auxilleries-Gas System | N.A. | - | 0 | 0.0056178 | 0 | 0.0056178 | 0 | 0 |  |  | 0 | 0.0056178
143 | Project-U#8-TG set and its auxilleries-GoveringSys | N.A. | - | 0 | 4.9466e-05 | 0 | 4.9466e-05 | 0 | 0 |  |  | 0 | 4.9466e-05
144 | Project-U#8-TG set and its auxilleries-HP/LP By-pa | N.A. | - | 0 | 0.010752 | 0 | 0.010752 | 0 | 0 |  |  | 0 | 0.010752
145 | Project-U#8-TG set and its auxilleries-HP/LP Dozin | N.A. | - | 0 | 0.00039941 | 0 | 0.00039941 | 0 | 0 |  |  | 0 | 0.00039941
146 | Project-U#8-TG set and its auxilleries-SealOilPump | N.A. | - | 0 | 9.8566e-05 | 0 | 9.8566e-05 | 0 | 0 |  |  | 0 | 9.8566e-05
147 | Project-U#8-TG set and its auxilleries-Vaccum Syst | N.A. | - | 0 | 0.010304 | 0 | 0.010304 | 0 | 0 |  |  | 0 | 0.010304
148 | Project-U#8-Turbine Lub. Oil System With Purifier | N.A. | - | 0 | 0.0022364 | 0 | 0.0022364 | 0 | 0 |  |  | 0 | 0.0022364
149 | Project-U#8-Ventillation system-10599 | N.A. | - | 0 | 0.0014389 | 0 | 0.0014389 | 0 | 0 |  |  | 0 | 0.0014389
150 | Asset Recived From Project-U#8-M.SPARE_Ventillation system-10599 | N.A. | - | 0 | 8.5482e-05 | 0 | 8.5482e-05 | 0 | 0 |  |  | 0 | 8.5482e-05
151 | Asset Recived From Project-U#8-Water Treatment Plant-10509 | N.A. | - | 0 | 0.0042384 | 0 | 0.0042384 | 0 | 0 |  |  | 0 | 0.0042384
152 | Asset Recived From Project-U#8-WORK SHOP MAD_SPARE-10565 | N.A. | - | 0 | 0.00030445 | 0 | 0.00030445 | 0 | 0 |  |  | 0 | 0.00030445
153 | Asset Recived From Project-U#8-Workshop-10565 | N.A. | - | 0 | 0.0013286 | 0 | 0.0013286 | 0 | 0 |  |  | 0 | 0.0013286
154 | Asset Recived From Project-U#8-CMR SYSTEM-10501 | N.A. | - | 0 | 0.0020736 | 0 | 0.0020736 | 0 | 0 |  |  | 0 | 0.0020736
155 | Asset Recived From Project-U#8-MandatorySpares-WTP-10.509 | N.A. | - | 0 | 8.1517e-05 | 0 | 8.1517e-05 | 0 | 0 |  |  | 0 | 8.1517e-05
156 | Asset Recived From Project-U#8-E.1.07_MandSpar 4 C&I MS 4MeasuringIns E.1.07_M S for C&I_ MS For Measuring Ins | N.A. | - | 0 | 0.078697 | 0 | 0.078697 | 0 | 0 |  |  | 0 | 0.078697
157 | Asset Recived From Project-U#8-BOP_ELECTRICAL-10612 | N.A. | - | 0 | 0.01637 | 0 | 0.01637 | 0 | 0 |  |  | 0 | 0.01637
158 | Asset Recived From Project-U#8-Bus Ducts-10612 | N.A. | - | 0 | 0.012548 | 0 | 0.012548 | 0 | 0 |  |  | 0 | 0.012548
159 | Asset Recived From Project-U#8-Cable trays & supports-10612 | N.A. | - | 0 | 0.00036009 | 0 | 0.00036009 | 0 | 0 |  |  | 0 | 0.00036009
160 | Project-U#8-PCR FURNITURE-10810 | N.A. | - | 0 | 0.00030684 | 0 | 0.00030684 | 0 | 0 |  |  | 0 | 0.00030684
161 | Project-U#8 Server Intel QUAD CORE 02No. HP Office Server | N.A. | - | 0 | 0.11918 | 0.11918 | 0 | 0 | 0 |  |  | 0 | 0
162 | Supply Erection testing and commissining of 1000 m3 ETP Civil works | N.A. | - | 0 | 0.68324 | 0.68324 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 826.3635 | 832.6426 | -6.2791 | 11.79 | 11.79 | 0 | 0 | 11.79 | -6.2791
FY 2029-30
0 | Add Cap (As per 296 of 2019)
A | Initial spares | Add Cap (As per 296 of 2019) | - | 0
1 | Boiler and Auxiliaries | Add Cap (As per 296 of 2019) | - | 7.2
1 | Procurement of Coal Mill XRP-903 Gear Box Type KMP-280 Spares of Unit # 8 at BM-NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 0 | 1.35 | 1.35 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply of Labyrinth Seal Rings with replaceable Inner liners for Coal Mill XRP-903 required for BM Unit-8, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.33134 | 0.33134 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply and Installation of coal mill liners(weld overlay) of XRP-903 Coal Mill in BM U-8, NPTPS,Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.33134 | 0.33134 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of Coal Mill XRP-903 Bowl & Bowl Hub of Unit # 8 at BM-NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 0 | 0.73326 | 0.73326 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply of impeller assembly for ID fan | Add Cap (As per 296 of 2019) | - | 0 | 0.5233 | 0.5233 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of Primary Air Fan & Forced Draught Fan Drive Coupling on OEM basis required at BM U-8, NPTPS, Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.1941 | 0.1941 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of Primary Air Fan PAF 17/11.8-2 Hydraulic Adjustment Device on OEM basis required at BM U-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.53521 | 0.53521 | 0 | 0 | 0 |  |  | 0 | 0
8 | Proc of spares for fabric expansion joints required at BM U-8, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.56972 | 0.56972 | 0 | 0 | 0 |  |  | 0 | 0
9 | Proc of separator body and seperator top spares for coal mill XRP-903 at BM U-8, NPTPS Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.42569 | 0.42569 | 0 | 0 | 0 |  |  | 0 | 0
10 | Proc of scrapper area & reject system spares for coal mill XRP-903 at BM U-8, NPTPS Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.27833 | 0.27833 | 0 | 0 | 0 |  |  | 0 | 0
11 | Proc of seal air fan spares at BM-8 NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.26432 | 0.26432 | 0 | 0 | 0 |  |  | 0 | 0
12 | Procurement of FD Fan Type FAF 17/9.5-1 Drive Coupling required at BM U-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | Procurement of complete planatary gear box-KMP -280/300 for coal mill XRP-903 at BM U-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Turbine and Auxiliaries | Add Cap (As per 296 of 2019) | - | 4.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of spares for Equipment Cooling Water Pumps (Make-FLOWMORE) of model FIG-5824 (SG Side) and FIG-5822 (TG side) at Unit-8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.51812 | 0.51812 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply of spars for recovery & FF Pumps along with work at U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0.37713 | 0.37713 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of seal oil vacuum pump in unit 08 | Add Cap (As per 296 of 2019) | - | 0 | 0.27502 | 0.27502 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of AC pressure pipes (235MM OD, 200MM ID, 4.5M Length) for NDCT hot spray water distribution system in Unit-8 NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 0 | 0.42522 | 0.42522 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply of M/s Summits make Instrument Air Dryer & spares at U # 8 TM, Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.54787 | 0.54787 | 0 | 0 | 0 |  |  | 0 | 0
6 | Supply of PVC fills for NDCTs at U # 8 TM, Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.58245 | 0.58245 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of NB 600MM Gate valves for ACW self cleaning strainers in U#8 TM NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.42338 | 0.42338 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of Mechanical seals ( Make Leak-Proof) for various pumps in TM Unit-8 NPTPS Parli. | Add Cap (As per 296 of 2019) | - | 0 | 0.49233 | 0.49233 | 0 | 0 | 0 |  |  | 0 | 0
9 | Supply of SS 304 pipes & others at U # 8 TM, Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.52905 | 0.52905 | 0 | 0 | 0 |  |  | 0 | 0
3 | Electrical and Instrumentation | Add Cap (As per 296 of 2019) | - | 6.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of Instrumentation Spares of LP Bypass System at Unit-8. | Add Cap (As per 296 of 2019) | - | 0 | 1.9615 | 1.9615 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of Schneider MICOM Numerical Relays for GRP and STPR swithcgear at NPTPS Unit-8 Testing | Add Cap (As per 296 of 2019) | - | 0 | 0.47613 | 0.47613 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of 220V DC Chloride make (formally caldyne) make battery chargers Spre of Unit 8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.23365 | 0.23365 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of 24V DC Chhabi make make battery chargers Spare of Unit 8 NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 0.22465 | 0.22465 | 0 | 0 | 0 |  |  | 0 | 0
5 | Procurement of Spare for Hitachi Hi-Rel make UPS systems installed at Unit-8 NPTPS Parli Vaijnath. | Add Cap (As per 296 of 2019) | - | 0 | 0.19186 | 0.19186 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of various test kit for testing U#8 such as energy meter calibration kit, DC earth faulth locator kit, promary current injection kit, breaker time measurement kit, numeric relay test kit and other testing instruments. | Add Cap (As per 296 of 2019) | - | 0 | 0.67345 | 0.67345 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of Energymeter Caliberation Software Module and hardware for upgrading Numeric Relay Test kit at Unit -8 Testing. | Add Cap (As per 296 of 2019) | - | 0 | 0.11863 | 0.11863 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of H T Motors. | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of critical L T Motors | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of ESP Hopper heaters (As a initial spares) Installed at EM U-8, NPTPS, Parli-Vaijnath under add cap scheme. | Add Cap (As per 296 of 2019) | - | 0 | 0.38586 | 0.38586 | 0 | 0 | 0 |  |  | 0 | 0
4 | Outdoor Plant(CHP/AHP/WTP) | Add Cap (As per 296 of 2019) | - | 6.64 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of Apron Feeder spares installed at CHP NPTPS Parli-V | Add Cap (As per 296 of 2019) | - | 0 | 1.6233 | 1.6233 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply of various drive and non drive pulleys for CHP U-8. | Add Cap (As per 296 of 2019) | - | 0 | 0.54529 | 0.54529 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply and installation of clamp pads & resting pads for Side Beam of Wagon Tippler for CHP U-8 | Add Cap (As per 296 of 2019) | - | 0 | 0.54802 | 0.54802 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply of unbalance motorozied vibrating feeder for S/R of U-7/8 CHP NPTPS Parli-V. | Add Cap (As per 296 of 2019) | - | 0 | 0.3958 | 0.3958 | 0 | 0 | 0 |  |  | 0 | 0
5 | Procurement of conveying and Instrument air compressor spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 1.77 | 1.77 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of vacuum pump spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0.2291 | 0.2291 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of fluidizing blower spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0.11796 | 0.11796 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of slurry pump spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of Clinker grinder spares at AHP U#8 | Add Cap (As per 296 of 2019) | - | 0 | 0.12334 | 0.12334 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B | Reassessment of remaining BOP work after insolvency of M/s Sunil Hi-Tech | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Project balance E&M and procurement of mandetory spares | MERC CAPEX Approval in MTR Order 296 of 2019 | Order 296 of 2019 | 41.4534 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work order for Contract of Supply and application of Fire Stop Mortar Seal and Fire Retardant Cable Coating Compound at NPTP U-8 Parli Project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 3.4589 | 3.4589 | 0 | 0 | 0 |  |  | 0 | 0
2 | Work order for contract for Supply Installaion Testing & Commissioning Smoke Detection & alaram system | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 2.5606 | 2.5606 | 0 | 0 | 0 |  |  | 0 | 0
3 | Work order for contract for Supply Installaion Testing & Commissioning of Balance Fire Fighting System at NPTP U-8 Parli Project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.0502 | 1.0502 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, Errection, testing & commissioning works of RWP, PT potable chlorination system, ETP system control panel, automation of LDO, HFO tank foam system Hose boxes with RRL hoses and branch pipe and allied system at NPTP | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.8496 | 0.8496 | 0 | 0 | 0 |  |  | 0 | 0
5 | Work Order contract for supply, installation Testing & Commissioning of telephone exchange (EPBAX) & Telephone System at NPTP U-8 Parli project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.91256 | 0.91256 | 0 | 0 | 0 |  |  | 0 | 0
6 | Balance Supply of Electrical Lab Equipment at NPTP parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.60826 | 0.60826 | 0 | 0 | 0 |  |  | 0 | 0
7 | Work order for contract for Supply Installaion Testing & Commissioning with required material to complete Balance CHP work at NPTP U-8 Parli Project | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.41 | 0.41 | 0 | 0 | 0 |  |  | 0 | 0
8 | Supply, Errection, testing & commissioning of Interconnecting Conveyor no.9 & 10 from U-8 to U-6&7 of CHP at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 5.3319 | 5.3262 | 0.0056593 | 0 | 0 |  |  | 0 | 0.0056593
9 | SUPPLY ,INSTA,TEST ,COMM ELECTRICAL SYS | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | SUPPLY,INSTAL,TEST,COMM OF CRANS&HOIST | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.8105 | 3.6223 | -1.8118 | 0 | 0 |  |  | 0 | -1.8118
11 | Supply, Errection, testing & commissioning of Dust Extraction system at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.8061 | 0 | 1.8061 | 0 | 0 |  |  | 0 | 1.8061
12 | Supply, Errection, testing & commissioning of DSS & DFDS at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 4.3391 | 4.34 | -0.0008856 | 0 | 0 |  |  | 0 | -0.0008856
13 | Supply, Errection, testing & commissioning of Monorail at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.1892 | 1.1891 | 7.77e-05 | 0 | 0 |  |  | 0 | 7.77e-05
14 | Supply, Errection, testing & commissioning of various Control & Instrumentation equipments at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.72225 | 0.72225 | 0 | 0 | 0 |  |  | 0 | 0
15 | Supply, Errection, testing & commissioning of Air Conditioning System at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.15304 | 0.44729 | -0.29425 | 0 | 0 |  |  | 0 | -0.29425
16 | Supply, Errection, testing & commissioning of Ventilation System at NPTP U-8, Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 2.1136 | 1.2036 | 0.91 | 0 | 0 |  |  | 0 | 0.91
17 | Supply, Errection, testing & commissioning of Elevator works. | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 3.5173 | 4.4273 | -0.91 | 0 | 0 |  |  | 0 | -0.91
18 | Work contract for dismentaling, supply, erection & commissioning of MRHS | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 2.2335 | 2.2335 | 0 | 0 | 0 |  |  | 0 | 0
19 | Supply, Errection, testing & commissioning of FF System, Smoke detection & Fire stop mortar & Fire retradant cable coating for conveyor 09 & 10 | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0.22171 | 0.51866 | -0.29696 | 0 | 0 |  |  | 0 | -0.29696
20 | Supply, Errection, testing & commissioning of Chimney Elevator | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.0608 | 0 | 1.0608 | 0 | 0 |  |  | 0 | 1.0608
21 | Supply, Errection, testing & commissioning work of GEHO Pumps. | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 0 | 1.06 | -1.06 | 0 | 0 |  |  | 0 | -1.06
22 | Procurement of various Mandetory spares of BOP packages | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 5.47 | 6.54 | -1.07 | 0 | 0 |  |  | 0 | -1.07
0 | Balance civil work of BOP scope at 250 MW Parli-V | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 45.3238 | 0.55712 | 16.72 | -16.1629 | 0 | 0 |  |  | 0 | -16.1629
1 | Area grading | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 6.9866 | 0.89 | 6.0966 | 0 | 0 |  |  | 0 | 6.0966
2 | CMD | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.2411 | 1.3549 | -0.11383 | 0 | 0 |  |  | 0 | -0.11383
3 | Conveyor 09, 10 & TP 06 | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 14.5605 | 12.13 | 2.4305 | 0 | 0 |  |  | 0 | 2.4305
4 | Finishing item | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 8.085 | 4.6506 | 3.4344 | 0 | 0 |  |  | 0 | 3.4344
5 | Drain & nala | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 5.0848 | 11.79 | -6.7052 | 0 | 0 |  |  | 0 | -6.7052
6 | Internal roads | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 9.7521 | 1.5 | 8.2521 | 0 | 0 |  |  | 0 | 8.2521
7 | Stacker & reclaimer | MERC CAPEX Approval in MTR Order 296 of 2019 | - | 0 | 1.1627 | 0 | 1.1627 | 0 | 0 |  |  | 0 | 1.1627
0 | Other Add Cap | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Laboratory set up | Add Cap (As per 296 of 2019) | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of Analytical Instruments for condition monitoring Laboratory for 1X250 MW of NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.5 | 0.49655 | 0.49655 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply of Analytical Instruments for Water Analysis Laboratory for 1X250 MW of NPTPS, Parli-V | Add Cap (As per 296 of 2019) | - | 1.23 | 0.29847 | 0.29847 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of Analytical Instruments for Environment Laboratory for 1 x 250 MW, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.39 | 0.3658 | 0.3658 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply of Analytical Instruments for Precision Laboratory for 1 x 250 MW, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply of Analytical Instruments for General Laboratory of Water Treatment Plant of 1 x 250 MW, NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Supply of Corrosion Monitor/Meter, Corrosion Coupon & Coupon Rack for 1X250 MW of NPTPS, Parli-V. | Add Cap (As per 296 of 2019) | - | 0.34 | 0.34736 | 0.34736 | 0 | 0 | 0 |  |  | 0 | 0
7 | Supply of Analytical Instruments for Coal Analysis Laboratory for 1X250 MW of NPTPS, Parli-V | Add Cap (As per 296 of 2019) | - | 1.65 | 0.39444 | 0.39444 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Grade slab (WTP Area) | Add Cap (As per 296 of 2019) | - | 1 | 0.99752 | 0.99752 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Grade slab (Near AHP Building) | Add Cap (As per 296 of 2019) | - | 0.75 | 0.74556 | 0.74556 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Temporary shed for empty barrles & filled barrles | Add Cap (As per 296 of 2019) | - | 0.5 | 0.45635 | 0.45635 | 0 | 0 | 0 |  |  | 0 | 0
12 | Cabins for operators at TP. | Add Cap (As per 296 of 2019) | - | 0.2 | 0.18583 | 0.18583 | 0 | 0 | 0 |  |  | 0 | 0
13 | Compound wall for isolation of administrative building. | Add Cap (As per 296 of 2019) | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Work of providing/ fixing of internal partitions of aluminium/Nova palm/glass/wooden for Unit 8 service building & other allied builings in the premises. | Add Cap (As per 296 of 2019) | - | 0.7 | 0.67356 | 0.67356 | 0 | 0 | 0 |  |  | 0 | 0
15 | Provision of DM and softening water line interconnection from u-6,7 to u-8 & Provision of recovery of waste water from sandava pump house,NDCT. | Add Cap (As per 296 of 2019) | - | 3 | 1.0266 | 1.0266 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | Add Cap (As per 296 of 2019) | - | 0 | 1.8371 | 1.8371 | 0 | 0 | 0 |  |  | 0 | 0
16 | Hydraulic drive system modification. | Add Cap (As per 296 of 2019) | - | 2.5 | 2.4384 | 2.4384 | 0 | 0 | 0 |  |  | 0 | 0
17 | Link conveyor from Con-2 of U-6/7 to Con.-2AB of U-8. | Add Cap (As per 296 of 2019) | - | 3.7 | 4.6434 | 22.6564 | -18.0129 | 0 | 0 |  |  | 0 | -18.0129
18 | Ozone plant for Unit -8 | Add Cap (As per 296 of 2019) | - | 20 | 20.0947 | 2.1929 | 17.9018 | 0 | 0 |  |  | 0 | 17.9018
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | Water management system | Add Cap (As per 296 of 2019) | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8, 20 | Procurement & Installation of EMS system at Unit-8 NPTPS Parli-Vaijnath | Add Cap (As per 296 of 2019) | - | 1 | 0.14417 | 0.14417 | 0 | 0 | 0 |  |  | 0 | 0
21 | Conveyor-5 of stacking/reclaiming belt double drive arrangement. | Add Cap (As per 296 of 2019) | - | 2 | 2.0432 | 2.0432 | 0 | 0 | 0 |  |  | 0 | 0
22 | Chemical lab building | Add Cap (As per 296 of 2019) | - | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Chemical store | Add Cap (As per 296 of 2019) | - | 2.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Lawn development around NDCT. | Add Cap (As per 296 of 2019) | - | 0.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | Tree plantation & greenery along road side. | Add Cap (As per 296 of 2019) | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | Greenery development in area between WTP & main plant. | Add Cap (As per 296 of 2019) | - | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | Construction of staff rooms & store for CHP maint.. | Add Cap (As per 296 of 2019) | - | 1 | 0.90703 | 0.90703 | 0 | 0 | 0 |  |  | 0 | 0
28 | Dsludg filteration for raw water | Add Cap (As per 296 of 2019) | - | 17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29 | PLC/UPS system upgradation | Add Cap (As per 296 of 2019) | - | 0.5 | 0.40149 | 0.40149 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | FGD at Parli Unit # 8 | MERC/CAPEX/2021-2022/0284 | 2022-06-27 | 89.24 | 4.1 | 0 | 4.1 | 0 | 0 |  |  | 0 | 4.1
22.1 | FGD at Parli Unit # 8 | MERC/CAPEX/2021-2022/0284 | 2022-06-27 | 85.2 | 95.21 | 108.86 | -13.65 | 0 | 0 |  |  | 0 | -13.65
0 | IDC | MERC/CAPEX/2021-2022/0284 | 2022-06-27 | 4.04 | 4.04 | 0 | 4.04 | 0 | 0 |  |  | 0 | 4.04
HO DPR 16 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 2.23 | 2.23 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Detailed Project Report on Boiler plant performance improvement and availability improvement schemes at Boiler Maintenance 1x250MW Unit-8 TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Procurement & Replacement of Complete Economizer Upper & Lower Bank Coil Assemblies at Unit-8, NPTPS Parli-V | Yet to be approved | - | 0 | 5.68 | 5.68 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 4.5 | 4.5 | 0 | 0 | 0 |  |  | 0 | 0
1.3 | Procurement & replacement of PA Fan PAF 17/11.8-2 and FD Fan FAF 17/9.5-1 Complete Blade set required at BM U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 5.45 | 5.45 | 0 | 0 | 0 |  |  | 0 | 0
1.4 | Procurement & Replacement of Coal Mill Gear Box Type KMP 280 at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 7.43 | 7.43 | 0 | 0 | 0 |  |  | 0 | 0
1.5 | Procurement & replacement of Bowl & Bowl Hub Assembly of Coal Mill XRP-903 required at BM U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 3.1 | 3.1 | 0 | 0 | 0 |  |  | 0 | 0
1.6 | Procurement of Complete Journal Assembly without Grinding roll for Coal Mill XRP-903 required at BM U-8 NPTPS Parli-V | Yet to be approved | - | 0 | 1.29 | 1.29 | 0 | 0 | 0 |  |  | 0 | 0
1.7 | Procurement of Hydraulic Adjustment Device for FD Fan FAF 17/9.5-1 at BM U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 1.4 | 1.4 | 0 | 0 | 0 |  |  | 0 | 0
1.8 | SWAS upgradation at U#8 | Yet to be approved | - | 0 | 4.8 | 4.8 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement & Replacement of Complete Platen super heater coils Coil Assemblies at Unit-8, TPS Parli-V, Procurement & Replacement of Complete LTSH upper & lower bank Coil Assemblies at Unit-8, TPS Parli-V & Procurement & Replacement of Coal Mill Gear Box Type KMP 280 at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Procurement & Replacement of Complete Platen super heater coils Coil Assemblies at Unit-8, TPS Parli-V | Yet to be approved | - | 0 | 12 | 12 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Procurement & Replacement of Complete LTSH upper & lower bank Coil Assemblies at Unit-8, TPS Parli-V | Yet to be approved | - | 0 | 9.35 | 9.35 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Procurement & Replacement of Coal Mill Gear Box Type KMP 280 at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 7.8 | 7.8 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-8, Parli TPS Procurement & replacement of PA & FD fan rotar hub assembly at Unit-8 TPS Parli-V | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement & Replacement of Two complete set of APH Baskets at 250 MW Unit-8, Parli TPS. | Yet to be approved | - | 0 | 0 | 0 | 0 | 6 | 6 |  |  | 6 | 0
3.2 | Procurement & replacement of PA & FD fan rotar hub assembly at Unit-8 TPS Parli-V | Yet to be approved | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
4 | DPR on Refurbishment of TG Governing system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Refurbishment of TG Governing system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
5 | DPR on Performance improvement of Natural Draft Cooling Tower (NDCT) at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Performance improvement of Natural Draft Cooling Tower (NDCT) by replacement of PVC fills, AC cement pipes, strengthening of Hot water distribution system, replacement of beams, columns, support structures, etc. at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
6 | DPR on Procurement of ACW & CW pump along with mandatory spares at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | DPR on Procurement of ACW & CW pump along with mandatory spares at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 35 | 35 | 0 | 0 | 0 |  |  | 0 | 0
7 | DPR on Procurement of CEP pump and BFP Booster pump along with mandatory spares at Unit-8, PTPS, Parli V and Procurement of Energy Efficient Cartridges of Boiler Feed Pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Procurement of CEP pump and BFP Booster pump along with mandatory spares at Unit-8, PTPS, Parli | Yet to be approved | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
7.2 | Procurement of Energy Efficient Cartridges of Boiler Feed Pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
8 | DPR on Procurement of turbine blades of HP, IP & LP rotor in Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.1 | DPR on Procurement of turbine blades of HP, IP & LP rotor in Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 35 | 35 | 0 | 0 | 0 |  |  | 0 | 0
9 | DPR on Repair & Reconditioning of Water treatment plant at Unit-8, PTPS, Parli V and Performance improvement of centralised AC plant at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.1 | Reconditioning of Acid and Alkali Unloading and storage system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
9.2 | Reconditioning & repairing of WTP DM Plant regeneration system at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
9.3 | Performance improvement of centralised AC plant by reconditioning of cooling tower, various pumps, heat exchangers, etc. at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
10 | DPR on Procurement of Control Fluid (HPCF) pump, Lube Oil pump, Emergency Oil pump, Jacking Oil pump, Seal oil pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.1 | DPR on Procurement of Control Fluid (HPCF) pump, Lube Oil pump, Emergency Oil pump, Jacking Oil pump, Seal oil pump at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
11 | DPR on Procurement of H2 cooler, BFP coolers, generator exciter cooler, Seal and Lube oil coolers at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.1 | DPR on Procurement of H2 cooler, BFP coolers, generator exciter cooler, Seal and Lube oil coolers at Unit-8, PTPS, Parli V. | Yet to be approved | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
12 | Supply, installation & commissioning of 220V 2140AH,24V 830AH & 710AH, 360V 570AH Mains UPS,110V 110AH AHP PLC , 110V , 103 AH DM plant battery set for unit 8 , NPTPS Parli-V & Procurement of HT motors at U#8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.1 | Supply, installation & commissioning of 220V 2140AH,24V 830AH & 710AH, 360V 570AH Mains UPS,110V 110AH AHP PLC , 110V , 103 AH DM plant battery set for unit 8 , NPTPS Parli-V | Yet to be approved | - | 0 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
12.2 | Procurement of HT motors at U#8 | Yet to be approved | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
13 | DPR on various instrumentation & control schemes at U#8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | Upgradation of MAX-DNA DCS system at U#8 (HMI upgradation) | Yet to be approved | - | 0 | 6.81 | 6.81 | 0 | 0 | 0 |  |  | 0 | 0
13.2 | Upgradation of existing Pcal system with plant performance analysis diagnostic and optimization system (PADO) at Unit 8 New Parli TPS | Yet to be approved | - | 0 | 1.4 | 1.4 | 0 | 0 | 0 |  |  | 0 | 0
13.3 | Upgradation of coal feeder for I&C Unit8 PTPS Parli V. | Yet to be approved | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
13.4 | Procurement of smart control positioner at I&C Unit8 PTPS Parli V. | Yet to be approved | - | 0 | 0.95 | 0.95 | 0 | 0 | 0 |  |  | 0 | 0
13.5 | Upgradation Electronic control drive for I&C Unit8 PTPS Parli V. | Yet to be approved | - | 0 | 3.05 | 3.05 | 0 | 0 | 0 |  |  | 0 | 0
13.6 | Upgradation of turbovisory & vibration monitoring system control panel. | Yet to be approved | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
14 | Performance improvement by system up gradation at CHP & DPR for normalization and stabilization of coal handling plant performance at Parli TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.1 | Supply and Commissioning of Energy Efficient Evaporative Cooling System for Control Panel & Breaker room of CHP Unit-8 For PARLI TPS | Yet to be approved | - | 0 | 1.38 | 1.38 | 0 | 0 | 0 |  |  | 0 | 0
14.2 | Supply and commissioning of Suspended Magnets for U-8 CHP NPTPS | Yet to be approved | - | 0 | 3.3 | 3.3 | 0 | 0 | 0 |  |  | 0 | 0
14.3 | Stacker-reclaimer Bucket wheel drive modification work of U- 8 CHP | Yet to be approved | - | 0 | 3.32 | 3.32 | 0 | 0 | 0 |  |  | 0 | 0
14.4 | Apron feeder drive modification from Hydraulic to Electro-Mechanical at CHP U-8 NPTPS | Yet to be approved | - | 0 | 4.02 | 4.02 | 0 | 0 | 0 |  |  | 0 | 0
14.5 | Procurement of U-8 W/T Major spares | Yet to be approved | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
14.6 | Provision of Soft starter / VFD for Various conveyor | Yet to be approved | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
14.7 | TP-3 chute modification at U-8 CHP. | Yet to be approved | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
14.8 | Design, supply and commissioning of solar operated lighting system in CHP U-8. | Yet to be approved | - | 0 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
14.9 | Installation of CCTV survillance system alongwith all conveyors. | Yet to be approved | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
15 | DPR for maximiation of Coal Handling Plant efficiency & DPR on life enhancement of Coal Handling Plant | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | W/T control room & bunker house battery & UPS upgradation | Yet to be approved | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Refurbishment of conveyor no. 2 A/B & 6 A/B drive system of CHP U-8 TPS Parli. | Yet to be approved | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Provision of Soft starter / VFD for Various conveyor | Yet to be approved | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Procurement & installation of Belt tear detection system | Yet to be approved | - | 0 | 4.5 | 4.5 | 0 | 0 | 0 |  |  | 0 | 0
15.5 | Conveyor gravity takeup infrastructure strengthening work | Yet to be approved | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
15.6 | U-8 CHP apron feeder-I to Conveyor 1 A/B chute modification work . | Yet to be approved | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
16 | DPR for stabiliazation of Coal Handling Performance. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.1 | Drive modification of Stacker Reclaimer slewing system. | Yet to be approved | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
16.2 | Retrofitting of Side Arm Charger-I & II at CHP U-8 | Yet to be approved | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
16.3 | Upgradation of GE/Schineder make PLC system atU-8 CHP. | Yet to be approved | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
16.4 | Refurbishment of Apron Feeder at CHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 12 | 12 |  |  | 12 | 0
16.5 | Provision of moveable stacker and crusher in CHP coal stack yard at CHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
16.6 | Procurement of Loco & Bulldozer at CHP U-8. | Yet to be approved | - | 0 | 0 | 0 | 0 | 12 | 12 |  |  | 12 | 0
17 | DPR on dry fly ash utilisation improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.1 | Design, supply, erection, installation & comissioning of intermediate silo with sub system at AHP U-8. | Yet to be approved | - | 0 | 38 | 38 | 0 | 0 | 0 |  |  | 0 | 0
18 | DPR on ash handling plant improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | Design, supply, erection & comissioning of weigh bridge for silo at AHP U-8. | Yet to be approved | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
18.2 | Supply, installation & comissioning of energy efficient air compressor at AHP U-8. | Yet to be approved | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
18.3 | PROCUREMENT OF COMPLETE ASSEMBLY OF SAM MAKE AR-150/510 PUMPS (2 NOS) FOR REPLACEMENT OF ASH SLURRY PUMPS OF BOTTOM ASH SLURRY DISPOSAL FROM SLURRY TANK TO ASH BUND IN SLURRY PUMP HOUSE. | Yet to be approved | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | PROCUREMENT OF COMPLETE ASSEMBLY OF SAM MAKE ZM-II 530/02 (2 NOS) FOR REPLACEMENT OF HP PUMPS OF BOTTOM ASH & COARSE ASH EVACUATION FROM BA/CA HOPPERS TO SLURRY TANK IN ASH WATER PUMP HOUSE. 0.75 0.89 | Yet to be approved | - | 0 | 0.4 | 0.4 | 0 | 0 | 0 |  |  | 0 | 0
18.5 | Procurement of vacuum pumps complete assembly for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
18.6 | Procurement of vacuum pumps complete assembly for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
18.7 | Procurement of Feed Gate Complete Assembly along with modified metallurgy to enhance the life of Clinker Grinder. | Yet to be approved | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
18.8 | Procurement of Double Roll Clinker Grinder Complete Assembly with Drive Unit installed at AHP | Yet to be approved | - | 0 | 1.25 | 1.25 | 0 | 0 | 0 |  |  | 0 | 0
18.9 | Procurement of Instrument Air Dryers assembly for performance improvement | Yet to be approved | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | Procurement of various types of Isolation Valves assembly, Dome Valves assembly, Root Valve Assembly & Expansion Bellows Assembly for Dry Ash Conveing performance improvement | Yet to be approved | - | 0 | 3.6 | 3.6 | 0 | 0 | 0 |  |  | 0 | 0
19 | DPR on ash handling plant improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | Design, supply, erection, installation & comissioning of DM water close loop cooling system for air compressors at AHP U-8. | Yet to be approved | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
19.2 | Up-gradation of Existing Schneider make PLC (HMI + PLC hardware) installed at AHP Unit -8 at Parli TPS. | Yet to be approved | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
19.3 | Procurement of HT motors for AHP U-8 Parli TPS. | Yet to be approved | - | 0 | 2.3 | 2.3 | 0 | 0 | 0 |  |  | 0 | 0
19.4 | PROCUREMENT OF CRITICAL GEARBOXES AND FLUID COUPLINGS INTERNAL ASSEMBLIES FOR SLURRY PUMPS AND SILO HCSD SYSTEM INSTALLED AT AHP, PARLI TPS. | Yet to be approved | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
19.5 | Procurement of Atlas Copco Make Instrument Air Compressors Critical/Non-Critical Spares sub-assembly for performance improvement | Yet to be approved | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
19.6 | Upgradation and improvement in Hopper Temperature monitoring system by providing Rf Type Hopper Level Sensors for performance improvement of conveying of Dry ash evacuation system. | Yet to be approved | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
20 | DPR on ash handling plant improvement scheme for AHP U-8 NPTPS Parli-V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.1 | Design, supply, erection, installation & comissioning ESP 1st & 2nd field dry fly ash evacuation & conveying system at AHP U-8. | Yet to be approved | - | 0 | 21.25 | 21.25 | 0 | 0 | 0 |  |  | 0 | 0
20.2 | Design, supply, erection, installation & comissioning of dry ash evacuation & conveying system for APH & Economiser ash hoppers at AHP U-8. | Yet to be approved | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
21 | Verious Civil schemes in Unit 8 NPTPS Parli V. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Construction of chemical laboratory building at Unit 8, NPTPS, Parli V. | Yet to be approved | - | 0 | 3.78 | 3.78 | 0 | 0 | 0 |  |  | 0 | 0
21.2 | Construction of Alum/salt storage area at Unit No.8 (1X250MW) NPTPS Parli Vaijnath. | Yet to be approved | - | 0 | 3.46 | 3.46 | 0 | 0 | 0 |  |  | 0 | 0
21.3 | Construction of Fire Fighting station at Unit-8, NPTPS Parli V. | Yet to be approved | - | 0 | 1.86 | 1.86 | 0 | 0 | 0 |  |  | 0 | 0
21.4 | Construction of workshop building at Unit-8, NPTPS Parli V. | Yet to be approved | - | 0 | 2.13 | 2.13 | 0 | 0 | 0 |  |  | 0 | 0
22 | CHP improvement scheme at 250 MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.1 | CHP improvement scheme at 250 MW | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0.56615 | 0.56615 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) GA | 0 | - | 0 | 1.5031 | 1.5637 | -0.060588 | 0.29 | 0.29 |  |  | 0.29 | -0.060588
0 | 0 | 0 | - | 0 | 0.29 | 0 | 0.29 | 0 | 0 |  |  | 0 | 0.29
0 | C) Asset received from Project U#8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Asset Recived From Civil-U#8-Land-10101 | N.A. | - | 0 | 0.0031293 | 0 | 0.0031293 | 0 | 0 |  |  | 0 | 0.0031293
2 | Asset Recived From Civil-U#8-T.G. Building-10201 | N.A. | - | 0 | 0.010038 | 0 | 0.010038 | 0 | 0 |  |  | 0 | 0.010038
3 | Asset Recived From Civil-U#8-T.G. Building(BC)bay&control room-10201 | N.A. | - | 0 | 0.0045784 | 0 | 0.0045784 | 0 | 0 |  |  | 0 | 0.0045784
4 | Asset Recived From Civil-U#8-StructuralSteelWorks4TGBldgA2EBays-10201 | N.A. | - | 0 | 0.0013976 | 0 | 0.0013976 | 0 | 0 |  |  | 0 | 0.0013976
5 | Asset Recived From Civil-U#8-WTP Building-10201 | N.A. | - | 0 | 0.00011482 | 0 | 0.00011482 | 0 | 0 |  |  | 0 | 0.00011482
6 | Asset Recived From Civil-U#8-DG SET ROOM CUM AIR COMP. HOUSE-10201 | N.A. | - | 0 | 0.00010598 | 0 | 0.00010598 | 0 | 0 |  |  | 0 | 0.00010598
7 | Asset Recived From Civil-U#8-WTP-Raw/Fire water pump House-10233 | N.A. | - | 0 | 0.00069019 | 0 | 0.00069019 | 0 | 0 |  |  | 0 | 0.00069019
8 | Asset Recived From Civil-U#8-SERVICE BUILDING -10211 | N.A. | - | 0 | 0.00055144 | 0 | 0.00055144 | 0 | 0 |  |  | 0 | 0.00055144
9 | Asset Recived From Civil-U#8-Canteen -10233 | N.A. | - | 0 | 0.00072491 | 0 | 0.00072491 | 0 | 0 |  |  | 0 | 0.00072491
10 | Asset Recived From Civil-U#8-PARKING SHED -10233 | N.A. | - | 0 | 6.111e-06 | 0 | 6.111e-06 | 0 | 0 |  |  | 0 | 6.111e-06
11 | Asset Recived From Civil-U#8-Time Security Building -10233 | N.A. | - | 0 | 3.595e-05 | 0 | 3.595e-05 | 0 | 0 |  |  | 0 | 3.595e-05
12 | Asset Recived From Civil-U#8-Misc.Building/structure/Watchtower-10233 | N.A. | - | 0 | 0.00017243 | 0 | 0.00017243 | 0 | 0 |  |  | 0 | 0.00017243
13 | Asset Recived From Civil-U#8-Boundry compound wall Mall-10233 | N.A. | - | 0 | 0.15766 | 0 | 0.15766 | 0 | 0 |  |  | 0 | 0.15766
14 | Asset Recived From Civil-U#8-Workshop civil work-10233 | N.A. | - | 0 | 4.188e-05 | 0 | 4.188e-05 | 0 | 0 |  |  | 0 | 4.188e-05
15 | Asset Recived From Civil-U#8-Interior Work for CEC-I Office-10233 | N.A. | - | 0 | 5.6438e-05 | 0 | 5.6438e-05 | 0 | 0 |  |  | 0 | 5.6438e-05
16 | Asset Recived From Civil-U#8-WTP-Raw water reservoir -10305 | N.A. | - | 0 | 0.0012248 | 0 | 0.0012248 | 0 | 0 |  |  | 0 | 0.0012248
17 | Asset Recived From Civil-U#8-WTP-Clarifier -10305 | N.A. | - | 0 | 0.0011652 | 0 | 0.0011652 | 0 | 0 |  |  | 0 | 0.0011652
18 | Asset Recived From Civil-U#8-WTP-Clarifier Water Storage Tank-10305 | N.A. | - | 0 | 0.00019514 | 0 | 0.00019514 | 0 | 0 |  |  | 0 | 0.00019514
19 | Asset Recived From Civil-U#8-C.W. pump house & forebay-10310 | N.A. | - | 0 | 0.00052946 | 0 | 0.00052946 | 0 | 0 |  |  | 0 | 0.00052946
20 | Asset Recived From Civil-U#8-Construction of STP for Colony-10322 | N.A. | - | 0 | 0.00017966 | 0 | 0.00017966 | 0 | 0 |  |  | 0 | 0.00017966
21 | Asset Recived From Civil-U#8-Cooling Towers-10311 | N.A. | - | 0 | 0.37628 | 0 | 0.37628 | 0 | 0 |  |  | 0 | 0.37628
22 | Asset Recived From Civil-U#8-Railway sidings-10412 | N.A. | - | 0 | 0.13615 | 0 | 0.13615 | 0 | 0 |  |  | 0 | 0.13615
23 | Asset Recived From Civil-U#8-In plant Roads -10401 | N.A. | - | 0 | 0.0009103 | 0 | 0.0009103 | 0 | 0 |  |  | 0 | 0.0009103
24 | Asset Recived From Civil-U#8-Pipe Rack -10419 | N.A. | - | 0 | 0.00041823 | 0 | 0.00041823 | 0 | 0 |  |  | 0 | 0.00041823
25 | Asset Recived From Civil-U#8-Transformar yard area -10541 | N.A. | - | 0 | 0.00053169 | 0 | 0.00053169 | 0 | 0 |  |  | 0 | 0.00053169
26 | Asset Recived From Civil-U#8-BA-Boiler and Auxilary foundation-10501 | N.A. | - | 0 | 0.0061116 | 0 | 0.0061116 | 0 | 0 |  |  | 0 | 0.0061116
27 | Asset Recived From Civil-U#8-BA-FD FAN FOUNDATIONS -10501 | N.A. | - | 0 | 0.00011166 | 0 | 0.00011166 | 0 | 0 |  |  | 0 | 0.00011166
28 | Asset Recived From Civil-U#8-BA-PA FAN FOUNDATION -10501 | N.A. | - | 0 | 0.00011166 | 0 | 0.00011166 | 0 | 0 |  |  | 0 | 0.00011166
29 | Asset Recived From Civil-U#8-BA-I.D. Fan foundation -10501 | N.A. | - | 0 | 0.00022332 | 0 | 0.00022332 | 0 | 0 |  |  | 0 | 0.00022332
30 | Asset Recived From Civil-U#8-BA-MILL FOUNDATION-10501 | N.A. | - | 0 | 0.00019826 | 0 | 0.00019826 | 0 | 0 |  |  | 0 | 0.00019826
31 | Asset Recived From Civil-U#8-BA-BUNKER FOUNDATION & STRUCTURE-10515 | N.A. | - | 0 | 0.0013925 | 0 | 0.0013925 | 0 | 0 |  |  | 0 | 0.0013925
32 | Asset Recived From Civil-U#8-ESP-10501 | N.A. | - | 0 | 0.00070722 | 0 | 0.00070722 | 0 | 0 |  |  | 0 | 0.00070722
33 | Asset Recived From Civil-U#8-ESP Control Room-10501 | N.A. | - | 0 | 0.00042763 | 0 | 0.00042763 | 0 | 0 |  |  | 0 | 0.00042763
34 | Asset Recived From Civil-U#8-RCC Chimney -10501 | N.A. | - | 0 | 0.0046127 | 0 | 0.0046127 | 0 | 0 |  |  | 0 | 0.0046127
35 | Asset Recived From Civil-U#8-WTP-D.M.Plant equipment fdn. etc.-10509 | N.A. | - | 0 | 6.3898e-05 | 0 | 6.3898e-05 | 0 | 0 |  |  | 0 | 6.3898e-05
36 | Asset Recived From Civil-U#8-CHP-Wagon Tippler-10515 | N.A. | - | 0 | 0.00094041 | 0 | 0.00094041 | 0 | 0 |  |  | 0 | 0.00094041
37 | Asset Recived From Civil-U#8-CHP-Crusher House -10515 | N.A. | - | 0 | 0.00074704 | 0 | 0.00074704 | 0 | 0 |  |  | 0 | 0.00074704
38 | Asset Recived From Civil-U#8-CHP-Stacker Reclaimer -10515 | N.A. | - | 0 | 0.00028485 | 0 | 0.00028485 | 0 | 0 |  |  | 0 | 0.00028485
39 | Asset Recived From Civil-U#8-CHP-Stock Yard-10515 | N.A. | - | 0 | 0.00015851 | 0 | 0.00015851 | 0 | 0 |  |  | 0 | 0.00015851
40 | Asset Recived From Civil-U#8-CHP-ConveyorPedetals&TransferPoint-10515 | N.A. | - | 0 | 0.00055408 | 0 | 0.00055408 | 0 | 0 |  |  | 0 | 0.00055408
41 | Asset Recived From Civil-U#8-CHP-MCC ROOM -10515 | N.A. | - | 0 | 0.00026945 | 0 | 0.00026945 | 0 | 0 |  |  | 0 | 0.00026945
42 | Asset Recived From Civil-U#8-AHP-RCC Ash Silo -10501 | N.A. | - | 0 | 0.00016423 | 0 | 0.00016423 | 0 | 0 |  |  | 0 | 0.00016423
43 | Asset Recived From Civil-U#8-AHP-Staicase near Silo-10501 | N.A. | - | 0 | 1.7302e-05 | 0 | 1.7302e-05 | 0 | 0 |  |  | 0 | 1.7302e-05
44 | Asset Recived From Civil-U#8-AHP-Drain sump in Silo Area -10501 | N.A. | - | 0 | 8.551e-06 | 0 | 8.551e-06 | 0 | 0 |  |  | 0 | 8.551e-06
45 | Asset Recived From Civil-U#8-AHP-Slurry Mixing Tank Fdn.-10501 | N.A. | - | 0 | 1.6923e-05 | 0 | 1.6923e-05 | 0 | 0 |  |  | 0 | 1.6923e-05
46 | Asset Recived From Civil-U#8-AHP-HCSD PUMP HOUSE-10501 | N.A. | - | 0 | 5.8934e-05 | 0 | 5.8934e-05 | 0 | 0 |  |  | 0 | 5.8934e-05
47 | Asset Recived From Civil-U#8-AHP-Ash Slurry Pump House -10501 | N.A. | - | 0 | 0.00014947 | 0 | 0.00014947 | 0 | 0 |  |  | 0 | 0.00014947
48 | Asset Recived From Civil-U#8-AHP-Ash Slurry Sump-10501 | N.A. | - | 0 | 4.5159e-05 | 0 | 4.5159e-05 | 0 | 0 |  |  | 0 | 4.5159e-05
49 | Asset Recived From Civil-U#8-AHP-Ash Water Tank-10501 | N.A. | - | 0 | 3.422e-05 | 0 | 3.422e-05 | 0 | 0 |  |  | 0 | 3.422e-05
50 | Asset Recived From Civil-U#8-AHP-Bottom Ash Hopper-10501 | N.A. | - | 0 | 4.409e-05 | 0 | 4.409e-05 | 0 | 0 |  |  | 0 | 4.409e-05
51 | Asset Recived From Civil-U#8-AHP-Drain sump in BAH Area -10501 | N.A. | - | 0 | 8.575e-06 | 0 | 8.575e-06 | 0 | 0 |  |  | 0 | 8.575e-06
52 | Asset Recived From Civil-U#8-Ash Slurry Pipe Line AHP-Pedestals-10501 | N.A. | - | 0 | 0.00013846 | 0 | 0.00013846 | 0 | 0 |  |  | 0 | 0.00013846
53 | Asset Recived From Civil-U#8-AHP-Buffer Hopper Foundation-10501 | N.A. | - | 0 | 3.5628e-05 | 0 | 3.5628e-05 | 0 | 0 |  |  | 0 | 3.5628e-05
54 | Asset Recived From Civil-U#8-AHP-Mill reject hopper foundation-10501 | N.A. | - | 0 | 1.7814e-05 | 0 | 1.7814e-05 | 0 | 0 |  |  | 0 | 1.7814e-05
55 | Asset Recived From Civil-U#8-FHP-Fuel Oil pump house-10516 | N.A. | - | 0 | 0.00065769 | 0 | 0.00065769 | 0 | 0 |  |  | 0 | 0.00065769
56 | Asset Recived From Civil-U#8-FHP-DYKE AREA -10516 | N.A. | - | 0 | 1.9339e-05 | 0 | 1.9339e-05 | 0 | 0 |  |  | 0 | 1.9339e-05
57 | Asset Recived From Civil-U#8-Effulent Treatment Plant -10509 | N.A. | - | 0 | 0.00014135 | 0 | 0.00014135 | 0 | 0 |  |  | 0 | 0.00014135
58 | Asset Recived From Project-U#8-Boiler Pressure parts-10501 | N.A. | - | 0 | 0.06549 | 0 | 0.06549 | 0 | 0 |  |  | 0 | 0.06549
59 | Asset Recived From Project-U#8-Mandatory Spares from BHEL–Trichy | N.A. | - | 0 | 0.0074619 | 0 | 0.0074619 | 0 | 0 |  |  | 0 | 0.0074619
60 | Asset Recived From Civil-U#8-Coal mill reject trench at coal mill D&E | N.A. | - | 0 | 0.04661 | 0 | 0.04661 | 0 | 0 |  |  | 0 | 0.04661
61 | Asset Recived From Project-U#8-Canteen Equipments & kitchen Utensils | N.A. | - | 0 | 0.21888 | 0 | 0.21888 | 0 | 0 |  |  | 0 | 0.21888
62 | Asset Recived From Project-U#8-Supply & Erection of ACW system-10310 | N.A. | - | 0 | 0.00083684 | 0 | 0.00083684 | 0 | 0 |  |  | 0 | 0.00083684
63 | Asset Recived From Project-U#8-SUPPLY & ERECTION OF CCW SYSTEM-10310 | N.A. | - | 0 | 0.004856 | 0 | 0.004856 | 0 | 0 |  |  | 0 | 0.004856
64 | Asset Recived From Project-U#8-TG set & its auxilleries-HP/LPFeedWate | N.A. | - | 0 | 0.016842 | 0 | 0.016842 | 0 | 0 |  |  | 0 | 0.016842
65 | Asset Recived From Project-U#8-TG set and its auxilleries- Boilerfeed | N.A. | - | 0 | 0.018479 | 0 | 0.018479 | 0 | 0 |  |  | 0 | 0.018479
66 | Asset Recived From Project-U#8-Air Conditioning-MandatorySpares-10576 | N.A. | - | 0 | 1.7256e-05 | 0 | 1.7256e-05 | 0 | 0 |  |  | 0 | 1.7256e-05
67 | Asset Recived From Project-U#8-Air Conditioning system-10576 | N.A. | - | 0 | 0.0013446 | 0 | 0.0013446 | 0 | 0 |  |  | 0 | 0.0013446
68 | Asset Recived From Project-U#8-AHP-FLY ASH & HCSD-SYSTEM-10501 | N.A. | - | 0 | 0.0021652 | 0 | 0.0021652 | 0 | 0 |  |  | 0 | 0.0021652
69 | Asset Recived From Project-U#8-AHP-FLYASH&HCSD-SYSTEMBOUGHT OUT-10501 | N.A. | - | 0 | 0.0070969 | 0 | 0.0070969 | 0 | 0 |  |  | 0 | 0.0070969
70 | Asset Recived From Project-U#8-AHP-BOTTOM ASH SYSTEM-10501 | N.A. | - | 0 | 0.012126 | 0 | 0.012126 | 0 | 0 |  |  | 0 | 0.012126
71 | Asset Recived From Project-U#8-AHP-ELECTRICAL C & I-10501 | N.A. | - | 0 | 0.004053 | 0 | 0.004053 | 0 | 0 |  |  | 0 | 0.004053
72 | Asset Recived From Project-U#8-AHP-GEHO PUMP-10501 | N.A. | - | 0 | 0.0095128 | 0 | 0.0095128 | 0 | 0 |  |  | 0 | 0.0095128
73 | Asset Recived FromProject-U#8-Boiler&Aux -Power Cycle Piping-10501 | N.A. | - | 0 | 0.041005 | 0 | 0.041005 | 0 | 0 |  |  | 0 | 0.041005
74 | Asset Recived From Project-U#8-Boiler&Aux-SUIT BLOWER & PIPING-10501 | N.A. | - | 0 | 0.083837 | 0 | 0.083837 | 0 | 0 |  |  | 0 | 0.083837
75 | Asset Recived From Project-U#8-Boiler & Auxillaries - PA FAN-10501 | N.A. | - | 0 | 0.0010226 | 0 | 0.0010226 | 0 | 0 |  |  | 0 | 0.0010226
76 | Asset Recived From Project-U#8-Boiler&Aux-Air Preheaters-10501 | N.A. | - | 0 | 0.013281 | 0 | 0.013281 | 0 | 0 |  |  | 0 | 0.013281
77 | Asset Recived From Project-U#8-Boiler & Auxillaries -COAL MILL-10501 | N.A. | - | 0 | 0.051244 | 0 | 0.051244 | 0 | 0 |  |  | 0 | 0.051244
78 | Asset Recived From Project-U#8-Boiler & Auxillaries -FD FAN-10501 | N.A. | - | 0 | 0.0006817 | 0 | 0.0006817 | 0 | 0 |  |  | 0 | 0.0006817
79 | Asset Recived From Project-U#8-Boiler & Auxillaries- ID FAN-10501 | N.A. | - | 0 | 0.0017043 | 0 | 0.0017043 | 0 | 0 |  |  | 0 | 0.0017043
80 | Asset Recived From Project-U#8-Boiler&Aux-Mandatory Spares-10501 | N.A. | - | 0 | 0.0097935 | 0 | 0.0097935 | 0 | 0 |  |  | 0 | 0.0097935
81 | Asset Recived From Project-U#8-Boiler&Aux-PLATFORM,STAIRS,GRATINGS, | N.A. | - | 0 | 0.030596 | 0 | 0.030596 | 0 | 0 |  |  | 0 | 0.030596
82 | Asset Recived From Project-U#8-Boiler Pressure parts-10501 | N.A. | - | 0 | 0.17807 | 0 | 0.17807 | 0 | 0 |  |  | 0 | 0.17807
83 | Asset Recived From Project-U#8-220V-BATTERY+CHARGERS-MAIN PLANT-10563 | N.A. | - | 0 | 0.0020848 | 0 | 0.0020848 | 0 | 0 |  |  | 0 | 0.0020848
84 | Asset Recived From Project-U#8-220V -BATTERY WITH CHARGERS(CHP)-10563 | N.A. | - | 0 | 0.00020745 | 0 | 0.00020745 | 0 | 0 |  |  | 0 | 0.00020745
85 | Asset Recived From Project-U#8-220V-BATTERY+CHARG-WAGON TRIP-2N-10563 | N.A. | - | 0 | 8.4674e-05 | 0 | 8.4674e-05 | 0 | 0 |  |  | 0 | 8.4674e-05
86 | Asset Recived From Project-U#8-BOP-OTHER C& i INSTRUMENTS-10509 | N.A. | - | 0 | 0.0013441 | 0 | 0.0013441 | 0 | 0 |  |  | 0 | 0.0013441
87 | Asset Recived From Project-U#8-CHP-CONVEYOR SYSTEM-10515 | N.A. | - | 0 | 0.015409 | 0 | 0.015409 | 0 | 0 |  |  | 0 | 0.015409
88 | Asset Recived From Project-U#8-CHP-WOBLER FEEDER-10515 | N.A. | - | 0 | 0.00054613 | 0 | 0.00054613 | 0 | 0 |  |  | 0 | 0.00054613
89 | Asset Recived From Project-U#8-CHP-APRON FEEDER-10515 | N.A. | - | 0 | 0.0028149 | 0 | 0.0028149 | 0 | 0 |  |  | 0 | 0.0028149
90 | Asset Recived From Project-U#8-CHP-ILMS,METAL DETECTOR,BELT WEIGHER | N.A. | - | 0 | 0.0011704 | 0 | 0.0011704 | 0 | 0 |  |  | 0 | 0.0011704
91 | Asset Recived From Project-U#8-CHP-IMPACT CRUSHER-10515 | N.A. | - | 0 | 0.0020638 | 0 | 0.0020638 | 0 | 0 |  |  | 0 | 0.0020638
92 | Project-U#8-CHP-STRACKER CUM RECLAIMER-10515 | N.A. | - | 0 | 0.0082014 | 0 | 0.0082014 | 0 | 0 |  |  | 0 | 0.0082014
93 | Project-U#8-CHP-SIDE DISCHARGE TYPE WAGON TRIPPLER | N.A. | - | 0 | 0.0077836 | 0 | 0.0077836 | 0 | 0 |  |  | 0 | 0.0077836
94 | Project-U#8-Coal Handling Plant-M.S.-10515 | N.A. | - | 0 | 0.00034267 | 0 | 0.00034267 | 0 | 0 |  |  | 0 | 0.00034267
95 | Project-U#8-communication system-10572 | N.A. | - | 0 | 0.0019253 | 0 | 0.0019253 | 0 | 0 |  |  | 0 | 0.0019253
96 | Project-U#8-UPS INVERTORS-10563 | N.A. | - | 0 | 0.00051465 | 0 | 0.00051465 | 0 | 0 |  |  | 0 | 0.00051465
97 | Project-U#8-UPS ACDS-10563 | N.A. | - | 0 | 8.9956e-05 | 0 | 8.9956e-05 | 0 | 0 |  |  | 0 | 8.9956e-05
98 | Project-U#8-UPS BATTERIRERS-10563 | N.A. | - | 0 | 0.00051465 | 0 | 0.00051465 | 0 | 0 |  |  | 0 | 0.00051465
99 | Project-U#8-24V BATTERY CHARGERS (SGTG)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
100 | Project-U#8-24V BATTERY CHARGERS (BOP)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
101 | Project-U#8-BATTERIS FOR (SGTG)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
102 | Project-U#8-BATTERIS FOR (BOP)-10563 | N.A. | - | 0 | 0.00022873 | 0 | 0.00022873 | 0 | 0 |  |  | 0 | 0.00022873
103 | Project-U#8-DCDB(SGTG)-10563 | N.A. | - | 0 | 5.7183e-05 | 0 | 5.7183e-05 | 0 | 0 |  |  | 0 | 5.7183e-05
104 | Project-U#8-DCDB(BOP)-10563 | N.A. | - | 0 | 5.7183e-05 | 0 | 5.7183e-05 | 0 | 0 |  |  | 0 | 5.7183e-05
105 | Project-U#8-Controls & Instru. for Main Plant(BTG) | N.A. | - | 0 | 0.044292 | 0 | 0.044292 | 0 | 0 |  |  | 0 | 0.044292
106 | Project-U#8-CW Chlorination system-10509 | N.A. | - | 0 | 0.0011974 | 0 | 0.0011974 | 0 | 0 |  |  | 0 | 0.0011974
107 | Project-U#8-D.G.SET-10509 | N.A. | - | 0 | 3.7894e-05 | 0 | 3.7894e-05 | 0 | 0 |  |  | 0 | 3.7894e-05
108 | Project-U#8-D.M.Water System-10509 | N.A. | - | 0 | 0.005785 | 0 | 0.005785 | 0 | 0 |  |  | 0 | 0.005785
109 | Project-U#8-DG set- Manadatory Spares-10509 | N.A. | - | 0 | 0.00025004 | 0 | 0.00025004 | 0 | 0 |  |  | 0 | 0.00025004
110 | Project-U#8-DG Set Room cum Air Compressor House | N.A. | - | 0 | 0.0055794 | 0 | 0.0055794 | 0 | 0 |  |  | 0 | 0.0055794
111 | Project-U#8-Steel for TechnologicalStructure-10501 | N.A. | - | 0 | 0.14836 | 0 | 0.14836 | 0 | 0 |  |  | 0 | 0.14836
112 | Project-U#8-Electrical Package for BOP-10509 | N.A. | - | 0 | 0.0024904 | 0 | 0.0024904 | 0 | 0 |  |  | 0 | 0.0024904
113 | Project-U#8-Electrical CHARGES-10509 | N.A. | - | 0 | 4.1155e-05 | 0 | 4.1155e-05 | 0 | 0 |  |  | 0 | 4.1155e-05
114 | Project-U#8-Electrical Package for BOP-Mandatory | N.A. | - | 0 | 0.0002757 | 0 | 0.0002757 | 0 | 0 |  |  | 0 | 0.0002757
115 | Project-U#8-Fire Protection, Alarm & Detection | N.A. | - | 0 | 0.0071788 | 0 | 0.0071788 | 0 | 0 |  |  | 0 | 0.0071788
116 | Project-U#8-Fuel Oil Pump House-10516 | N.A. | - | 0 | 0.0040925 | 0 | 0.0040925 | 0 | 0 |  |  | 0 | 0.0040925
117 | Project-U#8-Generator Transformer-10541 | N.A. | - | 0 | 0.012655 | 0 | 0.012655 | 0 | 0 |  |  | 0 | 0.012655
118 | Project-U#8-Generator/Transformer protection | N.A. | - | 0 | 0.00024539 | 0 | 0.00024539 | 0 | 0 |  |  | 0 | 0.00024539
119 | Project-U#8-H.T.Switchgear for main plant-10561 | N.A. | - | 0 | 0.025188 | 0 | 0.025188 | 0 | 0 |  |  | 0 | 0.025188
120 | Project-U#8-Indoor & Outdoor plant lighting-10599 | N.A. | - | 0 | 0.0004077 | 0 | 0.0004077 | 0 | 0 |  |  | 0 | 0.0004077
121 | Project-U#8-L.P.Piping including valves-10509 | N.A. | - | 0 | 0.0038246 | 0 | 0.0038246 | 0 | 0 |  |  | 0 | 0.0038246
122 | Project-U#8-L.T. Electrical for main plant.-10561 | N.A. | - | 0 | 8.7067e-05 | 0 | 8.7067e-05 | 0 | 0 |  |  | 0 | 8.7067e-05
123 | Project-U#8-Laying&Termination of HT cables-10561 | N.A. | - | 0 | 0.0008231 | 0 | 0.0008231 | 0 | 0 |  |  | 0 | 0.0008231
124 | Project-U#8-MainBoiler Structure&foundations-10501 | N.A. | - | 0 | 0.09941 | 0 | 0.09941 | 0 | 0 |  |  | 0 | 0.09941
125 | Project-U#8-Mandatory Spares for Ash HandlingPlant | N.A. | - | 0 | 0.0015616 | 0 | 0.0015616 | 0 | 0 |  |  | 0 | 0.0015616
126 | Project-U#8-Mandatory spares for C&I of Main Plant | N.A. | - | 0 | 0.0050295 | 0 | 0.0050295 | 0 | 0 |  |  | 0 | 0.0050295
127 | Project-U#8-Mandatory Spares for Electrical MainPa | N.A. | - | 0 | 0.015601 | 0 | 0.015601 | 0 | 0 |  |  | 0 | 0.015601
128 | Project-U#8-Mandatory Spares For TG & Auxilliaries | N.A. | - | 0 | 0.0062588 | 0 | 0.0062588 | 0 | 0 |  |  | 0 | 0.0062588
129 | Project-U#8-Misc. Cranes & hoists-10553 | N.A. | - | 0 | 0.0023537 | 0 | 0.0023537 | 0 | 0 |  |  | 0 | 0.0023537
130 | Project-U#8-Miscellaneous Pumps -10599 | N.A. | - | 0 | 0.0015672 | 0 | 0.0015672 | 0 | 0 |  |  | 0 | 0.0015672
131 | Project-U#8-Passanger lift for TG Building-10599 | N.A. | - | 0 | 0.0016358 | 0 | 0.0016358 | 0 | 0 |  |  | 0 | 0.0016358
132 | Project-U#8-Passanger/Material Lift at boiler side | N.A. | - | 0 | 0.00084731 | 0 | 0.00084731 | 0 | 0 |  |  | 0 | 0.00084731
133 | Project-U#8-Chemical Laboratory -10509 | N.A. | - | 0 | 0.0011648 | 0 | 0.0011648 | 0 | 0 |  |  | 0 | 0.0011648
134 | Project-U#8-Sewage Treatment Plant-10509 | N.A. | - | 0 | 0.0019006 | 0 | 0.0019006 | 0 | 0 |  |  | 0 | 0.0019006
135 | Project-U#8-Station Transformer-10541 | N.A. | - | 0 | 0.026576 | 0 | 0.026576 | 0 | 0 |  |  | 0 | 0.026576
136 | Project-U#8-Steam Turbine set-10503 | N.A. | - | 0 | 0.13864 | 0 | 0.13864 | 0 | 0 |  |  | 0 | 0.13864
137 | Project-U#8-TG set and its auxilleries- Condensor | N.A. | - | 0 | 0.012703 | 0 | 0.012703 | 0 | 0 |  |  | 0 | 0.012703
138 | Project-U#8-TG set and its auxilleries -Generator | N.A. | - | 0 | 0.032545 | 0 | 0.032545 | 0 | 0 |  |  | 0 | 0.032545
139 | Project-U#8-TG set and its auxilleries-Condensor | N.A. | - | 0 | 0.029273 | 0 | 0.029273 | 0 | 0 |  |  | 0 | 0.029273
140 | Project-U#8-TG set & its auxilleries-Derator-10503 | N.A. | - | 0 | 0.002758 | 0 | 0.002758 | 0 | 0 |  |  | 0 | 0.002758
141 | Project-U#8-TG set and its auxilleries-DMMakeUpSys | N.A. | - | 0 | 0.0010491 | 0 | 0.0010491 | 0 | 0 |  |  | 0 | 0.0010491
142 | Project-U#8-TG set and its auxilleries-Gas System | N.A. | - | 0 | 0.0056178 | 0 | 0.0056178 | 0 | 0 |  |  | 0 | 0.0056178
143 | Project-U#8-TG set and its auxilleries-GoveringSys | N.A. | - | 0 | 4.9466e-05 | 0 | 4.9466e-05 | 0 | 0 |  |  | 0 | 4.9466e-05
144 | Project-U#8-TG set and its auxilleries-HP/LP By-pa | N.A. | - | 0 | 0.010752 | 0 | 0.010752 | 0 | 0 |  |  | 0 | 0.010752
145 | Project-U#8-TG set and its auxilleries-HP/LP Dozin | N.A. | - | 0 | 0.00039941 | 0 | 0.00039941 | 0 | 0 |  |  | 0 | 0.00039941
146 | Project-U#8-TG set and its auxilleries-SealOilPump | N.A. | - | 0 | 9.8566e-05 | 0 | 9.8566e-05 | 0 | 0 |  |  | 0 | 9.8566e-05
147 | Project-U#8-TG set and its auxilleries-Vaccum Syst | N.A. | - | 0 | 0.010304 | 0 | 0.010304 | 0 | 0 |  |  | 0 | 0.010304
148 | Project-U#8-Turbine Lub. Oil System With Purifier | N.A. | - | 0 | 0.0022364 | 0 | 0.0022364 | 0 | 0 |  |  | 0 | 0.0022364
149 | Project-U#8-Ventillation system-10599 | N.A. | - | 0 | 0.0014389 | 0 | 0.0014389 | 0 | 0 |  |  | 0 | 0.0014389
150 | Asset Recived From Project-U#8-M.SPARE_Ventillation system-10599 | N.A. | - | 0 | 8.5482e-05 | 0 | 8.5482e-05 | 0 | 0 |  |  | 0 | 8.5482e-05
151 | Asset Recived From Project-U#8-Water Treatment Plant-10509 | N.A. | - | 0 | 0.0042384 | 0 | 0.0042384 | 0 | 0 |  |  | 0 | 0.0042384
152 | Asset Recived From Project-U#8-WORK SHOP MAD_SPARE-10565 | N.A. | - | 0 | 0.00030445 | 0 | 0.00030445 | 0 | 0 |  |  | 0 | 0.00030445
153 | Asset Recived From Project-U#8-Workshop-10565 | N.A. | - | 0 | 0.0013286 | 0 | 0.0013286 | 0 | 0 |  |  | 0 | 0.0013286
154 | Asset Recived From Project-U#8-CMR SYSTEM-10501 | N.A. | - | 0 | 0.0020736 | 0 | 0.0020736 | 0 | 0 |  |  | 0 | 0.0020736
155 | Asset Recived From Project-U#8-MandatorySpares-WTP-10.509 | N.A. | - | 0 | 8.1517e-05 | 0 | 8.1517e-05 | 0 | 0 |  |  | 0 | 8.1517e-05
156 | Asset Recived From Project-U#8-E.1.07_MandSpar 4 C&I MS 4MeasuringIns E.1.07_M S for C&I_ MS For Measuring Ins | N.A. | - | 0 | 0.078697 | 0 | 0.078697 | 0 | 0 |  |  | 0 | 0.078697
157 | Asset Recived From Project-U#8-BOP_ELECTRICAL-10612 | N.A. | - | 0 | 0.01637 | 0 | 0.01637 | 0 | 0 |  |  | 0 | 0.01637
158 | Asset Recived From Project-U#8-Bus Ducts-10612 | N.A. | - | 0 | 0.012548 | 0 | 0.012548 | 0 | 0 |  |  | 0 | 0.012548
159 | Asset Recived From Project-U#8-Cable trays & supports-10612 | N.A. | - | 0 | 0.00036009 | 0 | 0.00036009 | 0 | 0 |  |  | 0 | 0.00036009
160 | Project-U#8-PCR FURNITURE-10810 | N.A. | - | 0 | 0.00030684 | 0 | 0.00030684 | 0 | 0 |  |  | 0 | 0.00030684
161 | Project-U#8 Server Intel QUAD CORE 02No. HP Office Server | N.A. | - | 0 | 0.11918 | 0.11918 | 0 | 0 | 0 |  |  | 0 | 0
162 | Supply Erection testing and commissining of 1000 m3 ETP Civil works | N.A. | - | 0 | 0.68324 | 0.68324 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 838.1535 | 844.4326 | -6.2791 | 65.29 | 65.29 | 0 | 0 | 65.29 | -6.2791