## F4
MSPGCL: KGSC, Pophali
MTR Petition Formats - Generation
Form 4: Summary of Capital Expenditure and Capitalisation
(Rs. Crore)
Sr. No. | Particulars | FY 2022-23 |  |  | FY 2023-24 |  |  | FY 2024-25 |  |  |  |  | Ensuing Years |  |  |  |  | Remarks
|  | MYT Order (227 of 2022) | April-March (Audited ) | True-Up requirement | MYT Order (227 of 2022) | April-March (Audited ) | True-Up requirement | MYT Order (227 of 2022) | Apr-Sep (Estimated) | Oct-Mar (Projected) | April - March (Projected) | Provisional True-Up requirement | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30
|  | (a) | (b) | (c) = (b) - (a) | (d) | (e) | (f) = (e) - (d) | (g) | (h) | (i) | (j) = (h )+ (i) | (k) = (j) - (g) | Projected | Projected | Projected | Projected | Projected
1 | Capital Expenditure |  | 52.6829 | 52.6829 |  | 28.7356 | 28.7356 |  |  |  | 87.3246 | 87.3246 | 253.7407 | 236.2 | 173.44 | 80.99 | 90.43
2 | Capitalisation | 54.65 | 25.8191 | -28.8309 | 61.46 | 18.011 | -43.449 | 61.72 | 24.38 | 82.55 | 106.927 | 45.207 | 258.9307 | 231.72 | 173.44 | 80.99 | 90.43
3 | IDC |  |  | 0 |  |  | 0 |  |  |  |  | 0
4 | Capitalisation + IDC | 54.65 | 25.8191 | -28.8309 | 61.46 | 18.011 | -43.449 | 61.72 | 24.38 | 82.55 | 106.927 | 45.207 | 258.9307 | 231.72 | 173.44 | 80.99 | 90.43
Note: * - Truing Up for FY 2022-23 & FY 2023-24 to be done under MERC MYT Regulations 2019 with reference to amounts approved in the MERC Order on approval of Mid-Term Review for 4th MYT Control Period
Detailed Justification shall be provided for variation in approved capital expenditure and capitalisation vis-a-vis actual capital expenditure and capitalisation

## F4.1 KGSC
MSPGCL: KGSC, Pophali
MTR Petition Formats - Generation
| Project Details |  | Form 4.1: Capital Expenditure Plan | [14 empty] | (Rs. Crore)
Sr. No. | Project Code | Project Title | MERC Approval No. | MERC Approval Date | Project Purpose | Project Start Date |  |  | Project Completion date (Scheduled) |  |  | Capital Cost
[6 empty] | Original | Revised | Actual | Original | Revised | Actual | Approved | Actual Capital Cost Incurred | Deviation = Approved - Actual on account of
[14 empty] | Change in Scope of Work (a) | Material Cost (b) | IDC (c) | Others (d) | Total Deviation (a+b+c+d)
A) DPR Schemes
(i) Submitted to MERC
1 | Various improvement schemes at Pophali Hydro Power Station | DPR | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 0 | 2014-04-10 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
1.1 | ALSPA HMI Series 6 Centralog System | Scheme | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | Increase the unit availability due to improved reliability of the electronic equipments, resulting in the Grid stability | 2014-04-10 |  | 2014-03-13 | 2015-03-15 |  | 2015-03-25 | 6.8555 | 7.8386 |  |  |  |  | -0.98308
1.2 | 1 X 525 Tr chiller unit | Scheme | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | Increase the life of the electronic equipments and auxiliaries | 2014-04-10 |  | 2015-04-17 | 2015-05-15 |  | 2016-04-16 | 1.23 | 1.15 |  |  |  |  | 0.08
1.3 | Micom P343 Numerical generator protection relay with 24 DI & 24 DO with CLIO input. (5 Nos) | Scheme | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | More reliable and faster protection system for Generator and Transformer. | 2014-04-10 |  | 2016-04-27 | Mar-15 |  | 2017-05-17 | 1.4675 | 1.474 |  |  |  |  | -0.0065
1.4 | Security Building at Stage-IV | Scheme | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | Due to recent threats causes by the anti national activities and as per directives by the IB the security measures are being tightens. | 2014-04-10 |  | 2011-04-25 | - |  | 2014-03-07 | 0.16446 | 0.18377 |  |  |  |  | -0.019307
1.5 | Construction of recreation club building | Scheme | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | Good recreation is apparently generates lively and healthy atmosphere for achieving harmony among the whole community. | 2014-04-10 |  | 2011-01-05 | - |  | 24.09.2012 | 1.8204 | 2.1946 |  |  |  |  | -0.37421
1.6 | Security Building for Stage-IV at EVT | Scheme | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | Due to recent threats causes by the anti national activities and as per directives by the IB the security measures are being tightens. | 2014-04-10 |  | 2014-11-14 | 2015-11-14 |  | 2016-04-16 | 0.22776 | 0.25961 |  |  |  |  | -0.031858
0 | IDC | IDC | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 0 | 2014-04-10 |  | - | - |  | - | 0.1344 | 0 |  |  |  |  | 0.1344
3 | Various DPR Schemes for Civil Section, KGSC Pophali | DPR | MERC/CAPEX/20152016/00907 | 2015-11-05 | 0 | 2015-11-05 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
3.1 | Providing Road Network at KGSC, Pophali | Scheme | MERC/CAPEX/20152016/00907 | 2015-11-05 | Safety and smooth movement of vehicles and avoid accidents. | 2015-11-05 |  | 2016-12-28 | 2017-05-01 |  | 2019-12-19 | 7.776 | 7.0182 |  |  |  |  | 0.7578
3.2 | Modernisation & Refurbishing of Residential Complex | Scheme | MERC/CAPEX/20152016/00907 | 2015-11-05 | Conveniency for day to day work in the room | 2015-11-05 |  | 2017-06-17 | 2017-05-01 |  | 2020-06-30 | 8.985 | 8.9365 |  |  |  |  | 0.048533
3.3 | Water Supply & Sanitory Works | Scheme | MERC/CAPEX/20152016/00907 | 2015-11-05 | Clean and portable water to employees residence in colony & to Avoid leakages and save in water | 2015-11-05 |  | 2017-06-17 | 2017-04-01 |  | 2018-02-05 | 4.44 | 5.9018 |  |  |  |  | -1.4618
4 | Various Performance Improvement related schemes at KGSC, Pophali | DPR | MERC/CAPEX/20162017/01018 | 2016-11-17 | 0 | 2016-11-17 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
4.1 | Up gradation of 245 kV CTs at Stage-I&II SY | Scheme | MERC/CAPEX/20162017/01018 | 2016-11-17 | Improved accuracy class of CTs i.e. from 0.5S class to 0.2S class, and to accurate measurement & preciseness in reading | 2016-11-17 |  | 2018-08-02 | 2018-04-17 |  | 2020-03-31 | 1.9624 | 2.09 |  |  |  |  | -0.12758
4.2 | Up gradation of 245 kV PTs at Stage-I&II SY | Scheme | MERC/CAPEX/20162017/01018 | 2016-11-17 | Improved accuracy class of CTs i.e. from 0.5S class to 0.2S class, and to accurate measurement & preciseness in reading | 2016-11-17 |  | 2017-03-25 | 2017-10-17 |  | 2017-12-10 | 0.40509 | 0.3417 |  |  |  |  | 0.063385
4.3 | Up gradation of CW system of Stage-I&II Units | Scheme | MERC/CAPEX/20162017/01018 | 2016-11-17 | Aassured no any generation loss due the cooling water bus leakages and /or break down | 2016-11-17 |  | 2017-09-04 | 2017-12-17 |  | 2019-05-04 | 1.7099 | 1.4731 |  |  |  |  | 0.23685
4.4 | Up gradation of Intercom Exchange System between Stage-I&II PH & Admin. Bldg & Staff Colony. | Scheme | MERC/CAPEX/20162017/01018 | 2016-11-17 | Reliable, faster and improved communication system with better voice quality | 2016-11-17 |  | 2017-04-07 | 2017-11-17 |  | 2017-06-22 | 0.43826 | 0.359 |  |  |  |  | 0.079263
4.5 | Up gradation of 220 kV Breakers at KDPH SY | Scheme | MERC/CAPEX/20162017/01018 | 2016-11-17 | Increase the unit availability due to improved reliability of SF6 Breakers | 2016-11-17 |  | 2017-04-07 | 2017-11-17 |  | 2017-12-21 | 1.289 | 0.979 |  |  |  |  | 0.31005
4.6 | Procurement of Governing Oil Pumps for Stage-III Units. | Scheme | MERC/CAPEX/20162017/01018 | 2016-11-17 | Avoided reduction in generation of Stage-III due to failure of G.O. Pump. As stage-III Units are operated on tailrace water of Stage-I&II and Stage-IV, the operation of these Units will not be affected | 2016-11-17 |  | 2016-08-26 | 2017-10-17 |  | 2021-07-08 | 1.2316 | 0.70174 |  |  |  |  | 0.52988
4.7 | Up gradation of TG Governing system of Stage-IV Units. | Scheme | MERC/CAPEX/20162017/01018 | 2016-11-17 | The problems due to obsolete governing system will be eliminated | 2016-11-17 |  | 2016-09-01 | 2018-10-17 |  | - | 2.2152 | 2.7472 |  |  |  |  | -0.53204
4.8 | Up gradation of Numerical Protection system of Stage-IV Units. | Scheme | MERC/CAPEX/20162017/01018 | 2016-11-17 | 100% of the machine stator winding, including the star point, is protected under all operating modes, even at machine standstill. The innovative filtering technique enables high sensitivity for both stator and rotor protection, which enables early detection of faults | 2016-11-17 |  | 2017-10-05 | 2018-02-17 |  | 2021-03-04 | 2.8249 | 2.8674 |  |  |  |  | -0.04246
0 | IDC | IDC | MERC/CAPEX/20162017/01018 | 2016-11-17 | 0 | 2016-11-17 |  | - | - |  | - | 0.9 | 0 |  |  |  |  | 0.9
7 | Replacement of Generator Stator of unit No. 11 (80 MW), Stage III, KGSC Pophali | DPR | MERC/CAPEX/20172018/04592 | 2017-11-07 | 0 | 2017-11-07 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
7.1 | Replacement of Generator Stator of unit No. 11 (80 MW), Stage III, KGSC Pophali | Scheme | MERC/CAPEX/20172018/04592 | 2017-11-07 | Avoid the Generation loss due to unavailability of units | 2017-11-07 |  | 2023-07-10 | 2019-12-07 |  | 2024-04-23 | 22.54 | 16.579 |  |  |  |  | 5.961
8 | Procurement of new pelton wheel runners (2 Nos.) for Stage II at KGSC, Pophali | DPR | MERC/CAPEX/20172018/04421 | 2017-10-24 | 0 | 2017-10-24 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
8.1 | Procurement of new pelton wheel runners (2 Nos.) for Stage II at KGSC, Pophali | Scheme | MERC/CAPEX/20172018/04421 | 2017-10-24 | Avoid the Generation loss due to unavailability of units | 2017-10-24 |  | 2018-01-16 | 2019-10-24 |  | - | 13.07 | 0 |  |  |  |  | 13.07
11 | Implementation of 12 Nos. of various schemes at KGSC, Pophali. | DPR | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0 | 2019-05-24 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
11.1 | Replacement of UGB (8 Nos), LGB (8 Nos) & Generator air coolers (8 Nos) for Stage-I | Scheme | MERC/CAPEX/2019-2020/01 | 2019-05-24 | Better performance of Units | 2019-05-24 |  | 2022-01-19 | 2020-11-24 |  | - | 1.344 | 0 |  |  |  |  | 1.344
11.2 | Retrofitting of Generator & Gen-Transformer relays by new numerical protection system at Koyna Dam Power House (KDPH) Koynanagar | Scheme | MERC/CAPEX/2019-2020/01 | 2019-05-24 | Online testing facility with PC for testing of relay without disturbing the Generator and Offline testing facility with PC for secondary injection test including trip status. | 2019-05-24 |  | 2022-08-04 | 2021-02-24 |  | - | 1.097 | 0.82 |  |  |  |  | 0.277
11.3 | Replacement of two 220V Battery chargers with 220V dual float cum boost (60A) battery Charger including DCDB at KDPH, Koynanagar | Scheme | MERC/CAPEX/2019-2020/01 | 2019-05-24 | Increase the unit availability due to improved reliability of the 220 V D.C. Power Supply, resulting in the Grid stability. | 2019-05-24 |  | 2020-05-02 | 2020-09-24 |  | 25.02.2021 | 0.202 | 0.13782 |  |  |  |  | 0.064176
11.4 | Replacement of 220KV current transformer (54 Nos), Potential transformer (13 Nos),110KV Current Transformer (14 Nos)& Potential Transformer (4 Nos),Stage-III. | Scheme | MERC/CAPEX/2019-2020/01 | 2019-05-24 | Accurate measurement & preciseness in reading | 2019-05-24 |  | - | 2020-08-24 |  | - | 5.281 | 0 |  |  |  |  | 5.281
11.5 | Replacement of Generator Air Cooler (32 Nos), St-III | Scheme | MERC/CAPEX/2019-2020/01 | 2019-05-24 | Better performance of Units | 2019-05-24 |  | 2022-08-26 | 2020-04-24 |  | 08.09.2023 | 2.413 | 2.0541 |  |  |  |  | 0.35886
11.6 | Replacement of 48 Volt, 1000 AH tubular battery set with 48 Volt, 750AH Plante type battery set at KGSC, Stage-III | Scheme | MERC/CAPEX/2019-2020/01 | 2019-05-24 | Better Carrier Communication & to avoid unit trippings | 2019-05-24 |  | 2020-04-24 | 2020-07-24 |  | 2020-12-30 | 0.318 | 0.30942 |  |  |  |  | 0.008582
11.7 | Replacement of 220V-150AH Battery set with Ni-Cad type, along with standard accessories for UPS scheme at Stage-IV | Scheme | MERC/CAPEX/2019-2020/01 | 2019-05-24 | Major Outage and generation loss can be avoided due to failure of Battery Set. | 2019-05-24 |  | 2021-08-06 | 2020-06-24 |  | 2021-12-21 | 0.272 | 0.25759 |  |  |  |  | 0.014405
11.8 | Reliability enhancement of Gas Insulated Switchyard Stage-IV. | Scheme | MERC/CAPEX/2019-2020/01 | 2019-05-24 | Increase the life of the Gas Insulated Switchyard equipments and auxiliaries like Circuit Breaker, Disconnectors & Earth Switch etc. | 2019-05-24 |  | - | 2021-04-24 |  | - | 10.472 | 0 |  |  |  |  | 10.472
11.9 | Up-gradation of Vibration system at all units of Stage-IV:Stage-IV, KGSC, Pophali | Scheme | MERC/CAPEX/2019-2020/01 | 2019-05-24 | Existing system- electronic cards are obsolete | 2019-05-24 |  | 2023-02-09 | 2020-06-24 |  | 2024-01-13 | 1.443 | 1.5041 |  |  |  |  | -0.061059
11.10 | Replacement of station battery set of 220V, 2000Ah capacity at Stage-IV. | Scheme | MERC/CAPEX/2019-2020/01 | 2019-05-24 | Not replaced from installation.Battery life cycle improved | 2019-05-24 |  | 2020-06-27 | 2020-05-24 |  | 2021-04-23 | 2.385 | 2.3649 |  |  |  |  | 0.020115
11.11 | Renovations and modernization of 1500kg capacity passenger cum goods lifts (2 Nos) for KGSC, Stage-IV | Scheme | MERC/CAPEX/2019-2020/01 | 2019-05-24 | Speedy & Safety Movement | 2019-05-24 |  | 2023-03-07 | 2020-09-24 |  | 2023-11-08 | 0.968 | 0.85208 |  |  |  |  | 0.11592
11.12 | Replacement of existing 3x7.5 TR Air conditioning package units at Stage-I&II control room by new 3x11 TR Air conditioning package units | Scheme | MERC/CAPEX/2019-2020/01 | 2019-05-24 | Better control of temperature, humidity in control-room. | 2019-05-24 |  | 2020-04-10 | 2020-09-24 |  | 2021-01-17 | 0.345 | 0.16909 |  |  |  |  | 0.17591
0 | IDC | IDC | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0 | 2019-05-24 |  | - | - |  | - | 0.351 | 0 |  |  |  |  | 0.351
12 | Upgradation of Governing System at Stage-I, KDPH& Stage-III at KGSC, Pophali | DPR | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 0 | 2019-05-10 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
12.1 | Up gradation of DIGIPID1500 governing system with new governor (TSLG) for all units of stage-I | Scheme | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | Increased reliability of system | 2019-05-10 |  | 2023-03-28 | 2021-04-10 |  | - | 6.0888 | 0 |  |  |  |  | 6.0888
12.2 | Up-gradation of governing system at Koyna Dam Power House (KDPH) Koynanagar | Scheme | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | CEA mandatory features such as FGMO and RGMO will be available, which are not possible in old system. This will helps to maintain the grid stability. | 2019-05-10 |  | 2023-02-17 | 2020-10-10 |  | - | 2.924 | 0 |  |  |  |  | 2.924
12.3 | Up-gradation of the Governing system at Stage-III & Other Charges (P&F, Insurance etc) | Scheme | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | The Response and Characteristics of this Digital Governing System will be Very Fast and Accurate. | 2019-05-10 |  | 2023-02-17 | 2021-04-10 |  | - | 9.5523 | 0 |  |  |  |  | 9.5523
0 | IDC | IDC | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 0 | 2019-05-10 |  | - | - |  | - | 0.6 | 0 |  |  |  |  | 0.6
13 | Refurbishment of 24 KV Generator Circuit Breakers (ABB Make) for four units at stage-IV, KGSC, Pophali | DPR | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 0 | 2019-07-18 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
13.1 | Supply spares for 24KV Generator Circuit Breaker System refurbishment (For 4 Units) | Scheme | MERC/CAPEX/2019-2020/388 | 2019-07-18 | It will increase the life of 24 KV LT synchronous Generator | 2019-07-18 |  | 2020-09-20 | 2021-03-18 |  | 2022-09-02 | 6.5702 | 6.5421 |  |  |  |  | 0.0281
13.2 | Supervision charges for 24 KV Generator Circuit Breaker System Unit. Preparation charges, Travel & transportation charges, local conveyance. Lumpsum rental charges of necessary tools & tackles required during O/H work charges | Scheme | MERC/CAPEX/2019-2020/388 | 2019-07-18 | It will increase the life of 24 KV LT synchronous Generator | 2019-07-18 |  | 2020-09-20 | 2021-03-18 |  | 2022-09-02 | 3.8704 | 3.8216 |  |  |  |  | 0.0488
0 | IDC | IDC | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 0 | 2019-07-18 |  | - | - |  | - | 0.132 | 0 |  |  |  |  | 0.132
15 | Up-gradation of Excitation system at Stage-I&II, PLC & SCADA system at Stage-II and DG Set at Stage-IV at KGSC, Pophali | DPR | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 0 | 2019-09-27 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
15.1 | Up gradation of Stage-I&II(4x70MW+4x80 MW) Static Semipol Excitation System with Latest Advanced Excitation System | Scheme | MERC/CAPEX/2019-2020/800 | 2019-09-27 | Improved reliability. | 2019-09-27 |  | 2022-04-25 | 2022-04-27 |  | - | 9.863 | 4.163 |  |  |  |  | 5.7
15.2 | Up gradation of existing unit PLC and SCADA automation of 4x80 MW Koyna stage-II units | Scheme | MERC/CAPEX/2019-2020/800 | 2019-09-27 | Improved reliability. | 2019-09-27 |  | 2022-04-30 | 2021-05-27 |  | - | 4.232 | 3.4 |  |  |  |  | 0.832
15.3 | Up gradation of one 1500 KVA DG set, at KGSC, Stage-IV | Scheme | MERC/CAPEX/2019-2020/800 | 2019-09-27 | Improved reliability. | 2019-09-27 |  | 2023-05-22 | 2020-12-27 |  | - | 1.6 | 0 |  |  |  |  | 1.6
0 | IDC | IDC | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 0 | 2019-09-27 |  | - | - |  | - | 1.103 | 0 |  |  |  |  | 1.103
17 | Repair works in Emergency Valve Tunnel (EVT) and surge well at Stage I/II, KGSC, Pophali | DPR | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 0 | 2020-06-19 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
17.1 | Sealing and stabilization of EVT Tunnel left side wall and carven portion of EVT and Ventilation Tunnel. | Scheme | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | Avoid huge loss of power generations due to risk of major rock fall | 2020-06-19 |  | - | 2021-03-19 |  | - | 8.307 | 1.5431 |  |  |  |  | 6.7638
17.2 | Structural Strengthening and Sealing Cracks and Cavities in Surge Shaft RCC Staining Wall from inside | Scheme | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | Avoid huge loss of power generations due to risk of major rock fall | 2020-06-19 |  | - | 2021-03-19 |  | - | 18.6602 | 0.3875 |  |  |  |  | 18.2727
0 | IDC | IDC | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 0 | 2020-06-19 |  | - | - |  | - | 1.07 | 0 |  |  |  |  | 1.07
HO DPR-8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | DPR | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 2017-11-13 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
HO DPR-8.1 | Advance Multipurpose Fire Tender | Scheme | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 2017-11-13 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
HO DPR-8.2 | Normal Multipurpose Fire Tender | Scheme | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 2017-11-13 |  | - | - |  | - | 1.25 | 0 |  |  |  |  | 1.25
0 | IDC | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 2017-11-13 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
18 | Refurbishment of cooling and drainage water system along with replacement of 5 no's of cooling water pumps by new stage -IV KGSC Pophali | DPR | MERC/CAPEX/2023-2024/MSPGCL/0201 | 2024-03-21 | 0 | 2024-03-21 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
0 | Refurbishment of cooling and drainage water system along with replacement of 5 no's of cooling water pumps by new stage -IV KGSC Pophali | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0201 | 2024-03-21 | Improving efficiency, reliability & adequate capacity of cooling water. Improve the availability of 4 X 250 MW generating sets | 2024-03-21 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
0 | IDC | IDC | MERC/CAPEX/2023-2024/MSPGCL/0201 | 2024-03-21 | 0 | 2024-03-21 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
0 | 0 | 0 | 0 | - | 0 | - |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
Formulas:
Project Start Date = [MERC Approval Date]
Note on G5: MERC Approval date
Note on H5: 7 months after MERC approval date. i.e. scheduled PO placed date as per implementation plan
Note on I5: Actual PO placed date
Note on J5: Work completion date as per implementation plan from MERC approval date
Note on K5: Date as per implementation plan after actual PO placed
Note on L5: Actual capitalization date taken from account section

## F4.2 KGSC
|  |  | MSPGCL: KGSC, Pophali | [52 empty] | DPR | Not Initiated
|  |  | MTR Petition Formats - Generation | [52 empty] | Scheme | WIP
| Project Details |  | Form 4.2: Capitalisation Plan | [18 empty] | (Rs. Crore) | [24 empty] | (Rs. Crore) | [8 empty] | IDC | Partially Capitalised
Sr. No. | Project Code | DPR | MERC Approval No. | Date of Submission | MERC Approval Date | Cost as per DPR Crs. | MERC Approved Cost | Debt Equity Ratio | Grant Funding | Approved Start Date | Actual Start Date | Approved Date of Completion | Actual Date of Completion | Benefits in Quantified Terms | Capital Expenditure | [12 empty] | Physical Progress (%) | [11 empty] | Capitalisation | [12 empty] | Old Asset retired against capitalised item (in Rs. Cr) | Remarks | Current Status | Non-DPR | Capitalised
[15 empty] | Actual Capex till FY 2018-19 | Actual | Actual | Actual | Actual Capex till FY 2021-22 | Actual | Actual | Revised Projected | Projected | Projected | Projected | Projected | Projected | Actual Progress till FY 2018-19 | Actual | Actual | Actual | Actual | Actual | Revised Projected | Projected | Projected | Projected | Projected | Projected | Actual Capitalization till FY 2018-19 | Actual | Actual | Actual | Actual Capitalization till FY 2021-22 | Actual | Actual | Revised Projected | Projected | Projected | Projected | Projected | Projected |  |  |  |  | Cancelled
[16 empty] | FY 2019-20 | FY 2020-21 | FY 2021-22 |  | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY2025-26 | FY2026-27 | FY2027-28 | FY2028-29 | FY2029-30 |  | FY 2019-20 | FY 2020-21 | FY 2021-22 | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY2025-26 | FY2026-27 | FY2027-28 | FY2028-29 | FY2029-30 |  | FY 2019-20 | FY 2020-21 | FY 2021-22 |  | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY2025-26 | FY2026-27 | FY2027-28 | FY2028-29 | FY2029-30 |  |  |  |  | To be cancelled
[55 empty] | N.A. |  | N.A.
| A) DPR Schemes | [53 empty] | N.A. |  | To be confirmed
| (i) Submitted to MERC | [53 empty] | N.A.
1 | Various improvement schemes at Pophali Hydro Power Station | DPR | MERC/TECH 1/CAPEX/20142015/00086 | 2013-11-16 | 2014-04-10 | 11.9001 | 11.9001 |  |  | 2014-04-10 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
1.1 | ALSPA HMI Series 6 Centralog System | Scheme | MERC/TECH 1/CAPEX/20142015/00086 | 2013-11-16 | 2014-04-10 | 6.8555 | 6.8555 |  |  | 2014-04-10 | 2014-03-13 | 2015-03-15 | 2015-03-25 | Increase the unit availability due to improved reliability of the electronic equipments, resulting in the Grid stability | 7.8386 |  |  |  | 7.8386 | [8 empty] | 100% | [11 empty] | 7.8386 |  |  |  | 7.8386 | [9 empty] | Completed | Capitalised
1.2 | 1 X 525 Tr chiller unit | Scheme | MERC/TECH 1/CAPEX/20142015/00086 | 2013-11-16 | 2014-04-10 | 1.23 | 1.23 |  |  | 2014-04-10 | 2015-04-17 | 2015-05-15 | 2016-04-16 | Increase the life of the electronic equipments and auxiliaries | 1.15 |  |  |  | 1.15 | [8 empty] | 100% | [11 empty] | 1.15 |  |  |  | 1.15 | [9 empty] | Completed | Capitalised
1.3 | Micom P343 Numerical generator protection relay with 24 DI & 24 DO with CLIO input. (5 Nos) | Scheme | MERC/TECH 1/CAPEX/20142015/00086 | 2013-11-16 | 2014-04-10 | 1.4675 | 1.4675 |  |  | 2014-04-10 | 2016-04-27 | Mar-15 | 2017-05-17 | More reliable and faster protection system for Generator and Transformer. | 1.474 |  |  |  | 1.474 | [8 empty] | 100% | [11 empty] | 1.474 |  |  |  | 1.474 | [9 empty] | Completed | Capitalised
1.4 | Security Building at Stage-IV | Scheme | MERC/TECH 1/CAPEX/20142015/00086 | 2013-11-16 | 2014-04-10 | 0.16446 | 0.16446 |  |  | 2014-04-10 | 2011-04-25 |  | 2014-03-07 | Due to recent threats causes by the anti national activities and as per directives by the IB the security measures are being tightens. | 0.18377 |  |  |  | 0.18377 | [8 empty] | 100% | [11 empty] | 0.18377 |  |  |  | 0.18377 | [9 empty] | Completed | Capitalised
1.5 | Construction of recreation club building | Scheme | MERC/TECH 1/CAPEX/20142015/00086 | 2013-11-16 | 2014-04-10 | 1.8204 | 1.8204 |  |  | 2014-04-10 | 2011-01-05 |  | 24.09.2012 | Good recreation is apparently generates lively and healthy atmosphere for achieving harmony among the whole community. | 2.1946 |  |  |  | 2.1946 | [8 empty] | 100% | [11 empty] | 2.1946 |  |  |  | 2.1946 | [9 empty] | Completed | Capitalised
1.6 | Security Building for Stage-IV at EVT | Scheme | MERC/TECH 1/CAPEX/20142015/00086 | 2013-11-16 | 2014-04-10 | 0.22776 | 0.22776 |  |  | 2014-04-10 | 2014-11-14 | 2015-11-14 | 2016-04-16 | Due to recent threats causes by the anti national activities and as per directives by the IB the security measures are being tightens. | 0.25961 |  |  |  | 0.25961 | [8 empty] | 100% | [11 empty] | 0.25961 |  |  |  | 0.25961 | [9 empty] | Completed | Capitalised
| IDC | IDC | MERC/TECH 1/CAPEX/20142015/00086 | 2013-11-16 | 2014-04-10 | 0.1344 | 0.1344 |  |  | 2014-04-10 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | N.A.
3 | Various DPR Schemes for Civil Section, KGSC Pophali | DPR | MERC/CAPEX/20152016/00907 | 2015-11-03 | 2015-11-05 | 21.201 | 21.201 |  |  | 2015-11-05 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
3.1 | Providing Road Network at KGSC, Pophali | Scheme | MERC/CAPEX/20152016/00907 | 2015-11-03 | 2015-11-05 | 7.776 | 7.776 |  |  | 2015-11-05 | 2016-12-28 | 2017-05-01 | 2019-12-19 | Safety and smooth movement of vehicles and avoid accidents. | 5.2783 | 1.6457 |  |  | 6.924 |  | 0.09422 | [8 empty] | 100% | [9 empty] | 5.2783 | 1.6457 |  |  | 6.924 |  | 0.09422 | [7 empty] | Completed | Capitalised |  | 4370001055
3.2 | Modernisation & Refurbishing of Residential Complex | Scheme | MERC/CAPEX/20152016/00907 | 2015-11-03 | 2015-11-05 | 8.985 | 8.985 |  |  | 2015-11-05 | 2017-06-17 | 2017-05-01 | 2020-06-30 | Conveniency for day to day work in the room | 4.826 | 1.9106 | 1.4635 |  | 8.2 |  | 0.73647 | [9 empty] | 100% | [8 empty] | 4.826 | 1.9106 | 1.4635 |  | 8.2 |  | 0.73647 | [7 empty] | Completed | Capitalised |  | 4370001275
3.3 | Water Supply & Sanitory Works | Scheme | MERC/CAPEX/20152016/00907 | 2015-11-03 | 2015-11-05 | 4.44 | 4.44 |  |  | 2015-11-05 | 2017-06-17 | 2017-04-01 | 2018-02-05 | Clean and portable water to employees residence in colony & to Avoid leakages and save in water | 1.7997 | 0.23919 |  |  | 2.0389 |  | 3.863 | [9 empty] | 100% | [9 empty] | 0.23919 |  |  | 0.23919 |  | 3.863 | [7 empty] | Completed | Capitalised |  | 4370001100 | 35782963.85
4 | Various Performance Improvement related schemes at KGSC, Pophali | DPR | MERC/CAPEX/20162017/01018 | 2016-07-05 | 2016-11-17 | 12.9765 | 12.9765 |  |  | 2016-11-17 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
4.1 | Up gradation of 245 kV CTs at Stage-I&II SY | Scheme | MERC/CAPEX/20162017/01018 | 2016-07-05 | 2016-11-17 | 1.9624 | 1.9624 |  |  | 2016-11-17 | 2018-08-02 | 2018-04-17 | 2020-03-31 | Improved accuracy class of CTs i.e. from 0.5S class to 0.2S class, and to accurate measurement & preciseness in reading | 0 | 2.09 |  |  | 2.09 | [9 empty] | 100% | [10 empty] | 0 | 2.09 |  |  | 2.09 | [9 empty] | Completed | Capitalised |  | 4370001614
4.2 | Up gradation of 245 kV PTs at Stage-I&II SY | Scheme | MERC/CAPEX/20162017/01018 | 2016-07-05 | 2016-11-17 | 0.40509 | 0.40509 |  |  | 2016-11-17 | 2017-03-25 | 2017-10-17 | 2017-12-10 | Improved accuracy class of CTs i.e. from 0.5S class to 0.2S class, and to accurate measurement & preciseness in reading | 0.3417 |  |  |  | 0.3417 | [8 empty] | 100% | [11 empty] | 0.3417 |  |  |  | 0.3417 | [9 empty] | Completed | Capitalised |  | 4370000991
4.3 | Up gradation of CW system of Stage-I&II Units | Scheme | MERC/CAPEX/20162017/01018 | 2016-07-05 | 2016-11-17 | 1.7099 | 1.7099 |  |  | 2016-11-17 | 2017-09-04 | 2017-12-17 | 2019-05-04 | Aassured no any generation loss due the cooling water bus leakages and /or break down |  | 1.4731 |  |  | 1.4731 | [8 empty] | 100% | [11 empty] | 0 | 1.4731 |  |  | 1.4731 | [9 empty] | Completed | Capitalised |  | 4370001140
4.4 | Up gradation of Intercom Exchange System between Stage-I&II PH & Admin. Bldg & Staff Colony. | Scheme | MERC/CAPEX/20162017/01018 | 2016-07-05 | 2016-11-17 | 0.43826 | 0.43826 |  |  | 2016-11-17 | 2017-04-07 | 2017-11-17 | 2017-06-22 | Reliable, faster and improved communication system with better voice quality | 0.359 |  |  |  | 0.359 | [8 empty] | 100% | [11 empty] | 0.359 |  |  |  | 0.359 | [9 empty] | Completed | Capitalised |  | 4370001030
4.5 | Up gradation of 220 kV Breakers at KDPH SY | Scheme | MERC/CAPEX/20162017/01018 | 2016-07-05 | 2016-11-17 | 1.289 | 1.289 |  |  | 2016-11-17 | 2017-04-07 | 2017-11-17 | 2017-12-21 | Increase the unit availability due to improved reliability of SF6 Breakers | 0.979 |  |  |  | 0.979 | [8 empty] | 100% | [11 empty] | 0.979 |  |  |  | 0.979 | [9 empty] | Completed | Capitalised |  | 4370001031
4.6 | Procurement of Governing Oil Pumps for Stage-III Units. | Scheme | MERC/CAPEX/20162017/01018 | 2016-07-05 | 2016-11-17 | 1.2316 | 1.2316 |  |  | 2016-11-17 | 2016-08-26 | 2017-10-17 | 2021-07-08 | Avoided reduction in generation of Stage-III due to failure of G.O. Pump. As stage-III Units are operated on tailrace water of Stage-I&II and Stage-IV, the operation of these Units will not be affected | 0 | 0 | 0 | 0.70174 | 0.70174 | [11 empty] | 100% | [8 empty] | 0 | 0 | 0 | 0.70174 | 0.70174 | [9 empty] | Completed. | Capitalised |  | 4370001640
4.7 | Up gradation of TG Governing system of Stage-IV Units. | Scheme | MERC/CAPEX/20162017/01018 | 2016-07-05 | 2016-11-17 | 2.2152 | 2.2152 |  |  | 2016-11-17 | 2016-09-01 | 2018-10-17 |  | The problems due to obsolete governing system will be eliminated | 0 | 0 | 0 | 0 | 0 | 2.7472 | [11 empty] | 100% | [7 empty] | 0 | 0 | 0 | 0 | 0 | 2.7472 | [8 empty] | Completed. -PR 1100066699 created on 01.09.2016, approved on 30.11.2016 -Tender published in 25.05.2017, Vendor quoted 51% higher on 17.08.2017 -Price escaltion note put to HO on 03.10.2017 -1st P.O. No. 4370001746 created on dtd.04.12.2018 and send for approval -Query from CPA dtd.09.01.2019, compliance in Feb 2019 -Query from CPA dtd.25.03.2019, compliance on 24.04.2019 -Query from CPA dtd.06.05.2019, compliance on 13.05.2019 -Query from CPA dtd.03.05.2020, compliance on 08.07.2020 -Query from CPA dtd.20.08.2020, compliance with revised --Revised PO no-4370002555 dtd.23.10.2020 made by end Oct 2020 due revision in rates -Query from CPA dtd.03.11.2020, compliance on 03.11.2020 -PO aaproval received on dtd.27.01.2021, PO placed on agency on 11.02.2021 -Drawing approval received in Dec 2021 Work started as per LDK in June 2022 | Capitalised |  | 4370001746
4.8 | Up gradation of Numerical Protection system of Stage-IV Units. | Scheme | MERC/CAPEX/20162017/01018 | 2016-07-05 | 2016-11-17 | 2.8249 | 2.8249 |  |  | 2016-11-17 | 2017-10-05 | 2018-02-17 | 2021-03-04 | 100% of the machine stator winding, including the star point, is protected under all operating modes, even at machine standstill. The innovative filtering technique enables high sensitivity for both stator and rotor protection, which enables early detection of faults | 0 | 0 | 2.8674 |  | 2.8674 | [10 empty] | 100% | [9 empty] | 0 | 0 | 2.8674 |  | 2.8674 | [9 empty] | Completed. | Capitalised |  | 4370001170
| IDC | IDC | MERC/CAPEX/20162017/01018 | 2016-07-05 | 2016-11-17 | 0.9 | 0.9 |  |  | 2016-11-17 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | N.A.
7 | Replacement of Generator Stator of unit No. 11 (80 MW), Stage III, KGSC Pophali | DPR | MERC/CAPEX/20172018/04592 | 2017-08-29 | 2017-11-07 | 22.33 | 22.54 |  |  | 2017-11-07 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
7.1 | Replacement of Generator Stator of unit No. 11 (80 MW), Stage III, KGSC Pophali | Scheme | MERC/CAPEX/20172018/04592 | 2017-08-29 | 2017-11-07 | 22.33 | 22.54 |  |  | 2017-11-07 | 2023-07-10 | 2019-12-07 | 2024-04-23 | Avoid the Generation loss due to unavailability of units | 0 | 0 | 0 | 0 | 0 | 16.579 |  | 2.83 | [10 empty] | 100% | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.41 | [6 empty] | Completed -PR 1100081776 created on 12.01.2018, after number of compliance approved on 13.08.2019 -1st PO No-4385000126 send for approval on 18.03.2020, approval received on 07.12.2020. -Again proposal returened to CPA for review, query generated, compliance made on 16.01.2021. -Email for refloat of Tender from CPA on 24.02.2021, after all compliance refloated on 18.06.2021 -Revised PO 4385000514 placed on 10.11.2021, approval received on 16.12.2021 -Delivery period was 1 year - SLDC, denied outage due to high grid demand in year 2022 | Capitalised |  | 4385000514
8 | Procurement of new pelton wheel runners (2 Nos.) for Stage II at KGSC, Pophali | DPR | MERC/CAPEX/20172018/04421 | 2017-09-13 | 2017-10-24 | 12.9 | 13.07 |  |  | 2017-10-24 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
8.1 | Procurement of new pelton wheel runners (2 Nos.) for Stage II at KGSC, Pophali | Scheme | MERC/CAPEX/20172018/04421 | 2017-09-13 | 2017-10-24 | 12.9 | 13.07 |  |  | 2017-10-24 | 2018-01-16 | 2019-10-24 |  | Avoid the Generation loss due to unavailability of units | 0 |  |  |  | 0 |  |  | 5.19 | 5.19 | [10 empty] | 100% | 100% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | 10.38 | [5 empty] | Present Status: Material Awaited History: Tender published. -PR No-1100084118 created on 16.01.2018, approved on 22.06.2018 -Due to Covid pandemic situation delayed. -PO send for approval on 06.12.2021. -Bid validity not extended by bidder, hence refloated with changed QR -Tender published and extende 4 times. - PO No-4385000623 dtd.01.12.2022 is placed on M/s.Flovel Energy Pvt. Ltd on dt.03.03.2023. -The supply period is @ 16 Months. -Bidder requested for delivery extension. | WIP |  | PO not placed
11 | Implementation of 12 Nos. of various schemes at KGSC, Pophali. | DPR | MERC/CAPEX/2019-2020/01 | 2019-08-24 | 2019-05-24 | 26.891 | 26.891 |  |  | 2019-05-24 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
11.1 | Replacement of UGB (8 Nos), LGB (8 Nos) & Generator air coolers (8 Nos) for Stage-I | Scheme | MERC/CAPEX/2019-2020/01 | 2019-08-24 | 2019-05-24 | 1.344 | 1.344 |  |  | 2019-05-24 | 2022-01-19 | 2020-11-24 |  | Better performance of Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85 | [10 empty] | 100% | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85 | [6 empty] | Present Status: UGB, LGB coolers are received and Generator cooler is awaited History: -Due to Covid pandemic delyed -PR No-1100109096 created on 08.02.2020, approved on 14.01.2021 -Tender extended 3 times -PO No-4385000527 is placed on M/s. Laxmi Engineering Industries, Bhopal on dt.19.01.2022. -Supply delivery period is 6 months | WIP |  | 4385000527
11.2 | Retrofitting of Generator & Gen-Transformer relays by new numerical protection system at Koyna Dam Power House (KDPH) Koynanagar | Scheme | MERC/CAPEX/2019-2020/01 | 2019-08-24 | 2019-05-24 | 1.097 | 1.097 |  |  | 2019-05-24 | 2022-08-04 | 2021-02-24 |  | Online testing facility with PC for testing of relay without disturbing the Generator and Offline testing facility with PC for secondary injection test including trip status. | 0 | 0 | 0 | 0 | 0 | 0.82 |  | 0.26 | [9 empty] | 100% | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.08 | [6 empty] | Present Status: Completed History: PO placed on dtd.04.08.2022. -PR No-1100104562 created on 24.08.2019, approved on 29.01.2020. -Due to Covid pandemic situation work delayed -PO No-4385000593 send for approval on 08.07.2022, approved on 02.08.2022 | Capitalised |  | PO not placed
11.3 | Replacement of two 220V Battery chargers with 220V dual float cum boost (60A) battery Charger including DCDB at KDPH, Koynanagar | Scheme | MERC/CAPEX/2019-2020/01 | 2019-08-24 | 2019-05-24 | 0.202 | 0.202 |  |  | 2019-05-24 | 2020-05-02 | 2020-09-24 | 25.02.2021 | Increase the unit availability due to improved reliability of the 220 V D.C. Power Supply, resulting in the Grid stability. | 0 | 0 | 0.13782 |  | 0.13782 | [10 empty] | 100% | [9 empty] | 0 | 0 | 0.13782 |  | 0.13782 | [9 empty] | Completed | Capitalised |  | 4385000232
11.4 | Replacement of 220KV current transformer (54 Nos), Potential transformer (13 Nos),110KV Current Transformer (14 Nos)& Potential Transformer (4 Nos),Stage-III. | Scheme | MERC/CAPEX/2019-2020/01 | 2019-08-24 | 2019-05-24 | 5.281 | 5.281 |  |  | 2019-05-24 |  | 2020-08-24 |  | Accurate measurement & preciseness in reading | 0 |  |  |  | 0 | 0 | 0 | 0 | 5.28 | [10 empty] | 100% | 100% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 | [5 empty] | Present Status: Tender under deviation Bid scrutiny -The estimated amount of Rs.5.28 Cr. is required in FY 2025-26 History: Tender published. Poor Vendor response -Due to Covid pandemic situation work delayed --PR approved on 18.03.2021 -First Tenderization: Tender 3000018324 was published on 03.06.2021 and extended 5 times due to vendor request, even after prolonged publication, no any bidder submitted the bid. Tender is refloated with same specifications and Terms & Conditions with mail to prospective vendors for participation request. -Second tenderization: The New tender No. 3000031088 was published. Extended 2 times. It was found that tender was purchased by 4 bidders & submitted by two bidder. It was found that documents submitted by both the bidders against deviation raised by KGSC are not as per Q.R. Hence as per remarks of Tender committee tender is refloated after review. -Third tenderization: The tender No. 3000035712 was published. Extended 5 times. After opening of price bid, the L1 M/s. Punjab Machine Tools with 147.25 % higher than the estimate. Further, proposes to process the tender with revised estimate with due permission of C.A. After approval tenderization is in process. | WIP |  | PO not placed
11.5 | Replacement of Generator Air Cooler (32 Nos), St-III | Scheme | MERC/CAPEX/2019-2020/01 | 2019-08-24 | 2019-05-24 | 2.413 | 2.413 |  |  | 2019-05-24 | 2022-08-26 | 2020-04-24 | 08.09.2023 | Better performance of Units | 0 |  |  |  | 0 |  | 2.0541 | [11 empty] | 100% | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2.0541 | [7 empty] | Present Status: Completed History -Due to Covid pandemic situation work delayed -PR No-1100109088 send for approval on 23.04.2020 Query complied on 10.11.2020, PR approved on 11.01.2021 -Tender extended 3-4 times, deviation in bid 3 times -PO No-4385000574 send for aaproval on 07.04.2022, approved on 10.08.2022. | Capitalised |  | 4385000574
11.6 | Replacement of 48 Volt, 1000 AH tubular battery set with 48 Volt, 750AH Plante type battery set at KGSC, Stage-III | Scheme | MERC/CAPEX/2019-2020/01 | 2019-08-24 | 2019-05-24 | 0.318 | 0.318 |  |  | 2019-05-24 | 2020-04-24 | 2020-07-24 | 2020-12-30 | Better Carrier Communication & to avoid unit trippings | 0 |  | 0.30942 |  | 0.30942 | [10 empty] | 100% | [9 empty] | 0 | 0 | 0.30942 |  | 0.30942 | [9 empty] | Completed | Capitalised |  | 4385000230
11.7 | Replacement of 220V-150AH Battery set with Ni-Cad type, along with standard accessories for UPS scheme at Stage-IV | Scheme | MERC/CAPEX/2019-2020/01 | 2019-08-24 | 2019-05-24 | 0.272 | 0.272 |  |  | 2019-05-24 | 2021-08-06 | 2020-06-24 | 2021-12-21 | Major Outage and generation loss can be avoided due to failure of Battery Set. | 0 |  |  | 0.25759 | 0.25759 | [11 empty] | 100% | [8 empty] | 0 | 0 | 0 | 0.25759 | 0.25759 | [9 empty] | Completed | Capitalised |  | 4385000482
11.8 | Reliability enhancement of Gas Insulated Switchyard Stage-IV. | Scheme | MERC/CAPEX/2019-2020/01 | 2019-08-24 | 2019-05-24 | 10.472 | 10.472 |  |  | 2019-05-24 |  | 2021-04-24 |  | Increase the life of the Gas Insulated Switchyard equipments and auxiliaries like Circuit Breaker, Disconnectors & Earth Switch etc. | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [9 empty] | DPR proposed for cancellation. Note send to HO on dt.21.12.2021. New DPR proposal preparation is in process. | Not Initiated |  | PO not placed
11.9 | Up-gradation of Vibration system at all units of Stage-IV:Stage-IV, KGSC, Pophali | Scheme | MERC/CAPEX/2019-2020/01 | 2019-08-24 | 2019-05-24 | 1.443 | 1.443 |  |  | 2019-05-24 | 2023-02-09 | 2020-06-24 | 2024-01-13 | Existing system- electronic cards are obsolete | 0 |  |  |  | 0 | 1.01 | 0.49406 | [10 empty] | 100% | [7 empty] | 0 | 0 | 0 | 0 | 0 |  | 1.5041 | [7 empty] | Completed. -PR 1100109691 send for approval on 19.03.2020 -Query on 17.07.2020, complied on 21.07.2020, PR approved -Tender refloated due to single participation, again extended 4 times -PO No-4385000558 send for approval on 11.03.2022 -Due to budget issue new PO 4385000572 send to HO, approved on 23.04.2022. | Capitalised |  | 4385000572
11.10 | Replacement of station battery set of 220V, 2000Ah capacity at Stage-IV. | Scheme | MERC/CAPEX/2019-2020/01 | 2019-08-24 | 2019-05-24 | 2.385 | 2.385 |  |  | 2019-05-24 | 2020-06-27 | 2020-05-24 | 2021-04-23 | Not replaced from installation.Battery life cycle improved | 0 |  |  | 2.3649 | 2.3649 | [11 empty] | 100% | [8 empty] | 0 | 0 | 0 | 2.3649 | 2.3649 | [9 empty] | Completed | Capitalised |  | 4385000243
11.11 | Renovations and modernization of 1500kg capacity passenger cum goods lifts (2 Nos) for KGSC, Stage-IV | Scheme | MERC/CAPEX/2019-2020/01 | 2019-08-24 | 2019-05-24 | 0.968 | 0.968 |  |  | 2019-05-24 | 2023-03-07 | 2020-09-24 | 2023-11-08 | Speedy & Safety Movement | 0 |  |  |  | 0 |  | 0.85208 | [10 empty] | 100% | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0.85208 | [7 empty] | Completed Histrory: -PR No-1100116308 created on 09.11.2020 -Due to Covid pandemic situation work delayed -PR send for approval on 12.03.2021, approved on 23.04.2021 -Tender published, extended 3 times -Refloated due to single paticipated, again extended 2 times -Again refloated due to single paticipated, PO No-4385000592 sent to HO for approval. -PO No- 4385000592 is dispatched on 24.11.22 to M/s. Maknet Ind. Pvt. Ltd. | Capitalised |  | PO not placed
11.12 | Replacement of existing 3x7.5 TR Air conditioning package units at Stage-I&II control room by new 3x11 TR Air conditioning package units | Scheme | MERC/CAPEX/2019-2020/01 | 2019-08-24 | 2019-05-24 | 0.345 | 0.345 |  |  | 2019-05-24 | 2020-04-10 | 2020-09-24 | 2021-01-17 | Better control of temperature, humidity in control-room. | 0 |  | 0.16909 |  | 0.16909 | [10 empty] | 100% | [9 empty] | 0 | 0 | 0.16909 |  | 0.16909 | [9 empty] | Completed | Capitalised |  | 4385000224
| IDC | IDC | MERC/CAPEX/2019-2020/01 | 2019-08-24 | 2019-05-24 | 0.351 | 0.351 |  |  | 2019-05-24 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | N.A.
12 | Upgradation of Governing System at Stage-I, KDPH& Stage-III at KGSC, Pophali | DPR | MERC/CAPEX/2019-2020/0134 | 2018-11-13 | 2019-05-10 | 19.1651 | 19.1651 |  |  | 2019-05-10 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
12.1 | Up gradation of DIGIPID1500 governing system with new governor (TSLG) for all units of stage-I | Scheme | MERC/CAPEX/2019-2020/0134 | 2018-11-13 | 2019-05-10 | 6.0888 | 6.0888 |  |  | 2019-05-10 | 2023-03-28 | 2021-04-10 |  | Increased reliability of system | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.89 | [11 empty] | 100% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.89 | [6 empty] | Present Status: Completed -Due to Covid pandemic situation work delayed -PR No-1100126032 created on 16.09.2021 -Tender Published on 08.04.2022, extended 3 times -Again refloted due to poor response -PO No- 4385000650 is dispatched on dt.28.03.23 to M/s.GE Power India Ltd. | Capitalised
12.2 | Up-gradation of governing system at Koyna Dam Power House (KDPH) Koynanagar | Scheme | MERC/CAPEX/2019-2020/0134 | 2018-11-13 | 2019-05-10 | 2.924 | 2.924 |  |  | 2019-05-10 | 2023-02-17 | 2020-10-10 |  | CEA mandatory features such as FGMO and RGMO will be available, which are not possible in old system. This will helps to maintain the grid stability. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.41 | [11 empty] | 100% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.41 | [6 empty] | Present Status: Material received.Expected date of completion of work by Dec-2024 -PR No-1100095348 send for aaproval on 18.09.2019 -Query on 02.01.2019, complied one by one up to 20.07.2019 -Query on 13.11.2019, compliance not done & proposed for cancellation of DPR scheme. -As per discussion with C.A. case revoked -PR send for approval on 09.11.2020, query on 18.11.2020, complied on 20.11.2020 -Final query complied on 08.01.2021, PR approved on 10.02.2021 -Tender published, extended 5-6 times -After receiving approval for limitation of liability, tender republished, again extended 5 times, poor response of vendor. -PO No-4385000633 dispatched on 17.02.23 to M/s. Andriz Hydro Pvt. Ltd. | WIP
12.3 | Up-gradation of the Governing system at Stage-III & Other Charges (P&F, Insurance etc) | Scheme | MERC/CAPEX/2019-2020/0134 | 2018-11-13 | 2019-05-10 | 9.5523 | 9.5523 |  |  | 2019-05-10 | 2023-02-17 | 2021-04-10 |  | The Response and Characteristics of this Digital Governing System will be Very Fast and Accurate. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.6 | [11 empty] | 100% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.6 | [6 empty] | Present Status: Material received. Probable completion of scheme by March-2025. -PR No-1100096525 send for approval on 18.09.2019 -EST, HO represntative visted at site, corresponding compliance made on 01.01.2021 -Query on 26.02.2021, complied on 09.03.2021 -PR approved on 23.04.2021 -Email regarding Change in Standard QR send to HO on 14.07.2021, after all queries & compliance change in QR approved on 15.03.2022 -Tender published, extended 5 times, present submission date 26.09.2022 - PO No-4385000625 is dispatched on 17.02.23 to M/s. Andriz Hydro PVT. Ltd. | WIP
| IDC | IDC | MERC/CAPEX/2019-2020/0134 | 2018-11-13 | 2019-05-10 | 0.6 | 0.6 |  |  | 2019-05-10 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | N.A.
13 | Refurbishment of 24 KV Generator Circuit Breakers (ABB Make) for four units at stage-IV, KGSC, Pophali | DPR | MERC/CAPEX/2019-2020/388 | 2019-01-23 | 2019-07-18 | 10.5726 | 10.5726 |  |  | 2019-07-18 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
13.1 | Supply spares for 24KV Generator Circuit Breaker System refurbishment (For 4 Units) | Scheme | MERC/CAPEX/2019-2020/388 | 2019-01-23 | 2019-07-18 | 6.5702 | 6.5702 |  |  | 2019-07-18 | 2020-09-20 | 2021-03-18 | 2022-09-02 | It will increase the life of 24 KV LT synchronous Generator | 0 | 0 | 3.2721 | 0 | 3.2721 | 3.27 | [9 empty] | 50% |  | 100% | [7 empty] | 0 | 0 | 3.2721 | 0 | 3.2721 | 3.27 | [8 empty] | Completed For this DPR proposal two PO created. PO No-438500072 for 2 units and PO no-4385000442 is for remaining 2 units. Work is complited on dtd. 03.09.2022 Will be capitalized in FY 2022-23 | Capitalised |  | 4385000072
13.2 | Supervision charges for 24 KV Generator Circuit Breaker System Unit. Preparation charges, Travel & transportation charges, local conveyance. Lumpsum rental charges of necessary tools & tackles required during O/H work charges | Scheme | MERC/CAPEX/2019-2020/388 | 2019-01-23 | 2019-07-18 | 3.8704 | 3.8704 |  |  | 2019-07-18 | 2020-09-20 | 2021-03-18 | 2022-09-02 | It will increase the life of 24 KV LT synchronous Generator | 0 | 0 | 1.9116 | 0 | 1.9116 | 1.91 | [9 empty] | 50% |  | 100% | [7 empty] | 0 | 0 | 1.9116 | 0 | 1.9116 | 1.91 | [8 empty] | Completed For this DPR proposal two PO created. PO No-438500072 for 2 units and PO no-4385000442 is for remaining 2 units. Work is complited on dtd. 03.09.2022 Will be capitalized in FY 2022-23 | Capitalised |  | 4385000442
| IDC | IDC | MERC/CAPEX/2019-2020/388 | 2019-01-23 | 2019-07-18 | 0.132 | 0.132 |  |  | 2019-07-18 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | N.A.
15 | Up-gradation of Excitation system at Stage-I&II, PLC & SCADA system at Stage-II and DG Set at Stage-IV at KGSC, Pophali | DPR | MERC/CAPEX/2019-2020/800 | 2019-03-07 | 2019-09-27 | 9.863 | 9.863 |  |  | 2019-09-27 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
15.1 | Up gradation of Stage-I&II(4x70MW+4x80 MW) Static Semipol Excitation System with Latest Advanced Excitation System | Scheme | MERC/CAPEX/2019-2020/800 | 2019-03-07 | 2019-09-27 | 9.863 | 9.863 |  |  | 2019-09-27 | 2022-04-25 | 2022-04-27 |  | Improved reliability. | 0 | 0 | 0 | 0 | 0 | 0 | 4.163 | 1.6 | [10 empty] | 50% | 50% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.76 | [6 empty] | Present Status: DPR was for 8 units (4 units of Stage I & 4 units of Stage II). The 7 Units work is completed. Remaining one unit work will be completed by Oct.-2024. History: -PR No-1100104683 send for approval -Query on 05.12.2019, complied on 03.01.2020, approved on 21.12.2020 -Tender published, extended 2 times -PO No-4385000564 send for approval on 22.03.2022 -due to budget issue new PO created 4385000575 , approved on 23.04.2022. - PO No-4385000575 is dispatched on dt.25.04.2022 to M/s. Andriz Hydro PVT. LTD. | WIP |  | 4385000575
15.2 | Up gradation of existing unit PLC and SCADA automation of 4x80 MW Koyna stage-II units | Scheme | MERC/CAPEX/2019-2020/800 | 2019-03-07 | 2019-09-27 | 4.232 | 4.232 |  |  | 2019-09-27 | 2022-04-30 | 2021-05-27 |  | Improved reliability. | 0 | 0 | 0 | 0 | 0 | 0 | 3.4 | 0.9 | [10 empty] | 50% | 50% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.3 | [6 empty] | Present Status: TDPR was for 4 units of Stage II. The 3 Units work is completed. Remaining one unit work will be completed by Oct.-2024. History: -PR No-1100104744 send for approval on 28.11.2019 -Query on 05.12.2019, complied on 17.01.2020, -Query on 15.05.2020, complied on 14.05.2020 -Email from CPA to process in open tender, send to user for review -Letter to to process through OEM send to HO on 18.11.2021, approved on 26.11.2021 -PO No-4385000562 send for approval on 22.03.2022 -due to budget issue new PO 4385000573 created, approved on 29.04.2022. -PO No- 4385000573 is dispatched on dt.30.04.2022 to M/s. Andriz Hydro PVT. Ltd. | WIP |  | 4385000573
15.3 | Up gradation of one 1500 KVA DG set, at KGSC, Stage-IV | Scheme | MERC/CAPEX/2019-2020/800 | 2019-03-07 | 2019-09-27 | 1.6 | 1.6 |  |  | 2019-09-27 | 2023-05-22 | 2020-12-27 |  | Improved reliability. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.81 | [10 empty] | 100% | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.81 | [6 empty] | Present Status: Material received. Expected date of completion Dec-2024. History: -Due to Covid pandemic situation work delayed -PR No-1100124695 send to HO on 28.09.2021, approved on 24.01.2022 -Tender published, extended two times -Due to single participation, refloated, extended 3 times, now under TC bid scruitiny. -PO No-4385000652 is dispatched on 22.05.2023 to M/s. Vitrus Techno | WIP
| IDC | IDC | MERC/CAPEX/2019-2020/800 | 2019-03-07 | 2019-09-27 | 1.103 | 1.103 |  |  | 2019-09-27 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | N.A.
17 | Repair works in Emergency Valve Tunnel (EVT) and surge well at Stage I/II, KGSC, Pophali | DPR | MERC/CAPEX/2020-2021/WFH/18 | 2020-02-27 | 2020-06-19 | 28.0371 | 28.0371 |  |  | 2020-06-19 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
17.1 | Sealing and stabilization of EVT Tunnel left side wall and carven portion of EVT and Ventilation Tunnel. | Scheme | MERC/CAPEX/2020-2021/WFH/18 | 2020-02-27 | 2020-06-19 | 8.307 | 8.307 |  |  | 2020-06-19 |  | 2021-03-19 |  | Avoid huge loss of power generations due to risk of major rock fall | 1.5431 | 0 | 0 | 0 | 1.5431 |  |  | 5.61 | 12.42 | [8 empty] | 100% |  |  | 100% |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 5.61 | 12.42 | [5 empty] | Present status: The work execution is on depository basis to WRD. The PO placed by WRD. Work in progress. Probable date of completion- July 2025 -25% Advance payment done. Proposal processed at CE (Civil-III). | WIP |  | Advanced payment given plz check |  | 0.51437 | 2018-12-11 | 1.0287 | 2018-12-21 | 0.51437 | 2019-07-06
17.2 | Structural Strengthening and Sealing Cracks and Cavities in Surge Shaft RCC Staining Wall from inside | Scheme | MERC/CAPEX/2020-2021/WFH/18 | 2020-02-27 | 2020-06-19 | 18.6602 | 18.6602 |  |  | 2020-06-19 |  | 2021-03-19 |  | Avoid huge loss of power generations due to risk of major rock fall | 0.3875 | 0 | 0 | 0 | 0.3875 | [12 empty] | 100% |  |  | 100% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [9 empty] | Present status: The work execution is on depository basis to WRD. The PO placed by WRD. Work in progress. Probable date of completion- July 2025 -Advance payment done Proposal processed at CE (Civil-III) | WIP |  |  |  | 0.3875 | 2019-01-08
| IDC | IDC | MERC/CAPEX/2020-2021/WFH/18 | 2020-02-27 | 2020-06-19 | 1.07 | 1.07 |  |  | 2020-06-19 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | N.A.
HO DPR-8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | DPR | MERC/CAPEX/20172018/4653 | 2017-04-19 | 2017-11-13 | 1.25 | 1.25 |  |  | 2017-11-13 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
HO DPR-8.1 | Advance Multipurpose Fire Tender | Scheme | MERC/CAPEX/20172018/4653 | 2017-04-19 | 2017-11-13 | 0 | 0 |  |  | 2017-11-13 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [9 empty] | Not pertains to Pophali | N.A. |  | 4370002758
HO DPR-8.2 | Normal Multipurpose Fire Tender | Scheme | MERC/CAPEX/20172018/4653 | 2017-04-19 | 2017-11-13 | 1.25 | 1.25 |  |  | 2017-11-13 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [9 empty] | Not pertains to Pophali | N.A.
| IDC | IDC | MERC/CAPEX/20172018/4653 | 2017-04-19 | 2017-11-13 | 0 | 0 |  |  | 2017-11-13 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | N.A.
18 | Refurbishment of cooling and drainage water system along with replacement of 5 no's of cooling water pumps by new stage -IV KGSC Pophali | DPR | MERC/CAPEX/2023-2024/MSPGCL/0201 | 2023-08-29 | 2024-03-21 | 28.47 | [12 empty] | 0 | [24 empty] | 0
| Refurbishment of cooling and drainage water system along with replacement of 5 no's of cooling water pumps by new stage -IV KGSC Pophali | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0201 | 2023-08-29 | 2024-03-21 | 27.83 | [7 empty] | Improving efficiency, reliability & adequate capacity of cooling water. Improve the availability of 4 X 250 MW generating sets |  |  |  |  | 0 |  |  |  | 27.83 | [11 empty] | 100% | [8 empty] | 0 |  |  |  | 27.83 | [5 empty] | Material awaited. The PO No. 4385000760/ 2919 dtd.21/08/2024 is placed to M/s.Ajay Industries, Chiplun. | WIP
| IDC | IDC | MERC/CAPEX/2023-2024/MSPGCL/0201 | 2023-08-29 | 2024-03-21 | 0.64 | [12 empty] | 0 | [24 empty] | 0
[19 empty] | 0 | [24 empty] | 0
| (ii) Yet to be submitted to MERC | [17 empty] | 0 | [24 empty] | 0
19 | Refurbishment of GIS T155 as per M4 Schedule at KGSC Stage-IV, Pophali | DPR | Yet to be approved | Yet Not submitted |  | 49.08 | [12 empty] | 0 | [24 empty] | 0 | [10 empty] | Not Initiated | [11 empty] | Not Initiated
19.1 | Refurbishment of GIS T155 as per M4 Schedule at KGSC Stage-IV, Pophali | Scheme |  |  |  | 49.08 | [7 empty] | By refurbishing GIS units as per the M4 Schedule, critical components such as circuit breakers, disconnectors, and earth switches undergo necessary maintenance, repairs, and replacements, thereby extending their operational lifespan and optimizing performance. Refurbished GIS units operate more efficiently and reliably, contributing to overall system performance and stability. This optimization translates into improved power generation output, grid stability, and operational efficiency |  |  |  |  | 0 |  |  |  |  | 49.08 |  |  |  |  | 49.08 | [6 empty] | 100% | [7 empty] | 0 |  |  |  |  | 49.08 |  |  |  |  | BR approval received. BR: MSPGCL /BM-226/Item 226.9 dtd. 23.09.2024 Resolution No.:2024/3927. MERC approval awaited. Tenderization is initiated. | [7 empty] | 49.08 |  |  |  | Present Status: DPR preparation at KGSC level is in progress. DPR cost is Rs.49.08 Cr. The estmate amount is required in FY 2026-27
20 | Various Civil work as per IB recommendation at KGSC, Pophali | DPR | Yet to be approved | Submitted to HO |  | 14.98 | [12 empty] | 0 | [24 empty] | 0 | [10 empty] | Not Initiated | [11 empty] | Not Initiated
20.1 | Various Civil work as per IB recommendation at KGSC, Pophali | Scheme |  |  |  | 14.98 | [7 empty] | The important IB recommendations in view of security of plant shall be implemented. Incidence of thefts shall be minimized almost to NIL. Facilitate to restrict any illicit entry in plant . It shall act as a preventive measure to control any naxalite/terrorist attack on plant |  |  |  |  | 0 |  |  |  | 6 | 2.45 |  |  |  | 4.49 | [7 empty] | 100% | [7 empty] | 0 |  |  |  | 10.5 | [5 empty] | DPR sent to HO for aaproval of Competent authority. DPR cost is Rs.14.98 Cr. The balance amount of Rs.4.49 Cr. is required in FY 2025-26. | [5 empty] | 10.49 | 4.49 |  |  |  |  | DPR sent to HO for aaproval of Competent authority. DPR cost is Rs.14.98 Cr. The balance amount of Rs.4.49 Cr. is required in FY 2025-26.
20.2 | construction of chainlink caging along entrance of St-I&II, St-III & St-IV | Scheme |  |  |  | 6.5349 | [12 empty] | 0 |  |  |  | 4.5 | 2.03 | [19 empty] | 0
21 | Stabilization and Mitigation of Landslide Prone Areas at KGSC, Mahagenco, Pophali | DPR | Yet to be approved | Submitted to HO |  | 29.9 | [12 empty] | 0 | [24 empty] | 0 | [13 empty] | Not Initiated
21.1 | Stabilization and Mitigation of Landslide Prone Areas | Scheme | [11 empty] | Protection of life and property. Reduced risk of future landslides Preservation of powerhouse allied structures Reduced costs of disaster response Increased communication resilience |  |  |  |  | 0 |  |  |  | 17 | 5.6 | [11 empty] | 100% |  |  |  | 100% |  |  |  | 1 |  |  |  | 17 | 5.6 |  |  |  |  | Submitted to HO(CE Civil 3) on Dt.12.06.2024 for approval |  |  | DPR sent to HO for aaproval of Competent authority on dtd.12.06.2024
21.2 | Construction of retaining wall | Scheme | [16 empty] | 0 |  |  |  | 5 | 1.9 | [11 empty] | 100% | [7 empty] | 0 |  |  |  | 5 | 1.9
21.3 | Dredging river and nallah | Scheme | [16 empty] | 0 |  |  |  | 0.4 | [12 empty] | 100% | [7 empty] | 0 |  |  |  | 0.4
22 | Various Performance Improvement related schemes for FY 2026-27 at KGSC, Pophali | DPR | Yet to be approved | Yet Not submitted |  | 29 | [12 empty] | 0 | [24 empty] | 0
22.1 | Supply of New Runner for Francis Turbine 80 MW at KGSC Stage-III | Scheme |  |  |  | 11 | [7 empty] | Avoid the generation loss due to unavailability of runner |  |  |  |  | 0 |  |  |  |  | 11 |  |  |  |  | 11 | [6 empty] | 100% | [7 empty] | 0 |  |  |  |  | 11 | [12 empty] | 11
22.2 | Supply of 2 Nos. injector along with injector shaft for Stage-I Units (70 MW) at Stage I & II KGSC, Pophali . | Scheme |  |  |  | 4 | [7 empty] | For smooth operation of injector for smooth load variation. Problem of stuck up of Injector avoid the hampering of generation. |  |  |  |  | 0 |  |  |  |  | 4 |  |  |  |  | 4 | [6 empty] | 100% | [7 empty] | 0 |  |  |  |  | 4 | [12 empty] | 4
22.3 | Supply of 1 No. injector for Stage-II Units (80 MW) at Stage I & II KGSC, Pophali . | Scheme |  |  |  | 2 | [7 empty] | For smooth operation of injector for smooth load variation. Problem of stuck up of Injector avoid the hampering of generation. |  |  |  |  | 0 |  |  |  |  | 2 |  |  |  |  | 2 | [6 empty] | 100% | [7 empty] | 0 |  |  |  |  | 2 | [12 empty] | 2
22.4 | Upgradation of AC Chiiler system at Stage I & II | Scheme |  |  |  | 7 | [7 empty] | maintaining healthiness of all electrical and electronic cards, advance systems and also for maintaining healthiness of working staff in power house who works round the clock |  |  |  |  | 0 |  |  |  |  | 7 |  |  |  |  | 7 | [6 empty] | 100% | [7 empty] | 0 |  |  |  |  | 7 | [12 empty] | 7
22.5 | Design, manufacturing, supply, erection, testing and commissioning of LGB and UGB cooler modifications at KGSC Stage I&II | Scheme |  |  |  | 5 | [7 empty] | Better performance of Units |  |  |  |  | 0 |  |  |  |  | 5 |  |  |  |  | 5 | [6 empty] | 100% | [7 empty] | 0 |  |  |  |  | 5 | [12 empty] | 5
23 | Replacement of existing Generator transformer of all units (04 x 80 MW) in phase manner (one unit per year) at Stage-III, KGSC | DPR | Yet to be approved | Yet Not submitted |  | 120 | [12 empty] | 0 | [24 empty] | 0
23.1 | Replacement of existing Generator transformer of all units (04 x 80 MW) in phase manner (one unit per year) at Stage-III, KGSC | Scheme |  |  |  | 120 | [7 empty] | To avoid power losses occurred due to detoriation of existing transformer |  |  |  |  | 0 |  |  |  |  | 30 | 30 | 30 | 30 |  | 30 | 30 | 30 | 30 |  |  |  | 25% | 50% | 75% | 100% |  |  |  |  | 0 |  |  |  |  | 30 | 30 | 30 | 30 | [9 empty] | 30 | 30 | 30 | 30
24 | Implementation of PLC & SCADA system (DSC based) for all units (04 x 80 MW) units in phase manner (two unit per year) at Stage-III, KGSC | DPR | Yet to be approved | Yet Not submitted |  | 30 | [12 empty] | 0 | [24 empty] | 0
24.1 | Implementation of PLC & SCADA system (DSC based) for all units (04 x 80 MW) units in phase manner (two unit per year) at Stage-III, KGSC | Scheme |  |  |  | 30 | [7 empty] | Improved reliability with advanced system |  |  |  |  | 0 |  |  |  |  | 15 | 15 |  |  |  | 15 | 15 | [5 empty] | 50% | 100% | [6 empty] | 0 |  |  |  |  | 15 | 15 | [11 empty] | 15 | 15
25 | Various Performance Improvement related schemes for FY 2027-28 at KGSC, Pophali | DPR | Yet to be approved | Yet Not submitted |  | 32.5 | [12 empty] | 0 | [24 empty] | 0
25.1 | Refurbishment of Stage-1, Unit No-1,2,3 & 4 PLC System and Implementation of SCADA System. | Scheme |  |  |  | 4.5 | [7 empty] | Improved reliability with advanced system |  |  |  |  | 0 | [5 empty] | 4.5 |  |  |  |  | 4.5 | [6 empty] | 100% | [6 empty] | 0 | [5 empty] | 4.5 | [12 empty] | 4.5
25.2 | Supply, installation & commissioning of New PLC & Centralog system for all four units at St-IV, KGSC | Scheme |  |  |  | 20 | [7 empty] | Improved reliability with advanced system |  |  |  |  | 0 | [5 empty] | 20 |  |  |  |  | 20 | [6 empty] | 100% | [6 empty] | 0 | [5 empty] | 20 | [12 empty] | 20
25.3 | Supply, installation & commissioning of New excitation system for all four units at St-IV, KGSC | Scheme |  |  |  | 8 | [7 empty] | Improved reliability with advanced system |  |  |  |  | 0 | [5 empty] | 8 |  |  |  |  | 8 | [6 empty] | 100% | [6 empty] | 0 | [5 empty] | 8 | [12 empty] | 8
26 | Various Performance Improvement related schemes for FY 2028-29 at KGSC, Pophali | DPR | Yet to be approved | Yet Not submitted |  | 26 | [12 empty] | 0 | [24 empty] | 0
26.1 | Upgradation of 11 KV Auxiliary breaker at St-I&II | Scheme |  |  |  | 2.5 | [7 empty] | Avoid generation loss due to failure of auxiliary supply |  |  |  |  | 0 | [6 empty] | 2.5 |  |  |  |  | 2.5 | [6 empty] | 100% | [5 empty] | 0 | [6 empty] | 2.5 | [12 empty] | 2.5
26.2 | Supply of Dry Type, 630 KVA 16 KV / 570 V Single Phase Excitation Transformers (Qty. 12 Nos.) at KGSC Stage-IV, Pophali. | Scheme |  |  |  | 3.5 | [7 empty] | Improved reliability with improved power transmission |  |  |  |  | 0 | [6 empty] | 3.5 |  |  |  |  | 3.5 | [6 empty] | 100% | [5 empty] | 0 | [6 empty] | 3.5 | [12 empty] | 3.5
26.3 | Supply, Installation & Commissioning of 16.5 KV / 433 V, 5MVA Unit Auxiliary Transformers (Qty. 02) at KGSC Stage-IV. | Scheme |  |  |  | 2 | [7 empty] | Improved reliability with stable supply. |  |  |  |  | 0 | [6 empty] | 2 |  |  |  |  | 2 | [6 empty] | 100% | [5 empty] | 0 | [6 empty] | 2 | [12 empty] | 2
26.4 | Upgradation of 2.2 KV Auxiliary Breaker with 3.3 KV Breaker along with Auxiliary Transformers at St-I&II. | Scheme |  |  |  | 8 | [7 empty] | Improved reliability with stable supply. |  |  |  |  | 0 | [6 empty] | 8 |  |  |  |  | 8 | [6 empty] | 100% | [5 empty] | 0 | [6 empty] | 8 | [12 empty] | 8
26.5 | Supply of 11KV Cable alongwith Breaker Panels for Auxiliary Supply from 8-Pole Switchyard Stage- I and II to Stage-IV Powerhouse at KGSC Stage-IV, Pophali. | Scheme |  |  |  | 4.5 | [7 empty] | Improved reliability with stable supply. |  |  |  |  | 0 | [6 empty] | 4.5 |  |  |  |  | 4.5 | [6 empty] | 100% | [5 empty] | 0 | [6 empty] | 4.5 | [12 empty] | 4.5
26.6 | Replacement of 220 KV isolator of Stage II bay at 220 KV Stage I & II Switchyard | Scheme |  |  |  | 5.5 | [7 empty] | Smooth operation of Isolator, avoid further damges to equipment of switchyard in the vicinity of them |  |  |  |  | 0 | [6 empty] | 5.5 |  |  |  |  | 5.5 | [6 empty] | 100% | [5 empty] | 0 | [6 empty] | 5.5 | [12 empty] | 5.5
27 | Various Performance Improvement related schemes for FY 2029-30 at KGSC, Pophali | DPR | Yet to be approved | Yet Not submitted |  | 25.43 | [12 empty] | 0 | [24 empty] | 0
27.1 | Design Engineering and manufacturing, supply, erection, commissioning & testing of New Pelton runner for Stage-I units (70 MW) at Stage-I&II, KGSC, Pophali. | Scheme |  |  |  | 6 | [7 empty] | Avoid the Generation loss due to unavailability of units |  |  |  |  | 0 | [7 empty] | 6 |  |  |  |  | 6 | [6 empty] | 100% |  |  |  |  | 0 | [7 empty] | 6 | [12 empty] | 6
27.2 | Upgradation of Generator and Generator transformer electromagnetic protection relays with numeric relays for Stage 1 & 2. | Scheme |  |  |  | 1.5 | [7 empty] | Online testing facility with PC for testing of relay without disturbing the Generator and Offline testing facility with PC for secondary injection test including trip status. |  |  |  |  | 0 | [7 empty] | 1.5 |  |  |  |  | 1.5 | [6 empty] | 100% |  |  |  |  | 0 | [7 empty] | 1.5 | [12 empty] | 1.5
27.3 | Renovation of old system by full proof modern digital governing system, static/brushless excitation system and generator stator and rotor winding by class 'F' insulation at St-I&II | Scheme |  |  |  | 4.32 | [7 empty] | Upgradation of system improves reliability |  |  |  |  | 0 | [7 empty] | 4.32 |  |  |  |  | 4.32 | [6 empty] | 100% |  |  |  |  | 0 | [7 empty] | 4.32 | [12 empty] | 4.32
27.4 | Design, manufacturing, supply, erection, testing and commissioning of Hydrostatic lubrication system for Units at KGSC Stage I & II, Pophali. | Scheme |  |  |  | 6.41 | [7 empty] | Minimization of starting time from dead stop |  |  |  |  | 0 | [7 empty] | 6.41 |  |  |  |  | 6.41 | [6 empty] | 100% |  |  |  |  | 0 | [7 empty] | 6.41 | [12 empty] | 6.41
27.5 | Replacement of CW pumps and Motors along with starter pannel at St-I&II | Scheme |  |  |  | 2 | [7 empty] | Avoid the Generation loss due to unavailability of units |  |  |  |  | 0 | [7 empty] | 2 |  |  |  |  | 2 | [6 empty] | 100% |  |  |  |  | 0 | [7 empty] | 2 | [12 empty] | 2
27.6 | Supply of Generator air coolers (16 Nos) for Stage II Units (80 MW) at KGSC, Pophali. | Scheme |  |  |  | 1.2 | [7 empty] | Better performance of Units |  |  |  |  | 0 | [7 empty] | 1.2 |  |  |  |  | 1.2 | [6 empty] | 100% |  |  |  |  | 0 | [7 empty] | 1.2 | [12 empty] | 1.2
27.7 | Conversion of Stator Core Insulation & Stator Winding from Class ‘B’ to Class ‘F’ for Unit No. 8 (80MW, 11KV, 375RPM, AEG Germany make) of Stage II, KGSC, Pophali on Turnkey Basis. | Scheme |  |  |  | 2 | [7 empty] | Improved reliability with upgradation of better class insulation. |  |  |  |  | 0 | [7 empty] | 2 |  |  |  |  | 2 | [6 empty] | 100% |  |  |  |  | 0 | [7 empty] | 2 | [12 empty] | 2
27.8 | Up-gradation of existing 'B' class insulation of Generator stator to 'F' class insulation of 2X18MW Koyna Dam Power House, Koynanagar. | Scheme |  |  |  | 1.5 | [7 empty] | Improved reliability with upgradation of better class insulation. |  |  |  |  | 0 | [7 empty] | 1.5 |  |  |  |  | 1.5 | [6 empty] | 100% |  |  |  |  | 0 | [7 empty] | 1.5 | [12 empty] | 1.5
27.9 | Supply and replacement of Generator air cooler system by new higher efficiency coolers for 2X18MW Koyna Dam Power House, Koynanagar. | Scheme |  |  |  | 0.5 | [7 empty] | Better performance of Units |  |  |  |  | 0 | [7 empty] | 0.5 |  |  |  |  | 0.5 | [6 empty] | 100% |  |  |  |  | 0 | [7 empty] | 0.5 | [12 empty] | 0.5
[19 empty] | 0 | [24 empty] | 0
| B) Non-DPR Schemes | [17 empty] | 0 | [24 empty] | 0
1 | <Auto Transformer Oil Insulation Test kit (BDV Kit)> | Non-DPR | N.A. | [9 empty] | 02.05.2019 |  |  | 0.03953 |  |  | 0.03953 | [21 empty] | 0.03953 |  |  | 0.03953 | [10 empty] | Capitalised
2 | <Man coolers pedestal fans at KGSC,Pophali> | Non-DPR | N.A. | [9 empty] | 07.10.2019 |  |  | 0.034143 |  |  | 0.034143 | [21 empty] | 0.034143 |  |  | 0.034143 | [10 empty] | Capitalised
3 | < 5 KV Digital Insulation Tester> | Non-DPR | N.A. | [9 empty] | 15.07.2019 |  |  | 0.029798 |  |  | 0.029798 | [21 empty] | 0.029798 |  |  | 0.029798 | [10 empty] | Capitalised
4 | <Split AC Unit,Window AC Unit,Refrigerator,Ped> | Non-DPR | N.A. | [9 empty] | 02.07.2019 |  |  | 0.017857 |  |  | 0.017857 | [21 empty] | 0.017857 |  |  | 0.017857 | [10 empty] | Capitalised
5 | <Earth Resistance Tester at ,Pophali. TIC STAGE IV> | Non-DPR | N.A. | [9 empty] | 21.09.2019 |  |  | 0.016839 |  |  | 0.016839 | [21 empty] | 0.016839 |  |  | 0.016839 | [10 empty] | Capitalised
6 | <Tools and Tackles at St-IV,KGSC,Pophali> | Non-DPR | N.A. | [9 empty] | 16.12.2019 |  |  | 0.034609 |  |  | 0.034609 | [21 empty] | 0.034609 |  |  | 0.034609 | [10 empty] | Capitalised
7 | <New portable Fire Fighting Diesel Pumps for Dewatering> | Non-DPR | N.A. | [9 empty] | 30.01.2020 |  |  | 0.09697 |  |  | 0.09697 | [21 empty] | 0.09697 |  |  | 0.09697 | [10 empty] | Capitalised
8 | <Visitors chairs for, Pophali KGSC> | Non-DPR | N.A. | [9 empty] | 18.07.2019 |  |  | 0.033188 |  |  | 0.033188 | [21 empty] | 0.033188 |  |  | 0.033188 | [10 empty] | Capitalised
9 | <Installation of new racks inside various/new slotted angle racks > | Non-DPR | N.A. | [9 empty] | 15.01.2020 |  |  | 0.039648 |  |  | 0.039648 | [21 empty] | 0.039648 |  |  | 0.039648 | [10 empty] | Capitalised
10 | <Supply of chairs for KGSC, Pophali> | Non-DPR | N.A. | [9 empty] | 20.05.2019 |  |  | 0.044238 |  |  | 0.044238 | [21 empty] | 0.044238 |  |  | 0.044238 | [10 empty] | Capitalised
11 | <Laser Jet NetwoksPrinters at KGSC, Pophali> | Non-DPR | N.A. | [9 empty] | 12.04.2019 |  |  | 0.084075 |  |  | 0.084075 | [21 empty] | 0.084075 |  |  | 0.084075 | [10 empty] | Capitalised
12 | <Night Vision Binoculars> | Non-DPR | N.A. | [9 empty] | 05.02.2020 |  |  | 0.023411 |  |  | 0.023411 | [21 empty] | 0.023411 |  |  | 0.023411 | [10 empty] | Capitalised
13 | <TATA Star Bus-32 seater LCV MH08-9358> | Non-DPR | N.A. | [9 empty] | 01.04.2008 | [5 empty] | 0 | [24 empty] | 0 | [8 empty] | 0.092818 | Asset Withdrawn | N.A.
14 | <TATA Star Bus-32 seater LCV MH08-9359> | Non-DPR | N.A. | [9 empty] | 01.04.2008 | [5 empty] | 0 | [24 empty] | 0 | [8 empty] | 0.092818 | Asset Withdrawn | N.A.
15 | <Vehicle No.MH 08-9401 TATA Star Bus 32 seater> | Non-DPR | N.A. | [9 empty] | 01.04.2008 | [5 empty] | 0 | [24 empty] | 0 | [8 empty] | 0.091858 | Asset Withdrawn | N.A.
16 | <Not in use DCM Toyato Bus MH-1> | Non-DPR | N.A. | [9 empty] | 01.04.1993 | [5 empty] | 0 | [24 empty] | 0 | [8 empty] | 0.10005 | Asset Withdrawn | N.A.
17 | <Not in use DCM Toyato Mini Bus> | Non-DPR | N.A. | [9 empty] | 01.04.1993 | [5 empty] | 0 | [24 empty] | 0 | [8 empty] | 0.050027 | Asset Withdrawn | N.A.
18 | <Digital Multimeters, Clamp Meter & Insulation resistance tester for TIC, Stage I&II, Pophali> | Non-DPR | N.A. | [9 empty] | 27.07.2020 |  |  |  | 0.028928 |  | 0.028928 | [22 empty] | 0.028928 |  | 0.028928 | [10 empty] | Capitalised
19 | <Transformer Winding resistance measurement kit at Stage-III, Alore> | Non-DPR | N.A. | [9 empty] | 29.07.2020 |  |  |  | 0.024338 |  | 0.024338 | [22 empty] | 0.024338 |  | 0.024338 | [10 empty] | Capitalised
20 | <Multifunc A3 Scanner & all in one A4 laser printer Technical Purchase , Account Section, H.R. ,MPD> | Non-DPR | N.A. | [9 empty] | 01.07.2020 |  |  |  | 0.032521 |  | 0.032521 | [22 empty] | 0.032521 |  | 0.032521 | [10 empty] | Capitalised
21 | <Temperature Calibrator at St-IV, KGSC,Pophali> | Non-DPR | N.A. | [9 empty] | 30.09.2020 |  |  |  | 0.012272 |  | 0.012272 | [22 empty] | 0.012272 |  | 0.012272 | [10 empty] | Capitalised
22 | < 1 no. new departmental car Maruti Sweft Desire for conveyance of Chief Engr> | Non-DPR | N.A. | [9 empty] | 23.02.2021 |  |  |  | 0.077924 |  | 0.077924 | [22 empty] | 0.077924 |  | 0.077924 | [10 empty] | Capitalised
23 | <Hitachi A/c Two.NO.VIP Rest House> | Non-DPR | N.A. | [9 empty] | 09.12.2020 |  |  |  | 0.008 |  | 0.008 | [22 empty] | 0.008 |  | 0.008 | [10 empty] | Capitalised
24 | <Inverter Split AC Unit, Desert Coolers Water Coolers for KGSC, Pophali> | Non-DPR | N.A. | [9 empty] | 31.03.2021 |  |  |  | 0.0070799 |  | 0.0070799 | [22 empty] | 0.0070799 |  | 0.0070799 | [10 empty] | Capitalised
25 | <Advanced ISDN EPABX system for Koyna Generating St ntercom Telephone Advanced ISDN EPABX system for Koyna Generating Station Complex> | Non-DPR | N.A. | [9 empty] | 31.03.2021 |  |  |  | 0.029645 |  | 0.029645 | [22 empty] | 0.029645 |  | 0.029645 | [10 empty] | Capitalised
26 | <TATA Sumo MH-14/9763 1 No> | Non-DPR | N.A. | [9 empty] | 31.03.2000 |  |  |  | 0.041197 |  | 0.041197 | [22 empty] | 0.041197 |  | 0.041197 | [9 empty] | Transfer from Bhira Power Station, Now scrapped | N.A.
27 | <Ambulance TATA make MH-31/4475 1 No> | Non-DPR | N.A. | [9 empty] | 31.03.1991 |  |  |  | 0.036143 |  | 0.036143 | [22 empty] | 0.036143 |  | 0.036143 | [9 empty] | Transfer from Bhira Power Station, Now scrapped | N.A.
28 | <Supply of 1 No of Ambulance Vane for Pophali> | Non-DPR | N.A. | [9 empty] | 07.12.2020 |  |  |  | 0.14883 |  | 0.14883 | [22 empty] | 0.14883 |  | 0.14883 | [10 empty] | Capitalised
29 | <Supply of 1 No of Ambulance Vane for Pophali> | Non-DPR | N.A. | [9 empty] | 07.12.2020 |  |  |  | 0.14883 |  | 0.14883 | [22 empty] | 0.14883 |  | 0.14883 | [10 empty] | Capitalised
30 | <HITACHI Make 2 TR non inverter split Air conditioner> | Non-DPR | N.A. | [9 empty] | 30.06.2021 |  |  |  |  | 0.16739 | 0.16739 | [23 empty] | 0.16739 | 0.16739 | [10 empty] | Capitalised
31 | <250 KVA D.G. Set Model KG1-250WS> | Non-DPR | N.A. | [9 empty] | 07.08.2021 |  |  |  |  | 0.19222 | 0.19222 | [23 empty] | 0.19222 | 0.19222 | [10 empty] | Capitalised
32 | <Dell laptops at KGSC Pophali> | Non-DPR | N.A. | [9 empty] | 13.10.2021 |  |  |  |  | 0.0156 | 0.0156 | [23 empty] | 0.0156 | 0.0156 | [10 empty] | Capitalised
33 | <A.C. Plant chiller 515 to 535 TRx2 at kgsc,Pophali> | Non-DPR | N.A. | [9 empty] | 12.01.2022 |  |  |  |  | 2.1144 | 2.1144 | [23 empty] | 2.1144 | 2.1144 | [10 empty] | Capitalised
34 | <Supply of RDP make Computers at KGSC> | Non-DPR | N.A. | [9 empty] | 07.02.2022 |  |  |  |  | 0.43135 | 0.43135 | [23 empty] | 0.43135 | 0.43135 | [10 empty] | Capitalised
35 | <Welding Machine for KDPH> | Non-DPR | N.A. | [9 empty] | 12.07.2021 |  |  |  |  | 0.001039 | 0.001039 | [23 empty] | 0.001039 | 0.001039 | [10 empty] | Capitalised
36 | <Material handling trolley for Majot store> | Non-DPR | N.A. | [9 empty] | 25.08.2021 |  |  |  |  | 0.0014198 | 0.0014198 | [23 empty] | 0.0014198 | 0.0014198 | [10 empty] | Capitalised
37 | <Canon LiDe 300 IN Scanner> | Non-DPR | N.A. | [9 empty] | 01.07.2021 |  |  |  |  | 0.00048 | 0.00048 | [23 empty] | 0.00048 | 0.00048 | [10 empty] | Capitalised
38 | <Supply of Pedestal fan at KDPH> | Non-DPR | N.A. | [9 empty] | 30.04.2021 |  |  |  |  | 0.015 | 0.015 | [23 empty] | 0.015 | 0.015 | [10 empty] | Capitalised
39 | <Supply of Refrigerator 290 LTR double door capacity> | Non-DPR | N.A. | [9 empty] | 30.04.2021 |  |  |  |  | 0.0022 | 0.0022 | [23 empty] | 0.0022 | 0.0022 | [10 empty] | Capitalised
40 | <Supply of Refrigerator 290 LTR double door capacity> | Non-DPR | N.A. | [9 empty] | 30.04.2021 |  |  |  |  | 0.0022 | 0.0022 | [23 empty] | 0.0022 | 0.0022 | [10 empty] | Capitalised
41 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | Non-DPR | N.A. | [9 empty] | 01.02.2022 |  |  |  |  | 0.007 | 0.007 | [23 empty] | 0.007 | 0.007 | [10 empty] | Capitalised
42 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | Non-DPR | N.A. | [9 empty] | 01.02.2022 |  |  |  |  | 0.0035 | 0.0035 | [23 empty] | 0.0035 | 0.0035 | [10 empty] | Capitalised
43 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | Non-DPR | N.A. | [9 empty] | 01.02.2022 |  |  |  |  | 0.0035 | 0.0035 | [23 empty] | 0.0035 | 0.0035 | [10 empty] | Capitalised
44 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | Non-DPR | N.A. | [9 empty] | 01.02.2022 |  |  |  |  | 0.0035 | 0.0035 | [23 empty] | 0.0035 | 0.0035 | [10 empty] | Capitalised
45 | <Redmi 10 prime Mobile Black for Chief Engineer> | Non-DPR | N.A. | [9 empty] | 05.01.2022 |  |  |  |  | 0.0015 | 0.0015 | [23 empty] | 0.0015 | 0.0015 | [10 empty] | Capitalised
46 | <TATA Sumo MH-14/9763 1 No> | Non-DPR | N.A. | [9 empty] | 31.03.2000 | [5 empty] | 0 | [24 empty] | 0 | [8 empty] | 0.041197 | Transfer from Bhira Power Station, Now scrapped | N.A.
47 | <Ambulance TATA make MH-31/4475 1 No> | Non-DPR | N.A. | [9 empty] | 31.03.1991 | [5 empty] | 0 | [24 empty] | 0 | [8 empty] | 0.036143 | Transfer from Bhira Power Station, Now scrapped | N.A.
48 | <Supply of Two Post Lift (4 Ton) for Vehicle Maint.> | Non-DPR | N.A. | [9 empty] | 2022-09-22 | [5 empty] | 0 | 0.014396 | [23 empty] | 0 | 0.014396 | [9 empty] | Capitalised |  |  | 0.014396 | [8 empty] | Capitalised
49 | Supply,Installation, commissioning and testing of 415V, 3 Phase diesel generating setof 125 KVA capacity for Admin building emergency power supply backup at KGSC,Pophali. | Non-DPR | N.A. | [9 empty] | 2023-01-27 | [5 empty] | 0 | 0.0995 | [23 empty] | 0 | 0.0995 | [9 empty] | Capitalised |  |  | 0.0995 | [8 empty] | Capitalised
50 | Design,Manufacturing, supply erriction and commissioning of 60 MT surface mounted (pit type/ platform type) weighbridge at major stores 'c' pophali | Non-DPR | N.A. | [9 empty] | 2022-08-09 | [5 empty] | 0 | 0.21577 | [23 empty] | 0 | 0.21577 | [9 empty] | Capitalised |  |  | 0.21577 | [8 empty] | Capitalised
51 | Supply of Hydraulically operated manual stacker for Material Handling at Major Store "C", KGSC, Pophali | Non-DPR | N.A. | [9 empty] | 2022-08-18 | [5 empty] | 0 | 0.00524 | [23 empty] | 0 | 0.00524 | [9 empty] | Capitalised |  |  | 0.00524 | [8 empty] | Capitalised
52 | Supply of Indef makes Chain Pulley Blocks | Non-DPR | N.A. | [9 empty] | 2023-03-24 | [5 empty] | 0 | 0.011505 | [23 empty] | 0 | 0.011505 | [9 empty] | Capitalised |  |  | 0.011505 | [8 empty] | Capitalised
53 | Supply of Motwane Make ‘Digital Multimeter and AC Multimeter | Non-DPR | N.A. | [9 empty] | 2022-06-27 | [5 empty] | 0 | 0.018458 | [23 empty] | 0 | 0.018458 | [9 empty] | Capitalised |  |  | 0.018458 | [8 empty] | Capitalised
54 | Supply 1 Ton split AC Daiken make for control room cabin Operation Stage III | Non-DPR | N.A. | [9 empty] | 2022-12-31 | [5 empty] | 0 | 0.00396 | [23 empty] | 0 | 0.00396 | [9 empty] | Capitalised |  |  | 0.00396 | [8 empty] | Capitalised
55 | Emer Rescue cum Multipurpose Fire Tender | Non-DPR | N.A. | [9 empty] | 2022-04-26 | [5 empty] | 0 | 2.0039 | [23 empty] | 0 | 2.0039 | [9 empty] | Capitalised |  |  | 2.0039 | [8 empty] | Capitalised
56 | Procurement of portable chairs for training sub centre | Non-DPR | N.A. | [9 empty] | 2022-11-19 | [5 empty] | 0 | 0.01308 | [23 empty] | 0 | 0.01308 | [9 empty] | Capitalised |  |  | 0.01308 | [8 empty] | Capitalised
57 | Procurement of portable computer tables | Non-DPR | N.A. | [9 empty] | 2022-10-21 | [5 empty] | 0 | 0.0033449 | [23 empty] | 0 | 0.0033449 | [9 empty] | Capitalised |  |  | 0.0033449 | [8 empty] | Capitalised
58 | Purchase of High back chair (3 Nos.) in conferenc hall | Non-DPR | N.A. | [9 empty] | 2023-02-28 | [5 empty] | 0 | 0.0044014 | [23 empty] | 0 | 0.0044014 | [9 empty] | Capitalised |  |  | 0.0044014 | [8 empty] | Capitalised
59 | Supply of Water Purifier at MSPGCL KGSC Pophali. | Non-DPR | N.A. | [9 empty] | 2022-10-14 | [5 empty] | 0 | 0.005 | [23 empty] | 0 | 0.005 | [9 empty] | Capitalised |  |  | 0.005 | [8 empty] | Capitalised
60 | Interactive Digital LV SCREEN 6.56 FT X 3.28 FT | Non-DPR | N.A. | [9 empty] | 2022-12-22 | [5 empty] | 0 | 0.01295 | [23 empty] | 0 | 0.01295 | [9 empty] | Capitalised |  |  | 0.01295 | [8 empty] | Capitalised
61 | Network Attached Storage Server at KGSC, Pophali. | Non-DPR | N.A. | [9 empty] | 2022-11-17 | [5 empty] | 0 | 0.023333 | [23 empty] | 0 | 0.023333 | [9 empty] | Capitalised |  |  | 0.023333 | [8 empty] | Capitalised
62 | Supply of A4 Printer at KGSC, Pophali. | Non-DPR | N.A. | [9 empty] | 2022-10-06 | [5 empty] | 0 | 0.0099995 | [23 empty] | 0 | 0.0099995 | [9 empty] | Capitalised |  |  | 0.0099995 | [8 empty] | Capitalised
63 | Supply of A4 Scanner, A3 & MF Printer at KGSC, Pop | Non-DPR | N.A. | [9 empty] | 2022-11-10 | [5 empty] | 0 | 0.0586 | [23 empty] | 0 | 0.0586 | [9 empty] | Capitalised |  |  | 0.0586 | [8 empty] | Capitalised
64 | Supply of Various Hard Disks for Network Attached | Non-DPR | N.A. | [9 empty] | 2023-01-11 | [5 empty] | 0 | 0.021806 | [23 empty] | 0 | 0.021806 | [9 empty] | Capitalised |  |  | 0.021806 | [8 empty] | Capitalised
65 | Supply of Video conference Microphone at KGSC, | Non-DPR | N.A. | [9 empty] | 2022-08-22 | [5 empty] | 0 | 0.0021512 | [23 empty] | 0 | 0.0021512 | [9 empty] | Capitalised |  |  | 0.0021512 | [8 empty] | Capitalised
66 | Supply of Video Conference Screen at KGSC Pophali | Non-DPR | N.A. | [9 empty] | 2023-02-08 | [5 empty] | 0 | 0.02 | [23 empty] | 0 | 0.02 | [9 empty] | Capitalised |  |  | 0.02 | [8 empty] | Capitalised
67 | Supply of Video conference Screen at KGSC, Pophali | Non-DPR | N.A. | [9 empty] | 2022-09-06 | [5 empty] | 0 | 0.0109 | [23 empty] | 0 | 0.0109 | [9 empty] | Capitalised |  |  | 0.0109 | [8 empty] | Capitalised
68 | Supply of Kelvinator / Godrej / Croma Make Refrigerator | Non-DPR | N.A. | [9 empty] | 2022-05-05 | [5 empty] | 0 | 0.010932 | [23 empty] | 0 | 0.010932 | [9 empty] | Capitalised |  |  | 0.010932 | [8 empty] | Capitalised
69 | supply of Bosch make High Pressure Washer at Mecha | Non-DPR | N.A. | [9 empty] | 2023-04-01 | [5 empty] | 0 |  | 0.0020649 | [22 empty] | 0 |  | 0.0020649 | [8 empty] | Capitalised |  |  |  | 0.0020649 | [7 empty] | Capitalised
70 | Supply of Pneumatic Tools for Mechanical Maintenan | Non-DPR | N.A. | [9 empty] | 2023-04-25 | [5 empty] | 0 |  | 0.035259 | [22 empty] | 0 |  | 0.035259 | [8 empty] | Capitalised |  |  |  | 0.035259 | [7 empty] | Capitalised
72 | Low BACK Revolving Chairs 45 No & Desk Chair 2 No | Non-DPR | N.A. | [9 empty] | 2023-05-31 | [5 empty] | 0 |  | 0.020945 | [22 empty] | 0 |  | 0.020945 | [8 empty] | Capitalised |  |  |  | 0.020945 | [7 empty] | Capitalised
73 | Supply of Tables at KGSC | Non-DPR | N.A. | [9 empty] | 2023-06-26 | [5 empty] | 0 |  | 0.037339 | [22 empty] | 0 |  | 0.037339 | [8 empty] | Capitalised |  |  |  | 0.037339 | [7 empty] | Capitalised
74 | Supply of Visitor Chairs & Office chairs at KGSC, | Non-DPR | N.A. | [9 empty] | 2023-04-19 | [5 empty] | 0 |  | 0.033201 | [22 empty] | 0 |  | 0.033201 | [8 empty] | Capitalised |  |  |  | 0.033201 | [7 empty] | Capitalised
75 | water purifier for colony electrical maintenance | Non-DPR | N.A. | [9 empty] | 2023-08-03 | [5 empty] | 0 |  | 0.00174 | [22 empty] | 0 |  | 0.00174 | [8 empty] | Capitalised |  |  |  | 0.00174 | [7 empty] | Capitalised
76 | Projectors and Motorized Projector Screens (2+2) | Non-DPR | N.A. | [9 empty] | 2023-04-12 | [5 empty] | 0 |  | 0.03481 | [22 empty] | 0 |  | 0.03481 | [8 empty] | Capitalised |  |  |  | 0.03481 | [7 empty] | Capitalised
77 | Acer make Computers at KGSC Pophali.21 No. | Non-DPR | N.A. | [9 empty] | 2024-01-01 | [5 empty] | 0 |  | 0.119 | [22 empty] | 0 |  | 0.119 | [8 empty] | Capitalised |  |  |  | 0.119 | [7 empty] | Capitalised
78 | Acer make Laptops at KGSC Pophali. | Non-DPR | N.A. | [9 empty] | 2023-10-18 | [5 empty] | 0 |  | 0.030088 | [22 empty] | 0 |  | 0.030088 | [8 empty] | Capitalised |  |  |  | 0.030088 | [7 empty] | Capitalised
79 | APS Smart UPS Xl 2200 VA RM 3U 230 | Non-DPR | N.A. | [9 empty] | 2024-03-15 | [5 empty] | 0 |  | 0.015983 | [22 empty] | 0 |  | 0.015983 | [8 empty] | Capitalised |  |  |  | 0.015983 | [7 empty] | Capitalised
80 | BATRY 12V 75 AH BATTREY 11 PLATE | Non-DPR | N.A. | [9 empty] | 2024-03-15 | [5 empty] | 0 |  | 0.017629 | [22 empty] | 0 |  | 0.017629 | [8 empty] | Capitalised |  |  |  | 0.017629 | [7 empty] | Capitalised
81 | Supply & installation of IP Camera System and network spare | Non-DPR | N.A. | [9 empty] | 2023-11-01 | [5 empty] | 0 |  | 0.025807 | [22 empty] | 0 |  | 0.025807 | [8 empty] | Capitalised |  |  |  | 0.025807 | [7 empty] | Capitalised
82 | Gym Equipments at MSPGCL Recreation club , 33 Item | Non-DPR | N.A. | [9 empty] | 2023-04-20 | [5 empty] | 0 |  | 0.047834 | [22 empty] | 0 |  | 0.047834 | [8 empty] | Capitalised |  |  |  | 0.047834 | [7 empty] | Capitalised
| Non-DPR schemes (3 Nos) for FY 2024-25 at KGSC Pophali | Non-DPR | Board Resolution No-MSPGCL/BM-219/Item 219.7 dtd.24.07.2023 |  |  | 10.17 | [12 empty] | 0 | [24 empty] | 0
83 | Up-gradation of thyristor based 48V Battery Chargers (4 nos) by SMPS Microprocessor based dual float cum boost Battery Chargers at Stage-III, Stage-I&II and KDPH at KGSC, Pophali | Scheme |  |  |  | 1.57 | [7 empty] | Service reliability & avoid generation loss due to failure of charger |  |  |  |  | 0 |  |  | 1.57 | [21 empty] | 0 |  |  | 1.57 | [6 empty] | Tender under price bid scrutiny. | Not Initiated |  |  |  |  | 1.57 | [5 empty] | Tender under publication | Not Initiated
84 | Up-gradation of thyristor based 220V Battery Chargers (4 nos) by SMPS Microprocessor based dual float cum boost Battery Chargers at Stage-III and Stage-I&II at KGSC, Pophali | Scheme |  |  |  | 3.79 | [7 empty] | Service reliability & avoid generation loss due to failure of charger |  |  |  |  | 0 |  |  | 3.79 | [21 empty] | 0 |  |  | 3.79 | [6 empty] | Tender under price bid scrutiny. | Not Initiated |  |  |  |  | 3.79 | [5 empty] | Tender under publication | Not Initiated
85 | Retrofitting of Generator and Gen. Transformer protection relay by Numerical protection system at KGSC stage III, Alore | Scheme |  |  |  | 4.81 | [7 empty] | Online testing facility with PC for testing of relay without disturbing the Generator and Offline testing facility with PC for secondary injection test including trip status. |  |  |  |  | 0 |  |  | 4.78 | [21 empty] | 0 |  |  | 4.78 | [6 empty] | Material awaited. The PO No. 4385000774/ 2890 dtd.20/08/2024 is placed to M/s. Super Spare | Not Initiated |  |  |  |  | 4.81 | [5 empty] | TC bid under scrutiny | Not Initiated
| IDC | IDC |  |  |  | 0.28 | [12 empty] | 0 | [24 empty] | 0 | [23 empty] | 0 | 0
| Non-DPR schemes (2 Nos) for FY 2025-26 at KGSC Pophali | Non-DPR | Yet Not Submitted |  |  | 9.6 | [12 empty] | 0 | [24 empty] | 0
86 | Supply, Erection, Commissioning & Retrofitting of 220 VDC Ni-cadmium type Battery set (4 Nos) having different ampere hour capacity at Stage-I&II and Stage-IV | Scheme |  |  |  | 9.23 | [7 empty] | Service reliability & avoid generation loss due to failure of charger |  |  |  |  | 0 |  |  |  | 9.23 |  |  |  |  | 9.23 | [6 empty] | 100% | [8 empty] | 0 |  |  |  | 9.23 | [5 empty] | DPR submitted to HO (works) for approval on 30.08.2024 | Not Initiated | [5 empty] | 9.23 |  |  |  |  | Under Non-DPR preparation | Not Initiated
87 | Supply, Erection, Commissioning & Retrofitting of 48VDC, 300AH Ni-cadmium type Battery set at Stage-I&II switchyard | Scheme |  |  |  | 0.37 | [7 empty] | Service reliability & avoid generation loss due to failure of charger |  |  |  |  | 0 |  |  |  | 0.37 |  |  |  |  | 0.37 | [6 empty] | 100% | [8 empty] | 0 |  |  |  | 0.37 | [5 empty] | DPR submitted to HO (works) for approval on 30.08.2024 | Not Initiated | [5 empty] | 0.37 |  |  |  |  | Under Non-DPR preparation | Not Initiated
| Total | [13 empty] | 28.6148 | 7.8529 | 10.7267 | 6.2865 | 53.4809 | 28.9054 | 16.0786 | 39.09 | 93.22 | 135.06 | 77.5 | 56 | 55.43 | [12 empty] | 25.8845 | 7.8529 | 10.7267 | 6.2865 | 50.7506 | 10.4964 | 9.5256 | 58.86 | 98.41 | 130.58 | 77.5 | 56 | 55.43 | 0.50491
[45 empty] | 2.5692 | 0.4217 | 10.14
1.1579
0.2725
0.077792
0.20474
0.25038
0
0.39749
2.3608
[15 empty] | 0.32487 | [24 empty] | 0.32487
[15 empty] | 0.26213 | [24 empty] | 0.26213
[15 empty] | 0.1 | [24 empty] | 0.1
[15 empty] | 0.0925 | [24 empty] | 0.0925
[15 empty] | 0.31086 | [24 empty] | 0.31086
[15 empty] | 0.22553 | [24 empty] | 0.096788
[15 empty] | 1.3159 | [24 empty] | 1.1871
0.20057
0.13371
0.18378
0.384
0.20725
0
0.33133
1.4406
Formulas:
Date of Submission = [Date of Submission, row above]
MERC Approval Date = IF([MERC Approval Date, row above]=0,"-",[MERC Approval Date, row above])
Note on L4: Actual PO placed date
Note on M4: SSP-RCD As per the implementation plan submitted in the DPR/ Approved by MERC
Note on N4: Date of capitalization as per account section
Note on G53: SSP-RCD: P&F, Insurance charges were shown separately in the DPR
Note on H53: SSP-RCD: P&F, Insurance charges were shown separately in the DPR

## F4.3 KGSC
MSPGCL: KGSC, Pophali
MTR Petition Formats - Generation
| Project Details | Form 4.3: Capital Work-in-progress - Project-wise details | [9 empty] | (Rs. Crore)
Sr. No. | Project Code | MERC Approval No. | MERC Approval Date | Approved Project Cost | Cumulative Expenditure Incurred till beginning of the Year | Capital Expenditure Capitalised | Opening CWIP | Investment during the year | Capitalization |  |  |  | Closing CWIP
[9 empty] | Works Capitalised | Interest Capitalised | Expenses Capitalised | Total Capitalisation |  | Allowable Capitalisation | Probable Disallowance
FY 2022-23
a) DPR Schemes
(i) Submitted to MERC
1 | Various improvement schemes at Pophali Hydro Power Station | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 11.9001 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | ALSPA HMI Series 6 Centralog System | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 6.8555 | 7.8386 | 7.8386 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | 1 X 525 Tr chiller unit | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 1.23 | 1.15 | 1.15 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Micom P343 Numerical generator protection relay with 24 DI & 24 DO with CLIO input. (5 Nos) | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 1.4675 | 1.474 | 1.474 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.4 | Security Building at Stage-IV | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 0.16446 | 0.18377 | 0.18377 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.5 | Construction of recreation club building | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 1.8204 | 2.1946 | 2.1946 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.6 | Security Building for Stage-IV at EVT | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 0.22776 | 0.25961 | 0.25961 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 0.1344 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Various DPR Schemes for Civil Section, KGSC Pophali | MERC/CAPEX/20152016/00907 | 2015-11-05 | 21.201 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Providing Road Network at KGSC, Pophali | MERC/CAPEX/20152016/00907 | 2015-11-05 | 7.776 | 6.924 | 6.924 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.2 | Modernisation & Refurbishing of Residential Complex | MERC/CAPEX/20152016/00907 | 2015-11-05 | 8.985 | 8.2 | 8.2 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.3 | Water Supply & Sanitory Works | MERC/CAPEX/20152016/00907 | 2015-11-05 | 4.44 | 2.0389 | 0.23919 | 1.7997 | 0 | 0 |  |  | 0 | 1.7997 | 0 | 0
4 | Various Performance Improvement related schemes at KGSC, Pophali | MERC/CAPEX/20162017/01018 | 2016-11-17 | 12.9765 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Up gradation of 245 kV CTs at Stage-I&II SY | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.9624 | 2.09 | 2.09 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Up gradation of 245 kV PTs at Stage-I&II SY | MERC/CAPEX/20162017/01018 | 2016-11-17 | 0.40509 | 0.3417 | 0.3417 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.3 | Up gradation of CW system of Stage-I&II Units | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.7099 | 1.4731 | 1.4731 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.4 | Up gradation of Intercom Exchange System between Stage-I&II PH & Admin. Bldg & Staff Colony. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 0.43826 | 0.359 | 0.359 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.5 | Up gradation of 220 kV Breakers at KDPH SY | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.289 | 0.979 | 0.979 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.6 | Procurement of Governing Oil Pumps for Stage-III Units. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.2316 | 0.70174 | 0.70174 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.7 | Up gradation of TG Governing system of Stage-IV Units. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 2.2152 | 0 | 0 | 0 | 2.7472 | 2.7472 |  |  | 2.7472 | 0 | 2.2152 | 0.53204
4.8 | Up gradation of Numerical Protection system of Stage-IV Units. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 2.8249 | 2.8674 | 2.8674 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01018 | 2016-11-17 | 0.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7 | Replacement of Generator Stator of unit No. 11 (80 MW), Stage III, KGSC Pophali | MERC/CAPEX/20172018/04592 | 2017-11-07 | 22.54 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Replacement of Generator Stator of unit No. 11 (80 MW), Stage III, KGSC Pophali | MERC/CAPEX/20172018/04592 | 2017-11-07 | 22.54 | 0 | 0 | 0 | 16.579 | 0 |  |  | 0 | 16.579 | 0 | 0
8 | Procurement of new pelton wheel runners (2 Nos.) for Stage II at KGSC, Pophali | MERC/CAPEX/20172018/04421 | 2017-10-24 | 13.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement of new pelton wheel runners (2 Nos.) for Stage II at KGSC, Pophali | MERC/CAPEX/20172018/04421 | 2017-10-24 | 13.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Implementation of 12 Nos. of various schemes at KGSC, Pophali. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 26.891 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Replacement of UGB (8 Nos), LGB (8 Nos) & Generator air coolers (8 Nos) for Stage-I | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 1.344 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Retrofitting of Generator & Gen-Transformer relays by new numerical protection system at Koyna Dam Power House (KDPH) Koynanagar | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 1.097 | 0 | 0 | 0 | 0.82 | 0 |  |  | 0 | 0.82 | 0 | 0
11.3 | Replacement of two 220V Battery chargers with 220V dual float cum boost (60A) battery Charger including DCDB at KDPH, Koynanagar | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.202 | 0.13782 | 0.13782 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.4 | Replacement of 220KV current transformer (54 Nos), Potential transformer (13 Nos),110KV Current Transformer (14 Nos)& Potential Transformer (4 Nos),Stage-III. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 5.281 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.5 | Replacement of Generator Air Cooler (32 Nos), St-III | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 2.413 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.6 | Replacement of 48 Volt, 1000 AH tubular battery set with 48 Volt, 750AH Plante type battery set at KGSC, Stage-III | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.318 | 0.30942 | 0.30942 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.7 | Replacement of 220V-150AH Battery set with Ni-Cad type, along with standard accessories for UPS scheme at Stage-IV | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.272 | 0.25759 | 0.25759 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.8 | Reliability enhancement of Gas Insulated Switchyard Stage-IV. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 10.472 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.9 | Up-gradation of Vibration system at all units of Stage-IV:Stage-IV, KGSC, Pophali | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 1.443 | 0 | 0 | 0 | 1.01 | 0 |  |  | 0 | 1.01 | 0 | 0
11.10 | Replacement of station battery set of 220V, 2000Ah capacity at Stage-IV. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 2.385 | 2.3649 | 2.3649 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.11 | Renovations and modernization of 1500kg capacity passenger cum goods lifts (2 Nos) for KGSC, Stage-IV | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.968 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.12 | Replacement of existing 3x7.5 TR Air conditioning package units at Stage-I&II control room by new 3x11 TR Air conditioning package units | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.345 | 0.16909 | 0.16909 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.351 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Upgradation of Governing System at Stage-I, KDPH& Stage-III at KGSC, Pophali | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 19.1651 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Up gradation of DIGIPID1500 governing system with new governor (TSLG) for all units of stage-I | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 6.0888 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.2 | Up-gradation of governing system at Koyna Dam Power House (KDPH) Koynanagar | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 2.924 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.3 | Up-gradation of the Governing system at Stage-III & Other Charges (P&F, Insurance etc) | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 9.5523 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Refurbishment of 24 KV Generator Circuit Breakers (ABB Make) for four units at stage-IV, KGSC, Pophali | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 10.5726 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Supply spares for 24KV Generator Circuit Breaker System refurbishment (For 4 Units) | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 6.5702 | 3.2721 | 3.2721 | 0 | 3.27 | 3.27 |  |  | 3.27 | 0 | 3.27 | 0
13.2 | Supervision charges for 24 KV Generator Circuit Breaker System Unit. Preparation charges, Travel & transportation charges, local conveyance. Lumpsum rental charges of necessary tools & tackles required during O/H work charges | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 3.8704 | 1.9116 | 1.9116 | 0 | 1.91 | 1.91 |  |  | 1.91 | 0 | 1.91 | 0
0 | IDC | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 0.132 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Up-gradation of Excitation system at Stage-I&II, PLC & SCADA system at Stage-II and DG Set at Stage-IV at KGSC, Pophali | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 9.863 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | Up gradation of Stage-I&II(4x70MW+4x80 MW) Static Semipol Excitation System with Latest Advanced Excitation System | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 9.863 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.2 | Up gradation of existing unit PLC and SCADA automation of 4x80 MW Koyna stage-II units | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 4.232 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.3 | Up gradation of one 1500 KVA DG set, at KGSC, Stage-IV | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 1.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 1.103 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Repair works in Emergency Valve Tunnel (EVT) and surge well at Stage I/II, KGSC, Pophali | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 28.0371 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Sealing and stabilization of EVT Tunnel left side wall and carven portion of EVT and Ventilation Tunnel. | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 8.307 | 1.5431 | 0 | 1.5431 | 0 | 0 |  |  | 0 | 1.5431 | 0 | 0
17.2 | Structural Strengthening and Sealing Cracks and Cavities in Surge Shaft RCC Staining Wall from inside | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 18.6602 | 0.3875 | 0 | 0.3875 | 0 | 0 |  |  | 0 | 0.3875 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 1.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-8.1 | Advance Multipurpose Fire Tender | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-8.2 | Normal Multipurpose Fire Tender | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Refurbishment of cooling and drainage water system along with replacement of 5 no's of cooling water pumps by new stage -IV KGSC Pophali | MERC/CAPEX/2023-2024/MSPGCL/0201 | 2024-03-21 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Refurbishment of cooling and drainage water system along with replacement of 5 no's of cooling water pumps by new stage -IV KGSC Pophali | MERC/CAPEX/2023-2024/MSPGCL/0201 | 2024-03-21 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0201 | 2024-03-21 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | Refurbishment of GIS T155 as per M4 Schedule at KGSC Stage-IV, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | Refurbishment of GIS T155 as per M4 Schedule at KGSC Stage-IV, Pophali | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20 | Various Civil work as per IB recommendation at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.1 | Various Civil work as per IB recommendation at KGSC, Pophali | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.2 | construction of chainlink caging along entrance of St-I&II, St-III & St-IV | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Stabilization and Mitigation of Landslide Prone Areas at KGSC, Mahagenco, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Stabilization and Mitigation of Landslide Prone Areas | 0 | - | 0 | 0 | 1 | -1 | 0 | 0 |  |  | 0 | -1
21.2 | Construction of retaining wall | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.3 | Dredging river and nallah | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | Various Performance Improvement related schemes for FY 2026-27 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.1 | Supply of New Runner for Francis Turbine 80 MW at KGSC Stage-III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.2 | Supply of 2 Nos. injector along with injector shaft for Stage-I Units (70 MW) at Stage I & II KGSC, Pophali . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.3 | Supply of 1 No. injector for Stage-II Units (80 MW) at Stage I & II KGSC, Pophali . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.4 | Upgradation of AC Chiiler system at Stage I & II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.5 | Design, manufacturing, supply, erection, testing and commissioning of LGB and UGB cooler modifications at KGSC Stage I&II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Replacement of existing Generator transformer of all units (04 x 80 MW) in phase manner (one unit per year) at Stage-III, KGSC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.1 | Replacement of existing Generator transformer of all units (04 x 80 MW) in phase manner (one unit per year) at Stage-III, KGSC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Implementation of PLC & SCADA system (DSC based) for all units (04 x 80 MW) units in phase manner (two unit per year) at Stage-III, KGSC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.1 | Implementation of PLC & SCADA system (DSC based) for all units (04 x 80 MW) units in phase manner (two unit per year) at Stage-III, KGSC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | Various Performance Improvement related schemes for FY 2027-28 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.1 | Refurbishment of Stage-1, Unit No-1,2,3 & 4 PLC System and Implementation of SCADA System. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.2 | Supply, installation & commissioning of New PLC & Centralog system for all four units at St-IV, KGSC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.3 | Supply, installation & commissioning of New excitation system for all four units at St-IV, KGSC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | Various Performance Improvement related schemes for FY 2028-29 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.1 | Upgradation of 11 KV Auxiliary breaker at St-I&II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.2 | Supply of Dry Type, 630 KVA 16 KV / 570 V Single Phase Excitation Transformers (Qty. 12 Nos.) at KGSC Stage-IV, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.3 | Supply, Installation & Commissioning of 16.5 KV / 433 V, 5MVA Unit Auxiliary Transformers (Qty. 02) at KGSC Stage-IV. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.4 | Upgradation of 2.2 KV Auxiliary Breaker with 3.3 KV Breaker along with Auxiliary Transformers at St-I&II. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.5 | Supply of 11KV Cable alongwith Breaker Panels for Auxiliary Supply from 8-Pole Switchyard Stage- I and II to Stage-IV Powerhouse at KGSC Stage-IV, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.6 | Replacement of 220 KV isolator of Stage II bay at 220 KV Stage I & II Switchyard | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | Various Performance Improvement related schemes for FY 2029-30 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.1 | Design Engineering and manufacturing, supply, erection, commissioning & testing of New Pelton runner for Stage-I units (70 MW) at Stage-I&II, KGSC, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.2 | Upgradation of Generator and Generator transformer electromagnetic protection relays with numeric relays for Stage 1 & 2. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.3 | Renovation of old system by full proof modern digital governing system, static/brushless excitation system and generator stator and rotor winding by class 'F' insulation at St-I&II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.4 | Design, manufacturing, supply, erection, testing and commissioning of Hydrostatic lubrication system for Units at KGSC Stage I & II, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.5 | Replacement of CW pumps and Motors along with starter pannel at St-I&II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.6 | Supply of Generator air coolers (16 Nos) for Stage II Units (80 MW) at KGSC, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.7 | Conversion of Stator Core Insulation & Stator Winding from Class ‘B’ to Class ‘F’ for Unit No. 8 (80MW, 11KV, 375RPM, AEG Germany make) of Stage II, KGSC, Pophali on Turnkey Basis. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.8 | Up-gradation of existing 'B' class insulation of Generator stator to 'F' class insulation of 2X18MW Koyna Dam Power House, Koynanagar. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.9 | Supply and replacement of Generator air cooler system by new higher efficiency coolers for 2X18MW Koyna Dam Power House, Koynanagar. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | <Auto Transformer Oil Insulation Test kit (BDV Kit)> | N.A. | - | 0 | 0.03953 | 0.03953 | 0 | 0 | 0 |  |  | 0 | 0
2 | <Man coolers pedestal fans at KGSC,Pophali> | N.A. | - | 0 | 0.034143 | 0.034143 | 0 | 0 | 0 |  |  | 0 | 0
3 | < 5 KV Digital Insulation Tester> | N.A. | - | 0 | 0.029798 | 0.029798 | 0 | 0 | 0 |  |  | 0 | 0
4 | <Split AC Unit,Window AC Unit,Refrigerator,Ped> | N.A. | - | 0 | 0.017857 | 0.017857 | 0 | 0 | 0 |  |  | 0 | 0
5 | <Earth Resistance Tester at ,Pophali. TIC STAGE IV> | N.A. | - | 0 | 0.016839 | 0.016839 | 0 | 0 | 0 |  |  | 0 | 0
6 | <Tools and Tackles at St-IV,KGSC,Pophali> | N.A. | - | 0 | 0.034609 | 0.034609 | 0 | 0 | 0 |  |  | 0 | 0
7 | <New portable Fire Fighting Diesel Pumps for Dewatering> | N.A. | - | 0 | 0.09697 | 0.09697 | 0 | 0 | 0 |  |  | 0 | 0
8 | <Visitors chairs for, Pophali KGSC> | N.A. | - | 0 | 0.033188 | 0.033188 | 0 | 0 | 0 |  |  | 0 | 0
9 | <Installation of new racks inside various/new slotted angle racks > | N.A. | - | 0 | 0.039648 | 0.039648 | 0 | 0 | 0 |  |  | 0 | 0
10 | <Supply of chairs for KGSC, Pophali> | N.A. | - | 0 | 0.044238 | 0.044238 | 0 | 0 | 0 |  |  | 0 | 0
11 | <Laser Jet NetwoksPrinters at KGSC, Pophali> | N.A. | - | 0 | 0.084075 | 0.084075 | 0 | 0 | 0 |  |  | 0 | 0
12 | <Night Vision Binoculars> | N.A. | - | 0 | 0.023411 | 0.023411 | 0 | 0 | 0 |  |  | 0 | 0
13 | <TATA Star Bus-32 seater LCV MH08-9358> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | <TATA Star Bus-32 seater LCV MH08-9359> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | <Vehicle No.MH 08-9401 TATA Star Bus 32 seater> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | <Not in use DCM Toyato Bus MH-1> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | <Not in use DCM Toyato Mini Bus> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | <Digital Multimeters, Clamp Meter & Insulation resistance tester for TIC, Stage I&II, Pophali> | N.A. | - | 0 | 0.028928 | 0.028928 | 0 | 0 | 0 |  |  | 0 | 0
19 | <Transformer Winding resistance measurement kit at Stage-III, Alore> | N.A. | - | 0 | 0.024338 | 0.024338 | 0 | 0 | 0 |  |  | 0 | 0
20 | <Multifunc A3 Scanner & all in one A4 laser printer Technical Purchase , Account Section, H.R. ,MPD> | N.A. | - | 0 | 0.032521 | 0.032521 | 0 | 0 | 0 |  |  | 0 | 0
21 | <Temperature Calibrator at St-IV, KGSC,Pophali> | N.A. | - | 0 | 0.012272 | 0.012272 | 0 | 0 | 0 |  |  | 0 | 0
22 | < 1 no. new departmental car Maruti Sweft Desire for conveyance of Chief Engr> | N.A. | - | 0 | 0.077924 | 0.077924 | 0 | 0 | 0 |  |  | 0 | 0
23 | <Hitachi A/c Two.NO.VIP Rest House> | N.A. | - | 0 | 0.008 | 0.008 | 0 | 0 | 0 |  |  | 0 | 0
24 | <Inverter Split AC Unit, Desert Coolers Water Coolers for KGSC, Pophali> | N.A. | - | 0 | 0.0070799 | 0.0070799 | 0 | 0 | 0 |  |  | 0 | 0
25 | <Advanced ISDN EPABX system for Koyna Generating St ntercom Telephone Advanced ISDN EPABX system for Koyna Generating Station Complex> | N.A. | - | 0 | 0.029645 | 0.029645 | 0 | 0 | 0 |  |  | 0 | 0
26 | <TATA Sumo MH-14/9763 1 No> | N.A. | - | 0 | 0.041197 | 0.041197 | 0 | 0 | 0 |  |  | 0 | 0
27 | <Ambulance TATA make MH-31/4475 1 No> | N.A. | - | 0 | 0.036143 | 0.036143 | 0 | 0 | 0 |  |  | 0 | 0
28 | <Supply of 1 No of Ambulance Vane for Pophali> | N.A. | - | 0 | 0.14883 | 0.14883 | 0 | 0 | 0 |  |  | 0 | 0
29 | <Supply of 1 No of Ambulance Vane for Pophali> | N.A. | - | 0 | 0.14883 | 0.14883 | 0 | 0 | 0 |  |  | 0 | 0
30 | <HITACHI Make 2 TR non inverter split Air conditioner> | N.A. | - | 0 | 0.16739 | 0.16739 | 0 | 0 | 0 |  |  | 0 | 0
31 | <250 KVA D.G. Set Model KG1-250WS> | N.A. | - | 0 | 0.19222 | 0.19222 | 0 | 0 | 0 |  |  | 0 | 0
32 | <Dell laptops at KGSC Pophali> | N.A. | - | 0 | 0.0156 | 0.0156 | 0 | 0 | 0 |  |  | 0 | 0
33 | <A.C. Plant chiller 515 to 535 TRx2 at kgsc,Pophali> | N.A. | - | 0 | 2.1144 | 2.1144 | 0 | 0 | 0 |  |  | 0 | 0
34 | <Supply of RDP make Computers at KGSC> | N.A. | - | 0 | 0.43135 | 0.43135 | 0 | 0 | 0 |  |  | 0 | 0
35 | <Welding Machine for KDPH> | N.A. | - | 0 | 0.001039 | 0.001039 | 0 | 0 | 0 |  |  | 0 | 0
36 | <Material handling trolley for Majot store> | N.A. | - | 0 | 0.0014198 | 0.0014198 | 0 | 0 | 0 |  |  | 0 | 0
37 | <Canon LiDe 300 IN Scanner> | N.A. | - | 0 | 0.00048 | 0.00048 | 0 | 0 | 0 |  |  | 0 | 0
38 | <Supply of Pedestal fan at KDPH> | N.A. | - | 0 | 0.015 | 0.015 | 0 | 0 | 0 |  |  | 0 | 0
39 | <Supply of Refrigerator 290 LTR double door capacity> | N.A. | - | 0 | 0.0022 | 0.0022 | 0 | 0 | 0 |  |  | 0 | 0
40 | <Supply of Refrigerator 290 LTR double door capacity> | N.A. | - | 0 | 0.0022 | 0.0022 | 0 | 0 | 0 |  |  | 0 | 0
41 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.007 | 0.007 | 0 | 0 | 0 |  |  | 0 | 0
42 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.0035 | 0.0035 | 0 | 0 | 0 |  |  | 0 | 0
43 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.0035 | 0.0035 | 0 | 0 | 0 |  |  | 0 | 0
44 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.0035 | 0.0035 | 0 | 0 | 0 |  |  | 0 | 0
45 | <Redmi 10 prime Mobile Black for Chief Engineer> | N.A. | - | 0 | 0.0015 | 0.0015 | 0 | 0 | 0 |  |  | 0 | 0
46 | <TATA Sumo MH-14/9763 1 No> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47 | <Ambulance TATA make MH-31/4475 1 No> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48 | <Supply of Two Post Lift (4 Ton) for Vehicle Maint.> | N.A. | - | 0 | 0 | 0 | 0 | 0.014396 | 0.014396 |  |  | 0.014396 | 0
49 | Supply,Installation, commissioning and testing of 415V, 3 Phase diesel generating setof 125 KVA capacity for Admin building emergency power supply backup at KGSC,Pophali. | N.A. | - | 0 | 0 | 0 | 0 | 0.0995 | 0.0995 |  |  | 0.0995 | 0
50 | Design,Manufacturing, supply erriction and commissioning of 60 MT surface mounted (pit type/ platform type) weighbridge at major stores 'c' pophali | N.A. | - | 0 | 0 | 0 | 0 | 0.21577 | 0.21577 |  |  | 0.21577 | 0
51 | Supply of Hydraulically operated manual stacker for Material Handling at Major Store "C", KGSC, Pophali | N.A. | - | 0 | 0 | 0 | 0 | 0.00524 | 0.00524 |  |  | 0.00524 | 0
52 | Supply of Indef makes Chain Pulley Blocks | N.A. | - | 0 | 0 | 0 | 0 | 0.011505 | 0.011505 |  |  | 0.011505 | 0
53 | Supply of Motwane Make ‘Digital Multimeter and AC Multimeter | N.A. | - | 0 | 0 | 0 | 0 | 0.018458 | 0.018458 |  |  | 0.018458 | 0
54 | Supply 1 Ton split AC Daiken make for control room cabin Operation Stage III | N.A. | - | 0 | 0 | 0 | 0 | 0.00396 | 0.00396 |  |  | 0.00396 | 0
55 | Emer Rescue cum Multipurpose Fire Tender | N.A. | - | 0 | 0 | 0 | 0 | 2.0039 | 2.0039 |  |  | 2.0039 | 0
56 | Procurement of portable chairs for training sub centre | N.A. | - | 0 | 0 | 0 | 0 | 0.01308 | 0.01308 |  |  | 0.01308 | 0
57 | Procurement of portable computer tables | N.A. | - | 0 | 0 | 0 | 0 | 0.0033449 | 0.0033449 |  |  | 0.0033449 | 0
58 | Purchase of High back chair (3 Nos.) in conferenc hall | N.A. | - | 0 | 0 | 0 | 0 | 0.0044014 | 0.0044014 |  |  | 0.0044014 | 0
59 | Supply of Water Purifier at MSPGCL KGSC Pophali. | N.A. | - | 0 | 0 | 0 | 0 | 0.005 | 0.005 |  |  | 0.005 | 0
60 | Interactive Digital LV SCREEN 6.56 FT X 3.28 FT | N.A. | - | 0 | 0 | 0 | 0 | 0.01295 | 0.01295 |  |  | 0.01295 | 0
61 | Network Attached Storage Server at KGSC, Pophali. | N.A. | - | 0 | 0 | 0 | 0 | 0.023333 | 0.023333 |  |  | 0.023333 | 0
62 | Supply of A4 Printer at KGSC, Pophali. | N.A. | - | 0 | 0 | 0 | 0 | 0.0099995 | 0.0099995 |  |  | 0.0099995 | 0
63 | Supply of A4 Scanner, A3 & MF Printer at KGSC, Pop | N.A. | - | 0 | 0 | 0 | 0 | 0.0586 | 0.0586 |  |  | 0.0586 | 0
64 | Supply of Various Hard Disks for Network Attached | N.A. | - | 0 | 0 | 0 | 0 | 0.021806 | 0.021806 |  |  | 0.021806 | 0
65 | Supply of Video conference Microphone at KGSC, | N.A. | - | 0 | 0 | 0 | 0 | 0.0021512 | 0.0021512 |  |  | 0.0021512 | 0
66 | Supply of Video Conference Screen at KGSC Pophali | N.A. | - | 0 | 0 | 0 | 0 | 0.02 | 0.02 |  |  | 0.02 | 0
67 | Supply of Video conference Screen at KGSC, Pophali | N.A. | - | 0 | 0 | 0 | 0 | 0.0109 | 0.0109 |  |  | 0.0109 | 0
68 | Supply of Kelvinator / Godrej / Croma Make Refrigerator | N.A. | - | 0 | 0 | 0 | 0 | 0.010932 | 0.010932 |  |  | 0.010932 | 0
69 | supply of Bosch make High Pressure Washer at Mecha | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
70 | Supply of Pneumatic Tools for Mechanical Maintenan | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
72 | Low BACK Revolving Chairs 45 No & Desk Chair 2 No | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
73 | Supply of Tables at KGSC | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
74 | Supply of Visitor Chairs & Office chairs at KGSC, | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
75 | water purifier for colony electrical maintenance | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
76 | Projectors and Motorized Projector Screens (2+2) | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
77 | Acer make Computers at KGSC Pophali.21 No. | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
78 | Acer make Laptops at KGSC Pophali. | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
79 | APS Smart UPS Xl 2200 VA RM 3U 230 | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
80 | BATRY 12V 75 AH BATTREY 11 PLATE | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
81 | Supply & installation of IP Camera System and network spare | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
82 | Gym Equipments at MSPGCL Recreation club , 33 Item | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Non-DPR schemes (3 Nos) for FY 2024-25 at KGSC Pophali | Board Resolution No-MSPGCL/BM-219/Item 219.7 dtd.24.07.2023 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
83 | Up-gradation of thyristor based 48V Battery Chargers (4 nos) by SMPS Microprocessor based dual float cum boost Battery Chargers at Stage-III, Stage-I&II and KDPH at KGSC, Pophali | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
84 | Up-gradation of thyristor based 220V Battery Chargers (4 nos) by SMPS Microprocessor based dual float cum boost Battery Chargers at Stage-III and Stage-I&II at KGSC, Pophali | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
85 | Retrofitting of Generator and Gen. Transformer protection relay by Numerical protection system at KGSC stage III, Alore | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Non-DPR schemes (2 Nos) for FY 2025-26 at KGSC Pophali | Yet Not Submitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
86 | Supply, Erection, Commissioning & Retrofitting of 220 VDC Ni-cadmium type Battery set (4 Nos) having different ampere hour capacity at Stage-I&II and Stage-IV | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
87 | Supply, Erection, Commissioning & Retrofitting of 48VDC, 300AH Ni-cadmium type Battery set at Stage-I&II switchyard | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 53.4809 | 50.7506 | 2.7303 | 28.9054 | 10.4964 | 0 | 0 | 10.4964 | 21.1393
FY 2023-24
a) DPR Schemes
(i) Submitted to MERC
1 | Various improvement schemes at Pophali Hydro Power Station | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 11.9001 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | ALSPA HMI Series 6 Centralog System | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 6.8555 | 7.8386 | 7.8386 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | 1 X 525 Tr chiller unit | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 1.23 | 1.15 | 1.15 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Micom P343 Numerical generator protection relay with 24 DI & 24 DO with CLIO input. (5 Nos) | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 1.4675 | 1.474 | 1.474 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.4 | Security Building at Stage-IV | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 0.16446 | 0.18377 | 0.18377 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.5 | Construction of recreation club building | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 1.8204 | 2.1946 | 2.1946 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.6 | Security Building for Stage-IV at EVT | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 0.22776 | 0.25961 | 0.25961 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 0.1344 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Various DPR Schemes for Civil Section, KGSC Pophali | MERC/CAPEX/20152016/00907 | 2015-11-05 | 21.201 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Providing Road Network at KGSC, Pophali | MERC/CAPEX/20152016/00907 | 2015-11-05 | 7.776 | 6.924 | 6.924 | 0 | 0.09422 | 0.09422 |  |  | 0.09422 | 0 | 0.09422 | 0
3.2 | Modernisation & Refurbishing of Residential Complex | MERC/CAPEX/20152016/00907 | 2015-11-05 | 8.985 | 8.2 | 8.2 | 0 | 0.73647 | 0.73647 |  |  | 0.73647 | 0 | 0.73647 | 0
3.3 | Water Supply & Sanitory Works | MERC/CAPEX/20152016/00907 | 2015-11-05 | 4.44 | 2.0389 | 0.23919 | 1.7997 | 3.863 | 3.863 |  |  | 3.863 | 1.7997 | 3.863 | 0
4 | Various Performance Improvement related schemes at KGSC, Pophali | MERC/CAPEX/20162017/01018 | 2016-11-17 | 12.9765 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Up gradation of 245 kV CTs at Stage-I&II SY | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.9624 | 2.09 | 2.09 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Up gradation of 245 kV PTs at Stage-I&II SY | MERC/CAPEX/20162017/01018 | 2016-11-17 | 0.40509 | 0.3417 | 0.3417 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.3 | Up gradation of CW system of Stage-I&II Units | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.7099 | 1.4731 | 1.4731 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.4 | Up gradation of Intercom Exchange System between Stage-I&II PH & Admin. Bldg & Staff Colony. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 0.43826 | 0.359 | 0.359 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.5 | Up gradation of 220 kV Breakers at KDPH SY | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.289 | 0.979 | 0.979 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.6 | Procurement of Governing Oil Pumps for Stage-III Units. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.2316 | 0.70174 | 0.70174 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.7 | Up gradation of TG Governing system of Stage-IV Units. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 2.2152 | 2.7472 | 2.7472 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.8 | Up gradation of Numerical Protection system of Stage-IV Units. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 2.8249 | 2.8674 | 2.8674 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01018 | 2016-11-17 | 0.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7 | Replacement of Generator Stator of unit No. 11 (80 MW), Stage III, KGSC Pophali | MERC/CAPEX/20172018/04592 | 2017-11-07 | 22.54 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Replacement of Generator Stator of unit No. 11 (80 MW), Stage III, KGSC Pophali | MERC/CAPEX/20172018/04592 | 2017-11-07 | 22.54 | 16.579 | 0 | 16.579 | 0 | 0 |  |  | 0 | 16.579 | 0 | 0
8 | Procurement of new pelton wheel runners (2 Nos.) for Stage II at KGSC, Pophali | MERC/CAPEX/20172018/04421 | 2017-10-24 | 13.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement of new pelton wheel runners (2 Nos.) for Stage II at KGSC, Pophali | MERC/CAPEX/20172018/04421 | 2017-10-24 | 13.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Implementation of 12 Nos. of various schemes at KGSC, Pophali. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 26.891 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Replacement of UGB (8 Nos), LGB (8 Nos) & Generator air coolers (8 Nos) for Stage-I | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 1.344 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Retrofitting of Generator & Gen-Transformer relays by new numerical protection system at Koyna Dam Power House (KDPH) Koynanagar | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 1.097 | 0.82 | 0 | 0.82 | 0 | 0 |  |  | 0 | 0.82 | 0 | 0
11.3 | Replacement of two 220V Battery chargers with 220V dual float cum boost (60A) battery Charger including DCDB at KDPH, Koynanagar | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.202 | 0.13782 | 0.13782 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.4 | Replacement of 220KV current transformer (54 Nos), Potential transformer (13 Nos),110KV Current Transformer (14 Nos)& Potential Transformer (4 Nos),Stage-III. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 5.281 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.5 | Replacement of Generator Air Cooler (32 Nos), St-III | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 2.413 | 0 | 0 | 0 | 2.0541 | 2.0541 |  |  | 2.0541 | -4e-06 | 2.0541 | 0
11.6 | Replacement of 48 Volt, 1000 AH tubular battery set with 48 Volt, 750AH Plante type battery set at KGSC, Stage-III | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.318 | 0.30942 | 0.30942 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.7 | Replacement of 220V-150AH Battery set with Ni-Cad type, along with standard accessories for UPS scheme at Stage-IV | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.272 | 0.25759 | 0.25759 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.8 | Reliability enhancement of Gas Insulated Switchyard Stage-IV. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 10.472 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.9 | Up-gradation of Vibration system at all units of Stage-IV:Stage-IV, KGSC, Pophali | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 1.443 | 1.01 | 0 | 1.01 | 0.49406 | 1.5041 |  |  | 1.5041 | 0 | 1.443 | 0.06106
11.10 | Replacement of station battery set of 220V, 2000Ah capacity at Stage-IV. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 2.385 | 2.3649 | 2.3649 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.11 | Renovations and modernization of 1500kg capacity passenger cum goods lifts (2 Nos) for KGSC, Stage-IV | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.968 | 0 | 0 | 0 | 0.85208 | 0.85208 |  |  | 0.85208 | 0 | 0.85208 | 0
11.12 | Replacement of existing 3x7.5 TR Air conditioning package units at Stage-I&II control room by new 3x11 TR Air conditioning package units | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.345 | 0.16909 | 0.16909 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.351 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Upgradation of Governing System at Stage-I, KDPH& Stage-III at KGSC, Pophali | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 19.1651 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Up gradation of DIGIPID1500 governing system with new governor (TSLG) for all units of stage-I | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 6.0888 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.2 | Up-gradation of governing system at Koyna Dam Power House (KDPH) Koynanagar | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 2.924 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.3 | Up-gradation of the Governing system at Stage-III & Other Charges (P&F, Insurance etc) | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 9.5523 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Refurbishment of 24 KV Generator Circuit Breakers (ABB Make) for four units at stage-IV, KGSC, Pophali | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 10.5726 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Supply spares for 24KV Generator Circuit Breaker System refurbishment (For 4 Units) | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 6.5702 | 6.5421 | 6.5421 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Supervision charges for 24 KV Generator Circuit Breaker System Unit. Preparation charges, Travel & transportation charges, local conveyance. Lumpsum rental charges of necessary tools & tackles required during O/H work charges | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 3.8704 | 3.8216 | 3.8216 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 0.132 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Up-gradation of Excitation system at Stage-I&II, PLC & SCADA system at Stage-II and DG Set at Stage-IV at KGSC, Pophali | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 9.863 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | Up gradation of Stage-I&II(4x70MW+4x80 MW) Static Semipol Excitation System with Latest Advanced Excitation System | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 9.863 | 0 | 0 | 0 | 4.163 | 0 |  |  | 0 | 4.163 | 0 | 0
15.2 | Up gradation of existing unit PLC and SCADA automation of 4x80 MW Koyna stage-II units | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 4.232 | 0 | 0 | 0 | 3.4 | 0 |  |  | 0 | 3.4 | 0 | 0
15.3 | Up gradation of one 1500 KVA DG set, at KGSC, Stage-IV | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 1.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 1.103 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Repair works in Emergency Valve Tunnel (EVT) and surge well at Stage I/II, KGSC, Pophali | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 28.0371 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Sealing and stabilization of EVT Tunnel left side wall and carven portion of EVT and Ventilation Tunnel. | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 8.307 | 1.5431 | 0 | 1.5431 | 0 | 0 |  |  | 0 | 1.5431 | 0 | 0
17.2 | Structural Strengthening and Sealing Cracks and Cavities in Surge Shaft RCC Staining Wall from inside | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 18.6602 | 0.3875 | 0 | 0.3875 | 0 | 0 |  |  | 0 | 0.3875 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 1.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-8.1 | Advance Multipurpose Fire Tender | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-8.2 | Normal Multipurpose Fire Tender | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Refurbishment of cooling and drainage water system along with replacement of 5 no's of cooling water pumps by new stage -IV KGSC Pophali | MERC/CAPEX/2023-2024/MSPGCL/0201 | 2024-03-21 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Refurbishment of cooling and drainage water system along with replacement of 5 no's of cooling water pumps by new stage -IV KGSC Pophali | MERC/CAPEX/2023-2024/MSPGCL/0201 | 2024-03-21 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0201 | 2024-03-21 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | Refurbishment of GIS T155 as per M4 Schedule at KGSC Stage-IV, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | Refurbishment of GIS T155 as per M4 Schedule at KGSC Stage-IV, Pophali | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20 | Various Civil work as per IB recommendation at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.1 | Various Civil work as per IB recommendation at KGSC, Pophali | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.2 | construction of chainlink caging along entrance of St-I&II, St-III & St-IV | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Stabilization and Mitigation of Landslide Prone Areas at KGSC, Mahagenco, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Stabilization and Mitigation of Landslide Prone Areas | 0 | - | 0 | 0 | 1 | -1 | 0 | 0 |  |  | 0 | -1
21.2 | Construction of retaining wall | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.3 | Dredging river and nallah | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | Various Performance Improvement related schemes for FY 2026-27 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.1 | Supply of New Runner for Francis Turbine 80 MW at KGSC Stage-III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.2 | Supply of 2 Nos. injector along with injector shaft for Stage-I Units (70 MW) at Stage I & II KGSC, Pophali . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.3 | Supply of 1 No. injector for Stage-II Units (80 MW) at Stage I & II KGSC, Pophali . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.4 | Upgradation of AC Chiiler system at Stage I & II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.5 | Design, manufacturing, supply, erection, testing and commissioning of LGB and UGB cooler modifications at KGSC Stage I&II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Replacement of existing Generator transformer of all units (04 x 80 MW) in phase manner (one unit per year) at Stage-III, KGSC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.1 | Replacement of existing Generator transformer of all units (04 x 80 MW) in phase manner (one unit per year) at Stage-III, KGSC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Implementation of PLC & SCADA system (DSC based) for all units (04 x 80 MW) units in phase manner (two unit per year) at Stage-III, KGSC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.1 | Implementation of PLC & SCADA system (DSC based) for all units (04 x 80 MW) units in phase manner (two unit per year) at Stage-III, KGSC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | Various Performance Improvement related schemes for FY 2027-28 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.1 | Refurbishment of Stage-1, Unit No-1,2,3 & 4 PLC System and Implementation of SCADA System. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.2 | Supply, installation & commissioning of New PLC & Centralog system for all four units at St-IV, KGSC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.3 | Supply, installation & commissioning of New excitation system for all four units at St-IV, KGSC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | Various Performance Improvement related schemes for FY 2028-29 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.1 | Upgradation of 11 KV Auxiliary breaker at St-I&II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.2 | Supply of Dry Type, 630 KVA 16 KV / 570 V Single Phase Excitation Transformers (Qty. 12 Nos.) at KGSC Stage-IV, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.3 | Supply, Installation & Commissioning of 16.5 KV / 433 V, 5MVA Unit Auxiliary Transformers (Qty. 02) at KGSC Stage-IV. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.4 | Upgradation of 2.2 KV Auxiliary Breaker with 3.3 KV Breaker along with Auxiliary Transformers at St-I&II. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.5 | Supply of 11KV Cable alongwith Breaker Panels for Auxiliary Supply from 8-Pole Switchyard Stage- I and II to Stage-IV Powerhouse at KGSC Stage-IV, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.6 | Replacement of 220 KV isolator of Stage II bay at 220 KV Stage I & II Switchyard | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | Various Performance Improvement related schemes for FY 2029-30 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.1 | Design Engineering and manufacturing, supply, erection, commissioning & testing of New Pelton runner for Stage-I units (70 MW) at Stage-I&II, KGSC, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.2 | Upgradation of Generator and Generator transformer electromagnetic protection relays with numeric relays for Stage 1 & 2. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.3 | Renovation of old system by full proof modern digital governing system, static/brushless excitation system and generator stator and rotor winding by class 'F' insulation at St-I&II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.4 | Design, manufacturing, supply, erection, testing and commissioning of Hydrostatic lubrication system for Units at KGSC Stage I & II, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.5 | Replacement of CW pumps and Motors along with starter pannel at St-I&II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.6 | Supply of Generator air coolers (16 Nos) for Stage II Units (80 MW) at KGSC, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.7 | Conversion of Stator Core Insulation & Stator Winding from Class ‘B’ to Class ‘F’ for Unit No. 8 (80MW, 11KV, 375RPM, AEG Germany make) of Stage II, KGSC, Pophali on Turnkey Basis. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.8 | Up-gradation of existing 'B' class insulation of Generator stator to 'F' class insulation of 2X18MW Koyna Dam Power House, Koynanagar. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.9 | Supply and replacement of Generator air cooler system by new higher efficiency coolers for 2X18MW Koyna Dam Power House, Koynanagar. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | <Auto Transformer Oil Insulation Test kit (BDV Kit)> | N.A. | - | 0 | 0.03953 | 0.03953 | 0 | 0 | 0 |  |  | 0 | 0
2 | <Man coolers pedestal fans at KGSC,Pophali> | N.A. | - | 0 | 0.034143 | 0.034143 | 0 | 0 | 0 |  |  | 0 | 0
3 | < 5 KV Digital Insulation Tester> | N.A. | - | 0 | 0.029798 | 0.029798 | 0 | 0 | 0 |  |  | 0 | 0
4 | <Split AC Unit,Window AC Unit,Refrigerator,Ped> | N.A. | - | 0 | 0.017857 | 0.017857 | 0 | 0 | 0 |  |  | 0 | 0
5 | <Earth Resistance Tester at ,Pophali. TIC STAGE IV> | N.A. | - | 0 | 0.016839 | 0.016839 | 0 | 0 | 0 |  |  | 0 | 0
6 | <Tools and Tackles at St-IV,KGSC,Pophali> | N.A. | - | 0 | 0.034609 | 0.034609 | 0 | 0 | 0 |  |  | 0 | 0
7 | <New portable Fire Fighting Diesel Pumps for Dewatering> | N.A. | - | 0 | 0.09697 | 0.09697 | 0 | 0 | 0 |  |  | 0 | 0
8 | <Visitors chairs for, Pophali KGSC> | N.A. | - | 0 | 0.033188 | 0.033188 | 0 | 0 | 0 |  |  | 0 | 0
9 | <Installation of new racks inside various/new slotted angle racks > | N.A. | - | 0 | 0.039648 | 0.039648 | 0 | 0 | 0 |  |  | 0 | 0
10 | <Supply of chairs for KGSC, Pophali> | N.A. | - | 0 | 0.044238 | 0.044238 | 0 | 0 | 0 |  |  | 0 | 0
11 | <Laser Jet NetwoksPrinters at KGSC, Pophali> | N.A. | - | 0 | 0.084075 | 0.084075 | 0 | 0 | 0 |  |  | 0 | 0
12 | <Night Vision Binoculars> | N.A. | - | 0 | 0.023411 | 0.023411 | 0 | 0 | 0 |  |  | 0 | 0
13 | <TATA Star Bus-32 seater LCV MH08-9358> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | <TATA Star Bus-32 seater LCV MH08-9359> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | <Vehicle No.MH 08-9401 TATA Star Bus 32 seater> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | <Not in use DCM Toyato Bus MH-1> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | <Not in use DCM Toyato Mini Bus> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | <Digital Multimeters, Clamp Meter & Insulation resistance tester for TIC, Stage I&II, Pophali> | N.A. | - | 0 | 0.028928 | 0.028928 | 0 | 0 | 0 |  |  | 0 | 0
19 | <Transformer Winding resistance measurement kit at Stage-III, Alore> | N.A. | - | 0 | 0.024338 | 0.024338 | 0 | 0 | 0 |  |  | 0 | 0
20 | <Multifunc A3 Scanner & all in one A4 laser printer Technical Purchase , Account Section, H.R. ,MPD> | N.A. | - | 0 | 0.032521 | 0.032521 | 0 | 0 | 0 |  |  | 0 | 0
21 | <Temperature Calibrator at St-IV, KGSC,Pophali> | N.A. | - | 0 | 0.012272 | 0.012272 | 0 | 0 | 0 |  |  | 0 | 0
22 | < 1 no. new departmental car Maruti Sweft Desire for conveyance of Chief Engr> | N.A. | - | 0 | 0.077924 | 0.077924 | 0 | 0 | 0 |  |  | 0 | 0
23 | <Hitachi A/c Two.NO.VIP Rest House> | N.A. | - | 0 | 0.008 | 0.008 | 0 | 0 | 0 |  |  | 0 | 0
24 | <Inverter Split AC Unit, Desert Coolers Water Coolers for KGSC, Pophali> | N.A. | - | 0 | 0.0070799 | 0.0070799 | 0 | 0 | 0 |  |  | 0 | 0
25 | <Advanced ISDN EPABX system for Koyna Generating St ntercom Telephone Advanced ISDN EPABX system for Koyna Generating Station Complex> | N.A. | - | 0 | 0.029645 | 0.029645 | 0 | 0 | 0 |  |  | 0 | 0
26 | <TATA Sumo MH-14/9763 1 No> | N.A. | - | 0 | 0.041197 | 0.041197 | 0 | 0 | 0 |  |  | 0 | 0
27 | <Ambulance TATA make MH-31/4475 1 No> | N.A. | - | 0 | 0.036143 | 0.036143 | 0 | 0 | 0 |  |  | 0 | 0
28 | <Supply of 1 No of Ambulance Vane for Pophali> | N.A. | - | 0 | 0.14883 | 0.14883 | 0 | 0 | 0 |  |  | 0 | 0
29 | <Supply of 1 No of Ambulance Vane for Pophali> | N.A. | - | 0 | 0.14883 | 0.14883 | 0 | 0 | 0 |  |  | 0 | 0
30 | <HITACHI Make 2 TR non inverter split Air conditioner> | N.A. | - | 0 | 0.16739 | 0.16739 | 0 | 0 | 0 |  |  | 0 | 0
31 | <250 KVA D.G. Set Model KG1-250WS> | N.A. | - | 0 | 0.19222 | 0.19222 | 0 | 0 | 0 |  |  | 0 | 0
32 | <Dell laptops at KGSC Pophali> | N.A. | - | 0 | 0.0156 | 0.0156 | 0 | 0 | 0 |  |  | 0 | 0
33 | <A.C. Plant chiller 515 to 535 TRx2 at kgsc,Pophali> | N.A. | - | 0 | 2.1144 | 2.1144 | 0 | 0 | 0 |  |  | 0 | 0
34 | <Supply of RDP make Computers at KGSC> | N.A. | - | 0 | 0.43135 | 0.43135 | 0 | 0 | 0 |  |  | 0 | 0
35 | <Welding Machine for KDPH> | N.A. | - | 0 | 0.001039 | 0.001039 | 0 | 0 | 0 |  |  | 0 | 0
36 | <Material handling trolley for Majot store> | N.A. | - | 0 | 0.0014198 | 0.0014198 | 0 | 0 | 0 |  |  | 0 | 0
37 | <Canon LiDe 300 IN Scanner> | N.A. | - | 0 | 0.00048 | 0.00048 | 0 | 0 | 0 |  |  | 0 | 0
38 | <Supply of Pedestal fan at KDPH> | N.A. | - | 0 | 0.015 | 0.015 | 0 | 0 | 0 |  |  | 0 | 0
39 | <Supply of Refrigerator 290 LTR double door capacity> | N.A. | - | 0 | 0.0022 | 0.0022 | 0 | 0 | 0 |  |  | 0 | 0
40 | <Supply of Refrigerator 290 LTR double door capacity> | N.A. | - | 0 | 0.0022 | 0.0022 | 0 | 0 | 0 |  |  | 0 | 0
41 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.007 | 0.007 | 0 | 0 | 0 |  |  | 0 | 0
42 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.0035 | 0.0035 | 0 | 0 | 0 |  |  | 0 | 0
43 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.0035 | 0.0035 | 0 | 0 | 0 |  |  | 0 | 0
44 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.0035 | 0.0035 | 0 | 0 | 0 |  |  | 0 | 0
45 | <Redmi 10 prime Mobile Black for Chief Engineer> | N.A. | - | 0 | 0.0015 | 0.0015 | 0 | 0 | 0 |  |  | 0 | 0
46 | <TATA Sumo MH-14/9763 1 No> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47 | <Ambulance TATA make MH-31/4475 1 No> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48 | <Supply of Two Post Lift (4 Ton) for Vehicle Maint.> | N.A. | - | 0 | 0.014396 | 0.014396 | 0 | 0 | 0 |  |  | 0 | 0
49 | Supply,Installation, commissioning and testing of 415V, 3 Phase diesel generating setof 125 KVA capacity for Admin building emergency power supply backup at KGSC,Pophali. | N.A. | - | 0 | 0.0995 | 0.0995 | 0 | 0 | 0 |  |  | 0 | 0
50 | Design,Manufacturing, supply erriction and commissioning of 60 MT surface mounted (pit type/ platform type) weighbridge at major stores 'c' pophali | N.A. | - | 0 | 0.21577 | 0.21577 | 0 | 0 | 0 |  |  | 0 | 0
51 | Supply of Hydraulically operated manual stacker for Material Handling at Major Store "C", KGSC, Pophali | N.A. | - | 0 | 0.00524 | 0.00524 | 0 | 0 | 0 |  |  | 0 | 0
52 | Supply of Indef makes Chain Pulley Blocks | N.A. | - | 0 | 0.011505 | 0.011505 | 0 | 0 | 0 |  |  | 0 | 0
53 | Supply of Motwane Make ‘Digital Multimeter and AC Multimeter | N.A. | - | 0 | 0.018458 | 0.018458 | 0 | 0 | 0 |  |  | 0 | 0
54 | Supply 1 Ton split AC Daiken make for control room cabin Operation Stage III | N.A. | - | 0 | 0.00396 | 0.00396 | 0 | 0 | 0 |  |  | 0 | 0
55 | Emer Rescue cum Multipurpose Fire Tender | N.A. | - | 0 | 2.0039 | 2.0039 | 0 | 0 | 0 |  |  | 0 | 0
56 | Procurement of portable chairs for training sub centre | N.A. | - | 0 | 0.01308 | 0.01308 | 0 | 0 | 0 |  |  | 0 | 0
57 | Procurement of portable computer tables | N.A. | - | 0 | 0.0033449 | 0.0033449 | 0 | 0 | 0 |  |  | 0 | 0
58 | Purchase of High back chair (3 Nos.) in conferenc hall | N.A. | - | 0 | 0.0044014 | 0.0044014 | 0 | 0 | 0 |  |  | 0 | 0
59 | Supply of Water Purifier at MSPGCL KGSC Pophali. | N.A. | - | 0 | 0.005 | 0.005 | 0 | 0 | 0 |  |  | 0 | 0
60 | Interactive Digital LV SCREEN 6.56 FT X 3.28 FT | N.A. | - | 0 | 0.01295 | 0.01295 | 0 | 0 | 0 |  |  | 0 | 0
61 | Network Attached Storage Server at KGSC, Pophali. | N.A. | - | 0 | 0.023333 | 0.023333 | 0 | 0 | 0 |  |  | 0 | 0
62 | Supply of A4 Printer at KGSC, Pophali. | N.A. | - | 0 | 0.0099995 | 0.0099995 | 0 | 0 | 0 |  |  | 0 | 0
63 | Supply of A4 Scanner, A3 & MF Printer at KGSC, Pop | N.A. | - | 0 | 0.0586 | 0.0586 | 0 | 0 | 0 |  |  | 0 | 0
64 | Supply of Various Hard Disks for Network Attached | N.A. | - | 0 | 0.021806 | 0.021806 | 0 | 0 | 0 |  |  | 0 | 0
65 | Supply of Video conference Microphone at KGSC, | N.A. | - | 0 | 0.0021512 | 0.0021512 | 0 | 0 | 0 |  |  | 0 | 0
66 | Supply of Video Conference Screen at KGSC Pophali | N.A. | - | 0 | 0.02 | 0.02 | 0 | 0 | 0 |  |  | 0 | 0
67 | Supply of Video conference Screen at KGSC, Pophali | N.A. | - | 0 | 0.0109 | 0.0109 | 0 | 0 | 0 |  |  | 0 | 0
68 | Supply of Kelvinator / Godrej / Croma Make Refrigerator | N.A. | - | 0 | 0.010932 | 0.010932 | 0 | 0 | 0 |  |  | 0 | 0
69 | supply of Bosch make High Pressure Washer at Mecha | N.A. | - | 0 | 0 | 0 | 0 | 0.0020649 | 0.0020649 |  |  | 0.0020649 | 0
70 | Supply of Pneumatic Tools for Mechanical Maintenan | N.A. | - | 0 | 0 | 0 | 0 | 0.035259 | 0.035259 |  |  | 0.035259 | 0
72 | Low BACK Revolving Chairs 45 No & Desk Chair 2 No | N.A. | - | 0 | 0 | 0 | 0 | 0.020945 | 0.020945 |  |  | 0.020945 | 0
73 | Supply of Tables at KGSC | N.A. | - | 0 | 0 | 0 | 0 | 0.037339 | 0.037339 |  |  | 0.037339 | 0
74 | Supply of Visitor Chairs & Office chairs at KGSC, | N.A. | - | 0 | 0 | 0 | 0 | 0.033201 | 0.033201 |  |  | 0.033201 | 0
75 | water purifier for colony electrical maintenance | N.A. | - | 0 | 0 | 0 | 0 | 0.00174 | 0.00174 |  |  | 0.00174 | 0
76 | Projectors and Motorized Projector Screens (2+2) | N.A. | - | 0 | 0 | 0 | 0 | 0.03481 | 0.03481 |  |  | 0.03481 | 0
77 | Acer make Computers at KGSC Pophali.21 No. | N.A. | - | 0 | 0 | 0 | 0 | 0.119 | 0.119 |  |  | 0.119 | 0
78 | Acer make Laptops at KGSC Pophali. | N.A. | - | 0 | 0 | 0 | 0 | 0.030088 | 0.030088 |  |  | 0.030088 | 0
79 | APS Smart UPS Xl 2200 VA RM 3U 230 | N.A. | - | 0 | 0 | 0 | 0 | 0.015983 | 0.015983 |  |  | 0.015983 | 0
80 | BATRY 12V 75 AH BATTREY 11 PLATE | N.A. | - | 0 | 0 | 0 | 0 | 0.017629 | 0.017629 |  |  | 0.017629 | 0
81 | Supply & installation of IP Camera System and network spare | N.A. | - | 0 | 0 | 0 | 0 | 0.025807 | 0.025807 |  |  | 0.025807 | 0
82 | Gym Equipments at MSPGCL Recreation club , 33 Item | N.A. | - | 0 | 0 | 0 | 0 | 0.047834 | 0.047834 |  |  | 0.047834 | 0
0 | Non-DPR schemes (3 Nos) for FY 2024-25 at KGSC Pophali | Board Resolution No-MSPGCL/BM-219/Item 219.7 dtd.24.07.2023 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
83 | Up-gradation of thyristor based 48V Battery Chargers (4 nos) by SMPS Microprocessor based dual float cum boost Battery Chargers at Stage-III, Stage-I&II and KDPH at KGSC, Pophali | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
84 | Up-gradation of thyristor based 220V Battery Chargers (4 nos) by SMPS Microprocessor based dual float cum boost Battery Chargers at Stage-III and Stage-I&II at KGSC, Pophali | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
85 | Retrofitting of Generator and Gen. Transformer protection relay by Numerical protection system at KGSC stage III, Alore | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Non-DPR schemes (2 Nos) for FY 2025-26 at KGSC Pophali | Yet Not Submitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
86 | Supply, Erection, Commissioning & Retrofitting of 220 VDC Ni-cadmium type Battery set (4 Nos) having different ampere hour capacity at Stage-I&II and Stage-IV | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
87 | Supply, Erection, Commissioning & Retrofitting of 48VDC, 300AH Ni-cadmium type Battery set at Stage-I&II switchyard | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 82.3863 | 61.247 | 21.1393 | 16.0786 | 9.5256 | 0 | 0 | 9.5256 | 27.6923
FY 2024-25
a) DPR Schemes
(i) Submitted to MERC
1 | Various improvement schemes at Pophali Hydro Power Station | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 11.9001 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | ALSPA HMI Series 6 Centralog System | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 6.8555 | 7.8386 | 7.8386 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | 1 X 525 Tr chiller unit | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 1.23 | 1.15 | 1.15 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Micom P343 Numerical generator protection relay with 24 DI & 24 DO with CLIO input. (5 Nos) | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 1.4675 | 1.474 | 1.474 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.4 | Security Building at Stage-IV | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 0.16446 | 0.18377 | 0.18377 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.5 | Construction of recreation club building | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 1.8204 | 2.1946 | 2.1946 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.6 | Security Building for Stage-IV at EVT | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 0.22776 | 0.25961 | 0.25961 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 0.1344 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Various DPR Schemes for Civil Section, KGSC Pophali | MERC/CAPEX/20152016/00907 | 2015-11-05 | 21.201 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Providing Road Network at KGSC, Pophali | MERC/CAPEX/20152016/00907 | 2015-11-05 | 7.776 | 7.0182 | 7.0182 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.2 | Modernisation & Refurbishing of Residential Complex | MERC/CAPEX/20152016/00907 | 2015-11-05 | 8.985 | 8.9365 | 8.9365 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.3 | Water Supply & Sanitory Works | MERC/CAPEX/20152016/00907 | 2015-11-05 | 4.44 | 5.9018 | 4.1022 | 1.7997 | 0 | 0 |  |  | 0 | 1.7997 | 0 | 0
4 | Various Performance Improvement related schemes at KGSC, Pophali | MERC/CAPEX/20162017/01018 | 2016-11-17 | 12.9765 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Up gradation of 245 kV CTs at Stage-I&II SY | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.9624 | 2.09 | 2.09 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Up gradation of 245 kV PTs at Stage-I&II SY | MERC/CAPEX/20162017/01018 | 2016-11-17 | 0.40509 | 0.3417 | 0.3417 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.3 | Up gradation of CW system of Stage-I&II Units | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.7099 | 1.4731 | 1.4731 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.4 | Up gradation of Intercom Exchange System between Stage-I&II PH & Admin. Bldg & Staff Colony. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 0.43826 | 0.359 | 0.359 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.5 | Up gradation of 220 kV Breakers at KDPH SY | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.289 | 0.979 | 0.979 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.6 | Procurement of Governing Oil Pumps for Stage-III Units. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.2316 | 0.70174 | 0.70174 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.7 | Up gradation of TG Governing system of Stage-IV Units. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 2.2152 | 2.7472 | 2.7472 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.8 | Up gradation of Numerical Protection system of Stage-IV Units. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 2.8249 | 2.8674 | 2.8674 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01018 | 2016-11-17 | 0.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7 | Replacement of Generator Stator of unit No. 11 (80 MW), Stage III, KGSC Pophali | MERC/CAPEX/20172018/04592 | 2017-11-07 | 22.54 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Replacement of Generator Stator of unit No. 11 (80 MW), Stage III, KGSC Pophali | MERC/CAPEX/20172018/04592 | 2017-11-07 | 22.54 | 16.579 | 0 | 16.579 | 2.83 | 19.41 |  |  | 19.41 | -0.001 | 19.41 | 0
8 | Procurement of new pelton wheel runners (2 Nos.) for Stage II at KGSC, Pophali | MERC/CAPEX/20172018/04421 | 2017-10-24 | 13.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement of new pelton wheel runners (2 Nos.) for Stage II at KGSC, Pophali | MERC/CAPEX/20172018/04421 | 2017-10-24 | 13.07 | 0 | 0 | 0 | 5.19 | - |  |  | 0 | 5.19 | 0 | 0
11 | Implementation of 12 Nos. of various schemes at KGSC, Pophali. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 26.891 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Replacement of UGB (8 Nos), LGB (8 Nos) & Generator air coolers (8 Nos) for Stage-I | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 1.344 | 0 | 0 | 0 | 0.85 | 0.85 |  |  | 0.85 | 0 | 0.85 | 0
11.2 | Retrofitting of Generator & Gen-Transformer relays by new numerical protection system at Koyna Dam Power House (KDPH) Koynanagar | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 1.097 | 0.82 | 0 | 0.82 | 0.26 | 1.08 |  |  | 1.08 | 0 | 1.08 | 0
11.3 | Replacement of two 220V Battery chargers with 220V dual float cum boost (60A) battery Charger including DCDB at KDPH, Koynanagar | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.202 | 0.13782 | 0.13782 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.4 | Replacement of 220KV current transformer (54 Nos), Potential transformer (13 Nos),110KV Current Transformer (14 Nos)& Potential Transformer (4 Nos),Stage-III. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 5.281 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.5 | Replacement of Generator Air Cooler (32 Nos), St-III | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 2.413 | 2.0541 | 2.0541 | -4e-06 | 0 | 0 |  |  | 0 | -4e-06 | 0 | 0
11.6 | Replacement of 48 Volt, 1000 AH tubular battery set with 48 Volt, 750AH Plante type battery set at KGSC, Stage-III | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.318 | 0.30942 | 0.30942 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.7 | Replacement of 220V-150AH Battery set with Ni-Cad type, along with standard accessories for UPS scheme at Stage-IV | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.272 | 0.25759 | 0.25759 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.8 | Reliability enhancement of Gas Insulated Switchyard Stage-IV. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 10.472 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.9 | Up-gradation of Vibration system at all units of Stage-IV:Stage-IV, KGSC, Pophali | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 1.443 | 1.5041 | 1.5041 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.10 | Replacement of station battery set of 220V, 2000Ah capacity at Stage-IV. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 2.385 | 2.3649 | 2.3649 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.11 | Renovations and modernization of 1500kg capacity passenger cum goods lifts (2 Nos) for KGSC, Stage-IV | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.968 | 0.85208 | 0.85208 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.12 | Replacement of existing 3x7.5 TR Air conditioning package units at Stage-I&II control room by new 3x11 TR Air conditioning package units | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.345 | 0.16909 | 0.16909 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.351 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Upgradation of Governing System at Stage-I, KDPH& Stage-III at KGSC, Pophali | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 19.1651 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Up gradation of DIGIPID1500 governing system with new governor (TSLG) for all units of stage-I | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 6.0888 | 0 | 0 | 0 | 3.89 | 3.89 |  |  | 3.89 | 0 | 3.89 | 0
12.2 | Up-gradation of governing system at Koyna Dam Power House (KDPH) Koynanagar | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 2.924 | 0 | 0 | 0 | 1.41 | 1.41 |  |  | 1.41 | 0 | 1.41 | 0
12.3 | Up-gradation of the Governing system at Stage-III & Other Charges (P&F, Insurance etc) | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 9.5523 | 0 | 0 | 0 | 4.6 | 4.6 |  |  | 4.6 | 0 | 4.6 | 0
0 | IDC | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Refurbishment of 24 KV Generator Circuit Breakers (ABB Make) for four units at stage-IV, KGSC, Pophali | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 10.5726 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Supply spares for 24KV Generator Circuit Breaker System refurbishment (For 4 Units) | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 6.5702 | 6.5421 | 6.5421 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Supervision charges for 24 KV Generator Circuit Breaker System Unit. Preparation charges, Travel & transportation charges, local conveyance. Lumpsum rental charges of necessary tools & tackles required during O/H work charges | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 3.8704 | 3.8216 | 3.8216 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 0.132 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Up-gradation of Excitation system at Stage-I&II, PLC & SCADA system at Stage-II and DG Set at Stage-IV at KGSC, Pophali | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 9.863 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | Up gradation of Stage-I&II(4x70MW+4x80 MW) Static Semipol Excitation System with Latest Advanced Excitation System | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 9.863 | 4.163 | 0 | 4.163 | 1.6 | 5.76 |  |  | 5.76 | 0.003 | 5.76 | 0
15.2 | Up gradation of existing unit PLC and SCADA automation of 4x80 MW Koyna stage-II units | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 4.232 | 3.4 | 0 | 3.4 | 0.9 | 4.3 |  |  | 4.3 | 0 | 4.232 | 0.068
15.3 | Up gradation of one 1500 KVA DG set, at KGSC, Stage-IV | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 1.6 | 0 | 0 | 0 | 1.81 | 1.81 |  |  | 1.81 | 0 | 1.6 | 0.21
0 | IDC | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 1.103 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Repair works in Emergency Valve Tunnel (EVT) and surge well at Stage I/II, KGSC, Pophali | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 28.0371 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Sealing and stabilization of EVT Tunnel left side wall and carven portion of EVT and Ventilation Tunnel. | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 8.307 | 1.5431 | 0 | 1.5431 | 5.61 | 5.61 |  |  | 5.61 | 1.5431 | 5.61 | 0
17.2 | Structural Strengthening and Sealing Cracks and Cavities in Surge Shaft RCC Staining Wall from inside | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 18.6602 | 0.3875 | 0 | 0.3875 | 0 | 0 |  |  | 0 | 0.3875 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 1.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-8.1 | Advance Multipurpose Fire Tender | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-8.2 | Normal Multipurpose Fire Tender | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Refurbishment of cooling and drainage water system along with replacement of 5 no's of cooling water pumps by new stage -IV KGSC Pophali | MERC/CAPEX/2023-2024/MSPGCL/0201 | 2024-03-21 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Refurbishment of cooling and drainage water system along with replacement of 5 no's of cooling water pumps by new stage -IV KGSC Pophali | MERC/CAPEX/2023-2024/MSPGCL/0201 | 2024-03-21 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0201 | 2024-03-21 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[8 empty] | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | Refurbishment of GIS T155 as per M4 Schedule at KGSC Stage-IV, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | Refurbishment of GIS T155 as per M4 Schedule at KGSC Stage-IV, Pophali | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20 | Various Civil work as per IB recommendation at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.1 | Various Civil work as per IB recommendation at KGSC, Pophali | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.2 | construction of chainlink caging along entrance of St-I&II, St-III & St-IV | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Stabilization and Mitigation of Landslide Prone Areas at KGSC, Mahagenco, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Stabilization and Mitigation of Landslide Prone Areas | 0 | - | 0 | 0 | 1 | -1 | 0 | 0 |  |  | 0 | -1
21.2 | Construction of retaining wall | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.3 | Dredging river and nallah | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | Various Performance Improvement related schemes for FY 2026-27 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.1 | Supply of New Runner for Francis Turbine 80 MW at KGSC Stage-III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.2 | Supply of 2 Nos. injector along with injector shaft for Stage-I Units (70 MW) at Stage I & II KGSC, Pophali . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.3 | Supply of 1 No. injector for Stage-II Units (80 MW) at Stage I & II KGSC, Pophali . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.4 | Upgradation of AC Chiiler system at Stage I & II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.5 | Design, manufacturing, supply, erection, testing and commissioning of LGB and UGB cooler modifications at KGSC Stage I&II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Replacement of existing Generator transformer of all units (04 x 80 MW) in phase manner (one unit per year) at Stage-III, KGSC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.1 | Replacement of existing Generator transformer of all units (04 x 80 MW) in phase manner (one unit per year) at Stage-III, KGSC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Implementation of PLC & SCADA system (DSC based) for all units (04 x 80 MW) units in phase manner (two unit per year) at Stage-III, KGSC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.1 | Implementation of PLC & SCADA system (DSC based) for all units (04 x 80 MW) units in phase manner (two unit per year) at Stage-III, KGSC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | Various Performance Improvement related schemes for FY 2027-28 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.1 | Refurbishment of Stage-1, Unit No-1,2,3 & 4 PLC System and Implementation of SCADA System. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.2 | Supply, installation & commissioning of New PLC & Centralog system for all four units at St-IV, KGSC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.3 | Supply, installation & commissioning of New excitation system for all four units at St-IV, KGSC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | Various Performance Improvement related schemes for FY 2028-29 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.1 | Upgradation of 11 KV Auxiliary breaker at St-I&II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.2 | Supply of Dry Type, 630 KVA 16 KV / 570 V Single Phase Excitation Transformers (Qty. 12 Nos.) at KGSC Stage-IV, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.3 | Supply, Installation & Commissioning of 16.5 KV / 433 V, 5MVA Unit Auxiliary Transformers (Qty. 02) at KGSC Stage-IV. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.4 | Upgradation of 2.2 KV Auxiliary Breaker with 3.3 KV Breaker along with Auxiliary Transformers at St-I&II. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.5 | Supply of 11KV Cable alongwith Breaker Panels for Auxiliary Supply from 8-Pole Switchyard Stage- I and II to Stage-IV Powerhouse at KGSC Stage-IV, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.6 | Replacement of 220 KV isolator of Stage II bay at 220 KV Stage I & II Switchyard | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | Various Performance Improvement related schemes for FY 2029-30 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.1 | Design Engineering and manufacturing, supply, erection, commissioning & testing of New Pelton runner for Stage-I units (70 MW) at Stage-I&II, KGSC, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.2 | Upgradation of Generator and Generator transformer electromagnetic protection relays with numeric relays for Stage 1 & 2. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.3 | Renovation of old system by full proof modern digital governing system, static/brushless excitation system and generator stator and rotor winding by class 'F' insulation at St-I&II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.4 | Design, manufacturing, supply, erection, testing and commissioning of Hydrostatic lubrication system for Units at KGSC Stage I & II, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.5 | Replacement of CW pumps and Motors along with starter pannel at St-I&II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.6 | Supply of Generator air coolers (16 Nos) for Stage II Units (80 MW) at KGSC, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.7 | Conversion of Stator Core Insulation & Stator Winding from Class ‘B’ to Class ‘F’ for Unit No. 8 (80MW, 11KV, 375RPM, AEG Germany make) of Stage II, KGSC, Pophali on Turnkey Basis. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.8 | Up-gradation of existing 'B' class insulation of Generator stator to 'F' class insulation of 2X18MW Koyna Dam Power House, Koynanagar. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.9 | Supply and replacement of Generator air cooler system by new higher efficiency coolers for 2X18MW Koyna Dam Power House, Koynanagar. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | <Auto Transformer Oil Insulation Test kit (BDV Kit)> | N.A. | - | 0 | 0.03953 | 0.03953 | 0 | 0 | 0 |  |  | 0 | 0
2 | <Man coolers pedestal fans at KGSC,Pophali> | N.A. | - | 0 | 0.034143 | 0.034143 | 0 | 0 | 0 |  |  | 0 | 0
3 | < 5 KV Digital Insulation Tester> | N.A. | - | 0 | 0.029798 | 0.029798 | 0 | 0 | 0 |  |  | 0 | 0
4 | <Split AC Unit,Window AC Unit,Refrigerator,Ped> | N.A. | - | 0 | 0.017857 | 0.017857 | 0 | 0 | 0 |  |  | 0 | 0
5 | <Earth Resistance Tester at ,Pophali. TIC STAGE IV> | N.A. | - | 0 | 0.016839 | 0.016839 | 0 | 0 | 0 |  |  | 0 | 0
6 | <Tools and Tackles at St-IV,KGSC,Pophali> | N.A. | - | 0 | 0.034609 | 0.034609 | 0 | 0 | 0 |  |  | 0 | 0
7 | <New portable Fire Fighting Diesel Pumps for Dewatering> | N.A. | - | 0 | 0.09697 | 0.09697 | 0 | 0 | 0 |  |  | 0 | 0
8 | <Visitors chairs for, Pophali KGSC> | N.A. | - | 0 | 0.033188 | 0.033188 | 0 | 0 | 0 |  |  | 0 | 0
9 | <Installation of new racks inside various/new slotted angle racks > | N.A. | - | 0 | 0.039648 | 0.039648 | 0 | 0 | 0 |  |  | 0 | 0
10 | <Supply of chairs for KGSC, Pophali> | N.A. | - | 0 | 0.044238 | 0.044238 | 0 | 0 | 0 |  |  | 0 | 0
11 | <Laser Jet NetwoksPrinters at KGSC, Pophali> | N.A. | - | 0 | 0.084075 | 0.084075 | 0 | 0 | 0 |  |  | 0 | 0
12 | <Night Vision Binoculars> | N.A. | - | 0 | 0.023411 | 0.023411 | 0 | 0 | 0 |  |  | 0 | 0
13 | <TATA Star Bus-32 seater LCV MH08-9358> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | <TATA Star Bus-32 seater LCV MH08-9359> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | <Vehicle No.MH 08-9401 TATA Star Bus 32 seater> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | <Not in use DCM Toyato Bus MH-1> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | <Not in use DCM Toyato Mini Bus> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | <Digital Multimeters, Clamp Meter & Insulation resistance tester for TIC, Stage I&II, Pophali> | N.A. | - | 0 | 0.028928 | 0.028928 | 0 | 0 | 0 |  |  | 0 | 0
19 | <Transformer Winding resistance measurement kit at Stage-III, Alore> | N.A. | - | 0 | 0.024338 | 0.024338 | 0 | 0 | 0 |  |  | 0 | 0
20 | <Multifunc A3 Scanner & all in one A4 laser printer Technical Purchase , Account Section, H.R. ,MPD> | N.A. | - | 0 | 0.032521 | 0.032521 | 0 | 0 | 0 |  |  | 0 | 0
21 | <Temperature Calibrator at St-IV, KGSC,Pophali> | N.A. | - | 0 | 0.012272 | 0.012272 | 0 | 0 | 0 |  |  | 0 | 0
22 | < 1 no. new departmental car Maruti Sweft Desire for conveyance of Chief Engr> | N.A. | - | 0 | 0.077924 | 0.077924 | 0 | 0 | 0 |  |  | 0 | 0
23 | <Hitachi A/c Two.NO.VIP Rest House> | N.A. | - | 0 | 0.008 | 0.008 | 0 | 0 | 0 |  |  | 0 | 0
24 | <Inverter Split AC Unit, Desert Coolers Water Coolers for KGSC, Pophali> | N.A. | - | 0 | 0.0070799 | 0.0070799 | 0 | 0 | 0 |  |  | 0 | 0
25 | <Advanced ISDN EPABX system for Koyna Generating St ntercom Telephone Advanced ISDN EPABX system for Koyna Generating Station Complex> | N.A. | - | 0 | 0.029645 | 0.029645 | 0 | 0 | 0 |  |  | 0 | 0
26 | <TATA Sumo MH-14/9763 1 No> | N.A. | - | 0 | 0.041197 | 0.041197 | 0 | 0 | 0 |  |  | 0 | 0
27 | <Ambulance TATA make MH-31/4475 1 No> | N.A. | - | 0 | 0.036143 | 0.036143 | 0 | 0 | 0 |  |  | 0 | 0
28 | <Supply of 1 No of Ambulance Vane for Pophali> | N.A. | - | 0 | 0.14883 | 0.14883 | 0 | 0 | 0 |  |  | 0 | 0
29 | <Supply of 1 No of Ambulance Vane for Pophali> | N.A. | - | 0 | 0.14883 | 0.14883 | 0 | 0 | 0 |  |  | 0 | 0
30 | <HITACHI Make 2 TR non inverter split Air conditioner> | N.A. | - | 0 | 0.16739 | 0.16739 | 0 | 0 | 0 |  |  | 0 | 0
31 | <250 KVA D.G. Set Model KG1-250WS> | N.A. | - | 0 | 0.19222 | 0.19222 | 0 | 0 | 0 |  |  | 0 | 0
32 | <Dell laptops at KGSC Pophali> | N.A. | - | 0 | 0.0156 | 0.0156 | 0 | 0 | 0 |  |  | 0 | 0
33 | <A.C. Plant chiller 515 to 535 TRx2 at kgsc,Pophali> | N.A. | - | 0 | 2.1144 | 2.1144 | 0 | 0 | 0 |  |  | 0 | 0
34 | <Supply of RDP make Computers at KGSC> | N.A. | - | 0 | 0.43135 | 0.43135 | 0 | 0 | 0 |  |  | 0 | 0
35 | <Welding Machine for KDPH> | N.A. | - | 0 | 0.001039 | 0.001039 | 0 | 0 | 0 |  |  | 0 | 0
36 | <Material handling trolley for Majot store> | N.A. | - | 0 | 0.0014198 | 0.0014198 | 0 | 0 | 0 |  |  | 0 | 0
37 | <Canon LiDe 300 IN Scanner> | N.A. | - | 0 | 0.00048 | 0.00048 | 0 | 0 | 0 |  |  | 0 | 0
38 | <Supply of Pedestal fan at KDPH> | N.A. | - | 0 | 0.015 | 0.015 | 0 | 0 | 0 |  |  | 0 | 0
39 | <Supply of Refrigerator 290 LTR double door capacity> | N.A. | - | 0 | 0.0022 | 0.0022 | 0 | 0 | 0 |  |  | 0 | 0
40 | <Supply of Refrigerator 290 LTR double door capacity> | N.A. | - | 0 | 0.0022 | 0.0022 | 0 | 0 | 0 |  |  | 0 | 0
41 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.007 | 0.007 | 0 | 0 | 0 |  |  | 0 | 0
42 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.0035 | 0.0035 | 0 | 0 | 0 |  |  | 0 | 0
43 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.0035 | 0.0035 | 0 | 0 | 0 |  |  | 0 | 0
44 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.0035 | 0.0035 | 0 | 0 | 0 |  |  | 0 | 0
45 | <Redmi 10 prime Mobile Black for Chief Engineer> | N.A. | - | 0 | 0.0015 | 0.0015 | 0 | 0 | 0 |  |  | 0 | 0
46 | <TATA Sumo MH-14/9763 1 No> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47 | <Ambulance TATA make MH-31/4475 1 No> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48 | <Supply of Two Post Lift (4 Ton) for Vehicle Maint.> | N.A. | - | 0 | 0.014396 | 0.014396 | 0 | 0 | 0 |  |  | 0 | 0
49 | Supply,Installation, commissioning and testing of 415V, 3 Phase diesel generating setof 125 KVA capacity for Admin building emergency power supply backup at KGSC,Pophali. | N.A. | - | 0 | 0.0995 | 0.0995 | 0 | 0 | 0 |  |  | 0 | 0
50 | Design,Manufacturing, supply erriction and commissioning of 60 MT surface mounted (pit type/ platform type) weighbridge at major stores 'c' pophali | N.A. | - | 0 | 0.21577 | 0.21577 | 0 | 0 | 0 |  |  | 0 | 0
51 | Supply of Hydraulically operated manual stacker for Material Handling at Major Store "C", KGSC, Pophali | N.A. | - | 0 | 0.00524 | 0.00524 | 0 | 0 | 0 |  |  | 0 | 0
52 | Supply of Indef makes Chain Pulley Blocks | N.A. | - | 0 | 0.011505 | 0.011505 | 0 | 0 | 0 |  |  | 0 | 0
53 | Supply of Motwane Make ‘Digital Multimeter and AC Multimeter | N.A. | - | 0 | 0.018458 | 0.018458 | 0 | 0 | 0 |  |  | 0 | 0
54 | Supply 1 Ton split AC Daiken make for control room cabin Operation Stage III | N.A. | - | 0 | 0.00396 | 0.00396 | 0 | 0 | 0 |  |  | 0 | 0
55 | Emer Rescue cum Multipurpose Fire Tender | N.A. | - | 0 | 2.0039 | 2.0039 | 0 | 0 | 0 |  |  | 0 | 0
56 | Procurement of portable chairs for training sub centre | N.A. | - | 0 | 0.01308 | 0.01308 | 0 | 0 | 0 |  |  | 0 | 0
57 | Procurement of portable computer tables | N.A. | - | 0 | 0.0033449 | 0.0033449 | 0 | 0 | 0 |  |  | 0 | 0
58 | Purchase of High back chair (3 Nos.) in conferenc hall | N.A. | - | 0 | 0.0044014 | 0.0044014 | 0 | 0 | 0 |  |  | 0 | 0
59 | Supply of Water Purifier at MSPGCL KGSC Pophali. | N.A. | - | 0 | 0.005 | 0.005 | 0 | 0 | 0 |  |  | 0 | 0
60 | Interactive Digital LV SCREEN 6.56 FT X 3.28 FT | N.A. | - | 0 | 0.01295 | 0.01295 | 0 | 0 | 0 |  |  | 0 | 0
61 | Network Attached Storage Server at KGSC, Pophali. | N.A. | - | 0 | 0.023333 | 0.023333 | 0 | 0 | 0 |  |  | 0 | 0
62 | Supply of A4 Printer at KGSC, Pophali. | N.A. | - | 0 | 0.0099995 | 0.0099995 | 0 | 0 | 0 |  |  | 0 | 0
63 | Supply of A4 Scanner, A3 & MF Printer at KGSC, Pop | N.A. | - | 0 | 0.0586 | 0.0586 | 0 | 0 | 0 |  |  | 0 | 0
64 | Supply of Various Hard Disks for Network Attached | N.A. | - | 0 | 0.021806 | 0.021806 | 0 | 0 | 0 |  |  | 0 | 0
65 | Supply of Video conference Microphone at KGSC, | N.A. | - | 0 | 0.0021512 | 0.0021512 | 0 | 0 | 0 |  |  | 0 | 0
66 | Supply of Video Conference Screen at KGSC Pophali | N.A. | - | 0 | 0.02 | 0.02 | 0 | 0 | 0 |  |  | 0 | 0
67 | Supply of Video conference Screen at KGSC, Pophali | N.A. | - | 0 | 0.0109 | 0.0109 | 0 | 0 | 0 |  |  | 0 | 0
68 | Supply of Kelvinator / Godrej / Croma Make Refrigerator | N.A. | - | 0 | 0.010932 | 0.010932 | 0 | 0 | 0 |  |  | 0 | 0
69 | supply of Bosch make High Pressure Washer at Mecha | N.A. | - | 0 | 0.0020649 | 0.0020649 | 0 | 0 | 0 |  |  | 0 | 0
70 | Supply of Pneumatic Tools for Mechanical Maintenan | N.A. | - | 0 | 0.035259 | 0.035259 | 0 | 0 | 0 |  |  | 0 | 0
72 | Low BACK Revolving Chairs 45 No & Desk Chair 2 No | N.A. | - | 0 | 0.020945 | 0.020945 | 0 | 0 | 0 |  |  | 0 | 0
73 | Supply of Tables at KGSC | N.A. | - | 0 | 0.037339 | 0.037339 | 0 | 0 | 0 |  |  | 0 | 0
74 | Supply of Visitor Chairs & Office chairs at KGSC, | N.A. | - | 0 | 0.033201 | 0.033201 | 0 | 0 | 0 |  |  | 0 | 0
75 | water purifier for colony electrical maintenance | N.A. | - | 0 | 0.00174 | 0.00174 | 0 | 0 | 0 |  |  | 0 | 0
76 | Projectors and Motorized Projector Screens (2+2) | N.A. | - | 0 | 0.03481 | 0.03481 | 0 | 0 | 0 |  |  | 0 | 0
77 | Acer make Computers at KGSC Pophali.21 No. | N.A. | - | 0 | 0.119 | 0.119 | 0 | 0 | 0 |  |  | 0 | 0
78 | Acer make Laptops at KGSC Pophali. | N.A. | - | 0 | 0.030088 | 0.030088 | 0 | 0 | 0 |  |  | 0 | 0
79 | APS Smart UPS Xl 2200 VA RM 3U 230 | N.A. | - | 0 | 0.015983 | 0.015983 | 0 | 0 | 0 |  |  | 0 | 0
80 | BATRY 12V 75 AH BATTREY 11 PLATE | N.A. | - | 0 | 0.017629 | 0.017629 | 0 | 0 | 0 |  |  | 0 | 0
81 | Supply & installation of IP Camera System and network spare | N.A. | - | 0 | 0.025807 | 0.025807 | 0 | 0 | 0 |  |  | 0 | 0
82 | Gym Equipments at MSPGCL Recreation club , 33 Item | N.A. | - | 0 | 0.047834 | 0.047834 | 0 | 0 | 0 |  |  | 0 | 0
0 | Non-DPR schemes (3 Nos) for FY 2024-25 at KGSC Pophali | Board Resolution No-MSPGCL/BM-219/Item 219.7 dtd.24.07.2023 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
83 | Up-gradation of thyristor based 48V Battery Chargers (4 nos) by SMPS Microprocessor based dual float cum boost Battery Chargers at Stage-III, Stage-I&II and KDPH at KGSC, Pophali | 0 | - | 0 | 0 | 0 | 0 | 1.57 | 1.57 |  |  | 1.57 | 0
84 | Up-gradation of thyristor based 220V Battery Chargers (4 nos) by SMPS Microprocessor based dual float cum boost Battery Chargers at Stage-III and Stage-I&II at KGSC, Pophali | 0 | - | 0 | 0 | 0 | 0 | 3.79 | 3.79 |  |  | 3.79 | 0
85 | Retrofitting of Generator and Gen. Transformer protection relay by Numerical protection system at KGSC stage III, Alore | 0 | - | 0 | 0 | 0 | 0 | 4.78 | 4.78 |  |  | 4.78 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Non-DPR schemes (2 Nos) for FY 2025-26 at KGSC Pophali | Yet Not Submitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
86 | Supply, Erection, Commissioning & Retrofitting of 220 VDC Ni-cadmium type Battery set (4 Nos) having different ampere hour capacity at Stage-I&II and Stage-IV | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
87 | Supply, Erection, Commissioning & Retrofitting of 48VDC, 300AH Ni-cadmium type Battery set at Stage-I&II switchyard | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 98.4649 | 70.7726 | 27.6923 | 39.09 | 58.86 | 0 | 0 | 58.86 | 7.9223
FY 2025-26
a) DPR Schemes
(i) Submitted to MERC
1 | Various improvement schemes at Pophali Hydro Power Station | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 11.9001 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | ALSPA HMI Series 6 Centralog System | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 6.8555 | 7.8386 | 7.8386 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | 1 X 525 Tr chiller unit | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 1.23 | 1.15 | 1.15 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Micom P343 Numerical generator protection relay with 24 DI & 24 DO with CLIO input. (5 Nos) | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 1.4675 | 1.474 | 1.474 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.4 | Security Building at Stage-IV | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 0.16446 | 0.18377 | 0.18377 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.5 | Construction of recreation club building | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 1.8204 | 2.1946 | 2.1946 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.6 | Security Building for Stage-IV at EVT | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 0.22776 | 0.25961 | 0.25961 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 0.1344 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Various DPR Schemes for Civil Section, KGSC Pophali | MERC/CAPEX/20152016/00907 | 2015-11-05 | 21.201 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Providing Road Network at KGSC, Pophali | MERC/CAPEX/20152016/00907 | 2015-11-05 | 7.776 | 7.0182 | 7.0182 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.2 | Modernisation & Refurbishing of Residential Complex | MERC/CAPEX/20152016/00907 | 2015-11-05 | 8.985 | 8.9365 | 8.9365 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.3 | Water Supply & Sanitory Works | MERC/CAPEX/20152016/00907 | 2015-11-05 | 4.44 | 5.9018 | 4.1022 | 1.7997 | 0 | 0 |  |  | 0 | 1.7997 | 0 | 0
4 | Various Performance Improvement related schemes at KGSC, Pophali | MERC/CAPEX/20162017/01018 | 2016-11-17 | 12.9765 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Up gradation of 245 kV CTs at Stage-I&II SY | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.9624 | 2.09 | 2.09 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Up gradation of 245 kV PTs at Stage-I&II SY | MERC/CAPEX/20162017/01018 | 2016-11-17 | 0.40509 | 0.3417 | 0.3417 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.3 | Up gradation of CW system of Stage-I&II Units | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.7099 | 1.4731 | 1.4731 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.4 | Up gradation of Intercom Exchange System between Stage-I&II PH & Admin. Bldg & Staff Colony. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 0.43826 | 0.359 | 0.359 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.5 | Up gradation of 220 kV Breakers at KDPH SY | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.289 | 0.979 | 0.979 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.6 | Procurement of Governing Oil Pumps for Stage-III Units. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.2316 | 0.70174 | 0.70174 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.7 | Up gradation of TG Governing system of Stage-IV Units. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 2.2152 | 2.7472 | 2.7472 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.8 | Up gradation of Numerical Protection system of Stage-IV Units. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 2.8249 | 2.8674 | 2.8674 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01018 | 2016-11-17 | 0.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7 | Replacement of Generator Stator of unit No. 11 (80 MW), Stage III, KGSC Pophali | MERC/CAPEX/20172018/04592 | 2017-11-07 | 22.54 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Replacement of Generator Stator of unit No. 11 (80 MW), Stage III, KGSC Pophali | MERC/CAPEX/20172018/04592 | 2017-11-07 | 22.54 | 19.409 | 19.41 | -0.001 | 0 | 0 |  |  | 0 | -0.001 | 0 | 0
8 | Procurement of new pelton wheel runners (2 Nos.) for Stage II at KGSC, Pophali | MERC/CAPEX/20172018/04421 | 2017-10-24 | 13.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement of new pelton wheel runners (2 Nos.) for Stage II at KGSC, Pophali | MERC/CAPEX/20172018/04421 | 2017-10-24 | 13.07 | 5.19 | 0 | 5.19 | 5.19 | 10.38 |  |  | 10.38 | 0 | 10.38 | 0
11 | Implementation of 12 Nos. of various schemes at KGSC, Pophali. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 26.891 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Replacement of UGB (8 Nos), LGB (8 Nos) & Generator air coolers (8 Nos) for Stage-I | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 1.344 | 0.85 | 0.85 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Retrofitting of Generator & Gen-Transformer relays by new numerical protection system at Koyna Dam Power House (KDPH) Koynanagar | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 1.097 | 1.08 | 1.08 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.3 | Replacement of two 220V Battery chargers with 220V dual float cum boost (60A) battery Charger including DCDB at KDPH, Koynanagar | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.202 | 0.13782 | 0.13782 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.4 | Replacement of 220KV current transformer (54 Nos), Potential transformer (13 Nos),110KV Current Transformer (14 Nos)& Potential Transformer (4 Nos),Stage-III. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 5.281 | 0 | 0 | 0 | 5.28 | 5.28 |  |  | 5.28 | 0 | 5.28 | 0
11.5 | Replacement of Generator Air Cooler (32 Nos), St-III | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 2.413 | 2.0541 | 2.0541 | -4e-06 | 0 | 0 |  |  | 0 | -4e-06 | 0 | 0
11.6 | Replacement of 48 Volt, 1000 AH tubular battery set with 48 Volt, 750AH Plante type battery set at KGSC, Stage-III | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.318 | 0.30942 | 0.30942 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.7 | Replacement of 220V-150AH Battery set with Ni-Cad type, along with standard accessories for UPS scheme at Stage-IV | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.272 | 0.25759 | 0.25759 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.8 | Reliability enhancement of Gas Insulated Switchyard Stage-IV. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 10.472 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.9 | Up-gradation of Vibration system at all units of Stage-IV:Stage-IV, KGSC, Pophali | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 1.443 | 1.5041 | 1.5041 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.10 | Replacement of station battery set of 220V, 2000Ah capacity at Stage-IV. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 2.385 | 2.3649 | 2.3649 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.11 | Renovations and modernization of 1500kg capacity passenger cum goods lifts (2 Nos) for KGSC, Stage-IV | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.968 | 0.85208 | 0.85208 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.12 | Replacement of existing 3x7.5 TR Air conditioning package units at Stage-I&II control room by new 3x11 TR Air conditioning package units | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.345 | 0.16909 | 0.16909 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.351 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Upgradation of Governing System at Stage-I, KDPH& Stage-III at KGSC, Pophali | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 19.1651 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Up gradation of DIGIPID1500 governing system with new governor (TSLG) for all units of stage-I | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 6.0888 | 3.89 | 3.89 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.2 | Up-gradation of governing system at Koyna Dam Power House (KDPH) Koynanagar | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 2.924 | 1.41 | 1.41 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.3 | Up-gradation of the Governing system at Stage-III & Other Charges (P&F, Insurance etc) | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 9.5523 | 4.6 | 4.6 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Refurbishment of 24 KV Generator Circuit Breakers (ABB Make) for four units at stage-IV, KGSC, Pophali | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 10.5726 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Supply spares for 24KV Generator Circuit Breaker System refurbishment (For 4 Units) | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 6.5702 | 6.5421 | 6.5421 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Supervision charges for 24 KV Generator Circuit Breaker System Unit. Preparation charges, Travel & transportation charges, local conveyance. Lumpsum rental charges of necessary tools & tackles required during O/H work charges | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 3.8704 | 3.8216 | 3.8216 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 0.132 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Up-gradation of Excitation system at Stage-I&II, PLC & SCADA system at Stage-II and DG Set at Stage-IV at KGSC, Pophali | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 9.863 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | Up gradation of Stage-I&II(4x70MW+4x80 MW) Static Semipol Excitation System with Latest Advanced Excitation System | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 9.863 | 5.763 | 5.76 | 0.003 | 0 | 0 |  |  | 0 | 0.003 | 0 | 0
15.2 | Up gradation of existing unit PLC and SCADA automation of 4x80 MW Koyna stage-II units | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 4.232 | 4.3 | 4.3 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.3 | Up gradation of one 1500 KVA DG set, at KGSC, Stage-IV | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 1.6 | 1.81 | 1.81 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 1.103 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Repair works in Emergency Valve Tunnel (EVT) and surge well at Stage I/II, KGSC, Pophali | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 28.0371 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Sealing and stabilization of EVT Tunnel left side wall and carven portion of EVT and Ventilation Tunnel. | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 8.307 | 7.1531 | 5.61 | 1.5431 | 12.42 | 12.42 |  |  | 12.42 | 1.5431 | 2.697 | 9.723
17.2 | Structural Strengthening and Sealing Cracks and Cavities in Surge Shaft RCC Staining Wall from inside | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 18.6602 | 0.3875 | 0 | 0.3875 | 0 | 0 |  |  | 0 | 0.3875 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 1.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-8.1 | Advance Multipurpose Fire Tender | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-8.2 | Normal Multipurpose Fire Tender | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Refurbishment of cooling and drainage water system along with replacement of 5 no's of cooling water pumps by new stage -IV KGSC Pophali | MERC/CAPEX/2023-2024/MSPGCL/0201 | 2024-03-21 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Refurbishment of cooling and drainage water system along with replacement of 5 no's of cooling water pumps by new stage -IV KGSC Pophali | MERC/CAPEX/2023-2024/MSPGCL/0201 | 2024-03-21 | 0 | 0 | 0 | 0 | 27.83 | 27.83 |  |  | 27.83 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0201 | 2024-03-21 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[8 empty] | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | Refurbishment of GIS T155 as per M4 Schedule at KGSC Stage-IV, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | Refurbishment of GIS T155 as per M4 Schedule at KGSC Stage-IV, Pophali | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20 | Various Civil work as per IB recommendation at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.1 | Various Civil work as per IB recommendation at KGSC, Pophali | 0 | - | 0 | 0 | 0 | 0 | 6 | 10.5 |  |  | 10.5 | -4.5
20.2 | construction of chainlink caging along entrance of St-I&II, St-III & St-IV | 0 | - | 0 | 0 | 0 | 0 | 4.5 | 0 |  |  | 0 | 4.5
21 | Stabilization and Mitigation of Landslide Prone Areas at KGSC, Mahagenco, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Stabilization and Mitigation of Landslide Prone Areas | 0 | - | 0 | 0 | 1 | -1 | 17 | 17 |  |  | 17 | -1
21.2 | Construction of retaining wall | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
21.3 | Dredging river and nallah | 0 | - | 0 | 0 | 0 | 0 | 0.4 | 0.4 |  |  | 0.4 | 0
22 | Various Performance Improvement related schemes for FY 2026-27 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.1 | Supply of New Runner for Francis Turbine 80 MW at KGSC Stage-III | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.2 | Supply of 2 Nos. injector along with injector shaft for Stage-I Units (70 MW) at Stage I & II KGSC, Pophali . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.3 | Supply of 1 No. injector for Stage-II Units (80 MW) at Stage I & II KGSC, Pophali . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.4 | Upgradation of AC Chiiler system at Stage I & II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.5 | Design, manufacturing, supply, erection, testing and commissioning of LGB and UGB cooler modifications at KGSC Stage I&II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Replacement of existing Generator transformer of all units (04 x 80 MW) in phase manner (one unit per year) at Stage-III, KGSC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.1 | Replacement of existing Generator transformer of all units (04 x 80 MW) in phase manner (one unit per year) at Stage-III, KGSC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Implementation of PLC & SCADA system (DSC based) for all units (04 x 80 MW) units in phase manner (two unit per year) at Stage-III, KGSC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.1 | Implementation of PLC & SCADA system (DSC based) for all units (04 x 80 MW) units in phase manner (two unit per year) at Stage-III, KGSC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | Various Performance Improvement related schemes for FY 2027-28 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.1 | Refurbishment of Stage-1, Unit No-1,2,3 & 4 PLC System and Implementation of SCADA System. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.2 | Supply, installation & commissioning of New PLC & Centralog system for all four units at St-IV, KGSC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.3 | Supply, installation & commissioning of New excitation system for all four units at St-IV, KGSC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | Various Performance Improvement related schemes for FY 2028-29 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.1 | Upgradation of 11 KV Auxiliary breaker at St-I&II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.2 | Supply of Dry Type, 630 KVA 16 KV / 570 V Single Phase Excitation Transformers (Qty. 12 Nos.) at KGSC Stage-IV, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.3 | Supply, Installation & Commissioning of 16.5 KV / 433 V, 5MVA Unit Auxiliary Transformers (Qty. 02) at KGSC Stage-IV. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.4 | Upgradation of 2.2 KV Auxiliary Breaker with 3.3 KV Breaker along with Auxiliary Transformers at St-I&II. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.5 | Supply of 11KV Cable alongwith Breaker Panels for Auxiliary Supply from 8-Pole Switchyard Stage- I and II to Stage-IV Powerhouse at KGSC Stage-IV, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.6 | Replacement of 220 KV isolator of Stage II bay at 220 KV Stage I & II Switchyard | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | Various Performance Improvement related schemes for FY 2029-30 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.1 | Design Engineering and manufacturing, supply, erection, commissioning & testing of New Pelton runner for Stage-I units (70 MW) at Stage-I&II, KGSC, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.2 | Upgradation of Generator and Generator transformer electromagnetic protection relays with numeric relays for Stage 1 & 2. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.3 | Renovation of old system by full proof modern digital governing system, static/brushless excitation system and generator stator and rotor winding by class 'F' insulation at St-I&II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.4 | Design, manufacturing, supply, erection, testing and commissioning of Hydrostatic lubrication system for Units at KGSC Stage I & II, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.5 | Replacement of CW pumps and Motors along with starter pannel at St-I&II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.6 | Supply of Generator air coolers (16 Nos) for Stage II Units (80 MW) at KGSC, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.7 | Conversion of Stator Core Insulation & Stator Winding from Class ‘B’ to Class ‘F’ for Unit No. 8 (80MW, 11KV, 375RPM, AEG Germany make) of Stage II, KGSC, Pophali on Turnkey Basis. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.8 | Up-gradation of existing 'B' class insulation of Generator stator to 'F' class insulation of 2X18MW Koyna Dam Power House, Koynanagar. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.9 | Supply and replacement of Generator air cooler system by new higher efficiency coolers for 2X18MW Koyna Dam Power House, Koynanagar. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | <Auto Transformer Oil Insulation Test kit (BDV Kit)> | N.A. | - | 0 | 0.03953 | 0.03953 | 0 | 0 | 0 |  |  | 0 | 0
2 | <Man coolers pedestal fans at KGSC,Pophali> | N.A. | - | 0 | 0.034143 | 0.034143 | 0 | 0 | 0 |  |  | 0 | 0
3 | < 5 KV Digital Insulation Tester> | N.A. | - | 0 | 0.029798 | 0.029798 | 0 | 0 | 0 |  |  | 0 | 0
4 | <Split AC Unit,Window AC Unit,Refrigerator,Ped> | N.A. | - | 0 | 0.017857 | 0.017857 | 0 | 0 | 0 |  |  | 0 | 0
5 | <Earth Resistance Tester at ,Pophali. TIC STAGE IV> | N.A. | - | 0 | 0.016839 | 0.016839 | 0 | 0 | 0 |  |  | 0 | 0
6 | <Tools and Tackles at St-IV,KGSC,Pophali> | N.A. | - | 0 | 0.034609 | 0.034609 | 0 | 0 | 0 |  |  | 0 | 0
7 | <New portable Fire Fighting Diesel Pumps for Dewatering> | N.A. | - | 0 | 0.09697 | 0.09697 | 0 | 0 | 0 |  |  | 0 | 0
8 | <Visitors chairs for, Pophali KGSC> | N.A. | - | 0 | 0.033188 | 0.033188 | 0 | 0 | 0 |  |  | 0 | 0
9 | <Installation of new racks inside various/new slotted angle racks > | N.A. | - | 0 | 0.039648 | 0.039648 | 0 | 0 | 0 |  |  | 0 | 0
10 | <Supply of chairs for KGSC, Pophali> | N.A. | - | 0 | 0.044238 | 0.044238 | 0 | 0 | 0 |  |  | 0 | 0
11 | <Laser Jet NetwoksPrinters at KGSC, Pophali> | N.A. | - | 0 | 0.084075 | 0.084075 | 0 | 0 | 0 |  |  | 0 | 0
12 | <Night Vision Binoculars> | N.A. | - | 0 | 0.023411 | 0.023411 | 0 | 0 | 0 |  |  | 0 | 0
13 | <TATA Star Bus-32 seater LCV MH08-9358> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | <TATA Star Bus-32 seater LCV MH08-9359> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | <Vehicle No.MH 08-9401 TATA Star Bus 32 seater> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | <Not in use DCM Toyato Bus MH-1> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | <Not in use DCM Toyato Mini Bus> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | <Digital Multimeters, Clamp Meter & Insulation resistance tester for TIC, Stage I&II, Pophali> | N.A. | - | 0 | 0.028928 | 0.028928 | 0 | 0 | 0 |  |  | 0 | 0
19 | <Transformer Winding resistance measurement kit at Stage-III, Alore> | N.A. | - | 0 | 0.024338 | 0.024338 | 0 | 0 | 0 |  |  | 0 | 0
20 | <Multifunc A3 Scanner & all in one A4 laser printer Technical Purchase , Account Section, H.R. ,MPD> | N.A. | - | 0 | 0.032521 | 0.032521 | 0 | 0 | 0 |  |  | 0 | 0
21 | <Temperature Calibrator at St-IV, KGSC,Pophali> | N.A. | - | 0 | 0.012272 | 0.012272 | 0 | 0 | 0 |  |  | 0 | 0
22 | < 1 no. new departmental car Maruti Sweft Desire for conveyance of Chief Engr> | N.A. | - | 0 | 0.077924 | 0.077924 | 0 | 0 | 0 |  |  | 0 | 0
23 | <Hitachi A/c Two.NO.VIP Rest House> | N.A. | - | 0 | 0.008 | 0.008 | 0 | 0 | 0 |  |  | 0 | 0
24 | <Inverter Split AC Unit, Desert Coolers Water Coolers for KGSC, Pophali> | N.A. | - | 0 | 0.0070799 | 0.0070799 | 0 | 0 | 0 |  |  | 0 | 0
25 | <Advanced ISDN EPABX system for Koyna Generating St ntercom Telephone Advanced ISDN EPABX system for Koyna Generating Station Complex> | N.A. | - | 0 | 0.029645 | 0.029645 | 0 | 0 | 0 |  |  | 0 | 0
26 | <TATA Sumo MH-14/9763 1 No> | N.A. | - | 0 | 0.041197 | 0.041197 | 0 | 0 | 0 |  |  | 0 | 0
27 | <Ambulance TATA make MH-31/4475 1 No> | N.A. | - | 0 | 0.036143 | 0.036143 | 0 | 0 | 0 |  |  | 0 | 0
28 | <Supply of 1 No of Ambulance Vane for Pophali> | N.A. | - | 0 | 0.14883 | 0.14883 | 0 | 0 | 0 |  |  | 0 | 0
29 | <Supply of 1 No of Ambulance Vane for Pophali> | N.A. | - | 0 | 0.14883 | 0.14883 | 0 | 0 | 0 |  |  | 0 | 0
30 | <HITACHI Make 2 TR non inverter split Air conditioner> | N.A. | - | 0 | 0.16739 | 0.16739 | 0 | 0 | 0 |  |  | 0 | 0
31 | <250 KVA D.G. Set Model KG1-250WS> | N.A. | - | 0 | 0.19222 | 0.19222 | 0 | 0 | 0 |  |  | 0 | 0
32 | <Dell laptops at KGSC Pophali> | N.A. | - | 0 | 0.0156 | 0.0156 | 0 | 0 | 0 |  |  | 0 | 0
33 | <A.C. Plant chiller 515 to 535 TRx2 at kgsc,Pophali> | N.A. | - | 0 | 2.1144 | 2.1144 | 0 | 0 | 0 |  |  | 0 | 0
34 | <Supply of RDP make Computers at KGSC> | N.A. | - | 0 | 0.43135 | 0.43135 | 0 | 0 | 0 |  |  | 0 | 0
35 | <Welding Machine for KDPH> | N.A. | - | 0 | 0.001039 | 0.001039 | 0 | 0 | 0 |  |  | 0 | 0
36 | <Material handling trolley for Majot store> | N.A. | - | 0 | 0.0014198 | 0.0014198 | 0 | 0 | 0 |  |  | 0 | 0
37 | <Canon LiDe 300 IN Scanner> | N.A. | - | 0 | 0.00048 | 0.00048 | 0 | 0 | 0 |  |  | 0 | 0
38 | <Supply of Pedestal fan at KDPH> | N.A. | - | 0 | 0.015 | 0.015 | 0 | 0 | 0 |  |  | 0 | 0
39 | <Supply of Refrigerator 290 LTR double door capacity> | N.A. | - | 0 | 0.0022 | 0.0022 | 0 | 0 | 0 |  |  | 0 | 0
40 | <Supply of Refrigerator 290 LTR double door capacity> | N.A. | - | 0 | 0.0022 | 0.0022 | 0 | 0 | 0 |  |  | 0 | 0
41 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.007 | 0.007 | 0 | 0 | 0 |  |  | 0 | 0
42 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.0035 | 0.0035 | 0 | 0 | 0 |  |  | 0 | 0
43 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.0035 | 0.0035 | 0 | 0 | 0 |  |  | 0 | 0
44 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.0035 | 0.0035 | 0 | 0 | 0 |  |  | 0 | 0
45 | <Redmi 10 prime Mobile Black for Chief Engineer> | N.A. | - | 0 | 0.0015 | 0.0015 | 0 | 0 | 0 |  |  | 0 | 0
46 | <TATA Sumo MH-14/9763 1 No> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47 | <Ambulance TATA make MH-31/4475 1 No> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48 | <Supply of Two Post Lift (4 Ton) for Vehicle Maint.> | N.A. | - | 0 | 0.014396 | 0.014396 | 0 | 0 | 0 |  |  | 0 | 0
49 | Supply,Installation, commissioning and testing of 415V, 3 Phase diesel generating setof 125 KVA capacity for Admin building emergency power supply backup at KGSC,Pophali. | N.A. | - | 0 | 0.0995 | 0.0995 | 0 | 0 | 0 |  |  | 0 | 0
50 | Design,Manufacturing, supply erriction and commissioning of 60 MT surface mounted (pit type/ platform type) weighbridge at major stores 'c' pophali | N.A. | - | 0 | 0.21577 | 0.21577 | 0 | 0 | 0 |  |  | 0 | 0
51 | Supply of Hydraulically operated manual stacker for Material Handling at Major Store "C", KGSC, Pophali | N.A. | - | 0 | 0.00524 | 0.00524 | 0 | 0 | 0 |  |  | 0 | 0
52 | Supply of Indef makes Chain Pulley Blocks | N.A. | - | 0 | 0.011505 | 0.011505 | 0 | 0 | 0 |  |  | 0 | 0
53 | Supply of Motwane Make ‘Digital Multimeter and AC Multimeter | N.A. | - | 0 | 0.018458 | 0.018458 | 0 | 0 | 0 |  |  | 0 | 0
54 | Supply 1 Ton split AC Daiken make for control room cabin Operation Stage III | N.A. | - | 0 | 0.00396 | 0.00396 | 0 | 0 | 0 |  |  | 0 | 0
55 | Emer Rescue cum Multipurpose Fire Tender | N.A. | - | 0 | 2.0039 | 2.0039 | 0 | 0 | 0 |  |  | 0 | 0
56 | Procurement of portable chairs for training sub centre | N.A. | - | 0 | 0.01308 | 0.01308 | 0 | 0 | 0 |  |  | 0 | 0
57 | Procurement of portable computer tables | N.A. | - | 0 | 0.0033449 | 0.0033449 | 0 | 0 | 0 |  |  | 0 | 0
58 | Purchase of High back chair (3 Nos.) in conferenc hall | N.A. | - | 0 | 0.0044014 | 0.0044014 | 0 | 0 | 0 |  |  | 0 | 0
59 | Supply of Water Purifier at MSPGCL KGSC Pophali. | N.A. | - | 0 | 0.005 | 0.005 | 0 | 0 | 0 |  |  | 0 | 0
60 | Interactive Digital LV SCREEN 6.56 FT X 3.28 FT | N.A. | - | 0 | 0.01295 | 0.01295 | 0 | 0 | 0 |  |  | 0 | 0
61 | Network Attached Storage Server at KGSC, Pophali. | N.A. | - | 0 | 0.023333 | 0.023333 | 0 | 0 | 0 |  |  | 0 | 0
62 | Supply of A4 Printer at KGSC, Pophali. | N.A. | - | 0 | 0.0099995 | 0.0099995 | 0 | 0 | 0 |  |  | 0 | 0
63 | Supply of A4 Scanner, A3 & MF Printer at KGSC, Pop | N.A. | - | 0 | 0.0586 | 0.0586 | 0 | 0 | 0 |  |  | 0 | 0
64 | Supply of Various Hard Disks for Network Attached | N.A. | - | 0 | 0.021806 | 0.021806 | 0 | 0 | 0 |  |  | 0 | 0
65 | Supply of Video conference Microphone at KGSC, | N.A. | - | 0 | 0.0021512 | 0.0021512 | 0 | 0 | 0 |  |  | 0 | 0
66 | Supply of Video Conference Screen at KGSC Pophali | N.A. | - | 0 | 0.02 | 0.02 | 0 | 0 | 0 |  |  | 0 | 0
67 | Supply of Video conference Screen at KGSC, Pophali | N.A. | - | 0 | 0.0109 | 0.0109 | 0 | 0 | 0 |  |  | 0 | 0
68 | Supply of Kelvinator / Godrej / Croma Make Refrigerator | N.A. | - | 0 | 0.010932 | 0.010932 | 0 | 0 | 0 |  |  | 0 | 0
69 | supply of Bosch make High Pressure Washer at Mecha | N.A. | - | 0 | 0.0020649 | 0.0020649 | 0 | 0 | 0 |  |  | 0 | 0
70 | Supply of Pneumatic Tools for Mechanical Maintenan | N.A. | - | 0 | 0.035259 | 0.035259 | 0 | 0 | 0 |  |  | 0 | 0
72 | Low BACK Revolving Chairs 45 No & Desk Chair 2 No | N.A. | - | 0 | 0.020945 | 0.020945 | 0 | 0 | 0 |  |  | 0 | 0
73 | Supply of Tables at KGSC | N.A. | - | 0 | 0.037339 | 0.037339 | 0 | 0 | 0 |  |  | 0 | 0
74 | Supply of Visitor Chairs & Office chairs at KGSC, | N.A. | - | 0 | 0.033201 | 0.033201 | 0 | 0 | 0 |  |  | 0 | 0
75 | water purifier for colony electrical maintenance | N.A. | - | 0 | 0.00174 | 0.00174 | 0 | 0 | 0 |  |  | 0 | 0
76 | Projectors and Motorized Projector Screens (2+2) | N.A. | - | 0 | 0.03481 | 0.03481 | 0 | 0 | 0 |  |  | 0 | 0
77 | Acer make Computers at KGSC Pophali.21 No. | N.A. | - | 0 | 0.119 | 0.119 | 0 | 0 | 0 |  |  | 0 | 0
78 | Acer make Laptops at KGSC Pophali. | N.A. | - | 0 | 0.030088 | 0.030088 | 0 | 0 | 0 |  |  | 0 | 0
79 | APS Smart UPS Xl 2200 VA RM 3U 230 | N.A. | - | 0 | 0.015983 | 0.015983 | 0 | 0 | 0 |  |  | 0 | 0
80 | BATRY 12V 75 AH BATTREY 11 PLATE | N.A. | - | 0 | 0.017629 | 0.017629 | 0 | 0 | 0 |  |  | 0 | 0
81 | Supply & installation of IP Camera System and network spare | N.A. | - | 0 | 0.025807 | 0.025807 | 0 | 0 | 0 |  |  | 0 | 0
82 | Gym Equipments at MSPGCL Recreation club , 33 Item | N.A. | - | 0 | 0.047834 | 0.047834 | 0 | 0 | 0 |  |  | 0 | 0
0 | Non-DPR schemes (3 Nos) for FY 2024-25 at KGSC Pophali | Board Resolution No-MSPGCL/BM-219/Item 219.7 dtd.24.07.2023 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
83 | Up-gradation of thyristor based 48V Battery Chargers (4 nos) by SMPS Microprocessor based dual float cum boost Battery Chargers at Stage-III, Stage-I&II and KDPH at KGSC, Pophali | 0 | - | 0 | 1.57 | 1.57 | 0 | 0 | 0 |  |  | 0 | 0
84 | Up-gradation of thyristor based 220V Battery Chargers (4 nos) by SMPS Microprocessor based dual float cum boost Battery Chargers at Stage-III and Stage-I&II at KGSC, Pophali | 0 | - | 0 | 3.79 | 3.79 | 0 | 0 | 0 |  |  | 0 | 0
85 | Retrofitting of Generator and Gen. Transformer protection relay by Numerical protection system at KGSC stage III, Alore | 0 | - | 0 | 4.78 | 4.78 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Non-DPR schemes (2 Nos) for FY 2025-26 at KGSC Pophali | Yet Not Submitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
86 | Supply, Erection, Commissioning & Retrofitting of 220 VDC Ni-cadmium type Battery set (4 Nos) having different ampere hour capacity at Stage-I&II and Stage-IV | 0 | - | 0 | 0 | 0 | 0 | 9.23 | 9.23 |  |  | 9.23 | 0
87 | Supply, Erection, Commissioning & Retrofitting of 48VDC, 300AH Ni-cadmium type Battery set at Stage-I&II switchyard | 0 | - | 0 | 0 | 0 | 0 | 0.37 | 0.37 |  |  | 0.37 | 0
| Total |  |  |  | 137.5549 | 129.6326 | 7.9223 | 93.22 | 98.41 | 0 | 0 | 98.41 | 2.7323
FY 2026-27
a) DPR Schemes
(i) Submitted to MERC
1 | Various improvement schemes at Pophali Hydro Power Station | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 11.9001 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | ALSPA HMI Series 6 Centralog System | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 6.8555 | 7.8386 | 7.8386 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | 1 X 525 Tr chiller unit | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 1.23 | 1.15 | 1.15 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Micom P343 Numerical generator protection relay with 24 DI & 24 DO with CLIO input. (5 Nos) | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 1.4675 | 1.474 | 1.474 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.4 | Security Building at Stage-IV | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 0.16446 | 0.18377 | 0.18377 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.5 | Construction of recreation club building | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 1.8204 | 2.1946 | 2.1946 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.6 | Security Building for Stage-IV at EVT | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 0.22776 | 0.25961 | 0.25961 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 0.1344 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Various DPR Schemes for Civil Section, KGSC Pophali | MERC/CAPEX/20152016/00907 | 2015-11-05 | 21.201 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Providing Road Network at KGSC, Pophali | MERC/CAPEX/20152016/00907 | 2015-11-05 | 7.776 | 7.0182 | 7.0182 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.2 | Modernisation & Refurbishing of Residential Complex | MERC/CAPEX/20152016/00907 | 2015-11-05 | 8.985 | 8.9365 | 8.9365 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.3 | Water Supply & Sanitory Works | MERC/CAPEX/20152016/00907 | 2015-11-05 | 4.44 | 5.9018 | 4.1022 | 1.7997 | 0 | 0 |  |  | 0 | 1.7997 | 0 | 0
4 | Various Performance Improvement related schemes at KGSC, Pophali | MERC/CAPEX/20162017/01018 | 2016-11-17 | 12.9765 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Up gradation of 245 kV CTs at Stage-I&II SY | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.9624 | 2.09 | 2.09 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Up gradation of 245 kV PTs at Stage-I&II SY | MERC/CAPEX/20162017/01018 | 2016-11-17 | 0.40509 | 0.3417 | 0.3417 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.3 | Up gradation of CW system of Stage-I&II Units | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.7099 | 1.4731 | 1.4731 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.4 | Up gradation of Intercom Exchange System between Stage-I&II PH & Admin. Bldg & Staff Colony. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 0.43826 | 0.359 | 0.359 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.5 | Up gradation of 220 kV Breakers at KDPH SY | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.289 | 0.979 | 0.979 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.6 | Procurement of Governing Oil Pumps for Stage-III Units. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.2316 | 0.70174 | 0.70174 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.7 | Up gradation of TG Governing system of Stage-IV Units. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 2.2152 | 2.7472 | 2.7472 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.8 | Up gradation of Numerical Protection system of Stage-IV Units. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 2.8249 | 2.8674 | 2.8674 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01018 | 2016-11-17 | 0.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7 | Replacement of Generator Stator of unit No. 11 (80 MW), Stage III, KGSC Pophali | MERC/CAPEX/20172018/04592 | 2017-11-07 | 22.54 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Replacement of Generator Stator of unit No. 11 (80 MW), Stage III, KGSC Pophali | MERC/CAPEX/20172018/04592 | 2017-11-07 | 22.54 | 19.409 | 19.41 | -0.001 | 0 | 0 |  |  | 0 | -0.001 | 0 | 0
8 | Procurement of new pelton wheel runners (2 Nos.) for Stage II at KGSC, Pophali | MERC/CAPEX/20172018/04421 | 2017-10-24 | 13.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement of new pelton wheel runners (2 Nos.) for Stage II at KGSC, Pophali | MERC/CAPEX/20172018/04421 | 2017-10-24 | 13.07 | 10.38 | 10.38 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Implementation of 12 Nos. of various schemes at KGSC, Pophali. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 26.891 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Replacement of UGB (8 Nos), LGB (8 Nos) & Generator air coolers (8 Nos) for Stage-I | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 1.344 | 0.85 | 0.85 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Retrofitting of Generator & Gen-Transformer relays by new numerical protection system at Koyna Dam Power House (KDPH) Koynanagar | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 1.097 | 1.08 | 1.08 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.3 | Replacement of two 220V Battery chargers with 220V dual float cum boost (60A) battery Charger including DCDB at KDPH, Koynanagar | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.202 | 0.13782 | 0.13782 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.4 | Replacement of 220KV current transformer (54 Nos), Potential transformer (13 Nos),110KV Current Transformer (14 Nos)& Potential Transformer (4 Nos),Stage-III. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 5.281 | 5.28 | 5.28 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.5 | Replacement of Generator Air Cooler (32 Nos), St-III | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 2.413 | 2.0541 | 2.0541 | -4e-06 | 0 | 0 |  |  | 0 | -4e-06 | 0 | 0
11.6 | Replacement of 48 Volt, 1000 AH tubular battery set with 48 Volt, 750AH Plante type battery set at KGSC, Stage-III | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.318 | 0.30942 | 0.30942 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.7 | Replacement of 220V-150AH Battery set with Ni-Cad type, along with standard accessories for UPS scheme at Stage-IV | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.272 | 0.25759 | 0.25759 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.8 | Reliability enhancement of Gas Insulated Switchyard Stage-IV. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 10.472 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.9 | Up-gradation of Vibration system at all units of Stage-IV:Stage-IV, KGSC, Pophali | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 1.443 | 1.5041 | 1.5041 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.10 | Replacement of station battery set of 220V, 2000Ah capacity at Stage-IV. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 2.385 | 2.3649 | 2.3649 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.11 | Renovations and modernization of 1500kg capacity passenger cum goods lifts (2 Nos) for KGSC, Stage-IV | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.968 | 0.85208 | 0.85208 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.12 | Replacement of existing 3x7.5 TR Air conditioning package units at Stage-I&II control room by new 3x11 TR Air conditioning package units | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.345 | 0.16909 | 0.16909 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.351 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Upgradation of Governing System at Stage-I, KDPH& Stage-III at KGSC, Pophali | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 19.1651 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Up gradation of DIGIPID1500 governing system with new governor (TSLG) for all units of stage-I | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 6.0888 | 3.89 | 3.89 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.2 | Up-gradation of governing system at Koyna Dam Power House (KDPH) Koynanagar | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 2.924 | 1.41 | 1.41 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.3 | Up-gradation of the Governing system at Stage-III & Other Charges (P&F, Insurance etc) | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 9.5523 | 4.6 | 4.6 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Refurbishment of 24 KV Generator Circuit Breakers (ABB Make) for four units at stage-IV, KGSC, Pophali | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 10.5726 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Supply spares for 24KV Generator Circuit Breaker System refurbishment (For 4 Units) | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 6.5702 | 6.5421 | 6.5421 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Supervision charges for 24 KV Generator Circuit Breaker System Unit. Preparation charges, Travel & transportation charges, local conveyance. Lumpsum rental charges of necessary tools & tackles required during O/H work charges | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 3.8704 | 3.8216 | 3.8216 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 0.132 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Up-gradation of Excitation system at Stage-I&II, PLC & SCADA system at Stage-II and DG Set at Stage-IV at KGSC, Pophali | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 9.863 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | Up gradation of Stage-I&II(4x70MW+4x80 MW) Static Semipol Excitation System with Latest Advanced Excitation System | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 9.863 | 5.763 | 5.76 | 0.003 | 0 | 0 |  |  | 0 | 0.003 | 0 | 0
15.2 | Up gradation of existing unit PLC and SCADA automation of 4x80 MW Koyna stage-II units | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 4.232 | 4.3 | 4.3 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.3 | Up gradation of one 1500 KVA DG set, at KGSC, Stage-IV | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 1.6 | 1.81 | 1.81 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 1.103 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Repair works in Emergency Valve Tunnel (EVT) and surge well at Stage I/II, KGSC, Pophali | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 28.0371 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Sealing and stabilization of EVT Tunnel left side wall and carven portion of EVT and Ventilation Tunnel. | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 8.307 | 19.5731 | 18.03 | 1.5431 | 0 | 0 |  |  | 0 | 1.5431 | 0 | 0
17.2 | Structural Strengthening and Sealing Cracks and Cavities in Surge Shaft RCC Staining Wall from inside | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 18.6602 | 0.3875 | 0 | 0.3875 | 0 | 0 |  |  | 0 | 0.3875 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 1.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-8.1 | Advance Multipurpose Fire Tender | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-8.2 | Normal Multipurpose Fire Tender | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Refurbishment of cooling and drainage water system along with replacement of 5 no's of cooling water pumps by new stage -IV KGSC Pophali | MERC/CAPEX/2023-2024/MSPGCL/0201 | 2024-03-21 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Refurbishment of cooling and drainage water system along with replacement of 5 no's of cooling water pumps by new stage -IV KGSC Pophali | MERC/CAPEX/2023-2024/MSPGCL/0201 | 2024-03-21 | 0 | 27.83 | 27.83 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0201 | 2024-03-21 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[8 empty] | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | Refurbishment of GIS T155 as per M4 Schedule at KGSC Stage-IV, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | Refurbishment of GIS T155 as per M4 Schedule at KGSC Stage-IV, Pophali | 0 | - | 0 | 0 | 0 | 0 | 49.08 | 49.08 |  |  | 49.08 | 0
20 | Various Civil work as per IB recommendation at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.1 | Various Civil work as per IB recommendation at KGSC, Pophali | 0 | - | 0 | 6 | 10.5 | -4.5 | 2.45 | 0 |  |  | 0 | -2.05
20.2 | construction of chainlink caging along entrance of St-I&II, St-III & St-IV | 0 | - | 0 | 4.5 | 0 | 4.5 | 2.03 | 0 |  |  | 0 | 6.53
21 | Stabilization and Mitigation of Landslide Prone Areas at KGSC, Mahagenco, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Stabilization and Mitigation of Landslide Prone Areas | 0 | - | 0 | 17 | 18 | -1 | 5.6 | 5.6 |  |  | 5.6 | -1
21.2 | Construction of retaining wall | 0 | - | 0 | 5 | 5 | 0 | 1.9 | 1.9 |  |  | 1.9 | 0
21.3 | Dredging river and nallah | 0 | - | 0 | 0.4 | 0.4 | 0 | 0 | 0 |  |  | 0 | 0
22 | Various Performance Improvement related schemes for FY 2026-27 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.1 | Supply of New Runner for Francis Turbine 80 MW at KGSC Stage-III | 0 | - | 0 | 0 | 0 | 0 | 11 | 11 |  |  | 11 | 0
22.2 | Supply of 2 Nos. injector along with injector shaft for Stage-I Units (70 MW) at Stage I & II KGSC, Pophali . | 0 | - | 0 | 0 | 0 | 0 | 4 | 4 |  |  | 4 | 0
22.3 | Supply of 1 No. injector for Stage-II Units (80 MW) at Stage I & II KGSC, Pophali . | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
22.4 | Upgradation of AC Chiiler system at Stage I & II | 0 | - | 0 | 0 | 0 | 0 | 7 | 7 |  |  | 7 | 0
22.5 | Design, manufacturing, supply, erection, testing and commissioning of LGB and UGB cooler modifications at KGSC Stage I&II | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
23 | Replacement of existing Generator transformer of all units (04 x 80 MW) in phase manner (one unit per year) at Stage-III, KGSC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.1 | Replacement of existing Generator transformer of all units (04 x 80 MW) in phase manner (one unit per year) at Stage-III, KGSC | 0 | - | 0 | 0 | 0 | 0 | 30 | 30 |  |  | 30 | 0
24 | Implementation of PLC & SCADA system (DSC based) for all units (04 x 80 MW) units in phase manner (two unit per year) at Stage-III, KGSC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.1 | Implementation of PLC & SCADA system (DSC based) for all units (04 x 80 MW) units in phase manner (two unit per year) at Stage-III, KGSC | 0 | - | 0 | 0 | 0 | 0 | 15 | 15 |  |  | 15 | 0
25 | Various Performance Improvement related schemes for FY 2027-28 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.1 | Refurbishment of Stage-1, Unit No-1,2,3 & 4 PLC System and Implementation of SCADA System. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.2 | Supply, installation & commissioning of New PLC & Centralog system for all four units at St-IV, KGSC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.3 | Supply, installation & commissioning of New excitation system for all four units at St-IV, KGSC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | Various Performance Improvement related schemes for FY 2028-29 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.1 | Upgradation of 11 KV Auxiliary breaker at St-I&II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.2 | Supply of Dry Type, 630 KVA 16 KV / 570 V Single Phase Excitation Transformers (Qty. 12 Nos.) at KGSC Stage-IV, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.3 | Supply, Installation & Commissioning of 16.5 KV / 433 V, 5MVA Unit Auxiliary Transformers (Qty. 02) at KGSC Stage-IV. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.4 | Upgradation of 2.2 KV Auxiliary Breaker with 3.3 KV Breaker along with Auxiliary Transformers at St-I&II. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.5 | Supply of 11KV Cable alongwith Breaker Panels for Auxiliary Supply from 8-Pole Switchyard Stage- I and II to Stage-IV Powerhouse at KGSC Stage-IV, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.6 | Replacement of 220 KV isolator of Stage II bay at 220 KV Stage I & II Switchyard | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | Various Performance Improvement related schemes for FY 2029-30 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.1 | Design Engineering and manufacturing, supply, erection, commissioning & testing of New Pelton runner for Stage-I units (70 MW) at Stage-I&II, KGSC, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.2 | Upgradation of Generator and Generator transformer electromagnetic protection relays with numeric relays for Stage 1 & 2. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.3 | Renovation of old system by full proof modern digital governing system, static/brushless excitation system and generator stator and rotor winding by class 'F' insulation at St-I&II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.4 | Design, manufacturing, supply, erection, testing and commissioning of Hydrostatic lubrication system for Units at KGSC Stage I & II, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.5 | Replacement of CW pumps and Motors along with starter pannel at St-I&II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.6 | Supply of Generator air coolers (16 Nos) for Stage II Units (80 MW) at KGSC, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.7 | Conversion of Stator Core Insulation & Stator Winding from Class ‘B’ to Class ‘F’ for Unit No. 8 (80MW, 11KV, 375RPM, AEG Germany make) of Stage II, KGSC, Pophali on Turnkey Basis. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.8 | Up-gradation of existing 'B' class insulation of Generator stator to 'F' class insulation of 2X18MW Koyna Dam Power House, Koynanagar. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.9 | Supply and replacement of Generator air cooler system by new higher efficiency coolers for 2X18MW Koyna Dam Power House, Koynanagar. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | <Auto Transformer Oil Insulation Test kit (BDV Kit)> | N.A. | - | 0 | 0.03953 | 0.03953 | 0 | 0 | 0 |  |  | 0 | 0
2 | <Man coolers pedestal fans at KGSC,Pophali> | N.A. | - | 0 | 0.034143 | 0.034143 | 0 | 0 | 0 |  |  | 0 | 0
3 | < 5 KV Digital Insulation Tester> | N.A. | - | 0 | 0.029798 | 0.029798 | 0 | 0 | 0 |  |  | 0 | 0
4 | <Split AC Unit,Window AC Unit,Refrigerator,Ped> | N.A. | - | 0 | 0.017857 | 0.017857 | 0 | 0 | 0 |  |  | 0 | 0
5 | <Earth Resistance Tester at ,Pophali. TIC STAGE IV> | N.A. | - | 0 | 0.016839 | 0.016839 | 0 | 0 | 0 |  |  | 0 | 0
6 | <Tools and Tackles at St-IV,KGSC,Pophali> | N.A. | - | 0 | 0.034609 | 0.034609 | 0 | 0 | 0 |  |  | 0 | 0
7 | <New portable Fire Fighting Diesel Pumps for Dewatering> | N.A. | - | 0 | 0.09697 | 0.09697 | 0 | 0 | 0 |  |  | 0 | 0
8 | <Visitors chairs for, Pophali KGSC> | N.A. | - | 0 | 0.033188 | 0.033188 | 0 | 0 | 0 |  |  | 0 | 0
9 | <Installation of new racks inside various/new slotted angle racks > | N.A. | - | 0 | 0.039648 | 0.039648 | 0 | 0 | 0 |  |  | 0 | 0
10 | <Supply of chairs for KGSC, Pophali> | N.A. | - | 0 | 0.044238 | 0.044238 | 0 | 0 | 0 |  |  | 0 | 0
11 | <Laser Jet NetwoksPrinters at KGSC, Pophali> | N.A. | - | 0 | 0.084075 | 0.084075 | 0 | 0 | 0 |  |  | 0 | 0
12 | <Night Vision Binoculars> | N.A. | - | 0 | 0.023411 | 0.023411 | 0 | 0 | 0 |  |  | 0 | 0
13 | <TATA Star Bus-32 seater LCV MH08-9358> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | <TATA Star Bus-32 seater LCV MH08-9359> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | <Vehicle No.MH 08-9401 TATA Star Bus 32 seater> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | <Not in use DCM Toyato Bus MH-1> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | <Not in use DCM Toyato Mini Bus> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | <Digital Multimeters, Clamp Meter & Insulation resistance tester for TIC, Stage I&II, Pophali> | N.A. | - | 0 | 0.028928 | 0.028928 | 0 | 0 | 0 |  |  | 0 | 0
19 | <Transformer Winding resistance measurement kit at Stage-III, Alore> | N.A. | - | 0 | 0.024338 | 0.024338 | 0 | 0 | 0 |  |  | 0 | 0
20 | <Multifunc A3 Scanner & all in one A4 laser printer Technical Purchase , Account Section, H.R. ,MPD> | N.A. | - | 0 | 0.032521 | 0.032521 | 0 | 0 | 0 |  |  | 0 | 0
21 | <Temperature Calibrator at St-IV, KGSC,Pophali> | N.A. | - | 0 | 0.012272 | 0.012272 | 0 | 0 | 0 |  |  | 0 | 0
22 | < 1 no. new departmental car Maruti Sweft Desire for conveyance of Chief Engr> | N.A. | - | 0 | 0.077924 | 0.077924 | 0 | 0 | 0 |  |  | 0 | 0
23 | <Hitachi A/c Two.NO.VIP Rest House> | N.A. | - | 0 | 0.008 | 0.008 | 0 | 0 | 0 |  |  | 0 | 0
24 | <Inverter Split AC Unit, Desert Coolers Water Coolers for KGSC, Pophali> | N.A. | - | 0 | 0.0070799 | 0.0070799 | 0 | 0 | 0 |  |  | 0 | 0
25 | <Advanced ISDN EPABX system for Koyna Generating St ntercom Telephone Advanced ISDN EPABX system for Koyna Generating Station Complex> | N.A. | - | 0 | 0.029645 | 0.029645 | 0 | 0 | 0 |  |  | 0 | 0
26 | <TATA Sumo MH-14/9763 1 No> | N.A. | - | 0 | 0.041197 | 0.041197 | 0 | 0 | 0 |  |  | 0 | 0
27 | <Ambulance TATA make MH-31/4475 1 No> | N.A. | - | 0 | 0.036143 | 0.036143 | 0 | 0 | 0 |  |  | 0 | 0
28 | <Supply of 1 No of Ambulance Vane for Pophali> | N.A. | - | 0 | 0.14883 | 0.14883 | 0 | 0 | 0 |  |  | 0 | 0
29 | <Supply of 1 No of Ambulance Vane for Pophali> | N.A. | - | 0 | 0.14883 | 0.14883 | 0 | 0 | 0 |  |  | 0 | 0
30 | <HITACHI Make 2 TR non inverter split Air conditioner> | N.A. | - | 0 | 0.16739 | 0.16739 | 0 | 0 | 0 |  |  | 0 | 0
31 | <250 KVA D.G. Set Model KG1-250WS> | N.A. | - | 0 | 0.19222 | 0.19222 | 0 | 0 | 0 |  |  | 0 | 0
32 | <Dell laptops at KGSC Pophali> | N.A. | - | 0 | 0.0156 | 0.0156 | 0 | 0 | 0 |  |  | 0 | 0
33 | <A.C. Plant chiller 515 to 535 TRx2 at kgsc,Pophali> | N.A. | - | 0 | 2.1144 | 2.1144 | 0 | 0 | 0 |  |  | 0 | 0
34 | <Supply of RDP make Computers at KGSC> | N.A. | - | 0 | 0.43135 | 0.43135 | 0 | 0 | 0 |  |  | 0 | 0
35 | <Welding Machine for KDPH> | N.A. | - | 0 | 0.001039 | 0.001039 | 0 | 0 | 0 |  |  | 0 | 0
36 | <Material handling trolley for Majot store> | N.A. | - | 0 | 0.0014198 | 0.0014198 | 0 | 0 | 0 |  |  | 0 | 0
37 | <Canon LiDe 300 IN Scanner> | N.A. | - | 0 | 0.00048 | 0.00048 | 0 | 0 | 0 |  |  | 0 | 0
38 | <Supply of Pedestal fan at KDPH> | N.A. | - | 0 | 0.015 | 0.015 | 0 | 0 | 0 |  |  | 0 | 0
39 | <Supply of Refrigerator 290 LTR double door capacity> | N.A. | - | 0 | 0.0022 | 0.0022 | 0 | 0 | 0 |  |  | 0 | 0
40 | <Supply of Refrigerator 290 LTR double door capacity> | N.A. | - | 0 | 0.0022 | 0.0022 | 0 | 0 | 0 |  |  | 0 | 0
41 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.007 | 0.007 | 0 | 0 | 0 |  |  | 0 | 0
42 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.0035 | 0.0035 | 0 | 0 | 0 |  |  | 0 | 0
43 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.0035 | 0.0035 | 0 | 0 | 0 |  |  | 0 | 0
44 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.0035 | 0.0035 | 0 | 0 | 0 |  |  | 0 | 0
45 | <Redmi 10 prime Mobile Black for Chief Engineer> | N.A. | - | 0 | 0.0015 | 0.0015 | 0 | 0 | 0 |  |  | 0 | 0
46 | <TATA Sumo MH-14/9763 1 No> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47 | <Ambulance TATA make MH-31/4475 1 No> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48 | <Supply of Two Post Lift (4 Ton) for Vehicle Maint.> | N.A. | - | 0 | 0.014396 | 0.014396 | 0 | 0 | 0 |  |  | 0 | 0
49 | Supply,Installation, commissioning and testing of 415V, 3 Phase diesel generating setof 125 KVA capacity for Admin building emergency power supply backup at KGSC,Pophali. | N.A. | - | 0 | 0.0995 | 0.0995 | 0 | 0 | 0 |  |  | 0 | 0
50 | Design,Manufacturing, supply erriction and commissioning of 60 MT surface mounted (pit type/ platform type) weighbridge at major stores 'c' pophali | N.A. | - | 0 | 0.21577 | 0.21577 | 0 | 0 | 0 |  |  | 0 | 0
51 | Supply of Hydraulically operated manual stacker for Material Handling at Major Store "C", KGSC, Pophali | N.A. | - | 0 | 0.00524 | 0.00524 | 0 | 0 | 0 |  |  | 0 | 0
52 | Supply of Indef makes Chain Pulley Blocks | N.A. | - | 0 | 0.011505 | 0.011505 | 0 | 0 | 0 |  |  | 0 | 0
53 | Supply of Motwane Make ‘Digital Multimeter and AC Multimeter | N.A. | - | 0 | 0.018458 | 0.018458 | 0 | 0 | 0 |  |  | 0 | 0
54 | Supply 1 Ton split AC Daiken make for control room cabin Operation Stage III | N.A. | - | 0 | 0.00396 | 0.00396 | 0 | 0 | 0 |  |  | 0 | 0
55 | Emer Rescue cum Multipurpose Fire Tender | N.A. | - | 0 | 2.0039 | 2.0039 | 0 | 0 | 0 |  |  | 0 | 0
56 | Procurement of portable chairs for training sub centre | N.A. | - | 0 | 0.01308 | 0.01308 | 0 | 0 | 0 |  |  | 0 | 0
57 | Procurement of portable computer tables | N.A. | - | 0 | 0.0033449 | 0.0033449 | 0 | 0 | 0 |  |  | 0 | 0
58 | Purchase of High back chair (3 Nos.) in conferenc hall | N.A. | - | 0 | 0.0044014 | 0.0044014 | 0 | 0 | 0 |  |  | 0 | 0
59 | Supply of Water Purifier at MSPGCL KGSC Pophali. | N.A. | - | 0 | 0.005 | 0.005 | 0 | 0 | 0 |  |  | 0 | 0
60 | Interactive Digital LV SCREEN 6.56 FT X 3.28 FT | N.A. | - | 0 | 0.01295 | 0.01295 | 0 | 0 | 0 |  |  | 0 | 0
61 | Network Attached Storage Server at KGSC, Pophali. | N.A. | - | 0 | 0.023333 | 0.023333 | 0 | 0 | 0 |  |  | 0 | 0
62 | Supply of A4 Printer at KGSC, Pophali. | N.A. | - | 0 | 0.0099995 | 0.0099995 | 0 | 0 | 0 |  |  | 0 | 0
63 | Supply of A4 Scanner, A3 & MF Printer at KGSC, Pop | N.A. | - | 0 | 0.0586 | 0.0586 | 0 | 0 | 0 |  |  | 0 | 0
64 | Supply of Various Hard Disks for Network Attached | N.A. | - | 0 | 0.021806 | 0.021806 | 0 | 0 | 0 |  |  | 0 | 0
65 | Supply of Video conference Microphone at KGSC, | N.A. | - | 0 | 0.0021512 | 0.0021512 | 0 | 0 | 0 |  |  | 0 | 0
66 | Supply of Video Conference Screen at KGSC Pophali | N.A. | - | 0 | 0.02 | 0.02 | 0 | 0 | 0 |  |  | 0 | 0
67 | Supply of Video conference Screen at KGSC, Pophali | N.A. | - | 0 | 0.0109 | 0.0109 | 0 | 0 | 0 |  |  | 0 | 0
68 | Supply of Kelvinator / Godrej / Croma Make Refrigerator | N.A. | - | 0 | 0.010932 | 0.010932 | 0 | 0 | 0 |  |  | 0 | 0
69 | supply of Bosch make High Pressure Washer at Mecha | N.A. | - | 0 | 0.0020649 | 0.0020649 | 0 | 0 | 0 |  |  | 0 | 0
70 | Supply of Pneumatic Tools for Mechanical Maintenan | N.A. | - | 0 | 0.035259 | 0.035259 | 0 | 0 | 0 |  |  | 0 | 0
72 | Low BACK Revolving Chairs 45 No & Desk Chair 2 No | N.A. | - | 0 | 0.020945 | 0.020945 | 0 | 0 | 0 |  |  | 0 | 0
73 | Supply of Tables at KGSC | N.A. | - | 0 | 0.037339 | 0.037339 | 0 | 0 | 0 |  |  | 0 | 0
74 | Supply of Visitor Chairs & Office chairs at KGSC, | N.A. | - | 0 | 0.033201 | 0.033201 | 0 | 0 | 0 |  |  | 0 | 0
75 | water purifier for colony electrical maintenance | N.A. | - | 0 | 0.00174 | 0.00174 | 0 | 0 | 0 |  |  | 0 | 0
76 | Projectors and Motorized Projector Screens (2+2) | N.A. | - | 0 | 0.03481 | 0.03481 | 0 | 0 | 0 |  |  | 0 | 0
77 | Acer make Computers at KGSC Pophali.21 No. | N.A. | - | 0 | 0.119 | 0.119 | 0 | 0 | 0 |  |  | 0 | 0
78 | Acer make Laptops at KGSC Pophali. | N.A. | - | 0 | 0.030088 | 0.030088 | 0 | 0 | 0 |  |  | 0 | 0
79 | APS Smart UPS Xl 2200 VA RM 3U 230 | N.A. | - | 0 | 0.015983 | 0.015983 | 0 | 0 | 0 |  |  | 0 | 0
80 | BATRY 12V 75 AH BATTREY 11 PLATE | N.A. | - | 0 | 0.017629 | 0.017629 | 0 | 0 | 0 |  |  | 0 | 0
81 | Supply & installation of IP Camera System and network spare | N.A. | - | 0 | 0.025807 | 0.025807 | 0 | 0 | 0 |  |  | 0 | 0
82 | Gym Equipments at MSPGCL Recreation club , 33 Item | N.A. | - | 0 | 0.047834 | 0.047834 | 0 | 0 | 0 |  |  | 0 | 0
0 | Non-DPR schemes (3 Nos) for FY 2024-25 at KGSC Pophali | Board Resolution No-MSPGCL/BM-219/Item 219.7 dtd.24.07.2023 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
83 | Up-gradation of thyristor based 48V Battery Chargers (4 nos) by SMPS Microprocessor based dual float cum boost Battery Chargers at Stage-III, Stage-I&II and KDPH at KGSC, Pophali | 0 | - | 0 | 1.57 | 1.57 | 0 | 0 | 0 |  |  | 0 | 0
84 | Up-gradation of thyristor based 220V Battery Chargers (4 nos) by SMPS Microprocessor based dual float cum boost Battery Chargers at Stage-III and Stage-I&II at KGSC, Pophali | 0 | - | 0 | 3.79 | 3.79 | 0 | 0 | 0 |  |  | 0 | 0
85 | Retrofitting of Generator and Gen. Transformer protection relay by Numerical protection system at KGSC stage III, Alore | 0 | - | 0 | 4.78 | 4.78 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Non-DPR schemes (2 Nos) for FY 2025-26 at KGSC Pophali | Yet Not Submitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
86 | Supply, Erection, Commissioning & Retrofitting of 220 VDC Ni-cadmium type Battery set (4 Nos) having different ampere hour capacity at Stage-I&II and Stage-IV | 0 | - | 0 | 9.23 | 9.23 | 0 | 0 | 0 |  |  | 0 | 0
87 | Supply, Erection, Commissioning & Retrofitting of 48VDC, 300AH Ni-cadmium type Battery set at Stage-I&II switchyard | 0 | - | 0 | 0.37 | 0.37 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 230.7749 | 228.0426 | 2.7323 | 135.06 | 130.58 | 0 | 0 | 130.58 | 7.2123
FY 2027-28
a) DPR Schemes
(i) Submitted to MERC
1 | Various improvement schemes at Pophali Hydro Power Station | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 11.9001 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | ALSPA HMI Series 6 Centralog System | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 6.8555 | 7.8386 | 7.8386 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | 1 X 525 Tr chiller unit | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 1.23 | 1.15 | 1.15 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Micom P343 Numerical generator protection relay with 24 DI & 24 DO with CLIO input. (5 Nos) | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 1.4675 | 1.474 | 1.474 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.4 | Security Building at Stage-IV | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 0.16446 | 0.18377 | 0.18377 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.5 | Construction of recreation club building | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 1.8204 | 2.1946 | 2.1946 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.6 | Security Building for Stage-IV at EVT | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 0.22776 | 0.25961 | 0.25961 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 0.1344 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Various DPR Schemes for Civil Section, KGSC Pophali | MERC/CAPEX/20152016/00907 | 2015-11-05 | 21.201 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Providing Road Network at KGSC, Pophali | MERC/CAPEX/20152016/00907 | 2015-11-05 | 7.776 | 7.0182 | 7.0182 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.2 | Modernisation & Refurbishing of Residential Complex | MERC/CAPEX/20152016/00907 | 2015-11-05 | 8.985 | 8.9365 | 8.9365 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.3 | Water Supply & Sanitory Works | MERC/CAPEX/20152016/00907 | 2015-11-05 | 4.44 | 5.9018 | 4.1022 | 1.7997 | 0 | 0 |  |  | 0 | 1.7997 | 0 | 0
4 | Various Performance Improvement related schemes at KGSC, Pophali | MERC/CAPEX/20162017/01018 | 2016-11-17 | 12.9765 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Up gradation of 245 kV CTs at Stage-I&II SY | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.9624 | 2.09 | 2.09 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Up gradation of 245 kV PTs at Stage-I&II SY | MERC/CAPEX/20162017/01018 | 2016-11-17 | 0.40509 | 0.3417 | 0.3417 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.3 | Up gradation of CW system of Stage-I&II Units | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.7099 | 1.4731 | 1.4731 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.4 | Up gradation of Intercom Exchange System between Stage-I&II PH & Admin. Bldg & Staff Colony. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 0.43826 | 0.359 | 0.359 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.5 | Up gradation of 220 kV Breakers at KDPH SY | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.289 | 0.979 | 0.979 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.6 | Procurement of Governing Oil Pumps for Stage-III Units. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.2316 | 0.70174 | 0.70174 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.7 | Up gradation of TG Governing system of Stage-IV Units. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 2.2152 | 2.7472 | 2.7472 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.8 | Up gradation of Numerical Protection system of Stage-IV Units. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 2.8249 | 2.8674 | 2.8674 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01018 | 2016-11-17 | 0.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7 | Replacement of Generator Stator of unit No. 11 (80 MW), Stage III, KGSC Pophali | MERC/CAPEX/20172018/04592 | 2017-11-07 | 22.54 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Replacement of Generator Stator of unit No. 11 (80 MW), Stage III, KGSC Pophali | MERC/CAPEX/20172018/04592 | 2017-11-07 | 22.54 | 19.409 | 19.41 | -0.001 | 0 | 0 |  |  | 0 | -0.001 | 0 | 0
8 | Procurement of new pelton wheel runners (2 Nos.) for Stage II at KGSC, Pophali | MERC/CAPEX/20172018/04421 | 2017-10-24 | 13.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement of new pelton wheel runners (2 Nos.) for Stage II at KGSC, Pophali | MERC/CAPEX/20172018/04421 | 2017-10-24 | 13.07 | 10.38 | 10.38 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Implementation of 12 Nos. of various schemes at KGSC, Pophali. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 26.891 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Replacement of UGB (8 Nos), LGB (8 Nos) & Generator air coolers (8 Nos) for Stage-I | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 1.344 | 0.85 | 0.85 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Retrofitting of Generator & Gen-Transformer relays by new numerical protection system at Koyna Dam Power House (KDPH) Koynanagar | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 1.097 | 1.08 | 1.08 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.3 | Replacement of two 220V Battery chargers with 220V dual float cum boost (60A) battery Charger including DCDB at KDPH, Koynanagar | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.202 | 0.13782 | 0.13782 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.4 | Replacement of 220KV current transformer (54 Nos), Potential transformer (13 Nos),110KV Current Transformer (14 Nos)& Potential Transformer (4 Nos),Stage-III. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 5.281 | 5.28 | 5.28 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.5 | Replacement of Generator Air Cooler (32 Nos), St-III | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 2.413 | 2.0541 | 2.0541 | -4e-06 | 0 | 0 |  |  | 0 | -4e-06 | 0 | 0
11.6 | Replacement of 48 Volt, 1000 AH tubular battery set with 48 Volt, 750AH Plante type battery set at KGSC, Stage-III | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.318 | 0.30942 | 0.30942 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.7 | Replacement of 220V-150AH Battery set with Ni-Cad type, along with standard accessories for UPS scheme at Stage-IV | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.272 | 0.25759 | 0.25759 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.8 | Reliability enhancement of Gas Insulated Switchyard Stage-IV. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 10.472 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.9 | Up-gradation of Vibration system at all units of Stage-IV:Stage-IV, KGSC, Pophali | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 1.443 | 1.5041 | 1.5041 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.10 | Replacement of station battery set of 220V, 2000Ah capacity at Stage-IV. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 2.385 | 2.3649 | 2.3649 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.11 | Renovations and modernization of 1500kg capacity passenger cum goods lifts (2 Nos) for KGSC, Stage-IV | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.968 | 0.85208 | 0.85208 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.12 | Replacement of existing 3x7.5 TR Air conditioning package units at Stage-I&II control room by new 3x11 TR Air conditioning package units | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.345 | 0.16909 | 0.16909 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.351 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Upgradation of Governing System at Stage-I, KDPH& Stage-III at KGSC, Pophali | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 19.1651 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Up gradation of DIGIPID1500 governing system with new governor (TSLG) for all units of stage-I | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 6.0888 | 3.89 | 3.89 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.2 | Up-gradation of governing system at Koyna Dam Power House (KDPH) Koynanagar | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 2.924 | 1.41 | 1.41 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.3 | Up-gradation of the Governing system at Stage-III & Other Charges (P&F, Insurance etc) | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 9.5523 | 4.6 | 4.6 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Refurbishment of 24 KV Generator Circuit Breakers (ABB Make) for four units at stage-IV, KGSC, Pophali | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 10.5726 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Supply spares for 24KV Generator Circuit Breaker System refurbishment (For 4 Units) | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 6.5702 | 6.5421 | 6.5421 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Supervision charges for 24 KV Generator Circuit Breaker System Unit. Preparation charges, Travel & transportation charges, local conveyance. Lumpsum rental charges of necessary tools & tackles required during O/H work charges | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 3.8704 | 3.8216 | 3.8216 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 0.132 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Up-gradation of Excitation system at Stage-I&II, PLC & SCADA system at Stage-II and DG Set at Stage-IV at KGSC, Pophali | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 9.863 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | Up gradation of Stage-I&II(4x70MW+4x80 MW) Static Semipol Excitation System with Latest Advanced Excitation System | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 9.863 | 5.763 | 5.76 | 0.003 | 0 | 0 |  |  | 0 | 0.003 | 0 | 0
15.2 | Up gradation of existing unit PLC and SCADA automation of 4x80 MW Koyna stage-II units | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 4.232 | 4.3 | 4.3 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.3 | Up gradation of one 1500 KVA DG set, at KGSC, Stage-IV | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 1.6 | 1.81 | 1.81 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 1.103 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Repair works in Emergency Valve Tunnel (EVT) and surge well at Stage I/II, KGSC, Pophali | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 28.0371 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Sealing and stabilization of EVT Tunnel left side wall and carven portion of EVT and Ventilation Tunnel. | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 8.307 | 19.5731 | 18.03 | 1.5431 | 0 | 0 |  |  | 0 | 1.5431 | 0 | 0
17.2 | Structural Strengthening and Sealing Cracks and Cavities in Surge Shaft RCC Staining Wall from inside | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 18.6602 | 0.3875 | 0 | 0.3875 | 0 | 0 |  |  | 0 | 0.3875 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 1.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-8.1 | Advance Multipurpose Fire Tender | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-8.2 | Normal Multipurpose Fire Tender | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Refurbishment of cooling and drainage water system along with replacement of 5 no's of cooling water pumps by new stage -IV KGSC Pophali | MERC/CAPEX/2023-2024/MSPGCL/0201 | 2024-03-21 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Refurbishment of cooling and drainage water system along with replacement of 5 no's of cooling water pumps by new stage -IV KGSC Pophali | MERC/CAPEX/2023-2024/MSPGCL/0201 | 2024-03-21 | 0 | 27.83 | 27.83 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0201 | 2024-03-21 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[8 empty] | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | Refurbishment of GIS T155 as per M4 Schedule at KGSC Stage-IV, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | Refurbishment of GIS T155 as per M4 Schedule at KGSC Stage-IV, Pophali | 0 | - | 0 | 49.08 | 49.08 | 0 | 0 | 0 |  |  | 0 | 0
20 | Various Civil work as per IB recommendation at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.1 | Various Civil work as per IB recommendation at KGSC, Pophali | 0 | - | 0 | 8.45 | 10.5 | -2.05 | 0 | 0 |  |  | 0 | -2.05
20.2 | construction of chainlink caging along entrance of St-I&II, St-III & St-IV | 0 | - | 0 | 6.53 | 0 | 6.53 | 0 | 0 |  |  | 0 | 6.53
21 | Stabilization and Mitigation of Landslide Prone Areas at KGSC, Mahagenco, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Stabilization and Mitigation of Landslide Prone Areas | 0 | - | 0 | 22.6 | 23.6 | -1 | 0 | 0 |  |  | 0 | -1
21.2 | Construction of retaining wall | 0 | - | 0 | 6.9 | 6.9 | 0 | 0 | 0 |  |  | 0 | 0
21.3 | Dredging river and nallah | 0 | - | 0 | 0.4 | 0.4 | 0 | 0 | 0 |  |  | 0 | 0
22 | Various Performance Improvement related schemes for FY 2026-27 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.1 | Supply of New Runner for Francis Turbine 80 MW at KGSC Stage-III | 0 | - | 0 | 11 | 11 | 0 | 0 | 0 |  |  | 0 | 0
22.2 | Supply of 2 Nos. injector along with injector shaft for Stage-I Units (70 MW) at Stage I & II KGSC, Pophali . | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
22.3 | Supply of 1 No. injector for Stage-II Units (80 MW) at Stage I & II KGSC, Pophali . | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
22.4 | Upgradation of AC Chiiler system at Stage I & II | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
22.5 | Design, manufacturing, supply, erection, testing and commissioning of LGB and UGB cooler modifications at KGSC Stage I&II | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
23 | Replacement of existing Generator transformer of all units (04 x 80 MW) in phase manner (one unit per year) at Stage-III, KGSC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.1 | Replacement of existing Generator transformer of all units (04 x 80 MW) in phase manner (one unit per year) at Stage-III, KGSC | 0 | - | 0 | 30 | 30 | 0 | 30 | 30 |  |  | 30 | 0
24 | Implementation of PLC & SCADA system (DSC based) for all units (04 x 80 MW) units in phase manner (two unit per year) at Stage-III, KGSC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.1 | Implementation of PLC & SCADA system (DSC based) for all units (04 x 80 MW) units in phase manner (two unit per year) at Stage-III, KGSC | 0 | - | 0 | 15 | 15 | 0 | 15 | 15 |  |  | 15 | 0
25 | Various Performance Improvement related schemes for FY 2027-28 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.1 | Refurbishment of Stage-1, Unit No-1,2,3 & 4 PLC System and Implementation of SCADA System. | 0 | - | 0 | 0 | 0 | 0 | 4.5 | 4.5 |  |  | 4.5 | 0
25.2 | Supply, installation & commissioning of New PLC & Centralog system for all four units at St-IV, KGSC | 0 | - | 0 | 0 | 0 | 0 | 20 | 20 |  |  | 20 | 0
25.3 | Supply, installation & commissioning of New excitation system for all four units at St-IV, KGSC | 0 | - | 0 | 0 | 0 | 0 | 8 | 8 |  |  | 8 | 0
26 | Various Performance Improvement related schemes for FY 2028-29 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.1 | Upgradation of 11 KV Auxiliary breaker at St-I&II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.2 | Supply of Dry Type, 630 KVA 16 KV / 570 V Single Phase Excitation Transformers (Qty. 12 Nos.) at KGSC Stage-IV, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.3 | Supply, Installation & Commissioning of 16.5 KV / 433 V, 5MVA Unit Auxiliary Transformers (Qty. 02) at KGSC Stage-IV. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.4 | Upgradation of 2.2 KV Auxiliary Breaker with 3.3 KV Breaker along with Auxiliary Transformers at St-I&II. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.5 | Supply of 11KV Cable alongwith Breaker Panels for Auxiliary Supply from 8-Pole Switchyard Stage- I and II to Stage-IV Powerhouse at KGSC Stage-IV, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.6 | Replacement of 220 KV isolator of Stage II bay at 220 KV Stage I & II Switchyard | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | Various Performance Improvement related schemes for FY 2029-30 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.1 | Design Engineering and manufacturing, supply, erection, commissioning & testing of New Pelton runner for Stage-I units (70 MW) at Stage-I&II, KGSC, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.2 | Upgradation of Generator and Generator transformer electromagnetic protection relays with numeric relays for Stage 1 & 2. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.3 | Renovation of old system by full proof modern digital governing system, static/brushless excitation system and generator stator and rotor winding by class 'F' insulation at St-I&II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.4 | Design, manufacturing, supply, erection, testing and commissioning of Hydrostatic lubrication system for Units at KGSC Stage I & II, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.5 | Replacement of CW pumps and Motors along with starter pannel at St-I&II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.6 | Supply of Generator air coolers (16 Nos) for Stage II Units (80 MW) at KGSC, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.7 | Conversion of Stator Core Insulation & Stator Winding from Class ‘B’ to Class ‘F’ for Unit No. 8 (80MW, 11KV, 375RPM, AEG Germany make) of Stage II, KGSC, Pophali on Turnkey Basis. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.8 | Up-gradation of existing 'B' class insulation of Generator stator to 'F' class insulation of 2X18MW Koyna Dam Power House, Koynanagar. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.9 | Supply and replacement of Generator air cooler system by new higher efficiency coolers for 2X18MW Koyna Dam Power House, Koynanagar. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | <Auto Transformer Oil Insulation Test kit (BDV Kit)> | N.A. | - | 0 | 0.03953 | 0.03953 | 0 | 0 | 0 |  |  | 0 | 0
2 | <Man coolers pedestal fans at KGSC,Pophali> | N.A. | - | 0 | 0.034143 | 0.034143 | 0 | 0 | 0 |  |  | 0 | 0
3 | < 5 KV Digital Insulation Tester> | N.A. | - | 0 | 0.029798 | 0.029798 | 0 | 0 | 0 |  |  | 0 | 0
4 | <Split AC Unit,Window AC Unit,Refrigerator,Ped> | N.A. | - | 0 | 0.017857 | 0.017857 | 0 | 0 | 0 |  |  | 0 | 0
5 | <Earth Resistance Tester at ,Pophali. TIC STAGE IV> | N.A. | - | 0 | 0.016839 | 0.016839 | 0 | 0 | 0 |  |  | 0 | 0
6 | <Tools and Tackles at St-IV,KGSC,Pophali> | N.A. | - | 0 | 0.034609 | 0.034609 | 0 | 0 | 0 |  |  | 0 | 0
7 | <New portable Fire Fighting Diesel Pumps for Dewatering> | N.A. | - | 0 | 0.09697 | 0.09697 | 0 | 0 | 0 |  |  | 0 | 0
8 | <Visitors chairs for, Pophali KGSC> | N.A. | - | 0 | 0.033188 | 0.033188 | 0 | 0 | 0 |  |  | 0 | 0
9 | <Installation of new racks inside various/new slotted angle racks > | N.A. | - | 0 | 0.039648 | 0.039648 | 0 | 0 | 0 |  |  | 0 | 0
10 | <Supply of chairs for KGSC, Pophali> | N.A. | - | 0 | 0.044238 | 0.044238 | 0 | 0 | 0 |  |  | 0 | 0
11 | <Laser Jet NetwoksPrinters at KGSC, Pophali> | N.A. | - | 0 | 0.084075 | 0.084075 | 0 | 0 | 0 |  |  | 0 | 0
12 | <Night Vision Binoculars> | N.A. | - | 0 | 0.023411 | 0.023411 | 0 | 0 | 0 |  |  | 0 | 0
13 | <TATA Star Bus-32 seater LCV MH08-9358> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | <TATA Star Bus-32 seater LCV MH08-9359> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | <Vehicle No.MH 08-9401 TATA Star Bus 32 seater> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | <Not in use DCM Toyato Bus MH-1> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | <Not in use DCM Toyato Mini Bus> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | <Digital Multimeters, Clamp Meter & Insulation resistance tester for TIC, Stage I&II, Pophali> | N.A. | - | 0 | 0.028928 | 0.028928 | 0 | 0 | 0 |  |  | 0 | 0
19 | <Transformer Winding resistance measurement kit at Stage-III, Alore> | N.A. | - | 0 | 0.024338 | 0.024338 | 0 | 0 | 0 |  |  | 0 | 0
20 | <Multifunc A3 Scanner & all in one A4 laser printer Technical Purchase , Account Section, H.R. ,MPD> | N.A. | - | 0 | 0.032521 | 0.032521 | 0 | 0 | 0 |  |  | 0 | 0
21 | <Temperature Calibrator at St-IV, KGSC,Pophali> | N.A. | - | 0 | 0.012272 | 0.012272 | 0 | 0 | 0 |  |  | 0 | 0
22 | < 1 no. new departmental car Maruti Sweft Desire for conveyance of Chief Engr> | N.A. | - | 0 | 0.077924 | 0.077924 | 0 | 0 | 0 |  |  | 0 | 0
23 | <Hitachi A/c Two.NO.VIP Rest House> | N.A. | - | 0 | 0.008 | 0.008 | 0 | 0 | 0 |  |  | 0 | 0
24 | <Inverter Split AC Unit, Desert Coolers Water Coolers for KGSC, Pophali> | N.A. | - | 0 | 0.0070799 | 0.0070799 | 0 | 0 | 0 |  |  | 0 | 0
25 | <Advanced ISDN EPABX system for Koyna Generating St ntercom Telephone Advanced ISDN EPABX system for Koyna Generating Station Complex> | N.A. | - | 0 | 0.029645 | 0.029645 | 0 | 0 | 0 |  |  | 0 | 0
26 | <TATA Sumo MH-14/9763 1 No> | N.A. | - | 0 | 0.041197 | 0.041197 | 0 | 0 | 0 |  |  | 0 | 0
27 | <Ambulance TATA make MH-31/4475 1 No> | N.A. | - | 0 | 0.036143 | 0.036143 | 0 | 0 | 0 |  |  | 0 | 0
28 | <Supply of 1 No of Ambulance Vane for Pophali> | N.A. | - | 0 | 0.14883 | 0.14883 | 0 | 0 | 0 |  |  | 0 | 0
29 | <Supply of 1 No of Ambulance Vane for Pophali> | N.A. | - | 0 | 0.14883 | 0.14883 | 0 | 0 | 0 |  |  | 0 | 0
30 | <HITACHI Make 2 TR non inverter split Air conditioner> | N.A. | - | 0 | 0.16739 | 0.16739 | 0 | 0 | 0 |  |  | 0 | 0
31 | <250 KVA D.G. Set Model KG1-250WS> | N.A. | - | 0 | 0.19222 | 0.19222 | 0 | 0 | 0 |  |  | 0 | 0
32 | <Dell laptops at KGSC Pophali> | N.A. | - | 0 | 0.0156 | 0.0156 | 0 | 0 | 0 |  |  | 0 | 0
33 | <A.C. Plant chiller 515 to 535 TRx2 at kgsc,Pophali> | N.A. | - | 0 | 2.1144 | 2.1144 | 0 | 0 | 0 |  |  | 0 | 0
34 | <Supply of RDP make Computers at KGSC> | N.A. | - | 0 | 0.43135 | 0.43135 | 0 | 0 | 0 |  |  | 0 | 0
35 | <Welding Machine for KDPH> | N.A. | - | 0 | 0.001039 | 0.001039 | 0 | 0 | 0 |  |  | 0 | 0
36 | <Material handling trolley for Majot store> | N.A. | - | 0 | 0.0014198 | 0.0014198 | 0 | 0 | 0 |  |  | 0 | 0
37 | <Canon LiDe 300 IN Scanner> | N.A. | - | 0 | 0.00048 | 0.00048 | 0 | 0 | 0 |  |  | 0 | 0
38 | <Supply of Pedestal fan at KDPH> | N.A. | - | 0 | 0.015 | 0.015 | 0 | 0 | 0 |  |  | 0 | 0
39 | <Supply of Refrigerator 290 LTR double door capacity> | N.A. | - | 0 | 0.0022 | 0.0022 | 0 | 0 | 0 |  |  | 0 | 0
40 | <Supply of Refrigerator 290 LTR double door capacity> | N.A. | - | 0 | 0.0022 | 0.0022 | 0 | 0 | 0 |  |  | 0 | 0
41 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.007 | 0.007 | 0 | 0 | 0 |  |  | 0 | 0
42 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.0035 | 0.0035 | 0 | 0 | 0 |  |  | 0 | 0
43 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.0035 | 0.0035 | 0 | 0 | 0 |  |  | 0 | 0
44 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.0035 | 0.0035 | 0 | 0 | 0 |  |  | 0 | 0
45 | <Redmi 10 prime Mobile Black for Chief Engineer> | N.A. | - | 0 | 0.0015 | 0.0015 | 0 | 0 | 0 |  |  | 0 | 0
46 | <TATA Sumo MH-14/9763 1 No> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47 | <Ambulance TATA make MH-31/4475 1 No> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48 | <Supply of Two Post Lift (4 Ton) for Vehicle Maint.> | N.A. | - | 0 | 0.014396 | 0.014396 | 0 | 0 | 0 |  |  | 0 | 0
49 | Supply,Installation, commissioning and testing of 415V, 3 Phase diesel generating setof 125 KVA capacity for Admin building emergency power supply backup at KGSC,Pophali. | N.A. | - | 0 | 0.0995 | 0.0995 | 0 | 0 | 0 |  |  | 0 | 0
50 | Design,Manufacturing, supply erriction and commissioning of 60 MT surface mounted (pit type/ platform type) weighbridge at major stores 'c' pophali | N.A. | - | 0 | 0.21577 | 0.21577 | 0 | 0 | 0 |  |  | 0 | 0
51 | Supply of Hydraulically operated manual stacker for Material Handling at Major Store "C", KGSC, Pophali | N.A. | - | 0 | 0.00524 | 0.00524 | 0 | 0 | 0 |  |  | 0 | 0
52 | Supply of Indef makes Chain Pulley Blocks | N.A. | - | 0 | 0.011505 | 0.011505 | 0 | 0 | 0 |  |  | 0 | 0
53 | Supply of Motwane Make ‘Digital Multimeter and AC Multimeter | N.A. | - | 0 | 0.018458 | 0.018458 | 0 | 0 | 0 |  |  | 0 | 0
54 | Supply 1 Ton split AC Daiken make for control room cabin Operation Stage III | N.A. | - | 0 | 0.00396 | 0.00396 | 0 | 0 | 0 |  |  | 0 | 0
55 | Emer Rescue cum Multipurpose Fire Tender | N.A. | - | 0 | 2.0039 | 2.0039 | 0 | 0 | 0 |  |  | 0 | 0
56 | Procurement of portable chairs for training sub centre | N.A. | - | 0 | 0.01308 | 0.01308 | 0 | 0 | 0 |  |  | 0 | 0
57 | Procurement of portable computer tables | N.A. | - | 0 | 0.0033449 | 0.0033449 | 0 | 0 | 0 |  |  | 0 | 0
58 | Purchase of High back chair (3 Nos.) in conferenc hall | N.A. | - | 0 | 0.0044014 | 0.0044014 | 0 | 0 | 0 |  |  | 0 | 0
59 | Supply of Water Purifier at MSPGCL KGSC Pophali. | N.A. | - | 0 | 0.005 | 0.005 | 0 | 0 | 0 |  |  | 0 | 0
60 | Interactive Digital LV SCREEN 6.56 FT X 3.28 FT | N.A. | - | 0 | 0.01295 | 0.01295 | 0 | 0 | 0 |  |  | 0 | 0
61 | Network Attached Storage Server at KGSC, Pophali. | N.A. | - | 0 | 0.023333 | 0.023333 | 0 | 0 | 0 |  |  | 0 | 0
62 | Supply of A4 Printer at KGSC, Pophali. | N.A. | - | 0 | 0.0099995 | 0.0099995 | 0 | 0 | 0 |  |  | 0 | 0
63 | Supply of A4 Scanner, A3 & MF Printer at KGSC, Pop | N.A. | - | 0 | 0.0586 | 0.0586 | 0 | 0 | 0 |  |  | 0 | 0
64 | Supply of Various Hard Disks for Network Attached | N.A. | - | 0 | 0.021806 | 0.021806 | 0 | 0 | 0 |  |  | 0 | 0
65 | Supply of Video conference Microphone at KGSC, | N.A. | - | 0 | 0.0021512 | 0.0021512 | 0 | 0 | 0 |  |  | 0 | 0
66 | Supply of Video Conference Screen at KGSC Pophali | N.A. | - | 0 | 0.02 | 0.02 | 0 | 0 | 0 |  |  | 0 | 0
67 | Supply of Video conference Screen at KGSC, Pophali | N.A. | - | 0 | 0.0109 | 0.0109 | 0 | 0 | 0 |  |  | 0 | 0
68 | Supply of Kelvinator / Godrej / Croma Make Refrigerator | N.A. | - | 0 | 0.010932 | 0.010932 | 0 | 0 | 0 |  |  | 0 | 0
69 | supply of Bosch make High Pressure Washer at Mecha | N.A. | - | 0 | 0.0020649 | 0.0020649 | 0 | 0 | 0 |  |  | 0 | 0
70 | Supply of Pneumatic Tools for Mechanical Maintenan | N.A. | - | 0 | 0.035259 | 0.035259 | 0 | 0 | 0 |  |  | 0 | 0
72 | Low BACK Revolving Chairs 45 No & Desk Chair 2 No | N.A. | - | 0 | 0.020945 | 0.020945 | 0 | 0 | 0 |  |  | 0 | 0
73 | Supply of Tables at KGSC | N.A. | - | 0 | 0.037339 | 0.037339 | 0 | 0 | 0 |  |  | 0 | 0
74 | Supply of Visitor Chairs & Office chairs at KGSC, | N.A. | - | 0 | 0.033201 | 0.033201 | 0 | 0 | 0 |  |  | 0 | 0
75 | water purifier for colony electrical maintenance | N.A. | - | 0 | 0.00174 | 0.00174 | 0 | 0 | 0 |  |  | 0 | 0
76 | Projectors and Motorized Projector Screens (2+2) | N.A. | - | 0 | 0.03481 | 0.03481 | 0 | 0 | 0 |  |  | 0 | 0
77 | Acer make Computers at KGSC Pophali.21 No. | N.A. | - | 0 | 0.119 | 0.119 | 0 | 0 | 0 |  |  | 0 | 0
78 | Acer make Laptops at KGSC Pophali. | N.A. | - | 0 | 0.030088 | 0.030088 | 0 | 0 | 0 |  |  | 0 | 0
79 | APS Smart UPS Xl 2200 VA RM 3U 230 | N.A. | - | 0 | 0.015983 | 0.015983 | 0 | 0 | 0 |  |  | 0 | 0
80 | BATRY 12V 75 AH BATTREY 11 PLATE | N.A. | - | 0 | 0.017629 | 0.017629 | 0 | 0 | 0 |  |  | 0 | 0
81 | Supply & installation of IP Camera System and network spare | N.A. | - | 0 | 0.025807 | 0.025807 | 0 | 0 | 0 |  |  | 0 | 0
82 | Gym Equipments at MSPGCL Recreation club , 33 Item | N.A. | - | 0 | 0.047834 | 0.047834 | 0 | 0 | 0 |  |  | 0 | 0
0 | Non-DPR schemes (3 Nos) for FY 2024-25 at KGSC Pophali | Board Resolution No-MSPGCL/BM-219/Item 219.7 dtd.24.07.2023 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
83 | Up-gradation of thyristor based 48V Battery Chargers (4 nos) by SMPS Microprocessor based dual float cum boost Battery Chargers at Stage-III, Stage-I&II and KDPH at KGSC, Pophali | 0 | - | 0 | 1.57 | 1.57 | 0 | 0 | 0 |  |  | 0 | 0
84 | Up-gradation of thyristor based 220V Battery Chargers (4 nos) by SMPS Microprocessor based dual float cum boost Battery Chargers at Stage-III and Stage-I&II at KGSC, Pophali | 0 | - | 0 | 3.79 | 3.79 | 0 | 0 | 0 |  |  | 0 | 0
85 | Retrofitting of Generator and Gen. Transformer protection relay by Numerical protection system at KGSC stage III, Alore | 0 | - | 0 | 4.78 | 4.78 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Non-DPR schemes (2 Nos) for FY 2025-26 at KGSC Pophali | Yet Not Submitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
86 | Supply, Erection, Commissioning & Retrofitting of 220 VDC Ni-cadmium type Battery set (4 Nos) having different ampere hour capacity at Stage-I&II and Stage-IV | 0 | - | 0 | 9.23 | 9.23 | 0 | 0 | 0 |  |  | 0 | 0
87 | Supply, Erection, Commissioning & Retrofitting of 48VDC, 300AH Ni-cadmium type Battery set at Stage-I&II switchyard | 0 | - | 0 | 0.37 | 0.37 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 365.8349 | 358.6226 | 7.2123 | 77.5 | 77.5 | 0 | 0 | 77.5 | 7.2123
FY 2028-29
a) DPR Schemes
(i) Submitted to MERC
1 | Various improvement schemes at Pophali Hydro Power Station | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 11.9001 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | ALSPA HMI Series 6 Centralog System | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 6.8555 | 7.8386 | 7.8386 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | 1 X 525 Tr chiller unit | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 1.23 | 1.15 | 1.15 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Micom P343 Numerical generator protection relay with 24 DI & 24 DO with CLIO input. (5 Nos) | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 1.4675 | 1.474 | 1.474 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.4 | Security Building at Stage-IV | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 0.16446 | 0.18377 | 0.18377 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.5 | Construction of recreation club building | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 1.8204 | 2.1946 | 2.1946 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.6 | Security Building for Stage-IV at EVT | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 0.22776 | 0.25961 | 0.25961 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 0.1344 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Various DPR Schemes for Civil Section, KGSC Pophali | MERC/CAPEX/20152016/00907 | 2015-11-05 | 21.201 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Providing Road Network at KGSC, Pophali | MERC/CAPEX/20152016/00907 | 2015-11-05 | 7.776 | 7.0182 | 7.0182 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.2 | Modernisation & Refurbishing of Residential Complex | MERC/CAPEX/20152016/00907 | 2015-11-05 | 8.985 | 8.9365 | 8.9365 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.3 | Water Supply & Sanitory Works | MERC/CAPEX/20152016/00907 | 2015-11-05 | 4.44 | 5.9018 | 4.1022 | 1.7997 | 0 | 0 |  |  | 0 | 1.7997 | 0 | 0
4 | Various Performance Improvement related schemes at KGSC, Pophali | MERC/CAPEX/20162017/01018 | 2016-11-17 | 12.9765 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Up gradation of 245 kV CTs at Stage-I&II SY | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.9624 | 2.09 | 2.09 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Up gradation of 245 kV PTs at Stage-I&II SY | MERC/CAPEX/20162017/01018 | 2016-11-17 | 0.40509 | 0.3417 | 0.3417 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.3 | Up gradation of CW system of Stage-I&II Units | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.7099 | 1.4731 | 1.4731 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.4 | Up gradation of Intercom Exchange System between Stage-I&II PH & Admin. Bldg & Staff Colony. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 0.43826 | 0.359 | 0.359 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.5 | Up gradation of 220 kV Breakers at KDPH SY | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.289 | 0.979 | 0.979 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.6 | Procurement of Governing Oil Pumps for Stage-III Units. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.2316 | 0.70174 | 0.70174 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.7 | Up gradation of TG Governing system of Stage-IV Units. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 2.2152 | 2.7472 | 2.7472 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.8 | Up gradation of Numerical Protection system of Stage-IV Units. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 2.8249 | 2.8674 | 2.8674 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01018 | 2016-11-17 | 0.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7 | Replacement of Generator Stator of unit No. 11 (80 MW), Stage III, KGSC Pophali | MERC/CAPEX/20172018/04592 | 2017-11-07 | 22.54 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Replacement of Generator Stator of unit No. 11 (80 MW), Stage III, KGSC Pophali | MERC/CAPEX/20172018/04592 | 2017-11-07 | 22.54 | 19.409 | 19.41 | -0.001 | 0 | 0 |  |  | 0 | -0.001 | 0 | 0
8 | Procurement of new pelton wheel runners (2 Nos.) for Stage II at KGSC, Pophali | MERC/CAPEX/20172018/04421 | 2017-10-24 | 13.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement of new pelton wheel runners (2 Nos.) for Stage II at KGSC, Pophali | MERC/CAPEX/20172018/04421 | 2017-10-24 | 13.07 | 10.38 | 10.38 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Implementation of 12 Nos. of various schemes at KGSC, Pophali. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 26.891 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Replacement of UGB (8 Nos), LGB (8 Nos) & Generator air coolers (8 Nos) for Stage-I | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 1.344 | 0.85 | 0.85 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Retrofitting of Generator & Gen-Transformer relays by new numerical protection system at Koyna Dam Power House (KDPH) Koynanagar | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 1.097 | 1.08 | 1.08 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.3 | Replacement of two 220V Battery chargers with 220V dual float cum boost (60A) battery Charger including DCDB at KDPH, Koynanagar | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.202 | 0.13782 | 0.13782 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.4 | Replacement of 220KV current transformer (54 Nos), Potential transformer (13 Nos),110KV Current Transformer (14 Nos)& Potential Transformer (4 Nos),Stage-III. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 5.281 | 5.28 | 5.28 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.5 | Replacement of Generator Air Cooler (32 Nos), St-III | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 2.413 | 2.0541 | 2.0541 | -4e-06 | 0 | 0 |  |  | 0 | -4e-06 | 0 | 0
11.6 | Replacement of 48 Volt, 1000 AH tubular battery set with 48 Volt, 750AH Plante type battery set at KGSC, Stage-III | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.318 | 0.30942 | 0.30942 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.7 | Replacement of 220V-150AH Battery set with Ni-Cad type, along with standard accessories for UPS scheme at Stage-IV | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.272 | 0.25759 | 0.25759 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.8 | Reliability enhancement of Gas Insulated Switchyard Stage-IV. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 10.472 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.9 | Up-gradation of Vibration system at all units of Stage-IV:Stage-IV, KGSC, Pophali | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 1.443 | 1.5041 | 1.5041 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.10 | Replacement of station battery set of 220V, 2000Ah capacity at Stage-IV. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 2.385 | 2.3649 | 2.3649 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.11 | Renovations and modernization of 1500kg capacity passenger cum goods lifts (2 Nos) for KGSC, Stage-IV | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.968 | 0.85208 | 0.85208 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.12 | Replacement of existing 3x7.5 TR Air conditioning package units at Stage-I&II control room by new 3x11 TR Air conditioning package units | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.345 | 0.16909 | 0.16909 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.351 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Upgradation of Governing System at Stage-I, KDPH& Stage-III at KGSC, Pophali | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 19.1651 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Up gradation of DIGIPID1500 governing system with new governor (TSLG) for all units of stage-I | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 6.0888 | 3.89 | 3.89 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.2 | Up-gradation of governing system at Koyna Dam Power House (KDPH) Koynanagar | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 2.924 | 1.41 | 1.41 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.3 | Up-gradation of the Governing system at Stage-III & Other Charges (P&F, Insurance etc) | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 9.5523 | 4.6 | 4.6 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Refurbishment of 24 KV Generator Circuit Breakers (ABB Make) for four units at stage-IV, KGSC, Pophali | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 10.5726 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Supply spares for 24KV Generator Circuit Breaker System refurbishment (For 4 Units) | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 6.5702 | 6.5421 | 6.5421 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Supervision charges for 24 KV Generator Circuit Breaker System Unit. Preparation charges, Travel & transportation charges, local conveyance. Lumpsum rental charges of necessary tools & tackles required during O/H work charges | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 3.8704 | 3.8216 | 3.8216 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 0.132 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Up-gradation of Excitation system at Stage-I&II, PLC & SCADA system at Stage-II and DG Set at Stage-IV at KGSC, Pophali | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 9.863 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | Up gradation of Stage-I&II(4x70MW+4x80 MW) Static Semipol Excitation System with Latest Advanced Excitation System | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 9.863 | 5.763 | 5.76 | 0.003 | 0 | 0 |  |  | 0 | 0.003 | 0 | 0
15.2 | Up gradation of existing unit PLC and SCADA automation of 4x80 MW Koyna stage-II units | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 4.232 | 4.3 | 4.3 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.3 | Up gradation of one 1500 KVA DG set, at KGSC, Stage-IV | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 1.6 | 1.81 | 1.81 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 1.103 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Repair works in Emergency Valve Tunnel (EVT) and surge well at Stage I/II, KGSC, Pophali | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 28.0371 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Sealing and stabilization of EVT Tunnel left side wall and carven portion of EVT and Ventilation Tunnel. | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 8.307 | 19.5731 | 18.03 | 1.5431 | 0 | 0 |  |  | 0 | 1.5431 | 0 | 0
17.2 | Structural Strengthening and Sealing Cracks and Cavities in Surge Shaft RCC Staining Wall from inside | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 18.6602 | 0.3875 | 0 | 0.3875 | 0 | 0 |  |  | 0 | 0.3875 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 1.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-8.1 | Advance Multipurpose Fire Tender | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-8.2 | Normal Multipurpose Fire Tender | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Refurbishment of cooling and drainage water system along with replacement of 5 no's of cooling water pumps by new stage -IV KGSC Pophali | MERC/CAPEX/2023-2024/MSPGCL/0201 | 2024-03-21 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Refurbishment of cooling and drainage water system along with replacement of 5 no's of cooling water pumps by new stage -IV KGSC Pophali | MERC/CAPEX/2023-2024/MSPGCL/0201 | 2024-03-21 | 0 | 27.83 | 27.83 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0201 | 2024-03-21 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[8 empty] | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | Refurbishment of GIS T155 as per M4 Schedule at KGSC Stage-IV, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | Refurbishment of GIS T155 as per M4 Schedule at KGSC Stage-IV, Pophali | 0 | - | 0 | 49.08 | 49.08 | 0 | 0 | 0 |  |  | 0 | 0
20 | Various Civil work as per IB recommendation at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.1 | Various Civil work as per IB recommendation at KGSC, Pophali | 0 | - | 0 | 8.45 | 10.5 | -2.05 | 0 | 0 |  |  | 0 | -2.05
20.2 | construction of chainlink caging along entrance of St-I&II, St-III & St-IV | 0 | - | 0 | 6.53 | 0 | 6.53 | 0 | 0 |  |  | 0 | 6.53
21 | Stabilization and Mitigation of Landslide Prone Areas at KGSC, Mahagenco, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Stabilization and Mitigation of Landslide Prone Areas | 0 | - | 0 | 22.6 | 23.6 | -1 | 0 | 0 |  |  | 0 | -1
21.2 | Construction of retaining wall | 0 | - | 0 | 6.9 | 6.9 | 0 | 0 | 0 |  |  | 0 | 0
21.3 | Dredging river and nallah | 0 | - | 0 | 0.4 | 0.4 | 0 | 0 | 0 |  |  | 0 | 0
22 | Various Performance Improvement related schemes for FY 2026-27 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.1 | Supply of New Runner for Francis Turbine 80 MW at KGSC Stage-III | 0 | - | 0 | 11 | 11 | 0 | 0 | 0 |  |  | 0 | 0
22.2 | Supply of 2 Nos. injector along with injector shaft for Stage-I Units (70 MW) at Stage I & II KGSC, Pophali . | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
22.3 | Supply of 1 No. injector for Stage-II Units (80 MW) at Stage I & II KGSC, Pophali . | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
22.4 | Upgradation of AC Chiiler system at Stage I & II | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
22.5 | Design, manufacturing, supply, erection, testing and commissioning of LGB and UGB cooler modifications at KGSC Stage I&II | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
23 | Replacement of existing Generator transformer of all units (04 x 80 MW) in phase manner (one unit per year) at Stage-III, KGSC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.1 | Replacement of existing Generator transformer of all units (04 x 80 MW) in phase manner (one unit per year) at Stage-III, KGSC | 0 | - | 0 | 60 | 60 | 0 | 30 | 30 |  |  | 30 | 0
24 | Implementation of PLC & SCADA system (DSC based) for all units (04 x 80 MW) units in phase manner (two unit per year) at Stage-III, KGSC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.1 | Implementation of PLC & SCADA system (DSC based) for all units (04 x 80 MW) units in phase manner (two unit per year) at Stage-III, KGSC | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
25 | Various Performance Improvement related schemes for FY 2027-28 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.1 | Refurbishment of Stage-1, Unit No-1,2,3 & 4 PLC System and Implementation of SCADA System. | 0 | - | 0 | 4.5 | 4.5 | 0 | 0 | 0 |  |  | 0 | 0
25.2 | Supply, installation & commissioning of New PLC & Centralog system for all four units at St-IV, KGSC | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
25.3 | Supply, installation & commissioning of New excitation system for all four units at St-IV, KGSC | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
26 | Various Performance Improvement related schemes for FY 2028-29 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.1 | Upgradation of 11 KV Auxiliary breaker at St-I&II | 0 | - | 0 | 0 | 0 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
26.2 | Supply of Dry Type, 630 KVA 16 KV / 570 V Single Phase Excitation Transformers (Qty. 12 Nos.) at KGSC Stage-IV, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 3.5 | 3.5 |  |  | 3.5 | 0
26.3 | Supply, Installation & Commissioning of 16.5 KV / 433 V, 5MVA Unit Auxiliary Transformers (Qty. 02) at KGSC Stage-IV. | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
26.4 | Upgradation of 2.2 KV Auxiliary Breaker with 3.3 KV Breaker along with Auxiliary Transformers at St-I&II. | 0 | - | 0 | 0 | 0 | 0 | 8 | 8 |  |  | 8 | 0
26.5 | Supply of 11KV Cable alongwith Breaker Panels for Auxiliary Supply from 8-Pole Switchyard Stage- I and II to Stage-IV Powerhouse at KGSC Stage-IV, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 4.5 | 4.5 |  |  | 4.5 | 0
26.6 | Replacement of 220 KV isolator of Stage II bay at 220 KV Stage I & II Switchyard | 0 | - | 0 | 0 | 0 | 0 | 5.5 | 5.5 |  |  | 5.5 | 0
27 | Various Performance Improvement related schemes for FY 2029-30 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.1 | Design Engineering and manufacturing, supply, erection, commissioning & testing of New Pelton runner for Stage-I units (70 MW) at Stage-I&II, KGSC, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.2 | Upgradation of Generator and Generator transformer electromagnetic protection relays with numeric relays for Stage 1 & 2. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.3 | Renovation of old system by full proof modern digital governing system, static/brushless excitation system and generator stator and rotor winding by class 'F' insulation at St-I&II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.4 | Design, manufacturing, supply, erection, testing and commissioning of Hydrostatic lubrication system for Units at KGSC Stage I & II, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.5 | Replacement of CW pumps and Motors along with starter pannel at St-I&II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.6 | Supply of Generator air coolers (16 Nos) for Stage II Units (80 MW) at KGSC, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.7 | Conversion of Stator Core Insulation & Stator Winding from Class ‘B’ to Class ‘F’ for Unit No. 8 (80MW, 11KV, 375RPM, AEG Germany make) of Stage II, KGSC, Pophali on Turnkey Basis. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.8 | Up-gradation of existing 'B' class insulation of Generator stator to 'F' class insulation of 2X18MW Koyna Dam Power House, Koynanagar. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.9 | Supply and replacement of Generator air cooler system by new higher efficiency coolers for 2X18MW Koyna Dam Power House, Koynanagar. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | <Auto Transformer Oil Insulation Test kit (BDV Kit)> | N.A. | - | 0 | 0.03953 | 0.03953 | 0 | 0 | 0 |  |  | 0 | 0
2 | <Man coolers pedestal fans at KGSC,Pophali> | N.A. | - | 0 | 0.034143 | 0.034143 | 0 | 0 | 0 |  |  | 0 | 0
3 | < 5 KV Digital Insulation Tester> | N.A. | - | 0 | 0.029798 | 0.029798 | 0 | 0 | 0 |  |  | 0 | 0
4 | <Split AC Unit,Window AC Unit,Refrigerator,Ped> | N.A. | - | 0 | 0.017857 | 0.017857 | 0 | 0 | 0 |  |  | 0 | 0
5 | <Earth Resistance Tester at ,Pophali. TIC STAGE IV> | N.A. | - | 0 | 0.016839 | 0.016839 | 0 | 0 | 0 |  |  | 0 | 0
6 | <Tools and Tackles at St-IV,KGSC,Pophali> | N.A. | - | 0 | 0.034609 | 0.034609 | 0 | 0 | 0 |  |  | 0 | 0
7 | <New portable Fire Fighting Diesel Pumps for Dewatering> | N.A. | - | 0 | 0.09697 | 0.09697 | 0 | 0 | 0 |  |  | 0 | 0
8 | <Visitors chairs for, Pophali KGSC> | N.A. | - | 0 | 0.033188 | 0.033188 | 0 | 0 | 0 |  |  | 0 | 0
9 | <Installation of new racks inside various/new slotted angle racks > | N.A. | - | 0 | 0.039648 | 0.039648 | 0 | 0 | 0 |  |  | 0 | 0
10 | <Supply of chairs for KGSC, Pophali> | N.A. | - | 0 | 0.044238 | 0.044238 | 0 | 0 | 0 |  |  | 0 | 0
11 | <Laser Jet NetwoksPrinters at KGSC, Pophali> | N.A. | - | 0 | 0.084075 | 0.084075 | 0 | 0 | 0 |  |  | 0 | 0
12 | <Night Vision Binoculars> | N.A. | - | 0 | 0.023411 | 0.023411 | 0 | 0 | 0 |  |  | 0 | 0
13 | <TATA Star Bus-32 seater LCV MH08-9358> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | <TATA Star Bus-32 seater LCV MH08-9359> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | <Vehicle No.MH 08-9401 TATA Star Bus 32 seater> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | <Not in use DCM Toyato Bus MH-1> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | <Not in use DCM Toyato Mini Bus> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | <Digital Multimeters, Clamp Meter & Insulation resistance tester for TIC, Stage I&II, Pophali> | N.A. | - | 0 | 0.028928 | 0.028928 | 0 | 0 | 0 |  |  | 0 | 0
19 | <Transformer Winding resistance measurement kit at Stage-III, Alore> | N.A. | - | 0 | 0.024338 | 0.024338 | 0 | 0 | 0 |  |  | 0 | 0
20 | <Multifunc A3 Scanner & all in one A4 laser printer Technical Purchase , Account Section, H.R. ,MPD> | N.A. | - | 0 | 0.032521 | 0.032521 | 0 | 0 | 0 |  |  | 0 | 0
21 | <Temperature Calibrator at St-IV, KGSC,Pophali> | N.A. | - | 0 | 0.012272 | 0.012272 | 0 | 0 | 0 |  |  | 0 | 0
22 | < 1 no. new departmental car Maruti Sweft Desire for conveyance of Chief Engr> | N.A. | - | 0 | 0.077924 | 0.077924 | 0 | 0 | 0 |  |  | 0 | 0
23 | <Hitachi A/c Two.NO.VIP Rest House> | N.A. | - | 0 | 0.008 | 0.008 | 0 | 0 | 0 |  |  | 0 | 0
24 | <Inverter Split AC Unit, Desert Coolers Water Coolers for KGSC, Pophali> | N.A. | - | 0 | 0.0070799 | 0.0070799 | 0 | 0 | 0 |  |  | 0 | 0
25 | <Advanced ISDN EPABX system for Koyna Generating St ntercom Telephone Advanced ISDN EPABX system for Koyna Generating Station Complex> | N.A. | - | 0 | 0.029645 | 0.029645 | 0 | 0 | 0 |  |  | 0 | 0
26 | <TATA Sumo MH-14/9763 1 No> | N.A. | - | 0 | 0.041197 | 0.041197 | 0 | 0 | 0 |  |  | 0 | 0
27 | <Ambulance TATA make MH-31/4475 1 No> | N.A. | - | 0 | 0.036143 | 0.036143 | 0 | 0 | 0 |  |  | 0 | 0
28 | <Supply of 1 No of Ambulance Vane for Pophali> | N.A. | - | 0 | 0.14883 | 0.14883 | 0 | 0 | 0 |  |  | 0 | 0
29 | <Supply of 1 No of Ambulance Vane for Pophali> | N.A. | - | 0 | 0.14883 | 0.14883 | 0 | 0 | 0 |  |  | 0 | 0
30 | <HITACHI Make 2 TR non inverter split Air conditioner> | N.A. | - | 0 | 0.16739 | 0.16739 | 0 | 0 | 0 |  |  | 0 | 0
31 | <250 KVA D.G. Set Model KG1-250WS> | N.A. | - | 0 | 0.19222 | 0.19222 | 0 | 0 | 0 |  |  | 0 | 0
32 | <Dell laptops at KGSC Pophali> | N.A. | - | 0 | 0.0156 | 0.0156 | 0 | 0 | 0 |  |  | 0 | 0
33 | <A.C. Plant chiller 515 to 535 TRx2 at kgsc,Pophali> | N.A. | - | 0 | 2.1144 | 2.1144 | 0 | 0 | 0 |  |  | 0 | 0
34 | <Supply of RDP make Computers at KGSC> | N.A. | - | 0 | 0.43135 | 0.43135 | 0 | 0 | 0 |  |  | 0 | 0
35 | <Welding Machine for KDPH> | N.A. | - | 0 | 0.001039 | 0.001039 | 0 | 0 | 0 |  |  | 0 | 0
36 | <Material handling trolley for Majot store> | N.A. | - | 0 | 0.0014198 | 0.0014198 | 0 | 0 | 0 |  |  | 0 | 0
37 | <Canon LiDe 300 IN Scanner> | N.A. | - | 0 | 0.00048 | 0.00048 | 0 | 0 | 0 |  |  | 0 | 0
38 | <Supply of Pedestal fan at KDPH> | N.A. | - | 0 | 0.015 | 0.015 | 0 | 0 | 0 |  |  | 0 | 0
39 | <Supply of Refrigerator 290 LTR double door capacity> | N.A. | - | 0 | 0.0022 | 0.0022 | 0 | 0 | 0 |  |  | 0 | 0
40 | <Supply of Refrigerator 290 LTR double door capacity> | N.A. | - | 0 | 0.0022 | 0.0022 | 0 | 0 | 0 |  |  | 0 | 0
41 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.007 | 0.007 | 0 | 0 | 0 |  |  | 0 | 0
42 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.0035 | 0.0035 | 0 | 0 | 0 |  |  | 0 | 0
43 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.0035 | 0.0035 | 0 | 0 | 0 |  |  | 0 | 0
44 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.0035 | 0.0035 | 0 | 0 | 0 |  |  | 0 | 0
45 | <Redmi 10 prime Mobile Black for Chief Engineer> | N.A. | - | 0 | 0.0015 | 0.0015 | 0 | 0 | 0 |  |  | 0 | 0
46 | <TATA Sumo MH-14/9763 1 No> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47 | <Ambulance TATA make MH-31/4475 1 No> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48 | <Supply of Two Post Lift (4 Ton) for Vehicle Maint.> | N.A. | - | 0 | 0.014396 | 0.014396 | 0 | 0 | 0 |  |  | 0 | 0
49 | Supply,Installation, commissioning and testing of 415V, 3 Phase diesel generating setof 125 KVA capacity for Admin building emergency power supply backup at KGSC,Pophali. | N.A. | - | 0 | 0.0995 | 0.0995 | 0 | 0 | 0 |  |  | 0 | 0
50 | Design,Manufacturing, supply erriction and commissioning of 60 MT surface mounted (pit type/ platform type) weighbridge at major stores 'c' pophali | N.A. | - | 0 | 0.21577 | 0.21577 | 0 | 0 | 0 |  |  | 0 | 0
51 | Supply of Hydraulically operated manual stacker for Material Handling at Major Store "C", KGSC, Pophali | N.A. | - | 0 | 0.00524 | 0.00524 | 0 | 0 | 0 |  |  | 0 | 0
52 | Supply of Indef makes Chain Pulley Blocks | N.A. | - | 0 | 0.011505 | 0.011505 | 0 | 0 | 0 |  |  | 0 | 0
53 | Supply of Motwane Make ‘Digital Multimeter and AC Multimeter | N.A. | - | 0 | 0.018458 | 0.018458 | 0 | 0 | 0 |  |  | 0 | 0
54 | Supply 1 Ton split AC Daiken make for control room cabin Operation Stage III | N.A. | - | 0 | 0.00396 | 0.00396 | 0 | 0 | 0 |  |  | 0 | 0
55 | Emer Rescue cum Multipurpose Fire Tender | N.A. | - | 0 | 2.0039 | 2.0039 | 0 | 0 | 0 |  |  | 0 | 0
56 | Procurement of portable chairs for training sub centre | N.A. | - | 0 | 0.01308 | 0.01308 | 0 | 0 | 0 |  |  | 0 | 0
57 | Procurement of portable computer tables | N.A. | - | 0 | 0.0033449 | 0.0033449 | 0 | 0 | 0 |  |  | 0 | 0
58 | Purchase of High back chair (3 Nos.) in conferenc hall | N.A. | - | 0 | 0.0044014 | 0.0044014 | 0 | 0 | 0 |  |  | 0 | 0
59 | Supply of Water Purifier at MSPGCL KGSC Pophali. | N.A. | - | 0 | 0.005 | 0.005 | 0 | 0 | 0 |  |  | 0 | 0
60 | Interactive Digital LV SCREEN 6.56 FT X 3.28 FT | N.A. | - | 0 | 0.01295 | 0.01295 | 0 | 0 | 0 |  |  | 0 | 0
61 | Network Attached Storage Server at KGSC, Pophali. | N.A. | - | 0 | 0.023333 | 0.023333 | 0 | 0 | 0 |  |  | 0 | 0
62 | Supply of A4 Printer at KGSC, Pophali. | N.A. | - | 0 | 0.0099995 | 0.0099995 | 0 | 0 | 0 |  |  | 0 | 0
63 | Supply of A4 Scanner, A3 & MF Printer at KGSC, Pop | N.A. | - | 0 | 0.0586 | 0.0586 | 0 | 0 | 0 |  |  | 0 | 0
64 | Supply of Various Hard Disks for Network Attached | N.A. | - | 0 | 0.021806 | 0.021806 | 0 | 0 | 0 |  |  | 0 | 0
65 | Supply of Video conference Microphone at KGSC, | N.A. | - | 0 | 0.0021512 | 0.0021512 | 0 | 0 | 0 |  |  | 0 | 0
66 | Supply of Video Conference Screen at KGSC Pophali | N.A. | - | 0 | 0.02 | 0.02 | 0 | 0 | 0 |  |  | 0 | 0
67 | Supply of Video conference Screen at KGSC, Pophali | N.A. | - | 0 | 0.0109 | 0.0109 | 0 | 0 | 0 |  |  | 0 | 0
68 | Supply of Kelvinator / Godrej / Croma Make Refrigerator | N.A. | - | 0 | 0.010932 | 0.010932 | 0 | 0 | 0 |  |  | 0 | 0
69 | supply of Bosch make High Pressure Washer at Mecha | N.A. | - | 0 | 0.0020649 | 0.0020649 | 0 | 0 | 0 |  |  | 0 | 0
70 | Supply of Pneumatic Tools for Mechanical Maintenan | N.A. | - | 0 | 0.035259 | 0.035259 | 0 | 0 | 0 |  |  | 0 | 0
72 | Low BACK Revolving Chairs 45 No & Desk Chair 2 No | N.A. | - | 0 | 0.020945 | 0.020945 | 0 | 0 | 0 |  |  | 0 | 0
73 | Supply of Tables at KGSC | N.A. | - | 0 | 0.037339 | 0.037339 | 0 | 0 | 0 |  |  | 0 | 0
74 | Supply of Visitor Chairs & Office chairs at KGSC, | N.A. | - | 0 | 0.033201 | 0.033201 | 0 | 0 | 0 |  |  | 0 | 0
75 | water purifier for colony electrical maintenance | N.A. | - | 0 | 0.00174 | 0.00174 | 0 | 0 | 0 |  |  | 0 | 0
76 | Projectors and Motorized Projector Screens (2+2) | N.A. | - | 0 | 0.03481 | 0.03481 | 0 | 0 | 0 |  |  | 0 | 0
77 | Acer make Computers at KGSC Pophali.21 No. | N.A. | - | 0 | 0.119 | 0.119 | 0 | 0 | 0 |  |  | 0 | 0
78 | Acer make Laptops at KGSC Pophali. | N.A. | - | 0 | 0.030088 | 0.030088 | 0 | 0 | 0 |  |  | 0 | 0
79 | APS Smart UPS Xl 2200 VA RM 3U 230 | N.A. | - | 0 | 0.015983 | 0.015983 | 0 | 0 | 0 |  |  | 0 | 0
80 | BATRY 12V 75 AH BATTREY 11 PLATE | N.A. | - | 0 | 0.017629 | 0.017629 | 0 | 0 | 0 |  |  | 0 | 0
81 | Supply & installation of IP Camera System and network spare | N.A. | - | 0 | 0.025807 | 0.025807 | 0 | 0 | 0 |  |  | 0 | 0
82 | Gym Equipments at MSPGCL Recreation club , 33 Item | N.A. | - | 0 | 0.047834 | 0.047834 | 0 | 0 | 0 |  |  | 0 | 0
0 | Non-DPR schemes (3 Nos) for FY 2024-25 at KGSC Pophali | Board Resolution No-MSPGCL/BM-219/Item 219.7 dtd.24.07.2023 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
83 | Up-gradation of thyristor based 48V Battery Chargers (4 nos) by SMPS Microprocessor based dual float cum boost Battery Chargers at Stage-III, Stage-I&II and KDPH at KGSC, Pophali | 0 | - | 0 | 1.57 | 1.57 | 0 | 0 | 0 |  |  | 0 | 0
84 | Up-gradation of thyristor based 220V Battery Chargers (4 nos) by SMPS Microprocessor based dual float cum boost Battery Chargers at Stage-III and Stage-I&II at KGSC, Pophali | 0 | - | 0 | 3.79 | 3.79 | 0 | 0 | 0 |  |  | 0 | 0
85 | Retrofitting of Generator and Gen. Transformer protection relay by Numerical protection system at KGSC stage III, Alore | 0 | - | 0 | 4.78 | 4.78 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Non-DPR schemes (2 Nos) for FY 2025-26 at KGSC Pophali | Yet Not Submitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
86 | Supply, Erection, Commissioning & Retrofitting of 220 VDC Ni-cadmium type Battery set (4 Nos) having different ampere hour capacity at Stage-I&II and Stage-IV | 0 | - | 0 | 9.23 | 9.23 | 0 | 0 | 0 |  |  | 0 | 0
87 | Supply, Erection, Commissioning & Retrofitting of 48VDC, 300AH Ni-cadmium type Battery set at Stage-I&II switchyard | 0 | - | 0 | 0.37 | 0.37 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 443.3349 | 436.1226 | 7.2123 | 56 | 56 | 0 | 0 | 56 | 7.2123
FY 2029-30
a) DPR Schemes
(i) Submitted to MERC
1 | Various improvement schemes at Pophali Hydro Power Station | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 11.9001 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | ALSPA HMI Series 6 Centralog System | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 6.8555 | 7.8386 | 7.8386 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | 1 X 525 Tr chiller unit | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 1.23 | 1.15 | 1.15 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Micom P343 Numerical generator protection relay with 24 DI & 24 DO with CLIO input. (5 Nos) | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 1.4675 | 1.474 | 1.474 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.4 | Security Building at Stage-IV | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 0.16446 | 0.18377 | 0.18377 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.5 | Construction of recreation club building | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 1.8204 | 2.1946 | 2.1946 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.6 | Security Building for Stage-IV at EVT | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 0.22776 | 0.25961 | 0.25961 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/00086 | 2014-04-10 | 0.1344 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Various DPR Schemes for Civil Section, KGSC Pophali | MERC/CAPEX/20152016/00907 | 2015-11-05 | 21.201 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Providing Road Network at KGSC, Pophali | MERC/CAPEX/20152016/00907 | 2015-11-05 | 7.776 | 7.0182 | 7.0182 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.2 | Modernisation & Refurbishing of Residential Complex | MERC/CAPEX/20152016/00907 | 2015-11-05 | 8.985 | 8.9365 | 8.9365 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.3 | Water Supply & Sanitory Works | MERC/CAPEX/20152016/00907 | 2015-11-05 | 4.44 | 5.9018 | 4.1022 | 1.7997 | 0 | 0 |  |  | 0 | 1.7997 | 0 | 0
4 | Various Performance Improvement related schemes at KGSC, Pophali | MERC/CAPEX/20162017/01018 | 2016-11-17 | 12.9765 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Up gradation of 245 kV CTs at Stage-I&II SY | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.9624 | 2.09 | 2.09 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Up gradation of 245 kV PTs at Stage-I&II SY | MERC/CAPEX/20162017/01018 | 2016-11-17 | 0.40509 | 0.3417 | 0.3417 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.3 | Up gradation of CW system of Stage-I&II Units | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.7099 | 1.4731 | 1.4731 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.4 | Up gradation of Intercom Exchange System between Stage-I&II PH & Admin. Bldg & Staff Colony. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 0.43826 | 0.359 | 0.359 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.5 | Up gradation of 220 kV Breakers at KDPH SY | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.289 | 0.979 | 0.979 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.6 | Procurement of Governing Oil Pumps for Stage-III Units. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 1.2316 | 0.70174 | 0.70174 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.7 | Up gradation of TG Governing system of Stage-IV Units. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 2.2152 | 2.7472 | 2.7472 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.8 | Up gradation of Numerical Protection system of Stage-IV Units. | MERC/CAPEX/20162017/01018 | 2016-11-17 | 2.8249 | 2.8674 | 2.8674 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01018 | 2016-11-17 | 0.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7 | Replacement of Generator Stator of unit No. 11 (80 MW), Stage III, KGSC Pophali | MERC/CAPEX/20172018/04592 | 2017-11-07 | 22.54 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Replacement of Generator Stator of unit No. 11 (80 MW), Stage III, KGSC Pophali | MERC/CAPEX/20172018/04592 | 2017-11-07 | 22.54 | 19.409 | 19.41 | -0.001 | 0 | 0 |  |  | 0 | -0.001 | 0 | 0
8 | Procurement of new pelton wheel runners (2 Nos.) for Stage II at KGSC, Pophali | MERC/CAPEX/20172018/04421 | 2017-10-24 | 13.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Procurement of new pelton wheel runners (2 Nos.) for Stage II at KGSC, Pophali | MERC/CAPEX/20172018/04421 | 2017-10-24 | 13.07 | 10.38 | 10.38 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Implementation of 12 Nos. of various schemes at KGSC, Pophali. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 26.891 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Replacement of UGB (8 Nos), LGB (8 Nos) & Generator air coolers (8 Nos) for Stage-I | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 1.344 | 0.85 | 0.85 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Retrofitting of Generator & Gen-Transformer relays by new numerical protection system at Koyna Dam Power House (KDPH) Koynanagar | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 1.097 | 1.08 | 1.08 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.3 | Replacement of two 220V Battery chargers with 220V dual float cum boost (60A) battery Charger including DCDB at KDPH, Koynanagar | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.202 | 0.13782 | 0.13782 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.4 | Replacement of 220KV current transformer (54 Nos), Potential transformer (13 Nos),110KV Current Transformer (14 Nos)& Potential Transformer (4 Nos),Stage-III. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 5.281 | 5.28 | 5.28 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.5 | Replacement of Generator Air Cooler (32 Nos), St-III | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 2.413 | 2.0541 | 2.0541 | -4e-06 | 0 | 0 |  |  | 0 | -4e-06 | 0 | 0
11.6 | Replacement of 48 Volt, 1000 AH tubular battery set with 48 Volt, 750AH Plante type battery set at KGSC, Stage-III | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.318 | 0.30942 | 0.30942 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.7 | Replacement of 220V-150AH Battery set with Ni-Cad type, along with standard accessories for UPS scheme at Stage-IV | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.272 | 0.25759 | 0.25759 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.8 | Reliability enhancement of Gas Insulated Switchyard Stage-IV. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 10.472 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.9 | Up-gradation of Vibration system at all units of Stage-IV:Stage-IV, KGSC, Pophali | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 1.443 | 1.5041 | 1.5041 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.10 | Replacement of station battery set of 220V, 2000Ah capacity at Stage-IV. | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 2.385 | 2.3649 | 2.3649 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.11 | Renovations and modernization of 1500kg capacity passenger cum goods lifts (2 Nos) for KGSC, Stage-IV | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.968 | 0.85208 | 0.85208 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.12 | Replacement of existing 3x7.5 TR Air conditioning package units at Stage-I&II control room by new 3x11 TR Air conditioning package units | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.345 | 0.16909 | 0.16909 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/01 | 2019-05-24 | 0.351 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Upgradation of Governing System at Stage-I, KDPH& Stage-III at KGSC, Pophali | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 19.1651 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Up gradation of DIGIPID1500 governing system with new governor (TSLG) for all units of stage-I | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 6.0888 | 3.89 | 3.89 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.2 | Up-gradation of governing system at Koyna Dam Power House (KDPH) Koynanagar | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 2.924 | 1.41 | 1.41 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.3 | Up-gradation of the Governing system at Stage-III & Other Charges (P&F, Insurance etc) | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 9.5523 | 4.6 | 4.6 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/0134 | 2019-05-10 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Refurbishment of 24 KV Generator Circuit Breakers (ABB Make) for four units at stage-IV, KGSC, Pophali | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 10.5726 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Supply spares for 24KV Generator Circuit Breaker System refurbishment (For 4 Units) | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 6.5702 | 6.5421 | 6.5421 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Supervision charges for 24 KV Generator Circuit Breaker System Unit. Preparation charges, Travel & transportation charges, local conveyance. Lumpsum rental charges of necessary tools & tackles required during O/H work charges | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 3.8704 | 3.8216 | 3.8216 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/388 | 2019-07-18 | 0.132 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Up-gradation of Excitation system at Stage-I&II, PLC & SCADA system at Stage-II and DG Set at Stage-IV at KGSC, Pophali | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 9.863 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | Up gradation of Stage-I&II(4x70MW+4x80 MW) Static Semipol Excitation System with Latest Advanced Excitation System | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 9.863 | 5.763 | 5.76 | 0.003 | 0 | 0 |  |  | 0 | 0.003 | 0 | 0
15.2 | Up gradation of existing unit PLC and SCADA automation of 4x80 MW Koyna stage-II units | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 4.232 | 4.3 | 4.3 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.3 | Up gradation of one 1500 KVA DG set, at KGSC, Stage-IV | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 1.6 | 1.81 | 1.81 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/800 | 2019-09-27 | 1.103 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Repair works in Emergency Valve Tunnel (EVT) and surge well at Stage I/II, KGSC, Pophali | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 28.0371 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Sealing and stabilization of EVT Tunnel left side wall and carven portion of EVT and Ventilation Tunnel. | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 8.307 | 19.5731 | 18.03 | 1.5431 | 0 | 0 |  |  | 0 | 1.5431 | 0 | 0
17.2 | Structural Strengthening and Sealing Cracks and Cavities in Surge Shaft RCC Staining Wall from inside | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 18.6602 | 0.3875 | 0 | 0.3875 | 0 | 0 |  |  | 0 | 0.3875 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/18 | 2020-06-19 | 1.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-8.1 | Advance Multipurpose Fire Tender | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR-8.2 | Normal Multipurpose Fire Tender | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Refurbishment of cooling and drainage water system along with replacement of 5 no's of cooling water pumps by new stage -IV KGSC Pophali | MERC/CAPEX/2023-2024/MSPGCL/0201 | 2024-03-21 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Refurbishment of cooling and drainage water system along with replacement of 5 no's of cooling water pumps by new stage -IV KGSC Pophali | MERC/CAPEX/2023-2024/MSPGCL/0201 | 2024-03-21 | 0 | 27.83 | 27.83 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0201 | 2024-03-21 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[8 empty] | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | Refurbishment of GIS T155 as per M4 Schedule at KGSC Stage-IV, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | Refurbishment of GIS T155 as per M4 Schedule at KGSC Stage-IV, Pophali | 0 | - | 0 | 49.08 | 49.08 | 0 | 0 | 0 |  |  | 0 | 0
20 | Various Civil work as per IB recommendation at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.1 | Various Civil work as per IB recommendation at KGSC, Pophali | 0 | - | 0 | 8.45 | 10.5 | -2.05 | 0 | 0 |  |  | 0 | -2.05
20.2 | construction of chainlink caging along entrance of St-I&II, St-III & St-IV | 0 | - | 0 | 6.53 | 0 | 6.53 | 0 | 0 |  |  | 0 | 6.53
21 | Stabilization and Mitigation of Landslide Prone Areas at KGSC, Mahagenco, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Stabilization and Mitigation of Landslide Prone Areas | 0 | - | 0 | 22.6 | 23.6 | -1 | 0 | 0 |  |  | 0 | -1
21.2 | Construction of retaining wall | 0 | - | 0 | 6.9 | 6.9 | 0 | 0 | 0 |  |  | 0 | 0
21.3 | Dredging river and nallah | 0 | - | 0 | 0.4 | 0.4 | 0 | 0 | 0 |  |  | 0 | 0
22 | Various Performance Improvement related schemes for FY 2026-27 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.1 | Supply of New Runner for Francis Turbine 80 MW at KGSC Stage-III | 0 | - | 0 | 11 | 11 | 0 | 0 | 0 |  |  | 0 | 0
22.2 | Supply of 2 Nos. injector along with injector shaft for Stage-I Units (70 MW) at Stage I & II KGSC, Pophali . | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
22.3 | Supply of 1 No. injector for Stage-II Units (80 MW) at Stage I & II KGSC, Pophali . | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
22.4 | Upgradation of AC Chiiler system at Stage I & II | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
22.5 | Design, manufacturing, supply, erection, testing and commissioning of LGB and UGB cooler modifications at KGSC Stage I&II | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
23 | Replacement of existing Generator transformer of all units (04 x 80 MW) in phase manner (one unit per year) at Stage-III, KGSC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.1 | Replacement of existing Generator transformer of all units (04 x 80 MW) in phase manner (one unit per year) at Stage-III, KGSC | 0 | - | 0 | 90 | 90 | 0 | 30 | 30 |  |  | 30 | 0
24 | Implementation of PLC & SCADA system (DSC based) for all units (04 x 80 MW) units in phase manner (two unit per year) at Stage-III, KGSC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.1 | Implementation of PLC & SCADA system (DSC based) for all units (04 x 80 MW) units in phase manner (two unit per year) at Stage-III, KGSC | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
25 | Various Performance Improvement related schemes for FY 2027-28 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.1 | Refurbishment of Stage-1, Unit No-1,2,3 & 4 PLC System and Implementation of SCADA System. | 0 | - | 0 | 4.5 | 4.5 | 0 | 0 | 0 |  |  | 0 | 0
25.2 | Supply, installation & commissioning of New PLC & Centralog system for all four units at St-IV, KGSC | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
25.3 | Supply, installation & commissioning of New excitation system for all four units at St-IV, KGSC | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
26 | Various Performance Improvement related schemes for FY 2028-29 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.1 | Upgradation of 11 KV Auxiliary breaker at St-I&II | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
26.2 | Supply of Dry Type, 630 KVA 16 KV / 570 V Single Phase Excitation Transformers (Qty. 12 Nos.) at KGSC Stage-IV, Pophali. | 0 | - | 0 | 3.5 | 3.5 | 0 | 0 | 0 |  |  | 0 | 0
26.3 | Supply, Installation & Commissioning of 16.5 KV / 433 V, 5MVA Unit Auxiliary Transformers (Qty. 02) at KGSC Stage-IV. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
26.4 | Upgradation of 2.2 KV Auxiliary Breaker with 3.3 KV Breaker along with Auxiliary Transformers at St-I&II. | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
26.5 | Supply of 11KV Cable alongwith Breaker Panels for Auxiliary Supply from 8-Pole Switchyard Stage- I and II to Stage-IV Powerhouse at KGSC Stage-IV, Pophali. | 0 | - | 0 | 4.5 | 4.5 | 0 | 0 | 0 |  |  | 0 | 0
26.6 | Replacement of 220 KV isolator of Stage II bay at 220 KV Stage I & II Switchyard | 0 | - | 0 | 5.5 | 5.5 | 0 | 0 | 0 |  |  | 0 | 0
27 | Various Performance Improvement related schemes for FY 2029-30 at KGSC, Pophali | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.1 | Design Engineering and manufacturing, supply, erection, commissioning & testing of New Pelton runner for Stage-I units (70 MW) at Stage-I&II, KGSC, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 6 | 6 |  |  | 6 | 0
27.2 | Upgradation of Generator and Generator transformer electromagnetic protection relays with numeric relays for Stage 1 & 2. | 0 | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
27.3 | Renovation of old system by full proof modern digital governing system, static/brushless excitation system and generator stator and rotor winding by class 'F' insulation at St-I&II | 0 | - | 0 | 0 | 0 | 0 | 4.32 | 4.32 |  |  | 4.32 | 0
27.4 | Design, manufacturing, supply, erection, testing and commissioning of Hydrostatic lubrication system for Units at KGSC Stage I & II, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 6.41 | 6.41 |  |  | 6.41 | 0
27.5 | Replacement of CW pumps and Motors along with starter pannel at St-I&II | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
27.6 | Supply of Generator air coolers (16 Nos) for Stage II Units (80 MW) at KGSC, Pophali. | 0 | - | 0 | 0 | 0 | 0 | 1.2 | 1.2 |  |  | 1.2 | 0
27.7 | Conversion of Stator Core Insulation & Stator Winding from Class ‘B’ to Class ‘F’ for Unit No. 8 (80MW, 11KV, 375RPM, AEG Germany make) of Stage II, KGSC, Pophali on Turnkey Basis. | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
27.8 | Up-gradation of existing 'B' class insulation of Generator stator to 'F' class insulation of 2X18MW Koyna Dam Power House, Koynanagar. | 0 | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
27.9 | Supply and replacement of Generator air cooler system by new higher efficiency coolers for 2X18MW Koyna Dam Power House, Koynanagar. | 0 | - | 0 | 0 | 0 | 0 | 0.5 | 0.5 |  |  | 0.5 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | <Auto Transformer Oil Insulation Test kit (BDV Kit)> | N.A. | - | 0 | 0.03953 | 0.03953 | 0 | 0 | 0 |  |  | 0 | 0
2 | <Man coolers pedestal fans at KGSC,Pophali> | N.A. | - | 0 | 0.034143 | 0.034143 | 0 | 0 | 0 |  |  | 0 | 0
3 | < 5 KV Digital Insulation Tester> | N.A. | - | 0 | 0.029798 | 0.029798 | 0 | 0 | 0 |  |  | 0 | 0
4 | <Split AC Unit,Window AC Unit,Refrigerator,Ped> | N.A. | - | 0 | 0.017857 | 0.017857 | 0 | 0 | 0 |  |  | 0 | 0
5 | <Earth Resistance Tester at ,Pophali. TIC STAGE IV> | N.A. | - | 0 | 0.016839 | 0.016839 | 0 | 0 | 0 |  |  | 0 | 0
6 | <Tools and Tackles at St-IV,KGSC,Pophali> | N.A. | - | 0 | 0.034609 | 0.034609 | 0 | 0 | 0 |  |  | 0 | 0
7 | <New portable Fire Fighting Diesel Pumps for Dewatering> | N.A. | - | 0 | 0.09697 | 0.09697 | 0 | 0 | 0 |  |  | 0 | 0
8 | <Visitors chairs for, Pophali KGSC> | N.A. | - | 0 | 0.033188 | 0.033188 | 0 | 0 | 0 |  |  | 0 | 0
9 | <Installation of new racks inside various/new slotted angle racks > | N.A. | - | 0 | 0.039648 | 0.039648 | 0 | 0 | 0 |  |  | 0 | 0
10 | <Supply of chairs for KGSC, Pophali> | N.A. | - | 0 | 0.044238 | 0.044238 | 0 | 0 | 0 |  |  | 0 | 0
11 | <Laser Jet NetwoksPrinters at KGSC, Pophali> | N.A. | - | 0 | 0.084075 | 0.084075 | 0 | 0 | 0 |  |  | 0 | 0
12 | <Night Vision Binoculars> | N.A. | - | 0 | 0.023411 | 0.023411 | 0 | 0 | 0 |  |  | 0 | 0
13 | <TATA Star Bus-32 seater LCV MH08-9358> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | <TATA Star Bus-32 seater LCV MH08-9359> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | <Vehicle No.MH 08-9401 TATA Star Bus 32 seater> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | <Not in use DCM Toyato Bus MH-1> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | <Not in use DCM Toyato Mini Bus> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | <Digital Multimeters, Clamp Meter & Insulation resistance tester for TIC, Stage I&II, Pophali> | N.A. | - | 0 | 0.028928 | 0.028928 | 0 | 0 | 0 |  |  | 0 | 0
19 | <Transformer Winding resistance measurement kit at Stage-III, Alore> | N.A. | - | 0 | 0.024338 | 0.024338 | 0 | 0 | 0 |  |  | 0 | 0
20 | <Multifunc A3 Scanner & all in one A4 laser printer Technical Purchase , Account Section, H.R. ,MPD> | N.A. | - | 0 | 0.032521 | 0.032521 | 0 | 0 | 0 |  |  | 0 | 0
21 | <Temperature Calibrator at St-IV, KGSC,Pophali> | N.A. | - | 0 | 0.012272 | 0.012272 | 0 | 0 | 0 |  |  | 0 | 0
22 | < 1 no. new departmental car Maruti Sweft Desire for conveyance of Chief Engr> | N.A. | - | 0 | 0.077924 | 0.077924 | 0 | 0 | 0 |  |  | 0 | 0
23 | <Hitachi A/c Two.NO.VIP Rest House> | N.A. | - | 0 | 0.008 | 0.008 | 0 | 0 | 0 |  |  | 0 | 0
24 | <Inverter Split AC Unit, Desert Coolers Water Coolers for KGSC, Pophali> | N.A. | - | 0 | 0.0070799 | 0.0070799 | 0 | 0 | 0 |  |  | 0 | 0
25 | <Advanced ISDN EPABX system for Koyna Generating St ntercom Telephone Advanced ISDN EPABX system for Koyna Generating Station Complex> | N.A. | - | 0 | 0.029645 | 0.029645 | 0 | 0 | 0 |  |  | 0 | 0
26 | <TATA Sumo MH-14/9763 1 No> | N.A. | - | 0 | 0.041197 | 0.041197 | 0 | 0 | 0 |  |  | 0 | 0
27 | <Ambulance TATA make MH-31/4475 1 No> | N.A. | - | 0 | 0.036143 | 0.036143 | 0 | 0 | 0 |  |  | 0 | 0
28 | <Supply of 1 No of Ambulance Vane for Pophali> | N.A. | - | 0 | 0.14883 | 0.14883 | 0 | 0 | 0 |  |  | 0 | 0
29 | <Supply of 1 No of Ambulance Vane for Pophali> | N.A. | - | 0 | 0.14883 | 0.14883 | 0 | 0 | 0 |  |  | 0 | 0
30 | <HITACHI Make 2 TR non inverter split Air conditioner> | N.A. | - | 0 | 0.16739 | 0.16739 | 0 | 0 | 0 |  |  | 0 | 0
31 | <250 KVA D.G. Set Model KG1-250WS> | N.A. | - | 0 | 0.19222 | 0.19222 | 0 | 0 | 0 |  |  | 0 | 0
32 | <Dell laptops at KGSC Pophali> | N.A. | - | 0 | 0.0156 | 0.0156 | 0 | 0 | 0 |  |  | 0 | 0
33 | <A.C. Plant chiller 515 to 535 TRx2 at kgsc,Pophali> | N.A. | - | 0 | 2.1144 | 2.1144 | 0 | 0 | 0 |  |  | 0 | 0
34 | <Supply of RDP make Computers at KGSC> | N.A. | - | 0 | 0.43135 | 0.43135 | 0 | 0 | 0 |  |  | 0 | 0
35 | <Welding Machine for KDPH> | N.A. | - | 0 | 0.001039 | 0.001039 | 0 | 0 | 0 |  |  | 0 | 0
36 | <Material handling trolley for Majot store> | N.A. | - | 0 | 0.0014198 | 0.0014198 | 0 | 0 | 0 |  |  | 0 | 0
37 | <Canon LiDe 300 IN Scanner> | N.A. | - | 0 | 0.00048 | 0.00048 | 0 | 0 | 0 |  |  | 0 | 0
38 | <Supply of Pedestal fan at KDPH> | N.A. | - | 0 | 0.015 | 0.015 | 0 | 0 | 0 |  |  | 0 | 0
39 | <Supply of Refrigerator 290 LTR double door capacity> | N.A. | - | 0 | 0.0022 | 0.0022 | 0 | 0 | 0 |  |  | 0 | 0
40 | <Supply of Refrigerator 290 LTR double door capacity> | N.A. | - | 0 | 0.0022 | 0.0022 | 0 | 0 | 0 |  |  | 0 | 0
41 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.007 | 0.007 | 0 | 0 | 0 |  |  | 0 | 0
42 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.0035 | 0.0035 | 0 | 0 | 0 |  |  | 0 | 0
43 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.0035 | 0.0035 | 0 | 0 | 0 |  |  | 0 | 0
44 | <HEAVY DUTY AIR PURIFIURE 230V,50HZ> | N.A. | - | 0 | 0.0035 | 0.0035 | 0 | 0 | 0 |  |  | 0 | 0
45 | <Redmi 10 prime Mobile Black for Chief Engineer> | N.A. | - | 0 | 0.0015 | 0.0015 | 0 | 0 | 0 |  |  | 0 | 0
46 | <TATA Sumo MH-14/9763 1 No> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47 | <Ambulance TATA make MH-31/4475 1 No> | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48 | <Supply of Two Post Lift (4 Ton) for Vehicle Maint.> | N.A. | - | 0 | 0.014396 | 0.014396 | 0 | 0 | 0 |  |  | 0 | 0
49 | Supply,Installation, commissioning and testing of 415V, 3 Phase diesel generating setof 125 KVA capacity for Admin building emergency power supply backup at KGSC,Pophali. | N.A. | - | 0 | 0.0995 | 0.0995 | 0 | 0 | 0 |  |  | 0 | 0
50 | Design,Manufacturing, supply erriction and commissioning of 60 MT surface mounted (pit type/ platform type) weighbridge at major stores 'c' pophali | N.A. | - | 0 | 0.21577 | 0.21577 | 0 | 0 | 0 |  |  | 0 | 0
51 | Supply of Hydraulically operated manual stacker for Material Handling at Major Store "C", KGSC, Pophali | N.A. | - | 0 | 0.00524 | 0.00524 | 0 | 0 | 0 |  |  | 0 | 0
52 | Supply of Indef makes Chain Pulley Blocks | N.A. | - | 0 | 0.011505 | 0.011505 | 0 | 0 | 0 |  |  | 0 | 0
53 | Supply of Motwane Make ‘Digital Multimeter and AC Multimeter | N.A. | - | 0 | 0.018458 | 0.018458 | 0 | 0 | 0 |  |  | 0 | 0
54 | Supply 1 Ton split AC Daiken make for control room cabin Operation Stage III | N.A. | - | 0 | 0.00396 | 0.00396 | 0 | 0 | 0 |  |  | 0 | 0
55 | Emer Rescue cum Multipurpose Fire Tender | N.A. | - | 0 | 2.0039 | 2.0039 | 0 | 0 | 0 |  |  | 0 | 0
56 | Procurement of portable chairs for training sub centre | N.A. | - | 0 | 0.01308 | 0.01308 | 0 | 0 | 0 |  |  | 0 | 0
57 | Procurement of portable computer tables | N.A. | - | 0 | 0.0033449 | 0.0033449 | 0 | 0 | 0 |  |  | 0 | 0
58 | Purchase of High back chair (3 Nos.) in conferenc hall | N.A. | - | 0 | 0.0044014 | 0.0044014 | 0 | 0 | 0 |  |  | 0 | 0
59 | Supply of Water Purifier at MSPGCL KGSC Pophali. | N.A. | - | 0 | 0.005 | 0.005 | 0 | 0 | 0 |  |  | 0 | 0
60 | Interactive Digital LV SCREEN 6.56 FT X 3.28 FT | N.A. | - | 0 | 0.01295 | 0.01295 | 0 | 0 | 0 |  |  | 0 | 0
61 | Network Attached Storage Server at KGSC, Pophali. | N.A. | - | 0 | 0.023333 | 0.023333 | 0 | 0 | 0 |  |  | 0 | 0
62 | Supply of A4 Printer at KGSC, Pophali. | N.A. | - | 0 | 0.0099995 | 0.0099995 | 0 | 0 | 0 |  |  | 0 | 0
63 | Supply of A4 Scanner, A3 & MF Printer at KGSC, Pop | N.A. | - | 0 | 0.0586 | 0.0586 | 0 | 0 | 0 |  |  | 0 | 0
64 | Supply of Various Hard Disks for Network Attached | N.A. | - | 0 | 0.021806 | 0.021806 | 0 | 0 | 0 |  |  | 0 | 0
65 | Supply of Video conference Microphone at KGSC, | N.A. | - | 0 | 0.0021512 | 0.0021512 | 0 | 0 | 0 |  |  | 0 | 0
66 | Supply of Video Conference Screen at KGSC Pophali | N.A. | - | 0 | 0.02 | 0.02 | 0 | 0 | 0 |  |  | 0 | 0
67 | Supply of Video conference Screen at KGSC, Pophali | N.A. | - | 0 | 0.0109 | 0.0109 | 0 | 0 | 0 |  |  | 0 | 0
68 | Supply of Kelvinator / Godrej / Croma Make Refrigerator | N.A. | - | 0 | 0.010932 | 0.010932 | 0 | 0 | 0 |  |  | 0 | 0
69 | supply of Bosch make High Pressure Washer at Mecha | N.A. | - | 0 | 0.0020649 | 0.0020649 | 0 | 0 | 0 |  |  | 0 | 0
70 | Supply of Pneumatic Tools for Mechanical Maintenan | N.A. | - | 0 | 0.035259 | 0.035259 | 0 | 0 | 0 |  |  | 0 | 0
72 | Low BACK Revolving Chairs 45 No & Desk Chair 2 No | N.A. | - | 0 | 0.020945 | 0.020945 | 0 | 0 | 0 |  |  | 0 | 0
73 | Supply of Tables at KGSC | N.A. | - | 0 | 0.037339 | 0.037339 | 0 | 0 | 0 |  |  | 0 | 0
74 | Supply of Visitor Chairs & Office chairs at KGSC, | N.A. | - | 0 | 0.033201 | 0.033201 | 0 | 0 | 0 |  |  | 0 | 0
75 | water purifier for colony electrical maintenance | N.A. | - | 0 | 0.00174 | 0.00174 | 0 | 0 | 0 |  |  | 0 | 0
76 | Projectors and Motorized Projector Screens (2+2) | N.A. | - | 0 | 0.03481 | 0.03481 | 0 | 0 | 0 |  |  | 0 | 0
77 | Acer make Computers at KGSC Pophali.21 No. | N.A. | - | 0 | 0.119 | 0.119 | 0 | 0 | 0 |  |  | 0 | 0
78 | Acer make Laptops at KGSC Pophali. | N.A. | - | 0 | 0.030088 | 0.030088 | 0 | 0 | 0 |  |  | 0 | 0
79 | APS Smart UPS Xl 2200 VA RM 3U 230 | N.A. | - | 0 | 0.015983 | 0.015983 | 0 | 0 | 0 |  |  | 0 | 0
80 | BATRY 12V 75 AH BATTREY 11 PLATE | N.A. | - | 0 | 0.017629 | 0.017629 | 0 | 0 | 0 |  |  | 0 | 0
81 | Supply & installation of IP Camera System and network spare | N.A. | - | 0 | 0.025807 | 0.025807 | 0 | 0 | 0 |  |  | 0 | 0
82 | Gym Equipments at MSPGCL Recreation club , 33 Item | N.A. | - | 0 | 0.047834 | 0.047834 | 0 | 0 | 0 |  |  | 0 | 0
0 | Non-DPR schemes (3 Nos) for FY 2024-25 at KGSC Pophali | Board Resolution No-MSPGCL/BM-219/Item 219.7 dtd.24.07.2023 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
83 | Up-gradation of thyristor based 48V Battery Chargers (4 nos) by SMPS Microprocessor based dual float cum boost Battery Chargers at Stage-III, Stage-I&II and KDPH at KGSC, Pophali | 0 | - | 0 | 1.57 | 1.57 | 0 | 0 | 0 |  |  | 0 | 0
84 | Up-gradation of thyristor based 220V Battery Chargers (4 nos) by SMPS Microprocessor based dual float cum boost Battery Chargers at Stage-III and Stage-I&II at KGSC, Pophali | 0 | - | 0 | 3.79 | 3.79 | 0 | 0 | 0 |  |  | 0 | 0
85 | Retrofitting of Generator and Gen. Transformer protection relay by Numerical protection system at KGSC stage III, Alore | 0 | - | 0 | 4.78 | 4.78 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Non-DPR schemes (2 Nos) for FY 2025-26 at KGSC Pophali | Yet Not Submitted | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
86 | Supply, Erection, Commissioning & Retrofitting of 220 VDC Ni-cadmium type Battery set (4 Nos) having different ampere hour capacity at Stage-I&II and Stage-IV | 0 | - | 0 | 9.23 | 9.23 | 0 | 0 | 0 |  |  | 0 | 0
87 | Supply, Erection, Commissioning & Retrofitting of 48VDC, 300AH Ni-cadmium type Battery set at Stage-I&II switchyard | 0 | - | 0 | 0.37 | 0.37 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 499.3349 | 492.1226 | 7.2123 | 55.43 | 55.43 | 0 | 0 | 55.43 | 7.2123

## F4.1 Tillari
MSPGCL: Tillari HPS
MTR Petition Formats - Generation
| Project Details |  | Form 4.1: Capital Expenditure Plan | [14 empty] | (Rs. Crore)
Sr. No. | Project Code | Project Title | MERC Approval No. | MERC Approval Date | Project Purpose | Project Start Date |  |  | Project Completion date (Scheduled) |  |  | Capital Cost
[6 empty] | Original | Revised | Actual | Original | Revised | Actual | Approved | Actual Capital Cost Incurred | Deviation = Approved - Actual on account of
[14 empty] | Change in Scope of Work (a) | Material Cost (b) | IDC (c) | Others (d) | Total Deviation (a+b+c+d)
A) DPR Schemes
(i) Submitted to MERC
2 | Various schemes of Hydro Power Stations at HPC Pune & HPC Nasik | DPR | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 |  | 2014-08-20 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
2.1 | Replacement of Runner at Tillari Hydro Power Station for up rating Capacity from 60 MW to 66 MW. | Scheme | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | Toup rate the capcity of thr turbine from 60 to 66 MW | 2014-08-20 |  | - | - |  | 2014-01-01 | 2.37 | 2.3679 |  |  |  |  | 0.0020837
2.2 | Replacement of 235 KV Oil Filled Cables by 235 KV XLPE Cables at Tillari Hydro Power Station. | Scheme | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 1. Existing Oil Filled Cables have Oil Leakages. 2. Better Technology and Maintenance free Cables. | 2014-08-20 |  | 2016-07-01 | 2010-11-01 |  | 2018-02-01 | 4.71 | 5.7683 |  |  |  |  | -1.0583
2.3 | Replacement of existing AVR by SEE DVR system for Tillari Hydro Power Station. | Scheme | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 1. AVR is obsolete 2. Spares are not available. 3. Advanced Technology | 2014-08-20 |  | 2017-07-01 | 2012-02-01 |  | 2017-07-01 | 0.98 | 0.52724 |  |  |  |  | 0.45276
0 | IDC | IDC | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 |  | 2014-08-20 |  | - | - |  | - | 0.3312 | 0 |  |  |  |  | 0.3312
5 | Various Civil schemes for Modernisations of colonies at Various Locations under Pune HPC | DPR | MERC/CAPEX/20162017/01745 | 2017-03-31 |  | 2017-03-31 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
5.1 | Refurbishing of Residential complex | Scheme | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1. To Provoide healty envoirnment in Colony 2.Better appearance in colony premises 3. To increase life of buildings | 2017-03-31 |  | 2018-01-01 | 2018-02-01 |  | 2019-11-01 | 0.6454 | 0.56327 |  |  |  |  | 0.082129
5.2 | Internal Roads | Scheme | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1. For Safe and economical Transportstion 2. To prevent accidents and ensure safety | 2017-03-31 |  | 2018-01-01 | 2018-02-01 |  | 2018-08-01 | 0.4927 | 0.4706 |  |  |  |  | 0.022096
5.3 | Water supply, filteration & Sanitary works | Scheme | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1. To provide clesr & potable drinking water 2. To avoid water loss due to lekages | 2017-03-31 |  | 2018-02-01 | 2018-02-01 |  | WIP | 0.3308 | 0.33922 |  |  |  |  | -0.0084222
5.4 | Compound walls | Scheme | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1. To avoid encronchment & security of residaence | 2017-03-31 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | DPR | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 |  | 2020-07-17 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
14.3 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 |  | 2020-07-17 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
14.4 | Schme-D: Providing Oil Filtration Machines for all Divisions of REC, Pune | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1. Improvement in performance of Governor 2. Reduce forced outages | 2020-07-17 |  | 2020-07-01 | 2019-12-01 |  | 2021-03-01 | 0.14025 | 0.068098 |  |  |  |  | 0.072152
14.5 | Schme-E: Replacement of existing Centralized Air Conditioning System with new at Tillari Hydro Power Stn. | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1. Centralized AC Plant is obsolete & Spares are not available. 2. Replacement by Advanced Technology. 3. Increase in life of electronic equipments & auxiliaries. 4. Comfortable working environment in underground Tillari HPS | 2020-07-17 |  | 2020-07-01 | 2019-12-01 |  | WIP | 1.248 | 0 |  |  |  |  | 1.248
0 | IDC | IDC | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 |  | 2020-07-17 |  | - | - |  | - | 0.85 | 0 |  |  |  |  | 0.85
16 | Various 6 Nos. Schemes for Hydro Power Stations under Renewable Energy Circle, Pune | DPR | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 |  | 2020-07-25 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
16.1 | Replacement of existing Air Compressors at Bhira, Tilari, Pawana and Ujjani Hydro Power Stations under REC, Pune | Scheme | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1. Spares / Services providers are not available. 2. Replacement of existing one | 2020-07-25 |  | - | - |  | WIP | 0.15576 | 0 |  |  |  |  | 0.15576
16.3 | Replacement of Generator Air Coolers at Tilari HPS. | Scheme | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1. Existing Coolers beyond repairs. 2. Spares/services are not available. 3. Maintenance is Expensive | 2020-07-25 |  | - | - |  | 2023-12-07 | 0.853 | 0.68831 |  |  |  |  | 0.16469
16.4 | Replacement of 220 V, 400/300 AH Battery set with Tubular type Battery Banks at Bhira, Tilari, Kanher, Dimbhe and Ujani Hydro Power Stations. | Scheme | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1. Life is expected to over. 2. Replacement of existing one | 2020-07-25 |  | - | - |  | 2024-01-19 | 0.18 | 0.11943 |  |  |  |  | 0.060572
0 | IDC | IDC | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 |  | 2020-07-25 |  | - | - |  | - | 0.439 | 0 |  |  |  |  | 0.439
Formulas:
Project Start Date = [MERC Approval Date]
Capital Cost = IF([Project Title]="DPR",0,'F4.2 Tillari'!H19)

## F4.2 Tillari
|  |  | MSPGCL: Tillari HPS | [47 empty] | DPR | Not Initiated
|  |  | MTR Petition Formats - Generation | [47 empty] | Scheme | WIP
| Project Details |  | Form 4.2: Capitalisation Plan | [18 empty] | (Rs. Crore) | [19 empty] | (Rs. Crore) | [8 empty] | IDC | Partially Capitalized
Sr. No. | Project Code | DPR | MERC Approval No. | Date of Submission | MERC Approval Date | Cost as per DPR Crs. | MERC Approved Cost | Debt Equity Ratio | Grant Funding | Approved Start Date | Actual Start Date | Approved Date of Completion | Actual Date of Completion | Benefits in Quantified Terms | Capital Expenditure | [12 empty] | Physical Progress (%) | [6 empty] | Capitalisation | [12 empty] | Old Asset retired against capitalised item (in Rs. Cr) | Remarks | Current Status | Non-DPR | Capitalised
[15 empty] | Actual Capex till FY 2018-19 | Actual | Actual | Actual | Actual Capex till FY 2021-22 | Actual | Actual | Revised Projected | Projected | Projected | Projected | Projected | Projected | Actual Progress till FY 2018-19 | Actual | Actual | Actual | Actual | Actual | Revised Projected | Actual Capitalization till FY 2018-19 | Actual | Actual | Actual | Actual Capitalization till FY 2021-22 | Actual | Actual | Revised Projected | Projected | Projected | Projected | Projected | Projected |  |  |  |  | Cancelled
[16 empty] | FY 2019-20 | FY 2020-21 | FY 2021-22 |  | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY2025-26 | FY2026-27 | FY2027-28 | FY2028-29 | FY2029-30 |  | FY 2019-20 | FY 2020-21 | FY 2021-22 | FY 2022-23 | FY 2023-24 | FY 2024-25 |  | FY 2019-20 | FY 2020-21 | FY 2021-22 |  | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY2025-26 | FY2026-27 | FY2027-28 | FY2028-29 | FY2029-30 |  |  |  |  | To be cancelled
[50 empty] | N.A. |  | N.A.
| A) DPR Schemes | [48 empty] | N.A. |  | To be confirmed
| (i) Submitted to MERC | [48 empty] | N.A.
2 | Various schemes of Hydro Power Stations at HPC Pune & HPC Nasik | DPR | MERC/TECH 12/CAPEX/20142015/00876 | 2014-01-18 | 2014-08-20 | 8.3912 | 8.3912 |  |  | 2014-08-20 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
2.1 | Replacement of Runner at Tillari Hydro Power Station for up rating Capacity from 60 MW to 66 MW. | Scheme | MERC/TECH 12/CAPEX/20142015/00876 | 2014-01-18 | 2014-08-20 | 2.37 | 2.37 |  |  | 2014-08-20 |  |  | 2014-01-01 | 1. Runner at Tillari HPS has been replaced to up rate Turbine Capacity from 60 to 66 MW. 2. Since Quantum of Water available for generation is not changed, Benefit cannot be quantified. However, Machine Life is extended | 2.3679 |  |  |  | 2.3679 | [8 empty] | 100% | [6 empty] | 2.3679 |  |  |  | 2.3679 | [10 empty] | Capitalised
2.2 | Replacement of 235 KV Oil Filled Cables by 235 KV XLPE Cables at Tillari Hydro Power Station. | Scheme | MERC/TECH 12/CAPEX/20142015/00876 | 2014-01-18 | 2014-08-20 | 4.71 | 4.71 |  |  | 2014-08-20 | 2016-07-01 | 2010-11-01 | 2018-02-01 | 1. No routine maintenance is required – As XLPE Cables are Maintenance Free. 2. Avoid probable Major Forced Outage and Generation Loss thereof, in case of failure of existing Cables in future. | 5.7683 |  |  |  | 5.7683 | [8 empty] | 100% | [6 empty] | 5.7683 |  |  |  | 5.7683 | [10 empty] | Capitalised
2.3 | Replacement of existing AVR by SEE DVR system for Tillari Hydro Power Station. | Scheme | MERC/TECH 12/CAPEX/20142015/00876 | 2014-01-18 | 2014-08-20 | 0.98 | 0.98 |  |  | 2014-08-20 | 2017-07-01 | 2012-02-01 | 2017-07-01 | 1. Increase in Availability by reduction in Outage Period due to less Maintenance requirement compared to old AVR. 2. Avoid probable Major Forced Outage & Generation Loss thereof, in case of non-availability of AVR in future. | 0.52724 |  |  |  | 0.52724 | [8 empty] | 100% | [6 empty] | 0.52724 |  |  |  | 0.52724 | [10 empty] | Capitalised
| IDC | IDC | MERC/TECH 12/CAPEX/20142015/00876 | 2014-01-18 | 2014-08-20 | 0.3312 | 0.3312 |  |  | 2014-08-20 |  |  |  |  | 0 |  |  |  | 0 | [8 empty] | - | [6 empty] | 0 |  |  |  | 0 | [10 empty] | N.A.
5 | Various Civil schemes for Modernisations of colonies at Various Locations under Pune HPC | DPR | MERC/CAPEX/20162017/01745 | 2016-11-15 | 2017-03-31 | 1.4689 | 1.4689 |  |  | 2017-03-31 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
5.1 | Refurbishing of Residential complex | Scheme | MERC/CAPEX/20162017/01745 | 2016-11-15 | 2017-03-31 | 0.6454 | 0.6454 |  |  | 2017-03-31 | 2018-01-01 | 2018-02-01 | 2019-11-01 | 1. To Provoide healty envoirnment in Colony 2.Better appearance in colony premises 3. To increase life of buildings | 0.56327 | 0 | 0 | 0 | 0.56327 | [8 empty] | 100% | [6 empty] | 0.56327 | 0 | 0 | 0 | 0.56327 | [10 empty] | Capitalised
5.2 | Internal Roads | Scheme | MERC/CAPEX/20162017/01745 | 2016-11-15 | 2017-03-31 | 0.4927 | 0.4927 |  |  | 2017-03-31 | 2018-01-01 | 2018-02-01 | 2018-08-01 | 1. For Safe and economical Transportstion 2. To prevent accidents and ensure safety | 0.4706 | 0 | 0 | 0 | 0.4706 | [8 empty] | 100% | [6 empty] | 0.4706 | 0 | 0 | 0 | 0.4706 | [10 empty] | Capitalised
5.3 | Water supply, filteration & Sanitary works | Scheme | MERC/CAPEX/20162017/01745 | 2016-11-15 | 2017-03-31 | 0.3308 | 0.3308 |  |  | 2017-03-31 | 2018-02-01 | 2018-02-01 | WIP | 1. To provide clear & potable drinking water 2. To avoid water loss due to lekages | 0.33922 | 0 | 0 | 0 | 0.33922 | [8 empty] | 100% | [6 empty] | 0.33922 | 0 | 0 | 0 | 0.33922 | [10 empty] | Capitalised
5.4 | Compound walls | Scheme | MERC/CAPEX/20162017/01745 | 2016-11-15 | 2017-03-31 | 0 | 0 |  |  | 2017-03-31 |  |  |  | 1. To avoid encronchment & security of residaence | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0 | [10 empty] | Capitalised
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | DPR | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2019-01-29 | 2020-07-17 | 2.2382 | 2.2382 |  |  | 2020-07-17 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
14.3 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2019-01-29 | 2020-07-17 |  |  |  |  | 2020-07-17 |  |  |  |  | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [9 empty] | Not for Tillari HPS | N.A.
14.4 | Schme-D: Providing Oil Filtration Machines for all Divisions of REC, Pune | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2019-01-29 | 2020-07-17 | 0.14025 | 0.14025 |  |  | 2020-07-17 | 2020-07-01 | 2019-12-01 | 2021-03-01 | 1. Improvement in performance of Governor 2. Reduce forced outages | 0 |  | 0.068098 |  | 0.068098 | [10 empty] | 100% |  |  |  |  | 0 |  | 0.068098 |  | 0.068098 | [8 empty] | 0 |  | Capitalised
14.5 | Schme-E: Replacement of existing Centralized Air Conditioning System with new at Tillari Hydro Power Stn. | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2019-01-29 | 2020-07-17 | 1.248 | 1.248 |  |  | 2020-07-17 | 2020-07-01 | 2019-12-01 | WIP | 1. Centralized AC Plant is obsolete & Spares are not available. 2. Replacement by Advanced Technology. 3. Increase in life of electronic equipments & auxiliaries. 4. Comfortable working environment in underground Tillari HPS | 0 |  |  |  | 0 |  |  |  | 1.5057 | [11 empty] | 0 |  |  |  | 0 |  |  |  | 1.5057 | [6 empty] | WIP
| IDC | IDC | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2019-01-29 | 2020-07-17 | 0.85 | 0.85 |  |  | 2020-07-17 |  |  |  |  | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [10 empty] | N.A.
16 | Various 6 Nos. Schemes for Hydro Power Stations under Renewable Energy Circle, Pune | DPR | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2019-10-24 | 2020-07-25 | 1.6278 | 1.6278 |  |  | 2020-07-25 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
16.1 | Replacement of existing Air Compressors at Bhira, Tilari, Pawana and Ujjani Hydro Power Stations under REC, Pune | Scheme | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2019-10-24 | 2020-07-25 | 0.15576 | 0.15576 |  |  | 2020-07-25 |  |  | WIP | 1. Spares / Services providers are not available. 2. Replacement of existing one | 0 |  |  |  | 0 |  |  | 0.13216 | [12 empty] | 0 |  |  |  | 0 |  |  | 0.13216 | [7 empty] | WIP
16.3 | Replacement of Generator Air Coolers at Tilari HPS. | Scheme | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2019-10-24 | 2020-07-25 | 0.853 | 0.853 |  |  | 2020-07-25 |  |  | 2023-12-07 | 1. Existing Coolers beyond repairs. 2. Spares/services are not available. 3. Maintenance is Expensive | 0 |  |  |  | 0 |  | 0.68831 | [11 empty] | 100% |  | 0 |  |  |  | 0 |  | 0.68831 | [8 empty] | Capitalised
16.4 | Replacement of 220 V, 400/300 AH Battery set with Tubular type Battery Banks at Bhira, Tilari, Kanher, Dimbhe and Ujani Hydro Power Stations. | Scheme | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2019-10-24 | 2020-07-25 | 0.18 | 0.18 |  |  | 2020-07-25 |  |  | 2024-01-19 | 1. Life is expected to over. 2. Replacement of existing one | 0 |  |  |  | 0 |  | 0.11943 | [11 empty] | 100% |  | 0 |  |  |  | 0 |  | 0.11943 | [8 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2019-10-24 | 2020-07-25 | 0.439 | 0.439 |  |  | 2020-07-25 |  |  |  |  | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [10 empty] | N.A.
[19 empty] | 0 | [19 empty] | 0
| (ii) Yet to be submitted to MERC | [17 empty] | 0 | [19 empty] | 0
| DPR-5 | [17 empty] | 0 | [19 empty] | 0
| Upgradation of prortection system for Generator & generator transformer for Tillari HPS |  |  |  |  | 0.7847 | [7 empty] | Life is expected to over,replacement of existing one |  |  |  |  | 0 |  |  |  | 0.7847 | [15 empty] | 0 |  |  |  | 0.7847
| Supply & installation of one set ( 04 nos) of new nozzles assembly with deflector and new digital governer along with hydraulic pumping unit for Tillari HPS |  |  |  |  | 19.74 | [12 empty] | 0 |  |  |  | 19.74 | [15 empty] | 0 |  |  |  | 19.74
| DPR-7 | [17 empty] | 0 | [19 empty] | 0
| Generator Transformer for Tillari HPS |  |  |  |  | 8.33 | [7 empty] | Life is expected to over, replacement of existing one |  |  |  |  | 0 | [6 empty] | 8.33 | [12 empty] | 0 | [6 empty] | 8.33
[19 empty] | 0 | [19 empty] | 0
[19 empty] | 0 | [19 empty] | 0
| B) Non-DPR Schemes | [17 empty] | 0 | [19 empty] | 0
1 | Furniture & Fixture General Asset | Non-DPR | N.A. | [13 empty] | 0.04911 | 0.0025424 | 0.051652 | [9 empty] | 100% | 100% | 100% |  |  |  |  | 0 | 0.04911 | 0.0025424 | 0.051652 | [10 empty] | Capitalised
2 | Electrical General Asset | Non-DPR | N.A. | [12 empty] | 0.010372 | 0.013074 | 0.0032495 | 0.026696 | [9 empty] | 100% | 100% | 100% |  |  |  |  | 0.010372 | 0.013074 | 0.0032495 | 0.026696 |  | 0 | [8 empty] | Capitalised
3 | Electronics General Asset | Non-DPR | N.A. | [12 empty] | 0.0017498 | 0.0006395 | 0 | 0.0023893 | [9 empty] | 100% | 100% | 100% |  |  |  |  | 0.0017498 | 0.0006395 | 0 | 0.0023893 | [10 empty] | Capitalised
4 | Vehicle | Non-DPR | N.A. | [9 empty] | 2022-05-25 | [5 empty] | 0 | 2.0039 | [11 empty] | 100% | [6 empty] | 0 | 2.0039 | [9 empty] | Capitalised
| Total | [13 empty] | 10.0366 | 0.012122 | 0.13092 | 0.0057919 | 10.1854 | 2.0039 | 0.80774 | 0.13216 | 22.0304 | 0 | 0 | 8.33 | 0 | [7 empty] | 10.0366 | 0.012122 | 0.13092 | 0.0057919 | 10.1854 | 2.0039 | 0.80774 | 0.13216 | 22.0304 | 0 | 0 | 8.33 | 0 | 0
[36 empty] | 0.012122 | 0.13092 | 0.0057919
[36 empty] | -3e-09 | -9e-09 | 0 |  | 2.0039 | 0 | 0
1.1579
0.2725
0.077792
0.20474
0.25038
0
0.39749
2.3608
[15 empty] | 0.32487 | [19 empty] | 0.32487
[15 empty] | 0.26213 | [19 empty] | 0.26213
[15 empty] | 0.1 | [19 empty] | 0.1
[15 empty] | 0.0925 | [19 empty] | 0.0925
[15 empty] | 0.31086 | [19 empty] | 0.31086
[15 empty] | 0.22553 | [19 empty] | 0.096788
[15 empty] | 1.3159 | [19 empty] | 1.1871
0.20057
0.13371
0.18378
0.384
0.20725
0
0.33133
1.4406
Formulas:
Date of Submission = [Date of Submission, row above]
MERC Approval Date = IF([MERC Approval Date, row above]=0,"-",[MERC Approval Date, row above])
MERC Approval Date = [MERC Approval Date, row above]

## F4.3 Tillari
MSPGCL: Tillari HPS
MTR Petition Formats - Generation
| Project Details | Form 4.3: Capital Work-in-progress - Project-wise details | [9 empty] | (Rs. Crore)
Sr. No. | Project Code | MERC Approval No. | MERC Approval Date | Approved Project Cost | Cumulative Expenditure Incurred till beginning of the Year | Capital Expenditure Capitalised | Opening CWIP | Investment during the year | Capitalization |  |  |  | Closing CWIP
[9 empty] | Works Capitalised | Interest Capitalised | Expenses Capitalised | Total Capitalisation |  | Allowable Capitalisation | Probable Disallowance
FY 2022-23
a) DPR Schemes
(i) Submitted to MERC
2 | Various schemes of Hydro Power Stations at HPC Pune & HPC Nasik | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 8.3912 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Replacement of Runner at Tillari Hydro Power Station for up rating Capacity from 60 MW to 66 MW. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 2.37 | 2.3679 | 2.3679 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Replacement of 235 KV Oil Filled Cables by 235 KV XLPE Cables at Tillari Hydro Power Station. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 4.71 | 5.7683 | 5.7683 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | Replacement of existing AVR by SEE DVR system for Tillari Hydro Power Station. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.98 | 0.52724 | 0.52724 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.3312 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Various Civil schemes for Modernisations of colonies at Various Locations under Pune HPC | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1.4689 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Refurbishing of Residential complex | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.6454 | 0.56327 | 0.56327 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Internal Roads | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.4927 | 0.4706 | 0.4706 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Water supply, filteration & Sanitary works | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.3308 | 0.33922 | 0.33922 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Compound walls | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 2.2382 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.4 | Schme-D: Providing Oil Filtration Machines for all Divisions of REC, Pune | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.14025 | 0.068098 | 0.068098 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.5 | Schme-E: Replacement of existing Centralized Air Conditioning System with new at Tillari Hydro Power Stn. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1.248 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Various 6 Nos. Schemes for Hydro Power Stations under Renewable Energy Circle, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1.6278 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Replacement of existing Air Compressors at Bhira, Tilari, Pawana and Ujjani Hydro Power Stations under REC, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.15576 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.3 | Replacement of Generator Air Coolers at Tilari HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.853 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.4 | Replacement of 220 V, 400/300 AH Battery set with Tubular type Battery Banks at Bhira, Tilari, Kanher, Dimbhe and Ujani Hydro Power Stations. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.439 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR-5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of prortection system for Generator & generator transformer for Tillari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & installation of one set ( 04 nos) of new nozzles assembly with deflector and new digital governer along with hydraulic pumping unit for Tillari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR-7 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Generator Transformer for Tillari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Furniture & Fixture General Asset | N.A. | - | 0 | 0.051652 | 0.051652 | 0 | 0 | 0 |  |  | 0 | 0
2 | Electrical General Asset | N.A. | - | 0 | 0.026696 | 0.026696 | 0 | 0 | 0 |  |  | 0 | 0
3 | Electronics General Asset | N.A. | - | 0 | 0.0023893 | 0.0023893 | 0 | 0 | 0 |  |  | 0 | 0
4 | Vehicle | N.A. | - | 0 | 0 | 0 | 0 | 2.0039 | 2.0039 |  |  | 2.0039 | 0
| Total |  |  |  | 10.1854 | 10.1854 | 0 | 2.0039 | 2.0039 | 0 | 0 | 2.0039 | 0
FY 2023-24
a) DPR Schemes
(i) Submitted to MERC
2 | Various schemes of Hydro Power Stations at HPC Pune & HPC Nasik | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 8.3912 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Replacement of Runner at Tillari Hydro Power Station for up rating Capacity from 60 MW to 66 MW. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 2.37 | 2.3679 | 2.3679 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Replacement of 235 KV Oil Filled Cables by 235 KV XLPE Cables at Tillari Hydro Power Station. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 4.71 | 5.7683 | 5.7683 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | Replacement of existing AVR by SEE DVR system for Tillari Hydro Power Station. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.98 | 0.52724 | 0.52724 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.3312 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Various Civil schemes for Modernisations of colonies at Various Locations under Pune HPC | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1.4689 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Refurbishing of Residential complex | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.6454 | 0.56327 | 0.56327 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Internal Roads | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.4927 | 0.4706 | 0.4706 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Water supply, filteration & Sanitary works | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.3308 | 0.33922 | 0.33922 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Compound walls | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 2.2382 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.4 | Schme-D: Providing Oil Filtration Machines for all Divisions of REC, Pune | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.14025 | 0.068098 | 0.068098 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.5 | Schme-E: Replacement of existing Centralized Air Conditioning System with new at Tillari Hydro Power Stn. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1.248 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Various 6 Nos. Schemes for Hydro Power Stations under Renewable Energy Circle, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1.6278 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Replacement of existing Air Compressors at Bhira, Tilari, Pawana and Ujjani Hydro Power Stations under REC, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.15576 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.3 | Replacement of Generator Air Coolers at Tilari HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.853 | 0 | 0 | 0 | 0.68831 | 0.68831 |  |  | 0.68831 | 0 | 0.68831 | 0
16.4 | Replacement of 220 V, 400/300 AH Battery set with Tubular type Battery Banks at Bhira, Tilari, Kanher, Dimbhe and Ujani Hydro Power Stations. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.18 | 0 | 0 | 0 | 0.11943 | 0.11943 |  |  | 0.11943 | 0 | 0.11943 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.439 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR-5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of prortection system for Generator & generator transformer for Tillari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & installation of one set ( 04 nos) of new nozzles assembly with deflector and new digital governer along with hydraulic pumping unit for Tillari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR-7 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Generator Transformer for Tillari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Furniture & Fixture General Asset | N.A. | - | 0 | 0.051652 | 0.051652 | 0 | 0 | 0 |  |  | 0 | 0
2 | Electrical General Asset | N.A. | - | 0 | 0.026696 | 0.026696 | 0 | 0 | 0 |  |  | 0 | 0
3 | Electronics General Asset | N.A. | - | 0 | 0.0023893 | 0.0023893 | 0 | 0 | 0 |  |  | 0 | 0
4 | Vehicle | N.A. | - | 0 | 2.0039 | 2.0039 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 12.1893 | 12.1893 | 0 | 0.80774 | 0.80774 | 0 | 0 | 0.80774 | 0
FY 2024-25
a) DPR Schemes
(i) Submitted to MERC
2 | Various schemes of Hydro Power Stations at HPC Pune & HPC Nasik | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 8.3912 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Replacement of Runner at Tillari Hydro Power Station for up rating Capacity from 60 MW to 66 MW. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 2.37 | 2.3679 | 2.3679 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Replacement of 235 KV Oil Filled Cables by 235 KV XLPE Cables at Tillari Hydro Power Station. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 4.71 | 5.7683 | 5.7683 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | Replacement of existing AVR by SEE DVR system for Tillari Hydro Power Station. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.98 | 0.52724 | 0.52724 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.3312 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Various Civil schemes for Modernisations of colonies at Various Locations under Pune HPC | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1.4689 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Refurbishing of Residential complex | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.6454 | 0.56327 | 0.56327 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Internal Roads | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.4927 | 0.4706 | 0.4706 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Water supply, filteration & Sanitary works | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.3308 | 0.33922 | 0.33922 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Compound walls | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 2.2382 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.4 | Schme-D: Providing Oil Filtration Machines for all Divisions of REC, Pune | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.14025 | 0.068098 | 0.068098 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.5 | Schme-E: Replacement of existing Centralized Air Conditioning System with new at Tillari Hydro Power Stn. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1.248 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Various 6 Nos. Schemes for Hydro Power Stations under Renewable Energy Circle, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1.6278 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Replacement of existing Air Compressors at Bhira, Tilari, Pawana and Ujjani Hydro Power Stations under REC, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.15576 | 0 | 0 | 0 | 0.13216 | 0.13216 |  |  | 0.13216 | 0 | 0.13216 | 0
16.3 | Replacement of Generator Air Coolers at Tilari HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.853 | 0.68831 | 0.68831 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.4 | Replacement of 220 V, 400/300 AH Battery set with Tubular type Battery Banks at Bhira, Tilari, Kanher, Dimbhe and Ujani Hydro Power Stations. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.18 | 0.11943 | 0.11943 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.439 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR-5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of prortection system for Generator & generator transformer for Tillari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & installation of one set ( 04 nos) of new nozzles assembly with deflector and new digital governer along with hydraulic pumping unit for Tillari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR-7 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Generator Transformer for Tillari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Furniture & Fixture General Asset | N.A. | - | 0 | 0.051652 | 0.051652 | 0 | 0 | 0 |  |  | 0 | 0
2 | Electrical General Asset | N.A. | - | 0 | 0.026696 | 0.026696 | 0 | 0 | 0 |  |  | 0 | 0
3 | Electronics General Asset | N.A. | - | 0 | 0.0023893 | 0.0023893 | 0 | 0 | 0 |  |  | 0 | 0
4 | Vehicle | N.A. | - | 0 | 2.0039 | 2.0039 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 12.997 | 12.997 | 0 | 0.13216 | 0.13216 | 0 | 0 | 0.13216 | 0
FY 2025-26
a) DPR Schemes
(i) Submitted to MERC
2 | Various schemes of Hydro Power Stations at HPC Pune & HPC Nasik | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 8.3912 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Replacement of Runner at Tillari Hydro Power Station for up rating Capacity from 60 MW to 66 MW. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 2.37 | 2.3679 | 2.3679 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Replacement of 235 KV Oil Filled Cables by 235 KV XLPE Cables at Tillari Hydro Power Station. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 4.71 | 5.7683 | 5.7683 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | Replacement of existing AVR by SEE DVR system for Tillari Hydro Power Station. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.98 | 0.52724 | 0.52724 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.3312 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Various Civil schemes for Modernisations of colonies at Various Locations under Pune HPC | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1.4689 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Refurbishing of Residential complex | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.6454 | 0.56327 | 0.56327 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Internal Roads | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.4927 | 0.4706 | 0.4706 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Water supply, filteration & Sanitary works | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.3308 | 0.33922 | 0.33922 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Compound walls | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 2.2382 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.4 | Schme-D: Providing Oil Filtration Machines for all Divisions of REC, Pune | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.14025 | 0.068098 | 0.068098 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.5 | Schme-E: Replacement of existing Centralized Air Conditioning System with new at Tillari Hydro Power Stn. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1.248 | 0 | 0 | 0 | 1.5057 | 1.5057 |  |  | 1.5057 | 0 | 1.248 | 0.25774
0 | IDC | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Various 6 Nos. Schemes for Hydro Power Stations under Renewable Energy Circle, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1.6278 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Replacement of existing Air Compressors at Bhira, Tilari, Pawana and Ujjani Hydro Power Stations under REC, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.15576 | 0.13216 | 0.13216 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.3 | Replacement of Generator Air Coolers at Tilari HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.853 | 0.68831 | 0.68831 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.4 | Replacement of 220 V, 400/300 AH Battery set with Tubular type Battery Banks at Bhira, Tilari, Kanher, Dimbhe and Ujani Hydro Power Stations. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.18 | 0.11943 | 0.11943 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.439 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR-5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of prortection system for Generator & generator transformer for Tillari HPS | 0 | - | 0 | 0 | 0 | 0 | 0.7847 | 0.7847 |  |  | 0.7847 | 0
0 | Supply & installation of one set ( 04 nos) of new nozzles assembly with deflector and new digital governer along with hydraulic pumping unit for Tillari HPS | 0 | - | 0 | 0 | 0 | 0 | 19.74 | 19.74 |  |  | 19.74 | 0
0 | DPR-7 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Generator Transformer for Tillari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Furniture & Fixture General Asset | N.A. | - | 0 | 0.051652 | 0.051652 | 0 | 0 | 0 |  |  | 0 | 0
2 | Electrical General Asset | N.A. | - | 0 | 0.026696 | 0.026696 | 0 | 0 | 0 |  |  | 0 | 0
3 | Electronics General Asset | N.A. | - | 0 | 0.0023893 | 0.0023893 | 0 | 0 | 0 |  |  | 0 | 0
4 | Vehicle | N.A. | - | 0 | 2.0039 | 2.0039 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 13.1292 | 13.1292 | 0 | 22.0304 | 22.0304 | 0 | 0 | 22.0304 | 0
FY 2026-27
a) DPR Schemes
(i) Submitted to MERC
2 | Various schemes of Hydro Power Stations at HPC Pune & HPC Nasik | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 8.3912 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Replacement of Runner at Tillari Hydro Power Station for up rating Capacity from 60 MW to 66 MW. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 2.37 | 2.3679 | 2.3679 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Replacement of 235 KV Oil Filled Cables by 235 KV XLPE Cables at Tillari Hydro Power Station. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 4.71 | 5.7683 | 5.7683 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | Replacement of existing AVR by SEE DVR system for Tillari Hydro Power Station. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.98 | 0.52724 | 0.52724 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.3312 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Various Civil schemes for Modernisations of colonies at Various Locations under Pune HPC | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1.4689 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Refurbishing of Residential complex | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.6454 | 0.56327 | 0.56327 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Internal Roads | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.4927 | 0.4706 | 0.4706 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Water supply, filteration & Sanitary works | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.3308 | 0.33922 | 0.33922 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Compound walls | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 2.2382 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.4 | Schme-D: Providing Oil Filtration Machines for all Divisions of REC, Pune | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.14025 | 0.068098 | 0.068098 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.5 | Schme-E: Replacement of existing Centralized Air Conditioning System with new at Tillari Hydro Power Stn. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1.248 | 1.5057 | 1.5057 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Various 6 Nos. Schemes for Hydro Power Stations under Renewable Energy Circle, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1.6278 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Replacement of existing Air Compressors at Bhira, Tilari, Pawana and Ujjani Hydro Power Stations under REC, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.15576 | 0.13216 | 0.13216 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.3 | Replacement of Generator Air Coolers at Tilari HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.853 | 0.68831 | 0.68831 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.4 | Replacement of 220 V, 400/300 AH Battery set with Tubular type Battery Banks at Bhira, Tilari, Kanher, Dimbhe and Ujani Hydro Power Stations. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.18 | 0.11943 | 0.11943 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.439 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR-5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of prortection system for Generator & generator transformer for Tillari HPS | 0 | - | 0 | 0.7847 | 0.7847 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & installation of one set ( 04 nos) of new nozzles assembly with deflector and new digital governer along with hydraulic pumping unit for Tillari HPS | 0 | - | 0 | 19.74 | 19.74 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR-7 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Generator Transformer for Tillari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Furniture & Fixture General Asset | N.A. | - | 0 | 0.051652 | 0.051652 | 0 | 0 | 0 |  |  | 0 | 0
2 | Electrical General Asset | N.A. | - | 0 | 0.026696 | 0.026696 | 0 | 0 | 0 |  |  | 0 | 0
3 | Electronics General Asset | N.A. | - | 0 | 0.0023893 | 0.0023893 | 0 | 0 | 0 |  |  | 0 | 0
4 | Vehicle | N.A. | - | 0 | 2.0039 | 2.0039 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 35.1596 | 35.1596 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FY 2027-28
a) DPR Schemes
(i) Submitted to MERC
2 | Various schemes of Hydro Power Stations at HPC Pune & HPC Nasik | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 8.3912 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Replacement of Runner at Tillari Hydro Power Station for up rating Capacity from 60 MW to 66 MW. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 2.37 | 2.3679 | 2.3679 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Replacement of 235 KV Oil Filled Cables by 235 KV XLPE Cables at Tillari Hydro Power Station. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 4.71 | 5.7683 | 5.7683 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | Replacement of existing AVR by SEE DVR system for Tillari Hydro Power Station. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.98 | 0.52724 | 0.52724 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.3312 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Various Civil schemes for Modernisations of colonies at Various Locations under Pune HPC | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1.4689 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Refurbishing of Residential complex | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.6454 | 0.56327 | 0.56327 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Internal Roads | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.4927 | 0.4706 | 0.4706 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Water supply, filteration & Sanitary works | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.3308 | 0.33922 | 0.33922 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Compound walls | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 2.2382 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.4 | Schme-D: Providing Oil Filtration Machines for all Divisions of REC, Pune | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.14025 | 0.068098 | 0.068098 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.5 | Schme-E: Replacement of existing Centralized Air Conditioning System with new at Tillari Hydro Power Stn. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1.248 | 1.5057 | 1.5057 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Various 6 Nos. Schemes for Hydro Power Stations under Renewable Energy Circle, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1.6278 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Replacement of existing Air Compressors at Bhira, Tilari, Pawana and Ujjani Hydro Power Stations under REC, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.15576 | 0.13216 | 0.13216 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.3 | Replacement of Generator Air Coolers at Tilari HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.853 | 0.68831 | 0.68831 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.4 | Replacement of 220 V, 400/300 AH Battery set with Tubular type Battery Banks at Bhira, Tilari, Kanher, Dimbhe and Ujani Hydro Power Stations. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.18 | 0.11943 | 0.11943 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.439 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR-5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of prortection system for Generator & generator transformer for Tillari HPS | 0 | - | 0 | 0.7847 | 0.7847 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & installation of one set ( 04 nos) of new nozzles assembly with deflector and new digital governer along with hydraulic pumping unit for Tillari HPS | 0 | - | 0 | 19.74 | 19.74 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR-7 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Generator Transformer for Tillari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Furniture & Fixture General Asset | N.A. | - | 0 | 0.051652 | 0.051652 | 0 | 0 | 0 |  |  | 0 | 0
2 | Electrical General Asset | N.A. | - | 0 | 0.026696 | 0.026696 | 0 | 0 | 0 |  |  | 0 | 0
3 | Electronics General Asset | N.A. | - | 0 | 0.0023893 | 0.0023893 | 0 | 0 | 0 |  |  | 0 | 0
4 | Vehicle | N.A. | - | 0 | 2.0039 | 2.0039 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 35.1596 | 35.1596 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FY 2028-29
a) DPR Schemes
(i) Submitted to MERC
2 | Various schemes of Hydro Power Stations at HPC Pune & HPC Nasik | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 8.3912 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Replacement of Runner at Tillari Hydro Power Station for up rating Capacity from 60 MW to 66 MW. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 2.37 | 2.3679 | 2.3679 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Replacement of 235 KV Oil Filled Cables by 235 KV XLPE Cables at Tillari Hydro Power Station. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 4.71 | 5.7683 | 5.7683 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | Replacement of existing AVR by SEE DVR system for Tillari Hydro Power Station. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.98 | 0.52724 | 0.52724 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.3312 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Various Civil schemes for Modernisations of colonies at Various Locations under Pune HPC | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1.4689 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Refurbishing of Residential complex | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.6454 | 0.56327 | 0.56327 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Internal Roads | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.4927 | 0.4706 | 0.4706 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Water supply, filteration & Sanitary works | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.3308 | 0.33922 | 0.33922 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Compound walls | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 2.2382 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.4 | Schme-D: Providing Oil Filtration Machines for all Divisions of REC, Pune | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.14025 | 0.068098 | 0.068098 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.5 | Schme-E: Replacement of existing Centralized Air Conditioning System with new at Tillari Hydro Power Stn. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1.248 | 1.5057 | 1.5057 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Various 6 Nos. Schemes for Hydro Power Stations under Renewable Energy Circle, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1.6278 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Replacement of existing Air Compressors at Bhira, Tilari, Pawana and Ujjani Hydro Power Stations under REC, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.15576 | 0.13216 | 0.13216 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.3 | Replacement of Generator Air Coolers at Tilari HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.853 | 0.68831 | 0.68831 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.4 | Replacement of 220 V, 400/300 AH Battery set with Tubular type Battery Banks at Bhira, Tilari, Kanher, Dimbhe and Ujani Hydro Power Stations. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.18 | 0.11943 | 0.11943 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.439 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR-5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of prortection system for Generator & generator transformer for Tillari HPS | 0 | - | 0 | 0.7847 | 0.7847 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & installation of one set ( 04 nos) of new nozzles assembly with deflector and new digital governer along with hydraulic pumping unit for Tillari HPS | 0 | - | 0 | 19.74 | 19.74 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR-7 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Generator Transformer for Tillari HPS | 0 | - | 0 | 0 | 0 | 0 | 8.33 | 8.33 |  |  | 8.33 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Furniture & Fixture General Asset | N.A. | - | 0 | 0.051652 | 0.051652 | 0 | 0 | 0 |  |  | 0 | 0
2 | Electrical General Asset | N.A. | - | 0 | 0.026696 | 0.026696 | 0 | 0 | 0 |  |  | 0 | 0
3 | Electronics General Asset | N.A. | - | 0 | 0.0023893 | 0.0023893 | 0 | 0 | 0 |  |  | 0 | 0
4 | Vehicle | N.A. | - | 0 | 2.0039 | 2.0039 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 35.1596 | 35.1596 | 0 | 8.33 | 8.33 | 0 | 0 | 8.33 | 0
FY 2029-30
a) DPR Schemes
(i) Submitted to MERC
2 | Various schemes of Hydro Power Stations at HPC Pune & HPC Nasik | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 8.3912 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Replacement of Runner at Tillari Hydro Power Station for up rating Capacity from 60 MW to 66 MW. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 2.37 | 2.3679 | 2.3679 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Replacement of 235 KV Oil Filled Cables by 235 KV XLPE Cables at Tillari Hydro Power Station. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 4.71 | 5.7683 | 5.7683 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | Replacement of existing AVR by SEE DVR system for Tillari Hydro Power Station. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.98 | 0.52724 | 0.52724 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.3312 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Various Civil schemes for Modernisations of colonies at Various Locations under Pune HPC | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1.4689 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Refurbishing of Residential complex | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.6454 | 0.56327 | 0.56327 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Internal Roads | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.4927 | 0.4706 | 0.4706 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Water supply, filteration & Sanitary works | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.3308 | 0.33922 | 0.33922 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Compound walls | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 2.2382 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.4 | Schme-D: Providing Oil Filtration Machines for all Divisions of REC, Pune | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.14025 | 0.068098 | 0.068098 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.5 | Schme-E: Replacement of existing Centralized Air Conditioning System with new at Tillari Hydro Power Stn. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1.248 | 1.5057 | 1.5057 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Various 6 Nos. Schemes for Hydro Power Stations under Renewable Energy Circle, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1.6278 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Replacement of existing Air Compressors at Bhira, Tilari, Pawana and Ujjani Hydro Power Stations under REC, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.15576 | 0.13216 | 0.13216 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.3 | Replacement of Generator Air Coolers at Tilari HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.853 | 0.68831 | 0.68831 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.4 | Replacement of 220 V, 400/300 AH Battery set with Tubular type Battery Banks at Bhira, Tilari, Kanher, Dimbhe and Ujani Hydro Power Stations. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.18 | 0.11943 | 0.11943 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.439 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR-5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of prortection system for Generator & generator transformer for Tillari HPS | 0 | - | 0 | 0.7847 | 0.7847 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & installation of one set ( 04 nos) of new nozzles assembly with deflector and new digital governer along with hydraulic pumping unit for Tillari HPS | 0 | - | 0 | 19.74 | 19.74 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR-7 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Generator Transformer for Tillari HPS | 0 | - | 0 | 8.33 | 8.33 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Furniture & Fixture General Asset | N.A. | - | 0 | 0.051652 | 0.051652 | 0 | 0 | 0 |  |  | 0 | 0
2 | Electrical General Asset | N.A. | - | 0 | 0.026696 | 0.026696 | 0 | 0 | 0 |  |  | 0 | 0
3 | Electronics General Asset | N.A. | - | 0 | 0.0023893 | 0.0023893 | 0 | 0 | 0 |  |  | 0 | 0
4 | Vehicle | N.A. | - | 0 | 2.0039 | 2.0039 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 43.4896 | 43.4896 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## F4.1 Bhira
MSPGCL: Bhira HPS
MTR Petition Formats - Generation
| Project Details |  | Form 4.1: Capital Expenditure Plan | [14 empty] | (Rs. Crore)
Sr. No. | Project Code | Project Title | MERC Approval No. | MERC Approval Date | Project Purpose | Project Start Date |  |  | Project Completion date (Scheduled) |  |  | Capital Cost
[6 empty] | Original | Revised | Actual | Original | Revised | Actual | Approved | Actual Capital Cost Incurred | Deviation = Approved - Actual on account of
[14 empty] | Change in Scope of Work (a) | Material Cost (b) | IDC (c) | Others (d) | Total Deviation (a+b+c+d)
A) DPR Schemes
(i) In principally Approved by MERC
5 | Various Civil schemes for Modernisations of colonies at Various Locations under Pune HPC (Considered for Bhira HPS Only) | DPR | MERC/CAPEX/20162017/01745 | 2017-03-31 |  | 2017-03-31 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
5.1 | Refurbishing of Residential complex | Scheme | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1. To Provoide healty envoirnment in Colony 2.Better appearance in colony premises 3. To increase life of buildings | 2017-03-31 |  | - | - |  | 2019-11-01 | 0.6731 | 0.67693 |  |  |  |  | -0.0038253
5.2 | Internal Roads | Scheme | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1. For Safe and economical Transportstion 2. To prevent accidents and ensure safety | 2017-03-31 |  | - | - |  | 2018-08-01 | 0.1027 | 0.10089 |  |  |  |  | 0.0018112
5.3 | Water supply, filteration & Sanitary works | Scheme | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1. To provide clesr & potable drinking water 2. To avoid water loss due to lekages | 2017-03-31 |  | 2017-18 | 2018-19 |  | WIP | 0.4213 | 0 |  |  |  |  | 0.4213
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | DPR | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 |  | 2020-07-17 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
14.2 | Schme-B :Replacement of 220 kV Line CTs & PTs of Bhira Tail Race Hydro Power Station. | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1. More accurate Energy Accounting 2. Avoid forced outages | 2020-07-17 |  | 2018-12-01 | 2019-12-01 |  | 2021-03-01 | 0.25 | 0.21346 |  |  |  |  | 0.036538
14.3 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 |  | 2020-07-17 |  | - | - |  | - | 0.102 | 0 |  |  |  |  | 0.102
14.4 | Schme-D: Providing Oil Filtration Machines for all Divisions of REC, Pune | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1. Improvement in performance of Governor 2. Reduce forced outages | 2020-07-17 |  | 2018-12-01 | 2019-12-01 |  | 2021-03-01 | 0.14025 | 0.068098 |  |  |  |  | 0.072152
16 | Various 6 Nos. Schemes for Hydro Power Stations under Renewable Energy Circle, Pune | DPR | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 |  | 2020-07-25 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
16.1 | Replacement of existing Air Compressors at Bhira, Tilari, Pawana and Ujjani Hydro Power Stations under REC, Pune (2 Nos for Bhira HPS) | Scheme | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1. Spares / Services providers are not available. 2. Replacement of existing one | 2020-07-25 |  | 2019-09-01 | 2019-10-01 |  | WIP | 0.16756 | 0 |  |  |  |  | 0.16756
16.4 | Replacement of 220 V, 400/300 AH Battery set with Tubular type Battery Banks at Bhira, Tilari, Kanher, Dimbhe and Ujani Hydro Power Stations. | Scheme | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1. Life is expected to over. 2. Replacement of existing one | 2020-07-25 |  | 2019-09-01 | 2019-10-01 |  | 2024-02-16 | 0.25245 | 0.15059 |  |  |  |  | 0.10186
16.6 | Replacement of existing Protection Systems with Numerical Protection system at Bhira, Panshet, Varasgaon, Dimbhe & Manikdoh HPS. | Scheme | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1. Existing Protection is obsolete/outdated. 2. Spares are not available. 3. Replacement by Advanced Technology 4. Electrical Protection Committee suggessions | 2020-07-25 |  | 2019-09-01 | 2019-10-01 |  | WIP | 1.0704 | 0 |  |  |  |  | 1.0704
Formulas:
Project Start Date = [MERC Approval Date]

## F4.2 Bhira
|  |  | MSPGCL: Bhira HPS | [47 empty] | DPR | Not Initiated
|  |  | MTR Petition Formats - Generation | [47 empty] | Scheme | WIP
| Project Details |  | Form 4.2: Capitalisation Plan | [18 empty] | (Rs. Crore) | [19 empty] | (Rs. Crore) | [8 empty] | IDC | Partially Capitalized
Sr. No. | Project Code | DPR | MERC Approval No. | Date of Submission | MERC Approval Date | Cost as per DPR Crs. | MERC Approved Cost | Debt Equity Ratio | Grant Funding | Approved Start Date | Actual Start Date | Approved Date of Completion | Actual Date of Completion | Benefits in Quantified Terms | Capital Expenditure | [12 empty] | Physical Progress (%) | [6 empty] | Capitalisation | [12 empty] | Old Asset retired against capitalised item (in Rs. Cr) | Remarks | Current Status | Non-DPR | Capitalised
[15 empty] | Actual Capex till FY 2018-19 | Actual | Actual | Actual | Actual Capex till FY 2021-22 | Actual | Actual | Revised Projected | Projected | Projected | Projected | Projected | Projected | Actual Progress till FY 2018-19 | Actual | Actual | Actual | Actual | Actual | Revised Projected | Actual Capitalization till FY 2018-19 | Actual | Actual | Actual | Actual Capitalization till FY 2021-22 | Actual | Actual | Revised Projected | Projected | Projected | Projected | Projected | Projected |  |  |  |  | Cancelled
[16 empty] | FY 2019-20 | FY 2020-21 | FY 2021-22 |  | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY2025-26 | FY2026-27 | FY2027-28 | FY2028-29 | FY2029-30 |  | FY 2019-20 | FY 2020-21 | FY 2021-22 | FY 2022-23 | FY 2023-24 | FY 2024-25 |  | FY 2019-20 | FY 2020-21 | FY 2021-22 |  | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY2025-26 | FY2026-27 | FY2027-28 | FY2028-29 | FY2029-30 |  |  |  |  | To be cancelled
[50 empty] | N.A. |  | N.A.
| A) DPR Schemes | [48 empty] | N.A. |  | To be confirmed
| (i) In principally Approved by MERC | [48 empty] | N.A.
5 | Various Civil schemes for Modernisations of colonies at Various Locations under Pune HPC (Considered for Bhira HPS Only) | DPR | MERC/CAPEX/20162017/01745 | 2016-11-15 | 2017-03-31 | 1.1971 | 1.1971 |  |  | 2017-03-31 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
5.1 | Refurbishing of Residential complex | Scheme | MERC/CAPEX/20162017/01745 | 2016-11-15 | 2017-03-31 | 0.6731 | 0.6731 |  |  | 2017-03-31 |  |  | 2019-11-01 | 1. To Provoide healty envoirnment in Colony 2.Better appearance in colony premises 3. To increase life of buildings | 0 | 0.41417 | 0.26275 | 0 | 0.67693 | [10 empty] | 100% | 100% |  |  |  | 0 | 0.028017 | 0.64891 | 0 | 0.67693 | [8 empty] | 0 |  | Capitalised
5.2 | Internal Roads | Scheme | MERC/CAPEX/20162017/01745 | 2016-11-15 | 2017-03-31 | 0.1027 | 0.1027 |  |  | 2017-03-31 |  |  | 2018-08-01 | 1. For Safe and economical Transportstion 2. To prevent accidents and ensure safety | 0.10089 | 0 | 0 | 0 | 0.10089 | [8 empty] | 100% | 100% | 100% | 100% |  |  |  | 0.10089 | 0 | 0 | 0 | 0.10089 | [8 empty] | 0 |  | Capitalised
5.3 | Water supply, filteration & Sanitary works | Scheme | MERC/CAPEX/20162017/01745 | 2016-11-15 | 2017-03-31 | 0.4213 | 0.4213 |  |  | 2017-03-31 | 2017-18 | 2018-19 | WIP | 1. To provide clesr & potable drinking water 2. To avoid water loss due to lekages | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0 | [10 empty] | WIP
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | DPR | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2019-01-29 | 2020-07-17 | 0.49225 | 0.49225 |  |  | 2020-07-17 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
14.2 | Schme-B :Replacement of 220 kV Line CTs & PTs of Bhira Tail Race Hydro Power Station. | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2019-01-29 | 2020-07-17 | 0.25 | 0.25 |  |  | 2020-07-17 | 2018-12-01 | 2019-12-01 | 2021-03-01 | 1. More accurate Energy Accounting 2. Avoid forced outages | 0 |  |  | 0.21346 | 0.21346 | [11 empty] | 100% |  |  |  | 0 |  |  | 0.21346 | 0.21346 | [8 empty] | 0 |  | Capitalised
14.3 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2019-01-29 | 2020-07-17 | 0.102 | 0.102 |  |  | 2020-07-17 |  |  |  |  | 0 |  |  |  | 0 | [10 empty] | 70% |  |  |  |  | 0 |  |  |  | 0 | [9 empty] | Not for Bhira HPS | N.A.
14.4 | Schme-D: Providing Oil Filtration Machines for all Divisions of REC, Pune | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2019-01-29 | 2020-07-17 | 0.14025 | 0.14025 |  |  | 2020-07-17 | 2018-12-01 | 2019-12-01 | 2021-03-01 | 1. Improvement in performance of Governor 2. Reduce forced outages | 0 |  | 0.068098 |  | 0.068098 | [10 empty] | 100% |  |  |  |  | 0 |  | 0.068098 |  | 0.068098 | [8 empty] | 0 |  | Capitalised
16 | Various 6 Nos. Schemes for Hydro Power Stations under Renewable Energy Circle, Pune | DPR | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2019-10-24 | 2020-07-25 | 1.4904 | 1.4904 |  |  | 2020-07-25 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
16.1 | Replacement of existing Air Compressors at Bhira, Tilari, Pawana and Ujjani Hydro Power Stations under REC, Pune (2 Nos for Bhira HPS) | Scheme | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2019-10-24 | 2020-07-25 | 0.16756 | 0.16756 |  |  | 2020-07-25 | 2019-09-01 | 2019-10-01 | WIP | 1. Spares / Services providers are not available. 2. Replacement of existing one | 0 |  |  |  | 0 |  |  | 0.16756 | [12 empty] | 0 | 0 | 0 | 0 | 0 | [10 empty] | WIP
16.4 | Replacement of 220 V, 400/300 AH Battery set with Tubular type Battery Banks at Bhira, Tilari, Kanher, Dimbhe and Ujani Hydro Power Stations. | Scheme | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2019-10-24 | 2020-07-25 | 0.25245 | 0.25245 |  |  | 2020-07-25 | 2019-09-01 | 2019-10-01 | 2024-02-16 | 1. Life is expected to over. 2. Replacement of existing one | 0 |  |  |  | 0 |  | 0.15059 | [11 empty] | 100% |  | 0 | 0 | 0 | 0 | 0 |  | 0.15059 | [8 empty] | Capitalised
16.6 | Replacement of existing Protection Systems with Numerical Protection system at Bhira, Panshet, Varasgaon, Dimbhe & Manikdoh HPS. | Scheme | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2019-10-24 | 2020-07-25 | 1.0704 | 1.0704 |  |  | 2020-07-25 | 2019-09-01 | 2019-10-01 | WIP | 1. Existing Protection is obsolete/outdated. 2. Spares are not available. 3. Replacement by Advanced Technology 4. Electrical Protection Committee suggessions | 0 |  |  |  | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0 | [10 empty] | WIP
| (i) Submitted to MERC | [17 empty] | 0 | [19 empty] | 0
[19 empty] | 0 | [19 empty] | 0
| (ii) Yet to be submitted to MERC | [17 empty] | 0 | [19 empty] | 0
1 | DPR-5 |  | (ii) Yet to be submitted to MERC | [15 empty] | 0 | [19 empty] | 0
1.6 | Supply,Errection & Commissioning of DigitalGoverner at Bhira HPS |  |  |  |  | 6.74 | [7 empty] | With advanced microprocessor based digital governor, accurate speed control can be achieved during starting and stopping of unit. |  |  |  |  | 0 |  |  |  | 6.74 | [15 empty] | 0 |  |  |  | 6.74
2 | DPR-6 | [17 empty] | 0 | [19 empty] | 0
2.1 | Auto sequencer for Bhira HPS unit 1 & 2 |  |  |  |  | 2 | [7 empty] | 1. Advanced control algorithm using PID control with feed forward 2. High Reliability 3. Replacement by Advanced Technology |  |  |  |  | 0 | [5 empty] | 2 | [13 empty] | 0 | [5 empty] | 2
3 | DPR-7 | [17 empty] | 0 | [19 empty] | 0
3.1 | Generator Transformer at Bira HPS |  |  |  |  | 16.66 | [7 empty] | 1. Life is expected to over. 2. Replacement of existing one |  |  |  |  | 0 | [6 empty] | 16.66 | [12 empty] | 0 | [6 empty] | 16.66
[19 empty] | 0 | [19 empty] | 0
[19 empty] | 0 | [19 empty] | 0
| B) Non-DPR Schemes | [17 empty] | 0 | [19 empty] | 0
1 | Furniture & Fixture General Asset | Non-DPR | N.A. | [10 empty] | Essential for General Administration |  | 0 | 0.18419 | 0.016563 | 0.20075 | [9 empty] | 100% | 100% | 100% |  |  |  |  | 0 | 0.18419 | 0.016563 | 0.20075 | [10 empty] | Capitalised
2 | Electrical General Asset | Non-DPR | N.A. | [12 empty] | 0.0084279 | 0.01 | 0.023294 | 0.041722 |  | 0.02525 | [7 empty] | 100% | 100% | 100% |  | 100% |  |  | 0.0084279 | 0.01 | 0.023294 | 0.041722 |  | 0.02525 | [8 empty] | Capitalised
3 | Electronics General Asset | Non-DPR | N.A. | [12 empty] | 0.00085 | 0.0006395 | 0 | 0.0014895 | [9 empty] | 100% | 100% | 100% |  |  |  |  | 0.00085 | 0.0006395 | 0 | 0.0014895 | [10 empty] | Capitalised
| Total | [13 empty] | 0.10089 | 0.42345 | 0.52568 | 0.25332 | 1.3033 | 0 | 0.17584 | 0.16756 | 6.74 | 0 | 2 | 16.66 | 0 | [11 empty] | 1.3033 | 0 | 0.17584 | 0 | 6.74 | 0 | 2 | 16.66 | 0 | 0
[40 empty] | 0 | 0.02525 | 0
1.1579
0.2725
0.077792
0.20474
0.25038
0
0.39749
2.3608
[15 empty] | 0.32487 | [19 empty] | 0.32487
[15 empty] | 0.26213 | [19 empty] | 0.26213
[15 empty] | 0.1 | [19 empty] | 0.1
[15 empty] | 0.0925 | [19 empty] | 0.0925
[15 empty] | 0.31086 | [19 empty] | 0.31086
[15 empty] | 0.22553 | [19 empty] | 0.096788
[15 empty] | 1.3159 | [19 empty] | 1.1871
0.20057
0.13371
0.18378
0.384
0.20725
0
0.33133
1.4406
Formulas:
Approved Start Date = IF([MERC Approval Date]=0,"-",[MERC Approval Date])
Date of Submission = [Date of Submission, row above]
MERC Approval Date = IF([MERC Approval Date, row above]=0,"-",[MERC Approval Date, row above])
MERC Approval Date = [MERC Approval Date, row above]
Actual Date of Completion = +'[4]FY 2023-24'!L2

## F4.3 Bhira
MSPGCL: Bhira HPS
MTR Petition Formats - Generation
| Project Details | Form 4.3: Capital Work-in-progress - Project-wise details | [9 empty] | (Rs. Crore)
Sr. No. | Project Code | MERC Approval No. | MERC Approval Date | Approved Project Cost | Cumulative Expenditure Incurred till beginning of the Year | Capital Expenditure Capitalised | Opening CWIP | Investment during the year | Capitalization |  |  |  | Closing CWIP
[9 empty] | Works Capitalised | Interest Capitalised | Expenses Capitalised | Total Capitalisation |  | Allowable Capitalisation | Probable Disallowance
FY 2022-23
a) DPR Schemes
(i) In principally Approved by MERC
5 | Various Civil schemes for Modernisations of colonies at Various Locations under Pune HPC (Considered for Bhira HPS Only) | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1.1971 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Refurbishing of Residential complex | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.6731 | 0.67693 | 0.67693 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Internal Roads | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.1027 | 0.10089 | 0.10089 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Water supply, filteration & Sanitary works | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.4213 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.49225 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Schme-B :Replacement of 220 kV Line CTs & PTs of Bhira Tail Race Hydro Power Station. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.25 | 0.21346 | 0.21346 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.102 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.4 | Schme-D: Providing Oil Filtration Machines for all Divisions of REC, Pune | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.14025 | 0.068098 | 0.068098 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Various 6 Nos. Schemes for Hydro Power Stations under Renewable Energy Circle, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1.4904 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Replacement of existing Air Compressors at Bhira, Tilari, Pawana and Ujjani Hydro Power Stations under REC, Pune (2 Nos for Bhira HPS) | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.16756 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.4 | Replacement of 220 V, 400/300 AH Battery set with Tubular type Battery Banks at Bhira, Tilari, Kanher, Dimbhe and Ujani Hydro Power Stations. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.25245 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.6 | Replacement of existing Protection Systems with Numerical Protection system at Bhira, Panshet, Varasgaon, Dimbhe & Manikdoh HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1.0704 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | (i) Submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | DPR-5 | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.6 | Supply,Errection & Commissioning of DigitalGoverner at Bhira HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | DPR-6 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Auto sequencer for Bhira HPS unit 1 & 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | DPR-7 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Generator Transformer at Bira HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Furniture & Fixture General Asset | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Electrical General Asset | N.A. | - | 0 | 0.20075 | 0.20075 | 0 | 0 | 0 |  |  | 0 | 0
3 | Electronics General Asset | N.A. | - | 0 | 0.041722 | 0.041722 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 1.3018 | 1.3018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FY 2023-24
a) DPR Schemes
(i) In principally Approved by MERC
5 | Various Civil schemes for Modernisations of colonies at Various Locations under Pune HPC (Considered for Bhira HPS Only) | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1.1971 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Refurbishing of Residential complex | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.6731 | 0.67693 | 0.67693 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Internal Roads | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.1027 | 0.10089 | 0.10089 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Water supply, filteration & Sanitary works | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.4213 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.49225 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Schme-B :Replacement of 220 kV Line CTs & PTs of Bhira Tail Race Hydro Power Station. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.25 | 0.21346 | 0.21346 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.102 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.4 | Schme-D: Providing Oil Filtration Machines for all Divisions of REC, Pune | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.14025 | 0.068098 | 0.068098 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Various 6 Nos. Schemes for Hydro Power Stations under Renewable Energy Circle, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1.4904 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Replacement of existing Air Compressors at Bhira, Tilari, Pawana and Ujjani Hydro Power Stations under REC, Pune (2 Nos for Bhira HPS) | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.16756 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.4 | Replacement of 220 V, 400/300 AH Battery set with Tubular type Battery Banks at Bhira, Tilari, Kanher, Dimbhe and Ujani Hydro Power Stations. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.25245 | 0 | 0 | 0 | 0.15059 | 0.15059 |  |  | 0.15059 | 0 | 0.15059 | 0
16.6 | Replacement of existing Protection Systems with Numerical Protection system at Bhira, Panshet, Varasgaon, Dimbhe & Manikdoh HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1.0704 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | (i) Submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | DPR-5 | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.6 | Supply,Errection & Commissioning of DigitalGoverner at Bhira HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | DPR-6 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Auto sequencer for Bhira HPS unit 1 & 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | DPR-7 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Generator Transformer at Bira HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Furniture & Fixture General Asset | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Electrical General Asset | N.A. | - | 0 | 0.20075 | 0.20075 | 0 | 0.02525 | 0.02525 |  |  | 0.02525 | 0
3 | Electronics General Asset | N.A. | - | 0 | 0.041722 | 0.041722 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 1.3018 | 1.3018 | 0 | 0.17584 | 0.17584 | 0 | 0 | 0.17584 | 0
FY 2024-25
a) DPR Schemes
(i) In principally Approved by MERC
5 | Various Civil schemes for Modernisations of colonies at Various Locations under Pune HPC (Considered for Bhira HPS Only) | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1.1971 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Refurbishing of Residential complex | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.6731 | 0.67693 | 0.67693 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Internal Roads | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.1027 | 0.10089 | 0.10089 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Water supply, filteration & Sanitary works | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.4213 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.49225 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Schme-B :Replacement of 220 kV Line CTs & PTs of Bhira Tail Race Hydro Power Station. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.25 | 0.21346 | 0.21346 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.102 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.4 | Schme-D: Providing Oil Filtration Machines for all Divisions of REC, Pune | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.14025 | 0.068098 | 0.068098 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Various 6 Nos. Schemes for Hydro Power Stations under Renewable Energy Circle, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1.4904 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Replacement of existing Air Compressors at Bhira, Tilari, Pawana and Ujjani Hydro Power Stations under REC, Pune (2 Nos for Bhira HPS) | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.16756 | 0 | 0 | 0 | 0.16756 | 0 |  |  | 0 | 0.16756 | 0 | 0
16.4 | Replacement of 220 V, 400/300 AH Battery set with Tubular type Battery Banks at Bhira, Tilari, Kanher, Dimbhe and Ujani Hydro Power Stations. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.25245 | 0.15059 | 0.15059 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.6 | Replacement of existing Protection Systems with Numerical Protection system at Bhira, Panshet, Varasgaon, Dimbhe & Manikdoh HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1.0704 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | (i) Submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | DPR-5 | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.6 | Supply,Errection & Commissioning of DigitalGoverner at Bhira HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | DPR-6 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Auto sequencer for Bhira HPS unit 1 & 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | DPR-7 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Generator Transformer at Bira HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Furniture & Fixture General Asset | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Electrical General Asset | N.A. | - | 0 | 0.226 | 0.226 | 0 | 0 | 0 |  |  | 0 | 0
3 | Electronics General Asset | N.A. | - | 0 | 0.041722 | 0.041722 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 1.4777 | 1.4777 | 0 | 0.16756 | 0 | 0 | 0 | 0 | 0.16756
FY 2025-26
a) DPR Schemes
(i) In principally Approved by MERC
5 | Various Civil schemes for Modernisations of colonies at Various Locations under Pune HPC (Considered for Bhira HPS Only) | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1.1971 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Refurbishing of Residential complex | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.6731 | 0.67693 | 0.67693 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Internal Roads | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.1027 | 0.10089 | 0.10089 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Water supply, filteration & Sanitary works | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.4213 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.49225 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Schme-B :Replacement of 220 kV Line CTs & PTs of Bhira Tail Race Hydro Power Station. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.25 | 0.21346 | 0.21346 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.102 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.4 | Schme-D: Providing Oil Filtration Machines for all Divisions of REC, Pune | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.14025 | 0.068098 | 0.068098 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Various 6 Nos. Schemes for Hydro Power Stations under Renewable Energy Circle, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1.4904 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Replacement of existing Air Compressors at Bhira, Tilari, Pawana and Ujjani Hydro Power Stations under REC, Pune (2 Nos for Bhira HPS) | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.16756 | 0.16756 | 0 | 0.16756 | 0 | 0 |  |  | 0 | 0.16756 | 0 | 0
16.4 | Replacement of 220 V, 400/300 AH Battery set with Tubular type Battery Banks at Bhira, Tilari, Kanher, Dimbhe and Ujani Hydro Power Stations. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.25245 | 0.15059 | 0.15059 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.6 | Replacement of existing Protection Systems with Numerical Protection system at Bhira, Panshet, Varasgaon, Dimbhe & Manikdoh HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1.0704 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | (i) Submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | DPR-5 | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.6 | Supply,Errection & Commissioning of DigitalGoverner at Bhira HPS | 0 | - | 0 | 0 | 0 | 0 | 6.74 | 6.74 |  |  | 6.74 | 0 | 0 | 6.74
2 | DPR-6 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Auto sequencer for Bhira HPS unit 1 & 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | DPR-7 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Generator Transformer at Bira HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Furniture & Fixture General Asset | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Electrical General Asset | N.A. | - | 0 | 0.226 | 0.226 | 0 | 0 | 0 |  |  | 0 | 0
3 | Electronics General Asset | N.A. | - | 0 | 0.041722 | 0.041722 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 1.6452 | 1.4777 | 0.16756 | 6.74 | 6.74 | 0 | 0 | 6.74 | 0.16756
FY 2026-27
a) DPR Schemes
(i) In principally Approved by MERC
5 | Various Civil schemes for Modernisations of colonies at Various Locations under Pune HPC (Considered for Bhira HPS Only) | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1.1971 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Refurbishing of Residential complex | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.6731 | 0.67693 | 0.67693 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Internal Roads | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.1027 | 0.10089 | 0.10089 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Water supply, filteration & Sanitary works | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.4213 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.49225 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Schme-B :Replacement of 220 kV Line CTs & PTs of Bhira Tail Race Hydro Power Station. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.25 | 0.21346 | 0.21346 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.102 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.4 | Schme-D: Providing Oil Filtration Machines for all Divisions of REC, Pune | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.14025 | 0.068098 | 0.068098 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Various 6 Nos. Schemes for Hydro Power Stations under Renewable Energy Circle, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1.4904 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Replacement of existing Air Compressors at Bhira, Tilari, Pawana and Ujjani Hydro Power Stations under REC, Pune (2 Nos for Bhira HPS) | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.16756 | 0.16756 | 0 | 0.16756 | 0 | 0 |  |  | 0 | 0.16756 | 0 | 0
16.4 | Replacement of 220 V, 400/300 AH Battery set with Tubular type Battery Banks at Bhira, Tilari, Kanher, Dimbhe and Ujani Hydro Power Stations. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.25245 | 0.15059 | 0.15059 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.6 | Replacement of existing Protection Systems with Numerical Protection system at Bhira, Panshet, Varasgaon, Dimbhe & Manikdoh HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1.0704 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | (i) Submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | DPR-5 | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.6 | Supply,Errection & Commissioning of DigitalGoverner at Bhira HPS | 0 | - | 0 | 6.74 | 6.74 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | DPR-6 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Auto sequencer for Bhira HPS unit 1 & 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | DPR-7 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Generator Transformer at Bira HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Furniture & Fixture General Asset | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Electrical General Asset | N.A. | - | 0 | 0.226 | 0.226 | 0 | 0 | 0 |  |  | 0 | 0
3 | Electronics General Asset | N.A. | - | 0 | 0.041722 | 0.041722 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 8.3852 | 8.2177 | 0.16756 | 0 | 0 | 0 | 0 | 0 | 0.16756
FY 2027-28
a) DPR Schemes
(i) In principally Approved by MERC
5 | Various Civil schemes for Modernisations of colonies at Various Locations under Pune HPC (Considered for Bhira HPS Only) | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1.1971 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Refurbishing of Residential complex | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.6731 | 0.67693 | 0.67693 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Internal Roads | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.1027 | 0.10089 | 0.10089 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Water supply, filteration & Sanitary works | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.4213 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.49225 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Schme-B :Replacement of 220 kV Line CTs & PTs of Bhira Tail Race Hydro Power Station. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.25 | 0.21346 | 0.21346 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.102 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.4 | Schme-D: Providing Oil Filtration Machines for all Divisions of REC, Pune | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.14025 | 0.068098 | 0.068098 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Various 6 Nos. Schemes for Hydro Power Stations under Renewable Energy Circle, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1.4904 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Replacement of existing Air Compressors at Bhira, Tilari, Pawana and Ujjani Hydro Power Stations under REC, Pune (2 Nos for Bhira HPS) | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.16756 | 0.16756 | 0 | 0.16756 | 0 | 0 |  |  | 0 | 0.16756 | 0 | 0
16.4 | Replacement of 220 V, 400/300 AH Battery set with Tubular type Battery Banks at Bhira, Tilari, Kanher, Dimbhe and Ujani Hydro Power Stations. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.25245 | 0.15059 | 0.15059 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.6 | Replacement of existing Protection Systems with Numerical Protection system at Bhira, Panshet, Varasgaon, Dimbhe & Manikdoh HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1.0704 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | (i) Submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | DPR-5 | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.6 | Supply,Errection & Commissioning of DigitalGoverner at Bhira HPS | 0 | - | 0 | 6.74 | 6.74 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | DPR-6 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Auto sequencer for Bhira HPS unit 1 & 2 | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0 | 0 | 2
3 | DPR-7 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Generator Transformer at Bira HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Furniture & Fixture General Asset | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Electrical General Asset | N.A. | - | 0 | 0.226 | 0.226 | 0 | 0 | 0 |  |  | 0 | 0
3 | Electronics General Asset | N.A. | - | 0 | 0.041722 | 0.041722 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 8.3852 | 8.2177 | 0.16756 | 2 | 2 | 0 | 0 | 2 | 0.16756
FY 2028-29
a) DPR Schemes
(i) In principally Approved by MERC
5 | Various Civil schemes for Modernisations of colonies at Various Locations under Pune HPC (Considered for Bhira HPS Only) | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1.1971 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Refurbishing of Residential complex | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.6731 | 0.67693 | 0.67693 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Internal Roads | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.1027 | 0.10089 | 0.10089 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Water supply, filteration & Sanitary works | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.4213 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.49225 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Schme-B :Replacement of 220 kV Line CTs & PTs of Bhira Tail Race Hydro Power Station. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.25 | 0.21346 | 0.21346 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.102 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.4 | Schme-D: Providing Oil Filtration Machines for all Divisions of REC, Pune | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.14025 | 0.068098 | 0.068098 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Various 6 Nos. Schemes for Hydro Power Stations under Renewable Energy Circle, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1.4904 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Replacement of existing Air Compressors at Bhira, Tilari, Pawana and Ujjani Hydro Power Stations under REC, Pune (2 Nos for Bhira HPS) | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.16756 | 0.16756 | 0 | 0.16756 | 0 | 0 |  |  | 0 | 0.16756 | 0 | 0
16.4 | Replacement of 220 V, 400/300 AH Battery set with Tubular type Battery Banks at Bhira, Tilari, Kanher, Dimbhe and Ujani Hydro Power Stations. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.25245 | 0.15059 | 0.15059 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.6 | Replacement of existing Protection Systems with Numerical Protection system at Bhira, Panshet, Varasgaon, Dimbhe & Manikdoh HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1.0704 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | (i) Submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | DPR-5 | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.6 | Supply,Errection & Commissioning of DigitalGoverner at Bhira HPS | 0 | - | 0 | 6.74 | 6.74 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | DPR-6 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Auto sequencer for Bhira HPS unit 1 & 2 | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | DPR-7 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Generator Transformer at Bira HPS | 0 | - | 0 | 0 | 0 | 0 | 16.66 | 16.66 |  |  | 16.66 | 0 | 0 | 16.66
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Furniture & Fixture General Asset | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Electrical General Asset | N.A. | - | 0 | 0.226 | 0.226 | 0 | 0 | 0 |  |  | 0 | 0
3 | Electronics General Asset | N.A. | - | 0 | 0.041722 | 0.041722 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 10.3852 | 10.2177 | 0.16756 | 16.66 | 16.66 | 0 | 0 | 16.66 | 0.16756
FY 2029-30
a) DPR Schemes
(i) In principally Approved by MERC
5 | Various Civil schemes for Modernisations of colonies at Various Locations under Pune HPC (Considered for Bhira HPS Only) | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1.1971 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Refurbishing of Residential complex | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.6731 | 0.67693 | 0.67693 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Internal Roads | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.1027 | 0.10089 | 0.10089 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Water supply, filteration & Sanitary works | MERC/CAPEX/20162017/01745 | 2017-03-31 | 0.4213 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.49225 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Schme-B :Replacement of 220 kV Line CTs & PTs of Bhira Tail Race Hydro Power Station. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.25 | 0.21346 | 0.21346 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.102 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.4 | Schme-D: Providing Oil Filtration Machines for all Divisions of REC, Pune | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.14025 | 0.068098 | 0.068098 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Various 6 Nos. Schemes for Hydro Power Stations under Renewable Energy Circle, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1.4904 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Replacement of existing Air Compressors at Bhira, Tilari, Pawana and Ujjani Hydro Power Stations under REC, Pune (2 Nos for Bhira HPS) | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.16756 | 0.16756 | 0 | 0.16756 | 0 | 0 |  |  | 0 | 0.16756 | 0 | 0
16.4 | Replacement of 220 V, 400/300 AH Battery set with Tubular type Battery Banks at Bhira, Tilari, Kanher, Dimbhe and Ujani Hydro Power Stations. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.25245 | 0.15059 | 0.15059 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.6 | Replacement of existing Protection Systems with Numerical Protection system at Bhira, Panshet, Varasgaon, Dimbhe & Manikdoh HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1.0704 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | (i) Submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | DPR-5 | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.6 | Supply,Errection & Commissioning of DigitalGoverner at Bhira HPS | 0 | - | 0 | 6.74 | 6.74 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | DPR-6 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Auto sequencer for Bhira HPS unit 1 & 2 | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | DPR-7 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Generator Transformer at Bira HPS | 0 | - | 0 | 16.66 | 16.66 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Furniture & Fixture General Asset | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Electrical General Asset | N.A. | - | 0 | 0.226 | 0.226 | 0 | 0 | 0 |  |  | 0 | 0
3 | Electronics General Asset | N.A. | - | 0 | 0.041722 | 0.041722 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 27.0452 | 26.8777 | 0.16756 | 0 | 0 | 0 | 0 | 0 | 0.16756

## F4.1 SHPC Pune
MSPGCL: Pune HPC
MTR Petition Formats - Generation
| Project Details |  | Form 4.1: Capital Expenditure Plan | [14 empty] | (Rs. Crore)
Sr. No. | Project Code | Project Title | MERC Approval No. | MERC Approval Date | Project Purpose | Project Start Date |  |  | Project Completion date (Scheduled) |  |  | Capital Cost
[6 empty] | Original | Revised | Actual | Original | Revised | Actual | Approved | Actual Capital Cost Incurred | Deviation = Approved - Actual on account of
[14 empty] | Change in Scope of Work (a) | Material Cost (b) | IDC (c) | Others (d) | Total Deviation (a+b+c+d)
A) DPR Schemes
(i) Submitted to MERC
2 | Various schemes of Hydro Power Stations at HPC Pune & HPC Nasik | DPR | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 |  | 2014-08-20 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
2.4 | Replacement of existing AVR by SEE DVR system for Varasgaon Hydro Power Station. | Scheme | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 1. AVR is obsolete 2. Spares are not available. 3. Advanced Technology | 2014-08-20 | 2015-04-01 | 2017-07-02 | 2012-02-01 | 2016-03-31 | 2017-07-02 | 0.52 | 0.30933 |  |  |  |  | 0.21067
2.5 | Construction of Resthouse at Dimbhe HPS | Scheme | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 1. For convenience of Staff visiting Dimbhe HPS for Office Work | 2014-08-20 | 2014-10-01 | 2014-10-01 | 2015-03-31 | 2018-03-30 | 2017-10-30 | 0.7 | 0.73791 |  |  |  |  | -0.037912
0 | IDC | IDC | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 |  | 2014-08-20 |  | - | - |  | - | 0.3312 | 0 |  |  |  |  | 0.3312
5 | Various Civil schemes for Modernisations of colonies at Various Locations under Pune HPC | DPR | MERC/CAPEX/20162017/01745 | 2017-03-31 |  | 2017-03-31 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
5.1 | Refurbishing of Residential complex | Scheme | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1. To Provoide healty envoirnment in Colony 2.Better appearance in colony premises 3. To increase life of buildings | 2017-03-31 | 2017-11-01 | 2018-01-01 | 2018-02-01 |  | 2018-11-01 | 2.415 | 1.2675 |  |  |  |  | 1.1475
5.2 | Internal Roads | Scheme | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1. For Safe and economical Transportstion 2. To prevent accidents and ensure safety | 2017-03-31 | 2017-11-01 | 2018-01-01 | 2018-02-01 |  | Augst-18 | 2.29 | 1.6182 |  |  |  |  | 0.67176
5.3 | Water supply, filteration & Sanitary works | Scheme | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1. To provide clesr & potable drinking water 2. To avoid water loss due to lekages | 2017-03-31 | 2017-11-01 | 2017-12-01 | 2018-02-01 |  | 2018-10-01 | 1.427 | 0.57282 |  |  |  |  | 0.85418
5.4 | Compound walls | Scheme | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1. To avoid encronchment & security of residaence | 2017-03-31 | 2017-11-01 | 2017-11-01 | 2018-02-01 |  | 2019-01-01 | 6.681 | 7.5561 |  |  |  |  | -0.87508
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | DPR | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 |  | 2020-07-17 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
14.1 | Schme-A: Retrofitting of 12 KV Breakers at Ujjani Hydro Power Station | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1. Breakers are obsolete 2. Spares are not available 3. Replacement by Advanced Technology | 2020-07-17 | 2019-02-01 |  | 2020-11-01 | 2022-07-01 | 2022-07-01 | 0.395 | 0.26762 |  |  |  |  | 0.12738
14.3 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1. More accurate Energy Accounting 2. Avoid forced outages 3. Replacement by Advanced Technology | 2020-07-17 | 2019-02-01 |  | 2020-10-01 | 2022-12-01 | WIP | 0.102 | 0.096156 |  |  |  |  | 0.005844
14.4 | Schme-D: Providing Oil Filtration Machines for all Divisions of REC, Pune | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1. Improvement in performance of Governor 2. Reduce forced outages | 2020-07-17 | 2019-02-01 |  | 2016-10-01 | 2021-03-01 | 2021-03-01 | 0.561 | 0.27239 |  | 0.28861 |  |  | 0.28861
0 | IDC | IDC | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 |  | 2020-07-17 |  | - | - |  | - | 0.85 | 0 |  |  |  |  | 0.85
16 | Various 6 Nos. Schemes for Hydro Power Stations under Renewable Energy Circle, Pune | DPR | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 |  | 2020-07-25 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
16.1 | Replacement of existing Air Compressors at Bhira, Tilari, Pawana and Ujjani Hydro Power Stations under REC, Pune | Scheme | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1. Spares / Services providers are not available. 2. Replacement of existing one | 2020-07-25 | 2018-06-01 |  | 2020-03-31 |  | WIP | 0.951 | 0 |  |  |  |  | 0.951
16.2 | Replacement of existing Air conditioners of Plant Control Rooms at Ujjani, Warna, Kanher, Dhom, Dimbhe & Dudhganga HPS. | Scheme | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1. Existing A/C system is obsolete 2. Spares are not available. 3. Replacement by Advanced Technology | 2020-07-25 | 2018-05-01 |  | 2021-03-31 |  | 2022-03-01 | 0.292 | 0.25256 |  | 0.039436 |  |  | 0.039436
16.4 | Replacement of 220 V, 400/300 AH Battery set with Tubular type Battery Banks at Bhira, Tilari, Kanher, Dimbhe and Ujani Hydro Power Stations. | Scheme | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1. Life is expected to over. 2. Replacement of existing one | 2020-07-25 | 2018-07-01 |  | 2021-03-31 |  | WIP | 0.9 | 0.35828 |  |  |  |  | 0.54172
16.5 | Supply, installation and commissioning of Kaplan Turbine Runner Blades from BHEL (OEM) for Dudhganga U#1. | Scheme | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1. Repaired blades are in service which is not reliable. 2. Spare blades are not available. | 2020-07-25 | 2018-09-01 |  | 2019-03-31 |  | WIP | 4.657 | 4.573 |  |  |  |  | 0.083963
16.6 | Replacement of existing Protection Systems with Numerical Protection system at Bhira, Panshet, Varasgaon, Dimbhe & Manikdoh HPS. | Scheme | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 1. Existing Protection is obsolete/outdated. 2. Spares are not available. 3. Replacement by Advanced Technology 4. Electrical Protection Committee suggessions | 2020-07-25 | 2018-12-01 |  | 2019-03-31 |  | WIP | 3.622 | 0.53395 |  |  |  |  | 3.0881
0 | IDC | IDC | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 |  | 2020-07-25 |  | - | - |  | - | 0.439 | 0 |  |  |  |  | 0.439
17 | Fortification near Panshet hydro power station for arresting rock falling on HPS Building at panshet . | DPR | Not approved | - |  | - |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
17.1 | Fortification near Panshet hydro power station for arresting rock falling on HPS Building at panshet . | Scheme | Not approved | - |  | - |  | - | - |  | - | 0 | 12.06 |  |  |  |  | -12.06
Formulas:
Project Start Date = [MERC Approval Date]

## F4.2 SHPC Pune
|  |  | MSPGCL: Pune HPC | [47 empty] | DPR | Not Initiated
|  |  | MTR Petition Formats - Generation | [47 empty] | Scheme | WIP
| Project Details |  | Form 4.2: Capitalisation Plan | [18 empty] | (Rs. Crore) | [19 empty] | (Rs. Crore) | [8 empty] | IDC | Partially Capitalized
Sr. No. | Project Code | DPR | MERC Approval No. | Date of Submission | MERC Approval Date | Cost as per DPR Crs. | MERC Approved Cost | Debt Equity Ratio | Grant Funding | Approved Start Date | Actual Start Date | Approved Date of Completion | Actual Date of Completion | Benefits in Quantified Terms | Capital Expenditure | [12 empty] | Physical Progress (%) | [6 empty] | Capitalisation | [12 empty] | Old Asset retired against capitalised item (in Rs. Cr) | Remarks | Current Status | Non-DPR | Capitalised
[15 empty] | Actual Capex till FY 2018-19 | Actual | Actual | Actual | Actual Capex till FY 2021-22 | Actual | Actual | Revised Projected | Projected | Projected | Projected | Projected | Projected | Actual Progress till FY 2018-19 | Actual | Actual | Actual | Actual | Actual | Revised Projected | Actual Capitalization till FY 2018-19 | Actual | Actual | Actual | Actual Capitalization till FY 2021-22 | Actual | Actual | Revised Projected | Projected | Projected | Projected | Projected | Projected |  |  |  |  | Cancelled
[16 empty] | FY 2019-20 | FY 2020-21 | FY 2021-22 |  | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY2025-26 | FY2026-27 | FY2027-28 | FY2028-29 | FY2029-30 |  | FY 2019-20 | FY 2020-21 | FY 2021-22 | FY 2022-23 | FY 2023-24 | FY 2024-25 |  | FY 2019-20 | FY 2020-21 | FY 2021-22 |  | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY2025-26 | FY2026-27 | FY2027-28 | FY2028-29 | FY2029-30 |  |  |  |  | To be cancelled
[50 empty] | N.A. |  | N.A.
| A) DPR Schemes | [48 empty] | N.A. |  | To be confirmed
| (i) Submitted to MERC | [48 empty] | N.A.
2 | Various schemes of Hydro Power Stations at HPC Pune & HPC Nasik | DPR | MERC/TECH 12/CAPEX/20142015/00876 | 2014-01-18 | 2014-08-20 | 1.5512 | 1.5512 |  |  | 2014-08-20 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
2.4 | Replacement of existing AVR by SEE DVR system for Varasgaon Hydro Power Station. | Scheme | MERC/TECH 12/CAPEX/20142015/00876 | 2014-01-18 | 2014-08-20 | 0.52 | 0.52 |  |  | 2014-08-20 | 2017-07-02 | 2012-02-01 | 2017-07-02 | 1. AVR is obsolete 2. Spares are not available. 3. Advanced Technology | 0.30933 |  |  |  | 0.30933 | [8 empty] | 100% | [6 empty] | 0.30933 |  |  |  | 0.30933 | [10 empty] | Capitalised
2.5 | Construction of Resthouse at Dimbhe HPS | Scheme | MERC/TECH 12/CAPEX/20142015/00876 | 2014-01-18 | 2014-08-20 | 0.7 | 0.7 |  |  | 2014-08-20 | 2014-10-01 | 2015-03-31 | 2017-10-30 | For convenience of Staff visiting Dimbhe HPS for Office Work | 0.73791 |  |  |  | 0.73791 | [8 empty] | 100% | [6 empty] | 0.73791 |  |  |  | 0.73791 | [10 empty] | Capitalised
| IDC | IDC | MERC/TECH 12/CAPEX/20142015/00876 | 2014-01-18 | 2014-08-20 | 0.3312 | 0.3312 |  |  | 2014-08-20 |  |  |  |  | 0 |  |  |  | 0 | [8 empty] | - | [6 empty] | 0 |  |  |  | 0 | [10 empty] | N.A.
5 | Various Civil schemes for Modernisations of colonies at Various Locations under Pune HPC | DPR | MERC/CAPEX/20162017/01745 | 2016-11-15 | 2017-03-31 | 13.8089 | 12.813 |  |  | 2017-03-31 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
5.1 | Refurbishing of Residential complex | Scheme | MERC/CAPEX/20162017/01745 | 2016-11-15 | 2017-03-31 | 3.409 | 2.415 |  |  | 2017-03-31 | 2018-01-01 | 2018-02-01 | 2018-11-01 | 1. To Provoide healty envoirnment in Colony 2. Better appearance in colony premises 3. To increase life of buildings | 0.90914 | 0.26894 | 0.089428 | 0 | 1.2675 | [8 empty] | 78.91% | 100% | [5 empty] | 0.55544 | 0.62264 | 0.089428 | 0 | 1.2675 | 0 | [7 empty] | 0 |  | Capitalised
5.2 | Internal Roads | Scheme | MERC/CAPEX/20162017/01745 | 2016-11-15 | 2017-03-31 | 2.2907 | 2.29 |  |  | 2017-03-31 | 2018-01-01 | 2018-02-01 | Augst-18 | 1. For Safe and economical Transportstion 2. To prevent accidents and ensure safety | 1.5809 | 0.037367 | 0 | 0 | 1.6182 | [8 empty] | 98.04% | 100.3% | [5 empty] | 1.2435 | 0.37472 | 0 | 0 | 1.6182 | 0 | [7 empty] | 0 |  | Capitalised
5.3 | Water supply, filteration & Sanitary works | Scheme | MERC/CAPEX/20162017/01745 | 2016-11-15 | 2017-03-31 | 1.4279 | 1.427 |  |  | 2017-03-31 | 2017-12-01 | 2018-02-01 | 2018-10-01 | 1. To provide clesr & potable drinking water 2. To avoid water loss due to lekages | 0.43234 | 0.14049 | 0 | 0 | 0.57282 | [8 empty] | 78.22% | 100% | [5 empty] | 0 | 0.27952 | 0.2933 | 0 | 0.57282 | 0 | [7 empty] | 0 |  | Capitalised
5.4 | Compound walls | Scheme | MERC/CAPEX/20162017/01745 | 2016-11-15 | 2017-03-31 | 6.6813 | 6.681 |  |  | 2017-03-31 | 2017-11-01 | 2018-02-01 | 2023-09-05 | 1. To avoid encronchment & security of residaence | 3.8515 | 0.22897 | 0 | 0.71989 | 4.8004 |  | 2.7557 | [6 empty] | 79.68% | 84.44% | 84.44% | 100.3% |  |  |  | 2.7822 | 0.90667 | 0.39161 | 0.71989 | 4.8004 |  | 2.7557 | [6 empty] | 0 |  | Capitalised
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | DPR | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2019-01-29 | 2020-07-17 | 1.908 | 1.908 |  |  | 2020-07-17 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
14.1 | Schme-A: Retrofitting of 12 KV Breakers at Ujjani Hydro Power Station | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2019-01-29 | 2020-07-17 | 0.395 | 0.395 |  |  | 2020-07-17 | 2021-10-01 | 2020-11-01 | 2022-05-10 | 1. Breakers are obsolete 2. Spares are not available 3. Replacement by Advanced Technology | 0 | 0 | 0 | 0 | 0 | 0.26762 | [11 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0.26762 | [9 empty] | Capitalised
14.3 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2019-01-29 | 2020-07-17 | 0.102 | 0.102 |  |  | 2020-07-17 | 2020-12-01 | 2021-02-12 | WIP | 1. More accurate Energy Accounting 2. Avoid forced outages 3. Replacement by Advanced Technology | 0 | 0 | 0.096156 | 0 | 0.096156 | [11 empty] | 70% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0.079692 | [9 empty] | WIP
14.4 | Schme-D: Providing Oil Filtration Machines for all Divisions of REC, Pune | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2019-01-29 | 2020-07-17 | 0.561 | 0.561 |  |  | 2020-07-17 |  | 2016-10-01 | 2021-03-01 | 1. Improvement in performance of Governor 2. Reduce forced outages | 0 | 0 | 0.27239 |  | 0.27239 | [10 empty] | 100% |  |  |  |  | 0 | 0 | 0.27239 |  | 0.27239 | [10 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2019-01-29 | 2020-07-17 | 0.85 | 0.85 |  |  | 2020-07-17 |  |  |  |  | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [10 empty] | N.A.
16 | Various 6 Nos. Schemes for Hydro Power Stations under Renewable Energy Circle, Pune | DPR | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2019-10-24 | 2020-07-25 | 10.861 | 10.861 |  |  | 2020-07-25 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
16.1 | Replacement of existing Air Compressors at Bhira, Tilari, Pawana and Ujjani Hydro Power Stations under REC, Pune | Scheme | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2019-10-24 | 2020-07-25 | 0.951 | 0.951 |  |  | 2020-07-25 |  | 2020-03-31 | WIP | 1. Spares / Services providers are not available. 2. Replacement of existing one | 0 | 0 | 0 | 0 | 0 |  |  | 0.13 | 0.48 | [8 empty] | 100% |  |  | 0 |  |  |  | 0 |  |  | 0.13 | 0.48 | [6 empty] | WIP
16.2 | Replacement of existing Air conditioners of Plant Control Rooms at Ujjani, Warna, Kanher, Dhom, Dimbhe & Dudhganga HPS. | Scheme | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2019-10-24 | 2020-07-25 | 0.292 | 0.292 |  |  | 2020-07-25 |  | 2021-03-31 | 2022-03-01 | 1. Existing A/C system is obsolete 2. Spares are not available. 3. Replacement by Advanced Technology | 0 | 0 | 0 | 0.25256 | 0.25256 | [11 empty] | 100% |  |  |  | 0 |  |  | 0.25256 | 0.25256 | [10 empty] | Capitalised
16.4 | Replacement of 220 V, 400/300 AH Battery set with Tubular type Battery Banks at Bhira, Tilari, Kanher, Dimbhe and Ujani Hydro Power Stations. | Scheme | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2019-10-24 | 2020-07-25 | 0.9 | 0.9 |  |  | 2020-07-25 |  | 2021-03-31 | 2024-02-07 | 1. Life is expected to over. 2. Replacement of existing one | 0 | 0 | 0 | 0 | 0 |  | 0.35828 | [10 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 |  | 0.35828 | [8 empty] | Capitalised
16.5 | Supply, installation and commissioning of Kaplan Turbine Runner Blades from BHEL (OEM) for Dudhganga U#1. | Scheme | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2019-10-24 | 2020-07-25 | 4.657 | 4.657 |  |  | 2020-07-25 | 2022-01-01 | 2019-03-31 | 2022-08-03 | 1. Repaired blades are in service which is not reliable. 2. Spare blades are not available. | 0 |  | 0.20886 | 2.8097 | 3.0186 | 1.4337 | 0.12074 | [10 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 4.4592 | 0.12074 | [8 empty] | Capitalised
16.6 | Replacement of existing Protection Systems with Numerical Protection system at Bhira, Panshet, Varasgaon, Dimbhe & Manikdoh HPS. | Scheme | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2019-10-24 | 2020-07-25 | 3.622 | 3.622 |  |  | 2020-07-25 |  | 2019-03-31 | WIP | 1. Existing Protection is obsolete/outdated. 2. Spares are not available. 3. Replacement by Advanced Technology 4. Electrical Protection Committee suggessions | 0 | 0 | 0 | 0 | 0 |  | 0.53395 | 1.6 | [9 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 |  | 0.53395 | 1.6 | [7 empty] | WIP
| IDC | IDC | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2019-10-24 | 2020-07-25 | 0.439 | 0.439 |  |  | 2020-07-25 |  |  |  |  | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [10 empty] | N.A.
17 | Fortification near Panshet hydro power station for arresting rock falling on HPS Building at panshet . | DPR | Not approved | 2022-06-30 |  | 12.33 | 0 | [6 empty] | For HPS Safety |  |  |  |  | 0 | [19 empty] | 0 | [10 empty] | N.A.
17.1 | Fortification near Panshet hydro power station for arresting rock falling on HPS Building at panshet . | Scheme | Not approved | 2022-06-30 | - | 12.33 |  |  |  | - | [8 empty] | 0 | 12.06 | [18 empty] | 0 | [10 empty] | N.A.
| (ii) Yet to be submitted to MERC | [17 empty] | 0 | [19 empty] | 0
1 | DPR-5 |  | (ii) Yet to be submitted to MERC | [15 empty] | 0 | [19 empty] | 0
1.1 | Supply, erection & commissioning of Digital Governor and DAVR for Panshet HPS under REC, Pune |  | (ii) Yet to be submitted to MERC |  |  | 4.5 | [7 empty] | With advanced microprocessor based digital governor, accurate speed control can be achieved during starting and stopping of unit. |  | 0 | 0 | 0 | 0 |  |  |  | 4.5 | [12 empty] | 0 | 0 | 0 | 0 |  | 0 |  | 4.5 | [6 empty] | Not Initiated
1.2 | Supply, erection & commissioning of Digital Governor, Excitation system (DAVR) at Warana & Dudhganga HPS |  | (ii) Yet to be submitted to MERC |  |  | 18.79 | [7 empty] | 1. Advanced control algorithm using PID control with feed forward 2. High Reliability 3. Replacement by Advanced Technology |  | 0 | 0 | 0 | 0 |  |  |  |  | 18.79 | [11 empty] | 0 | 0 | 0 | 0 |  | 0 |  |  | 18.79 | [5 empty] | Not Initiated
1.3 | Supply,erection & commissioningof Governor, Excitation System (DAVR) and Autosequencer for Manikdoh, Kanher & Dimbhe HPS. |  | (ii) Yet to be submitted to MERC |  |  | 14.35 | [7 empty] | 1. Advanced control algorithm using PID control with feed forward 2. High Reliability 3. Replacement by Advanced Technology |  | 0 | 0 | 0 | 0 |  |  |  |  | 14.35 | [11 empty] | 0 | 0 | 0 | 0 |  | 0 |  |  | 14.35 | [5 empty] | Not Initiated
1.4 | Supply, erection & commissioning of Digital Governor Pawana & Varasgaon HPS |  | (ii) Yet to be submitted to MERC |  |  | 6.74 | [7 empty] | With advanced microprocessor based digital governor, accurate speed control can be achieved during starting and stopping of unit. |  | 0 | 0 | 0 | 0 |  |  |  | 6.74 | [12 empty] | 0 | 0 | 0 | 0 |  | 0 |  | 6.74 | [6 empty] | Not Initiated
1.5 | Upgradation of Protection system for Generator and Generator transformer at bhatghar,Dudhganga,Ujani,Warana,Kanher & Dhom |  | (ii) Yet to be submitted to MERC |  |  | 7.22 | [7 empty] | 1. Existing Protection is obsolete/outdated. 2. Spares are not available. 3. Replacement by Advanced Technology 4. Electrical Protection Committee suggessions |  |  |  |  | 0 |  |  |  | 7.22 | [15 empty] | 0 |  | 0 |  | 7.22 | [6 empty] | Not Initiated
| DPR-6 | [17 empty] | 0 | [19 empty] | 0
| Synchronising & Line Breakers at HPS under REC, Pune |  | (ii) Yet to be submitted to MERC |  |  | 5.1 | [7 empty] | 1. Reduced size and Compact. 2. Improves the reliability 3. Avoid unwanted tripping of units. 4. New technology Breakers |  |  |  |  | 0 | [5 empty] | 5.1 | [13 empty] | 0 | [5 empty] | 5.1
| Digital Governor, Excitation (DAVR) with Auto sequencer at Ujjani HPS |  | (ii) Yet to be submitted to MERC |  |  | 3.12 | [7 empty] | 1. Advanced control algorithm using PID control with feed forward 2. High Reliability 3. Replacement by Advanced Technology |  |  |  |  | 0 | [5 empty] | 3.12 | [13 empty] | 0 | [5 empty] | 3.12
| Supply of station battery sets at Panshet, Varasgaon, Pawana, Dhom, Terwanmedhe |  | (ii) Yet to be submitted to MERC |  |  | 1 | [7 empty] | 1. Battery voltage & protection system accuracy is improved. 2. Maintenance cost will be reduced. 3. Breakdown and plant tripping event also reduced. |  |  |  |  | 0 | [5 empty] | 1 | [13 empty] | 0 | [5 empty] | 1
| Digital Governor, Excitation (DAVR) with Auto sequencer at Dhom HPS |  | (ii) Yet to be submitted to MERC |  |  | 6.22 | [7 empty] | 1. Advanced control algorithm using PID control with feed forward 2. High Reliability 3. Replacement by Advanced Technology |  |  |  |  | 0 | [5 empty] | 6.22 | [13 empty] | 0 | [5 empty] | 6.22
| R & M of Bhatghar HPS |  | (ii) Yet to be submitted to MERC |  |  | 10 | [7 empty] | 1. Life is expected to over. 2. Replacement of existing one |  |  |  |  | 0 | [5 empty] | 10 | [13 empty] | 0 | [5 empty] | 10
1.7 | DPR-8 | [17 empty] | 0 | [19 empty] | 0
| Gen. transformers for Dudhganga, Warana, Ujjani, Panshet, Varasgaon & Pawana HPS |  | (ii) Yet to be submitted to MERC |  |  | 35 | [7 empty] | 1. Life is expected to over. 2. Replacement of existing one |  |  |  |  | 0 | [7 empty] | 35 | [11 empty] | 0 | [7 empty] | 35
[19 empty] | 0 | [19 empty] | 0
| B) Non-DPR Schemes | [17 empty] | 0 | [19 empty] | 0
1 | Replacement of 220V/300 AH Tubular type Battery Set at Manikdoh HPS | Non-DPR | N.A. | [7 empty] | 2022-12-01 |  | 2023-03-25 | 1. Battery voltage & protection system accuracy is improved. 2. Maintenance cost will be reduced. 3. Breakdown and plant tripping event also reduced. |  | 0 | 0 | 0 | 0 | 0.1138 | [15 empty] | 0 | 0 | 0 | 0 | 0.1138 | [9 empty] | Capitalised
2 | Replacement of existing AVR by DAVR for Static Excitation System at Pawana HPS. | Non-DPR | N.A. | [10 empty] | 1. Advanced control algorithm using PID control with feed forward 2. High Availability & Reliability 3. Availability of Spares. 4. Replacement by Advanced Technology |  | 0 | 0 | 0 | 0 |  |  | 1.01 | [13 empty] | 0 | 0 | 0 | 0 |  |  | 1.01 | [7 empty] | WIP
3 | Retrofitting of 415 V LT Breakers at Kanher & Dhom HPS. | Non-DPR | N.A. | [7 empty] | 2022-11-01 |  | 2023-03-28 | 1. Reduced size and Compact. 2. Improves the reliability 3. Avoid unwanted tripping of units. 4. New technology Breakers |  | 0 | 0 |  | 0 | 0.098744 | [15 empty] | 0 | 0 | 0 | 0 | 0.098744 | [9 empty] | Capitalised
4 | Furniture & Fixture General Asset | Non-DPR | N.A. | [9 empty] | 2023-10-24 | Essential for General Administration |  | 0.052665 | 0.94423 | 0.031609 | 1.0285 |  | 0.029146 | 0.01 | [6 empty] | 100% | 100% | 100% |  |  |  |  | 0.052665 | 0.94423 | 0.031609 | 1.0285 |  | 0.029146 | 0.01 | [7 empty] | Capitalised
5 | Electrical General Asset | Non-DPR | N.A. | [6 empty] | 2024-02-22 | 2024-02-22 |  | 2024-02-22 |  |  | 0.063437 | 0.020934 | 0.042755 | 0.12713 | 0.0036 | 0.063954 | [7 empty] | 100% | 100% | 100% |  |  |  |  | 0.063437 | 0.020934 | 0.042755 | 0.12713 | 0.0036 | 0.063954 | [8 empty] | Capitalised
6 | Electronics General Asset | Non-DPR | N.A. | [6 empty] | 2024-01-17 | 2024-01-17 |  | 2024-01-17 |  |  | 0.012199 | 0.18481 | 0.041452 | 0.23846 | 0.001344 | 0.016809 | 0.02 | [6 empty] | 100% | 100% | 100% |  |  |  |  | 0.012199 | 0.18481 | 0.041452 | 0.23846 | 0.001344 | 0.016809 | 0.02 | [7 empty] | Capitalised
7 | Vehicle General Asset | Non-DPR | N.A. | [12 empty] | 0.14352 | 0.029364 |  | 0.17289 | [9 empty] | 100% | 100% | [5 empty] | 0.14352 | 0.029364 | 0 | 0.17289 | 0 | [9 empty] | Capitalised
8 | Numerical protection system at Pawana Hydro Power Station | Non-DPR | N.A. | [10 empty] | 1. Existing Protection is obsolete/outdated. 2. Spares are not available. 3. Replacement by Advanced Technology 4. Electrical Protection Committee suggessions |  | 0.30562 | 0.02462 |  | 0.33024 | [9 empty] | 100% | [6 empty] | 0.30562 | 0.02462 |  | 0.33024 | [10 empty] | Capitalised
| Total | [13 empty] | 7.8211 | 1.2532 | 1.8708 | 3.898 | 14.8431 | 13.9788 | 3.8786 | 2.77 | 18.94 | 33.14 | 25.44 | 0 | 35 | [7 empty] | 5.6284 | 2.761 | 2.2507 | 1.0883 | 11.7284 | 5.024 | 3.8786 | 2.77 | 18.94 | 33.14 | 25.44 | 0 | 35 | 0
[18 empty] | 6+6+6+6+6+6+ | [17 empty] | 2.761 | 2.2507 | 1.0883
[36 empty] | 0 | 1.1e-08 | -4.6e-08 |  | 0.21749 | 0.10991
[36 empty] | 0.30562 | 0.02462 |  |  | 7.79 | 3.49 | 35.32
0.30562
[38 empty] | 1.9207 |  | 13.3188 | 7.5017 | 47.9349 | 131.7502 | 101.14 | 93.94 | 0 | 35
1.1579
0.2725
0.077792
0.20474
0.25038
0
0.39749
2.3608
[15 empty] | 0.32487 | [19 empty] | 0.32487
[15 empty] | 0.26213 | [19 empty] | 0.26213
[15 empty] | 0.1 | [19 empty] | 0.1
[15 empty] | 0.0925 | [19 empty] | 0.0925
[15 empty] | 0.31086 | [19 empty] | 0.31086
[15 empty] | 0.22553 | [19 empty] | 0.096788
[15 empty] | 1.3159 | [19 empty] | 1.1871
0.20057
0.13371
0.18378
0.384
0.20725
0
0.33133
1.4406
[18 empty] | 0 | 0
Formulas:
Approved Start Date = IF([MERC Approval Date]=0,"-",[MERC Approval Date])
Approved Start Date = [Actual Date of Completion]
Date of Submission = [Date of Submission, row above]
MERC Approval Date = [MERC Approval Date, row above]
MERC Approval Date = IF([MERC Approval Date, row above]=0,"-",[MERC Approval Date, row above])
Actual Start Date = +'[5]F4.1'!I11
Actual Start Date = [Actual Date of Completion]
Approved Date of Completion = +'[5]F4.1'!J11
Approved Date of Completion = +'[5]FY 2022-23'!L12
Actual Date of Completion = '[5]F4.1'!L15
Actual Date of Completion = +'[5]FY 2023-24'!L2

## F4.3 SHPC Pune
MSPGCL: Pune HPC
MTR Petition Formats - Generation
| Project Details | Form 4.3: Capital Work-in-progress - Project-wise details | [9 empty] | (Rs. Crore)
Sr. No. | Project Code | MERC Approval No. | MERC Approval Date | Approved Project Cost | Cumulative Expenditure Incurred till beginning of the Year | Capital Expenditure Capitalised | Opening CWIP | Investment during the year | Capitalization |  |  |  | Closing CWIP
[9 empty] | Works Capitalised | Interest Capitalised | Expenses Capitalised | Total Capitalisation |  | Allowable Capitalisation | Probable Disallowance
FY 2022-23
a) DPR Schemes
(i) Submitted to MERC
2 | Various schemes of Hydro Power Stations at HPC Pune & HPC Nasik | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 1.5512 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Replacement of existing AVR by SEE DVR system for Varasgaon Hydro Power Station. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.52 | 0.30933 | 0.30933 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Construction of Resthouse at Dimbhe HPS | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.7 | 0.73791 | 0.73791 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.3312 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Various Civil schemes for Modernisations of colonies at Various Locations under Pune HPC | MERC/CAPEX/20162017/01745 | 2017-03-31 | 12.813 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Refurbishing of Residential complex | MERC/CAPEX/20162017/01745 | 2017-03-31 | 2.415 | 1.2675 | 1.2675 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Internal Roads | MERC/CAPEX/20162017/01745 | 2017-03-31 | 2.29 | 1.6182 | 1.6182 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Water supply, filteration & Sanitary works | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1.427 | 0.57282 | 0.57282 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Compound walls | MERC/CAPEX/20162017/01745 | 2017-03-31 | 6.681 | 4.8004 | 4.8004 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1.908 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | Schme-A: Retrofitting of 12 KV Breakers at Ujjani Hydro Power Station | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.395 | 0 | 0 | 0 | 0.26762 | 0.26762 |  |  | 0.26762 | 0 | 0.26762 | 0
14.3 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.102 | 0.096156 | 0 | 0.096156 | 0 | 0.079692 |  |  | 0.079692 | 0.016464 | 0.079692 | 0
14.4 | Schme-D: Providing Oil Filtration Machines for all Divisions of REC, Pune | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.561 | 0.27239 | 0.27239 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Various 6 Nos. Schemes for Hydro Power Stations under Renewable Energy Circle, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 10.861 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Replacement of existing Air Compressors at Bhira, Tilari, Pawana and Ujjani Hydro Power Stations under REC, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.951 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.2 | Replacement of existing Air conditioners of Plant Control Rooms at Ujjani, Warna, Kanher, Dhom, Dimbhe & Dudhganga HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.292 | 0.25256 | 0.25256 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.4 | Replacement of 220 V, 400/300 AH Battery set with Tubular type Battery Banks at Bhira, Tilari, Kanher, Dimbhe and Ujani Hydro Power Stations. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.5 | Supply, installation and commissioning of Kaplan Turbine Runner Blades from BHEL (OEM) for Dudhganga U#1. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 4.657 | 3.0186 | 0 | 3.0186 | 1.4337 | 4.4592 |  |  | 4.4592 | -0.0069088 | 4.4592 | 0
16.6 | Replacement of existing Protection Systems with Numerical Protection system at Bhira, Panshet, Varasgaon, Dimbhe & Manikdoh HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 3.622 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.439 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Fortification near Panshet hydro power station for arresting rock falling on HPS Building at panshet . | Not approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Fortification near Panshet hydro power station for arresting rock falling on HPS Building at panshet . | Not approved | - | 0 | 0 | 0 | 0 | 12.06 | 0 |  |  | 0 | 12.06 | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR-5 | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Supply, erection & commissioning of Digital Governor and DAVR for Panshet HPS under REC, Pune | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Supply, erection & commissioning of Digital Governor, Excitation system (DAVR) at Warana & Dudhganga HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.3 | Supply,erection & commissioningof Governor, Excitation System (DAVR) and Autosequencer for Manikdoh, Kanher & Dimbhe HPS. | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.4 | Supply, erection & commissioning of Digital Governor Pawana & Varasgaon HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.5 | Upgradation of Protection system for Generator and Generator transformer at bhatghar,Dudhganga,Ujani,Warana,Kanher & Dhom | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR-6 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Synchronising & Line Breakers at HPS under REC, Pune | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Digital Governor, Excitation (DAVR) with Auto sequencer at Ujjani HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of station battery sets at Panshet, Varasgaon, Pawana, Dhom, Terwanmedhe | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Digital Governor, Excitation (DAVR) with Auto sequencer at Dhom HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | R & M of Bhatghar HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.7 | DPR-8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Gen. transformers for Dudhganga, Warana, Ujjani, Panshet, Varasgaon & Pawana HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Replacement of 220V/300 AH Tubular type Battery Set at Manikdoh HPS | N.A. | - | 0 | 0 | 0 | 0 | 0.1138 | 0.1138 |  |  | 0.1138 | 0
2 | Replacement of existing AVR by DAVR for Static Excitation System at Pawana HPS. | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Retrofitting of 415 V LT Breakers at Kanher & Dhom HPS. | N.A. | - | 0 | 0 | 0 | 0 | 0.098744 | 0.098744 |  |  | 0.098744 | 0
4 | Furniture & Fixture General Asset | N.A. | - | 0 | 1.0285 | 1.0285 | 0 | 0 | 0 |  |  | 0 | 0
5 | Electrical General Asset | N.A. | - | 0 | 0.12713 | 0.12713 | 0 | 0.0036 | 0.0036 |  |  | 0.0036 | 0
6 | Electronics General Asset | N.A. | - | 0 | 0.23846 | 0.23846 | 0 | 0.001344 | 0.001344 |  |  | 0.001344 | 0
7 | Vehicle General Asset | N.A. | - | 0 | 0.17289 | 0.17289 | 0 | 0 | 0 |  |  | 0 | 0
8 | Numerical protection system at Pawana Hydro Power Station | N.A. | - | 0 | 0.33024 | 0.33024 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 14.8431 | 11.7284 | 3.1147 | 13.9788 | 5.024 | 0 | 0 | 5.024 | 12.0696
FY 2023-24
a) DPR Schemes
(i) Submitted to MERC
2 | Various schemes of Hydro Power Stations at HPC Pune & HPC Nasik | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 1.5512 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Replacement of existing AVR by SEE DVR system for Varasgaon Hydro Power Station. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.52 | 0.30933 | 0.30933 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Construction of Resthouse at Dimbhe HPS | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.7 | 0.73791 | 0.73791 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.3312 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Various Civil schemes for Modernisations of colonies at Various Locations under Pune HPC | MERC/CAPEX/20162017/01745 | 2017-03-31 | 12.813 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Refurbishing of Residential complex | MERC/CAPEX/20162017/01745 | 2017-03-31 | 2.415 | 1.2675 | 1.2675 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Internal Roads | MERC/CAPEX/20162017/01745 | 2017-03-31 | 2.29 | 1.6182 | 1.6182 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Water supply, filteration & Sanitary works | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1.427 | 0.57282 | 0.57282 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Compound walls | MERC/CAPEX/20162017/01745 | 2017-03-31 | 6.681 | 4.8004 | 4.8004 | 0 | 2.7557 | 2.7557 |  |  | 2.7557 | 0 | 1.8806 | 0.87508 | -0.023409
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1.908 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | Schme-A: Retrofitting of 12 KV Breakers at Ujjani Hydro Power Station | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.395 | 0.26762 | 0.26762 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.102 | 0.096156 | 0.079692 | 0.016464 | 0 | 0 |  |  | 0 | 0.016464 | 0 | 0
14.4 | Schme-D: Providing Oil Filtration Machines for all Divisions of REC, Pune | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.561 | 0.27239 | 0.27239 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Various 6 Nos. Schemes for Hydro Power Stations under Renewable Energy Circle, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 10.861 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Replacement of existing Air Compressors at Bhira, Tilari, Pawana and Ujjani Hydro Power Stations under REC, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.951 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.2 | Replacement of existing Air conditioners of Plant Control Rooms at Ujjani, Warna, Kanher, Dhom, Dimbhe & Dudhganga HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.292 | 0.25256 | 0.25256 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.4 | Replacement of 220 V, 400/300 AH Battery set with Tubular type Battery Banks at Bhira, Tilari, Kanher, Dimbhe and Ujani Hydro Power Stations. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.9 | 0 | 0 | 0 | 0.35828 | 0.35828 |  |  | 0.35828 | 0 | 0.35828 | 0
16.5 | Supply, installation and commissioning of Kaplan Turbine Runner Blades from BHEL (OEM) for Dudhganga U#1. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 4.657 | 4.4523 | 4.4592 | -0.0069088 | 0.12074 | 0.12074 |  |  | 0.12074 | -0.0069088 | 0.12074 | 0
16.6 | Replacement of existing Protection Systems with Numerical Protection system at Bhira, Panshet, Varasgaon, Dimbhe & Manikdoh HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 3.622 | 0 | 0 | 0 | 0.53395 | 0.53395 |  |  | 0.53395 | 0 | 0.53395 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.439 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Fortification near Panshet hydro power station for arresting rock falling on HPS Building at panshet . | Not approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Fortification near Panshet hydro power station for arresting rock falling on HPS Building at panshet . | Not approved | - | 0 | 12.06 | 0 | 12.06 | 0 | 0 |  |  | 0 | 12.06 | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR-5 | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Supply, erection & commissioning of Digital Governor and DAVR for Panshet HPS under REC, Pune | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Supply, erection & commissioning of Digital Governor, Excitation system (DAVR) at Warana & Dudhganga HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.3 | Supply,erection & commissioningof Governor, Excitation System (DAVR) and Autosequencer for Manikdoh, Kanher & Dimbhe HPS. | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.4 | Supply, erection & commissioning of Digital Governor Pawana & Varasgaon HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.5 | Upgradation of Protection system for Generator and Generator transformer at bhatghar,Dudhganga,Ujani,Warana,Kanher & Dhom | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR-6 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Synchronising & Line Breakers at HPS under REC, Pune | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Digital Governor, Excitation (DAVR) with Auto sequencer at Ujjani HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of station battery sets at Panshet, Varasgaon, Pawana, Dhom, Terwanmedhe | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Digital Governor, Excitation (DAVR) with Auto sequencer at Dhom HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | R & M of Bhatghar HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.7 | DPR-8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Gen. transformers for Dudhganga, Warana, Ujjani, Panshet, Varasgaon & Pawana HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Replacement of 220V/300 AH Tubular type Battery Set at Manikdoh HPS | N.A. | - | 0 | 0.1138 | 0.1138 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement of existing AVR by DAVR for Static Excitation System at Pawana HPS. | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Retrofitting of 415 V LT Breakers at Kanher & Dhom HPS. | N.A. | - | 0 | 0.098744 | 0.098744 | 0 | 0 | 0 |  |  | 0 | 0
4 | Furniture & Fixture General Asset | N.A. | - | 0 | 1.0285 | 1.0285 | 0 | 0.029146 | 0.029146 |  |  | 0.029146 | 0
5 | Electrical General Asset | N.A. | - | 0 | 0.13073 | 0.13073 | 0 | 0.063954 | 0.063954 |  |  | 0.063954 | 0
6 | Electronics General Asset | N.A. | - | 0 | 0.2398 | 0.2398 | 0 | 0.016809 | 0.016809 |  |  | 0.016809 | 0
7 | Vehicle General Asset | N.A. | - | 0 | 0.17289 | 0.17289 | 0 | 0 | 0 |  |  | 0 | 0
8 | Numerical protection system at Pawana Hydro Power Station | N.A. | - | 0 | 0.33024 | 0.33024 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 28.8219 | 16.7524 | 12.0696 | 3.8786 | 3.8786 | 0 | 0 | 3.8786 | 12.0696
FY 2024-25
a) DPR Schemes
(i) Submitted to MERC
2 | Various schemes of Hydro Power Stations at HPC Pune & HPC Nasik | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 1.5512 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Replacement of existing AVR by SEE DVR system for Varasgaon Hydro Power Station. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.52 | 0.30933 | 0.30933 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Construction of Resthouse at Dimbhe HPS | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.7 | 0.73791 | 0.73791 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.3312 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Various Civil schemes for Modernisations of colonies at Various Locations under Pune HPC | MERC/CAPEX/20162017/01745 | 2017-03-31 | 12.813 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Refurbishing of Residential complex | MERC/CAPEX/20162017/01745 | 2017-03-31 | 2.415 | 1.2675 | 1.2675 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Internal Roads | MERC/CAPEX/20162017/01745 | 2017-03-31 | 2.29 | 1.6182 | 1.6182 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Water supply, filteration & Sanitary works | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1.427 | 0.57282 | 0.57282 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Compound walls | MERC/CAPEX/20162017/01745 | 2017-03-31 | 6.681 | 7.5561 | 7.5561 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | -0.023409
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1.908 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | Schme-A: Retrofitting of 12 KV Breakers at Ujjani Hydro Power Station | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.395 | 0.26762 | 0.26762 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.102 | 0.096156 | 0.079692 | 0.016464 | 0 | 0 |  |  | 0 | 0.016464 | 0 | 0
14.4 | Schme-D: Providing Oil Filtration Machines for all Divisions of REC, Pune | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.561 | 0.27239 | 0.27239 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Various 6 Nos. Schemes for Hydro Power Stations under Renewable Energy Circle, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 10.861 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Replacement of existing Air Compressors at Bhira, Tilari, Pawana and Ujjani Hydro Power Stations under REC, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.951 | 0 | 0 | 0 | 0.13 | 0.13 |  |  | 0.13 | 0 | 0.13 | 0
16.2 | Replacement of existing Air conditioners of Plant Control Rooms at Ujjani, Warna, Kanher, Dhom, Dimbhe & Dudhganga HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.292 | 0.25256 | 0.25256 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.4 | Replacement of 220 V, 400/300 AH Battery set with Tubular type Battery Banks at Bhira, Tilari, Kanher, Dimbhe and Ujani Hydro Power Stations. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.9 | 0.35828 | 0.35828 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.5 | Supply, installation and commissioning of Kaplan Turbine Runner Blades from BHEL (OEM) for Dudhganga U#1. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 4.657 | 4.573 | 4.5799 | -0.0069088 | 0 | 0 |  |  | 0 | -0.0069088 | 0 | 0
16.6 | Replacement of existing Protection Systems with Numerical Protection system at Bhira, Panshet, Varasgaon, Dimbhe & Manikdoh HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 3.622 | 0.53395 | 0.53395 | 0 | 1.6 | 1.6 |  |  | 1.6 | 0 | 1.6 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.439 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Fortification near Panshet hydro power station for arresting rock falling on HPS Building at panshet . | Not approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Fortification near Panshet hydro power station for arresting rock falling on HPS Building at panshet . | Not approved | - | 0 | 12.06 | 0 | 12.06 | 0 | 0 |  |  | 0 | 12.06 | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR-5 | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Supply, erection & commissioning of Digital Governor and DAVR for Panshet HPS under REC, Pune | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Supply, erection & commissioning of Digital Governor, Excitation system (DAVR) at Warana & Dudhganga HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.3 | Supply,erection & commissioningof Governor, Excitation System (DAVR) and Autosequencer for Manikdoh, Kanher & Dimbhe HPS. | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.4 | Supply, erection & commissioning of Digital Governor Pawana & Varasgaon HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.5 | Upgradation of Protection system for Generator and Generator transformer at bhatghar,Dudhganga,Ujani,Warana,Kanher & Dhom | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR-6 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Synchronising & Line Breakers at HPS under REC, Pune | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Digital Governor, Excitation (DAVR) with Auto sequencer at Ujjani HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of station battery sets at Panshet, Varasgaon, Pawana, Dhom, Terwanmedhe | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Digital Governor, Excitation (DAVR) with Auto sequencer at Dhom HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | R & M of Bhatghar HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.7 | DPR-8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Gen. transformers for Dudhganga, Warana, Ujjani, Panshet, Varasgaon & Pawana HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Replacement of 220V/300 AH Tubular type Battery Set at Manikdoh HPS | N.A. | - | 0 | 0.1138 | 0.1138 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement of existing AVR by DAVR for Static Excitation System at Pawana HPS. | N.A. | - | 0 | 0 | 0 | 0 | 1.01 | 1.01 |  |  | 1.01 | 0
3 | Retrofitting of 415 V LT Breakers at Kanher & Dhom HPS. | N.A. | - | 0 | 0.098744 | 0.098744 | 0 | 0 | 0 |  |  | 0 | 0
4 | Furniture & Fixture General Asset | N.A. | - | 0 | 1.0577 | 1.0577 | 0 | 0.01 | 0.01 |  |  | 0.01 | 0
5 | Electrical General Asset | N.A. | - | 0 | 0.19468 | 0.19468 | 0 | 0 | 0 |  |  | 0 | 0
6 | Electronics General Asset | N.A. | - | 0 | 0.25661 | 0.25661 | 0 | 0.02 | 0.02 |  |  | 0.02 | 0
7 | Vehicle General Asset | N.A. | - | 0 | 0.17289 | 0.17289 | 0 | 0 | 0 |  |  | 0 | 0
8 | Numerical protection system at Pawana Hydro Power Station | N.A. | - | 0 | 0.33024 | 0.33024 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 32.7005 | 20.631 | 12.0696 | 2.77 | 2.77 | 0 | 0 | 2.77 | 12.0696
FY 2025-26
a) DPR Schemes
(i) Submitted to MERC
2 | Various schemes of Hydro Power Stations at HPC Pune & HPC Nasik | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 1.5512 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Replacement of existing AVR by SEE DVR system for Varasgaon Hydro Power Station. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.52 | 0.30933 | 0.30933 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Construction of Resthouse at Dimbhe HPS | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.7 | 0.73791 | 0.73791 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.3312 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Various Civil schemes for Modernisations of colonies at Various Locations under Pune HPC | MERC/CAPEX/20162017/01745 | 2017-03-31 | 12.813 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Refurbishing of Residential complex | MERC/CAPEX/20162017/01745 | 2017-03-31 | 2.415 | 1.2675 | 1.2675 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Internal Roads | MERC/CAPEX/20162017/01745 | 2017-03-31 | 2.29 | 1.6182 | 1.6182 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Water supply, filteration & Sanitary works | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1.427 | 0.57282 | 0.57282 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Compound walls | MERC/CAPEX/20162017/01745 | 2017-03-31 | 6.681 | 7.5561 | 7.5561 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | -0.023409
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1.908 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | Schme-A: Retrofitting of 12 KV Breakers at Ujjani Hydro Power Station | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.395 | 0.26762 | 0.26762 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.102 | 0.096156 | 0.079692 | 0.016464 | 0 | 0 |  |  | 0 | 0.016464 | 0 | 0
14.4 | Schme-D: Providing Oil Filtration Machines for all Divisions of REC, Pune | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.561 | 0.27239 | 0.27239 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Various 6 Nos. Schemes for Hydro Power Stations under Renewable Energy Circle, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 10.861 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Replacement of existing Air Compressors at Bhira, Tilari, Pawana and Ujjani Hydro Power Stations under REC, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.951 | 0.13 | 0.13 | 0 | 0.48 | 0.48 |  |  | 0.48 | 0 | 0.48 | 0
16.2 | Replacement of existing Air conditioners of Plant Control Rooms at Ujjani, Warna, Kanher, Dhom, Dimbhe & Dudhganga HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.292 | 0.25256 | 0.25256 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.4 | Replacement of 220 V, 400/300 AH Battery set with Tubular type Battery Banks at Bhira, Tilari, Kanher, Dimbhe and Ujani Hydro Power Stations. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.9 | 0.35828 | 0.35828 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.5 | Supply, installation and commissioning of Kaplan Turbine Runner Blades from BHEL (OEM) for Dudhganga U#1. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 4.657 | 4.573 | 4.5799 | -0.0069088 | 0 | 0 |  |  | 0 | -0.0069088 | 0 | 0
16.6 | Replacement of existing Protection Systems with Numerical Protection system at Bhira, Panshet, Varasgaon, Dimbhe & Manikdoh HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 3.622 | 2.134 | 2.134 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.439 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Fortification near Panshet hydro power station for arresting rock falling on HPS Building at panshet . | Not approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Fortification near Panshet hydro power station for arresting rock falling on HPS Building at panshet . | Not approved | - | 0 | 12.06 | 0 | 12.06 | 0 | 0 |  |  | 0 | 12.06 | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR-5 | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Supply, erection & commissioning of Digital Governor and DAVR for Panshet HPS under REC, Pune | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 4.5 | 4.5 |  |  | 4.5 | 0
1.2 | Supply, erection & commissioning of Digital Governor, Excitation system (DAVR) at Warana & Dudhganga HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.3 | Supply,erection & commissioningof Governor, Excitation System (DAVR) and Autosequencer for Manikdoh, Kanher & Dimbhe HPS. | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.4 | Supply, erection & commissioning of Digital Governor Pawana & Varasgaon HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 6.74 | 6.74 |  |  | 6.74 | 0
1.5 | Upgradation of Protection system for Generator and Generator transformer at bhatghar,Dudhganga,Ujani,Warana,Kanher & Dhom | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 7.22 | 7.22 |  |  | 7.22 | 0
0 | DPR-6 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Synchronising & Line Breakers at HPS under REC, Pune | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Digital Governor, Excitation (DAVR) with Auto sequencer at Ujjani HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of station battery sets at Panshet, Varasgaon, Pawana, Dhom, Terwanmedhe | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Digital Governor, Excitation (DAVR) with Auto sequencer at Dhom HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | R & M of Bhatghar HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.7 | DPR-8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Gen. transformers for Dudhganga, Warana, Ujjani, Panshet, Varasgaon & Pawana HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Replacement of 220V/300 AH Tubular type Battery Set at Manikdoh HPS | N.A. | - | 0 | 0.1138 | 0.1138 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement of existing AVR by DAVR for Static Excitation System at Pawana HPS. | N.A. | - | 0 | 1.01 | 1.01 | 0 | 0 | 0 |  |  | 0 | 0
3 | Retrofitting of 415 V LT Breakers at Kanher & Dhom HPS. | N.A. | - | 0 | 0.098744 | 0.098744 | 0 | 0 | 0 |  |  | 0 | 0
4 | Furniture & Fixture General Asset | N.A. | - | 0 | 1.0677 | 1.0677 | 0 | 0 | 0 |  |  | 0 | 0
5 | Electrical General Asset | N.A. | - | 0 | 0.19468 | 0.19468 | 0 | 0 | 0 |  |  | 0 | 0
6 | Electronics General Asset | N.A. | - | 0 | 0.27661 | 0.27661 | 0 | 0 | 0 |  |  | 0 | 0
7 | Vehicle General Asset | N.A. | - | 0 | 0.17289 | 0.17289 | 0 | 0 | 0 |  |  | 0 | 0
8 | Numerical protection system at Pawana Hydro Power Station | N.A. | - | 0 | 0.33024 | 0.33024 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 35.4705 | 23.401 | 12.0696 | 18.94 | 18.94 | 0 | 0 | 18.94 | 12.0696
FY 2026-27
a) DPR Schemes
(i) Submitted to MERC
2 | Various schemes of Hydro Power Stations at HPC Pune & HPC Nasik | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 1.5512 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Replacement of existing AVR by SEE DVR system for Varasgaon Hydro Power Station. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.52 | 0.30933 | 0.30933 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Construction of Resthouse at Dimbhe HPS | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.7 | 0.73791 | 0.73791 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.3312 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Various Civil schemes for Modernisations of colonies at Various Locations under Pune HPC | MERC/CAPEX/20162017/01745 | 2017-03-31 | 12.813 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Refurbishing of Residential complex | MERC/CAPEX/20162017/01745 | 2017-03-31 | 2.415 | 1.2675 | 1.2675 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Internal Roads | MERC/CAPEX/20162017/01745 | 2017-03-31 | 2.29 | 1.6182 | 1.6182 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Water supply, filteration & Sanitary works | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1.427 | 0.57282 | 0.57282 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Compound walls | MERC/CAPEX/20162017/01745 | 2017-03-31 | 6.681 | 7.5561 | 7.5561 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | -0.023409
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1.908 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | Schme-A: Retrofitting of 12 KV Breakers at Ujjani Hydro Power Station | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.395 | 0.26762 | 0.26762 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.102 | 0.096156 | 0.079692 | 0.016464 | 0 | 0 |  |  | 0 | 0.016464 | 0 | 0
14.4 | Schme-D: Providing Oil Filtration Machines for all Divisions of REC, Pune | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.561 | 0.27239 | 0.27239 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Various 6 Nos. Schemes for Hydro Power Stations under Renewable Energy Circle, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 10.861 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Replacement of existing Air Compressors at Bhira, Tilari, Pawana and Ujjani Hydro Power Stations under REC, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.951 | 0.61 | 0.61 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.2 | Replacement of existing Air conditioners of Plant Control Rooms at Ujjani, Warna, Kanher, Dhom, Dimbhe & Dudhganga HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.292 | 0.25256 | 0.25256 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.4 | Replacement of 220 V, 400/300 AH Battery set with Tubular type Battery Banks at Bhira, Tilari, Kanher, Dimbhe and Ujani Hydro Power Stations. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.9 | 0.35828 | 0.35828 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.5 | Supply, installation and commissioning of Kaplan Turbine Runner Blades from BHEL (OEM) for Dudhganga U#1. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 4.657 | 4.573 | 4.5799 | -0.0069088 | 0 | 0 |  |  | 0 | -0.0069088 | 0 | 0
16.6 | Replacement of existing Protection Systems with Numerical Protection system at Bhira, Panshet, Varasgaon, Dimbhe & Manikdoh HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 3.622 | 2.134 | 2.134 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.439 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Fortification near Panshet hydro power station for arresting rock falling on HPS Building at panshet . | Not approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Fortification near Panshet hydro power station for arresting rock falling on HPS Building at panshet . | Not approved | - | 0 | 12.06 | 0 | 12.06 | 0 | 0 |  |  | 0 | 12.06 | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR-5 | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Supply, erection & commissioning of Digital Governor and DAVR for Panshet HPS under REC, Pune | (ii) Yet to be submitted to MERC | - | 0 | 4.5 | 4.5 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Supply, erection & commissioning of Digital Governor, Excitation system (DAVR) at Warana & Dudhganga HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 18.79 | 18.79 |  |  | 18.79 | 0
1.3 | Supply,erection & commissioningof Governor, Excitation System (DAVR) and Autosequencer for Manikdoh, Kanher & Dimbhe HPS. | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 14.35 | 14.35 |  |  | 14.35 | 0
1.4 | Supply, erection & commissioning of Digital Governor Pawana & Varasgaon HPS | (ii) Yet to be submitted to MERC | - | 0 | 6.74 | 6.74 | 0 | 0 | 0 |  |  | 0 | 0
1.5 | Upgradation of Protection system for Generator and Generator transformer at bhatghar,Dudhganga,Ujani,Warana,Kanher & Dhom | (ii) Yet to be submitted to MERC | - | 0 | 7.22 | 7.22 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR-6 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Synchronising & Line Breakers at HPS under REC, Pune | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Digital Governor, Excitation (DAVR) with Auto sequencer at Ujjani HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of station battery sets at Panshet, Varasgaon, Pawana, Dhom, Terwanmedhe | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Digital Governor, Excitation (DAVR) with Auto sequencer at Dhom HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | R & M of Bhatghar HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.7 | DPR-8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Gen. transformers for Dudhganga, Warana, Ujjani, Panshet, Varasgaon & Pawana HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Replacement of 220V/300 AH Tubular type Battery Set at Manikdoh HPS | N.A. | - | 0 | 0.1138 | 0.1138 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement of existing AVR by DAVR for Static Excitation System at Pawana HPS. | N.A. | - | 0 | 1.01 | 1.01 | 0 | 0 | 0 |  |  | 0 | 0
3 | Retrofitting of 415 V LT Breakers at Kanher & Dhom HPS. | N.A. | - | 0 | 0.098744 | 0.098744 | 0 | 0 | 0 |  |  | 0 | 0
4 | Furniture & Fixture General Asset | N.A. | - | 0 | 1.0677 | 1.0677 | 0 | 0 | 0 |  |  | 0 | 0
5 | Electrical General Asset | N.A. | - | 0 | 0.19468 | 0.19468 | 0 | 0 | 0 |  |  | 0 | 0
6 | Electronics General Asset | N.A. | - | 0 | 0.27661 | 0.27661 | 0 | 0 | 0 |  |  | 0 | 0
7 | Vehicle General Asset | N.A. | - | 0 | 0.17289 | 0.17289 | 0 | 0 | 0 |  |  | 0 | 0
8 | Numerical protection system at Pawana Hydro Power Station | N.A. | - | 0 | 0.33024 | 0.33024 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 54.4105 | 42.341 | 12.0696 | 33.14 | 33.14 | 0 | 0 | 33.14 | 12.0696
FY 2027-28
a) DPR Schemes
(i) Submitted to MERC
2 | Various schemes of Hydro Power Stations at HPC Pune & HPC Nasik | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 1.5512 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Replacement of existing AVR by SEE DVR system for Varasgaon Hydro Power Station. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.52 | 0.30933 | 0.30933 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Construction of Resthouse at Dimbhe HPS | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.7 | 0.73791 | 0.73791 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.3312 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Various Civil schemes for Modernisations of colonies at Various Locations under Pune HPC | MERC/CAPEX/20162017/01745 | 2017-03-31 | 12.813 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Refurbishing of Residential complex | MERC/CAPEX/20162017/01745 | 2017-03-31 | 2.415 | 1.2675 | 1.2675 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Internal Roads | MERC/CAPEX/20162017/01745 | 2017-03-31 | 2.29 | 1.6182 | 1.6182 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Water supply, filteration & Sanitary works | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1.427 | 0.57282 | 0.57282 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Compound walls | MERC/CAPEX/20162017/01745 | 2017-03-31 | 6.681 | 7.5561 | 7.5561 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | -0.023409
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1.908 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | Schme-A: Retrofitting of 12 KV Breakers at Ujjani Hydro Power Station | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.395 | 0.26762 | 0.26762 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.102 | 0.096156 | 0.079692 | 0.016464 | 0 | 0 |  |  | 0 | 0.016464 | 0 | 0
14.4 | Schme-D: Providing Oil Filtration Machines for all Divisions of REC, Pune | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.561 | 0.27239 | 0.27239 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Various 6 Nos. Schemes for Hydro Power Stations under Renewable Energy Circle, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 10.861 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Replacement of existing Air Compressors at Bhira, Tilari, Pawana and Ujjani Hydro Power Stations under REC, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.951 | 0.61 | 0.61 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.2 | Replacement of existing Air conditioners of Plant Control Rooms at Ujjani, Warna, Kanher, Dhom, Dimbhe & Dudhganga HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.292 | 0.25256 | 0.25256 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.4 | Replacement of 220 V, 400/300 AH Battery set with Tubular type Battery Banks at Bhira, Tilari, Kanher, Dimbhe and Ujani Hydro Power Stations. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.9 | 0.35828 | 0.35828 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.5 | Supply, installation and commissioning of Kaplan Turbine Runner Blades from BHEL (OEM) for Dudhganga U#1. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 4.657 | 4.573 | 4.5799 | -0.0069088 | 0 | 0 |  |  | 0 | -0.0069088 | 0 | 0
16.6 | Replacement of existing Protection Systems with Numerical Protection system at Bhira, Panshet, Varasgaon, Dimbhe & Manikdoh HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 3.622 | 2.134 | 2.134 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.439 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Fortification near Panshet hydro power station for arresting rock falling on HPS Building at panshet . | Not approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Fortification near Panshet hydro power station for arresting rock falling on HPS Building at panshet . | Not approved | - | 0 | 12.06 | 0 | 12.06 | 0 | 0 |  |  | 0 | 12.06 | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR-5 | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Supply, erection & commissioning of Digital Governor and DAVR for Panshet HPS under REC, Pune | (ii) Yet to be submitted to MERC | - | 0 | 4.5 | 4.5 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Supply, erection & commissioning of Digital Governor, Excitation system (DAVR) at Warana & Dudhganga HPS | (ii) Yet to be submitted to MERC | - | 0 | 18.79 | 18.79 | 0 | 0 | 0 |  |  | 0 | 0
1.3 | Supply,erection & commissioningof Governor, Excitation System (DAVR) and Autosequencer for Manikdoh, Kanher & Dimbhe HPS. | (ii) Yet to be submitted to MERC | - | 0 | 14.35 | 14.35 | 0 | 0 | 0 |  |  | 0 | 0
1.4 | Supply, erection & commissioning of Digital Governor Pawana & Varasgaon HPS | (ii) Yet to be submitted to MERC | - | 0 | 6.74 | 6.74 | 0 | 0 | 0 |  |  | 0 | 0
1.5 | Upgradation of Protection system for Generator and Generator transformer at bhatghar,Dudhganga,Ujani,Warana,Kanher & Dhom | (ii) Yet to be submitted to MERC | - | 0 | 7.22 | 7.22 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR-6 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Synchronising & Line Breakers at HPS under REC, Pune | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 5.1 | 5.1 |  |  | 5.1 | 0
0 | Digital Governor, Excitation (DAVR) with Auto sequencer at Ujjani HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 3.12 | 3.12 |  |  | 3.12 | 0
0 | Supply of station battery sets at Panshet, Varasgaon, Pawana, Dhom, Terwanmedhe | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
0 | Digital Governor, Excitation (DAVR) with Auto sequencer at Dhom HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 6.22 | 6.22 |  |  | 6.22 | 0
0 | R & M of Bhatghar HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
1.7 | DPR-8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Gen. transformers for Dudhganga, Warana, Ujjani, Panshet, Varasgaon & Pawana HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Replacement of 220V/300 AH Tubular type Battery Set at Manikdoh HPS | N.A. | - | 0 | 0.1138 | 0.1138 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement of existing AVR by DAVR for Static Excitation System at Pawana HPS. | N.A. | - | 0 | 1.01 | 1.01 | 0 | 0 | 0 |  |  | 0 | 0
3 | Retrofitting of 415 V LT Breakers at Kanher & Dhom HPS. | N.A. | - | 0 | 0.098744 | 0.098744 | 0 | 0 | 0 |  |  | 0 | 0
4 | Furniture & Fixture General Asset | N.A. | - | 0 | 1.0677 | 1.0677 | 0 | 0 | 0 |  |  | 0 | 0
5 | Electrical General Asset | N.A. | - | 0 | 0.19468 | 0.19468 | 0 | 0 | 0 |  |  | 0 | 0
6 | Electronics General Asset | N.A. | - | 0 | 0.27661 | 0.27661 | 0 | 0 | 0 |  |  | 0 | 0
7 | Vehicle General Asset | N.A. | - | 0 | 0.17289 | 0.17289 | 0 | 0 | 0 |  |  | 0 | 0
8 | Numerical protection system at Pawana Hydro Power Station | N.A. | - | 0 | 0.33024 | 0.33024 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 87.5505 | 75.481 | 12.0696 | 25.44 | 25.44 | 0 | 0 | 25.44 | 12.0696
FY 2028-29
a) DPR Schemes
(i) Submitted to MERC
2 | Various schemes of Hydro Power Stations at HPC Pune & HPC Nasik | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 1.5512 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Replacement of existing AVR by SEE DVR system for Varasgaon Hydro Power Station. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.52 | 0.30933 | 0.30933 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Construction of Resthouse at Dimbhe HPS | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.7 | 0.73791 | 0.73791 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.3312 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Various Civil schemes for Modernisations of colonies at Various Locations under Pune HPC | MERC/CAPEX/20162017/01745 | 2017-03-31 | 12.813 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Refurbishing of Residential complex | MERC/CAPEX/20162017/01745 | 2017-03-31 | 2.415 | 1.2675 | 1.2675 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Internal Roads | MERC/CAPEX/20162017/01745 | 2017-03-31 | 2.29 | 1.6182 | 1.6182 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Water supply, filteration & Sanitary works | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1.427 | 0.57282 | 0.57282 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Compound walls | MERC/CAPEX/20162017/01745 | 2017-03-31 | 6.681 | 7.5561 | 7.5561 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | -0.023409
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1.908 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | Schme-A: Retrofitting of 12 KV Breakers at Ujjani Hydro Power Station | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.395 | 0.26762 | 0.26762 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.102 | 0.096156 | 0.079692 | 0.016464 | 0 | 0 |  |  | 0 | 0.016464 | 0 | 0
14.4 | Schme-D: Providing Oil Filtration Machines for all Divisions of REC, Pune | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.561 | 0.27239 | 0.27239 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Various 6 Nos. Schemes for Hydro Power Stations under Renewable Energy Circle, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 10.861 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Replacement of existing Air Compressors at Bhira, Tilari, Pawana and Ujjani Hydro Power Stations under REC, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.951 | 0.61 | 0.61 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.2 | Replacement of existing Air conditioners of Plant Control Rooms at Ujjani, Warna, Kanher, Dhom, Dimbhe & Dudhganga HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.292 | 0.25256 | 0.25256 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.4 | Replacement of 220 V, 400/300 AH Battery set with Tubular type Battery Banks at Bhira, Tilari, Kanher, Dimbhe and Ujani Hydro Power Stations. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.9 | 0.35828 | 0.35828 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.5 | Supply, installation and commissioning of Kaplan Turbine Runner Blades from BHEL (OEM) for Dudhganga U#1. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 4.657 | 4.573 | 4.5799 | -0.0069088 | 0 | 0 |  |  | 0 | -0.0069088 | 0 | 0
16.6 | Replacement of existing Protection Systems with Numerical Protection system at Bhira, Panshet, Varasgaon, Dimbhe & Manikdoh HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 3.622 | 2.134 | 2.134 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.439 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Fortification near Panshet hydro power station for arresting rock falling on HPS Building at panshet . | Not approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Fortification near Panshet hydro power station for arresting rock falling on HPS Building at panshet . | Not approved | - | 0 | 12.06 | 0 | 12.06 | 0 | 0 |  |  | 0 | 12.06 | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR-5 | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Supply, erection & commissioning of Digital Governor and DAVR for Panshet HPS under REC, Pune | (ii) Yet to be submitted to MERC | - | 0 | 4.5 | 4.5 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Supply, erection & commissioning of Digital Governor, Excitation system (DAVR) at Warana & Dudhganga HPS | (ii) Yet to be submitted to MERC | - | 0 | 18.79 | 18.79 | 0 | 0 | 0 |  |  | 0 | 0
1.3 | Supply,erection & commissioningof Governor, Excitation System (DAVR) and Autosequencer for Manikdoh, Kanher & Dimbhe HPS. | (ii) Yet to be submitted to MERC | - | 0 | 14.35 | 14.35 | 0 | 0 | 0 |  |  | 0 | 0
1.4 | Supply, erection & commissioning of Digital Governor Pawana & Varasgaon HPS | (ii) Yet to be submitted to MERC | - | 0 | 6.74 | 6.74 | 0 | 0 | 0 |  |  | 0 | 0
1.5 | Upgradation of Protection system for Generator and Generator transformer at bhatghar,Dudhganga,Ujani,Warana,Kanher & Dhom | (ii) Yet to be submitted to MERC | - | 0 | 7.22 | 7.22 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR-6 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Synchronising & Line Breakers at HPS under REC, Pune | (ii) Yet to be submitted to MERC | - | 0 | 5.1 | 5.1 | 0 | 0 | 0 |  |  | 0 | 0
0 | Digital Governor, Excitation (DAVR) with Auto sequencer at Ujjani HPS | (ii) Yet to be submitted to MERC | - | 0 | 3.12 | 3.12 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of station battery sets at Panshet, Varasgaon, Pawana, Dhom, Terwanmedhe | (ii) Yet to be submitted to MERC | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
0 | Digital Governor, Excitation (DAVR) with Auto sequencer at Dhom HPS | (ii) Yet to be submitted to MERC | - | 0 | 6.22 | 6.22 | 0 | 0 | 0 |  |  | 0 | 0
0 | R & M of Bhatghar HPS | (ii) Yet to be submitted to MERC | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
1.7 | DPR-8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Gen. transformers for Dudhganga, Warana, Ujjani, Panshet, Varasgaon & Pawana HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Replacement of 220V/300 AH Tubular type Battery Set at Manikdoh HPS | N.A. | - | 0 | 0.1138 | 0.1138 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement of existing AVR by DAVR for Static Excitation System at Pawana HPS. | N.A. | - | 0 | 1.01 | 1.01 | 0 | 0 | 0 |  |  | 0 | 0
3 | Retrofitting of 415 V LT Breakers at Kanher & Dhom HPS. | N.A. | - | 0 | 0.098744 | 0.098744 | 0 | 0 | 0 |  |  | 0 | 0
4 | Furniture & Fixture General Asset | N.A. | - | 0 | 1.0677 | 1.0677 | 0 | 0 | 0 |  |  | 0 | 0
5 | Electrical General Asset | N.A. | - | 0 | 0.19468 | 0.19468 | 0 | 0 | 0 |  |  | 0 | 0
6 | Electronics General Asset | N.A. | - | 0 | 0.27661 | 0.27661 | 0 | 0 | 0 |  |  | 0 | 0
7 | Vehicle General Asset | N.A. | - | 0 | 0.17289 | 0.17289 | 0 | 0 | 0 |  |  | 0 | 0
8 | Numerical protection system at Pawana Hydro Power Station | N.A. | - | 0 | 0.33024 | 0.33024 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 112.9905 | 100.921 | 12.0696 | 0 | 0 | 0 | 0 | 0 | 12.0696
FY 2029-30
a) DPR Schemes
(i) Submitted to MERC
2 | Various schemes of Hydro Power Stations at HPC Pune & HPC Nasik | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 1.5512 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Replacement of existing AVR by SEE DVR system for Varasgaon Hydro Power Station. | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.52 | 0.30933 | 0.30933 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Construction of Resthouse at Dimbhe HPS | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.7 | 0.73791 | 0.73791 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.3312 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Various Civil schemes for Modernisations of colonies at Various Locations under Pune HPC | MERC/CAPEX/20162017/01745 | 2017-03-31 | 12.813 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Refurbishing of Residential complex | MERC/CAPEX/20162017/01745 | 2017-03-31 | 2.415 | 1.2675 | 1.2675 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Internal Roads | MERC/CAPEX/20162017/01745 | 2017-03-31 | 2.29 | 1.6182 | 1.6182 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Water supply, filteration & Sanitary works | MERC/CAPEX/20162017/01745 | 2017-03-31 | 1.427 | 0.57282 | 0.57282 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Compound walls | MERC/CAPEX/20162017/01745 | 2017-03-31 | 6.681 | 7.5561 | 7.5561 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | -0.023409
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1.908 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | Schme-A: Retrofitting of 12 KV Breakers at Ujjani Hydro Power Station | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.395 | 0.26762 | 0.26762 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.102 | 0.096156 | 0.079692 | 0.016464 | 0 | 0 |  |  | 0 | 0.016464 | 0 | 0
14.4 | Schme-D: Providing Oil Filtration Machines for all Divisions of REC, Pune | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.561 | 0.27239 | 0.27239 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Various 6 Nos. Schemes for Hydro Power Stations under Renewable Energy Circle, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 10.861 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Replacement of existing Air Compressors at Bhira, Tilari, Pawana and Ujjani Hydro Power Stations under REC, Pune | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.951 | 0.61 | 0.61 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.2 | Replacement of existing Air conditioners of Plant Control Rooms at Ujjani, Warna, Kanher, Dhom, Dimbhe & Dudhganga HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.292 | 0.25256 | 0.25256 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.4 | Replacement of 220 V, 400/300 AH Battery set with Tubular type Battery Banks at Bhira, Tilari, Kanher, Dimbhe and Ujani Hydro Power Stations. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.9 | 0.35828 | 0.35828 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.5 | Supply, installation and commissioning of Kaplan Turbine Runner Blades from BHEL (OEM) for Dudhganga U#1. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 4.657 | 4.573 | 4.5799 | -0.0069088 | 0 | 0 |  |  | 0 | -0.0069088 | 0 | 0
16.6 | Replacement of existing Protection Systems with Numerical Protection system at Bhira, Panshet, Varasgaon, Dimbhe & Manikdoh HPS. | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 3.622 | 2.134 | 2.134 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/ SBR/22 | 2020-07-25 | 0.439 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Fortification near Panshet hydro power station for arresting rock falling on HPS Building at panshet . | Not approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Fortification near Panshet hydro power station for arresting rock falling on HPS Building at panshet . | Not approved | - | 0 | 12.06 | 0 | 12.06 | 0 | 0 |  |  | 0 | 12.06 | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR-5 | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Supply, erection & commissioning of Digital Governor and DAVR for Panshet HPS under REC, Pune | (ii) Yet to be submitted to MERC | - | 0 | 4.5 | 4.5 | 0 | 0 | 0 |  |  | 0 | 0
1.2 | Supply, erection & commissioning of Digital Governor, Excitation system (DAVR) at Warana & Dudhganga HPS | (ii) Yet to be submitted to MERC | - | 0 | 18.79 | 18.79 | 0 | 0 | 0 |  |  | 0 | 0
1.3 | Supply,erection & commissioningof Governor, Excitation System (DAVR) and Autosequencer for Manikdoh, Kanher & Dimbhe HPS. | (ii) Yet to be submitted to MERC | - | 0 | 14.35 | 14.35 | 0 | 0 | 0 |  |  | 0 | 0
1.4 | Supply, erection & commissioning of Digital Governor Pawana & Varasgaon HPS | (ii) Yet to be submitted to MERC | - | 0 | 6.74 | 6.74 | 0 | 0 | 0 |  |  | 0 | 0
1.5 | Upgradation of Protection system for Generator and Generator transformer at bhatghar,Dudhganga,Ujani,Warana,Kanher & Dhom | (ii) Yet to be submitted to MERC | - | 0 | 7.22 | 7.22 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR-6 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Synchronising & Line Breakers at HPS under REC, Pune | (ii) Yet to be submitted to MERC | - | 0 | 5.1 | 5.1 | 0 | 0 | 0 |  |  | 0 | 0
0 | Digital Governor, Excitation (DAVR) with Auto sequencer at Ujjani HPS | (ii) Yet to be submitted to MERC | - | 0 | 3.12 | 3.12 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of station battery sets at Panshet, Varasgaon, Pawana, Dhom, Terwanmedhe | (ii) Yet to be submitted to MERC | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
0 | Digital Governor, Excitation (DAVR) with Auto sequencer at Dhom HPS | (ii) Yet to be submitted to MERC | - | 0 | 6.22 | 6.22 | 0 | 0 | 0 |  |  | 0 | 0
0 | R & M of Bhatghar HPS | (ii) Yet to be submitted to MERC | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
1.7 | DPR-8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Gen. transformers for Dudhganga, Warana, Ujjani, Panshet, Varasgaon & Pawana HPS | (ii) Yet to be submitted to MERC | - | 0 | 0 | 0 | 0 | 35 | 35 |  |  | 35 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Replacement of 220V/300 AH Tubular type Battery Set at Manikdoh HPS | N.A. | - | 0 | 0.1138 | 0.1138 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement of existing AVR by DAVR for Static Excitation System at Pawana HPS. | N.A. | - | 0 | 1.01 | 1.01 | 0 | 0 | 0 |  |  | 0 | 0
3 | Retrofitting of 415 V LT Breakers at Kanher & Dhom HPS. | N.A. | - | 0 | 0.098744 | 0.098744 | 0 | 0 | 0 |  |  | 0 | 0
4 | Furniture & Fixture General Asset | N.A. | - | 0 | 1.0677 | 1.0677 | 0 | 0 | 0 |  |  | 0 | 0
5 | Electrical General Asset | N.A. | - | 0 | 0.19468 | 0.19468 | 0 | 0 | 0 |  |  | 0 | 0
6 | Electronics General Asset | N.A. | - | 0 | 0.27661 | 0.27661 | 0 | 0 | 0 |  |  | 0 | 0
7 | Vehicle General Asset | N.A. | - | 0 | 0.17289 | 0.17289 | 0 | 0 | 0 |  |  | 0 | 0
8 | Numerical protection system at Pawana Hydro Power Station | N.A. | - | 0 | 0.33024 | 0.33024 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 112.9905 | 100.921 | 12.0696 | 35 | 35 | 0 | 0 | 35 | 12.0696

## F4.1 SHPC Nashik
MSPGCL: Nasik HPC
MTR Petition Formats - Generation
| Project Details |  | Form 4.1: Capital Expenditure Plan | [14 empty] | (Rs. Crore)
Sr. No. | Project Code | Project Title | MERC Approval No. | MERC Approval Date | Project Purpose | Project Start Date |  |  | Project Completion date (Scheduled) |  |  | Capital Cost
[6 empty] | Original | Revised | Actual | Original | Revised | Actual | Approved | Actual Capital Cost Incurred | Deviation = Approved - Actual on account of
[14 empty] | Change in Scope of Work (a) | Material Cost (b) | IDC (c) | Others (d) | Total Deviation (a+b+c+d)
A) DPR Schemes
(i) Submitted to MERC
2 | Various schemes of Hydro Power Stations at HPC Pune & HPC Nasik | DPR | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 |  | 2014-08-20 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
2.6 | Supply, testing, installation and commissioning of Exide make 300 AH 220 V Lead acid stationary Plante type station battery set for Vaitarna HPS | Scheme | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 |  | 2014-08-20 |  | - | - |  | - | 0.2 | 0.19886 |  |  |  |  | 0.0011385
2.7 | Supply, testing, installation and commissioning of Exide make 300 AH 220 V Lead acid stationary Plante type station battery set for Bhatsa HPS | Scheme | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 |  | 2014-08-20 |  | - | - |  | - | 0.2 | 0.19886 |  |  |  |  | 0.0011385
0 | IDC | IDC | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 |  | 2014-08-20 |  | - | - |  | - | 0.3312 | 0 |  |  |  |  | 0.3312
6 | Upgradation of Protection Systems at Ghatghar (2x125MW) and Bhatsa (1x15MW) HPS under HPC Nasik | DPR | MERC/CAPEX/20172018/04220 | 2017-09-19 |  | 2017-09-19 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
6.1 | Up gradation of Protection System &unitrol excitation system at Ghatghar Hydro Power Station. | Scheme | MERC/CAPEX/20172018/04220 | 2017-09-19 |  | 2017-09-19 |  | - | - |  | - | 9.678 | 0 |  |  |  |  | 9.678
0 | Part A : upgradation of unitrol excitation system for both units at GHPS | 0 | 0 | - |  | - |  | - | - |  | - | 5 | 0 |  |  |  |  | 5
0 | Part B : upgradation of Protection system for both units at GHPS | 0 | 0 | - |  | - |  | - | - |  | - | 4.68 | 0 |  |  |  |  | 4.68
6.2 | Up gradation of ABB Make Protection System & Automatic Voltage Regulator, Relay Based Unit & Auxiliary control for Bhatsa Hydro Power Station(1 X 15MW). | Scheme | MERC/CAPEX/20172018/04220 | 2017-09-19 |  | 2017-09-19 |  | - | - |  | - | 5.426 | 0 |  |  |  |  | 5.426
0 | Protection system Part A:- Restoration and up-gradation of electromechanical and static relays with numerical relays along with installation, testing, commissioning, and misc. allied works | 0 | 0 | - |  | - |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
0 | Protection system Part B:- Procure of redundant & spare Numerical relays for Generator and G T Protection system. | 0 | 0 | - |  | - |  | - | - |  | - | 0.65 | 0 |  |  |  |  | 0.65
0 | C- Supply erection, testing and Commissioning and supervision of dismantling and erection of static excitation system and control system along with field instrumentation at Bhatsa HPS | 0 | 0 | - |  | - |  | - | - |  | - | 3.8232 | 0 |  |  |  |  | 3.8232
9 | Various Civil schemes for Modernisations of colonies at Various Locations under Nasik HPC | DPR | MERC/CAPEX/20162017/04757 | 2017-11-22 |  | 2017-11-22 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
9.1 | Part A: Refurbishment of quarters in colony, administartive buidings club building, guest house at various HPS under Nashik HPS | Scheme | MERC/CAPEX/20162017/04757 | 2017-11-22 |  | 2017-11-22 |  | - | - |  | - | 3.7364 | 3.642 |  |  |  |  | 0.094366
9.2 | Part B: Providing and laying water supply lines within colony and power house area at various HPS under Nashik HPS | Scheme | MERC/CAPEX/20162017/04757 | 2017-11-22 |  | 2017-11-22 |  | - | - |  | - | 0.50088 | 0.11901 |  |  |  |  | 0.38187
9.3 | Part C: Construction of compund wall/chainlink fencing around colony and power house area at various HPS under Nashik HPS. | Scheme | MERC/CAPEX/20162017/04757 | 2017-11-22 |  | 2017-11-22 |  | - | - |  | - | 0.74833 | 0.17 |  |  |  |  | 0.57833
9.4 | Part D: Providing & relaying of existing internal roads within colony area and approach roads to power house & construction of storm water gutter along road at various HPS under HPC Nashik | Scheme | MERC/CAPEX/20162017/04757 | 2017-11-22 |  | 2017-11-22 |  | - | - |  | - | 9.5811 | 4.0537 |  |  |  |  | 5.5274
10 | Upgradation of existing PLC system to latest symphony plus SCADA & DCS system of Ghatghar HPS (2x125 MW) under HPS Nasik | DPR | MERC/CAPEX/20172018/0198 | 2018-02-06 |  | 2018-02-06 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
10.1 | Upgradation of existing PLC system to latest symphony plus SCADA & DCS system of Ghatghar HPS (2x125 MW) under HPS Nasik | Scheme | MERC/CAPEX/20172018/0198 | 2018-02-06 |  | 2018-02-06 |  | - | - |  | - | 13.345 | 0 |  |  |  |  | 13.345
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | DPR | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 |  | 2020-07-17 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
14.1 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 |  | 2020-07-17 |  | - | - |  | - | 0.102 | 0 |  |  |  |  | 0.102
14.2 | Schme-F: Replacement of 220V / 300AH Float cum boost charger with integrated DCDB for Bhatsa Hydro Power Stn. | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 |  | 2020-07-17 |  | - | - |  | - | 0.173 | 0.11446 |  |  |  |  | 0.05854
14.3 | Schme-G: Replacement of 220V / 300AH Float cum boost charger with integrated DCDB for Surya Hydro Power Stn. | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 |  | 2020-07-17 |  | - | - |  | - | 0.173 | 0.11446 |  |  |  |  | 0.05854
14.4 | Schme-H: Supply 24 point Chartless recorder for Bhatsa HPS. | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 |  | 2020-07-17 |  | - | - |  | - | 0.059 | 0.020245 |  |  |  |  | 0.038754
14.5 | Schme-I: Supply Erection, testing & commissioning of Digital governing system for 06MW Surya HPS. | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 |  | 2020-07-17 |  | - | - |  | - | 1.954 | 0 |  |  |  |  | 1.954
14.6 | Schme-J: Supply, Erection, testing & commissioning of Digital governing system and Hydraulic oil pressure unit for 15 MW Bhatsa HPS. | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 |  | 2020-07-17 |  | - | - |  | - | 2.027 | 2.0503 |  |  |  |  | -0.023297
14.7 | Schme-K: Supply, Retrofitting, up gradation, Commissioning of Generator protection system at Paithan HPS. | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 |  | 2020-07-17 |  | - | - |  | - | 0.87 | 0 |  |  |  |  | 0.87
14.8 | Schme-L: Replacement of existing compressor with new compressor (1 Nos.) at Paithan HPS | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 |  | 2020-07-17 |  | - | - |  | - | 0.467 | 0 |  |  |  |  | 0.467
14.9 | Schme-M: Retrofitting, up gradation & Commissioning of Protection System for Generator, Transformer and Line at Surya Hydro Power Station | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 |  | 2020-07-17 |  | - | - |  | - | 0.691 | 0.69731 |  |  |  |  | -0.0063094
14.1 | Schme-N: Procurement of Static excitation system at Surya Hydro Power Station. | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 |  | 2020-07-17 |  | - | - |  | - | 1.547 | 0 |  |  |  |  | 1.547
0 | IDC | IDC | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 |  | 2020-07-17 |  | - | - |  | - | 0.85 | 0 |  |  |  |  | 0.85
Formulas:
Project Start Date = [MERC Approval Date]

## F4.2 SHPC Nashik
|  |  | MSPGCL: Nasik HPC | [49 empty] | DPR | Not Initiated
|  |  | MTR Petition Formats - Generation | [49 empty] | Scheme | WIP
| Project Details |  | Form 4.2: Capitalisation Plan | [18 empty] | (Rs. Crore) | [22 empty] | (Rs. Crore) | [7 empty] | IDC | Partially Capitalized
Sr. No. | Project Code | DPR | MERC Approval No. | Date of Submission | MERC Approval Date | Cost as per DPR Crs. | MERC Approved Cost | Debt Equity Ratio | Grant Funding | Approved Start Date | Actual Start Date | Approved Date of Completion | Actual Date of Completion | Benefits in Quantified Terms | Capital Expenditure | [11 empty] | Physical Progress (%) | [10 empty] | Capitalisation | [11 empty] | Old Asset retired against capitalised item (in Rs. Cr) | Remarks | Current Status | Non-DPR | Capitalised
[15 empty] | Actual Capex till FY 2018-19 | Actual | Actual | Actual | Actual Capex till FY 2021-22 | Actual | Actual | Revised Projected | Revised Projected | Revised Projected | Revised Projected | Revised Projected | Actual Progress till FY 2018-19 | Actual | Actual | Actual | Actual | Actual | Revised Projected | Revised Projected | Revised Projected | Revised Projected | Revised Projected | Actual Capitalization till FY 2018-19 | Actual | Actual | Actual | Actual Capitalization till FY 2021-22 | Actual | Actual | Revised Projected | Revised Projected | Revised Projected | Revised Projected | Revised Projected |  |  |  |  | Cancelled
[16 empty] | FY 2019-20 | FY 2020-21 | FY 2021-22 |  | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 |  | FY 2019-20 | FY 2020-21 | FY 2021-22 | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 |  | FY 2019-20 | FY 2020-21 | FY 2021-22 |  | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 |  |  |  |  | To be cancelled
[52 empty] | N.A. |  | N.A.
| A) DPR Schemes | [50 empty] | N.A. |  | To be confirmed
| (i) Submitted to MERC | [50 empty] | N.A.
2 | Various schemes of Hydro Power Stations at HPC Pune & HPC Nasik | DPR | MERC/TECH 12/CAPEX/20142015/00876 | 2014-01-18 | 2014-08-20 | 0.7312 | 0.7312 |  |  | 2014-08-20 | [8 empty] | 0 | [22 empty] | 0 | [9 empty] | N.A.
2.6 | Supply, testing, installation and commissioning of Exide make 300 AH 220 V Lead acid stationary Plante type station battery set for Vaitarna HPS | Scheme | MERC/TECH 12/CAPEX/20142015/00876 | 2014-01-18 | 2014-08-20 | 0.2 | 0.2 |  |  | 2014-08-20 |  |  |  |  | 0.19886 |  |  |  | 0.19886 | [7 empty] | 100% | [10 empty] | 0.19886 |  |  |  | 0.19886 | [9 empty] | Capitalised
2.7 | Supply, testing, installation and commissioning of Exide make 300 AH 220 V Lead acid stationary Plante type station battery set for Bhatsa HPS | Scheme | MERC/TECH 12/CAPEX/20142015/00876 | 2014-01-18 | 2014-08-20 | 0.2 | 0.2 |  |  | 2014-08-20 |  |  |  | Safe, healthy and reliable DC supply available for control circuit and protections | 0.19886 |  |  |  | 0.19886 | [7 empty] | 100% | [10 empty] | 0.19886 |  |  |  | 0.19886 | [9 empty] | Capitalised
| IDC | IDC | MERC/TECH 12/CAPEX/20142015/00876 | 2014-01-18 | 2014-08-20 | 0.3312 | 0.3312 |  |  | 2014-08-20 |  |  |  | Safe, healthy and reliable DC supply available for control circuit and protections | 0 |  |  |  | 0 | [7 empty] | - | [10 empty] | 0 |  |  |  | 0 | [9 empty] | N.A.
6 | Upgradation of Protection Systems at Ghatghar (2x125MW) and Bhatsa (1x15MW) HPS under HPC Nasik | DPR | MERC/CAPEX/20172018/04220 | 2017-07-13 | 2017-09-19 | 15.104 | 15.104 |  |  | 2017-09-19 | [8 empty] | 0 | [22 empty] | 0 | [9 empty] | N.A.
6.1 | Up gradation of Protection System &unitrol excitation system at Ghatghar Hydro Power Station. | Scheme | MERC/CAPEX/20172018/04220 | 2017-07-13 | 2017-09-19 | 9.678 | 9.678 |  |  | 2017-09-19 |  |  |  |  | 0 |  |  |  | 0 | [18 empty] | 0 |  |  |  | 0 | [9 empty] | WIP
| Part A : upgradation of unitrol excitation system for both units at GHPS | [12 empty] | To obtain fast, accurate, protection & control system with long term technical support. Was obsolete, absence of critical and lack of assistance from OEM in supply. Hecne upgradation will help in ensuring reliability, reduction is system down time and faster restoration of system. |  |  |  |  | 0 |  |  | 3.419 | [19 empty] | 0 |  |  | 3.419 | [6 empty] | WIP
| Part B : upgradation of Protection system for both units at GHPS | [12 empty] | To obtain fast, accurate, protection & control system with long term technical support. Was obsolete, absence of critical and lack of assistance from OEM in supply. Hecne upgradation will help in ensuring reliability, reduction is system down time and faster restoration of system. |  |  |  |  | 0 |  |  | 2.9146 | [19 empty] | 0 |  |  | 2.9146 | [6 empty] | WIP
6.2 | Up gradation of ABB Make Protection System & Automatic Voltage Regulator, Relay Based Unit & Auxiliary control for Bhatsa Hydro Power Station(1 X 15MW). | Scheme | MERC/CAPEX/20172018/04220 | 2017-07-13 | 2017-09-19 | 5.426 | 5.426 |  |  | 2017-09-19 |  |  |  |  | 0 |  |  |  | 0 | [18 empty] | 0 |  |  |  | 0 | [9 empty] | WIP
| Protection system Part A:- Restoration and up-gradation of electromechanical and static relays with numerical relays along with installation, testing, commissioning, and misc. allied works | [12 empty] | 1. Generation loss of 0.35 MU’s per day from this plant due to outage on accounts of submergence has been nullified. 2. Installation of latest relays enabled, settings of alarm and tripping as per requirement, customized modifications for getting desired protections, easy trouble shooting and fault diagnosis. |  |  |  |  | 0 | [22 empty] | 0 |  | 0.45666 | [7 empty] | Capitalised
| Protection system Part B:- Procure of redundant & spare Numerical relays for Generator and G T Protection system. | [12 empty] | 1. Generation loss of 0.35 MU’s per day from this plant due to outage on accounts of submergence has been nullified. 2. Redundancy increases reliability and availability even in case of failure of one of the redundant relay. 3. Spare availibility is essential to restore unit in case of failure within minimum downtime. |  |  |  |  | 0 |  |  | 0.65 | [19 empty] | 0 |  |  | 0.65 | [6 empty] | WIP
| C- Supply erection, testing and Commissioning and supervision of dismantling and erection of static excitation system and control system along with field instrumentation at Bhatsa HPS | [12 empty] | 1. Generation loss of 0.35 MU’s per day from this plant due to outage on accounts of submergence has been nullified. 2. Current scheme is not directly linked to improvement in technical performance however essential to ensure reliability of system. 3. As AVR, excitation system and control system are the major part of any Generation process, ensuring their healthiness is of utmost importance to avoid any unseen emergency and to avoid probable Generation loss. |  |  |  |  | 0 |  |  | 3.8232 | [19 empty] | 0 |  |  | 3.8232 | [6 empty] | WIP
9 | Various Civil schemes for Modernisations of colonies at Various Locations under Nasik HPC | DPR | MERC/CAPEX/20162017/04757 | 2017-11-10 | 2017-11-22 | 14.5667 | 14.5667 |  |  | 2017-11-22 | [8 empty] | 0 | [22 empty] | 0 | [9 empty] | N.A.
9.1 | Part A: Refurbishment of quarters in colony, administartive buidings club building, guest house at various HPS under Nashik HPS | Scheme | MERC/CAPEX/20162017/04757 | 2017-11-10 | 2017-11-22 | 3.7364 | 3.7364 |  |  | 2017-11-22 |  |  |  | 1) Provided pleasant and healthy enviroment in quarters. 2) Better apperence of colony premises has achieved. 3) We had provided better services to employee with minimum effort by reducing maintance cost. 4)Maintanance of quarters,Club House and Admin.Building are reduced and All building life has increased. | 0.70901 | 0.16871 |  | 0.66608 | 1.5438 | 1.9668 | 0.13142 | [16 empty] | 0.70901 | 0.16871 |  | 0.66608 | 1.5438 | 2.4568 | 0.25044 | [7 empty] | Capitalised
9.2 | Part B: Providing and laying water supply lines within colony and power house area at various HPS under Nashik HPS | Scheme | MERC/CAPEX/20162017/04757 | 2017-11-10 | 2017-11-22 | 0.50088 | 0.50088 |  |  | 2017-11-22 |  |  |  | )1Easy Installation. Galvanised iron pipes are effortless to install and have a sturdy protective covering that boosts resistance to corrosion and stress. 2)Corrosion Resistance. 3)Long Lifespan. 4)Easy Maintenance. 5)Eco-Friendly. 6)Cost-Friendly. | 0 | 0.11901 |  |  | 0.11901 | [18 empty] | 0 | 0.11901 |  |  | 0.11901 | [9 empty] | Capitalised
9.3 | Part C: Construction of compund wall/chainlink fencing around colony and power house area at various HPS under Nashik HPS. | Scheme | MERC/CAPEX/20162017/04757 | 2017-11-10 | 2017-11-22 | 0.74833 | 0.74833 |  |  | 2017-11-22 |  |  |  | 1)provided security, privacy TO COLONY PREMISES. 2) It provided a physical barrier that enhances safety, reduces noise 3)It provided barrier for animals to enter into colony and power house premises | 0.17 |  |  |  | 0.17 | [18 empty] | 0.17 |  |  |  | 0.17 | [9 empty] | Capitalised
9.4 | Part D: Providing & relaying of existing internal roads within colony area and approach roads to power house & construction of storm water gutter along road at various HPS under HPC Nashik | Scheme | MERC/CAPEX/20162017/04757 | 2017-11-10 | 2017-11-22 | 9.5811 | 9.5811 |  |  | 2017-11-22 |  |  |  | 1) Reduced frequent maintenance of road. 2) Avoided any unwanted accident on road during rainy season. 3) To flush out the rain water on road surface and water from hillock side smoothly into nallah. | 0.5 | 1.5831 | 0.16462 |  | 2.2477 | 1.806 | [17 empty] | 0.5 | 1.5831 | 0.16462 |  | 2.2477 | 1.806 | [8 empty] | Capitalised
10 | Upgradation of existing PLC system to latest symphony plus SCADA & DCS system of Ghatghar HPS (2x125 MW) under HPS Nasik | DPR | MERC/CAPEX/20172018/0198 | 2018-01-10 | 2018-02-06 | 13.345 | 13.345 |  |  | 2018-02-06 | [8 empty] | 0 | [22 empty] | 0 | [9 empty] | N.A.
10.1 | Upgradation of existing PLC system to latest symphony plus SCADA & DCS system of Ghatghar HPS (2x125 MW) under HPS Nasik | Scheme | MERC/CAPEX/20172018/0198 | 2018-01-10 | 2018-02-06 | 13.345 | 13.345 |  |  | 2018-02-06 |  |  |  | Avoiding possible generation loss with reduced fault attending time, fast & assured protection, improvement in capacityutilization factor | 0 |  |  |  | 0 |  |  |  | 14.5503 | [14 empty] | 0 |  |  |  | 0 |  |  |  | 14.5503 | [5 empty] | WIP
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | DPR | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2019-01-29 | 2020-07-17 | 8.913 | 8.913 |  |  | 2020-07-17 | [8 empty] | 0 | [22 empty] | 0 | [9 empty] | N.A.
14.1 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2019-01-29 | 2020-07-17 | 0.102 | 0.102 |  |  | 2020-07-17 |  |  |  |  | 0 |  |  |  | 0 | [18 empty] | 0 |  |  |  | 0 | [9 empty] | Capitalised
14.2 | Schme-F: Replacement of 220V / 300AH Float cum boost charger with integrated DCDB for Bhatsa Hydro Power Stn. | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2019-01-29 | 2020-07-17 | 0.173 | 0.173 |  |  | 2020-07-17 |  |  |  | Increase in Availability Factor and Reduction in Outage Period, less maintenance require and healthy DC supply available. | 0 |  |  |  | 0 |  | 0.11446 | [16 empty] | 0 |  |  |  | 0 |  | 0.11446 | [7 empty] | Capitalised
14.3 | Schme-G: Replacement of 220V / 300AH Float cum boost charger with integrated DCDB for Surya Hydro Power Stn. | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2019-01-29 | 2020-07-17 | 0.173 | 0.173 |  |  | 2020-07-17 |  |  |  | Increase in Availability Factor and Reduction in Outage Period, less maintenance require and healthy DC supply available. | 0 |  |  |  | 0 |  | 0.11446 | [16 empty] | 0 |  |  |  | 0 |  | 0.11446 | [7 empty] | Capitalised
14.4 | Schme-H: Supply 24 point Chartless recorder for Bhatsa HPS. | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2019-01-29 | 2020-07-17 | 0.059 | 0.059 |  |  | 2020-07-17 |  |  |  | System updating essential to maintain system healthiness | 0 |  |  |  | 0 |  | 0.020245 | [16 empty] | 0 |  |  |  | 0 |  | 0.020245 | [7 empty] | Capitalised
14.5 | Schme-I: Supply Erection, testing & commissioning of Digital governing system for 06MW Surya HPS. | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2019-01-29 | 2020-07-17 | 1.954 | 1.954 |  |  | 2020-07-17 |  |  |  | 1. Major Outages and generation loss avaoided due to less failure and malfunctioning of Governor enabling maximum availability. 2. Faster response to load variations minimises consequences of faults. | 0 |  |  |  | 0 |  |  | 1.954 | [15 empty] | 0 |  |  |  | 0 |  |  | 1.954 | [6 empty] | WIP
14.6 | Schme-J: Supply, Erection, testing & commissioning of Digital governing system and Hydraulic oil pressure unit for 15 MW Bhatsa HPS. | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2019-01-29 | 2020-07-17 | 2.027 | 2.027 |  |  | 2020-07-17 |  |  |  | 1. Major Outages and generation loss avaoided due to less failure and malfunctioning of Governor enabling maximum availability. 2. Faster response to load variations minimises consequences of faults. | 0 |  |  |  | 0 |  | 2.0503 | [16 empty] | 0 |  |  |  | 0 |  | 1.5936 | [7 empty] | WIP
14.7 | Schme-K: Supply, Retrofitting, up gradation, Commissioning of Generator protection system at Paithan HPS. | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2019-01-29 | 2020-07-17 | 0.87 | 0.87 |  |  | 2020-07-17 |  |  |  | 1. Enhamced protection . 2.Multi functionalility. 3.Improved accuracy 4. Data logging and Analysis 5. Reduced maintenance 6. Flexibility and Scalability | 0 |  |  |  | 0 |  |  | 0.87 | [15 empty] | 0 |  |  |  | 0 |  |  | 0.87 | [6 empty] | WIP
14.8 | Schme-L: Replacement of existing compressor with new compressor (1 Nos.) at Paithan HPS | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2019-01-29 | 2020-07-17 | 0.467 | 0.467 |  |  | 2020-07-17 |  |  |  | 1. Energy efficiency 2. Reliability 3. Advance technology better performance. 4. Reduce emissions and improve environmental compliance | 0 |  |  |  | 0 |  |  | 0.467 | [15 empty] | 0 |  |  |  | 0 |  |  | 0.467 | [6 empty] | WIP
14.9 | Schme-M: Retrofitting, up gradation & Commissioning of Protection System for Generator, Transformer and Line at Surya Hydro Power Station | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2019-01-29 | 2020-07-17 | 0.691 | 0.691 |  |  | 2020-07-17 |  |  |  | 1. Major Outages and generation loss avaoided due to less failure and malfunctioning of Protection Relays enabling maximum availability. 2. Faster response to faults ensures safety of man and machine. | 0 |  |  |  | 0 |  | 0.69731 | [16 empty] | 0 |  |  |  | 0 |  | 0.68499 | [7 empty] | WIP
14.1 | Schme-N: Procurement of Static excitation system at Surya Hydro Power Station. | Scheme | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2019-01-29 | 2020-07-17 | 1.547 | 1.547 |  |  | 2020-07-17 |  |  |  | 1. Increased continuous generation, Major outage and generation loss due to failure or malfunctionining of AVR avoided. 2. Fast response to grid voltage fluctuations and corrective voltage balancing ensures minimum fault triping and generation loss. 3. FGMO scheme implemntation ensured. | 0 |  |  |  | 0 |  |  | 1.547 | [15 empty] | 0 |  |  |  | 0 |  |  | 1.547 | [6 empty] | WIP
| IDC | IDC | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2019-01-29 | 2020-07-17 | 0.85 | 0.85 |  |  | 2020-07-17 |  |  |  |  | 0 |  |  |  | 0 | [18 empty] | 0 |  |  |  | 0 | [9 empty] | N.A.
[19 empty] | 0 | [22 empty] | 0
| Yet to be approved by MERC (F Y 2024-25) | [17 empty] | 0 | [22 empty] | 0
1 | Post-facto DPR for “Urgent restoration and Life Enhancement of Unit-1, 125MW M/s Fuji make Hydro Generator for prolonged efficient operation at Ghatghar HPS |  |  |  |  | 14.34 | [7 empty] | Life enhancement of unit 1 generator and increase availability of unit. |  |  |  |  | 0 |  |  | 14.34 | [19 empty] | 0 |  |  | 14.34 | [6 empty] | WIP
2 | Dismantling and assembly of Unit-2 stator and other allied works at Ghatghar HPS |  |  |  |  | 0.92 | [7 empty] | Life enhancement of unit 2 generator and increase availability of unit. |  |  |  |  | 0 |  |  | 0.92 | [19 empty] | 0 |  |  | 0.92 | [6 empty] | WIP
3 | Urgent restoration and Life Enhancement of Unit-2, 125MW M/s Fuji make Hydro Generator for prolonged efficient operation at Ghatghar HPS |  |  |  |  | 12.69 | [7 empty] | Life enhancement of unit 2 generator and increase availability of unit. |  |  |  |  | 0 |  |  | 12.69 | [19 empty] | 0 |  |  | 12.69 | [6 empty] | WIP
4 | Work of unit 2 stator core top lamination replacement work of GHPS |  |  |  |  | 1.57 | [7 empty] | Life enhancement of unit 2 generator and increase availability of unit. |  |  |  |  | 0 |  |  | 1.57 | [19 empty] | 0 |  |  | 1.57 | [6 empty] | WIP
| (ii) Yet to be submitted to MERC(F Y 2025-26) | [17 empty] | 0 | [22 empty] | 0
| DPR 1 | [17 empty] | 0 | [22 empty] | 0
1 | Procurement & commissioning of Battery bank, 55 cells of 2V 2035AH YHP39 Exide make at Ghatghar HPS |  |  |  |  | 1.25 | [7 empty] | Shall reduce downtime & increase availability |  |  |  |  | 0 |  |  |  | 1.25 | [18 empty] | 0 |  |  |  | 1.25 |  |  |  |  | DPR Yet to be submitted | N.A.
2 | Complete refurbishment of Stator frame , core & winding of 01 No generator stator at Ghatghar HPS. |  |  |  |  | 23.9 | [7 empty] | Shall increase availability, improve system performance |  |  |  |  | 0 |  |  |  | 23.9 | [18 empty] | 0 |  |  |  | 23.9
3 | Generator Circuit breaker Electrical OH at Ghatghar HPS. |  |  |  |  | 7.2 | [7 empty] | Provide potable water to employees at Ghatghar HPS |  |  |  |  | 0 |  |  |  | 7.2 | [18 empty] | 0 |  |  |  | 7.2
4 | Water filter treatment plant and pipeline at Ghatghar HPS. |  |  |  |  | 1.25 | [7 empty] | Shall increase availability, improve system performance |  |  |  |  | 0 |  |  |  | 1.25 | [18 empty] | 0 |  |  |  | 1.25
| DPR 2 | [17 empty] | 0 | [22 empty] | 0
1 | Design,supply,errection,testing & commissioning of digital governing system at Paithan HPS. |  |  |  |  | 4.5 | [7 empty] | 1)Transidyn tyepe analog cards used in governing ssytem are absolete 2)Spares are not available 3)Existing cards are prone to maifunction & temds to probem in system. 4)Replacement by highly efficient electronic digital governor. 5) In order to implement Free Governing Mode of operation (FGMO) as per CERC directives |  |  |  |  | 0 |  |  |  | 4.5 | 0 | [17 empty] | 0 |  |  |  | 4.5 | 0 |  |  |  | DPR Yet to be submitted | N.A.
2 | Design,Supply ,testing ,erection and commissioing of DAVR system at Paithan HPS. |  |  |  |  | 2 | [7 empty] | 1. AVR is obsolete 2. Spares are not available. 3. Advanced control capabilities 4.Voltage sag mitigation |  |  |  |  | 0 |  |  |  | 2 | 0 | [17 empty] | 0 |  |  |  | 2 | 0
3 | Design,supply,testing ,erection and commissioing of DCS control system at Paithan HPS. |  |  |  |  | 1.7 | [7 empty] | 1)Existing system of Electromechnaical relay is obsolete. 2)Spares are not avialble in market 3)Advanced technology |  |  |  |  | 0 |  |  |  | 1.7 | 0 | [17 empty] | 0 |  |  |  | 1.7 | 0
4 | Design,supply ,testing ,erection and commissioing of Automated Co2 fire extinguishers system at Paithan HPS. |  |  |  |  | 0.35 | [7 empty] | 1)Currently only smoke detectors are provided at Generator barrel2)Automated Co2 system will ensure safety of generator from fire |  |  |  |  | 0 |  |  |  | 0.35 | 0 | [17 empty] | 0 |  |  |  | 0.35 | 0
5 | Design,Supply ,testing ,erection and commissioing of Numerical protection system at Yeldari HPS. |  |  |  |  | 2.55 | [7 empty] | 1. Existing Protection is obsolete/outdated. 2. Spares are not available. 3. Replacement by Advanced Technology 4. Electrical Protection Committee suggessions |  |  |  |  | 0 |  |  |  | 2.55 | 0 | [17 empty] | 0 |  |  |  | 2.55 | 0
6 | Design,Supply ,testing ,erection and commissioing of C&I control & measurement with SCADA at Yeldari HPS. |  |  |  |  | 1 | [7 empty] | 1. Real-Time monitoring & Control. 2. Enhanced data accuracy. 3.Improved data management. 4.Remote access. 5. Alarm & Event management. 6. Enhanced security |  |  |  |  | 0 |  |  |  | 1 | 0 | [17 empty] | 0 |  |  |  | 1 | 0
7 | Design,Supply ,testing ,erection and commissioing of DAVR system at Yeldari HPS |  |  |  |  | 6 | [7 empty] | 1. AVR is obsolete 2. Spares are not available. 3. Advanced control capabilities 4.Voltage sag mitigation |  |  |  |  | 0 |  |  |  | 6 | 0 | 0 | [16 empty] | 0 |  |  |  | 6 | 0 | 0
8 | Design,supply,errection,testing & commissioning of digital governing system at Yeldari HPS. |  |  |  |  | 7 | [7 empty] | 1. Enhanced Precision and Control 2. Spares are not available. 3. Advanced Technology 4.Improved diagnostics |  |  |  |  | 0 |  |  |  | 7 | 0 | 0 | [16 empty] | 0 |  |  |  | 7 | 0 | 0
| DPR 3 (CIVIL) | [17 empty] | 0 | [22 empty] | 0
1 | Fortification and Rock fall protection Measures in Vaitarna Hydro Electric Power Project Premises ,Tal- Igatpuri , Dist-Nashik. |  |  |  |  | 36.53 | [7 empty] | 1) To increase stability & life of hydro pow station Structures/buildings. 2) To protect the portal switchyard area and electrical equipment such as support insulator for cable joints and tunnel area. 3) To safeguard the assets Hydro power station. 4) To protect health of the staff working Power Station 5) To enhance the stability of Structures/ Building. |  |  |  |  | 0 |  |  |  | 36.53 | [18 empty] | 0 |  |  |  | 36.53 |  |  |  |  | DPR submitted | N.A.
2 | Work of construction of Bituminous approach road to Portal Switchyard at Vaitarna HPS. |  |  |  |  | 2.77 | [7 empty] | 1) To avoid frequent maintenance of road. 2) To avoid any unwanted accident on road during rainy season. 3) To flush out the rain water smoothly in concrete drain |  |  |  |  | 0 |  |  |  | 2.77 | [18 empty] | 0 |  |  |  | 2.77
3 | Work of construction of Gabion wall structure on down stream of nallah near Tunnel at Vaitarna HPS. |  |  |  |  | 0.26 | [7 empty] | 1) Gabions offer an easy-to-use method for decreasing water velocity and protecting slopes from erosion. 2) Speed of construction is fast. 3) Gabion wall has good Permeability to water (Good drainage) |  |  |  |  | 0 |  |  |  | 0.26 | [18 empty] | 0 |  |  |  | 0.26
| (ii) Yet to be submitted to MERC(F Y 2026-27) | [17 empty] | 0 | [22 empty] | 0
| DPR 4 | [17 empty] | 0 | [22 empty] | 0
1 | Comprehensive work of redesign,manufacture, supply erection, testing & commissioning of Digital Governing, Protection and control system Consisting of SCADA on single point responsibility at 60 MW Vaitarna HPS. |  |  |  |  | 14 | [7 empty] | 1. Major Outages and generation loss avaoided due to less failure and malfunctioning of Governor and Protection Relays will ensure maximum availability. 2. Faster response to load variations and faults minimises consequences of tripings. |  |  |  |  | 0 |  |  |  |  | 14 | [17 empty] | 0 |  |  |  |  | 14 |  |  |  | DPR Yet to be submitted | N.A.
2 | Comprehensive work of Replacement, Modification,upgradation of cooling water system along with replacement of pipeline,pumps,panel etc at 60 MW Vaitarna HPS. |  |  |  |  | 2.5 | [7 empty] | Cooling water system healthiness will be ensured and less breakdown of pump and pipelines avoiding generation loss. |  |  |  |  | 0 |  |  |  |  | 2.5 | [17 empty] | 0 |  |  |  |  | 2.5
3 | Design, Manufacture, Supply, Erection, Testing and commissioning of 1000 KVA UAT & EAT at 60MW Vaitarna HPS. |  |  |  |  | 0.6 | [7 empty] | Air conditioning in power house will be achieved as current transformers not sufficient for running both chiller units and any other extra auxilaries. |  |  |  |  | 0 |  |  |  |  | 0.6 | [17 empty] | 0 |  |  |  |  | 0.6
4 | Supply, Erection, Testing & Commissioning of 500 KVA DG set along with cable and changeover system at 60 MW Vaitarna HPS |  |  |  |  | 0.6 | [7 empty] | Generation loss on account of AC supply failure will be avoided and downtime will be reduced. |  |  |  |  | 0 |  |  |  |  | 0.6 | [17 empty] | 0 |  |  |  |  | 0.6
5 | Supply, erection, testing and commissioning of 132kV Single core 300sqmm copper conductor XLPE insulated Lead sheathed power cable from Portal switchyard to Main switchyard along with fabrication of cable trays and misc. allied works at 60 MW Vaitarna HPS |  |  |  |  | 11 | [7 empty] | Portal Switch yard will be eliminated in future and risk of portal switch yard failure due to land sliding will be avoided. Also generation loss on this scenario will be avoided. |  |  |  |  | 0 |  |  |  |  | 11 | [17 empty] | 0 |  |  |  |  | 11
| DPR 5 | [17 empty] | 0 | [22 empty] | 0 | [8 empty] | DPR Yet to be submitted | N.A.
1 | Upgradation of Insulation class Yeldari HPS |  |  |  |  | 6 | [7 empty] | 1. Increased thermal Endurance 2.Extended lifespan 3. Enhanced reliability 4. Better performance in Harsh condition. |  |  |  |  | 0 |  |  |  |  | 6 |  |  | 0 | [14 empty] | 0 |  |  |  |  | 6
2 | Design,Supply ,testing ,erection and commissioing of with modification of HT power circuit from 66KV to 132 KV by providing 03 Nos GT of 6.6/132 KV capcity 10 MVA with allied compatible aux. equipments & 01 Aux X`mer 2MVA of 132/11 KV at Yeldari HPS |  |  |  |  | 10.2 | [7 empty] | 1. Improved reliability .2. Reduce maint cost 3. Energy Aefficiency 4. Avoiding downtime |  |  |  |  | 0 |  |  |  |  | 10.2 | [17 empty] | 0 |  |  |  |  | 10.2
3 | Design,supply ,testing ,erection and commissioing of Automated Co2 fire extinguishers system including supply of Co2 cylinder banks,detectors accessories and associated work at Yeldari HPS |  |  |  |  | 0.6 | [7 empty] | 1. Rapid fire supression 2. No Residue. 3. Enhanced safety 4. Compliance with standards |  |  |  |  | 0 |  |  |  |  | 0.6 | [17 empty] | 0 |  |  |  |  | 0.6
4 | Design,supply ,testing ,erection and commissioing of UAT capacity 250 KVA ration 6.6KV/415V with ACDB, DCDB , auto change over system |  |  |  |  | 3 | [7 empty] | 1. Improved reliability 2. Reduce maint cost 3. Energy Efficiency 4. Avoiding downtime |  |  |  |  | 0 |  |  |  |  | 3 | [17 empty] | 0 |  |  |  |  | 3
5 | Design,supply ,testing ,erection and commissioing of Power cables for GT and control cables at Yeldari HPS |  |  |  |  | 3.75 | [7 empty] | 1. Improved reliability 2. Reduce maint cost 3. Improved safety 4. Avoiding downtime |  |  |  |  | 0 |  |  |  |  | 3.75 | [17 empty] | 0 |  |  |  |  | 3.75
6 | Design,supply ,testing ,erection and commissioing of Power cables for GT and control cables at Yeldari HPS |  |  |  |  | 1.5 | [7 empty] | 1. Improved reliability 2. Reduce maint cost 3. Improved safety 4. Avoiding downtime |  |  |  |  | 0 |  |  |  |  | 1.5 | [17 empty] | 0 |  |  |  |  | 1.5
| DPR 6(CIVIL) | [17 empty] | 0 | [22 empty] | 0
1 | Package shade roof change at Ghatghar HPS |  |  |  |  | 2 | [7 empty] | 1)Necessary for maintainng spares/inventories at package shed in good condition by avoiding leakages from old roofshed. |  |  |  |  | 0 |  |  |  |  | 2 | [17 empty] | 0 |  |  |  |  | 2 |  |  |  | DPR Yet to be submitted | N.A.
2 | PROCUREMENT OF MOBILE RACKS FOR STORES atGhatghar HPS |  |  |  |  | 0.25 | [7 empty] | Maintain and arrange spares/inventories efficiently |  |  |  |  | 0 |  |  |  |  | 0.25 | [17 empty] | 0 |  |  |  |  | 0.25
3 | Wall compound Rising of height and Wire fence on wall at package shade at Ghatghar HPS |  |  |  |  | 1.5 | [7 empty] | Improve safety of colony and package shed. |  |  |  |  | 0 |  |  |  |  | 1.5 | [17 empty] | 0 |  |  |  |  | 1.5
4 | Wall compound colony UCR at Ghatghar HPS |  |  |  |  | 1.5 | [7 empty] | Improve safety of colony and avoid theft incident. |  |  |  |  | 0 |  |  |  |  | 1.5 | [17 empty] | 0 |  |  |  |  | 1.5
5 | Colony and office Road asphalting at Ghatghar HPS |  |  |  |  | 2 | [7 empty] | Improve safety, health & avoid accidents of employees travelling to Power house, office etc. |  |  |  |  | 0 |  |  |  |  | 2 | [17 empty] | 0 |  |  |  |  | 2
6 | Road colony to power house at Ghatghar HPS |  |  |  |  | 7 | [7 empty] | Improve safety, health & avoid accidents of employees travelling to Power house, office etc. |  |  |  |  | 0 |  |  |  |  | 7 |  | 0 | 0 | [14 empty] | 0 |  |  |  |  | 7 |  | 0
[19 empty] | 0 | [22 empty] | 0
| (ii) Yet to be submitted to MERC(F Y 2027-28) | [17 empty] | 0 | [22 empty] | 0
| DPR 7 | [17 empty] | 0 | [22 empty] | 0
1 | UPGRADATION OF SFC & DDC PANEL at Ghatghar HPS |  |  |  |  | 10 | [7 empty] | Shall increase availability, improve system performance |  |  |  |  | 0 | [5 empty] | 10 |  | 0 | [14 empty] | 0 | [5 empty] | 10 |  |  | DPR Yet to be submitted | N.A.
2 | BATTERY CHARGER PROCUREMENT at Ghatghar HPS |  |  |  |  | 0.5 | [7 empty] | Shall increase availability, improve system performance |  |  |  |  | 0 | [5 empty] | 0.5 | [16 empty] | 0 | [5 empty] | 0.5
3 | PHASE REVERSAL SWITCH PROCUREMENT at Ghatghar HPS |  |  |  |  | 0.5 | [7 empty] | Shall increase availability, improve system performance |  |  |  |  | 0 | [5 empty] | 0.5 | [16 empty] | 0 | [5 empty] | 0.5
4 | PROCUREMENT OF SPARES FOR 220kV GIS at Ghatghar HPS |  |  |  |  | 6.5 | [7 empty] | Shall increase availability, improve system performance |  |  |  |  | 0 | [5 empty] | 6.5 | [16 empty] | 0 | [5 empty] | 6.5
5 | PROCUREMENT OF RBDV at Ghatghar HPS |  |  |  |  | 1 | [7 empty] | Shall increase availability, improve system performance |  |  |  |  | 0 | [5 empty] | 1 | [16 empty] | 0 | [5 empty] | 1
[19 empty] | 0 | [22 empty] | 0
| DPR 8 | [17 empty] | 0 | [22 empty] | 0
1 | Comprehensive work of Renovation, Modification, Design, Manufacture, Supply, Erection, Testing & Commissioning of new Generator on single point responsibility at 60 MW Vaitarna HPS. |  |  |  |  | 50 | [7 empty] | New Generator with higher class insulation will increase life of genrator and will generate power continuously. |  |  |  |  | 0 | [5 empty] | 50 | 0 | [15 empty] | 0 | [5 empty] | 50 | 0 |  | DPR Yet to be submitted | N.A.
| B) Non-DPR Schemes | [17 empty] | 0 | [22 empty] | 0
1 | Office Equipment | Non-DPR | N.A. | [12 empty] | 0.20626 | 0.17357 | 0.16633 | 0.54617 | 0.014272 | 0.10329 | [17 empty] | 0.20626 | 0.17357 | 0.16633 | 0.54617 | 0.024272 | 0.13
2 | Furniture & Fixtures | Non-DPR | N.A. | [12 empty] | 0.005756 | 0 | 0 | 0.005756 |  | 0.029992 | [17 empty] | 0.005756 | 0 | 0 | 0.005756 |  | 0.029992
3 | Replacement of existing 300AH/220VDC & 200AH/220VDC Battery Set with new Lead acid Tubular Battery Set along with Design, manufacture, supply, installation, commissioning & testing at Yeldari & Paithan HPS | Non-DPR | N.A. | [15 empty] | 0 |  | 0.2283 | [20 empty] | 0 |  | 0.2283 | [7 empty] | Capitalised
4 | Vehicle (Fire Tender ) | [17 empty] | 0 | 4.0078 | [21 empty] | 0 | 4.0078
| Total | [13 empty] | 1.7767 | 2.0828 | 0.33819 | 0.83242 | 5.0301 | 7.7948 | 3.4898 | 45.1649 | 112.8102 | 68 | 68.5 | 0 | [11 empty] | 1.7767 | 2.0828 | 0.33819 | 0.83242 | 5.0301 | 8.2948 | 3.6232 | 45.1649 | 112.8102 | 68 | 68.5 | 0 | 0
[43 empty] | 4.032 | 0.38829 | 0
Formulas:
Date of Submission = [Date of Submission, row above]
MERC Approval Date = [MERC Approval Date, row above]
MERC Approval Date = IF([MERC Approval Date, row above]=0,"-",[MERC Approval Date, row above])
Approved Start Date = IF([MERC Approval Date]=0,"-",[MERC Approval Date])
Note on M4: SSP-RCD As per the implementation plan submitted in the DPR/ Approved by MERC
Note on P11: SSP-RCD: FY 2013-14
Note on AM11: SSP-RCD: FY 2013-14
Note on P12: SSP-RCD: FY 2013-14
Note on AM12: SSP-RCD: FY 2013-14

## F4.3 SHPC Nashik
MSPGCL: Nasik HPC
MTR Petition Formats - Generation
| Project Details | Form 4.3: Capital Work-in-progress - Project-wise details | [9 empty] | (Rs. Crore)
Sr. No. | Project Code | MERC Approval No. | MERC Approval Date | Approved Project Cost | Cumulative Expenditure Incurred till beginning of the Year | Capital Expenditure Capitalised | Opening CWIP | Investment during the year | Capitalization |  |  |  | Closing CWIP
[9 empty] | Works Capitalised | Interest Capitalised | Expenses Capitalised | Total Capitalisation |  | Allowable Capitalisation | Probable Disallowance
FY 2022-23
a) DPR Schemes
(i) Submitted to MERC
2 | Various schemes of Hydro Power Stations at HPC Pune & HPC Nasik | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.7312 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.6 | Supply, testing, installation and commissioning of Exide make 300 AH 220 V Lead acid stationary Plante type station battery set for Vaitarna HPS | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.2 | 0.19886 | 0.19886 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.7 | Supply, testing, installation and commissioning of Exide make 300 AH 220 V Lead acid stationary Plante type station battery set for Bhatsa HPS | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.2 | 0.19886 | 0.19886 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.3312 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Upgradation of Protection Systems at Ghatghar (2x125MW) and Bhatsa (1x15MW) HPS under HPC Nasik | MERC/CAPEX/20172018/04220 | 2017-09-19 | 15.104 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Up gradation of Protection System &unitrol excitation system at Ghatghar Hydro Power Station. | MERC/CAPEX/20172018/04220 | 2017-09-19 | 9.678 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Part A : upgradation of unitrol excitation system for both units at GHPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Part B : upgradation of Protection system for both units at GHPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.2 | Up gradation of ABB Make Protection System & Automatic Voltage Regulator, Relay Based Unit & Auxiliary control for Bhatsa Hydro Power Station(1 X 15MW). | MERC/CAPEX/20172018/04220 | 2017-09-19 | 5.426 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Protection system Part A:- Restoration and up-gradation of electromechanical and static relays with numerical relays along with installation, testing, commissioning, and misc. allied works | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Protection system Part B:- Procure of redundant & spare Numerical relays for Generator and G T Protection system. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | C- Supply erection, testing and Commissioning and supervision of dismantling and erection of static excitation system and control system along with field instrumentation at Bhatsa HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Various Civil schemes for Modernisations of colonies at Various Locations under Nasik HPC | MERC/CAPEX/20162017/04757 | 2017-11-22 | 14.5667 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Part A: Refurbishment of quarters in colony, administartive buidings club building, guest house at various HPS under Nashik HPS | MERC/CAPEX/20162017/04757 | 2017-11-22 | 3.7364 | 1.5438 | 1.5438 | 0 | 1.9668 | 2.4568 |  |  | 2.4568 | -0.49 | 2.1925 | 0.26421
9.2 | Part B: Providing and laying water supply lines within colony and power house area at various HPS under Nashik HPS | MERC/CAPEX/20162017/04757 | 2017-11-22 | 0.50088 | 0.11901 | 0.11901 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.3 | Part C: Construction of compund wall/chainlink fencing around colony and power house area at various HPS under Nashik HPS. | MERC/CAPEX/20162017/04757 | 2017-11-22 | 0.74833 | 0.17 | 0.17 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.4 | Part D: Providing & relaying of existing internal roads within colony area and approach roads to power house & construction of storm water gutter along road at various HPS under HPC Nashik | MERC/CAPEX/20162017/04757 | 2017-11-22 | 9.5811 | 2.2477 | 2.2477 | 0 | 1.806 | 1.806 |  |  | 1.806 | 0 | 1.806 | 0
10 | Upgradation of existing PLC system to latest symphony plus SCADA & DCS system of Ghatghar HPS (2x125 MW) under HPS Nasik | MERC/CAPEX/20172018/0198 | 2018-02-06 | 13.345 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Upgradation of existing PLC system to latest symphony plus SCADA & DCS system of Ghatghar HPS (2x125 MW) under HPS Nasik | MERC/CAPEX/20172018/0198 | 2018-02-06 | 13.345 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 8.913 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.102 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Schme-F: Replacement of 220V / 300AH Float cum boost charger with integrated DCDB for Bhatsa Hydro Power Stn. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.173 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Schme-G: Replacement of 220V / 300AH Float cum boost charger with integrated DCDB for Surya Hydro Power Stn. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.173 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.4 | Schme-H: Supply 24 point Chartless recorder for Bhatsa HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.059 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.5 | Schme-I: Supply Erection, testing & commissioning of Digital governing system for 06MW Surya HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1.954 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.6 | Schme-J: Supply, Erection, testing & commissioning of Digital governing system and Hydraulic oil pressure unit for 15 MW Bhatsa HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 2.027 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.7 | Schme-K: Supply, Retrofitting, up gradation, Commissioning of Generator protection system at Paithan HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.87 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.8 | Schme-L: Replacement of existing compressor with new compressor (1 Nos.) at Paithan HPS | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.467 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.9 | Schme-M: Retrofitting, up gradation & Commissioning of Protection System for Generator, Transformer and Line at Surya Hydro Power Station | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.691 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | Schme-N: Procurement of Static excitation system at Surya Hydro Power Station. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1.547 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Yet to be approved by MERC (F Y 2024-25) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Post-facto DPR for “Urgent restoration and Life Enhancement of Unit-1, 125MW M/s Fuji make Hydro Generator for prolonged efficient operation at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Dismantling and assembly of Unit-2 stator and other allied works at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Urgent restoration and Life Enhancement of Unit-2, 125MW M/s Fuji make Hydro Generator for prolonged efficient operation at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Work of unit 2 stator core top lamination replacement work of GHPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC(F Y 2025-26) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement & commissioning of Battery bank, 55 cells of 2V 2035AH YHP39 Exide make at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Complete refurbishment of Stator frame , core & winding of 01 No generator stator at Ghatghar HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Generator Circuit breaker Electrical OH at Ghatghar HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Water filter treatment plant and pipeline at Ghatghar HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Design,supply,errection,testing & commissioning of digital governing system at Paithan HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Design,Supply ,testing ,erection and commissioing of DAVR system at Paithan HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Design,supply,testing ,erection and commissioing of DCS control system at Paithan HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Design,supply ,testing ,erection and commissioing of Automated Co2 fire extinguishers system at Paithan HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design,Supply ,testing ,erection and commissioing of Numerical protection system at Yeldari HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Design,Supply ,testing ,erection and commissioing of C&I control & measurement with SCADA at Yeldari HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Design,Supply ,testing ,erection and commissioing of DAVR system at Yeldari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Design,supply,errection,testing & commissioning of digital governing system at Yeldari HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 3 (CIVIL) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Fortification and Rock fall protection Measures in Vaitarna Hydro Electric Power Project Premises ,Tal- Igatpuri , Dist-Nashik. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Work of construction of Bituminous approach road to Portal Switchyard at Vaitarna HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Work of construction of Gabion wall structure on down stream of nallah near Tunnel at Vaitarna HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC(F Y 2026-27) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Comprehensive work of redesign,manufacture, supply erection, testing & commissioning of Digital Governing, Protection and control system Consisting of SCADA on single point responsibility at 60 MW Vaitarna HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Comprehensive work of Replacement, Modification,upgradation of cooling water system along with replacement of pipeline,pumps,panel etc at 60 MW Vaitarna HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Design, Manufacture, Supply, Erection, Testing and commissioning of 1000 KVA UAT & EAT at 60MW Vaitarna HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, Erection, Testing & Commissioning of 500 KVA DG set along with cable and changeover system at 60 MW Vaitarna HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply, erection, testing and commissioning of 132kV Single core 300sqmm copper conductor XLPE insulated Lead sheathed power cable from Portal switchyard to Main switchyard along with fabrication of cable trays and misc. allied works at 60 MW Vaitarna HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Upgradation of Insulation class Yeldari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Design,Supply ,testing ,erection and commissioing of with modification of HT power circuit from 66KV to 132 KV by providing 03 Nos GT of 6.6/132 KV capcity 10 MVA with allied compatible aux. equipments & 01 Aux X`mer 2MVA of 132/11 KV at Yeldari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Design,supply ,testing ,erection and commissioing of Automated Co2 fire extinguishers system including supply of Co2 cylinder banks,detectors accessories and associated work at Yeldari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Design,supply ,testing ,erection and commissioing of UAT capacity 250 KVA ration 6.6KV/415V with ACDB, DCDB , auto change over system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design,supply ,testing ,erection and commissioing of Power cables for GT and control cables at Yeldari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Design,supply ,testing ,erection and commissioing of Power cables for GT and control cables at Yeldari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 6(CIVIL) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Package shade roof change at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | PROCUREMENT OF MOBILE RACKS FOR STORES atGhatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Wall compound Rising of height and Wire fence on wall at package shade at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Wall compound colony UCR at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Colony and office Road asphalting at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Road colony to power house at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC(F Y 2027-28) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 7 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | UPGRADATION OF SFC & DDC PANEL at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | BATTERY CHARGER PROCUREMENT at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | PHASE REVERSAL SWITCH PROCUREMENT at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | PROCUREMENT OF SPARES FOR 220kV GIS at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | PROCUREMENT OF RBDV at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Comprehensive work of Renovation, Modification, Design, Manufacture, Supply, Erection, Testing & Commissioning of new Generator on single point responsibility at 60 MW Vaitarna HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Office Equipment |  | - | 0 | 0.54617 | 0.54617 | 0 | 0.014272 | 0.024272 |  |  | 0.024272 | -0.01
2 | Furniture & Fixtures |  | - | 0 | 0.005756 | 0.005756 | 0 | 0 | 0 |  |  | 0 | 0
3 | Replacement of existing 300AH/220VDC & 200AH/220VDC Battery Set with new Lead acid Tubular Battery Set along with Design, manufacture, supply, installation, commissioning & testing at Yeldari & Paithan HPS |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Vehicle (Fire Tender ) |  | - | 0 | 0 | 0 | 0 | 4.0078 | 4.0078 |  |  | 4.0078 | 0
| Total |  |  |  | 5.0301 | 5.0301 | 0 | 7.7948 | 8.2948 | 0 | 0 | 8.2948 | -0.5
FY 2023-24
a) DPR Schemes
(i) Submitted to MERC
2 | Various schemes of Hydro Power Stations at HPC Pune & HPC Nasik | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.7312 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.6 | Supply, testing, installation and commissioning of Exide make 300 AH 220 V Lead acid stationary Plante type station battery set for Vaitarna HPS | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.2 | 0.19886 | 0.19886 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.7 | Supply, testing, installation and commissioning of Exide make 300 AH 220 V Lead acid stationary Plante type station battery set for Bhatsa HPS | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.2 | 0.19886 | 0.19886 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.3312 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Upgradation of Protection Systems at Ghatghar (2x125MW) and Bhatsa (1x15MW) HPS under HPC Nasik | MERC/CAPEX/20172018/04220 | 2017-09-19 | 15.104 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Up gradation of Protection System &unitrol excitation system at Ghatghar Hydro Power Station. | MERC/CAPEX/20172018/04220 | 2017-09-19 | 9.678 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Part A : upgradation of unitrol excitation system for both units at GHPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Part B : upgradation of Protection system for both units at GHPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.2 | Up gradation of ABB Make Protection System & Automatic Voltage Regulator, Relay Based Unit & Auxiliary control for Bhatsa Hydro Power Station(1 X 15MW). | MERC/CAPEX/20172018/04220 | 2017-09-19 | 5.426 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Protection system Part A:- Restoration and up-gradation of electromechanical and static relays with numerical relays along with installation, testing, commissioning, and misc. allied works | 0 | - | 0 | 0 | 0 | 0 | 0 | 0.45666 |  |  | 0.45666 | -0.45666
0 | Protection system Part B:- Procure of redundant & spare Numerical relays for Generator and G T Protection system. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | C- Supply erection, testing and Commissioning and supervision of dismantling and erection of static excitation system and control system along with field instrumentation at Bhatsa HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Various Civil schemes for Modernisations of colonies at Various Locations under Nasik HPC | MERC/CAPEX/20162017/04757 | 2017-11-22 | 14.5667 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Part A: Refurbishment of quarters in colony, administartive buidings club building, guest house at various HPS under Nashik HPS | MERC/CAPEX/20162017/04757 | 2017-11-22 | 3.7364 | 3.5106 | 4.0006 | -0.49 | 0.13142 | 0.25044 |  |  | 0.25044 | -0.60901 | 0 | 0.25044
9.2 | Part B: Providing and laying water supply lines within colony and power house area at various HPS under Nashik HPS | MERC/CAPEX/20162017/04757 | 2017-11-22 | 0.50088 | 0.11901 | 0.11901 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.3 | Part C: Construction of compund wall/chainlink fencing around colony and power house area at various HPS under Nashik HPS. | MERC/CAPEX/20162017/04757 | 2017-11-22 | 0.74833 | 0.17 | 0.17 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.4 | Part D: Providing & relaying of existing internal roads within colony area and approach roads to power house & construction of storm water gutter along road at various HPS under HPC Nashik | MERC/CAPEX/20162017/04757 | 2017-11-22 | 9.5811 | 4.0537 | 4.0537 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Upgradation of existing PLC system to latest symphony plus SCADA & DCS system of Ghatghar HPS (2x125 MW) under HPS Nasik | MERC/CAPEX/20172018/0198 | 2018-02-06 | 13.345 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Upgradation of existing PLC system to latest symphony plus SCADA & DCS system of Ghatghar HPS (2x125 MW) under HPS Nasik | MERC/CAPEX/20172018/0198 | 2018-02-06 | 13.345 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 8.913 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.102 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Schme-F: Replacement of 220V / 300AH Float cum boost charger with integrated DCDB for Bhatsa Hydro Power Stn. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.173 | 0 | 0 | 0 | 0.11446 | 0.11446 |  |  | 0.11446 | 0 | 0.11446 | 0
14.3 | Schme-G: Replacement of 220V / 300AH Float cum boost charger with integrated DCDB for Surya Hydro Power Stn. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.173 | 0 | 0 | 0 | 0.11446 | 0.11446 |  |  | 0.11446 | 0 | 0.11446 | 0
14.4 | Schme-H: Supply 24 point Chartless recorder for Bhatsa HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.059 | 0 | 0 | 0 | 0.020245 | 0.020245 |  |  | 0.020245 | 0 | 0.020245 | 0
14.5 | Schme-I: Supply Erection, testing & commissioning of Digital governing system for 06MW Surya HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1.954 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.6 | Schme-J: Supply, Erection, testing & commissioning of Digital governing system and Hydraulic oil pressure unit for 15 MW Bhatsa HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 2.027 | 0 | 0 | 0 | 2.0503 | 1.5936 |  |  | 1.5936 | 0.45666 | 1.5936 | 0
14.7 | Schme-K: Supply, Retrofitting, up gradation, Commissioning of Generator protection system at Paithan HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.87 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.8 | Schme-L: Replacement of existing compressor with new compressor (1 Nos.) at Paithan HPS | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.467 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.9 | Schme-M: Retrofitting, up gradation & Commissioning of Protection System for Generator, Transformer and Line at Surya Hydro Power Station | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.691 | 0 | 0 | 0 | 0.69731 | 0.68499 |  |  | 0.68499 | 0.012319 | 0.68499 | 0
14.1 | Schme-N: Procurement of Static excitation system at Surya Hydro Power Station. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1.547 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Yet to be approved by MERC (F Y 2024-25) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Post-facto DPR for “Urgent restoration and Life Enhancement of Unit-1, 125MW M/s Fuji make Hydro Generator for prolonged efficient operation at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Dismantling and assembly of Unit-2 stator and other allied works at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Urgent restoration and Life Enhancement of Unit-2, 125MW M/s Fuji make Hydro Generator for prolonged efficient operation at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Work of unit 2 stator core top lamination replacement work of GHPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC(F Y 2025-26) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement & commissioning of Battery bank, 55 cells of 2V 2035AH YHP39 Exide make at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Complete refurbishment of Stator frame , core & winding of 01 No generator stator at Ghatghar HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Generator Circuit breaker Electrical OH at Ghatghar HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Water filter treatment plant and pipeline at Ghatghar HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Design,supply,errection,testing & commissioning of digital governing system at Paithan HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Design,Supply ,testing ,erection and commissioing of DAVR system at Paithan HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Design,supply,testing ,erection and commissioing of DCS control system at Paithan HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Design,supply ,testing ,erection and commissioing of Automated Co2 fire extinguishers system at Paithan HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design,Supply ,testing ,erection and commissioing of Numerical protection system at Yeldari HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Design,Supply ,testing ,erection and commissioing of C&I control & measurement with SCADA at Yeldari HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Design,Supply ,testing ,erection and commissioing of DAVR system at Yeldari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Design,supply,errection,testing & commissioning of digital governing system at Yeldari HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 3 (CIVIL) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Fortification and Rock fall protection Measures in Vaitarna Hydro Electric Power Project Premises ,Tal- Igatpuri , Dist-Nashik. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Work of construction of Bituminous approach road to Portal Switchyard at Vaitarna HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Work of construction of Gabion wall structure on down stream of nallah near Tunnel at Vaitarna HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC(F Y 2026-27) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Comprehensive work of redesign,manufacture, supply erection, testing & commissioning of Digital Governing, Protection and control system Consisting of SCADA on single point responsibility at 60 MW Vaitarna HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Comprehensive work of Replacement, Modification,upgradation of cooling water system along with replacement of pipeline,pumps,panel etc at 60 MW Vaitarna HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Design, Manufacture, Supply, Erection, Testing and commissioning of 1000 KVA UAT & EAT at 60MW Vaitarna HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, Erection, Testing & Commissioning of 500 KVA DG set along with cable and changeover system at 60 MW Vaitarna HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply, erection, testing and commissioning of 132kV Single core 300sqmm copper conductor XLPE insulated Lead sheathed power cable from Portal switchyard to Main switchyard along with fabrication of cable trays and misc. allied works at 60 MW Vaitarna HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Upgradation of Insulation class Yeldari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Design,Supply ,testing ,erection and commissioing of with modification of HT power circuit from 66KV to 132 KV by providing 03 Nos GT of 6.6/132 KV capcity 10 MVA with allied compatible aux. equipments & 01 Aux X`mer 2MVA of 132/11 KV at Yeldari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Design,supply ,testing ,erection and commissioing of Automated Co2 fire extinguishers system including supply of Co2 cylinder banks,detectors accessories and associated work at Yeldari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Design,supply ,testing ,erection and commissioing of UAT capacity 250 KVA ration 6.6KV/415V with ACDB, DCDB , auto change over system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design,supply ,testing ,erection and commissioing of Power cables for GT and control cables at Yeldari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Design,supply ,testing ,erection and commissioing of Power cables for GT and control cables at Yeldari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 6(CIVIL) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Package shade roof change at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | PROCUREMENT OF MOBILE RACKS FOR STORES atGhatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Wall compound Rising of height and Wire fence on wall at package shade at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Wall compound colony UCR at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Colony and office Road asphalting at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Road colony to power house at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC(F Y 2027-28) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 7 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | UPGRADATION OF SFC & DDC PANEL at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | BATTERY CHARGER PROCUREMENT at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | PHASE REVERSAL SWITCH PROCUREMENT at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | PROCUREMENT OF SPARES FOR 220kV GIS at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | PROCUREMENT OF RBDV at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Comprehensive work of Renovation, Modification, Design, Manufacture, Supply, Erection, Testing & Commissioning of new Generator on single point responsibility at 60 MW Vaitarna HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Office Equipment | 0 | - | 0 | 0.56044 | 0.57044 | -0.01 | 0.10329 | 0.13 |  |  | 0.13 | -0.036705
2 | Furniture & Fixtures | 0 | - | 0 | 0.005756 | 0.005756 | 0 | 0.029992 | 0.029992 |  |  | 0.029992 | 0
3 | Replacement of existing 300AH/220VDC & 200AH/220VDC Battery Set with new Lead acid Tubular Battery Set along with Design, manufacture, supply, installation, commissioning & testing at Yeldari & Paithan HPS | 0 | - | 0 | 0 | 0 | 0 | 0.2283 | 0.2283 |  |  | 0.2283 | 0
4 | Vehicle (Fire Tender ) | 0 | - | 0 | 4.0078 | 4.0078 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 12.825 | 13.325 | -0.5 | 3.4898 | 3.6232 | 0 | 0 | 3.6232 | -0.6334
FY 2024-25
a) DPR Schemes
(i) Submitted to MERC
2 | Various schemes of Hydro Power Stations at HPC Pune & HPC Nasik | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.7312 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.6 | Supply, testing, installation and commissioning of Exide make 300 AH 220 V Lead acid stationary Plante type station battery set for Vaitarna HPS | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.2 | 0.19886 | 0.19886 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.7 | Supply, testing, installation and commissioning of Exide make 300 AH 220 V Lead acid stationary Plante type station battery set for Bhatsa HPS | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.2 | 0.19886 | 0.19886 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.3312 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Upgradation of Protection Systems at Ghatghar (2x125MW) and Bhatsa (1x15MW) HPS under HPC Nasik | MERC/CAPEX/20172018/04220 | 2017-09-19 | 15.104 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Up gradation of Protection System &unitrol excitation system at Ghatghar Hydro Power Station. | MERC/CAPEX/20172018/04220 | 2017-09-19 | 9.678 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Part A : upgradation of unitrol excitation system for both units at GHPS | 0 | - | 0 | 0 | 0 | 0 | 3.419 | 3.419 |  |  | 3.419 | 0
0 | Part B : upgradation of Protection system for both units at GHPS | 0 | - | 0 | 0 | 0 | 0 | 2.9146 | 2.9146 |  |  | 2.9146 | 0
6.2 | Up gradation of ABB Make Protection System & Automatic Voltage Regulator, Relay Based Unit & Auxiliary control for Bhatsa Hydro Power Station(1 X 15MW). | MERC/CAPEX/20172018/04220 | 2017-09-19 | 5.426 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Protection system Part A:- Restoration and up-gradation of electromechanical and static relays with numerical relays along with installation, testing, commissioning, and misc. allied works | 0 | - | 0 | 0 | 0.45666 | -0.45666 | 0 | 0 |  |  | 0 | -0.45666
0 | Protection system Part B:- Procure of redundant & spare Numerical relays for Generator and G T Protection system. | 0 | - | 0 | 0 | 0 | 0 | 0.65 | 0.65 |  |  | 0.65 | 0
0 | C- Supply erection, testing and Commissioning and supervision of dismantling and erection of static excitation system and control system along with field instrumentation at Bhatsa HPS | 0 | - | 0 | 0 | 0 | 0 | 3.8232 | 3.8232 |  |  | 3.8232 | 0
9 | Various Civil schemes for Modernisations of colonies at Various Locations under Nasik HPC | MERC/CAPEX/20162017/04757 | 2017-11-22 | 14.5667 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Part A: Refurbishment of quarters in colony, administartive buidings club building, guest house at various HPS under Nashik HPS | MERC/CAPEX/20162017/04757 | 2017-11-22 | 3.7364 | 3.642 | 4.251 | -0.60901 | 0 | 0 |  |  | 0 | -0.60901 | 0 | 0
9.2 | Part B: Providing and laying water supply lines within colony and power house area at various HPS under Nashik HPS | MERC/CAPEX/20162017/04757 | 2017-11-22 | 0.50088 | 0.11901 | 0.11901 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.3 | Part C: Construction of compund wall/chainlink fencing around colony and power house area at various HPS under Nashik HPS. | MERC/CAPEX/20162017/04757 | 2017-11-22 | 0.74833 | 0.17 | 0.17 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.4 | Part D: Providing & relaying of existing internal roads within colony area and approach roads to power house & construction of storm water gutter along road at various HPS under HPC Nashik | MERC/CAPEX/20162017/04757 | 2017-11-22 | 9.5811 | 4.0537 | 4.0537 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Upgradation of existing PLC system to latest symphony plus SCADA & DCS system of Ghatghar HPS (2x125 MW) under HPS Nasik | MERC/CAPEX/20172018/0198 | 2018-02-06 | 13.345 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Upgradation of existing PLC system to latest symphony plus SCADA & DCS system of Ghatghar HPS (2x125 MW) under HPS Nasik | MERC/CAPEX/20172018/0198 | 2018-02-06 | 13.345 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 8.913 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.102 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Schme-F: Replacement of 220V / 300AH Float cum boost charger with integrated DCDB for Bhatsa Hydro Power Stn. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.173 | 0.11446 | 0.11446 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Schme-G: Replacement of 220V / 300AH Float cum boost charger with integrated DCDB for Surya Hydro Power Stn. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.173 | 0.11446 | 0.11446 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.4 | Schme-H: Supply 24 point Chartless recorder for Bhatsa HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.059 | 0.020245 | 0.020245 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.5 | Schme-I: Supply Erection, testing & commissioning of Digital governing system for 06MW Surya HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1.954 | 0 | 0 | 0 | 1.954 | 1.954 |  |  | 1.954 | 0 | 1.954 | 0
14.6 | Schme-J: Supply, Erection, testing & commissioning of Digital governing system and Hydraulic oil pressure unit for 15 MW Bhatsa HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 2.027 | 2.0503 | 1.5936 | 0.45666 | 0 | 0 |  |  | 0 | 0.45666 | 0 | 0
14.7 | Schme-K: Supply, Retrofitting, up gradation, Commissioning of Generator protection system at Paithan HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.87 | 0 | 0 | 0 | 0.87 | 0.87 |  |  | 0.87 | 0 | 0.87 | 0
14.8 | Schme-L: Replacement of existing compressor with new compressor (1 Nos.) at Paithan HPS | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.467 | 0 | 0 | 0 | 0.467 | 0.467 |  |  | 0.467 | 0 | 0.467 | 0
14.9 | Schme-M: Retrofitting, up gradation & Commissioning of Protection System for Generator, Transformer and Line at Surya Hydro Power Station | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.691 | 0.69731 | 0.68499 | 0.012319 | 0 | 0 |  |  | 0 | 0.012319 | 0 | 0
14.1 | Schme-N: Procurement of Static excitation system at Surya Hydro Power Station. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1.547 | 0 | 0 | 0 | 1.547 | 1.547 |  |  | 1.547 | 0 | 1.547 | 0
0 | IDC | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Yet to be approved by MERC (F Y 2024-25) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Post-facto DPR for “Urgent restoration and Life Enhancement of Unit-1, 125MW M/s Fuji make Hydro Generator for prolonged efficient operation at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 14.34 | 14.34 |  |  | 14.34 | 0
2 | Dismantling and assembly of Unit-2 stator and other allied works at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0.92 | 0.92 |  |  | 0.92 | 0
3 | Urgent restoration and Life Enhancement of Unit-2, 125MW M/s Fuji make Hydro Generator for prolonged efficient operation at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 12.69 | 12.69 |  |  | 12.69 | 0
4 | Work of unit 2 stator core top lamination replacement work of GHPS | 0 | - | 0 | 0 | 0 | 0 | 1.57 | 1.57 |  |  | 1.57 | 0
0 | (ii) Yet to be submitted to MERC(F Y 2025-26) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement & commissioning of Battery bank, 55 cells of 2V 2035AH YHP39 Exide make at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Complete refurbishment of Stator frame , core & winding of 01 No generator stator at Ghatghar HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Generator Circuit breaker Electrical OH at Ghatghar HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Water filter treatment plant and pipeline at Ghatghar HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Design,supply,errection,testing & commissioning of digital governing system at Paithan HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Design,Supply ,testing ,erection and commissioing of DAVR system at Paithan HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Design,supply,testing ,erection and commissioing of DCS control system at Paithan HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Design,supply ,testing ,erection and commissioing of Automated Co2 fire extinguishers system at Paithan HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design,Supply ,testing ,erection and commissioing of Numerical protection system at Yeldari HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Design,Supply ,testing ,erection and commissioing of C&I control & measurement with SCADA at Yeldari HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Design,Supply ,testing ,erection and commissioing of DAVR system at Yeldari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Design,supply,errection,testing & commissioning of digital governing system at Yeldari HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 3 (CIVIL) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Fortification and Rock fall protection Measures in Vaitarna Hydro Electric Power Project Premises ,Tal- Igatpuri , Dist-Nashik. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Work of construction of Bituminous approach road to Portal Switchyard at Vaitarna HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Work of construction of Gabion wall structure on down stream of nallah near Tunnel at Vaitarna HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC(F Y 2026-27) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Comprehensive work of redesign,manufacture, supply erection, testing & commissioning of Digital Governing, Protection and control system Consisting of SCADA on single point responsibility at 60 MW Vaitarna HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Comprehensive work of Replacement, Modification,upgradation of cooling water system along with replacement of pipeline,pumps,panel etc at 60 MW Vaitarna HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Design, Manufacture, Supply, Erection, Testing and commissioning of 1000 KVA UAT & EAT at 60MW Vaitarna HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, Erection, Testing & Commissioning of 500 KVA DG set along with cable and changeover system at 60 MW Vaitarna HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply, erection, testing and commissioning of 132kV Single core 300sqmm copper conductor XLPE insulated Lead sheathed power cable from Portal switchyard to Main switchyard along with fabrication of cable trays and misc. allied works at 60 MW Vaitarna HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Upgradation of Insulation class Yeldari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Design,Supply ,testing ,erection and commissioing of with modification of HT power circuit from 66KV to 132 KV by providing 03 Nos GT of 6.6/132 KV capcity 10 MVA with allied compatible aux. equipments & 01 Aux X`mer 2MVA of 132/11 KV at Yeldari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Design,supply ,testing ,erection and commissioing of Automated Co2 fire extinguishers system including supply of Co2 cylinder banks,detectors accessories and associated work at Yeldari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Design,supply ,testing ,erection and commissioing of UAT capacity 250 KVA ration 6.6KV/415V with ACDB, DCDB , auto change over system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design,supply ,testing ,erection and commissioing of Power cables for GT and control cables at Yeldari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Design,supply ,testing ,erection and commissioing of Power cables for GT and control cables at Yeldari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 6(CIVIL) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Package shade roof change at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | PROCUREMENT OF MOBILE RACKS FOR STORES atGhatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Wall compound Rising of height and Wire fence on wall at package shade at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Wall compound colony UCR at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Colony and office Road asphalting at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Road colony to power house at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC(F Y 2027-28) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 7 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | UPGRADATION OF SFC & DDC PANEL at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | BATTERY CHARGER PROCUREMENT at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | PHASE REVERSAL SWITCH PROCUREMENT at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | PROCUREMENT OF SPARES FOR 220kV GIS at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | PROCUREMENT OF RBDV at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Comprehensive work of Renovation, Modification, Design, Manufacture, Supply, Erection, Testing & Commissioning of new Generator on single point responsibility at 60 MW Vaitarna HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Office Equipment | 0 | - | 0 | 0.66374 | 0.70044 | -0.036705 | 0 | 0 |  |  | 0 | -0.036705
2 | Furniture & Fixtures | 0 | - | 0 | 0.035748 | 0.035748 | 0 | 0 | 0 |  |  | 0 | 0
3 | Replacement of existing 300AH/220VDC & 200AH/220VDC Battery Set with new Lead acid Tubular Battery Set along with Design, manufacture, supply, installation, commissioning & testing at Yeldari & Paithan HPS | 0 | - | 0 | 0.2283 | 0.2283 | 0 | 0 | 0 |  |  | 0 | 0
4 | Vehicle (Fire Tender ) | 0 | - | 0 | 4.0078 | 4.0078 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 16.3148 | 16.9482 | -0.6334 | 45.1649 | 45.1649 | 0 | 0 | 45.1649 | -0.6334
FY 2025-26
a) DPR Schemes
(i) Submitted to MERC
2 | Various schemes of Hydro Power Stations at HPC Pune & HPC Nasik | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.7312 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.6 | Supply, testing, installation and commissioning of Exide make 300 AH 220 V Lead acid stationary Plante type station battery set for Vaitarna HPS | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.2 | 0.19886 | 0.19886 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.7 | Supply, testing, installation and commissioning of Exide make 300 AH 220 V Lead acid stationary Plante type station battery set for Bhatsa HPS | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.2 | 0.19886 | 0.19886 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.3312 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Upgradation of Protection Systems at Ghatghar (2x125MW) and Bhatsa (1x15MW) HPS under HPC Nasik | MERC/CAPEX/20172018/04220 | 2017-09-19 | 15.104 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Up gradation of Protection System &unitrol excitation system at Ghatghar Hydro Power Station. | MERC/CAPEX/20172018/04220 | 2017-09-19 | 9.678 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Part A : upgradation of unitrol excitation system for both units at GHPS | 0 | - | 0 | 3.419 | 3.419 | 0 | 0 | 0 |  |  | 0 | 0
0 | Part B : upgradation of Protection system for both units at GHPS | 0 | - | 0 | 2.9146 | 2.9146 | 0 | 0 | 0 |  |  | 0 | 0
6.2 | Up gradation of ABB Make Protection System & Automatic Voltage Regulator, Relay Based Unit & Auxiliary control for Bhatsa Hydro Power Station(1 X 15MW). | MERC/CAPEX/20172018/04220 | 2017-09-19 | 5.426 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Protection system Part A:- Restoration and up-gradation of electromechanical and static relays with numerical relays along with installation, testing, commissioning, and misc. allied works | 0 | - | 0 | 0 | 0.45666 | -0.45666 | 0 | 0 |  |  | 0 | -0.45666
0 | Protection system Part B:- Procure of redundant & spare Numerical relays for Generator and G T Protection system. | 0 | - | 0 | 0.65 | 0.65 | 0 | 0 | 0 |  |  | 0 | 0
0 | C- Supply erection, testing and Commissioning and supervision of dismantling and erection of static excitation system and control system along with field instrumentation at Bhatsa HPS | 0 | - | 0 | 3.8232 | 3.8232 | 0 | 0 | 0 |  |  | 0 | 0
9 | Various Civil schemes for Modernisations of colonies at Various Locations under Nasik HPC | MERC/CAPEX/20162017/04757 | 2017-11-22 | 14.5667 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Part A: Refurbishment of quarters in colony, administartive buidings club building, guest house at various HPS under Nashik HPS | MERC/CAPEX/20162017/04757 | 2017-11-22 | 3.7364 | 3.642 | 4.251 | -0.60901 | 0 | 0 |  |  | 0 | -0.60901 | 0 | 0
9.2 | Part B: Providing and laying water supply lines within colony and power house area at various HPS under Nashik HPS | MERC/CAPEX/20162017/04757 | 2017-11-22 | 0.50088 | 0.11901 | 0.11901 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.3 | Part C: Construction of compund wall/chainlink fencing around colony and power house area at various HPS under Nashik HPS. | MERC/CAPEX/20162017/04757 | 2017-11-22 | 0.74833 | 0.17 | 0.17 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.4 | Part D: Providing & relaying of existing internal roads within colony area and approach roads to power house & construction of storm water gutter along road at various HPS under HPC Nashik | MERC/CAPEX/20162017/04757 | 2017-11-22 | 9.5811 | 4.0537 | 4.0537 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Upgradation of existing PLC system to latest symphony plus SCADA & DCS system of Ghatghar HPS (2x125 MW) under HPS Nasik | MERC/CAPEX/20172018/0198 | 2018-02-06 | 13.345 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Upgradation of existing PLC system to latest symphony plus SCADA & DCS system of Ghatghar HPS (2x125 MW) under HPS Nasik | MERC/CAPEX/20172018/0198 | 2018-02-06 | 13.345 | 0 | 0 | 0 | 14.5503 | 14.5503 |  |  | 14.5503 | 0 | 13.345 | 1.2052
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 8.913 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.102 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Schme-F: Replacement of 220V / 300AH Float cum boost charger with integrated DCDB for Bhatsa Hydro Power Stn. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.173 | 0.11446 | 0.11446 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Schme-G: Replacement of 220V / 300AH Float cum boost charger with integrated DCDB for Surya Hydro Power Stn. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.173 | 0.11446 | 0.11446 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.4 | Schme-H: Supply 24 point Chartless recorder for Bhatsa HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.059 | 0.020245 | 0.020245 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.5 | Schme-I: Supply Erection, testing & commissioning of Digital governing system for 06MW Surya HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1.954 | 1.954 | 1.954 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.6 | Schme-J: Supply, Erection, testing & commissioning of Digital governing system and Hydraulic oil pressure unit for 15 MW Bhatsa HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 2.027 | 2.0503 | 1.5936 | 0.45666 | 0 | 0 |  |  | 0 | 0.45666 | 0 | 0
14.7 | Schme-K: Supply, Retrofitting, up gradation, Commissioning of Generator protection system at Paithan HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.87 | 0.87 | 0.87 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.8 | Schme-L: Replacement of existing compressor with new compressor (1 Nos.) at Paithan HPS | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.467 | 0.467 | 0.467 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.9 | Schme-M: Retrofitting, up gradation & Commissioning of Protection System for Generator, Transformer and Line at Surya Hydro Power Station | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.691 | 0.69731 | 0.68499 | 0.012319 | 0 | 0 |  |  | 0 | 0.012319 | 0 | 0
14.1 | Schme-N: Procurement of Static excitation system at Surya Hydro Power Station. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1.547 | 1.547 | 1.547 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Yet to be approved by MERC (F Y 2024-25) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Post-facto DPR for “Urgent restoration and Life Enhancement of Unit-1, 125MW M/s Fuji make Hydro Generator for prolonged efficient operation at Ghatghar HPS | 0 | - | 0 | 14.34 | 14.34 | 0 | 0 | 0 |  |  | 0 | 0
2 | Dismantling and assembly of Unit-2 stator and other allied works at Ghatghar HPS | 0 | - | 0 | 0.92 | 0.92 | 0 | 0 | 0 |  |  | 0 | 0
3 | Urgent restoration and Life Enhancement of Unit-2, 125MW M/s Fuji make Hydro Generator for prolonged efficient operation at Ghatghar HPS | 0 | - | 0 | 12.69 | 12.69 | 0 | 0 | 0 |  |  | 0 | 0
4 | Work of unit 2 stator core top lamination replacement work of GHPS | 0 | - | 0 | 1.57 | 1.57 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC(F Y 2025-26) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement & commissioning of Battery bank, 55 cells of 2V 2035AH YHP39 Exide make at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 1.25 | 1.25 |  |  | 1.25 | 0
2 | Complete refurbishment of Stator frame , core & winding of 01 No generator stator at Ghatghar HPS. | 0 | - | 0 | 0 | 0 | 0 | 23.9 | 23.9 |  |  | 23.9 | 0
3 | Generator Circuit breaker Electrical OH at Ghatghar HPS. | 0 | - | 0 | 0 | 0 | 0 | 7.2 | 7.2 |  |  | 7.2 | 0
4 | Water filter treatment plant and pipeline at Ghatghar HPS. | 0 | - | 0 | 0 | 0 | 0 | 1.25 | 1.25 |  |  | 1.25 | 0
0 | DPR 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Design,supply,errection,testing & commissioning of digital governing system at Paithan HPS. | 0 | - | 0 | 0 | 0 | 0 | 4.5 | 4.5 |  |  | 4.5 | 0
2 | Design,Supply ,testing ,erection and commissioing of DAVR system at Paithan HPS. | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
3 | Design,supply,testing ,erection and commissioing of DCS control system at Paithan HPS. | 0 | - | 0 | 0 | 0 | 0 | 1.7 | 1.7 |  |  | 1.7 | 0
4 | Design,supply ,testing ,erection and commissioing of Automated Co2 fire extinguishers system at Paithan HPS. | 0 | - | 0 | 0 | 0 | 0 | 0.35 | 0.35 |  |  | 0.35 | 0
5 | Design,Supply ,testing ,erection and commissioing of Numerical protection system at Yeldari HPS. | 0 | - | 0 | 0 | 0 | 0 | 2.55 | 2.55 |  |  | 2.55 | 0
6 | Design,Supply ,testing ,erection and commissioing of C&I control & measurement with SCADA at Yeldari HPS. | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
7 | Design,Supply ,testing ,erection and commissioing of DAVR system at Yeldari HPS | 0 | - | 0 | 0 | 0 | 0 | 6 | 6 |  |  | 6 | 0
8 | Design,supply,errection,testing & commissioning of digital governing system at Yeldari HPS. | 0 | - | 0 | 0 | 0 | 0 | 7 | 7 |  |  | 7 | 0
0 | DPR 3 (CIVIL) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Fortification and Rock fall protection Measures in Vaitarna Hydro Electric Power Project Premises ,Tal- Igatpuri , Dist-Nashik. | 0 | - | 0 | 0 | 0 | 0 | 36.53 | 36.53 |  |  | 36.53 | 0
2 | Work of construction of Bituminous approach road to Portal Switchyard at Vaitarna HPS. | 0 | - | 0 | 0 | 0 | 0 | 2.77 | 2.77 |  |  | 2.77 | 0
3 | Work of construction of Gabion wall structure on down stream of nallah near Tunnel at Vaitarna HPS. | 0 | - | 0 | 0 | 0 | 0 | 0.26 | 0.26 |  |  | 0.26 | 0
0 | (ii) Yet to be submitted to MERC(F Y 2026-27) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Comprehensive work of redesign,manufacture, supply erection, testing & commissioning of Digital Governing, Protection and control system Consisting of SCADA on single point responsibility at 60 MW Vaitarna HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Comprehensive work of Replacement, Modification,upgradation of cooling water system along with replacement of pipeline,pumps,panel etc at 60 MW Vaitarna HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Design, Manufacture, Supply, Erection, Testing and commissioning of 1000 KVA UAT & EAT at 60MW Vaitarna HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, Erection, Testing & Commissioning of 500 KVA DG set along with cable and changeover system at 60 MW Vaitarna HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply, erection, testing and commissioning of 132kV Single core 300sqmm copper conductor XLPE insulated Lead sheathed power cable from Portal switchyard to Main switchyard along with fabrication of cable trays and misc. allied works at 60 MW Vaitarna HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Upgradation of Insulation class Yeldari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Design,Supply ,testing ,erection and commissioing of with modification of HT power circuit from 66KV to 132 KV by providing 03 Nos GT of 6.6/132 KV capcity 10 MVA with allied compatible aux. equipments & 01 Aux X`mer 2MVA of 132/11 KV at Yeldari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Design,supply ,testing ,erection and commissioing of Automated Co2 fire extinguishers system including supply of Co2 cylinder banks,detectors accessories and associated work at Yeldari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Design,supply ,testing ,erection and commissioing of UAT capacity 250 KVA ration 6.6KV/415V with ACDB, DCDB , auto change over system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design,supply ,testing ,erection and commissioing of Power cables for GT and control cables at Yeldari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Design,supply ,testing ,erection and commissioing of Power cables for GT and control cables at Yeldari HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 6(CIVIL) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Package shade roof change at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | PROCUREMENT OF MOBILE RACKS FOR STORES atGhatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Wall compound Rising of height and Wire fence on wall at package shade at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Wall compound colony UCR at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Colony and office Road asphalting at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Road colony to power house at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC(F Y 2027-28) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 7 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | UPGRADATION OF SFC & DDC PANEL at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | BATTERY CHARGER PROCUREMENT at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | PHASE REVERSAL SWITCH PROCUREMENT at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | PROCUREMENT OF SPARES FOR 220kV GIS at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | PROCUREMENT OF RBDV at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Comprehensive work of Renovation, Modification, Design, Manufacture, Supply, Erection, Testing & Commissioning of new Generator on single point responsibility at 60 MW Vaitarna HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Office Equipment | 0 | - | 0 | 0.66374 | 0.70044 | -0.036705 | 0 | 0 |  |  | 0 | -0.036705
2 | Furniture & Fixtures | 0 | - | 0 | 0.035748 | 0.035748 | 0 | 0 | 0 |  |  | 0 | 0
3 | Replacement of existing 300AH/220VDC & 200AH/220VDC Battery Set with new Lead acid Tubular Battery Set along with Design, manufacture, supply, installation, commissioning & testing at Yeldari & Paithan HPS | 0 | - | 0 | 0.2283 | 0.2283 | 0 | 0 | 0 |  |  | 0 | 0
4 | Vehicle (Fire Tender ) | 0 | - | 0 | 4.0078 | 4.0078 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 61.4796 | 62.113 | -0.6334 | 112.8102 | 112.8102 | 0 | 0 | 112.8102 | -0.6334
FY 2026-27
a) DPR Schemes
(i) Submitted to MERC
2 | Various schemes of Hydro Power Stations at HPC Pune & HPC Nasik | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.7312 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.6 | Supply, testing, installation and commissioning of Exide make 300 AH 220 V Lead acid stationary Plante type station battery set for Vaitarna HPS | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.2 | 0.19886 | 0.19886 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.7 | Supply, testing, installation and commissioning of Exide make 300 AH 220 V Lead acid stationary Plante type station battery set for Bhatsa HPS | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.2 | 0.19886 | 0.19886 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.3312 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Upgradation of Protection Systems at Ghatghar (2x125MW) and Bhatsa (1x15MW) HPS under HPC Nasik | MERC/CAPEX/20172018/04220 | 2017-09-19 | 15.104 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Up gradation of Protection System &unitrol excitation system at Ghatghar Hydro Power Station. | MERC/CAPEX/20172018/04220 | 2017-09-19 | 9.678 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Part A : upgradation of unitrol excitation system for both units at GHPS | 0 | - | 0 | 3.419 | 3.419 | 0 | 0 | 0 |  |  | 0 | 0
0 | Part B : upgradation of Protection system for both units at GHPS | 0 | - | 0 | 2.9146 | 2.9146 | 0 | 0 | 0 |  |  | 0 | 0
6.2 | Up gradation of ABB Make Protection System & Automatic Voltage Regulator, Relay Based Unit & Auxiliary control for Bhatsa Hydro Power Station(1 X 15MW). | MERC/CAPEX/20172018/04220 | 2017-09-19 | 5.426 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Protection system Part A:- Restoration and up-gradation of electromechanical and static relays with numerical relays along with installation, testing, commissioning, and misc. allied works | 0 | - | 0 | 0 | 0.45666 | -0.45666 | 0 | 0 |  |  | 0 | -0.45666
0 | Protection system Part B:- Procure of redundant & spare Numerical relays for Generator and G T Protection system. | 0 | - | 0 | 0.65 | 0.65 | 0 | 0 | 0 |  |  | 0 | 0
0 | C- Supply erection, testing and Commissioning and supervision of dismantling and erection of static excitation system and control system along with field instrumentation at Bhatsa HPS | 0 | - | 0 | 3.8232 | 3.8232 | 0 | 0 | 0 |  |  | 0 | 0
9 | Various Civil schemes for Modernisations of colonies at Various Locations under Nasik HPC | MERC/CAPEX/20162017/04757 | 2017-11-22 | 14.5667 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Part A: Refurbishment of quarters in colony, administartive buidings club building, guest house at various HPS under Nashik HPS | MERC/CAPEX/20162017/04757 | 2017-11-22 | 3.7364 | 3.642 | 4.251 | -0.60901 | 0 | 0 |  |  | 0 | -0.60901 | 0 | 0
9.2 | Part B: Providing and laying water supply lines within colony and power house area at various HPS under Nashik HPS | MERC/CAPEX/20162017/04757 | 2017-11-22 | 0.50088 | 0.11901 | 0.11901 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.3 | Part C: Construction of compund wall/chainlink fencing around colony and power house area at various HPS under Nashik HPS. | MERC/CAPEX/20162017/04757 | 2017-11-22 | 0.74833 | 0.17 | 0.17 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.4 | Part D: Providing & relaying of existing internal roads within colony area and approach roads to power house & construction of storm water gutter along road at various HPS under HPC Nashik | MERC/CAPEX/20162017/04757 | 2017-11-22 | 9.5811 | 4.0537 | 4.0537 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Upgradation of existing PLC system to latest symphony plus SCADA & DCS system of Ghatghar HPS (2x125 MW) under HPS Nasik | MERC/CAPEX/20172018/0198 | 2018-02-06 | 13.345 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Upgradation of existing PLC system to latest symphony plus SCADA & DCS system of Ghatghar HPS (2x125 MW) under HPS Nasik | MERC/CAPEX/20172018/0198 | 2018-02-06 | 13.345 | 14.5503 | 14.5503 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 8.913 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.102 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Schme-F: Replacement of 220V / 300AH Float cum boost charger with integrated DCDB for Bhatsa Hydro Power Stn. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.173 | 0.11446 | 0.11446 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Schme-G: Replacement of 220V / 300AH Float cum boost charger with integrated DCDB for Surya Hydro Power Stn. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.173 | 0.11446 | 0.11446 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.4 | Schme-H: Supply 24 point Chartless recorder for Bhatsa HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.059 | 0.020245 | 0.020245 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.5 | Schme-I: Supply Erection, testing & commissioning of Digital governing system for 06MW Surya HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1.954 | 1.954 | 1.954 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.6 | Schme-J: Supply, Erection, testing & commissioning of Digital governing system and Hydraulic oil pressure unit for 15 MW Bhatsa HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 2.027 | 2.0503 | 1.5936 | 0.45666 | 0 | 0 |  |  | 0 | 0.45666 | 0 | 0
14.7 | Schme-K: Supply, Retrofitting, up gradation, Commissioning of Generator protection system at Paithan HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.87 | 0.87 | 0.87 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.8 | Schme-L: Replacement of existing compressor with new compressor (1 Nos.) at Paithan HPS | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.467 | 0.467 | 0.467 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.9 | Schme-M: Retrofitting, up gradation & Commissioning of Protection System for Generator, Transformer and Line at Surya Hydro Power Station | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.691 | 0.69731 | 0.68499 | 0.012319 | 0 | 0 |  |  | 0 | 0.012319 | 0 | 0
14.1 | Schme-N: Procurement of Static excitation system at Surya Hydro Power Station. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1.547 | 1.547 | 1.547 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Yet to be approved by MERC (F Y 2024-25) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Post-facto DPR for “Urgent restoration and Life Enhancement of Unit-1, 125MW M/s Fuji make Hydro Generator for prolonged efficient operation at Ghatghar HPS | 0 | - | 0 | 14.34 | 14.34 | 0 | 0 | 0 |  |  | 0 | 0
2 | Dismantling and assembly of Unit-2 stator and other allied works at Ghatghar HPS | 0 | - | 0 | 0.92 | 0.92 | 0 | 0 | 0 |  |  | 0 | 0
3 | Urgent restoration and Life Enhancement of Unit-2, 125MW M/s Fuji make Hydro Generator for prolonged efficient operation at Ghatghar HPS | 0 | - | 0 | 12.69 | 12.69 | 0 | 0 | 0 |  |  | 0 | 0
4 | Work of unit 2 stator core top lamination replacement work of GHPS | 0 | - | 0 | 1.57 | 1.57 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC(F Y 2025-26) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement & commissioning of Battery bank, 55 cells of 2V 2035AH YHP39 Exide make at Ghatghar HPS | 0 | - | 0 | 1.25 | 1.25 | 0 | 0 | 0 |  |  | 0 | 0
2 | Complete refurbishment of Stator frame , core & winding of 01 No generator stator at Ghatghar HPS. | 0 | - | 0 | 23.9 | 23.9 | 0 | 0 | 0 |  |  | 0 | 0
3 | Generator Circuit breaker Electrical OH at Ghatghar HPS. | 0 | - | 0 | 7.2 | 7.2 | 0 | 0 | 0 |  |  | 0 | 0
4 | Water filter treatment plant and pipeline at Ghatghar HPS. | 0 | - | 0 | 1.25 | 1.25 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Design,supply,errection,testing & commissioning of digital governing system at Paithan HPS. | 0 | - | 0 | 4.5 | 4.5 | 0 | 0 | 0 |  |  | 0 | 0
2 | Design,Supply ,testing ,erection and commissioing of DAVR system at Paithan HPS. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
3 | Design,supply,testing ,erection and commissioing of DCS control system at Paithan HPS. | 0 | - | 0 | 1.7 | 1.7 | 0 | 0 | 0 |  |  | 0 | 0
4 | Design,supply ,testing ,erection and commissioing of Automated Co2 fire extinguishers system at Paithan HPS. | 0 | - | 0 | 0.35 | 0.35 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design,Supply ,testing ,erection and commissioing of Numerical protection system at Yeldari HPS. | 0 | - | 0 | 2.55 | 2.55 | 0 | 0 | 0 |  |  | 0 | 0
6 | Design,Supply ,testing ,erection and commissioing of C&I control & measurement with SCADA at Yeldari HPS. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
7 | Design,Supply ,testing ,erection and commissioing of DAVR system at Yeldari HPS | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
8 | Design,supply,errection,testing & commissioning of digital governing system at Yeldari HPS. | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 3 (CIVIL) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Fortification and Rock fall protection Measures in Vaitarna Hydro Electric Power Project Premises ,Tal- Igatpuri , Dist-Nashik. | 0 | - | 0 | 36.53 | 36.53 | 0 | 0 | 0 |  |  | 0 | 0
2 | Work of construction of Bituminous approach road to Portal Switchyard at Vaitarna HPS. | 0 | - | 0 | 2.77 | 2.77 | 0 | 0 | 0 |  |  | 0 | 0
3 | Work of construction of Gabion wall structure on down stream of nallah near Tunnel at Vaitarna HPS. | 0 | - | 0 | 0.26 | 0.26 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC(F Y 2026-27) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Comprehensive work of redesign,manufacture, supply erection, testing & commissioning of Digital Governing, Protection and control system Consisting of SCADA on single point responsibility at 60 MW Vaitarna HPS. | 0 | - | 0 | 0 | 0 | 0 | 14 | 14 |  |  | 14 | 0
2 | Comprehensive work of Replacement, Modification,upgradation of cooling water system along with replacement of pipeline,pumps,panel etc at 60 MW Vaitarna HPS. | 0 | - | 0 | 0 | 0 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
3 | Design, Manufacture, Supply, Erection, Testing and commissioning of 1000 KVA UAT & EAT at 60MW Vaitarna HPS. | 0 | - | 0 | 0 | 0 | 0 | 0.6 | 0.6 |  |  | 0.6 | 0
4 | Supply, Erection, Testing & Commissioning of 500 KVA DG set along with cable and changeover system at 60 MW Vaitarna HPS | 0 | - | 0 | 0 | 0 | 0 | 0.6 | 0.6 |  |  | 0.6 | 0
5 | Supply, erection, testing and commissioning of 132kV Single core 300sqmm copper conductor XLPE insulated Lead sheathed power cable from Portal switchyard to Main switchyard along with fabrication of cable trays and misc. allied works at 60 MW Vaitarna HPS | 0 | - | 0 | 0 | 0 | 0 | 11 | 11 |  |  | 11 | 0
0 | DPR 5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Upgradation of Insulation class Yeldari HPS | 0 | - | 0 | 0 | 0 | 0 | 6 | 6 |  |  | 6 | 0
2 | Design,Supply ,testing ,erection and commissioing of with modification of HT power circuit from 66KV to 132 KV by providing 03 Nos GT of 6.6/132 KV capcity 10 MVA with allied compatible aux. equipments & 01 Aux X`mer 2MVA of 132/11 KV at Yeldari HPS | 0 | - | 0 | 0 | 0 | 0 | 10.2 | 10.2 |  |  | 10.2 | 0
3 | Design,supply ,testing ,erection and commissioing of Automated Co2 fire extinguishers system including supply of Co2 cylinder banks,detectors accessories and associated work at Yeldari HPS | 0 | - | 0 | 0 | 0 | 0 | 0.6 | 0.6 |  |  | 0.6 | 0
4 | Design,supply ,testing ,erection and commissioing of UAT capacity 250 KVA ration 6.6KV/415V with ACDB, DCDB , auto change over system | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
5 | Design,supply ,testing ,erection and commissioing of Power cables for GT and control cables at Yeldari HPS | 0 | - | 0 | 0 | 0 | 0 | 3.75 | 3.75 |  |  | 3.75 | 0
6 | Design,supply ,testing ,erection and commissioing of Power cables for GT and control cables at Yeldari HPS | 0 | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
0 | DPR 6(CIVIL) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Package shade roof change at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
2 | PROCUREMENT OF MOBILE RACKS FOR STORES atGhatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0.25 | 0.25 |  |  | 0.25 | 0
3 | Wall compound Rising of height and Wire fence on wall at package shade at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
4 | Wall compound colony UCR at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
5 | Colony and office Road asphalting at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
6 | Road colony to power house at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 7 | 7 |  |  | 7 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC(F Y 2027-28) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 7 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | UPGRADATION OF SFC & DDC PANEL at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | BATTERY CHARGER PROCUREMENT at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | PHASE REVERSAL SWITCH PROCUREMENT at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | PROCUREMENT OF SPARES FOR 220kV GIS at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | PROCUREMENT OF RBDV at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Comprehensive work of Renovation, Modification, Design, Manufacture, Supply, Erection, Testing & Commissioning of new Generator on single point responsibility at 60 MW Vaitarna HPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Office Equipment | 0 | - | 0 | 0.66374 | 0.70044 | -0.036705 | 0 | 0 |  |  | 0 | -0.036705
2 | Furniture & Fixtures | 0 | - | 0 | 0.035748 | 0.035748 | 0 | 0 | 0 |  |  | 0 | 0
3 | Replacement of existing 300AH/220VDC & 200AH/220VDC Battery Set with new Lead acid Tubular Battery Set along with Design, manufacture, supply, installation, commissioning & testing at Yeldari & Paithan HPS | 0 | - | 0 | 0.2283 | 0.2283 | 0 | 0 | 0 |  |  | 0 | 0
4 | Vehicle (Fire Tender ) | 0 | - | 0 | 4.0078 | 4.0078 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 174.2899 | 174.9233 | -0.6334 | 68 | 68 | 0 | 0 | 68 | -0.6334
FY 2027-28
a) DPR Schemes
(i) Submitted to MERC
2 | Various schemes of Hydro Power Stations at HPC Pune & HPC Nasik | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.7312 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.6 | Supply, testing, installation and commissioning of Exide make 300 AH 220 V Lead acid stationary Plante type station battery set for Vaitarna HPS | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.2 | 0.19886 | 0.19886 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.7 | Supply, testing, installation and commissioning of Exide make 300 AH 220 V Lead acid stationary Plante type station battery set for Bhatsa HPS | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.2 | 0.19886 | 0.19886 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.3312 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Upgradation of Protection Systems at Ghatghar (2x125MW) and Bhatsa (1x15MW) HPS under HPC Nasik | MERC/CAPEX/20172018/04220 | 2017-09-19 | 15.104 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Up gradation of Protection System &unitrol excitation system at Ghatghar Hydro Power Station. | MERC/CAPEX/20172018/04220 | 2017-09-19 | 9.678 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Part A : upgradation of unitrol excitation system for both units at GHPS | 0 | - | 0 | 3.419 | 3.419 | 0 | 0 | 0 |  |  | 0 | 0
0 | Part B : upgradation of Protection system for both units at GHPS | 0 | - | 0 | 2.9146 | 2.9146 | 0 | 0 | 0 |  |  | 0 | 0
6.2 | Up gradation of ABB Make Protection System & Automatic Voltage Regulator, Relay Based Unit & Auxiliary control for Bhatsa Hydro Power Station(1 X 15MW). | MERC/CAPEX/20172018/04220 | 2017-09-19 | 5.426 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Protection system Part A:- Restoration and up-gradation of electromechanical and static relays with numerical relays along with installation, testing, commissioning, and misc. allied works | 0 | - | 0 | 0 | 0.45666 | -0.45666 | 0 | 0 |  |  | 0 | -0.45666
0 | Protection system Part B:- Procure of redundant & spare Numerical relays for Generator and G T Protection system. | 0 | - | 0 | 0.65 | 0.65 | 0 | 0 | 0 |  |  | 0 | 0
0 | C- Supply erection, testing and Commissioning and supervision of dismantling and erection of static excitation system and control system along with field instrumentation at Bhatsa HPS | 0 | - | 0 | 3.8232 | 3.8232 | 0 | 0 | 0 |  |  | 0 | 0
9 | Various Civil schemes for Modernisations of colonies at Various Locations under Nasik HPC | MERC/CAPEX/20162017/04757 | 2017-11-22 | 14.5667 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Part A: Refurbishment of quarters in colony, administartive buidings club building, guest house at various HPS under Nashik HPS | MERC/CAPEX/20162017/04757 | 2017-11-22 | 3.7364 | 3.642 | 4.251 | -0.60901 | 0 | 0 |  |  | 0 | -0.60901 | 0 | 0
9.2 | Part B: Providing and laying water supply lines within colony and power house area at various HPS under Nashik HPS | MERC/CAPEX/20162017/04757 | 2017-11-22 | 0.50088 | 0.11901 | 0.11901 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.3 | Part C: Construction of compund wall/chainlink fencing around colony and power house area at various HPS under Nashik HPS. | MERC/CAPEX/20162017/04757 | 2017-11-22 | 0.74833 | 0.17 | 0.17 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.4 | Part D: Providing & relaying of existing internal roads within colony area and approach roads to power house & construction of storm water gutter along road at various HPS under HPC Nashik | MERC/CAPEX/20162017/04757 | 2017-11-22 | 9.5811 | 4.0537 | 4.0537 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Upgradation of existing PLC system to latest symphony plus SCADA & DCS system of Ghatghar HPS (2x125 MW) under HPS Nasik | MERC/CAPEX/20172018/0198 | 2018-02-06 | 13.345 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Upgradation of existing PLC system to latest symphony plus SCADA & DCS system of Ghatghar HPS (2x125 MW) under HPS Nasik | MERC/CAPEX/20172018/0198 | 2018-02-06 | 13.345 | 14.5503 | 14.5503 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 8.913 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.102 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Schme-F: Replacement of 220V / 300AH Float cum boost charger with integrated DCDB for Bhatsa Hydro Power Stn. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.173 | 0.11446 | 0.11446 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Schme-G: Replacement of 220V / 300AH Float cum boost charger with integrated DCDB for Surya Hydro Power Stn. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.173 | 0.11446 | 0.11446 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.4 | Schme-H: Supply 24 point Chartless recorder for Bhatsa HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.059 | 0.020245 | 0.020245 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.5 | Schme-I: Supply Erection, testing & commissioning of Digital governing system for 06MW Surya HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1.954 | 1.954 | 1.954 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.6 | Schme-J: Supply, Erection, testing & commissioning of Digital governing system and Hydraulic oil pressure unit for 15 MW Bhatsa HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 2.027 | 2.0503 | 1.5936 | 0.45666 | 0 | 0 |  |  | 0 | 0.45666 | 0 | 0
14.7 | Schme-K: Supply, Retrofitting, up gradation, Commissioning of Generator protection system at Paithan HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.87 | 0.87 | 0.87 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.8 | Schme-L: Replacement of existing compressor with new compressor (1 Nos.) at Paithan HPS | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.467 | 0.467 | 0.467 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.9 | Schme-M: Retrofitting, up gradation & Commissioning of Protection System for Generator, Transformer and Line at Surya Hydro Power Station | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.691 | 0.69731 | 0.68499 | 0.012319 | 0 | 0 |  |  | 0 | 0.012319 | 0 | 0
14.1 | Schme-N: Procurement of Static excitation system at Surya Hydro Power Station. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1.547 | 1.547 | 1.547 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Yet to be approved by MERC (F Y 2024-25) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Post-facto DPR for “Urgent restoration and Life Enhancement of Unit-1, 125MW M/s Fuji make Hydro Generator for prolonged efficient operation at Ghatghar HPS | 0 | - | 0 | 14.34 | 14.34 | 0 | 0 | 0 |  |  | 0 | 0
2 | Dismantling and assembly of Unit-2 stator and other allied works at Ghatghar HPS | 0 | - | 0 | 0.92 | 0.92 | 0 | 0 | 0 |  |  | 0 | 0
3 | Urgent restoration and Life Enhancement of Unit-2, 125MW M/s Fuji make Hydro Generator for prolonged efficient operation at Ghatghar HPS | 0 | - | 0 | 12.69 | 12.69 | 0 | 0 | 0 |  |  | 0 | 0
4 | Work of unit 2 stator core top lamination replacement work of GHPS | 0 | - | 0 | 1.57 | 1.57 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC(F Y 2025-26) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement & commissioning of Battery bank, 55 cells of 2V 2035AH YHP39 Exide make at Ghatghar HPS | 0 | - | 0 | 1.25 | 1.25 | 0 | 0 | 0 |  |  | 0 | 0
2 | Complete refurbishment of Stator frame , core & winding of 01 No generator stator at Ghatghar HPS. | 0 | - | 0 | 23.9 | 23.9 | 0 | 0 | 0 |  |  | 0 | 0
3 | Generator Circuit breaker Electrical OH at Ghatghar HPS. | 0 | - | 0 | 7.2 | 7.2 | 0 | 0 | 0 |  |  | 0 | 0
4 | Water filter treatment plant and pipeline at Ghatghar HPS. | 0 | - | 0 | 1.25 | 1.25 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Design,supply,errection,testing & commissioning of digital governing system at Paithan HPS. | 0 | - | 0 | 4.5 | 4.5 | 0 | 0 | 0 |  |  | 0 | 0
2 | Design,Supply ,testing ,erection and commissioing of DAVR system at Paithan HPS. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
3 | Design,supply,testing ,erection and commissioing of DCS control system at Paithan HPS. | 0 | - | 0 | 1.7 | 1.7 | 0 | 0 | 0 |  |  | 0 | 0
4 | Design,supply ,testing ,erection and commissioing of Automated Co2 fire extinguishers system at Paithan HPS. | 0 | - | 0 | 0.35 | 0.35 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design,Supply ,testing ,erection and commissioing of Numerical protection system at Yeldari HPS. | 0 | - | 0 | 2.55 | 2.55 | 0 | 0 | 0 |  |  | 0 | 0
6 | Design,Supply ,testing ,erection and commissioing of C&I control & measurement with SCADA at Yeldari HPS. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
7 | Design,Supply ,testing ,erection and commissioing of DAVR system at Yeldari HPS | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
8 | Design,supply,errection,testing & commissioning of digital governing system at Yeldari HPS. | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 3 (CIVIL) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Fortification and Rock fall protection Measures in Vaitarna Hydro Electric Power Project Premises ,Tal- Igatpuri , Dist-Nashik. | 0 | - | 0 | 36.53 | 36.53 | 0 | 0 | 0 |  |  | 0 | 0
2 | Work of construction of Bituminous approach road to Portal Switchyard at Vaitarna HPS. | 0 | - | 0 | 2.77 | 2.77 | 0 | 0 | 0 |  |  | 0 | 0
3 | Work of construction of Gabion wall structure on down stream of nallah near Tunnel at Vaitarna HPS. | 0 | - | 0 | 0.26 | 0.26 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC(F Y 2026-27) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Comprehensive work of redesign,manufacture, supply erection, testing & commissioning of Digital Governing, Protection and control system Consisting of SCADA on single point responsibility at 60 MW Vaitarna HPS. | 0 | - | 0 | 14 | 14 | 0 | 0 | 0 |  |  | 0 | 0
2 | Comprehensive work of Replacement, Modification,upgradation of cooling water system along with replacement of pipeline,pumps,panel etc at 60 MW Vaitarna HPS. | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
3 | Design, Manufacture, Supply, Erection, Testing and commissioning of 1000 KVA UAT & EAT at 60MW Vaitarna HPS. | 0 | - | 0 | 0.6 | 0.6 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, Erection, Testing & Commissioning of 500 KVA DG set along with cable and changeover system at 60 MW Vaitarna HPS | 0 | - | 0 | 0.6 | 0.6 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply, erection, testing and commissioning of 132kV Single core 300sqmm copper conductor XLPE insulated Lead sheathed power cable from Portal switchyard to Main switchyard along with fabrication of cable trays and misc. allied works at 60 MW Vaitarna HPS | 0 | - | 0 | 11 | 11 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Upgradation of Insulation class Yeldari HPS | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
2 | Design,Supply ,testing ,erection and commissioing of with modification of HT power circuit from 66KV to 132 KV by providing 03 Nos GT of 6.6/132 KV capcity 10 MVA with allied compatible aux. equipments & 01 Aux X`mer 2MVA of 132/11 KV at Yeldari HPS | 0 | - | 0 | 10.2 | 10.2 | 0 | 0 | 0 |  |  | 0 | 0
3 | Design,supply ,testing ,erection and commissioing of Automated Co2 fire extinguishers system including supply of Co2 cylinder banks,detectors accessories and associated work at Yeldari HPS | 0 | - | 0 | 0.6 | 0.6 | 0 | 0 | 0 |  |  | 0 | 0
4 | Design,supply ,testing ,erection and commissioing of UAT capacity 250 KVA ration 6.6KV/415V with ACDB, DCDB , auto change over system | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design,supply ,testing ,erection and commissioing of Power cables for GT and control cables at Yeldari HPS | 0 | - | 0 | 3.75 | 3.75 | 0 | 0 | 0 |  |  | 0 | 0
6 | Design,supply ,testing ,erection and commissioing of Power cables for GT and control cables at Yeldari HPS | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 6(CIVIL) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Package shade roof change at Ghatghar HPS | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
2 | PROCUREMENT OF MOBILE RACKS FOR STORES atGhatghar HPS | 0 | - | 0 | 0.25 | 0.25 | 0 | 0 | 0 |  |  | 0 | 0
3 | Wall compound Rising of height and Wire fence on wall at package shade at Ghatghar HPS | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
4 | Wall compound colony UCR at Ghatghar HPS | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
5 | Colony and office Road asphalting at Ghatghar HPS | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
6 | Road colony to power house at Ghatghar HPS | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC(F Y 2027-28) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 7 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | UPGRADATION OF SFC & DDC PANEL at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
2 | BATTERY CHARGER PROCUREMENT at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0.5 | 0.5 |  |  | 0.5 | 0
3 | PHASE REVERSAL SWITCH PROCUREMENT at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 0.5 | 0.5 |  |  | 0.5 | 0
4 | PROCUREMENT OF SPARES FOR 220kV GIS at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 6.5 | 6.5 |  |  | 6.5 | 0
5 | PROCUREMENT OF RBDV at Ghatghar HPS | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Comprehensive work of Renovation, Modification, Design, Manufacture, Supply, Erection, Testing & Commissioning of new Generator on single point responsibility at 60 MW Vaitarna HPS. | 0 | - | 0 | 0 | 0 | 0 | 50 | 50 |  |  | 50 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Office Equipment | 0 | - | 0 | 0.66374 | 0.70044 | -0.036705 | 0 | 0 |  |  | 0 | -0.036705
2 | Furniture & Fixtures | 0 | - | 0 | 0.035748 | 0.035748 | 0 | 0 | 0 |  |  | 0 | 0
3 | Replacement of existing 300AH/220VDC & 200AH/220VDC Battery Set with new Lead acid Tubular Battery Set along with Design, manufacture, supply, installation, commissioning & testing at Yeldari & Paithan HPS | 0 | - | 0 | 0.2283 | 0.2283 | 0 | 0 | 0 |  |  | 0 | 0
4 | Vehicle (Fire Tender ) | 0 | - | 0 | 4.0078 | 4.0078 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 242.2899 | 242.9233 | -0.6334 | 68.5 | 68.5 | 0 | 0 | 68.5 | -0.6334
FY 2028-29
a) DPR Schemes
(i) Submitted to MERC
2 | Various schemes of Hydro Power Stations at HPC Pune & HPC Nasik | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.7312 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.6 | Supply, testing, installation and commissioning of Exide make 300 AH 220 V Lead acid stationary Plante type station battery set for Vaitarna HPS | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.2 | 0.19886 | 0.19886 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.7 | Supply, testing, installation and commissioning of Exide make 300 AH 220 V Lead acid stationary Plante type station battery set for Bhatsa HPS | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.2 | 0.19886 | 0.19886 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 12/CAPEX/20142015/00876 | 2014-08-20 | 0.3312 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Upgradation of Protection Systems at Ghatghar (2x125MW) and Bhatsa (1x15MW) HPS under HPC Nasik | MERC/CAPEX/20172018/04220 | 2017-09-19 | 15.104 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Up gradation of Protection System &unitrol excitation system at Ghatghar Hydro Power Station. | MERC/CAPEX/20172018/04220 | 2017-09-19 | 9.678 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Part A : upgradation of unitrol excitation system for both units at GHPS | 0 | - | 0 | 3.419 | 3.419 | 0 | 0 | 0 |  |  | 0 | 0
0 | Part B : upgradation of Protection system for both units at GHPS | 0 | - | 0 | 2.9146 | 2.9146 | 0 | 0 | 0 |  |  | 0 | 0
6.2 | Up gradation of ABB Make Protection System & Automatic Voltage Regulator, Relay Based Unit & Auxiliary control for Bhatsa Hydro Power Station(1 X 15MW). | MERC/CAPEX/20172018/04220 | 2017-09-19 | 5.426 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Protection system Part A:- Restoration and up-gradation of electromechanical and static relays with numerical relays along with installation, testing, commissioning, and misc. allied works | 0 | - | 0 | 0 | 0.45666 | -0.45666 | 0 | 0 |  |  | 0 | -0.45666
0 | Protection system Part B:- Procure of redundant & spare Numerical relays for Generator and G T Protection system. | 0 | - | 0 | 0.65 | 0.65 | 0 | 0 | 0 |  |  | 0 | 0
0 | C- Supply erection, testing and Commissioning and supervision of dismantling and erection of static excitation system and control system along with field instrumentation at Bhatsa HPS | 0 | - | 0 | 3.8232 | 3.8232 | 0 | 0 | 0 |  |  | 0 | 0
9 | Various Civil schemes for Modernisations of colonies at Various Locations under Nasik HPC | MERC/CAPEX/20162017/04757 | 2017-11-22 | 14.5667 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Part A: Refurbishment of quarters in colony, administartive buidings club building, guest house at various HPS under Nashik HPS | MERC/CAPEX/20162017/04757 | 2017-11-22 | 3.7364 | 3.642 | 4.251 | -0.60901 | 0 | 0 |  |  | 0 | -0.60901 | 0 | 0
9.2 | Part B: Providing and laying water supply lines within colony and power house area at various HPS under Nashik HPS | MERC/CAPEX/20162017/04757 | 2017-11-22 | 0.50088 | 0.11901 | 0.11901 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.3 | Part C: Construction of compund wall/chainlink fencing around colony and power house area at various HPS under Nashik HPS. | MERC/CAPEX/20162017/04757 | 2017-11-22 | 0.74833 | 0.17 | 0.17 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.4 | Part D: Providing & relaying of existing internal roads within colony area and approach roads to power house & construction of storm water gutter along road at various HPS under HPC Nashik | MERC/CAPEX/20162017/04757 | 2017-11-22 | 9.5811 | 4.0537 | 4.0537 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Upgradation of existing PLC system to latest symphony plus SCADA & DCS system of Ghatghar HPS (2x125 MW) under HPS Nasik | MERC/CAPEX/20172018/0198 | 2018-02-06 | 13.345 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Upgradation of existing PLC system to latest symphony plus SCADA & DCS system of Ghatghar HPS (2x125 MW) under HPS Nasik | MERC/CAPEX/20172018/0198 | 2018-02-06 | 13.345 | 14.5503 | 14.5503 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Various 14 Nos. of schemes for Hydro Power Stations under Renewable Energy Circle, Pune & Nasik | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 8.913 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | Schme-C :Replacement of existing Energy meters by 0.2S Class Energy meters at various HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.102 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Schme-F: Replacement of 220V / 300AH Float cum boost charger with integrated DCDB for Bhatsa Hydro Power Stn. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.173 | 0.11446 | 0.11446 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Schme-G: Replacement of 220V / 300AH Float cum boost charger with integrated DCDB for Surya Hydro Power Stn. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.173 | 0.11446 | 0.11446 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.4 | Schme-H: Supply 24 point Chartless recorder for Bhatsa HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.059 | 0.020245 | 0.020245 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.5 | Schme-I: Supply Erection, testing & commissioning of Digital governing system for 06MW Surya HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1.954 | 1.954 | 1.954 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.6 | Schme-J: Supply, Erection, testing & commissioning of Digital governing system and Hydraulic oil pressure unit for 15 MW Bhatsa HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 2.027 | 2.0503 | 1.5936 | 0.45666 | 0 | 0 |  |  | 0 | 0.45666 | 0 | 0
14.7 | Schme-K: Supply, Retrofitting, up gradation, Commissioning of Generator protection system at Paithan HPS. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.87 | 0.87 | 0.87 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.8 | Schme-L: Replacement of existing compressor with new compressor (1 Nos.) at Paithan HPS | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.467 | 0.467 | 0.467 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.9 | Schme-M: Retrofitting, up gradation & Commissioning of Protection System for Generator, Transformer and Line at Surya Hydro Power Station | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.691 | 0.69731 | 0.68499 | 0.012319 | 0 | 0 |  |  | 0 | 0.012319 | 0 | 0
14.1 | Schme-N: Procurement of Static excitation system at Surya Hydro Power Station. | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 1.547 | 1.547 | 1.547 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-21/WFH/SBR/ 19 | 2020-07-17 | 0.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Yet to be approved by MERC (F Y 2024-25) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Post-facto DPR for “Urgent restoration and Life Enhancement of Unit-1, 125MW M/s Fuji make Hydro Generator for prolonged efficient operation at Ghatghar HPS | 0 | - | 0 | 14.34 | 14.34 | 0 | 0 | 0 |  |  | 0 | 0
2 | Dismantling and assembly of Unit-2 stator and other allied works at Ghatghar HPS | 0 | - | 0 | 0.92 | 0.92 | 0 | 0 | 0 |  |  | 0 | 0
3 | Urgent restoration and Life Enhancement of Unit-2, 125MW M/s Fuji make Hydro Generator for prolonged efficient operation at Ghatghar HPS | 0 | - | 0 | 12.69 | 12.69 | 0 | 0 | 0 |  |  | 0 | 0
4 | Work of unit 2 stator core top lamination replacement work of GHPS | 0 | - | 0 | 1.57 | 1.57 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC(F Y 2025-26) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement & commissioning of Battery bank, 55 cells of 2V 2035AH YHP39 Exide make at Ghatghar HPS | 0 | - | 0 | 1.25 | 1.25 | 0 | 0 | 0 |  |  | 0 | 0
2 | Complete refurbishment of Stator frame , core & winding of 01 No generator stator at Ghatghar HPS. | 0 | - | 0 | 23.9 | 23.9 | 0 | 0 | 0 |  |  | 0 | 0
3 | Generator Circuit breaker Electrical OH at Ghatghar HPS. | 0 | - | 0 | 7.2 | 7.2 | 0 | 0 | 0 |  |  | 0 | 0
4 | Water filter treatment plant and pipeline at Ghatghar HPS. | 0 | - | 0 | 1.25 | 1.25 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Design,supply,errection,testing & commissioning of digital governing system at Paithan HPS. | 0 | - | 0 | 4.5 | 4.5 | 0 | 0 | 0 |  |  | 0 | 0
2 | Design,Supply ,testing ,erection and commissioing of DAVR system at Paithan HPS. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
3 | Design,supply,testing ,erection and commissioing of DCS control system at Paithan HPS. | 0 | - | 0 | 1.7 | 1.7 | 0 | 0 | 0 |  |  | 0 | 0
4 | Design,supply ,testing ,erection and commissioing of Automated Co2 fire extinguishers system at Paithan HPS. | 0 | - | 0 | 0.35 | 0.35 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design,Supply ,testing ,erection and commissioing of Numerical protection system at Yeldari HPS. | 0 | - | 0 | 2.55 | 2.55 | 0 | 0 | 0 |  |  | 0 | 0
6 | Design,Supply ,testing ,erection and commissioing of C&I control & measurement with SCADA at Yeldari HPS. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
7 | Design,Supply ,testing ,erection and commissioing of DAVR system at Yeldari HPS | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
8 | Design,supply,errection,testing & commissioning of digital governing system at Yeldari HPS. | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 3 (CIVIL) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Fortification and Rock fall protection Measures in Vaitarna Hydro Electric Power Project Premises ,Tal- Igatpuri , Dist-Nashik. | 0 | - | 0 | 36.53 | 36.53 | 0 | 0 | 0 |  |  | 0 | 0
2 | Work of construction of Bituminous approach road to Portal Switchyard at Vaitarna HPS. | 0 | - | 0 | 2.77 | 2.77 | 0 | 0 | 0 |  |  | 0 | 0
3 | Work of construction of Gabion wall structure on down stream of nallah near Tunnel at Vaitarna HPS. | 0 | - | 0 | 0.26 | 0.26 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC(F Y 2026-27) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 4 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Comprehensive work of redesign,manufacture, supply erection, testing & commissioning of Digital Governing, Protection and control system Consisting of SCADA on single point responsibility at 60 MW Vaitarna HPS. | 0 | - | 0 | 14 | 14 | 0 | 0 | 0 |  |  | 0 | 0
2 | Comprehensive work of Replacement, Modification,upgradation of cooling water system along with replacement of pipeline,pumps,panel etc at 60 MW Vaitarna HPS. | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
3 | Design, Manufacture, Supply, Erection, Testing and commissioning of 1000 KVA UAT & EAT at 60MW Vaitarna HPS. | 0 | - | 0 | 0.6 | 0.6 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, Erection, Testing & Commissioning of 500 KVA DG set along with cable and changeover system at 60 MW Vaitarna HPS | 0 | - | 0 | 0.6 | 0.6 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply, erection, testing and commissioning of 132kV Single core 300sqmm copper conductor XLPE insulated Lead sheathed power cable from Portal switchyard to Main switchyard along with fabrication of cable trays and misc. allied works at 60 MW Vaitarna HPS | 0 | - | 0 | 11 | 11 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Upgradation of Insulation class Yeldari HPS | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
2 | Design,Supply ,testing ,erection and commissioing of with modification of HT power circuit from 66KV to 132 KV by providing 03 Nos GT of 6.6/132 KV capcity 10 MVA with allied compatible aux. equipments & 01 Aux X`mer 2MVA of 132/11 KV at Yeldari HPS | 0 | - | 0 | 10.2 | 10.2 | 0 | 0 | 0 |  |  | 0 | 0
3 | Design,supply ,testing ,erection and commissioing of Automated Co2 fire extinguishers system including supply of Co2 cylinder banks,detectors accessories and associated work at Yeldari HPS | 0 | - | 0 | 0.6 | 0.6 | 0 | 0 | 0 |  |  | 0 | 0
4 | Design,supply ,testing ,erection and commissioing of UAT capacity 250 KVA ration 6.6KV/415V with ACDB, DCDB , auto change over system | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design,supply ,testing ,erection and commissioing of Power cables for GT and control cables at Yeldari HPS | 0 | - | 0 | 3.75 | 3.75 | 0 | 0 | 0 |  |  | 0 | 0
6 | Design,supply ,testing ,erection and commissioing of Power cables for GT and control cables at Yeldari HPS | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 6(CIVIL) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Package shade roof change at Ghatghar HPS | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
2 | PROCUREMENT OF MOBILE RACKS FOR STORES atGhatghar HPS | 0 | - | 0 | 0.25 | 0.25 | 0 | 0 | 0 |  |  | 0 | 0
3 | Wall compound Rising of height and Wire fence on wall at package shade at Ghatghar HPS | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
4 | Wall compound colony UCR at Ghatghar HPS | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
5 | Colony and office Road asphalting at Ghatghar HPS | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
6 | Road colony to power house at Ghatghar HPS | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC(F Y 2027-28) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 7 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | UPGRADATION OF SFC & DDC PANEL at Ghatghar HPS | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
2 | BATTERY CHARGER PROCUREMENT at Ghatghar HPS | 0 | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
3 | PHASE REVERSAL SWITCH PROCUREMENT at Ghatghar HPS | 0 | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
4 | PROCUREMENT OF SPARES FOR 220kV GIS at Ghatghar HPS | 0 | - | 0 | 6.5 | 6.5 | 0 | 0 | 0 |  |  | 0 | 0
5 | PROCUREMENT OF RBDV at Ghatghar HPS | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR 8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Comprehensive work of Renovation, Modification, Design, Manufacture, Supply, Erection, Testing & Commissioning of new Generator on single point responsibility at 60 MW Vaitarna HPS. | 0 | - | 0 | 50 | 50 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Office Equipment | 0 | - | 0 | 0.66374 | 0.70044 | -0.036705 | 0 | 0 |  |  | 0 | -0.036705
2 | Furniture & Fixtures | 0 | - | 0 | 0.035748 | 0.035748 | 0 | 0 | 0 |  |  | 0 | 0
3 | Replacement of existing 300AH/220VDC & 200AH/220VDC Battery Set with new Lead acid Tubular Battery Set along with Design, manufacture, supply, installation, commissioning & testing at Yeldari & Paithan HPS | 0 | - | 0 | 0.2283 | 0.2283 | 0 | 0 | 0 |  |  | 0 | 0
4 | Vehicle (Fire Tender ) | 0 | - | 0 | 4.0078 | 4.0078 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 310.7899 | 311.4233 | -0.6334 | 0 | 0 | 0 | 0 | 0 | -0.6334