## F4
MSPGCL: Koradi 8-10
MTR Petition Formats - Generation
Form 4: Summary of Capital Expenditure and Capitalisation
(Rs. Crore)
Sr. No. | Particulars | FY 2022-23 |  |  | FY 2023-24 |  |  | FY 2024-25 |  |  |  |  | Ensuing Years |  |  |  |  | Remarks
|  | MYT Order (227 of 2022) | April-March (Audited ) | True-Up requirement | MYT Order (227 of 2022) | April-March (Audited ) | True-Up requirement | MYT Order (227 of 2022) | Apr-Sep (Estimated) | Oct-Mar (Projected) | April - March (Projected) | Provisional True-Up requirement | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30
|  | (a) | (b) | (c) = (b) - (a) | (d) | (e) | (f) = (e) - (d) | (g) | (h) | (i) | (j) = (h )+ (i) | (k) = (j) - (g) | Projected | Projected | Projected | Projected | Projected
1 | Capital Expenditure |  | 138.9621 | 138.9621 |  | 42.8633 | 42.8633 |  |  |  | 574.3088 | 574.3088 | 2577.9688 | 1452.84 | 569.56 | 219.954 | 122.86
2 | Capitalisation | 306.92 | 93.6906 | -213.2294 | 41.59 | 31.8996 | -9.6904 | 997 | 5.22 | 569.09 | 574.3088 | -422.6912 | 2585.8688 | 1639.84 | 654.5 | 219.954 | 122.86
3 | IDC |  |  | 0 |  |  | 0 |  |  |  |  | 0
4 | Capitalisation + IDC | 306.92 | 93.6906 | -213.2294 | 41.59 | 31.8996 | -9.6904 | 997 | 5.22 | 569.09 | 574.3088 | -422.6912 | 2585.8688 | 1639.84 | 654.5 | 219.954 | 122.86 | 0
Note: * - Truing Up for FY 2022-23 & FY 2023-24 to be done under MERC MYT Regulations 2015 with reference to amounts approved in the MYT Order for FY 2020-21 to FY 2024-25.
Detailed Justification shall be provided for variation in approved capital expenditure and capitalisation vis-a-vis actual capital expenditure and capitalisation

## F4.1
MSPGCL: Koradi 8-10
MTR Petition Formats - Generation
| Project Details |  | Form 4.1: Capital Expenditure Plan | [14 empty] | (Rs. Crore)
Sr. No. | Project Code | Project Title | MERC Approval No. | MERC Approval Date | Project Purpose | Project Start Date |  |  | Project Completion date (Scheduled) |  |  | Capital Cost
[6 empty] | Original | Revised | Actual | Original | Revised | Actual | Approved | Actual Capital Cost Incurred | Deviation = Approved - Actual on account of
[14 empty] | Change in Scope of Work (a) | Material Cost (b) | IDC (c) | Others (d) | Total Deviation (a+b+c+d)
9 | Flue Gas Desulphurization FGD is for Unit 8, 9, 10 of 3x660MW Koradi TPS | DPR | MERC/CAPEX/FY 2020-21/WFH/SBR/05 | 2020-05-31 | 0 | 2020-05-31 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
9.1 | Flue Gas Desulphurization is for Unit 8, 9, 10 of 3x660MW Koradi TPS | Scheme | MERC/CAPEX/FY 2020-21/WFH/SBR/05 | 2020-05-31 | 0 | 2020-05-31 |  | - | - |  | - | 847.78 | 0 |  | 847.78 |  |  | 847.78
0 | IDC | IDC | MERC/CAPEX/FY 2020-21/WFH/SBR/05 | 2020-05-31 | 0 | 2020-05-31 |  | - | - |  | - | 92.22 | 0 |  | 92.22 |  |  | 92.22
HO DPR 13 | Construction of new admin building at Vidyut Bhavan, Katol Road, Nagpur | DPR | MERC/Capex/2021-2022/MSPGCL/063 | 2022-02-18 | 0 | 2022-02-18 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 13.1 | Construction of new admin building at Vidyut Bhavan, Katol Road, Nagpur | 0 | 0 | 2022-02-18 | 0 | 2022-02-18 |  | - | - |  | - | 54.24 | 0 |  | 54.24 |  |  | 54.24
0 | IDC | 0 | 0 | 2022-02-18 | 0 | 2022-02-18 |  | - | - |  | - | 2.76 | 0 |  | 2.76 |  |  | 2.76
18 | Improvement in Regenerative Air Pre-heater Performance at Unit # 9 of 3x660 MW, Koradi TPS | DPR | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 0 | 2022-10-06 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
18.1 | Procurement of heating elements for RAPH installed in Unit 9 (660MW) at KTPS Koradi THROUGH LIMITED TENDER | Scheme | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | • Reduction in loss due to Dry flue gas • Reduction in PA fan & FD loading. • Improvement in unit heat rate. | 2022-10-06 |  | - | - |  | - | 15.33 | 11.8 |  | 3.53 |  |  | 3.53
18.2 | Replacement of heating elements for RAPH installed in Unit 9 (660MW) at KTPS Koradi | Scheme | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 0 | 2022-10-06 |  | - | - |  | - | 0.349 | 0.37 |  | -0.021 |  |  | -0.021
0 | IDC | IDC | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 0 | 2022-10-06 |  | - | - |  | - | 0.19 | 0 |  | 0.19 |  |  | 0.19
19 | CHP Improvement (7 Nos) Schemes & Procurement of Bulldozers, Wheel Loaders and Hydraulic Cranes at CHP 3X660MW, KTPS, Koradi | DPR | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 0 | 2024-04-18 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
19.1 | Sch-1: Revamping of Apron Feeder in CHP at 3X660MW, KTPS, Koradi. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | • System outages will be reduced. • Unloading time will be improved thereby reduce demurrages. • Demurrage charges will be reduced. • Maintenance cost of apron feeder will be reduced. | 2024-04-18 |  | - | - |  | - | 4.68 | 0 |  | 4.68 |  |  | 4.68
19.2 | Sch-2: Procurement of Hydraulic motors and pumps in CHP at 3X660 MW, KTPS, Koradi | Scheme | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | • Reduction in demurrages. • Spare motor and pump ensure system availability in case of failure of existing one. • Increase plant availability & reduction in generation loss | 2024-04-18 |  | - | - |  | - | 4.44 | 0 |  | 4.44 |  |  | 4.44
19.3 | Sch-3: Capacity enhancement of Hydraulic motor of Apron Feeder in CHP, 3X660 MW, KTPS, Koradi | Scheme | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | • Reduction in conveyor stream outages. • Reduction in demurrage charges. • Capacity of apron feeder will increase • Higher unloading rate • System availability will increase. • Repetitive maintenances will reduce. • Reduction in the inventory. | 2024-04-18 |  | - | - |  | - | 2.01 | 0 |  | 2.01 |  |  | 2.01
19.4 | Sch-4: Modification, supply and replacement of Transfer chutes in CHP 3x660MW KTPS, Koradi. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | • Reduction in conveyor stream outages. • Reduction in maintenance cost. • Reduction in cleaning problems. • Improvement in performance of unloading & reduction in generation loss. • Demurrage charges will be reduced. | 2024-04-18 |  | - | - |  | - | 4.39 | 0 |  | 4.39 |  |  | 4.39
19.5 | Sch-5: Design, supply, installation & commissioning of High performance IGUS energy chain system with chain flex cable for Tripper trolleys at CHP at 3x660 MW, KTPS, Koradi. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | • Less down time of critical auxiliary • Less maintenance cost • Increase in reliability • Uninterrupted coal bunkering • Less downtime of critical auxiliary • Increase in plant loadability and availability • Aversion of generation loss | 2024-04-18 |  | - | - |  | - | 4.37 | 0 |  | 4.37 |  |  | 4.37
19.6 | Sch-6: Procurement of B3-630 gear box for BCN 6 A/B in CHP at 3x660 MW, KTPS, Koradi. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | • Higher system availability with high bunker level • Spare gear box ensure system availability in case of failure of existing one. • Increase plant availability & reduction in generation loss | 2024-04-18 |  | - | - |  | - | 0.57 | 0 |  | 0.57 |  |  | 0.57
19.7 | Sch-7: Supply and installation of Belt tear detector system for conveyor belt in CHP 3x660 MW, KTPS, Koradi. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | • Costly conveyor will be protected • Reduction in conveyor stream outages. • Reduction in maintenance cost. • Reduction in cleaning problems. • Consumption of the costly conveyor belt will be reduced. | 2024-04-18 |  | - | - |  | - | 1.18 | 0 |  | 1.18 |  |  | 1.18
19.8 | Sch-8: Procurement of 5 Nos of Bulldozers BD 155 at CHP 3X660 MW Koradi Thermal Power station. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | • System outages will be reduced. • Unloading time will be improved thereby reduce demurrages. • Maximum power & efficiency of equipment based on load. • Service & Maintenance cost will be reduced. • Proper stack yard management Less diesel consumption | 2024-04-18 |  | - | - |  | - | 12.83 | 0 |  | 12.83 |  |  | 12.83
19.9 | Sch-9:- Procurement of 02 nos. of Wheel loaders at CHP 3X660 MW, KTPS, Koradi. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | • Unloading time will be improved thereby reduce demurrages. • Move more coal/material in less time with less fuel. • Service & Maintenance cost will be reduced. • Proper stack yard management Less diesel consumption | 2024-04-18 |  | - | - |  | - | 3.07 | 0 |  | 3.07 |  |  | 3.07
19.1 | Sch-10:- Procurement of 15 Ton & 20 Ton capacity hydraulic Cranes at CHP 3X660 MW, KTPS, Koradi. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | • Safe and reliable operation. • Time saving and reduction in manpower • Down time of auxiliaries will reduced • System availability will increase. | 2024-04-18 |  | - | - |  | - | 0.69 | 0 |  | 0.69 |  |  | 0.69
0 | IDC | IDC | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 0 | 2024-04-18 |  | - | - |  | - | 0.64 | 0 |  | 0.64 |  |  | 0.64
20 | Construction of bridge cum bandhara across Pond No. 3 and allied works at Pond No. 3 at Koradi TPS | DPR | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 0 | 2024-04-18 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
20.1 | Construction of cement concrete bridge cum bandhara alongwith gated arrangement. | Scheme | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 0 | 2024-04-18 |  | - | - |  | - | 14.75 | 0 |  | 14.75 |  |  | 14.75
20.2 | Construction of earthen embankment connecting bridge cum bandhara on both side of embankment by excavating soil / typha / silt from Pond No.3 & tree plantation. | Scheme | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 0 | 2024-04-18 |  | - | - |  | - | 14.3252 | 0 |  | 14.3252 |  |  | 14.3252
20.3 | Providing structural steel pathway on the existing waste weir (west side of the Pond No.3) and roads connecting to bridge behind Pond No.3 and bridge cum bandhara. | Scheme | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 0 | 2024-04-18 |  | - | - |  | - | 2.4308 | 0 |  | 2.4308 |  |  | 2.4308
0 | IDC | IDC | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 0 | 2024-04-18 |  | - | - |  | - | 1.61 | 0 |  | 1.61 |  |  | 1.61
6 | Procurement & replacement of Superheater Pass Economizer Coils (Modified Design) for Unit 8, 9 & 10 at 3x660MW KTPS, Koradi | DPR | Not Approved | 0 | 0 | 0 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
6.1 | Procurement & replacement of Superheater Pass Economizer Coils (Modified Design) for Unit 8, 9 & 10 at 3x660MW KTPS, Koradi | Scheme | Not Approved | 0 | 1) By modified design it will easy for inspection and maintenance of economizer coils, hence preventive measures can be taken on eoded tubes to avoid the BTL. 2) By implementing this scheme BTL will reduce in economizer coils. | 0 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
0 | IDC | IDC | Not Approved | 0 | 0 | 0 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
7 | Improvement in Boiler Performance at U-8,9 & 10 KTPS, Koradi | DPR | MERC/CAPEX/MSPGCL/2023-24/0638 | 0 | 0 | 0 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
7.1 | Scheme-1: Procurement of Blade Sets for ID, FD & PA Fans at 3x660MW Units. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0638 | 0 | 1) Availability & Reliability of fans will be increased 2) Breakdown of fans will be avoided. | 0 |  | - | - |  | - | 11.34 | 0 |  | 11.34 |  |  | 11.34
7.2 | Scheme-2: Procurement of RAPH Bottom Support Bearing Assembly at 3X660MW Units. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0638 | 0 | 1) Long shutdown of unit shall be avoided. As the availability of this bearing in stock shall be replaced one to one as and when required, which reduces the outage of unit and generation loss thereof. | 0 |  | - | - |  | - | 2.478 | 0 |  | 2.478 |  |  | 2.478
7.3 | Scheme-3: Procurement of RAPH Top Guide Bearing Assembly at 3x660MW Units. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0638 | 0 | 1) Long shutdown of unit shall be avoided. As the availability of this bearing in stock shall be replaced one to one as and when required, which reduces the outage of unit and generation loss thereof. | 0 |  | - | - |  | - | 0.684 | 0 |  | 0.684 |  |  | 0.684
7.4 | Scheme-4: Procurement of RAPH Gear Box at 3x660MW Units. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0638 | 0 | 1) Long shutdown of unit shall be avoided. As the availability of this gearbox in stock shall be replaced one to one as and when required, which reduces the outage of unit and generation loss thereof. | 0 |  | - | - |  | - | 3.44 | 0 |  | 3.44 |  |  | 3.44
7.5 | Scheme-5: Procurement of RAPH Spares at 3x660MW Units. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0638 | 0 | 1) Availability of these spares will keep RAPH internal sealing system in healthy condition. Which will reduce heat loss, erosion of internals of RAPH and reduce Fans loading. | 0 |  | - | - |  | - | 1.13 | 0 |  | 1.13 |  |  | 1.13
7.6 | Scheme-6: Procurement of Coal Burner Assembly with windbox air nozzles for Unit 8 & 9 at 3x660MW. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0638 | 0 | 1) Combustion tunning will improve 2) Reduction in tube leakages due to temperature excursion | 0 |  | - | - |  | - | 15.407 | 0 |  | 15.407 |  |  | 15.407
7.7 | Scheme-7: Procurement of Boiler Circulation Pump (BCP) with Impeller & Diffuser at 3x660MW Units. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0638 | 0 | 1) 100% availability of all the Boiler Circulation Pumps will help to reduce fuel consumption during the start-up/light-up activities 2) Delay for synchronization will reduce by 2-3 hrs. | 0 |  | - | - |  | - | 11.12 | 0 |  | 11.12 |  |  | 11.12
7.8 | Scheme-8: Procurement and Replacement of Heating Elements for RAPH Installed for Unit 8 at 3x660MW. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0638 | 0 | • Reduction in loss due to Dry flue gas • Reduction in PA fan & FD loading. • Improvement in unit heat rate. | 0 |  | - | - |  | - | 15.96 | 0 |  | 15.96 |  |  | 15.96
0 | IDC | IDC | MERC/CAPEX/MSPGCL/2023-24/0638 | 0 | 0 | 0 |  | - | - |  | - | 1.37 | 0 |  | 1.37 |  |  | 1.37
23 | Design, Engineering, Supply, Installation, Testing, Commissioning including all civil works for Natural resource treatment and Laboratory equipment with mandatory spares at Koradi TPS, 3 X 660 MW | DPR | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0 | 2024-03-11 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
23.1 | Supply of Natural resource treatment and lab equipment for Water, Coal, Oil, Meteorology with supporting AI computing, all auxiliaries, and accessories. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0 | 2024-03-11 |  | - | - |  | - | 35.28 | 0 |  | 35.28 |  |  | 35.28
23.2 | Supply of Mandatory spares on lump-sum basis. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0 | 2024-03-11 |  | - | - |  | - | 0.8 | 0 |  | 0.8 |  |  | 0.8
23.3 | Supply of Tools and Tackles on lump-sum basis. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0 | 2024-03-11 |  | - | - |  | - | 0.15 | 0 |  | 0.15 |  |  | 0.15
23.4 | Complete Civil Work with 10 KLD ETP/ STP on lump-sum basis. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0 | 2024-03-11 |  | - | - |  | - | 3.6 | 0 |  | 3.6 |  |  | 3.6
23.5 | Services - Charges of Inland transport of plant and equipment on lump-sum basis. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0 | 2024-03-11 |  | - | - |  | - | 0.2 | 0 |  | 0.2 |  |  | 0.2
23.6 | Charges for Testing, Commissioning and PG Test of plant and equipment. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0 | 2024-03-11 |  | - | - |  | - | 0.05 | 0 |  | 0.05 |  |  | 0.05
0 | IDC | IDC | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0 | 2024-03-11 |  | - | - |  | - | 0.82 | 0 |  | 0.82 |  |  | 0.82
24 | Improvement in Regenerative Air Preheater Performance & Complete Replacement of NDCT fills at Unit # 10, Koradi TPS | DPR | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 0 | 2024-04-18 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
24.1 | Procurement of heating elements for RAPH installed in Unit 10 (660MW) at KTPS Koradi through OEM | Scheme | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | • Reduction in loss due to Dry flue gas • Reduction in PA fan & FD loading. • Improvement in unit heat rate. | 2024-04-18 |  | - | - |  | - | 12.23 | 14.521 |  | -2.291 |  |  | -2.291
24.2 | Complete Supply & Replacement of NDCT fills of U#10. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 0 | 2024-04-18 |  | - | - |  | - | 13 | 0 |  | 13 |  |  | 13
0 | IDC | IDC | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 0 | 2024-04-18 |  | - | - |  | - | 0.22 | 0 |  | 0.22 |  |  | 0.22
HO DPR 14 | Centralized Monitoring Solution | DPR | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 0 | 2023-11-02 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 14.1 | Centralized Monitoring Solution | Scheme | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 0 | 2023-11-02 |  | - | - |  | - | 66.009 | 0 |  | 66.009 |  |  | 66.009
0 | IDC | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 0 | 2023-11-02 |  | - | - |  | - | 3.3 | 0 |  | 3.3 |  |  | 3.3
HO DPR 15 | HMI (Human Machine Interface) Upgradation of ‘SSPA-T3000’ DCS (Distribution Control System), Rockwell make PLC System installed at 3x660MW Unit No. 8, 9 & 10 at Koradi TPS and HMI (Human Machine Interface) Upgradation of MaxDNA DCS System at Unit 8-9, CSTPS, Chandrapur | DPR | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0 | 2023-10-09 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 15.1 | Supply: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0 | 2023-10-09 |  | - | - |  | - | 10.52 | 0 |  | 10.52 |  |  | 10.52
HO DPR 15.2 | Works: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0 | 2023-10-09 |  | - | - |  | - | 0.41 | 0 |  | 0.41 |  |  | 0.41
15.3 | HMI (Human Machine Interface) Upgradation of ‘SPPA-T3000’ DCS (Distributed Control System) installed at 3x660MW Unit- 8, 9 & 10 at Koradi TPS to match with the external aspects and process improvement | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | The scheme is proposed as necessity Scheme which is essential for implementation to Keep the system up and running. | 2023-10-09 |  | - | - |  | - | 24.33 | 0 |  | 24.33 |  |  | 24.33
15.4 | Upgradation of Rockwell Make PLC System installed at 3x660MW ,Koradi TPS to match with the external aspects and process improvement.(C&I) | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | The scheme is proposed as necessity Scheme which is essential for implementation to Keep the system up and running. | 2023-10-09 |  | - | - |  | - | 20.2 | 0 |  | 20.2 |  |  | 20.2
0 | IDC | IDC | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0 | 2023-10-09 |  | - | - |  | - | 0.15 | 0 |  | 0.15 |  |  | 0.15
Formulas:
Project Start Date = [MERC Approval Date]

## F4.2
|  |  | MSPGCL: Koradi 8-10 | [52 empty] | DPR | Not Initiated
|  |  | MTR Petition Formats - Generation | [52 empty] | Scheme | WIP
| Project Details |  | Form 4.2: Capitalisation Plan | [18 empty] | (Rs. Crore) | [24 empty] | (Rs. Crore) | [8 empty] | IDC | Partially Capitalised
Sr. No. | Project Code | DPR | MERC Approval No. | Date of Submission | MERC Approval Date | Cost as per DPR Crs. | MERC Approved Cost | Debt Equity Ratio | Grant Funding | Approved Start Date | Actual Start Date | Approved Date of Completion | Actual Date of Completion | Benefits in Quantified Terms | Capital Expenditure | [12 empty] | Physical Progress (%) | [11 empty] | Capitalisation | [12 empty] | Old Asset retired against capitalised item (in Rs. Cr) | Remarks | Current Status | Non-DPR | Capitalised
[15 empty] | Actual Capex till FY 2018-19 | Actual | Actual | Actual Capex till FY 2021-22 | Actual | Actual | Actual | Revised Projected | Estimated |  |  |  |  | Actual Progress till FY 2018-19 | Actual | Actual | Actual | Actual | Actual | Revised Projected | Estimated |  |  |  |  | Actual Capitalization till FY 2018-19 | Actual | Actual | Actual | Actual Capitalization till FY 2021-22 | Actual | Actual | Revised Estimated | Estimated | [8 empty] | Cancelled
[16 empty] | FY 2019-20 | FY 2020-21 |  | FY 2021-22 | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 |  | FY 2019-20 | FY 2020-21 | FY 2021-22 | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 |  | FY 2019-20 | FY 2020-21 | FY 2021-22 |  | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 |  |  |  |  | To be cancelled
[55 empty] | N.A. |  | N.A.
A) Approved Add cap:
A | BoP |  |  |  |  | 246.34 | 246.34 | [8 empty] | 61.694 | 13.7496 | 75.4436 | 130.0638 | 15.27 | 12.9668 | [19 empty] | 61.694 | 13.7396 | 130.0638 | 205.4974 | 15.09 | 12.1055 | [7 empty] | BOP Justification: Mahagenco had issued PO to M/s LITL for BOP works on dtd. 27.07.2010 amounting to Rs. (1305.72 Inc. Taxes) Crores. However M/s LITL has not completed the BOP works due to finanacial crises and bankruptcy. Hence, Mahagenco has terminated the contract and decided to carry out the work at the Risk & Cost of M/s LITL. Mahagenco has made payment to M/s LITL= Rs. 1247.54 Cr (Inc. Taxes). Expenditure incurred after termination of contract till 31.03.2022 is Rs. 170.12 Cr. (Inc. Taxes) & estimated cost of future work is Rs. 50.23 Cr (Inc. Taxes) .Therefore total revised expenditure of BOP Package is Rs. 1467.89 Cr. (Inc. Taxes) till date. Cost of BoP package is enhanced due revision in rates. Expected date of completion of BoP package is 31-07-2023. Reason for delay in works is as follows: 1) MSPGCL has issued P.O. to sub -vendors of M/s LITL at the same terms and condition of LITL P.O., however sub-vendors has not executed the work of CW treatment and ETP plant. 2) Due to covid-19 pandemic and lock-down, vendors were unable to visit the site for survey and budgetory offer. After relaxation in lockdowns some vendors have visited the sith and submitted their offers. 3) After preparation of proposals and approvals of competent authority; Koradi Projects has recently floated tenders. In view of above, BoP package shall complete by 31st July 2023. Remarks- As on date expenses of 10.56 Cr. are there & expected expenditure of 17.70 Cr. will be made upto 31.03.2023, till date no capatalisation in 2022-23. Complete expenditure of 2022-23 may be capatalisied before 31.05.2023.
B | BTG |  |  |  |  | 44.15 | 44.15 | [10 empty] | 0 | [25 empty] | 0 | [9 empty] | BTG balance billing to be capitalised in March 2023
B1 | Supply |  |  |  |  | 13.33 | 13.33 | [10 empty] | 0 | 13.33 | [24 empty] | 0 | 13.33
B2 | Works |  |  |  |  | 0.98 | 0.98 | [10 empty] | 0 | 0.98 | [24 empty] | 0
B3 | Taxes and duties |  |  |  |  | 23.29 | 23.29 | [10 empty] | 0 | 23.29 | [24 empty] | 0
B4 | Civil |  |  |  |  | 0.19 | 0.19 | [8 empty] | 0.19 |  | 0.19 | [25 empty] | 0 | 0
B5 | Mandatory Spares |  |  |  |  | 5.03 | 5.03 | [10 empty] | 0 | 5.03 | 1.29 | [23 empty] | 0 | 6.32
B6 | BTG (L&T) Work |  |  |  |  | 1.33 | 1.33 | [10 empty] | 0 | 1.33 | [24 empty] | 0 | 0
C | Other Works (Plant) |  |  |  |  | 136.33 | 136.33 | [10 empty] | 0 | [25 empty] | 0
C1 | Fully Integrated Security System |  |  |  |  | 27.36 | 27.36 | [8 empty] | 30.724 | 0.7375 | 31.4615 | [22 empty] | 30.724 | 0.7375 |  | 31.4615
C2 | Administrative Expenses and overhead |  |  |  |  | 7.25 | 7.25 | [9 empty] | 0.24 | 0.24 | 0.56 | 0.45 | 6 | [22 empty] | 0
C3 | Contingencies E&M |  |  |  |  | 0.04 | 0.04 | [10 empty] | 0 |  | 0.04 | [23 empty] | 0
C4 | Mobile storage racks, fork lifts, hoists & hydra for material handling in major stores shed |  |  |  |  | 0.95 | 0.95 | [8 empty] | 0.93645 |  | 0.93645 | [22 empty] | 0.93645 |  |  | 0.93645
C5 | Development of working models of Plant Layout, Boiler, Turbine- Generetaor, Coal mill, Fans, etc. at KTC, Koradi. |  |  |  |  | 1.2 | 1.2 | [9 empty] | 1.2 | 1.2 | [22 empty] | 0.93043 | 0.00664 | 0.04897 | 0.98604
C6 | Workshop equipment |  |  |  |  | 0.26 | 0.26 | [8 empty] | 0.0377 |  | 0.0377 | 0.2223 | 0.22422 | [20 empty] | 0.0377 | 0.22422 |  | 0.26192 | [9 empty] | Capitalisation done
C7 | Design, engg, manufacture, supply , erection, testing & commissioning of Ozonization Plant for circulating cooling water system |  |  |  |  | 54.05 | 54.05 | [8 empty] | 3.89 | 27.6083 | 31.4983 | 24.32 | 0.27 | [21 empty] | 0.63289 | 30.7115 | 31.3444 | 0.27 | [8 empty] | Sanctioned - 54.05 Cr, Mahagenco has placed P.O. for 3*15 Kg amounting Rs. 29.73 Cr. & decided to place balance amount of PO after satisisfactory performance of placed PO. Amount of Rs. 24.47 is consided in year 22-23 below as a second phase.
C8 | Supply, installation & commissioning of water flow meters including required SCADA software and other accessories for water management system |  |  |  |  | 5.08 | 5.08 |  |  | - | [7 empty] | 0 | [25 empty] | 0 | [9 empty] | Complete Scheme is cancelled
C9 | Provision of wet ash evacuation system for first two rows of ESP for Unit-8,9 & 19 |  |  |  |  | 26.59 | 26.59 |  |  | - | [6 empty] | 20.79 | 20.79 | 4.6281 | 0.9 | [20 empty] | 0 | 0 | 25.4181 | 25.4181 | 0.9 | [8 empty] | completion date upto 31.03.2023
C10 | Procurement of portable mercury analyser for flue gas monitoring |  |  |  |  | 6.2 | 6.2 |  |  | - | [7 empty] | 0 | [25 empty] | 0 | [9 empty] | Complete Scheme is cancelled
C11 | Administrative Expenses and overhead |  |  |  |  | 5 | 5 |  |  | - | [5 empty] | 5.12 | 5.5557 | 10.6757 | 5.56 | 5.0111 | 5.3133 | [22 empty] | 0
C12 | Compressor of Hydrogen plant |  |  |  |  | 1.5 | 1.5 |  |  | - | [5 empty] | 0 | 1.5 | 1.5 | [25 empty] | 0
C13 | Rail Cum road stone grabbler |  |  |  |  | 0.85 | 0.85 |  |  | - | [5 empty] | 0 | 0.85 | 0.85 | [25 empty] | 0
D | Other Works (Civil) |  |  |  |  | 122.62 | 103.19 |  |  | - | [7 empty] | 0 | [25 empty] | 0
D1 | Road, Bridges railway system |  |  |  |  | 20.1 | 20.1 |  |  | - |  |  |  |  | 0 | 0 | 0.10806 | 0.10806 | 0 | [21 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | The expenditure/capitalisation under this head till date is nil, however the expenditure/capitalisation shown in financial year 2022-23 may be done upto 31.03.2023
| S&T System with Panel Interlocking System | [8 empty] | - |  |  |  |  | 9.88 | 0.1 | 0.42467 | 10.4047 | 0 | 0 | 0.053794 | [18 empty] | 0 | 9.9812 | 0 | 0.42467 | 10.4058 | 0 | 0.053794
D2 | Staff quarters |  |  |  |  | 5.25 | 5.25 |  |  | - |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0 | 0 | 0 | 0 | 0
D3 | Other Misc & Unforseen Item |  |  |  |  | 25.79 | 25.79 |  |  | - |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9.3 | [20 empty] | 0 | 0 | 0 | 0 | 7.53
| Check Post, Inspection Office & Facility Complex | [8 empty] | - |  |  |  |  | 0.82 | 2.07 | 0.62 | 3.51 | 0 | 0.17443 | [19 empty] | 0 | 2.8855 | 0.62164 | 0 | 3.5071 | 0.17443
| CPRI Building | [8 empty] | - |  |  |  |  | 4.5847 | 0 | 0 | 4.5847 | 0 | 1.6199 | [19 empty] | 0 | 0 | 4.5847 | 0 | 4.5847 | 1.6199
| Foam cum DCP fire tender- 1 | [16 empty] | 0 | 0.76926 | [23 empty] | 0.76926 | 0.76926 | 0
| Fire water Bowser-cum-fire Tender- 1No. | [15 empty] | 0.73537 | 0.73537 | [23 empty] | 0.73537 |  | 0.73537 | 0
D4 | Const. facility |  |  |  |  | 3.28 | 3.28 |  |  | - |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0 | 0 | 0 | 0 | 0
D5 | Contigency Other Civil Work |  |  |  |  | 5.27 | 5.27 |  |  | - |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0 | 0 | 0 | 0 | 0
D6 | Adminstrative Exp. & Overhead (Salary & Overhead, Civil & E&M) |  |  |  |  | 21.47 | 21.47 |  |  | - |  |  |  |  | 0 | 11.47 | 10 | 21.47 | 9.26 | 10.17 | [20 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | Administrative Expenses salary & overhead was not included in ongoing project of Pipe Conveyor System, hence the cost of establishment were expended from this budget head. As on date expenses of 30.73 Cr.is there & expected expenditure of 10.17 Cr. will be made upto 31.03.2023, till date no capatalisation in 2022-23. Complete expenditure upto date will be capatalisied before 31.03.2023.
D7 | Future unforseen works(Jalyukta Shiwar) |  |  |  |  | 0.27 | 0.27 |  |  | - |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0 | 0 | 0 | 0
D8 | Landscaping work |  |  |  |  | 21.76 | 21.76 |  |  | - |  |  |  |  | 0 | 20.53 | 0 | 20.53 | 2.99 | 0 | [21 empty] | 0 |  | 0 | [9 empty] | Amount exceeded due to applicability of Price Variation in Contract.
E | Initial Spares | [16 empty] | 0 | [25 empty] | 0
E1 | Boiler & its auxilliaries |  |  |  |  | 14 | 14 | [10 empty] | 0 | [25 empty] | 0
i | Procurement of Table liners and Roller liners Of MVM 32R Coal Mills of 3 X 660MW Units at KTPS, Koradi | [14 empty] | 0 | 10.0686 | 10.0686 | 0 | [21 empty] | 0 | 10.0686 | 0 | 10.0686
ii | Procurement of couplings for Coal mill MVM 32 R of 3 X 660 MW Units at KTPS, Koradi | [14 empty] | 0 | 0 | 0 | 1.5944 | [21 empty] | 0 | 0 | 1.5944 | 1.5944
iii | Procurement of Set of internal spares for Coal Mill Gear Box (KMP-450) for 3 X 660MW Units at KTPS, Koradi | [14 empty] | 0 | 0 | 0 | 2.2253 | [21 empty] | 0 | 0 | 2.2253 | 2.2253
E2 | Turbine & its auxilliaries |  |  |  |  | 18.81 | 18.81 | [10 empty] | 0 | [25 empty] | 0
i | ULTRAFILTRATION MEMBRANE | [14 empty] | 0 | 0 | 0 |  | 1.6511 | [20 empty] | 0 | 0 |  | 0 | 1.6511 | [8 empty] | Scheme capitalization is not done as on date but will be capitalised by 2022-2023
ii | Supply of Main turbine Vibration Monitoring System spares at 3x660MW, KTPS,Koradi. | [14 empty] | 0 | 0 | 0 | 1.1469 | [21 empty] | 0 | 0 | 1.1469 | 1.1469
iii | Procurement of Cartridge for Turbine Driven Boiler Feed Pump (Model No.: FK6E40) at 3X660 MW KTPS Koradi | [12 empty] | The projected benefits by implementation of schemes are as follows: a) Reduced downtime during overhaul/ breakdown. b) Fitment guarantee. c) Long service life for equipment. d) Reliability of equipment. e) Improvement in unit loadability. f) Performance guarantee of equipment. |  | 0 | 14.2864 | 14.2864 | 0 | [21 empty] | 0 | 14.2864 | 0 | 14.2864
iv | Procurement of Critical Insurance Spares for L&T-MHI Make Turbine for attending major overhauling work of Turbine at KTPS, 3x660MW Units Koradi. | [12 empty] | • Gross Turbine Heat rate. • Gross Turbine Cycle Efficiency. • HPT_A1 Efficiency- HPT Stage-8 to Ext. HPH8. • HPT_A1Efficiency-- HPT Stage-11 to Ext HPH7 • IPT Stage A1 Efficiency (Ext. 6) • IPT Stage A2 Efficiency (Ext. 5) • Heat Rate saving. • APC saving. |  | 0 | 0 | 0 | 0 | 11.1013 | [20 empty] | 0 | 0 | 0 | 0 | 11.1013 | [8 empty] | Being critical items for overhaul; amount of following schemes are diverted for this scheme to avoid overall cost overrun: 1)Provision of additional facility for manual unloading track in CHP of Koradi TPS U-8,9 & 10 (Rs.5.12Cr) 2)3D LEVEL SCANNER (Rs.4.00Cr)
E3 | Generator & its auxilliaries |  |  |  |  | 0 | 0 | [10 empty] | 0 | [25 empty] | 0
E4 | Electrical auxilliaries |  |  |  |  | 1.6 | 1.6 | [10 empty] | 0 | [25 empty] | 0
i | Procurement of HT Motors of BOP | [14 empty] | 0 | 0 | 0 | 0.29335 | [21 empty] | 0 | 0 | 0.29335 | 0.29335
ii | [15 empty] | 0 | 0 | 0 | 0.84594 | [21 empty] | 0 | 0 | 0.84594 | 0.84594
iii | Supply of Schneider make Differential Protection Relays for 3X660 MW, Koradi (OEM) | [14 empty] | 0 | 0 | 0 | 0.10502 | [21 empty] | 0 | 0 | 0.10502 | 0.10502
iv | Supply of Professional Large Format Display for display of DCS parameters PCR | [14 empty] | 0 | 0.14885 | 0.14885 | 0 | [21 empty] | 0 | 0.14885 | 0 | 0.14885
v | Procurement of ABT Energy meter with software for 3X660 MW, TPS, Koradi | [14 empty] | 0 | 0 | 0 | 0.18337 | [21 empty] | 0 | 0 | 0.18337 | 0.18337
E5 | Outdoor Plant i.e. CHP, AHP, WTP etc |  |  |  |  | 19.05 | 19.05 | [10 empty] | 0 | [25 empty] | 0
i | Procurement of Forced Lubrication system for Premium make Gear box B3-450 installed for bunker conveyor BCN 7A/B at CHP 3X660MW Units at KTPS, Koradi. | [14 empty] | 0 | 0 | 0 | 0.15314 | [21 empty] | 0 | 0 | 0.15314 | 0.15314
ii | Procurement of rotary spares for travel drive of Stacker and conveyor drive system in Coal Handling Plant of 3x660 MW Units at KTPS, Koradi. | [14 empty] | 0 | 0 | 0 | 0.35199 | [21 empty] | 0 | 0 | 0.35199 | 0.35199
iii | Procurement of Complete assembly of Dome Valve ( 100NB, 200NB, 300NB) with power cylinder for dry Ash evacuation system of 3X660MW KTPS, Koradi. | [14 empty] | 0 | 0.2225 | 0.2225 | 0 | [21 empty] | 0 | 0.2225 | 0 | 0.2225
iv | Procurement of Modified Apron Pans for M/s. ELECON Engineering Company ltd make Apron Feeder in CHP 3x660MW Units at KTPS, Koradi. | [14 empty] | 3.3233 | 0 | 3.3233 | 0 | [21 empty] | 3.3233 | 0 | 0 | 3.3233
v | Procurement of Single Roll Clinker Grinder with Feed Sump and Jet Pump Complete Assembly with Drive, Driven Sprocket and Chain at AHP, 3X660 MW, KTPS, Koradi. | [14 empty] | 0 | 0.56357 | 0.56357 | 0 | [21 empty] | 0 | 0.56357 | 0 | 0.56357
vi | Procurement of spares of Dome Valve (100NB, 200NB, 300NB) for Ash Evacuation System of 3X660MW Unit KTPS, Koradi. | [14 empty] | 0 | 0.16431 | 0.16431 | 0 | [21 empty] | 0 | 0.16431 | 0 | 0.16431
vii | [16 empty] | 0.10064 | 0.10064 | 0 | [21 empty] | 0 | 0.10064 | 0 | 0.10064
viii | [15 empty] | 0 | 0.00708 | 0.00708 | 0 | [21 empty] | 0 | 0.00708 | 0 | 0.00708
ix | Procurement of Hydraulic Motor for Apron feeder in Coal Handling Plant 3X660 MW, KTPS, Koradi. | [14 empty] | 0.7965 | 0 | 0.7965 | 0 | [21 empty] | 0.7965 | 0 | 0 | 0.7965
x | Procurement of Peristaltic Hose Pump (Model no: RP2 – 40) Spares for HCSD System of Ash Handling Plant, 3X660 MW, KTPS, Koradi. | [14 empty] | 0 | 0.20622 | 0.20622 | 0 | [21 empty] | 0 | 0.20622 | 0 | 0.20622
xi | Procurement of spares for HP Water Pump, Mather & Platt make, model 10/12 EME for AHP at 3X660 MW, KTPS, Koradi | [14 empty] | 0 | 0.28246 | 0.28246 | 0 | [21 empty] | 0 | 0.28246 | 0 | 0.28246
xii | Procurement of Rotor shaft assembly for M/s. ELECON Engineering Company ltd make Impact Crusher in CHP 3x660MW Units at KTPS, Koradi. | [14 empty] | 0 | 0.76369 | 0.76369 | 0 | [21 empty] | 0 | 0.76369 | 0 | 0.76369
xiii | Procurement of Sam Turbo Make Pumps Spare parts for Ash Handling Plant of 3X660 MW Units at KTPS, Koradi | [14 empty] | 0.17166 | 0 | 0.17166 | 0 | [21 empty] | 0.17166 | 0 | 0 | 0.17166
xiv | Procurement of Wagon Tippler Spares for M/s. ELECON Engineering Company ltd. make Wagon Tippler in CHP 3X660MW Units at KTPS, Koradi. | [14 empty] | 0 | 1.3975 | 1.3975 | 0 | [21 empty] | 0 | 1.3975 | 0 | 1.3975
xv | Procurement of Pneumatic Y Type Control Valve (Blow Valve Size 50mm & 80mm) for Fly Ash Evacuation System of 3X660MW Unit KTPS, Koradi. | [14 empty] | 0 | 0.029205 | 0.029205 | 0 | [21 empty] | 0 | 0.029205 | 0 | 0.029205
xvi | Procurement of the various spares required for Warman make Ash Slurry Pump Model 10/8 EEM & Over Flow Pump Model 8/6 EXU installed at AHP, 3X660 MW TPS Koradi through Limited Tender. | [14 empty] | 0 | 0.20886 | 0.20886 | 0 | [21 empty] | 0 | 0.20886 | 0 | 0.20886
xvii | [15 empty] | 0 | 0.0076261 | 0.0076261 | 0.025171 | [21 empty] | 0 | 0.0076261 | 0.025171 | 0.032797
xviii | Procurement of Spares of Single Roll Clinker Grinder Ayems Engineers make, Model AE-1005-89-100 at AHP, 3X660 MW Koradi TPS. | [14 empty] | 0 | 0.82826 | 0.82826 | 0 | [21 empty] | 0 | 0.82826 | 0 | 0.82826
xix | Procurement of Hydraulic Motor for Bucket Wheel of Stacker Reclaimer in CHP, 3X660MW, KTPS, Koradi. | [14 empty] | 0 | 1.1168 | 1.1168 | 0 | [21 empty] | 0 | 1.1168 | 0 | 1.1168
xx | Procurement of Rotors, Maintenance Kits, Couplings and other spares required for Atlas Copco make Instrument Air Compressor of Ash Handling Plant of 3 X 660 MW Units at KTPS, Koradi. | [14 empty] | 0 | 0.62625 | 0.62625 | 0.55655 |  | 0.55655 | [19 empty] | 0 | 0.62625 |  | 0.62625 |  | 0.55655
xxi | Procurement of spares of intermediate conveyor | [14 empty] | 0 | 0 | 0 | 0.3186 | [21 empty] | 0 | 0 | 0.3186 | 0.3186
xxii | Procurement of Hydraulic motor for wagon tippler drive in CHP, 3X660 MW, KTPS, Koradi. | [14 empty] | 0 | 0.46494 | 0.46494 | 0 | [21 empty] | 0 | 0.46494 | 0 | 0.46494
xxiii | Procurement of GEHO Pump (Model No. TZPM 400) Spares of Ash Handling Plant, 3 X 660 MW Units, KTPS, Koradi. | [14 empty] | 0 | 0 | 0 | 0.83656 | [21 empty] | 0 | 0 | 0.83656 | 0.83656
xxiv | Procurement of Beater Arms for Impact crushers installed at in Coal Handling Plant of 3x660 MW at KTPS, Koradi. | [14 empty] | 0 | 0 | 0 | 1.0093 | [21 empty] | 0 | 0 | 1.0093 | 1.0093
xxv | Supply of Atlas Copco make compressor spares for at Koradi TPS 660MW | [14 empty] | 0 | 0 | 0 | 0.39813 | [21 empty] | 0 | 0 | 0.39813 | 0.39813
xxvi | Procurement of spares for side arm charger, wagon tippler, impact crushers and stacker reclaimer at CHP 3x660 MW KTPS | [14 empty] | 0 | 0 | 0 | 0.42626 | 0.010573 | [20 empty] | 0 | 0 | 0.42626 | 0.42626 | 0.010573
xxvii | Procurement of Beater heads with Pin for Impact crushers installed at in Coal Handling Plant of 3x660 MW at KTPS, Koradi. | [14 empty] | 0 | 0 | 0 | 1.1256 | [21 empty] | 0 | 0 | 1.1256 | 1.1256
xxviii | Procurement of spares of Hyd Motor of SAC | [14 empty] | 0 | 0 | 0 | 0.36029 | [21 empty] | 0 | 0 | 0.36029 | 0.36029
xxix | Procurement of hydraulic power packs for Flap Gates in CHP 3X660MW, KTPS, Koradi. | [14 empty] | 0 | 0 | 0 | 0.1888 | [21 empty] | 0 | 0 | 0.1888 | 0.1888
xxx | Procurement of Mobile Grilling Equipment for CHP 3x660MW, KTPS, Koradi. | [14 empty] | 0 | 0 | 0 | 0.33866 | [21 empty] | 0 | 0 | 0.33866 | 0.33866
xxxi | Procurement of Weld overlay Flap Gate assembly in CHP 3x660MW, KTPS, Koradi. | [14 empty] | 0 | 0 | 0 | 0.5841 | [21 empty] | 0 | 0 | 0.5841 | 0.5841
E6 | Capital Spares |  |  |  |  | 89.62 | 89.62 | [10 empty] | 0 | [25 empty] | 0
| Procurement of critical insurance spares for Turbine & its critical auxiliaries for 3 x 660 MW, Koradi (4370001538 dtd. 18/06/2018 d.p. 21 Months) | [5 empty] | 89.62 | [8 empty] | 89.6234 | 0 | 89.6234 | 0 | [21 empty] | 88.736 | 0 | 0 | 88.736
E7 | Additional Capitalization |  |  |  |  | 57.88 | 57.88 | [10 empty] | 0 | [25 empty] | 0
i | Contruction of various infrastructure such as roads etc and public amenities in the rehabilitated villages of koradi and khasara |  |  |  |  | 13.1 | 13.1 | [8 empty] | 11.99 | 0.75 | 12.74 | [25 empty] | 0 | [9 empty] | Civil
ii | Procurement of 7 nos of school buses |  |  |  |  | 2 | 2 | [8 empty] | 1.3109 |  | 1.3109 | [22 empty] | 1.3109 |  |  | 1.3109 | [9 empty] | Project
iii | Development of green belt & fodder farm for fulfillment of environmental clearance of MoEF for Koradi 3x660MW |  |  |  |  | 3.16 | 3.16 | [8 empty] | 3.16 |  | 3.16 | [25 empty] | 0 | [9 empty] | Civil
iv | Provision of Ground Hopper & Short Conveyor Belt from Existing Stackyard 1 & 2 ti existing Main Stream i.e. BCN 4A/4B of CHP 3x660 MW, KTPS, Koradi |  |  |  |  | 4.36 | 4.36 | [8 empty] | 1.3066 | 3.0488 | 4.3555 | 0 | [21 empty] | 0 | 0 | 4.3555 | 4.3555
v | Provision of Ground Hopper & Conveyor Belt for Conveying Unloaded Coal form Open Wagon Tippler in CHP of Koradi Unit 8, 9 & 10. |  |  |  |  | 4.7 | 4.7 | [8 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 | [9 empty] | This scheme is cancelled
vi | Provision of Additional Facility for Manual Unloading Track in CHP of Koradi Unit No. 8, 9 & 10 |  |  |  |  | 5.25 | 5.25 | [8 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 | [9 empty] | Sanctioned amount of this scheme is diverted to "Procurement of Critical Insurance Spares for L&T-MHI Make Turbine for attending major overhauling work of Turbine at KTPS, 3x660MW Units Koradi."PO NO. 4385000537
vii | Construction of drains |  |  |  |  | 4.31 | 4.31 | [8 empty] | 0 | 0 | 0 | 0 | 2.7927 | [20 empty] | 0 | 0 | 0 | 0 | [9 empty] | Scheme capitalization is not done as on date but will be capitalised by 2022-2023
viii | Supply erection commissioning of medium voltage variable frequency drive for conveyors BCN 6A,6B,7A,7B in CHP 3x660MW |  |  |  |  | 17 | 17 | [8 empty] | 0 | 16.9859 | 16.9859 | 0 | [21 empty] | 0 | 0 | 16.9859 | 16.9859
ix | Supply, Installation & commissioning of 3D level sensors for first two ESP field hoppers |  |  |  |  | 4 | 4 | [8 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 | [9 empty] | Sanctioned amount of this scheme is diverted to "Procurement of Critical Insurance Spares for L&T-MHI Make Turbine for attending major overhauling work of Turbine at KTPS, 3x660MW Units Koradi."PO NO. 4385000537
F | Koradi TPS 3x660 MW Expansion Project – Construction of 2nd raising of existing Khasara Ash Bund from T.B.L. 308.50 M to T.B.L 312.00 M with construction of concrete dam (Broad crest weir structure), approach to drain wells and raising height of drain well No. 1, 2 & 3, construction of ash Compartment, cleaning of Khasara bund Nallah and construction of peripheral roads connecting to nearby villages for Khasara ash bund at TPS Koradi |  |  |  |  | 86.914 | 86.914 | [8 empty] | 60.44 | 15.21 | 75.65 | 4.61 | 12.4 | 0.63298 | [19 empty] | 0 | 75.6525 | 4.6055 | 80.258 | 12.4 | 0.63298 | [7 empty] | Excesses amounting to Rs. 6.72 Cr has been approved vide BR No. 2019/2946 Dt. 18.02.2019 and excesses amounting to Rs. 12.53 Cr has been approved vide BR No. MSPGCL/CS/BM-215/215.31 Dt. 05.01.2023.
G | Discharge of UDL | [14 empty] | 12.23 | 80.23 | 92.46 | 19.02 | 19.51 | [20 empty] | 12.23 | 80.23 | 19.02 | 111.48
H | Asset Addition due to change in classification of inventory | [16 empty] | 0 |  | 21.7503 | [23 empty] | 0 | [9 empty] | Koradi TPS 660MW is in receipt of varoius critical spares required for turbine and generator capital overhaul. These spares are procured in O&M Budget but the COH is differed due to some technical reasons resulting in inflation of inventory at Koradi TPS. hence, as a part of implementing advisory issued by Central Electricity Authority (CEA) regarding spare part management; Koradi TPS has undertaken the activity of identifying the critical spares. These spares are not easily available in the market & may not be utilised for routine maintenance work & are procured from OEM.
I | Medical Oxygen Gr&Cyl Ozonization Plant (Covid Related Work) | [16 empty] | 0 |  | 11.4034 | [23 empty] | 0 | 9.6702
| B) DPR Schemes | [16 empty] | 0 | [25 empty] | 0 | [10 empty] | N.A. |  | To be confirmed
| (i) Submitted to MERC | [16 empty] | 0 | [25 empty] | 0 | [10 empty] | N.A.
9 | Flue Gas Desulphurization FGD is for Unit 8, 9, 10 of 3x660MW Koradi TPS | DPR | MERC/CAPEX/FY 2020-21/WFH/SBR/05 | 2019-02-18 | 2020-05-31 | 940 | 940 |  |  | 2020-05-31 | [7 empty] | 0 | [25 empty] | 0 | [10 empty] | N.A.
9.1 | Flue Gas Desulphurization is for Unit 8, 9, 10 of 3x660MW Koradi TPS | Scheme | MERC/CAPEX/FY 2020-21/WFH/SBR/05 | 2019-02-18 | 2020-05-31 | 847.78 | 847.78 |  |  | 2020-05-31 | [7 empty] | 0 |  |  |  | 233.42 | 855.88 | 466.85 | [19 empty] | 0 |  |  | 233.42 | 855.88 | 466.85 | [5 empty] | WIP
| IDC | IDC | MERC/CAPEX/FY 2020-21/WFH/SBR/05 | 2019-02-18 | 2020-05-31 | 92.22 | 92.22 |  |  | 2020-05-31 | [7 empty] | 0 | [25 empty] | 0 |  |  |  | 0
HO DPR 13 | Construction of new admin building at Vidyut Bhavan, Katol Road, Nagpur | DPR | MERC/Capex/2021-2022/MSPGCL/063 | 2018-08-31 | 2022-02-18 | 113.91 | 57 |  |  | 2022-02-18 | [7 empty] | 0 | [25 empty] | 0 | [10 empty] | N.A.
HO DPR 13.1 | Construction of new admin building at Vidyut Bhavan, Katol Road, Nagpur |  |  | 2018-08-31 | 2022-02-18 | 108.48 | 54.24 |  |  | 2022-02-18 | [7 empty] | 0 | [25 empty] | 0 | [10 empty] | Not Initiated
| IDC |  |  | 2018-08-31 | 2022-02-18 | 5.43 | 2.76 |  |  | 2022-02-18 | [7 empty] | 0 | [25 empty] | 0 | [10 empty] | Not Initiated
18 | Improvement in Regenerative Air Pre-heater Performance at Unit # 9 of 3x660 MW, Koradi TPS | DPR | MERC/CAPEX/2022-2023/0469 | 2021-08-12 | 2022-10-06 | 15.869 | 15.869 |  |  | 2022-10-06 | [7 empty] | 0 | [25 empty] | 0 | [10 empty] | Capitalised
18.1 | Procurement of heating elements for RAPH installed in Unit 9 (660MW) at KTPS Koradi THROUGH LIMITED TENDER | Scheme | MERC/CAPEX/2022-2023/0469 | 2021-08-12 | 2022-10-06 | 15.33 | 15.33 |  |  | 2022-10-06 |  |  |  | • Reduction in loss due to Dry flue gas • Reduction in PA fan & FD loading. • Improvement in unit heat rate. |  |  |  | 0 |  | 11.8 | [23 empty] | 0 | 11.8 | [8 empty] | CAPITALIZED in F.Y.2022-23(4500119316) | Capitalised
18.2 | Replacement of heating elements for RAPH installed in Unit 9 (660MW) at KTPS Koradi | Scheme | MERC/CAPEX/2022-2023/0469 | 2021-08-12 | 2022-10-06 | 0.349 | 0.349 |  |  | 2022-10-06 | [7 empty] | 0 |  | 0.37 | [23 empty] | 0 | 0.37 | [8 empty] | CAPITALIZED in F.Y.2022-23[(a)4385000570 b)4385000571] | Capitalised
| IDC | IDC | MERC/CAPEX/2022-2023/0469 | 2021-08-12 | 2022-10-06 | 0.19 | 0.19 |  |  | 2022-10-06 | [7 empty] | 0 | [25 empty] | 0 | [10 empty] | Capitalised
19 | CHP Improvement (7 Nos) Schemes & Procurement of Bulldozers, Wheel Loaders and Hydraulic Cranes at CHP 3X660MW, KTPS, Koradi | DPR | MERC/CAPEX/MSPGCL/2024-25/0252 | 2023-10-31 | 2024-04-18 | 38.87 | 38.87 | [10 empty] | 0 | [25 empty] | 0 | [9 empty] | WILL be capitalized in F.Y.2024-12
19.1 | Sch-1: Revamping of Apron Feeder in CHP at 3X660MW, KTPS, Koradi. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0252 | 2023-10-31 | 2024-04-18 | 4.68 | 4.68 | [6 empty] | • System outages will be reduced. • Unloading time will be improved thereby reduce demurrages. • Demurrage charges will be reduced. • Maintenance cost of apron feeder will be reduced. |  |  |  | 0 |  |  |  | 4.68 | [21 empty] | 0 |  |  | 4.68 | [7 empty] | WIP
19.2 | Sch-2: Procurement of Hydraulic motors and pumps in CHP at 3X660 MW, KTPS, Koradi | Scheme | MERC/CAPEX/MSPGCL/2024-25/0252 | 2023-10-31 | 2024-04-18 | 4.44 | 4.44 | [6 empty] | • Reduction in demurrages. • Spare motor and pump ensure system availability in case of failure of existing one. • Increase plant availability & reduction in generation loss |  |  |  | 0 |  |  |  | 4.44 | [21 empty] | 0 |  |  | 4.44 | [7 empty] | WIP
19.3 | Sch-3: Capacity enhancement of Hydraulic motor of Apron Feeder in CHP, 3X660 MW, KTPS, Koradi | Scheme | MERC/CAPEX/MSPGCL/2024-25/0252 | 2023-10-31 | 2024-04-18 | 2.01 | 2.01 | [6 empty] | • Reduction in conveyor stream outages. • Reduction in demurrage charges. • Capacity of apron feeder will increase • Higher unloading rate • System availability will increase. • Repetitive maintenances will reduce. • Reduction in the inventory. |  |  |  | 0 |  |  |  | 2.01 | [21 empty] | 0 |  |  | 2.01 | [7 empty] | WIP
19.4 | Sch-4: Modification, supply and replacement of Transfer chutes in CHP 3x660MW KTPS, Koradi. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0252 | 2023-10-31 | 2024-04-18 | 4.39 | 4.39 | [6 empty] | • Reduction in conveyor stream outages. • Reduction in maintenance cost. • Reduction in cleaning problems. • Improvement in performance of unloading & reduction in generation loss. • Demurrage charges will be reduced. |  |  |  | 0 |  |  |  | 4.39 | [21 empty] | 0 |  |  | 4.39 | [7 empty] | WIP
19.5 | Sch-5: Design, supply, installation & commissioning of High performance IGUS energy chain system with chain flex cable for Tripper trolleys at CHP at 3x660 MW, KTPS, Koradi. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0252 | 2023-10-31 | 2024-04-18 | 4.37 | 4.37 | [6 empty] | • Less down time of critical auxiliary • Less maintenance cost • Increase in reliability • Uninterrupted coal bunkering • Less downtime of critical auxiliary • Increase in plant loadability and availability • Aversion of generation loss |  |  |  | 0 |  |  |  | 4.37 | [21 empty] | 0 |  |  | 4.37 | [7 empty] | WIP
19.6 | Sch-6: Procurement of B3-630 gear box for BCN 6 A/B in CHP at 3x660 MW, KTPS, Koradi. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0252 | 2023-10-31 | 2024-04-18 | 0.57 | 0.57 | [6 empty] | • Higher system availability with high bunker level • Spare gear box ensure system availability in case of failure of existing one. • Increase plant availability & reduction in generation loss |  |  |  | 0 |  |  |  | 0.57 | [21 empty] | 0 |  |  | 0.57 | [7 empty] | WIP
19.7 | Sch-7: Supply and installation of Belt tear detector system for conveyor belt in CHP 3x660 MW, KTPS, Koradi. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0252 | 2023-10-31 | 2024-04-18 | 1.18 | 1.18 | [6 empty] | • Costly conveyor will be protected • Reduction in conveyor stream outages. • Reduction in maintenance cost. • Reduction in cleaning problems. • Consumption of the costly conveyor belt will be reduced. |  |  |  | 0 |  |  |  | 1.18 | [21 empty] | 0 |  |  | 1.18 | [7 empty] | WIP
19.8 | Sch-8: Procurement of 5 Nos of Bulldozers BD 155 at CHP 3X660 MW Koradi Thermal Power station. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0252 | 2023-10-31 | 2024-04-18 | 12.83 | 12.83 | [6 empty] | • System outages will be reduced. • Unloading time will be improved thereby reduce demurrages. • Maximum power & efficiency of equipment based on load. • Service & Maintenance cost will be reduced. • Proper stack yard management Less diesel consumption |  |  |  | 0 |  |  |  | 12.83 | [21 empty] | 0 |  |  | 12.83 | [7 empty] | WIP
19.9 | Sch-9:- Procurement of 02 nos. of Wheel loaders at CHP 3X660 MW, KTPS, Koradi. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0252 | 2023-10-31 | 2024-04-18 | 3.07 | 3.07 | [6 empty] | • Unloading time will be improved thereby reduce demurrages. • Move more coal/material in less time with less fuel. • Service & Maintenance cost will be reduced. • Proper stack yard management Less diesel consumption |  |  |  | 0 |  |  |  | 3.07 | [21 empty] | 0 |  |  | 3.07 | [7 empty] | WIP
19.1 | Sch-10:- Procurement of 15 Ton & 20 Ton capacity hydraulic Cranes at CHP 3X660 MW, KTPS, Koradi. | Scheme | MERC/CAPEX/MSPGCL/2024-25/0252 | 2023-10-31 | 2024-04-18 | 0.69 | 0.69 | [6 empty] | • Safe and reliable operation. • Time saving and reduction in manpower • Down time of auxiliaries will reduced • System availability will increase. |  |  |  | 0 |  |  |  | 0.69 | [21 empty] | 0 |  |  | 0.69 | [7 empty] | WIP
| IDC | IDC | MERC/CAPEX/MSPGCL/2024-25/0252 | 2023-10-31 | 2024-04-18 | 0.64 | 0.64 | [10 empty] | 0 | [25 empty] | 0
20 | Construction of bridge cum bandhara across Pond No. 3 and allied works at Pond No. 3 at Koradi TPS | DPR | MERC/CAPEX/2024-25/MSPGCL/0250 | 2023-10-31 | 2024-04-18 | 33.116 | 33.116 | [10 empty] | 0 | [25 empty] | 0 | [9 empty] | DPR pertains to project civil
20.1 | Construction of cement concrete bridge cum bandhara alongwith gated arrangement. | Scheme | MERC/CAPEX/2024-25/MSPGCL/0250 | 2023-10-31 | 2024-04-18 | 14.75 | 14.75 | [10 empty] | 0 |  |  |  | 5 | 9.75 | [20 empty] | 0 |  |  | 5 | 9.75
20.2 | Construction of earthen embankment connecting bridge cum bandhara on both side of embankment by excavating soil / typha / silt from Pond No.3 & tree plantation. | Scheme | MERC/CAPEX/2024-25/MSPGCL/0250 | 2023-10-31 | 2024-04-18 | 14.3252 | 14.3252 | [10 empty] | 0 |  |  |  | 5 | 9.3252 | [20 empty] | 0 |  |  | 5 | 9.3252
20.3 | Providing structural steel pathway on the existing waste weir (west side of the Pond No.3) and roads connecting to bridge behind Pond No.3 and bridge cum bandhara. | Scheme | MERC/CAPEX/2024-25/MSPGCL/0250 | 2023-10-31 | 2024-04-18 | 2.4308 | 2.4308 | [10 empty] | 0 |  |  |  | 2.43 | 0.0008 | [20 empty] | 0 |  |  | 2.43 | 0.0008
| IDC | IDC | MERC/CAPEX/2024-25/MSPGCL/0250 | 2023-10-31 | 2024-04-18 | 1.61 | 1.61 | [10 empty] | 0 | [25 empty] | 0
6 | Procurement & replacement of Superheater Pass Economizer Coils (Modified Design) for Unit 8, 9 & 10 at 3x660MW KTPS, Koradi | DPR | Not Approved | 2024-01-31 |  | 147.78 | [11 empty] | 0 | [25 empty] | 0 | [9 empty] | 1. PO- 4370003294 placed by HO of Rs.48.14Cr for U8 on Dt.04.03.2024 2.Put up to MERC on Dt.17.10.2024
6.1 | Procurement & replacement of Superheater Pass Economizer Coils (Modified Design) for Unit 8, 9 & 10 at 3x660MW KTPS, Koradi | Scheme | Not Approved | 2024-01-31 |  | 145.15 | [7 empty] | 1) By modified design it will easy for inspection and maintenance of economizer coils, hence preventive measures can be taken on eoded tubes to avoid the BTL. 2) By implementing this scheme BTL will reduce in economizer coils. |  |  |  | 0 |  |  |  | 48.14 | 48.14 | 48.14 | [19 empty] | 0 |  |  | 48.14 | 48.14 | 48.14 | [5 empty] | N.A.
| IDC | IDC | Not Approved | 2024-01-31 |  | 2.63 | [11 empty] | 0 | [25 empty] | 0
7 | Improvement in Boiler Performance at U-8,9 & 10 KTPS, Koradi | DPR | MERC/CAPEX/MSPGCL/2023-24/0638 | 2024-04-12 |  | 62.929 | 62.929 | [10 empty] | 0 | [25 empty] | 0 | [9 empty] | PR SENT TO H.O.
7.1 | Scheme-1: Procurement of Blade Sets for ID, FD & PA Fans at 3x660MW Units. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0638 | 2024-04-12 |  | 11.34 | 11.34 | [6 empty] | 1) Availability & Reliability of fans will be increased 2) Breakdown of fans will be avoided. |  |  |  | 0 |  |  |  | 11.34 | [21 empty] | 0 |  |  | 11.34 | [6 empty] | 1. PO 4500135315 ( Supply ) placed by H.O. 2. PO 4500136167 and 4500136168 Dispatched
7.2 | Scheme-2: Procurement of RAPH Bottom Support Bearing Assembly at 3X660MW Units. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0638 | 2024-04-12 |  | 2.478 | 2.478 | [6 empty] | 1) Long shutdown of unit shall be avoided. As the availability of this bearing in stock shall be replaced one to one as and when required, which reduces the outage of unit and generation loss thereof. |  |  |  | 0 |  |  |  | 2.478 | [21 empty] | 0 |  |  | 2.478 | [6 empty] | 1. PR Sent to H.O. on Dt.19.07.2024 2. Put up technical committee at H.O.
7.3 | Scheme-3: Procurement of RAPH Top Guide Bearing Assembly at 3x660MW Units. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0638 | 2024-04-12 |  | 0.684 | 0.684 | [6 empty] | 1) Long shutdown of unit shall be avoided. As the availability of this bearing in stock shall be replaced one to one as and when required, which reduces the outage of unit and generation loss thereof. |  |  |  | 0 |  |  |  | 0.684 | [21 empty] | 0 |  |  | 0.684 | [6 empty] | 1. PR Sent to H.O. on Dt.19.07.2024 2. Put up technical committee at H.O. 3.H.O observations received
7.4 | Scheme-4: Procurement of RAPH Gear Box at 3x660MW Units. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0638 | 2024-04-12 |  | 3.44 | 3.44 | [6 empty] | 1) Long shutdown of unit shall be avoided. As the availability of this gearbox in stock shall be replaced one to one as and when required, which reduces the outage of unit and generation loss thereof. |  |  |  | 0 |  |  |  | 3.44 | [21 empty] | 0 |  |  | 3.44 | [6 empty] | 1. PR Sent to H.O. on Dt.11.06.2024 2. H.O. observations received on Dt.27.07.2024. 3. Reply to H.O. observations sent on Dt.18.10.2024. 4. CE release done. Dt.24.10.2024
7.5 | Scheme-5: Procurement of RAPH Spares at 3x660MW Units. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0638 | 2024-04-12 |  | 1.13 | 1.13 | [6 empty] | 1) Availability of these spares will keep RAPH internal sealing system in healthy condition. Which will reduce heat loss, erosion of internals of RAPH and reduce Fans loading. |  |  |  | 0 |  |  |  | 1.13 | [21 empty] | 0 |  |  | 1.13 | [6 empty] | 1. PR Sent to H.O. on Dt.13.07.2024 2. Reply to H.O. observations sent on Dt.Put up technical committee at H.O. 3. HO observation received Dt.31.10.2024
7.6 | Scheme-6: Procurement of Coal Burner Assembly with windbox air nozzles for Unit 8 & 9 at 3x660MW. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0638 | 2024-04-12 |  | 15.407 | 15.407 | [6 empty] | 1) Combustion tunning will improve 2) Reduction in tube leakages due to temperature excursion |  |  |  | 0 |  |  |  | 15.407 | [21 empty] | 0 |  |  | 15.407 | [6 empty] | 1. PR Sent to H.O. on Dt.13.07.2024 2. Put up technical committee at H.O.
7.7 | Scheme-7: Procurement of Boiler Circulation Pump (BCP) with Impeller & Diffuser at 3x660MW Units. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0638 | 2024-04-12 |  | 11.12 | 11.12 | [6 empty] | 1) 100% availability of all the Boiler Circulation Pumps will help to reduce fuel consumption during the start-up/light-up activities 2) Delay for synchronization will reduce by 2-3 hrs. |  |  |  | 0 |  |  |  | 11.12 | [21 empty] | 0 |  |  | 11.12 | [6 empty] | 1. PR Sent to H.O. on Dt.27.07.2024 2.Put up technical committee at H.O.
7.8 | Scheme-8: Procurement and Replacement of Heating Elements for RAPH Installed for Unit 8 at 3x660MW. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0638 | 2024-04-12 |  | 15.96 | 15.96 | [6 empty] | • Reduction in loss due to Dry flue gas • Reduction in PA fan & FD loading. • Improvement in unit heat rate. |  |  |  | 0 |  |  |  | 15.96 | [21 empty] | 0 |  |  | 15.96 | [6 empty] | 1. PR Sent to H.O. on Dt.27.07.2024 2. Put up technical committee at H.O.
| IDC | IDC | MERC/CAPEX/MSPGCL/2023-24/0638 | 2024-04-12 |  | 1.37 | 1.37 | [10 empty] | 0 | [25 empty] | 0
23 | Design, Engineering, Supply, Installation, Testing, Commissioning including all civil works for Natural resource treatment and Laboratory equipment with mandatory spares at Koradi TPS, 3 X 660 MW | DPR | MERC/CAPEX/MSPGCL/2023-24/0177 | 2022-11-16 | 2024-03-11 | 49.06 | 49.06 |  |  | 2024-03-11 | [7 empty] | 0 | [25 empty] | 0 | [9 empty] | 1. PR 1100142780 approved. 2. PO Dispatched Dt.10.10.2024
23.1 | Supply of Natural resource treatment and lab equipment for Water, Coal, Oil, Meteorology with supporting AI computing, all auxiliaries, and accessories. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0177 | 2022-11-16 | 2024-03-11 | 35.28 | 35.28 |  |  | 2024-03-11 | [7 empty] | 0 |  |  |  |  | 42.5744 | [20 empty] | 0 |  |  | 0 | 42.5744 | [5 empty] | *Audited PR sent to HO on Dt.22.02.2023 *Reply to observations sent to Ho on Dt.11.04.2024
23.2 | Supply of Mandatory spares on lump-sum basis. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0177 | 2022-11-16 | 2024-03-11 | 0.8 | 0.8 | [10 empty] | 0 |  |  |  |  | 0.944 | [20 empty] | 0 |  |  | 0 | 0.944
23.3 | Supply of Tools and Tackles on lump-sum basis. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0177 | 2022-11-16 | 2024-03-11 | 0.15 | 0.15 | [10 empty] | 0 |  |  |  |  | 0.177 | [20 empty] | 0 |  |  | 0 | 0.177
23.4 | Complete Civil Work with 10 KLD ETP/ STP on lump-sum basis. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0177 | 2022-11-16 | 2024-03-11 | 3.6 | 3.6 | [10 empty] | 0 |  |  |  | 4.25 | [21 empty] | 0 |  |  | 4.25 | 0 | [5 empty] | Tender under process at H.O.
23.5 | Services - Charges of Inland transport of plant and equipment on lump-sum basis. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0177 | 2022-11-16 | 2024-03-11 | 0.2 | 0.2 | [10 empty] | 0 |  |  |  |  | 0.236 | [20 empty] | 0 |  |  | 0 | 0.236
23.6 | Charges for Testing, Commissioning and PG Test of plant and equipment. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0177 | 2022-11-16 | 2024-03-11 | 0.05 | 0.05 | [10 empty] | 0 |  |  |  |  | 0.059 | [20 empty] | 0 |  |  | 0 | 0.059
| IDC | IDC | MERC/CAPEX/MSPGCL/2023-24/0177 | 2022-11-16 | 2024-03-11 | 0.82 | 0.82 |  |  | 2024-03-11 | [7 empty] | 0 | [25 empty] | 0
24 | Improvement in Regenerative Air Preheater Performance & Complete Replacement of NDCT fills at Unit # 10, Koradi TPS | DPR | MERC/CAPEX/MSPGCL/2023-24/0249 | 2022-11-16 | 2024-04-18 | 25.45 | 25.45 | [10 empty] | 0 | [25 empty] | 0
24.1 | Procurement of heating elements for RAPH installed in Unit 10 (660MW) at KTPS Koradi through OEM | Scheme | MERC/CAPEX/MSPGCL/2023-24/0249 | 2022-11-16 | 2024-04-18 | 12.23 | 12.23 | [6 empty] | • Reduction in loss due to Dry flue gas • Reduction in PA fan & FD loading. • Improvement in unit heat rate. |  |  |  | 0 |  |  | 14.521 | [22 empty] | 0 |  | 14.521 | [7 empty] | CAPITALIZED in F.Y.2023-24 Supply PO-44500126618(14.14Cr.) Work PO a)4550019652 b) 4550019653 (0.29Cr.) | Capitalised
24.2 | Complete Supply & Replacement of NDCT fills of U#10. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0249 | 2022-11-16 | 2024-04-18 | 13 | 13 | [10 empty] | 0 |  |  |  | 13 | [21 empty] | 0 |  |  | 13 | [6 empty] | Tender refloating under process | WIP
| IDC | IDC | MERC/CAPEX/MSPGCL/2023-24/0249 | 2022-11-16 | 2024-04-18 | 0.22 | 0.22 | [10 empty] | 0 | [25 empty] | 0
HO DPR 14 | Centralized Monitoring Solution | DPR | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-03-28 | 2023-11-02 | 69.309 | 69.309 |  |  | 2023-11-02 | [7 empty] | 0 | [25 empty] | 0 | [10 empty] | N.A.
HO DPR 14.1 | Centralized Monitoring Solution | Scheme | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-03-28 | 2023-11-02 | 66.009 | 66.009 |  |  | 2023-11-02 | [7 empty] | 0 |  |  |  |  | 10.994 | [20 empty] | 0 |  |  |  | 10.994 | [6 empty] | To be confirmed
| IDC | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-03-28 | 2023-11-02 | 3.3 | 3.3 |  |  | 2023-11-02 | [7 empty] | 0 | [25 empty] | 0 | [10 empty] | N.A.
HO DPR 15 | HMI (Human Machine Interface) Upgradation of ‘SSPA-T3000’ DCS (Distribution Control System), Rockwell make PLC System installed at 3x660MW Unit No. 8, 9 & 10 at Koradi TPS and HMI (Human Machine Interface) Upgradation of MaxDNA DCS System at Unit 8-9, CSTPS, Chandrapur | DPR | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-03-28 | 2023-10-09 | 56.02 | 55.61 | [10 empty] | 0 | [25 empty] | 0 | [9 empty] | 1. PR 1100136920, Enquiry opened. 2. To MPD for budget 12.09.2024, sent to Purchase 14.09.2024
HO DPR 15.1 | Supply: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-03-28 | 2023-10-09 | 10.52 | 10.52 | [10 empty] | 0 | [25 empty] | 0
HO DPR 15.2 | Works: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-03-28 | 2023-10-09 | 0.41 | 0.41 | [10 empty] | 0 | [25 empty] | 0
15.3 | HMI (Human Machine Interface) Upgradation of ‘SPPA-T3000’ DCS (Distributed Control System) installed at 3x660MW Unit- 8, 9 & 10 at Koradi TPS to match with the external aspects and process improvement | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-03-28 | 2023-10-09 | 24.74 | 24.33 | [6 empty] | The scheme is proposed as necessity Scheme which is essential for implementation to Keep the system up and running. |  |  |  | 0 |  |  |  |  | 24.33 | [20 empty] | 0 |  |  |  | 24.33 | [5 empty] | PR approval received on Dt.12.04.2024.enquiry 48175 dispatched LSD 10.05.2024 .ENQUIRY EXTENDED |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15.4 | Upgradation of Rockwell Make PLC System installed at 3x660MW ,Koradi TPS to match with the external aspects and process improvement.(C&I) | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-03-28 | 2023-10-09 | 20.2 | 20.2 | [6 empty] | The scheme is proposed as necessity Scheme which is essential for implementation to Keep the system up and running. |  |  |  | 0 |  |  |  | 20.2 | [21 empty] | 0 |  |  | 20.2 | [6 empty] | CHP PO-4370003368 DISP DT.-02/05/2024 CNI DPO -4370003322 DISP DT.-22/08/2024 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| IDC | IDC | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-03-28 | 2023-10-09 | 0.15 | 0.15 | [10 empty] | 0 | [25 empty] | 0
| Work of provision of platform beside railway siding at backside of chord cabin for loading of fly ash in railway wagon for ash utilization at 3x660 MW TPS, Koradi | [12 empty] | Scheme processed through ASH revenue fund but capitalized as NO-DPR scheme in FY 2022-23,however rectified in FY 2023-24. |  |  |  | 0 |  | 1.2838 | -1.28 | [22 empty] | 0 | 1.2838 | -1.28 | [7 empty] | Scheme processed through ASH revenue fund but capitalized as NO-DPR scheme in FY 2022-23,however rectified in FY 2023-24. |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Capital Exenditure schemes for in-principle clearance regarding "EPC contract for the wok of construction of quarters and development of KTPS colony at Koradi" under CAPEX scheme | DPR | MERC/CAPEX/MSPGCL/2024-12/0569 DTD.13.09.2024 |  | 45548 | 210.48 | 210.48 | [6 empty] | DPR pertains to Project Civil. |  |  |  | 0 |  |  |  | 50 | 150 | 10.48 | [19 empty] | 0 |  |  | 50 | 150 | 10.48 |  |  |  |  | DPR pertains to Project Civil. | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| IDC |  |  |  |  | 24.87 | [11 empty] | 0 | [25 empty] | 0
3 | Procurement of spares for L&T-MHI make Turbine for COH work of Turbine at KTPS, 3x660MW units Koradi | DPR | MERC/CAPEX/MSPGCL/2023-24/0639 |  |  | 35.84 |  |  |  | - |  |  |  | 1. PO- 4500136124 & 4550022732 dispatched |  |  |  | 0 | [25 empty] | 0 | [9 empty] | 1. PO- 4500136124 & 4550022732 dispatched
3.1 | Procurement of spares for L&T-MHI make Turbine for COH work of Turbine at KTPS, 3x660MW units Koradi | Scheme | MERC/CAPEX/MSPGCL/2023-24/0639 |  |  | 31.6358 |  |  |  | - |  |  |  | To optimize the Turbine System performance with respect to availability & reliability |  |  |  | 0 |  |  |  | 31.6358 | [21 empty] | 0 |  |  | 31.6358 | [6 empty] | 1. PO 4500136124 dispatched Dt.07.08.2024
3.2 | Procurement of HP Nozzle assembly for L&T-MHI Make Turbine installed at 3x660MW Units Koradi | Scheme | MERC/CAPEX/MSPGCL/2023-24/0639 |  |  | 4.189 |  |  |  | - |  |  |  | During capital overhaul of Unit-10 in the month of July-August-2023, on inspection it is observed that HP Nozzle assembly of HIP Turbine is completely damaged. As per OEM experts’ recommendation, the HP nozzle assembly needs to be spared to complete capital overhaul in stipulated time period and in view of last experience of U#10 COH. |  |  |  | 0 |  |  |  | 4.189 | [21 empty] | 0 |  |  | 4.189 | [6 empty] | 1. PO 4550022732 dispatched Dt.25.05.24
[18 empty] | 0 | [25 empty] | 0
| C) DPRs Yet to be submitted to MERC | [16 empty] | 0 | [25 empty] | 0
2 | Control & instrumentation related Various Upgradation schemes viz.Emission Monitoring & Water Quality Analysers ,Vibration Monitoring Schemes,Water Flow Monitoring etc. at 3X660MW, KTPS, Koradi | DPR |  |  |  | 26.62 | [11 empty] | 0 | [25 empty] | 0 | [9 empty] | 1. DPR sent to HO on Dt.10.06.2023 2. Third party vetting awaited. 3. Datagap reply sent to third party on Dt.17.02.2024. 4. Sent to E&S for vetting Sept 2023.
2.1 | Upgradation of Emission Monitoring Analysers | Scheme |  |  |  | 9.58 | [7 empty] | 1. To maintain parameters as per MPCB/CPCB Statutory norms 2.Reduction in Manpower Hrs required for troubleshooting |  |  |  | 0 |  |  |  |  | 9.58 | [20 empty] | 0 |  |  |  | 9.58
2.2 | Upgradation of Water Quality Analysers | Scheme |  |  |  | 5.33 | [7 empty] | 1. To maintain parameters as per MPCB/CPCB Statutory norms 2.Reduction in Manpower Hrs required for troubleshooting |  |  |  | 0 |  |  |  |  | 5.33 | [20 empty] | 0 |  |  |  | 5.33
2.3 | Revamping & Supply Of Upgraded VM7B Version of Vibration Monitoring Rack | Scheme |  |  |  | 4.84 | [7 empty] | The scheme is proposed as necessity Scheme which is essential for implementation to Keep the system up and running. |  |  |  | 0 |  |  |  |  | 4.84 | [20 empty] | 0 |  |  |  | 4.84
2.4 | Implementation of ‘Flow Monitoring System’ at 3x660MW Balance of Plant (BOP) Unit- 8, 9 & 10 at Koradi TPS | Scheme |  |  |  | 6.87 | [7 empty] | Reduction in Raw & DM water consumption Reduction in Manpower Hrs required for troubleshooting. |  |  |  | 0 |  |  |  |  | 6.87 | [20 empty] | 0 |  |  |  | 6.87
3 | CHP Improvement Scheme-I | DPR |  |  |  | 50.9 | [11 empty] | 0 | [25 empty] | 0 | [9 empty] | 1. DPR sent to HO on Dt.28.05.2024 2. Under scrutiny at H.O. 3. Admin query received Dt.11.11.2024
3.1 | Supply, Erection, Commissioning of set of Internals for Wagon Tipplers at CHP 3X660MW, KTPS, Koradi. | Scheme |  |  |  | 10.96 | [7 empty] | • Reduction in operational and maintenance cost. • Reduction in Coal Handling Plant downtime. • Reduction in wear & tear of wagon tippler internals • Improvement in coal flow in rainy season. • System outages will be reduced. • Life enhancement of auxiliary |  |  |  | 0 |  |  |  |  | 10.96 | [20 empty] | 0 |  |  |  | 10.96
3.2 | Supply, Erection, Commissioning of set of Internals for Side Arm Chargers at CHP 3X660MW, KTPS, Koradi. | Scheme |  |  |  | 3.54 | [7 empty] | • Reduction in operational and maintenance cost. • Reduction in Coal Handling Plant downtime. • Reduction in wear & tear of side arm charger internals • System outages will be reduced. • Life enhancement of auxiliary |  |  |  | 0 |  |  |  |  | 3.54 | [20 empty] | 0 |  |  |  | 3.54
3.3 | Supply, Erection, Commissioning of set of Internals for Wobbler Feeders at CHP 3X660MW, KTPS, Koradi. | Scheme |  |  |  | 4.96 | [7 empty] | • Improvement in performance of unloading & reduction in generation loss. • Demurrage charges will be reduced • Reduction in wear & tear of wobbler feeder internals • System outages will be reduced. • Life enhancement of auxiliary |  |  |  | 0 |  |  |  |  | 4.96 | [20 empty] | 0 |  |  |  | 4.96
3.4 | Supply, Erection, Commissioning of set of Internals for Apron Feeders at CHP 3X660MW, KTPS, Koradi. | Scheme |  |  |  | 15.55 | [7 empty] | • Reduction in operational and maintenance cost. • Reduction in Coal Handling Plant downtime. • Reduction in wear & tear of Apron Feeder internals • System outages will be reduced. • Life enhancement of auxiliary |  |  |  | 0 |  |  |  |  | 15.55 | [20 empty] | 0 |  |  |  | 15.55
3.5 | Supply, Erection, Commissioning of set of Internals for Impact Crushers at CHP 3X660MW, KTPS, Koradi. | Scheme |  |  |  | 9.63 | [7 empty] | • Reduction in operational and maintenance cost. • Reduction in Coal Handling Plant downtime. • Reduction in wear & tear of Impact Crusher internals • System outages will be reduced. • Life enhancement of auxiliary |  |  |  | 0 |  |  |  |  | 9.63 | [20 empty] | 0 |  |  |  | 9.63
3.6 | Supply, Erection, Commissioning of set of Internals for Stacker cum Reclaimers at CHP 3X660MW, KTPS, Koradi. | Scheme |  |  |  | 6.26 | [7 empty] | • Reduction in operational and maintenance cost. • Reduction in Coal Handling Plant downtime. • Reduction in wear & tear of Stacker cum reclaimer internals • System outages will be reduced. • Life enhancement of auxiliary |  |  |  | 0 |  |  |  |  | 6.26 | [20 empty] | 0 |  |  |  | 6.26
4 | Performance improvement and availability of various Auxiliaries of TG at 3x660MW KTPS Koradi. | DPR |  |  |  | 50.28 | [7 empty] | Scheme-1 (Detail Submission on Page No- 77of the DPR) Payback Period: Payback period = (Cost of capital spares/disallowance fixed cost saved per day per unit.) Payback Period = 3.25 / 2.01 = 1.61 ~ 02 Days Thus, the payback period comes out to be 02 Days. Scheme-2 (Detail Submission on Page No- 78of the DPR) Payback Period: Payback period = (Cost of capital spares/disallowance fixed cost saved per day per unit.) Payback Period = 7.30 / 2.01 = 3.63 ~ 04 Days Thus, the payback period comes out to be 04 Days. Scheme-3 (Detail Submission on Page No- 80of the DPR) Payback Period: Payback period = (Cost of capital spares/disallowance fixed cost saved per day per unit.) Payback Period = 10.54 / 1.207 = 8.73 ~ 09 Days Thus, the payback period comes out to be 09 Days. Scheme-4 (Detail Submission on Page No- 81of the DPR) Payback Period: Payback period = (Cost of capital spares/disallowance fixed cost saved per day per unit.) Payback Period = 2.279 / 0.105 = 21.7 ~ 22 Days Thus, the payback period comes out to be 22 Days. Scheme-5 (Detail Submission on Page No- 82of the DPR) Payback Period: Payback period = (Cost of capital spares/disallowance fixed cost saved per day per unit.) Payback Period = 7.83 / 2.01 = 3.89~ 04 Days Thus, the payback period comes out to be 04 Days. Scheme-6 (Detail Submission on Page No- 83of the DPR) Payback Period: Payback period = (Cost of capital spares/disallowance fixed cost saved per day per unit.) Payback Period = 14.86 / 0.804 = 18.49~ 18 Days Thus, the payback period comes out to be 18 Days. Scheme-7 (Detail Submission on Page No- 85of the DPR) As the scheme is for Process Improvement and to save our assets, exact cost benefit and payback period cannot be calculated. |  |  |  | 0 | [25 empty] | 0 | [9 empty] | 1. Board approval received dtd 30.08.2024 2. Put up to MERC on Dt.17.10.2024
4.1 | Performance improvement and availability of various Auxiliaries for Oil Systems of Main Turbine. | Scheme |  |  |  | 3.26 | [7 empty] |  No additional cost/modification in existing system.  Maintenance cost of will be reduced.  Generation losses will be reduced.  No costs overruns due to unavailability of equipments.  Inventory will reduce.  Improvement in Plant Loadability.  Minimum time required for system restoration.  Long Service life with minimum maintenance cost. |  |  |  | 0 |  |  |  |  | 3.26 | [20 empty] | 0 |  |  |  | 3.26 | [5 empty] | PR 1100162860 sent to Audit Dt.17.10.24
4.2 | Performance improvement and availability of various Auxiliaries of Generator System. | Scheme |  |  |  | 7.31 | [7 empty] |  No additional cost/modification in existing system.  Maintenance cost of will be reduced.  Generation losses will be reduced.  No costs overruns due to unavailability of equipments.  Inventory will reduce.  Improvement in Plant Loadability.  Minimum time required for system restoration.  Long Service life with minimum maintenance cost. |  |  |  | 0 |  |  |  |  | 7.31 | [20 empty] | 0 |  |  |  | 7.31 | [5 empty] | PR 1100162819 for Audit Dt.23.10.24
4.3 | Performance improvement and availability of Feed Water System. | Scheme |  |  |  | 10.54 | [7 empty] |  No additional cost/modification in existing system.  Maintenance cost of will be reduced.  Generation losses will be reduced.  No costs overruns due to unavailability of equipments.  Inventory will reduce.  Improvement in Plant Loadability.  Minimum time required for system restoration.  Long Service life with minimum maintenance cost. |  |  |  | 0 |  |  |  |  | 10.54 | [20 empty] | 0 |  |  |  | 10.54 | [5 empty] | PR 1100162749 for Audit Dt.23.10.24
4.4 | Performance improvement and availability of Vacuum System. | Scheme |  |  |  | 2.28 | [7 empty] |  No additional cost/modification in existing system.  Maintenance cost of will be reduced.  Generation losses will be reduced.  No costs overruns due to unavailability of equipments.  Inventory will reduce.  Improvement in Plant Loadability.  Minimum time required for system restoration.  Long Service life with minimum maintenance cost. |  |  |  | 0 |  |  |  |  | 2.28 | [20 empty] | 0 |  |  |  | 2.28 | [5 empty] | PR 1100162848 for Audit Dt.23.10.24
4.5 | Performance improvement and availability of CEP System. | Scheme |  |  |  | 7.83 | [7 empty] |  No additional cost/modification in existing system.  Maintenance cost of will be reduced.  Generation losses will be reduced.  No costs overruns due to unavailability of equipments.  Inventory will reduce.  Improvement in Plant Loadability.  Minimum time required for system restoration.  Long Service life with minimum maintenance cost. |  |  |  | 0 |  |  |  |  | 7.83 | [20 empty] | 0 |  |  |  | 7.83 | [5 empty] | PR 1100162808 for Audit Dt.23.10.24
4.6 | Procurement of Complete Pull out Assembly along with Impeller and wear ring of Cooling Water Pump. | Scheme |  |  |  | 14.87 | [7 empty] |  No additional cost/modification in existing system.  Maintenance cost of will be reduced.  Generation losses will be reduced.  No costs overruns due to unavailability of equipments.  Inventory will reduce.  Improvement in Plant Loadability.  Minimum time required for system restoration.  Long Service life with minimum maintenance cost. |  |  |  | 0 |  |  |  |  | 14.87 | [20 empty] | 0 |  |  |  | 14.87 | [5 empty] | PR 1100162801 for Audit Dt.23.10.24
4.7 | Procurement of complete assembly of HP and LP Elements for Atlas Copco make Compressors. | Scheme |  |  |  | 4.19 | [7 empty] |  No additional cost/modification in existing system.  Maintenance cost of will be reduced.  Generation losses will be reduced.  No costs overruns due to unavailability of equipments.  Inventory will reduce.  Improvement in Plant Loadability.  Minimum time required for system restoration.  Long Service life with minimum maintenance cost. |  |  |  | 0 |  |  |  |  | 4.19 | [20 empty] | 0 |  |  |  | 4.19 | [5 empty] | PR 1100162841 for Audit Dt.23.10.24
5 | Improvement in Wet ash evacuation system at 3x660MW Units, KTPS, Koradi | DPR |  |  |  | 21.19 | [11 empty] | 0 | [25 empty] | 0 | [9 empty] | 1. Sent to HO on Dt.15.01.2024. 2. Datagap received on Dt.26.09.2024. 3. Third party vetting awaited 4. Sent to EST
5.1 | Procurement & installation of Ash Slurry Series Pump Assembly with modified metallurgy and Critical Wet End Sub Assembly to enhance the performance & slurry disposal capacity. | Scheme |  |  |  | 7.53 | [7 empty] | • Wet Ash Evacuation System outages will be reduced. • Due to modified metallurgy, wear & tear of spares will be reduced, hence repetitive maintenance will be minimised. • Maximum ash slurry series pumps will be guaranteed available for ash disposal. • Work planning will be better. • Inventory of spares will be reduced as life of spares will be enhanced. • Due to modifications in internal spares design & MOC, leakages will be minimised that will reduce the wear & tear of other related parts and wastage of water. • Being unavailability of ash slurry pump series, it becomes mandatory to repair the damaged pump on priority that creates an emergency for maintenance activities. • Increased pump Head & ash disposal capacity will enhance the performance of ash evacuation system. • Increase in plant availability. |  |  |  | 0 |  |  |  |  | 7.53 | [20 empty] | 0 |  |  |  | 7.53
5.2 | Procurement & installation of Ash Slurry Series Pump Assembly with modified metallurgy along with Gear Box, Fluid Coupling & Motor (4’th Series) and Critical Wet End Sub Assembly to enhance the performance & slurry disposal capacity. | Scheme |  |  |  | 2.51 | [7 empty] | • Wet Ash Evacuation System outages will be reduced. • Due to modified metallurgy, wear & tear of spares will be reduced, hence repetitive maintenance will be minimised. • Due to 4’th series, maximum ash slurry series pumps will be guaranteed available for ash disposal. • Work planning will be better. • Inventory of spares will be reduced as life of spares will be enhanced. • Due to modifications in internal spares design & MOC, leakages will be minimised that will reduce the wear & tear of other related parts and wastage of water. • Being unavailability of ash slurry pump series, it becomes mandatory to repair the damaged pump on priority that creates an emergency for maintenance activities. • Increased pump Head & ash disposal capacity will enhance the performance of ash evacuation system. • Increase plant availability. |  |  |  | 0 |  |  |  |  | 2.51 | [20 empty] | 0 |  |  |  | 2.51
5.3 | Procurement & installation of Overflow Transfer Pump Assembly with upgradation in metallurgy and Critical Wet End Sub Assembly to enhance the performance. | Scheme |  |  |  | 3.59 | [7 empty] | • Wet Ash Evacuation System outages will be reduced. • Ash water overflowing & spreading will be avoided due to installation of higher capacity pumps. • Due to modified metallurgy, wear & tear of spares will be reduced, hence repetitive maintenance will be minimised. • Due to installation of higher capacity pumps, cleaning & housekeeping in bottom ash area, delay in maintenance activities can be minimised. • Hazardous situation due to unsafe work condition will be eliminated. • Work planning will be better. • Inventory of spares will be reduced as life of spares will be enhanced. • Due to modifications in internal spares design & MOC, leakages will be minimised that will reduce the wear & tear of other related parts and wastage of water. • Being unavailability of spare Overflow Transfer Pump, it becomes mandatory to repair the damaged pump on priority that creates an emergency for maintenance activities. • Modified metallurgy & capacity will enhance the performance of ash evacuation system. • Increase plant availability. |  |  |  | 0 |  |  |  |  | 3.59 | [20 empty] | 0 |  |  |  | 3.59
5.4 | Procurement & installation of IAC Compressor Assembly: Model –ZR110 STD 7.5 IMD Atlas Copco Make Oil free water cooled screw air compressor with inbuilt atlas copco make heat of compression single drum rotator air dryer to enhance the performance. | Scheme |  |  |  | 7.56 | [7 empty] | • Damaged spares when replaced, it does not give its full efficiency as the allied spares have been completed it noticeable life or worn out up to the remarkable extent & may fail at any time. Hence, replacement of complete assembly will give maximum performance & reliability. • IAC availability will be increased that will lead to ash evacuation system smooth operation. • Downtime will be reduced thereby reduction in wear & tear of spares. • Work planning will be better hence maintenance cost will be reduced. • Due to minimized wear & tear, spares breakage will be reduced. • System availability will be increased & system outages will be reduced. • Due to frequent failures of IAC, it becomes mandatory to repair the damaged one on priority that creates an emergency for maintenance activities. • By implementing above scheme, there will be substantial reduction in outages of the IAC which will confirm improvement in the performance of Ash Handling Plant. |  |  |  | 0 |  |  |  |  | 7.56 | [20 empty] | 0 |  |  |  | 7.56
6 | HMI Upgradation of Diasys Netmation DCS at 3x660MW KTPS Koradi Units 8,9 & 9 | DPR |  |  |  | 77.15 | [11 empty] | 0 | [25 empty] | 0 | [9 empty] | 1. DPR sent to HO on Dt.10.01.2024 2. Datagap received on Dt.16.04.2024 3. Reply sent to H.O. 08.08.2024 4. Third party vetting report sent to H.O.
6.1 | HMI Upgradation of Diasys Netmation DCS at 3x660MW KTPS Koradi Units 8,9 & 10 | Scheme |  |  |  | 77.15 | [7 empty] | The scheme is proposed as necessity Scheme which is essential for implementation to Keep the system up and running. |  |  |  | 0 |  |  |  |  | 77.15 | [20 empty] | 0 |  |  |  | 77.15
7 | Improvement in Dry ash evacuation system at 3x660MW Units, KTPS, Koradi | DPR |  |  |  | 29.57 | [11 empty] | 0 | [25 empty] | 0 | [9 empty] | 1. DPR sent to HO on Dt.26.10.2023 2. Datagaps received on dt.02.04.2024 3. Reply sent to H.O. on Dt.11.07.2024. 4. Third party vetting report sent to H.O. 5. Processed for approval
7.1 | Procurement of Ingersoll Rand Make Transport Air Compressors Critical/Non-Critical Spares sub-assembly for performance improvement. | Scheme |  |  |  | 29.57 | [7 empty] | 1. TAC availabilty will be increased that will lead to dry ash evacuation system smooth operation. 2. Downtime will reduced thereby reduction in wear tear of spares |  |  |  | 0 |  |  |  |  | 29.57 | [20 empty] | 0 |  |  |  | 29.57 | [5 empty] | 1. PR send to TC Dt.06.11.2024 2. PR to Purchase for section compliance Dt.11.11.2024 3. PR to Audit Dt.15.11.2024
8 | MSERW Pipes for Garlanding arrangement | DPR |  |  |  | 98.83 | [11 empty] | 0 | [25 empty] | 0 | [9 empty] | 1. Third party vetting sent to H.O. 2. DPR resubmitted on.Dt.14.02.2024 3. Datagap received on Dt.22.05.2024
8.1 | Work of Garlanding arrangement to changeover ash slurry feed points for even filling of pond by providing MSERW Pipes along the periphery of Ash Bund Dyke Wall at Khasara Ash Bund. | Scheme |  |  |  | 98.83 | [7 empty] | • Uniform ash deposition will be done in ash bund. • Excessive pressurization of ash water accumulated in specific area will be eliminated. • Ash spreads in layers enabling vertical filling, hence land requirement is reduced. • Due to uniform ash deposition, more margin will be made available for ash accumulation. • No water releases out due to uniform deposition, hence no need for water retaining walls. • Reduced leaches at the ash disposal area. Hence dyke wall can be protected. • Frequent diversion of dropping ends of ash slurry pipelines will be eliminated. Hence, Maintenance cost will be reduced. • In order to have effective drainage of clear water, inspection & maintenance of drain well can be easily carried out. • Ash bund area slope can be maintained towards Waste-Weir side due to feasibility of various dropping points made available. • Improvement in structural stability and safety of ash bund can be ensured. • Lower velocity, hence longer life of pipe line. • Raising of ash bund dyke wall can be done uniformly. • It will enhance the feasibility of ash lifting and therefore maximum ash utilization. • Ash slurry disposal will be done effectively as per the lagoons availability & margin for ash deposition. • Due to garlanding of pipelines, availability of dropping ends for ash deposition. |  |  |  | 0 |  |  |  |  | 98.83 | [20 empty] | 0 |  |  |  | 98.83
9 | Capacity Enhancement & Performance optimization at WTP 3X660MW,KTPS,Koradi | DPR |  |  |  | 78.19 | [11 empty] | 0 | [25 empty] | 0 | [9 empty] | 1. *DPR sent to HO on Dt.23.11.2023. 2. Datagap received on Dt.10.06.2024. 3. Reply sent to H.O. on Dt.16.08.2024 4. Third party vetting report sent to H.O.
9.1 | Capacity enhancement of DM water stream in WTP at 3X660MW, KTPS, Koradi. | Scheme |  |  |  | 58.94 | [7 empty] | • Prevention or minimising the unforeseen failures • Conservation and protection of natural resources |  |  |  | 0 |  |  |  |  | 58.94 | [20 empty] | 0 |  |  |  | 58.94
9.2 | Capacity enhancement Condensate polishing unit regeneration area in WTP at 3X660 MW, KTPS, Koradi | Scheme |  |  |  | 13.41 | [7 empty] | • Flexibility of system shall be available for Resin regeneration. |  |  |  | 0 |  |  |  |  | 13.41 | [20 empty] | 0 |  |  |  | 13.41
9.3 | Provision of Ozone generating plant of 1.0 Kg capacity in WTP at 3X660 MW, KTPS, Koradi | Scheme |  |  |  | 5.84 | [7 empty] | . Reduced microbiological impurities. . Do not have any adverse impact on DM plant performance like chlorine gas. . No adverse effect associated auxiliaries due to sludge formation from other disinfectant. . No adverse health hazard effect. . Prevent algae and bio growth. |  |  |  | 0 |  |  |  |  | 5.84 | [20 empty] | 0 |  |  |  | 5.84
10 | DPR for Construction of CC Road alongwith RCC Drain, CC platform for heavy machinery movement at 3x660 MW, TPS, Koradi | DPR |  |  |  | 33.57 | [11 empty] | 0 | [25 empty] | 0 | [9 empty] | 1. Revised Audited DPR sent to Civil-III. DPR HO on Dt.04.11.2023 2. Third Party vetting Certificate sent to HO on Dt.26.04.2023.
10.1 | DPR for Construction of CC Road alongwith RCC Drain, CC platform for heavy machinery movement at 3x660 MW, TPS, Koradi | Scheme |  |  |  | 33.57 | [7 empty] | 1. Vehicle will move in safe condition 2. Accidents/casualities will be avoided by providing cement/concrete 3. Regular maintainance cost will be zero 4. Air/ Enviornmental pollution will be zero |  |  |  | 0 |  |  |  |  | 33.57 | [20 empty] | 0 |  |  |  | 33.57
11 | Improvement in Coal Mill Performance-I | DPR |  |  |  | 30.87 | [11 empty] | 0 | [25 empty] | 0 | [9 empty] | 1. DPR sent to HO on Dt.17.01.2023 2. Third party vetting certificate sent to HO on Dt. 28.04.2023. 3. Under scrutiny at HO
11.1 | Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi through OEM. | Scheme |  |  |  | 6.15 | [7 empty] | 1) By implementing this scheme the availability and loadability of Coal Mills will Increase. 2) Generation loss will reduce on account of coal mills |  |  |  | 0 |  |  |  |  | 6.15 | [20 empty] | 0 |  |  |  | 6.15 | [5 empty] | 1. Under scrutiny at HO
11.2 | Procurement of Mill Rotary Separator Blades for coal mill MVM 32R at 3x660 MW, KTPS, Koradi through open tender | Scheme |  |  |  | 4.01 | [7 empty] | 1) By implementing this scheme one spares assembly will be available in stock which will ensure availability of auxiliary. 2) In case of failure of existing assembly, the outage till will reduce, as the available assembly will be replaced one to one. |  |  |  | 0 |  |  |  |  | 4.01 | [20 empty] | 0 |  |  |  | 4.01 | [5 empty] | 1. Under scrutiny at HO
11.3 | Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi through OEM. | Scheme |  |  |  | 14.57 | [7 empty] | 1) By implementing this scheme the availability and loadability of Coal Mills will Increase. 2) Generation loss will reduce on account of coal mills |  |  |  | 0 |  |  |  |  | 14.57 | [20 empty] | 0 |  |  |  | 14.57 | [5 empty] | 1. Under scrutiny at HO
11.4 | Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi through OEM | Scheme |  |  |  | 6.14 | [7 empty] | 1) By implementing this scheme the availability and loadability of Coal Mills will Increase. 2) Generation loss will reduce on account of coal mills |  |  |  | 0 |  |  |  |  | 6.14 | [20 empty] | 0 |  |  |  | 6.14 | [5 empty] | 1. Under scrutiny at HO
12 | Improvement in Boiler performance-II at 3X660MW,KTPS,Koradi | DPR |  |  |  | 32.37 | [11 empty] | 0 | [25 empty] | 0 | [9 empty] | DPR under preparation | Not Initiated
12.1 | Scheme1:Procurement of Coal compartment assembly for Unit8 at 3x660MW KTPS, Koradi | Scheme |  |  |  | 12.7 | [7 empty] | 1) Combustion tunning will improve 2) Reduction in tube leakages due to temperature excursion |  |  |  | 0 |  |  |  |  | 12.7 | [20 empty] | 0 |  |  |  | 12.7 | [6 empty] | Not Initiated
12.2 | Scheme2:Procurement of blade sets for ID, FD & PA Fan at 3x660 MW, Units at KTPS Koradi through OEM. | Scheme |  |  |  | 11.34 | [7 empty] | 1) Availability & Reliability of fans will be increased 2) Breakdown of fans will be avoided. |  |  |  | 0 |  |  |  |  | 11.34 | [20 empty] | 0 |  |  |  | 11.34 | [6 empty] | Not Initiated
12.3 | Scheme3:Procurement of RAPH internal Spares for 3X660MW units at KTPS Koradi through OEM (Qty- 6 Sets) | Scheme |  |  |  | 1.13 | [7 empty] | 1) Availability of these spares will keep RAPH internal sealing system in healthy condition. Which will reduce heat loss, erosion of internals of RAPH and reduce Fans loading. |  |  |  | 0 |  |  |  |  | 1.13 | [20 empty] | 0 |  |  |  | 1.13 | [6 empty] | Not Initiated
12.4 | Scheme4:Procurement of RAPH Sector plate with Actuating mechanism assembly for Unit9 3 X 660MW Units at KTPS, Koradi. | Scheme |  |  |  | 7.2 | [7 empty] | 1) Availability of these spares will keep RAPH internal sealing system in healthy condition. Which will reduce heat loss, erosion of internals of RAPH and reduce Fans loading. |  |  |  | 0 |  |  |  |  | 7.2 | [20 empty] | 0 |  |  |  | 7.2 | [6 empty] | Not Initiated
13 | Improvement in Coal Mill performance-II at 3X660MW,KTPS,Koradi | DPR |  |  |  | 26.05 | [11 empty] | 0 | [25 empty] | 0 | [9 empty] | 1. Sent to H.O.on Dt.04.10.2024
13.1 | Procurement of FLENDER make Gearbox model kmp-450 along with motor for coal mill MVM32R at 3x660mw KTPS, koradi through OEM. | Scheme |  |  |  | 20.91 | [7 empty] | 1) With availability of gear box, and motor, Outage/down time will reduce. 2) With availability of gear box and motor availability of Coal Mill will get increase. 3) With availability of gear box, and motor generation loss on account of mill will reduce. |  |  |  | 0 |  |  |  |  | 20.91 | [20 empty] | 0 |  |  |  | 20.91 | [5 empty] | Proposal not initiated yet | Not Initiated
13.2 | Procurement of complete set of couplings for PA, ID & FD fans at 3X660MW units at KTPS Koradi through OEM | Scheme |  |  |  | 5.14 | [7 empty] | 1)With availability of another spare ID, FD & PA Fan couplings the reliability of operation will increase. Also, in case of major work in running fan, by replacing with spare couplings, availability of fans will increase. 2)Reduction in auxiliary down time. 3)Reduction in generation loss due to outages |  |  |  | 0 |  |  |  |  | 5.14 | [20 empty] | 0 |  |  |  | 5.14 | [5 empty] | Proposal not initiated yet | Not Initiated
14 | Improvement in Coal Mill performance-III at 3X660MW,KTPS,Koradi | DPR |  |  |  | 37.86 | [11 empty] | 0 | [25 empty] | 0 | [9 empty] | DPR under preparation | Not Initiated
14.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | Scheme |  |  |  | 6.15 | [7 empty] | 1) Combustion tunning will improve 2) Reduction in tube leakages due to temperature excursion |  |  |  | 0 |  |  |  |  | 6.15 | [20 empty] | 0 |  |  |  | 6.15 | [5 empty] | Proposal not initiated yet
14.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | Scheme |  |  |  | 14.57 | [7 empty] | 1) Availability & Reliability of fans will be increased 2) Breakdown of fans will be avoided. |  |  |  | 0 |  |  |  |  | 14.57 | [20 empty] | 0 |  |  |  | 14.57 | [5 empty] | Proposal not initiated yet
14.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | Scheme |  |  |  | 6.14 | [7 empty] | 1) Reduction in loss due to Dry flue gas 2)Reduction in PA fan & FD loading. 3)Improvement in unit heat rate. |  |  |  | 0 |  |  |  |  | 6.14 | [20 empty] | 0 |  |  |  | 6.14 | [5 empty] | Proposal not initiated yet
14.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit10 at 3x660 MW, KTPS, Koradi | Scheme |  |  |  | 1 | [7 empty] | 1) Improvement in heat rate 2) Improvement in boiler efficiency |  |  |  | 0 |  |  |  |  | 1 | [20 empty] | 0 |  |  |  | 1 | [5 empty] | Proposal not initiated yet
14.5 | Scheme5:Procurement of Complete MRHS System along with Pneumatic Compressors at 3x660 MW, KTPS, Koradi | Scheme |  |  |  | 10 | [7 empty] | 1) Availability of these spares will keep RAPH internal sealing system in healthy condition. Which will reduce heat loss, erosion of internals of RAPH and reduce Fans loading. |  |  |  | 0 |  |  |  |  | 10 | [20 empty] | 0 |  |  |  | 10 | [5 empty] | Proposal not initiated yet
15 | Improvement in Boiler performance-III at 3X660MW,KTPS,Koradi | DPR |  |  |  | 57.24 | [11 empty] | 0 | [25 empty] | 0 | [9 empty] | DPR under preparation | Not Initiated
15.1 | Scheme1:Procurement of Coal compartment assembly for Unit8at 3x660MW KTPS, Koradi | Scheme |  |  |  | 12.7 | [7 empty] | 1) Combustion tunning will improve 2) Reduction in tube leakages due to temperature excursion |  |  |  | 0 | [5 empty] | 12.7 | [19 empty] | 0 |  |  |  |  | 12.7 |  |  |  |  | Proposal not initiated yet | Not Initiated
15.2 | Scheme2:Procurement of blade sets for ID, FD & PA Fan at 3x660 MW, Units at KTPS Koradi through OEM. | Scheme |  |  |  | 11.34 | [7 empty] | 1) Availability & Reliability of fans will be increased 2) Breakdown of fans will be avoided. |  |  |  | 0 | [5 empty] | 11.34 | [19 empty] | 0 |  |  |  |  | 11.34 |  |  |  |  | Proposal not initiated yet | Not Initiated
15.3 | Scheme3:Procurement and replacement of heating elements for RAPH installed in Unit 9 (660MW) at KTPS Koradi THROUGH OEM/OES (Qty- 2 Sets) | Scheme |  |  |  | 16 | [7 empty] | 1) Reduction in loss due to Dry flue gas 2)Reduction in PA fan & FD loading. 3)Improvement in unit heat rate. |  |  |  | 0 | [5 empty] | 16 | [19 empty] | 0 |  |  |  |  | 16 |  |  |  |  | Proposal not initiated yet | Not Initiated
15.4 | Scheme4:Procurement of HP valves, safety valves and ERV's for 3X660MW units at KTPS Koradi through OEM | Scheme |  |  |  | 10 | [7 empty] | 1) Improvement in heat rate 2) Improvement in boiler efficiency |  |  |  | 0 | [5 empty] | 10 | [19 empty] | 0 |  |  |  |  | 10 |  |  |  |  | Proposal not initiated yet | Not Initiated
15.5 | Scheme5:Procurement of RAPH Sector plate with Actuating mechanism assembly for Unit8 3 X 660MW Units at KTPS, Koradi. | Scheme |  |  |  | 7.2 | [7 empty] | 1) Availability of these spares will keep RAPH internal sealing system in healthy condition. Which will reduce heat loss, erosion of internals of RAPH and reduce Fans loading. |  |  |  | 0 | [5 empty] | 7.2 | [19 empty] | 0 |  |  |  |  | 7.2 |  |  |  |  | Proposal not initiated yet | Not Initiated
15 | Improvement in Coal Mill performance-IV at 3X660MW,KTPS,Koradi | DPR |  |  |  | 27.86 | [11 empty] | 0 | [25 empty] | 0 | [9 empty] | DPR under preparation
15.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | Scheme |  |  |  | 6.15 | [7 empty] | 1) By implementing this scheme the availability and loadability of Coal Mills will Increase. 2) Generation loss will reduce on account of coal mills |  |  |  | 0 | [5 empty] | 6.15 | [19 empty] | 0 |  |  |  |  | 6.15 |  |  |  |  | Proposal not initiated yet | Not Initiated
15.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | Scheme |  |  |  | 14.57 | [7 empty] | 1) By implementing this scheme the availability and loadability of Coal Mills will Increase. 2) Generation loss will reduce on account of coal mills |  |  |  | 0 | [5 empty] | 14.57 | [19 empty] | 0 |  |  |  |  | 14.57 |  |  |  |  | Proposal not initiated yet | Not Initiated
15.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | Scheme |  |  |  | 6.14 | [7 empty] | 1) By implementing this scheme the availability and loadability of Coal Mills will Increase. 2) Generation loss will reduce on account of coal mills |  |  |  | 0 | [5 empty] | 6.14 | [19 empty] | 0 |  |  |  |  | 6.14 |  |  |  |  | Proposal not initiated yet | Not Initiated
15.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit8 at 3x660 MW, KTPS, Koradi | Scheme |  |  |  | 1 | [7 empty] | 1) Combustion tunning of furnace will improve which will further reduce BTL due to temp excursion 2) Mill availability will improve |  |  |  | 0 | [5 empty] | 1 | [19 empty] | 0 |  |  |  |  | 1 |  |  |  |  | Proposal not initiated yet | Not Initiated
16 | Improvement in Coal Mill performance-V at 3X660MW,KTPS,Koradi | DPR |  |  |  | 27.86 | [11 empty] | 0 | [25 empty] | 0 | [9 empty] | DPR under preparation
16.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | Scheme |  |  |  | 6.15 | [7 empty] | 1) By implementing this scheme the availability and loadability of Coal Mills will Increase. 2) Generation loss will reduce on account of coal mills |  |  |  | 0 | [6 empty] | 6.15 | [18 empty] | 0 | [5 empty] | 6.15 |  |  |  | Proposal not initiated yet | Not Initiated
16.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | Scheme |  |  |  | 14.57 | [7 empty] | 1) By implementing this scheme the availability and loadability of Coal Mills will Increase. 2) Generation loss will reduce on account of coal mills |  |  |  | 0 | [6 empty] | 14.57 | [18 empty] | 0 | [5 empty] | 14.57 |  |  |  | Proposal not initiated yet | Not Initiated
16.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | Scheme |  |  |  | 6.14 | [7 empty] | 1) By implementing this scheme the availability and loadability of Coal Mills will Increase. 2) Generation loss will reduce on account of coal mills |  |  |  | 0 | [6 empty] | 6.14 | [18 empty] | 0 | [5 empty] | 6.14 |  |  |  | Proposal not initiated yet | Not Initiated
16.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit9 at 3x660 MW, KTPS, Koradi | Scheme |  |  |  | 1 | [7 empty] | 1) Combustion tunning of furnace will improve which will further reduce BTL due to temp excursion 2) Mill availability will improve |  |  |  | 0 | [6 empty] | 1 | [18 empty] | 0 | [5 empty] | 1 |  |  |  | Proposal not initiated yet | Not Initiated
17 | Improvement in Boiler performance-IV at 3X660MW,KTPS,Koradi | DPR |  |  |  | 64.954 | [11 empty] | 0 | [25 empty] | 0 | [9 empty] | DPR under preparation
17.1 | Scheme1:Procurement of Coal compartment assembly for Unit8 at 3x660MW KTPS, Koradi | Scheme |  |  |  | 12.7 | [7 empty] | 1) Combustion tunning will improve 2) Reduction in tube leakages due to temperature excursion |  |  |  | 0 | [7 empty] | 12.7 | [17 empty] | 0 | [6 empty] | 12.7 |  |  | Proposal not initiated yet | Not Initiated
17.2 | Scheme2:Procurement of blade sets for ID, FD & PA Fan at 3x660 MW, Units at KTPS Koradi through OEM. | Scheme |  |  |  | 11.34 | [7 empty] | 1) Availability & Reliability of fans will be increased 2) Breakdown of fans will be avoided. |  |  |  | 0 | [7 empty] | 11.34 | [17 empty] | 0 | [6 empty] | 11.34 |  |  | Proposal not initiated yet | Not Initiated
17.3 | Scheme3:Procurement of RAPH bottom support bearing assembly for 3X660MW units at KTPS Koradi through OEM (Qty- 2 Sets) | Scheme |  |  |  | 2.47 | [7 empty] | 1) Long shutdown of unit shall be avoided. As the availability of this bearing in stock shall be replaced one to one as and when required, which reduces the outage of unit and generation loss thereof. |  |  |  | 0 | [7 empty] | 2.47 | [17 empty] | 0 | [6 empty] | 2.47 |  |  | Proposal not initiated yet | Not Initiated
17.4 | Scheme4:Procurement of RAPH top guide bearing assembly for 3X660MW units at KTPS Koradi | Scheme |  |  |  | 0.684 | [7 empty] | 1) Long shutdown of unit shall be avoided. As the availability of this bearing in stock shall be replaced one to one as and when required, which reduces the outage of unit and generation loss thereof. |  |  |  | 0 | [7 empty] | 0.684 | [17 empty] | 0 | [6 empty] | 0.684 |  |  | Proposal not initiated yet | Not Initiated
17.5 | Scheme5:Procurement of RAPH Gear Box for 3X660MW units at KTPS Koradi through OEM (Qty- 1 Sets) | Scheme |  |  |  | 3.44 | [7 empty] | 1) Long shutdown of unit shall be avoided. As the availability of this gearbox in stock shall be replaced one to one as and when required, which reduces the outage of unit and generation loss thereof. |  |  |  | 0 | [7 empty] | 3.44 | [17 empty] | 0 | [6 empty] | 3.44 |  |  | Proposal not initiated yet | Not Initiated
17.6 | Scheme6:Procurement of RAPH Sector plate with Actuating mechanism assembly for Unit10 at 3 X 660MW Units at KTPS, Koradi. | Scheme |  |  |  | 7.2 | [7 empty] | 1) Availability of these spares will keep RAPH internal sealing system in healthy condition. Which will reduce heat loss, erosion of internals of RAPH and reduce Fans loading. |  |  |  | 0 | [7 empty] | 7.2 | [17 empty] | 0 | [6 empty] | 7.2 |  |  | Proposal not initiated yet | Not Initiated
17.7 | Scheme7:Procurement and replacement of heating elements for RAPH installed in Unit 10 (660MW) at KTPS Koradi THROUGH OEM/OES (Qty- 2 Sets) | Scheme |  |  |  | 16 | [7 empty] | • Reduction in loss due to Dry flue gas • Reduction in PA fan & FD loading. • Improvement in unit heat rate. |  |  |  | 0 | [7 empty] | 16 | [17 empty] | 0 | [6 empty] | 16 |  |  | Proposal not initiated yet | Not Initiated
17.8 | Scheme8:Procurement of Boiler Circulating Pump (1 Nos) | Scheme |  |  |  | 11.12 | [7 empty] | 1) 100% availability of all the Boiler Circulation Pumps will help to reduce fuel consumption during the start-up/light-up activities 2) Delay for synchronization will reduce by 2-3 hrs. |  |  |  | 0 | [7 empty] | 11.12 | [17 empty] | 0 | [6 empty] | 11.12 |  |  | Proposal not initiated yet | Not Initiated
18 | Improvement in Coal Mill performance-VI at 3X660MW,KTPS,Koradi | DPR |  |  |  | 27.86 | [11 empty] | 0 | [25 empty] | 0 | [9 empty] | DPR under preparation
18.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | Scheme |  |  |  | 6.15 | [7 empty] | 1) By implementing this scheme the availability and loadability of Coal Mills will Increase. 2) Generation loss will reduce on account of coal mills |  |  |  | 0 | [8 empty] | 6.15 | [16 empty] | 0 | [7 empty] | 6.15 |  | Proposal not initiated yet | Not Initiated
18.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | Scheme |  |  |  | 14.57 | [7 empty] | 1) By implementing this scheme the availability and loadability of Coal Mills will Increase. 2) Generation loss will reduce on account of coal mills |  |  |  | 0 | [8 empty] | 14.57 | [16 empty] | 0 | [7 empty] | 14.57 |  | Proposal not initiated yet | Not Initiated
18.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | Scheme |  |  |  | 6.14 | [7 empty] | 1) By implementing this scheme the availability and loadability of Coal Mills will Increase. 2) Generation loss will reduce on account of coal mills |  |  |  | 0 | [8 empty] | 6.14 | [16 empty] | 0 | [7 empty] | 6.14 |  | Proposal not initiated yet | Not Initiated
18.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit9 at 3x660 MW, KTPS, Koradi | Scheme |  |  |  | 1 | [7 empty] | 1) Combustion tunning of furnace will improve which will further reduce BTL due to temp excursion 2) Mill availability will improve |  |  |  | 0 | [8 empty] | 1 | [16 empty] | 0 | [7 empty] | 1 |  | Proposal not initiated yet | Not Initiated
19.3 | Reliability Improvement schemes of generators at 3X660MW, KTPS, Koradi | DPR |  |  |  | 80.79 | [11 empty] | 0 | [25 empty] | 0 | [9 empty] | 1. Board approval received dtd 26.09.2024 2. Put up to MERC on Dt.17.10.2024
19.1 | Scheme No. 1 :PROCUREMENT OF MELCO/LMTG MAKE GENERATOR ROTOR ASSEMBLY with excitation transformer AT 3X660MW KTPS, KORADI THROUGH OEM | Scheme |  |  |  | 45.39 | [7 empty] | To maintain the maximum plant availability (PLF) of all the units, the generator insurance spares (Generator stator coils,Rotor,Excitation transformer) availability at site will facilitate to reduce the time to restore in case of major fault as the lead time to procure these spares are almost 14 months as per OEM 2) |  |  |  | 0 |  |  |  |  | 45.39 | [20 empty] | 0 |  |  |  | 45.39 | [5 empty] | Budget uploaded (A-KRD-EMT660MW-24-S00-02) proposal under preparation at section Dt.24.10.24024
19.2 | Scheme No. 2:PROCUREMENT OF ONE COMPLETE SET OF GENERATOR STATOR COILS FOR GENERATOR AT 3X660MW UNITS AT KTPS KORADI THROUGH OEM | Scheme |  |  |  | 35.4 | [11 empty] | 0 |  |  |  |  | 35.4 | [20 empty] | 0 |  |  |  | 35.4 | [5 empty] | Budget uploaded (A-KRD-EMT660MW-24-S00-03) proposal under preparation at section Dt.24.10.24024
25 | DPR on Procurement of Critical Speares for L&T make Main Turbine(typeTC4F-30) installed at 3x660MW KTPS Koradi. | DPR | [15 empty] | 0 | [25 empty] | 0 | [9 empty] | Not initiated | Not Initiated
25.1 | Scheme No. 1 :Procurement of Critical Speares for L&T make Main Turbine(typeTC4F-30) installed at 3x660MW KTPS Koradi. | Scheme |  |  |  | 126.41 | [7 empty] | • No schedule over-run or delay during overhaul/ breakdown on account of unavailability of these critical spares. • Capitalized under insured spares hence help in reducing the high cost inventory. • PLF improvement. • Stable operation and increase in plant availability. • Long service life hence reduced maintenance cost. |  |  |  | 0 |  |  |  |  | 126.41 | [20 empty] | 0 |  |  |  | 126.41 | [5 empty] | Proposal not initiated yet
26 | DPR for Coal Handling Plant Performance Improvement Schemes -II at 3x660MW KTPS ,Koradi. | DPR |  |  |  | 27.8 | [11 empty] | 0 | [25 empty] | 0 | [9 empty] | Not initiated | Not Initiated
26.1 | Scheme No. 1 : Performance Improvement of Unloading System Wagon Tipplers at CHP 3x660MW KTPS Koradi | Scheme |  |  |  | 5.8 | [7 empty] | • Reduction in operational and maintenance cost. • Reduction in Coal Handling Plant downtime. • Reduction in wear & tear of wagon tippler internals • Improvement in coal flow in rainy season. • System outages will be reduced. • Life enhancement of auxiliary |  |  |  | 0 |  |  |  |  | 5.8 | [20 empty] | 0 |  |  |  | 5.8 | [5 empty] | Proposal not initiated yet
26.2 | Scheme No. 2 : Performance Improvement of Unloading System Side Arm Chargers at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Side Arm Charger Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 2.8 | [7 empty] | • Reduction in operational and maintenance cost. • Reduction in Coal Handling Plant downtime. • Reduction in wear & tear of side arm charger internals • System outages will be reduced. • Life enhancement of auxiliary |  |  |  | 0 |  |  |  |  | 2.8 | [20 empty] | 0 |  |  |  | 2.8 | [5 empty] | Proposal not initiated yet
26.3 | Scheme No. 3 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 3.2 | [7 empty] | • Reduction in operational and maintenance cost. • Reduction in Coal Handling Plant downtime. • Reduction in wear & tear of Apron Feeder internals • System outages will be reduced. • Life enhancement of auxiliary |  |  |  | 0 |  |  |  |  | 3.2 | [20 empty] | 0 |  |  |  | 3.2 | [5 empty] | Proposal not initiated yet
26.4 | Scheme No. 4 : Performance Improvement of Stacking & Reclaiming System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Stacking & Reclaiming System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 6.5 | [7 empty] | • Reduction in operational and maintenance cost. • Reduction in Coal Handling Plant downtime. • Reduction in wear & tear of Stacker cum reclaimer internals • System outages will be reduced. • Life enhancement of auxiliary |  |  |  | 0 |  |  |  |  | 6.5 | [20 empty] | 0 |  |  |  | 6.5 | [5 empty] | Proposal not initiated yet
26.5 | Scheme No. 5 : Performance Improvement of Crushing System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Impact Crusher & Wobbler Feeders Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 8.5 | [7 empty] | • Reduction in operational and maintenance cost. • Reduction in Coal Handling Plant downtime. • Reduction in wear & tear of Impact Crusher internals • System outages will be reduced. • Life enhancement of auxiliary |  |  |  | 0 |  |  |  |  | 8.5 | [20 empty] | 0 |  |  |  | 8.5 | [5 empty] | Proposal not initiated yet
26.6 | Scheme No. 6 : Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -1 at CHP 3x660MW KTPS Koradi A) Brief scope of work: Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -1 at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 1 | [7 empty] | • Reduction in operational and maintenance cost. • Reduction in Coal Handling Plant downtime. • Reduction in wear & tear of Stacker cum reclaimer internals • System outages will be reduced. • Life enhancement of auxiliary • safety operation |  |  |  | 0 |  |  |  |  | 1 | [20 empty] | 0 |  |  |  | 1 | [5 empty] | Proposal not initiated yet
27 | DPR for Coal Handling Plant Performance Improvement Schemes -III at 3x660MW KTPS ,Koradi. | DPR |  |  |  | 50.12 | [11 empty] | 0 | [25 empty] | 0 | [9 empty] | Not initiated | Not Initiated
27.1 | Scheme No. 1 : Performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Hydraulic system for Wagon Tippler, Side Arm Charger , Apron Feeder ( 1 & 2) Stacker Reclaimer 1 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 10.5 | [7 empty] | • Reduction in demurrages. • Spare motor and pump ensure system availability in case of failure of existing one. • Increase plant availability & reduction in generation loss |  |  |  | 0 |  |  |  |  | 10.5 | [20 empty] | 0 |  |  |  | 10.5 | [5 empty] | Proposal not initiated yet
27.2 | Scheme No. 2 : Construction of Air tight Hydraulic power pack room along with necessary cooling system for performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Construction of Air tight Hydraulic power pack room along with necessary cooling system for Wagon Tippler & Apron Feeder ( 1 to 4) Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 3.2 | [7 empty] | • Reduction in demurrages. • motor and pump failure will be reduced • Increase plant availability & reduction in generation loss |  |  |  | 0 |  |  |  |  | 3.2 | [20 empty] | 0 |  |  |  | 3.2 | [5 empty] | Proposal not initiated yet
27.3 | Scheme No. 3 : Performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory Hydraulic Power Cylinders of Wagon Tippler, Side Arm Charger ( 1 to 4) Stacker Reclaimer 1 & 2 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 1 | [7 empty] | • Reduction in demurrages. • Spare power cylinders ensure system availability in case of failure of existing one. • Increase plant availability & reduction in generation loss |  |  |  | 0 |  |  |  |  | 1 | [20 empty] | 0 |  |  |  | 1 | [5 empty] | Proposal not initiated yet
27.4 | Scheme No. 4 : Performance Improvement of Stacker Reclaimer by providing Hydraulic Drive to Boom Conveyor at CHP 3x660MW KTPS Koradi A) Brief scope of work: Hydraulic Drive to Boom Conveyor Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 0.9 | [7 empty] | • Reduction in demurrages. • hydraulic system ensure system availability in case of failure of existing one. • Increase plant availability & reduction in generation loss |  |  |  | 0 |  |  |  |  | 0.9 | [20 empty] | 0 |  |  |  | 0.9 | [5 empty] | Proposal not initiated yet
27.5 | Scheme No. 5 : Performance Improvement of Illumination system with energy conservation at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Solar High masts along the rail track in railway yard Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 3.75 | [7 empty] | • Reduction in demurrages. • improved efficiency at night hours . • Increase plant availability & reduction in generation loss • reduction in accidents /mishaps |  |  |  | 0 |  |  |  |  | 3.75 | [20 empty] | 0 |  |  |  | 3.75 | [5 empty] | Proposal not initiated yet
27.6 | Scheme No. 6 : Design, Supply & Installation of LT VFD Drives for Critical Conveyors at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of LT VFD Drives for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 1.2 | [7 empty] | • Reduction in demurrages. • motor failure will be reduced • Increase plant availability & reduction in generation loss • improved efficiency of motors • reduction in energy consumption |  |  |  | 0 |  |  |  |  | 1.2 | [20 empty] | 0 |  |  |  | 1.2 | [5 empty] | Proposal not initiated yet
27.7 | Scheme No. 7 : Design , supply, Erection & Commissioning of Short Conveyor for Stacking Purpose at CHP 3x660MW KTPS Koradi A) Brief scope of work: Short Conveyor for Stacking Purpose at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 9.6 | [7 empty] | • Coal requirement can be catered, even after non availability of existing stacking stream BCN-13A /13B . • Similarly receipt of wet and sticky coal particularly in rainy season choke up the wagon tippler hoppers and also receiving as well as discharge chute of conveyor belt. Many times, rakes are received in Bunching. Due to above reasons heavy demurrage is to be paid to Railway. Due to system constraints of above mention reason, number of times it is essential to stack the coal wagons at CHP stack yard instead of bunkering. Such coal can be stacked by using this short conveyor and can be used later. Stacker reclaimer can be used for bunkering mode with good quality coal. • Additional / alternate stream for stacking with less energy consumption compared to existing Stacker reclaimer stream due to involvement of lesser auxiliaries & short set up. • Planned maintenance outage of conveyor stram & stacker reclaimer can be carried out as additional stacking stream is available. • Parallel stacking can be made possible thereby increasing the plant loadability and decreasing demurrage charges . • Overloading of belt can be eliminated. • Increase in overall plant loadability & booster for achieving the maximum PLF. • High reliability due to less auxiliaries. |  |  |  | 0 |  |  |  |  | 9.6 | [20 empty] | 0 |  |  |  | 9.6 | [5 empty] | Proposal not initiated yet
27.8 | Scheme No. 8 : Capacity Enhancement of BCN-7/5/4/3 /1 AB in CHP 3x660MW KTPS Koradi A) Brief scope of work: Short Conveyor for Stacking Purpose at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 8.6 | [7 empty] | 1) Increase plant availability & reduction in generation loss 2) avaibility of converyors will be incrased 3) reduction in system down time |  |  |  | 0 |  |  |  |  | 8.6 | [20 empty] | 0 |  |  |  | 8.6 | [5 empty] | Proposal not initiated yet
27.9 | Scheme No. 9 : Design , Engineering & modification along with strengthening of Existing Travel Track structure for Side Arm Charger & Stacker Reclaimer A) Brief scope of work: strengthening of Existing Travel Track structure for Side Arm Charger & Stacker Reclaimer Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 1.5 | [7 empty] | 1. strengthening of Existing Travel Track structure for Side Arm Charger & Stacker Reclaimer Increases in useful life of travel structure 2. Renovation and Modernisation for minimizing failures |  |  |  | 0 |  |  |  |  | 1.5 | [20 empty] | 0 |  |  |  | 1.5
27.1 | Scheme No. 10 : Design , Engineering & Erection of modified Energy Efficient Ventilation System for Wagon Tippler Complex Area in CHP 3X660MW KTPS Koradi A) Brief scope of work: Energy Efficient Ventilation System for Wagon Tippler Complex Area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 2 | [7 empty] | 1. improved safety of operation & maintenance in WT area 2. reduction in accidents 3.Increase in efficiency of plant |  |  |  | 0 |  |  |  |  | 2 | [20 empty] | 0 |  |  |  | 2 | [5 empty] | Proposal not initiated yet
27.11 | Scheme No. 11 : Design , Engineering & Installtion of Vibration & temprature Monitoring Systems for critical auxiliaries in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Installtion of Vibration & temprature Monitoring Systems for critical auxiliaries Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 1.2 | [7 empty] | 1. Better monitoring of auxiliaries 2. Increased efficiency of plant 3. reduction in energy consumption |  |  |  | 0 |  |  |  |  | 1.2 | [20 empty] | 0 |  |  |  | 1.2 | [5 empty] | Proposal not initiated yet
27.12 | Scheme No. 12 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 1.2 | [7 empty] | • Eliminates belt slip. • Increased running life of lagging up to 5 years. • Increased availability/loadability of belt conveyor system. • Reduces overall operating cost. • Generation loss will decrease. |  |  |  | 0 |  |  |  |  | 1.2 | [20 empty] | 0 |  |  |  | 1.2 | [5 empty] | Proposal not initiated yet
27.13 | Scheme No. 13 : Design , Engineering & Provision of Stone Grappling Equipment System for Wagon Tippler 3 &4 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Stone Grappling Equipment System for Wagon Tippler 3 &4 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 0.9 | [7 empty] | 1. Efficiency of plant increases 2. reduction in accidents 3. Unloding of wagons will be improved |  |  |  | 0 |  |  |  |  | 0.9 | [20 empty] | 0 |  |  |  | 0.9 | [5 empty] | Proposal not initiated yet
27.14 | Scheme No. 14 : Design , Engineering & Provision of Public Addressing System for Wagon Tippler Complex in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Public Addressing System for Wagon Tippler Complex in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 1 | [7 empty] | 1. Efficiency of plant increases 2. reduction in accidents 3. Unloding of wagons will be improved by better communication among working manpower |  |  |  | 0 |  |  |  |  | 1 | [20 empty] | 0 |  |  |  | 1 | [5 empty] | Proposal not initiated yet
27.15 | Scheme No. 15 : Design , Engineering & Provision of Belt Tracking System for Critical Conveyors in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Belt Tracking System for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 1.5 | [7 empty] | 1. Plant availability increases 2. Reduction in belt wear & tear 3. Improvement in plant house keeping |  |  |  | 0 |  |  |  |  | 1.5 | [20 empty] | 0 |  |  |  | 1.5 | [5 empty] | Proposal not initiated yet
27.16 | Scheme No. 16 : Design , Engineering & Provision of Dust supression System for stacker reclaimer-1 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 0.6 | [7 empty] | 1. Reduction in pollution 2. Better working environment 3. Efficiency of plant increases |  |  |  | 0 |  |  |  |  | 0.6 | [20 empty] | 0 |  |  |  | 0.6 | [5 empty] | Proposal not initiated yet
27.17 | Scheme No. 17 : Work of Life Enhancement of wobbler Feeder 1 &2 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 1.6 | [7 empty] | • Improvement in performance of unloading & reduction in generation loss. • Demurrage charges will be reduced • Reduction in wear & tear of wobbler feeder internals • System outages will be reduced. • Life enhancement of auxiliary |  |  |  | 0 |  |  |  |  | 1.6 | [20 empty] | 0 |  |  |  | 1.6 | [5 empty] | Proposal not initiated yet
28 | DPR for Coal Handling Plant Performance Improvement Schemes -IV at 3x660MW KTPS ,Koradi. | DPR |  |  |  | 12.1 | [11 empty] | 0 | [25 empty] | 0 | [9 empty] | Not initiated | Not Initiated
28.1 | Scheme No.1 : Design , Engineering , Supply & Installation of Modular Transfer chutes for Critical Conveyor System in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of Modular Transfer chutes for Conveyor System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 14 | [7 empty] | • Reduction in conveyor stream outages. • Reduction in maintenance cost. • Reduction in cleaning problems. • Improvement in performance of unloading & reduction in generation loss. • Demurrage charges will be reduced. |  |  |  | 0 |  |  |  |  | 14 | [20 empty] | 0 |  |  |  | 14
28.2 | Scheme No.2 :Upgradtion of Exsisting Fire Fighting System at Stack yard area in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradtion of Exsisting Fire Fighting System at Stack yard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 2.6 | [7 empty] | 1. Upgradation in fire fighting opeartion system 2. Efficiency of plant incrases 3. reduction in pant mishaps |  |  |  | 0 |  |  |  |  | 2.6 | [20 empty] | 0 |  |  |  | 2.6
28.3 | Scheme No.3 : Design , Engineering , Supply & Strengthening of engineering structure of BCN- 7A/B along with track alignment in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Strengthening of engineering structure of BCN- 7A/B Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 2.4 | [7 empty] | 1. Efficient operation of Bunker TTR |  |  |  | 0 |  |  |  |  | 2.4 | [20 empty] | 0 |  |  |  | 2.4
28.4 | Scheme No.4 : Design , Engineering , Supply & Installation of Mist Cannon Spray System around stackyard area in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of Mist Cannon Spray System at stackyard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 1.6 | [7 empty] | 1. It help to prevent from fire in yard during heavy summer. 2. with help of sprinkling dust pollution can be avoided. |  |  |  | 0 |  |  |  |  | 1.6 | [20 empty] | 0 |  |  |  | 1.6
28.5 | Scheme No.5 : Design , Engineering , Supply & Installation of EOT cranes at Bunker in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of EOT cranes at Bunker Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 4.5 | [7 empty] | • System outages will be reduced. • Unloading time will be improved thereby reduce demurrages. • Demurrage charges will be reduced. • safe environment for working persons. |  |  |  | 0 |  |  |  |  | 4.5 | [20 empty] | 0 |  |  |  | 4.5
29 | DPR for Procurment of various Heavy Vehicles at CHP 3x660MW KTPS ,Koradi. | DPR |  |  |  | 33 | [11 empty] | 0 | [25 empty] | 0 | [9 empty] | Not initiated | Not Initiated
29.1 | Scheme No.1 : Procurment of Heavy Vehicles like dozers, wheel loaders , locomotives, Crane, Hydra , Disel Browser , Jcb & Bobcats etc. in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurment of Heavy Vehicles like dozers, wheel loaders , locomotives etc Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 30 | [7 empty] | • System outages will be reduced. • Unloading time will be improved thereby reduce demurrages. • Maximum power & efficiency of equipment based on load. • Service & Maintenance cost will be reduced. • Proper stack yard management Less diesel consumption |  |  |  | 0 |  |  |  |  | 30 | [20 empty] | 0 |  |  |  | 30
29.2 | Scheme No.2 : Procurment of Auger Machines for coal sampling in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurment of Auger Machines for coal sampling Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 2.2 | [7 empty] | • System outages will be reduced. • Unloading time will be improved thereby reduce demurrages. • Maximum power & efficiency of equipment based on load. • Service & Maintenance cost will be reduced. • Proper coal sample management |  |  |  | 0 |  |  |  |  | 2.2 | [20 empty] | 0 |  |  |  | 2.2
29.3 | Scheme No.3 : Procurment of Truck Mounted mist cannon dust supression system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurment of Truck Mounted mist cannon dust supression system in CHP Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 0.8 | [7 empty] | 1. Reduction in environmental pollution 2. Safe working for humans 3. Redution in coal losses |  |  |  | 0 |  |  |  |  | 0.8 | [20 empty] | 0 |  |  |  | 0.8
30 | DPR for Coal Handling Plant Performance Improvement Schemes -V at 3x660MW KTPS ,Koradi. | DPR |  |  |  | 12.35 | [11 empty] | 0 | [25 empty] | 0 | [9 empty] | Not initiated | Not Initiated
30.1 | Scheme No. 1 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 3.2 | [7 empty] | • System outages will be reduced. • Unloading time will be improved thereby reduce demurrages. • Demurrage charges will be reduced. • Maintenance cost of apron feeder will be reduced. |  |  |  | 0 | [5 empty] | 3.2 | [19 empty] | 0 |  |  |  |  | 3.2
30.2 | Scheme No. 2 : Performance Improvement of Stacking & Reclaiming / Side Arm Charger System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Energy Chain System of Stacking & Reclaiming System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 10 | [7 empty] | • System outages will be reduced. • Unloading time will be improved thereby reduce demurrages. • Demurrage charges will be reduced. • Maintenance cost of SR /SAC will be reduced. |  |  |  | 0 | [5 empty] | 10 | [19 empty] | 0 |  |  |  |  | 10
30.3 | Scheme No. 3 : Performance Improvement of unloading System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Energy Chain System of side arm acharger Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 1.5 | [7 empty] | • Less down time of critical auxiliary • Less maintenance cost • Increase in reliability • Uninterrupted coal bunkering • Less downtime of critical auxiliary • Increase in plant loadability and availability • Aversion of generation loss |  |  |  | 0 | [5 empty] | 1.5 | [19 empty] | 0 |  |  |  |  | 1.5
30.4 | Scheme No. 4 : Upgradation to 100 MT Ton Weighbridge of existing road weighbridge at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of LT VFD Drives for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 0.8 | [7 empty] | • Less down time of critical auxiliary • Less maintenance cost • Increase in reliability • Uninterrupted coal bunkering • Less downtime of critical auxiliary • Increase in plant loadability and availability • Aversion of generation loss |  |  |  | 0 | [5 empty] | 0.8 | [19 empty] | 0 |  |  |  |  | 0.8
30.5 | Scheme No. 5 : Design , Engineering & Erection of modified Energy Efficient Ventilation System for Crusher House Area in CHP 3X660MW KTPS Koradi A) Brief scope of work: Energy Efficient Ventilation System for Wagon Tippler Complex Area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 2.5 | [7 empty] | • System outages will be reduced. • Unloading time will be improved thereby reduce demurrages. • Maximum power & efficiency of equipment based on load. • Service & Maintenance cost will be reduced. |  |  |  | 0 | [5 empty] | 2.5 | [19 empty] | 0 |  |  |  |  | 2.5
30.6 | Scheme No. 6 : Design , supply & Installation of Cooling Arrangement for Switchgear rooms at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Cooling Arrangement for Switchgear rooms Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 5 | [7 empty] | • System outages will be reduced. • Unloading time will be improved thereby reduce demurrages. • Maximum power & efficiency of equipment based on load. • Service & Maintenance cost will be reduced. |  |  |  | 0 | [5 empty] | 5 | [19 empty] | 0 |  |  |  |  | 5
30.7 | Scheme No. 7 : Design , Engineering & Erection of modified Engineering Structure of Tunnel Conveyor 1A &1 B in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Erection of modified Engineering Structure of Tunnel Conveyor 1A &1 B Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 2.35 | [7 empty] | • System outages will be reduced. • Unloading time will be improved thereby reduce demurrages. • Maximum power & efficiency of equipment based on load. • Service & Maintenance cost will be reduced. |  |  |  | 0 | [5 empty] | 2.35 | [19 empty] | 0 |  |  |  |  | 2.35
31 | DPR for Coal Handling Plant Performance Improvement Schemes -VI at 3x660MW KTPS ,Koradi. | DPR |  |  |  | 26.1 | [11 empty] | 0 | [25 empty] | 0 | [9 empty] | Not initiated | Not Initiated
31.1 | Scheme No. 1 : Performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Wagon Tippler, Side Arm Charger , Apron Feeder ( 3 & 4) Stacker Reclaimer 2 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 11.5 | [7 empty] | • Reduction in demurrages. • Available Spares ensure system availability in case of failure of existing one. • Increase plant availability & reduction in generation loss |  |  |  | 0 | [5 empty] | 11.5 | [19 empty] | 0 |  |  |  |  | 11.5
31.2 | Scheme No. 2 : Design Supply & Installation of Wagon Locking system for all four wagon tipplers at CHP 3x660MW KTPS Koradi A) Brief scope of work: Wagon Locking system for all four wagon tipplers Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 8 | [7 empty] | • System outages will be reduced. • Unloading time will be improved thereby reduce demurrages. • Maximum power & efficiency of equipment based on load. • Service & Maintenance cost will be reduced. |  |  |  | 0 | [5 empty] | 8 | [19 empty] | 0 |  |  |  |  | 8
31.3 | Scheme No. 3 : Design, Supply & Installation of upgraded Vibrating Feeders for Stacker Reclaimer at CHP 3x660MW KTPS Koradi A) Brief scope of work: Design, Supply & Installation of upgraded Vibrating Feeders for Stacker Reclaimer Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 0.9 | [7 empty] | • Spare vibrating feeder assembly ensures system healthiness & availability in case of failure of existing one. • Unloading time of coal rakes will be reduced resulting into reduction in demurrage charges further overall performance of CHP will be improved. • Increase plant availability & reduction in generation loss. |  |  |  | 0 | [5 empty] | 0.9 | [19 empty] | 0 |  |  |  |  | 0.9
31.4 | Scheme No. 4: Performance Improvement of Stacker Reclaimer by providing Hydraulic Drive to Boom Conveyor at CHP 3x660MW KTPS Koradi A) Brief scope of work: Hydraulic Drive to Boom Conveyor Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 0.9 | [7 empty] | • System outages will be reduced. • Unloading time will be improved thereby reduce demurrages. • Maximum power & efficiency of equipment based on load. • Service & Maintenance cost will be reduced. • Proper stack yard management |  |  |  | 0 | [5 empty] | 0.9 | [19 empty] | 0 |  |  |  |  | 0.9
31.5 | Scheme No. 5 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 1 | [7 empty] | • Eliminates belt slip. • Increased running life of lagging up to 5 years. • Increased availability/loadability of belt conveyor system. • Reduces overall operating cost. • Generation loss will decrease. |  |  |  | 0 | [5 empty] | 1 | [19 empty] | 0 |  |  |  |  | 1
31.6 | Scheme No. 6 : Design , Engineering & Provision of Belt Tracking System for Critical Conveyors in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Belt Tracking System for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 1.6 | [7 empty] | • Less friction of rollers with conveyor belt resulting in increase of belt life. • No rusting tendency, high rollers life. • Less maintenance. Decrease the repeated damage of rollers. • System availability will increase. • Generation loss will decrease. |  |  |  | 0 | [5 empty] | 1.6 | [19 empty] | 0 |  |  |  |  | 1.6
31.7 | Scheme No. 7 : Design , Engineering & Provision of Dust supression System for stacker reclaimer-1 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 0.6 | [7 empty] | • Reduction in conveyor stream outages. • Reduction in maintenance cost. • Reduction in cleaning problems. • Improvement in performance of unloading & reduction in generation loss. • Demurrage charges will be reduced. |  |  |  | 0 | [5 empty] | 0.6 | [19 empty] | 0 |  |  |  |  | 0.6
31.8 | Scheme No. 8 : Work of Life Enhancement of wobbler Feeder 3 &4 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 1.6 | [7 empty] | • System outages will be reduced. • Unloading time will be improved thereby reduce demurrages. • Demurrage charges will be reduced. • Maintenance cost of apron feeder will be reduced. |  |  |  | 0 | [5 empty] | 1.6 | [19 empty] | 0 |  |  |  |  | 1.6
32 | DPR for Coal Handling Plant Performance Improvement Schemes -VII at 3x660MW KTPS ,Koradi. | DPR |  |  |  | 27.2 | [11 empty] | 0 | [25 empty] | 0 | [9 empty] | Not initiated | Not Initiated
32.1 | Scheme No.1 : Design , Engineering , Supply & Installation of Modular Transfer chutes for Crusher House Complex & other Critical Conveyor System in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of Modular Transfer chutes for Conveyor System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 13 | [7 empty] | • Reduction in conveyor stream outages. • Reduction in maintenance cost. • Reduction in cleaning problems. • Improvement in performance of unloading & reduction in generation loss. • Demurrage charges will be reduced. |  |  |  | 0 | [5 empty] | 13 | [19 empty] | 0 |  |  |  |  | 13
32.2 | Scheme No.2 :Upgradtion of Exsisting Fire Fighting System along the conveyor length in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradtion of Exsisting Fire Fighting System at Stack yard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 3.2 | [7 empty] | • Higher system availability • Uninterrupted coal stacking and bunkering • Less downtime of critical auxiliary • Increase in plant loadability and availability • Aversion of demurrage charges • Aversion of generation loss • Increase in reliability |  |  |  | 0 | [5 empty] | 3.2 | [19 empty] | 0 |  |  |  |  | 3.2
32.3 | Scheme No.3 : Supply , Erection & Installation of Rack & Pinion Elevators at Bunker in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Supply , Erection & Installation of Rack & Pinion Elevators at Bunker in CHP 3X660MW KTPS Koradi. Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 0.8 | [7 empty] | • Higher system availability • Uninterrupted coal bunkering • Less downtime of critical auxiliary • Increase in plant loadability and availability • Aversion of demurrage charges • Aversion of generation loss • Increase in reliability |  |  |  | 0 | [5 empty] | 0.8 | [19 empty] | 0 |  |  |  |  | 0.8
32.4 | Scheme No.4 :Up Liftment f Exsisting Fire Fighting lines in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradtion of Exsisting Fire Fighting System at Stack yard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 3.2 | [7 empty] | • Higher system availability • Uninterrupted coal stacking and bunkering • Less downtime of critical auxiliary • Increase in plant loadability and availability • Aversion of demurrage charges • Aversion of generation loss • Increase in reliability Increase in industrial safety |  |  |  | 0 | [5 empty] | 3.2 | [19 empty] | 0 |  |  |  |  | 3.2
32.5 | Scheme No.5 : Procurement of HPPE Polymer Roller for Conveyor system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurement of HPPE Polymer Roller for Conveyor system Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 0.8 | [7 empty] | • Less friction of rollers with conveyor belt resulting in increase of belt life. • No rusting tendency, high rollers life. • Less maintenance. Decrease the repeated damage of rollers. • System availability will increase. • Generation loss will decrease. |  |  |  | 0 | [5 empty] | 0.8 | [19 empty] | 0 |  |  |  |  | 0.8
32.6 | Scheme No.6 : Design , Engineering , Supply & Installation of EOT cranes at Wagon Tippler Complex in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of EOT cranes at Wagon Tippler Complex Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 6.2 | [7 empty] | • System outages will be reduced. • Unloading time will be improved thereby reduce demurrages. • Demurrage charges will be reduced. • safe environment for working persons. |  |  |  | 0 | [5 empty] | 6.2 | [19 empty] | 0 |  |  |  |  | 6.2
33 | DPR for Coal Handling Plant Performance Improvement Schemes -VIII at 3x660MW KTPS ,Koradi. | DPR |  |  |  | 26.9 | [11 empty] | 0 | [25 empty] | 0 | [9 empty] | Not initiated | Not Initiated
33.1 | Scheme No. 1 : Performance Improvement of Unloading System Wagon Tipplers at CHP 3x660MW KTPS Koradi Estimated Cost : 3.6 Cr. | Scheme |  |  |  | 3.6 | [7 empty] | • Reduction in conveyor stream outages. • Reduction in demurrage charges. • Capacity of apron feeder will increase • Higher unloading rate • System availability will increase. • Repetitive maintenances will reduce. • Reduction in the inventory. |  |  |  | 0 | [6 empty] | 3.6 | [18 empty] | 0 | [5 empty] | 3.6
33.2 | Scheme No. 2 : Performance Improvement of Unloading System Side Arm Chargers at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Side Arm Charger Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 2.8 | [7 empty] | • Reduction in conveyor stream outages. • Reduction in demurrage charges. • Capacity of SAC feeder will increase • Higher unloading rate • System availability will increase. • Repetitive maintenances will reduce. • Reduction in the inventory. |  |  |  | 0 | [6 empty] | 2.8 | [18 empty] | 0 | [5 empty] | 2.8
33.3 | Scheme No. 3 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 3.4 | [7 empty] | • Reduction in conveyor stream outages. • Reduction in demurrage charges. • Capacity of apron feeder will increase • Higher unloading rate • System availability will increase. • Repetitive maintenances will reduce. • Reduction in the inventory. |  |  |  | 0 | [6 empty] | 3.4 | [18 empty] | 0 | [5 empty] | 3.4
33.4 | Scheme No. 4 : Performance Improvement of Stacking & Reclaiming System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Stacking & Reclaiming System -2 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 3.5 | [7 empty] | • Reduction in conveyor stream outages. • Reduction in demurrage charges. • Capacity ofstacker will increase • Higher unloading rate • System availability will increase. • Repetitive maintenances will reduce. • Reduction in the inventory. |  |  |  | 0 | [6 empty] | 3.5 | [18 empty] | 0 | [5 empty] | 3.5
33.5 | Scheme No. 5 : Performance Improvement of Crushing System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Impact Crusher & Wobbler Feeders Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 8.5 | [7 empty] | • Reduction in conveyor stream outages. • Reduction in demurrage charges. • Capacity of crusher will increase • Higher unloading rate • System availability will increase. • Repetitive maintenances will reduce. • Reduction in the inventory. |  |  |  | 0 | [6 empty] | 8.5 | [18 empty] | 0 | [5 empty] | 8.5
33.6 | Scheme No. 6 : Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -2 at CHP 3x660MW KTPS Koradi A) Brief scope of work: Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -2 at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 1 | [7 empty] | • Reduction in demurrage charges. • Higher unloading rate • System availability will increase. • Repetitive maintenances will reduce. • Reduction in the inventory. |  |  |  | 0 | [6 empty] | 1 | [18 empty] | 0 | [5 empty] | 1
33.7 | Scheme No. 7 : Other Mislenious Schemes at CHP 3x660MW KTPS Koradi A) Brief scope of work: Other Mislenious works Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 2.5 | [7 empty] | • Reduction in conveyor stream outages. • Reduction in demurrage charges. • Higher unloading rate • System availability will increase. • Repetitive maintenances will reduce. • Reduction in the inventory. |  |  |  | 0 | [6 empty] | 2.5 | [18 empty] | 0 | [5 empty] | 2.5
33.8 | Scheme No. 4 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 0.8 | [7 empty] | • Eliminates belt slip. • Increased running life of lagging up to 5 years. • Increased availability/loadability of belt conveyor system. • Reduces overall operating cost. • Generation loss will decrease. |  |  |  | 0 | [6 empty] | 0.8 | [18 empty] | 0 | [5 empty] | 0.8
33.9 | Scheme No.8: Procurement of HPPE Polymer Roller for Conveyor system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurement of HPPE Polymer Roller for Conveyor system Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 0.8 | [7 empty] | • Less friction of rollers with conveyor belt resulting in increase of belt life. • No rusting tendency, high rollers life. • Less maintenance. Decrease the repeated damage of rollers. • System availability will increase. • Generation loss will decrease. |  |  |  | 0 | [6 empty] | 0.8 | [18 empty] | 0 | [5 empty] | 0.8
34 | DPR for Coal Handling Plant Performance Improvement Schemes -IX at 3x660MW KTPS ,Koradi. | DPR |  |  |  | 12 | [11 empty] | 0 | [25 empty] | 0 | [9 empty] | Not initiated | Not Initiated
34.1 | Scheme No. 1 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 3.6 | [7 empty] | • System outages will be reduced. • Unloading time will be improved thereby reduce demurrages. • Demurrage charges will be reduced. • Maintenance cost of apron feeder will be reduced. |  |  |  | 0 | [7 empty] | 3.6 | [17 empty] | 0 | [6 empty] | 3.6
34.2 | Scheme No. 2 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 1 | [7 empty] | • Eliminates belt slip. • Increased running life of lagging up to 5 years. • Increased availability/loadability of belt conveyor system. • Reduces overall operating cost. • Generation loss will decrease. |  |  |  | 0 | [7 empty] | 1 | [17 empty] | 0 | [6 empty] | 1
34.3 | Scheme No.3 : Upgradation of Exsisting Rack & Pinion Elevators at CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradation of Exsisting Rack & Pinion Elevators Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 1.6 | [7 empty] | • Higher system availability • Uninterrupted OPERATION OF CHP • Less downtime of critical auxiliary • Increase in plant loadability and availability • Aversion of demurrage charges • Aversion of generation loss • Increase in reliability |  |  |  | 0 | [7 empty] | 1.6 | [17 empty] | 0 | [6 empty] | 1.6
34.4 | Scheme No.4 : Procurement of HPPE Polymer Roller for Conveyor system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurement of HPPE Polymer Roller for Conveyor system Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 0.8 | [7 empty] | • Less friction of rollers with conveyor belt resulting in increase of belt life. • No rusting tendency, high rollers life. • Less maintenance. Decrease the repeated damage of rollers. • System availability will increase. • Generation loss will decrease. |  |  |  | 0 | [7 empty] | 0.8 | [17 empty] | 0 | [6 empty] | 0.8
34.5 | Scheme No.5 : Other miscellaneous scheme regarding sustainable performance improvement of CHP 3X660MW KTPS Koradi. A) Brief scope of work: ther miscellaneous scheme regarding sustainable performance improvement Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | Scheme |  |  |  | 18 | [7 empty] | • Higher system availability • Uninterrupted coal stacking and bunkering • Less downtime of critical auxiliary • Increase in plant loadability and availability • Aversion of demurrage charges • Aversion of generation loss • Increase in reliability |  |  |  | 0 | [7 empty] | 18 | [17 empty] | 0 | [6 empty] | 18
35 | Design & engineering, procurement, supply, installation & commissioning of Ozone Generator system of capacity 45.0 Kg/hr for CW system | DPR |  |  |  | 45 | [11 empty] | 0 | [25 empty] | 0 | [9 empty] | Not initiated | Not Initiated
35.1 | Scheme1:Design & engineering, procurement, supply, installation & commissioning of Ozone Generator system of capacity 45.0 Kg/hr for CW system | Scheme |  |  |  | 45 | [11 empty] | 0 | [5 empty] | 45 | [19 empty] | 0 |  |  |  |  | 45
36 | Pipeline expansion to improve dry ash evacuation system | DPR |  |  |  | 75 | [11 empty] | 0 | [25 empty] | 0
36.1 | Scheme1: Pipeline expansion to improve dry ash evacuation system along with target box modification and also to erect & commission dry ash evacuation directly to remote silo. | Scheme |  |  |  | 75 | [11 empty] | 0 |  |  |  |  | 75 | [20 empty] | 0 |  |  |  | 75
37 | Modification at intermediate silo and HCSD system | DPR |  |  |  | 29 | [11 empty] | 0 | [25 empty] | 0
37.1 | Scheme1: Additional charge pump. | Scheme |  |  |  | 3 | [7 empty] | • 100% availability of all the 3 nos. Charge Pumps for suction of Geho Pumps, thus reduction in system outages. • Generation loss incurred due to non-availability of auxiliaries & ash slurry disposal through HCSD System may be avoided. |  |  |  | 0 |  |  |  |  | 3 | [20 empty] | 0 |  |  |  | 3
37.2 | Scheme 2: Supply & Installation Air washery at silo top. | Scheme |  |  |  | 3 | [7 empty] | • Dust emmission in to the atmosphere will be avoided from top of silo due to Dust suppression system. • Downtime of system will be reduced. |  |  |  | 0 |  |  |  |  | 3 | [20 empty] | 0 |  |  |  | 3
37.3 | Scheme 3: Shed above silo top. | Scheme |  |  |  | 3 | [7 empty] | • Silo top will be protected from Rain water ingress inside Silo. • Downtime of system will be reduced. |  |  |  | 0 |  |  |  |  | 3 | [20 empty] | 0 |  |  |  | 3
37.4 | Scheme 4: Supply & Installation Construction of platform at pipe rack up to Remote silo. | Scheme |  |  |  | 7 | [7 empty] | • Approach will be available for day to day mantenance works. • Downtime of system will be reduced. |  |  |  | 0 |  |  |  |  | 7 | [20 empty] | 0 |  |  |  | 7
37.5 | Scheme 5: Shifting of pipeline above pipe rack. | Scheme |  |  |  | 10 | [7 empty] | • Easy for inspection & thickness survey of line. • Day to day mantenance works & defect attending will be more feasible. • Downtime of system will be reduced. |  |  |  | 0 |  |  |  |  | 10 | [20 empty] | 0 |  |  |  | 10
37.6 | Scheme 6: Supply & Installation ART sub assemblies. | Scheme |  |  |  | 3 | [7 empty] | • 100% availability of all the 3 nos. ART Gear Box Drive Units, thus reduction in system outages. • Generation loss incurred due to non-availability of auxiliaries & ash slurry disposal through HCSD System may be avoided. |  |  |  | 0 |  |  |  |  | 3 | [20 empty] | 0 |  |  |  | 3
38 | ESP field strengthening at U#8 | DPR |  |  |  | 120 | [11 empty] | 0 | [25 empty] | 0
38.1 | Scheme1: ESP field strengthening at U#8 | Scheme |  |  |  | 120 | [7 empty] | • Existing Unit#8 ESP F-Pass : Collecting & Emitting Electrodes are found heavily bend leading to Low Field Strength. Therefore, Field strengthening by replacement of Collecting & Emitting Electrodes will ensure the enhanced performance of ESP & thereby reduced stack emission so that SPM level can be maintained within permissible limit. • ESP Field availability will be increased that will lead to smooth functioning of dry ash evacuation system. • Reduction in wear & tear of spares thereby Downtime will be reduced. • Work planning will be better, hence maintenance cost will be reduced. • Due to minimized wear & tear, spares damage will be reduced. |  |  |  | 0 |  |  |  |  | 120 | [20 empty] | 0 |  |  |  | 120
39 | Procurement of various pumps for AHP performance improvement | DPR |  |  |  | 28 | [11 empty] | 0 | [25 empty] | 0
39.1 | Scheme1: Procurement of various pumps for AHP performance improvement. | Scheme |  |  |  | 28 | [7 empty] | • 100% availability of all pumps including stand-by auxilliaries. It will lead to reduction in system outages. • Water Consumption & Power Consumption will be optimum. • System performance & efficiency will be improved. • Generation loss incurred due to non-availability of auxiliaries will be avoided. |  |  |  | 0 |  |  |  |  | 28 | [20 empty] | 0 |  |  |  | 28
40 | Modification in Dry Ash Evacuation System D/V Assemblies & allied equipments to improve performance | DPR |  |  |  | 35 | [11 empty] | 0 | [25 empty] | 0
40.1 | Scheme1: Procurement of D/V Assemblies & allied equipments to improve performance. | Scheme |  |  |  | 35 | [7 empty] | • Dome Valves availability will be ensured for dry ash evacuation system. It will lead to reduction in system outages. • System performance & efficiency will be improved. • Work planning will be better. Inventory of spares will be reduced as life of spares will be enhanced. • Stack emmission will be minimum as the system will work more efficiently & effectively. |  |  |  | 0 |  |  |  |  | 35 | [20 empty] | 0 |  |  |  | 35
41 | Additional IAC house for Intermediate silo and Remote silo along with erection of S.S. Pipeline | DPR |  |  |  | 50 | [11 empty] | 0 | [25 empty] | 0
41.1 | Scheme1: Supply & Installation Additional IAC house for Intermediate silo and Remote silo along with erection of S.S. Pipeline | Scheme |  |  |  | 50 | [7 empty] | • IAC availability will be increased that will lead to ash evacuation system smooth operation. • Downtime will be reduced as SS pipelines are corrosion & wear resistant, thereby reduction in frequent maintenance. • Work planning will be better hence maintenance cost will be reduced. • Due to minimized wear & tear, spares breakage will be reduced. • System availability will be increased & system outages will be reduced. • Due to frequent failures of IAC, it becomes mandatory to repair the damaged one on priority that creates an emergency for maintenance activities. • By implementing above scheme, there will be substantial reduction in outages of the IAC which will confirm improvement in the performance of Ash Handling Plant. |  |  |  | 0 | [5 empty] | 50 | [19 empty] | 0 |  |  |  |  | 50
42 | Waste water system modification to have zero water discharge | DPR |  |  |  | 26 | [11 empty] | 0 | [25 empty] | 0
42.1 | Scheme1: Waste water system modification to have zero water discharge at 3x660MW, KTPS, Koradi along with Pump Procurement along with arrangement of sludge discharge at ESP water Washing system. | Scheme |  |  |  | 26 | [7 empty] | • Water consumption will be minimised. • Running hours of the various sub-systems will be minimised. That will lead to reduction in spares consumption, inventory cost & outages. |  |  |  | 0 | [5 empty] | 26 | [19 empty] | 0 |  |  |  |  | 26
43 | ESP field strengthening at U#9 | DPR |  |  |  | 275 | [11 empty] | 0 | [25 empty] | 0
43.1 | Scheme1: ESP field strengthening at U#9 | Scheme |  |  |  | 275 | [7 empty] | In one Pass of Unit#9 ESP: • Collecting & Emitting Electrodes are found heavily bend leading to Low Field Strength. Therefore, Field strengthening by replacement of Collecting & Emitting Electrodes will ensure the enhanced performance of ESP & thereby reduced stack emission so that SPM level can be maintained within permissible limit. • ESP Field availability will be increased that will lead to smooth functioning of dry ash evacuation system. • Reduction in wear & tear of spares thereby Downtime will be reduced. • Work planning will be better, hence maintenance cost will be reduced. • Due to minimized wear & tear, spares damage will be reduced. |  |  |  | 0 | [5 empty] | 275 | [19 empty] | 0 |  |  |  |  | 275
44 | Procurement of HCSD GEHO Pump (TZPM-400) critical items sub-assemblies | DPR |  |  |  | 30 | [11 empty] | 0 | [25 empty] | 0
44.1 | Scheme1: Procurement of HCSD GEHO Pump TZPM-400) critical items sub-assemblies. | Scheme |  |  |  | 30 | [7 empty] | • 100% availability of all the 3 nos. of Geho Pumps, thus reduction in water consumption. • Generation loss incurred due to non-availability of auxiliaries & ash slurry disposal through HCSD System may be avoided. |  |  |  | 0 | [5 empty] | 30 | [19 empty] | 0 |  |  |  |  | 30
45 | MSERW Pipes & Seamless Pipes replacement to improve ash conveying & its disposal-1 | DPR |  |  |  | 70 | [11 empty] | 0 | [25 empty] | 0
45.1 | Scheme1: Supply & Work of Replacement of MSERW Pipes & Seamless Pipes in Bottom ash/Coarse ash evacuation & Ash Slurry Disposal Pipelines, Dry ash conveying system in phase manner to improve the ash evacuation performance. | Scheme |  |  |  | 70 | [7 empty] | • Less wear & tear as compaired with existing MS Seamless Pipes. • Frequent line leakages, System down time & Maintenance will be reduced. • Material consumption & inventory cost will be minimised. • System availability & performance will be enhanced. |  |  |  | 0 | [5 empty] | 70 | [19 empty] | 0 |  |  |  |  | 70
46 | Improvement in Ash Water Recovery System | DPR |  |  |  | 35 | [11 empty] | 0 | [25 empty] | 0
46.1 | Scheme1: Supply & Installation of Pumps along with Pipeline for Improvement in Ash Water Recovery System. | Scheme |  |  |  | 35 | [7 empty] | • Higher capacity pumps will be provided to enhance the ash water recovery capacity. • Water consumption will be minimised. |  |  |  | 0 | [6 empty] | 35 | [18 empty] | 0 | [5 empty] | 35
47 | Replacement of Instrument air pipeline from M.S. to S.S for AHP main plant | DPR |  |  |  | 40 | [11 empty] | 0 | [25 empty] | 0
47.1 | Scheme1: Replacement of Instrument air pipeline from M.S. to S.S for AHP main plant | Scheme |  |  |  | 40 | [7 empty] | • Ash Handling System outages will be reduced. • Due to moisture and rust free air, life & performance of instrumentation installed at AHP such as pressure switches, Solenoid operating valves (SOV), etc. will be improved. Due to frequent failure of instrumentations, secondary damages of various valves such as dome vale, poppet valve has increased significantly leading to excessive maintenance outages, addition in spares/material consumption, etc. • Due to moisture and rust free air, clogging of Filter bags while purging will be reduced significantly, thereby Silo pressurization issues will be minimized. • Due to moisture and rust free air, issues observed on rotor assembly of Transport Air Compressor will be avoided. Being high value items, its replacement/repairing cost will be saved and its life & performance will be enhanced. • Vibration probe & gauges functioning will be better. • Increase plant availability & reduction in generation loss. • Inventory of spares will be reduced. Work planning will be better. |  |  |  | 0 | [6 empty] | 40 | [18 empty] | 0 | [5 empty] | 40
48 | Modification of sludge pumps and its pipeline with pumps of higher capacity and discharge line of higher capacity. | DPR |  |  |  | 50 | [11 empty] | 0 | [25 empty] | 0
48.1 | Scheme1: Modification of sludge pumps and its pipeline with pumps of higher capacity and discharge line of higher capacity. | Scheme |  |  |  | 50 | [7 empty] | • Due to ash sludge pump capacity enhancement, Wet Ash Evacuation will be done in minimum time. • Due to enhancement, bottom ash pile up condition will be minimized. • Work planning will be better & it will make redundancy in ash sludge disposal pipelines operation & maintenance. • Inventory of spares will be reduced as life of spares will be enhanced. |  |  |  | 0 | [6 empty] | 50 | [18 empty] | 0 | [5 empty] | 50
49 | ESP field strengthening at U#10 | DPR |  |  |  | 310 | [11 empty] | 0 | [25 empty] | 0
49.1 | Scheme1: ESP field strengthening at U#10 | Scheme |  |  |  | 310 | [7 empty] | In one Pass of Unit#10 ESP: • Collecting & Emitting Electrodes are found heavily bend leading to Low Field Strength. Therefore, Field strengthening by replacement of Collecting & Emitting Electrodes will ensure the enhanced performance of ESP & thereby reduced stack emission so that SPM level can be maintained within permissible limit. • ESP Field availability will be increased that will lead to smooth functioning of dry ash evacuation system. • Reduction in wear & tear of spares thereby Downtime will be reduced. • Work planning will be better, hence maintenance cost will be reduced. • Due to minimized wear & tear, spares damage will be reduced. |  |  |  | 0 | [6 empty] | 310 | [18 empty] | 0 | [5 empty] | 310
50 | MSERW Pipes & Seamless Pipes replacement to improve ash conveying & its disposal-2 | DPR |  |  |  | 90 | [11 empty] | 0 | [25 empty] | 0
50.1 | Scheme1: Supply & Work of Replacement of MSERW Pipes & Seamless Pipes in Bottom ash/Coarse ash evacuation & Ash Slurry Disposal Pipelines, Dry ash conveying system in phase manner to improve the ash evacuation performance. | Scheme |  |  |  | 90 | [7 empty] | • Less wear & tear as compaired with existing MS Seamless Pipes. • Frequent line leakages, System down time & Maintenance will be reduced. • Material consumption & inventory cost will be minimised. • System availability & performance will be enhanced. |  |  |  | 0 | [7 empty] | 90 | [17 empty] | 0 | [6 empty] | 90
51 | Replacement of IAC for AHP Main Plant | DPR |  |  |  | 60 | [11 empty] | 0 | [25 empty] | 0
51.1 | Scheme1: Supply & Installation of IAC for AHP Main Plant | Scheme |  |  |  | 60 | [7 empty] | • IAC availability will be increased that will lead to ash evacuation system smooth operation. • Downtime will be reduced as SS pipelines are corrosion & wear resistant, thereby reduction in frequent maintenance. • Work planning will be better hence maintenance cost will be reduced. • Due to minimized wear & tear, spares breakage will be reduced. • System availability will be increased & system outages will be reduced. • Due to frequent failures of IAC, it becomes mandatory to repair the damaged one on priority that creates an emergency for maintenance activities. • By implementing above scheme, there will be substantial reduction in outages of the IAC which will confirm improvement in the performance of Ash Handling Plant. |  |  |  | 0 | [8 empty] | 60 | [16 empty] | 0 | [7 empty] | 60
52 | Improvement in DRY ASH Evacuation system-2 | DPR |  |  |  | 40 | [11 empty] | 0 | [25 empty] | 0
52.1 | Scheme1: Supply & Installation of TAC, Replacement of Air Lock Vessel, Various Valves, ESP Hopper Doors, ESP access doors. | Scheme |  |  |  | 40 | [7 empty] | • TAC availability will be increased that will lead to smooth functioning of dry ash evacuation system. • Reduction in wear & tear of spares thereby Downtime will be reduced. • Work planning will be better hence maintenance cost will be reduced. • Due to minimized wear & tear, spares damage will be reduced. |  |  |  | 0 | [7 empty] | 40 | [17 empty] | 0 | [6 empty] | 40
53 | Improvement in DRY ASH Evacuation system-3 | DPR |  |  |  | 35 | [11 empty] | 0 | [25 empty] | 0
53.1 | Scheme1: Procurement of Ingersoll Rand Make Transport Air Compressors Critical/Non-Critical Spares sub-assembly for performance improvement. | Scheme |  |  |  | 35 | [7 empty] | • TAC availability will be increased that will lead to smooth functioning of dry ash evacuation system. • Reduction in wear & tear of spares thereby Downtime will be reduced. • Work planning will be better hence maintenance cost will be reduced. • Due to minimized wear & tear, spares damage will be reduced. • Spare sub-assembly ensure the system availability in case of failure of existing one. • Being unavailability of sub-assemblies, it becomes mandatory to repair/replace the damaged spares on priority that creates an emergency for maintenance activities. Hence one to one replacement is essential to reduce the down time and fast availability of auxiliary in time. |  |  |  | 0 | [8 empty] | 35 | [16 empty] | 0 | [7 empty] | 35
54 | Detailed project report for various works of security section as per the IB recommendations. | DPR |  |  |  | 1.9374 | [11 empty] | 0 | [25 empty] | 0
54.1 | Repairing & raising height of compound wall with provision of concertina coil at various location of peripheral compound wall at 3x660MW KTPS Koradi. | Scheme |  |  |  | 1.593 | [11 empty] | 0 |  |  |  |  | 1.593 | [20 empty] | 0 |  |  |  | 1.593
54.2 | Work of Providing structural three quarter turn staircase with landing along pheriphery of FISS watch tower at 3x660MW, TPS, Koradi. | Scheme |  |  |  | 0.34444 | [11 empty] | 0 |  |  |  |  | 0.34444 | [20 empty] | 0 |  |  |  | 0.34444 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | Supply, installation, comissioning and testing of 220V station & 360V UPS batteries installed at U 8, 9 & 0 of 3x660 MW KTPS, Koradi. | DPR |  |  |  | 74.11 | [11 empty] | 0 | [25 empty] | 0
55.1 | Supply, installation, comissioning and testing of 220V station & 360V UPS batteries installed at U 8, 9 & 0 of 3x660 MW KTPS, Koradi. (scheme) | Scheme |  |  |  | 68.4 | [7 empty] | Due to non-availability of battery supply in case of A.C failure, major damages may take place to the various important auxiliaries such as Turbine and Generator due to non availability of lub oil and seal oil system. This may further increase the breakdown period of unit resulting in heavy economic loss which cannot be quantified exactly. The new battery set will help to enhance the safe operation of system. |  |  |  | 0 |  |  |  |  | 22.8 | 22.8 | 22.8 | [18 empty] | 0 |  |  |  | 22.8 | 22.8 | 22.8
| IDC |  |  |  |  | 5.71 | [11 empty] | 0 | [25 empty] | 0
56 | TDBFP Governing valve's LPCV ,HPCV MSV AND Trip lock replacement | DPR |  |  |  | 25 | [7 empty] | • No schedule over-run or delay during overhaul/ breakdown on account of unavailability of these critical spares. • Capitalized under insured spares hence help in reducing the high cost inventory. • PLF improvement. • Stable operation and increase in plant availability. • Long service life hence reduced maintenance cost. |  |  |  | 0 | [5 empty] | 25 | [19 empty] | 0 |  |  |  |  | 25
61 | Procurement & replacement of HP Heaters at 3x660 MW KTPS, Koradi. | DPR |  |  |  | 25 | [7 empty] | A) Improvement in system heat rate.b.)Improvement in performance of hp heaters c) Improvement in PLF D.) Stable operation and increase plat availiability. E)Long service life hence reduce mainteance cost. G) Capitalised under isured spares hence help reducing the hihg cost inventroy . |  |  |  | 0 | [25 empty] | 0 |  |  |  |  | 25
[18 empty] | 0 | [25 empty] | 0
| Upgradation of Vibration Monitoring & Analysis system installed at 3x660MW Koradi TPS. | DPR |  |  |  | 63 | [11 empty] | 0 |  |  |  |  | 63 | [20 empty] | 0 |  |  |  | 63 | [5 empty] | 2025-26
| Scheme 1: Upgradation of sinkawa make vibration monitoring and Analysis system for main turbine at 3x660MW koradi TPS. | Scheme | [11 empty] | The scheme is proposed as necessity Scheme which is essential for implementation to Keep the system up and running. To ensure Turbine supervisory instruments & protections in service. |  |  |  | 0 | [25 empty] | 0 | [9 empty] | Newly added Scheme
| Scheme 2: Upgradation of Bently Nevada make vibration monitoring and Analysis system for RMCMS system at 3x660MW Koradi TPS. | Scheme | [11 empty] | The scheme is proposed as necessity Scheme which is essential for implementation to Keep the system up and running. To ensure all HT/LT auxiliaries supervisory instruments & protections in service. |  |  |  | 0 | [25 empty] | 0 | [9 empty] | Newly added Scheme
| Scheme 3 :-Emerson PLC upgradation | Scheme | [11 empty] | The scheme is proposed as necessity Scheme which is essential for implementation to Keep the system up and running. |  |  |  | 0 | [25 empty] | 0 | [9 empty] | Newly added Scheme
| Upgradation of various Level Transmitters installed at 3x660 MW koradi TPS. | DPR |  |  |  | 31 | [11 empty] | 0 | [6 empty] | 31 | [18 empty] | 0 | [5 empty] | 31 |  |  |  | 2027-28
| Scheme 1: Upgradation of Guided wave Radar Level TX installed at Condenser Hotwell and LPH 1,2 and 3 | Scheme | [11 empty] | 1. For process improvement and to ensure auto control loops in service 2.Reduction in Manpower Hrs required for troubleshooting |  |  |  | 0 | [25 empty] | 0 | [9 empty] | Newly added Scheme
| Scheme 2: Upgradation of Displacer type level TX into Guided wave radar level Tx installed at various Drain Tank, Flash tank and pit | Scheme | [11 empty] | 1. For process improvement and to ensure auto control loops in service 2.Reduction in Manpower Hrs required for troubleshooting |  |  |  | 0 | [25 empty] | 0 | [9 empty] | Newly added Scheme
| Scheme 3: Upgradation of non- contact type Ultrasonic level Tx into IP68 non- contact type Radar level TX. | Scheme | [11 empty] | 1. For process improvement and to ensure auto control loops in service 2.Reduction in Manpower Hrs required for troubleshooting |  |  |  | 0 | [25 empty] | 0 | [9 empty] | Newly added Scheme
| Upgradation of ESP Hopper level Probes installed at 3x660 MW koradi TPS. | DPR |  |  |  | 40 | [11 empty] | 0 | [5 empty] | 40 | [19 empty] | 0 |  |  |  |  | 40 |  |  |  |  | 2026-27
| Scheme 1: Upgradation of 1st three fields ESP Hopper level probes into continuous level monitoring NOGS system at 3x660 MW Koradi TPS. | Scheme | [11 empty] | 1. For process improvement 2.Reduction in Manpower Hrs required for troubleshooting |  |  |  | 0 | [25 empty] | 0 | [9 empty] | Newly added Scheme
| Scheme 2: Upgradation of RF capacitance Hopper level probe into of RF admittance level probe at 4,5,6,7,8 & 9 ESP Hoppers | Scheme | [11 empty] | 1. For process improvement 2.Reduction in Manpower Hrs required for troubleshooting |  |  |  | 0 | [25 empty] | 0 | [9 empty] | Newly added Scheme
| Scheme 3: Upgradation of ESP hopper heater monitoring , control and real time monitoring system at 3X660MW Koradi TPS | Scheme | [11 empty] | 1. For process improvement 2.Reduction in Manpower Hrs required for troubleshooting |  |  |  | 0 | [25 empty] | 0 | [9 empty] | Newly added Scheme
| Upgradation of various scheme viz ASLD, Furnace tv camera FEGT and acoustic Pyrometer installed at 3x660 MW koradi TPS. | DPR |  |  |  | 61 | [11 empty] | 0 | [5 empty] | 61 | [19 empty] | 0 |  |  |  |  | 61 |  |  |  |  | 2026-27
| Scheme 1: Upgradation of ASLD system | Scheme | [11 empty] | 1. For process improvement 2. Reduction in Unit downtime |  |  |  | 0 | [25 empty] | 0 | [9 empty] | Newly added Scheme
| Scheme 2: Upgradation of Furnace TV Camera | Scheme | [11 empty] | 1. For process improvement 2. Combustion tuning |  |  |  | 0 | [25 empty] | 0 | [9 empty] | Newly added Scheme
| Scheme 3:Upgradation of FEGT system | Scheme | [11 empty] | 1. For process improvement 2. Combustion tuning |  |  |  | 0 | [25 empty] | 0 | [9 empty] | Newly added Scheme
| Scheme 4:Upgradation of acoustic pyrometer | Scheme | [11 empty] | 1. For process improvement 2. Combustion tuning |  |  |  | 0 | [25 empty] | 0 | [9 empty] | Newly added Scheme
| Upgradation of various scheme viz instrument Air pipe at ESP Area, wet Ash Evacuation system, HCSD Silo. | DPR |  |  |  | 26 | [11 empty] | 0 | [6 empty] | 26 | [18 empty] | 0 | [5 empty] | 26 |  |  |  | 2027-28
| Scheme 1: Upgradation of instrument Air pipeline system at ESP of M.S into SS installed at 3x660 MW Koradi TPS. | Scheme | [11 empty] | The scheme is proposed as necessity Scheme which is essential for implementation to Keep the system up and running. |  |  |  | 0 | [25 empty] | 0 | [9 empty] | Newly added Scheme
| Scheme 2: Upgradation of instrument Air pipeline system at wet Ash system of M.S into SS . | Scheme | [11 empty] | The scheme is proposed as necessity Scheme which is essential for implementation to Keep the system up and running. |  |  |  | 0 | [25 empty] | 0 | [9 empty] | Newly added Scheme
| Scheme 3: Upgradation of instrument Air pipeline system at HCSD silo of M.S. into SS. | Scheme | [11 empty] | The scheme is proposed as necessity Scheme which is essential for implementation to Keep the system up and running. |  |  |  | 0 | [25 empty] | 0 | [9 empty] | Newly added Scheme
| Scheme 4: Upgradation of instrument Air pipeline system at Remote Silo of M.S into SS. | Scheme | [11 empty] | The scheme is proposed as necessity Scheme which is essential for implementation to Keep the system up and running. |  |  |  | 0 | [25 empty] | 0 | [9 empty] | Newly added Scheme
| Scheme 5: Upgradation of Control & Instrument section lab with Hydraulic Servo Valve Test, Pneumatic System test and calibration lab set up. | Scheme | [11 empty] | The scheme is proposed as necessity Scheme which is essential for implementation to Keep the system up and running. |  |  |  | 0 | [25 empty] | 0 | [9 empty] | Newly added Scheme
| Upgradation of Flame scanner for flexible operation of 3X660MW Koradi TPS. | DPR |  |  |  | 35 | [11 empty] | 0 |  |  |  |  | 35 | [20 empty] | 0 |  |  |  | 35 | [5 empty] | 2025-26
| Scheme 1: Upgradation of Flame scanner for flexible operation of 3X660MW Koradi TPS. | Scheme | [11 empty] | For process improvement during mandatory flexible operation of unit |  |  |  | 0 | [25 empty] | 0 | [9 empty] | Newly added Scheme
| Replacement of DRC Pipes, Bends & Fittings in phase manner to improve the dry ash conveying & its disposal (2 years) |  |  |  |  | 30 | [11 empty] | 0 |  |  |  |  | 30 | [20 empty] | 0 |  |  |  | 30
| Replacement of DRC Pipes, Bends & Fittings in phase manner to improve the dry ash conveying & its disposal (2 years) (Rs.30 Cr.) (Bottom ash/Coarse ash evacuation & Ash Slurry Disposal Pipelines, Dry ash conveying system) |  |  |  |  | 30 | [7 empty] | • Less wear & tear as compaired with existing MS Seamless Pipes. • Frequent line leakages, System down time & Maintenance will be reduced. • Material consumption & inventory cost will be minimised. • System availability & performance will be enhanced. |  |  |  | 0 | [25 empty] | 0
| Augmentation of Coarse Ash disposal system at U10 at KTPS, Koradi |  |  |  |  | 84.94 | [11 empty] | 0 | [25 empty] | 0
| WORK OF INSTALLATION & COMMISSIONING OF ASH DISPOSAL SYSTEM AT UNIT#10 |  |  |  |  | 82.01 | [7 empty] | • Due to ash slurry series capacity enhancement, U#10 Wet Ash Evacuation will be done in minimum time. Existing slurry pump house is away from Unit#10, however in proposed scheme new slurry pump house is near Unit#10 bottom ash area. • Proposed slurry pump house will take seperate load of Unit#10 for wet ash evacuation. Hence, loading in existing slurry pump house will be minimised. • Due to reduction in time for evacuation, grinders running hours will be reduced which will reduce wear & tear of spares, hence repetitive maintenance will be minimised. Due to reduction in grinders running hours, water consumption will be reduced. Also bottom ash pile up condition will be minimized. • To meet the site requirement, ash slurry pumps & HP pumps are running continuously as 1 series pump is taking 2-3 jet pump (each jet pump of 225m3 flow). So at a time only 6 jets can be taken in service from respective area, so parallel evacuation is having this limit. For taking evacuation one by one in all three units, it requires sufficient time for changeover, flushing of lines as only one ash water pump house and ash slurry pump house is available. • Also for wet ash evacuation of ESP 1'st and 2'nd field, new HP pump house and wet ash evacuation system (feeder ejectors & submersible slurry pumps) was commissioned & handed over by project in the year of 2022. But considering the extra burden on existing slurry series pumps, no additional slurry series was provided. The proposed scheme will fulfill this requirement. • Design of new slurry system is taken by considering ash slurry pump to ash pond distance - 3.5 Kms. This distance is increased to 7-8 Kms now. • Work planning will be better as inclusion of garlanding work in proposed scheme will make redundancy in ash slurry disposal pipelines operation & maintenance. • Inventory of spares will be reduced as life of spares will be enhanced as separate scheme for Unit#10 will be installed & burden on existing system will be reduced. • Reduction in bottom ash evacuation timing will lead to reduction in generation loss due to bottom ash pile up. • Uniform ash deposition will be done in ash bund due to garlanding of pipelines for various ash slurry feed points in ash bund. That will lead to elimination of excessive pressurization of ash water accumulated in specific area. • Ash spreads in layers enabling vertical filling, hence land requirement is reduced. • Due to uniform ash deposition, more margin will be made available for ash accumulation. • No water releases out due to uniform deposition, hence no need for water retaining walls. • Frequent diversion of dropping ends of ash slurry pipelines will be eliminated. Hence, Maintenance cost will be reduced. • Lower velocity, hence longer life of pipe line. It will enhance the feasibility of ash lifting and therefore maximum ash utilization. • Ash slurry disposal will be done effectively as per the lagoons availability & margin for ash deposition. • Due to garlanding of pipelines, availability of dropping ends for ash deposition. |  |  |  | 0 | [25 empty] | 0 | [5 empty] | 82.01
| IDC |  |  |  |  | 2.93 | [11 empty] | 0 | [25 empty] | 0 |  |  |  | 0 | 0 | 2.93
| DPR for Railway Track Siding Performance Improvement Schemes at 3x660MW KTPS ,Koradi. | [16 empty] | 0 | [25 empty] | 0
| Scheme No. 1 : Work of complete track renovation of existing Rail yard of CHP, 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. Due to continuous movement of Railway's precious rolling stock, the track spares are worn out and are due for complete replacement. Hence, to maintain rail track parameters in healthy condition as per Railway norms so as to avoid untoward incidences of derailment the execution of work of complete track renewal is essential. |  |  |  |  | 30 | [7 empty] | • Higher system availability • Uninterrupted coal stacking and bunkering • Less downtime of critical auxiliary • Increase in plant loadability and availability • Aversion of demurrage charges • Aversion of generation loss • Increase in reliability |  |  |  | 0 | [5 empty] | 30 | [19 empty] | 0 |  |  |  |  | 30
| Scheme No. 2 : Scheme Name- Work of laying of additional track at 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. However, as per the existing infrastructure, at present there is no dedicated empty formation line. Due to non-availability of empty formation line, most often unloading gets hampered due to blocking of outhaul line by empty rake. The hampering in unloading affects the plant performance and incurrs unnecessary financial burden on KTPS account under the head of demurrage charges. Hence, to maintain the plant loadability and availability, it is essential to lay additional track at 3x660MW, KTPS, Koradi. |  |  |  |  | 1 | [7 empty] | • Higher system availability • Uninterrupted coal stacking and bunkering • Less downtime of critical auxiliary • Increase in plant loadability and availability • Aversion of demurrage charges • Aversion of generation loss • Increase in reliability |  |  |  | 0 | [5 empty] | 1 | [19 empty] | 0 |  |  |  |  | 1
| Scheme No. 3 : Scheme Name- Work of rectification and upgradtion of existing SSP at CHP, 3x660MW, KTPS, Koradi. Justification- The SSP has been erected at 3x660MW, KTPS, Koradi. However, till date the same has not been commissioned. With lapse of @ 5-6 years after erection and its non commissioning, the existing SSP set up has been completely detoriorated. Now, Railway's is pressing hard for early commissioning of the same. The said set up shall ensure isolation of OHE of existing yard with Railway's main line. |  |  |  |  | 1 | [7 empty] | • Higher system availability • Uninterrupted coal stacking and bunkering • Less downtime of critical auxiliary • Increase in plant loadability and availability • Aversion of demurrage charges • Aversion of generation loss • Increase in reliability |  |  |  | 0 | [5 empty] | 1 | [19 empty] | 0 |  |  |  |  | 1
| Scheme No. 4 : Scheme Name- Work of construction of apron RCC platforms at inhaul and outhaul of Wagon tipllers 1, 2, 3 & 4 of CHP 3x660MW, KTPS, Koradi. Justification- The 04 Nos. of wagon tipplers are installed at CHP-3x660MW, KTPS, Koradi. In this regards, it is to submit that, the wagon unloading is being carried out through these tipplers. Hence, presence of fugitive dust in tippler area is predominant. The said dust is being accumulated at inhaul and outhaul of wagon tipplers. Due to presence of loaded wagons at inhaul and empty wagons at outhaul, this office gets least opportunity for clearance of the said coal dust along the track. Due to accumulation of coal dust, the rail track parameters along with gradient are getting distubed. The disturbance in gradient is causing rolling of wagons which is not recommended in view of safety of both man and machine. Besides, this due to rolling of wagons, the occurnece of untoward incidence of derailment is predominant. Hence, to maintain uniform rail track gradient it shall be enviable to construct the apron RCC platforms at inhaul and outhaul of Wagon tipplers 1, 2, 3 & 4 of CHP-3x660MW, KTPS, Koradi. Estimated cost- Rs. 4 Cr. |  |  |  |  | 4 | [7 empty] | • Higher system availability • Uninterrupted coal stacking and bunkering • Less downtime of critical auxiliary • Increase in plant loadability and availability • Aversion of demurrage charges • Aversion of generation loss • Increase in reliability |  |  |  | 0 | [5 empty] | 4 | [19 empty] | 0 |  |  |  |  | 4
| Scheme No. 5 : Scheme Name- Work of construction of apron RCC platforms at inhaul and outhaul of Wagon tipllers 1, 2, 3 & 4 of CHP 3x660MW, KTPS, Koradi. Justification- The 04 Nos. of wagon tipplers are installed at CHP-3x660MW, KTPS, Koradi. In this regards, it is to submit that, the wagon unloading is being carried out through these tipplers. Hence, presence of fugitive dust in tippler area is predominant. The said dust is being accumulated at inhaul and outhaul of wagon tipplers. Due to presence of loaded wagons at inhaul and empty wagons at outhaul, this office gets least opportunity for clearance of the said coal dust along the track. Due to accumulation of coal dust, the rail track parameters along with gradient are getting distubed. The disturbance in gradient is causing rolling of wagons which is not recommended in view of safety of both man and machine. Besides, this due to rolling of wagons, the occurnece of untoward incidence of derailment is predominant. Hence, to maintain uniform rail track gradient it shall be enviable to construct the apron RCC platforms at inhaul and outhaul of Wagon tipplers 1, 2, 3 & 4 of CHP-3x660MW, KTPS, Koradi. Estimated cost- Rs. 4 Cr. |  |  |  |  | 4 | [7 empty] | • Higher system availability • Uninterrupted coal stacking and bunkering • Less downtime of critical auxiliary • Increase in plant loadability and availability • Aversion of demurrage charges • Aversion of generation loss • Increase in reliability |  |  |  | 0 | [5 empty] | 4 | [19 empty] | 0 |  |  |  |  | 4
| Scheme No. 6 : Scheme Name- Work of construction of RCC platforms along the rail track of CHP 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. In this regards, it is to submit that, after unloading of rakes the empty rakes are being examined by Railway's C&W staff camped at KTPS, Koradi. Hence, for safe movement of Railway's staff, Railway's is pressing hard for provision of RCC platforms along the rail track of CHP-3x660MW, KTPS, Koradi. Estimated cost- Rs. 10 Cr. |  |  |  |  | 10 | [7 empty] | • Higher system availability • Uninterrupted coal stacking and bunkering • Less downtime of critical auxiliary • Increase in plant loadability and availability • Aversion of demurrage charges • Aversion of generation loss • Increase in reliability |  |  |  | 0 | [5 empty] | 10 | [19 empty] | 0 |  |  |  |  | 10
| Scheme No. 7 : Scheme Name- Work of repairing and construction of RCC permanent revenue canal at, KTPS, Koradi. Justification- The temporary revenue canal is being flowing beside the existing Railway exchange yard of 210 MW, KTPS, Koradi. The said canal gets clogged inview of ash accumulation. Due to clogging this canal overflows and its overrun enters the 210 MW rail yard thereby creating track surface marshy and unsafe for Rail movement. Hence, it is essential to repair and construct RCC permanent revenue canal at KTPS, Koradi so that proper and timely cleaning of canal along with proper outlet can be arranged. Estimated cost- Rs. 15 Cr. |  |  |  |  | 15 | [7 empty] | • Higher system availability • Uninterrupted coal stacking and bunkering • Less downtime of critical auxiliary • Increase in plant loadability and availability • Aversion of demurrage charges • Aversion of generation loss • Increase in reliability |  |  |  | 0 | [5 empty] | 15 | [19 empty] | 0 |  |  |  |  | 15
| Scheme Name-08 Work of construction of RCCretaining wall at Godhani and Kalumna end of KTPS, Koradi. Justification- The separate rail infrastructure has been commissioned for Koradi TPS to cope up the daily coal requirement. The rail traffic at KTPS, Koradi is being catered through Godhani and Kalumna end respectively. In this regards, it is to submit that, the take off points at Godhani and Kalumna both are S&T operated. During monsoon, it is often witnessed that, the rain water enters the plant premises from others land thereby submerging the S&T operated point. Due to this, signals gets lost and hampers the Rail traffic movement completely. Hence, it is essential to restrict the entrance of rain water in plant premises. This can be possible by constructing retaining wall at required loaction. Estimated cost- Rs. 1 Cr. |  |  |  |  | 1 | [7 empty] | • Higher system availability • Uninterrupted coal stacking and bunkering • Less downtime of critical auxiliary • Increase in plant loadability and availability • Aversion of demurrage charges • Aversion of generation loss • Increase in reliability |  |  |  | 0 | [5 empty] | 1 | [19 empty] | 0 |  |  |  |  | 1
| Scheme Name-09 OHE maintenance at CHP, KTPS, Koradi Justification-As per the Railway board circular, Railway's has mandated that OHE maintenance cost for existing as well as new sidings shall be borne by the siding owner in accordance with Railway guidelines. Railway will carry out necessary inspection of maintenance work once in six months. Maintenance charges per TKM per annum of OHE as finalized by SECR zonal office is Rs.291566/- per TKM per annum. Also, inspection charges at the rate of Rs.106974/- per day towards inspection to be carried out by Railways every si x months shall be charged on actual basis by Railway's from the sidings.Accordingly, Railway.s has calimed amount of Rs.31314519/- for two years. Hence for 5 yeards it is expected to be Rs.7.82 Cr. Estimated cost- Rs. 7.82 Cr. |  |  |  |  | 7.82 | [7 empty] | • Higher system availability • Uninterrupted coal stacking and bunkering • Less downtime of critical auxiliary • Increase in plant loadability and availability • Aversion of demurrage charges • Aversion of generation loss • Increase in reliability |  |  |  | 0 | [5 empty] | 7.82 | [19 empty] | 0 |  |  |  |  | 7.82
| Scheme 10 Name-Remodelling and upgradation of existing S & T system with Panel Interlocking system and associated S & T gears to S & T system with Electronic Interlocking system and associated S & T gears in connection with services for BG Railway facility (660 MW Rail yard) for Koradi Thermal Power Station of MSPGCL Justification-As per the prevailing Railway norms, it is mandatory to commission the S & T system in private Railway siding for fast and safe movement of Railway’s precious rolling stock. Unless and until remodeling is carried out the S&T system cannot be started at Koradi Railway yard.With commissioning and operation of S & T system there shall be least possibility for derailments during internal shunting through crossovers, as the said points shall be motorized operated. Estimated cost- Rs. 20 Cr. |  |  |  |  | 20 | [7 empty] | • Higher system availability • Uninterrupted coal stacking and bunkering • Less downtime of critical auxiliary • Increase in plant loadability and availability • Aversion of demurrage charges • Aversion of generation loss • Increase in reliability |  |  |  | 0 | [5 empty] | 20 | [19 empty] | 0 |  |  |  |  | 20
| Scheme No. 11 : Work of supply and provision of lights and high mast at CHP Railway exchange yard of 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. In this regards, it is to submit that, after unloading of rakes the empty rakes are being examined by Railway's C&W staff camped at KTPS, Koradi on round the clock basis. Hence, for safe movement of Railway's staff, Railway's is pressing hard for availability of proper illumination in complete yard. Estimated cost- Rs.2.5 Cr. |  |  |  |  | 25 | [7 empty] | • Higher system availability • Uninterrupted coal stacking and bunkering • Less downtime of critical auxiliary • Increase in plant loadability and availability • Aversion of demurrage charges • Aversion of generation loss • Increase in reliability |  |  |  | 0 | [5 empty] | 25 | [19 empty] | 0 |  |  |  |  | 25
| DPR for Provision of cover shed for stack yard -2 at 3x660MW KTPS ,Koradi. |  |  |  |  | 135 | [11 empty] | 0 | [25 empty] | 0
| Scheme No. 1 : Provision of cover shed for stack yard -2 at 3x660MW KTPS ,Koradi. |  |  |  |  | 135 | [7 empty] | 1) Protection from weather conditions 2) Improved livestock handling 3) Enhanced operational efficiency 4) Increased longitivity of equipment 5) Cleaner working conditions 6) Reduction in manpower fatigue |  |  |  | 0 | [25 empty] | 0 |  |  |  |  | 135
| DPR for Procurement of Pipe Conveyor Drive System Internals at 3x660MW KTPS ,Koradi. |  |  |  |  | 27 | [11 empty] | 0 | [25 empty] | 0
| Scheme No. 1 : Procurement of Pipe Conveyor Drive System Internals at 3x660MW KTPS ,Koradi. |  |  |  |  | 27 | [11 empty] | 0 | [25 empty] | 0 |  |  |  |  | 27
| DPR for Provision of service building along with vehicle bay at 3x660MW KTPS ,Koradi. |  |  |  |  | 30 | [11 empty] | 0 | [25 empty] | 0
| Scheme No. 1 : Provision of service building along with vehicle bay at 3x660MW KTPS ,Koradi. |  |  |  |  | 30 | [11 empty] | 0 | [25 empty] | 0
| GENERAL ASSET | [16 empty] | 0 | [25 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | GENERAL ASSET--AKRDFOGA01-OFFICE FURNITURE | Non-DPR | N.A. | [6 empty] | - | [5 empty] | 0.25116 |  | 0.25116 | 0.1846 | 0.088895 | 0.08293 | 0.15 | [18 empty] | 0.25116 |  | 0.1846 | 0.43576 | 0.088895 | 0.08293 | 0.15 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | GENERAL ASSET--AKRDFOGA02-COMPUTERS,PRINTER,SCANNER | Non-DPR | N.A. | [6 empty] | - | [5 empty] | 0.91932 | 0.24746 | 1.1668 | 0.049645 | 0.045849 | 0.24775 | 0.19 | [18 empty] | 0.91932 | 0.24746 | 0.049645 | 1.2164 | 0.045849 | 1.4587 | 0.19 | [10 empty] | 0 | 0 | 0 | 0 | 0 | -1.211 | 0 | -1.211
3 | GENERAL ASSET--AKRDFOGA03-AC,WATER COOLER | Non-DPR | N.A. | [6 empty] | - | [5 empty] | 0.062631 | 0.16053 | 0.22316 | 0.033135 | 0.0345 | 0.038181 | 0.17 | [18 empty] | 0.062631 | 0.16053 | 0.033135 | 0.2563 | 0.0345 | 0.038181 | 0.17 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | GENERAL ASSET--AKRDFOGA04-AIR PURIFIER | Non-DPR | N.A. | [6 empty] | - | [7 empty] | 0 | 0.0105 | [23 empty] | 0.0105 | 0.0105 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D) Non-DPR Schemes | [8 empty] | - | [7 empty] | 0 | [25 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Procurement of KLEP Unit for 'HCSD Pump | Non-DPR |  |  |  |  | 3.73 |  |  | - |  |  |  | • 100% availability of all the 3 nos. of Geho Pumps, thus reduction in water consumption. • Generation loss incurred due to non-availability of auxiliaries may be avoided. |  |  |  | 0 |  |  | 3.73 | [22 empty] | 0 |  | 3.73 | [7 empty] | *PO 4385000679 DISP VIDE DISP NO-01299 DT.-26/10/2023 Capitalized in F.Y.2023-24 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Restoration of Boiler Circulation Pump at 3X660MW KTPS, Koradi | Non-DPR |  |  |  | 4.73 | [7 empty] | 1)Due to availability of BCP the heat recovery by means of recirculation is achieved. 2)Delay in synchronization for achieving water chemistry & temperature gets reduced. This also result in reduced fuel oil consumption. |  |  |  | 0 |  |  |  | 4.73 | [21 empty] | 0 |  |  | 4.73 | [6 empty] | 1. Capitalized in April 2024.
3 | Procurement of Coal Compartment Assemblies for Unit-10 at 3x660MW KTPS, Koradi. | Non-DPR |  |  |  | 3.73 | [7 empty] | 1) Combustion tunning will improve 2) Reduction in tube leakages due to temperature excursion |  |  |  | 0 |  |  |  | 3.73 | [21 empty] | 0 |  |  | 3.73 | [6 empty] | 1. BOARD APPROVED. 2. PO 4370003260 placed. 3. Material Awaited​
4 | Repairing and Refurbishment of TDBFP cartridge Model FK6E40 installed at 3X660MW KTPS, Koradi | Non-DPR |  |  |  | 11.86 | [7 empty] | Scheme-1 As such this Non- DPR is does not has direct implication on system improvement or any adaption of new technology. The Non DPR scheme is proposed as a remedial measure to prevent the tremendous loss on account of unforeseen failures of TDBFP cartridge by reducing the auxiliary downtime and restoration. Hence impact on tariff cannot be calculated since there is no impact on plant operating parameters. The implementation of scheme shall ensure reduction in the downtime for auxiliary restoration, it will increase system reliability, TDBFP system efficiency and also improve the plant loadability in long run. Payback calculation is done on the basis of lead time of 10 Months that is required to make TDBFP cartridge available in case when it is not readily available at section for immediate replacement:- The implementation of scheme shall ensure reduction in the downtime for auxiliary restoration, it will increase system reliability, TDBFP system efficiency and also improve the plant loadability in long run and also payback period is calculated. Simple payback comes out to be 09 Days (0.314 Months) |  |  |  | 0 |  |  |  | 11.86 | [21 empty] | 0 |  |  | 11.86 | [6 empty] | 1. BOARD APPROVED. 2. PO 4385000770 Dispatched
5 | Non-DPR for Upgradation of Honeywell Make PLC for Mill Reject Handling System installed at 3x660MW Balance of Plant (BOP) Unit- 8, 9 & 10 at Koradi TPS | Non-DPR |  |  |  | 0.85 | [7 empty] | a. To make compatible existing PLC hardware with new operating system. b. To prevent operating system from virus attack by installing latest antivirus software. c. Make compatible current market software with new operating system. d. To cope up with current Honeywell Automation hardware support. e. To avail new software product from M/s Honeywell Automation Pvt. Ltd. f. To achieve spare workstations machines availability for hardware failure replacements. |  |  |  | 0 |  |  |  | 0.85 | [21 empty] | 0 |  |  | 0.85 | [6 empty] | 1. BOARD APPROVED. 2. PR 1100156048, Enquiry extended upto 05.09.2024. 3. DPO to Audit Dt.18.10.2024 4.Budget allotted Dt.14.11.2024
6 | Procurement of Sky Climber for furnace repairing at 3x660MW KTPS, Koradi | Non-DPR |  |  |  | 3.02 | [7 empty] | 1) This will ensure safety of persons working at height 2) With complete set availability, the BTL attending time will reduce |  |  |  | 0 |  |  |  | 3.02 | [21 empty] | 0 |  |  | 3.02 | [6 empty] | 1. PO 4370003475 Dispatched. 2. Material awaited
7 | Double Roll Clinker Grinder | Non-DPR |  |  |  | 1.68 | [7 empty] | • Wet Ash Evacuation System outages will be reduced. • Due to modified metallurgy, wear & tear of spares will be reduced, hence repetitive maintenance will be minimized. • Maximum Double Roll Clinker grinders will be guaranteed available for bottom ash evacuation. • Work planning will be better. Inventory of spares will be reduced as life of spares will be enhanced. • Due to modifications in internal spares design & MOC, leakages will be minimized that will reduce the wear & tear of other related parts and wastage of water. • Being unavailability of spare Double Roll Clinker Grinder Assembly with Drive Unit, it becomes mandatory to repair the damaged grinder on priority that creates an emergency for maintenance activities. Increase plant availability & reduction in generation loss. |  |  |  | 0 |  |  |  | 1.68 | [21 empty] | 0 |  |  | 1.68 | [6 empty] | 1. BOARD APPROVED. 2. PO-4385000766 Dispatched
8 | Procurement along with Installation of Clear Water Booster Pump with Motor, Panel Cable and other allied accessories in Unit#10 bottom ash area at AHP, 3x660MW, KTPS, Koradi. | Non-DPR | N.A. |  |  | 2.56 |  |  |  | - |  |  |  | • Due to enhancement of jet pump inlet pressure, U#10 Bottom Ash Evacuation will be done in minimum time. • Due to enhancement of pressure, bottom ash pile up condition will be minimized. • Due to reduction in time for evacuation, grinders running hours will be reduced which will reduce wear & tear of spares, hence repetitive maintenance will be minimized. • Work planning will be better. • Inventory of spares will be reduced as life of spares will be enhanced. • Due to reduction in grinders running hours, water consumption will be reduced. Reduction in bottom ash evacuation timing will lead to reduction in generation loss due to bottom ash pile up. |  | 0.25116 |  | 0.25116 | 0.1846 |  |  | 2.56 | [21 empty] | 0 |  |  | 2.56 | [6 empty] | 1. BOARD APPROVED. 2. PO 4370003477 dispatched on dt 12.10.2024
9 | Procurement of single Roll Clinker Grinder with Feed Pump & Jet Pump Complete Assembly with modified metallurgy installed at AHP ,3x660MW Units, KTPs, Koradi | Non-DPR | N.A. |  |  | 2.12 |  |  |  | - |  |  |  | • Wet Ash Evacuation System outages will be reduced. • Due to modified metallurgy, wear & tear of spares will be reduced, hence repetitive maintenance will be minimized. • Maximum Single Roll Clinker grinders will be guaranteed available for bottom ash evacuation. • Work planning will be better. Inventory of spares will be reduced as life of spares will be enhanced. • Due to modifications in internal spares design & MOC, leakages will be minimized that will reduce the wear & tear of other related parts and wastage of water. • Being unavailability of spare Single Roll Clinker Grinder Assembly, it becomes mandatory to repair the damaged grinder on priority that creates an emergency for maintenance activities. Increase plant availability & reduction in generation loss. |  | 0.91932 | 0.24746 | 1.1668 | 0.049645 |  |  | 2.12 | [21 empty] | 0 |  |  | 2.12 | [6 empty] | 1. Board Approved 16.08.2024. 2. PR 1100147292 approval received on dt 05.10.2024 3.TB opened 01.11.2024
10 | Work of Repairing and Refurbishment of HIP Rotor along with balancing and over speed trial for L&T-MHI make turbine (Type: TC4F-30”) installed at 3X660MW KTPS, Koradi | Non-DPR | N.A. |  |  | 7.13 |  |  |  | - |  |  |  | The removed HIP Rotor is rejected as per OEM standards and it is a sitting liability.This rotor cannot be used unless it is repaired and refurbished. Also,it’s balancing and over speed trial is essential. Furthermore, the cost for repairing and refurbishment of HIP Rotor is less than procuring a new HIP Rotor by Rs.27.18 Cr. which is a huge saving in itself. Thus, to make the HIP rotor available,the scheme is proposed. The implementation of scheme shall ensure availability of HIP Rotor, reduction in the downtime for restoration and shall help in saving huge financial loss on account of unavailability of HIP Rotor.The payback period is also calculated considering the delay for restoration in case the HIP Rotor is not available. |  | 0.062631 | 0.16053 | 0.22316 | 0.033135 |  |  | 7.13 | [21 empty] | 0 |  |  | 7.13 | [6 empty] | 1. BOARD APPROVED. 2. PR Sent to HO on dt.30.01.2024 3. Reply to H.O. observations sent on Dt. 26.07.2024.
11 | Procurement of spares for Flue gas distribution dampers, PA fan discharge dampers and Coal mill Hot PA Gate and Dampers at 3x660mw KTPS units through OEM | Non-DPR | N.A. |  |  | 3.7 |  |  |  | - | [7 empty] | 0 | 0.0105 |  |  | 3.7 | [21 empty] | 0 |  |  | 3.7 | [6 empty] | 1. PR Sent to H.O. on Dt.22.08.2024, 2. H.O. Observations received 27.08.2024
12 | Work of Modification & Installation of Take up trolley & arrangement for take up lifting for conveyor BCN-13A at CHP 3X660MW,KTPS,Koradi | Non-DPR | N.A. |  |  | 0.75 | [7 empty] | • Expedite the work with safe working condition • Damaging to the costly take up pulleys will decrease. • Consumption of conveyor pulleys will be decreased. • System availability will increase. • Generation loss will decrease. • Avoid subsequent damages and heavy generation loss | 0 | 207.3486 | 148.5344 | 355.8831 | 40.2432 |  |  | 0.75 | [17 empty] | 0 |  |  |  | 0 |  |  | 0.75 | [6 empty] | 1. NON-DPR Sent to HO on dt.23.08.2023. 2. Datagaps received 12.09.2024 3. PR to Audit 05.11.2024
13 | Work of Design, Modification & streingthening of Tripper trolley structure with provision of Antiwear plates discharge chute box at CHP 3X660MW,KTPS,Koradi | Non-DPR | N.A. |  |  | 1.16 | [7 empty] | • Decrease in breakdown of tripper trolley • Damaging to the costly conveyor belt will decrease. • System availability will increase. • Less maintenance time required • Generation loss will decrease. |  |  |  | 0 |  |  |  | 1.16 | [21 empty] | 0 |  |  | 1.16 | [6 empty] | 1. NON-DPR Sent to HO on dt.23.08.2023. 2. Datagaps reply sent to H.O. on Dt.12.09.2024
14 | Upgradation of Management Information System (MIS) Server and Associated Software for C&I at 3x660MW Unit- 8, 9 & 10 at Koradi TPS | Non-DPR | N.A. |  |  | 2.145 | [7 empty] | The scheme is proposed as necessity Scheme which is essential for implementation to Keep the system up and running. |  |  |  | 0 |  |  |  | 2.145 | [21 empty] | 0 |  |  | 2.145 | [6 empty] | 1. NON-DPR sent to H.O. on dt.21.05.2024 2. PR-1100160480 sent to H.O. on Dt.08.08.2024 3. Reply ro HO observation sent on dt 31.08.2024
15 | Procurement of Vibrating Tranfer chute with double exciter Drive for stacker reclaimer at CHP,3X660MW,KTPS ,Koradi | Non-DPR | N.A. |  |  | 0.934 | [7 empty] | • Spare vibrating feeder assembly ensures system healthiness & availability in case of failure of existing one. • Unloading time of coal rakes will be reduced resulting into reduction in demurrage charges further overall performance of CHP will be improved. • Increase plant availability & reduction in generation loss. |  |  |  | 0 |  |  |  | 0.934 | [21 empty] | 0 |  |  | 0.934 | [6 empty] | 1. NON-DPR sent to H.O.on dt.31.07.2024 2. Data gap reply sent 17.09.2024
16 | Supply & Installation of Ash Slurry Density Transmitter at High Concentrated Slurry Disposal (HCSD) System of BOP area of 3x660MW Unit- 8, 9 & 10 at Koradi TPS | Non-DPR | N.A. |  |  | 1.26 | [7 empty] | 1. For process improvement 2. Reduction in Manpower Hrs required for troubleshooting. |  |  |  | 0 |  |  |  | 1.26 | [21 empty] | 0 |  |  | 1.26 | [6 empty] | 1. NON-DPR sent to H.O.on dt.27.07.2024 2. Datagaps received on Dt.21.10.2024
17 | Supply & Installation of Fiber Optic Sensing System for Conveyor Health Monitoring At CHP 3x660MW KTPS, Koradi | Non-DPR |  |  |  | 11.72 | [7 empty] | 1) Early detection warnings allow operator to control down time & avoid catastrophic costly unplanned shutdown. 2) Increase plant availability & reduction in generation loss. 3) Reduction in demurrage charges |  |  |  | 0 |  |  |  |  | 11.72 | [20 empty] | 0 |  |  |  | 11.72 | [5 empty] | 1. Board Approved 08.08.2024 2. PO in process at H.O.
18 | Procurement of Leak- proof make complete Mechanical Seal Assembly for Concrete Volute CW Pump installed at 3X660MW KTPS,Koradi on OEM bASIS. | Non-DPR |  |  |  | 1.94 | [7 empty] | All the three Units are in continuous working on optimum load. Presently, CWP-10A is running with mechanical seal leakage, for which continuous monitoring and dewatering is required. CW Pumps are itself critical and crucial auxiliary in generation path. |  |  |  | 0 |  |  |  | 1.94 | [21 empty] | 0 |  |  | 1.94 | [6 empty] | 1. NON-DPR sent to HO on Dt.01.10.2024 2.PR sent to DYCE for TC Dt.13.11.2024 3. PR to Audit Dt.15.11.2024
19 | Work of Design , Engineering , Manufacturing , Supply Erection & Commissioning of Conveyor Belt From Discharge of RBF 1 &2 at Crusher House to Stack Yard At CHP 3x660MW KTPS, Koradi . | Non-DPR |  |  |  | 11.39 | [7 empty] | • Coal requirement can be catered, even after non availability of existing stacking stream BCN-13A /13B . • Similarly receipt of wet and sticky coal particularly in rainy season choke up the wagon tippler hoppers and also receiving as well as discharge chute of conveyor belt. Many times, rakes are received in Bunching. Due to above reasons heavy demurrage is to be paid to Railway. Due to system constraints of above mention reason, number of times it is essential to stack the coal wagons at CHP stack yard instead of bunkering. Such coal can be stacked by using this short conveyor and can be used later. Stacker reclaimer can be used for bunkering mode with good quality coal. • Additional / alternate stream for stacking with less energy consumption compared to existing Stacker reclaimer stream due to involvement of lesser auxiliaries & short set up. • Planned maintenance outage of conveyor stram & stacker reclaimer can be carried out as additional stacking stream is available. • Parallel stacking can be made possible thereby increasing the plant loadability and decreasing demurrage charges . • Overloading of belt can be eliminated. • Increase in overall plant loadability & booster for achieving the maximum PLF. • High reliability due to less auxiliaries |  |  |  | 0 |  |  |  |  | 11.39 | [20 empty] | 0 |  |  |  | 11.39 | [5 empty] | 1. NON-DPR sent to H.O.dt.18.05.2024. Third Party vetting under process
20 | Supply & Installation of Artificial Intelligence PMMS Accurex Diagnostic matrix based vibration & temperature monitoring for critical auxiliaries at CHP 3x660MW KTPS, Koradi. | Non-DPR |  |  |  | 6.431 | [11 empty] | 0 |  |  |  |  | 6.431 | [20 empty] | 0 |  |  |  | 6.431 | [5 empty] | 1. NON-DPR set to H.O. on Dt.22.06.2024 2.ToAudit after compliance Dt.21.10.24
21 | Restoration of online dissolved gas analysers of Unit 8,9,10 | Non-DPR |  |  |  | 1.109 | [11 empty] | 0 |  |  |  |  | 1.11 | [20 empty] | 0 |  |  |  | 1.11 | [5 empty] | 1.Non-DPR sent to H.O. on Dt.15.04.2024
22 | Complete Replacement of Existing Water Separator Drain Tank Control (WDC) Valves with New Valves of modified trim design along with hydraulic Actuators, Power Pack assembly, necessary instrumentation, erection & commissioning 3X660MW KTPS, Koradi. | Non-DPR |  |  |  | 5.33 | [7 empty] | The proposed Non-DPR have a direct implication on system improvement which can be deduced from following :- • Shall prevent any forced outages on account of WDC. • Reliable valve operation. • Better control. • Reduction on condenser loading. • Improvement in plant parameters • Increase in plant loadability. • Increase in plant availability. • Increase in plant reliability. In addition to this, the replacement of existing valves with hydraulic actuators and with modified trip design is an adaptation of new technology that shall bring upon following improvements :- • Long service life. • Better performance of WDC System. • Precision in control. • Valve tightness with no passing of valves. The Non-DPR scheme is proposed as a remedial measure to prevent unit tripping on account of WDC valve getting stuck/ inoperative during system emergencies or unit commissioning activities and thus shall help in saving the tremendous loss on account of WDC. It is submitted to the Honorable Commission that under conditions where other parameters are adversely affected, demonstration of the projected improvement may not be achieved to the full extent. However, it is submitted that it will be the endeavor of the plant to achieve the full benefits from the implementation of scheme. Furthermore, payback period is also calculated which comes out to be just 3 days.CASE-1: When the New Hydraulic Valves are Not Available Ø Minimum time required to supply and make the Hydraulic valves available at site is11 Months i.e. 330 Days. Ø Minimum time required for replacement after it is made available at site is 30 days Ø Total No. of days for days unit will be under shutdown = 360 days Now, Fixed cost disallowance per unit per day for generation= Rs. 2.05 Cr. Thus, total loss due to unit outage for 360 days = 360 x 2.05 = Rs. 738 Cr. CASE-2: If the Hydraulic Valves are kept available at site Ø Time required for valves replacement = 30 days Now, Fixed cost disallowance per unit per day for generation= Rs. 2.05 Cr. Thus, total loss due to unit outage for 30 days = 30 x 2.05 = Rs. 61.5Cr. Hence, considering both the cases, if the Hydraulic valves are kept available for replacement, then the availability of unit increases by 330 Days. Total savings for 330 Days = 330 x 2.05 = Rs. 676.5 Cr. Payback Period: Payback period = (Cost of capital spares/disallowance fixed cost saved per day per unit.) Payback Period = 5.33 / 2.05 = 2.6 ~ 03 Days Thus, the payback period comes out to be 03 Days. |  |  |  | 0 |  |  |  |  | 5.33 | [20 empty] | 0 |  |  |  | 5.33 | [5 empty] | 1.Non-DPR sent to H.O. on Dt.15.06.2024 2.Datagap reply sent to H.O. On Dt.09.07.2024 3.PO 4550023920 is dispatched in R&M budget dt.12.09.2024
23 | Procurement of mandatory set of Hydraulic system internals for Wagon Tippler Drive & side arm charger Drive at CHP,3X660MW,KTPS ,Koradi | Non-DPR |  |  |  | 6.35 | [7 empty] | • Reduction in demurrages. • Spare Prime mover and Drive ensure system availability in case of failure of existing one. • Increase plant availability & reduction in generation loss. |  |  |  | 0 |  |  |  |  | 6.35 | [20 empty] | 0 |  |  |  | 6.35 | [5 empty] | 1. NON-DPR sent to H.O.on dt.13.07.2024
24 | "Supply & installation of Anodized winding Oil cooled over band magnetic separator & control panel for conveyor 5A,5B &13C at CHP 3x660MW KTPS, Koradi. | Non-DPR |  |  |  | 1.896 | [7 empty] | 1) Damaging to the costly conveyor belt will decrease. 2) Consumption of conveyor belt will be decreased. 3) Belt replacement and belt jointing time will be decrease. 4) System availability will increase. 5) Generation loss will decrease. |  |  |  | 0 |  |  |  | 1.896 | [21 empty] | 0 |  |  | 1.896 | [6 empty] | 1. NON-DPR sent to H.O.on dt.13.07.2024
25 | Procurement of Grinding Wall Assembly for Impact Crusher At CHP 3x660MW KTPS, Koradi | Non-DPR |  |  |  | 2.01 | [7 empty] | • Spare Grinding Wall Assembly ensures system healthiness & availability in case of failure of existing one. • Unloading time of coal rakes will be reduced resulting into reduction in demurrage charges further overall performance of CHP will be improved. • Increase plant availability & reduction in generation loss. • Reduction in operational and maintenance cost. • Reduction in Coal Handling Plant downtime. • Reduction in wear & tear of Coal Mills internals due to proper sized coal supply • System outages will be reduced. • Life enhancement of auxiliary |  |  |  | 0 |  |  |  | 2.01 | [21 empty] | 0 |  |  | 2.01 | [6 empty] | 1. NON-DPR sent to H.O.on dt.03.08.2024
26 | Restoration of Boiler Circulation Pump of U10 at 3X660MW KTPS, Koradi | Non-DPR |  |  |  | 6.69 | [7 empty] | 1) 100% availability of all the Boiler Circulation Pumps will help to reduce fuel consumption during the start-up/light-up activities 2) Delay for synchronization will reduce by 2-3 hrs. |  |  |  | 0 |  |  |  |  | 6.69 | [20 empty] | 0 |  |  |  | 6.69 | [5 empty] | NON-DPR scrutiny under process.
27 | Design,Engineering,Customization,Implementation,Installation & testing of Data Analytical/Artificial Intellegence softwae for automated monitoring & diagnostics system to improve Power plant reliability & efficiency,at one unit of 3X660MW KTPS, Koradi. | Non-DPR |  |  |  | 3.27 | [7 empty] | 1. For process improvement 2. Reduction in Manpower Hrs required for troubleshooting. |  |  |  | 0 |  |  |  | 3.27 | [21 empty] | 0 |  |  | 3.27 | [6 empty] | 1.NON-DPR sent to section for compliance Dt.26.09.24 2. Summary prepared. Dt.26.09.24 3. To audit after compliance on Dt.04.11.2024
28 | Supply of Feed Gate Complete Assembly along with installation to enhance the performance of Feed Gate at Ash Handling Plant, 3x660MW, KTPS, Koradi. | Non-DPR |  |  |  | 2.4 | [7 empty] | • Wet Ash Evacuation System outages will be reduced. • Due to modified metallurgy, wear & tear of spares will be reduced, hence repetitive maintenance will be minimized. • Maximum Double Roll Clinker grinders will be guaranteed available for bottom ash evacuation. • Work planning will be better. Inventory of spares will be reduced as life of spares will be enhanced. • Due to modifications in internal spares design & MOC, leakages will be minimized that will reduce the wear & tear of other related parts and wastage of water. • Being unavailability of spare Double Roll Clinker Grinder Assembly with Drive Unit, it becomes mandatory to repair the damaged grinder on priority that creates an emergency for maintenance activities. Increase plant availability & reduction in generation loss. |  |  |  | 0 |  |  |  |  | 2.4 | [20 empty] | 0 |  |  |  | 2.4
29 | Design, Supply, Installation & Commissioning of Instrument Air Dryer Assembly with Prefilters & Stainless steel piping along with valves suitable for Instrument Air Compressors at AHP, 3x660MW Units, KTPS, Koradi | Non-DPR |  |  |  | 5.5 | [7 empty] | • Ash Handling System outages will be reduced. • Due to moisture free air, life & performance of instrumentation installed at AHP such as pressure switches, Solenoid operating valves (SOV), etc. will be improved. Due to frequent failure of instrumentations, secondary damages of various valves such as dome vale, poppet valve has increased significantly leading to excessive maintenance outages, addition in spares/material consumption, etc. This can be avoided by installation of new Dryers. • Due to moisture free air, clogging of Filter bags while purging will be reduced significantly, thereby Silo pressurization issues will be minimized. • Due to moisture free air, rusting issues observed on rotor assembly of Transport Air Compressor will be avoided. Being high value items, its replacement/repairing cost will be saved and its life & performance will be enhanced. • Vibration probe & gauges functioning will be better. • Being unavailability of spares, it becomes mandatory to repair installed dryers on priority that creates an emergency for maintenance activities. • Increase plant availability & reduction in generation loss. • Due to latest design & MOC, maintenance will be minimized that will reduce the wear & tear of other related systems. • Inventory of spares will be reduced. Work planning will be better. |  |  |  | 0 |  |  |  |  | 5.5 | [20 empty] | 0 |  |  |  | 5.5
| Total | [13 empty] | 15.2847 | 322.3477 | 232.2456 |  | 259.3088 | 138.9621 | 42.8633 | 574.3088 | 2577.9688 | 1452.84 | 569.56 | 219.954 | 122.86 | 0 | [11 empty] | 0 | 214.9907 | 209.0669 | 245.192 | 669.2496 | 93.6906 | 31.8996 | 574.3088 | 2585.8688 | 1639.84 | 654.5 | 219.954 | 122.86
[45 empty] | 0.16924 | 5.3098 | 57.255 | 56.921
Formulas:
Date of Submission = [Date of Submission, row above]
MERC Approval Date = IF([MERC Approval Date, row above]=0,"-",[MERC Approval Date, row above])
MERC Approval Date = [MERC Approval Date, row above]
Note on M4: SSP-RCD As per the implementation plan submitted in the DPR/ Approved by MERC

## F4.3
MSPGCL: Koradi 8-10
MTR Petition Formats - Generation
| Project Details | Form 4.3: Capital Work-in-progress - Project-wise details | [9 empty] | (Rs. Crore)
Sr. No. | Project Code | MERC Approval No. | MERC Approval Date | Approved Project Cost | Cumulative Expenditure Incurred till beginning of the Year | Capital Expenditure Capitalised | Opening CWIP | Investment during the year | Capitalization |  |  |  | Closing CWIP
[9 empty] | Works Capitalised | Interest Capitalised | Expenses Capitalised | Total Capitalisation |  | Allowable Capitalisation | Probable Disallowance
FY 2022-23
| A) Approved Add cap: |  | -
A | BoP | 0 | - | 246.34 | 75.4436 | 205.4974 | -130.0538 | 15.27 | 15.09 |  |  | 15.09 | -129.8738
B | BTG | 0 | - | 44.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B1 | Supply | 0 | - | 13.33 | 0 | 0 | 0 | 0 | 13.33 |  |  | 13.33 | -13.33
B2 | Works | 0 | - | 0.98 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B3 | Taxes and duties | 0 | - | 23.29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B4 | Civil | 0 | - | 0.19 | 0.19 | 0 | 0.19 | 0 | 0 |  |  | 0 | 0.19
B5 | Mandatory Spares | 0 | - | 5.03 | 0 | 0 | 0 | 1.29 | 6.32 |  |  | 6.32 | -5.03
B6 | BTG (L&T) Work | 0 | - | 1.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C | Other Works (Plant) | 0 | - | 136.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C1 | Fully Integrated Security System | 0 | - | 27.36 | 31.4615 | 31.4615 | 0 | 0 | 0 |  |  | 0 | 0
C2 | Administrative Expenses and overhead | 0 | - | 7.25 | 0.24 | 0 | 0.24 | 0.45 | 0 |  |  | 0 | 0.69
C3 | Contingencies E&M | 0 | - | 0.04 | 0 | 0 | 0 | 0.04 | 0 |  |  | 0 | 0.04
C4 | Mobile storage racks, fork lifts, hoists & hydra for material handling in major stores shed | 0 | - | 0.95 | 0.93645 | 0.93645 | 0 | 0 | 0 |  |  | 0 | 0
C5 | Development of working models of Plant Layout, Boiler, Turbine- Generetaor, Coal mill, Fans, etc. at KTC, Koradi. | 0 | - | 1.2 | 1.2 | 0.98604 | 0.21396 | 0 | 0 |  |  | 0 | 0.21396
C6 | Workshop equipment | 0 | - | 0.26 | 0.0377 | 0.26192 | -0.22422 | 0.22422 | 0 |  |  | 0 | 2.7756e-17
C7 | Design, engg, manufacture, supply , erection, testing & commissioning of Ozonization Plant for circulating cooling water system | 0 | - | 54.05 | 31.4983 | 31.3444 | 0.15388 | 0.27 | 0.27 |  |  | 0.27 | 0.15388
C8 | Supply, installation & commissioning of water flow meters including required SCADA software and other accessories for water management system | 0 | - | 5.08 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C9 | Provision of wet ash evacuation system for first two rows of ESP for Unit-8,9 & 19 | 0 | - | 26.59 | 20.79 | 25.4181 | -4.6281 | 0.9 | 0.9 |  |  | 0.9 | -4.6281
C10 | Procurement of portable mercury analyser for flue gas monitoring | 0 | - | 6.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C11 | Administrative Expenses and overhead | 0 | - | 5 | 10.6757 | 0 | 10.6757 | 5.0111 | 0 |  |  | 0 | 15.6868
C12 | Compressor of Hydrogen plant | 0 | - | 1.5 | 1.5 | 0 | 1.5 | 0 | 0 |  |  | 0 | 1.5
C13 | Rail Cum road stone grabbler | 0 | - | 0.85 | 0.85 | 0 | 0.85 | 0 | 0 |  |  | 0 | 0.85
D | Other Works (Civil) | 0 | - | 103.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D1 | Road, Bridges railway system | 0 | - | 20.1 | 0.10806 | 0 | 0.10806 | 0 | 0 |  |  | 0 | 0.10806
0 | S&T System with Panel Interlocking System | 0 | - | 0 | 10.4047 | 10.4058 | -0.0011606 | 0 | 0 |  |  | 0 | -0.0011606
D2 | Staff quarters | 0 | - | 5.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D3 | Other Misc & Unforseen Item | 0 | - | 25.79 | 0 | 0 | 0 | 9.3 | 7.53 |  |  | 7.53 | 1.77
0 | Check Post, Inspection Office & Facility Complex | 0 | - | 0 | 3.51 | 3.5071 | 0.0028689 | 0.17443 | 0.17443 |  |  | 0.17443 | 0.0028689
0 | CPRI Building | 0 | - | 0 | 4.5847 | 4.5847 | 0 | 1.6199 | 1.6199 |  |  | 1.6199 | 0
0 | Foam cum DCP fire tender- 1 | 0 | - | 0 | 0 | 0.76926 | -0.76926 | 0 | 0 |  |  | 0 | -0.76926
0 | Fire water Bowser-cum-fire Tender- 1No. | 0 | - | 0 | 0.73537 | 0.73537 | 0 | 0 | 0 |  |  | 0 | 0
D4 | Const. facility | 0 | - | 3.28 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D5 | Contigency Other Civil Work | 0 | - | 5.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D6 | Adminstrative Exp. & Overhead (Salary & Overhead, Civil & E&M) | 0 | - | 21.47 | 21.47 | 0 | 21.47 | 10.17 | 0 |  |  | 0 | 31.64
D7 | Future unforseen works(Jalyukta Shiwar) | 0 | - | 0.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D8 | Landscaping work | 0 | - | 21.76 | 20.53 | 0 | 20.53 | 0 | 0 |  |  | 0 | 20.53
E | Initial Spares | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
E1 | Boiler & its auxilliaries | 0 | - | 14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Procurement of Table liners and Roller liners Of MVM 32R Coal Mills of 3 X 660MW Units at KTPS, Koradi | 0 | - | 0 | 10.0686 | 10.0686 | 0 | 0 | 0 |  |  | 0 | 0
ii | Procurement of couplings for Coal mill MVM 32 R of 3 X 660 MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 1.5944 | -1.5944 | 0 | 0 |  |  | 0 | -1.5944
iii | Procurement of Set of internal spares for Coal Mill Gear Box (KMP-450) for 3 X 660MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 2.2253 | -2.2253 | 0 | 0 |  |  | 0 | -2.2253
E2 | Turbine & its auxilliaries | 0 | - | 18.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | ULTRAFILTRATION MEMBRANE | 0 | - | 0 | 0 | 0 | 0 | 1.6511 | 1.6511 |  |  | 1.6511 | 0
ii | Supply of Main turbine Vibration Monitoring System spares at 3x660MW, KTPS,Koradi. | 0 | - | 0 | 0 | 1.1469 | -1.1469 | 0 | 0 |  |  | 0 | -1.1469
iii | Procurement of Cartridge for Turbine Driven Boiler Feed Pump (Model No.: FK6E40) at 3X660 MW KTPS Koradi | 0 | - | 0 | 14.2864 | 14.2864 | 0 | 0 | 0 |  |  | 0 | 0
iv | Procurement of Critical Insurance Spares for L&T-MHI Make Turbine for attending major overhauling work of Turbine at KTPS, 3x660MW Units Koradi. | 0 | - | 0 | 0 | 0 | 0 | 11.1013 | 11.1013 |  |  | 11.1013 | 0
E3 | Generator & its auxilliaries | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
E4 | Electrical auxilliaries | 0 | - | 1.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Procurement of HT Motors of BOP | 0 | - | 0 | 0 | 0.29335 | -0.29335 | 0 | 0 |  |  | 0 | -0.29335
ii | 0 | 0 | - | 0 | 0 | 0.84594 | -0.84594 | 0 | 0 |  |  | 0 | -0.84594
iii | Supply of Schneider make Differential Protection Relays for 3X660 MW, Koradi (OEM) | 0 | - | 0 | 0 | 0.10502 | -0.10502 | 0 | 0 |  |  | 0 | -0.10502
iv | Supply of Professional Large Format Display for display of DCS parameters PCR | 0 | - | 0 | 0.14885 | 0.14885 | 0 | 0 | 0 |  |  | 0 | 0
v | Procurement of ABT Energy meter with software for 3X660 MW, TPS, Koradi | 0 | - | 0 | 0 | 0.18337 | -0.18337 | 0 | 0 |  |  | 0 | -0.18337
E5 | Outdoor Plant i.e. CHP, AHP, WTP etc | 0 | - | 19.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Procurement of Forced Lubrication system for Premium make Gear box B3-450 installed for bunker conveyor BCN 7A/B at CHP 3X660MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0.15314 | -0.15314 | 0 | 0 |  |  | 0 | -0.15314
ii | Procurement of rotary spares for travel drive of Stacker and conveyor drive system in Coal Handling Plant of 3x660 MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0.35199 | -0.35199 | 0 | 0 |  |  | 0 | -0.35199
iii | Procurement of Complete assembly of Dome Valve ( 100NB, 200NB, 300NB) with power cylinder for dry Ash evacuation system of 3X660MW KTPS, Koradi. | 0 | - | 0 | 0.2225 | 0.2225 | 0 | 0 | 0 |  |  | 0 | 0
iv | Procurement of Modified Apron Pans for M/s. ELECON Engineering Company ltd make Apron Feeder in CHP 3x660MW Units at KTPS, Koradi. | 0 | - | 0 | 3.3233 | 3.3233 | 0 | 0 | 0 |  |  | 0 | 0
v | Procurement of Single Roll Clinker Grinder with Feed Sump and Jet Pump Complete Assembly with Drive, Driven Sprocket and Chain at AHP, 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.56357 | 0.56357 | 0 | 0 | 0 |  |  | 0 | 0
vi | Procurement of spares of Dome Valve (100NB, 200NB, 300NB) for Ash Evacuation System of 3X660MW Unit KTPS, Koradi. | 0 | - | 0 | 0.16431 | 0.16431 | 0 | 0 | 0 |  |  | 0 | 0
vii | 0 | 0 | - | 0 | 0.10064 | 0.10064 | 0 | 0 | 0 |  |  | 0 | 0
viii | 0 | 0 | - | 0 | 0.00708 | 0.00708 | 0 | 0 | 0 |  |  | 0 | 0
ix | Procurement of Hydraulic Motor for Apron feeder in Coal Handling Plant 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.7965 | 0.7965 | 0 | 0 | 0 |  |  | 0 | 0
x | Procurement of Peristaltic Hose Pump (Model no: RP2 – 40) Spares for HCSD System of Ash Handling Plant, 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.20622 | 0.20622 | 0 | 0 | 0 |  |  | 0 | 0
xi | Procurement of spares for HP Water Pump, Mather & Platt make, model 10/12 EME for AHP at 3X660 MW, KTPS, Koradi | 0 | - | 0 | 0.28246 | 0.28246 | 0 | 0 | 0 |  |  | 0 | 0
xii | Procurement of Rotor shaft assembly for M/s. ELECON Engineering Company ltd make Impact Crusher in CHP 3x660MW Units at KTPS, Koradi. | 0 | - | 0 | 0.76369 | 0.76369 | 0 | 0 | 0 |  |  | 0 | 0
xiii | Procurement of Sam Turbo Make Pumps Spare parts for Ash Handling Plant of 3X660 MW Units at KTPS, Koradi | 0 | - | 0 | 0.17166 | 0.17166 | 0 | 0 | 0 |  |  | 0 | 0
xiv | Procurement of Wagon Tippler Spares for M/s. ELECON Engineering Company ltd. make Wagon Tippler in CHP 3X660MW Units at KTPS, Koradi. | 0 | - | 0 | 1.3975 | 1.3975 | 0 | 0 | 0 |  |  | 0 | 0
xv | Procurement of Pneumatic Y Type Control Valve (Blow Valve Size 50mm & 80mm) for Fly Ash Evacuation System of 3X660MW Unit KTPS, Koradi. | 0 | - | 0 | 0.029205 | 0.029205 | 0 | 0 | 0 |  |  | 0 | 0
xvi | Procurement of the various spares required for Warman make Ash Slurry Pump Model 10/8 EEM & Over Flow Pump Model 8/6 EXU installed at AHP, 3X660 MW TPS Koradi through Limited Tender. | 0 | - | 0 | 0.20886 | 0.20886 | 0 | 0 | 0 |  |  | 0 | 0
xvii | 0 | 0 | - | 0 | 0.0076261 | 0.032797 | -0.025171 | 0 | 0 |  |  | 0 | -0.025171
xviii | Procurement of Spares of Single Roll Clinker Grinder Ayems Engineers make, Model AE-1005-89-100 at AHP, 3X660 MW Koradi TPS. | 0 | - | 0 | 0.82826 | 0.82826 | 0 | 0 | 0 |  |  | 0 | 0
xix | Procurement of Hydraulic Motor for Bucket Wheel of Stacker Reclaimer in CHP, 3X660MW, KTPS, Koradi. | 0 | - | 0 | 1.1168 | 1.1168 | 0 | 0 | 0 |  |  | 0 | 0
xx | Procurement of Rotors, Maintenance Kits, Couplings and other spares required for Atlas Copco make Instrument Air Compressor of Ash Handling Plant of 3 X 660 MW Units at KTPS, Koradi. | 0 | - | 0 | 0.62625 | 0.62625 | 0 | 0 | 0 |  |  | 0 | 0
xxi | Procurement of spares of intermediate conveyor | 0 | - | 0 | 0 | 0.3186 | -0.3186 | 0 | 0 |  |  | 0 | -0.3186
xxii | Procurement of Hydraulic motor for wagon tippler drive in CHP, 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.46494 | 0.46494 | 0 | 0 | 0 |  |  | 0 | 0
xxiii | Procurement of GEHO Pump (Model No. TZPM 400) Spares of Ash Handling Plant, 3 X 660 MW Units, KTPS, Koradi. | 0 | - | 0 | 0 | 0.83656 | -0.83656 | 0 | 0 |  |  | 0 | -0.83656
xxiv | Procurement of Beater Arms for Impact crushers installed at in Coal Handling Plant of 3x660 MW at KTPS, Koradi. | 0 | - | 0 | 0 | 1.0093 | -1.0093 | 0 | 0 |  |  | 0 | -1.0093
xxv | Supply of Atlas Copco make compressor spares for at Koradi TPS 660MW | 0 | - | 0 | 0 | 0.39813 | -0.39813 | 0 | 0 |  |  | 0 | -0.39813
xxvi | Procurement of spares for side arm charger, wagon tippler, impact crushers and stacker reclaimer at CHP 3x660 MW KTPS | 0 | - | 0 | 0 | 0.42626 | -0.42626 | 0.010573 | 0.010573 |  |  | 0.010573 | -0.42626
xxvii | Procurement of Beater heads with Pin for Impact crushers installed at in Coal Handling Plant of 3x660 MW at KTPS, Koradi. | 0 | - | 0 | 0 | 1.1256 | -1.1256 | 0 | 0 |  |  | 0 | -1.1256
xxviii | Procurement of spares of Hyd Motor of SAC | 0 | - | 0 | 0 | 0.36029 | -0.36029 | 0 | 0 |  |  | 0 | -0.36029
xxix | Procurement of hydraulic power packs for Flap Gates in CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0.1888 | -0.1888 | 0 | 0 |  |  | 0 | -0.1888
xxx | Procurement of Mobile Grilling Equipment for CHP 3x660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0.33866 | -0.33866 | 0 | 0 |  |  | 0 | -0.33866
xxxi | Procurement of Weld overlay Flap Gate assembly in CHP 3x660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0.5841 | -0.5841 | 0 | 0 |  |  | 0 | -0.5841
E6 | Capital Spares | 0 | - | 89.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of critical insurance spares for Turbine & its critical auxiliaries for 3 x 660 MW, Koradi (4370001538 dtd. 18/06/2018 d.p. 21 Months) | 0 | - | 89.62 | 89.6234 | 88.736 | 0.88736 | 0 | 0 |  |  | 0 | 0.88736
E7 | Additional Capitalization | 0 | - | 57.88 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Contruction of various infrastructure such as roads etc and public amenities in the rehabilitated villages of koradi and khasara | 0 | - | 13.1 | 12.74 | 0 | 12.74 | 0 | 0 |  |  | 0 | 12.74
ii | Procurement of 7 nos of school buses | 0 | - | 2 | 1.3109 | 1.3109 | 0 | 0 | 0 |  |  | 0 | 0
iii | Development of green belt & fodder farm for fulfillment of environmental clearance of MoEF for Koradi 3x660MW | 0 | - | 3.16 | 3.16 | 0 | 3.16 | 0 | 0 |  |  | 0 | 3.16
iv | Provision of Ground Hopper & Short Conveyor Belt from Existing Stackyard 1 & 2 ti existing Main Stream i.e. BCN 4A/4B of CHP 3x660 MW, KTPS, Koradi | 0 | - | 4.36 | 4.3555 | 4.3555 | 0 | 0 | 0 |  |  | 0 | 0
v | Provision of Ground Hopper & Conveyor Belt for Conveying Unloaded Coal form Open Wagon Tippler in CHP of Koradi Unit 8, 9 & 10. | 0 | - | 4.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
vi | Provision of Additional Facility for Manual Unloading Track in CHP of Koradi Unit No. 8, 9 & 10 | 0 | - | 5.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
vii | Construction of drains | 0 | - | 4.31 | 0 | 0 | 0 | 2.7927 | 0 |  |  | 0 | 2.7927
viii | Supply erection commissioning of medium voltage variable frequency drive for conveyors BCN 6A,6B,7A,7B in CHP 3x660MW | 0 | - | 17 | 16.9859 | 16.9859 | 0 | 0 | 0 |  |  | 0 | 0
ix | Supply, Installation & commissioning of 3D level sensors for first two ESP field hoppers | 0 | - | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
F | Koradi TPS 3x660 MW Expansion Project – Construction of 2nd raising of existing Khasara Ash Bund from T.B.L. 308.50 M to T.B.L 312.00 M with construction of concrete dam (Broad crest weir structure), approach to drain wells and raising height of drain well No. 1, 2 & 3, construction of ash Compartment, cleaning of Khasara bund Nallah and construction of peripheral roads connecting to nearby villages for Khasara ash bund at TPS Koradi | 0 | - | 86.914 | 75.65 | 80.258 | -4.608 | 12.4 | 12.4 |  |  | 12.4 | -4.608
G | Discharge of UDL | 0 | - | 0 | 92.46 | 111.48 | -19.02 | 19.51 | 0 |  |  | 0 | 0.49
H | Asset Addition due to change in classification of inventory | 0 | - | 0 | 0 | 0 | 0 | 21.7503 | 0 |  |  | 0 | 21.7503
I | Medical Oxygen Gr&Cyl Ozonization Plant (Covid Related Work) | 0 | - | 0 | 0 | 0 | 0 | 11.4034 | 9.6702 |  |  | 9.6702 | 1.7332
0 | B) DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (i) Submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Flue Gas Desulphurization FGD is for Unit 8, 9, 10 of 3x660MW Koradi TPS | MERC/CAPEX/FY 2020-21/WFH/SBR/05 | 2020-05-31 | 940 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Flue Gas Desulphurization is for Unit 8, 9, 10 of 3x660MW Koradi TPS | MERC/CAPEX/FY 2020-21/WFH/SBR/05 | 2020-05-31 | 847.78 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/FY 2020-21/WFH/SBR/05 | 2020-05-31 | 92.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13 | Construction of new admin building at Vidyut Bhavan, Katol Road, Nagpur | MERC/Capex/2021-2022/MSPGCL/063 | 2022-02-18 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13.1 | Construction of new admin building at Vidyut Bhavan, Katol Road, Nagpur | 0 | 2022-02-18 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | 2022-02-18 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Improvement in Regenerative Air Pre-heater Performance at Unit # 9 of 3x660 MW, Koradi TPS | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 15.869 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Procurement of heating elements for RAPH installed in Unit 9 (660MW) at KTPS Koradi THROUGH LIMITED TENDER | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 15.33 | 0 | 0 | 0 | 11.8 | 11.8 |  |  | 11.8 | 0 | 11.8 | 0
18.2 | Replacement of heating elements for RAPH installed in Unit 9 (660MW) at KTPS Koradi | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 0.349 | 0 | 0 | 0 | 0.37 | 0.37 |  |  | 0.37 | 0 | 0.349 | 0.021
0 | IDC | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 0.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | CHP Improvement (7 Nos) Schemes & Procurement of Bulldozers, Wheel Loaders and Hydraulic Cranes at CHP 3X660MW, KTPS, Koradi | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 38.87 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Sch-1: Revamping of Apron Feeder in CHP at 3X660MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Sch-2: Procurement of Hydraulic motors and pumps in CHP at 3X660 MW, KTPS, Koradi | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.3 | Sch-3: Capacity enhancement of Hydraulic motor of Apron Feeder in CHP, 3X660 MW, KTPS, Koradi | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 2.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.4 | Sch-4: Modification, supply and replacement of Transfer chutes in CHP 3x660MW KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.39 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.5 | Sch-5: Design, supply, installation & commissioning of High performance IGUS energy chain system with chain flex cable for Tripper trolleys at CHP at 3x660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.37 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.6 | Sch-6: Procurement of B3-630 gear box for BCN 6 A/B in CHP at 3x660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 0.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.7 | Sch-7: Supply and installation of Belt tear detector system for conveyor belt in CHP 3x660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 1.18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.8 | Sch-8: Procurement of 5 Nos of Bulldozers BD 155 at CHP 3X660 MW Koradi Thermal Power station. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 12.83 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.9 | Sch-9:- Procurement of 02 nos. of Wheel loaders at CHP 3X660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 3.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Sch-10:- Procurement of 15 Ton & 20 Ton capacity hydraulic Cranes at CHP 3X660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 0.69 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 0.64 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Construction of bridge cum bandhara across Pond No. 3 and allied works at Pond No. 3 at Koradi TPS | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 33.116 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Construction of cement concrete bridge cum bandhara alongwith gated arrangement. | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 14.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.2 | Construction of earthen embankment connecting bridge cum bandhara on both side of embankment by excavating soil / typha / silt from Pond No.3 & tree plantation. | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 14.3252 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.3 | Providing structural steel pathway on the existing waste weir (west side of the Pond No.3) and roads connecting to bridge behind Pond No.3 and bridge cum bandhara. | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 2.4308 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 1.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement & replacement of Superheater Pass Economizer Coils (Modified Design) for Unit 8, 9 & 10 at 3x660MW KTPS, Koradi | Not Approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Procurement & replacement of Superheater Pass Economizer Coils (Modified Design) for Unit 8, 9 & 10 at 3x660MW KTPS, Koradi | Not Approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Not Approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Improvement in Boiler Performance at U-8,9 & 10 KTPS, Koradi | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 62.929 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Scheme-1: Procurement of Blade Sets for ID, FD & PA Fans at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 11.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.2 | Scheme-2: Procurement of RAPH Bottom Support Bearing Assembly at 3X660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 2.478 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.3 | Scheme-3: Procurement of RAPH Top Guide Bearing Assembly at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 0.684 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.4 | Scheme-4: Procurement of RAPH Gear Box at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 3.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.5 | Scheme-5: Procurement of RAPH Spares at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 1.13 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.6 | Scheme-6: Procurement of Coal Burner Assembly with windbox air nozzles for Unit 8 & 9 at 3x660MW. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 15.407 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.7 | Scheme-7: Procurement of Boiler Circulation Pump (BCP) with Impeller & Diffuser at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 11.12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.8 | Scheme-8: Procurement and Replacement of Heating Elements for RAPH Installed for Unit 8 at 3x660MW. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 15.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 1.37 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Design, Engineering, Supply, Installation, Testing, Commissioning including all civil works for Natural resource treatment and Laboratory equipment with mandatory spares at Koradi TPS, 3 X 660 MW | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 49.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.1 | Supply of Natural resource treatment and lab equipment for Water, Coal, Oil, Meteorology with supporting AI computing, all auxiliaries, and accessories. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 35.28 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.2 | Supply of Mandatory spares on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.3 | Supply of Tools and Tackles on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.4 | Complete Civil Work with 10 KLD ETP/ STP on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 3.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.5 | Services - Charges of Inland transport of plant and equipment on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.6 | Charges for Testing, Commissioning and PG Test of plant and equipment. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Improvement in Regenerative Air Preheater Performance & Complete Replacement of NDCT fills at Unit # 10, Koradi TPS | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 25.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.1 | Procurement of heating elements for RAPH installed in Unit 10 (660MW) at KTPS Koradi through OEM | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 12.23 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.2 | Complete Supply & Replacement of NDCT fills of U#10. | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 13 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 0.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 14 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 14.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 15 | HMI (Human Machine Interface) Upgradation of ‘SSPA-T3000’ DCS (Distribution Control System), Rockwell make PLC System installed at 3x660MW Unit No. 8, 9 & 10 at Koradi TPS and HMI (Human Machine Interface) Upgradation of MaxDNA DCS System at Unit 8-9, CSTPS, Chandrapur | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 55.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 15.1 | Supply: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 10.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 15.2 | Works: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | HMI (Human Machine Interface) Upgradation of ‘SPPA-T3000’ DCS (Distributed Control System) installed at 3x660MW Unit- 8, 9 & 10 at Koradi TPS to match with the external aspects and process improvement | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 24.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Upgradation of Rockwell Make PLC System installed at 3x660MW ,Koradi TPS to match with the external aspects and process improvement.(C&I) | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 20.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Work of provision of platform beside railway siding at backside of chord cabin for loading of fly ash in railway wagon for ash utilization at 3x660 MW TPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 1.2838 | 1.2838 |  |  | 1.2838 | 0
13 | Capital Exenditure schemes for in-principle clearance regarding "EPC contract for the wok of construction of quarters and development of KTPS colony at Koradi" under CAPEX scheme | MERC/CAPEX/MSPGCL/2024-12/0569 DTD.13.09.2024 | 2024-09-13 | 210.48 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of spares for L&T-MHI make Turbine for COH work of Turbine at KTPS, 3x660MW units Koradi | MERC/CAPEX/MSPGCL/2023-24/0639 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement of spares for L&T-MHI make Turbine for COH work of Turbine at KTPS, 3x660MW units Koradi | MERC/CAPEX/MSPGCL/2023-24/0639 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Procurement of HP Nozzle assembly for L&T-MHI Make Turbine installed at 3x660MW Units Koradi | MERC/CAPEX/MSPGCL/2023-24/0639 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | C) DPRs Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Control & instrumentation related Various Upgradation schemes viz.Emission Monitoring & Water Quality Analysers ,Vibration Monitoring Schemes,Water Flow Monitoring etc. at 3X660MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Upgradation of Emission Monitoring Analysers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Upgradation of Water Quality Analysers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Revamping & Supply Of Upgraded VM7B Version of Vibration Monitoring Rack | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.4 | Implementation of ‘Flow Monitoring System’ at 3x660MW Balance of Plant (BOP) Unit- 8, 9 & 10 at Koradi TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | CHP Improvement Scheme-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Supply, Erection, Commissioning of set of Internals for Wagon Tipplers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Supply, Erection, Commissioning of set of Internals for Side Arm Chargers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Supply, Erection, Commissioning of set of Internals for Wobbler Feeders at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.4 | Supply, Erection, Commissioning of set of Internals for Apron Feeders at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.5 | Supply, Erection, Commissioning of set of Internals for Impact Crushers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.6 | Supply, Erection, Commissioning of set of Internals for Stacker cum Reclaimers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Performance improvement and availability of various Auxiliaries of TG at 3x660MW KTPS Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Performance improvement and availability of various Auxiliaries for Oil Systems of Main Turbine. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.2 | Performance improvement and availability of various Auxiliaries of Generator System. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.3 | Performance improvement and availability of Feed Water System. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.4 | Performance improvement and availability of Vacuum System. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.5 | Performance improvement and availability of CEP System. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.6 | Procurement of Complete Pull out Assembly along with Impeller and wear ring of Cooling Water Pump. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.7 | Procurement of complete assembly of HP and LP Elements for Atlas Copco make Compressors. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Improvement in Wet ash evacuation system at 3x660MW Units, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Procurement & installation of Ash Slurry Series Pump Assembly with modified metallurgy and Critical Wet End Sub Assembly to enhance the performance & slurry disposal capacity. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.2 | Procurement & installation of Ash Slurry Series Pump Assembly with modified metallurgy along with Gear Box, Fluid Coupling & Motor (4’th Series) and Critical Wet End Sub Assembly to enhance the performance & slurry disposal capacity. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.3 | Procurement & installation of Overflow Transfer Pump Assembly with upgradation in metallurgy and Critical Wet End Sub Assembly to enhance the performance. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.4 | Procurement & installation of IAC Compressor Assembly: Model –ZR110 STD 7.5 IMD Atlas Copco Make Oil free water cooled screw air compressor with inbuilt atlas copco make heat of compression single drum rotator air dryer to enhance the performance. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | HMI Upgradation of Diasys Netmation DCS at 3x660MW KTPS Koradi Units 8,9 & 9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | HMI Upgradation of Diasys Netmation DCS at 3x660MW KTPS Koradi Units 8,9 & 10 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Improvement in Dry ash evacuation system at 3x660MW Units, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Procurement of Ingersoll Rand Make Transport Air Compressors Critical/Non-Critical Spares sub-assembly for performance improvement. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | MSERW Pipes for Garlanding arrangement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.1 | Work of Garlanding arrangement to changeover ash slurry feed points for even filling of pond by providing MSERW Pipes along the periphery of Ash Bund Dyke Wall at Khasara Ash Bund. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Capacity Enhancement & Performance optimization at WTP 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.1 | Capacity enhancement of DM water stream in WTP at 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.2 | Capacity enhancement Condensate polishing unit regeneration area in WTP at 3X660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.3 | Provision of Ozone generating plant of 1.0 Kg capacity in WTP at 3X660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | DPR for Construction of CC Road alongwith RCC Drain, CC platform for heavy machinery movement at 3x660 MW, TPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.1 | DPR for Construction of CC Road alongwith RCC Drain, CC platform for heavy machinery movement at 3x660 MW, TPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Improvement in Coal Mill Performance-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.1 | Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi through OEM. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.2 | Procurement of Mill Rotary Separator Blades for coal mill MVM 32R at 3x660 MW, KTPS, Koradi through open tender | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.3 | Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi through OEM. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.4 | Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi through OEM | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Improvement in Boiler performance-II at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.1 | Scheme1:Procurement of Coal compartment assembly for Unit8 at 3x660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.2 | Scheme2:Procurement of blade sets for ID, FD & PA Fan at 3x660 MW, Units at KTPS Koradi through OEM. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.3 | Scheme3:Procurement of RAPH internal Spares for 3X660MW units at KTPS Koradi through OEM (Qty- 6 Sets) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.4 | Scheme4:Procurement of RAPH Sector plate with Actuating mechanism assembly for Unit9 3 X 660MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | Improvement in Coal Mill performance-II at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | Procurement of FLENDER make Gearbox model kmp-450 along with motor for coal mill MVM32R at 3x660mw KTPS, koradi through OEM. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.2 | Procurement of complete set of couplings for PA, ID & FD fans at 3X660MW units at KTPS Koradi through OEM | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Improvement in Coal Mill performance-III at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit10 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.5 | Scheme5:Procurement of Complete MRHS System along with Pneumatic Compressors at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | Improvement in Boiler performance-III at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | Scheme1:Procurement of Coal compartment assembly for Unit8at 3x660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Scheme2:Procurement of blade sets for ID, FD & PA Fan at 3x660 MW, Units at KTPS Koradi through OEM. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Scheme3:Procurement and replacement of heating elements for RAPH installed in Unit 9 (660MW) at KTPS Koradi THROUGH OEM/OES (Qty- 2 Sets) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Scheme4:Procurement of HP valves, safety valves and ERV's for 3X660MW units at KTPS Koradi through OEM | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.5 | Scheme5:Procurement of RAPH Sector plate with Actuating mechanism assembly for Unit8 3 X 660MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | Improvement in Coal Mill performance-IV at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit8 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | Improvement in Coal Mill performance-V at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit9 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | Improvement in Boiler performance-IV at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.1 | Scheme1:Procurement of Coal compartment assembly for Unit8 at 3x660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.2 | Scheme2:Procurement of blade sets for ID, FD & PA Fan at 3x660 MW, Units at KTPS Koradi through OEM. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.3 | Scheme3:Procurement of RAPH bottom support bearing assembly for 3X660MW units at KTPS Koradi through OEM (Qty- 2 Sets) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.4 | Scheme4:Procurement of RAPH top guide bearing assembly for 3X660MW units at KTPS Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.5 | Scheme5:Procurement of RAPH Gear Box for 3X660MW units at KTPS Koradi through OEM (Qty- 1 Sets) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.6 | Scheme6:Procurement of RAPH Sector plate with Actuating mechanism assembly for Unit10 at 3 X 660MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.7 | Scheme7:Procurement and replacement of heating elements for RAPH installed in Unit 10 (660MW) at KTPS Koradi THROUGH OEM/OES (Qty- 2 Sets) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.8 | Scheme8:Procurement of Boiler Circulating Pump (1 Nos) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | Improvement in Coal Mill performance-VI at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit9 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.3 | Reliability Improvement schemes of generators at 3X660MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | Scheme No. 1 :PROCUREMENT OF MELCO/LMTG MAKE GENERATOR ROTOR ASSEMBLY with excitation transformer AT 3X660MW KTPS, KORADI THROUGH OEM | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.2 | Scheme No. 2:PROCUREMENT OF ONE COMPLETE SET OF GENERATOR STATOR COILS FOR GENERATOR AT 3X660MW UNITS AT KTPS KORADI THROUGH OEM | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | DPR on Procurement of Critical Speares for L&T make Main Turbine(typeTC4F-30) installed at 3x660MW KTPS Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.1 | Scheme No. 1 :Procurement of Critical Speares for L&T make Main Turbine(typeTC4F-30) installed at 3x660MW KTPS Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | DPR for Coal Handling Plant Performance Improvement Schemes -II at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.1 | Scheme No. 1 : Performance Improvement of Unloading System Wagon Tipplers at CHP 3x660MW KTPS Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.2 | Scheme No. 2 : Performance Improvement of Unloading System Side Arm Chargers at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Side Arm Charger Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.3 | Scheme No. 3 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.4 | Scheme No. 4 : Performance Improvement of Stacking & Reclaiming System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Stacking & Reclaiming System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.5 | Scheme No. 5 : Performance Improvement of Crushing System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Impact Crusher & Wobbler Feeders Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.6 | Scheme No. 6 : Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -1 at CHP 3x660MW KTPS Koradi A) Brief scope of work: Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -1 at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | DPR for Coal Handling Plant Performance Improvement Schemes -III at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.1 | Scheme No. 1 : Performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Hydraulic system for Wagon Tippler, Side Arm Charger , Apron Feeder ( 1 & 2) Stacker Reclaimer 1 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.2 | Scheme No. 2 : Construction of Air tight Hydraulic power pack room along with necessary cooling system for performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Construction of Air tight Hydraulic power pack room along with necessary cooling system for Wagon Tippler & Apron Feeder ( 1 to 4) Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.3 | Scheme No. 3 : Performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory Hydraulic Power Cylinders of Wagon Tippler, Side Arm Charger ( 1 to 4) Stacker Reclaimer 1 & 2 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.4 | Scheme No. 4 : Performance Improvement of Stacker Reclaimer by providing Hydraulic Drive to Boom Conveyor at CHP 3x660MW KTPS Koradi A) Brief scope of work: Hydraulic Drive to Boom Conveyor Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.5 | Scheme No. 5 : Performance Improvement of Illumination system with energy conservation at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Solar High masts along the rail track in railway yard Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.6 | Scheme No. 6 : Design, Supply & Installation of LT VFD Drives for Critical Conveyors at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of LT VFD Drives for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.7 | Scheme No. 7 : Design , supply, Erection & Commissioning of Short Conveyor for Stacking Purpose at CHP 3x660MW KTPS Koradi A) Brief scope of work: Short Conveyor for Stacking Purpose at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.8 | Scheme No. 8 : Capacity Enhancement of BCN-7/5/4/3 /1 AB in CHP 3x660MW KTPS Koradi A) Brief scope of work: Short Conveyor for Stacking Purpose at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.9 | Scheme No. 9 : Design , Engineering & modification along with strengthening of Existing Travel Track structure for Side Arm Charger & Stacker Reclaimer A) Brief scope of work: strengthening of Existing Travel Track structure for Side Arm Charger & Stacker Reclaimer Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.1 | Scheme No. 10 : Design , Engineering & Erection of modified Energy Efficient Ventilation System for Wagon Tippler Complex Area in CHP 3X660MW KTPS Koradi A) Brief scope of work: Energy Efficient Ventilation System for Wagon Tippler Complex Area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.11 | Scheme No. 11 : Design , Engineering & Installtion of Vibration & temprature Monitoring Systems for critical auxiliaries in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Installtion of Vibration & temprature Monitoring Systems for critical auxiliaries Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.12 | Scheme No. 12 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.13 | Scheme No. 13 : Design , Engineering & Provision of Stone Grappling Equipment System for Wagon Tippler 3 &4 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Stone Grappling Equipment System for Wagon Tippler 3 &4 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.14 | Scheme No. 14 : Design , Engineering & Provision of Public Addressing System for Wagon Tippler Complex in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Public Addressing System for Wagon Tippler Complex in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.15 | Scheme No. 15 : Design , Engineering & Provision of Belt Tracking System for Critical Conveyors in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Belt Tracking System for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.16 | Scheme No. 16 : Design , Engineering & Provision of Dust supression System for stacker reclaimer-1 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.17 | Scheme No. 17 : Work of Life Enhancement of wobbler Feeder 1 &2 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28 | DPR for Coal Handling Plant Performance Improvement Schemes -IV at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28.1 | Scheme No.1 : Design , Engineering , Supply & Installation of Modular Transfer chutes for Critical Conveyor System in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of Modular Transfer chutes for Conveyor System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28.2 | Scheme No.2 :Upgradtion of Exsisting Fire Fighting System at Stack yard area in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradtion of Exsisting Fire Fighting System at Stack yard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28.3 | Scheme No.3 : Design , Engineering , Supply & Strengthening of engineering structure of BCN- 7A/B along with track alignment in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Strengthening of engineering structure of BCN- 7A/B Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28.4 | Scheme No.4 : Design , Engineering , Supply & Installation of Mist Cannon Spray System around stackyard area in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of Mist Cannon Spray System at stackyard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28.5 | Scheme No.5 : Design , Engineering , Supply & Installation of EOT cranes at Bunker in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of EOT cranes at Bunker Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29 | DPR for Procurment of various Heavy Vehicles at CHP 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29.1 | Scheme No.1 : Procurment of Heavy Vehicles like dozers, wheel loaders , locomotives, Crane, Hydra , Disel Browser , Jcb & Bobcats etc. in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurment of Heavy Vehicles like dozers, wheel loaders , locomotives etc Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29.2 | Scheme No.2 : Procurment of Auger Machines for coal sampling in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurment of Auger Machines for coal sampling Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29.3 | Scheme No.3 : Procurment of Truck Mounted mist cannon dust supression system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurment of Truck Mounted mist cannon dust supression system in CHP Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30 | DPR for Coal Handling Plant Performance Improvement Schemes -V at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.1 | Scheme No. 1 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.2 | Scheme No. 2 : Performance Improvement of Stacking & Reclaiming / Side Arm Charger System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Energy Chain System of Stacking & Reclaiming System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.3 | Scheme No. 3 : Performance Improvement of unloading System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Energy Chain System of side arm acharger Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.4 | Scheme No. 4 : Upgradation to 100 MT Ton Weighbridge of existing road weighbridge at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of LT VFD Drives for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.5 | Scheme No. 5 : Design , Engineering & Erection of modified Energy Efficient Ventilation System for Crusher House Area in CHP 3X660MW KTPS Koradi A) Brief scope of work: Energy Efficient Ventilation System for Wagon Tippler Complex Area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.6 | Scheme No. 6 : Design , supply & Installation of Cooling Arrangement for Switchgear rooms at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Cooling Arrangement for Switchgear rooms Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.7 | Scheme No. 7 : Design , Engineering & Erection of modified Engineering Structure of Tunnel Conveyor 1A &1 B in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Erection of modified Engineering Structure of Tunnel Conveyor 1A &1 B Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31 | DPR for Coal Handling Plant Performance Improvement Schemes -VI at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.1 | Scheme No. 1 : Performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Wagon Tippler, Side Arm Charger , Apron Feeder ( 3 & 4) Stacker Reclaimer 2 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.2 | Scheme No. 2 : Design Supply & Installation of Wagon Locking system for all four wagon tipplers at CHP 3x660MW KTPS Koradi A) Brief scope of work: Wagon Locking system for all four wagon tipplers Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.3 | Scheme No. 3 : Design, Supply & Installation of upgraded Vibrating Feeders for Stacker Reclaimer at CHP 3x660MW KTPS Koradi A) Brief scope of work: Design, Supply & Installation of upgraded Vibrating Feeders for Stacker Reclaimer Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.4 | Scheme No. 4: Performance Improvement of Stacker Reclaimer by providing Hydraulic Drive to Boom Conveyor at CHP 3x660MW KTPS Koradi A) Brief scope of work: Hydraulic Drive to Boom Conveyor Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.5 | Scheme No. 5 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.6 | Scheme No. 6 : Design , Engineering & Provision of Belt Tracking System for Critical Conveyors in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Belt Tracking System for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.7 | Scheme No. 7 : Design , Engineering & Provision of Dust supression System for stacker reclaimer-1 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.8 | Scheme No. 8 : Work of Life Enhancement of wobbler Feeder 3 &4 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32 | DPR for Coal Handling Plant Performance Improvement Schemes -VII at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.1 | Scheme No.1 : Design , Engineering , Supply & Installation of Modular Transfer chutes for Crusher House Complex & other Critical Conveyor System in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of Modular Transfer chutes for Conveyor System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.2 | Scheme No.2 :Upgradtion of Exsisting Fire Fighting System along the conveyor length in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradtion of Exsisting Fire Fighting System at Stack yard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.3 | Scheme No.3 : Supply , Erection & Installation of Rack & Pinion Elevators at Bunker in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Supply , Erection & Installation of Rack & Pinion Elevators at Bunker in CHP 3X660MW KTPS Koradi. Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.4 | Scheme No.4 :Up Liftment f Exsisting Fire Fighting lines in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradtion of Exsisting Fire Fighting System at Stack yard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.5 | Scheme No.5 : Procurement of HPPE Polymer Roller for Conveyor system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurement of HPPE Polymer Roller for Conveyor system Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.6 | Scheme No.6 : Design , Engineering , Supply & Installation of EOT cranes at Wagon Tippler Complex in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of EOT cranes at Wagon Tippler Complex Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33 | DPR for Coal Handling Plant Performance Improvement Schemes -VIII at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.1 | Scheme No. 1 : Performance Improvement of Unloading System Wagon Tipplers at CHP 3x660MW KTPS Koradi Estimated Cost : 3.6 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.2 | Scheme No. 2 : Performance Improvement of Unloading System Side Arm Chargers at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Side Arm Charger Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.3 | Scheme No. 3 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.4 | Scheme No. 4 : Performance Improvement of Stacking & Reclaiming System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Stacking & Reclaiming System -2 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.5 | Scheme No. 5 : Performance Improvement of Crushing System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Impact Crusher & Wobbler Feeders Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.6 | Scheme No. 6 : Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -2 at CHP 3x660MW KTPS Koradi A) Brief scope of work: Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -2 at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.7 | Scheme No. 7 : Other Mislenious Schemes at CHP 3x660MW KTPS Koradi A) Brief scope of work: Other Mislenious works Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.8 | Scheme No. 4 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.9 | Scheme No.8: Procurement of HPPE Polymer Roller for Conveyor system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurement of HPPE Polymer Roller for Conveyor system Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34 | DPR for Coal Handling Plant Performance Improvement Schemes -IX at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.1 | Scheme No. 1 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.2 | Scheme No. 2 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.3 | Scheme No.3 : Upgradation of Exsisting Rack & Pinion Elevators at CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradation of Exsisting Rack & Pinion Elevators Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.4 | Scheme No.4 : Procurement of HPPE Polymer Roller for Conveyor system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurement of HPPE Polymer Roller for Conveyor system Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.5 | Scheme No.5 : Other miscellaneous scheme regarding sustainable performance improvement of CHP 3X660MW KTPS Koradi. A) Brief scope of work: ther miscellaneous scheme regarding sustainable performance improvement Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | Design & engineering, procurement, supply, installation & commissioning of Ozone Generator system of capacity 45.0 Kg/hr for CW system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Scheme1:Design & engineering, procurement, supply, installation & commissioning of Ozone Generator system of capacity 45.0 Kg/hr for CW system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36 | Pipeline expansion to improve dry ash evacuation system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.1 | Scheme1: Pipeline expansion to improve dry ash evacuation system along with target box modification and also to erect & commission dry ash evacuation directly to remote silo. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37 | Modification at intermediate silo and HCSD system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.1 | Scheme1: Additional charge pump. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.2 | Scheme 2: Supply & Installation Air washery at silo top. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.3 | Scheme 3: Shed above silo top. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.4 | Scheme 4: Supply & Installation Construction of platform at pipe rack up to Remote silo. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.5 | Scheme 5: Shifting of pipeline above pipe rack. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.6 | Scheme 6: Supply & Installation ART sub assemblies. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38 | ESP field strengthening at U#8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.1 | Scheme1: ESP field strengthening at U#8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
39 | Procurement of various pumps for AHP performance improvement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
39.1 | Scheme1: Procurement of various pumps for AHP performance improvement. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
40 | Modification in Dry Ash Evacuation System D/V Assemblies & allied equipments to improve performance | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
40.1 | Scheme1: Procurement of D/V Assemblies & allied equipments to improve performance. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41 | Additional IAC house for Intermediate silo and Remote silo along with erection of S.S. Pipeline | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.1 | Scheme1: Supply & Installation Additional IAC house for Intermediate silo and Remote silo along with erection of S.S. Pipeline | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42 | Waste water system modification to have zero water discharge | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.1 | Scheme1: Waste water system modification to have zero water discharge at 3x660MW, KTPS, Koradi along with Pump Procurement along with arrangement of sludge discharge at ESP water Washing system. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
43 | ESP field strengthening at U#9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
43.1 | Scheme1: ESP field strengthening at U#9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44 | Procurement of HCSD GEHO Pump (TZPM-400) critical items sub-assemblies | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.1 | Scheme1: Procurement of HCSD GEHO Pump TZPM-400) critical items sub-assemblies. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45 | MSERW Pipes & Seamless Pipes replacement to improve ash conveying & its disposal-1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.1 | Scheme1: Supply & Work of Replacement of MSERW Pipes & Seamless Pipes in Bottom ash/Coarse ash evacuation & Ash Slurry Disposal Pipelines, Dry ash conveying system in phase manner to improve the ash evacuation performance. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46 | Improvement in Ash Water Recovery System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.1 | Scheme1: Supply & Installation of Pumps along with Pipeline for Improvement in Ash Water Recovery System. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47 | Replacement of Instrument air pipeline from M.S. to S.S for AHP main plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.1 | Scheme1: Replacement of Instrument air pipeline from M.S. to S.S for AHP main plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48 | Modification of sludge pumps and its pipeline with pumps of higher capacity and discharge line of higher capacity. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.1 | Scheme1: Modification of sludge pumps and its pipeline with pumps of higher capacity and discharge line of higher capacity. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
49 | ESP field strengthening at U#10 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
49.1 | Scheme1: ESP field strengthening at U#10 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50 | MSERW Pipes & Seamless Pipes replacement to improve ash conveying & its disposal-2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50.1 | Scheme1: Supply & Work of Replacement of MSERW Pipes & Seamless Pipes in Bottom ash/Coarse ash evacuation & Ash Slurry Disposal Pipelines, Dry ash conveying system in phase manner to improve the ash evacuation performance. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
51 | Replacement of IAC for AHP Main Plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
51.1 | Scheme1: Supply & Installation of IAC for AHP Main Plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
52 | Improvement in DRY ASH Evacuation system-2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
52.1 | Scheme1: Supply & Installation of TAC, Replacement of Air Lock Vessel, Various Valves, ESP Hopper Doors, ESP access doors. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
53 | Improvement in DRY ASH Evacuation system-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
53.1 | Scheme1: Procurement of Ingersoll Rand Make Transport Air Compressors Critical/Non-Critical Spares sub-assembly for performance improvement. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
54 | Detailed project report for various works of security section as per the IB recommendations. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
54.1 | Repairing & raising height of compound wall with provision of concertina coil at various location of peripheral compound wall at 3x660MW KTPS Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
54.2 | Work of Providing structural three quarter turn staircase with landing along pheriphery of FISS watch tower at 3x660MW, TPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
55 | Supply, installation, comissioning and testing of 220V station & 360V UPS batteries installed at U 8, 9 & 0 of 3x660 MW KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
55.1 | Supply, installation, comissioning and testing of 220V station & 360V UPS batteries installed at U 8, 9 & 0 of 3x660 MW KTPS, Koradi. (scheme) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
56 | TDBFP Governing valve's LPCV ,HPCV MSV AND Trip lock replacement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
61 | Procurement & replacement of HP Heaters at 3x660 MW KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Vibration Monitoring & Analysis system installed at 3x660MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of sinkawa make vibration monitoring and Analysis system for main turbine at 3x660MW koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of Bently Nevada make vibration monitoring and Analysis system for RMCMS system at 3x660MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3 :-Emerson PLC upgradation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of various Level Transmitters installed at 3x660 MW koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of Guided wave Radar Level TX installed at Condenser Hotwell and LPH 1,2 and 3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of Displacer type level TX into Guided wave radar level Tx installed at various Drain Tank, Flash tank and pit | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3: Upgradation of non- contact type Ultrasonic level Tx into IP68 non- contact type Radar level TX. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of ESP Hopper level Probes installed at 3x660 MW koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of 1st three fields ESP Hopper level probes into continuous level monitoring NOGS system at 3x660 MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of RF capacitance Hopper level probe into of RF admittance level probe at 4,5,6,7,8 & 9 ESP Hoppers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3: Upgradation of ESP hopper heater monitoring , control and real time monitoring system at 3X660MW Koradi TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of various scheme viz ASLD, Furnace tv camera FEGT and acoustic Pyrometer installed at 3x660 MW koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of ASLD system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of Furnace TV Camera | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3:Upgradation of FEGT system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 4:Upgradation of acoustic pyrometer | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of various scheme viz instrument Air pipe at ESP Area, wet Ash Evacuation system, HCSD Silo. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of instrument Air pipeline system at ESP of M.S into SS installed at 3x660 MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of instrument Air pipeline system at wet Ash system of M.S into SS . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3: Upgradation of instrument Air pipeline system at HCSD silo of M.S. into SS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 4: Upgradation of instrument Air pipeline system at Remote Silo of M.S into SS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 5: Upgradation of Control & Instrument section lab with Hydraulic Servo Valve Test, Pneumatic System test and calibration lab set up. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Flame scanner for flexible operation of 3X660MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of Flame scanner for flexible operation of 3X660MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of DRC Pipes, Bends & Fittings in phase manner to improve the dry ash conveying & its disposal (2 years) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of DRC Pipes, Bends & Fittings in phase manner to improve the dry ash conveying & its disposal (2 years) (Rs.30 Cr.) (Bottom ash/Coarse ash evacuation & Ash Slurry Disposal Pipelines, Dry ash conveying system) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Augmentation of Coarse Ash disposal system at U10 at KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | WORK OF INSTALLATION & COMMISSIONING OF ASH DISPOSAL SYSTEM AT UNIT#10 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Railway Track Siding Performance Improvement Schemes at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 1 : Work of complete track renovation of existing Rail yard of CHP, 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. Due to continuous movement of Railway's precious rolling stock, the track spares are worn out and are due for complete replacement. Hence, to maintain rail track parameters in healthy condition as per Railway norms so as to avoid untoward incidences of derailment the execution of work of complete track renewal is essential. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 2 : Scheme Name- Work of laying of additional track at 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. However, as per the existing infrastructure, at present there is no dedicated empty formation line. Due to non-availability of empty formation line, most often unloading gets hampered due to blocking of outhaul line by empty rake. The hampering in unloading affects the plant performance and incurrs unnecessary financial burden on KTPS account under the head of demurrage charges. Hence, to maintain the plant loadability and availability, it is essential to lay additional track at 3x660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 3 : Scheme Name- Work of rectification and upgradtion of existing SSP at CHP, 3x660MW, KTPS, Koradi. Justification- The SSP has been erected at 3x660MW, KTPS, Koradi. However, till date the same has not been commissioned. With lapse of @ 5-6 years after erection and its non commissioning, the existing SSP set up has been completely detoriorated. Now, Railway's is pressing hard for early commissioning of the same. The said set up shall ensure isolation of OHE of existing yard with Railway's main line. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 4 : Scheme Name- Work of construction of apron RCC platforms at inhaul and outhaul of Wagon tipllers 1, 2, 3 & 4 of CHP 3x660MW, KTPS, Koradi. Justification- The 04 Nos. of wagon tipplers are installed at CHP-3x660MW, KTPS, Koradi. In this regards, it is to submit that, the wagon unloading is being carried out through these tipplers. Hence, presence of fugitive dust in tippler area is predominant. The said dust is being accumulated at inhaul and outhaul of wagon tipplers. Due to presence of loaded wagons at inhaul and empty wagons at outhaul, this office gets least opportunity for clearance of the said coal dust along the track. Due to accumulation of coal dust, the rail track parameters along with gradient are getting distubed. The disturbance in gradient is causing rolling of wagons which is not recommended in view of safety of both man and machine. Besides, this due to rolling of wagons, the occurnece of untoward incidence of derailment is predominant. Hence, to maintain uniform rail track gradient it shall be enviable to construct the apron RCC platforms at inhaul and outhaul of Wagon tipplers 1, 2, 3 & 4 of CHP-3x660MW, KTPS, Koradi. Estimated cost- Rs. 4 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 5 : Scheme Name- Work of construction of apron RCC platforms at inhaul and outhaul of Wagon tipllers 1, 2, 3 & 4 of CHP 3x660MW, KTPS, Koradi. Justification- The 04 Nos. of wagon tipplers are installed at CHP-3x660MW, KTPS, Koradi. In this regards, it is to submit that, the wagon unloading is being carried out through these tipplers. Hence, presence of fugitive dust in tippler area is predominant. The said dust is being accumulated at inhaul and outhaul of wagon tipplers. Due to presence of loaded wagons at inhaul and empty wagons at outhaul, this office gets least opportunity for clearance of the said coal dust along the track. Due to accumulation of coal dust, the rail track parameters along with gradient are getting distubed. The disturbance in gradient is causing rolling of wagons which is not recommended in view of safety of both man and machine. Besides, this due to rolling of wagons, the occurnece of untoward incidence of derailment is predominant. Hence, to maintain uniform rail track gradient it shall be enviable to construct the apron RCC platforms at inhaul and outhaul of Wagon tipplers 1, 2, 3 & 4 of CHP-3x660MW, KTPS, Koradi. Estimated cost- Rs. 4 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 6 : Scheme Name- Work of construction of RCC platforms along the rail track of CHP 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. In this regards, it is to submit that, after unloading of rakes the empty rakes are being examined by Railway's C&W staff camped at KTPS, Koradi. Hence, for safe movement of Railway's staff, Railway's is pressing hard for provision of RCC platforms along the rail track of CHP-3x660MW, KTPS, Koradi. Estimated cost- Rs. 10 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 7 : Scheme Name- Work of repairing and construction of RCC permanent revenue canal at, KTPS, Koradi. Justification- The temporary revenue canal is being flowing beside the existing Railway exchange yard of 210 MW, KTPS, Koradi. The said canal gets clogged inview of ash accumulation. Due to clogging this canal overflows and its overrun enters the 210 MW rail yard thereby creating track surface marshy and unsafe for Rail movement. Hence, it is essential to repair and construct RCC permanent revenue canal at KTPS, Koradi so that proper and timely cleaning of canal along with proper outlet can be arranged. Estimated cost- Rs. 15 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme Name-08 Work of construction of RCCretaining wall at Godhani and Kalumna end of KTPS, Koradi. Justification- The separate rail infrastructure has been commissioned for Koradi TPS to cope up the daily coal requirement. The rail traffic at KTPS, Koradi is being catered through Godhani and Kalumna end respectively. In this regards, it is to submit that, the take off points at Godhani and Kalumna both are S&T operated. During monsoon, it is often witnessed that, the rain water enters the plant premises from others land thereby submerging the S&T operated point. Due to this, signals gets lost and hampers the Rail traffic movement completely. Hence, it is essential to restrict the entrance of rain water in plant premises. This can be possible by constructing retaining wall at required loaction. Estimated cost- Rs. 1 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme Name-09 OHE maintenance at CHP, KTPS, Koradi Justification-As per the Railway board circular, Railway's has mandated that OHE maintenance cost for existing as well as new sidings shall be borne by the siding owner in accordance with Railway guidelines. Railway will carry out necessary inspection of maintenance work once in six months. Maintenance charges per TKM per annum of OHE as finalized by SECR zonal office is Rs.291566/- per TKM per annum. Also, inspection charges at the rate of Rs.106974/- per day towards inspection to be carried out by Railways every si x months shall be charged on actual basis by Railway's from the sidings.Accordingly, Railway.s has calimed amount of Rs.31314519/- for two years. Hence for 5 yeards it is expected to be Rs.7.82 Cr. Estimated cost- Rs. 7.82 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 10 Name-Remodelling and upgradation of existing S & T system with Panel Interlocking system and associated S & T gears to S & T system with Electronic Interlocking system and associated S & T gears in connection with services for BG Railway facility (660 MW Rail yard) for Koradi Thermal Power Station of MSPGCL Justification-As per the prevailing Railway norms, it is mandatory to commission the S & T system in private Railway siding for fast and safe movement of Railway’s precious rolling stock. Unless and until remodeling is carried out the S&T system cannot be started at Koradi Railway yard.With commissioning and operation of S & T system there shall be least possibility for derailments during internal shunting through crossovers, as the said points shall be motorized operated. Estimated cost- Rs. 20 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 11 : Work of supply and provision of lights and high mast at CHP Railway exchange yard of 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. In this regards, it is to submit that, after unloading of rakes the empty rakes are being examined by Railway's C&W staff camped at KTPS, Koradi on round the clock basis. Hence, for safe movement of Railway's staff, Railway's is pressing hard for availability of proper illumination in complete yard. Estimated cost- Rs.2.5 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Provision of cover shed for stack yard -2 at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 1 : Provision of cover shed for stack yard -2 at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Procurement of Pipe Conveyor Drive System Internals at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 1 : Procurement of Pipe Conveyor Drive System Internals at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Provision of service building along with vehicle bay at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 1 : Provision of service building along with vehicle bay at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | GENERAL ASSET | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | GENERAL ASSET--AKRDFOGA01-OFFICE FURNITURE | N.A. | - | 0 | 0.25116 | 0.43576 | -0.1846 | 0.088895 | 0.088895 |  |  | 0.088895 | -0.1846
2 | GENERAL ASSET--AKRDFOGA02-COMPUTERS,PRINTER,SCANNER | N.A. | - | 0 | 1.1668 | 1.2164 | -0.049645 | 0.045849 | 0.045849 |  |  | 0.045849 | -0.049645
3 | GENERAL ASSET--AKRDFOGA03-AC,WATER COOLER | N.A. | - | 0 | 0.22316 | 0.2563 | -0.033135 | 0.0345 | 0.0345 |  |  | 0.0345 | -0.033135
4 | GENERAL ASSET--AKRDFOGA04-AIR PURIFIER | N.A. | - | 0 | 0 | 0.0105 | -0.0105 | 0 | 0 |  |  | 0 | -0.0105
0 | D) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of KLEP Unit for 'HCSD Pump | 0 | - | 3.73 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Restoration of Boiler Circulation Pump at 3X660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of Coal Compartment Assemblies for Unit-10 at 3x660MW KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Repairing and Refurbishment of TDBFP cartridge Model FK6E40 installed at 3X660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Non-DPR for Upgradation of Honeywell Make PLC for Mill Reject Handling System installed at 3x660MW Balance of Plant (BOP) Unit- 8, 9 & 10 at Koradi TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of Sky Climber for furnace repairing at 3x660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Double Roll Clinker Grinder | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement along with Installation of Clear Water Booster Pump with Motor, Panel Cable and other allied accessories in Unit#10 bottom ash area at AHP, 3x660MW, KTPS, Koradi. | N.A. | - | 0 | 0.25116 | 0 | 0.25116 | 0 | 0 |  |  | 0 | 0.25116
9 | Procurement of single Roll Clinker Grinder with Feed Pump & Jet Pump Complete Assembly with modified metallurgy installed at AHP ,3x660MW Units, KTPs, Koradi | N.A. | - | 0 | 1.1668 | 0 | 1.1668 | 0 | 0 |  |  | 0 | 1.1668
10 | Work of Repairing and Refurbishment of HIP Rotor along with balancing and over speed trial for L&T-MHI make turbine (Type: TC4F-30”) installed at 3X660MW KTPS, Koradi | N.A. | - | 0 | 0.22316 | 0 | 0.22316 | 0 | 0 |  |  | 0 | 0.22316
11 | Procurement of spares for Flue gas distribution dampers, PA fan discharge dampers and Coal mill Hot PA Gate and Dampers at 3x660mw KTPS units through OEM | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Work of Modification & Installation of Take up trolley & arrangement for take up lifting for conveyor BCN-13A at CHP 3X660MW,KTPS,Koradi | N.A. | - | 0 | 355.8831 | 0 | 355.8831 | 0 | 0 |  |  | 0 | 355.8831
13 | Work of Design, Modification & streingthening of Tripper trolley structure with provision of Antiwear plates discharge chute box at CHP 3X660MW,KTPS,Koradi | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Upgradation of Management Information System (MIS) Server and Associated Software for C&I at 3x660MW Unit- 8, 9 & 10 at Koradi TPS | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | Procurement of Vibrating Tranfer chute with double exciter Drive for stacker reclaimer at CHP,3X660MW,KTPS ,Koradi | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | Supply & Installation of Ash Slurry Density Transmitter at High Concentrated Slurry Disposal (HCSD) System of BOP area of 3x660MW Unit- 8, 9 & 10 at Koradi TPS | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | Supply & Installation of Fiber Optic Sensing System for Conveyor Health Monitoring At CHP 3x660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | Procurement of Leak- proof make complete Mechanical Seal Assembly for Concrete Volute CW Pump installed at 3X660MW KTPS,Koradi on OEM bASIS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | Work of Design , Engineering , Manufacturing , Supply Erection & Commissioning of Conveyor Belt From Discharge of RBF 1 &2 at Crusher House to Stack Yard At CHP 3x660MW KTPS, Koradi . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20 | Supply & Installation of Artificial Intelligence PMMS Accurex Diagnostic matrix based vibration & temperature monitoring for critical auxiliaries at CHP 3x660MW KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Restoration of online dissolved gas analysers of Unit 8,9,10 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | Complete Replacement of Existing Water Separator Drain Tank Control (WDC) Valves with New Valves of modified trim design along with hydraulic Actuators, Power Pack assembly, necessary instrumentation, erection & commissioning 3X660MW KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Procurement of mandatory set of Hydraulic system internals for Wagon Tippler Drive & side arm charger Drive at CHP,3X660MW,KTPS ,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | "Supply & installation of Anodized winding Oil cooled over band magnetic separator & control panel for conveyor 5A,5B &13C at CHP 3x660MW KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | Procurement of Grinding Wall Assembly for Impact Crusher At CHP 3x660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | Restoration of Boiler Circulation Pump of U10 at 3X660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | Design,Engineering,Customization,Implementation,Installation & testing of Data Analytical/Artificial Intellegence softwae for automated monitoring & diagnostics system to improve Power plant reliability & efficiency,at one unit of 3X660MW KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28 | Supply of Feed Gate Complete Assembly along with installation to enhance the performance of Feed Gate at Ash Handling Plant, 3x660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29 | Design, Supply, Installation & Commissioning of Instrument Air Dryer Assembly with Prefilters & Stainless steel piping along with valves suitable for Instrument Air Compressors at AHP, 3x660MW Units, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 569.878 | 669.2496 | -99.3716 | 138.9621 | 93.6906 | 0 | 0 | 93.6906 | -54.1001
FY 2023-24
0 | A) Approved Add cap: | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
A | BoP | 0 | - | 246.34 | 90.7136 | 220.5874 | -129.8738 | 12.9668 | 12.1055 |  |  | 12.1055 | -129.0125
B | BTG | 0 | - | 44.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B1 | Supply | 0 | - | 13.33 | 0 | 13.33 | -13.33 | 0 | 0 |  |  | 0 | -13.33
B2 | Works | 0 | - | 0.98 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B3 | Taxes and duties | 0 | - | 23.29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B4 | Civil | 0 | - | 0.19 | 0.19 | 0 | 0.19 | 0 | 0 |  |  | 0 | 0.19
B5 | Mandatory Spares | 0 | - | 5.03 | 1.29 | 6.32 | -5.03 | 0 | 0 |  |  | 0 | -5.03
B6 | BTG (L&T) Work | 0 | - | 1.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C | Other Works (Plant) | 0 | - | 136.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C1 | Fully Integrated Security System | 0 | - | 27.36 | 31.4615 | 31.4615 | 0 | 0 | 0 |  |  | 0 | 0
C2 | Administrative Expenses and overhead | 0 | - | 7.25 | 0.69 | 0 | 0.69 | 6 | 0 |  |  | 0 | 6.69
C3 | Contingencies E&M | 0 | - | 0.04 | 0.04 | 0 | 0.04 | 0 | 0 |  |  | 0 | 0.04
C4 | Mobile storage racks, fork lifts, hoists & hydra for material handling in major stores shed | 0 | - | 0.95 | 0.93645 | 0.93645 | 0 | 0 | 0 |  |  | 0 | 0
C5 | Development of working models of Plant Layout, Boiler, Turbine- Generetaor, Coal mill, Fans, etc. at KTC, Koradi. | 0 | - | 1.2 | 1.2 | 0.98604 | 0.21396 | 0 | 0 |  |  | 0 | 0.21396
C6 | Workshop equipment | 0 | - | 0.26 | 0.26192 | 0.26192 | 0 | 0 | 0 |  |  | 0 | 0
C7 | Design, engg, manufacture, supply , erection, testing & commissioning of Ozonization Plant for circulating cooling water system | 0 | - | 54.05 | 31.7683 | 31.6144 | 0.15388 | 0 | 0 |  |  | 0 | 0.15388
C8 | Supply, installation & commissioning of water flow meters including required SCADA software and other accessories for water management system | 0 | - | 5.08 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C9 | Provision of wet ash evacuation system for first two rows of ESP for Unit-8,9 & 19 | 0 | - | 26.59 | 21.69 | 26.3181 | -4.6281 | 0 | 0 |  |  | 0 | -4.6281
C10 | Procurement of portable mercury analyser for flue gas monitoring | 0 | - | 6.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C11 | Administrative Expenses and overhead | 0 | - | 5 | 15.6868 | 0 | 15.6868 | 5.3133 | 0 |  |  | 0 | 21.0001
C12 | Compressor of Hydrogen plant | 0 | - | 1.5 | 1.5 | 0 | 1.5 | 0 | 0 |  |  | 0 | 1.5
C13 | Rail Cum road stone grabbler | 0 | - | 0.85 | 0.85 | 0 | 0.85 | 0 | 0 |  |  | 0 | 0.85
D | Other Works (Civil) | 0 | - | 103.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D1 | Road, Bridges railway system | 0 | - | 20.1 | 0.10806 | 0 | 0.10806 | 0 | 0 |  |  | 0 | 0.10806
0 | S&T System with Panel Interlocking System | 0 | - | 0 | 10.4047 | 10.4058 | -0.0011606 | 0.053794 | 0.053794 |  |  | 0.053794 | -0.0011606
D2 | Staff quarters | 0 | - | 5.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D3 | Other Misc & Unforseen Item | 0 | - | 25.79 | 9.3 | 7.53 | 1.77 | 0 | 0 |  |  | 0 | 1.77
0 | Check Post, Inspection Office & Facility Complex | 0 | - | 0 | 3.6844 | 3.6816 | 0.0028689 | 0 | 0 |  |  | 0 | 0.0028689
0 | CPRI Building | 0 | - | 0 | 6.2046 | 6.2046 | 0 | 0 | 0 |  |  | 0 | 0
0 | Foam cum DCP fire tender- 1 | 0 | - | 0 | 0 | 0.76926 | -0.76926 | 0 | 0 |  |  | 0 | -0.76926
0 | Fire water Bowser-cum-fire Tender- 1No. | 0 | - | 0 | 0.73537 | 0.73537 | 0 | 0 | 0 |  |  | 0 | 0
D4 | Const. facility | 0 | - | 3.28 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D5 | Contigency Other Civil Work | 0 | - | 5.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D6 | Adminstrative Exp. & Overhead (Salary & Overhead, Civil & E&M) | 0 | - | 21.47 | 31.64 | 0 | 31.64 | 0 | 0 |  |  | 0 | 31.64
D7 | Future unforseen works(Jalyukta Shiwar) | 0 | - | 0.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D8 | Landscaping work | 0 | - | 21.76 | 20.53 | 0 | 20.53 | 0 | 0 |  |  | 0 | 20.53
E | Initial Spares | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
E1 | Boiler & its auxilliaries | 0 | - | 14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Procurement of Table liners and Roller liners Of MVM 32R Coal Mills of 3 X 660MW Units at KTPS, Koradi | 0 | - | 0 | 10.0686 | 10.0686 | 0 | 0 | 0 |  |  | 0 | 0
ii | Procurement of couplings for Coal mill MVM 32 R of 3 X 660 MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 1.5944 | -1.5944 | 0 | 0 |  |  | 0 | -1.5944
iii | Procurement of Set of internal spares for Coal Mill Gear Box (KMP-450) for 3 X 660MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 2.2253 | -2.2253 | 0 | 0 |  |  | 0 | -2.2253
E2 | Turbine & its auxilliaries | 0 | - | 18.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | ULTRAFILTRATION MEMBRANE | 0 | - | 0 | 1.6511 | 1.6511 | 0 | 0 | 0 |  |  | 0 | 0
ii | Supply of Main turbine Vibration Monitoring System spares at 3x660MW, KTPS,Koradi. | 0 | - | 0 | 0 | 1.1469 | -1.1469 | 0 | 0 |  |  | 0 | -1.1469
iii | Procurement of Cartridge for Turbine Driven Boiler Feed Pump (Model No.: FK6E40) at 3X660 MW KTPS Koradi | 0 | - | 0 | 14.2864 | 14.2864 | 0 | 0 | 0 |  |  | 0 | 0
iv | Procurement of Critical Insurance Spares for L&T-MHI Make Turbine for attending major overhauling work of Turbine at KTPS, 3x660MW Units Koradi. | 0 | - | 0 | 11.1013 | 11.1013 | 0 | 0 | 0 |  |  | 0 | 0
E3 | Generator & its auxilliaries | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
E4 | Electrical auxilliaries | 0 | - | 1.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Procurement of HT Motors of BOP | 0 | - | 0 | 0 | 0.29335 | -0.29335 | 0 | 0 |  |  | 0 | -0.29335
ii | 0 | 0 | - | 0 | 0 | 0.84594 | -0.84594 | 0 | 0 |  |  | 0 | -0.84594
iii | Supply of Schneider make Differential Protection Relays for 3X660 MW, Koradi (OEM) | 0 | - | 0 | 0 | 0.10502 | -0.10502 | 0 | 0 |  |  | 0 | -0.10502
iv | Supply of Professional Large Format Display for display of DCS parameters PCR | 0 | - | 0 | 0.14885 | 0.14885 | 0 | 0 | 0 |  |  | 0 | 0
v | Procurement of ABT Energy meter with software for 3X660 MW, TPS, Koradi | 0 | - | 0 | 0 | 0.18337 | -0.18337 | 0 | 0 |  |  | 0 | -0.18337
E5 | Outdoor Plant i.e. CHP, AHP, WTP etc | 0 | - | 19.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Procurement of Forced Lubrication system for Premium make Gear box B3-450 installed for bunker conveyor BCN 7A/B at CHP 3X660MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0.15314 | -0.15314 | 0 | 0 |  |  | 0 | -0.15314
ii | Procurement of rotary spares for travel drive of Stacker and conveyor drive system in Coal Handling Plant of 3x660 MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0.35199 | -0.35199 | 0 | 0 |  |  | 0 | -0.35199
iii | Procurement of Complete assembly of Dome Valve ( 100NB, 200NB, 300NB) with power cylinder for dry Ash evacuation system of 3X660MW KTPS, Koradi. | 0 | - | 0 | 0.2225 | 0.2225 | 0 | 0 | 0 |  |  | 0 | 0
iv | Procurement of Modified Apron Pans for M/s. ELECON Engineering Company ltd make Apron Feeder in CHP 3x660MW Units at KTPS, Koradi. | 0 | - | 0 | 3.3233 | 3.3233 | 0 | 0 | 0 |  |  | 0 | 0
v | Procurement of Single Roll Clinker Grinder with Feed Sump and Jet Pump Complete Assembly with Drive, Driven Sprocket and Chain at AHP, 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.56357 | 0.56357 | 0 | 0 | 0 |  |  | 0 | 0
vi | Procurement of spares of Dome Valve (100NB, 200NB, 300NB) for Ash Evacuation System of 3X660MW Unit KTPS, Koradi. | 0 | - | 0 | 0.16431 | 0.16431 | 0 | 0 | 0 |  |  | 0 | 0
vii | 0 | 0 | - | 0 | 0.10064 | 0.10064 | 0 | 0 | 0 |  |  | 0 | 0
viii | 0 | 0 | - | 0 | 0.00708 | 0.00708 | 0 | 0 | 0 |  |  | 0 | 0
ix | Procurement of Hydraulic Motor for Apron feeder in Coal Handling Plant 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.7965 | 0.7965 | 0 | 0 | 0 |  |  | 0 | 0
x | Procurement of Peristaltic Hose Pump (Model no: RP2 – 40) Spares for HCSD System of Ash Handling Plant, 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.20622 | 0.20622 | 0 | 0 | 0 |  |  | 0 | 0
xi | Procurement of spares for HP Water Pump, Mather & Platt make, model 10/12 EME for AHP at 3X660 MW, KTPS, Koradi | 0 | - | 0 | 0.28246 | 0.28246 | 0 | 0 | 0 |  |  | 0 | 0
xii | Procurement of Rotor shaft assembly for M/s. ELECON Engineering Company ltd make Impact Crusher in CHP 3x660MW Units at KTPS, Koradi. | 0 | - | 0 | 0.76369 | 0.76369 | 0 | 0 | 0 |  |  | 0 | 0
xiii | Procurement of Sam Turbo Make Pumps Spare parts for Ash Handling Plant of 3X660 MW Units at KTPS, Koradi | 0 | - | 0 | 0.17166 | 0.17166 | 0 | 0 | 0 |  |  | 0 | 0
xiv | Procurement of Wagon Tippler Spares for M/s. ELECON Engineering Company ltd. make Wagon Tippler in CHP 3X660MW Units at KTPS, Koradi. | 0 | - | 0 | 1.3975 | 1.3975 | 0 | 0 | 0 |  |  | 0 | 0
xv | Procurement of Pneumatic Y Type Control Valve (Blow Valve Size 50mm & 80mm) for Fly Ash Evacuation System of 3X660MW Unit KTPS, Koradi. | 0 | - | 0 | 0.029205 | 0.029205 | 0 | 0 | 0 |  |  | 0 | 0
xvi | Procurement of the various spares required for Warman make Ash Slurry Pump Model 10/8 EEM & Over Flow Pump Model 8/6 EXU installed at AHP, 3X660 MW TPS Koradi through Limited Tender. | 0 | - | 0 | 0.20886 | 0.20886 | 0 | 0 | 0 |  |  | 0 | 0
xvii | 0 | 0 | - | 0 | 0.0076261 | 0.032797 | -0.025171 | 0 | 0 |  |  | 0 | -0.025171
xviii | Procurement of Spares of Single Roll Clinker Grinder Ayems Engineers make, Model AE-1005-89-100 at AHP, 3X660 MW Koradi TPS. | 0 | - | 0 | 0.82826 | 0.82826 | 0 | 0 | 0 |  |  | 0 | 0
xix | Procurement of Hydraulic Motor for Bucket Wheel of Stacker Reclaimer in CHP, 3X660MW, KTPS, Koradi. | 0 | - | 0 | 1.1168 | 1.1168 | 0 | 0 | 0 |  |  | 0 | 0
xx | Procurement of Rotors, Maintenance Kits, Couplings and other spares required for Atlas Copco make Instrument Air Compressor of Ash Handling Plant of 3 X 660 MW Units at KTPS, Koradi. | 0 | - | 0 | 0.62625 | 0.62625 | 0 | 0.55655 | 0.55655 |  |  | 0.55655 | 0
xxi | Procurement of spares of intermediate conveyor | 0 | - | 0 | 0 | 0.3186 | -0.3186 | 0 | 0 |  |  | 0 | -0.3186
xxii | Procurement of Hydraulic motor for wagon tippler drive in CHP, 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.46494 | 0.46494 | 0 | 0 | 0 |  |  | 0 | 0
xxiii | Procurement of GEHO Pump (Model No. TZPM 400) Spares of Ash Handling Plant, 3 X 660 MW Units, KTPS, Koradi. | 0 | - | 0 | 0 | 0.83656 | -0.83656 | 0 | 0 |  |  | 0 | -0.83656
xxiv | Procurement of Beater Arms for Impact crushers installed at in Coal Handling Plant of 3x660 MW at KTPS, Koradi. | 0 | - | 0 | 0 | 1.0093 | -1.0093 | 0 | 0 |  |  | 0 | -1.0093
xxv | Supply of Atlas Copco make compressor spares for at Koradi TPS 660MW | 0 | - | 0 | 0 | 0.39813 | -0.39813 | 0 | 0 |  |  | 0 | -0.39813
xxvi | Procurement of spares for side arm charger, wagon tippler, impact crushers and stacker reclaimer at CHP 3x660 MW KTPS | 0 | - | 0 | 0.010573 | 0.43684 | -0.42626 | 0 | 0 |  |  | 0 | -0.42626
xxvii | Procurement of Beater heads with Pin for Impact crushers installed at in Coal Handling Plant of 3x660 MW at KTPS, Koradi. | 0 | - | 0 | 0 | 1.1256 | -1.1256 | 0 | 0 |  |  | 0 | -1.1256
xxviii | Procurement of spares of Hyd Motor of SAC | 0 | - | 0 | 0 | 0.36029 | -0.36029 | 0 | 0 |  |  | 0 | -0.36029
xxix | Procurement of hydraulic power packs for Flap Gates in CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0.1888 | -0.1888 | 0 | 0 |  |  | 0 | -0.1888
xxx | Procurement of Mobile Grilling Equipment for CHP 3x660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0.33866 | -0.33866 | 0 | 0 |  |  | 0 | -0.33866
xxxi | Procurement of Weld overlay Flap Gate assembly in CHP 3x660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0.5841 | -0.5841 | 0 | 0 |  |  | 0 | -0.5841
E6 | Capital Spares | 0 | - | 89.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of critical insurance spares for Turbine & its critical auxiliaries for 3 x 660 MW, Koradi (4370001538 dtd. 18/06/2018 d.p. 21 Months) | 0 | - | 89.62 | 89.6234 | 88.736 | 0.88736 | 0 | 0 |  |  | 0 | 0.88736
E7 | Additional Capitalization | 0 | - | 57.88 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Contruction of various infrastructure such as roads etc and public amenities in the rehabilitated villages of koradi and khasara | 0 | - | 13.1 | 12.74 | 0 | 12.74 | 0 | 0 |  |  | 0 | 12.74
ii | Procurement of 7 nos of school buses | 0 | - | 2 | 1.3109 | 1.3109 | 0 | 0 | 0 |  |  | 0 | 0
iii | Development of green belt & fodder farm for fulfillment of environmental clearance of MoEF for Koradi 3x660MW | 0 | - | 3.16 | 3.16 | 0 | 3.16 | 0 | 0 |  |  | 0 | 3.16
iv | Provision of Ground Hopper & Short Conveyor Belt from Existing Stackyard 1 & 2 ti existing Main Stream i.e. BCN 4A/4B of CHP 3x660 MW, KTPS, Koradi | 0 | - | 4.36 | 4.3555 | 4.3555 | 0 | 0 | 0 |  |  | 0 | 0
v | Provision of Ground Hopper & Conveyor Belt for Conveying Unloaded Coal form Open Wagon Tippler in CHP of Koradi Unit 8, 9 & 10. | 0 | - | 4.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
vi | Provision of Additional Facility for Manual Unloading Track in CHP of Koradi Unit No. 8, 9 & 10 | 0 | - | 5.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
vii | Construction of drains | 0 | - | 4.31 | 2.7927 | 0 | 2.7927 | 0 | 0 |  |  | 0 | 2.7927
viii | Supply erection commissioning of medium voltage variable frequency drive for conveyors BCN 6A,6B,7A,7B in CHP 3x660MW | 0 | - | 17 | 16.9859 | 16.9859 | 0 | 0 | 0 |  |  | 0 | 0
ix | Supply, Installation & commissioning of 3D level sensors for first two ESP field hoppers | 0 | - | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
F | Koradi TPS 3x660 MW Expansion Project – Construction of 2nd raising of existing Khasara Ash Bund from T.B.L. 308.50 M to T.B.L 312.00 M with construction of concrete dam (Broad crest weir structure), approach to drain wells and raising height of drain well No. 1, 2 & 3, construction of ash Compartment, cleaning of Khasara bund Nallah and construction of peripheral roads connecting to nearby villages for Khasara ash bund at TPS Koradi | 0 | - | 86.914 | 88.05 | 92.658 | -4.608 | 0.63298 | 0.63298 |  |  | 0.63298 | -4.608
G | Discharge of UDL | 0 | - | 0 | 111.97 | 111.48 | 0.49 | 0 | 0 |  |  | 0 | 0.49
H | Asset Addition due to change in classification of inventory | 0 | - | 0 | 21.7503 | 0 | 21.7503 | 0 | 0 |  |  | 0 | 21.7503
I | Medical Oxygen Gr&Cyl Ozonization Plant (Covid Related Work) | 0 | - | 0 | 11.4034 | 9.6702 | 1.7332 | 0 | 0 |  |  | 0 | 1.7332
0 | B) DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (i) Submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Flue Gas Desulphurization FGD is for Unit 8, 9, 10 of 3x660MW Koradi TPS | MERC/CAPEX/FY 2020-21/WFH/SBR/05 | 2020-05-31 | 940 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Flue Gas Desulphurization is for Unit 8, 9, 10 of 3x660MW Koradi TPS | MERC/CAPEX/FY 2020-21/WFH/SBR/05 | 2020-05-31 | 847.78 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/FY 2020-21/WFH/SBR/05 | 2020-05-31 | 92.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13 | Construction of new admin building at Vidyut Bhavan, Katol Road, Nagpur | MERC/Capex/2021-2022/MSPGCL/063 | 2022-02-18 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13.1 | Construction of new admin building at Vidyut Bhavan, Katol Road, Nagpur | 0 | 2022-02-18 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | 2022-02-18 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Improvement in Regenerative Air Pre-heater Performance at Unit # 9 of 3x660 MW, Koradi TPS | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 15.869 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Procurement of heating elements for RAPH installed in Unit 9 (660MW) at KTPS Koradi THROUGH LIMITED TENDER | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 15.33 | 11.8 | 11.8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.2 | Replacement of heating elements for RAPH installed in Unit 9 (660MW) at KTPS Koradi | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 0.349 | 0.37 | 0.37 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 0.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | CHP Improvement (7 Nos) Schemes & Procurement of Bulldozers, Wheel Loaders and Hydraulic Cranes at CHP 3X660MW, KTPS, Koradi | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 38.87 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Sch-1: Revamping of Apron Feeder in CHP at 3X660MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Sch-2: Procurement of Hydraulic motors and pumps in CHP at 3X660 MW, KTPS, Koradi | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.3 | Sch-3: Capacity enhancement of Hydraulic motor of Apron Feeder in CHP, 3X660 MW, KTPS, Koradi | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 2.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.4 | Sch-4: Modification, supply and replacement of Transfer chutes in CHP 3x660MW KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.39 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.5 | Sch-5: Design, supply, installation & commissioning of High performance IGUS energy chain system with chain flex cable for Tripper trolleys at CHP at 3x660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.37 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.6 | Sch-6: Procurement of B3-630 gear box for BCN 6 A/B in CHP at 3x660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 0.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.7 | Sch-7: Supply and installation of Belt tear detector system for conveyor belt in CHP 3x660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 1.18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.8 | Sch-8: Procurement of 5 Nos of Bulldozers BD 155 at CHP 3X660 MW Koradi Thermal Power station. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 12.83 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.9 | Sch-9:- Procurement of 02 nos. of Wheel loaders at CHP 3X660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 3.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Sch-10:- Procurement of 15 Ton & 20 Ton capacity hydraulic Cranes at CHP 3X660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 0.69 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 0.64 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Construction of bridge cum bandhara across Pond No. 3 and allied works at Pond No. 3 at Koradi TPS | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 33.116 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Construction of cement concrete bridge cum bandhara alongwith gated arrangement. | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 14.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.2 | Construction of earthen embankment connecting bridge cum bandhara on both side of embankment by excavating soil / typha / silt from Pond No.3 & tree plantation. | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 14.3252 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.3 | Providing structural steel pathway on the existing waste weir (west side of the Pond No.3) and roads connecting to bridge behind Pond No.3 and bridge cum bandhara. | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 2.4308 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 1.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement & replacement of Superheater Pass Economizer Coils (Modified Design) for Unit 8, 9 & 10 at 3x660MW KTPS, Koradi | Not Approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Procurement & replacement of Superheater Pass Economizer Coils (Modified Design) for Unit 8, 9 & 10 at 3x660MW KTPS, Koradi | Not Approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Not Approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Improvement in Boiler Performance at U-8,9 & 10 KTPS, Koradi | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 62.929 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Scheme-1: Procurement of Blade Sets for ID, FD & PA Fans at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 11.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.2 | Scheme-2: Procurement of RAPH Bottom Support Bearing Assembly at 3X660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 2.478 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.3 | Scheme-3: Procurement of RAPH Top Guide Bearing Assembly at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 0.684 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.4 | Scheme-4: Procurement of RAPH Gear Box at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 3.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.5 | Scheme-5: Procurement of RAPH Spares at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 1.13 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.6 | Scheme-6: Procurement of Coal Burner Assembly with windbox air nozzles for Unit 8 & 9 at 3x660MW. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 15.407 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.7 | Scheme-7: Procurement of Boiler Circulation Pump (BCP) with Impeller & Diffuser at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 11.12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.8 | Scheme-8: Procurement and Replacement of Heating Elements for RAPH Installed for Unit 8 at 3x660MW. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 15.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 1.37 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Design, Engineering, Supply, Installation, Testing, Commissioning including all civil works for Natural resource treatment and Laboratory equipment with mandatory spares at Koradi TPS, 3 X 660 MW | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 49.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.1 | Supply of Natural resource treatment and lab equipment for Water, Coal, Oil, Meteorology with supporting AI computing, all auxiliaries, and accessories. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 35.28 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.2 | Supply of Mandatory spares on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.3 | Supply of Tools and Tackles on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.4 | Complete Civil Work with 10 KLD ETP/ STP on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 3.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.5 | Services - Charges of Inland transport of plant and equipment on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.6 | Charges for Testing, Commissioning and PG Test of plant and equipment. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Improvement in Regenerative Air Preheater Performance & Complete Replacement of NDCT fills at Unit # 10, Koradi TPS | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 25.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.1 | Procurement of heating elements for RAPH installed in Unit 10 (660MW) at KTPS Koradi through OEM | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 12.23 | 0 | 0 | 0 | 14.521 | 14.521 |  |  | 14.521 | 0
24.2 | Complete Supply & Replacement of NDCT fills of U#10. | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 13 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 0.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 14 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 14.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 15 | HMI (Human Machine Interface) Upgradation of ‘SSPA-T3000’ DCS (Distribution Control System), Rockwell make PLC System installed at 3x660MW Unit No. 8, 9 & 10 at Koradi TPS and HMI (Human Machine Interface) Upgradation of MaxDNA DCS System at Unit 8-9, CSTPS, Chandrapur | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 55.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 15.1 | Supply: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 10.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 15.2 | Works: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | HMI (Human Machine Interface) Upgradation of ‘SPPA-T3000’ DCS (Distributed Control System) installed at 3x660MW Unit- 8, 9 & 10 at Koradi TPS to match with the external aspects and process improvement | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 24.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Upgradation of Rockwell Make PLC System installed at 3x660MW ,Koradi TPS to match with the external aspects and process improvement.(C&I) | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 20.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Work of provision of platform beside railway siding at backside of chord cabin for loading of fly ash in railway wagon for ash utilization at 3x660 MW TPS, Koradi | 0 | - | 0 | 1.2838 | 1.2838 | 0 | -1.28 | -1.28 |  |  | -1.28 | 0
13 | Capital Exenditure schemes for in-principle clearance regarding "EPC contract for the wok of construction of quarters and development of KTPS colony at Koradi" under CAPEX scheme | MERC/CAPEX/MSPGCL/2024-12/0569 DTD.13.09.2024 | 2024-09-13 | 210.48 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of spares for L&T-MHI make Turbine for COH work of Turbine at KTPS, 3x660MW units Koradi | MERC/CAPEX/MSPGCL/2023-24/0639 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement of spares for L&T-MHI make Turbine for COH work of Turbine at KTPS, 3x660MW units Koradi | MERC/CAPEX/MSPGCL/2023-24/0639 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Procurement of HP Nozzle assembly for L&T-MHI Make Turbine installed at 3x660MW Units Koradi | MERC/CAPEX/MSPGCL/2023-24/0639 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | C) DPRs Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Control & instrumentation related Various Upgradation schemes viz.Emission Monitoring & Water Quality Analysers ,Vibration Monitoring Schemes,Water Flow Monitoring etc. at 3X660MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Upgradation of Emission Monitoring Analysers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Upgradation of Water Quality Analysers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Revamping & Supply Of Upgraded VM7B Version of Vibration Monitoring Rack | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.4 | Implementation of ‘Flow Monitoring System’ at 3x660MW Balance of Plant (BOP) Unit- 8, 9 & 10 at Koradi TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | CHP Improvement Scheme-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Supply, Erection, Commissioning of set of Internals for Wagon Tipplers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Supply, Erection, Commissioning of set of Internals for Side Arm Chargers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Supply, Erection, Commissioning of set of Internals for Wobbler Feeders at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.4 | Supply, Erection, Commissioning of set of Internals for Apron Feeders at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.5 | Supply, Erection, Commissioning of set of Internals for Impact Crushers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.6 | Supply, Erection, Commissioning of set of Internals for Stacker cum Reclaimers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Performance improvement and availability of various Auxiliaries of TG at 3x660MW KTPS Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Performance improvement and availability of various Auxiliaries for Oil Systems of Main Turbine. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.2 | Performance improvement and availability of various Auxiliaries of Generator System. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.3 | Performance improvement and availability of Feed Water System. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.4 | Performance improvement and availability of Vacuum System. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.5 | Performance improvement and availability of CEP System. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.6 | Procurement of Complete Pull out Assembly along with Impeller and wear ring of Cooling Water Pump. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.7 | Procurement of complete assembly of HP and LP Elements for Atlas Copco make Compressors. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Improvement in Wet ash evacuation system at 3x660MW Units, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Procurement & installation of Ash Slurry Series Pump Assembly with modified metallurgy and Critical Wet End Sub Assembly to enhance the performance & slurry disposal capacity. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.2 | Procurement & installation of Ash Slurry Series Pump Assembly with modified metallurgy along with Gear Box, Fluid Coupling & Motor (4’th Series) and Critical Wet End Sub Assembly to enhance the performance & slurry disposal capacity. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.3 | Procurement & installation of Overflow Transfer Pump Assembly with upgradation in metallurgy and Critical Wet End Sub Assembly to enhance the performance. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.4 | Procurement & installation of IAC Compressor Assembly: Model –ZR110 STD 7.5 IMD Atlas Copco Make Oil free water cooled screw air compressor with inbuilt atlas copco make heat of compression single drum rotator air dryer to enhance the performance. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | HMI Upgradation of Diasys Netmation DCS at 3x660MW KTPS Koradi Units 8,9 & 9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | HMI Upgradation of Diasys Netmation DCS at 3x660MW KTPS Koradi Units 8,9 & 10 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Improvement in Dry ash evacuation system at 3x660MW Units, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Procurement of Ingersoll Rand Make Transport Air Compressors Critical/Non-Critical Spares sub-assembly for performance improvement. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | MSERW Pipes for Garlanding arrangement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.1 | Work of Garlanding arrangement to changeover ash slurry feed points for even filling of pond by providing MSERW Pipes along the periphery of Ash Bund Dyke Wall at Khasara Ash Bund. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Capacity Enhancement & Performance optimization at WTP 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.1 | Capacity enhancement of DM water stream in WTP at 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.2 | Capacity enhancement Condensate polishing unit regeneration area in WTP at 3X660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.3 | Provision of Ozone generating plant of 1.0 Kg capacity in WTP at 3X660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | DPR for Construction of CC Road alongwith RCC Drain, CC platform for heavy machinery movement at 3x660 MW, TPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.1 | DPR for Construction of CC Road alongwith RCC Drain, CC platform for heavy machinery movement at 3x660 MW, TPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Improvement in Coal Mill Performance-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.1 | Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi through OEM. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.2 | Procurement of Mill Rotary Separator Blades for coal mill MVM 32R at 3x660 MW, KTPS, Koradi through open tender | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.3 | Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi through OEM. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.4 | Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi through OEM | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Improvement in Boiler performance-II at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.1 | Scheme1:Procurement of Coal compartment assembly for Unit8 at 3x660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.2 | Scheme2:Procurement of blade sets for ID, FD & PA Fan at 3x660 MW, Units at KTPS Koradi through OEM. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.3 | Scheme3:Procurement of RAPH internal Spares for 3X660MW units at KTPS Koradi through OEM (Qty- 6 Sets) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.4 | Scheme4:Procurement of RAPH Sector plate with Actuating mechanism assembly for Unit9 3 X 660MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | Improvement in Coal Mill performance-II at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | Procurement of FLENDER make Gearbox model kmp-450 along with motor for coal mill MVM32R at 3x660mw KTPS, koradi through OEM. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.2 | Procurement of complete set of couplings for PA, ID & FD fans at 3X660MW units at KTPS Koradi through OEM | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Improvement in Coal Mill performance-III at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit10 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.5 | Scheme5:Procurement of Complete MRHS System along with Pneumatic Compressors at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | Improvement in Boiler performance-III at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | Scheme1:Procurement of Coal compartment assembly for Unit8at 3x660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Scheme2:Procurement of blade sets for ID, FD & PA Fan at 3x660 MW, Units at KTPS Koradi through OEM. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Scheme3:Procurement and replacement of heating elements for RAPH installed in Unit 9 (660MW) at KTPS Koradi THROUGH OEM/OES (Qty- 2 Sets) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Scheme4:Procurement of HP valves, safety valves and ERV's for 3X660MW units at KTPS Koradi through OEM | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.5 | Scheme5:Procurement of RAPH Sector plate with Actuating mechanism assembly for Unit8 3 X 660MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | Improvement in Coal Mill performance-IV at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit8 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | Improvement in Coal Mill performance-V at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit9 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | Improvement in Boiler performance-IV at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.1 | Scheme1:Procurement of Coal compartment assembly for Unit8 at 3x660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.2 | Scheme2:Procurement of blade sets for ID, FD & PA Fan at 3x660 MW, Units at KTPS Koradi through OEM. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.3 | Scheme3:Procurement of RAPH bottom support bearing assembly for 3X660MW units at KTPS Koradi through OEM (Qty- 2 Sets) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.4 | Scheme4:Procurement of RAPH top guide bearing assembly for 3X660MW units at KTPS Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.5 | Scheme5:Procurement of RAPH Gear Box for 3X660MW units at KTPS Koradi through OEM (Qty- 1 Sets) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.6 | Scheme6:Procurement of RAPH Sector plate with Actuating mechanism assembly for Unit10 at 3 X 660MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.7 | Scheme7:Procurement and replacement of heating elements for RAPH installed in Unit 10 (660MW) at KTPS Koradi THROUGH OEM/OES (Qty- 2 Sets) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.8 | Scheme8:Procurement of Boiler Circulating Pump (1 Nos) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | Improvement in Coal Mill performance-VI at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit9 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.3 | Reliability Improvement schemes of generators at 3X660MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | Scheme No. 1 :PROCUREMENT OF MELCO/LMTG MAKE GENERATOR ROTOR ASSEMBLY with excitation transformer AT 3X660MW KTPS, KORADI THROUGH OEM | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.2 | Scheme No. 2:PROCUREMENT OF ONE COMPLETE SET OF GENERATOR STATOR COILS FOR GENERATOR AT 3X660MW UNITS AT KTPS KORADI THROUGH OEM | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | DPR on Procurement of Critical Speares for L&T make Main Turbine(typeTC4F-30) installed at 3x660MW KTPS Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.1 | Scheme No. 1 :Procurement of Critical Speares for L&T make Main Turbine(typeTC4F-30) installed at 3x660MW KTPS Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | DPR for Coal Handling Plant Performance Improvement Schemes -II at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.1 | Scheme No. 1 : Performance Improvement of Unloading System Wagon Tipplers at CHP 3x660MW KTPS Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.2 | Scheme No. 2 : Performance Improvement of Unloading System Side Arm Chargers at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Side Arm Charger Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.3 | Scheme No. 3 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.4 | Scheme No. 4 : Performance Improvement of Stacking & Reclaiming System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Stacking & Reclaiming System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.5 | Scheme No. 5 : Performance Improvement of Crushing System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Impact Crusher & Wobbler Feeders Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.6 | Scheme No. 6 : Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -1 at CHP 3x660MW KTPS Koradi A) Brief scope of work: Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -1 at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | DPR for Coal Handling Plant Performance Improvement Schemes -III at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.1 | Scheme No. 1 : Performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Hydraulic system for Wagon Tippler, Side Arm Charger , Apron Feeder ( 1 & 2) Stacker Reclaimer 1 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.2 | Scheme No. 2 : Construction of Air tight Hydraulic power pack room along with necessary cooling system for performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Construction of Air tight Hydraulic power pack room along with necessary cooling system for Wagon Tippler & Apron Feeder ( 1 to 4) Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.3 | Scheme No. 3 : Performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory Hydraulic Power Cylinders of Wagon Tippler, Side Arm Charger ( 1 to 4) Stacker Reclaimer 1 & 2 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.4 | Scheme No. 4 : Performance Improvement of Stacker Reclaimer by providing Hydraulic Drive to Boom Conveyor at CHP 3x660MW KTPS Koradi A) Brief scope of work: Hydraulic Drive to Boom Conveyor Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.5 | Scheme No. 5 : Performance Improvement of Illumination system with energy conservation at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Solar High masts along the rail track in railway yard Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.6 | Scheme No. 6 : Design, Supply & Installation of LT VFD Drives for Critical Conveyors at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of LT VFD Drives for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.7 | Scheme No. 7 : Design , supply, Erection & Commissioning of Short Conveyor for Stacking Purpose at CHP 3x660MW KTPS Koradi A) Brief scope of work: Short Conveyor for Stacking Purpose at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.8 | Scheme No. 8 : Capacity Enhancement of BCN-7/5/4/3 /1 AB in CHP 3x660MW KTPS Koradi A) Brief scope of work: Short Conveyor for Stacking Purpose at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.9 | Scheme No. 9 : Design , Engineering & modification along with strengthening of Existing Travel Track structure for Side Arm Charger & Stacker Reclaimer A) Brief scope of work: strengthening of Existing Travel Track structure for Side Arm Charger & Stacker Reclaimer Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.1 | Scheme No. 10 : Design , Engineering & Erection of modified Energy Efficient Ventilation System for Wagon Tippler Complex Area in CHP 3X660MW KTPS Koradi A) Brief scope of work: Energy Efficient Ventilation System for Wagon Tippler Complex Area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.11 | Scheme No. 11 : Design , Engineering & Installtion of Vibration & temprature Monitoring Systems for critical auxiliaries in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Installtion of Vibration & temprature Monitoring Systems for critical auxiliaries Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.12 | Scheme No. 12 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.13 | Scheme No. 13 : Design , Engineering & Provision of Stone Grappling Equipment System for Wagon Tippler 3 &4 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Stone Grappling Equipment System for Wagon Tippler 3 &4 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.14 | Scheme No. 14 : Design , Engineering & Provision of Public Addressing System for Wagon Tippler Complex in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Public Addressing System for Wagon Tippler Complex in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.15 | Scheme No. 15 : Design , Engineering & Provision of Belt Tracking System for Critical Conveyors in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Belt Tracking System for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.16 | Scheme No. 16 : Design , Engineering & Provision of Dust supression System for stacker reclaimer-1 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.17 | Scheme No. 17 : Work of Life Enhancement of wobbler Feeder 1 &2 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28 | DPR for Coal Handling Plant Performance Improvement Schemes -IV at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28.1 | Scheme No.1 : Design , Engineering , Supply & Installation of Modular Transfer chutes for Critical Conveyor System in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of Modular Transfer chutes for Conveyor System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28.2 | Scheme No.2 :Upgradtion of Exsisting Fire Fighting System at Stack yard area in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradtion of Exsisting Fire Fighting System at Stack yard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28.3 | Scheme No.3 : Design , Engineering , Supply & Strengthening of engineering structure of BCN- 7A/B along with track alignment in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Strengthening of engineering structure of BCN- 7A/B Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28.4 | Scheme No.4 : Design , Engineering , Supply & Installation of Mist Cannon Spray System around stackyard area in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of Mist Cannon Spray System at stackyard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28.5 | Scheme No.5 : Design , Engineering , Supply & Installation of EOT cranes at Bunker in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of EOT cranes at Bunker Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29 | DPR for Procurment of various Heavy Vehicles at CHP 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29.1 | Scheme No.1 : Procurment of Heavy Vehicles like dozers, wheel loaders , locomotives, Crane, Hydra , Disel Browser , Jcb & Bobcats etc. in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurment of Heavy Vehicles like dozers, wheel loaders , locomotives etc Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29.2 | Scheme No.2 : Procurment of Auger Machines for coal sampling in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurment of Auger Machines for coal sampling Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29.3 | Scheme No.3 : Procurment of Truck Mounted mist cannon dust supression system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurment of Truck Mounted mist cannon dust supression system in CHP Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30 | DPR for Coal Handling Plant Performance Improvement Schemes -V at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.1 | Scheme No. 1 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.2 | Scheme No. 2 : Performance Improvement of Stacking & Reclaiming / Side Arm Charger System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Energy Chain System of Stacking & Reclaiming System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.3 | Scheme No. 3 : Performance Improvement of unloading System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Energy Chain System of side arm acharger Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.4 | Scheme No. 4 : Upgradation to 100 MT Ton Weighbridge of existing road weighbridge at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of LT VFD Drives for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.5 | Scheme No. 5 : Design , Engineering & Erection of modified Energy Efficient Ventilation System for Crusher House Area in CHP 3X660MW KTPS Koradi A) Brief scope of work: Energy Efficient Ventilation System for Wagon Tippler Complex Area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.6 | Scheme No. 6 : Design , supply & Installation of Cooling Arrangement for Switchgear rooms at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Cooling Arrangement for Switchgear rooms Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.7 | Scheme No. 7 : Design , Engineering & Erection of modified Engineering Structure of Tunnel Conveyor 1A &1 B in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Erection of modified Engineering Structure of Tunnel Conveyor 1A &1 B Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31 | DPR for Coal Handling Plant Performance Improvement Schemes -VI at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.1 | Scheme No. 1 : Performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Wagon Tippler, Side Arm Charger , Apron Feeder ( 3 & 4) Stacker Reclaimer 2 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.2 | Scheme No. 2 : Design Supply & Installation of Wagon Locking system for all four wagon tipplers at CHP 3x660MW KTPS Koradi A) Brief scope of work: Wagon Locking system for all four wagon tipplers Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.3 | Scheme No. 3 : Design, Supply & Installation of upgraded Vibrating Feeders for Stacker Reclaimer at CHP 3x660MW KTPS Koradi A) Brief scope of work: Design, Supply & Installation of upgraded Vibrating Feeders for Stacker Reclaimer Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.4 | Scheme No. 4: Performance Improvement of Stacker Reclaimer by providing Hydraulic Drive to Boom Conveyor at CHP 3x660MW KTPS Koradi A) Brief scope of work: Hydraulic Drive to Boom Conveyor Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.5 | Scheme No. 5 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.6 | Scheme No. 6 : Design , Engineering & Provision of Belt Tracking System for Critical Conveyors in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Belt Tracking System for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.7 | Scheme No. 7 : Design , Engineering & Provision of Dust supression System for stacker reclaimer-1 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.8 | Scheme No. 8 : Work of Life Enhancement of wobbler Feeder 3 &4 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32 | DPR for Coal Handling Plant Performance Improvement Schemes -VII at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.1 | Scheme No.1 : Design , Engineering , Supply & Installation of Modular Transfer chutes for Crusher House Complex & other Critical Conveyor System in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of Modular Transfer chutes for Conveyor System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.2 | Scheme No.2 :Upgradtion of Exsisting Fire Fighting System along the conveyor length in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradtion of Exsisting Fire Fighting System at Stack yard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.3 | Scheme No.3 : Supply , Erection & Installation of Rack & Pinion Elevators at Bunker in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Supply , Erection & Installation of Rack & Pinion Elevators at Bunker in CHP 3X660MW KTPS Koradi. Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.4 | Scheme No.4 :Up Liftment f Exsisting Fire Fighting lines in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradtion of Exsisting Fire Fighting System at Stack yard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.5 | Scheme No.5 : Procurement of HPPE Polymer Roller for Conveyor system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurement of HPPE Polymer Roller for Conveyor system Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.6 | Scheme No.6 : Design , Engineering , Supply & Installation of EOT cranes at Wagon Tippler Complex in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of EOT cranes at Wagon Tippler Complex Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33 | DPR for Coal Handling Plant Performance Improvement Schemes -VIII at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.1 | Scheme No. 1 : Performance Improvement of Unloading System Wagon Tipplers at CHP 3x660MW KTPS Koradi Estimated Cost : 3.6 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.2 | Scheme No. 2 : Performance Improvement of Unloading System Side Arm Chargers at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Side Arm Charger Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.3 | Scheme No. 3 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.4 | Scheme No. 4 : Performance Improvement of Stacking & Reclaiming System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Stacking & Reclaiming System -2 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.5 | Scheme No. 5 : Performance Improvement of Crushing System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Impact Crusher & Wobbler Feeders Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.6 | Scheme No. 6 : Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -2 at CHP 3x660MW KTPS Koradi A) Brief scope of work: Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -2 at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.7 | Scheme No. 7 : Other Mislenious Schemes at CHP 3x660MW KTPS Koradi A) Brief scope of work: Other Mislenious works Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.8 | Scheme No. 4 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.9 | Scheme No.8: Procurement of HPPE Polymer Roller for Conveyor system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurement of HPPE Polymer Roller for Conveyor system Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34 | DPR for Coal Handling Plant Performance Improvement Schemes -IX at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.1 | Scheme No. 1 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.2 | Scheme No. 2 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.3 | Scheme No.3 : Upgradation of Exsisting Rack & Pinion Elevators at CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradation of Exsisting Rack & Pinion Elevators Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.4 | Scheme No.4 : Procurement of HPPE Polymer Roller for Conveyor system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurement of HPPE Polymer Roller for Conveyor system Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.5 | Scheme No.5 : Other miscellaneous scheme regarding sustainable performance improvement of CHP 3X660MW KTPS Koradi. A) Brief scope of work: ther miscellaneous scheme regarding sustainable performance improvement Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | Design & engineering, procurement, supply, installation & commissioning of Ozone Generator system of capacity 45.0 Kg/hr for CW system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Scheme1:Design & engineering, procurement, supply, installation & commissioning of Ozone Generator system of capacity 45.0 Kg/hr for CW system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36 | Pipeline expansion to improve dry ash evacuation system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.1 | Scheme1: Pipeline expansion to improve dry ash evacuation system along with target box modification and also to erect & commission dry ash evacuation directly to remote silo. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37 | Modification at intermediate silo and HCSD system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.1 | Scheme1: Additional charge pump. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.2 | Scheme 2: Supply & Installation Air washery at silo top. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.3 | Scheme 3: Shed above silo top. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.4 | Scheme 4: Supply & Installation Construction of platform at pipe rack up to Remote silo. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.5 | Scheme 5: Shifting of pipeline above pipe rack. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.6 | Scheme 6: Supply & Installation ART sub assemblies. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38 | ESP field strengthening at U#8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.1 | Scheme1: ESP field strengthening at U#8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
39 | Procurement of various pumps for AHP performance improvement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
39.1 | Scheme1: Procurement of various pumps for AHP performance improvement. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
40 | Modification in Dry Ash Evacuation System D/V Assemblies & allied equipments to improve performance | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
40.1 | Scheme1: Procurement of D/V Assemblies & allied equipments to improve performance. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41 | Additional IAC house for Intermediate silo and Remote silo along with erection of S.S. Pipeline | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.1 | Scheme1: Supply & Installation Additional IAC house for Intermediate silo and Remote silo along with erection of S.S. Pipeline | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42 | Waste water system modification to have zero water discharge | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.1 | Scheme1: Waste water system modification to have zero water discharge at 3x660MW, KTPS, Koradi along with Pump Procurement along with arrangement of sludge discharge at ESP water Washing system. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
43 | ESP field strengthening at U#9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
43.1 | Scheme1: ESP field strengthening at U#9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44 | Procurement of HCSD GEHO Pump (TZPM-400) critical items sub-assemblies | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.1 | Scheme1: Procurement of HCSD GEHO Pump TZPM-400) critical items sub-assemblies. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45 | MSERW Pipes & Seamless Pipes replacement to improve ash conveying & its disposal-1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.1 | Scheme1: Supply & Work of Replacement of MSERW Pipes & Seamless Pipes in Bottom ash/Coarse ash evacuation & Ash Slurry Disposal Pipelines, Dry ash conveying system in phase manner to improve the ash evacuation performance. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46 | Improvement in Ash Water Recovery System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.1 | Scheme1: Supply & Installation of Pumps along with Pipeline for Improvement in Ash Water Recovery System. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47 | Replacement of Instrument air pipeline from M.S. to S.S for AHP main plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.1 | Scheme1: Replacement of Instrument air pipeline from M.S. to S.S for AHP main plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48 | Modification of sludge pumps and its pipeline with pumps of higher capacity and discharge line of higher capacity. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.1 | Scheme1: Modification of sludge pumps and its pipeline with pumps of higher capacity and discharge line of higher capacity. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
49 | ESP field strengthening at U#10 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
49.1 | Scheme1: ESP field strengthening at U#10 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50 | MSERW Pipes & Seamless Pipes replacement to improve ash conveying & its disposal-2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50.1 | Scheme1: Supply & Work of Replacement of MSERW Pipes & Seamless Pipes in Bottom ash/Coarse ash evacuation & Ash Slurry Disposal Pipelines, Dry ash conveying system in phase manner to improve the ash evacuation performance. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
51 | Replacement of IAC for AHP Main Plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
51.1 | Scheme1: Supply & Installation of IAC for AHP Main Plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
52 | Improvement in DRY ASH Evacuation system-2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
52.1 | Scheme1: Supply & Installation of TAC, Replacement of Air Lock Vessel, Various Valves, ESP Hopper Doors, ESP access doors. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
53 | Improvement in DRY ASH Evacuation system-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
53.1 | Scheme1: Procurement of Ingersoll Rand Make Transport Air Compressors Critical/Non-Critical Spares sub-assembly for performance improvement. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
54 | Detailed project report for various works of security section as per the IB recommendations. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
54.1 | Repairing & raising height of compound wall with provision of concertina coil at various location of peripheral compound wall at 3x660MW KTPS Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
54.2 | Work of Providing structural three quarter turn staircase with landing along pheriphery of FISS watch tower at 3x660MW, TPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
55 | Supply, installation, comissioning and testing of 220V station & 360V UPS batteries installed at U 8, 9 & 0 of 3x660 MW KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
55.1 | Supply, installation, comissioning and testing of 220V station & 360V UPS batteries installed at U 8, 9 & 0 of 3x660 MW KTPS, Koradi. (scheme) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
56 | TDBFP Governing valve's LPCV ,HPCV MSV AND Trip lock replacement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
61 | Procurement & replacement of HP Heaters at 3x660 MW KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Vibration Monitoring & Analysis system installed at 3x660MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of sinkawa make vibration monitoring and Analysis system for main turbine at 3x660MW koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of Bently Nevada make vibration monitoring and Analysis system for RMCMS system at 3x660MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3 :-Emerson PLC upgradation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of various Level Transmitters installed at 3x660 MW koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of Guided wave Radar Level TX installed at Condenser Hotwell and LPH 1,2 and 3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of Displacer type level TX into Guided wave radar level Tx installed at various Drain Tank, Flash tank and pit | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3: Upgradation of non- contact type Ultrasonic level Tx into IP68 non- contact type Radar level TX. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of ESP Hopper level Probes installed at 3x660 MW koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of 1st three fields ESP Hopper level probes into continuous level monitoring NOGS system at 3x660 MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of RF capacitance Hopper level probe into of RF admittance level probe at 4,5,6,7,8 & 9 ESP Hoppers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3: Upgradation of ESP hopper heater monitoring , control and real time monitoring system at 3X660MW Koradi TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of various scheme viz ASLD, Furnace tv camera FEGT and acoustic Pyrometer installed at 3x660 MW koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of ASLD system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of Furnace TV Camera | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3:Upgradation of FEGT system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 4:Upgradation of acoustic pyrometer | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of various scheme viz instrument Air pipe at ESP Area, wet Ash Evacuation system, HCSD Silo. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of instrument Air pipeline system at ESP of M.S into SS installed at 3x660 MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of instrument Air pipeline system at wet Ash system of M.S into SS . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3: Upgradation of instrument Air pipeline system at HCSD silo of M.S. into SS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 4: Upgradation of instrument Air pipeline system at Remote Silo of M.S into SS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 5: Upgradation of Control & Instrument section lab with Hydraulic Servo Valve Test, Pneumatic System test and calibration lab set up. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Flame scanner for flexible operation of 3X660MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of Flame scanner for flexible operation of 3X660MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of DRC Pipes, Bends & Fittings in phase manner to improve the dry ash conveying & its disposal (2 years) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of DRC Pipes, Bends & Fittings in phase manner to improve the dry ash conveying & its disposal (2 years) (Rs.30 Cr.) (Bottom ash/Coarse ash evacuation & Ash Slurry Disposal Pipelines, Dry ash conveying system) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Augmentation of Coarse Ash disposal system at U10 at KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | WORK OF INSTALLATION & COMMISSIONING OF ASH DISPOSAL SYSTEM AT UNIT#10 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Railway Track Siding Performance Improvement Schemes at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 1 : Work of complete track renovation of existing Rail yard of CHP, 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. Due to continuous movement of Railway's precious rolling stock, the track spares are worn out and are due for complete replacement. Hence, to maintain rail track parameters in healthy condition as per Railway norms so as to avoid untoward incidences of derailment the execution of work of complete track renewal is essential. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 2 : Scheme Name- Work of laying of additional track at 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. However, as per the existing infrastructure, at present there is no dedicated empty formation line. Due to non-availability of empty formation line, most often unloading gets hampered due to blocking of outhaul line by empty rake. The hampering in unloading affects the plant performance and incurrs unnecessary financial burden on KTPS account under the head of demurrage charges. Hence, to maintain the plant loadability and availability, it is essential to lay additional track at 3x660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 3 : Scheme Name- Work of rectification and upgradtion of existing SSP at CHP, 3x660MW, KTPS, Koradi. Justification- The SSP has been erected at 3x660MW, KTPS, Koradi. However, till date the same has not been commissioned. With lapse of @ 5-6 years after erection and its non commissioning, the existing SSP set up has been completely detoriorated. Now, Railway's is pressing hard for early commissioning of the same. The said set up shall ensure isolation of OHE of existing yard with Railway's main line. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 4 : Scheme Name- Work of construction of apron RCC platforms at inhaul and outhaul of Wagon tipllers 1, 2, 3 & 4 of CHP 3x660MW, KTPS, Koradi. Justification- The 04 Nos. of wagon tipplers are installed at CHP-3x660MW, KTPS, Koradi. In this regards, it is to submit that, the wagon unloading is being carried out through these tipplers. Hence, presence of fugitive dust in tippler area is predominant. The said dust is being accumulated at inhaul and outhaul of wagon tipplers. Due to presence of loaded wagons at inhaul and empty wagons at outhaul, this office gets least opportunity for clearance of the said coal dust along the track. Due to accumulation of coal dust, the rail track parameters along with gradient are getting distubed. The disturbance in gradient is causing rolling of wagons which is not recommended in view of safety of both man and machine. Besides, this due to rolling of wagons, the occurnece of untoward incidence of derailment is predominant. Hence, to maintain uniform rail track gradient it shall be enviable to construct the apron RCC platforms at inhaul and outhaul of Wagon tipplers 1, 2, 3 & 4 of CHP-3x660MW, KTPS, Koradi. Estimated cost- Rs. 4 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 5 : Scheme Name- Work of construction of apron RCC platforms at inhaul and outhaul of Wagon tipllers 1, 2, 3 & 4 of CHP 3x660MW, KTPS, Koradi. Justification- The 04 Nos. of wagon tipplers are installed at CHP-3x660MW, KTPS, Koradi. In this regards, it is to submit that, the wagon unloading is being carried out through these tipplers. Hence, presence of fugitive dust in tippler area is predominant. The said dust is being accumulated at inhaul and outhaul of wagon tipplers. Due to presence of loaded wagons at inhaul and empty wagons at outhaul, this office gets least opportunity for clearance of the said coal dust along the track. Due to accumulation of coal dust, the rail track parameters along with gradient are getting distubed. The disturbance in gradient is causing rolling of wagons which is not recommended in view of safety of both man and machine. Besides, this due to rolling of wagons, the occurnece of untoward incidence of derailment is predominant. Hence, to maintain uniform rail track gradient it shall be enviable to construct the apron RCC platforms at inhaul and outhaul of Wagon tipplers 1, 2, 3 & 4 of CHP-3x660MW, KTPS, Koradi. Estimated cost- Rs. 4 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 6 : Scheme Name- Work of construction of RCC platforms along the rail track of CHP 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. In this regards, it is to submit that, after unloading of rakes the empty rakes are being examined by Railway's C&W staff camped at KTPS, Koradi. Hence, for safe movement of Railway's staff, Railway's is pressing hard for provision of RCC platforms along the rail track of CHP-3x660MW, KTPS, Koradi. Estimated cost- Rs. 10 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 7 : Scheme Name- Work of repairing and construction of RCC permanent revenue canal at, KTPS, Koradi. Justification- The temporary revenue canal is being flowing beside the existing Railway exchange yard of 210 MW, KTPS, Koradi. The said canal gets clogged inview of ash accumulation. Due to clogging this canal overflows and its overrun enters the 210 MW rail yard thereby creating track surface marshy and unsafe for Rail movement. Hence, it is essential to repair and construct RCC permanent revenue canal at KTPS, Koradi so that proper and timely cleaning of canal along with proper outlet can be arranged. Estimated cost- Rs. 15 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme Name-08 Work of construction of RCCretaining wall at Godhani and Kalumna end of KTPS, Koradi. Justification- The separate rail infrastructure has been commissioned for Koradi TPS to cope up the daily coal requirement. The rail traffic at KTPS, Koradi is being catered through Godhani and Kalumna end respectively. In this regards, it is to submit that, the take off points at Godhani and Kalumna both are S&T operated. During monsoon, it is often witnessed that, the rain water enters the plant premises from others land thereby submerging the S&T operated point. Due to this, signals gets lost and hampers the Rail traffic movement completely. Hence, it is essential to restrict the entrance of rain water in plant premises. This can be possible by constructing retaining wall at required loaction. Estimated cost- Rs. 1 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme Name-09 OHE maintenance at CHP, KTPS, Koradi Justification-As per the Railway board circular, Railway's has mandated that OHE maintenance cost for existing as well as new sidings shall be borne by the siding owner in accordance with Railway guidelines. Railway will carry out necessary inspection of maintenance work once in six months. Maintenance charges per TKM per annum of OHE as finalized by SECR zonal office is Rs.291566/- per TKM per annum. Also, inspection charges at the rate of Rs.106974/- per day towards inspection to be carried out by Railways every si x months shall be charged on actual basis by Railway's from the sidings.Accordingly, Railway.s has calimed amount of Rs.31314519/- for two years. Hence for 5 yeards it is expected to be Rs.7.82 Cr. Estimated cost- Rs. 7.82 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 10 Name-Remodelling and upgradation of existing S & T system with Panel Interlocking system and associated S & T gears to S & T system with Electronic Interlocking system and associated S & T gears in connection with services for BG Railway facility (660 MW Rail yard) for Koradi Thermal Power Station of MSPGCL Justification-As per the prevailing Railway norms, it is mandatory to commission the S & T system in private Railway siding for fast and safe movement of Railway’s precious rolling stock. Unless and until remodeling is carried out the S&T system cannot be started at Koradi Railway yard.With commissioning and operation of S & T system there shall be least possibility for derailments during internal shunting through crossovers, as the said points shall be motorized operated. Estimated cost- Rs. 20 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 11 : Work of supply and provision of lights and high mast at CHP Railway exchange yard of 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. In this regards, it is to submit that, after unloading of rakes the empty rakes are being examined by Railway's C&W staff camped at KTPS, Koradi on round the clock basis. Hence, for safe movement of Railway's staff, Railway's is pressing hard for availability of proper illumination in complete yard. Estimated cost- Rs.2.5 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Provision of cover shed for stack yard -2 at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 1 : Provision of cover shed for stack yard -2 at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Procurement of Pipe Conveyor Drive System Internals at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 1 : Procurement of Pipe Conveyor Drive System Internals at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Provision of service building along with vehicle bay at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 1 : Provision of service building along with vehicle bay at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | GENERAL ASSET | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | GENERAL ASSET--AKRDFOGA01-OFFICE FURNITURE | N.A. | - | 0 | 0.34006 | 0.52466 | -0.1846 | 0.08293 | 0.08293 |  |  | 0.08293 | -0.1846
2 | GENERAL ASSET--AKRDFOGA02-COMPUTERS,PRINTER,SCANNER | N.A. | - | 0 | 1.2126 | 1.2623 | -0.049645 | 0.24775 | 1.4587 |  |  | 1.4587 | -1.2606
3 | GENERAL ASSET--AKRDFOGA03-AC,WATER COOLER | N.A. | - | 0 | 0.25766 | 0.2908 | -0.033135 | 0.038181 | 0.038181 |  |  | 0.038181 | -0.033135
4 | GENERAL ASSET--AKRDFOGA04-AIR PURIFIER | N.A. | - | 0 | 0 | 0.0105 | -0.0105 | 0 | 0 |  |  | 0 | -0.0105
0 | D) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of KLEP Unit for 'HCSD Pump | 0 | - | 3.73 | 0 | 0 | 0 | 3.73 | 3.73 |  |  | 3.73 | 0
2 | Restoration of Boiler Circulation Pump at 3X660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of Coal Compartment Assemblies for Unit-10 at 3x660MW KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Repairing and Refurbishment of TDBFP cartridge Model FK6E40 installed at 3X660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Non-DPR for Upgradation of Honeywell Make PLC for Mill Reject Handling System installed at 3x660MW Balance of Plant (BOP) Unit- 8, 9 & 10 at Koradi TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of Sky Climber for furnace repairing at 3x660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Double Roll Clinker Grinder | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement along with Installation of Clear Water Booster Pump with Motor, Panel Cable and other allied accessories in Unit#10 bottom ash area at AHP, 3x660MW, KTPS, Koradi. | N.A. | - | 0 | 0.25116 | 0 | 0.25116 | 0 | 0 |  |  | 0 | 0.25116
9 | Procurement of single Roll Clinker Grinder with Feed Pump & Jet Pump Complete Assembly with modified metallurgy installed at AHP ,3x660MW Units, KTPs, Koradi | N.A. | - | 0 | 1.1668 | 0 | 1.1668 | 0 | 0 |  |  | 0 | 1.1668
10 | Work of Repairing and Refurbishment of HIP Rotor along with balancing and over speed trial for L&T-MHI make turbine (Type: TC4F-30”) installed at 3X660MW KTPS, Koradi | N.A. | - | 0 | 0.22316 | 0 | 0.22316 | 0 | 0 |  |  | 0 | 0.22316
11 | Procurement of spares for Flue gas distribution dampers, PA fan discharge dampers and Coal mill Hot PA Gate and Dampers at 3x660mw KTPS units through OEM | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Work of Modification & Installation of Take up trolley & arrangement for take up lifting for conveyor BCN-13A at CHP 3X660MW,KTPS,Koradi | N.A. | - | 0 | 355.8831 | 0 | 355.8831 | 0 | 0 |  |  | 0 | 355.8831
13 | Work of Design, Modification & streingthening of Tripper trolley structure with provision of Antiwear plates discharge chute box at CHP 3X660MW,KTPS,Koradi | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Upgradation of Management Information System (MIS) Server and Associated Software for C&I at 3x660MW Unit- 8, 9 & 10 at Koradi TPS | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | Procurement of Vibrating Tranfer chute with double exciter Drive for stacker reclaimer at CHP,3X660MW,KTPS ,Koradi | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | Supply & Installation of Ash Slurry Density Transmitter at High Concentrated Slurry Disposal (HCSD) System of BOP area of 3x660MW Unit- 8, 9 & 10 at Koradi TPS | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | Supply & Installation of Fiber Optic Sensing System for Conveyor Health Monitoring At CHP 3x660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | Procurement of Leak- proof make complete Mechanical Seal Assembly for Concrete Volute CW Pump installed at 3X660MW KTPS,Koradi on OEM bASIS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | Work of Design , Engineering , Manufacturing , Supply Erection & Commissioning of Conveyor Belt From Discharge of RBF 1 &2 at Crusher House to Stack Yard At CHP 3x660MW KTPS, Koradi . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20 | Supply & Installation of Artificial Intelligence PMMS Accurex Diagnostic matrix based vibration & temperature monitoring for critical auxiliaries at CHP 3x660MW KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Restoration of online dissolved gas analysers of Unit 8,9,10 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | Complete Replacement of Existing Water Separator Drain Tank Control (WDC) Valves with New Valves of modified trim design along with hydraulic Actuators, Power Pack assembly, necessary instrumentation, erection & commissioning 3X660MW KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Procurement of mandatory set of Hydraulic system internals for Wagon Tippler Drive & side arm charger Drive at CHP,3X660MW,KTPS ,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | "Supply & installation of Anodized winding Oil cooled over band magnetic separator & control panel for conveyor 5A,5B &13C at CHP 3x660MW KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | Procurement of Grinding Wall Assembly for Impact Crusher At CHP 3x660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | Restoration of Boiler Circulation Pump of U10 at 3X660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | Design,Engineering,Customization,Implementation,Installation & testing of Data Analytical/Artificial Intellegence softwae for automated monitoring & diagnostics system to improve Power plant reliability & efficiency,at one unit of 3X660MW KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28 | Supply of Feed Gate Complete Assembly along with installation to enhance the performance of Feed Gate at Ash Handling Plant, 3x660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29 | Design, Supply, Installation & Commissioning of Instrument Air Dryer Assembly with Prefilters & Stainless steel piping along with valves suitable for Instrument Air Compressors at AHP, 3x660MW Units, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 1066.3642 | 762.9402 | 303.4241 | 42.8633 | 31.8996 | 0 | 0 | 31.8996 | 314.3877
FY 2024-25
0 | A) Approved Add cap: | 0 | - | 0 | 0
A | BoP | 0 | - | 246.34 | 103.6804 | 232.6929 | -129.0125 | 0 | 0 |  |  | 0 | -129.0125
B | BTG | 0 | - | 44.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B1 | Supply | 0 | - | 13.33 | 0 | 13.33 | -13.33 | 0 | 0 |  |  | 0 | -13.33
B2 | Works | 0 | - | 0.98 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B3 | Taxes and duties | 0 | - | 23.29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B4 | Civil | 0 | - | 0.19 | 0.19 | 0 | 0.19 | 0 | 0 |  |  | 0 | 0.19
B5 | Mandatory Spares | 0 | - | 5.03 | 1.29 | 6.32 | -5.03 | 0 | 0 |  |  | 0 | -5.03
B6 | BTG (L&T) Work | 0 | - | 1.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C | Other Works (Plant) | 0 | - | 136.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C1 | Fully Integrated Security System | 0 | - | 27.36 | 31.4615 | 31.4615 | 0 | 0 | 0 |  |  | 0 | 0
C2 | Administrative Expenses and overhead | 0 | - | 7.25 | 6.69 | 0 | 6.69 | 0 | 0 |  |  | 0 | 6.69
C3 | Contingencies E&M | 0 | - | 0.04 | 0.04 | 0 | 0.04 | 0 | 0 |  |  | 0 | 0.04
C4 | Mobile storage racks, fork lifts, hoists & hydra for material handling in major stores shed | 0 | - | 0.95 | 0.93645 | 0.93645 | 0 | 0 | 0 |  |  | 0 | 0
C5 | Development of working models of Plant Layout, Boiler, Turbine- Generetaor, Coal mill, Fans, etc. at KTC, Koradi. | 0 | - | 1.2 | 1.2 | 0.98604 | 0.21396 | 0 | 0 |  |  | 0 | 0.21396
C6 | Workshop equipment | 0 | - | 0.26 | 0.26192 | 0.26192 | 0 | 0 | 0 |  |  | 0 | 0
C7 | Design, engg, manufacture, supply , erection, testing & commissioning of Ozonization Plant for circulating cooling water system | 0 | - | 54.05 | 31.7683 | 31.6144 | 0.15388 | 0 | 0 |  |  | 0 | 0.15388
C8 | Supply, installation & commissioning of water flow meters including required SCADA software and other accessories for water management system | 0 | - | 5.08 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C9 | Provision of wet ash evacuation system for first two rows of ESP for Unit-8,9 & 19 | 0 | - | 26.59 | 21.69 | 26.3181 | -4.6281 | 0 | 0 |  |  | 0 | -4.6281
C10 | Procurement of portable mercury analyser for flue gas monitoring | 0 | - | 6.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C11 | Administrative Expenses and overhead | 0 | - | 5 | 21.0001 | 0 | 21.0001 | 0 | 0 |  |  | 0 | 21.0001
C12 | Compressor of Hydrogen plant | 0 | - | 1.5 | 1.5 | 0 | 1.5 | 0 | 0 |  |  | 0 | 1.5
C13 | Rail Cum road stone grabbler | 0 | - | 0.85 | 0.85 | 0 | 0.85 | 0 | 0 |  |  | 0 | 0.85
D | Other Works (Civil) | 0 | - | 103.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D1 | Road, Bridges railway system | 0 | - | 20.1 | 0.10806 | 0 | 0.10806 | 0 | 0 |  |  | 0 | 0.10806
0 | S&T System with Panel Interlocking System | 0 | - | 0 | 10.4585 | 10.4596 | -0.0011606 | 0 | 0 |  |  | 0 | -0.0011606
D2 | Staff quarters | 0 | - | 5.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D3 | Other Misc & Unforseen Item | 0 | - | 25.79 | 9.3 | 7.53 | 1.77 | 0 | 0 |  |  | 0 | 1.77
0 | Check Post, Inspection Office & Facility Complex | 0 | - | 0 | 3.6844 | 3.6816 | 0.0028689 | 0 | 0 |  |  | 0 | 0.0028689
0 | CPRI Building | 0 | - | 0 | 6.2046 | 6.2046 | 0 | 0 | 0 |  |  | 0 | 0
0 | Foam cum DCP fire tender- 1 | 0 | - | 0 | 0 | 0.76926 | -0.76926 | 0 | 0 |  |  | 0 | -0.76926
0 | Fire water Bowser-cum-fire Tender- 1No. | 0 | - | 0 | 0.73537 | 0.73537 | 0 | 0 | 0 |  |  | 0 | 0
D4 | Const. facility | 0 | - | 3.28 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D5 | Contigency Other Civil Work | 0 | - | 5.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D6 | Adminstrative Exp. & Overhead (Salary & Overhead, Civil & E&M) | 0 | - | 21.47 | 31.64 | 0 | 31.64 | 0 | 0 |  |  | 0 | 31.64
D7 | Future unforseen works(Jalyukta Shiwar) | 0 | - | 0.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D8 | Landscaping work | 0 | - | 21.76 | 20.53 | 0 | 20.53 | 0 | 0 |  |  | 0 | 20.53
E | Initial Spares | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
E1 | Boiler & its auxilliaries | 0 | - | 14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Procurement of Table liners and Roller liners Of MVM 32R Coal Mills of 3 X 660MW Units at KTPS, Koradi | 0 | - | 0 | 10.0686 | 10.0686 | 0 | 0 | 0 |  |  | 0 | 0
ii | Procurement of couplings for Coal mill MVM 32 R of 3 X 660 MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 1.5944 | -1.5944 | 0 | 0 |  |  | 0 | -1.5944
iii | Procurement of Set of internal spares for Coal Mill Gear Box (KMP-450) for 3 X 660MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 2.2253 | -2.2253 | 0 | 0 |  |  | 0 | -2.2253
E2 | Turbine & its auxilliaries | 0 | - | 18.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | ULTRAFILTRATION MEMBRANE | 0 | - | 0 | 1.6511 | 1.6511 | 0 | 0 | 0 |  |  | 0 | 0
ii | Supply of Main turbine Vibration Monitoring System spares at 3x660MW, KTPS,Koradi. | 0 | - | 0 | 0 | 1.1469 | -1.1469 | 0 | 0 |  |  | 0 | -1.1469
iii | Procurement of Cartridge for Turbine Driven Boiler Feed Pump (Model No.: FK6E40) at 3X660 MW KTPS Koradi | 0 | - | 0 | 14.2864 | 14.2864 | 0 | 0 | 0 |  |  | 0 | 0
iv | Procurement of Critical Insurance Spares for L&T-MHI Make Turbine for attending major overhauling work of Turbine at KTPS, 3x660MW Units Koradi. | 0 | - | 0 | 11.1013 | 11.1013 | 0 | 0 | 0 |  |  | 0 | 0
E3 | Generator & its auxilliaries | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
E4 | Electrical auxilliaries | 0 | - | 1.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Procurement of HT Motors of BOP | 0 | - | 0 | 0 | 0.29335 | -0.29335 | 0 | 0 |  |  | 0 | -0.29335
ii | 0 | 0 | - | 0 | 0 | 0.84594 | -0.84594 | 0 | 0 |  |  | 0 | -0.84594
iii | Supply of Schneider make Differential Protection Relays for 3X660 MW, Koradi (OEM) | 0 | - | 0 | 0 | 0.10502 | -0.10502 | 0 | 0 |  |  | 0 | -0.10502
iv | Supply of Professional Large Format Display for display of DCS parameters PCR | 0 | - | 0 | 0.14885 | 0.14885 | 0 | 0 | 0 |  |  | 0 | 0
v | Procurement of ABT Energy meter with software for 3X660 MW, TPS, Koradi | 0 | - | 0 | 0 | 0.18337 | -0.18337 | 0 | 0 |  |  | 0 | -0.18337
E5 | Outdoor Plant i.e. CHP, AHP, WTP etc | 0 | - | 19.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Procurement of Forced Lubrication system for Premium make Gear box B3-450 installed for bunker conveyor BCN 7A/B at CHP 3X660MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0.15314 | -0.15314 | 0 | 0 |  |  | 0 | -0.15314
ii | Procurement of rotary spares for travel drive of Stacker and conveyor drive system in Coal Handling Plant of 3x660 MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0.35199 | -0.35199 | 0 | 0 |  |  | 0 | -0.35199
iii | Procurement of Complete assembly of Dome Valve ( 100NB, 200NB, 300NB) with power cylinder for dry Ash evacuation system of 3X660MW KTPS, Koradi. | 0 | - | 0 | 0.2225 | 0.2225 | 0 | 0 | 0 |  |  | 0 | 0
iv | Procurement of Modified Apron Pans for M/s. ELECON Engineering Company ltd make Apron Feeder in CHP 3x660MW Units at KTPS, Koradi. | 0 | - | 0 | 3.3233 | 3.3233 | 0 | 0 | 0 |  |  | 0 | 0
v | Procurement of Single Roll Clinker Grinder with Feed Sump and Jet Pump Complete Assembly with Drive, Driven Sprocket and Chain at AHP, 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.56357 | 0.56357 | 0 | 0 | 0 |  |  | 0 | 0
vi | Procurement of spares of Dome Valve (100NB, 200NB, 300NB) for Ash Evacuation System of 3X660MW Unit KTPS, Koradi. | 0 | - | 0 | 0.16431 | 0.16431 | 0 | 0 | 0 |  |  | 0 | 0
vii | 0 | 0 | - | 0 | 0.10064 | 0.10064 | 0 | 0 | 0 |  |  | 0 | 0
viii | 0 | 0 | - | 0 | 0.00708 | 0.00708 | 0 | 0 | 0 |  |  | 0 | 0
ix | Procurement of Hydraulic Motor for Apron feeder in Coal Handling Plant 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.7965 | 0.7965 | 0 | 0 | 0 |  |  | 0 | 0
x | Procurement of Peristaltic Hose Pump (Model no: RP2 – 40) Spares for HCSD System of Ash Handling Plant, 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.20622 | 0.20622 | 0 | 0 | 0 |  |  | 0 | 0
xi | Procurement of spares for HP Water Pump, Mather & Platt make, model 10/12 EME for AHP at 3X660 MW, KTPS, Koradi | 0 | - | 0 | 0.28246 | 0.28246 | 0 | 0 | 0 |  |  | 0 | 0
xii | Procurement of Rotor shaft assembly for M/s. ELECON Engineering Company ltd make Impact Crusher in CHP 3x660MW Units at KTPS, Koradi. | 0 | - | 0 | 0.76369 | 0.76369 | 0 | 0 | 0 |  |  | 0 | 0
xiii | Procurement of Sam Turbo Make Pumps Spare parts for Ash Handling Plant of 3X660 MW Units at KTPS, Koradi | 0 | - | 0 | 0.17166 | 0.17166 | 0 | 0 | 0 |  |  | 0 | 0
xiv | Procurement of Wagon Tippler Spares for M/s. ELECON Engineering Company ltd. make Wagon Tippler in CHP 3X660MW Units at KTPS, Koradi. | 0 | - | 0 | 1.3975 | 1.3975 | 0 | 0 | 0 |  |  | 0 | 0
xv | Procurement of Pneumatic Y Type Control Valve (Blow Valve Size 50mm & 80mm) for Fly Ash Evacuation System of 3X660MW Unit KTPS, Koradi. | 0 | - | 0 | 0.029205 | 0.029205 | 0 | 0 | 0 |  |  | 0 | 0
xvi | Procurement of the various spares required for Warman make Ash Slurry Pump Model 10/8 EEM & Over Flow Pump Model 8/6 EXU installed at AHP, 3X660 MW TPS Koradi through Limited Tender. | 0 | - | 0 | 0.20886 | 0.20886 | 0 | 0 | 0 |  |  | 0 | 0
xvii | 0 | 0 | - | 0 | 0.0076261 | 0.032797 | -0.025171 | 0 | 0 |  |  | 0 | -0.025171
xviii | Procurement of Spares of Single Roll Clinker Grinder Ayems Engineers make, Model AE-1005-89-100 at AHP, 3X660 MW Koradi TPS. | 0 | - | 0 | 0.82826 | 0.82826 | 0 | 0 | 0 |  |  | 0 | 0
xix | Procurement of Hydraulic Motor for Bucket Wheel of Stacker Reclaimer in CHP, 3X660MW, KTPS, Koradi. | 0 | - | 0 | 1.1168 | 1.1168 | 0 | 0 | 0 |  |  | 0 | 0
xx | Procurement of Rotors, Maintenance Kits, Couplings and other spares required for Atlas Copco make Instrument Air Compressor of Ash Handling Plant of 3 X 660 MW Units at KTPS, Koradi. | 0 | - | 0 | 1.1828 | 1.1828 | 0 | 0 | 0 |  |  | 0 | 0
xxi | Procurement of spares of intermediate conveyor | 0 | - | 0 | 0 | 0.3186 | -0.3186 | 0 | 0 |  |  | 0 | -0.3186
xxii | Procurement of Hydraulic motor for wagon tippler drive in CHP, 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.46494 | 0.46494 | 0 | 0 | 0 |  |  | 0 | 0
xxiii | Procurement of GEHO Pump (Model No. TZPM 400) Spares of Ash Handling Plant, 3 X 660 MW Units, KTPS, Koradi. | 0 | - | 0 | 0 | 0.83656 | -0.83656 | 0 | 0 |  |  | 0 | -0.83656
xxiv | Procurement of Beater Arms for Impact crushers installed at in Coal Handling Plant of 3x660 MW at KTPS, Koradi. | 0 | - | 0 | 0 | 1.0093 | -1.0093 | 0 | 0 |  |  | 0 | -1.0093
xxv | Supply of Atlas Copco make compressor spares for at Koradi TPS 660MW | 0 | - | 0 | 0 | 0.39813 | -0.39813 | 0 | 0 |  |  | 0 | -0.39813
xxvi | Procurement of spares for side arm charger, wagon tippler, impact crushers and stacker reclaimer at CHP 3x660 MW KTPS | 0 | - | 0 | 0.010573 | 0.43684 | -0.42626 | 0 | 0 |  |  | 0 | -0.42626
xxvii | Procurement of Beater heads with Pin for Impact crushers installed at in Coal Handling Plant of 3x660 MW at KTPS, Koradi. | 0 | - | 0 | 0 | 1.1256 | -1.1256 | 0 | 0 |  |  | 0 | -1.1256
xxviii | Procurement of spares of Hyd Motor of SAC | 0 | - | 0 | 0 | 0.36029 | -0.36029 | 0 | 0 |  |  | 0 | -0.36029
xxix | Procurement of hydraulic power packs for Flap Gates in CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0.1888 | -0.1888 | 0 | 0 |  |  | 0 | -0.1888
xxx | Procurement of Mobile Grilling Equipment for CHP 3x660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0.33866 | -0.33866 | 0 | 0 |  |  | 0 | -0.33866
xxxi | Procurement of Weld overlay Flap Gate assembly in CHP 3x660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0.5841 | -0.5841 | 0 | 0 |  |  | 0 | -0.5841
E6 | Capital Spares | 0 | - | 89.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of critical insurance spares for Turbine & its critical auxiliaries for 3 x 660 MW, Koradi (4370001538 dtd. 18/06/2018 d.p. 21 Months) | 0 | - | 89.62 | 89.6234 | 88.736 | 0.88736 | 0 | 0 |  |  | 0 | 0.88736
E7 | Additional Capitalization | 0 | - | 57.88 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Contruction of various infrastructure such as roads etc and public amenities in the rehabilitated villages of koradi and khasara | 0 | - | 13.1 | 12.74 | 0 | 12.74 | 0 | 0 |  |  | 0 | 12.74
ii | Procurement of 7 nos of school buses | 0 | - | 2 | 1.3109 | 1.3109 | 0 | 0 | 0 |  |  | 0 | 0
iii | Development of green belt & fodder farm for fulfillment of environmental clearance of MoEF for Koradi 3x660MW | 0 | - | 3.16 | 3.16 | 0 | 3.16 | 0 | 0 |  |  | 0 | 3.16
iv | Provision of Ground Hopper & Short Conveyor Belt from Existing Stackyard 1 & 2 ti existing Main Stream i.e. BCN 4A/4B of CHP 3x660 MW, KTPS, Koradi | 0 | - | 4.36 | 4.3555 | 4.3555 | 0 | 0 | 0 |  |  | 0 | 0
v | Provision of Ground Hopper & Conveyor Belt for Conveying Unloaded Coal form Open Wagon Tippler in CHP of Koradi Unit 8, 9 & 10. | 0 | - | 4.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
vi | Provision of Additional Facility for Manual Unloading Track in CHP of Koradi Unit No. 8, 9 & 10 | 0 | - | 5.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
vii | Construction of drains | 0 | - | 4.31 | 2.7927 | 0 | 2.7927 | 0 | 0 |  |  | 0 | 2.7927
viii | Supply erection commissioning of medium voltage variable frequency drive for conveyors BCN 6A,6B,7A,7B in CHP 3x660MW | 0 | - | 17 | 16.9859 | 16.9859 | 0 | 0 | 0 |  |  | 0 | 0
ix | Supply, Installation & commissioning of 3D level sensors for first two ESP field hoppers | 0 | - | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
F | Koradi TPS 3x660 MW Expansion Project – Construction of 2nd raising of existing Khasara Ash Bund from T.B.L. 308.50 M to T.B.L 312.00 M with construction of concrete dam (Broad crest weir structure), approach to drain wells and raising height of drain well No. 1, 2 & 3, construction of ash Compartment, cleaning of Khasara bund Nallah and construction of peripheral roads connecting to nearby villages for Khasara ash bund at TPS Koradi | 0 | - | 86.914 | 88.683 | 93.291 | -4.608 | 0 | 0 |  |  | 0 | -4.608
G | Discharge of UDL | 0 | - | 0 | 111.97 | 111.48 | 0.49 | 0 | 0 |  |  | 0 | 0.49
H | Asset Addition due to change in classification of inventory | 0 | - | 0 | 21.7503 | 0 | 21.7503 | 0 | 0 |  |  | 0 | 21.7503
I | Medical Oxygen Gr&Cyl Ozonization Plant (Covid Related Work) | 0 | - | 0 | 11.4034 | 9.6702 | 1.7332 | 0 | 0 |  |  | 0 | 1.7332
0 | B) DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (i) Submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Flue Gas Desulphurization FGD is for Unit 8, 9, 10 of 3x660MW Koradi TPS | MERC/CAPEX/FY 2020-21/WFH/SBR/05 | 2020-05-31 | 940 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Flue Gas Desulphurization is for Unit 8, 9, 10 of 3x660MW Koradi TPS | MERC/CAPEX/FY 2020-21/WFH/SBR/05 | 2020-05-31 | 847.78 | 0 | 0 | 0 | 233.42 | 233.42 |  |  | 233.42 |  | 233.42 | 0
0 | IDC | MERC/CAPEX/FY 2020-21/WFH/SBR/05 | 2020-05-31 | 92.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13 | Construction of new admin building at Vidyut Bhavan, Katol Road, Nagpur | MERC/Capex/2021-2022/MSPGCL/063 | 2022-02-18 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13.1 | Construction of new admin building at Vidyut Bhavan, Katol Road, Nagpur | 0 | 2022-02-18 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | 2022-02-18 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Improvement in Regenerative Air Pre-heater Performance at Unit # 9 of 3x660 MW, Koradi TPS | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 15.869 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Procurement of heating elements for RAPH installed in Unit 9 (660MW) at KTPS Koradi THROUGH LIMITED TENDER | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 15.33 | 11.8 | 11.8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.2 | Replacement of heating elements for RAPH installed in Unit 9 (660MW) at KTPS Koradi | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 0.349 | 0.37 | 0.37 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 0.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | CHP Improvement (7 Nos) Schemes & Procurement of Bulldozers, Wheel Loaders and Hydraulic Cranes at CHP 3X660MW, KTPS, Koradi | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 38.87 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Sch-1: Revamping of Apron Feeder in CHP at 3X660MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.68 | 0 | 0 | 0 | 4.68 | 4.68 |  |  | 4.68 | 0 | 4.68 | 0
19.2 | Sch-2: Procurement of Hydraulic motors and pumps in CHP at 3X660 MW, KTPS, Koradi | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.44 | 0 | 0 | 0 | 4.44 | 4.44 |  |  | 4.44 | 0 | 4.44 | 0
19.3 | Sch-3: Capacity enhancement of Hydraulic motor of Apron Feeder in CHP, 3X660 MW, KTPS, Koradi | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 2.01 | 0 | 0 | 0 | 2.01 | 2.01 |  |  | 2.01 | 0 | 2.01 | 0
19.4 | Sch-4: Modification, supply and replacement of Transfer chutes in CHP 3x660MW KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.39 | 0 | 0 | 0 | 4.39 | 4.39 |  |  | 4.39 | 0 | 4.39 | 0
19.5 | Sch-5: Design, supply, installation & commissioning of High performance IGUS energy chain system with chain flex cable for Tripper trolleys at CHP at 3x660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.37 | 0 | 0 | 0 | 4.37 | 4.37 |  |  | 4.37 | 0 | 4.37 | 0
19.6 | Sch-6: Procurement of B3-630 gear box for BCN 6 A/B in CHP at 3x660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 0.57 | 0 | 0 | 0 | 0.57 | 0.57 |  |  | 0.57 | 0 | 0.57 | 0
19.7 | Sch-7: Supply and installation of Belt tear detector system for conveyor belt in CHP 3x660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 1.18 | 0 | 0 | 0 | 1.18 | 1.18 |  |  | 1.18 | 0 | 1.18 | 0
19.8 | Sch-8: Procurement of 5 Nos of Bulldozers BD 155 at CHP 3X660 MW Koradi Thermal Power station. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 12.83 | 0 | 0 | 0 | 12.83 | 12.83 |  |  | 12.83 | 0 | 12.83 | 0
19.9 | Sch-9:- Procurement of 02 nos. of Wheel loaders at CHP 3X660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 3.07 | 0 | 0 | 0 | 3.07 | 3.07 |  |  | 3.07 | 0 | 3.07 | 0
19.1 | Sch-10:- Procurement of 15 Ton & 20 Ton capacity hydraulic Cranes at CHP 3X660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 0.69 | 0 | 0 | 0 | 0.69 | 0.69 |  |  | 0.69 | 0 | 0.69 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 0.64 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Construction of bridge cum bandhara across Pond No. 3 and allied works at Pond No. 3 at Koradi TPS | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 33.116 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Construction of cement concrete bridge cum bandhara alongwith gated arrangement. | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 14.75 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0 | 5 | 0
20.2 | Construction of earthen embankment connecting bridge cum bandhara on both side of embankment by excavating soil / typha / silt from Pond No.3 & tree plantation. | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 14.3252 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0 | 5 | 0
20.3 | Providing structural steel pathway on the existing waste weir (west side of the Pond No.3) and roads connecting to bridge behind Pond No.3 and bridge cum bandhara. | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 2.4308 | 0 | 0 | 0 | 2.43 | 2.43 |  |  | 2.43 | 0
0 | IDC | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 1.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement & replacement of Superheater Pass Economizer Coils (Modified Design) for Unit 8, 9 & 10 at 3x660MW KTPS, Koradi | Not Approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Procurement & replacement of Superheater Pass Economizer Coils (Modified Design) for Unit 8, 9 & 10 at 3x660MW KTPS, Koradi | Not Approved | - | 0 | 0 | 0 | 0 | 48.14 | 48.14 |  |  | 48.14 | 0
0 | IDC | Not Approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Improvement in Boiler Performance at U-8,9 & 10 KTPS, Koradi | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 62.929 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Scheme-1: Procurement of Blade Sets for ID, FD & PA Fans at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 11.34 | 0 | 0 | 0 | 11.34 | 11.34 |  |  | 11.34 | 0
7.2 | Scheme-2: Procurement of RAPH Bottom Support Bearing Assembly at 3X660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 2.478 | 0 | 0 | 0 | 2.478 | 2.478 |  |  | 2.478 | 0
7.3 | Scheme-3: Procurement of RAPH Top Guide Bearing Assembly at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 0.684 | 0 | 0 | 0 | 0.684 | 0.684 |  |  | 0.684 | 0
7.4 | Scheme-4: Procurement of RAPH Gear Box at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 3.44 | 0 | 0 | 0 | 3.44 | 3.44 |  |  | 3.44 | 0
7.5 | Scheme-5: Procurement of RAPH Spares at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 1.13 | 0 | 0 | 0 | 1.13 | 1.13 |  |  | 1.13 | 0
7.6 | Scheme-6: Procurement of Coal Burner Assembly with windbox air nozzles for Unit 8 & 9 at 3x660MW. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 15.407 | 0 | 0 | 0 | 15.407 | 15.407 |  |  | 15.407 | 0
7.7 | Scheme-7: Procurement of Boiler Circulation Pump (BCP) with Impeller & Diffuser at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 11.12 | 0 | 0 | 0 | 11.12 | 11.12 |  |  | 11.12 | 0
7.8 | Scheme-8: Procurement and Replacement of Heating Elements for RAPH Installed for Unit 8 at 3x660MW. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 15.96 | 0 | 0 | 0 | 15.96 | 15.96 |  |  | 15.96 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 1.37 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Design, Engineering, Supply, Installation, Testing, Commissioning including all civil works for Natural resource treatment and Laboratory equipment with mandatory spares at Koradi TPS, 3 X 660 MW | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 49.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.1 | Supply of Natural resource treatment and lab equipment for Water, Coal, Oil, Meteorology with supporting AI computing, all auxiliaries, and accessories. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 35.28 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.2 | Supply of Mandatory spares on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.3 | Supply of Tools and Tackles on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.4 | Complete Civil Work with 10 KLD ETP/ STP on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 3.6 | 0 | 0 | 0 | 4.25 | 4.25 |  |  | 4.25 | 0
23.5 | Services - Charges of Inland transport of plant and equipment on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.6 | Charges for Testing, Commissioning and PG Test of plant and equipment. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Improvement in Regenerative Air Preheater Performance & Complete Replacement of NDCT fills at Unit # 10, Koradi TPS | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 25.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.1 | Procurement of heating elements for RAPH installed in Unit 10 (660MW) at KTPS Koradi through OEM | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 12.23 | 14.521 | 14.521 | 0 | 0 | 0 |  |  | 0 | 0
24.2 | Complete Supply & Replacement of NDCT fills of U#10. | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 13 | 0 | 0 | 0 | 13 | 13 |  |  | 13 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 0.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 14 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 14.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 15 | HMI (Human Machine Interface) Upgradation of ‘SSPA-T3000’ DCS (Distribution Control System), Rockwell make PLC System installed at 3x660MW Unit No. 8, 9 & 10 at Koradi TPS and HMI (Human Machine Interface) Upgradation of MaxDNA DCS System at Unit 8-9, CSTPS, Chandrapur | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 55.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 15.1 | Supply: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 10.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 15.2 | Works: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | HMI (Human Machine Interface) Upgradation of ‘SPPA-T3000’ DCS (Distributed Control System) installed at 3x660MW Unit- 8, 9 & 10 at Koradi TPS to match with the external aspects and process improvement | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 24.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Upgradation of Rockwell Make PLC System installed at 3x660MW ,Koradi TPS to match with the external aspects and process improvement.(C&I) | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 20.2 | 0 | 0 | 0 | 20.2 | 20.2 |  |  | 20.2 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Work of provision of platform beside railway siding at backside of chord cabin for loading of fly ash in railway wagon for ash utilization at 3x660 MW TPS, Koradi | 0 | - | 0 | 0.0038356 | 0.0038356 | 0 | 0 | 0 |  |  | 0 | 0
13 | Capital Exenditure schemes for in-principle clearance regarding "EPC contract for the wok of construction of quarters and development of KTPS colony at Koradi" under CAPEX scheme | MERC/CAPEX/MSPGCL/2024-12/0569 DTD.13.09.2024 | 2024-09-13 | 210.48 | 0 | 0 | 0 | 50 | 50 |  |  | 50 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of spares for L&T-MHI make Turbine for COH work of Turbine at KTPS, 3x660MW units Koradi | MERC/CAPEX/MSPGCL/2023-24/0639 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement of spares for L&T-MHI make Turbine for COH work of Turbine at KTPS, 3x660MW units Koradi | MERC/CAPEX/MSPGCL/2023-24/0639 | - | 0 | 0 | 0 | 0 | 31.6358 | 31.6358 |  |  | 31.6358 | 0
3.2 | Procurement of HP Nozzle assembly for L&T-MHI Make Turbine installed at 3x660MW Units Koradi | MERC/CAPEX/MSPGCL/2023-24/0639 | - | 0 | 0 | 0 | 0 | 4.189 | 4.189 |  |  | 4.189 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | C) DPRs Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Control & instrumentation related Various Upgradation schemes viz.Emission Monitoring & Water Quality Analysers ,Vibration Monitoring Schemes,Water Flow Monitoring etc. at 3X660MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Upgradation of Emission Monitoring Analysers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Upgradation of Water Quality Analysers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Revamping & Supply Of Upgraded VM7B Version of Vibration Monitoring Rack | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.4 | Implementation of ‘Flow Monitoring System’ at 3x660MW Balance of Plant (BOP) Unit- 8, 9 & 10 at Koradi TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | CHP Improvement Scheme-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Supply, Erection, Commissioning of set of Internals for Wagon Tipplers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Supply, Erection, Commissioning of set of Internals for Side Arm Chargers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Supply, Erection, Commissioning of set of Internals for Wobbler Feeders at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.4 | Supply, Erection, Commissioning of set of Internals for Apron Feeders at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.5 | Supply, Erection, Commissioning of set of Internals for Impact Crushers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.6 | Supply, Erection, Commissioning of set of Internals for Stacker cum Reclaimers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Performance improvement and availability of various Auxiliaries of TG at 3x660MW KTPS Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Performance improvement and availability of various Auxiliaries for Oil Systems of Main Turbine. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.2 | Performance improvement and availability of various Auxiliaries of Generator System. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.3 | Performance improvement and availability of Feed Water System. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.4 | Performance improvement and availability of Vacuum System. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.5 | Performance improvement and availability of CEP System. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.6 | Procurement of Complete Pull out Assembly along with Impeller and wear ring of Cooling Water Pump. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.7 | Procurement of complete assembly of HP and LP Elements for Atlas Copco make Compressors. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Improvement in Wet ash evacuation system at 3x660MW Units, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Procurement & installation of Ash Slurry Series Pump Assembly with modified metallurgy and Critical Wet End Sub Assembly to enhance the performance & slurry disposal capacity. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.2 | Procurement & installation of Ash Slurry Series Pump Assembly with modified metallurgy along with Gear Box, Fluid Coupling & Motor (4’th Series) and Critical Wet End Sub Assembly to enhance the performance & slurry disposal capacity. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.3 | Procurement & installation of Overflow Transfer Pump Assembly with upgradation in metallurgy and Critical Wet End Sub Assembly to enhance the performance. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.4 | Procurement & installation of IAC Compressor Assembly: Model –ZR110 STD 7.5 IMD Atlas Copco Make Oil free water cooled screw air compressor with inbuilt atlas copco make heat of compression single drum rotator air dryer to enhance the performance. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | HMI Upgradation of Diasys Netmation DCS at 3x660MW KTPS Koradi Units 8,9 & 9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | HMI Upgradation of Diasys Netmation DCS at 3x660MW KTPS Koradi Units 8,9 & 10 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Improvement in Dry ash evacuation system at 3x660MW Units, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Procurement of Ingersoll Rand Make Transport Air Compressors Critical/Non-Critical Spares sub-assembly for performance improvement. | 0 | - | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
8 | MSERW Pipes for Garlanding arrangement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.1 | Work of Garlanding arrangement to changeover ash slurry feed points for even filling of pond by providing MSERW Pipes along the periphery of Ash Bund Dyke Wall at Khasara Ash Bund. | 0 | - | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
9 | Capacity Enhancement & Performance optimization at WTP 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.1 | Capacity enhancement of DM water stream in WTP at 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.2 | Capacity enhancement Condensate polishing unit regeneration area in WTP at 3X660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.3 | Provision of Ozone generating plant of 1.0 Kg capacity in WTP at 3X660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | DPR for Construction of CC Road alongwith RCC Drain, CC platform for heavy machinery movement at 3x660 MW, TPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.1 | DPR for Construction of CC Road alongwith RCC Drain, CC platform for heavy machinery movement at 3x660 MW, TPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Improvement in Coal Mill Performance-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.1 | Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi through OEM. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.2 | Procurement of Mill Rotary Separator Blades for coal mill MVM 32R at 3x660 MW, KTPS, Koradi through open tender | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.3 | Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi through OEM. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.4 | Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi through OEM | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Improvement in Boiler performance-II at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.1 | Scheme1:Procurement of Coal compartment assembly for Unit8 at 3x660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.2 | Scheme2:Procurement of blade sets for ID, FD & PA Fan at 3x660 MW, Units at KTPS Koradi through OEM. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.3 | Scheme3:Procurement of RAPH internal Spares for 3X660MW units at KTPS Koradi through OEM (Qty- 6 Sets) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.4 | Scheme4:Procurement of RAPH Sector plate with Actuating mechanism assembly for Unit9 3 X 660MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | Improvement in Coal Mill performance-II at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | Procurement of FLENDER make Gearbox model kmp-450 along with motor for coal mill MVM32R at 3x660mw KTPS, koradi through OEM. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.2 | Procurement of complete set of couplings for PA, ID & FD fans at 3X660MW units at KTPS Koradi through OEM | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Improvement in Coal Mill performance-III at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit10 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.5 | Scheme5:Procurement of Complete MRHS System along with Pneumatic Compressors at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | Improvement in Boiler performance-III at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | Scheme1:Procurement of Coal compartment assembly for Unit8at 3x660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Scheme2:Procurement of blade sets for ID, FD & PA Fan at 3x660 MW, Units at KTPS Koradi through OEM. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Scheme3:Procurement and replacement of heating elements for RAPH installed in Unit 9 (660MW) at KTPS Koradi THROUGH OEM/OES (Qty- 2 Sets) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Scheme4:Procurement of HP valves, safety valves and ERV's for 3X660MW units at KTPS Koradi through OEM | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.5 | Scheme5:Procurement of RAPH Sector plate with Actuating mechanism assembly for Unit8 3 X 660MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | Improvement in Coal Mill performance-IV at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit8 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | Improvement in Coal Mill performance-V at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit9 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | Improvement in Boiler performance-IV at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.1 | Scheme1:Procurement of Coal compartment assembly for Unit8 at 3x660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.2 | Scheme2:Procurement of blade sets for ID, FD & PA Fan at 3x660 MW, Units at KTPS Koradi through OEM. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.3 | Scheme3:Procurement of RAPH bottom support bearing assembly for 3X660MW units at KTPS Koradi through OEM (Qty- 2 Sets) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.4 | Scheme4:Procurement of RAPH top guide bearing assembly for 3X660MW units at KTPS Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.5 | Scheme5:Procurement of RAPH Gear Box for 3X660MW units at KTPS Koradi through OEM (Qty- 1 Sets) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.6 | Scheme6:Procurement of RAPH Sector plate with Actuating mechanism assembly for Unit10 at 3 X 660MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.7 | Scheme7:Procurement and replacement of heating elements for RAPH installed in Unit 10 (660MW) at KTPS Koradi THROUGH OEM/OES (Qty- 2 Sets) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.8 | Scheme8:Procurement of Boiler Circulating Pump (1 Nos) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | Improvement in Coal Mill performance-VI at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit9 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.3 | Reliability Improvement schemes of generators at 3X660MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | Scheme No. 1 :PROCUREMENT OF MELCO/LMTG MAKE GENERATOR ROTOR ASSEMBLY with excitation transformer AT 3X660MW KTPS, KORADI THROUGH OEM | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.2 | Scheme No. 2:PROCUREMENT OF ONE COMPLETE SET OF GENERATOR STATOR COILS FOR GENERATOR AT 3X660MW UNITS AT KTPS KORADI THROUGH OEM | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | DPR on Procurement of Critical Speares for L&T make Main Turbine(typeTC4F-30) installed at 3x660MW KTPS Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.1 | Scheme No. 1 :Procurement of Critical Speares for L&T make Main Turbine(typeTC4F-30) installed at 3x660MW KTPS Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | DPR for Coal Handling Plant Performance Improvement Schemes -II at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.1 | Scheme No. 1 : Performance Improvement of Unloading System Wagon Tipplers at CHP 3x660MW KTPS Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.2 | Scheme No. 2 : Performance Improvement of Unloading System Side Arm Chargers at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Side Arm Charger Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.3 | Scheme No. 3 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.4 | Scheme No. 4 : Performance Improvement of Stacking & Reclaiming System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Stacking & Reclaiming System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.5 | Scheme No. 5 : Performance Improvement of Crushing System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Impact Crusher & Wobbler Feeders Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.6 | Scheme No. 6 : Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -1 at CHP 3x660MW KTPS Koradi A) Brief scope of work: Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -1 at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | DPR for Coal Handling Plant Performance Improvement Schemes -III at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.1 | Scheme No. 1 : Performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Hydraulic system for Wagon Tippler, Side Arm Charger , Apron Feeder ( 1 & 2) Stacker Reclaimer 1 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.2 | Scheme No. 2 : Construction of Air tight Hydraulic power pack room along with necessary cooling system for performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Construction of Air tight Hydraulic power pack room along with necessary cooling system for Wagon Tippler & Apron Feeder ( 1 to 4) Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.3 | Scheme No. 3 : Performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory Hydraulic Power Cylinders of Wagon Tippler, Side Arm Charger ( 1 to 4) Stacker Reclaimer 1 & 2 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.4 | Scheme No. 4 : Performance Improvement of Stacker Reclaimer by providing Hydraulic Drive to Boom Conveyor at CHP 3x660MW KTPS Koradi A) Brief scope of work: Hydraulic Drive to Boom Conveyor Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.5 | Scheme No. 5 : Performance Improvement of Illumination system with energy conservation at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Solar High masts along the rail track in railway yard Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.6 | Scheme No. 6 : Design, Supply & Installation of LT VFD Drives for Critical Conveyors at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of LT VFD Drives for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.7 | Scheme No. 7 : Design , supply, Erection & Commissioning of Short Conveyor for Stacking Purpose at CHP 3x660MW KTPS Koradi A) Brief scope of work: Short Conveyor for Stacking Purpose at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.8 | Scheme No. 8 : Capacity Enhancement of BCN-7/5/4/3 /1 AB in CHP 3x660MW KTPS Koradi A) Brief scope of work: Short Conveyor for Stacking Purpose at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.9 | Scheme No. 9 : Design , Engineering & modification along with strengthening of Existing Travel Track structure for Side Arm Charger & Stacker Reclaimer A) Brief scope of work: strengthening of Existing Travel Track structure for Side Arm Charger & Stacker Reclaimer Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.1 | Scheme No. 10 : Design , Engineering & Erection of modified Energy Efficient Ventilation System for Wagon Tippler Complex Area in CHP 3X660MW KTPS Koradi A) Brief scope of work: Energy Efficient Ventilation System for Wagon Tippler Complex Area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.11 | Scheme No. 11 : Design , Engineering & Installtion of Vibration & temprature Monitoring Systems for critical auxiliaries in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Installtion of Vibration & temprature Monitoring Systems for critical auxiliaries Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.12 | Scheme No. 12 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.13 | Scheme No. 13 : Design , Engineering & Provision of Stone Grappling Equipment System for Wagon Tippler 3 &4 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Stone Grappling Equipment System for Wagon Tippler 3 &4 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.14 | Scheme No. 14 : Design , Engineering & Provision of Public Addressing System for Wagon Tippler Complex in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Public Addressing System for Wagon Tippler Complex in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.15 | Scheme No. 15 : Design , Engineering & Provision of Belt Tracking System for Critical Conveyors in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Belt Tracking System for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.16 | Scheme No. 16 : Design , Engineering & Provision of Dust supression System for stacker reclaimer-1 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.17 | Scheme No. 17 : Work of Life Enhancement of wobbler Feeder 1 &2 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28 | DPR for Coal Handling Plant Performance Improvement Schemes -IV at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28.1 | Scheme No.1 : Design , Engineering , Supply & Installation of Modular Transfer chutes for Critical Conveyor System in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of Modular Transfer chutes for Conveyor System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28.2 | Scheme No.2 :Upgradtion of Exsisting Fire Fighting System at Stack yard area in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradtion of Exsisting Fire Fighting System at Stack yard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28.3 | Scheme No.3 : Design , Engineering , Supply & Strengthening of engineering structure of BCN- 7A/B along with track alignment in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Strengthening of engineering structure of BCN- 7A/B Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28.4 | Scheme No.4 : Design , Engineering , Supply & Installation of Mist Cannon Spray System around stackyard area in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of Mist Cannon Spray System at stackyard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28.5 | Scheme No.5 : Design , Engineering , Supply & Installation of EOT cranes at Bunker in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of EOT cranes at Bunker Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29 | DPR for Procurment of various Heavy Vehicles at CHP 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29.1 | Scheme No.1 : Procurment of Heavy Vehicles like dozers, wheel loaders , locomotives, Crane, Hydra , Disel Browser , Jcb & Bobcats etc. in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurment of Heavy Vehicles like dozers, wheel loaders , locomotives etc Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29.2 | Scheme No.2 : Procurment of Auger Machines for coal sampling in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurment of Auger Machines for coal sampling Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29.3 | Scheme No.3 : Procurment of Truck Mounted mist cannon dust supression system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurment of Truck Mounted mist cannon dust supression system in CHP Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30 | DPR for Coal Handling Plant Performance Improvement Schemes -V at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.1 | Scheme No. 1 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.2 | Scheme No. 2 : Performance Improvement of Stacking & Reclaiming / Side Arm Charger System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Energy Chain System of Stacking & Reclaiming System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.3 | Scheme No. 3 : Performance Improvement of unloading System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Energy Chain System of side arm acharger Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.4 | Scheme No. 4 : Upgradation to 100 MT Ton Weighbridge of existing road weighbridge at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of LT VFD Drives for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.5 | Scheme No. 5 : Design , Engineering & Erection of modified Energy Efficient Ventilation System for Crusher House Area in CHP 3X660MW KTPS Koradi A) Brief scope of work: Energy Efficient Ventilation System for Wagon Tippler Complex Area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.6 | Scheme No. 6 : Design , supply & Installation of Cooling Arrangement for Switchgear rooms at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Cooling Arrangement for Switchgear rooms Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.7 | Scheme No. 7 : Design , Engineering & Erection of modified Engineering Structure of Tunnel Conveyor 1A &1 B in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Erection of modified Engineering Structure of Tunnel Conveyor 1A &1 B Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31 | DPR for Coal Handling Plant Performance Improvement Schemes -VI at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.1 | Scheme No. 1 : Performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Wagon Tippler, Side Arm Charger , Apron Feeder ( 3 & 4) Stacker Reclaimer 2 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.2 | Scheme No. 2 : Design Supply & Installation of Wagon Locking system for all four wagon tipplers at CHP 3x660MW KTPS Koradi A) Brief scope of work: Wagon Locking system for all four wagon tipplers Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.3 | Scheme No. 3 : Design, Supply & Installation of upgraded Vibrating Feeders for Stacker Reclaimer at CHP 3x660MW KTPS Koradi A) Brief scope of work: Design, Supply & Installation of upgraded Vibrating Feeders for Stacker Reclaimer Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.4 | Scheme No. 4: Performance Improvement of Stacker Reclaimer by providing Hydraulic Drive to Boom Conveyor at CHP 3x660MW KTPS Koradi A) Brief scope of work: Hydraulic Drive to Boom Conveyor Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.5 | Scheme No. 5 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.6 | Scheme No. 6 : Design , Engineering & Provision of Belt Tracking System for Critical Conveyors in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Belt Tracking System for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.7 | Scheme No. 7 : Design , Engineering & Provision of Dust supression System for stacker reclaimer-1 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.8 | Scheme No. 8 : Work of Life Enhancement of wobbler Feeder 3 &4 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32 | DPR for Coal Handling Plant Performance Improvement Schemes -VII at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.1 | Scheme No.1 : Design , Engineering , Supply & Installation of Modular Transfer chutes for Crusher House Complex & other Critical Conveyor System in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of Modular Transfer chutes for Conveyor System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.2 | Scheme No.2 :Upgradtion of Exsisting Fire Fighting System along the conveyor length in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradtion of Exsisting Fire Fighting System at Stack yard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.3 | Scheme No.3 : Supply , Erection & Installation of Rack & Pinion Elevators at Bunker in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Supply , Erection & Installation of Rack & Pinion Elevators at Bunker in CHP 3X660MW KTPS Koradi. Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.4 | Scheme No.4 :Up Liftment f Exsisting Fire Fighting lines in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradtion of Exsisting Fire Fighting System at Stack yard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.5 | Scheme No.5 : Procurement of HPPE Polymer Roller for Conveyor system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurement of HPPE Polymer Roller for Conveyor system Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.6 | Scheme No.6 : Design , Engineering , Supply & Installation of EOT cranes at Wagon Tippler Complex in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of EOT cranes at Wagon Tippler Complex Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33 | DPR for Coal Handling Plant Performance Improvement Schemes -VIII at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.1 | Scheme No. 1 : Performance Improvement of Unloading System Wagon Tipplers at CHP 3x660MW KTPS Koradi Estimated Cost : 3.6 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.2 | Scheme No. 2 : Performance Improvement of Unloading System Side Arm Chargers at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Side Arm Charger Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.3 | Scheme No. 3 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.4 | Scheme No. 4 : Performance Improvement of Stacking & Reclaiming System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Stacking & Reclaiming System -2 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.5 | Scheme No. 5 : Performance Improvement of Crushing System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Impact Crusher & Wobbler Feeders Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.6 | Scheme No. 6 : Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -2 at CHP 3x660MW KTPS Koradi A) Brief scope of work: Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -2 at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.7 | Scheme No. 7 : Other Mislenious Schemes at CHP 3x660MW KTPS Koradi A) Brief scope of work: Other Mislenious works Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.8 | Scheme No. 4 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.9 | Scheme No.8: Procurement of HPPE Polymer Roller for Conveyor system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurement of HPPE Polymer Roller for Conveyor system Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34 | DPR for Coal Handling Plant Performance Improvement Schemes -IX at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.1 | Scheme No. 1 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.2 | Scheme No. 2 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.3 | Scheme No.3 : Upgradation of Exsisting Rack & Pinion Elevators at CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradation of Exsisting Rack & Pinion Elevators Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.4 | Scheme No.4 : Procurement of HPPE Polymer Roller for Conveyor system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurement of HPPE Polymer Roller for Conveyor system Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.5 | Scheme No.5 : Other miscellaneous scheme regarding sustainable performance improvement of CHP 3X660MW KTPS Koradi. A) Brief scope of work: ther miscellaneous scheme regarding sustainable performance improvement Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | Design & engineering, procurement, supply, installation & commissioning of Ozone Generator system of capacity 45.0 Kg/hr for CW system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Scheme1:Design & engineering, procurement, supply, installation & commissioning of Ozone Generator system of capacity 45.0 Kg/hr for CW system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36 | Pipeline expansion to improve dry ash evacuation system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.1 | Scheme1: Pipeline expansion to improve dry ash evacuation system along with target box modification and also to erect & commission dry ash evacuation directly to remote silo. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37 | Modification at intermediate silo and HCSD system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.1 | Scheme1: Additional charge pump. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.2 | Scheme 2: Supply & Installation Air washery at silo top. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.3 | Scheme 3: Shed above silo top. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.4 | Scheme 4: Supply & Installation Construction of platform at pipe rack up to Remote silo. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.5 | Scheme 5: Shifting of pipeline above pipe rack. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.6 | Scheme 6: Supply & Installation ART sub assemblies. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38 | ESP field strengthening at U#8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.1 | Scheme1: ESP field strengthening at U#8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
39 | Procurement of various pumps for AHP performance improvement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
39.1 | Scheme1: Procurement of various pumps for AHP performance improvement. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
40 | Modification in Dry Ash Evacuation System D/V Assemblies & allied equipments to improve performance | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
40.1 | Scheme1: Procurement of D/V Assemblies & allied equipments to improve performance. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41 | Additional IAC house for Intermediate silo and Remote silo along with erection of S.S. Pipeline | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.1 | Scheme1: Supply & Installation Additional IAC house for Intermediate silo and Remote silo along with erection of S.S. Pipeline | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42 | Waste water system modification to have zero water discharge | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.1 | Scheme1: Waste water system modification to have zero water discharge at 3x660MW, KTPS, Koradi along with Pump Procurement along with arrangement of sludge discharge at ESP water Washing system. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
43 | ESP field strengthening at U#9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
43.1 | Scheme1: ESP field strengthening at U#9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44 | Procurement of HCSD GEHO Pump (TZPM-400) critical items sub-assemblies | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.1 | Scheme1: Procurement of HCSD GEHO Pump TZPM-400) critical items sub-assemblies. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45 | MSERW Pipes & Seamless Pipes replacement to improve ash conveying & its disposal-1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.1 | Scheme1: Supply & Work of Replacement of MSERW Pipes & Seamless Pipes in Bottom ash/Coarse ash evacuation & Ash Slurry Disposal Pipelines, Dry ash conveying system in phase manner to improve the ash evacuation performance. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46 | Improvement in Ash Water Recovery System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.1 | Scheme1: Supply & Installation of Pumps along with Pipeline for Improvement in Ash Water Recovery System. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47 | Replacement of Instrument air pipeline from M.S. to S.S for AHP main plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.1 | Scheme1: Replacement of Instrument air pipeline from M.S. to S.S for AHP main plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48 | Modification of sludge pumps and its pipeline with pumps of higher capacity and discharge line of higher capacity. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.1 | Scheme1: Modification of sludge pumps and its pipeline with pumps of higher capacity and discharge line of higher capacity. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
49 | ESP field strengthening at U#10 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
49.1 | Scheme1: ESP field strengthening at U#10 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50 | MSERW Pipes & Seamless Pipes replacement to improve ash conveying & its disposal-2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50.1 | Scheme1: Supply & Work of Replacement of MSERW Pipes & Seamless Pipes in Bottom ash/Coarse ash evacuation & Ash Slurry Disposal Pipelines, Dry ash conveying system in phase manner to improve the ash evacuation performance. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
51 | Replacement of IAC for AHP Main Plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
51.1 | Scheme1: Supply & Installation of IAC for AHP Main Plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
52 | Improvement in DRY ASH Evacuation system-2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
52.1 | Scheme1: Supply & Installation of TAC, Replacement of Air Lock Vessel, Various Valves, ESP Hopper Doors, ESP access doors. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
53 | Improvement in DRY ASH Evacuation system-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
53.1 | Scheme1: Procurement of Ingersoll Rand Make Transport Air Compressors Critical/Non-Critical Spares sub-assembly for performance improvement. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
54 | Detailed project report for various works of security section as per the IB recommendations. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
54.1 | Repairing & raising height of compound wall with provision of concertina coil at various location of peripheral compound wall at 3x660MW KTPS Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
54.2 | Work of Providing structural three quarter turn staircase with landing along pheriphery of FISS watch tower at 3x660MW, TPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
55 | Supply, installation, comissioning and testing of 220V station & 360V UPS batteries installed at U 8, 9 & 0 of 3x660 MW KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
55.1 | Supply, installation, comissioning and testing of 220V station & 360V UPS batteries installed at U 8, 9 & 0 of 3x660 MW KTPS, Koradi. (scheme) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
56 | TDBFP Governing valve's LPCV ,HPCV MSV AND Trip lock replacement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
61 | Procurement & replacement of HP Heaters at 3x660 MW KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Vibration Monitoring & Analysis system installed at 3x660MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of sinkawa make vibration monitoring and Analysis system for main turbine at 3x660MW koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of Bently Nevada make vibration monitoring and Analysis system for RMCMS system at 3x660MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3 :-Emerson PLC upgradation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of various Level Transmitters installed at 3x660 MW koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of Guided wave Radar Level TX installed at Condenser Hotwell and LPH 1,2 and 3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of Displacer type level TX into Guided wave radar level Tx installed at various Drain Tank, Flash tank and pit | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3: Upgradation of non- contact type Ultrasonic level Tx into IP68 non- contact type Radar level TX. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of ESP Hopper level Probes installed at 3x660 MW koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of 1st three fields ESP Hopper level probes into continuous level monitoring NOGS system at 3x660 MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of RF capacitance Hopper level probe into of RF admittance level probe at 4,5,6,7,8 & 9 ESP Hoppers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3: Upgradation of ESP hopper heater monitoring , control and real time monitoring system at 3X660MW Koradi TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of various scheme viz ASLD, Furnace tv camera FEGT and acoustic Pyrometer installed at 3x660 MW koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of ASLD system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of Furnace TV Camera | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3:Upgradation of FEGT system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 4:Upgradation of acoustic pyrometer | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of various scheme viz instrument Air pipe at ESP Area, wet Ash Evacuation system, HCSD Silo. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of instrument Air pipeline system at ESP of M.S into SS installed at 3x660 MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of instrument Air pipeline system at wet Ash system of M.S into SS . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3: Upgradation of instrument Air pipeline system at HCSD silo of M.S. into SS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 4: Upgradation of instrument Air pipeline system at Remote Silo of M.S into SS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 5: Upgradation of Control & Instrument section lab with Hydraulic Servo Valve Test, Pneumatic System test and calibration lab set up. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Flame scanner for flexible operation of 3X660MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of Flame scanner for flexible operation of 3X660MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of DRC Pipes, Bends & Fittings in phase manner to improve the dry ash conveying & its disposal (2 years) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of DRC Pipes, Bends & Fittings in phase manner to improve the dry ash conveying & its disposal (2 years) (Rs.30 Cr.) (Bottom ash/Coarse ash evacuation & Ash Slurry Disposal Pipelines, Dry ash conveying system) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Augmentation of Coarse Ash disposal system at U10 at KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | WORK OF INSTALLATION & COMMISSIONING OF ASH DISPOSAL SYSTEM AT UNIT#10 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Railway Track Siding Performance Improvement Schemes at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 1 : Work of complete track renovation of existing Rail yard of CHP, 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. Due to continuous movement of Railway's precious rolling stock, the track spares are worn out and are due for complete replacement. Hence, to maintain rail track parameters in healthy condition as per Railway norms so as to avoid untoward incidences of derailment the execution of work of complete track renewal is essential. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 2 : Scheme Name- Work of laying of additional track at 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. However, as per the existing infrastructure, at present there is no dedicated empty formation line. Due to non-availability of empty formation line, most often unloading gets hampered due to blocking of outhaul line by empty rake. The hampering in unloading affects the plant performance and incurrs unnecessary financial burden on KTPS account under the head of demurrage charges. Hence, to maintain the plant loadability and availability, it is essential to lay additional track at 3x660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 3 : Scheme Name- Work of rectification and upgradtion of existing SSP at CHP, 3x660MW, KTPS, Koradi. Justification- The SSP has been erected at 3x660MW, KTPS, Koradi. However, till date the same has not been commissioned. With lapse of @ 5-6 years after erection and its non commissioning, the existing SSP set up has been completely detoriorated. Now, Railway's is pressing hard for early commissioning of the same. The said set up shall ensure isolation of OHE of existing yard with Railway's main line. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 4 : Scheme Name- Work of construction of apron RCC platforms at inhaul and outhaul of Wagon tipllers 1, 2, 3 & 4 of CHP 3x660MW, KTPS, Koradi. Justification- The 04 Nos. of wagon tipplers are installed at CHP-3x660MW, KTPS, Koradi. In this regards, it is to submit that, the wagon unloading is being carried out through these tipplers. Hence, presence of fugitive dust in tippler area is predominant. The said dust is being accumulated at inhaul and outhaul of wagon tipplers. Due to presence of loaded wagons at inhaul and empty wagons at outhaul, this office gets least opportunity for clearance of the said coal dust along the track. Due to accumulation of coal dust, the rail track parameters along with gradient are getting distubed. The disturbance in gradient is causing rolling of wagons which is not recommended in view of safety of both man and machine. Besides, this due to rolling of wagons, the occurnece of untoward incidence of derailment is predominant. Hence, to maintain uniform rail track gradient it shall be enviable to construct the apron RCC platforms at inhaul and outhaul of Wagon tipplers 1, 2, 3 & 4 of CHP-3x660MW, KTPS, Koradi. Estimated cost- Rs. 4 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 5 : Scheme Name- Work of construction of apron RCC platforms at inhaul and outhaul of Wagon tipllers 1, 2, 3 & 4 of CHP 3x660MW, KTPS, Koradi. Justification- The 04 Nos. of wagon tipplers are installed at CHP-3x660MW, KTPS, Koradi. In this regards, it is to submit that, the wagon unloading is being carried out through these tipplers. Hence, presence of fugitive dust in tippler area is predominant. The said dust is being accumulated at inhaul and outhaul of wagon tipplers. Due to presence of loaded wagons at inhaul and empty wagons at outhaul, this office gets least opportunity for clearance of the said coal dust along the track. Due to accumulation of coal dust, the rail track parameters along with gradient are getting distubed. The disturbance in gradient is causing rolling of wagons which is not recommended in view of safety of both man and machine. Besides, this due to rolling of wagons, the occurnece of untoward incidence of derailment is predominant. Hence, to maintain uniform rail track gradient it shall be enviable to construct the apron RCC platforms at inhaul and outhaul of Wagon tipplers 1, 2, 3 & 4 of CHP-3x660MW, KTPS, Koradi. Estimated cost- Rs. 4 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 6 : Scheme Name- Work of construction of RCC platforms along the rail track of CHP 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. In this regards, it is to submit that, after unloading of rakes the empty rakes are being examined by Railway's C&W staff camped at KTPS, Koradi. Hence, for safe movement of Railway's staff, Railway's is pressing hard for provision of RCC platforms along the rail track of CHP-3x660MW, KTPS, Koradi. Estimated cost- Rs. 10 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 7 : Scheme Name- Work of repairing and construction of RCC permanent revenue canal at, KTPS, Koradi. Justification- The temporary revenue canal is being flowing beside the existing Railway exchange yard of 210 MW, KTPS, Koradi. The said canal gets clogged inview of ash accumulation. Due to clogging this canal overflows and its overrun enters the 210 MW rail yard thereby creating track surface marshy and unsafe for Rail movement. Hence, it is essential to repair and construct RCC permanent revenue canal at KTPS, Koradi so that proper and timely cleaning of canal along with proper outlet can be arranged. Estimated cost- Rs. 15 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme Name-08 Work of construction of RCCretaining wall at Godhani and Kalumna end of KTPS, Koradi. Justification- The separate rail infrastructure has been commissioned for Koradi TPS to cope up the daily coal requirement. The rail traffic at KTPS, Koradi is being catered through Godhani and Kalumna end respectively. In this regards, it is to submit that, the take off points at Godhani and Kalumna both are S&T operated. During monsoon, it is often witnessed that, the rain water enters the plant premises from others land thereby submerging the S&T operated point. Due to this, signals gets lost and hampers the Rail traffic movement completely. Hence, it is essential to restrict the entrance of rain water in plant premises. This can be possible by constructing retaining wall at required loaction. Estimated cost- Rs. 1 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme Name-09 OHE maintenance at CHP, KTPS, Koradi Justification-As per the Railway board circular, Railway's has mandated that OHE maintenance cost for existing as well as new sidings shall be borne by the siding owner in accordance with Railway guidelines. Railway will carry out necessary inspection of maintenance work once in six months. Maintenance charges per TKM per annum of OHE as finalized by SECR zonal office is Rs.291566/- per TKM per annum. Also, inspection charges at the rate of Rs.106974/- per day towards inspection to be carried out by Railways every si x months shall be charged on actual basis by Railway's from the sidings.Accordingly, Railway.s has calimed amount of Rs.31314519/- for two years. Hence for 5 yeards it is expected to be Rs.7.82 Cr. Estimated cost- Rs. 7.82 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 10 Name-Remodelling and upgradation of existing S & T system with Panel Interlocking system and associated S & T gears to S & T system with Electronic Interlocking system and associated S & T gears in connection with services for BG Railway facility (660 MW Rail yard) for Koradi Thermal Power Station of MSPGCL Justification-As per the prevailing Railway norms, it is mandatory to commission the S & T system in private Railway siding for fast and safe movement of Railway’s precious rolling stock. Unless and until remodeling is carried out the S&T system cannot be started at Koradi Railway yard.With commissioning and operation of S & T system there shall be least possibility for derailments during internal shunting through crossovers, as the said points shall be motorized operated. Estimated cost- Rs. 20 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 11 : Work of supply and provision of lights and high mast at CHP Railway exchange yard of 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. In this regards, it is to submit that, after unloading of rakes the empty rakes are being examined by Railway's C&W staff camped at KTPS, Koradi on round the clock basis. Hence, for safe movement of Railway's staff, Railway's is pressing hard for availability of proper illumination in complete yard. Estimated cost- Rs.2.5 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Provision of cover shed for stack yard -2 at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 1 : Provision of cover shed for stack yard -2 at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Procurement of Pipe Conveyor Drive System Internals at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 1 : Procurement of Pipe Conveyor Drive System Internals at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Provision of service building along with vehicle bay at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 1 : Provision of service building along with vehicle bay at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | GENERAL ASSET | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | GENERAL ASSET--AKRDFOGA01-OFFICE FURNITURE | N.A. | - | 0 | 0.42299 | 0.60759 | -0.1846 | 0.15 | 0.15 |  |  | 0.15 | -0.1846
2 | GENERAL ASSET--AKRDFOGA02-COMPUTERS,PRINTER,SCANNER | N.A. | - | 0 | 1.4604 | 2.721 | -1.2606 | 0.19 | 0.19 |  |  | 0.19 | -1.2606
3 | GENERAL ASSET--AKRDFOGA03-AC,WATER COOLER | N.A. | - | 0 | 0.29584 | 0.32898 | -0.033135 | 0.17 | 0.17 |  |  | 0.17 | -0.033135
4 | GENERAL ASSET--AKRDFOGA04-AIR PURIFIER | N.A. | - | 0 | 0 | 0.0105 | -0.0105 | 0 | 0 |  |  | 0 | -0.0105
0 | D) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of KLEP Unit for 'HCSD Pump | 0 | - | 3.73 | 3.73 | 3.73 | 0 | 0 | 0 |  |  | 0 | 0
2 | Restoration of Boiler Circulation Pump at 3X660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 4.73 | 4.73 |  |  | 4.73 | 0
3 | Procurement of Coal Compartment Assemblies for Unit-10 at 3x660MW KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 3.73 | 3.73 |  |  | 3.73 | 0
4 | Repairing and Refurbishment of TDBFP cartridge Model FK6E40 installed at 3X660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 11.86 | 11.86 |  |  | 11.86 | 0
5 | Non-DPR for Upgradation of Honeywell Make PLC for Mill Reject Handling System installed at 3x660MW Balance of Plant (BOP) Unit- 8, 9 & 10 at Koradi TPS | 0 | - | 0 | 0 | 0 | 0 | 0.85 | 0.85 |  |  | 0.85 | 0
6 | Procurement of Sky Climber for furnace repairing at 3x660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 3.02 | 3.02 |  |  | 3.02 | 0
7 | Double Roll Clinker Grinder | 0 | - | 0 | 0 | 0 | 0 | 1.68 | 1.68 |  |  | 1.68 | 0
8 | Procurement along with Installation of Clear Water Booster Pump with Motor, Panel Cable and other allied accessories in Unit#10 bottom ash area at AHP, 3x660MW, KTPS, Koradi. | N.A. | - | 0 | 0.25116 | 0 | 0.25116 | 2.56 | 2.56 |  |  | 2.56 | 0.25116
9 | Procurement of single Roll Clinker Grinder with Feed Pump & Jet Pump Complete Assembly with modified metallurgy installed at AHP ,3x660MW Units, KTPs, Koradi | N.A. | - | 0 | 1.1668 | 0 | 1.1668 | 2.12 | 2.12 |  |  | 2.12 | 1.1668
10 | Work of Repairing and Refurbishment of HIP Rotor along with balancing and over speed trial for L&T-MHI make turbine (Type: TC4F-30”) installed at 3X660MW KTPS, Koradi | N.A. | - | 0 | 0.22316 | 0 | 0.22316 | 7.13 | 7.13 |  |  | 7.13 | 0.22316
11 | Procurement of spares for Flue gas distribution dampers, PA fan discharge dampers and Coal mill Hot PA Gate and Dampers at 3x660mw KTPS units through OEM | N.A. | - | 0 | 0 | 0 | 0 | 3.7 | 3.7 |  |  | 3.7 | 0
12 | Work of Modification & Installation of Take up trolley & arrangement for take up lifting for conveyor BCN-13A at CHP 3X660MW,KTPS,Koradi | N.A. | - | 0 | 355.8831 | 0 | 355.8831 | 0.75 | 0.75 |  |  | 0.75 | 355.8831
13 | Work of Design, Modification & streingthening of Tripper trolley structure with provision of Antiwear plates discharge chute box at CHP 3X660MW,KTPS,Koradi | N.A. | - | 0 | 0 | 0 | 0 | 1.16 | 1.16 |  |  | 1.16 | 0
14 | Upgradation of Management Information System (MIS) Server and Associated Software for C&I at 3x660MW Unit- 8, 9 & 10 at Koradi TPS | N.A. | - | 0 | 0 | 0 | 0 | 2.145 | 2.145 |  |  | 2.145 | 0
15 | Procurement of Vibrating Tranfer chute with double exciter Drive for stacker reclaimer at CHP,3X660MW,KTPS ,Koradi | N.A. | - | 0 | 0 | 0 | 0 | 0.934 | 0.934 |  |  | 0.934 | 0
16 | Supply & Installation of Ash Slurry Density Transmitter at High Concentrated Slurry Disposal (HCSD) System of BOP area of 3x660MW Unit- 8, 9 & 10 at Koradi TPS | N.A. | - | 0 | 0 | 0 | 0 | 1.26 | 1.26 |  |  | 1.26 | 0
17 | Supply & Installation of Fiber Optic Sensing System for Conveyor Health Monitoring At CHP 3x660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | Procurement of Leak- proof make complete Mechanical Seal Assembly for Concrete Volute CW Pump installed at 3X660MW KTPS,Koradi on OEM bASIS. | 0 | - | 0 | 0 | 0 | 0 | 1.94 | 1.94 |  |  | 1.94 | 0
19 | Work of Design , Engineering , Manufacturing , Supply Erection & Commissioning of Conveyor Belt From Discharge of RBF 1 &2 at Crusher House to Stack Yard At CHP 3x660MW KTPS, Koradi . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20 | Supply & Installation of Artificial Intelligence PMMS Accurex Diagnostic matrix based vibration & temperature monitoring for critical auxiliaries at CHP 3x660MW KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Restoration of online dissolved gas analysers of Unit 8,9,10 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | Complete Replacement of Existing Water Separator Drain Tank Control (WDC) Valves with New Valves of modified trim design along with hydraulic Actuators, Power Pack assembly, necessary instrumentation, erection & commissioning 3X660MW KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Procurement of mandatory set of Hydraulic system internals for Wagon Tippler Drive & side arm charger Drive at CHP,3X660MW,KTPS ,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | "Supply & installation of Anodized winding Oil cooled over band magnetic separator & control panel for conveyor 5A,5B &13C at CHP 3x660MW KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 1.896 | 1.896 |  |  | 1.896 | 0
25 | Procurement of Grinding Wall Assembly for Impact Crusher At CHP 3x660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 2.01 | 2.01 |  |  | 2.01 | 0
26 | Restoration of Boiler Circulation Pump of U10 at 3X660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | Design,Engineering,Customization,Implementation,Installation & testing of Data Analytical/Artificial Intellegence softwae for automated monitoring & diagnostics system to improve Power plant reliability & efficiency,at one unit of 3X660MW KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 3.27 | 3.27 |  |  | 3.27 | 0
28 | Supply of Feed Gate Complete Assembly along with installation to enhance the performance of Feed Gate at Ash Handling Plant, 3x660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29 | Design, Supply, Installation & Commissioning of Instrument Air Dryer Assembly with Prefilters & Stainless steel piping along with valves suitable for Instrument Air Compressors at AHP, 3x660MW Units, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 1109.2275 | 794.8398 | 314.3877 | 574.3088 | 574.3088 | 0 | 0 | 574.3088 | 314.3877
FY 2025-26
0 | A) Approved Add cap: | 0 | - | 0 | 0
A | BoP | 0 | - | 246.34 | 103.6804 | 232.6929 | -129.0125 | 0 | 0 |  |  | 0 | -129.0125
B | BTG | 0 | - | 44.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B1 | Supply | 0 | - | 13.33 | 0 | 13.33 | -13.33 | 0 | 0 |  |  | 0 | -13.33
B2 | Works | 0 | - | 0.98 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B3 | Taxes and duties | 0 | - | 23.29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B4 | Civil | 0 | - | 0.19 | 0.19 | 0 | 0.19 | 0 | 0 |  |  | 0 | 0.19
B5 | Mandatory Spares | 0 | - | 5.03 | 1.29 | 6.32 | -5.03 | 0 | 0 |  |  | 0 | -5.03
B6 | BTG (L&T) Work | 0 | - | 1.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C | Other Works (Plant) | 0 | - | 136.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C1 | Fully Integrated Security System | 0 | - | 27.36 | 31.4615 | 31.4615 | 0 | 0 | 0 |  |  | 0 | 0
C2 | Administrative Expenses and overhead | 0 | - | 7.25 | 6.69 | 0 | 6.69 | 0 | 0 |  |  | 0 | 6.69
C3 | Contingencies E&M | 0 | - | 0.04 | 0.04 | 0 | 0.04 | 0 | 0 |  |  | 0 | 0.04
C4 | Mobile storage racks, fork lifts, hoists & hydra for material handling in major stores shed | 0 | - | 0.95 | 0.93645 | 0.93645 | 0 | 0 | 0 |  |  | 0 | 0
C5 | Development of working models of Plant Layout, Boiler, Turbine- Generetaor, Coal mill, Fans, etc. at KTC, Koradi. | 0 | - | 1.2 | 1.2 | 0.98604 | 0.21396 | 0 | 0 |  |  | 0 | 0.21396
C6 | Workshop equipment | 0 | - | 0.26 | 0.26192 | 0.26192 | 0 | 0 | 0 |  |  | 0 | 0
C7 | Design, engg, manufacture, supply , erection, testing & commissioning of Ozonization Plant for circulating cooling water system | 0 | - | 54.05 | 31.7683 | 31.6144 | 0.15388 | 0 | 0 |  |  | 0 | 0.15388
C8 | Supply, installation & commissioning of water flow meters including required SCADA software and other accessories for water management system | 0 | - | 5.08 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C9 | Provision of wet ash evacuation system for first two rows of ESP for Unit-8,9 & 19 | 0 | - | 26.59 | 21.69 | 26.3181 | -4.6281 | 0 | 0 |  |  | 0 | -4.6281
C10 | Procurement of portable mercury analyser for flue gas monitoring | 0 | - | 6.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C11 | Administrative Expenses and overhead | 0 | - | 5 | 21.0001 | 0 | 21.0001 | 0 | 0 |  |  | 0 | 21.0001
C12 | Compressor of Hydrogen plant | 0 | - | 1.5 | 1.5 | 0 | 1.5 | 0 | 0 |  |  | 0 | 1.5
C13 | Rail Cum road stone grabbler | 0 | - | 0.85 | 0.85 | 0 | 0.85 | 0 | 0 |  |  | 0 | 0.85
D | Other Works (Civil) | 0 | - | 103.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D1 | Road, Bridges railway system | 0 | - | 20.1 | 0.10806 | 0 | 0.10806 | 0 | 0 |  |  | 0 | 0.10806
0 | S&T System with Panel Interlocking System | 0 | - | 0 | 10.4585 | 10.4596 | -0.0011606 | 0 | 0 |  |  | 0 | -0.0011606
D2 | Staff quarters | 0 | - | 5.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D3 | Other Misc & Unforseen Item | 0 | - | 25.79 | 9.3 | 7.53 | 1.77 | 0 | 0 |  |  | 0 | 1.77
0 | Check Post, Inspection Office & Facility Complex | 0 | - | 0 | 3.6844 | 3.6816 | 0.0028689 | 0 | 0 |  |  | 0 | 0.0028689
0 | CPRI Building | 0 | - | 0 | 6.2046 | 6.2046 | 0 | 0 | 0 |  |  | 0 | 0
0 | Foam cum DCP fire tender- 1 | 0 | - | 0 | 0 | 0.76926 | -0.76926 | 0 | 0 |  |  | 0 | -0.76926
0 | Fire water Bowser-cum-fire Tender- 1No. | 0 | - | 0 | 0.73537 | 0.73537 | 0 | 0 | 0 |  |  | 0 | 0
D4 | Const. facility | 0 | - | 3.28 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D5 | Contigency Other Civil Work | 0 | - | 5.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D6 | Adminstrative Exp. & Overhead (Salary & Overhead, Civil & E&M) | 0 | - | 21.47 | 31.64 | 0 | 31.64 | 0 | 0 |  |  | 0 | 31.64
D7 | Future unforseen works(Jalyukta Shiwar) | 0 | - | 0.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D8 | Landscaping work | 0 | - | 21.76 | 20.53 | 0 | 20.53 | 0 | 0 |  |  | 0 | 20.53
E | Initial Spares | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
E1 | Boiler & its auxilliaries | 0 | - | 14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Procurement of Table liners and Roller liners Of MVM 32R Coal Mills of 3 X 660MW Units at KTPS, Koradi | 0 | - | 0 | 10.0686 | 10.0686 | 0 | 0 | 0 |  |  | 0 | 0
ii | Procurement of couplings for Coal mill MVM 32 R of 3 X 660 MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 1.5944 | -1.5944 | 0 | 0 |  |  | 0 | -1.5944
iii | Procurement of Set of internal spares for Coal Mill Gear Box (KMP-450) for 3 X 660MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 2.2253 | -2.2253 | 0 | 0 |  |  | 0 | -2.2253
E2 | Turbine & its auxilliaries | 0 | - | 18.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | ULTRAFILTRATION MEMBRANE | 0 | - | 0 | 1.6511 | 1.6511 | 0 | 0 | 0 |  |  | 0 | 0
ii | Supply of Main turbine Vibration Monitoring System spares at 3x660MW, KTPS,Koradi. | 0 | - | 0 | 0 | 1.1469 | -1.1469 | 0 | 0 |  |  | 0 | -1.1469
iii | Procurement of Cartridge for Turbine Driven Boiler Feed Pump (Model No.: FK6E40) at 3X660 MW KTPS Koradi | 0 | - | 0 | 14.2864 | 14.2864 | 0 | 0 | 0 |  |  | 0 | 0
iv | Procurement of Critical Insurance Spares for L&T-MHI Make Turbine for attending major overhauling work of Turbine at KTPS, 3x660MW Units Koradi. | 0 | - | 0 | 11.1013 | 11.1013 | 0 | 0 | 0 |  |  | 0 | 0
E3 | Generator & its auxilliaries | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
E4 | Electrical auxilliaries | 0 | - | 1.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Procurement of HT Motors of BOP | 0 | - | 0 | 0 | 0.29335 | -0.29335 | 0 | 0 |  |  | 0 | -0.29335
ii | 0 | 0 | - | 0 | 0 | 0.84594 | -0.84594 | 0 | 0 |  |  | 0 | -0.84594
iii | Supply of Schneider make Differential Protection Relays for 3X660 MW, Koradi (OEM) | 0 | - | 0 | 0 | 0.10502 | -0.10502 | 0 | 0 |  |  | 0 | -0.10502
iv | Supply of Professional Large Format Display for display of DCS parameters PCR | 0 | - | 0 | 0.14885 | 0.14885 | 0 | 0 | 0 |  |  | 0 | 0
v | Procurement of ABT Energy meter with software for 3X660 MW, TPS, Koradi | 0 | - | 0 | 0 | 0.18337 | -0.18337 | 0 | 0 |  |  | 0 | -0.18337
E5 | Outdoor Plant i.e. CHP, AHP, WTP etc | 0 | - | 19.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Procurement of Forced Lubrication system for Premium make Gear box B3-450 installed for bunker conveyor BCN 7A/B at CHP 3X660MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0.15314 | -0.15314 | 0 | 0 |  |  | 0 | -0.15314
ii | Procurement of rotary spares for travel drive of Stacker and conveyor drive system in Coal Handling Plant of 3x660 MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0.35199 | -0.35199 | 0 | 0 |  |  | 0 | -0.35199
iii | Procurement of Complete assembly of Dome Valve ( 100NB, 200NB, 300NB) with power cylinder for dry Ash evacuation system of 3X660MW KTPS, Koradi. | 0 | - | 0 | 0.2225 | 0.2225 | 0 | 0 | 0 |  |  | 0 | 0
iv | Procurement of Modified Apron Pans for M/s. ELECON Engineering Company ltd make Apron Feeder in CHP 3x660MW Units at KTPS, Koradi. | 0 | - | 0 | 3.3233 | 3.3233 | 0 | 0 | 0 |  |  | 0 | 0
v | Procurement of Single Roll Clinker Grinder with Feed Sump and Jet Pump Complete Assembly with Drive, Driven Sprocket and Chain at AHP, 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.56357 | 0.56357 | 0 | 0 | 0 |  |  | 0 | 0
vi | Procurement of spares of Dome Valve (100NB, 200NB, 300NB) for Ash Evacuation System of 3X660MW Unit KTPS, Koradi. | 0 | - | 0 | 0.16431 | 0.16431 | 0 | 0 | 0 |  |  | 0 | 0
vii | 0 | 0 | - | 0 | 0.10064 | 0.10064 | 0 | 0 | 0 |  |  | 0 | 0
viii | 0 | 0 | - | 0 | 0.00708 | 0.00708 | 0 | 0 | 0 |  |  | 0 | 0
ix | Procurement of Hydraulic Motor for Apron feeder in Coal Handling Plant 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.7965 | 0.7965 | 0 | 0 | 0 |  |  | 0 | 0
x | Procurement of Peristaltic Hose Pump (Model no: RP2 – 40) Spares for HCSD System of Ash Handling Plant, 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.20622 | 0.20622 | 0 | 0 | 0 |  |  | 0 | 0
xi | Procurement of spares for HP Water Pump, Mather & Platt make, model 10/12 EME for AHP at 3X660 MW, KTPS, Koradi | 0 | - | 0 | 0.28246 | 0.28246 | 0 | 0 | 0 |  |  | 0 | 0
xii | Procurement of Rotor shaft assembly for M/s. ELECON Engineering Company ltd make Impact Crusher in CHP 3x660MW Units at KTPS, Koradi. | 0 | - | 0 | 0.76369 | 0.76369 | 0 | 0 | 0 |  |  | 0 | 0
xiii | Procurement of Sam Turbo Make Pumps Spare parts for Ash Handling Plant of 3X660 MW Units at KTPS, Koradi | 0 | - | 0 | 0.17166 | 0.17166 | 0 | 0 | 0 |  |  | 0 | 0
xiv | Procurement of Wagon Tippler Spares for M/s. ELECON Engineering Company ltd. make Wagon Tippler in CHP 3X660MW Units at KTPS, Koradi. | 0 | - | 0 | 1.3975 | 1.3975 | 0 | 0 | 0 |  |  | 0 | 0
xv | Procurement of Pneumatic Y Type Control Valve (Blow Valve Size 50mm & 80mm) for Fly Ash Evacuation System of 3X660MW Unit KTPS, Koradi. | 0 | - | 0 | 0.029205 | 0.029205 | 0 | 0 | 0 |  |  | 0 | 0
xvi | Procurement of the various spares required for Warman make Ash Slurry Pump Model 10/8 EEM & Over Flow Pump Model 8/6 EXU installed at AHP, 3X660 MW TPS Koradi through Limited Tender. | 0 | - | 0 | 0.20886 | 0.20886 | 0 | 0 | 0 |  |  | 0 | 0
xvii | 0 | 0 | - | 0 | 0.0076261 | 0.032797 | -0.025171 | 0 | 0 |  |  | 0 | -0.025171
xviii | Procurement of Spares of Single Roll Clinker Grinder Ayems Engineers make, Model AE-1005-89-100 at AHP, 3X660 MW Koradi TPS. | 0 | - | 0 | 0.82826 | 0.82826 | 0 | 0 | 0 |  |  | 0 | 0
xix | Procurement of Hydraulic Motor for Bucket Wheel of Stacker Reclaimer in CHP, 3X660MW, KTPS, Koradi. | 0 | - | 0 | 1.1168 | 1.1168 | 0 | 0 | 0 |  |  | 0 | 0
xx | Procurement of Rotors, Maintenance Kits, Couplings and other spares required for Atlas Copco make Instrument Air Compressor of Ash Handling Plant of 3 X 660 MW Units at KTPS, Koradi. | 0 | - | 0 | 1.1828 | 1.1828 | 0 | 0 | 0 |  |  | 0 | 0
xxi | Procurement of spares of intermediate conveyor | 0 | - | 0 | 0 | 0.3186 | -0.3186 | 0 | 0 |  |  | 0 | -0.3186
xxii | Procurement of Hydraulic motor for wagon tippler drive in CHP, 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.46494 | 0.46494 | 0 | 0 | 0 |  |  | 0 | 0
xxiii | Procurement of GEHO Pump (Model No. TZPM 400) Spares of Ash Handling Plant, 3 X 660 MW Units, KTPS, Koradi. | 0 | - | 0 | 0 | 0.83656 | -0.83656 | 0 | 0 |  |  | 0 | -0.83656
xxiv | Procurement of Beater Arms for Impact crushers installed at in Coal Handling Plant of 3x660 MW at KTPS, Koradi. | 0 | - | 0 | 0 | 1.0093 | -1.0093 | 0 | 0 |  |  | 0 | -1.0093
xxv | Supply of Atlas Copco make compressor spares for at Koradi TPS 660MW | 0 | - | 0 | 0 | 0.39813 | -0.39813 | 0 | 0 |  |  | 0 | -0.39813
xxvi | Procurement of spares for side arm charger, wagon tippler, impact crushers and stacker reclaimer at CHP 3x660 MW KTPS | 0 | - | 0 | 0.010573 | 0.43684 | -0.42626 | 0 | 0 |  |  | 0 | -0.42626
xxvii | Procurement of Beater heads with Pin for Impact crushers installed at in Coal Handling Plant of 3x660 MW at KTPS, Koradi. | 0 | - | 0 | 0 | 1.1256 | -1.1256 | 0 | 0 |  |  | 0 | -1.1256
xxviii | Procurement of spares of Hyd Motor of SAC | 0 | - | 0 | 0 | 0.36029 | -0.36029 | 0 | 0 |  |  | 0 | -0.36029
xxix | Procurement of hydraulic power packs for Flap Gates in CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0.1888 | -0.1888 | 0 | 0 |  |  | 0 | -0.1888
xxx | Procurement of Mobile Grilling Equipment for CHP 3x660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0.33866 | -0.33866 | 0 | 0 |  |  | 0 | -0.33866
xxxi | Procurement of Weld overlay Flap Gate assembly in CHP 3x660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0.5841 | -0.5841 | 0 | 0 |  |  | 0 | -0.5841
E6 | Capital Spares | 0 | - | 89.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of critical insurance spares for Turbine & its critical auxiliaries for 3 x 660 MW, Koradi (4370001538 dtd. 18/06/2018 d.p. 21 Months) | 0 | - | 89.62 | 89.6234 | 88.736 | 0.88736 | 0 | 0 |  |  | 0 | 0.88736
E7 | Additional Capitalization | 0 | - | 57.88 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Contruction of various infrastructure such as roads etc and public amenities in the rehabilitated villages of koradi and khasara | 0 | - | 13.1 | 12.74 | 0 | 12.74 | 0 | 0 |  |  | 0 | 12.74
ii | Procurement of 7 nos of school buses | 0 | - | 2 | 1.3109 | 1.3109 | 0 | 0 | 0 |  |  | 0 | 0
iii | Development of green belt & fodder farm for fulfillment of environmental clearance of MoEF for Koradi 3x660MW | 0 | - | 3.16 | 3.16 | 0 | 3.16 | 0 | 0 |  |  | 0 | 3.16
iv | Provision of Ground Hopper & Short Conveyor Belt from Existing Stackyard 1 & 2 ti existing Main Stream i.e. BCN 4A/4B of CHP 3x660 MW, KTPS, Koradi | 0 | - | 4.36 | 4.3555 | 4.3555 | 0 | 0 | 0 |  |  | 0 | 0
v | Provision of Ground Hopper & Conveyor Belt for Conveying Unloaded Coal form Open Wagon Tippler in CHP of Koradi Unit 8, 9 & 10. | 0 | - | 4.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
vi | Provision of Additional Facility for Manual Unloading Track in CHP of Koradi Unit No. 8, 9 & 10 | 0 | - | 5.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
vii | Construction of drains | 0 | - | 4.31 | 2.7927 | 0 | 2.7927 | 0 | 0 |  |  | 0 | 2.7927
viii | Supply erection commissioning of medium voltage variable frequency drive for conveyors BCN 6A,6B,7A,7B in CHP 3x660MW | 0 | - | 17 | 16.9859 | 16.9859 | 0 | 0 | 0 |  |  | 0 | 0
ix | Supply, Installation & commissioning of 3D level sensors for first two ESP field hoppers | 0 | - | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
F | Koradi TPS 3x660 MW Expansion Project – Construction of 2nd raising of existing Khasara Ash Bund from T.B.L. 308.50 M to T.B.L 312.00 M with construction of concrete dam (Broad crest weir structure), approach to drain wells and raising height of drain well No. 1, 2 & 3, construction of ash Compartment, cleaning of Khasara bund Nallah and construction of peripheral roads connecting to nearby villages for Khasara ash bund at TPS Koradi | 0 | - | 86.914 | 88.683 | 93.291 | -4.608 | 0 | 0 |  |  | 0 | -4.608
G | Discharge of UDL | 0 | - | 0 | 111.97 | 111.48 | 0.49 | 0 | 0 |  |  | 0 | 0.49
H | Asset Addition due to change in classification of inventory | 0 | - | 0 | 21.7503 | 0 | 21.7503 | 0 | 0 |  |  | 0 | 21.7503
I | Medical Oxygen Gr&Cyl Ozonization Plant (Covid Related Work) | 0 | - | 0 | 11.4034 | 9.6702 | 1.7332 | 0 | 0 |  |  | 0 | 1.7332
0 | B) DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (i) Submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Flue Gas Desulphurization FGD is for Unit 8, 9, 10 of 3x660MW Koradi TPS | MERC/CAPEX/FY 2020-21/WFH/SBR/05 | 2020-05-31 | 940 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Flue Gas Desulphurization is for Unit 8, 9, 10 of 3x660MW Koradi TPS | MERC/CAPEX/FY 2020-21/WFH/SBR/05 | 2020-05-31 | 847.78 | 233.42 | 233.42 | 0 | 855.88 | 855.88 |  |  | 855.88 | 0 | 614.36 | 241.52
0 | IDC | MERC/CAPEX/FY 2020-21/WFH/SBR/05 | 2020-05-31 | 92.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13 | Construction of new admin building at Vidyut Bhavan, Katol Road, Nagpur | MERC/Capex/2021-2022/MSPGCL/063 | 2022-02-18 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13.1 | Construction of new admin building at Vidyut Bhavan, Katol Road, Nagpur | 0 | 2022-02-18 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | 2022-02-18 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Improvement in Regenerative Air Pre-heater Performance at Unit # 9 of 3x660 MW, Koradi TPS | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 15.869 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Procurement of heating elements for RAPH installed in Unit 9 (660MW) at KTPS Koradi THROUGH LIMITED TENDER | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 15.33 | 11.8 | 11.8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.2 | Replacement of heating elements for RAPH installed in Unit 9 (660MW) at KTPS Koradi | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 0.349 | 0.37 | 0.37 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 0.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | CHP Improvement (7 Nos) Schemes & Procurement of Bulldozers, Wheel Loaders and Hydraulic Cranes at CHP 3X660MW, KTPS, Koradi | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 38.87 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Sch-1: Revamping of Apron Feeder in CHP at 3X660MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.68 | 4.68 | 4.68 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Sch-2: Procurement of Hydraulic motors and pumps in CHP at 3X660 MW, KTPS, Koradi | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.44 | 4.44 | 4.44 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.3 | Sch-3: Capacity enhancement of Hydraulic motor of Apron Feeder in CHP, 3X660 MW, KTPS, Koradi | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 2.01 | 2.01 | 2.01 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.4 | Sch-4: Modification, supply and replacement of Transfer chutes in CHP 3x660MW KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.39 | 4.39 | 4.39 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.5 | Sch-5: Design, supply, installation & commissioning of High performance IGUS energy chain system with chain flex cable for Tripper trolleys at CHP at 3x660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.37 | 4.37 | 4.37 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.6 | Sch-6: Procurement of B3-630 gear box for BCN 6 A/B in CHP at 3x660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 0.57 | 0.57 | 0.57 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.7 | Sch-7: Supply and installation of Belt tear detector system for conveyor belt in CHP 3x660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 1.18 | 1.18 | 1.18 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.8 | Sch-8: Procurement of 5 Nos of Bulldozers BD 155 at CHP 3X660 MW Koradi Thermal Power station. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 12.83 | 12.83 | 12.83 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.9 | Sch-9:- Procurement of 02 nos. of Wheel loaders at CHP 3X660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 3.07 | 3.07 | 3.07 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Sch-10:- Procurement of 15 Ton & 20 Ton capacity hydraulic Cranes at CHP 3X660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 0.69 | 0.69 | 0.69 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 0.64 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Construction of bridge cum bandhara across Pond No. 3 and allied works at Pond No. 3 at Koradi TPS | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 33.116 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Construction of cement concrete bridge cum bandhara alongwith gated arrangement. | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 14.75 | 5 | 5 | 0 | 9.75 | 9.75 |  |  | 9.75 | 0 | 9.75 | 0
20.2 | Construction of earthen embankment connecting bridge cum bandhara on both side of embankment by excavating soil / typha / silt from Pond No.3 & tree plantation. | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 14.3252 | 5 | 5 | 0 | 9.3252 | 9.3252 |  |  | 9.3252 | 0 | 9.3252 | 0
20.3 | Providing structural steel pathway on the existing waste weir (west side of the Pond No.3) and roads connecting to bridge behind Pond No.3 and bridge cum bandhara. | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 2.4308 | 2.43 | 2.43 | 0 | 0.0008 | 0.0008 |  |  | 0.0008 | 0
0 | IDC | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 1.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement & replacement of Superheater Pass Economizer Coils (Modified Design) for Unit 8, 9 & 10 at 3x660MW KTPS, Koradi | Not Approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Procurement & replacement of Superheater Pass Economizer Coils (Modified Design) for Unit 8, 9 & 10 at 3x660MW KTPS, Koradi | Not Approved | - | 0 | 48.14 | 48.14 | 0 | 48.14 | 48.14 |  |  | 48.14 | 0
0 | IDC | Not Approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Improvement in Boiler Performance at U-8,9 & 10 KTPS, Koradi | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 62.929 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Scheme-1: Procurement of Blade Sets for ID, FD & PA Fans at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 11.34 | 11.34 | 11.34 | 0 | 0 | 0 |  |  | 0 | 0
7.2 | Scheme-2: Procurement of RAPH Bottom Support Bearing Assembly at 3X660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 2.478 | 2.478 | 2.478 | 0 | 0 | 0 |  |  | 0 | 0
7.3 | Scheme-3: Procurement of RAPH Top Guide Bearing Assembly at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 0.684 | 0.684 | 0.684 | 0 | 0 | 0 |  |  | 0 | 0
7.4 | Scheme-4: Procurement of RAPH Gear Box at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 3.44 | 3.44 | 3.44 | 0 | 0 | 0 |  |  | 0 | 0
7.5 | Scheme-5: Procurement of RAPH Spares at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 1.13 | 1.13 | 1.13 | 0 | 0 | 0 |  |  | 0 | 0
7.6 | Scheme-6: Procurement of Coal Burner Assembly with windbox air nozzles for Unit 8 & 9 at 3x660MW. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 15.407 | 15.407 | 15.407 | 0 | 0 | 0 |  |  | 0 | 0
7.7 | Scheme-7: Procurement of Boiler Circulation Pump (BCP) with Impeller & Diffuser at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 11.12 | 11.12 | 11.12 | 0 | 0 | 0 |  |  | 0 | 0
7.8 | Scheme-8: Procurement and Replacement of Heating Elements for RAPH Installed for Unit 8 at 3x660MW. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 15.96 | 15.96 | 15.96 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 1.37 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Design, Engineering, Supply, Installation, Testing, Commissioning including all civil works for Natural resource treatment and Laboratory equipment with mandatory spares at Koradi TPS, 3 X 660 MW | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 49.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.1 | Supply of Natural resource treatment and lab equipment for Water, Coal, Oil, Meteorology with supporting AI computing, all auxiliaries, and accessories. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 35.28 | 0 | 0 | 0 | 42.5744 | 42.5744 |  |  | 42.5744 | 0
23.2 | Supply of Mandatory spares on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.8 | 0 | 0 | 0 | 0.944 | 0.944 |  |  | 0.944 | 0
23.3 | Supply of Tools and Tackles on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.15 | 0 | 0 | 0 | 0.177 | 0.177 |  |  | 0.177 | 0
23.4 | Complete Civil Work with 10 KLD ETP/ STP on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 3.6 | 4.25 | 4.25 | 0 | 0 | 0 |  |  | 0 | 0
23.5 | Services - Charges of Inland transport of plant and equipment on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.2 | 0 | 0 | 0 | 0.236 | 0.236 |  |  | 0.236 | 0
23.6 | Charges for Testing, Commissioning and PG Test of plant and equipment. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.05 | 0 | 0 | 0 | 0.059 | 0.059 |  |  | 0.059 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Improvement in Regenerative Air Preheater Performance & Complete Replacement of NDCT fills at Unit # 10, Koradi TPS | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 25.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.1 | Procurement of heating elements for RAPH installed in Unit 10 (660MW) at KTPS Koradi through OEM | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 12.23 | 14.521 | 14.521 | 0 | 0 | 0 |  |  | 0 | 0
24.2 | Complete Supply & Replacement of NDCT fills of U#10. | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 13 | 13 | 13 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 0.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 14 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 14.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 10.994 | 10.994 |  |  | 10.994 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 15 | HMI (Human Machine Interface) Upgradation of ‘SSPA-T3000’ DCS (Distribution Control System), Rockwell make PLC System installed at 3x660MW Unit No. 8, 9 & 10 at Koradi TPS and HMI (Human Machine Interface) Upgradation of MaxDNA DCS System at Unit 8-9, CSTPS, Chandrapur | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 55.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 15.1 | Supply: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 10.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 15.2 | Works: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | HMI (Human Machine Interface) Upgradation of ‘SPPA-T3000’ DCS (Distributed Control System) installed at 3x660MW Unit- 8, 9 & 10 at Koradi TPS to match with the external aspects and process improvement | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 24.33 | 0 | 0 | 0 | 24.33 | 24.33 |  |  | 24.33 | 0
15.4 | Upgradation of Rockwell Make PLC System installed at 3x660MW ,Koradi TPS to match with the external aspects and process improvement.(C&I) | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 20.2 | 20.2 | 20.2 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Work of provision of platform beside railway siding at backside of chord cabin for loading of fly ash in railway wagon for ash utilization at 3x660 MW TPS, Koradi | 0 | - | 0 | 0.0038356 | 0.0038356 | 0 | 0 | 0 |  |  | 0 | 0
13 | Capital Exenditure schemes for in-principle clearance regarding "EPC contract for the wok of construction of quarters and development of KTPS colony at Koradi" under CAPEX scheme | MERC/CAPEX/MSPGCL/2024-12/0569 DTD.13.09.2024 | 2024-09-13 | 210.48 | 50 | 50 | 0 | 150 | 150 |  |  | 150 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of spares for L&T-MHI make Turbine for COH work of Turbine at KTPS, 3x660MW units Koradi | MERC/CAPEX/MSPGCL/2023-24/0639 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement of spares for L&T-MHI make Turbine for COH work of Turbine at KTPS, 3x660MW units Koradi | MERC/CAPEX/MSPGCL/2023-24/0639 | - | 0 | 31.6358 | 31.6358 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Procurement of HP Nozzle assembly for L&T-MHI Make Turbine installed at 3x660MW Units Koradi | MERC/CAPEX/MSPGCL/2023-24/0639 | - | 0 | 4.189 | 4.189 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | C) DPRs Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Control & instrumentation related Various Upgradation schemes viz.Emission Monitoring & Water Quality Analysers ,Vibration Monitoring Schemes,Water Flow Monitoring etc. at 3X660MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Upgradation of Emission Monitoring Analysers | 0 | - | 0 | 0 | 0 | 0 | 9.58 | 9.58 |  |  | 9.58 | 0
2.2 | Upgradation of Water Quality Analysers | 0 | - | 0 | 0 | 0 | 0 | 5.33 | 5.33 |  |  | 5.33 | 0
2.3 | Revamping & Supply Of Upgraded VM7B Version of Vibration Monitoring Rack | 0 | - | 0 | 0 | 0 | 0 | 4.84 | 4.84 |  |  | 4.84 | 0
2.4 | Implementation of ‘Flow Monitoring System’ at 3x660MW Balance of Plant (BOP) Unit- 8, 9 & 10 at Koradi TPS | 0 | - | 0 | 0 | 0 | 0 | 6.87 | 6.87 |  |  | 6.87 | 0
3 | CHP Improvement Scheme-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Supply, Erection, Commissioning of set of Internals for Wagon Tipplers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 10.96 | 10.96 |  |  | 10.96 | 0
3.2 | Supply, Erection, Commissioning of set of Internals for Side Arm Chargers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 3.54 | 3.54 |  |  | 3.54 | 0
3.3 | Supply, Erection, Commissioning of set of Internals for Wobbler Feeders at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 4.96 | 4.96 |  |  | 4.96 | 0
3.4 | Supply, Erection, Commissioning of set of Internals for Apron Feeders at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 15.55 | 15.55 |  |  | 15.55 | 0
3.5 | Supply, Erection, Commissioning of set of Internals for Impact Crushers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 9.63 | 9.63 |  |  | 9.63 | 0
3.6 | Supply, Erection, Commissioning of set of Internals for Stacker cum Reclaimers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 6.26 | 6.26 |  |  | 6.26 | 0
4 | Performance improvement and availability of various Auxiliaries of TG at 3x660MW KTPS Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Performance improvement and availability of various Auxiliaries for Oil Systems of Main Turbine. | 0 | - | 0 | 0 | 0 | 0 | 3.26 | 3.26 |  |  | 3.26 | 0
4.2 | Performance improvement and availability of various Auxiliaries of Generator System. | 0 | - | 0 | 0 | 0 | 0 | 7.31 | 7.31 |  |  | 7.31 | 0
4.3 | Performance improvement and availability of Feed Water System. | 0 | - | 0 | 0 | 0 | 0 | 10.54 | 10.54 |  |  | 10.54 | 0
4.4 | Performance improvement and availability of Vacuum System. | 0 | - | 0 | 0 | 0 | 0 | 2.28 | 2.28 |  |  | 2.28 | 0
4.5 | Performance improvement and availability of CEP System. | 0 | - | 0 | 0 | 0 | 0 | 7.83 | 7.83 |  |  | 7.83 | 0
4.6 | Procurement of Complete Pull out Assembly along with Impeller and wear ring of Cooling Water Pump. | 0 | - | 0 | 0 | 0 | 0 | 14.87 | 14.87 |  |  | 14.87 | 0
4.7 | Procurement of complete assembly of HP and LP Elements for Atlas Copco make Compressors. | 0 | - | 0 | 0 | 0 | 0 | 4.19 | 4.19 |  |  | 4.19 | 0
5 | Improvement in Wet ash evacuation system at 3x660MW Units, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Procurement & installation of Ash Slurry Series Pump Assembly with modified metallurgy and Critical Wet End Sub Assembly to enhance the performance & slurry disposal capacity. | 0 | - | 0 | 0 | 0 | 0 | 7.53 | 7.53 |  |  | 7.53 | 0
5.2 | Procurement & installation of Ash Slurry Series Pump Assembly with modified metallurgy along with Gear Box, Fluid Coupling & Motor (4’th Series) and Critical Wet End Sub Assembly to enhance the performance & slurry disposal capacity. | 0 | - | 0 | 0 | 0 | 0 | 2.51 | 2.51 |  |  | 2.51 | 0
5.3 | Procurement & installation of Overflow Transfer Pump Assembly with upgradation in metallurgy and Critical Wet End Sub Assembly to enhance the performance. | 0 | - | 0 | 0 | 0 | 0 | 3.59 | 3.59 |  |  | 3.59 | 0
5.4 | Procurement & installation of IAC Compressor Assembly: Model –ZR110 STD 7.5 IMD Atlas Copco Make Oil free water cooled screw air compressor with inbuilt atlas copco make heat of compression single drum rotator air dryer to enhance the performance. | 0 | - | 0 | 0 | 0 | 0 | 7.56 | 7.56 |  |  | 7.56 | 0
6 | HMI Upgradation of Diasys Netmation DCS at 3x660MW KTPS Koradi Units 8,9 & 9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | HMI Upgradation of Diasys Netmation DCS at 3x660MW KTPS Koradi Units 8,9 & 10 | 0 | - | 0 | 0 | 0 | 0 | 77.15 | 77.15 |  |  | 77.15 | 0
7 | Improvement in Dry ash evacuation system at 3x660MW Units, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Procurement of Ingersoll Rand Make Transport Air Compressors Critical/Non-Critical Spares sub-assembly for performance improvement. | 0 | - | 0 | 0 | 0 | 0 | 29.57 | 29.57 |  |  | 29.57 | 0
8 | MSERW Pipes for Garlanding arrangement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.1 | Work of Garlanding arrangement to changeover ash slurry feed points for even filling of pond by providing MSERW Pipes along the periphery of Ash Bund Dyke Wall at Khasara Ash Bund. | 0 | - | 0 | 0 | 0 | 0 | 98.83 | 98.83 |  |  | 98.83 | 0
9 | Capacity Enhancement & Performance optimization at WTP 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.1 | Capacity enhancement of DM water stream in WTP at 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 58.94 | 58.94 |  |  | 58.94 | 0
9.2 | Capacity enhancement Condensate polishing unit regeneration area in WTP at 3X660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 13.41 | 13.41 |  |  | 13.41 | 0
9.3 | Provision of Ozone generating plant of 1.0 Kg capacity in WTP at 3X660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 5.84 | 5.84 |  |  | 5.84 | 0
10 | DPR for Construction of CC Road alongwith RCC Drain, CC platform for heavy machinery movement at 3x660 MW, TPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.1 | DPR for Construction of CC Road alongwith RCC Drain, CC platform for heavy machinery movement at 3x660 MW, TPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 33.57 | 33.57 |  |  | 33.57 | 0
11 | Improvement in Coal Mill Performance-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.1 | Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi through OEM. | 0 | - | 0 | 0 | 0 | 0 | 6.15 | 6.15 |  |  | 6.15 | 0
11.2 | Procurement of Mill Rotary Separator Blades for coal mill MVM 32R at 3x660 MW, KTPS, Koradi through open tender | 0 | - | 0 | 0 | 0 | 0 | 4.01 | 4.01 |  |  | 4.01 | 0
11.3 | Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi through OEM. | 0 | - | 0 | 0 | 0 | 0 | 14.57 | 14.57 |  |  | 14.57 | 0
11.4 | Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi through OEM | 0 | - | 0 | 0 | 0 | 0 | 6.14 | 6.14 |  |  | 6.14 | 0
12 | Improvement in Boiler performance-II at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.1 | Scheme1:Procurement of Coal compartment assembly for Unit8 at 3x660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 12.7 | 12.7 |  |  | 12.7 | 0
12.2 | Scheme2:Procurement of blade sets for ID, FD & PA Fan at 3x660 MW, Units at KTPS Koradi through OEM. | 0 | - | 0 | 0 | 0 | 0 | 11.34 | 11.34 |  |  | 11.34 | 0
12.3 | Scheme3:Procurement of RAPH internal Spares for 3X660MW units at KTPS Koradi through OEM (Qty- 6 Sets) | 0 | - | 0 | 0 | 0 | 0 | 1.13 | 1.13 |  |  | 1.13 | 0
12.4 | Scheme4:Procurement of RAPH Sector plate with Actuating mechanism assembly for Unit9 3 X 660MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 7.2 | 7.2 |  |  | 7.2 | 0
13 | Improvement in Coal Mill performance-II at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | Procurement of FLENDER make Gearbox model kmp-450 along with motor for coal mill MVM32R at 3x660mw KTPS, koradi through OEM. | 0 | - | 0 | 0 | 0 | 0 | 20.91 | 20.91 |  |  | 20.91 | 0
13.2 | Procurement of complete set of couplings for PA, ID & FD fans at 3X660MW units at KTPS Koradi through OEM | 0 | - | 0 | 0 | 0 | 0 | 5.14 | 5.14 |  |  | 5.14 | 0
14 | Improvement in Coal Mill performance-III at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 6.15 | 6.15 |  |  | 6.15 | 0
14.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 14.57 | 14.57 |  |  | 14.57 | 0
14.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 6.14 | 6.14 |  |  | 6.14 | 0
14.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit10 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
14.5 | Scheme5:Procurement of Complete MRHS System along with Pneumatic Compressors at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
15 | Improvement in Boiler performance-III at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | Scheme1:Procurement of Coal compartment assembly for Unit8at 3x660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Scheme2:Procurement of blade sets for ID, FD & PA Fan at 3x660 MW, Units at KTPS Koradi through OEM. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Scheme3:Procurement and replacement of heating elements for RAPH installed in Unit 9 (660MW) at KTPS Koradi THROUGH OEM/OES (Qty- 2 Sets) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Scheme4:Procurement of HP valves, safety valves and ERV's for 3X660MW units at KTPS Koradi through OEM | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.5 | Scheme5:Procurement of RAPH Sector plate with Actuating mechanism assembly for Unit8 3 X 660MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | Improvement in Coal Mill performance-IV at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit8 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | Improvement in Coal Mill performance-V at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit9 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | Improvement in Boiler performance-IV at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.1 | Scheme1:Procurement of Coal compartment assembly for Unit8 at 3x660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.2 | Scheme2:Procurement of blade sets for ID, FD & PA Fan at 3x660 MW, Units at KTPS Koradi through OEM. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.3 | Scheme3:Procurement of RAPH bottom support bearing assembly for 3X660MW units at KTPS Koradi through OEM (Qty- 2 Sets) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.4 | Scheme4:Procurement of RAPH top guide bearing assembly for 3X660MW units at KTPS Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.5 | Scheme5:Procurement of RAPH Gear Box for 3X660MW units at KTPS Koradi through OEM (Qty- 1 Sets) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.6 | Scheme6:Procurement of RAPH Sector plate with Actuating mechanism assembly for Unit10 at 3 X 660MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.7 | Scheme7:Procurement and replacement of heating elements for RAPH installed in Unit 10 (660MW) at KTPS Koradi THROUGH OEM/OES (Qty- 2 Sets) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.8 | Scheme8:Procurement of Boiler Circulating Pump (1 Nos) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | Improvement in Coal Mill performance-VI at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit9 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.3 | Reliability Improvement schemes of generators at 3X660MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | Scheme No. 1 :PROCUREMENT OF MELCO/LMTG MAKE GENERATOR ROTOR ASSEMBLY with excitation transformer AT 3X660MW KTPS, KORADI THROUGH OEM | 0 | - | 0 | 0 | 0 | 0 | 45.39 | 45.39 |  |  | 45.39 | 0
19.2 | Scheme No. 2:PROCUREMENT OF ONE COMPLETE SET OF GENERATOR STATOR COILS FOR GENERATOR AT 3X660MW UNITS AT KTPS KORADI THROUGH OEM | 0 | - | 0 | 0 | 0 | 0 | 35.4 | 35.4 |  |  | 35.4 | 0
25 | DPR on Procurement of Critical Speares for L&T make Main Turbine(typeTC4F-30) installed at 3x660MW KTPS Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.1 | Scheme No. 1 :Procurement of Critical Speares for L&T make Main Turbine(typeTC4F-30) installed at 3x660MW KTPS Koradi. | 0 | - | 0 | 0 | 0 | 0 | 126.41 | 126.41 |  |  | 126.41 | 0
26 | DPR for Coal Handling Plant Performance Improvement Schemes -II at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.1 | Scheme No. 1 : Performance Improvement of Unloading System Wagon Tipplers at CHP 3x660MW KTPS Koradi | 0 | - | 0 | 0 | 0 | 0 | 5.8 | 5.8 |  |  | 5.8 | 0
26.2 | Scheme No. 2 : Performance Improvement of Unloading System Side Arm Chargers at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Side Arm Charger Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 2.8 | 2.8 |  |  | 2.8 | 0
26.3 | Scheme No. 3 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 3.2 | 3.2 |  |  | 3.2 | 0
26.4 | Scheme No. 4 : Performance Improvement of Stacking & Reclaiming System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Stacking & Reclaiming System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 6.5 | 6.5 |  |  | 6.5 | 0
26.5 | Scheme No. 5 : Performance Improvement of Crushing System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Impact Crusher & Wobbler Feeders Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 8.5 | 8.5 |  |  | 8.5 | 0
26.6 | Scheme No. 6 : Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -1 at CHP 3x660MW KTPS Koradi A) Brief scope of work: Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -1 at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
27 | DPR for Coal Handling Plant Performance Improvement Schemes -III at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.1 | Scheme No. 1 : Performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Hydraulic system for Wagon Tippler, Side Arm Charger , Apron Feeder ( 1 & 2) Stacker Reclaimer 1 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 10.5 | 10.5 |  |  | 10.5 | 0
27.2 | Scheme No. 2 : Construction of Air tight Hydraulic power pack room along with necessary cooling system for performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Construction of Air tight Hydraulic power pack room along with necessary cooling system for Wagon Tippler & Apron Feeder ( 1 to 4) Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 3.2 | 3.2 |  |  | 3.2 | 0
27.3 | Scheme No. 3 : Performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory Hydraulic Power Cylinders of Wagon Tippler, Side Arm Charger ( 1 to 4) Stacker Reclaimer 1 & 2 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
27.4 | Scheme No. 4 : Performance Improvement of Stacker Reclaimer by providing Hydraulic Drive to Boom Conveyor at CHP 3x660MW KTPS Koradi A) Brief scope of work: Hydraulic Drive to Boom Conveyor Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0.9 | 0.9 |  |  | 0.9 | 0
27.5 | Scheme No. 5 : Performance Improvement of Illumination system with energy conservation at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Solar High masts along the rail track in railway yard Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 3.75 | 3.75 |  |  | 3.75 | 0
27.6 | Scheme No. 6 : Design, Supply & Installation of LT VFD Drives for Critical Conveyors at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of LT VFD Drives for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 1.2 | 1.2 |  |  | 1.2 | 0
27.7 | Scheme No. 7 : Design , supply, Erection & Commissioning of Short Conveyor for Stacking Purpose at CHP 3x660MW KTPS Koradi A) Brief scope of work: Short Conveyor for Stacking Purpose at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 9.6 | 9.6 |  |  | 9.6 | 0
27.8 | Scheme No. 8 : Capacity Enhancement of BCN-7/5/4/3 /1 AB in CHP 3x660MW KTPS Koradi A) Brief scope of work: Short Conveyor for Stacking Purpose at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 8.6 | 8.6 |  |  | 8.6 | 0
27.9 | Scheme No. 9 : Design , Engineering & modification along with strengthening of Existing Travel Track structure for Side Arm Charger & Stacker Reclaimer A) Brief scope of work: strengthening of Existing Travel Track structure for Side Arm Charger & Stacker Reclaimer Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
27.1 | Scheme No. 10 : Design , Engineering & Erection of modified Energy Efficient Ventilation System for Wagon Tippler Complex Area in CHP 3X660MW KTPS Koradi A) Brief scope of work: Energy Efficient Ventilation System for Wagon Tippler Complex Area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
27.11 | Scheme No. 11 : Design , Engineering & Installtion of Vibration & temprature Monitoring Systems for critical auxiliaries in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Installtion of Vibration & temprature Monitoring Systems for critical auxiliaries Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 1.2 | 1.2 |  |  | 1.2 | 0
27.12 | Scheme No. 12 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 1.2 | 1.2 |  |  | 1.2 | 0
27.13 | Scheme No. 13 : Design , Engineering & Provision of Stone Grappling Equipment System for Wagon Tippler 3 &4 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Stone Grappling Equipment System for Wagon Tippler 3 &4 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0.9 | 0.9 |  |  | 0.9 | 0
27.14 | Scheme No. 14 : Design , Engineering & Provision of Public Addressing System for Wagon Tippler Complex in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Public Addressing System for Wagon Tippler Complex in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
27.15 | Scheme No. 15 : Design , Engineering & Provision of Belt Tracking System for Critical Conveyors in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Belt Tracking System for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
27.16 | Scheme No. 16 : Design , Engineering & Provision of Dust supression System for stacker reclaimer-1 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0.6 | 0.6 |  |  | 0.6 | 0
27.17 | Scheme No. 17 : Work of Life Enhancement of wobbler Feeder 1 &2 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 1.6 | 1.6 |  |  | 1.6 | 0
28 | DPR for Coal Handling Plant Performance Improvement Schemes -IV at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28.1 | Scheme No.1 : Design , Engineering , Supply & Installation of Modular Transfer chutes for Critical Conveyor System in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of Modular Transfer chutes for Conveyor System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 14 | 14 |  |  | 14 | 0
28.2 | Scheme No.2 :Upgradtion of Exsisting Fire Fighting System at Stack yard area in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradtion of Exsisting Fire Fighting System at Stack yard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 2.6 | 2.6 |  |  | 2.6 | 0
28.3 | Scheme No.3 : Design , Engineering , Supply & Strengthening of engineering structure of BCN- 7A/B along with track alignment in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Strengthening of engineering structure of BCN- 7A/B Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 2.4 | 2.4 |  |  | 2.4 | 0
28.4 | Scheme No.4 : Design , Engineering , Supply & Installation of Mist Cannon Spray System around stackyard area in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of Mist Cannon Spray System at stackyard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 1.6 | 1.6 |  |  | 1.6 | 0
28.5 | Scheme No.5 : Design , Engineering , Supply & Installation of EOT cranes at Bunker in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of EOT cranes at Bunker Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 4.5 | 4.5 |  |  | 4.5 | 0
29 | DPR for Procurment of various Heavy Vehicles at CHP 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29.1 | Scheme No.1 : Procurment of Heavy Vehicles like dozers, wheel loaders , locomotives, Crane, Hydra , Disel Browser , Jcb & Bobcats etc. in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurment of Heavy Vehicles like dozers, wheel loaders , locomotives etc Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 30 | 30 |  |  | 30 | 0
29.2 | Scheme No.2 : Procurment of Auger Machines for coal sampling in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurment of Auger Machines for coal sampling Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 2.2 | 2.2 |  |  | 2.2 | 0
29.3 | Scheme No.3 : Procurment of Truck Mounted mist cannon dust supression system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurment of Truck Mounted mist cannon dust supression system in CHP Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0.8 | 0.8 |  |  | 0.8 | 0
30 | DPR for Coal Handling Plant Performance Improvement Schemes -V at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.1 | Scheme No. 1 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.2 | Scheme No. 2 : Performance Improvement of Stacking & Reclaiming / Side Arm Charger System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Energy Chain System of Stacking & Reclaiming System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.3 | Scheme No. 3 : Performance Improvement of unloading System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Energy Chain System of side arm acharger Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.4 | Scheme No. 4 : Upgradation to 100 MT Ton Weighbridge of existing road weighbridge at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of LT VFD Drives for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.5 | Scheme No. 5 : Design , Engineering & Erection of modified Energy Efficient Ventilation System for Crusher House Area in CHP 3X660MW KTPS Koradi A) Brief scope of work: Energy Efficient Ventilation System for Wagon Tippler Complex Area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.6 | Scheme No. 6 : Design , supply & Installation of Cooling Arrangement for Switchgear rooms at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Cooling Arrangement for Switchgear rooms Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.7 | Scheme No. 7 : Design , Engineering & Erection of modified Engineering Structure of Tunnel Conveyor 1A &1 B in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Erection of modified Engineering Structure of Tunnel Conveyor 1A &1 B Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31 | DPR for Coal Handling Plant Performance Improvement Schemes -VI at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.1 | Scheme No. 1 : Performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Wagon Tippler, Side Arm Charger , Apron Feeder ( 3 & 4) Stacker Reclaimer 2 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.2 | Scheme No. 2 : Design Supply & Installation of Wagon Locking system for all four wagon tipplers at CHP 3x660MW KTPS Koradi A) Brief scope of work: Wagon Locking system for all four wagon tipplers Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.3 | Scheme No. 3 : Design, Supply & Installation of upgraded Vibrating Feeders for Stacker Reclaimer at CHP 3x660MW KTPS Koradi A) Brief scope of work: Design, Supply & Installation of upgraded Vibrating Feeders for Stacker Reclaimer Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.4 | Scheme No. 4: Performance Improvement of Stacker Reclaimer by providing Hydraulic Drive to Boom Conveyor at CHP 3x660MW KTPS Koradi A) Brief scope of work: Hydraulic Drive to Boom Conveyor Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.5 | Scheme No. 5 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.6 | Scheme No. 6 : Design , Engineering & Provision of Belt Tracking System for Critical Conveyors in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Belt Tracking System for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.7 | Scheme No. 7 : Design , Engineering & Provision of Dust supression System for stacker reclaimer-1 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.8 | Scheme No. 8 : Work of Life Enhancement of wobbler Feeder 3 &4 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32 | DPR for Coal Handling Plant Performance Improvement Schemes -VII at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.1 | Scheme No.1 : Design , Engineering , Supply & Installation of Modular Transfer chutes for Crusher House Complex & other Critical Conveyor System in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of Modular Transfer chutes for Conveyor System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.2 | Scheme No.2 :Upgradtion of Exsisting Fire Fighting System along the conveyor length in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradtion of Exsisting Fire Fighting System at Stack yard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.3 | Scheme No.3 : Supply , Erection & Installation of Rack & Pinion Elevators at Bunker in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Supply , Erection & Installation of Rack & Pinion Elevators at Bunker in CHP 3X660MW KTPS Koradi. Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.4 | Scheme No.4 :Up Liftment f Exsisting Fire Fighting lines in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradtion of Exsisting Fire Fighting System at Stack yard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.5 | Scheme No.5 : Procurement of HPPE Polymer Roller for Conveyor system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurement of HPPE Polymer Roller for Conveyor system Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.6 | Scheme No.6 : Design , Engineering , Supply & Installation of EOT cranes at Wagon Tippler Complex in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of EOT cranes at Wagon Tippler Complex Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33 | DPR for Coal Handling Plant Performance Improvement Schemes -VIII at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.1 | Scheme No. 1 : Performance Improvement of Unloading System Wagon Tipplers at CHP 3x660MW KTPS Koradi Estimated Cost : 3.6 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.2 | Scheme No. 2 : Performance Improvement of Unloading System Side Arm Chargers at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Side Arm Charger Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.3 | Scheme No. 3 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.4 | Scheme No. 4 : Performance Improvement of Stacking & Reclaiming System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Stacking & Reclaiming System -2 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.5 | Scheme No. 5 : Performance Improvement of Crushing System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Impact Crusher & Wobbler Feeders Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.6 | Scheme No. 6 : Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -2 at CHP 3x660MW KTPS Koradi A) Brief scope of work: Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -2 at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.7 | Scheme No. 7 : Other Mislenious Schemes at CHP 3x660MW KTPS Koradi A) Brief scope of work: Other Mislenious works Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.8 | Scheme No. 4 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.9 | Scheme No.8: Procurement of HPPE Polymer Roller for Conveyor system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurement of HPPE Polymer Roller for Conveyor system Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34 | DPR for Coal Handling Plant Performance Improvement Schemes -IX at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.1 | Scheme No. 1 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.2 | Scheme No. 2 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.3 | Scheme No.3 : Upgradation of Exsisting Rack & Pinion Elevators at CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradation of Exsisting Rack & Pinion Elevators Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.4 | Scheme No.4 : Procurement of HPPE Polymer Roller for Conveyor system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurement of HPPE Polymer Roller for Conveyor system Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.5 | Scheme No.5 : Other miscellaneous scheme regarding sustainable performance improvement of CHP 3X660MW KTPS Koradi. A) Brief scope of work: ther miscellaneous scheme regarding sustainable performance improvement Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | Design & engineering, procurement, supply, installation & commissioning of Ozone Generator system of capacity 45.0 Kg/hr for CW system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Scheme1:Design & engineering, procurement, supply, installation & commissioning of Ozone Generator system of capacity 45.0 Kg/hr for CW system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36 | Pipeline expansion to improve dry ash evacuation system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.1 | Scheme1: Pipeline expansion to improve dry ash evacuation system along with target box modification and also to erect & commission dry ash evacuation directly to remote silo. | 0 | - | 0 | 0 | 0 | 0 | 75 | 75 |  |  | 75 | 0
37 | Modification at intermediate silo and HCSD system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.1 | Scheme1: Additional charge pump. | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
37.2 | Scheme 2: Supply & Installation Air washery at silo top. | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
37.3 | Scheme 3: Shed above silo top. | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
37.4 | Scheme 4: Supply & Installation Construction of platform at pipe rack up to Remote silo. | 0 | - | 0 | 0 | 0 | 0 | 7 | 7 |  |  | 7 | 0
37.5 | Scheme 5: Shifting of pipeline above pipe rack. | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
37.6 | Scheme 6: Supply & Installation ART sub assemblies. | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
38 | ESP field strengthening at U#8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.1 | Scheme1: ESP field strengthening at U#8 | 0 | - | 0 | 0 | 0 | 0 | 120 | 120 |  |  | 120 | 0
39 | Procurement of various pumps for AHP performance improvement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
39.1 | Scheme1: Procurement of various pumps for AHP performance improvement. | 0 | - | 0 | 0 | 0 | 0 | 28 | 28 |  |  | 28 | 0
40 | Modification in Dry Ash Evacuation System D/V Assemblies & allied equipments to improve performance | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
40.1 | Scheme1: Procurement of D/V Assemblies & allied equipments to improve performance. | 0 | - | 0 | 0 | 0 | 0 | 35 | 35 |  |  | 35 | 0
41 | Additional IAC house for Intermediate silo and Remote silo along with erection of S.S. Pipeline | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.1 | Scheme1: Supply & Installation Additional IAC house for Intermediate silo and Remote silo along with erection of S.S. Pipeline | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42 | Waste water system modification to have zero water discharge | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.1 | Scheme1: Waste water system modification to have zero water discharge at 3x660MW, KTPS, Koradi along with Pump Procurement along with arrangement of sludge discharge at ESP water Washing system. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
43 | ESP field strengthening at U#9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
43.1 | Scheme1: ESP field strengthening at U#9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44 | Procurement of HCSD GEHO Pump (TZPM-400) critical items sub-assemblies | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.1 | Scheme1: Procurement of HCSD GEHO Pump TZPM-400) critical items sub-assemblies. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45 | MSERW Pipes & Seamless Pipes replacement to improve ash conveying & its disposal-1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.1 | Scheme1: Supply & Work of Replacement of MSERW Pipes & Seamless Pipes in Bottom ash/Coarse ash evacuation & Ash Slurry Disposal Pipelines, Dry ash conveying system in phase manner to improve the ash evacuation performance. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46 | Improvement in Ash Water Recovery System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.1 | Scheme1: Supply & Installation of Pumps along with Pipeline for Improvement in Ash Water Recovery System. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47 | Replacement of Instrument air pipeline from M.S. to S.S for AHP main plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.1 | Scheme1: Replacement of Instrument air pipeline from M.S. to S.S for AHP main plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48 | Modification of sludge pumps and its pipeline with pumps of higher capacity and discharge line of higher capacity. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.1 | Scheme1: Modification of sludge pumps and its pipeline with pumps of higher capacity and discharge line of higher capacity. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
49 | ESP field strengthening at U#10 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
49.1 | Scheme1: ESP field strengthening at U#10 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50 | MSERW Pipes & Seamless Pipes replacement to improve ash conveying & its disposal-2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50.1 | Scheme1: Supply & Work of Replacement of MSERW Pipes & Seamless Pipes in Bottom ash/Coarse ash evacuation & Ash Slurry Disposal Pipelines, Dry ash conveying system in phase manner to improve the ash evacuation performance. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
51 | Replacement of IAC for AHP Main Plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
51.1 | Scheme1: Supply & Installation of IAC for AHP Main Plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
52 | Improvement in DRY ASH Evacuation system-2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
52.1 | Scheme1: Supply & Installation of TAC, Replacement of Air Lock Vessel, Various Valves, ESP Hopper Doors, ESP access doors. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
53 | Improvement in DRY ASH Evacuation system-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
53.1 | Scheme1: Procurement of Ingersoll Rand Make Transport Air Compressors Critical/Non-Critical Spares sub-assembly for performance improvement. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
54 | Detailed project report for various works of security section as per the IB recommendations. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
54.1 | Repairing & raising height of compound wall with provision of concertina coil at various location of peripheral compound wall at 3x660MW KTPS Koradi. | 0 | - | 0 | 0 | 0 | 0 | 1.593 | 1.593 |  |  | 1.593 | 0
54.2 | Work of Providing structural three quarter turn staircase with landing along pheriphery of FISS watch tower at 3x660MW, TPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0.34444 | 0.34444 |  |  | 0.34444 | 0
55 | Supply, installation, comissioning and testing of 220V station & 360V UPS batteries installed at U 8, 9 & 0 of 3x660 MW KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
55.1 | Supply, installation, comissioning and testing of 220V station & 360V UPS batteries installed at U 8, 9 & 0 of 3x660 MW KTPS, Koradi. (scheme) | 0 | - | 0 | 0 | 0 | 0 | 22.8 | 22.8 |  |  | 22.8 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
56 | TDBFP Governing valve's LPCV ,HPCV MSV AND Trip lock replacement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
61 | Procurement & replacement of HP Heaters at 3x660 MW KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Vibration Monitoring & Analysis system installed at 3x660MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 63 | 63 |  |  | 63 | 0
0 | Scheme 1: Upgradation of sinkawa make vibration monitoring and Analysis system for main turbine at 3x660MW koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of Bently Nevada make vibration monitoring and Analysis system for RMCMS system at 3x660MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3 :-Emerson PLC upgradation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of various Level Transmitters installed at 3x660 MW koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of Guided wave Radar Level TX installed at Condenser Hotwell and LPH 1,2 and 3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of Displacer type level TX into Guided wave radar level Tx installed at various Drain Tank, Flash tank and pit | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3: Upgradation of non- contact type Ultrasonic level Tx into IP68 non- contact type Radar level TX. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of ESP Hopper level Probes installed at 3x660 MW koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of 1st three fields ESP Hopper level probes into continuous level monitoring NOGS system at 3x660 MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of RF capacitance Hopper level probe into of RF admittance level probe at 4,5,6,7,8 & 9 ESP Hoppers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3: Upgradation of ESP hopper heater monitoring , control and real time monitoring system at 3X660MW Koradi TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of various scheme viz ASLD, Furnace tv camera FEGT and acoustic Pyrometer installed at 3x660 MW koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of ASLD system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of Furnace TV Camera | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3:Upgradation of FEGT system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 4:Upgradation of acoustic pyrometer | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of various scheme viz instrument Air pipe at ESP Area, wet Ash Evacuation system, HCSD Silo. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of instrument Air pipeline system at ESP of M.S into SS installed at 3x660 MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of instrument Air pipeline system at wet Ash system of M.S into SS . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3: Upgradation of instrument Air pipeline system at HCSD silo of M.S. into SS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 4: Upgradation of instrument Air pipeline system at Remote Silo of M.S into SS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 5: Upgradation of Control & Instrument section lab with Hydraulic Servo Valve Test, Pneumatic System test and calibration lab set up. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Flame scanner for flexible operation of 3X660MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 35 | 35 |  |  | 35 | 0
0 | Scheme 1: Upgradation of Flame scanner for flexible operation of 3X660MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of DRC Pipes, Bends & Fittings in phase manner to improve the dry ash conveying & its disposal (2 years) | 0 | - | 0 | 0 | 0 | 0 | 30 | 30 |  |  | 30 | 0
0 | Replacement of DRC Pipes, Bends & Fittings in phase manner to improve the dry ash conveying & its disposal (2 years) (Rs.30 Cr.) (Bottom ash/Coarse ash evacuation & Ash Slurry Disposal Pipelines, Dry ash conveying system) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Augmentation of Coarse Ash disposal system at U10 at KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | WORK OF INSTALLATION & COMMISSIONING OF ASH DISPOSAL SYSTEM AT UNIT#10 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Railway Track Siding Performance Improvement Schemes at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 1 : Work of complete track renovation of existing Rail yard of CHP, 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. Due to continuous movement of Railway's precious rolling stock, the track spares are worn out and are due for complete replacement. Hence, to maintain rail track parameters in healthy condition as per Railway norms so as to avoid untoward incidences of derailment the execution of work of complete track renewal is essential. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 2 : Scheme Name- Work of laying of additional track at 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. However, as per the existing infrastructure, at present there is no dedicated empty formation line. Due to non-availability of empty formation line, most often unloading gets hampered due to blocking of outhaul line by empty rake. The hampering in unloading affects the plant performance and incurrs unnecessary financial burden on KTPS account under the head of demurrage charges. Hence, to maintain the plant loadability and availability, it is essential to lay additional track at 3x660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 3 : Scheme Name- Work of rectification and upgradtion of existing SSP at CHP, 3x660MW, KTPS, Koradi. Justification- The SSP has been erected at 3x660MW, KTPS, Koradi. However, till date the same has not been commissioned. With lapse of @ 5-6 years after erection and its non commissioning, the existing SSP set up has been completely detoriorated. Now, Railway's is pressing hard for early commissioning of the same. The said set up shall ensure isolation of OHE of existing yard with Railway's main line. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 4 : Scheme Name- Work of construction of apron RCC platforms at inhaul and outhaul of Wagon tipllers 1, 2, 3 & 4 of CHP 3x660MW, KTPS, Koradi. Justification- The 04 Nos. of wagon tipplers are installed at CHP-3x660MW, KTPS, Koradi. In this regards, it is to submit that, the wagon unloading is being carried out through these tipplers. Hence, presence of fugitive dust in tippler area is predominant. The said dust is being accumulated at inhaul and outhaul of wagon tipplers. Due to presence of loaded wagons at inhaul and empty wagons at outhaul, this office gets least opportunity for clearance of the said coal dust along the track. Due to accumulation of coal dust, the rail track parameters along with gradient are getting distubed. The disturbance in gradient is causing rolling of wagons which is not recommended in view of safety of both man and machine. Besides, this due to rolling of wagons, the occurnece of untoward incidence of derailment is predominant. Hence, to maintain uniform rail track gradient it shall be enviable to construct the apron RCC platforms at inhaul and outhaul of Wagon tipplers 1, 2, 3 & 4 of CHP-3x660MW, KTPS, Koradi. Estimated cost- Rs. 4 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 5 : Scheme Name- Work of construction of apron RCC platforms at inhaul and outhaul of Wagon tipllers 1, 2, 3 & 4 of CHP 3x660MW, KTPS, Koradi. Justification- The 04 Nos. of wagon tipplers are installed at CHP-3x660MW, KTPS, Koradi. In this regards, it is to submit that, the wagon unloading is being carried out through these tipplers. Hence, presence of fugitive dust in tippler area is predominant. The said dust is being accumulated at inhaul and outhaul of wagon tipplers. Due to presence of loaded wagons at inhaul and empty wagons at outhaul, this office gets least opportunity for clearance of the said coal dust along the track. Due to accumulation of coal dust, the rail track parameters along with gradient are getting distubed. The disturbance in gradient is causing rolling of wagons which is not recommended in view of safety of both man and machine. Besides, this due to rolling of wagons, the occurnece of untoward incidence of derailment is predominant. Hence, to maintain uniform rail track gradient it shall be enviable to construct the apron RCC platforms at inhaul and outhaul of Wagon tipplers 1, 2, 3 & 4 of CHP-3x660MW, KTPS, Koradi. Estimated cost- Rs. 4 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 6 : Scheme Name- Work of construction of RCC platforms along the rail track of CHP 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. In this regards, it is to submit that, after unloading of rakes the empty rakes are being examined by Railway's C&W staff camped at KTPS, Koradi. Hence, for safe movement of Railway's staff, Railway's is pressing hard for provision of RCC platforms along the rail track of CHP-3x660MW, KTPS, Koradi. Estimated cost- Rs. 10 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 7 : Scheme Name- Work of repairing and construction of RCC permanent revenue canal at, KTPS, Koradi. Justification- The temporary revenue canal is being flowing beside the existing Railway exchange yard of 210 MW, KTPS, Koradi. The said canal gets clogged inview of ash accumulation. Due to clogging this canal overflows and its overrun enters the 210 MW rail yard thereby creating track surface marshy and unsafe for Rail movement. Hence, it is essential to repair and construct RCC permanent revenue canal at KTPS, Koradi so that proper and timely cleaning of canal along with proper outlet can be arranged. Estimated cost- Rs. 15 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme Name-08 Work of construction of RCCretaining wall at Godhani and Kalumna end of KTPS, Koradi. Justification- The separate rail infrastructure has been commissioned for Koradi TPS to cope up the daily coal requirement. The rail traffic at KTPS, Koradi is being catered through Godhani and Kalumna end respectively. In this regards, it is to submit that, the take off points at Godhani and Kalumna both are S&T operated. During monsoon, it is often witnessed that, the rain water enters the plant premises from others land thereby submerging the S&T operated point. Due to this, signals gets lost and hampers the Rail traffic movement completely. Hence, it is essential to restrict the entrance of rain water in plant premises. This can be possible by constructing retaining wall at required loaction. Estimated cost- Rs. 1 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme Name-09 OHE maintenance at CHP, KTPS, Koradi Justification-As per the Railway board circular, Railway's has mandated that OHE maintenance cost for existing as well as new sidings shall be borne by the siding owner in accordance with Railway guidelines. Railway will carry out necessary inspection of maintenance work once in six months. Maintenance charges per TKM per annum of OHE as finalized by SECR zonal office is Rs.291566/- per TKM per annum. Also, inspection charges at the rate of Rs.106974/- per day towards inspection to be carried out by Railways every si x months shall be charged on actual basis by Railway's from the sidings.Accordingly, Railway.s has calimed amount of Rs.31314519/- for two years. Hence for 5 yeards it is expected to be Rs.7.82 Cr. Estimated cost- Rs. 7.82 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 10 Name-Remodelling and upgradation of existing S & T system with Panel Interlocking system and associated S & T gears to S & T system with Electronic Interlocking system and associated S & T gears in connection with services for BG Railway facility (660 MW Rail yard) for Koradi Thermal Power Station of MSPGCL Justification-As per the prevailing Railway norms, it is mandatory to commission the S & T system in private Railway siding for fast and safe movement of Railway’s precious rolling stock. Unless and until remodeling is carried out the S&T system cannot be started at Koradi Railway yard.With commissioning and operation of S & T system there shall be least possibility for derailments during internal shunting through crossovers, as the said points shall be motorized operated. Estimated cost- Rs. 20 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 11 : Work of supply and provision of lights and high mast at CHP Railway exchange yard of 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. In this regards, it is to submit that, after unloading of rakes the empty rakes are being examined by Railway's C&W staff camped at KTPS, Koradi on round the clock basis. Hence, for safe movement of Railway's staff, Railway's is pressing hard for availability of proper illumination in complete yard. Estimated cost- Rs.2.5 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Provision of cover shed for stack yard -2 at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 1 : Provision of cover shed for stack yard -2 at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Procurement of Pipe Conveyor Drive System Internals at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 1 : Procurement of Pipe Conveyor Drive System Internals at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Provision of service building along with vehicle bay at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 1 : Provision of service building along with vehicle bay at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | GENERAL ASSET | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | GENERAL ASSET--AKRDFOGA01-OFFICE FURNITURE | N.A. | - | 0 | 0.57299 | 0.75759 | -0.1846 | 0 | 0 |  |  | 0 | -0.1846
2 | GENERAL ASSET--AKRDFOGA02-COMPUTERS,PRINTER,SCANNER | N.A. | - | 0 | 1.6504 | 2.911 | -1.2606 | 0 | 0 |  |  | 0 | -1.2606
3 | GENERAL ASSET--AKRDFOGA03-AC,WATER COOLER | N.A. | - | 0 | 0.46584 | 0.49898 | -0.033135 | 0 | 0 |  |  | 0 | -0.033135
4 | GENERAL ASSET--AKRDFOGA04-AIR PURIFIER | N.A. | - | 0 | 0 | 0.0105 | -0.0105 | 0 | 0 |  |  | 0 | -0.0105
0 | D) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of KLEP Unit for 'HCSD Pump | 0 | - | 3.73 | 3.73 | 3.73 | 0 | 0 | 0 |  |  | 0 | 0
2 | Restoration of Boiler Circulation Pump at 3X660MW KTPS, Koradi | 0 | - | 0 | 4.73 | 4.73 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of Coal Compartment Assemblies for Unit-10 at 3x660MW KTPS, Koradi. | 0 | - | 0 | 3.73 | 3.73 | 0 | 0 | 0 |  |  | 0 | 0
4 | Repairing and Refurbishment of TDBFP cartridge Model FK6E40 installed at 3X660MW KTPS, Koradi | 0 | - | 0 | 11.86 | 11.86 | 0 | 0 | 0 |  |  | 0 | 0
5 | Non-DPR for Upgradation of Honeywell Make PLC for Mill Reject Handling System installed at 3x660MW Balance of Plant (BOP) Unit- 8, 9 & 10 at Koradi TPS | 0 | - | 0 | 0.85 | 0.85 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of Sky Climber for furnace repairing at 3x660MW KTPS, Koradi | 0 | - | 0 | 3.02 | 3.02 | 0 | 0 | 0 |  |  | 0 | 0
7 | Double Roll Clinker Grinder | 0 | - | 0 | 1.68 | 1.68 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement along with Installation of Clear Water Booster Pump with Motor, Panel Cable and other allied accessories in Unit#10 bottom ash area at AHP, 3x660MW, KTPS, Koradi. | N.A. | - | 0 | 2.8112 | 2.56 | 0.25116 | 0 | 0 |  |  | 0 | 0.25116
9 | Procurement of single Roll Clinker Grinder with Feed Pump & Jet Pump Complete Assembly with modified metallurgy installed at AHP ,3x660MW Units, KTPs, Koradi | N.A. | - | 0 | 3.2868 | 2.12 | 1.1668 | 0 | 0 |  |  | 0 | 1.1668
10 | Work of Repairing and Refurbishment of HIP Rotor along with balancing and over speed trial for L&T-MHI make turbine (Type: TC4F-30”) installed at 3X660MW KTPS, Koradi | N.A. | - | 0 | 7.3532 | 7.13 | 0.22316 | 0 | 0 |  |  | 0 | 0.22316
11 | Procurement of spares for Flue gas distribution dampers, PA fan discharge dampers and Coal mill Hot PA Gate and Dampers at 3x660mw KTPS units through OEM | N.A. | - | 0 | 3.7 | 3.7 | 0 | 0 | 0 |  |  | 0 | 0
12 | Work of Modification & Installation of Take up trolley & arrangement for take up lifting for conveyor BCN-13A at CHP 3X660MW,KTPS,Koradi | N.A. | - | 0 | 356.6331 | 0.75 | 355.8831 | 0 | 0 |  |  | 0 | 355.8831
13 | Work of Design, Modification & streingthening of Tripper trolley structure with provision of Antiwear plates discharge chute box at CHP 3X660MW,KTPS,Koradi | N.A. | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
14 | Upgradation of Management Information System (MIS) Server and Associated Software for C&I at 3x660MW Unit- 8, 9 & 10 at Koradi TPS | N.A. | - | 0 | 2.145 | 2.145 | 0 | 0 | 0 |  |  | 0 | 0
15 | Procurement of Vibrating Tranfer chute with double exciter Drive for stacker reclaimer at CHP,3X660MW,KTPS ,Koradi | N.A. | - | 0 | 0.934 | 0.934 | 0 | 0 | 0 |  |  | 0 | 0
16 | Supply & Installation of Ash Slurry Density Transmitter at High Concentrated Slurry Disposal (HCSD) System of BOP area of 3x660MW Unit- 8, 9 & 10 at Koradi TPS | N.A. | - | 0 | 1.26 | 1.26 | 0 | 0 | 0 |  |  | 0 | 0
17 | Supply & Installation of Fiber Optic Sensing System for Conveyor Health Monitoring At CHP 3x660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 11.72 | 11.72 |  |  | 11.72 | 0
18 | Procurement of Leak- proof make complete Mechanical Seal Assembly for Concrete Volute CW Pump installed at 3X660MW KTPS,Koradi on OEM bASIS. | 0 | - | 0 | 1.94 | 1.94 | 0 | 0 | 0 |  |  | 0 | 0
19 | Work of Design , Engineering , Manufacturing , Supply Erection & Commissioning of Conveyor Belt From Discharge of RBF 1 &2 at Crusher House to Stack Yard At CHP 3x660MW KTPS, Koradi . | 0 | - | 0 | 0 | 0 | 0 | 11.39 | 11.39 |  |  | 11.39 | 0
20 | Supply & Installation of Artificial Intelligence PMMS Accurex Diagnostic matrix based vibration & temperature monitoring for critical auxiliaries at CHP 3x660MW KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 6.431 | 6.431 |  |  | 6.431 | 0
21 | Restoration of online dissolved gas analysers of Unit 8,9,10 | 0 | - | 0 | 0 | 0 | 0 | 1.11 | 1.11 |  |  | 1.11 | 0
22 | Complete Replacement of Existing Water Separator Drain Tank Control (WDC) Valves with New Valves of modified trim design along with hydraulic Actuators, Power Pack assembly, necessary instrumentation, erection & commissioning 3X660MW KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 5.33 | 5.33 |  |  | 5.33 | 0
23 | Procurement of mandatory set of Hydraulic system internals for Wagon Tippler Drive & side arm charger Drive at CHP,3X660MW,KTPS ,Koradi | 0 | - | 0 | 0 | 0 | 0 | 6.35 | 6.35 |  |  | 6.35 | 0
24 | "Supply & installation of Anodized winding Oil cooled over band magnetic separator & control panel for conveyor 5A,5B &13C at CHP 3x660MW KTPS, Koradi. | 0 | - | 0 | 1.896 | 1.896 | 0 | 0 | 0 |  |  | 0 | 0
25 | Procurement of Grinding Wall Assembly for Impact Crusher At CHP 3x660MW KTPS, Koradi | 0 | - | 0 | 2.01 | 2.01 | 0 | 0 | 0 |  |  | 0 | 0
26 | Restoration of Boiler Circulation Pump of U10 at 3X660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 6.69 | 6.69 |  |  | 6.69 | 0
27 | Design,Engineering,Customization,Implementation,Installation & testing of Data Analytical/Artificial Intellegence softwae for automated monitoring & diagnostics system to improve Power plant reliability & efficiency,at one unit of 3X660MW KTPS, Koradi. | 0 | - | 0 | 3.27 | 3.27 | 0 | 0 | 0 |  |  | 0 | 0
28 | Supply of Feed Gate Complete Assembly along with installation to enhance the performance of Feed Gate at Ash Handling Plant, 3x660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 2.4 | 2.4 |  |  | 2.4 | 0
29 | Design, Supply, Installation & Commissioning of Instrument Air Dryer Assembly with Prefilters & Stainless steel piping along with valves suitable for Instrument Air Compressors at AHP, 3x660MW Units, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 5.5 | 5.5 |  |  | 5.5 | 0
| Total |  |  |  | 1683.5363 | 1369.1486 | 314.3877 | 2585.8688 | 2585.8688 | 0 | 0 | 2585.8688 | 314.3877
FY 2026-27
0 | A) Approved Add cap: | 0 | - | 0 | 0
A | BoP | 0 | - | 246.34 | 103.6804 | 232.6929 | -129.0125 | 0 | 0 |  |  | 0 | -129.0125
B | BTG | 0 | - | 44.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B1 | Supply | 0 | - | 13.33 | 0 | 13.33 | -13.33 | 0 | 0 |  |  | 0 | -13.33
B2 | Works | 0 | - | 0.98 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B3 | Taxes and duties | 0 | - | 23.29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B4 | Civil | 0 | - | 0.19 | 0.19 | 0 | 0.19 | 0 | 0 |  |  | 0 | 0.19
B5 | Mandatory Spares | 0 | - | 5.03 | 1.29 | 6.32 | -5.03 | 0 | 0 |  |  | 0 | -5.03
B6 | BTG (L&T) Work | 0 | - | 1.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C | Other Works (Plant) | 0 | - | 136.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C1 | Fully Integrated Security System | 0 | - | 27.36 | 31.4615 | 31.4615 | 0 | 0 | 0 |  |  | 0 | 0
C2 | Administrative Expenses and overhead | 0 | - | 7.25 | 6.69 | 0 | 6.69 | 0 | 0 |  |  | 0 | 6.69
C3 | Contingencies E&M | 0 | - | 0.04 | 0.04 | 0 | 0.04 | 0 | 0 |  |  | 0 | 0.04
C4 | Mobile storage racks, fork lifts, hoists & hydra for material handling in major stores shed | 0 | - | 0.95 | 0.93645 | 0.93645 | 0 | 0 | 0 |  |  | 0 | 0
C5 | Development of working models of Plant Layout, Boiler, Turbine- Generetaor, Coal mill, Fans, etc. at KTC, Koradi. | 0 | - | 1.2 | 1.2 | 0.98604 | 0.21396 | 0 | 0 |  |  | 0 | 0.21396
C6 | Workshop equipment | 0 | - | 0.26 | 0.26192 | 0.26192 | 0 | 0 | 0 |  |  | 0 | 0
C7 | Design, engg, manufacture, supply , erection, testing & commissioning of Ozonization Plant for circulating cooling water system | 0 | - | 54.05 | 31.7683 | 31.6144 | 0.15388 | 0 | 0 |  |  | 0 | 0.15388
C8 | Supply, installation & commissioning of water flow meters including required SCADA software and other accessories for water management system | 0 | - | 5.08 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C9 | Provision of wet ash evacuation system for first two rows of ESP for Unit-8,9 & 19 | 0 | - | 26.59 | 21.69 | 26.3181 | -4.6281 | 0 | 0 |  |  | 0 | -4.6281
C10 | Procurement of portable mercury analyser for flue gas monitoring | 0 | - | 6.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C11 | Administrative Expenses and overhead | 0 | - | 5 | 21.0001 | 0 | 21.0001 | 0 | 0 |  |  | 0 | 21.0001
C12 | Compressor of Hydrogen plant | 0 | - | 1.5 | 1.5 | 0 | 1.5 | 0 | 0 |  |  | 0 | 1.5
C13 | Rail Cum road stone grabbler | 0 | - | 0.85 | 0.85 | 0 | 0.85 | 0 | 0 |  |  | 0 | 0.85
D | Other Works (Civil) | 0 | - | 103.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D1 | Road, Bridges railway system | 0 | - | 20.1 | 0.10806 | 0 | 0.10806 | 0 | 0 |  |  | 0 | 0.10806
0 | S&T System with Panel Interlocking System | 0 | - | 0 | 10.4585 | 10.4596 | -0.0011606 | 0 | 0 |  |  | 0 | -0.0011606
D2 | Staff quarters | 0 | - | 5.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D3 | Other Misc & Unforseen Item | 0 | - | 25.79 | 9.3 | 7.53 | 1.77 | 0 | 0 |  |  | 0 | 1.77
0 | Check Post, Inspection Office & Facility Complex | 0 | - | 0 | 3.6844 | 3.6816 | 0.0028689 | 0 | 0 |  |  | 0 | 0.0028689
0 | CPRI Building | 0 | - | 0 | 6.2046 | 6.2046 | 0 | 0 | 0 |  |  | 0 | 0
0 | Foam cum DCP fire tender- 1 | 0 | - | 0 | 0 | 0.76926 | -0.76926 | 0 | 0 |  |  | 0 | -0.76926
0 | Fire water Bowser-cum-fire Tender- 1No. | 0 | - | 0 | 0.73537 | 0.73537 | 0 | 0 | 0 |  |  | 0 | 0
D4 | Const. facility | 0 | - | 3.28 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D5 | Contigency Other Civil Work | 0 | - | 5.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D6 | Adminstrative Exp. & Overhead (Salary & Overhead, Civil & E&M) | 0 | - | 21.47 | 31.64 | 0 | 31.64 | 0 | 0 |  |  | 0 | 31.64
D7 | Future unforseen works(Jalyukta Shiwar) | 0 | - | 0.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D8 | Landscaping work | 0 | - | 21.76 | 20.53 | 0 | 20.53 | 0 | 0 |  |  | 0 | 20.53
E | Initial Spares | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
E1 | Boiler & its auxilliaries | 0 | - | 14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Procurement of Table liners and Roller liners Of MVM 32R Coal Mills of 3 X 660MW Units at KTPS, Koradi | 0 | - | 0 | 10.0686 | 10.0686 | 0 | 0 | 0 |  |  | 0 | 0
ii | Procurement of couplings for Coal mill MVM 32 R of 3 X 660 MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 1.5944 | -1.5944 | 0 | 0 |  |  | 0 | -1.5944
iii | Procurement of Set of internal spares for Coal Mill Gear Box (KMP-450) for 3 X 660MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 2.2253 | -2.2253 | 0 | 0 |  |  | 0 | -2.2253
E2 | Turbine & its auxilliaries | 0 | - | 18.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | ULTRAFILTRATION MEMBRANE | 0 | - | 0 | 1.6511 | 1.6511 | 0 | 0 | 0 |  |  | 0 | 0
ii | Supply of Main turbine Vibration Monitoring System spares at 3x660MW, KTPS,Koradi. | 0 | - | 0 | 0 | 1.1469 | -1.1469 | 0 | 0 |  |  | 0 | -1.1469
iii | Procurement of Cartridge for Turbine Driven Boiler Feed Pump (Model No.: FK6E40) at 3X660 MW KTPS Koradi | 0 | - | 0 | 14.2864 | 14.2864 | 0 | 0 | 0 |  |  | 0 | 0
iv | Procurement of Critical Insurance Spares for L&T-MHI Make Turbine for attending major overhauling work of Turbine at KTPS, 3x660MW Units Koradi. | 0 | - | 0 | 11.1013 | 11.1013 | 0 | 0 | 0 |  |  | 0 | 0
E3 | Generator & its auxilliaries | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
E4 | Electrical auxilliaries | 0 | - | 1.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Procurement of HT Motors of BOP | 0 | - | 0 | 0 | 0.29335 | -0.29335 | 0 | 0 |  |  | 0 | -0.29335
ii | 0 | 0 | - | 0 | 0 | 0.84594 | -0.84594 | 0 | 0 |  |  | 0 | -0.84594
iii | Supply of Schneider make Differential Protection Relays for 3X660 MW, Koradi (OEM) | 0 | - | 0 | 0 | 0.10502 | -0.10502 | 0 | 0 |  |  | 0 | -0.10502
iv | Supply of Professional Large Format Display for display of DCS parameters PCR | 0 | - | 0 | 0.14885 | 0.14885 | 0 | 0 | 0 |  |  | 0 | 0
v | Procurement of ABT Energy meter with software for 3X660 MW, TPS, Koradi | 0 | - | 0 | 0 | 0.18337 | -0.18337 | 0 | 0 |  |  | 0 | -0.18337
E5 | Outdoor Plant i.e. CHP, AHP, WTP etc | 0 | - | 19.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Procurement of Forced Lubrication system for Premium make Gear box B3-450 installed for bunker conveyor BCN 7A/B at CHP 3X660MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0.15314 | -0.15314 | 0 | 0 |  |  | 0 | -0.15314
ii | Procurement of rotary spares for travel drive of Stacker and conveyor drive system in Coal Handling Plant of 3x660 MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0.35199 | -0.35199 | 0 | 0 |  |  | 0 | -0.35199
iii | Procurement of Complete assembly of Dome Valve ( 100NB, 200NB, 300NB) with power cylinder for dry Ash evacuation system of 3X660MW KTPS, Koradi. | 0 | - | 0 | 0.2225 | 0.2225 | 0 | 0 | 0 |  |  | 0 | 0
iv | Procurement of Modified Apron Pans for M/s. ELECON Engineering Company ltd make Apron Feeder in CHP 3x660MW Units at KTPS, Koradi. | 0 | - | 0 | 3.3233 | 3.3233 | 0 | 0 | 0 |  |  | 0 | 0
v | Procurement of Single Roll Clinker Grinder with Feed Sump and Jet Pump Complete Assembly with Drive, Driven Sprocket and Chain at AHP, 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.56357 | 0.56357 | 0 | 0 | 0 |  |  | 0 | 0
vi | Procurement of spares of Dome Valve (100NB, 200NB, 300NB) for Ash Evacuation System of 3X660MW Unit KTPS, Koradi. | 0 | - | 0 | 0.16431 | 0.16431 | 0 | 0 | 0 |  |  | 0 | 0
vii | 0 | 0 | - | 0 | 0.10064 | 0.10064 | 0 | 0 | 0 |  |  | 0 | 0
viii | 0 | 0 | - | 0 | 0.00708 | 0.00708 | 0 | 0 | 0 |  |  | 0 | 0
ix | Procurement of Hydraulic Motor for Apron feeder in Coal Handling Plant 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.7965 | 0.7965 | 0 | 0 | 0 |  |  | 0 | 0
x | Procurement of Peristaltic Hose Pump (Model no: RP2 – 40) Spares for HCSD System of Ash Handling Plant, 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.20622 | 0.20622 | 0 | 0 | 0 |  |  | 0 | 0
xi | Procurement of spares for HP Water Pump, Mather & Platt make, model 10/12 EME for AHP at 3X660 MW, KTPS, Koradi | 0 | - | 0 | 0.28246 | 0.28246 | 0 | 0 | 0 |  |  | 0 | 0
xii | Procurement of Rotor shaft assembly for M/s. ELECON Engineering Company ltd make Impact Crusher in CHP 3x660MW Units at KTPS, Koradi. | 0 | - | 0 | 0.76369 | 0.76369 | 0 | 0 | 0 |  |  | 0 | 0
xiii | Procurement of Sam Turbo Make Pumps Spare parts for Ash Handling Plant of 3X660 MW Units at KTPS, Koradi | 0 | - | 0 | 0.17166 | 0.17166 | 0 | 0 | 0 |  |  | 0 | 0
xiv | Procurement of Wagon Tippler Spares for M/s. ELECON Engineering Company ltd. make Wagon Tippler in CHP 3X660MW Units at KTPS, Koradi. | 0 | - | 0 | 1.3975 | 1.3975 | 0 | 0 | 0 |  |  | 0 | 0
xv | Procurement of Pneumatic Y Type Control Valve (Blow Valve Size 50mm & 80mm) for Fly Ash Evacuation System of 3X660MW Unit KTPS, Koradi. | 0 | - | 0 | 0.029205 | 0.029205 | 0 | 0 | 0 |  |  | 0 | 0
xvi | Procurement of the various spares required for Warman make Ash Slurry Pump Model 10/8 EEM & Over Flow Pump Model 8/6 EXU installed at AHP, 3X660 MW TPS Koradi through Limited Tender. | 0 | - | 0 | 0.20886 | 0.20886 | 0 | 0 | 0 |  |  | 0 | 0
xvii | 0 | 0 | - | 0 | 0.0076261 | 0.032797 | -0.025171 | 0 | 0 |  |  | 0 | -0.025171
xviii | Procurement of Spares of Single Roll Clinker Grinder Ayems Engineers make, Model AE-1005-89-100 at AHP, 3X660 MW Koradi TPS. | 0 | - | 0 | 0.82826 | 0.82826 | 0 | 0 | 0 |  |  | 0 | 0
xix | Procurement of Hydraulic Motor for Bucket Wheel of Stacker Reclaimer in CHP, 3X660MW, KTPS, Koradi. | 0 | - | 0 | 1.1168 | 1.1168 | 0 | 0 | 0 |  |  | 0 | 0
xx | Procurement of Rotors, Maintenance Kits, Couplings and other spares required for Atlas Copco make Instrument Air Compressor of Ash Handling Plant of 3 X 660 MW Units at KTPS, Koradi. | 0 | - | 0 | 1.1828 | 1.1828 | 0 | 0 | 0 |  |  | 0 | 0
xxi | Procurement of spares of intermediate conveyor | 0 | - | 0 | 0 | 0.3186 | -0.3186 | 0 | 0 |  |  | 0 | -0.3186
xxii | Procurement of Hydraulic motor for wagon tippler drive in CHP, 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.46494 | 0.46494 | 0 | 0 | 0 |  |  | 0 | 0
xxiii | Procurement of GEHO Pump (Model No. TZPM 400) Spares of Ash Handling Plant, 3 X 660 MW Units, KTPS, Koradi. | 0 | - | 0 | 0 | 0.83656 | -0.83656 | 0 | 0 |  |  | 0 | -0.83656
xxiv | Procurement of Beater Arms for Impact crushers installed at in Coal Handling Plant of 3x660 MW at KTPS, Koradi. | 0 | - | 0 | 0 | 1.0093 | -1.0093 | 0 | 0 |  |  | 0 | -1.0093
xxv | Supply of Atlas Copco make compressor spares for at Koradi TPS 660MW | 0 | - | 0 | 0 | 0.39813 | -0.39813 | 0 | 0 |  |  | 0 | -0.39813
xxvi | Procurement of spares for side arm charger, wagon tippler, impact crushers and stacker reclaimer at CHP 3x660 MW KTPS | 0 | - | 0 | 0.010573 | 0.43684 | -0.42626 | 0 | 0 |  |  | 0 | -0.42626
xxvii | Procurement of Beater heads with Pin for Impact crushers installed at in Coal Handling Plant of 3x660 MW at KTPS, Koradi. | 0 | - | 0 | 0 | 1.1256 | -1.1256 | 0 | 0 |  |  | 0 | -1.1256
xxviii | Procurement of spares of Hyd Motor of SAC | 0 | - | 0 | 0 | 0.36029 | -0.36029 | 0 | 0 |  |  | 0 | -0.36029
xxix | Procurement of hydraulic power packs for Flap Gates in CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0.1888 | -0.1888 | 0 | 0 |  |  | 0 | -0.1888
xxx | Procurement of Mobile Grilling Equipment for CHP 3x660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0.33866 | -0.33866 | 0 | 0 |  |  | 0 | -0.33866
xxxi | Procurement of Weld overlay Flap Gate assembly in CHP 3x660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0.5841 | -0.5841 | 0 | 0 |  |  | 0 | -0.5841
E6 | Capital Spares | 0 | - | 89.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of critical insurance spares for Turbine & its critical auxiliaries for 3 x 660 MW, Koradi (4370001538 dtd. 18/06/2018 d.p. 21 Months) | 0 | - | 89.62 | 89.6234 | 88.736 | 0.88736 | 0 | 0 |  |  | 0 | 0.88736
E7 | Additional Capitalization | 0 | - | 57.88 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Contruction of various infrastructure such as roads etc and public amenities in the rehabilitated villages of koradi and khasara | 0 | - | 13.1 | 12.74 | 0 | 12.74 | 0 | 0 |  |  | 0 | 12.74
ii | Procurement of 7 nos of school buses | 0 | - | 2 | 1.3109 | 1.3109 | 0 | 0 | 0 |  |  | 0 | 0
iii | Development of green belt & fodder farm for fulfillment of environmental clearance of MoEF for Koradi 3x660MW | 0 | - | 3.16 | 3.16 | 0 | 3.16 | 0 | 0 |  |  | 0 | 3.16
iv | Provision of Ground Hopper & Short Conveyor Belt from Existing Stackyard 1 & 2 ti existing Main Stream i.e. BCN 4A/4B of CHP 3x660 MW, KTPS, Koradi | 0 | - | 4.36 | 4.3555 | 4.3555 | 0 | 0 | 0 |  |  | 0 | 0
v | Provision of Ground Hopper & Conveyor Belt for Conveying Unloaded Coal form Open Wagon Tippler in CHP of Koradi Unit 8, 9 & 10. | 0 | - | 4.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
vi | Provision of Additional Facility for Manual Unloading Track in CHP of Koradi Unit No. 8, 9 & 10 | 0 | - | 5.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
vii | Construction of drains | 0 | - | 4.31 | 2.7927 | 0 | 2.7927 | 0 | 0 |  |  | 0 | 2.7927
viii | Supply erection commissioning of medium voltage variable frequency drive for conveyors BCN 6A,6B,7A,7B in CHP 3x660MW | 0 | - | 17 | 16.9859 | 16.9859 | 0 | 0 | 0 |  |  | 0 | 0
ix | Supply, Installation & commissioning of 3D level sensors for first two ESP field hoppers | 0 | - | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
F | Koradi TPS 3x660 MW Expansion Project – Construction of 2nd raising of existing Khasara Ash Bund from T.B.L. 308.50 M to T.B.L 312.00 M with construction of concrete dam (Broad crest weir structure), approach to drain wells and raising height of drain well No. 1, 2 & 3, construction of ash Compartment, cleaning of Khasara bund Nallah and construction of peripheral roads connecting to nearby villages for Khasara ash bund at TPS Koradi | 0 | - | 86.914 | 88.683 | 93.291 | -4.608 | 0 | 0 |  |  | 0 | -4.608
G | Discharge of UDL | 0 | - | 0 | 111.97 | 111.48 | 0.49 | 0 | 0 |  |  | 0 | 0.49
H | Asset Addition due to change in classification of inventory | 0 | - | 0 | 21.7503 | 0 | 21.7503 | 0 | 0 |  |  | 0 | 21.7503
I | Medical Oxygen Gr&Cyl Ozonization Plant (Covid Related Work) | 0 | - | 0 | 11.4034 | 9.6702 | 1.7332 | 0 | 0 |  |  | 0 | 1.7332
0 | B) DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (i) Submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Flue Gas Desulphurization FGD is for Unit 8, 9, 10 of 3x660MW Koradi TPS | MERC/CAPEX/FY 2020-21/WFH/SBR/05 | 2020-05-31 | 940 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Flue Gas Desulphurization is for Unit 8, 9, 10 of 3x660MW Koradi TPS | MERC/CAPEX/FY 2020-21/WFH/SBR/05 | 2020-05-31 | 847.78 | 1089.3 | 1089.3 | 0 | 466.85 | 466.85 |  |  | 466.85 | 0 | 0 | 466.85
0 | IDC | MERC/CAPEX/FY 2020-21/WFH/SBR/05 | 2020-05-31 | 92.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13 | Construction of new admin building at Vidyut Bhavan, Katol Road, Nagpur | MERC/Capex/2021-2022/MSPGCL/063 | 2022-02-18 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13.1 | Construction of new admin building at Vidyut Bhavan, Katol Road, Nagpur | 0 | 2022-02-18 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | 2022-02-18 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Improvement in Regenerative Air Pre-heater Performance at Unit # 9 of 3x660 MW, Koradi TPS | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 15.869 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Procurement of heating elements for RAPH installed in Unit 9 (660MW) at KTPS Koradi THROUGH LIMITED TENDER | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 15.33 | 11.8 | 11.8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.2 | Replacement of heating elements for RAPH installed in Unit 9 (660MW) at KTPS Koradi | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 0.349 | 0.37 | 0.37 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 0.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | CHP Improvement (7 Nos) Schemes & Procurement of Bulldozers, Wheel Loaders and Hydraulic Cranes at CHP 3X660MW, KTPS, Koradi | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 38.87 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Sch-1: Revamping of Apron Feeder in CHP at 3X660MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.68 | 4.68 | 4.68 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Sch-2: Procurement of Hydraulic motors and pumps in CHP at 3X660 MW, KTPS, Koradi | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.44 | 4.44 | 4.44 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.3 | Sch-3: Capacity enhancement of Hydraulic motor of Apron Feeder in CHP, 3X660 MW, KTPS, Koradi | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 2.01 | 2.01 | 2.01 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.4 | Sch-4: Modification, supply and replacement of Transfer chutes in CHP 3x660MW KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.39 | 4.39 | 4.39 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.5 | Sch-5: Design, supply, installation & commissioning of High performance IGUS energy chain system with chain flex cable for Tripper trolleys at CHP at 3x660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.37 | 4.37 | 4.37 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.6 | Sch-6: Procurement of B3-630 gear box for BCN 6 A/B in CHP at 3x660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 0.57 | 0.57 | 0.57 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.7 | Sch-7: Supply and installation of Belt tear detector system for conveyor belt in CHP 3x660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 1.18 | 1.18 | 1.18 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.8 | Sch-8: Procurement of 5 Nos of Bulldozers BD 155 at CHP 3X660 MW Koradi Thermal Power station. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 12.83 | 12.83 | 12.83 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.9 | Sch-9:- Procurement of 02 nos. of Wheel loaders at CHP 3X660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 3.07 | 3.07 | 3.07 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Sch-10:- Procurement of 15 Ton & 20 Ton capacity hydraulic Cranes at CHP 3X660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 0.69 | 0.69 | 0.69 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 0.64 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Construction of bridge cum bandhara across Pond No. 3 and allied works at Pond No. 3 at Koradi TPS | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 33.116 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Construction of cement concrete bridge cum bandhara alongwith gated arrangement. | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 14.75 | 14.75 | 14.75 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.2 | Construction of earthen embankment connecting bridge cum bandhara on both side of embankment by excavating soil / typha / silt from Pond No.3 & tree plantation. | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 14.3252 | 14.3252 | 14.3252 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.3 | Providing structural steel pathway on the existing waste weir (west side of the Pond No.3) and roads connecting to bridge behind Pond No.3 and bridge cum bandhara. | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 2.4308 | 2.4308 | 2.4308 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 1.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement & replacement of Superheater Pass Economizer Coils (Modified Design) for Unit 8, 9 & 10 at 3x660MW KTPS, Koradi | Not Approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Procurement & replacement of Superheater Pass Economizer Coils (Modified Design) for Unit 8, 9 & 10 at 3x660MW KTPS, Koradi | Not Approved | - | 0 | 96.28 | 96.28 | 0 | 48.14 | 48.14 |  |  | 48.14 | 0
0 | IDC | Not Approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Improvement in Boiler Performance at U-8,9 & 10 KTPS, Koradi | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 62.929 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Scheme-1: Procurement of Blade Sets for ID, FD & PA Fans at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 11.34 | 11.34 | 11.34 | 0 | 0 | 0 |  |  | 0 | 0
7.2 | Scheme-2: Procurement of RAPH Bottom Support Bearing Assembly at 3X660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 2.478 | 2.478 | 2.478 | 0 | 0 | 0 |  |  | 0 | 0
7.3 | Scheme-3: Procurement of RAPH Top Guide Bearing Assembly at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 0.684 | 0.684 | 0.684 | 0 | 0 | 0 |  |  | 0 | 0
7.4 | Scheme-4: Procurement of RAPH Gear Box at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 3.44 | 3.44 | 3.44 | 0 | 0 | 0 |  |  | 0 | 0
7.5 | Scheme-5: Procurement of RAPH Spares at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 1.13 | 1.13 | 1.13 | 0 | 0 | 0 |  |  | 0 | 0
7.6 | Scheme-6: Procurement of Coal Burner Assembly with windbox air nozzles for Unit 8 & 9 at 3x660MW. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 15.407 | 15.407 | 15.407 | 0 | 0 | 0 |  |  | 0 | 0
7.7 | Scheme-7: Procurement of Boiler Circulation Pump (BCP) with Impeller & Diffuser at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 11.12 | 11.12 | 11.12 | 0 | 0 | 0 |  |  | 0 | 0
7.8 | Scheme-8: Procurement and Replacement of Heating Elements for RAPH Installed for Unit 8 at 3x660MW. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 15.96 | 15.96 | 15.96 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 1.37 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Design, Engineering, Supply, Installation, Testing, Commissioning including all civil works for Natural resource treatment and Laboratory equipment with mandatory spares at Koradi TPS, 3 X 660 MW | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 49.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.1 | Supply of Natural resource treatment and lab equipment for Water, Coal, Oil, Meteorology with supporting AI computing, all auxiliaries, and accessories. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 35.28 | 42.5744 | 42.5744 | 0 | 0 | 0 |  |  | 0 | 0
23.2 | Supply of Mandatory spares on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.8 | 0.944 | 0.944 | 0 | 0 | 0 |  |  | 0 | 0
23.3 | Supply of Tools and Tackles on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.15 | 0.177 | 0.177 | 0 | 0 | 0 |  |  | 0 | 0
23.4 | Complete Civil Work with 10 KLD ETP/ STP on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 3.6 | 4.25 | 4.25 | 0 | 0 | 0 |  |  | 0 | 0
23.5 | Services - Charges of Inland transport of plant and equipment on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.2 | 0.236 | 0.236 | 0 | 0 | 0 |  |  | 0 | 0
23.6 | Charges for Testing, Commissioning and PG Test of plant and equipment. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.05 | 0.059 | 0.059 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Improvement in Regenerative Air Preheater Performance & Complete Replacement of NDCT fills at Unit # 10, Koradi TPS | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 25.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.1 | Procurement of heating elements for RAPH installed in Unit 10 (660MW) at KTPS Koradi through OEM | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 12.23 | 14.521 | 14.521 | 0 | 0 | 0 |  |  | 0 | 0
24.2 | Complete Supply & Replacement of NDCT fills of U#10. | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 13 | 13 | 13 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 0.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 14 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 14.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 10.994 | 10.994 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 15 | HMI (Human Machine Interface) Upgradation of ‘SSPA-T3000’ DCS (Distribution Control System), Rockwell make PLC System installed at 3x660MW Unit No. 8, 9 & 10 at Koradi TPS and HMI (Human Machine Interface) Upgradation of MaxDNA DCS System at Unit 8-9, CSTPS, Chandrapur | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 55.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 15.1 | Supply: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 10.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 15.2 | Works: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | HMI (Human Machine Interface) Upgradation of ‘SPPA-T3000’ DCS (Distributed Control System) installed at 3x660MW Unit- 8, 9 & 10 at Koradi TPS to match with the external aspects and process improvement | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 24.33 | 24.33 | 24.33 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Upgradation of Rockwell Make PLC System installed at 3x660MW ,Koradi TPS to match with the external aspects and process improvement.(C&I) | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 20.2 | 20.2 | 20.2 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Work of provision of platform beside railway siding at backside of chord cabin for loading of fly ash in railway wagon for ash utilization at 3x660 MW TPS, Koradi | 0 | - | 0 | 0.0038356 | 0.0038356 | 0 | 0 | 0 |  |  | 0 | 0
13 | Capital Exenditure schemes for in-principle clearance regarding "EPC contract for the wok of construction of quarters and development of KTPS colony at Koradi" under CAPEX scheme | MERC/CAPEX/MSPGCL/2024-12/0569 DTD.13.09.2024 | 2024-09-13 | 210.48 | 200 | 200 | 0 | 10.48 | 10.48 |  |  | 10.48 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of spares for L&T-MHI make Turbine for COH work of Turbine at KTPS, 3x660MW units Koradi | MERC/CAPEX/MSPGCL/2023-24/0639 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement of spares for L&T-MHI make Turbine for COH work of Turbine at KTPS, 3x660MW units Koradi | MERC/CAPEX/MSPGCL/2023-24/0639 | - | 0 | 31.6358 | 31.6358 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Procurement of HP Nozzle assembly for L&T-MHI Make Turbine installed at 3x660MW Units Koradi | MERC/CAPEX/MSPGCL/2023-24/0639 | - | 0 | 4.189 | 4.189 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | C) DPRs Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Control & instrumentation related Various Upgradation schemes viz.Emission Monitoring & Water Quality Analysers ,Vibration Monitoring Schemes,Water Flow Monitoring etc. at 3X660MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Upgradation of Emission Monitoring Analysers | 0 | - | 0 | 9.58 | 9.58 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Upgradation of Water Quality Analysers | 0 | - | 0 | 5.33 | 5.33 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Revamping & Supply Of Upgraded VM7B Version of Vibration Monitoring Rack | 0 | - | 0 | 4.84 | 4.84 | 0 | 0 | 0 |  |  | 0 | 0
2.4 | Implementation of ‘Flow Monitoring System’ at 3x660MW Balance of Plant (BOP) Unit- 8, 9 & 10 at Koradi TPS | 0 | - | 0 | 6.87 | 6.87 | 0 | 0 | 0 |  |  | 0 | 0
3 | CHP Improvement Scheme-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Supply, Erection, Commissioning of set of Internals for Wagon Tipplers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 10.96 | 10.96 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Supply, Erection, Commissioning of set of Internals for Side Arm Chargers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 3.54 | 3.54 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Supply, Erection, Commissioning of set of Internals for Wobbler Feeders at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 4.96 | 4.96 | 0 | 0 | 0 |  |  | 0 | 0
3.4 | Supply, Erection, Commissioning of set of Internals for Apron Feeders at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 15.55 | 15.55 | 0 | 0 | 0 |  |  | 0 | 0
3.5 | Supply, Erection, Commissioning of set of Internals for Impact Crushers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 9.63 | 9.63 | 0 | 0 | 0 |  |  | 0 | 0
3.6 | Supply, Erection, Commissioning of set of Internals for Stacker cum Reclaimers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 6.26 | 6.26 | 0 | 0 | 0 |  |  | 0 | 0
4 | Performance improvement and availability of various Auxiliaries of TG at 3x660MW KTPS Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Performance improvement and availability of various Auxiliaries for Oil Systems of Main Turbine. | 0 | - | 0 | 3.26 | 3.26 | 0 | 0 | 0 |  |  | 0 | 0
4.2 | Performance improvement and availability of various Auxiliaries of Generator System. | 0 | - | 0 | 7.31 | 7.31 | 0 | 0 | 0 |  |  | 0 | 0
4.3 | Performance improvement and availability of Feed Water System. | 0 | - | 0 | 10.54 | 10.54 | 0 | 0 | 0 |  |  | 0 | 0
4.4 | Performance improvement and availability of Vacuum System. | 0 | - | 0 | 2.28 | 2.28 | 0 | 0 | 0 |  |  | 0 | 0
4.5 | Performance improvement and availability of CEP System. | 0 | - | 0 | 7.83 | 7.83 | 0 | 0 | 0 |  |  | 0 | 0
4.6 | Procurement of Complete Pull out Assembly along with Impeller and wear ring of Cooling Water Pump. | 0 | - | 0 | 14.87 | 14.87 | 0 | 0 | 0 |  |  | 0 | 0
4.7 | Procurement of complete assembly of HP and LP Elements for Atlas Copco make Compressors. | 0 | - | 0 | 4.19 | 4.19 | 0 | 0 | 0 |  |  | 0 | 0
5 | Improvement in Wet ash evacuation system at 3x660MW Units, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Procurement & installation of Ash Slurry Series Pump Assembly with modified metallurgy and Critical Wet End Sub Assembly to enhance the performance & slurry disposal capacity. | 0 | - | 0 | 7.53 | 7.53 | 0 | 0 | 0 |  |  | 0 | 0
5.2 | Procurement & installation of Ash Slurry Series Pump Assembly with modified metallurgy along with Gear Box, Fluid Coupling & Motor (4’th Series) and Critical Wet End Sub Assembly to enhance the performance & slurry disposal capacity. | 0 | - | 0 | 2.51 | 2.51 | 0 | 0 | 0 |  |  | 0 | 0
5.3 | Procurement & installation of Overflow Transfer Pump Assembly with upgradation in metallurgy and Critical Wet End Sub Assembly to enhance the performance. | 0 | - | 0 | 3.59 | 3.59 | 0 | 0 | 0 |  |  | 0 | 0
5.4 | Procurement & installation of IAC Compressor Assembly: Model –ZR110 STD 7.5 IMD Atlas Copco Make Oil free water cooled screw air compressor with inbuilt atlas copco make heat of compression single drum rotator air dryer to enhance the performance. | 0 | - | 0 | 7.56 | 7.56 | 0 | 0 | 0 |  |  | 0 | 0
6 | HMI Upgradation of Diasys Netmation DCS at 3x660MW KTPS Koradi Units 8,9 & 9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | HMI Upgradation of Diasys Netmation DCS at 3x660MW KTPS Koradi Units 8,9 & 10 | 0 | - | 0 | 77.15 | 77.15 | 0 | 0 | 0 |  |  | 0 | 0
7 | Improvement in Dry ash evacuation system at 3x660MW Units, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Procurement of Ingersoll Rand Make Transport Air Compressors Critical/Non-Critical Spares sub-assembly for performance improvement. | 0 | - | 0 | 29.57 | 29.57 | 0 | 0 | 0 |  |  | 0 | 0
8 | MSERW Pipes for Garlanding arrangement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.1 | Work of Garlanding arrangement to changeover ash slurry feed points for even filling of pond by providing MSERW Pipes along the periphery of Ash Bund Dyke Wall at Khasara Ash Bund. | 0 | - | 0 | 98.83 | 98.83 | 0 | 0 | 0 |  |  | 0 | 0
9 | Capacity Enhancement & Performance optimization at WTP 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.1 | Capacity enhancement of DM water stream in WTP at 3X660MW, KTPS, Koradi. | 0 | - | 0 | 58.94 | 58.94 | 0 | 0 | 0 |  |  | 0 | 0
9.2 | Capacity enhancement Condensate polishing unit regeneration area in WTP at 3X660 MW, KTPS, Koradi | 0 | - | 0 | 13.41 | 13.41 | 0 | 0 | 0 |  |  | 0 | 0
9.3 | Provision of Ozone generating plant of 1.0 Kg capacity in WTP at 3X660 MW, KTPS, Koradi | 0 | - | 0 | 5.84 | 5.84 | 0 | 0 | 0 |  |  | 0 | 0
10 | DPR for Construction of CC Road alongwith RCC Drain, CC platform for heavy machinery movement at 3x660 MW, TPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.1 | DPR for Construction of CC Road alongwith RCC Drain, CC platform for heavy machinery movement at 3x660 MW, TPS, Koradi | 0 | - | 0 | 33.57 | 33.57 | 0 | 0 | 0 |  |  | 0 | 0
11 | Improvement in Coal Mill Performance-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.1 | Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi through OEM. | 0 | - | 0 | 6.15 | 6.15 | 0 | 0 | 0 |  |  | 0 | 0
11.2 | Procurement of Mill Rotary Separator Blades for coal mill MVM 32R at 3x660 MW, KTPS, Koradi through open tender | 0 | - | 0 | 4.01 | 4.01 | 0 | 0 | 0 |  |  | 0 | 0
11.3 | Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi through OEM. | 0 | - | 0 | 14.57 | 14.57 | 0 | 0 | 0 |  |  | 0 | 0
11.4 | Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi through OEM | 0 | - | 0 | 6.14 | 6.14 | 0 | 0 | 0 |  |  | 0 | 0
12 | Improvement in Boiler performance-II at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.1 | Scheme1:Procurement of Coal compartment assembly for Unit8 at 3x660MW KTPS, Koradi | 0 | - | 0 | 12.7 | 12.7 | 0 | 0 | 0 |  |  | 0 | 0
12.2 | Scheme2:Procurement of blade sets for ID, FD & PA Fan at 3x660 MW, Units at KTPS Koradi through OEM. | 0 | - | 0 | 11.34 | 11.34 | 0 | 0 | 0 |  |  | 0 | 0
12.3 | Scheme3:Procurement of RAPH internal Spares for 3X660MW units at KTPS Koradi through OEM (Qty- 6 Sets) | 0 | - | 0 | 1.13 | 1.13 | 0 | 0 | 0 |  |  | 0 | 0
12.4 | Scheme4:Procurement of RAPH Sector plate with Actuating mechanism assembly for Unit9 3 X 660MW Units at KTPS, Koradi. | 0 | - | 0 | 7.2 | 7.2 | 0 | 0 | 0 |  |  | 0 | 0
13 | Improvement in Coal Mill performance-II at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | Procurement of FLENDER make Gearbox model kmp-450 along with motor for coal mill MVM32R at 3x660mw KTPS, koradi through OEM. | 0 | - | 0 | 20.91 | 20.91 | 0 | 0 | 0 |  |  | 0 | 0
13.2 | Procurement of complete set of couplings for PA, ID & FD fans at 3X660MW units at KTPS Koradi through OEM | 0 | - | 0 | 5.14 | 5.14 | 0 | 0 | 0 |  |  | 0 | 0
14 | Improvement in Coal Mill performance-III at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 6.15 | 6.15 | 0 | 0 | 0 |  |  | 0 | 0
14.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 14.57 | 14.57 | 0 | 0 | 0 |  |  | 0 | 0
14.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 6.14 | 6.14 | 0 | 0 | 0 |  |  | 0 | 0
14.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit10 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
14.5 | Scheme5:Procurement of Complete MRHS System along with Pneumatic Compressors at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
15 | Improvement in Boiler performance-III at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | Scheme1:Procurement of Coal compartment assembly for Unit8at 3x660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 12.7 | 12.7 |  |  | 12.7 | 0
15.2 | Scheme2:Procurement of blade sets for ID, FD & PA Fan at 3x660 MW, Units at KTPS Koradi through OEM. | 0 | - | 0 | 0 | 0 | 0 | 11.34 | 11.34 |  |  | 11.34 | 0
15.3 | Scheme3:Procurement and replacement of heating elements for RAPH installed in Unit 9 (660MW) at KTPS Koradi THROUGH OEM/OES (Qty- 2 Sets) | 0 | - | 0 | 0 | 0 | 0 | 16 | 16 |  |  | 16 | 0
15.4 | Scheme4:Procurement of HP valves, safety valves and ERV's for 3X660MW units at KTPS Koradi through OEM | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
15.5 | Scheme5:Procurement of RAPH Sector plate with Actuating mechanism assembly for Unit8 3 X 660MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 7.2 | 7.2 |  |  | 7.2 | 0
15 | Improvement in Coal Mill performance-IV at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 6.15 | 6.15 |  |  | 6.15 | 0
15.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 14.57 | 14.57 |  |  | 14.57 | 0
15.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 6.14 | 6.14 |  |  | 6.14 | 0
15.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit8 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
16 | Improvement in Coal Mill performance-V at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit9 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | Improvement in Boiler performance-IV at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.1 | Scheme1:Procurement of Coal compartment assembly for Unit8 at 3x660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.2 | Scheme2:Procurement of blade sets for ID, FD & PA Fan at 3x660 MW, Units at KTPS Koradi through OEM. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.3 | Scheme3:Procurement of RAPH bottom support bearing assembly for 3X660MW units at KTPS Koradi through OEM (Qty- 2 Sets) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.4 | Scheme4:Procurement of RAPH top guide bearing assembly for 3X660MW units at KTPS Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.5 | Scheme5:Procurement of RAPH Gear Box for 3X660MW units at KTPS Koradi through OEM (Qty- 1 Sets) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.6 | Scheme6:Procurement of RAPH Sector plate with Actuating mechanism assembly for Unit10 at 3 X 660MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.7 | Scheme7:Procurement and replacement of heating elements for RAPH installed in Unit 10 (660MW) at KTPS Koradi THROUGH OEM/OES (Qty- 2 Sets) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.8 | Scheme8:Procurement of Boiler Circulating Pump (1 Nos) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | Improvement in Coal Mill performance-VI at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit9 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.3 | Reliability Improvement schemes of generators at 3X660MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | Scheme No. 1 :PROCUREMENT OF MELCO/LMTG MAKE GENERATOR ROTOR ASSEMBLY with excitation transformer AT 3X660MW KTPS, KORADI THROUGH OEM | 0 | - | 0 | 45.39 | 45.39 | 0 | 0 | 0 |  |  | 0 | 0
19.2 | Scheme No. 2:PROCUREMENT OF ONE COMPLETE SET OF GENERATOR STATOR COILS FOR GENERATOR AT 3X660MW UNITS AT KTPS KORADI THROUGH OEM | 0 | - | 0 | 35.4 | 35.4 | 0 | 0 | 0 |  |  | 0 | 0
25 | DPR on Procurement of Critical Speares for L&T make Main Turbine(typeTC4F-30) installed at 3x660MW KTPS Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.1 | Scheme No. 1 :Procurement of Critical Speares for L&T make Main Turbine(typeTC4F-30) installed at 3x660MW KTPS Koradi. | 0 | - | 0 | 126.41 | 126.41 | 0 | 0 | 0 |  |  | 0 | 0
26 | DPR for Coal Handling Plant Performance Improvement Schemes -II at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.1 | Scheme No. 1 : Performance Improvement of Unloading System Wagon Tipplers at CHP 3x660MW KTPS Koradi | 0 | - | 0 | 5.8 | 5.8 | 0 | 0 | 0 |  |  | 0 | 0
26.2 | Scheme No. 2 : Performance Improvement of Unloading System Side Arm Chargers at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Side Arm Charger Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 2.8 | 2.8 | 0 | 0 | 0 |  |  | 0 | 0
26.3 | Scheme No. 3 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 3.2 | 3.2 | 0 | 0 | 0 |  |  | 0 | 0
26.4 | Scheme No. 4 : Performance Improvement of Stacking & Reclaiming System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Stacking & Reclaiming System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 6.5 | 6.5 | 0 | 0 | 0 |  |  | 0 | 0
26.5 | Scheme No. 5 : Performance Improvement of Crushing System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Impact Crusher & Wobbler Feeders Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 8.5 | 8.5 | 0 | 0 | 0 |  |  | 0 | 0
26.6 | Scheme No. 6 : Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -1 at CHP 3x660MW KTPS Koradi A) Brief scope of work: Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -1 at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
27 | DPR for Coal Handling Plant Performance Improvement Schemes -III at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.1 | Scheme No. 1 : Performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Hydraulic system for Wagon Tippler, Side Arm Charger , Apron Feeder ( 1 & 2) Stacker Reclaimer 1 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 10.5 | 10.5 | 0 | 0 | 0 |  |  | 0 | 0
27.2 | Scheme No. 2 : Construction of Air tight Hydraulic power pack room along with necessary cooling system for performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Construction of Air tight Hydraulic power pack room along with necessary cooling system for Wagon Tippler & Apron Feeder ( 1 to 4) Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 3.2 | 3.2 | 0 | 0 | 0 |  |  | 0 | 0
27.3 | Scheme No. 3 : Performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory Hydraulic Power Cylinders of Wagon Tippler, Side Arm Charger ( 1 to 4) Stacker Reclaimer 1 & 2 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
27.4 | Scheme No. 4 : Performance Improvement of Stacker Reclaimer by providing Hydraulic Drive to Boom Conveyor at CHP 3x660MW KTPS Koradi A) Brief scope of work: Hydraulic Drive to Boom Conveyor Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.9 | 0.9 | 0 | 0 | 0 |  |  | 0 | 0
27.5 | Scheme No. 5 : Performance Improvement of Illumination system with energy conservation at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Solar High masts along the rail track in railway yard Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 3.75 | 3.75 | 0 | 0 | 0 |  |  | 0 | 0
27.6 | Scheme No. 6 : Design, Supply & Installation of LT VFD Drives for Critical Conveyors at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of LT VFD Drives for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
27.7 | Scheme No. 7 : Design , supply, Erection & Commissioning of Short Conveyor for Stacking Purpose at CHP 3x660MW KTPS Koradi A) Brief scope of work: Short Conveyor for Stacking Purpose at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 9.6 | 9.6 | 0 | 0 | 0 |  |  | 0 | 0
27.8 | Scheme No. 8 : Capacity Enhancement of BCN-7/5/4/3 /1 AB in CHP 3x660MW KTPS Koradi A) Brief scope of work: Short Conveyor for Stacking Purpose at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 8.6 | 8.6 | 0 | 0 | 0 |  |  | 0 | 0
27.9 | Scheme No. 9 : Design , Engineering & modification along with strengthening of Existing Travel Track structure for Side Arm Charger & Stacker Reclaimer A) Brief scope of work: strengthening of Existing Travel Track structure for Side Arm Charger & Stacker Reclaimer Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
27.1 | Scheme No. 10 : Design , Engineering & Erection of modified Energy Efficient Ventilation System for Wagon Tippler Complex Area in CHP 3X660MW KTPS Koradi A) Brief scope of work: Energy Efficient Ventilation System for Wagon Tippler Complex Area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
27.11 | Scheme No. 11 : Design , Engineering & Installtion of Vibration & temprature Monitoring Systems for critical auxiliaries in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Installtion of Vibration & temprature Monitoring Systems for critical auxiliaries Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
27.12 | Scheme No. 12 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
27.13 | Scheme No. 13 : Design , Engineering & Provision of Stone Grappling Equipment System for Wagon Tippler 3 &4 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Stone Grappling Equipment System for Wagon Tippler 3 &4 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.9 | 0.9 | 0 | 0 | 0 |  |  | 0 | 0
27.14 | Scheme No. 14 : Design , Engineering & Provision of Public Addressing System for Wagon Tippler Complex in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Public Addressing System for Wagon Tippler Complex in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
27.15 | Scheme No. 15 : Design , Engineering & Provision of Belt Tracking System for Critical Conveyors in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Belt Tracking System for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
27.16 | Scheme No. 16 : Design , Engineering & Provision of Dust supression System for stacker reclaimer-1 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.6 | 0.6 | 0 | 0 | 0 |  |  | 0 | 0
27.17 | Scheme No. 17 : Work of Life Enhancement of wobbler Feeder 1 &2 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.6 | 1.6 | 0 | 0 | 0 |  |  | 0 | 0
28 | DPR for Coal Handling Plant Performance Improvement Schemes -IV at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28.1 | Scheme No.1 : Design , Engineering , Supply & Installation of Modular Transfer chutes for Critical Conveyor System in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of Modular Transfer chutes for Conveyor System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 14 | 14 | 0 | 0 | 0 |  |  | 0 | 0
28.2 | Scheme No.2 :Upgradtion of Exsisting Fire Fighting System at Stack yard area in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradtion of Exsisting Fire Fighting System at Stack yard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 2.6 | 2.6 | 0 | 0 | 0 |  |  | 0 | 0
28.3 | Scheme No.3 : Design , Engineering , Supply & Strengthening of engineering structure of BCN- 7A/B along with track alignment in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Strengthening of engineering structure of BCN- 7A/B Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 2.4 | 2.4 | 0 | 0 | 0 |  |  | 0 | 0
28.4 | Scheme No.4 : Design , Engineering , Supply & Installation of Mist Cannon Spray System around stackyard area in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of Mist Cannon Spray System at stackyard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.6 | 1.6 | 0 | 0 | 0 |  |  | 0 | 0
28.5 | Scheme No.5 : Design , Engineering , Supply & Installation of EOT cranes at Bunker in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of EOT cranes at Bunker Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 4.5 | 4.5 | 0 | 0 | 0 |  |  | 0 | 0
29 | DPR for Procurment of various Heavy Vehicles at CHP 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29.1 | Scheme No.1 : Procurment of Heavy Vehicles like dozers, wheel loaders , locomotives, Crane, Hydra , Disel Browser , Jcb & Bobcats etc. in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurment of Heavy Vehicles like dozers, wheel loaders , locomotives etc Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
29.2 | Scheme No.2 : Procurment of Auger Machines for coal sampling in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurment of Auger Machines for coal sampling Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 2.2 | 2.2 | 0 | 0 | 0 |  |  | 0 | 0
29.3 | Scheme No.3 : Procurment of Truck Mounted mist cannon dust supression system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurment of Truck Mounted mist cannon dust supression system in CHP Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.8 | 0.8 | 0 | 0 | 0 |  |  | 0 | 0
30 | DPR for Coal Handling Plant Performance Improvement Schemes -V at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.1 | Scheme No. 1 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 3.2 | 3.2 |  |  | 3.2 | 0
30.2 | Scheme No. 2 : Performance Improvement of Stacking & Reclaiming / Side Arm Charger System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Energy Chain System of Stacking & Reclaiming System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
30.3 | Scheme No. 3 : Performance Improvement of unloading System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Energy Chain System of side arm acharger Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
30.4 | Scheme No. 4 : Upgradation to 100 MT Ton Weighbridge of existing road weighbridge at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of LT VFD Drives for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0.8 | 0.8 |  |  | 0.8 | 0
30.5 | Scheme No. 5 : Design , Engineering & Erection of modified Energy Efficient Ventilation System for Crusher House Area in CHP 3X660MW KTPS Koradi A) Brief scope of work: Energy Efficient Ventilation System for Wagon Tippler Complex Area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
30.6 | Scheme No. 6 : Design , supply & Installation of Cooling Arrangement for Switchgear rooms at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Cooling Arrangement for Switchgear rooms Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
30.7 | Scheme No. 7 : Design , Engineering & Erection of modified Engineering Structure of Tunnel Conveyor 1A &1 B in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Erection of modified Engineering Structure of Tunnel Conveyor 1A &1 B Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 2.35 | 2.35 |  |  | 2.35 | 0
31 | DPR for Coal Handling Plant Performance Improvement Schemes -VI at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.1 | Scheme No. 1 : Performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Wagon Tippler, Side Arm Charger , Apron Feeder ( 3 & 4) Stacker Reclaimer 2 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 11.5 | 11.5 |  |  | 11.5 | 0
31.2 | Scheme No. 2 : Design Supply & Installation of Wagon Locking system for all four wagon tipplers at CHP 3x660MW KTPS Koradi A) Brief scope of work: Wagon Locking system for all four wagon tipplers Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 8 | 8 |  |  | 8 | 0
31.3 | Scheme No. 3 : Design, Supply & Installation of upgraded Vibrating Feeders for Stacker Reclaimer at CHP 3x660MW KTPS Koradi A) Brief scope of work: Design, Supply & Installation of upgraded Vibrating Feeders for Stacker Reclaimer Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0.9 | 0.9 |  |  | 0.9 | 0
31.4 | Scheme No. 4: Performance Improvement of Stacker Reclaimer by providing Hydraulic Drive to Boom Conveyor at CHP 3x660MW KTPS Koradi A) Brief scope of work: Hydraulic Drive to Boom Conveyor Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0.9 | 0.9 |  |  | 0.9 | 0
31.5 | Scheme No. 5 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
31.6 | Scheme No. 6 : Design , Engineering & Provision of Belt Tracking System for Critical Conveyors in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Belt Tracking System for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 1.6 | 1.6 |  |  | 1.6 | 0
31.7 | Scheme No. 7 : Design , Engineering & Provision of Dust supression System for stacker reclaimer-1 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0.6 | 0.6 |  |  | 0.6 | 0
31.8 | Scheme No. 8 : Work of Life Enhancement of wobbler Feeder 3 &4 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 1.6 | 1.6 |  |  | 1.6 | 0
32 | DPR for Coal Handling Plant Performance Improvement Schemes -VII at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.1 | Scheme No.1 : Design , Engineering , Supply & Installation of Modular Transfer chutes for Crusher House Complex & other Critical Conveyor System in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of Modular Transfer chutes for Conveyor System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 13 | 13 |  |  | 13 | 0
32.2 | Scheme No.2 :Upgradtion of Exsisting Fire Fighting System along the conveyor length in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradtion of Exsisting Fire Fighting System at Stack yard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 3.2 | 3.2 |  |  | 3.2 | 0
32.3 | Scheme No.3 : Supply , Erection & Installation of Rack & Pinion Elevators at Bunker in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Supply , Erection & Installation of Rack & Pinion Elevators at Bunker in CHP 3X660MW KTPS Koradi. Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0.8 | 0.8 |  |  | 0.8 | 0
32.4 | Scheme No.4 :Up Liftment f Exsisting Fire Fighting lines in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradtion of Exsisting Fire Fighting System at Stack yard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 3.2 | 3.2 |  |  | 3.2 | 0
32.5 | Scheme No.5 : Procurement of HPPE Polymer Roller for Conveyor system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurement of HPPE Polymer Roller for Conveyor system Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0.8 | 0.8 |  |  | 0.8 | 0
32.6 | Scheme No.6 : Design , Engineering , Supply & Installation of EOT cranes at Wagon Tippler Complex in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of EOT cranes at Wagon Tippler Complex Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 6.2 | 6.2 |  |  | 6.2 | 0
33 | DPR for Coal Handling Plant Performance Improvement Schemes -VIII at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.1 | Scheme No. 1 : Performance Improvement of Unloading System Wagon Tipplers at CHP 3x660MW KTPS Koradi Estimated Cost : 3.6 Cr. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.2 | Scheme No. 2 : Performance Improvement of Unloading System Side Arm Chargers at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Side Arm Charger Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.3 | Scheme No. 3 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.4 | Scheme No. 4 : Performance Improvement of Stacking & Reclaiming System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Stacking & Reclaiming System -2 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.5 | Scheme No. 5 : Performance Improvement of Crushing System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Impact Crusher & Wobbler Feeders Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.6 | Scheme No. 6 : Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -2 at CHP 3x660MW KTPS Koradi A) Brief scope of work: Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -2 at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.7 | Scheme No. 7 : Other Mislenious Schemes at CHP 3x660MW KTPS Koradi A) Brief scope of work: Other Mislenious works Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.8 | Scheme No. 4 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.9 | Scheme No.8: Procurement of HPPE Polymer Roller for Conveyor system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurement of HPPE Polymer Roller for Conveyor system Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34 | DPR for Coal Handling Plant Performance Improvement Schemes -IX at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.1 | Scheme No. 1 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.2 | Scheme No. 2 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.3 | Scheme No.3 : Upgradation of Exsisting Rack & Pinion Elevators at CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradation of Exsisting Rack & Pinion Elevators Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.4 | Scheme No.4 : Procurement of HPPE Polymer Roller for Conveyor system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurement of HPPE Polymer Roller for Conveyor system Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.5 | Scheme No.5 : Other miscellaneous scheme regarding sustainable performance improvement of CHP 3X660MW KTPS Koradi. A) Brief scope of work: ther miscellaneous scheme regarding sustainable performance improvement Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | Design & engineering, procurement, supply, installation & commissioning of Ozone Generator system of capacity 45.0 Kg/hr for CW system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Scheme1:Design & engineering, procurement, supply, installation & commissioning of Ozone Generator system of capacity 45.0 Kg/hr for CW system | 0 | - | 0 | 0 | 0 | 0 | 45 | 45 |  |  | 45 | 0
36 | Pipeline expansion to improve dry ash evacuation system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.1 | Scheme1: Pipeline expansion to improve dry ash evacuation system along with target box modification and also to erect & commission dry ash evacuation directly to remote silo. | 0 | - | 0 | 75 | 75 | 0 | 0 | 0 |  |  | 0 | 0
37 | Modification at intermediate silo and HCSD system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.1 | Scheme1: Additional charge pump. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
37.2 | Scheme 2: Supply & Installation Air washery at silo top. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
37.3 | Scheme 3: Shed above silo top. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
37.4 | Scheme 4: Supply & Installation Construction of platform at pipe rack up to Remote silo. | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
37.5 | Scheme 5: Shifting of pipeline above pipe rack. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
37.6 | Scheme 6: Supply & Installation ART sub assemblies. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
38 | ESP field strengthening at U#8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.1 | Scheme1: ESP field strengthening at U#8 | 0 | - | 0 | 120 | 120 | 0 | 0 | 0 |  |  | 0 | 0
39 | Procurement of various pumps for AHP performance improvement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
39.1 | Scheme1: Procurement of various pumps for AHP performance improvement. | 0 | - | 0 | 28 | 28 | 0 | 0 | 0 |  |  | 0 | 0
40 | Modification in Dry Ash Evacuation System D/V Assemblies & allied equipments to improve performance | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
40.1 | Scheme1: Procurement of D/V Assemblies & allied equipments to improve performance. | 0 | - | 0 | 35 | 35 | 0 | 0 | 0 |  |  | 0 | 0
41 | Additional IAC house for Intermediate silo and Remote silo along with erection of S.S. Pipeline | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.1 | Scheme1: Supply & Installation Additional IAC house for Intermediate silo and Remote silo along with erection of S.S. Pipeline | 0 | - | 0 | 0 | 0 | 0 | 50 | 50 |  |  | 50 | 0
42 | Waste water system modification to have zero water discharge | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.1 | Scheme1: Waste water system modification to have zero water discharge at 3x660MW, KTPS, Koradi along with Pump Procurement along with arrangement of sludge discharge at ESP water Washing system. | 0 | - | 0 | 0 | 0 | 0 | 26 | 26 |  |  | 26 | 0
43 | ESP field strengthening at U#9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
43.1 | Scheme1: ESP field strengthening at U#9 | 0 | - | 0 | 0 | 0 | 0 | 275 | 275 |  |  | 275 | 0
44 | Procurement of HCSD GEHO Pump (TZPM-400) critical items sub-assemblies | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.1 | Scheme1: Procurement of HCSD GEHO Pump TZPM-400) critical items sub-assemblies. | 0 | - | 0 | 0 | 0 | 0 | 30 | 30 |  |  | 30 | 0
45 | MSERW Pipes & Seamless Pipes replacement to improve ash conveying & its disposal-1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.1 | Scheme1: Supply & Work of Replacement of MSERW Pipes & Seamless Pipes in Bottom ash/Coarse ash evacuation & Ash Slurry Disposal Pipelines, Dry ash conveying system in phase manner to improve the ash evacuation performance. | 0 | - | 0 | 0 | 0 | 0 | 70 | 70 |  |  | 70 | 0
46 | Improvement in Ash Water Recovery System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.1 | Scheme1: Supply & Installation of Pumps along with Pipeline for Improvement in Ash Water Recovery System. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47 | Replacement of Instrument air pipeline from M.S. to S.S for AHP main plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.1 | Scheme1: Replacement of Instrument air pipeline from M.S. to S.S for AHP main plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48 | Modification of sludge pumps and its pipeline with pumps of higher capacity and discharge line of higher capacity. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.1 | Scheme1: Modification of sludge pumps and its pipeline with pumps of higher capacity and discharge line of higher capacity. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
49 | ESP field strengthening at U#10 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
49.1 | Scheme1: ESP field strengthening at U#10 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50 | MSERW Pipes & Seamless Pipes replacement to improve ash conveying & its disposal-2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50.1 | Scheme1: Supply & Work of Replacement of MSERW Pipes & Seamless Pipes in Bottom ash/Coarse ash evacuation & Ash Slurry Disposal Pipelines, Dry ash conveying system in phase manner to improve the ash evacuation performance. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
51 | Replacement of IAC for AHP Main Plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
51.1 | Scheme1: Supply & Installation of IAC for AHP Main Plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
52 | Improvement in DRY ASH Evacuation system-2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
52.1 | Scheme1: Supply & Installation of TAC, Replacement of Air Lock Vessel, Various Valves, ESP Hopper Doors, ESP access doors. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
53 | Improvement in DRY ASH Evacuation system-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
53.1 | Scheme1: Procurement of Ingersoll Rand Make Transport Air Compressors Critical/Non-Critical Spares sub-assembly for performance improvement. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
54 | Detailed project report for various works of security section as per the IB recommendations. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
54.1 | Repairing & raising height of compound wall with provision of concertina coil at various location of peripheral compound wall at 3x660MW KTPS Koradi. | 0 | - | 0 | 1.593 | 1.593 | 0 | 0 | 0 |  |  | 0 | 0
54.2 | Work of Providing structural three quarter turn staircase with landing along pheriphery of FISS watch tower at 3x660MW, TPS, Koradi. | 0 | - | 0 | 0.34444 | 0.34444 | 0 | 0 | 0 |  |  | 0 | 0
55 | Supply, installation, comissioning and testing of 220V station & 360V UPS batteries installed at U 8, 9 & 0 of 3x660 MW KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
55.1 | Supply, installation, comissioning and testing of 220V station & 360V UPS batteries installed at U 8, 9 & 0 of 3x660 MW KTPS, Koradi. (scheme) | 0 | - | 0 | 22.8 | 22.8 | 0 | 22.8 | 22.8 |  |  | 22.8 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
56 | TDBFP Governing valve's LPCV ,HPCV MSV AND Trip lock replacement | 0 | - | 0 | 0 | 0 | 0 | 25 | 25 |  |  | 25 | 0
61 | Procurement & replacement of HP Heaters at 3x660 MW KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 25 |  |  | 25 | -25
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Vibration Monitoring & Analysis system installed at 3x660MW Koradi TPS. | 0 | - | 0 | 63 | 63 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of sinkawa make vibration monitoring and Analysis system for main turbine at 3x660MW koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of Bently Nevada make vibration monitoring and Analysis system for RMCMS system at 3x660MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3 :-Emerson PLC upgradation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of various Level Transmitters installed at 3x660 MW koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of Guided wave Radar Level TX installed at Condenser Hotwell and LPH 1,2 and 3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of Displacer type level TX into Guided wave radar level Tx installed at various Drain Tank, Flash tank and pit | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3: Upgradation of non- contact type Ultrasonic level Tx into IP68 non- contact type Radar level TX. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of ESP Hopper level Probes installed at 3x660 MW koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 40 | 40 |  |  | 40 | 0
0 | Scheme 1: Upgradation of 1st three fields ESP Hopper level probes into continuous level monitoring NOGS system at 3x660 MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of RF capacitance Hopper level probe into of RF admittance level probe at 4,5,6,7,8 & 9 ESP Hoppers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3: Upgradation of ESP hopper heater monitoring , control and real time monitoring system at 3X660MW Koradi TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of various scheme viz ASLD, Furnace tv camera FEGT and acoustic Pyrometer installed at 3x660 MW koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 61 | 61 |  |  | 61 | 0
0 | Scheme 1: Upgradation of ASLD system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of Furnace TV Camera | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3:Upgradation of FEGT system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 4:Upgradation of acoustic pyrometer | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of various scheme viz instrument Air pipe at ESP Area, wet Ash Evacuation system, HCSD Silo. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of instrument Air pipeline system at ESP of M.S into SS installed at 3x660 MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of instrument Air pipeline system at wet Ash system of M.S into SS . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3: Upgradation of instrument Air pipeline system at HCSD silo of M.S. into SS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 4: Upgradation of instrument Air pipeline system at Remote Silo of M.S into SS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 5: Upgradation of Control & Instrument section lab with Hydraulic Servo Valve Test, Pneumatic System test and calibration lab set up. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Flame scanner for flexible operation of 3X660MW Koradi TPS. | 0 | - | 0 | 35 | 35 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of Flame scanner for flexible operation of 3X660MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of DRC Pipes, Bends & Fittings in phase manner to improve the dry ash conveying & its disposal (2 years) | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of DRC Pipes, Bends & Fittings in phase manner to improve the dry ash conveying & its disposal (2 years) (Rs.30 Cr.) (Bottom ash/Coarse ash evacuation & Ash Slurry Disposal Pipelines, Dry ash conveying system) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Augmentation of Coarse Ash disposal system at U10 at KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | WORK OF INSTALLATION & COMMISSIONING OF ASH DISPOSAL SYSTEM AT UNIT#10 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Railway Track Siding Performance Improvement Schemes at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 1 : Work of complete track renovation of existing Rail yard of CHP, 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. Due to continuous movement of Railway's precious rolling stock, the track spares are worn out and are due for complete replacement. Hence, to maintain rail track parameters in healthy condition as per Railway norms so as to avoid untoward incidences of derailment the execution of work of complete track renewal is essential. | 0 | - | 0 | 0 | 0 | 0 | 30 | 30 |  |  | 30 | 0
0 | Scheme No. 2 : Scheme Name- Work of laying of additional track at 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. However, as per the existing infrastructure, at present there is no dedicated empty formation line. Due to non-availability of empty formation line, most often unloading gets hampered due to blocking of outhaul line by empty rake. The hampering in unloading affects the plant performance and incurrs unnecessary financial burden on KTPS account under the head of demurrage charges. Hence, to maintain the plant loadability and availability, it is essential to lay additional track at 3x660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
0 | Scheme No. 3 : Scheme Name- Work of rectification and upgradtion of existing SSP at CHP, 3x660MW, KTPS, Koradi. Justification- The SSP has been erected at 3x660MW, KTPS, Koradi. However, till date the same has not been commissioned. With lapse of @ 5-6 years after erection and its non commissioning, the existing SSP set up has been completely detoriorated. Now, Railway's is pressing hard for early commissioning of the same. The said set up shall ensure isolation of OHE of existing yard with Railway's main line. | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
0 | Scheme No. 4 : Scheme Name- Work of construction of apron RCC platforms at inhaul and outhaul of Wagon tipllers 1, 2, 3 & 4 of CHP 3x660MW, KTPS, Koradi. Justification- The 04 Nos. of wagon tipplers are installed at CHP-3x660MW, KTPS, Koradi. In this regards, it is to submit that, the wagon unloading is being carried out through these tipplers. Hence, presence of fugitive dust in tippler area is predominant. The said dust is being accumulated at inhaul and outhaul of wagon tipplers. Due to presence of loaded wagons at inhaul and empty wagons at outhaul, this office gets least opportunity for clearance of the said coal dust along the track. Due to accumulation of coal dust, the rail track parameters along with gradient are getting distubed. The disturbance in gradient is causing rolling of wagons which is not recommended in view of safety of both man and machine. Besides, this due to rolling of wagons, the occurnece of untoward incidence of derailment is predominant. Hence, to maintain uniform rail track gradient it shall be enviable to construct the apron RCC platforms at inhaul and outhaul of Wagon tipplers 1, 2, 3 & 4 of CHP-3x660MW, KTPS, Koradi. Estimated cost- Rs. 4 Cr. | 0 | - | 0 | 0 | 0 | 0 | 4 | 4 |  |  | 4 | 0
0 | Scheme No. 5 : Scheme Name- Work of construction of apron RCC platforms at inhaul and outhaul of Wagon tipllers 1, 2, 3 & 4 of CHP 3x660MW, KTPS, Koradi. Justification- The 04 Nos. of wagon tipplers are installed at CHP-3x660MW, KTPS, Koradi. In this regards, it is to submit that, the wagon unloading is being carried out through these tipplers. Hence, presence of fugitive dust in tippler area is predominant. The said dust is being accumulated at inhaul and outhaul of wagon tipplers. Due to presence of loaded wagons at inhaul and empty wagons at outhaul, this office gets least opportunity for clearance of the said coal dust along the track. Due to accumulation of coal dust, the rail track parameters along with gradient are getting distubed. The disturbance in gradient is causing rolling of wagons which is not recommended in view of safety of both man and machine. Besides, this due to rolling of wagons, the occurnece of untoward incidence of derailment is predominant. Hence, to maintain uniform rail track gradient it shall be enviable to construct the apron RCC platforms at inhaul and outhaul of Wagon tipplers 1, 2, 3 & 4 of CHP-3x660MW, KTPS, Koradi. Estimated cost- Rs. 4 Cr. | 0 | - | 0 | 0 | 0 | 0 | 4 | 4 |  |  | 4 | 0
0 | Scheme No. 6 : Scheme Name- Work of construction of RCC platforms along the rail track of CHP 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. In this regards, it is to submit that, after unloading of rakes the empty rakes are being examined by Railway's C&W staff camped at KTPS, Koradi. Hence, for safe movement of Railway's staff, Railway's is pressing hard for provision of RCC platforms along the rail track of CHP-3x660MW, KTPS, Koradi. Estimated cost- Rs. 10 Cr. | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
0 | Scheme No. 7 : Scheme Name- Work of repairing and construction of RCC permanent revenue canal at, KTPS, Koradi. Justification- The temporary revenue canal is being flowing beside the existing Railway exchange yard of 210 MW, KTPS, Koradi. The said canal gets clogged inview of ash accumulation. Due to clogging this canal overflows and its overrun enters the 210 MW rail yard thereby creating track surface marshy and unsafe for Rail movement. Hence, it is essential to repair and construct RCC permanent revenue canal at KTPS, Koradi so that proper and timely cleaning of canal along with proper outlet can be arranged. Estimated cost- Rs. 15 Cr. | 0 | - | 0 | 0 | 0 | 0 | 15 | 15 |  |  | 15 | 0
0 | Scheme Name-08 Work of construction of RCCretaining wall at Godhani and Kalumna end of KTPS, Koradi. Justification- The separate rail infrastructure has been commissioned for Koradi TPS to cope up the daily coal requirement. The rail traffic at KTPS, Koradi is being catered through Godhani and Kalumna end respectively. In this regards, it is to submit that, the take off points at Godhani and Kalumna both are S&T operated. During monsoon, it is often witnessed that, the rain water enters the plant premises from others land thereby submerging the S&T operated point. Due to this, signals gets lost and hampers the Rail traffic movement completely. Hence, it is essential to restrict the entrance of rain water in plant premises. This can be possible by constructing retaining wall at required loaction. Estimated cost- Rs. 1 Cr. | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
0 | Scheme Name-09 OHE maintenance at CHP, KTPS, Koradi Justification-As per the Railway board circular, Railway's has mandated that OHE maintenance cost for existing as well as new sidings shall be borne by the siding owner in accordance with Railway guidelines. Railway will carry out necessary inspection of maintenance work once in six months. Maintenance charges per TKM per annum of OHE as finalized by SECR zonal office is Rs.291566/- per TKM per annum. Also, inspection charges at the rate of Rs.106974/- per day towards inspection to be carried out by Railways every si x months shall be charged on actual basis by Railway's from the sidings.Accordingly, Railway.s has calimed amount of Rs.31314519/- for two years. Hence for 5 yeards it is expected to be Rs.7.82 Cr. Estimated cost- Rs. 7.82 Cr. | 0 | - | 0 | 0 | 0 | 0 | 7.82 | 7.82 |  |  | 7.82 | 0
0 | Scheme 10 Name-Remodelling and upgradation of existing S & T system with Panel Interlocking system and associated S & T gears to S & T system with Electronic Interlocking system and associated S & T gears in connection with services for BG Railway facility (660 MW Rail yard) for Koradi Thermal Power Station of MSPGCL Justification-As per the prevailing Railway norms, it is mandatory to commission the S & T system in private Railway siding for fast and safe movement of Railway’s precious rolling stock. Unless and until remodeling is carried out the S&T system cannot be started at Koradi Railway yard.With commissioning and operation of S & T system there shall be least possibility for derailments during internal shunting through crossovers, as the said points shall be motorized operated. Estimated cost- Rs. 20 Cr. | 0 | - | 0 | 0 | 0 | 0 | 20 | 20 |  |  | 20 | 0
0 | Scheme No. 11 : Work of supply and provision of lights and high mast at CHP Railway exchange yard of 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. In this regards, it is to submit that, after unloading of rakes the empty rakes are being examined by Railway's C&W staff camped at KTPS, Koradi on round the clock basis. Hence, for safe movement of Railway's staff, Railway's is pressing hard for availability of proper illumination in complete yard. Estimated cost- Rs.2.5 Cr. | 0 | - | 0 | 0 | 0 | 0 | 25 | 25 |  |  | 25 | 0
0 | DPR for Provision of cover shed for stack yard -2 at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | Scheme No. 1 : Provision of cover shed for stack yard -2 at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 135 |  |  | 135 | -135
0 | DPR for Procurement of Pipe Conveyor Drive System Internals at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 1 : Procurement of Pipe Conveyor Drive System Internals at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 27 |  |  | 27 | -27
0 | DPR for Provision of service building along with vehicle bay at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 1 : Provision of service building along with vehicle bay at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | GENERAL ASSET | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | GENERAL ASSET--AKRDFOGA01-OFFICE FURNITURE | N.A. | - | 0 | 0.57299 | 0.75759 | -0.1846 | 0 | 0 |  |  | 0 | -0.1846
2 | GENERAL ASSET--AKRDFOGA02-COMPUTERS,PRINTER,SCANNER | N.A. | - | 0 | 1.6504 | 2.911 | -1.2606 | 0 | 0 |  |  | 0 | -1.2606
3 | GENERAL ASSET--AKRDFOGA03-AC,WATER COOLER | N.A. | - | 0 | 0.46584 | 0.49898 | -0.033135 | 0 | 0 |  |  | 0 | -0.033135
4 | GENERAL ASSET--AKRDFOGA04-AIR PURIFIER | N.A. | - | 0 | 0 | 0.0105 | -0.0105 | 0 | 0 |  |  | 0 | -0.0105
0 | D) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of KLEP Unit for 'HCSD Pump | 0 | - | 3.73 | 3.73 | 3.73 | 0 | 0 | 0 |  |  | 0 | 0
2 | Restoration of Boiler Circulation Pump at 3X660MW KTPS, Koradi | 0 | - | 0 | 4.73 | 4.73 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of Coal Compartment Assemblies for Unit-10 at 3x660MW KTPS, Koradi. | 0 | - | 0 | 3.73 | 3.73 | 0 | 0 | 0 |  |  | 0 | 0
4 | Repairing and Refurbishment of TDBFP cartridge Model FK6E40 installed at 3X660MW KTPS, Koradi | 0 | - | 0 | 11.86 | 11.86 | 0 | 0 | 0 |  |  | 0 | 0
5 | Non-DPR for Upgradation of Honeywell Make PLC for Mill Reject Handling System installed at 3x660MW Balance of Plant (BOP) Unit- 8, 9 & 10 at Koradi TPS | 0 | - | 0 | 0.85 | 0.85 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of Sky Climber for furnace repairing at 3x660MW KTPS, Koradi | 0 | - | 0 | 3.02 | 3.02 | 0 | 0 | 0 |  |  | 0 | 0
7 | Double Roll Clinker Grinder | 0 | - | 0 | 1.68 | 1.68 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement along with Installation of Clear Water Booster Pump with Motor, Panel Cable and other allied accessories in Unit#10 bottom ash area at AHP, 3x660MW, KTPS, Koradi. | N.A. | - | 0 | 2.8112 | 2.56 | 0.25116 | 0 | 0 |  |  | 0 | 0.25116
9 | Procurement of single Roll Clinker Grinder with Feed Pump & Jet Pump Complete Assembly with modified metallurgy installed at AHP ,3x660MW Units, KTPs, Koradi | N.A. | - | 0 | 3.2868 | 2.12 | 1.1668 | 0 | 0 |  |  | 0 | 1.1668
10 | Work of Repairing and Refurbishment of HIP Rotor along with balancing and over speed trial for L&T-MHI make turbine (Type: TC4F-30”) installed at 3X660MW KTPS, Koradi | N.A. | - | 0 | 7.3532 | 7.13 | 0.22316 | 0 | 0 |  |  | 0 | 0.22316
11 | Procurement of spares for Flue gas distribution dampers, PA fan discharge dampers and Coal mill Hot PA Gate and Dampers at 3x660mw KTPS units through OEM | N.A. | - | 0 | 3.7 | 3.7 | 0 | 0 | 0 |  |  | 0 | 0
12 | Work of Modification & Installation of Take up trolley & arrangement for take up lifting for conveyor BCN-13A at CHP 3X660MW,KTPS,Koradi | N.A. | - | 0 | 356.6331 | 0.75 | 355.8831 | 0 | 0 |  |  | 0 | 355.8831
13 | Work of Design, Modification & streingthening of Tripper trolley structure with provision of Antiwear plates discharge chute box at CHP 3X660MW,KTPS,Koradi | N.A. | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
14 | Upgradation of Management Information System (MIS) Server and Associated Software for C&I at 3x660MW Unit- 8, 9 & 10 at Koradi TPS | N.A. | - | 0 | 2.145 | 2.145 | 0 | 0 | 0 |  |  | 0 | 0
15 | Procurement of Vibrating Tranfer chute with double exciter Drive for stacker reclaimer at CHP,3X660MW,KTPS ,Koradi | N.A. | - | 0 | 0.934 | 0.934 | 0 | 0 | 0 |  |  | 0 | 0
16 | Supply & Installation of Ash Slurry Density Transmitter at High Concentrated Slurry Disposal (HCSD) System of BOP area of 3x660MW Unit- 8, 9 & 10 at Koradi TPS | N.A. | - | 0 | 1.26 | 1.26 | 0 | 0 | 0 |  |  | 0 | 0
17 | Supply & Installation of Fiber Optic Sensing System for Conveyor Health Monitoring At CHP 3x660MW KTPS, Koradi | 0 | - | 0 | 11.72 | 11.72 | 0 | 0 | 0 |  |  | 0 | 0
18 | Procurement of Leak- proof make complete Mechanical Seal Assembly for Concrete Volute CW Pump installed at 3X660MW KTPS,Koradi on OEM bASIS. | 0 | - | 0 | 1.94 | 1.94 | 0 | 0 | 0 |  |  | 0 | 0
19 | Work of Design , Engineering , Manufacturing , Supply Erection & Commissioning of Conveyor Belt From Discharge of RBF 1 &2 at Crusher House to Stack Yard At CHP 3x660MW KTPS, Koradi . | 0 | - | 0 | 11.39 | 11.39 | 0 | 0 | 0 |  |  | 0 | 0
20 | Supply & Installation of Artificial Intelligence PMMS Accurex Diagnostic matrix based vibration & temperature monitoring for critical auxiliaries at CHP 3x660MW KTPS, Koradi. | 0 | - | 0 | 6.431 | 6.431 | 0 | 0 | 0 |  |  | 0 | 0
21 | Restoration of online dissolved gas analysers of Unit 8,9,10 | 0 | - | 0 | 1.11 | 1.11 | 0 | 0 | 0 |  |  | 0 | 0
22 | Complete Replacement of Existing Water Separator Drain Tank Control (WDC) Valves with New Valves of modified trim design along with hydraulic Actuators, Power Pack assembly, necessary instrumentation, erection & commissioning 3X660MW KTPS, Koradi. | 0 | - | 0 | 5.33 | 5.33 | 0 | 0 | 0 |  |  | 0 | 0
23 | Procurement of mandatory set of Hydraulic system internals for Wagon Tippler Drive & side arm charger Drive at CHP,3X660MW,KTPS ,Koradi | 0 | - | 0 | 6.35 | 6.35 | 0 | 0 | 0 |  |  | 0 | 0
24 | "Supply & installation of Anodized winding Oil cooled over band magnetic separator & control panel for conveyor 5A,5B &13C at CHP 3x660MW KTPS, Koradi. | 0 | - | 0 | 1.896 | 1.896 | 0 | 0 | 0 |  |  | 0 | 0
25 | Procurement of Grinding Wall Assembly for Impact Crusher At CHP 3x660MW KTPS, Koradi | 0 | - | 0 | 2.01 | 2.01 | 0 | 0 | 0 |  |  | 0 | 0
26 | Restoration of Boiler Circulation Pump of U10 at 3X660MW KTPS, Koradi | 0 | - | 0 | 6.69 | 6.69 | 0 | 0 | 0 |  |  | 0 | 0
27 | Design,Engineering,Customization,Implementation,Installation & testing of Data Analytical/Artificial Intellegence softwae for automated monitoring & diagnostics system to improve Power plant reliability & efficiency,at one unit of 3X660MW KTPS, Koradi. | 0 | - | 0 | 3.27 | 3.27 | 0 | 0 | 0 |  |  | 0 | 0
28 | Supply of Feed Gate Complete Assembly along with installation to enhance the performance of Feed Gate at Ash Handling Plant, 3x660MW, KTPS, Koradi. | 0 | - | 0 | 2.4 | 2.4 | 0 | 0 | 0 |  |  | 0 | 0
29 | Design, Supply, Installation & Commissioning of Instrument Air Dryer Assembly with Prefilters & Stainless steel piping along with valves suitable for Instrument Air Compressors at AHP, 3x660MW Units, KTPS, Koradi | 0 | - | 0 | 5.5 | 5.5 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 4269.4051 | 3955.0174 | 314.3877 | 1452.84 | 1639.84 | 0 | 0 | 1639.84 | 127.3877
FY 2027-28
0 | A) Approved Add cap: | 0 | - | 0 | 0
A | BoP | 0 | - | 246.34 | 103.6804 | 232.6929 | -129.0125 | 0 | 0 |  |  | 0 | -129.0125
B | BTG | 0 | - | 44.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B1 | Supply | 0 | - | 13.33 | 0 | 13.33 | -13.33 | 0 | 0 |  |  | 0 | -13.33
B2 | Works | 0 | - | 0.98 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B3 | Taxes and duties | 0 | - | 23.29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B4 | Civil | 0 | - | 0.19 | 0.19 | 0 | 0.19 | 0 | 0 |  |  | 0 | 0.19
B5 | Mandatory Spares | 0 | - | 5.03 | 1.29 | 6.32 | -5.03 | 0 | 0 |  |  | 0 | -5.03
B6 | BTG (L&T) Work | 0 | - | 1.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C | Other Works (Plant) | 0 | - | 136.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C1 | Fully Integrated Security System | 0 | - | 27.36 | 31.4615 | 31.4615 | 0 | 0 | 0 |  |  | 0 | 0
C2 | Administrative Expenses and overhead | 0 | - | 7.25 | 6.69 | 0 | 6.69 | 0 | 0 |  |  | 0 | 6.69
C3 | Contingencies E&M | 0 | - | 0.04 | 0.04 | 0 | 0.04 | 0 | 0 |  |  | 0 | 0.04
C4 | Mobile storage racks, fork lifts, hoists & hydra for material handling in major stores shed | 0 | - | 0.95 | 0.93645 | 0.93645 | 0 | 0 | 0 |  |  | 0 | 0
C5 | Development of working models of Plant Layout, Boiler, Turbine- Generetaor, Coal mill, Fans, etc. at KTC, Koradi. | 0 | - | 1.2 | 1.2 | 0.98604 | 0.21396 | 0 | 0 |  |  | 0 | 0.21396
C6 | Workshop equipment | 0 | - | 0.26 | 0.26192 | 0.26192 | 0 | 0 | 0 |  |  | 0 | 0
C7 | Design, engg, manufacture, supply , erection, testing & commissioning of Ozonization Plant for circulating cooling water system | 0 | - | 54.05 | 31.7683 | 31.6144 | 0.15388 | 0 | 0 |  |  | 0 | 0.15388
C8 | Supply, installation & commissioning of water flow meters including required SCADA software and other accessories for water management system | 0 | - | 5.08 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C9 | Provision of wet ash evacuation system for first two rows of ESP for Unit-8,9 & 19 | 0 | - | 26.59 | 21.69 | 26.3181 | -4.6281 | 0 | 0 |  |  | 0 | -4.6281
C10 | Procurement of portable mercury analyser for flue gas monitoring | 0 | - | 6.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C11 | Administrative Expenses and overhead | 0 | - | 5 | 21.0001 | 0 | 21.0001 | 0 | 0 |  |  | 0 | 21.0001
C12 | Compressor of Hydrogen plant | 0 | - | 1.5 | 1.5 | 0 | 1.5 | 0 | 0 |  |  | 0 | 1.5
C13 | Rail Cum road stone grabbler | 0 | - | 0.85 | 0.85 | 0 | 0.85 | 0 | 0 |  |  | 0 | 0.85
D | Other Works (Civil) | 0 | - | 103.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D1 | Road, Bridges railway system | 0 | - | 20.1 | 0.10806 | 0 | 0.10806 | 0 | 0 |  |  | 0 | 0.10806
0 | S&T System with Panel Interlocking System | 0 | - | 0 | 10.4585 | 10.4596 | -0.0011606 | 0 | 0 |  |  | 0 | -0.0011606
D2 | Staff quarters | 0 | - | 5.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D3 | Other Misc & Unforseen Item | 0 | - | 25.79 | 9.3 | 7.53 | 1.77 | 0 | 0 |  |  | 0 | 1.77
0 | Check Post, Inspection Office & Facility Complex | 0 | - | 0 | 3.6844 | 3.6816 | 0.0028689 | 0 | 0 |  |  | 0 | 0.0028689
0 | CPRI Building | 0 | - | 0 | 6.2046 | 6.2046 | 0 | 0 | 0 |  |  | 0 | 0
0 | Foam cum DCP fire tender- 1 | 0 | - | 0 | 0 | 0.76926 | -0.76926 | 0 | 0 |  |  | 0 | -0.76926
0 | Fire water Bowser-cum-fire Tender- 1No. | 0 | - | 0 | 0.73537 | 0.73537 | 0 | 0 | 0 |  |  | 0 | 0
D4 | Const. facility | 0 | - | 3.28 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D5 | Contigency Other Civil Work | 0 | - | 5.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D6 | Adminstrative Exp. & Overhead (Salary & Overhead, Civil & E&M) | 0 | - | 21.47 | 31.64 | 0 | 31.64 | 0 | 0 |  |  | 0 | 31.64
D7 | Future unforseen works(Jalyukta Shiwar) | 0 | - | 0.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D8 | Landscaping work | 0 | - | 21.76 | 20.53 | 0 | 20.53 | 0 | 0 |  |  | 0 | 20.53
E | Initial Spares | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
E1 | Boiler & its auxilliaries | 0 | - | 14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Procurement of Table liners and Roller liners Of MVM 32R Coal Mills of 3 X 660MW Units at KTPS, Koradi | 0 | - | 0 | 10.0686 | 10.0686 | 0 | 0 | 0 |  |  | 0 | 0
ii | Procurement of couplings for Coal mill MVM 32 R of 3 X 660 MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 1.5944 | -1.5944 | 0 | 0 |  |  | 0 | -1.5944
iii | Procurement of Set of internal spares for Coal Mill Gear Box (KMP-450) for 3 X 660MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 2.2253 | -2.2253 | 0 | 0 |  |  | 0 | -2.2253
E2 | Turbine & its auxilliaries | 0 | - | 18.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | ULTRAFILTRATION MEMBRANE | 0 | - | 0 | 1.6511 | 1.6511 | 0 | 0 | 0 |  |  | 0 | 0
ii | Supply of Main turbine Vibration Monitoring System spares at 3x660MW, KTPS,Koradi. | 0 | - | 0 | 0 | 1.1469 | -1.1469 | 0 | 0 |  |  | 0 | -1.1469
iii | Procurement of Cartridge for Turbine Driven Boiler Feed Pump (Model No.: FK6E40) at 3X660 MW KTPS Koradi | 0 | - | 0 | 14.2864 | 14.2864 | 0 | 0 | 0 |  |  | 0 | 0
iv | Procurement of Critical Insurance Spares for L&T-MHI Make Turbine for attending major overhauling work of Turbine at KTPS, 3x660MW Units Koradi. | 0 | - | 0 | 11.1013 | 11.1013 | 0 | 0 | 0 |  |  | 0 | 0
E3 | Generator & its auxilliaries | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
E4 | Electrical auxilliaries | 0 | - | 1.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Procurement of HT Motors of BOP | 0 | - | 0 | 0 | 0.29335 | -0.29335 | 0 | 0 |  |  | 0 | -0.29335
ii | 0 | 0 | - | 0 | 0 | 0.84594 | -0.84594 | 0 | 0 |  |  | 0 | -0.84594
iii | Supply of Schneider make Differential Protection Relays for 3X660 MW, Koradi (OEM) | 0 | - | 0 | 0 | 0.10502 | -0.10502 | 0 | 0 |  |  | 0 | -0.10502
iv | Supply of Professional Large Format Display for display of DCS parameters PCR | 0 | - | 0 | 0.14885 | 0.14885 | 0 | 0 | 0 |  |  | 0 | 0
v | Procurement of ABT Energy meter with software for 3X660 MW, TPS, Koradi | 0 | - | 0 | 0 | 0.18337 | -0.18337 | 0 | 0 |  |  | 0 | -0.18337
E5 | Outdoor Plant i.e. CHP, AHP, WTP etc | 0 | - | 19.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Procurement of Forced Lubrication system for Premium make Gear box B3-450 installed for bunker conveyor BCN 7A/B at CHP 3X660MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0.15314 | -0.15314 | 0 | 0 |  |  | 0 | -0.15314
ii | Procurement of rotary spares for travel drive of Stacker and conveyor drive system in Coal Handling Plant of 3x660 MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0.35199 | -0.35199 | 0 | 0 |  |  | 0 | -0.35199
iii | Procurement of Complete assembly of Dome Valve ( 100NB, 200NB, 300NB) with power cylinder for dry Ash evacuation system of 3X660MW KTPS, Koradi. | 0 | - | 0 | 0.2225 | 0.2225 | 0 | 0 | 0 |  |  | 0 | 0
iv | Procurement of Modified Apron Pans for M/s. ELECON Engineering Company ltd make Apron Feeder in CHP 3x660MW Units at KTPS, Koradi. | 0 | - | 0 | 3.3233 | 3.3233 | 0 | 0 | 0 |  |  | 0 | 0
v | Procurement of Single Roll Clinker Grinder with Feed Sump and Jet Pump Complete Assembly with Drive, Driven Sprocket and Chain at AHP, 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.56357 | 0.56357 | 0 | 0 | 0 |  |  | 0 | 0
vi | Procurement of spares of Dome Valve (100NB, 200NB, 300NB) for Ash Evacuation System of 3X660MW Unit KTPS, Koradi. | 0 | - | 0 | 0.16431 | 0.16431 | 0 | 0 | 0 |  |  | 0 | 0
vii | 0 | 0 | - | 0 | 0.10064 | 0.10064 | 0 | 0 | 0 |  |  | 0 | 0
viii | 0 | 0 | - | 0 | 0.00708 | 0.00708 | 0 | 0 | 0 |  |  | 0 | 0
ix | Procurement of Hydraulic Motor for Apron feeder in Coal Handling Plant 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.7965 | 0.7965 | 0 | 0 | 0 |  |  | 0 | 0
x | Procurement of Peristaltic Hose Pump (Model no: RP2 – 40) Spares for HCSD System of Ash Handling Plant, 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.20622 | 0.20622 | 0 | 0 | 0 |  |  | 0 | 0
xi | Procurement of spares for HP Water Pump, Mather & Platt make, model 10/12 EME for AHP at 3X660 MW, KTPS, Koradi | 0 | - | 0 | 0.28246 | 0.28246 | 0 | 0 | 0 |  |  | 0 | 0
xii | Procurement of Rotor shaft assembly for M/s. ELECON Engineering Company ltd make Impact Crusher in CHP 3x660MW Units at KTPS, Koradi. | 0 | - | 0 | 0.76369 | 0.76369 | 0 | 0 | 0 |  |  | 0 | 0
xiii | Procurement of Sam Turbo Make Pumps Spare parts for Ash Handling Plant of 3X660 MW Units at KTPS, Koradi | 0 | - | 0 | 0.17166 | 0.17166 | 0 | 0 | 0 |  |  | 0 | 0
xiv | Procurement of Wagon Tippler Spares for M/s. ELECON Engineering Company ltd. make Wagon Tippler in CHP 3X660MW Units at KTPS, Koradi. | 0 | - | 0 | 1.3975 | 1.3975 | 0 | 0 | 0 |  |  | 0 | 0
xv | Procurement of Pneumatic Y Type Control Valve (Blow Valve Size 50mm & 80mm) for Fly Ash Evacuation System of 3X660MW Unit KTPS, Koradi. | 0 | - | 0 | 0.029205 | 0.029205 | 0 | 0 | 0 |  |  | 0 | 0
xvi | Procurement of the various spares required for Warman make Ash Slurry Pump Model 10/8 EEM & Over Flow Pump Model 8/6 EXU installed at AHP, 3X660 MW TPS Koradi through Limited Tender. | 0 | - | 0 | 0.20886 | 0.20886 | 0 | 0 | 0 |  |  | 0 | 0
xvii | 0 | 0 | - | 0 | 0.0076261 | 0.032797 | -0.025171 | 0 | 0 |  |  | 0 | -0.025171
xviii | Procurement of Spares of Single Roll Clinker Grinder Ayems Engineers make, Model AE-1005-89-100 at AHP, 3X660 MW Koradi TPS. | 0 | - | 0 | 0.82826 | 0.82826 | 0 | 0 | 0 |  |  | 0 | 0
xix | Procurement of Hydraulic Motor for Bucket Wheel of Stacker Reclaimer in CHP, 3X660MW, KTPS, Koradi. | 0 | - | 0 | 1.1168 | 1.1168 | 0 | 0 | 0 |  |  | 0 | 0
xx | Procurement of Rotors, Maintenance Kits, Couplings and other spares required for Atlas Copco make Instrument Air Compressor of Ash Handling Plant of 3 X 660 MW Units at KTPS, Koradi. | 0 | - | 0 | 1.1828 | 1.1828 | 0 | 0 | 0 |  |  | 0 | 0
xxi | Procurement of spares of intermediate conveyor | 0 | - | 0 | 0 | 0.3186 | -0.3186 | 0 | 0 |  |  | 0 | -0.3186
xxii | Procurement of Hydraulic motor for wagon tippler drive in CHP, 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.46494 | 0.46494 | 0 | 0 | 0 |  |  | 0 | 0
xxiii | Procurement of GEHO Pump (Model No. TZPM 400) Spares of Ash Handling Plant, 3 X 660 MW Units, KTPS, Koradi. | 0 | - | 0 | 0 | 0.83656 | -0.83656 | 0 | 0 |  |  | 0 | -0.83656
xxiv | Procurement of Beater Arms for Impact crushers installed at in Coal Handling Plant of 3x660 MW at KTPS, Koradi. | 0 | - | 0 | 0 | 1.0093 | -1.0093 | 0 | 0 |  |  | 0 | -1.0093
xxv | Supply of Atlas Copco make compressor spares for at Koradi TPS 660MW | 0 | - | 0 | 0 | 0.39813 | -0.39813 | 0 | 0 |  |  | 0 | -0.39813
xxvi | Procurement of spares for side arm charger, wagon tippler, impact crushers and stacker reclaimer at CHP 3x660 MW KTPS | 0 | - | 0 | 0.010573 | 0.43684 | -0.42626 | 0 | 0 |  |  | 0 | -0.42626
xxvii | Procurement of Beater heads with Pin for Impact crushers installed at in Coal Handling Plant of 3x660 MW at KTPS, Koradi. | 0 | - | 0 | 0 | 1.1256 | -1.1256 | 0 | 0 |  |  | 0 | -1.1256
xxviii | Procurement of spares of Hyd Motor of SAC | 0 | - | 0 | 0 | 0.36029 | -0.36029 | 0 | 0 |  |  | 0 | -0.36029
xxix | Procurement of hydraulic power packs for Flap Gates in CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0.1888 | -0.1888 | 0 | 0 |  |  | 0 | -0.1888
xxx | Procurement of Mobile Grilling Equipment for CHP 3x660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0.33866 | -0.33866 | 0 | 0 |  |  | 0 | -0.33866
xxxi | Procurement of Weld overlay Flap Gate assembly in CHP 3x660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0.5841 | -0.5841 | 0 | 0 |  |  | 0 | -0.5841
E6 | Capital Spares | 0 | - | 89.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of critical insurance spares for Turbine & its critical auxiliaries for 3 x 660 MW, Koradi (4370001538 dtd. 18/06/2018 d.p. 21 Months) | 0 | - | 89.62 | 89.6234 | 88.736 | 0.88736 | 0 | 0 |  |  | 0 | 0.88736
E7 | Additional Capitalization | 0 | - | 57.88 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Contruction of various infrastructure such as roads etc and public amenities in the rehabilitated villages of koradi and khasara | 0 | - | 13.1 | 12.74 | 0 | 12.74 | 0 | 0 |  |  | 0 | 12.74
ii | Procurement of 7 nos of school buses | 0 | - | 2 | 1.3109 | 1.3109 | 0 | 0 | 0 |  |  | 0 | 0
iii | Development of green belt & fodder farm for fulfillment of environmental clearance of MoEF for Koradi 3x660MW | 0 | - | 3.16 | 3.16 | 0 | 3.16 | 0 | 0 |  |  | 0 | 3.16
iv | Provision of Ground Hopper & Short Conveyor Belt from Existing Stackyard 1 & 2 ti existing Main Stream i.e. BCN 4A/4B of CHP 3x660 MW, KTPS, Koradi | 0 | - | 4.36 | 4.3555 | 4.3555 | 0 | 0 | 0 |  |  | 0 | 0
v | Provision of Ground Hopper & Conveyor Belt for Conveying Unloaded Coal form Open Wagon Tippler in CHP of Koradi Unit 8, 9 & 10. | 0 | - | 4.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
vi | Provision of Additional Facility for Manual Unloading Track in CHP of Koradi Unit No. 8, 9 & 10 | 0 | - | 5.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
vii | Construction of drains | 0 | - | 4.31 | 2.7927 | 0 | 2.7927 | 0 | 0 |  |  | 0 | 2.7927
viii | Supply erection commissioning of medium voltage variable frequency drive for conveyors BCN 6A,6B,7A,7B in CHP 3x660MW | 0 | - | 17 | 16.9859 | 16.9859 | 0 | 0 | 0 |  |  | 0 | 0
ix | Supply, Installation & commissioning of 3D level sensors for first two ESP field hoppers | 0 | - | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
F | Koradi TPS 3x660 MW Expansion Project – Construction of 2nd raising of existing Khasara Ash Bund from T.B.L. 308.50 M to T.B.L 312.00 M with construction of concrete dam (Broad crest weir structure), approach to drain wells and raising height of drain well No. 1, 2 & 3, construction of ash Compartment, cleaning of Khasara bund Nallah and construction of peripheral roads connecting to nearby villages for Khasara ash bund at TPS Koradi | 0 | - | 86.914 | 88.683 | 93.291 | -4.608 | 0 | 0 |  |  | 0 | -4.608
G | Discharge of UDL | 0 | - | 0 | 111.97 | 111.48 | 0.49 | 0 | 0 |  |  | 0 | 0.49
H | Asset Addition due to change in classification of inventory | 0 | - | 0 | 21.7503 | 0 | 21.7503 | 0 | 0 |  |  | 0 | 21.7503
I | Medical Oxygen Gr&Cyl Ozonization Plant (Covid Related Work) | 0 | - | 0 | 11.4034 | 9.6702 | 1.7332 | 0 | 0 |  |  | 0 | 1.7332
0 | B) DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (i) Submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Flue Gas Desulphurization FGD is for Unit 8, 9, 10 of 3x660MW Koradi TPS | MERC/CAPEX/FY 2020-21/WFH/SBR/05 | 2020-05-31 | 940 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Flue Gas Desulphurization is for Unit 8, 9, 10 of 3x660MW Koradi TPS | MERC/CAPEX/FY 2020-21/WFH/SBR/05 | 2020-05-31 | 847.78 | 1556.15 | 1556.15 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/FY 2020-21/WFH/SBR/05 | 2020-05-31 | 92.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13 | Construction of new admin building at Vidyut Bhavan, Katol Road, Nagpur | MERC/Capex/2021-2022/MSPGCL/063 | 2022-02-18 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13.1 | Construction of new admin building at Vidyut Bhavan, Katol Road, Nagpur | 0 | 2022-02-18 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | 2022-02-18 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Improvement in Regenerative Air Pre-heater Performance at Unit # 9 of 3x660 MW, Koradi TPS | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 15.869 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Procurement of heating elements for RAPH installed in Unit 9 (660MW) at KTPS Koradi THROUGH LIMITED TENDER | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 15.33 | 11.8 | 11.8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.2 | Replacement of heating elements for RAPH installed in Unit 9 (660MW) at KTPS Koradi | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 0.349 | 0.37 | 0.37 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 0.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | CHP Improvement (7 Nos) Schemes & Procurement of Bulldozers, Wheel Loaders and Hydraulic Cranes at CHP 3X660MW, KTPS, Koradi | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 38.87 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Sch-1: Revamping of Apron Feeder in CHP at 3X660MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.68 | 4.68 | 4.68 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Sch-2: Procurement of Hydraulic motors and pumps in CHP at 3X660 MW, KTPS, Koradi | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.44 | 4.44 | 4.44 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.3 | Sch-3: Capacity enhancement of Hydraulic motor of Apron Feeder in CHP, 3X660 MW, KTPS, Koradi | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 2.01 | 2.01 | 2.01 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.4 | Sch-4: Modification, supply and replacement of Transfer chutes in CHP 3x660MW KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.39 | 4.39 | 4.39 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.5 | Sch-5: Design, supply, installation & commissioning of High performance IGUS energy chain system with chain flex cable for Tripper trolleys at CHP at 3x660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.37 | 4.37 | 4.37 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.6 | Sch-6: Procurement of B3-630 gear box for BCN 6 A/B in CHP at 3x660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 0.57 | 0.57 | 0.57 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.7 | Sch-7: Supply and installation of Belt tear detector system for conveyor belt in CHP 3x660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 1.18 | 1.18 | 1.18 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.8 | Sch-8: Procurement of 5 Nos of Bulldozers BD 155 at CHP 3X660 MW Koradi Thermal Power station. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 12.83 | 12.83 | 12.83 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.9 | Sch-9:- Procurement of 02 nos. of Wheel loaders at CHP 3X660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 3.07 | 3.07 | 3.07 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Sch-10:- Procurement of 15 Ton & 20 Ton capacity hydraulic Cranes at CHP 3X660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 0.69 | 0.69 | 0.69 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 0.64 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Construction of bridge cum bandhara across Pond No. 3 and allied works at Pond No. 3 at Koradi TPS | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 33.116 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Construction of cement concrete bridge cum bandhara alongwith gated arrangement. | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 14.75 | 14.75 | 14.75 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.2 | Construction of earthen embankment connecting bridge cum bandhara on both side of embankment by excavating soil / typha / silt from Pond No.3 & tree plantation. | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 14.3252 | 14.3252 | 14.3252 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.3 | Providing structural steel pathway on the existing waste weir (west side of the Pond No.3) and roads connecting to bridge behind Pond No.3 and bridge cum bandhara. | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 2.4308 | 2.4308 | 2.4308 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 1.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement & replacement of Superheater Pass Economizer Coils (Modified Design) for Unit 8, 9 & 10 at 3x660MW KTPS, Koradi | Not Approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Procurement & replacement of Superheater Pass Economizer Coils (Modified Design) for Unit 8, 9 & 10 at 3x660MW KTPS, Koradi | Not Approved | - | 0 | 144.42 | 144.42 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Not Approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Improvement in Boiler Performance at U-8,9 & 10 KTPS, Koradi | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 62.929 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Scheme-1: Procurement of Blade Sets for ID, FD & PA Fans at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 11.34 | 11.34 | 11.34 | 0 | 0 | 0 |  |  | 0 | 0
7.2 | Scheme-2: Procurement of RAPH Bottom Support Bearing Assembly at 3X660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 2.478 | 2.478 | 2.478 | 0 | 0 | 0 |  |  | 0 | 0
7.3 | Scheme-3: Procurement of RAPH Top Guide Bearing Assembly at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 0.684 | 0.684 | 0.684 | 0 | 0 | 0 |  |  | 0 | 0
7.4 | Scheme-4: Procurement of RAPH Gear Box at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 3.44 | 3.44 | 3.44 | 0 | 0 | 0 |  |  | 0 | 0
7.5 | Scheme-5: Procurement of RAPH Spares at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 1.13 | 1.13 | 1.13 | 0 | 0 | 0 |  |  | 0 | 0
7.6 | Scheme-6: Procurement of Coal Burner Assembly with windbox air nozzles for Unit 8 & 9 at 3x660MW. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 15.407 | 15.407 | 15.407 | 0 | 0 | 0 |  |  | 0 | 0
7.7 | Scheme-7: Procurement of Boiler Circulation Pump (BCP) with Impeller & Diffuser at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 11.12 | 11.12 | 11.12 | 0 | 0 | 0 |  |  | 0 | 0
7.8 | Scheme-8: Procurement and Replacement of Heating Elements for RAPH Installed for Unit 8 at 3x660MW. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 15.96 | 15.96 | 15.96 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 1.37 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Design, Engineering, Supply, Installation, Testing, Commissioning including all civil works for Natural resource treatment and Laboratory equipment with mandatory spares at Koradi TPS, 3 X 660 MW | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 49.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.1 | Supply of Natural resource treatment and lab equipment for Water, Coal, Oil, Meteorology with supporting AI computing, all auxiliaries, and accessories. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 35.28 | 42.5744 | 42.5744 | 0 | 0 | 0 |  |  | 0 | 0
23.2 | Supply of Mandatory spares on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.8 | 0.944 | 0.944 | 0 | 0 | 0 |  |  | 0 | 0
23.3 | Supply of Tools and Tackles on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.15 | 0.177 | 0.177 | 0 | 0 | 0 |  |  | 0 | 0
23.4 | Complete Civil Work with 10 KLD ETP/ STP on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 3.6 | 4.25 | 4.25 | 0 | 0 | 0 |  |  | 0 | 0
23.5 | Services - Charges of Inland transport of plant and equipment on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.2 | 0.236 | 0.236 | 0 | 0 | 0 |  |  | 0 | 0
23.6 | Charges for Testing, Commissioning and PG Test of plant and equipment. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.05 | 0.059 | 0.059 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Improvement in Regenerative Air Preheater Performance & Complete Replacement of NDCT fills at Unit # 10, Koradi TPS | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 25.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.1 | Procurement of heating elements for RAPH installed in Unit 10 (660MW) at KTPS Koradi through OEM | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 12.23 | 14.521 | 14.521 | 0 | 0 | 0 |  |  | 0 | 0
24.2 | Complete Supply & Replacement of NDCT fills of U#10. | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 13 | 13 | 13 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 0.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 14 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 14.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 10.994 | 10.994 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 15 | HMI (Human Machine Interface) Upgradation of ‘SSPA-T3000’ DCS (Distribution Control System), Rockwell make PLC System installed at 3x660MW Unit No. 8, 9 & 10 at Koradi TPS and HMI (Human Machine Interface) Upgradation of MaxDNA DCS System at Unit 8-9, CSTPS, Chandrapur | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 55.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 15.1 | Supply: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 10.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 15.2 | Works: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | HMI (Human Machine Interface) Upgradation of ‘SPPA-T3000’ DCS (Distributed Control System) installed at 3x660MW Unit- 8, 9 & 10 at Koradi TPS to match with the external aspects and process improvement | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 24.33 | 24.33 | 24.33 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Upgradation of Rockwell Make PLC System installed at 3x660MW ,Koradi TPS to match with the external aspects and process improvement.(C&I) | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 20.2 | 20.2 | 20.2 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Work of provision of platform beside railway siding at backside of chord cabin for loading of fly ash in railway wagon for ash utilization at 3x660 MW TPS, Koradi | 0 | - | 0 | 0.0038356 | 0.0038356 | 0 | 0 | 0 |  |  | 0 | 0
13 | Capital Exenditure schemes for in-principle clearance regarding "EPC contract for the wok of construction of quarters and development of KTPS colony at Koradi" under CAPEX scheme | MERC/CAPEX/MSPGCL/2024-12/0569 DTD.13.09.2024 | 2024-09-13 | 210.48 | 210.48 | 210.48 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of spares for L&T-MHI make Turbine for COH work of Turbine at KTPS, 3x660MW units Koradi | MERC/CAPEX/MSPGCL/2023-24/0639 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement of spares for L&T-MHI make Turbine for COH work of Turbine at KTPS, 3x660MW units Koradi | MERC/CAPEX/MSPGCL/2023-24/0639 | - | 0 | 31.6358 | 31.6358 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Procurement of HP Nozzle assembly for L&T-MHI Make Turbine installed at 3x660MW Units Koradi | MERC/CAPEX/MSPGCL/2023-24/0639 | - | 0 | 4.189 | 4.189 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | C) DPRs Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Control & instrumentation related Various Upgradation schemes viz.Emission Monitoring & Water Quality Analysers ,Vibration Monitoring Schemes,Water Flow Monitoring etc. at 3X660MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Upgradation of Emission Monitoring Analysers | 0 | - | 0 | 9.58 | 9.58 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Upgradation of Water Quality Analysers | 0 | - | 0 | 5.33 | 5.33 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Revamping & Supply Of Upgraded VM7B Version of Vibration Monitoring Rack | 0 | - | 0 | 4.84 | 4.84 | 0 | 0 | 0 |  |  | 0 | 0
2.4 | Implementation of ‘Flow Monitoring System’ at 3x660MW Balance of Plant (BOP) Unit- 8, 9 & 10 at Koradi TPS | 0 | - | 0 | 6.87 | 6.87 | 0 | 0 | 0 |  |  | 0 | 0
3 | CHP Improvement Scheme-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Supply, Erection, Commissioning of set of Internals for Wagon Tipplers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 10.96 | 10.96 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Supply, Erection, Commissioning of set of Internals for Side Arm Chargers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 3.54 | 3.54 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Supply, Erection, Commissioning of set of Internals for Wobbler Feeders at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 4.96 | 4.96 | 0 | 0 | 0 |  |  | 0 | 0
3.4 | Supply, Erection, Commissioning of set of Internals for Apron Feeders at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 15.55 | 15.55 | 0 | 0 | 0 |  |  | 0 | 0
3.5 | Supply, Erection, Commissioning of set of Internals for Impact Crushers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 9.63 | 9.63 | 0 | 0 | 0 |  |  | 0 | 0
3.6 | Supply, Erection, Commissioning of set of Internals for Stacker cum Reclaimers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 6.26 | 6.26 | 0 | 0 | 0 |  |  | 0 | 0
4 | Performance improvement and availability of various Auxiliaries of TG at 3x660MW KTPS Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Performance improvement and availability of various Auxiliaries for Oil Systems of Main Turbine. | 0 | - | 0 | 3.26 | 3.26 | 0 | 0 | 0 |  |  | 0 | 0
4.2 | Performance improvement and availability of various Auxiliaries of Generator System. | 0 | - | 0 | 7.31 | 7.31 | 0 | 0 | 0 |  |  | 0 | 0
4.3 | Performance improvement and availability of Feed Water System. | 0 | - | 0 | 10.54 | 10.54 | 0 | 0 | 0 |  |  | 0 | 0
4.4 | Performance improvement and availability of Vacuum System. | 0 | - | 0 | 2.28 | 2.28 | 0 | 0 | 0 |  |  | 0 | 0
4.5 | Performance improvement and availability of CEP System. | 0 | - | 0 | 7.83 | 7.83 | 0 | 0 | 0 |  |  | 0 | 0
4.6 | Procurement of Complete Pull out Assembly along with Impeller and wear ring of Cooling Water Pump. | 0 | - | 0 | 14.87 | 14.87 | 0 | 0 | 0 |  |  | 0 | 0
4.7 | Procurement of complete assembly of HP and LP Elements for Atlas Copco make Compressors. | 0 | - | 0 | 4.19 | 4.19 | 0 | 0 | 0 |  |  | 0 | 0
5 | Improvement in Wet ash evacuation system at 3x660MW Units, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Procurement & installation of Ash Slurry Series Pump Assembly with modified metallurgy and Critical Wet End Sub Assembly to enhance the performance & slurry disposal capacity. | 0 | - | 0 | 7.53 | 7.53 | 0 | 0 | 0 |  |  | 0 | 0
5.2 | Procurement & installation of Ash Slurry Series Pump Assembly with modified metallurgy along with Gear Box, Fluid Coupling & Motor (4’th Series) and Critical Wet End Sub Assembly to enhance the performance & slurry disposal capacity. | 0 | - | 0 | 2.51 | 2.51 | 0 | 0 | 0 |  |  | 0 | 0
5.3 | Procurement & installation of Overflow Transfer Pump Assembly with upgradation in metallurgy and Critical Wet End Sub Assembly to enhance the performance. | 0 | - | 0 | 3.59 | 3.59 | 0 | 0 | 0 |  |  | 0 | 0
5.4 | Procurement & installation of IAC Compressor Assembly: Model –ZR110 STD 7.5 IMD Atlas Copco Make Oil free water cooled screw air compressor with inbuilt atlas copco make heat of compression single drum rotator air dryer to enhance the performance. | 0 | - | 0 | 7.56 | 7.56 | 0 | 0 | 0 |  |  | 0 | 0
6 | HMI Upgradation of Diasys Netmation DCS at 3x660MW KTPS Koradi Units 8,9 & 9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | HMI Upgradation of Diasys Netmation DCS at 3x660MW KTPS Koradi Units 8,9 & 10 | 0 | - | 0 | 77.15 | 77.15 | 0 | 0 | 0 |  |  | 0 | 0
7 | Improvement in Dry ash evacuation system at 3x660MW Units, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Procurement of Ingersoll Rand Make Transport Air Compressors Critical/Non-Critical Spares sub-assembly for performance improvement. | 0 | - | 0 | 29.57 | 29.57 | 0 | 0 | 0 |  |  | 0 | 0
8 | MSERW Pipes for Garlanding arrangement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.1 | Work of Garlanding arrangement to changeover ash slurry feed points for even filling of pond by providing MSERW Pipes along the periphery of Ash Bund Dyke Wall at Khasara Ash Bund. | 0 | - | 0 | 98.83 | 98.83 | 0 | 0 | 0 |  |  | 0 | 0
9 | Capacity Enhancement & Performance optimization at WTP 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.1 | Capacity enhancement of DM water stream in WTP at 3X660MW, KTPS, Koradi. | 0 | - | 0 | 58.94 | 58.94 | 0 | 0 | 0 |  |  | 0 | 0
9.2 | Capacity enhancement Condensate polishing unit regeneration area in WTP at 3X660 MW, KTPS, Koradi | 0 | - | 0 | 13.41 | 13.41 | 0 | 0 | 0 |  |  | 0 | 0
9.3 | Provision of Ozone generating plant of 1.0 Kg capacity in WTP at 3X660 MW, KTPS, Koradi | 0 | - | 0 | 5.84 | 5.84 | 0 | 0 | 0 |  |  | 0 | 0
10 | DPR for Construction of CC Road alongwith RCC Drain, CC platform for heavy machinery movement at 3x660 MW, TPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.1 | DPR for Construction of CC Road alongwith RCC Drain, CC platform for heavy machinery movement at 3x660 MW, TPS, Koradi | 0 | - | 0 | 33.57 | 33.57 | 0 | 0 | 0 |  |  | 0 | 0
11 | Improvement in Coal Mill Performance-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.1 | Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi through OEM. | 0 | - | 0 | 6.15 | 6.15 | 0 | 0 | 0 |  |  | 0 | 0
11.2 | Procurement of Mill Rotary Separator Blades for coal mill MVM 32R at 3x660 MW, KTPS, Koradi through open tender | 0 | - | 0 | 4.01 | 4.01 | 0 | 0 | 0 |  |  | 0 | 0
11.3 | Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi through OEM. | 0 | - | 0 | 14.57 | 14.57 | 0 | 0 | 0 |  |  | 0 | 0
11.4 | Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi through OEM | 0 | - | 0 | 6.14 | 6.14 | 0 | 0 | 0 |  |  | 0 | 0
12 | Improvement in Boiler performance-II at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.1 | Scheme1:Procurement of Coal compartment assembly for Unit8 at 3x660MW KTPS, Koradi | 0 | - | 0 | 12.7 | 12.7 | 0 | 0 | 0 |  |  | 0 | 0
12.2 | Scheme2:Procurement of blade sets for ID, FD & PA Fan at 3x660 MW, Units at KTPS Koradi through OEM. | 0 | - | 0 | 11.34 | 11.34 | 0 | 0 | 0 |  |  | 0 | 0
12.3 | Scheme3:Procurement of RAPH internal Spares for 3X660MW units at KTPS Koradi through OEM (Qty- 6 Sets) | 0 | - | 0 | 1.13 | 1.13 | 0 | 0 | 0 |  |  | 0 | 0
12.4 | Scheme4:Procurement of RAPH Sector plate with Actuating mechanism assembly for Unit9 3 X 660MW Units at KTPS, Koradi. | 0 | - | 0 | 7.2 | 7.2 | 0 | 0 | 0 |  |  | 0 | 0
13 | Improvement in Coal Mill performance-II at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | Procurement of FLENDER make Gearbox model kmp-450 along with motor for coal mill MVM32R at 3x660mw KTPS, koradi through OEM. | 0 | - | 0 | 20.91 | 20.91 | 0 | 0 | 0 |  |  | 0 | 0
13.2 | Procurement of complete set of couplings for PA, ID & FD fans at 3X660MW units at KTPS Koradi through OEM | 0 | - | 0 | 5.14 | 5.14 | 0 | 0 | 0 |  |  | 0 | 0
14 | Improvement in Coal Mill performance-III at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 6.15 | 6.15 | 0 | 0 | 0 |  |  | 0 | 0
14.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 14.57 | 14.57 | 0 | 0 | 0 |  |  | 0 | 0
14.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 6.14 | 6.14 | 0 | 0 | 0 |  |  | 0 | 0
14.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit10 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
14.5 | Scheme5:Procurement of Complete MRHS System along with Pneumatic Compressors at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
15 | Improvement in Boiler performance-III at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | Scheme1:Procurement of Coal compartment assembly for Unit8at 3x660MW KTPS, Koradi | 0 | - | 0 | 12.7 | 12.7 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Scheme2:Procurement of blade sets for ID, FD & PA Fan at 3x660 MW, Units at KTPS Koradi through OEM. | 0 | - | 0 | 11.34 | 11.34 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Scheme3:Procurement and replacement of heating elements for RAPH installed in Unit 9 (660MW) at KTPS Koradi THROUGH OEM/OES (Qty- 2 Sets) | 0 | - | 0 | 16 | 16 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Scheme4:Procurement of HP valves, safety valves and ERV's for 3X660MW units at KTPS Koradi through OEM | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
15.5 | Scheme5:Procurement of RAPH Sector plate with Actuating mechanism assembly for Unit8 3 X 660MW Units at KTPS, Koradi. | 0 | - | 0 | 7.2 | 7.2 | 0 | 0 | 0 |  |  | 0 | 0
15 | Improvement in Coal Mill performance-IV at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 6.15 | 6.15 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 14.57 | 14.57 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 6.14 | 6.14 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit8 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
16 | Improvement in Coal Mill performance-V at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 6.15 | 6.15 |  |  | 6.15 | 0
16.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 14.57 | 14.57 |  |  | 14.57 | 0
16.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 6.14 | 6.14 |  |  | 6.14 | 0
16.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit9 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
17 | Improvement in Boiler performance-IV at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.1 | Scheme1:Procurement of Coal compartment assembly for Unit8 at 3x660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.2 | Scheme2:Procurement of blade sets for ID, FD & PA Fan at 3x660 MW, Units at KTPS Koradi through OEM. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.3 | Scheme3:Procurement of RAPH bottom support bearing assembly for 3X660MW units at KTPS Koradi through OEM (Qty- 2 Sets) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.4 | Scheme4:Procurement of RAPH top guide bearing assembly for 3X660MW units at KTPS Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.5 | Scheme5:Procurement of RAPH Gear Box for 3X660MW units at KTPS Koradi through OEM (Qty- 1 Sets) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.6 | Scheme6:Procurement of RAPH Sector plate with Actuating mechanism assembly for Unit10 at 3 X 660MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.7 | Scheme7:Procurement and replacement of heating elements for RAPH installed in Unit 10 (660MW) at KTPS Koradi THROUGH OEM/OES (Qty- 2 Sets) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.8 | Scheme8:Procurement of Boiler Circulating Pump (1 Nos) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | Improvement in Coal Mill performance-VI at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit9 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.3 | Reliability Improvement schemes of generators at 3X660MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | Scheme No. 1 :PROCUREMENT OF MELCO/LMTG MAKE GENERATOR ROTOR ASSEMBLY with excitation transformer AT 3X660MW KTPS, KORADI THROUGH OEM | 0 | - | 0 | 45.39 | 45.39 | 0 | 0 | 0 |  |  | 0 | 0
19.2 | Scheme No. 2:PROCUREMENT OF ONE COMPLETE SET OF GENERATOR STATOR COILS FOR GENERATOR AT 3X660MW UNITS AT KTPS KORADI THROUGH OEM | 0 | - | 0 | 35.4 | 35.4 | 0 | 0 | 0 |  |  | 0 | 0
25 | DPR on Procurement of Critical Speares for L&T make Main Turbine(typeTC4F-30) installed at 3x660MW KTPS Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.1 | Scheme No. 1 :Procurement of Critical Speares for L&T make Main Turbine(typeTC4F-30) installed at 3x660MW KTPS Koradi. | 0 | - | 0 | 126.41 | 126.41 | 0 | 0 | 0 |  |  | 0 | 0
26 | DPR for Coal Handling Plant Performance Improvement Schemes -II at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.1 | Scheme No. 1 : Performance Improvement of Unloading System Wagon Tipplers at CHP 3x660MW KTPS Koradi | 0 | - | 0 | 5.8 | 5.8 | 0 | 0 | 0 |  |  | 0 | 0
26.2 | Scheme No. 2 : Performance Improvement of Unloading System Side Arm Chargers at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Side Arm Charger Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 2.8 | 2.8 | 0 | 0 | 0 |  |  | 0 | 0
26.3 | Scheme No. 3 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 3.2 | 3.2 | 0 | 0 | 0 |  |  | 0 | 0
26.4 | Scheme No. 4 : Performance Improvement of Stacking & Reclaiming System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Stacking & Reclaiming System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 6.5 | 6.5 | 0 | 0 | 0 |  |  | 0 | 0
26.5 | Scheme No. 5 : Performance Improvement of Crushing System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Impact Crusher & Wobbler Feeders Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 8.5 | 8.5 | 0 | 0 | 0 |  |  | 0 | 0
26.6 | Scheme No. 6 : Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -1 at CHP 3x660MW KTPS Koradi A) Brief scope of work: Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -1 at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
27 | DPR for Coal Handling Plant Performance Improvement Schemes -III at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.1 | Scheme No. 1 : Performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Hydraulic system for Wagon Tippler, Side Arm Charger , Apron Feeder ( 1 & 2) Stacker Reclaimer 1 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 10.5 | 10.5 | 0 | 0 | 0 |  |  | 0 | 0
27.2 | Scheme No. 2 : Construction of Air tight Hydraulic power pack room along with necessary cooling system for performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Construction of Air tight Hydraulic power pack room along with necessary cooling system for Wagon Tippler & Apron Feeder ( 1 to 4) Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 3.2 | 3.2 | 0 | 0 | 0 |  |  | 0 | 0
27.3 | Scheme No. 3 : Performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory Hydraulic Power Cylinders of Wagon Tippler, Side Arm Charger ( 1 to 4) Stacker Reclaimer 1 & 2 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
27.4 | Scheme No. 4 : Performance Improvement of Stacker Reclaimer by providing Hydraulic Drive to Boom Conveyor at CHP 3x660MW KTPS Koradi A) Brief scope of work: Hydraulic Drive to Boom Conveyor Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.9 | 0.9 | 0 | 0 | 0 |  |  | 0 | 0
27.5 | Scheme No. 5 : Performance Improvement of Illumination system with energy conservation at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Solar High masts along the rail track in railway yard Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 3.75 | 3.75 | 0 | 0 | 0 |  |  | 0 | 0
27.6 | Scheme No. 6 : Design, Supply & Installation of LT VFD Drives for Critical Conveyors at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of LT VFD Drives for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
27.7 | Scheme No. 7 : Design , supply, Erection & Commissioning of Short Conveyor for Stacking Purpose at CHP 3x660MW KTPS Koradi A) Brief scope of work: Short Conveyor for Stacking Purpose at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 9.6 | 9.6 | 0 | 0 | 0 |  |  | 0 | 0
27.8 | Scheme No. 8 : Capacity Enhancement of BCN-7/5/4/3 /1 AB in CHP 3x660MW KTPS Koradi A) Brief scope of work: Short Conveyor for Stacking Purpose at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 8.6 | 8.6 | 0 | 0 | 0 |  |  | 0 | 0
27.9 | Scheme No. 9 : Design , Engineering & modification along with strengthening of Existing Travel Track structure for Side Arm Charger & Stacker Reclaimer A) Brief scope of work: strengthening of Existing Travel Track structure for Side Arm Charger & Stacker Reclaimer Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
27.1 | Scheme No. 10 : Design , Engineering & Erection of modified Energy Efficient Ventilation System for Wagon Tippler Complex Area in CHP 3X660MW KTPS Koradi A) Brief scope of work: Energy Efficient Ventilation System for Wagon Tippler Complex Area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
27.11 | Scheme No. 11 : Design , Engineering & Installtion of Vibration & temprature Monitoring Systems for critical auxiliaries in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Installtion of Vibration & temprature Monitoring Systems for critical auxiliaries Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
27.12 | Scheme No. 12 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
27.13 | Scheme No. 13 : Design , Engineering & Provision of Stone Grappling Equipment System for Wagon Tippler 3 &4 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Stone Grappling Equipment System for Wagon Tippler 3 &4 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.9 | 0.9 | 0 | 0 | 0 |  |  | 0 | 0
27.14 | Scheme No. 14 : Design , Engineering & Provision of Public Addressing System for Wagon Tippler Complex in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Public Addressing System for Wagon Tippler Complex in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
27.15 | Scheme No. 15 : Design , Engineering & Provision of Belt Tracking System for Critical Conveyors in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Belt Tracking System for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
27.16 | Scheme No. 16 : Design , Engineering & Provision of Dust supression System for stacker reclaimer-1 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.6 | 0.6 | 0 | 0 | 0 |  |  | 0 | 0
27.17 | Scheme No. 17 : Work of Life Enhancement of wobbler Feeder 1 &2 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.6 | 1.6 | 0 | 0 | 0 |  |  | 0 | 0
28 | DPR for Coal Handling Plant Performance Improvement Schemes -IV at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28.1 | Scheme No.1 : Design , Engineering , Supply & Installation of Modular Transfer chutes for Critical Conveyor System in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of Modular Transfer chutes for Conveyor System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 14 | 14 | 0 | 0 | 0 |  |  | 0 | 0
28.2 | Scheme No.2 :Upgradtion of Exsisting Fire Fighting System at Stack yard area in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradtion of Exsisting Fire Fighting System at Stack yard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 2.6 | 2.6 | 0 | 0 | 0 |  |  | 0 | 0
28.3 | Scheme No.3 : Design , Engineering , Supply & Strengthening of engineering structure of BCN- 7A/B along with track alignment in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Strengthening of engineering structure of BCN- 7A/B Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 2.4 | 2.4 | 0 | 0 | 0 |  |  | 0 | 0
28.4 | Scheme No.4 : Design , Engineering , Supply & Installation of Mist Cannon Spray System around stackyard area in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of Mist Cannon Spray System at stackyard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.6 | 1.6 | 0 | 0 | 0 |  |  | 0 | 0
28.5 | Scheme No.5 : Design , Engineering , Supply & Installation of EOT cranes at Bunker in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of EOT cranes at Bunker Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 4.5 | 4.5 | 0 | 0 | 0 |  |  | 0 | 0
29 | DPR for Procurment of various Heavy Vehicles at CHP 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29.1 | Scheme No.1 : Procurment of Heavy Vehicles like dozers, wheel loaders , locomotives, Crane, Hydra , Disel Browser , Jcb & Bobcats etc. in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurment of Heavy Vehicles like dozers, wheel loaders , locomotives etc Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
29.2 | Scheme No.2 : Procurment of Auger Machines for coal sampling in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurment of Auger Machines for coal sampling Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 2.2 | 2.2 | 0 | 0 | 0 |  |  | 0 | 0
29.3 | Scheme No.3 : Procurment of Truck Mounted mist cannon dust supression system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurment of Truck Mounted mist cannon dust supression system in CHP Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.8 | 0.8 | 0 | 0 | 0 |  |  | 0 | 0
30 | DPR for Coal Handling Plant Performance Improvement Schemes -V at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.1 | Scheme No. 1 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 3.2 | 3.2 | 0 | 0 | 0 |  |  | 0 | 0
30.2 | Scheme No. 2 : Performance Improvement of Stacking & Reclaiming / Side Arm Charger System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Energy Chain System of Stacking & Reclaiming System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
30.3 | Scheme No. 3 : Performance Improvement of unloading System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Energy Chain System of side arm acharger Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
30.4 | Scheme No. 4 : Upgradation to 100 MT Ton Weighbridge of existing road weighbridge at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of LT VFD Drives for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.8 | 0.8 | 0 | 0 | 0 |  |  | 0 | 0
30.5 | Scheme No. 5 : Design , Engineering & Erection of modified Energy Efficient Ventilation System for Crusher House Area in CHP 3X660MW KTPS Koradi A) Brief scope of work: Energy Efficient Ventilation System for Wagon Tippler Complex Area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
30.6 | Scheme No. 6 : Design , supply & Installation of Cooling Arrangement for Switchgear rooms at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Cooling Arrangement for Switchgear rooms Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
30.7 | Scheme No. 7 : Design , Engineering & Erection of modified Engineering Structure of Tunnel Conveyor 1A &1 B in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Erection of modified Engineering Structure of Tunnel Conveyor 1A &1 B Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 2.35 | 2.35 | 0 | 0 | 0 |  |  | 0 | 0
31 | DPR for Coal Handling Plant Performance Improvement Schemes -VI at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.1 | Scheme No. 1 : Performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Wagon Tippler, Side Arm Charger , Apron Feeder ( 3 & 4) Stacker Reclaimer 2 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 11.5 | 11.5 | 0 | 0 | 0 |  |  | 0 | 0
31.2 | Scheme No. 2 : Design Supply & Installation of Wagon Locking system for all four wagon tipplers at CHP 3x660MW KTPS Koradi A) Brief scope of work: Wagon Locking system for all four wagon tipplers Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
31.3 | Scheme No. 3 : Design, Supply & Installation of upgraded Vibrating Feeders for Stacker Reclaimer at CHP 3x660MW KTPS Koradi A) Brief scope of work: Design, Supply & Installation of upgraded Vibrating Feeders for Stacker Reclaimer Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.9 | 0.9 | 0 | 0 | 0 |  |  | 0 | 0
31.4 | Scheme No. 4: Performance Improvement of Stacker Reclaimer by providing Hydraulic Drive to Boom Conveyor at CHP 3x660MW KTPS Koradi A) Brief scope of work: Hydraulic Drive to Boom Conveyor Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.9 | 0.9 | 0 | 0 | 0 |  |  | 0 | 0
31.5 | Scheme No. 5 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
31.6 | Scheme No. 6 : Design , Engineering & Provision of Belt Tracking System for Critical Conveyors in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Belt Tracking System for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.6 | 1.6 | 0 | 0 | 0 |  |  | 0 | 0
31.7 | Scheme No. 7 : Design , Engineering & Provision of Dust supression System for stacker reclaimer-1 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.6 | 0.6 | 0 | 0 | 0 |  |  | 0 | 0
31.8 | Scheme No. 8 : Work of Life Enhancement of wobbler Feeder 3 &4 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.6 | 1.6 | 0 | 0 | 0 |  |  | 0 | 0
32 | DPR for Coal Handling Plant Performance Improvement Schemes -VII at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.1 | Scheme No.1 : Design , Engineering , Supply & Installation of Modular Transfer chutes for Crusher House Complex & other Critical Conveyor System in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of Modular Transfer chutes for Conveyor System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 13 | 13 | 0 | 0 | 0 |  |  | 0 | 0
32.2 | Scheme No.2 :Upgradtion of Exsisting Fire Fighting System along the conveyor length in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradtion of Exsisting Fire Fighting System at Stack yard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 3.2 | 3.2 | 0 | 0 | 0 |  |  | 0 | 0
32.3 | Scheme No.3 : Supply , Erection & Installation of Rack & Pinion Elevators at Bunker in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Supply , Erection & Installation of Rack & Pinion Elevators at Bunker in CHP 3X660MW KTPS Koradi. Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.8 | 0.8 | 0 | 0 | 0 |  |  | 0 | 0
32.4 | Scheme No.4 :Up Liftment f Exsisting Fire Fighting lines in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradtion of Exsisting Fire Fighting System at Stack yard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 3.2 | 3.2 | 0 | 0 | 0 |  |  | 0 | 0
32.5 | Scheme No.5 : Procurement of HPPE Polymer Roller for Conveyor system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurement of HPPE Polymer Roller for Conveyor system Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.8 | 0.8 | 0 | 0 | 0 |  |  | 0 | 0
32.6 | Scheme No.6 : Design , Engineering , Supply & Installation of EOT cranes at Wagon Tippler Complex in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of EOT cranes at Wagon Tippler Complex Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 6.2 | 6.2 | 0 | 0 | 0 |  |  | 0 | 0
33 | DPR for Coal Handling Plant Performance Improvement Schemes -VIII at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.1 | Scheme No. 1 : Performance Improvement of Unloading System Wagon Tipplers at CHP 3x660MW KTPS Koradi Estimated Cost : 3.6 Cr. | 0 | - | 0 | 0 | 0 | 0 | 3.6 | 3.6 |  |  | 3.6 | 0
33.2 | Scheme No. 2 : Performance Improvement of Unloading System Side Arm Chargers at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Side Arm Charger Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 2.8 | 2.8 |  |  | 2.8 | 0
33.3 | Scheme No. 3 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 3.4 | 3.4 |  |  | 3.4 | 0
33.4 | Scheme No. 4 : Performance Improvement of Stacking & Reclaiming System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Stacking & Reclaiming System -2 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 3.5 | 3.5 |  |  | 3.5 | 0
33.5 | Scheme No. 5 : Performance Improvement of Crushing System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Impact Crusher & Wobbler Feeders Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 8.5 | 8.5 |  |  | 8.5 | 0
33.6 | Scheme No. 6 : Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -2 at CHP 3x660MW KTPS Koradi A) Brief scope of work: Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -2 at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
33.7 | Scheme No. 7 : Other Mislenious Schemes at CHP 3x660MW KTPS Koradi A) Brief scope of work: Other Mislenious works Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
33.8 | Scheme No. 4 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0.8 | 0.8 |  |  | 0.8 | 0
33.9 | Scheme No.8: Procurement of HPPE Polymer Roller for Conveyor system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurement of HPPE Polymer Roller for Conveyor system Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0.8 | 0.8 |  |  | 0.8 | 0
34 | DPR for Coal Handling Plant Performance Improvement Schemes -IX at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.1 | Scheme No. 1 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.2 | Scheme No. 2 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.3 | Scheme No.3 : Upgradation of Exsisting Rack & Pinion Elevators at CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradation of Exsisting Rack & Pinion Elevators Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.4 | Scheme No.4 : Procurement of HPPE Polymer Roller for Conveyor system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurement of HPPE Polymer Roller for Conveyor system Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.5 | Scheme No.5 : Other miscellaneous scheme regarding sustainable performance improvement of CHP 3X660MW KTPS Koradi. A) Brief scope of work: ther miscellaneous scheme regarding sustainable performance improvement Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | Design & engineering, procurement, supply, installation & commissioning of Ozone Generator system of capacity 45.0 Kg/hr for CW system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Scheme1:Design & engineering, procurement, supply, installation & commissioning of Ozone Generator system of capacity 45.0 Kg/hr for CW system | 0 | - | 0 | 45 | 45 | 0 | 0 | 0 |  |  | 0 | 0
36 | Pipeline expansion to improve dry ash evacuation system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.1 | Scheme1: Pipeline expansion to improve dry ash evacuation system along with target box modification and also to erect & commission dry ash evacuation directly to remote silo. | 0 | - | 0 | 75 | 75 | 0 | 0 | 0 |  |  | 0 | 0
37 | Modification at intermediate silo and HCSD system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.1 | Scheme1: Additional charge pump. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
37.2 | Scheme 2: Supply & Installation Air washery at silo top. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
37.3 | Scheme 3: Shed above silo top. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
37.4 | Scheme 4: Supply & Installation Construction of platform at pipe rack up to Remote silo. | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
37.5 | Scheme 5: Shifting of pipeline above pipe rack. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
37.6 | Scheme 6: Supply & Installation ART sub assemblies. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
38 | ESP field strengthening at U#8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.1 | Scheme1: ESP field strengthening at U#8 | 0 | - | 0 | 120 | 120 | 0 | 0 | 0 |  |  | 0 | 0
39 | Procurement of various pumps for AHP performance improvement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
39.1 | Scheme1: Procurement of various pumps for AHP performance improvement. | 0 | - | 0 | 28 | 28 | 0 | 0 | 0 |  |  | 0 | 0
40 | Modification in Dry Ash Evacuation System D/V Assemblies & allied equipments to improve performance | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
40.1 | Scheme1: Procurement of D/V Assemblies & allied equipments to improve performance. | 0 | - | 0 | 35 | 35 | 0 | 0 | 0 |  |  | 0 | 0
41 | Additional IAC house for Intermediate silo and Remote silo along with erection of S.S. Pipeline | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.1 | Scheme1: Supply & Installation Additional IAC house for Intermediate silo and Remote silo along with erection of S.S. Pipeline | 0 | - | 0 | 50 | 50 | 0 | 0 | 0 |  |  | 0 | 0
42 | Waste water system modification to have zero water discharge | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.1 | Scheme1: Waste water system modification to have zero water discharge at 3x660MW, KTPS, Koradi along with Pump Procurement along with arrangement of sludge discharge at ESP water Washing system. | 0 | - | 0 | 26 | 26 | 0 | 0 | 0 |  |  | 0 | 0
43 | ESP field strengthening at U#9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
43.1 | Scheme1: ESP field strengthening at U#9 | 0 | - | 0 | 275 | 275 | 0 | 0 | 0 |  |  | 0 | 0
44 | Procurement of HCSD GEHO Pump (TZPM-400) critical items sub-assemblies | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.1 | Scheme1: Procurement of HCSD GEHO Pump TZPM-400) critical items sub-assemblies. | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
45 | MSERW Pipes & Seamless Pipes replacement to improve ash conveying & its disposal-1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.1 | Scheme1: Supply & Work of Replacement of MSERW Pipes & Seamless Pipes in Bottom ash/Coarse ash evacuation & Ash Slurry Disposal Pipelines, Dry ash conveying system in phase manner to improve the ash evacuation performance. | 0 | - | 0 | 70 | 70 | 0 | 0 | 0 |  |  | 0 | 0
46 | Improvement in Ash Water Recovery System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.1 | Scheme1: Supply & Installation of Pumps along with Pipeline for Improvement in Ash Water Recovery System. | 0 | - | 0 | 0 | 0 | 0 | 35 | 35 |  |  | 35 | 0
47 | Replacement of Instrument air pipeline from M.S. to S.S for AHP main plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.1 | Scheme1: Replacement of Instrument air pipeline from M.S. to S.S for AHP main plant | 0 | - | 0 | 0 | 0 | 0 | 40 | 40 |  |  | 40 | 0
48 | Modification of sludge pumps and its pipeline with pumps of higher capacity and discharge line of higher capacity. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.1 | Scheme1: Modification of sludge pumps and its pipeline with pumps of higher capacity and discharge line of higher capacity. | 0 | - | 0 | 0 | 0 | 0 | 50 | 50 |  |  | 50 | 0
49 | ESP field strengthening at U#10 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
49.1 | Scheme1: ESP field strengthening at U#10 | 0 | - | 0 | 0 | 0 | 0 | 310 | 310 |  |  | 310 | 0
50 | MSERW Pipes & Seamless Pipes replacement to improve ash conveying & its disposal-2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50.1 | Scheme1: Supply & Work of Replacement of MSERW Pipes & Seamless Pipes in Bottom ash/Coarse ash evacuation & Ash Slurry Disposal Pipelines, Dry ash conveying system in phase manner to improve the ash evacuation performance. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
51 | Replacement of IAC for AHP Main Plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
51.1 | Scheme1: Supply & Installation of IAC for AHP Main Plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
52 | Improvement in DRY ASH Evacuation system-2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
52.1 | Scheme1: Supply & Installation of TAC, Replacement of Air Lock Vessel, Various Valves, ESP Hopper Doors, ESP access doors. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
53 | Improvement in DRY ASH Evacuation system-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
53.1 | Scheme1: Procurement of Ingersoll Rand Make Transport Air Compressors Critical/Non-Critical Spares sub-assembly for performance improvement. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
54 | Detailed project report for various works of security section as per the IB recommendations. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
54.1 | Repairing & raising height of compound wall with provision of concertina coil at various location of peripheral compound wall at 3x660MW KTPS Koradi. | 0 | - | 0 | 1.593 | 1.593 | 0 | 0 | 0 |  |  | 0 | 0
54.2 | Work of Providing structural three quarter turn staircase with landing along pheriphery of FISS watch tower at 3x660MW, TPS, Koradi. | 0 | - | 0 | 0.34444 | 0.34444 | 0 | 0 | 0 |  |  | 0 | 0
55 | Supply, installation, comissioning and testing of 220V station & 360V UPS batteries installed at U 8, 9 & 0 of 3x660 MW KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
55.1 | Supply, installation, comissioning and testing of 220V station & 360V UPS batteries installed at U 8, 9 & 0 of 3x660 MW KTPS, Koradi. (scheme) | 0 | - | 0 | 45.6 | 45.6 | 0 | 22.8 | 22.8 |  |  | 22.8 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
56 | TDBFP Governing valve's LPCV ,HPCV MSV AND Trip lock replacement | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
61 | Procurement & replacement of HP Heaters at 3x660 MW KTPS, Koradi. | 0 | - | 0 | 0 | 25 | -25 | 0 | 0 |  |  | 0 | -25
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Vibration Monitoring & Analysis system installed at 3x660MW Koradi TPS. | 0 | - | 0 | 63 | 63 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of sinkawa make vibration monitoring and Analysis system for main turbine at 3x660MW koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of Bently Nevada make vibration monitoring and Analysis system for RMCMS system at 3x660MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3 :-Emerson PLC upgradation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of various Level Transmitters installed at 3x660 MW koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 31 | 31 |  |  | 31 | 0
0 | Scheme 1: Upgradation of Guided wave Radar Level TX installed at Condenser Hotwell and LPH 1,2 and 3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of Displacer type level TX into Guided wave radar level Tx installed at various Drain Tank, Flash tank and pit | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3: Upgradation of non- contact type Ultrasonic level Tx into IP68 non- contact type Radar level TX. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of ESP Hopper level Probes installed at 3x660 MW koradi TPS. | 0 | - | 0 | 40 | 40 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of 1st three fields ESP Hopper level probes into continuous level monitoring NOGS system at 3x660 MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of RF capacitance Hopper level probe into of RF admittance level probe at 4,5,6,7,8 & 9 ESP Hoppers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3: Upgradation of ESP hopper heater monitoring , control and real time monitoring system at 3X660MW Koradi TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of various scheme viz ASLD, Furnace tv camera FEGT and acoustic Pyrometer installed at 3x660 MW koradi TPS. | 0 | - | 0 | 61 | 61 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of ASLD system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of Furnace TV Camera | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3:Upgradation of FEGT system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 4:Upgradation of acoustic pyrometer | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of various scheme viz instrument Air pipe at ESP Area, wet Ash Evacuation system, HCSD Silo. | 0 | - | 0 | 0 | 0 | 0 | 26 | 26 |  |  | 26 | 0
0 | Scheme 1: Upgradation of instrument Air pipeline system at ESP of M.S into SS installed at 3x660 MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of instrument Air pipeline system at wet Ash system of M.S into SS . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3: Upgradation of instrument Air pipeline system at HCSD silo of M.S. into SS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 4: Upgradation of instrument Air pipeline system at Remote Silo of M.S into SS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 5: Upgradation of Control & Instrument section lab with Hydraulic Servo Valve Test, Pneumatic System test and calibration lab set up. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Flame scanner for flexible operation of 3X660MW Koradi TPS. | 0 | - | 0 | 35 | 35 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of Flame scanner for flexible operation of 3X660MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of DRC Pipes, Bends & Fittings in phase manner to improve the dry ash conveying & its disposal (2 years) | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of DRC Pipes, Bends & Fittings in phase manner to improve the dry ash conveying & its disposal (2 years) (Rs.30 Cr.) (Bottom ash/Coarse ash evacuation & Ash Slurry Disposal Pipelines, Dry ash conveying system) | 0 | - | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | Augmentation of Coarse Ash disposal system at U10 at KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | WORK OF INSTALLATION & COMMISSIONING OF ASH DISPOSAL SYSTEM AT UNIT#10 | 0 | - | 0 | 0 | 0 | 0 | 0 | 82.01 |  |  | 82.01 | -82.01
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 2.93 |  |  | 2.93 | -2.93
0 | DPR for Railway Track Siding Performance Improvement Schemes at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 1 : Work of complete track renovation of existing Rail yard of CHP, 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. Due to continuous movement of Railway's precious rolling stock, the track spares are worn out and are due for complete replacement. Hence, to maintain rail track parameters in healthy condition as per Railway norms so as to avoid untoward incidences of derailment the execution of work of complete track renewal is essential. | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 2 : Scheme Name- Work of laying of additional track at 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. However, as per the existing infrastructure, at present there is no dedicated empty formation line. Due to non-availability of empty formation line, most often unloading gets hampered due to blocking of outhaul line by empty rake. The hampering in unloading affects the plant performance and incurrs unnecessary financial burden on KTPS account under the head of demurrage charges. Hence, to maintain the plant loadability and availability, it is essential to lay additional track at 3x660MW, KTPS, Koradi. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 3 : Scheme Name- Work of rectification and upgradtion of existing SSP at CHP, 3x660MW, KTPS, Koradi. Justification- The SSP has been erected at 3x660MW, KTPS, Koradi. However, till date the same has not been commissioned. With lapse of @ 5-6 years after erection and its non commissioning, the existing SSP set up has been completely detoriorated. Now, Railway's is pressing hard for early commissioning of the same. The said set up shall ensure isolation of OHE of existing yard with Railway's main line. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 4 : Scheme Name- Work of construction of apron RCC platforms at inhaul and outhaul of Wagon tipllers 1, 2, 3 & 4 of CHP 3x660MW, KTPS, Koradi. Justification- The 04 Nos. of wagon tipplers are installed at CHP-3x660MW, KTPS, Koradi. In this regards, it is to submit that, the wagon unloading is being carried out through these tipplers. Hence, presence of fugitive dust in tippler area is predominant. The said dust is being accumulated at inhaul and outhaul of wagon tipplers. Due to presence of loaded wagons at inhaul and empty wagons at outhaul, this office gets least opportunity for clearance of the said coal dust along the track. Due to accumulation of coal dust, the rail track parameters along with gradient are getting distubed. The disturbance in gradient is causing rolling of wagons which is not recommended in view of safety of both man and machine. Besides, this due to rolling of wagons, the occurnece of untoward incidence of derailment is predominant. Hence, to maintain uniform rail track gradient it shall be enviable to construct the apron RCC platforms at inhaul and outhaul of Wagon tipplers 1, 2, 3 & 4 of CHP-3x660MW, KTPS, Koradi. Estimated cost- Rs. 4 Cr. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 5 : Scheme Name- Work of construction of apron RCC platforms at inhaul and outhaul of Wagon tipllers 1, 2, 3 & 4 of CHP 3x660MW, KTPS, Koradi. Justification- The 04 Nos. of wagon tipplers are installed at CHP-3x660MW, KTPS, Koradi. In this regards, it is to submit that, the wagon unloading is being carried out through these tipplers. Hence, presence of fugitive dust in tippler area is predominant. The said dust is being accumulated at inhaul and outhaul of wagon tipplers. Due to presence of loaded wagons at inhaul and empty wagons at outhaul, this office gets least opportunity for clearance of the said coal dust along the track. Due to accumulation of coal dust, the rail track parameters along with gradient are getting distubed. The disturbance in gradient is causing rolling of wagons which is not recommended in view of safety of both man and machine. Besides, this due to rolling of wagons, the occurnece of untoward incidence of derailment is predominant. Hence, to maintain uniform rail track gradient it shall be enviable to construct the apron RCC platforms at inhaul and outhaul of Wagon tipplers 1, 2, 3 & 4 of CHP-3x660MW, KTPS, Koradi. Estimated cost- Rs. 4 Cr. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 6 : Scheme Name- Work of construction of RCC platforms along the rail track of CHP 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. In this regards, it is to submit that, after unloading of rakes the empty rakes are being examined by Railway's C&W staff camped at KTPS, Koradi. Hence, for safe movement of Railway's staff, Railway's is pressing hard for provision of RCC platforms along the rail track of CHP-3x660MW, KTPS, Koradi. Estimated cost- Rs. 10 Cr. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 7 : Scheme Name- Work of repairing and construction of RCC permanent revenue canal at, KTPS, Koradi. Justification- The temporary revenue canal is being flowing beside the existing Railway exchange yard of 210 MW, KTPS, Koradi. The said canal gets clogged inview of ash accumulation. Due to clogging this canal overflows and its overrun enters the 210 MW rail yard thereby creating track surface marshy and unsafe for Rail movement. Hence, it is essential to repair and construct RCC permanent revenue canal at KTPS, Koradi so that proper and timely cleaning of canal along with proper outlet can be arranged. Estimated cost- Rs. 15 Cr. | 0 | - | 0 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme Name-08 Work of construction of RCCretaining wall at Godhani and Kalumna end of KTPS, Koradi. Justification- The separate rail infrastructure has been commissioned for Koradi TPS to cope up the daily coal requirement. The rail traffic at KTPS, Koradi is being catered through Godhani and Kalumna end respectively. In this regards, it is to submit that, the take off points at Godhani and Kalumna both are S&T operated. During monsoon, it is often witnessed that, the rain water enters the plant premises from others land thereby submerging the S&T operated point. Due to this, signals gets lost and hampers the Rail traffic movement completely. Hence, it is essential to restrict the entrance of rain water in plant premises. This can be possible by constructing retaining wall at required loaction. Estimated cost- Rs. 1 Cr. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme Name-09 OHE maintenance at CHP, KTPS, Koradi Justification-As per the Railway board circular, Railway's has mandated that OHE maintenance cost for existing as well as new sidings shall be borne by the siding owner in accordance with Railway guidelines. Railway will carry out necessary inspection of maintenance work once in six months. Maintenance charges per TKM per annum of OHE as finalized by SECR zonal office is Rs.291566/- per TKM per annum. Also, inspection charges at the rate of Rs.106974/- per day towards inspection to be carried out by Railways every si x months shall be charged on actual basis by Railway's from the sidings.Accordingly, Railway.s has calimed amount of Rs.31314519/- for two years. Hence for 5 yeards it is expected to be Rs.7.82 Cr. Estimated cost- Rs. 7.82 Cr. | 0 | - | 0 | 7.82 | 7.82 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 10 Name-Remodelling and upgradation of existing S & T system with Panel Interlocking system and associated S & T gears to S & T system with Electronic Interlocking system and associated S & T gears in connection with services for BG Railway facility (660 MW Rail yard) for Koradi Thermal Power Station of MSPGCL Justification-As per the prevailing Railway norms, it is mandatory to commission the S & T system in private Railway siding for fast and safe movement of Railway’s precious rolling stock. Unless and until remodeling is carried out the S&T system cannot be started at Koradi Railway yard.With commissioning and operation of S & T system there shall be least possibility for derailments during internal shunting through crossovers, as the said points shall be motorized operated. Estimated cost- Rs. 20 Cr. | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 11 : Work of supply and provision of lights and high mast at CHP Railway exchange yard of 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. In this regards, it is to submit that, after unloading of rakes the empty rakes are being examined by Railway's C&W staff camped at KTPS, Koradi on round the clock basis. Hence, for safe movement of Railway's staff, Railway's is pressing hard for availability of proper illumination in complete yard. Estimated cost- Rs.2.5 Cr. | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Provision of cover shed for stack yard -2 at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 1 : Provision of cover shed for stack yard -2 at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 135 | -135 | 0 | 0 |  |  | 0 | -135
0 | DPR for Procurement of Pipe Conveyor Drive System Internals at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 1 : Procurement of Pipe Conveyor Drive System Internals at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 27 | -27 | 0 | 0 |  |  | 0 | -27
0 | DPR for Provision of service building along with vehicle bay at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 1 : Provision of service building along with vehicle bay at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | GENERAL ASSET | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | GENERAL ASSET--AKRDFOGA01-OFFICE FURNITURE | N.A. | - | 0 | 0.57299 | 0.75759 | -0.1846 | 0 | 0 |  |  | 0 | -0.1846
2 | GENERAL ASSET--AKRDFOGA02-COMPUTERS,PRINTER,SCANNER | N.A. | - | 0 | 1.6504 | 2.911 | -1.2606 | 0 | 0 |  |  | 0 | -1.2606
3 | GENERAL ASSET--AKRDFOGA03-AC,WATER COOLER | N.A. | - | 0 | 0.46584 | 0.49898 | -0.033135 | 0 | 0 |  |  | 0 | -0.033135
4 | GENERAL ASSET--AKRDFOGA04-AIR PURIFIER | N.A. | - | 0 | 0 | 0.0105 | -0.0105 | 0 | 0 |  |  | 0 | -0.0105
0 | D) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of KLEP Unit for 'HCSD Pump | 0 | - | 3.73 | 3.73 | 3.73 | 0 | 0 | 0 |  |  | 0 | 0
2 | Restoration of Boiler Circulation Pump at 3X660MW KTPS, Koradi | 0 | - | 0 | 4.73 | 4.73 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of Coal Compartment Assemblies for Unit-10 at 3x660MW KTPS, Koradi. | 0 | - | 0 | 3.73 | 3.73 | 0 | 0 | 0 |  |  | 0 | 0
4 | Repairing and Refurbishment of TDBFP cartridge Model FK6E40 installed at 3X660MW KTPS, Koradi | 0 | - | 0 | 11.86 | 11.86 | 0 | 0 | 0 |  |  | 0 | 0
5 | Non-DPR for Upgradation of Honeywell Make PLC for Mill Reject Handling System installed at 3x660MW Balance of Plant (BOP) Unit- 8, 9 & 10 at Koradi TPS | 0 | - | 0 | 0.85 | 0.85 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of Sky Climber for furnace repairing at 3x660MW KTPS, Koradi | 0 | - | 0 | 3.02 | 3.02 | 0 | 0 | 0 |  |  | 0 | 0
7 | Double Roll Clinker Grinder | 0 | - | 0 | 1.68 | 1.68 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement along with Installation of Clear Water Booster Pump with Motor, Panel Cable and other allied accessories in Unit#10 bottom ash area at AHP, 3x660MW, KTPS, Koradi. | N.A. | - | 0 | 2.8112 | 2.56 | 0.25116 | 0 | 0 |  |  | 0 | 0.25116
9 | Procurement of single Roll Clinker Grinder with Feed Pump & Jet Pump Complete Assembly with modified metallurgy installed at AHP ,3x660MW Units, KTPs, Koradi | N.A. | - | 0 | 3.2868 | 2.12 | 1.1668 | 0 | 0 |  |  | 0 | 1.1668
10 | Work of Repairing and Refurbishment of HIP Rotor along with balancing and over speed trial for L&T-MHI make turbine (Type: TC4F-30”) installed at 3X660MW KTPS, Koradi | N.A. | - | 0 | 7.3532 | 7.13 | 0.22316 | 0 | 0 |  |  | 0 | 0.22316
11 | Procurement of spares for Flue gas distribution dampers, PA fan discharge dampers and Coal mill Hot PA Gate and Dampers at 3x660mw KTPS units through OEM | N.A. | - | 0 | 3.7 | 3.7 | 0 | 0 | 0 |  |  | 0 | 0
12 | Work of Modification & Installation of Take up trolley & arrangement for take up lifting for conveyor BCN-13A at CHP 3X660MW,KTPS,Koradi | N.A. | - | 0 | 356.6331 | 0.75 | 355.8831 | 0 | 0 |  |  | 0 | 355.8831
13 | Work of Design, Modification & streingthening of Tripper trolley structure with provision of Antiwear plates discharge chute box at CHP 3X660MW,KTPS,Koradi | N.A. | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
14 | Upgradation of Management Information System (MIS) Server and Associated Software for C&I at 3x660MW Unit- 8, 9 & 10 at Koradi TPS | N.A. | - | 0 | 2.145 | 2.145 | 0 | 0 | 0 |  |  | 0 | 0
15 | Procurement of Vibrating Tranfer chute with double exciter Drive for stacker reclaimer at CHP,3X660MW,KTPS ,Koradi | N.A. | - | 0 | 0.934 | 0.934 | 0 | 0 | 0 |  |  | 0 | 0
16 | Supply & Installation of Ash Slurry Density Transmitter at High Concentrated Slurry Disposal (HCSD) System of BOP area of 3x660MW Unit- 8, 9 & 10 at Koradi TPS | N.A. | - | 0 | 1.26 | 1.26 | 0 | 0 | 0 |  |  | 0 | 0
17 | Supply & Installation of Fiber Optic Sensing System for Conveyor Health Monitoring At CHP 3x660MW KTPS, Koradi | 0 | - | 0 | 11.72 | 11.72 | 0 | 0 | 0 |  |  | 0 | 0
18 | Procurement of Leak- proof make complete Mechanical Seal Assembly for Concrete Volute CW Pump installed at 3X660MW KTPS,Koradi on OEM bASIS. | 0 | - | 0 | 1.94 | 1.94 | 0 | 0 | 0 |  |  | 0 | 0
19 | Work of Design , Engineering , Manufacturing , Supply Erection & Commissioning of Conveyor Belt From Discharge of RBF 1 &2 at Crusher House to Stack Yard At CHP 3x660MW KTPS, Koradi . | 0 | - | 0 | 11.39 | 11.39 | 0 | 0 | 0 |  |  | 0 | 0
20 | Supply & Installation of Artificial Intelligence PMMS Accurex Diagnostic matrix based vibration & temperature monitoring for critical auxiliaries at CHP 3x660MW KTPS, Koradi. | 0 | - | 0 | 6.431 | 6.431 | 0 | 0 | 0 |  |  | 0 | 0
21 | Restoration of online dissolved gas analysers of Unit 8,9,10 | 0 | - | 0 | 1.11 | 1.11 | 0 | 0 | 0 |  |  | 0 | 0
22 | Complete Replacement of Existing Water Separator Drain Tank Control (WDC) Valves with New Valves of modified trim design along with hydraulic Actuators, Power Pack assembly, necessary instrumentation, erection & commissioning 3X660MW KTPS, Koradi. | 0 | - | 0 | 5.33 | 5.33 | 0 | 0 | 0 |  |  | 0 | 0
23 | Procurement of mandatory set of Hydraulic system internals for Wagon Tippler Drive & side arm charger Drive at CHP,3X660MW,KTPS ,Koradi | 0 | - | 0 | 6.35 | 6.35 | 0 | 0 | 0 |  |  | 0 | 0
24 | "Supply & installation of Anodized winding Oil cooled over band magnetic separator & control panel for conveyor 5A,5B &13C at CHP 3x660MW KTPS, Koradi. | 0 | - | 0 | 1.896 | 1.896 | 0 | 0 | 0 |  |  | 0 | 0
25 | Procurement of Grinding Wall Assembly for Impact Crusher At CHP 3x660MW KTPS, Koradi | 0 | - | 0 | 2.01 | 2.01 | 0 | 0 | 0 |  |  | 0 | 0
26 | Restoration of Boiler Circulation Pump of U10 at 3X660MW KTPS, Koradi | 0 | - | 0 | 6.69 | 6.69 | 0 | 0 | 0 |  |  | 0 | 0
27 | Design,Engineering,Customization,Implementation,Installation & testing of Data Analytical/Artificial Intellegence softwae for automated monitoring & diagnostics system to improve Power plant reliability & efficiency,at one unit of 3X660MW KTPS, Koradi. | 0 | - | 0 | 3.27 | 3.27 | 0 | 0 | 0 |  |  | 0 | 0
28 | Supply of Feed Gate Complete Assembly along with installation to enhance the performance of Feed Gate at Ash Handling Plant, 3x660MW, KTPS, Koradi. | 0 | - | 0 | 2.4 | 2.4 | 0 | 0 | 0 |  |  | 0 | 0
29 | Design, Supply, Installation & Commissioning of Instrument Air Dryer Assembly with Prefilters & Stainless steel piping along with valves suitable for Instrument Air Compressors at AHP, 3x660MW Units, KTPS, Koradi | 0 | - | 0 | 5.5 | 5.5 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 5722.2451 | 5594.8574 | 127.3877 | 569.56 | 654.5 | 0 | 0 | 654.5 | 42.4477
0 | FY 2028-29 | 0 |  | 0 | 0
0 | A) Approved Add cap: | 0 | - | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
A | BoP | 0 | - | 246.34 | 103.6804 | 232.6929 | -129.0125 | 0 | 0 |  |  | 0 | -129.0125
B | BTG | 0 | - | 44.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B1 | Supply | 0 | - | 13.33 | 0 | 13.33 | -13.33 | 0 | 0 |  |  | 0 | -13.33
B2 | Works | 0 | - | 0.98 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B3 | Taxes and duties | 0 | - | 23.29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B4 | Civil | 0 | - | 0.19 | 0.19 | 0 | 0.19 | 0 | 0 |  |  | 0 | 0.19
B5 | Mandatory Spares | 0 | - | 5.03 | 1.29 | 6.32 | -5.03 | 0 | 0 |  |  | 0 | -5.03
B6 | BTG (L&T) Work | 0 | - | 1.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C | Other Works (Plant) | 0 | - | 136.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C1 | Fully Integrated Security System | 0 | - | 27.36 | 31.4615 | 31.4615 | 0 | 0 | 0 |  |  | 0 | 0
C2 | Administrative Expenses and overhead | 0 | - | 7.25 | 6.69 | 0 | 6.69 | 0 | 0 |  |  | 0 | 6.69
C3 | Contingencies E&M | 0 | - | 0.04 | 0.04 | 0 | 0.04 | 0 | 0 |  |  | 0 | 0.04
C4 | Mobile storage racks, fork lifts, hoists & hydra for material handling in major stores shed | 0 | - | 0.95 | 0.93645 | 0.93645 | 0 | 0 | 0 |  |  | 0 | 0
C5 | Development of working models of Plant Layout, Boiler, Turbine- Generetaor, Coal mill, Fans, etc. at KTC, Koradi. | 0 | - | 1.2 | 1.2 | 0.98604 | 0.21396 | 0 | 0 |  |  | 0 | 0.21396
C6 | Workshop equipment | 0 | - | 0.26 | 0.26192 | 0.26192 | 0 | 0 | 0 |  |  | 0 | 0
C7 | Design, engg, manufacture, supply , erection, testing & commissioning of Ozonization Plant for circulating cooling water system | 0 | - | 54.05 | 31.7683 | 31.6144 | 0.15388 | 0 | 0 |  |  | 0 | 0.15388
C8 | Supply, installation & commissioning of water flow meters including required SCADA software and other accessories for water management system | 0 | - | 5.08 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C9 | Provision of wet ash evacuation system for first two rows of ESP for Unit-8,9 & 19 | 0 | - | 26.59 | 21.69 | 26.3181 | -4.6281 | 0 | 0 |  |  | 0 | -4.6281
C10 | Procurement of portable mercury analyser for flue gas monitoring | 0 | - | 6.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C11 | Administrative Expenses and overhead | 0 | - | 5 | 21.0001 | 0 | 21.0001 | 0 | 0 |  |  | 0 | 21.0001
C12 | Compressor of Hydrogen plant | 0 | - | 1.5 | 1.5 | 0 | 1.5 | 0 | 0 |  |  | 0 | 1.5
C13 | Rail Cum road stone grabbler | 0 | - | 0.85 | 0.85 | 0 | 0.85 | 0 | 0 |  |  | 0 | 0.85
D | Other Works (Civil) | 0 | - | 103.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D1 | Road, Bridges railway system | 0 | - | 20.1 | 0.10806 | 0 | 0.10806 | 0 | 0 |  |  | 0 | 0.10806
0 | S&T System with Panel Interlocking System | 0 | - | 0 | 10.4585 | 10.4596 | -0.0011606 | 0 | 0 |  |  | 0 | -0.0011606
D2 | Staff quarters | 0 | - | 5.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D3 | Other Misc & Unforseen Item | 0 | - | 25.79 | 9.3 | 7.53 | 1.77 | 0 | 0 |  |  | 0 | 1.77
0 | Check Post, Inspection Office & Facility Complex | 0 | - | 0 | 3.6844 | 3.6816 | 0.0028689 | 0 | 0 |  |  | 0 | 0.0028689
0 | CPRI Building | 0 | - | 0 | 6.2046 | 6.2046 | 0 | 0 | 0 |  |  | 0 | 0
0 | Foam cum DCP fire tender- 1 | 0 | - | 0 | 0 | 0.76926 | -0.76926 | 0 | 0 |  |  | 0 | -0.76926
0 | Fire water Bowser-cum-fire Tender- 1No. | 0 | - | 0 | 0.73537 | 0.73537 | 0 | 0 | 0 |  |  | 0 | 0
D4 | Const. facility | 0 | - | 3.28 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D5 | Contigency Other Civil Work | 0 | - | 5.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D6 | Adminstrative Exp. & Overhead (Salary & Overhead, Civil & E&M) | 0 | - | 21.47 | 31.64 | 0 | 31.64 | 0 | 0 |  |  | 0 | 31.64
D7 | Future unforseen works(Jalyukta Shiwar) | 0 | - | 0.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D8 | Landscaping work | 0 | - | 21.76 | 20.53 | 0 | 20.53 | 0 | 0 |  |  | 0 | 20.53
E | Initial Spares | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
E1 | Boiler & its auxilliaries | 0 | - | 14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Procurement of Table liners and Roller liners Of MVM 32R Coal Mills of 3 X 660MW Units at KTPS, Koradi | 0 | - | 0 | 10.0686 | 10.0686 | 0 | 0 | 0 |  |  | 0 | 0
ii | Procurement of couplings for Coal mill MVM 32 R of 3 X 660 MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 1.5944 | -1.5944 | 0 | 0 |  |  | 0 | -1.5944
iii | Procurement of Set of internal spares for Coal Mill Gear Box (KMP-450) for 3 X 660MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 2.2253 | -2.2253 | 0 | 0 |  |  | 0 | -2.2253
E2 | Turbine & its auxilliaries | 0 | - | 18.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | ULTRAFILTRATION MEMBRANE | 0 | - | 0 | 1.6511 | 1.6511 | 0 | 0 | 0 |  |  | 0 | 0
ii | Supply of Main turbine Vibration Monitoring System spares at 3x660MW, KTPS,Koradi. | 0 | - | 0 | 0 | 1.1469 | -1.1469 | 0 | 0 |  |  | 0 | -1.1469
iii | Procurement of Cartridge for Turbine Driven Boiler Feed Pump (Model No.: FK6E40) at 3X660 MW KTPS Koradi | 0 | - | 0 | 14.2864 | 14.2864 | 0 | 0 | 0 |  |  | 0 | 0
iv | Procurement of Critical Insurance Spares for L&T-MHI Make Turbine for attending major overhauling work of Turbine at KTPS, 3x660MW Units Koradi. | 0 | - | 0 | 11.1013 | 11.1013 | 0 | 0 | 0 |  |  | 0 | 0
E3 | Generator & its auxilliaries | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
E4 | Electrical auxilliaries | 0 | - | 1.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Procurement of HT Motors of BOP | 0 | - | 0 | 0 | 0.29335 | -0.29335 | 0 | 0 |  |  | 0 | -0.29335
ii | 0 | 0 | - | 0 | 0 | 0.84594 | -0.84594 | 0 | 0 |  |  | 0 | -0.84594
iii | Supply of Schneider make Differential Protection Relays for 3X660 MW, Koradi (OEM) | 0 | - | 0 | 0 | 0.10502 | -0.10502 | 0 | 0 |  |  | 0 | -0.10502
iv | Supply of Professional Large Format Display for display of DCS parameters PCR | 0 | - | 0 | 0.14885 | 0.14885 | 0 | 0 | 0 |  |  | 0 | 0
v | Procurement of ABT Energy meter with software for 3X660 MW, TPS, Koradi | 0 | - | 0 | 0 | 0.18337 | -0.18337 | 0 | 0 |  |  | 0 | -0.18337
E5 | Outdoor Plant i.e. CHP, AHP, WTP etc | 0 | - | 19.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Procurement of Forced Lubrication system for Premium make Gear box B3-450 installed for bunker conveyor BCN 7A/B at CHP 3X660MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0.15314 | -0.15314 | 0 | 0 |  |  | 0 | -0.15314
ii | Procurement of rotary spares for travel drive of Stacker and conveyor drive system in Coal Handling Plant of 3x660 MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0.35199 | -0.35199 | 0 | 0 |  |  | 0 | -0.35199
iii | Procurement of Complete assembly of Dome Valve ( 100NB, 200NB, 300NB) with power cylinder for dry Ash evacuation system of 3X660MW KTPS, Koradi. | 0 | - | 0 | 0.2225 | 0.2225 | 0 | 0 | 0 |  |  | 0 | 0
iv | Procurement of Modified Apron Pans for M/s. ELECON Engineering Company ltd make Apron Feeder in CHP 3x660MW Units at KTPS, Koradi. | 0 | - | 0 | 3.3233 | 3.3233 | 0 | 0 | 0 |  |  | 0 | 0
v | Procurement of Single Roll Clinker Grinder with Feed Sump and Jet Pump Complete Assembly with Drive, Driven Sprocket and Chain at AHP, 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.56357 | 0.56357 | 0 | 0 | 0 |  |  | 0 | 0
vi | Procurement of spares of Dome Valve (100NB, 200NB, 300NB) for Ash Evacuation System of 3X660MW Unit KTPS, Koradi. | 0 | - | 0 | 0.16431 | 0.16431 | 0 | 0 | 0 |  |  | 0 | 0
vii | 0 | 0 | - | 0 | 0.10064 | 0.10064 | 0 | 0 | 0 |  |  | 0 | 0
viii | 0 | 0 | - | 0 | 0.00708 | 0.00708 | 0 | 0 | 0 |  |  | 0 | 0
ix | Procurement of Hydraulic Motor for Apron feeder in Coal Handling Plant 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.7965 | 0.7965 | 0 | 0 | 0 |  |  | 0 | 0
x | Procurement of Peristaltic Hose Pump (Model no: RP2 – 40) Spares for HCSD System of Ash Handling Plant, 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.20622 | 0.20622 | 0 | 0 | 0 |  |  | 0 | 0
xi | Procurement of spares for HP Water Pump, Mather & Platt make, model 10/12 EME for AHP at 3X660 MW, KTPS, Koradi | 0 | - | 0 | 0.28246 | 0.28246 | 0 | 0 | 0 |  |  | 0 | 0
xii | Procurement of Rotor shaft assembly for M/s. ELECON Engineering Company ltd make Impact Crusher in CHP 3x660MW Units at KTPS, Koradi. | 0 | - | 0 | 0.76369 | 0.76369 | 0 | 0 | 0 |  |  | 0 | 0
xiii | Procurement of Sam Turbo Make Pumps Spare parts for Ash Handling Plant of 3X660 MW Units at KTPS, Koradi | 0 | - | 0 | 0.17166 | 0.17166 | 0 | 0 | 0 |  |  | 0 | 0
xiv | Procurement of Wagon Tippler Spares for M/s. ELECON Engineering Company ltd. make Wagon Tippler in CHP 3X660MW Units at KTPS, Koradi. | 0 | - | 0 | 1.3975 | 1.3975 | 0 | 0 | 0 |  |  | 0 | 0
xv | Procurement of Pneumatic Y Type Control Valve (Blow Valve Size 50mm & 80mm) for Fly Ash Evacuation System of 3X660MW Unit KTPS, Koradi. | 0 | - | 0 | 0.029205 | 0.029205 | 0 | 0 | 0 |  |  | 0 | 0
xvi | Procurement of the various spares required for Warman make Ash Slurry Pump Model 10/8 EEM & Over Flow Pump Model 8/6 EXU installed at AHP, 3X660 MW TPS Koradi through Limited Tender. | 0 | - | 0 | 0.20886 | 0.20886 | 0 | 0 | 0 |  |  | 0 | 0
xvii | 0 | 0 | - | 0 | 0.0076261 | 0.032797 | -0.025171 | 0 | 0 |  |  | 0 | -0.025171
xviii | Procurement of Spares of Single Roll Clinker Grinder Ayems Engineers make, Model AE-1005-89-100 at AHP, 3X660 MW Koradi TPS. | 0 | - | 0 | 0.82826 | 0.82826 | 0 | 0 | 0 |  |  | 0 | 0
xix | Procurement of Hydraulic Motor for Bucket Wheel of Stacker Reclaimer in CHP, 3X660MW, KTPS, Koradi. | 0 | - | 0 | 1.1168 | 1.1168 | 0 | 0 | 0 |  |  | 0 | 0
xx | Procurement of Rotors, Maintenance Kits, Couplings and other spares required for Atlas Copco make Instrument Air Compressor of Ash Handling Plant of 3 X 660 MW Units at KTPS, Koradi. | 0 | - | 0 | 1.1828 | 1.1828 | 0 | 0 | 0 |  |  | 0 | 0
xxi | Procurement of spares of intermediate conveyor | 0 | - | 0 | 0 | 0.3186 | -0.3186 | 0 | 0 |  |  | 0 | -0.3186
xxii | Procurement of Hydraulic motor for wagon tippler drive in CHP, 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.46494 | 0.46494 | 0 | 0 | 0 |  |  | 0 | 0
xxiii | Procurement of GEHO Pump (Model No. TZPM 400) Spares of Ash Handling Plant, 3 X 660 MW Units, KTPS, Koradi. | 0 | - | 0 | 0 | 0.83656 | -0.83656 | 0 | 0 |  |  | 0 | -0.83656
xxiv | Procurement of Beater Arms for Impact crushers installed at in Coal Handling Plant of 3x660 MW at KTPS, Koradi. | 0 | - | 0 | 0 | 1.0093 | -1.0093 | 0 | 0 |  |  | 0 | -1.0093
xxv | Supply of Atlas Copco make compressor spares for at Koradi TPS 660MW | 0 | - | 0 | 0 | 0.39813 | -0.39813 | 0 | 0 |  |  | 0 | -0.39813
xxvi | Procurement of spares for side arm charger, wagon tippler, impact crushers and stacker reclaimer at CHP 3x660 MW KTPS | 0 | - | 0 | 0.010573 | 0.43684 | -0.42626 | 0 | 0 |  |  | 0 | -0.42626
xxvii | Procurement of Beater heads with Pin for Impact crushers installed at in Coal Handling Plant of 3x660 MW at KTPS, Koradi. | 0 | - | 0 | 0 | 1.1256 | -1.1256 | 0 | 0 |  |  | 0 | -1.1256
xxviii | Procurement of spares of Hyd Motor of SAC | 0 | - | 0 | 0 | 0.36029 | -0.36029 | 0 | 0 |  |  | 0 | -0.36029
xxix | Procurement of hydraulic power packs for Flap Gates in CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0.1888 | -0.1888 | 0 | 0 |  |  | 0 | -0.1888
xxx | Procurement of Mobile Grilling Equipment for CHP 3x660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0.33866 | -0.33866 | 0 | 0 |  |  | 0 | -0.33866
xxxi | Procurement of Weld overlay Flap Gate assembly in CHP 3x660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0.5841 | -0.5841 | 0 | 0 |  |  | 0 | -0.5841
E6 | Capital Spares | 0 | - | 89.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of critical insurance spares for Turbine & its critical auxiliaries for 3 x 660 MW, Koradi (4370001538 dtd. 18/06/2018 d.p. 21 Months) | 0 | - | 89.62 | 89.6234 | 88.736 | 0.88736 | 0 | 0 |  |  | 0 | 0.88736
E7 | Additional Capitalization | 0 | - | 57.88 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Contruction of various infrastructure such as roads etc and public amenities in the rehabilitated villages of koradi and khasara | 0 | - | 13.1 | 12.74 | 0 | 12.74 | 0 | 0 |  |  | 0 | 12.74
ii | Procurement of 7 nos of school buses | 0 | - | 2 | 1.3109 | 1.3109 | 0 | 0 | 0 |  |  | 0 | 0
iii | Development of green belt & fodder farm for fulfillment of environmental clearance of MoEF for Koradi 3x660MW | 0 | - | 3.16 | 3.16 | 0 | 3.16 | 0 | 0 |  |  | 0 | 3.16
iv | Provision of Ground Hopper & Short Conveyor Belt from Existing Stackyard 1 & 2 ti existing Main Stream i.e. BCN 4A/4B of CHP 3x660 MW, KTPS, Koradi | 0 | - | 4.36 | 4.3555 | 4.3555 | 0 | 0 | 0 |  |  | 0 | 0
v | Provision of Ground Hopper & Conveyor Belt for Conveying Unloaded Coal form Open Wagon Tippler in CHP of Koradi Unit 8, 9 & 10. | 0 | - | 4.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
vi | Provision of Additional Facility for Manual Unloading Track in CHP of Koradi Unit No. 8, 9 & 10 | 0 | - | 5.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
vii | Construction of drains | 0 | - | 4.31 | 2.7927 | 0 | 2.7927 | 0 | 0 |  |  | 0 | 2.7927
viii | Supply erection commissioning of medium voltage variable frequency drive for conveyors BCN 6A,6B,7A,7B in CHP 3x660MW | 0 | - | 17 | 16.9859 | 16.9859 | 0 | 0 | 0 |  |  | 0 | 0
ix | Supply, Installation & commissioning of 3D level sensors for first two ESP field hoppers | 0 | - | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
F | Koradi TPS 3x660 MW Expansion Project – Construction of 2nd raising of existing Khasara Ash Bund from T.B.L. 308.50 M to T.B.L 312.00 M with construction of concrete dam (Broad crest weir structure), approach to drain wells and raising height of drain well No. 1, 2 & 3, construction of ash Compartment, cleaning of Khasara bund Nallah and construction of peripheral roads connecting to nearby villages for Khasara ash bund at TPS Koradi | 0 | - | 86.914 | 88.683 | 93.291 | -4.608 | 0 | 0 |  |  | 0 | -4.608
G | Discharge of UDL | 0 | - | 0 | 111.97 | 111.48 | 0.49 | 0 | 0 |  |  | 0 | 0.49
H | Asset Addition due to change in classification of inventory | 0 | - | 0 | 21.7503 | 0 | 21.7503 | 0 | 0 |  |  | 0 | 21.7503
I | Medical Oxygen Gr&Cyl Ozonization Plant (Covid Related Work) | 0 | - | 0 | 11.4034 | 9.6702 | 1.7332 | 0 | 0 |  |  | 0 | 1.7332
0 | B) DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (i) Submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Flue Gas Desulphurization FGD is for Unit 8, 9, 10 of 3x660MW Koradi TPS | MERC/CAPEX/FY 2020-21/WFH/SBR/05 | 2020-05-31 | 940 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Flue Gas Desulphurization is for Unit 8, 9, 10 of 3x660MW Koradi TPS | MERC/CAPEX/FY 2020-21/WFH/SBR/05 | 2020-05-31 | 847.78 | 1556.15 | 1556.15 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/FY 2020-21/WFH/SBR/05 | 2020-05-31 | 92.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13 | Construction of new admin building at Vidyut Bhavan, Katol Road, Nagpur | MERC/Capex/2021-2022/MSPGCL/063 | 2022-02-18 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13.1 | Construction of new admin building at Vidyut Bhavan, Katol Road, Nagpur | 0 | 2022-02-18 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | 2022-02-18 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Improvement in Regenerative Air Pre-heater Performance at Unit # 9 of 3x660 MW, Koradi TPS | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 15.869 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Procurement of heating elements for RAPH installed in Unit 9 (660MW) at KTPS Koradi THROUGH LIMITED TENDER | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 15.33 | 11.8 | 11.8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.2 | Replacement of heating elements for RAPH installed in Unit 9 (660MW) at KTPS Koradi | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 0.349 | 0.37 | 0.37 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 0.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | CHP Improvement (7 Nos) Schemes & Procurement of Bulldozers, Wheel Loaders and Hydraulic Cranes at CHP 3X660MW, KTPS, Koradi | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 38.87 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Sch-1: Revamping of Apron Feeder in CHP at 3X660MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.68 | 4.68 | 4.68 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Sch-2: Procurement of Hydraulic motors and pumps in CHP at 3X660 MW, KTPS, Koradi | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.44 | 4.44 | 4.44 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.3 | Sch-3: Capacity enhancement of Hydraulic motor of Apron Feeder in CHP, 3X660 MW, KTPS, Koradi | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 2.01 | 2.01 | 2.01 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.4 | Sch-4: Modification, supply and replacement of Transfer chutes in CHP 3x660MW KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.39 | 4.39 | 4.39 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.5 | Sch-5: Design, supply, installation & commissioning of High performance IGUS energy chain system with chain flex cable for Tripper trolleys at CHP at 3x660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.37 | 4.37 | 4.37 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.6 | Sch-6: Procurement of B3-630 gear box for BCN 6 A/B in CHP at 3x660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 0.57 | 0.57 | 0.57 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.7 | Sch-7: Supply and installation of Belt tear detector system for conveyor belt in CHP 3x660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 1.18 | 1.18 | 1.18 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.8 | Sch-8: Procurement of 5 Nos of Bulldozers BD 155 at CHP 3X660 MW Koradi Thermal Power station. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 12.83 | 12.83 | 12.83 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.9 | Sch-9:- Procurement of 02 nos. of Wheel loaders at CHP 3X660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 3.07 | 3.07 | 3.07 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Sch-10:- Procurement of 15 Ton & 20 Ton capacity hydraulic Cranes at CHP 3X660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 0.69 | 0.69 | 0.69 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 0.64 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Construction of bridge cum bandhara across Pond No. 3 and allied works at Pond No. 3 at Koradi TPS | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 33.116 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Construction of cement concrete bridge cum bandhara alongwith gated arrangement. | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 14.75 | 14.75 | 14.75 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.2 | Construction of earthen embankment connecting bridge cum bandhara on both side of embankment by excavating soil / typha / silt from Pond No.3 & tree plantation. | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 14.3252 | 14.3252 | 14.3252 | 0 | 0 | 0 |  |  | 0 | 0
20.3 | Providing structural steel pathway on the existing waste weir (west side of the Pond No.3) and roads connecting to bridge behind Pond No.3 and bridge cum bandhara. | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 2.4308 | 2.4308 | 2.4308 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 1.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement & replacement of Superheater Pass Economizer Coils (Modified Design) for Unit 8, 9 & 10 at 3x660MW KTPS, Koradi | Not Approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Procurement & replacement of Superheater Pass Economizer Coils (Modified Design) for Unit 8, 9 & 10 at 3x660MW KTPS, Koradi | Not Approved | - | 0 | 144.42 | 144.42 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Not Approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Improvement in Boiler Performance at U-8,9 & 10 KTPS, Koradi | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 62.929 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Scheme-1: Procurement of Blade Sets for ID, FD & PA Fans at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 11.34 | 11.34 | 11.34 | 0 | 0 | 0 |  |  | 0 | 0
7.2 | Scheme-2: Procurement of RAPH Bottom Support Bearing Assembly at 3X660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 2.478 | 2.478 | 2.478 | 0 | 0 | 0 |  |  | 0 | 0
7.3 | Scheme-3: Procurement of RAPH Top Guide Bearing Assembly at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 0.684 | 0.684 | 0.684 | 0 | 0 | 0 |  |  | 0 | 0
7.4 | Scheme-4: Procurement of RAPH Gear Box at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 3.44 | 3.44 | 3.44 | 0 | 0 | 0 |  |  | 0 | 0
7.5 | Scheme-5: Procurement of RAPH Spares at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 1.13 | 1.13 | 1.13 | 0 | 0 | 0 |  |  | 0 | 0
7.6 | Scheme-6: Procurement of Coal Burner Assembly with windbox air nozzles for Unit 8 & 9 at 3x660MW. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 15.407 | 15.407 | 15.407 | 0 | 0 | 0 |  |  | 0 | 0
7.7 | Scheme-7: Procurement of Boiler Circulation Pump (BCP) with Impeller & Diffuser at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 11.12 | 11.12 | 11.12 | 0 | 0 | 0 |  |  | 0 | 0
7.8 | Scheme-8: Procurement and Replacement of Heating Elements for RAPH Installed for Unit 8 at 3x660MW. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 15.96 | 15.96 | 15.96 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 1.37 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Design, Engineering, Supply, Installation, Testing, Commissioning including all civil works for Natural resource treatment and Laboratory equipment with mandatory spares at Koradi TPS, 3 X 660 MW | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 49.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.1 | Supply of Natural resource treatment and lab equipment for Water, Coal, Oil, Meteorology with supporting AI computing, all auxiliaries, and accessories. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 35.28 | 42.5744 | 42.5744 | 0 | 0 | 0 |  |  | 0 | 0
23.2 | Supply of Mandatory spares on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.8 | 0.944 | 0.944 | 0 | 0 | 0 |  |  | 0 | 0
23.3 | Supply of Tools and Tackles on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.15 | 0.177 | 0.177 | 0 | 0 | 0 |  |  | 0 | 0
23.4 | Complete Civil Work with 10 KLD ETP/ STP on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 3.6 | 4.25 | 4.25 | 0 | 0 | 0 |  |  | 0 | 0
23.5 | Services - Charges of Inland transport of plant and equipment on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.2 | 0.236 | 0.236 | 0 | 0 | 0 |  |  | 0 | 0
23.6 | Charges for Testing, Commissioning and PG Test of plant and equipment. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.05 | 0.059 | 0.059 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Improvement in Regenerative Air Preheater Performance & Complete Replacement of NDCT fills at Unit # 10, Koradi TPS | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 25.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.1 | Procurement of heating elements for RAPH installed in Unit 10 (660MW) at KTPS Koradi through OEM | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 12.23 | 14.521 | 14.521 | 0 | 0 | 0 |  |  | 0 | 0
24.2 | Complete Supply & Replacement of NDCT fills of U#10. | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 13 | 13 | 13 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 0.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 14 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 14.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 10.994 | 10.994 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 15 | HMI (Human Machine Interface) Upgradation of ‘SSPA-T3000’ DCS (Distribution Control System), Rockwell make PLC System installed at 3x660MW Unit No. 8, 9 & 10 at Koradi TPS and HMI (Human Machine Interface) Upgradation of MaxDNA DCS System at Unit 8-9, CSTPS, Chandrapur | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 55.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 15.1 | Supply: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 10.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 15.2 | Works: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | HMI (Human Machine Interface) Upgradation of ‘SPPA-T3000’ DCS (Distributed Control System) installed at 3x660MW Unit- 8, 9 & 10 at Koradi TPS to match with the external aspects and process improvement | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 24.33 | 24.33 | 24.33 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Upgradation of Rockwell Make PLC System installed at 3x660MW ,Koradi TPS to match with the external aspects and process improvement.(C&I) | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 20.2 | 20.2 | 20.2 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Work of provision of platform beside railway siding at backside of chord cabin for loading of fly ash in railway wagon for ash utilization at 3x660 MW TPS, Koradi | 0 | - | 0 | 0.0038356 | 0.0038356 | 0 | 0 | 0 |  |  | 0 | 0
13 | Capital Exenditure schemes for in-principle clearance regarding "EPC contract for the wok of construction of quarters and development of KTPS colony at Koradi" under CAPEX scheme | MERC/CAPEX/MSPGCL/2024-12/0569 DTD.13.09.2024 | 2024-09-13 | 210.48 | 210.48 | 210.48 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of spares for L&T-MHI make Turbine for COH work of Turbine at KTPS, 3x660MW units Koradi | MERC/CAPEX/MSPGCL/2023-24/0639 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement of spares for L&T-MHI make Turbine for COH work of Turbine at KTPS, 3x660MW units Koradi | MERC/CAPEX/MSPGCL/2023-24/0639 | - | 0 | 31.6358 | 31.6358 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Procurement of HP Nozzle assembly for L&T-MHI Make Turbine installed at 3x660MW Units Koradi | MERC/CAPEX/MSPGCL/2023-24/0639 | - | 0 | 4.189 | 4.189 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | C) DPRs Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Control & instrumentation related Various Upgradation schemes viz.Emission Monitoring & Water Quality Analysers ,Vibration Monitoring Schemes,Water Flow Monitoring etc. at 3X660MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Upgradation of Emission Monitoring Analysers | 0 | - | 0 | 9.58 | 9.58 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Upgradation of Water Quality Analysers | 0 | - | 0 | 5.33 | 5.33 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Revamping & Supply Of Upgraded VM7B Version of Vibration Monitoring Rack | 0 | - | 0 | 4.84 | 4.84 | 0 | 0 | 0 |  |  | 0 | 0
2.4 | Implementation of ‘Flow Monitoring System’ at 3x660MW Balance of Plant (BOP) Unit- 8, 9 & 10 at Koradi TPS | 0 | - | 0 | 6.87 | 6.87 | 0 | 0 | 0 |  |  | 0 | 0
3 | CHP Improvement Scheme-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Supply, Erection, Commissioning of set of Internals for Wagon Tipplers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 10.96 | 10.96 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Supply, Erection, Commissioning of set of Internals for Side Arm Chargers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 3.54 | 3.54 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Supply, Erection, Commissioning of set of Internals for Wobbler Feeders at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 4.96 | 4.96 | 0 | 0 | 0 |  |  | 0 | 0
3.4 | Supply, Erection, Commissioning of set of Internals for Apron Feeders at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 15.55 | 15.55 | 0 | 0 | 0 |  |  | 0 | 0
3.5 | Supply, Erection, Commissioning of set of Internals for Impact Crushers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 9.63 | 9.63 | 0 | 0 | 0 |  |  | 0 | 0
3.6 | Supply, Erection, Commissioning of set of Internals for Stacker cum Reclaimers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 6.26 | 6.26 | 0 | 0 | 0 |  |  | 0 | 0
4 | Performance improvement and availability of various Auxiliaries of TG at 3x660MW KTPS Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Performance improvement and availability of various Auxiliaries for Oil Systems of Main Turbine. | 0 | - | 0 | 3.26 | 3.26 | 0 | 0 | 0 |  |  | 0 | 0
4.2 | Performance improvement and availability of various Auxiliaries of Generator System. | 0 | - | 0 | 7.31 | 7.31 | 0 | 0 | 0 |  |  | 0 | 0
4.3 | Performance improvement and availability of Feed Water System. | 0 | - | 0 | 10.54 | 10.54 | 0 | 0 | 0 |  |  | 0 | 0
4.4 | Performance improvement and availability of Vacuum System. | 0 | - | 0 | 2.28 | 2.28 | 0 | 0 | 0 |  |  | 0 | 0
4.5 | Performance improvement and availability of CEP System. | 0 | - | 0 | 7.83 | 7.83 | 0 | 0 | 0 |  |  | 0 | 0
4.6 | Procurement of Complete Pull out Assembly along with Impeller and wear ring of Cooling Water Pump. | 0 | - | 0 | 14.87 | 14.87 | 0 | 0 | 0 |  |  | 0 | 0
4.7 | Procurement of complete assembly of HP and LP Elements for Atlas Copco make Compressors. | 0 | - | 0 | 4.19 | 4.19 | 0 | 0 | 0 |  |  | 0 | 0
5 | Improvement in Wet ash evacuation system at 3x660MW Units, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Procurement & installation of Ash Slurry Series Pump Assembly with modified metallurgy and Critical Wet End Sub Assembly to enhance the performance & slurry disposal capacity. | 0 | - | 0 | 7.53 | 7.53 | 0 | 0 | 0 |  |  | 0 | 0
5.2 | Procurement & installation of Ash Slurry Series Pump Assembly with modified metallurgy along with Gear Box, Fluid Coupling & Motor (4’th Series) and Critical Wet End Sub Assembly to enhance the performance & slurry disposal capacity. | 0 | - | 0 | 2.51 | 2.51 | 0 | 0 | 0 |  |  | 0 | 0
5.3 | Procurement & installation of Overflow Transfer Pump Assembly with upgradation in metallurgy and Critical Wet End Sub Assembly to enhance the performance. | 0 | - | 0 | 3.59 | 3.59 | 0 | 0 | 0 |  |  | 0 | 0
5.4 | Procurement & installation of IAC Compressor Assembly: Model –ZR110 STD 7.5 IMD Atlas Copco Make Oil free water cooled screw air compressor with inbuilt atlas copco make heat of compression single drum rotator air dryer to enhance the performance. | 0 | - | 0 | 7.56 | 7.56 | 0 | 0 | 0 |  |  | 0 | 0
6 | HMI Upgradation of Diasys Netmation DCS at 3x660MW KTPS Koradi Units 8,9 & 9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | HMI Upgradation of Diasys Netmation DCS at 3x660MW KTPS Koradi Units 8,9 & 10 | 0 | - | 0 | 77.15 | 77.15 | 0 | 0 | 0 |  |  | 0 | 0
7 | Improvement in Dry ash evacuation system at 3x660MW Units, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Procurement of Ingersoll Rand Make Transport Air Compressors Critical/Non-Critical Spares sub-assembly for performance improvement. | 0 | - | 0 | 29.57 | 29.57 | 0 | 0 | 0 |  |  | 0 | 0
8 | MSERW Pipes for Garlanding arrangement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.1 | Work of Garlanding arrangement to changeover ash slurry feed points for even filling of pond by providing MSERW Pipes along the periphery of Ash Bund Dyke Wall at Khasara Ash Bund. | 0 | - | 0 | 98.83 | 98.83 | 0 | 0 | 0 |  |  | 0 | 0
9 | Capacity Enhancement & Performance optimization at WTP 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.1 | Capacity enhancement of DM water stream in WTP at 3X660MW, KTPS, Koradi. | 0 | - | 0 | 58.94 | 58.94 | 0 | 0 | 0 |  |  | 0 | 0
9.2 | Capacity enhancement Condensate polishing unit regeneration area in WTP at 3X660 MW, KTPS, Koradi | 0 | - | 0 | 13.41 | 13.41 | 0 | 0 | 0 |  |  | 0 | 0
9.3 | Provision of Ozone generating plant of 1.0 Kg capacity in WTP at 3X660 MW, KTPS, Koradi | 0 | - | 0 | 5.84 | 5.84 | 0 | 0 | 0 |  |  | 0 | 0
10 | DPR for Construction of CC Road alongwith RCC Drain, CC platform for heavy machinery movement at 3x660 MW, TPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.1 | DPR for Construction of CC Road alongwith RCC Drain, CC platform for heavy machinery movement at 3x660 MW, TPS, Koradi | 0 | - | 0 | 33.57 | 33.57 | 0 | 0 | 0 |  |  | 0 | 0
11 | Improvement in Coal Mill Performance-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.1 | Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi through OEM. | 0 | - | 0 | 6.15 | 6.15 | 0 | 0 | 0 |  |  | 0 | 0
11.2 | Procurement of Mill Rotary Separator Blades for coal mill MVM 32R at 3x660 MW, KTPS, Koradi through open tender | 0 | - | 0 | 4.01 | 4.01 | 0 | 0 | 0 |  |  | 0 | 0
11.3 | Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi through OEM. | 0 | - | 0 | 14.57 | 14.57 | 0 | 0 | 0 |  |  | 0 | 0
11.4 | Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi through OEM | 0 | - | 0 | 6.14 | 6.14 | 0 | 0 | 0 |  |  | 0 | 0
12 | Improvement in Boiler performance-II at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.1 | Scheme1:Procurement of Coal compartment assembly for Unit8 at 3x660MW KTPS, Koradi | 0 | - | 0 | 12.7 | 12.7 | 0 | 0 | 0 |  |  | 0 | 0
12.2 | Scheme2:Procurement of blade sets for ID, FD & PA Fan at 3x660 MW, Units at KTPS Koradi through OEM. | 0 | - | 0 | 11.34 | 11.34 | 0 | 0 | 0 |  |  | 0 | 0
12.3 | Scheme3:Procurement of RAPH internal Spares for 3X660MW units at KTPS Koradi through OEM (Qty- 6 Sets) | 0 | - | 0 | 1.13 | 1.13 | 0 | 0 | 0 |  |  | 0 | 0
12.4 | Scheme4:Procurement of RAPH Sector plate with Actuating mechanism assembly for Unit9 3 X 660MW Units at KTPS, Koradi. | 0 | - | 0 | 7.2 | 7.2 | 0 | 0 | 0 |  |  | 0 | 0
13 | Improvement in Coal Mill performance-II at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | Procurement of FLENDER make Gearbox model kmp-450 along with motor for coal mill MVM32R at 3x660mw KTPS, koradi through OEM. | 0 | - | 0 | 20.91 | 20.91 | 0 | 0 | 0 |  |  | 0 | 0
13.2 | Procurement of complete set of couplings for PA, ID & FD fans at 3X660MW units at KTPS Koradi through OEM | 0 | - | 0 | 5.14 | 5.14 | 0 | 0 | 0 |  |  | 0 | 0
14 | Improvement in Coal Mill performance-III at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 6.15 | 6.15 | 0 | 0 | 0 |  |  | 0 | 0
14.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 14.57 | 14.57 | 0 | 0 | 0 |  |  | 0 | 0
14.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 6.14 | 6.14 | 0 | 0 | 0 |  |  | 0 | 0
14.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit10 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
14.5 | Scheme5:Procurement of Complete MRHS System along with Pneumatic Compressors at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
15 | Improvement in Boiler performance-III at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | Scheme1:Procurement of Coal compartment assembly for Unit8at 3x660MW KTPS, Koradi | 0 | - | 0 | 12.7 | 12.7 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Scheme2:Procurement of blade sets for ID, FD & PA Fan at 3x660 MW, Units at KTPS Koradi through OEM. | 0 | - | 0 | 11.34 | 11.34 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Scheme3:Procurement and replacement of heating elements for RAPH installed in Unit 9 (660MW) at KTPS Koradi THROUGH OEM/OES (Qty- 2 Sets) | 0 | - | 0 | 16 | 16 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Scheme4:Procurement of HP valves, safety valves and ERV's for 3X660MW units at KTPS Koradi through OEM | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
15.5 | Scheme5:Procurement of RAPH Sector plate with Actuating mechanism assembly for Unit8 3 X 660MW Units at KTPS, Koradi. | 0 | - | 0 | 7.2 | 7.2 | 0 | 0 | 0 |  |  | 0 | 0
15 | Improvement in Coal Mill performance-IV at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 6.15 | 6.15 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 14.57 | 14.57 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 6.14 | 6.14 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit8 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
16 | Improvement in Coal Mill performance-V at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 6.15 | 6.15 | 0 | 0 | 0 |  |  | 0 | 0
16.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 14.57 | 14.57 | 0 | 0 | 0 |  |  | 0 | 0
16.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 6.14 | 6.14 | 0 | 0 | 0 |  |  | 0 | 0
16.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit9 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
17 | Improvement in Boiler performance-IV at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.1 | Scheme1:Procurement of Coal compartment assembly for Unit8 at 3x660MW KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 12.7 | 12.7 |  |  | 12.7 | 0
17.2 | Scheme2:Procurement of blade sets for ID, FD & PA Fan at 3x660 MW, Units at KTPS Koradi through OEM. | 0 | - | 0 | 0 | 0 | 0 | 11.34 | 11.34 |  |  | 11.34 | 0
17.3 | Scheme3:Procurement of RAPH bottom support bearing assembly for 3X660MW units at KTPS Koradi through OEM (Qty- 2 Sets) | 0 | - | 0 | 0 | 0 | 0 | 2.47 | 2.47 |  |  | 2.47 | 0
17.4 | Scheme4:Procurement of RAPH top guide bearing assembly for 3X660MW units at KTPS Koradi | 0 | - | 0 | 0 | 0 | 0 | 0.684 | 0.684 |  |  | 0.684 | 0
17.5 | Scheme5:Procurement of RAPH Gear Box for 3X660MW units at KTPS Koradi through OEM (Qty- 1 Sets) | 0 | - | 0 | 0 | 0 | 0 | 3.44 | 3.44 |  |  | 3.44 | 0
17.6 | Scheme6:Procurement of RAPH Sector plate with Actuating mechanism assembly for Unit10 at 3 X 660MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 7.2 | 7.2 |  |  | 7.2 | 0
17.7 | Scheme7:Procurement and replacement of heating elements for RAPH installed in Unit 10 (660MW) at KTPS Koradi THROUGH OEM/OES (Qty- 2 Sets) | 0 | - | 0 | 0 | 0 | 0 | 16 | 16 |  |  | 16 | 0
17.8 | Scheme8:Procurement of Boiler Circulating Pump (1 Nos) | 0 | - | 0 | 0 | 0 | 0 | 11.12 | 11.12 |  |  | 11.12 | 0
18 | Improvement in Coal Mill performance-VI at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit9 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.3 | Reliability Improvement schemes of generators at 3X660MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | Scheme No. 1 :PROCUREMENT OF MELCO/LMTG MAKE GENERATOR ROTOR ASSEMBLY with excitation transformer AT 3X660MW KTPS, KORADI THROUGH OEM | 0 | - | 0 | 45.39 | 45.39 | 0 | 0 | 0 |  |  | 0 | 0
19.2 | Scheme No. 2:PROCUREMENT OF ONE COMPLETE SET OF GENERATOR STATOR COILS FOR GENERATOR AT 3X660MW UNITS AT KTPS KORADI THROUGH OEM | 0 | - | 0 | 35.4 | 35.4 | 0 | 0 | 0 |  |  | 0 | 0
25 | DPR on Procurement of Critical Speares for L&T make Main Turbine(typeTC4F-30) installed at 3x660MW KTPS Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.1 | Scheme No. 1 :Procurement of Critical Speares for L&T make Main Turbine(typeTC4F-30) installed at 3x660MW KTPS Koradi. | 0 | - | 0 | 126.41 | 126.41 | 0 | 0 | 0 |  |  | 0 | 0
26 | DPR for Coal Handling Plant Performance Improvement Schemes -II at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.1 | Scheme No. 1 : Performance Improvement of Unloading System Wagon Tipplers at CHP 3x660MW KTPS Koradi | 0 | - | 0 | 5.8 | 5.8 | 0 | 0 | 0 |  |  | 0 | 0
26.2 | Scheme No. 2 : Performance Improvement of Unloading System Side Arm Chargers at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Side Arm Charger Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 2.8 | 2.8 | 0 | 0 | 0 |  |  | 0 | 0
26.3 | Scheme No. 3 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 3.2 | 3.2 | 0 | 0 | 0 |  |  | 0 | 0
26.4 | Scheme No. 4 : Performance Improvement of Stacking & Reclaiming System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Stacking & Reclaiming System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 6.5 | 6.5 | 0 | 0 | 0 |  |  | 0 | 0
26.5 | Scheme No. 5 : Performance Improvement of Crushing System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Impact Crusher & Wobbler Feeders Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 8.5 | 8.5 | 0 | 0 | 0 |  |  | 0 | 0
26.6 | Scheme No. 6 : Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -1 at CHP 3x660MW KTPS Koradi A) Brief scope of work: Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -1 at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
27 | DPR for Coal Handling Plant Performance Improvement Schemes -III at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.1 | Scheme No. 1 : Performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Hydraulic system for Wagon Tippler, Side Arm Charger , Apron Feeder ( 1 & 2) Stacker Reclaimer 1 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 10.5 | 10.5 | 0 | 0 | 0 |  |  | 0 | 0
27.2 | Scheme No. 2 : Construction of Air tight Hydraulic power pack room along with necessary cooling system for performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Construction of Air tight Hydraulic power pack room along with necessary cooling system for Wagon Tippler & Apron Feeder ( 1 to 4) Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 3.2 | 3.2 | 0 | 0 | 0 |  |  | 0 | 0
27.3 | Scheme No. 3 : Performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory Hydraulic Power Cylinders of Wagon Tippler, Side Arm Charger ( 1 to 4) Stacker Reclaimer 1 & 2 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
27.4 | Scheme No. 4 : Performance Improvement of Stacker Reclaimer by providing Hydraulic Drive to Boom Conveyor at CHP 3x660MW KTPS Koradi A) Brief scope of work: Hydraulic Drive to Boom Conveyor Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.9 | 0.9 | 0 | 0 | 0 |  |  | 0 | 0
27.5 | Scheme No. 5 : Performance Improvement of Illumination system with energy conservation at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Solar High masts along the rail track in railway yard Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 3.75 | 3.75 | 0 | 0 | 0 |  |  | 0 | 0
27.6 | Scheme No. 6 : Design, Supply & Installation of LT VFD Drives for Critical Conveyors at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of LT VFD Drives for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
27.7 | Scheme No. 7 : Design , supply, Erection & Commissioning of Short Conveyor for Stacking Purpose at CHP 3x660MW KTPS Koradi A) Brief scope of work: Short Conveyor for Stacking Purpose at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 9.6 | 9.6 | 0 | 0 | 0 |  |  | 0 | 0
27.8 | Scheme No. 8 : Capacity Enhancement of BCN-7/5/4/3 /1 AB in CHP 3x660MW KTPS Koradi A) Brief scope of work: Short Conveyor for Stacking Purpose at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 8.6 | 8.6 | 0 | 0 | 0 |  |  | 0 | 0
27.9 | Scheme No. 9 : Design , Engineering & modification along with strengthening of Existing Travel Track structure for Side Arm Charger & Stacker Reclaimer A) Brief scope of work: strengthening of Existing Travel Track structure for Side Arm Charger & Stacker Reclaimer Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
27.1 | Scheme No. 10 : Design , Engineering & Erection of modified Energy Efficient Ventilation System for Wagon Tippler Complex Area in CHP 3X660MW KTPS Koradi A) Brief scope of work: Energy Efficient Ventilation System for Wagon Tippler Complex Area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
27.11 | Scheme No. 11 : Design , Engineering & Installtion of Vibration & temprature Monitoring Systems for critical auxiliaries in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Installtion of Vibration & temprature Monitoring Systems for critical auxiliaries Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
27.12 | Scheme No. 12 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
27.13 | Scheme No. 13 : Design , Engineering & Provision of Stone Grappling Equipment System for Wagon Tippler 3 &4 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Stone Grappling Equipment System for Wagon Tippler 3 &4 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.9 | 0.9 | 0 | 0 | 0 |  |  | 0 | 0
27.14 | Scheme No. 14 : Design , Engineering & Provision of Public Addressing System for Wagon Tippler Complex in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Public Addressing System for Wagon Tippler Complex in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
27.15 | Scheme No. 15 : Design , Engineering & Provision of Belt Tracking System for Critical Conveyors in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Belt Tracking System for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
27.16 | Scheme No. 16 : Design , Engineering & Provision of Dust supression System for stacker reclaimer-1 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.6 | 0.6 | 0 | 0 | 0 |  |  | 0 | 0
27.17 | Scheme No. 17 : Work of Life Enhancement of wobbler Feeder 1 &2 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.6 | 1.6 | 0 | 0 | 0 |  |  | 0 | 0
28 | DPR for Coal Handling Plant Performance Improvement Schemes -IV at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28.1 | Scheme No.1 : Design , Engineering , Supply & Installation of Modular Transfer chutes for Critical Conveyor System in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of Modular Transfer chutes for Conveyor System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 14 | 14 | 0 | 0 | 0 |  |  | 0 | 0
28.2 | Scheme No.2 :Upgradtion of Exsisting Fire Fighting System at Stack yard area in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradtion of Exsisting Fire Fighting System at Stack yard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 2.6 | 2.6 | 0 | 0 | 0 |  |  | 0 | 0
28.3 | Scheme No.3 : Design , Engineering , Supply & Strengthening of engineering structure of BCN- 7A/B along with track alignment in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Strengthening of engineering structure of BCN- 7A/B Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 2.4 | 2.4 | 0 | 0 | 0 |  |  | 0 | 0
28.4 | Scheme No.4 : Design , Engineering , Supply & Installation of Mist Cannon Spray System around stackyard area in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of Mist Cannon Spray System at stackyard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.6 | 1.6 | 0 | 0 | 0 |  |  | 0 | 0
28.5 | Scheme No.5 : Design , Engineering , Supply & Installation of EOT cranes at Bunker in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of EOT cranes at Bunker Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 4.5 | 4.5 | 0 | 0 | 0 |  |  | 0 | 0
29 | DPR for Procurment of various Heavy Vehicles at CHP 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29.1 | Scheme No.1 : Procurment of Heavy Vehicles like dozers, wheel loaders , locomotives, Crane, Hydra , Disel Browser , Jcb & Bobcats etc. in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurment of Heavy Vehicles like dozers, wheel loaders , locomotives etc Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
29.2 | Scheme No.2 : Procurment of Auger Machines for coal sampling in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurment of Auger Machines for coal sampling Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 2.2 | 2.2 | 0 | 0 | 0 |  |  | 0 | 0
29.3 | Scheme No.3 : Procurment of Truck Mounted mist cannon dust supression system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurment of Truck Mounted mist cannon dust supression system in CHP Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.8 | 0.8 | 0 | 0 | 0 |  |  | 0 | 0
30 | DPR for Coal Handling Plant Performance Improvement Schemes -V at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.1 | Scheme No. 1 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 3.2 | 3.2 | 0 | 0 | 0 |  |  | 0 | 0
30.2 | Scheme No. 2 : Performance Improvement of Stacking & Reclaiming / Side Arm Charger System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Energy Chain System of Stacking & Reclaiming System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
30.3 | Scheme No. 3 : Performance Improvement of unloading System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Energy Chain System of side arm acharger Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
30.4 | Scheme No. 4 : Upgradation to 100 MT Ton Weighbridge of existing road weighbridge at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of LT VFD Drives for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.8 | 0.8 | 0 | 0 | 0 |  |  | 0 | 0
30.5 | Scheme No. 5 : Design , Engineering & Erection of modified Energy Efficient Ventilation System for Crusher House Area in CHP 3X660MW KTPS Koradi A) Brief scope of work: Energy Efficient Ventilation System for Wagon Tippler Complex Area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
30.6 | Scheme No. 6 : Design , supply & Installation of Cooling Arrangement for Switchgear rooms at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Cooling Arrangement for Switchgear rooms Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
30.7 | Scheme No. 7 : Design , Engineering & Erection of modified Engineering Structure of Tunnel Conveyor 1A &1 B in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Erection of modified Engineering Structure of Tunnel Conveyor 1A &1 B Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 2.35 | 2.35 | 0 | 0 | 0 |  |  | 0 | 0
31 | DPR for Coal Handling Plant Performance Improvement Schemes -VI at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.1 | Scheme No. 1 : Performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Wagon Tippler, Side Arm Charger , Apron Feeder ( 3 & 4) Stacker Reclaimer 2 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 11.5 | 11.5 | 0 | 0 | 0 |  |  | 0 | 0
31.2 | Scheme No. 2 : Design Supply & Installation of Wagon Locking system for all four wagon tipplers at CHP 3x660MW KTPS Koradi A) Brief scope of work: Wagon Locking system for all four wagon tipplers Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
31.3 | Scheme No. 3 : Design, Supply & Installation of upgraded Vibrating Feeders for Stacker Reclaimer at CHP 3x660MW KTPS Koradi A) Brief scope of work: Design, Supply & Installation of upgraded Vibrating Feeders for Stacker Reclaimer Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.9 | 0.9 | 0 | 0 | 0 |  |  | 0 | 0
31.4 | Scheme No. 4: Performance Improvement of Stacker Reclaimer by providing Hydraulic Drive to Boom Conveyor at CHP 3x660MW KTPS Koradi A) Brief scope of work: Hydraulic Drive to Boom Conveyor Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.9 | 0.9 | 0 | 0 | 0 |  |  | 0 | 0
31.5 | Scheme No. 5 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
31.6 | Scheme No. 6 : Design , Engineering & Provision of Belt Tracking System for Critical Conveyors in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Belt Tracking System for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.6 | 1.6 | 0 | 0 | 0 |  |  | 0 | 0
31.7 | Scheme No. 7 : Design , Engineering & Provision of Dust supression System for stacker reclaimer-1 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.6 | 0.6 | 0 | 0 | 0 |  |  | 0 | 0
31.8 | Scheme No. 8 : Work of Life Enhancement of wobbler Feeder 3 &4 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.6 | 1.6 | 0 | 0 | 0 |  |  | 0 | 0
32 | DPR for Coal Handling Plant Performance Improvement Schemes -VII at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.1 | Scheme No.1 : Design , Engineering , Supply & Installation of Modular Transfer chutes for Crusher House Complex & other Critical Conveyor System in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of Modular Transfer chutes for Conveyor System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 13 | 13 | 0 | 0 | 0 |  |  | 0 | 0
32.2 | Scheme No.2 :Upgradtion of Exsisting Fire Fighting System along the conveyor length in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradtion of Exsisting Fire Fighting System at Stack yard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 3.2 | 3.2 | 0 | 0 | 0 |  |  | 0 | 0
32.3 | Scheme No.3 : Supply , Erection & Installation of Rack & Pinion Elevators at Bunker in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Supply , Erection & Installation of Rack & Pinion Elevators at Bunker in CHP 3X660MW KTPS Koradi. Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.8 | 0.8 | 0 | 0 | 0 |  |  | 0 | 0
32.4 | Scheme No.4 :Up Liftment f Exsisting Fire Fighting lines in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradtion of Exsisting Fire Fighting System at Stack yard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 3.2 | 3.2 | 0 | 0 | 0 |  |  | 0 | 0
32.5 | Scheme No.5 : Procurement of HPPE Polymer Roller for Conveyor system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurement of HPPE Polymer Roller for Conveyor system Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.8 | 0.8 | 0 | 0 | 0 |  |  | 0 | 0
32.6 | Scheme No.6 : Design , Engineering , Supply & Installation of EOT cranes at Wagon Tippler Complex in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of EOT cranes at Wagon Tippler Complex Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 6.2 | 6.2 | 0 | 0 | 0 |  |  | 0 | 0
33 | DPR for Coal Handling Plant Performance Improvement Schemes -VIII at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.1 | Scheme No. 1 : Performance Improvement of Unloading System Wagon Tipplers at CHP 3x660MW KTPS Koradi Estimated Cost : 3.6 Cr. | 0 | - | 0 | 3.6 | 3.6 | 0 | 0 | 0 |  |  | 0 | 0
33.2 | Scheme No. 2 : Performance Improvement of Unloading System Side Arm Chargers at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Side Arm Charger Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 2.8 | 2.8 | 0 | 0 | 0 |  |  | 0 | 0
33.3 | Scheme No. 3 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 3.4 | 3.4 | 0 | 0 | 0 |  |  | 0 | 0
33.4 | Scheme No. 4 : Performance Improvement of Stacking & Reclaiming System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Stacking & Reclaiming System -2 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 3.5 | 3.5 | 0 | 0 | 0 |  |  | 0 | 0
33.5 | Scheme No. 5 : Performance Improvement of Crushing System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Impact Crusher & Wobbler Feeders Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 8.5 | 8.5 | 0 | 0 | 0 |  |  | 0 | 0
33.6 | Scheme No. 6 : Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -2 at CHP 3x660MW KTPS Koradi A) Brief scope of work: Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -2 at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
33.7 | Scheme No. 7 : Other Mislenious Schemes at CHP 3x660MW KTPS Koradi A) Brief scope of work: Other Mislenious works Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
33.8 | Scheme No. 4 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.8 | 0.8 | 0 | 0 | 0 |  |  | 0 | 0
33.9 | Scheme No.8: Procurement of HPPE Polymer Roller for Conveyor system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurement of HPPE Polymer Roller for Conveyor system Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.8 | 0.8 | 0 | 0 | 0 |  |  | 0 | 0
34 | DPR for Coal Handling Plant Performance Improvement Schemes -IX at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.1 | Scheme No. 1 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 3.6 | 3.6 |  |  | 3.6 | 0
34.2 | Scheme No. 2 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
34.3 | Scheme No.3 : Upgradation of Exsisting Rack & Pinion Elevators at CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradation of Exsisting Rack & Pinion Elevators Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 1.6 | 1.6 |  |  | 1.6 | 0
34.4 | Scheme No.4 : Procurement of HPPE Polymer Roller for Conveyor system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurement of HPPE Polymer Roller for Conveyor system Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 0.8 | 0.8 |  |  | 0.8 | 0
34.5 | Scheme No.5 : Other miscellaneous scheme regarding sustainable performance improvement of CHP 3X660MW KTPS Koradi. A) Brief scope of work: ther miscellaneous scheme regarding sustainable performance improvement Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0 | 0 | 0 | 18 | 18 |  |  | 18 | 0
35 | Design & engineering, procurement, supply, installation & commissioning of Ozone Generator system of capacity 45.0 Kg/hr for CW system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Scheme1:Design & engineering, procurement, supply, installation & commissioning of Ozone Generator system of capacity 45.0 Kg/hr for CW system | 0 | - | 0 | 45 | 45 | 0 | 0 | 0 |  |  | 0 | 0
36 | Pipeline expansion to improve dry ash evacuation system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.1 | Scheme1: Pipeline expansion to improve dry ash evacuation system along with target box modification and also to erect & commission dry ash evacuation directly to remote silo. | 0 | - | 0 | 75 | 75 | 0 | 0 | 0 |  |  | 0 | 0
37 | Modification at intermediate silo and HCSD system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.1 | Scheme1: Additional charge pump. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
37.2 | Scheme 2: Supply & Installation Air washery at silo top. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
37.3 | Scheme 3: Shed above silo top. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
37.4 | Scheme 4: Supply & Installation Construction of platform at pipe rack up to Remote silo. | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
37.5 | Scheme 5: Shifting of pipeline above pipe rack. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
37.6 | Scheme 6: Supply & Installation ART sub assemblies. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
38 | ESP field strengthening at U#8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.1 | Scheme1: ESP field strengthening at U#8 | 0 | - | 0 | 120 | 120 | 0 | 0 | 0 |  |  | 0 | 0
39 | Procurement of various pumps for AHP performance improvement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
39.1 | Scheme1: Procurement of various pumps for AHP performance improvement. | 0 | - | 0 | 28 | 28 | 0 | 0 | 0 |  |  | 0 | 0
40 | Modification in Dry Ash Evacuation System D/V Assemblies & allied equipments to improve performance | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
40.1 | Scheme1: Procurement of D/V Assemblies & allied equipments to improve performance. | 0 | - | 0 | 35 | 35 | 0 | 0 | 0 |  |  | 0 | 0
41 | Additional IAC house for Intermediate silo and Remote silo along with erection of S.S. Pipeline | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.1 | Scheme1: Supply & Installation Additional IAC house for Intermediate silo and Remote silo along with erection of S.S. Pipeline | 0 | - | 0 | 50 | 50 | 0 | 0 | 0 |  |  | 0 | 0
42 | Waste water system modification to have zero water discharge | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.1 | Scheme1: Waste water system modification to have zero water discharge at 3x660MW, KTPS, Koradi along with Pump Procurement along with arrangement of sludge discharge at ESP water Washing system. | 0 | - | 0 | 26 | 26 | 0 | 0 | 0 |  |  | 0 | 0
43 | ESP field strengthening at U#9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
43.1 | Scheme1: ESP field strengthening at U#9 | 0 | - | 0 | 275 | 275 | 0 | 0 | 0 |  |  | 0 | 0
44 | Procurement of HCSD GEHO Pump (TZPM-400) critical items sub-assemblies | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.1 | Scheme1: Procurement of HCSD GEHO Pump TZPM-400) critical items sub-assemblies. | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
45 | MSERW Pipes & Seamless Pipes replacement to improve ash conveying & its disposal-1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.1 | Scheme1: Supply & Work of Replacement of MSERW Pipes & Seamless Pipes in Bottom ash/Coarse ash evacuation & Ash Slurry Disposal Pipelines, Dry ash conveying system in phase manner to improve the ash evacuation performance. | 0 | - | 0 | 70 | 70 | 0 | 0 | 0 |  |  | 0 | 0
46 | Improvement in Ash Water Recovery System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.1 | Scheme1: Supply & Installation of Pumps along with Pipeline for Improvement in Ash Water Recovery System. | 0 | - | 0 | 35 | 35 | 0 | 0 | 0 |  |  | 0 | 0
47 | Replacement of Instrument air pipeline from M.S. to S.S for AHP main plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.1 | Scheme1: Replacement of Instrument air pipeline from M.S. to S.S for AHP main plant | 0 | - | 0 | 40 | 40 | 0 | 0 | 0 |  |  | 0 | 0
48 | Modification of sludge pumps and its pipeline with pumps of higher capacity and discharge line of higher capacity. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.1 | Scheme1: Modification of sludge pumps and its pipeline with pumps of higher capacity and discharge line of higher capacity. | 0 | - | 0 | 50 | 50 | 0 | 0 | 0 |  |  | 0 | 0
49 | ESP field strengthening at U#10 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
49.1 | Scheme1: ESP field strengthening at U#10 | 0 | - | 0 | 310 | 310 | 0 | 0 | 0 |  |  | 0 | 0
50 | MSERW Pipes & Seamless Pipes replacement to improve ash conveying & its disposal-2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50.1 | Scheme1: Supply & Work of Replacement of MSERW Pipes & Seamless Pipes in Bottom ash/Coarse ash evacuation & Ash Slurry Disposal Pipelines, Dry ash conveying system in phase manner to improve the ash evacuation performance. | 0 | - | 0 | 0 | 0 | 0 | 90 | 90 |  |  | 90 | 0
51 | Replacement of IAC for AHP Main Plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
51.1 | Scheme1: Supply & Installation of IAC for AHP Main Plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
52 | Improvement in DRY ASH Evacuation system-2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
52.1 | Scheme1: Supply & Installation of TAC, Replacement of Air Lock Vessel, Various Valves, ESP Hopper Doors, ESP access doors. | 0 | - | 0 | 0 | 0 | 0 | 40 | 40 |  |  | 40 | 0
53 | Improvement in DRY ASH Evacuation system-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
53.1 | Scheme1: Procurement of Ingersoll Rand Make Transport Air Compressors Critical/Non-Critical Spares sub-assembly for performance improvement. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
54 | Detailed project report for various works of security section as per the IB recommendations. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
54.1 | Repairing & raising height of compound wall with provision of concertina coil at various location of peripheral compound wall at 3x660MW KTPS Koradi. | 0 | - | 0 | 1.593 | 1.593 | 0 | 0 | 0 |  |  | 0 | 0
54.2 | Work of Providing structural three quarter turn staircase with landing along pheriphery of FISS watch tower at 3x660MW, TPS, Koradi. | 0 | - | 0 | 0.34444 | 0.34444 | 0 | 0 | 0 |  |  | 0 | 0
55 | Supply, installation, comissioning and testing of 220V station & 360V UPS batteries installed at U 8, 9 & 0 of 3x660 MW KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
55.1 | Supply, installation, comissioning and testing of 220V station & 360V UPS batteries installed at U 8, 9 & 0 of 3x660 MW KTPS, Koradi. (scheme) | 0 | - | 0 | 68.4 | 68.4 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
56 | TDBFP Governing valve's LPCV ,HPCV MSV AND Trip lock replacement | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
61 | Procurement & replacement of HP Heaters at 3x660 MW KTPS, Koradi. | 0 | - | 0 | 0 | 25 | -25 | 0 | 0 |  |  | 0 | -25
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Vibration Monitoring & Analysis system installed at 3x660MW Koradi TPS. | 0 | - | 0 | 63 | 63 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of sinkawa make vibration monitoring and Analysis system for main turbine at 3x660MW koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of Bently Nevada make vibration monitoring and Analysis system for RMCMS system at 3x660MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3 :-Emerson PLC upgradation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of various Level Transmitters installed at 3x660 MW koradi TPS. | 0 | - | 0 | 31 | 31 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of Guided wave Radar Level TX installed at Condenser Hotwell and LPH 1,2 and 3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of Displacer type level TX into Guided wave radar level Tx installed at various Drain Tank, Flash tank and pit | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3: Upgradation of non- contact type Ultrasonic level Tx into IP68 non- contact type Radar level TX. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of ESP Hopper level Probes installed at 3x660 MW koradi TPS. | 0 | - | 0 | 40 | 40 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of 1st three fields ESP Hopper level probes into continuous level monitoring NOGS system at 3x660 MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of RF capacitance Hopper level probe into of RF admittance level probe at 4,5,6,7,8 & 9 ESP Hoppers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3: Upgradation of ESP hopper heater monitoring , control and real time monitoring system at 3X660MW Koradi TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of various scheme viz ASLD, Furnace tv camera FEGT and acoustic Pyrometer installed at 3x660 MW koradi TPS. | 0 | - | 0 | 61 | 61 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of ASLD system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of Furnace TV Camera | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3:Upgradation of FEGT system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 4:Upgradation of acoustic pyrometer | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of various scheme viz instrument Air pipe at ESP Area, wet Ash Evacuation system, HCSD Silo. | 0 | - | 0 | 26 | 26 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of instrument Air pipeline system at ESP of M.S into SS installed at 3x660 MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of instrument Air pipeline system at wet Ash system of M.S into SS . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3: Upgradation of instrument Air pipeline system at HCSD silo of M.S. into SS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 4: Upgradation of instrument Air pipeline system at Remote Silo of M.S into SS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 5: Upgradation of Control & Instrument section lab with Hydraulic Servo Valve Test, Pneumatic System test and calibration lab set up. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Flame scanner for flexible operation of 3X660MW Koradi TPS. | 0 | - | 0 | 35 | 35 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of Flame scanner for flexible operation of 3X660MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of DRC Pipes, Bends & Fittings in phase manner to improve the dry ash conveying & its disposal (2 years) | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of DRC Pipes, Bends & Fittings in phase manner to improve the dry ash conveying & its disposal (2 years) (Rs.30 Cr.) (Bottom ash/Coarse ash evacuation & Ash Slurry Disposal Pipelines, Dry ash conveying system) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Augmentation of Coarse Ash disposal system at U10 at KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | WORK OF INSTALLATION & COMMISSIONING OF ASH DISPOSAL SYSTEM AT UNIT#10 | 0 | - | 0 | 0 | 82.01 | -82.01 | 0 | 0 |  |  | 0 | -82.01
0 | IDC | 0 | - | 0 | 0 | 2.93 | -2.93 | 0 | 0 |  |  | 0 | -2.93
0 | DPR for Railway Track Siding Performance Improvement Schemes at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 1 : Work of complete track renovation of existing Rail yard of CHP, 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. Due to continuous movement of Railway's precious rolling stock, the track spares are worn out and are due for complete replacement. Hence, to maintain rail track parameters in healthy condition as per Railway norms so as to avoid untoward incidences of derailment the execution of work of complete track renewal is essential. | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 2 : Scheme Name- Work of laying of additional track at 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. However, as per the existing infrastructure, at present there is no dedicated empty formation line. Due to non-availability of empty formation line, most often unloading gets hampered due to blocking of outhaul line by empty rake. The hampering in unloading affects the plant performance and incurrs unnecessary financial burden on KTPS account under the head of demurrage charges. Hence, to maintain the plant loadability and availability, it is essential to lay additional track at 3x660MW, KTPS, Koradi. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 3 : Scheme Name- Work of rectification and upgradtion of existing SSP at CHP, 3x660MW, KTPS, Koradi. Justification- The SSP has been erected at 3x660MW, KTPS, Koradi. However, till date the same has not been commissioned. With lapse of @ 5-6 years after erection and its non commissioning, the existing SSP set up has been completely detoriorated. Now, Railway's is pressing hard for early commissioning of the same. The said set up shall ensure isolation of OHE of existing yard with Railway's main line. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 4 : Scheme Name- Work of construction of apron RCC platforms at inhaul and outhaul of Wagon tipllers 1, 2, 3 & 4 of CHP 3x660MW, KTPS, Koradi. Justification- The 04 Nos. of wagon tipplers are installed at CHP-3x660MW, KTPS, Koradi. In this regards, it is to submit that, the wagon unloading is being carried out through these tipplers. Hence, presence of fugitive dust in tippler area is predominant. The said dust is being accumulated at inhaul and outhaul of wagon tipplers. Due to presence of loaded wagons at inhaul and empty wagons at outhaul, this office gets least opportunity for clearance of the said coal dust along the track. Due to accumulation of coal dust, the rail track parameters along with gradient are getting distubed. The disturbance in gradient is causing rolling of wagons which is not recommended in view of safety of both man and machine. Besides, this due to rolling of wagons, the occurnece of untoward incidence of derailment is predominant. Hence, to maintain uniform rail track gradient it shall be enviable to construct the apron RCC platforms at inhaul and outhaul of Wagon tipplers 1, 2, 3 & 4 of CHP-3x660MW, KTPS, Koradi. Estimated cost- Rs. 4 Cr. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 5 : Scheme Name- Work of construction of apron RCC platforms at inhaul and outhaul of Wagon tipllers 1, 2, 3 & 4 of CHP 3x660MW, KTPS, Koradi. Justification- The 04 Nos. of wagon tipplers are installed at CHP-3x660MW, KTPS, Koradi. In this regards, it is to submit that, the wagon unloading is being carried out through these tipplers. Hence, presence of fugitive dust in tippler area is predominant. The said dust is being accumulated at inhaul and outhaul of wagon tipplers. Due to presence of loaded wagons at inhaul and empty wagons at outhaul, this office gets least opportunity for clearance of the said coal dust along the track. Due to accumulation of coal dust, the rail track parameters along with gradient are getting distubed. The disturbance in gradient is causing rolling of wagons which is not recommended in view of safety of both man and machine. Besides, this due to rolling of wagons, the occurnece of untoward incidence of derailment is predominant. Hence, to maintain uniform rail track gradient it shall be enviable to construct the apron RCC platforms at inhaul and outhaul of Wagon tipplers 1, 2, 3 & 4 of CHP-3x660MW, KTPS, Koradi. Estimated cost- Rs. 4 Cr. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 6 : Scheme Name- Work of construction of RCC platforms along the rail track of CHP 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. In this regards, it is to submit that, after unloading of rakes the empty rakes are being examined by Railway's C&W staff camped at KTPS, Koradi. Hence, for safe movement of Railway's staff, Railway's is pressing hard for provision of RCC platforms along the rail track of CHP-3x660MW, KTPS, Koradi. Estimated cost- Rs. 10 Cr. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 7 : Scheme Name- Work of repairing and construction of RCC permanent revenue canal at, KTPS, Koradi. Justification- The temporary revenue canal is being flowing beside the existing Railway exchange yard of 210 MW, KTPS, Koradi. The said canal gets clogged inview of ash accumulation. Due to clogging this canal overflows and its overrun enters the 210 MW rail yard thereby creating track surface marshy and unsafe for Rail movement. Hence, it is essential to repair and construct RCC permanent revenue canal at KTPS, Koradi so that proper and timely cleaning of canal along with proper outlet can be arranged. Estimated cost- Rs. 15 Cr. | 0 | - | 0 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme Name-08 Work of construction of RCCretaining wall at Godhani and Kalumna end of KTPS, Koradi. Justification- The separate rail infrastructure has been commissioned for Koradi TPS to cope up the daily coal requirement. The rail traffic at KTPS, Koradi is being catered through Godhani and Kalumna end respectively. In this regards, it is to submit that, the take off points at Godhani and Kalumna both are S&T operated. During monsoon, it is often witnessed that, the rain water enters the plant premises from others land thereby submerging the S&T operated point. Due to this, signals gets lost and hampers the Rail traffic movement completely. Hence, it is essential to restrict the entrance of rain water in plant premises. This can be possible by constructing retaining wall at required loaction. Estimated cost- Rs. 1 Cr. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme Name-09 OHE maintenance at CHP, KTPS, Koradi Justification-As per the Railway board circular, Railway's has mandated that OHE maintenance cost for existing as well as new sidings shall be borne by the siding owner in accordance with Railway guidelines. Railway will carry out necessary inspection of maintenance work once in six months. Maintenance charges per TKM per annum of OHE as finalized by SECR zonal office is Rs.291566/- per TKM per annum. Also, inspection charges at the rate of Rs.106974/- per day towards inspection to be carried out by Railways every si x months shall be charged on actual basis by Railway's from the sidings.Accordingly, Railway.s has calimed amount of Rs.31314519/- for two years. Hence for 5 yeards it is expected to be Rs.7.82 Cr. Estimated cost- Rs. 7.82 Cr. | 0 | - | 0 | 7.82 | 7.82 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 10 Name-Remodelling and upgradation of existing S & T system with Panel Interlocking system and associated S & T gears to S & T system with Electronic Interlocking system and associated S & T gears in connection with services for BG Railway facility (660 MW Rail yard) for Koradi Thermal Power Station of MSPGCL Justification-As per the prevailing Railway norms, it is mandatory to commission the S & T system in private Railway siding for fast and safe movement of Railway’s precious rolling stock. Unless and until remodeling is carried out the S&T system cannot be started at Koradi Railway yard.With commissioning and operation of S & T system there shall be least possibility for derailments during internal shunting through crossovers, as the said points shall be motorized operated. Estimated cost- Rs. 20 Cr. | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 11 : Work of supply and provision of lights and high mast at CHP Railway exchange yard of 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. In this regards, it is to submit that, after unloading of rakes the empty rakes are being examined by Railway's C&W staff camped at KTPS, Koradi on round the clock basis. Hence, for safe movement of Railway's staff, Railway's is pressing hard for availability of proper illumination in complete yard. Estimated cost- Rs.2.5 Cr. | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Provision of cover shed for stack yard -2 at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 1 : Provision of cover shed for stack yard -2 at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 135 | -135 | 0 | 0 |  |  | 0 | -135
0 | DPR for Procurement of Pipe Conveyor Drive System Internals at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 1 : Procurement of Pipe Conveyor Drive System Internals at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 27 | -27 | 0 | 0 |  |  | 0 | -27
0 | DPR for Provision of service building along with vehicle bay at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 1 : Provision of service building along with vehicle bay at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | GENERAL ASSET | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | GENERAL ASSET--AKRDFOGA01-OFFICE FURNITURE | N.A. | - | 0 | 0.57299 | 0.75759 | -0.1846 | 0 | 0 |  |  | 0 | -0.1846
2 | GENERAL ASSET--AKRDFOGA02-COMPUTERS,PRINTER,SCANNER | N.A. | - | 0 | 1.6504 | 2.911 | -1.2606 | 0 | 0 |  |  | 0 | -1.2606
3 | GENERAL ASSET--AKRDFOGA03-AC,WATER COOLER | N.A. | - | 0 | 0.46584 | 0.49898 | -0.033135 | 0 | 0 |  |  | 0 | -0.033135
4 | GENERAL ASSET--AKRDFOGA04-AIR PURIFIER | N.A. | - | 0 | 0 | 0.0105 | -0.0105 | 0 | 0 |  |  | 0 | -0.0105
0 | D) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of KLEP Unit for 'HCSD Pump | 0 | - | 3.73 | 3.73 | 3.73 | 0 | 0 | 0 |  |  | 0 | 0
2 | Restoration of Boiler Circulation Pump at 3X660MW KTPS, Koradi | 0 | - | 0 | 4.73 | 4.73 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of Coal Compartment Assemblies for Unit-10 at 3x660MW KTPS, Koradi. | 0 | - | 0 | 3.73 | 3.73 | 0 | 0 | 0 |  |  | 0 | 0
4 | Repairing and Refurbishment of TDBFP cartridge Model FK6E40 installed at 3X660MW KTPS, Koradi | 0 | - | 0 | 11.86 | 11.86 | 0 | 0 | 0 |  |  | 0 | 0
5 | Non-DPR for Upgradation of Honeywell Make PLC for Mill Reject Handling System installed at 3x660MW Balance of Plant (BOP) Unit- 8, 9 & 10 at Koradi TPS | 0 | - | 0 | 0.85 | 0.85 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of Sky Climber for furnace repairing at 3x660MW KTPS, Koradi | 0 | - | 0 | 3.02 | 3.02 | 0 | 0 | 0 |  |  | 0 | 0
7 | Double Roll Clinker Grinder | 0 | - | 0 | 1.68 | 1.68 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement along with Installation of Clear Water Booster Pump with Motor, Panel Cable and other allied accessories in Unit#10 bottom ash area at AHP, 3x660MW, KTPS, Koradi. | N.A. | - | 0 | 2.8112 | 2.56 | 0.25116 | 0 | 0 |  |  | 0 | 0.25116
9 | Procurement of single Roll Clinker Grinder with Feed Pump & Jet Pump Complete Assembly with modified metallurgy installed at AHP ,3x660MW Units, KTPs, Koradi | N.A. | - | 0 | 3.2868 | 2.12 | 1.1668 | 0 | 0 |  |  | 0 | 1.1668
10 | Work of Repairing and Refurbishment of HIP Rotor along with balancing and over speed trial for L&T-MHI make turbine (Type: TC4F-30”) installed at 3X660MW KTPS, Koradi | N.A. | - | 0 | 7.3532 | 7.13 | 0.22316 | 0 | 0 |  |  | 0 | 0.22316
11 | Procurement of spares for Flue gas distribution dampers, PA fan discharge dampers and Coal mill Hot PA Gate and Dampers at 3x660mw KTPS units through OEM | N.A. | - | 0 | 3.7 | 3.7 | 0 | 0 | 0 |  |  | 0 | 0
12 | Work of Modification & Installation of Take up trolley & arrangement for take up lifting for conveyor BCN-13A at CHP 3X660MW,KTPS,Koradi | N.A. | - | 0 | 356.6331 | 0.75 | 355.8831 | 0 | 0 |  |  | 0 | 355.8831
13 | Work of Design, Modification & streingthening of Tripper trolley structure with provision of Antiwear plates discharge chute box at CHP 3X660MW,KTPS,Koradi | N.A. | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
14 | Upgradation of Management Information System (MIS) Server and Associated Software for C&I at 3x660MW Unit- 8, 9 & 10 at Koradi TPS | N.A. | - | 0 | 2.145 | 2.145 | 0 | 0 | 0 |  |  | 0 | 0
15 | Procurement of Vibrating Tranfer chute with double exciter Drive for stacker reclaimer at CHP,3X660MW,KTPS ,Koradi | N.A. | - | 0 | 0.934 | 0.934 | 0 | 0 | 0 |  |  | 0 | 0
16 | Supply & Installation of Ash Slurry Density Transmitter at High Concentrated Slurry Disposal (HCSD) System of BOP area of 3x660MW Unit- 8, 9 & 10 at Koradi TPS | N.A. | - | 0 | 1.26 | 1.26 | 0 | 0 | 0 |  |  | 0 | 0
17 | Supply & Installation of Fiber Optic Sensing System for Conveyor Health Monitoring At CHP 3x660MW KTPS, Koradi | 0 | - | 0 | 11.72 | 11.72 | 0 | 0 | 0 |  |  | 0 | 0
18 | Procurement of Leak- proof make complete Mechanical Seal Assembly for Concrete Volute CW Pump installed at 3X660MW KTPS,Koradi on OEM bASIS. | 0 | - | 0 | 1.94 | 1.94 | 0 | 0 | 0 |  |  | 0 | 0
19 | Work of Design , Engineering , Manufacturing , Supply Erection & Commissioning of Conveyor Belt From Discharge of RBF 1 &2 at Crusher House to Stack Yard At CHP 3x660MW KTPS, Koradi . | 0 | - | 0 | 11.39 | 11.39 | 0 | 0 | 0 |  |  | 0 | 0
20 | Supply & Installation of Artificial Intelligence PMMS Accurex Diagnostic matrix based vibration & temperature monitoring for critical auxiliaries at CHP 3x660MW KTPS, Koradi. | 0 | - | 0 | 6.431 | 6.431 | 0 | 0 | 0 |  |  | 0 | 0
21 | Restoration of online dissolved gas analysers of Unit 8,9,10 | 0 | - | 0 | 1.11 | 1.11 | 0 | 0 | 0 |  |  | 0 | 0
22 | Complete Replacement of Existing Water Separator Drain Tank Control (WDC) Valves with New Valves of modified trim design along with hydraulic Actuators, Power Pack assembly, necessary instrumentation, erection & commissioning 3X660MW KTPS, Koradi. | 0 | - | 0 | 5.33 | 5.33 | 0 | 0 | 0 |  |  | 0 | 0
23 | Procurement of mandatory set of Hydraulic system internals for Wagon Tippler Drive & side arm charger Drive at CHP,3X660MW,KTPS ,Koradi | 0 | - | 0 | 6.35 | 6.35 | 0 | 0 | 0 |  |  | 0 | 0
24 | "Supply & installation of Anodized winding Oil cooled over band magnetic separator & control panel for conveyor 5A,5B &13C at CHP 3x660MW KTPS, Koradi. | 0 | - | 0 | 1.896 | 1.896 | 0 | 0 | 0 |  |  | 0 | 0
25 | Procurement of Grinding Wall Assembly for Impact Crusher At CHP 3x660MW KTPS, Koradi | 0 | - | 0 | 2.01 | 2.01 | 0 | 0 | 0 |  |  | 0 | 0
26 | Restoration of Boiler Circulation Pump of U10 at 3X660MW KTPS, Koradi | 0 | - | 0 | 6.69 | 6.69 | 0 | 0 | 0 |  |  | 0 | 0
27 | Design,Engineering,Customization,Implementation,Installation & testing of Data Analytical/Artificial Intellegence softwae for automated monitoring & diagnostics system to improve Power plant reliability & efficiency,at one unit of 3X660MW KTPS, Koradi. | 0 | - | 0 | 3.27 | 3.27 | 0 | 0 | 0 |  |  | 0 | 0
28 | Supply of Feed Gate Complete Assembly along with installation to enhance the performance of Feed Gate at Ash Handling Plant, 3x660MW, KTPS, Koradi. | 0 | - | 0 | 2.4 | 2.4 | 0 | 0 | 0 |  |  | 0 | 0
29 | Design, Supply, Installation & Commissioning of Instrument Air Dryer Assembly with Prefilters & Stainless steel piping along with valves suitable for Instrument Air Compressors at AHP, 3x660MW Units, KTPS, Koradi | 0 | - | 0 | 5.5 | 5.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Total | 0 |  | 0 | 6291.8051 | 6249.3574 | 42.4477 | 219.954 | 219.954 |  |  | 219.954 | 42.4477
0 | FY 2029-30 |  |  | 0 | 0
0 | A) Approved Add cap: | 0 | - | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
A | BoP | 0 | - | 246.34 | 103.6804 | 232.6929 | -129.0125 | 0 | 0 |  |  | 0 | -129.0125
B | BTG | 0 | - | 44.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B1 | Supply | 0 | - | 13.33 | 0 | 13.33 | -13.33 | 0 | 0 |  |  | 0 | -13.33
B2 | Works | 0 | - | 0.98 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B3 | Taxes and duties | 0 | - | 23.29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
B4 | Civil | 0 | - | 0.19 | 0.19 | 0 | 0.19 | 0 | 0 |  |  | 0 | 0.19
B5 | Mandatory Spares | 0 | - | 5.03 | 1.29 | 6.32 | -5.03 | 0 | 0 |  |  | 0 | -5.03
B6 | BTG (L&T) Work | 0 | - | 1.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C | Other Works (Plant) | 0 | - | 136.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C1 | Fully Integrated Security System | 0 | - | 27.36 | 31.4615 | 31.4615 | 0 | 0 | 0 |  |  | 0 | 0
C2 | Administrative Expenses and overhead | 0 | - | 7.25 | 6.69 | 0 | 6.69 | 0 | 0 |  |  | 0 | 6.69
C3 | Contingencies E&M | 0 | - | 0.04 | 0.04 | 0 | 0.04 | 0 | 0 |  |  | 0 | 0.04
C4 | Mobile storage racks, fork lifts, hoists & hydra for material handling in major stores shed | 0 | - | 0.95 | 0.93645 | 0.93645 | 0 | 0 | 0 |  |  | 0 | 0
C5 | Development of working models of Plant Layout, Boiler, Turbine- Generetaor, Coal mill, Fans, etc. at KTC, Koradi. | 0 | - | 1.2 | 1.2 | 0.98604 | 0.21396 | 0 | 0 |  |  | 0 | 0.21396
C6 | Workshop equipment | 0 | - | 0.26 | 0.26192 | 0.26192 | 0 | 0 | 0 |  |  | 0 | 0
C7 | Design, engg, manufacture, supply , erection, testing & commissioning of Ozonization Plant for circulating cooling water system | 0 | - | 54.05 | 31.7683 | 31.6144 | 0.15388 | 0 | 0 |  |  | 0 | 0.15388
C8 | Supply, installation & commissioning of water flow meters including required SCADA software and other accessories for water management system | 0 | - | 5.08 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C9 | Provision of wet ash evacuation system for first two rows of ESP for Unit-8,9 & 19 | 0 | - | 26.59 | 21.69 | 26.3181 | -4.6281 | 0 | 0 |  |  | 0 | -4.6281
C10 | Procurement of portable mercury analyser for flue gas monitoring | 0 | - | 6.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
C11 | Administrative Expenses and overhead | 0 | - | 5 | 21.0001 | 0 | 21.0001 | 0 | 0 |  |  | 0 | 21.0001
C12 | Compressor of Hydrogen plant | 0 | - | 1.5 | 1.5 | 0 | 1.5 | 0 | 0 |  |  | 0 | 1.5
C13 | Rail Cum road stone grabbler | 0 | - | 0.85 | 0.85 | 0 | 0.85 | 0 | 0 |  |  | 0 | 0.85
D | Other Works (Civil) | 0 | - | 103.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D1 | Road, Bridges railway system | 0 | - | 20.1 | 0.10806 | 0 | 0.10806 | 0 | 0 |  |  | 0 | 0.10806
0 | S&T System with Panel Interlocking System | 0 | - | 0 | 10.4585 | 10.4596 | -0.0011606 | 0 | 0 |  |  | 0 | -0.0011606
D2 | Staff quarters | 0 | - | 5.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D3 | Other Misc & Unforseen Item | 0 | - | 25.79 | 9.3 | 7.53 | 1.77 | 0 | 0 |  |  | 0 | 1.77
0 | Check Post, Inspection Office & Facility Complex | 0 | - | 0 | 3.6844 | 3.6816 | 0.0028689 | 0 | 0 |  |  | 0 | 0.0028689
0 | CPRI Building | 0 | - | 0 | 6.2046 | 6.2046 | 0 | 0 | 0 |  |  | 0 | 0
0 | Foam cum DCP fire tender- 1 | 0 | - | 0 | 0 | 0.76926 | -0.76926 | 0 | 0 |  |  | 0 | -0.76926
0 | Fire water Bowser-cum-fire Tender- 1No. | 0 | - | 0 | 0.73537 | 0.73537 | 0 | 0 | 0 |  |  | 0 | 0
D4 | Const. facility | 0 | - | 3.28 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D5 | Contigency Other Civil Work | 0 | - | 5.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D6 | Adminstrative Exp. & Overhead (Salary & Overhead, Civil & E&M) | 0 | - | 21.47 | 31.64 | 0 | 31.64 | 0 | 0 |  |  | 0 | 31.64
D7 | Future unforseen works(Jalyukta Shiwar) | 0 | - | 0.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
D8 | Landscaping work | 0 | - | 21.76 | 20.53 | 0 | 20.53 | 0 | 0 |  |  | 0 | 20.53
E | Initial Spares | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
E1 | Boiler & its auxilliaries | 0 | - | 14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Procurement of Table liners and Roller liners Of MVM 32R Coal Mills of 3 X 660MW Units at KTPS, Koradi | 0 | - | 0 | 10.0686 | 10.0686 | 0 | 0 | 0 |  |  | 0 | 0
ii | Procurement of couplings for Coal mill MVM 32 R of 3 X 660 MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 1.5944 | -1.5944 | 0 | 0 |  |  | 0 | -1.5944
iii | Procurement of Set of internal spares for Coal Mill Gear Box (KMP-450) for 3 X 660MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 2.2253 | -2.2253 | 0 | 0 |  |  | 0 | -2.2253
E2 | Turbine & its auxilliaries | 0 | - | 18.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | ULTRAFILTRATION MEMBRANE | 0 | - | 0 | 1.6511 | 1.6511 | 0 | 0 | 0 |  |  | 0 | 0
ii | Supply of Main turbine Vibration Monitoring System spares at 3x660MW, KTPS,Koradi. | 0 | - | 0 | 0 | 1.1469 | -1.1469 | 0 | 0 |  |  | 0 | -1.1469
iii | Procurement of Cartridge for Turbine Driven Boiler Feed Pump (Model No.: FK6E40) at 3X660 MW KTPS Koradi | 0 | - | 0 | 14.2864 | 14.2864 | 0 | 0 | 0 |  |  | 0 | 0
iv | Procurement of Critical Insurance Spares for L&T-MHI Make Turbine for attending major overhauling work of Turbine at KTPS, 3x660MW Units Koradi. | 0 | - | 0 | 11.1013 | 11.1013 | 0 | 0 | 0 |  |  | 0 | 0
E3 | Generator & its auxilliaries | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
E4 | Electrical auxilliaries | 0 | - | 1.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Procurement of HT Motors of BOP | 0 | - | 0 | 0 | 0.29335 | -0.29335 | 0 | 0 |  |  | 0 | -0.29335
ii | 0 | 0 | - | 0 | 0 | 0.84594 | -0.84594 | 0 | 0 |  |  | 0 | -0.84594
iii | Supply of Schneider make Differential Protection Relays for 3X660 MW, Koradi (OEM) | 0 | - | 0 | 0 | 0.10502 | -0.10502 | 0 | 0 |  |  | 0 | -0.10502
iv | Supply of Professional Large Format Display for display of DCS parameters PCR | 0 | - | 0 | 0.14885 | 0.14885 | 0 | 0 | 0 |  |  | 0 | 0
v | Procurement of ABT Energy meter with software for 3X660 MW, TPS, Koradi | 0 | - | 0 | 0 | 0.18337 | -0.18337 | 0 | 0 |  |  | 0 | -0.18337
E5 | Outdoor Plant i.e. CHP, AHP, WTP etc | 0 | - | 19.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Procurement of Forced Lubrication system for Premium make Gear box B3-450 installed for bunker conveyor BCN 7A/B at CHP 3X660MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0.15314 | -0.15314 | 0 | 0 |  |  | 0 | -0.15314
ii | Procurement of rotary spares for travel drive of Stacker and conveyor drive system in Coal Handling Plant of 3x660 MW Units at KTPS, Koradi. | 0 | - | 0 | 0 | 0.35199 | -0.35199 | 0 | 0 |  |  | 0 | -0.35199
iii | Procurement of Complete assembly of Dome Valve ( 100NB, 200NB, 300NB) with power cylinder for dry Ash evacuation system of 3X660MW KTPS, Koradi. | 0 | - | 0 | 0.2225 | 0.2225 | 0 | 0 | 0 |  |  | 0 | 0
iv | Procurement of Modified Apron Pans for M/s. ELECON Engineering Company ltd make Apron Feeder in CHP 3x660MW Units at KTPS, Koradi. | 0 | - | 0 | 3.3233 | 3.3233 | 0 | 0 | 0 |  |  | 0 | 0
v | Procurement of Single Roll Clinker Grinder with Feed Sump and Jet Pump Complete Assembly with Drive, Driven Sprocket and Chain at AHP, 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.56357 | 0.56357 | 0 | 0 | 0 |  |  | 0 | 0
vi | Procurement of spares of Dome Valve (100NB, 200NB, 300NB) for Ash Evacuation System of 3X660MW Unit KTPS, Koradi. | 0 | - | 0 | 0.16431 | 0.16431 | 0 | 0 | 0 |  |  | 0 | 0
vii | 0 | 0 | - | 0 | 0.10064 | 0.10064 | 0 | 0 | 0 |  |  | 0 | 0
viii | 0 | 0 | - | 0 | 0.00708 | 0.00708 | 0 | 0 | 0 |  |  | 0 | 0
ix | Procurement of Hydraulic Motor for Apron feeder in Coal Handling Plant 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.7965 | 0.7965 | 0 | 0 | 0 |  |  | 0 | 0
x | Procurement of Peristaltic Hose Pump (Model no: RP2 – 40) Spares for HCSD System of Ash Handling Plant, 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.20622 | 0.20622 | 0 | 0 | 0 |  |  | 0 | 0
xi | Procurement of spares for HP Water Pump, Mather & Platt make, model 10/12 EME for AHP at 3X660 MW, KTPS, Koradi | 0 | - | 0 | 0.28246 | 0.28246 | 0 | 0 | 0 |  |  | 0 | 0
xii | Procurement of Rotor shaft assembly for M/s. ELECON Engineering Company ltd make Impact Crusher in CHP 3x660MW Units at KTPS, Koradi. | 0 | - | 0 | 0.76369 | 0.76369 | 0 | 0 | 0 |  |  | 0 | 0
xiii | Procurement of Sam Turbo Make Pumps Spare parts for Ash Handling Plant of 3X660 MW Units at KTPS, Koradi | 0 | - | 0 | 0.17166 | 0.17166 | 0 | 0 | 0 |  |  | 0 | 0
xiv | Procurement of Wagon Tippler Spares for M/s. ELECON Engineering Company ltd. make Wagon Tippler in CHP 3X660MW Units at KTPS, Koradi. | 0 | - | 0 | 1.3975 | 1.3975 | 0 | 0 | 0 |  |  | 0 | 0
xv | Procurement of Pneumatic Y Type Control Valve (Blow Valve Size 50mm & 80mm) for Fly Ash Evacuation System of 3X660MW Unit KTPS, Koradi. | 0 | - | 0 | 0.029205 | 0.029205 | 0 | 0 | 0 |  |  | 0 | 0
xvi | Procurement of the various spares required for Warman make Ash Slurry Pump Model 10/8 EEM & Over Flow Pump Model 8/6 EXU installed at AHP, 3X660 MW TPS Koradi through Limited Tender. | 0 | - | 0 | 0.20886 | 0.20886 | 0 | 0 | 0 |  |  | 0 | 0
xvii | 0 | 0 | - | 0 | 0.0076261 | 0.032797 | -0.025171 | 0 | 0 |  |  | 0 | -0.025171
xviii | Procurement of Spares of Single Roll Clinker Grinder Ayems Engineers make, Model AE-1005-89-100 at AHP, 3X660 MW Koradi TPS. | 0 | - | 0 | 0.82826 | 0.82826 | 0 | 0 | 0 |  |  | 0 | 0
xix | Procurement of Hydraulic Motor for Bucket Wheel of Stacker Reclaimer in CHP, 3X660MW, KTPS, Koradi. | 0 | - | 0 | 1.1168 | 1.1168 | 0 | 0 | 0 |  |  | 0 | 0
xx | Procurement of Rotors, Maintenance Kits, Couplings and other spares required for Atlas Copco make Instrument Air Compressor of Ash Handling Plant of 3 X 660 MW Units at KTPS, Koradi. | 0 | - | 0 | 1.1828 | 1.1828 | 0 | 0 | 0 |  |  | 0 | 0
xxi | Procurement of spares of intermediate conveyor | 0 | - | 0 | 0 | 0.3186 | -0.3186 | 0 | 0 |  |  | 0 | -0.3186
xxii | Procurement of Hydraulic motor for wagon tippler drive in CHP, 3X660 MW, KTPS, Koradi. | 0 | - | 0 | 0.46494 | 0.46494 | 0 | 0 | 0 |  |  | 0 | 0
xxiii | Procurement of GEHO Pump (Model No. TZPM 400) Spares of Ash Handling Plant, 3 X 660 MW Units, KTPS, Koradi. | 0 | - | 0 | 0 | 0.83656 | -0.83656 | 0 | 0 |  |  | 0 | -0.83656
xxiv | Procurement of Beater Arms for Impact crushers installed at in Coal Handling Plant of 3x660 MW at KTPS, Koradi. | 0 | - | 0 | 0 | 1.0093 | -1.0093 | 0 | 0 |  |  | 0 | -1.0093
xxv | Supply of Atlas Copco make compressor spares for at Koradi TPS 660MW | 0 | - | 0 | 0 | 0.39813 | -0.39813 | 0 | 0 |  |  | 0 | -0.39813
xxvi | Procurement of spares for side arm charger, wagon tippler, impact crushers and stacker reclaimer at CHP 3x660 MW KTPS | 0 | - | 0 | 0.010573 | 0.43684 | -0.42626 | 0 | 0 |  |  | 0 | -0.42626
xxvii | Procurement of Beater heads with Pin for Impact crushers installed at in Coal Handling Plant of 3x660 MW at KTPS, Koradi. | 0 | - | 0 | 0 | 1.1256 | -1.1256 | 0 | 0 |  |  | 0 | -1.1256
xxviii | Procurement of spares of Hyd Motor of SAC | 0 | - | 0 | 0 | 0.36029 | -0.36029 | 0 | 0 |  |  | 0 | -0.36029
xxix | Procurement of hydraulic power packs for Flap Gates in CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0.1888 | -0.1888 | 0 | 0 |  |  | 0 | -0.1888
xxx | Procurement of Mobile Grilling Equipment for CHP 3x660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0.33866 | -0.33866 | 0 | 0 |  |  | 0 | -0.33866
xxxi | Procurement of Weld overlay Flap Gate assembly in CHP 3x660MW, KTPS, Koradi. | 0 | - | 0 | 0 | 0.5841 | -0.5841 | 0 | 0 |  |  | 0 | -0.5841
E6 | Capital Spares | 0 | - | 89.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of critical insurance spares for Turbine & its critical auxiliaries for 3 x 660 MW, Koradi (4370001538 dtd. 18/06/2018 d.p. 21 Months) | 0 | - | 89.62 | 89.6234 | 88.736 | 0.88736 | 0 | 0 |  |  | 0 | 0.88736
E7 | Additional Capitalization | 0 | - | 57.88 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
i | Contruction of various infrastructure such as roads etc and public amenities in the rehabilitated villages of koradi and khasara | 0 | - | 13.1 | 12.74 | 0 | 12.74 | 0 | 0 |  |  | 0 | 12.74
ii | Procurement of 7 nos of school buses | 0 | - | 2 | 1.3109 | 1.3109 | 0 | 0 | 0 |  |  | 0 | 0
iii | Development of green belt & fodder farm for fulfillment of environmental clearance of MoEF for Koradi 3x660MW | 0 | - | 3.16 | 3.16 | 0 | 3.16 | 0 | 0 |  |  | 0 | 3.16
iv | Provision of Ground Hopper & Short Conveyor Belt from Existing Stackyard 1 & 2 ti existing Main Stream i.e. BCN 4A/4B of CHP 3x660 MW, KTPS, Koradi | 0 | - | 4.36 | 4.3555 | 4.3555 | 0 | 0 | 0 |  |  | 0 | 0
v | Provision of Ground Hopper & Conveyor Belt for Conveying Unloaded Coal form Open Wagon Tippler in CHP of Koradi Unit 8, 9 & 10. | 0 | - | 4.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
vi | Provision of Additional Facility for Manual Unloading Track in CHP of Koradi Unit No. 8, 9 & 10 | 0 | - | 5.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
vii | Construction of drains | 0 | - | 4.31 | 2.7927 | 0 | 2.7927 | 0 | 0 |  |  | 0 | 2.7927
viii | Supply erection commissioning of medium voltage variable frequency drive for conveyors BCN 6A,6B,7A,7B in CHP 3x660MW | 0 | - | 17 | 16.9859 | 16.9859 | 0 | 0 | 0 |  |  | 0 | 0
ix | Supply, Installation & commissioning of 3D level sensors for first two ESP field hoppers | 0 | - | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
F | Koradi TPS 3x660 MW Expansion Project – Construction of 2nd raising of existing Khasara Ash Bund from T.B.L. 308.50 M to T.B.L 312.00 M with construction of concrete dam (Broad crest weir structure), approach to drain wells and raising height of drain well No. 1, 2 & 3, construction of ash Compartment, cleaning of Khasara bund Nallah and construction of peripheral roads connecting to nearby villages for Khasara ash bund at TPS Koradi | 0 | - | 86.914 | 88.683 | 93.291 | -4.608 | 0 | 0 |  |  | 0 | -4.608
G | Discharge of UDL | 0 | - | 0 | 111.97 | 111.48 | 0.49 | 0 | 0 |  |  | 0 | 0.49
H | Asset Addition due to change in classification of inventory | 0 | - | 0 | 21.7503 | 0 | 21.7503 | 0 | 0 |  |  | 0 | 21.7503
I | Medical Oxygen Gr&Cyl Ozonization Plant (Covid Related Work) | 0 | - | 0 | 11.4034 | 9.6702 | 1.7332 | 0 | 0 |  |  | 0 | 1.7332
0 | B) DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (i) Submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Flue Gas Desulphurization FGD is for Unit 8, 9, 10 of 3x660MW Koradi TPS | MERC/CAPEX/FY 2020-21/WFH/SBR/05 | 2020-05-31 | 940 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Flue Gas Desulphurization is for Unit 8, 9, 10 of 3x660MW Koradi TPS | MERC/CAPEX/FY 2020-21/WFH/SBR/05 | 2020-05-31 | 847.78 | 1556.15 | 1556.15 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/FY 2020-21/WFH/SBR/05 | 2020-05-31 | 92.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13 | Construction of new admin building at Vidyut Bhavan, Katol Road, Nagpur | MERC/Capex/2021-2022/MSPGCL/063 | 2022-02-18 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13.1 | Construction of new admin building at Vidyut Bhavan, Katol Road, Nagpur | 0 | 2022-02-18 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | 2022-02-18 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Improvement in Regenerative Air Pre-heater Performance at Unit # 9 of 3x660 MW, Koradi TPS | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 15.869 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Procurement of heating elements for RAPH installed in Unit 9 (660MW) at KTPS Koradi THROUGH LIMITED TENDER | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 15.33 | 11.8 | 11.8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.2 | Replacement of heating elements for RAPH installed in Unit 9 (660MW) at KTPS Koradi | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 0.349 | 0.37 | 0.37 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/0469 | 2022-10-06 | 0.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | CHP Improvement (7 Nos) Schemes & Procurement of Bulldozers, Wheel Loaders and Hydraulic Cranes at CHP 3X660MW, KTPS, Koradi | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 38.87 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Sch-1: Revamping of Apron Feeder in CHP at 3X660MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.68 | 4.68 | 4.68 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Sch-2: Procurement of Hydraulic motors and pumps in CHP at 3X660 MW, KTPS, Koradi | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.44 | 4.44 | 4.44 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.3 | Sch-3: Capacity enhancement of Hydraulic motor of Apron Feeder in CHP, 3X660 MW, KTPS, Koradi | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 2.01 | 2.01 | 2.01 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.4 | Sch-4: Modification, supply and replacement of Transfer chutes in CHP 3x660MW KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.39 | 4.39 | 4.39 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.5 | Sch-5: Design, supply, installation & commissioning of High performance IGUS energy chain system with chain flex cable for Tripper trolleys at CHP at 3x660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 4.37 | 4.37 | 4.37 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.6 | Sch-6: Procurement of B3-630 gear box for BCN 6 A/B in CHP at 3x660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 0.57 | 0.57 | 0.57 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.7 | Sch-7: Supply and installation of Belt tear detector system for conveyor belt in CHP 3x660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 1.18 | 1.18 | 1.18 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.8 | Sch-8: Procurement of 5 Nos of Bulldozers BD 155 at CHP 3X660 MW Koradi Thermal Power station. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 12.83 | 12.83 | 12.83 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.9 | Sch-9:- Procurement of 02 nos. of Wheel loaders at CHP 3X660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 3.07 | 3.07 | 3.07 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Sch-10:- Procurement of 15 Ton & 20 Ton capacity hydraulic Cranes at CHP 3X660 MW, KTPS, Koradi. | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 0.69 | 0.69 | 0.69 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2024-25/0252 | 2024-04-18 | 0.64 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Construction of bridge cum bandhara across Pond No. 3 and allied works at Pond No. 3 at Koradi TPS | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 33.116 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Construction of cement concrete bridge cum bandhara alongwith gated arrangement. | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 14.75 | 14.75 | 14.75 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.2 | Construction of earthen embankment connecting bridge cum bandhara on both side of embankment by excavating soil / typha / silt from Pond No.3 & tree plantation. | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 14.3252 | 14.3252 | 14.3252 | 0 | 0 | 0 |  |  | 0 | 0
20.3 | Providing structural steel pathway on the existing waste weir (west side of the Pond No.3) and roads connecting to bridge behind Pond No.3 and bridge cum bandhara. | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 2.4308 | 2.4308 | 2.4308 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-25/MSPGCL/0250 | 2024-04-18 | 1.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement & replacement of Superheater Pass Economizer Coils (Modified Design) for Unit 8, 9 & 10 at 3x660MW KTPS, Koradi | Not Approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Procurement & replacement of Superheater Pass Economizer Coils (Modified Design) for Unit 8, 9 & 10 at 3x660MW KTPS, Koradi | Not Approved | - | 0 | 144.42 | 144.42 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Not Approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Improvement in Boiler Performance at U-8,9 & 10 KTPS, Koradi | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 62.929 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Scheme-1: Procurement of Blade Sets for ID, FD & PA Fans at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 11.34 | 11.34 | 11.34 | 0 | 0 | 0 |  |  | 0 | 0
7.2 | Scheme-2: Procurement of RAPH Bottom Support Bearing Assembly at 3X660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 2.478 | 2.478 | 2.478 | 0 | 0 | 0 |  |  | 0 | 0
7.3 | Scheme-3: Procurement of RAPH Top Guide Bearing Assembly at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 0.684 | 0.684 | 0.684 | 0 | 0 | 0 |  |  | 0 | 0
7.4 | Scheme-4: Procurement of RAPH Gear Box at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 3.44 | 3.44 | 3.44 | 0 | 0 | 0 |  |  | 0 | 0
7.5 | Scheme-5: Procurement of RAPH Spares at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 1.13 | 1.13 | 1.13 | 0 | 0 | 0 |  |  | 0 | 0
7.6 | Scheme-6: Procurement of Coal Burner Assembly with windbox air nozzles for Unit 8 & 9 at 3x660MW. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 15.407 | 15.407 | 15.407 | 0 | 0 | 0 |  |  | 0 | 0
7.7 | Scheme-7: Procurement of Boiler Circulation Pump (BCP) with Impeller & Diffuser at 3x660MW Units. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 11.12 | 11.12 | 11.12 | 0 | 0 | 0 |  |  | 0 | 0
7.8 | Scheme-8: Procurement and Replacement of Heating Elements for RAPH Installed for Unit 8 at 3x660MW. | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 15.96 | 15.96 | 15.96 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0638 | - | 1.37 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Design, Engineering, Supply, Installation, Testing, Commissioning including all civil works for Natural resource treatment and Laboratory equipment with mandatory spares at Koradi TPS, 3 X 660 MW | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 49.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.1 | Supply of Natural resource treatment and lab equipment for Water, Coal, Oil, Meteorology with supporting AI computing, all auxiliaries, and accessories. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 35.28 | 42.5744 | 42.5744 | 0 | 0 | 0 |  |  | 0 | 0
23.2 | Supply of Mandatory spares on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.8 | 0.944 | 0.944 | 0 | 0 | 0 |  |  | 0 | 0
23.3 | Supply of Tools and Tackles on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.15 | 0.177 | 0.177 | 0 | 0 | 0 |  |  | 0 | 0
23.4 | Complete Civil Work with 10 KLD ETP/ STP on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 3.6 | 4.25 | 4.25 | 0 | 0 | 0 |  |  | 0 | 0
23.5 | Services - Charges of Inland transport of plant and equipment on lump-sum basis. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.2 | 0.236 | 0.236 | 0 | 0 | 0 |  |  | 0 | 0
23.6 | Charges for Testing, Commissioning and PG Test of plant and equipment. | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.05 | 0.059 | 0.059 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0177 | 2024-03-11 | 0.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Improvement in Regenerative Air Preheater Performance & Complete Replacement of NDCT fills at Unit # 10, Koradi TPS | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 25.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.1 | Procurement of heating elements for RAPH installed in Unit 10 (660MW) at KTPS Koradi through OEM | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 12.23 | 14.521 | 14.521 | 0 | 0 | 0 |  |  | 0 | 0
24.2 | Complete Supply & Replacement of NDCT fills of U#10. | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 13 | 13 | 13 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0249 | 2024-04-18 | 0.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 14 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 14.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 10.994 | 10.994 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 15 | HMI (Human Machine Interface) Upgradation of ‘SSPA-T3000’ DCS (Distribution Control System), Rockwell make PLC System installed at 3x660MW Unit No. 8, 9 & 10 at Koradi TPS and HMI (Human Machine Interface) Upgradation of MaxDNA DCS System at Unit 8-9, CSTPS, Chandrapur | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 55.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 15.1 | Supply: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 10.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 15.2 | Works: HMI (Human machine Interface) up gradation of maxDNA DCS system at Unit – 8 & 9, CSTPS, Chandrapur. | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | HMI (Human Machine Interface) Upgradation of ‘SPPA-T3000’ DCS (Distributed Control System) installed at 3x660MW Unit- 8, 9 & 10 at Koradi TPS to match with the external aspects and process improvement | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 24.33 | 24.33 | 24.33 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Upgradation of Rockwell Make PLC System installed at 3x660MW ,Koradi TPS to match with the external aspects and process improvement.(C&I) | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 20.2 | 20.2 | 20.2 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0515 | 2023-10-09 | 0.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Work of provision of platform beside railway siding at backside of chord cabin for loading of fly ash in railway wagon for ash utilization at 3x660 MW TPS, Koradi | 0 | - | 0 | 0.0038356 | 0.0038356 | 0 | 0 | 0 |  |  | 0 | 0
13 | Capital Exenditure schemes for in-principle clearance regarding "EPC contract for the wok of construction of quarters and development of KTPS colony at Koradi" under CAPEX scheme | MERC/CAPEX/MSPGCL/2024-12/0569 DTD.13.09.2024 | 2024-09-13 | 210.48 | 210.48 | 210.48 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of spares for L&T-MHI make Turbine for COH work of Turbine at KTPS, 3x660MW units Koradi | MERC/CAPEX/MSPGCL/2023-24/0639 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Procurement of spares for L&T-MHI make Turbine for COH work of Turbine at KTPS, 3x660MW units Koradi | MERC/CAPEX/MSPGCL/2023-24/0639 | - | 0 | 31.6358 | 31.6358 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Procurement of HP Nozzle assembly for L&T-MHI Make Turbine installed at 3x660MW Units Koradi | MERC/CAPEX/MSPGCL/2023-24/0639 | - | 0 | 4.189 | 4.189 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | C) DPRs Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Control & instrumentation related Various Upgradation schemes viz.Emission Monitoring & Water Quality Analysers ,Vibration Monitoring Schemes,Water Flow Monitoring etc. at 3X660MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Upgradation of Emission Monitoring Analysers | 0 | - | 0 | 9.58 | 9.58 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Upgradation of Water Quality Analysers | 0 | - | 0 | 5.33 | 5.33 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Revamping & Supply Of Upgraded VM7B Version of Vibration Monitoring Rack | 0 | - | 0 | 4.84 | 4.84 | 0 | 0 | 0 |  |  | 0 | 0
2.4 | Implementation of ‘Flow Monitoring System’ at 3x660MW Balance of Plant (BOP) Unit- 8, 9 & 10 at Koradi TPS | 0 | - | 0 | 6.87 | 6.87 | 0 | 0 | 0 |  |  | 0 | 0
3 | CHP Improvement Scheme-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Supply, Erection, Commissioning of set of Internals for Wagon Tipplers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 10.96 | 10.96 | 0 | 0 | 0 |  |  | 0 | 0
3.2 | Supply, Erection, Commissioning of set of Internals for Side Arm Chargers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 3.54 | 3.54 | 0 | 0 | 0 |  |  | 0 | 0
3.3 | Supply, Erection, Commissioning of set of Internals for Wobbler Feeders at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 4.96 | 4.96 | 0 | 0 | 0 |  |  | 0 | 0
3.4 | Supply, Erection, Commissioning of set of Internals for Apron Feeders at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 15.55 | 15.55 | 0 | 0 | 0 |  |  | 0 | 0
3.5 | Supply, Erection, Commissioning of set of Internals for Impact Crushers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 9.63 | 9.63 | 0 | 0 | 0 |  |  | 0 | 0
3.6 | Supply, Erection, Commissioning of set of Internals for Stacker cum Reclaimers at CHP 3X660MW, KTPS, Koradi. | 0 | - | 0 | 6.26 | 6.26 | 0 | 0 | 0 |  |  | 0 | 0
4 | Performance improvement and availability of various Auxiliaries of TG at 3x660MW KTPS Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Performance improvement and availability of various Auxiliaries for Oil Systems of Main Turbine. | 0 | - | 0 | 3.26 | 3.26 | 0 | 0 | 0 |  |  | 0 | 0
4.2 | Performance improvement and availability of various Auxiliaries of Generator System. | 0 | - | 0 | 7.31 | 7.31 | 0 | 0 | 0 |  |  | 0 | 0
4.3 | Performance improvement and availability of Feed Water System. | 0 | - | 0 | 10.54 | 10.54 | 0 | 0 | 0 |  |  | 0 | 0
4.4 | Performance improvement and availability of Vacuum System. | 0 | - | 0 | 2.28 | 2.28 | 0 | 0 | 0 |  |  | 0 | 0
4.5 | Performance improvement and availability of CEP System. | 0 | - | 0 | 7.83 | 7.83 | 0 | 0 | 0 |  |  | 0 | 0
4.6 | Procurement of Complete Pull out Assembly along with Impeller and wear ring of Cooling Water Pump. | 0 | - | 0 | 14.87 | 14.87 | 0 | 0 | 0 |  |  | 0 | 0
4.7 | Procurement of complete assembly of HP and LP Elements for Atlas Copco make Compressors. | 0 | - | 0 | 4.19 | 4.19 | 0 | 0 | 0 |  |  | 0 | 0
5 | Improvement in Wet ash evacuation system at 3x660MW Units, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Procurement & installation of Ash Slurry Series Pump Assembly with modified metallurgy and Critical Wet End Sub Assembly to enhance the performance & slurry disposal capacity. | 0 | - | 0 | 7.53 | 7.53 | 0 | 0 | 0 |  |  | 0 | 0
5.2 | Procurement & installation of Ash Slurry Series Pump Assembly with modified metallurgy along with Gear Box, Fluid Coupling & Motor (4’th Series) and Critical Wet End Sub Assembly to enhance the performance & slurry disposal capacity. | 0 | - | 0 | 2.51 | 2.51 | 0 | 0 | 0 |  |  | 0 | 0
5.3 | Procurement & installation of Overflow Transfer Pump Assembly with upgradation in metallurgy and Critical Wet End Sub Assembly to enhance the performance. | 0 | - | 0 | 3.59 | 3.59 | 0 | 0 | 0 |  |  | 0 | 0
5.4 | Procurement & installation of IAC Compressor Assembly: Model –ZR110 STD 7.5 IMD Atlas Copco Make Oil free water cooled screw air compressor with inbuilt atlas copco make heat of compression single drum rotator air dryer to enhance the performance. | 0 | - | 0 | 7.56 | 7.56 | 0 | 0 | 0 |  |  | 0 | 0
6 | HMI Upgradation of Diasys Netmation DCS at 3x660MW KTPS Koradi Units 8,9 & 9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | HMI Upgradation of Diasys Netmation DCS at 3x660MW KTPS Koradi Units 8,9 & 10 | 0 | - | 0 | 77.15 | 77.15 | 0 | 0 | 0 |  |  | 0 | 0
7 | Improvement in Dry ash evacuation system at 3x660MW Units, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Procurement of Ingersoll Rand Make Transport Air Compressors Critical/Non-Critical Spares sub-assembly for performance improvement. | 0 | - | 0 | 29.57 | 29.57 | 0 | 0 | 0 |  |  | 0 | 0
8 | MSERW Pipes for Garlanding arrangement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.1 | Work of Garlanding arrangement to changeover ash slurry feed points for even filling of pond by providing MSERW Pipes along the periphery of Ash Bund Dyke Wall at Khasara Ash Bund. | 0 | - | 0 | 98.83 | 98.83 | 0 | 0 | 0 |  |  | 0 | 0
9 | Capacity Enhancement & Performance optimization at WTP 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.1 | Capacity enhancement of DM water stream in WTP at 3X660MW, KTPS, Koradi. | 0 | - | 0 | 58.94 | 58.94 | 0 | 0 | 0 |  |  | 0 | 0
9.2 | Capacity enhancement Condensate polishing unit regeneration area in WTP at 3X660 MW, KTPS, Koradi | 0 | - | 0 | 13.41 | 13.41 | 0 | 0 | 0 |  |  | 0 | 0
9.3 | Provision of Ozone generating plant of 1.0 Kg capacity in WTP at 3X660 MW, KTPS, Koradi | 0 | - | 0 | 5.84 | 5.84 | 0 | 0 | 0 |  |  | 0 | 0
10 | DPR for Construction of CC Road alongwith RCC Drain, CC platform for heavy machinery movement at 3x660 MW, TPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.1 | DPR for Construction of CC Road alongwith RCC Drain, CC platform for heavy machinery movement at 3x660 MW, TPS, Koradi | 0 | - | 0 | 33.57 | 33.57 | 0 | 0 | 0 |  |  | 0 | 0
11 | Improvement in Coal Mill Performance-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.1 | Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi through OEM. | 0 | - | 0 | 6.15 | 6.15 | 0 | 0 | 0 |  |  | 0 | 0
11.2 | Procurement of Mill Rotary Separator Blades for coal mill MVM 32R at 3x660 MW, KTPS, Koradi through open tender | 0 | - | 0 | 4.01 | 4.01 | 0 | 0 | 0 |  |  | 0 | 0
11.3 | Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi through OEM. | 0 | - | 0 | 14.57 | 14.57 | 0 | 0 | 0 |  |  | 0 | 0
11.4 | Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi through OEM | 0 | - | 0 | 6.14 | 6.14 | 0 | 0 | 0 |  |  | 0 | 0
12 | Improvement in Boiler performance-II at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.1 | Scheme1:Procurement of Coal compartment assembly for Unit8 at 3x660MW KTPS, Koradi | 0 | - | 0 | 12.7 | 12.7 | 0 | 0 | 0 |  |  | 0 | 0
12.2 | Scheme2:Procurement of blade sets for ID, FD & PA Fan at 3x660 MW, Units at KTPS Koradi through OEM. | 0 | - | 0 | 11.34 | 11.34 | 0 | 0 | 0 |  |  | 0 | 0
12.3 | Scheme3:Procurement of RAPH internal Spares for 3X660MW units at KTPS Koradi through OEM (Qty- 6 Sets) | 0 | - | 0 | 1.13 | 1.13 | 0 | 0 | 0 |  |  | 0 | 0
12.4 | Scheme4:Procurement of RAPH Sector plate with Actuating mechanism assembly for Unit9 3 X 660MW Units at KTPS, Koradi. | 0 | - | 0 | 7.2 | 7.2 | 0 | 0 | 0 |  |  | 0 | 0
13 | Improvement in Coal Mill performance-II at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | Procurement of FLENDER make Gearbox model kmp-450 along with motor for coal mill MVM32R at 3x660mw KTPS, koradi through OEM. | 0 | - | 0 | 20.91 | 20.91 | 0 | 0 | 0 |  |  | 0 | 0
13.2 | Procurement of complete set of couplings for PA, ID & FD fans at 3X660MW units at KTPS Koradi through OEM | 0 | - | 0 | 5.14 | 5.14 | 0 | 0 | 0 |  |  | 0 | 0
14 | Improvement in Coal Mill performance-III at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 6.15 | 6.15 | 0 | 0 | 0 |  |  | 0 | 0
14.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 14.57 | 14.57 | 0 | 0 | 0 |  |  | 0 | 0
14.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 6.14 | 6.14 | 0 | 0 | 0 |  |  | 0 | 0
14.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit10 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
14.5 | Scheme5:Procurement of Complete MRHS System along with Pneumatic Compressors at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
15 | Improvement in Boiler performance-III at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | Scheme1:Procurement of Coal compartment assembly for Unit8at 3x660MW KTPS, Koradi | 0 | - | 0 | 12.7 | 12.7 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Scheme2:Procurement of blade sets for ID, FD & PA Fan at 3x660 MW, Units at KTPS Koradi through OEM. | 0 | - | 0 | 11.34 | 11.34 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Scheme3:Procurement and replacement of heating elements for RAPH installed in Unit 9 (660MW) at KTPS Koradi THROUGH OEM/OES (Qty- 2 Sets) | 0 | - | 0 | 16 | 16 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Scheme4:Procurement of HP valves, safety valves and ERV's for 3X660MW units at KTPS Koradi through OEM | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
15.5 | Scheme5:Procurement of RAPH Sector plate with Actuating mechanism assembly for Unit8 3 X 660MW Units at KTPS, Koradi. | 0 | - | 0 | 7.2 | 7.2 | 0 | 0 | 0 |  |  | 0 | 0
15 | Improvement in Coal Mill performance-IV at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 6.15 | 6.15 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 14.57 | 14.57 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 6.14 | 6.14 | 0 | 0 | 0 |  |  | 0 | 0
15.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit8 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
16 | Improvement in Coal Mill performance-V at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 6.15 | 6.15 | 0 | 0 | 0 |  |  | 0 | 0
16.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 14.57 | 14.57 | 0 | 0 | 0 |  |  | 0 | 0
16.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 6.14 | 6.14 | 0 | 0 | 0 |  |  | 0 | 0
16.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit9 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
17 | Improvement in Boiler performance-IV at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.1 | Scheme1:Procurement of Coal compartment assembly for Unit8 at 3x660MW KTPS, Koradi | 0 | - | 0 | 12.7 | 12.7 | 0 | 0 | 0 |  |  | 0 | 0
17.2 | Scheme2:Procurement of blade sets for ID, FD & PA Fan at 3x660 MW, Units at KTPS Koradi through OEM. | 0 | - | 0 | 11.34 | 11.34 | 0 | 0 | 0 |  |  | 0 | 0
17.3 | Scheme3:Procurement of RAPH bottom support bearing assembly for 3X660MW units at KTPS Koradi through OEM (Qty- 2 Sets) | 0 | - | 0 | 2.47 | 2.47 | 0 | 0 | 0 |  |  | 0 | 0
17.4 | Scheme4:Procurement of RAPH top guide bearing assembly for 3X660MW units at KTPS Koradi | 0 | - | 0 | 0.684 | 0.684 | 0 | 0 | 0 |  |  | 0 | 0
17.5 | Scheme5:Procurement of RAPH Gear Box for 3X660MW units at KTPS Koradi through OEM (Qty- 1 Sets) | 0 | - | 0 | 3.44 | 3.44 | 0 | 0 | 0 |  |  | 0 | 0
17.6 | Scheme6:Procurement of RAPH Sector plate with Actuating mechanism assembly for Unit10 at 3 X 660MW Units at KTPS, Koradi. | 0 | - | 0 | 7.2 | 7.2 | 0 | 0 | 0 |  |  | 0 | 0
17.7 | Scheme7:Procurement and replacement of heating elements for RAPH installed in Unit 10 (660MW) at KTPS Koradi THROUGH OEM/OES (Qty- 2 Sets) | 0 | - | 0 | 16 | 16 | 0 | 0 | 0 |  |  | 0 | 0
17.8 | Scheme8:Procurement of Boiler Circulating Pump (1 Nos) | 0 | - | 0 | 11.12 | 11.12 | 0 | 0 | 0 |  |  | 0 | 0
18 | Improvement in Coal Mill performance-VI at 3X660MW,KTPS,Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | Scheme1:Procurement of Roller journal Assembly set for coal mill MVM 32R at 3x660 MW Units at KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 6.15 | 6.15 |  |  | 6.15 | 0
18.2 | Scheme2:Procurement of SINTERCAST TABLE LINERS AND SINTERCAST ROLLER LINERS for coal mill MVM32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 14.57 | 14.57 |  |  | 14.57 | 0
18.3 | Scheme3:Procurement of Bearings for roller Journal Assembly & Rotary Separator for coal mill MVM 32R at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 6.14 | 6.14 |  |  | 6.14 | 0
18.4 | Scheme4:Procurement of Coal Pipe Orifice for Unit9 at 3x660 MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
19.3 | Reliability Improvement schemes of generators at 3X660MW, KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | Scheme No. 1 :PROCUREMENT OF MELCO/LMTG MAKE GENERATOR ROTOR ASSEMBLY with excitation transformer AT 3X660MW KTPS, KORADI THROUGH OEM | 0 | - | 0 | 45.39 | 45.39 | 0 | 0 | 0 |  |  | 0 | 0
19.2 | Scheme No. 2:PROCUREMENT OF ONE COMPLETE SET OF GENERATOR STATOR COILS FOR GENERATOR AT 3X660MW UNITS AT KTPS KORADI THROUGH OEM | 0 | - | 0 | 35.4 | 35.4 | 0 | 0 | 0 |  |  | 0 | 0
25 | DPR on Procurement of Critical Speares for L&T make Main Turbine(typeTC4F-30) installed at 3x660MW KTPS Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.1 | Scheme No. 1 :Procurement of Critical Speares for L&T make Main Turbine(typeTC4F-30) installed at 3x660MW KTPS Koradi. | 0 | - | 0 | 126.41 | 126.41 | 0 | 0 | 0 |  |  | 0 | 0
26 | DPR for Coal Handling Plant Performance Improvement Schemes -II at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26.1 | Scheme No. 1 : Performance Improvement of Unloading System Wagon Tipplers at CHP 3x660MW KTPS Koradi | 0 | - | 0 | 5.8 | 5.8 | 0 | 0 | 0 |  |  | 0 | 0
26.2 | Scheme No. 2 : Performance Improvement of Unloading System Side Arm Chargers at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Side Arm Charger Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 2.8 | 2.8 | 0 | 0 | 0 |  |  | 0 | 0
26.3 | Scheme No. 3 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 3.2 | 3.2 | 0 | 0 | 0 |  |  | 0 | 0
26.4 | Scheme No. 4 : Performance Improvement of Stacking & Reclaiming System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Stacking & Reclaiming System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 6.5 | 6.5 | 0 | 0 | 0 |  |  | 0 | 0
26.5 | Scheme No. 5 : Performance Improvement of Crushing System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Impact Crusher & Wobbler Feeders Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 8.5 | 8.5 | 0 | 0 | 0 |  |  | 0 | 0
26.6 | Scheme No. 6 : Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -1 at CHP 3x660MW KTPS Koradi A) Brief scope of work: Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -1 at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
27 | DPR for Coal Handling Plant Performance Improvement Schemes -III at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27.1 | Scheme No. 1 : Performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Hydraulic system for Wagon Tippler, Side Arm Charger , Apron Feeder ( 1 & 2) Stacker Reclaimer 1 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 10.5 | 10.5 | 0 | 0 | 0 |  |  | 0 | 0
27.2 | Scheme No. 2 : Construction of Air tight Hydraulic power pack room along with necessary cooling system for performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Construction of Air tight Hydraulic power pack room along with necessary cooling system for Wagon Tippler & Apron Feeder ( 1 to 4) Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 3.2 | 3.2 | 0 | 0 | 0 |  |  | 0 | 0
27.3 | Scheme No. 3 : Performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory Hydraulic Power Cylinders of Wagon Tippler, Side Arm Charger ( 1 to 4) Stacker Reclaimer 1 & 2 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
27.4 | Scheme No. 4 : Performance Improvement of Stacker Reclaimer by providing Hydraulic Drive to Boom Conveyor at CHP 3x660MW KTPS Koradi A) Brief scope of work: Hydraulic Drive to Boom Conveyor Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.9 | 0.9 | 0 | 0 | 0 |  |  | 0 | 0
27.5 | Scheme No. 5 : Performance Improvement of Illumination system with energy conservation at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Solar High masts along the rail track in railway yard Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 3.75 | 3.75 | 0 | 0 | 0 |  |  | 0 | 0
27.6 | Scheme No. 6 : Design, Supply & Installation of LT VFD Drives for Critical Conveyors at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of LT VFD Drives for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
27.7 | Scheme No. 7 : Design , supply, Erection & Commissioning of Short Conveyor for Stacking Purpose at CHP 3x660MW KTPS Koradi A) Brief scope of work: Short Conveyor for Stacking Purpose at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 9.6 | 9.6 | 0 | 0 | 0 |  |  | 0 | 0
27.8 | Scheme No. 8 : Capacity Enhancement of BCN-7/5/4/3 /1 AB in CHP 3x660MW KTPS Koradi A) Brief scope of work: Short Conveyor for Stacking Purpose at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 8.6 | 8.6 | 0 | 0 | 0 |  |  | 0 | 0
27.9 | Scheme No. 9 : Design , Engineering & modification along with strengthening of Existing Travel Track structure for Side Arm Charger & Stacker Reclaimer A) Brief scope of work: strengthening of Existing Travel Track structure for Side Arm Charger & Stacker Reclaimer Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
27.1 | Scheme No. 10 : Design , Engineering & Erection of modified Energy Efficient Ventilation System for Wagon Tippler Complex Area in CHP 3X660MW KTPS Koradi A) Brief scope of work: Energy Efficient Ventilation System for Wagon Tippler Complex Area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
27.11 | Scheme No. 11 : Design , Engineering & Installtion of Vibration & temprature Monitoring Systems for critical auxiliaries in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Installtion of Vibration & temprature Monitoring Systems for critical auxiliaries Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
27.12 | Scheme No. 12 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
27.13 | Scheme No. 13 : Design , Engineering & Provision of Stone Grappling Equipment System for Wagon Tippler 3 &4 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Stone Grappling Equipment System for Wagon Tippler 3 &4 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.9 | 0.9 | 0 | 0 | 0 |  |  | 0 | 0
27.14 | Scheme No. 14 : Design , Engineering & Provision of Public Addressing System for Wagon Tippler Complex in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Public Addressing System for Wagon Tippler Complex in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
27.15 | Scheme No. 15 : Design , Engineering & Provision of Belt Tracking System for Critical Conveyors in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Belt Tracking System for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
27.16 | Scheme No. 16 : Design , Engineering & Provision of Dust supression System for stacker reclaimer-1 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.6 | 0.6 | 0 | 0 | 0 |  |  | 0 | 0
27.17 | Scheme No. 17 : Work of Life Enhancement of wobbler Feeder 1 &2 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.6 | 1.6 | 0 | 0 | 0 |  |  | 0 | 0
28 | DPR for Coal Handling Plant Performance Improvement Schemes -IV at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28.1 | Scheme No.1 : Design , Engineering , Supply & Installation of Modular Transfer chutes for Critical Conveyor System in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of Modular Transfer chutes for Conveyor System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 14 | 14 | 0 | 0 | 0 |  |  | 0 | 0
28.2 | Scheme No.2 :Upgradtion of Exsisting Fire Fighting System at Stack yard area in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradtion of Exsisting Fire Fighting System at Stack yard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 2.6 | 2.6 | 0 | 0 | 0 |  |  | 0 | 0
28.3 | Scheme No.3 : Design , Engineering , Supply & Strengthening of engineering structure of BCN- 7A/B along with track alignment in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Strengthening of engineering structure of BCN- 7A/B Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 2.4 | 2.4 | 0 | 0 | 0 |  |  | 0 | 0
28.4 | Scheme No.4 : Design , Engineering , Supply & Installation of Mist Cannon Spray System around stackyard area in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of Mist Cannon Spray System at stackyard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.6 | 1.6 | 0 | 0 | 0 |  |  | 0 | 0
28.5 | Scheme No.5 : Design , Engineering , Supply & Installation of EOT cranes at Bunker in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of EOT cranes at Bunker Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 4.5 | 4.5 | 0 | 0 | 0 |  |  | 0 | 0
29 | DPR for Procurment of various Heavy Vehicles at CHP 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29.1 | Scheme No.1 : Procurment of Heavy Vehicles like dozers, wheel loaders , locomotives, Crane, Hydra , Disel Browser , Jcb & Bobcats etc. in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurment of Heavy Vehicles like dozers, wheel loaders , locomotives etc Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
29.2 | Scheme No.2 : Procurment of Auger Machines for coal sampling in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurment of Auger Machines for coal sampling Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 2.2 | 2.2 | 0 | 0 | 0 |  |  | 0 | 0
29.3 | Scheme No.3 : Procurment of Truck Mounted mist cannon dust supression system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurment of Truck Mounted mist cannon dust supression system in CHP Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.8 | 0.8 | 0 | 0 | 0 |  |  | 0 | 0
30 | DPR for Coal Handling Plant Performance Improvement Schemes -V at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30.1 | Scheme No. 1 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 3.2 | 3.2 | 0 | 0 | 0 |  |  | 0 | 0
30.2 | Scheme No. 2 : Performance Improvement of Stacking & Reclaiming / Side Arm Charger System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Energy Chain System of Stacking & Reclaiming System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
30.3 | Scheme No. 3 : Performance Improvement of unloading System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Energy Chain System of side arm acharger Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
30.4 | Scheme No. 4 : Upgradation to 100 MT Ton Weighbridge of existing road weighbridge at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of LT VFD Drives for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.8 | 0.8 | 0 | 0 | 0 |  |  | 0 | 0
30.5 | Scheme No. 5 : Design , Engineering & Erection of modified Energy Efficient Ventilation System for Crusher House Area in CHP 3X660MW KTPS Koradi A) Brief scope of work: Energy Efficient Ventilation System for Wagon Tippler Complex Area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
30.6 | Scheme No. 6 : Design , supply & Installation of Cooling Arrangement for Switchgear rooms at CHP 3x660MW KTPS Koradi A) Brief scope of work: Supply & Installation of Cooling Arrangement for Switchgear rooms Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
30.7 | Scheme No. 7 : Design , Engineering & Erection of modified Engineering Structure of Tunnel Conveyor 1A &1 B in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Erection of modified Engineering Structure of Tunnel Conveyor 1A &1 B Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 2.35 | 2.35 | 0 | 0 | 0 |  |  | 0 | 0
31 | DPR for Coal Handling Plant Performance Improvement Schemes -VI at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.1 | Scheme No. 1 : Performance Improvement of Hydraulic Drive & Driven at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Wagon Tippler, Side Arm Charger , Apron Feeder ( 3 & 4) Stacker Reclaimer 2 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 11.5 | 11.5 | 0 | 0 | 0 |  |  | 0 | 0
31.2 | Scheme No. 2 : Design Supply & Installation of Wagon Locking system for all four wagon tipplers at CHP 3x660MW KTPS Koradi A) Brief scope of work: Wagon Locking system for all four wagon tipplers Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
31.3 | Scheme No. 3 : Design, Supply & Installation of upgraded Vibrating Feeders for Stacker Reclaimer at CHP 3x660MW KTPS Koradi A) Brief scope of work: Design, Supply & Installation of upgraded Vibrating Feeders for Stacker Reclaimer Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.9 | 0.9 | 0 | 0 | 0 |  |  | 0 | 0
31.4 | Scheme No. 4: Performance Improvement of Stacker Reclaimer by providing Hydraulic Drive to Boom Conveyor at CHP 3x660MW KTPS Koradi A) Brief scope of work: Hydraulic Drive to Boom Conveyor Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.9 | 0.9 | 0 | 0 | 0 |  |  | 0 | 0
31.5 | Scheme No. 5 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
31.6 | Scheme No. 6 : Design , Engineering & Provision of Belt Tracking System for Critical Conveyors in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Belt Tracking System for Critical Conveyors Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.6 | 1.6 | 0 | 0 | 0 |  |  | 0 | 0
31.7 | Scheme No. 7 : Design , Engineering & Provision of Dust supression System for stacker reclaimer-1 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.6 | 0.6 | 0 | 0 | 0 |  |  | 0 | 0
31.8 | Scheme No. 8 : Work of Life Enhancement of wobbler Feeder 3 &4 in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Dust supression System for stacker reclaimer in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.6 | 1.6 | 0 | 0 | 0 |  |  | 0 | 0
32 | DPR for Coal Handling Plant Performance Improvement Schemes -VII at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32.1 | Scheme No.1 : Design , Engineering , Supply & Installation of Modular Transfer chutes for Crusher House Complex & other Critical Conveyor System in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of Modular Transfer chutes for Conveyor System Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 13 | 13 | 0 | 0 | 0 |  |  | 0 | 0
32.2 | Scheme No.2 :Upgradtion of Exsisting Fire Fighting System along the conveyor length in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradtion of Exsisting Fire Fighting System at Stack yard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 3.2 | 3.2 | 0 | 0 | 0 |  |  | 0 | 0
32.3 | Scheme No.3 : Supply , Erection & Installation of Rack & Pinion Elevators at Bunker in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Supply , Erection & Installation of Rack & Pinion Elevators at Bunker in CHP 3X660MW KTPS Koradi. Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.8 | 0.8 | 0 | 0 | 0 |  |  | 0 | 0
32.4 | Scheme No.4 :Up Liftment f Exsisting Fire Fighting lines in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradtion of Exsisting Fire Fighting System at Stack yard area Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 3.2 | 3.2 | 0 | 0 | 0 |  |  | 0 | 0
32.5 | Scheme No.5 : Procurement of HPPE Polymer Roller for Conveyor system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurement of HPPE Polymer Roller for Conveyor system Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.8 | 0.8 | 0 | 0 | 0 |  |  | 0 | 0
32.6 | Scheme No.6 : Design , Engineering , Supply & Installation of EOT cranes at Wagon Tippler Complex in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Design , Engineering , Supply & Installation of EOT cranes at Wagon Tippler Complex Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 6.2 | 6.2 | 0 | 0 | 0 |  |  | 0 | 0
33 | DPR for Coal Handling Plant Performance Improvement Schemes -VIII at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33.1 | Scheme No. 1 : Performance Improvement of Unloading System Wagon Tipplers at CHP 3x660MW KTPS Koradi Estimated Cost : 3.6 Cr. | 0 | - | 0 | 3.6 | 3.6 | 0 | 0 | 0 |  |  | 0 | 0
33.2 | Scheme No. 2 : Performance Improvement of Unloading System Side Arm Chargers at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Side Arm Charger Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 2.8 | 2.8 | 0 | 0 | 0 |  |  | 0 | 0
33.3 | Scheme No. 3 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 3.4 | 3.4 | 0 | 0 | 0 |  |  | 0 | 0
33.4 | Scheme No. 4 : Performance Improvement of Stacking & Reclaiming System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Stacking & Reclaiming System -2 Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 3.5 | 3.5 | 0 | 0 | 0 |  |  | 0 | 0
33.5 | Scheme No. 5 : Performance Improvement of Crushing System at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of Impact Crusher & Wobbler Feeders Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 8.5 | 8.5 | 0 | 0 | 0 |  |  | 0 | 0
33.6 | Scheme No. 6 : Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -2 at CHP 3x660MW KTPS Koradi A) Brief scope of work: Design , supply & Installation of Auto Lubrication system for Travel drive & Slew Drive of Stacker Reclaimer -2 at CHP 3x660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
33.7 | Scheme No. 7 : Other Mislenious Schemes at CHP 3x660MW KTPS Koradi A) Brief scope of work: Other Mislenious works Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
33.8 | Scheme No. 4 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.8 | 0.8 | 0 | 0 | 0 |  |  | 0 | 0
33.9 | Scheme No.8: Procurement of HPPE Polymer Roller for Conveyor system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurement of HPPE Polymer Roller for Conveyor system Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.8 | 0.8 | 0 | 0 | 0 |  |  | 0 | 0
34 | DPR for Coal Handling Plant Performance Improvement Schemes -IX at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.1 | Scheme No. 1 : Performance Improvement of Unloading System Apron Feeders at CHP 3x660MW KTPS Koradi A) Brief scope of work: Procurement & Replacement of mandatory internals of unloading system Apron Feeder Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 3.6 | 3.6 | 0 | 0 | 0 |  |  | 0 | 0
34.2 | Scheme No. 2 : Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi A) Brief scope of work: Design , Engineering & Provision of Ceramic Lagging to conveyor pulleys I in CHP 3X660MW KTPS Koradi Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
34.3 | Scheme No.3 : Upgradation of Exsisting Rack & Pinion Elevators at CHP 3X660MW KTPS Koradi. A) Brief scope of work: Upgradation of Exsisting Rack & Pinion Elevators Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 1.6 | 1.6 | 0 | 0 | 0 |  |  | 0 | 0
34.4 | Scheme No.4 : Procurement of HPPE Polymer Roller for Conveyor system in CHP 3X660MW KTPS Koradi. A) Brief scope of work: Procurement of HPPE Polymer Roller for Conveyor system Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 0.8 | 0.8 | 0 | 0 | 0 |  |  | 0 | 0
34.5 | Scheme No.5 : Other miscellaneous scheme regarding sustainable performance improvement of CHP 3X660MW KTPS Koradi. A) Brief scope of work: ther miscellaneous scheme regarding sustainable performance improvement Justification 1. Increase in useful life of entire project/scheme/assets 2. Renovation and Modernisation for life extension of entire project. | 0 | - | 0 | 18 | 18 | 0 | 0 | 0 |  |  | 0 | 0
35 | Design & engineering, procurement, supply, installation & commissioning of Ozone Generator system of capacity 45.0 Kg/hr for CW system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Scheme1:Design & engineering, procurement, supply, installation & commissioning of Ozone Generator system of capacity 45.0 Kg/hr for CW system | 0 | - | 0 | 45 | 45 | 0 | 0 | 0 |  |  | 0 | 0
36 | Pipeline expansion to improve dry ash evacuation system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
36.1 | Scheme1: Pipeline expansion to improve dry ash evacuation system along with target box modification and also to erect & commission dry ash evacuation directly to remote silo. | 0 | - | 0 | 75 | 75 | 0 | 0 | 0 |  |  | 0 | 0
37 | Modification at intermediate silo and HCSD system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
37.1 | Scheme1: Additional charge pump. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
37.2 | Scheme 2: Supply & Installation Air washery at silo top. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
37.3 | Scheme 3: Shed above silo top. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
37.4 | Scheme 4: Supply & Installation Construction of platform at pipe rack up to Remote silo. | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
37.5 | Scheme 5: Shifting of pipeline above pipe rack. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
37.6 | Scheme 6: Supply & Installation ART sub assemblies. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
38 | ESP field strengthening at U#8 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
38.1 | Scheme1: ESP field strengthening at U#8 | 0 | - | 0 | 120 | 120 | 0 | 0 | 0 |  |  | 0 | 0
39 | Procurement of various pumps for AHP performance improvement | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
39.1 | Scheme1: Procurement of various pumps for AHP performance improvement. | 0 | - | 0 | 28 | 28 | 0 | 0 | 0 |  |  | 0 | 0
40 | Modification in Dry Ash Evacuation System D/V Assemblies & allied equipments to improve performance | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
40.1 | Scheme1: Procurement of D/V Assemblies & allied equipments to improve performance. | 0 | - | 0 | 35 | 35 | 0 | 0 | 0 |  |  | 0 | 0
41 | Additional IAC house for Intermediate silo and Remote silo along with erection of S.S. Pipeline | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
41.1 | Scheme1: Supply & Installation Additional IAC house for Intermediate silo and Remote silo along with erection of S.S. Pipeline | 0 | - | 0 | 50 | 50 | 0 | 0 | 0 |  |  | 0 | 0
42 | Waste water system modification to have zero water discharge | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
42.1 | Scheme1: Waste water system modification to have zero water discharge at 3x660MW, KTPS, Koradi along with Pump Procurement along with arrangement of sludge discharge at ESP water Washing system. | 0 | - | 0 | 26 | 26 | 0 | 0 | 0 |  |  | 0 | 0
43 | ESP field strengthening at U#9 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
43.1 | Scheme1: ESP field strengthening at U#9 | 0 | - | 0 | 275 | 275 | 0 | 0 | 0 |  |  | 0 | 0
44 | Procurement of HCSD GEHO Pump (TZPM-400) critical items sub-assemblies | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
44.1 | Scheme1: Procurement of HCSD GEHO Pump TZPM-400) critical items sub-assemblies. | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
45 | MSERW Pipes & Seamless Pipes replacement to improve ash conveying & its disposal-1 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.1 | Scheme1: Supply & Work of Replacement of MSERW Pipes & Seamless Pipes in Bottom ash/Coarse ash evacuation & Ash Slurry Disposal Pipelines, Dry ash conveying system in phase manner to improve the ash evacuation performance. | 0 | - | 0 | 70 | 70 | 0 | 0 | 0 |  |  | 0 | 0
46 | Improvement in Ash Water Recovery System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.1 | Scheme1: Supply & Installation of Pumps along with Pipeline for Improvement in Ash Water Recovery System. | 0 | - | 0 | 35 | 35 | 0 | 0 | 0 |  |  | 0 | 0
47 | Replacement of Instrument air pipeline from M.S. to S.S for AHP main plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.1 | Scheme1: Replacement of Instrument air pipeline from M.S. to S.S for AHP main plant | 0 | - | 0 | 40 | 40 | 0 | 0 | 0 |  |  | 0 | 0
48 | Modification of sludge pumps and its pipeline with pumps of higher capacity and discharge line of higher capacity. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
48.1 | Scheme1: Modification of sludge pumps and its pipeline with pumps of higher capacity and discharge line of higher capacity. | 0 | - | 0 | 50 | 50 | 0 | 0 | 0 |  |  | 0 | 0
49 | ESP field strengthening at U#10 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
49.1 | Scheme1: ESP field strengthening at U#10 | 0 | - | 0 | 310 | 310 | 0 | 0 | 0 |  |  | 0 | 0
50 | MSERW Pipes & Seamless Pipes replacement to improve ash conveying & its disposal-2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50.1 | Scheme1: Supply & Work of Replacement of MSERW Pipes & Seamless Pipes in Bottom ash/Coarse ash evacuation & Ash Slurry Disposal Pipelines, Dry ash conveying system in phase manner to improve the ash evacuation performance. | 0 | - | 0 | 90 | 90 | 0 | 0 | 0 |  |  | 0 | 0
51 | Replacement of IAC for AHP Main Plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
51.1 | Scheme1: Supply & Installation of IAC for AHP Main Plant | 0 | - | 0 | 0 | 0 | 0 | 60 | 60 |  |  | 60 | 0
52 | Improvement in DRY ASH Evacuation system-2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
52.1 | Scheme1: Supply & Installation of TAC, Replacement of Air Lock Vessel, Various Valves, ESP Hopper Doors, ESP access doors. | 0 | - | 0 | 40 | 40 | 0 | 0 | 0 |  |  | 0 | 0
53 | Improvement in DRY ASH Evacuation system-3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
53.1 | Scheme1: Procurement of Ingersoll Rand Make Transport Air Compressors Critical/Non-Critical Spares sub-assembly for performance improvement. | 0 | - | 0 | 0 | 0 | 0 | 35 | 35 |  |  | 35 | 0
54 | Detailed project report for various works of security section as per the IB recommendations. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
54.1 | Repairing & raising height of compound wall with provision of concertina coil at various location of peripheral compound wall at 3x660MW KTPS Koradi. | 0 | - | 0 | 1.593 | 1.593 | 0 | 0 | 0 |  |  | 0 | 0
54.2 | Work of Providing structural three quarter turn staircase with landing along pheriphery of FISS watch tower at 3x660MW, TPS, Koradi. | 0 | - | 0 | 0.34444 | 0.34444 | 0 | 0 | 0 |  |  | 0 | 0
55 | Supply, installation, comissioning and testing of 220V station & 360V UPS batteries installed at U 8, 9 & 0 of 3x660 MW KTPS, Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
55.1 | Supply, installation, comissioning and testing of 220V station & 360V UPS batteries installed at U 8, 9 & 0 of 3x660 MW KTPS, Koradi. (scheme) | 0 | - | 0 | 68.4 | 68.4 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
56 | TDBFP Governing valve's LPCV ,HPCV MSV AND Trip lock replacement | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
61 | Procurement & replacement of HP Heaters at 3x660 MW KTPS, Koradi. | 0 | - | 0 | 0 | 25 | -25 | 0 | 0 |  |  | 0 | -25
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Vibration Monitoring & Analysis system installed at 3x660MW Koradi TPS. | 0 | - | 0 | 63 | 63 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of sinkawa make vibration monitoring and Analysis system for main turbine at 3x660MW koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of Bently Nevada make vibration monitoring and Analysis system for RMCMS system at 3x660MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3 :-Emerson PLC upgradation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of various Level Transmitters installed at 3x660 MW koradi TPS. | 0 | - | 0 | 31 | 31 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of Guided wave Radar Level TX installed at Condenser Hotwell and LPH 1,2 and 3 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of Displacer type level TX into Guided wave radar level Tx installed at various Drain Tank, Flash tank and pit | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3: Upgradation of non- contact type Ultrasonic level Tx into IP68 non- contact type Radar level TX. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of ESP Hopper level Probes installed at 3x660 MW koradi TPS. | 0 | - | 0 | 40 | 40 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of 1st three fields ESP Hopper level probes into continuous level monitoring NOGS system at 3x660 MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of RF capacitance Hopper level probe into of RF admittance level probe at 4,5,6,7,8 & 9 ESP Hoppers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3: Upgradation of ESP hopper heater monitoring , control and real time monitoring system at 3X660MW Koradi TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of various scheme viz ASLD, Furnace tv camera FEGT and acoustic Pyrometer installed at 3x660 MW koradi TPS. | 0 | - | 0 | 61 | 61 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of ASLD system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of Furnace TV Camera | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3:Upgradation of FEGT system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 4:Upgradation of acoustic pyrometer | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of various scheme viz instrument Air pipe at ESP Area, wet Ash Evacuation system, HCSD Silo. | 0 | - | 0 | 26 | 26 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of instrument Air pipeline system at ESP of M.S into SS installed at 3x660 MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 2: Upgradation of instrument Air pipeline system at wet Ash system of M.S into SS . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3: Upgradation of instrument Air pipeline system at HCSD silo of M.S. into SS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 4: Upgradation of instrument Air pipeline system at Remote Silo of M.S into SS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 5: Upgradation of Control & Instrument section lab with Hydraulic Servo Valve Test, Pneumatic System test and calibration lab set up. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Flame scanner for flexible operation of 3X660MW Koradi TPS. | 0 | - | 0 | 35 | 35 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 1: Upgradation of Flame scanner for flexible operation of 3X660MW Koradi TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of DRC Pipes, Bends & Fittings in phase manner to improve the dry ash conveying & its disposal (2 years) | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of DRC Pipes, Bends & Fittings in phase manner to improve the dry ash conveying & its disposal (2 years) (Rs.30 Cr.) (Bottom ash/Coarse ash evacuation & Ash Slurry Disposal Pipelines, Dry ash conveying system) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Augmentation of Coarse Ash disposal system at U10 at KTPS, Koradi | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | WORK OF INSTALLATION & COMMISSIONING OF ASH DISPOSAL SYSTEM AT UNIT#10 | 0 | - | 0 | 0 | 82.01 | -82.01 | 0 | 0 |  |  | 0 | -82.01
0 | IDC | 0 | - | 0 | 0 | 2.93 | -2.93 | 0 | 0 |  |  | 0 | -2.93
0 | DPR for Railway Track Siding Performance Improvement Schemes at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 1 : Work of complete track renovation of existing Rail yard of CHP, 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. Due to continuous movement of Railway's precious rolling stock, the track spares are worn out and are due for complete replacement. Hence, to maintain rail track parameters in healthy condition as per Railway norms so as to avoid untoward incidences of derailment the execution of work of complete track renewal is essential. | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 2 : Scheme Name- Work of laying of additional track at 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. However, as per the existing infrastructure, at present there is no dedicated empty formation line. Due to non-availability of empty formation line, most often unloading gets hampered due to blocking of outhaul line by empty rake. The hampering in unloading affects the plant performance and incurrs unnecessary financial burden on KTPS account under the head of demurrage charges. Hence, to maintain the plant loadability and availability, it is essential to lay additional track at 3x660MW, KTPS, Koradi. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 3 : Scheme Name- Work of rectification and upgradtion of existing SSP at CHP, 3x660MW, KTPS, Koradi. Justification- The SSP has been erected at 3x660MW, KTPS, Koradi. However, till date the same has not been commissioned. With lapse of @ 5-6 years after erection and its non commissioning, the existing SSP set up has been completely detoriorated. Now, Railway's is pressing hard for early commissioning of the same. The said set up shall ensure isolation of OHE of existing yard with Railway's main line. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 4 : Scheme Name- Work of construction of apron RCC platforms at inhaul and outhaul of Wagon tipllers 1, 2, 3 & 4 of CHP 3x660MW, KTPS, Koradi. Justification- The 04 Nos. of wagon tipplers are installed at CHP-3x660MW, KTPS, Koradi. In this regards, it is to submit that, the wagon unloading is being carried out through these tipplers. Hence, presence of fugitive dust in tippler area is predominant. The said dust is being accumulated at inhaul and outhaul of wagon tipplers. Due to presence of loaded wagons at inhaul and empty wagons at outhaul, this office gets least opportunity for clearance of the said coal dust along the track. Due to accumulation of coal dust, the rail track parameters along with gradient are getting distubed. The disturbance in gradient is causing rolling of wagons which is not recommended in view of safety of both man and machine. Besides, this due to rolling of wagons, the occurnece of untoward incidence of derailment is predominant. Hence, to maintain uniform rail track gradient it shall be enviable to construct the apron RCC platforms at inhaul and outhaul of Wagon tipplers 1, 2, 3 & 4 of CHP-3x660MW, KTPS, Koradi. Estimated cost- Rs. 4 Cr. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 5 : Scheme Name- Work of construction of apron RCC platforms at inhaul and outhaul of Wagon tipllers 1, 2, 3 & 4 of CHP 3x660MW, KTPS, Koradi. Justification- The 04 Nos. of wagon tipplers are installed at CHP-3x660MW, KTPS, Koradi. In this regards, it is to submit that, the wagon unloading is being carried out through these tipplers. Hence, presence of fugitive dust in tippler area is predominant. The said dust is being accumulated at inhaul and outhaul of wagon tipplers. Due to presence of loaded wagons at inhaul and empty wagons at outhaul, this office gets least opportunity for clearance of the said coal dust along the track. Due to accumulation of coal dust, the rail track parameters along with gradient are getting distubed. The disturbance in gradient is causing rolling of wagons which is not recommended in view of safety of both man and machine. Besides, this due to rolling of wagons, the occurnece of untoward incidence of derailment is predominant. Hence, to maintain uniform rail track gradient it shall be enviable to construct the apron RCC platforms at inhaul and outhaul of Wagon tipplers 1, 2, 3 & 4 of CHP-3x660MW, KTPS, Koradi. Estimated cost- Rs. 4 Cr. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 6 : Scheme Name- Work of construction of RCC platforms along the rail track of CHP 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. In this regards, it is to submit that, after unloading of rakes the empty rakes are being examined by Railway's C&W staff camped at KTPS, Koradi. Hence, for safe movement of Railway's staff, Railway's is pressing hard for provision of RCC platforms along the rail track of CHP-3x660MW, KTPS, Koradi. Estimated cost- Rs. 10 Cr. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 7 : Scheme Name- Work of repairing and construction of RCC permanent revenue canal at, KTPS, Koradi. Justification- The temporary revenue canal is being flowing beside the existing Railway exchange yard of 210 MW, KTPS, Koradi. The said canal gets clogged inview of ash accumulation. Due to clogging this canal overflows and its overrun enters the 210 MW rail yard thereby creating track surface marshy and unsafe for Rail movement. Hence, it is essential to repair and construct RCC permanent revenue canal at KTPS, Koradi so that proper and timely cleaning of canal along with proper outlet can be arranged. Estimated cost- Rs. 15 Cr. | 0 | - | 0 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme Name-08 Work of construction of RCCretaining wall at Godhani and Kalumna end of KTPS, Koradi. Justification- The separate rail infrastructure has been commissioned for Koradi TPS to cope up the daily coal requirement. The rail traffic at KTPS, Koradi is being catered through Godhani and Kalumna end respectively. In this regards, it is to submit that, the take off points at Godhani and Kalumna both are S&T operated. During monsoon, it is often witnessed that, the rain water enters the plant premises from others land thereby submerging the S&T operated point. Due to this, signals gets lost and hampers the Rail traffic movement completely. Hence, it is essential to restrict the entrance of rain water in plant premises. This can be possible by constructing retaining wall at required loaction. Estimated cost- Rs. 1 Cr. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme Name-09 OHE maintenance at CHP, KTPS, Koradi Justification-As per the Railway board circular, Railway's has mandated that OHE maintenance cost for existing as well as new sidings shall be borne by the siding owner in accordance with Railway guidelines. Railway will carry out necessary inspection of maintenance work once in six months. Maintenance charges per TKM per annum of OHE as finalized by SECR zonal office is Rs.291566/- per TKM per annum. Also, inspection charges at the rate of Rs.106974/- per day towards inspection to be carried out by Railways every si x months shall be charged on actual basis by Railway's from the sidings.Accordingly, Railway.s has calimed amount of Rs.31314519/- for two years. Hence for 5 yeards it is expected to be Rs.7.82 Cr. Estimated cost- Rs. 7.82 Cr. | 0 | - | 0 | 7.82 | 7.82 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 10 Name-Remodelling and upgradation of existing S & T system with Panel Interlocking system and associated S & T gears to S & T system with Electronic Interlocking system and associated S & T gears in connection with services for BG Railway facility (660 MW Rail yard) for Koradi Thermal Power Station of MSPGCL Justification-As per the prevailing Railway norms, it is mandatory to commission the S & T system in private Railway siding for fast and safe movement of Railway’s precious rolling stock. Unless and until remodeling is carried out the S&T system cannot be started at Koradi Railway yard.With commissioning and operation of S & T system there shall be least possibility for derailments during internal shunting through crossovers, as the said points shall be motorized operated. Estimated cost- Rs. 20 Cr. | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 11 : Work of supply and provision of lights and high mast at CHP Railway exchange yard of 3x660MW, KTPS, Koradi. Justification- The existing rail track of 3 x 660MW rail yard has been commissioned in 2015 and since then continuous movement of @ 8-10 rakes loaded and empty on daily basis is being taking placed. In this regards, it is to submit that, after unloading of rakes the empty rakes are being examined by Railway's C&W staff camped at KTPS, Koradi on round the clock basis. Hence, for safe movement of Railway's staff, Railway's is pressing hard for availability of proper illumination in complete yard. Estimated cost- Rs.2.5 Cr. | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Provision of cover shed for stack yard -2 at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 1 : Provision of cover shed for stack yard -2 at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 135 | -135 | 0 | 0 |  |  | 0 | -135
0 | DPR for Procurement of Pipe Conveyor Drive System Internals at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 1 : Procurement of Pipe Conveyor Drive System Internals at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 27 | -27 | 0 | 0 |  |  | 0 | -27
0 | DPR for Provision of service building along with vehicle bay at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme No. 1 : Provision of service building along with vehicle bay at 3x660MW KTPS ,Koradi. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | GENERAL ASSET | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | GENERAL ASSET--AKRDFOGA01-OFFICE FURNITURE | N.A. | - | 0 | 0.57299 | 0.75759 | -0.1846 | 0 | 0 |  |  | 0 | -0.1846
2 | GENERAL ASSET--AKRDFOGA02-COMPUTERS,PRINTER,SCANNER | N.A. | - | 0 | 1.6504 | 2.911 | -1.2606 | 0 | 0 |  |  | 0 | -1.2606
3 | GENERAL ASSET--AKRDFOGA03-AC,WATER COOLER | N.A. | - | 0 | 0.46584 | 0.49898 | -0.033135 | 0 | 0 |  |  | 0 | -0.033135
4 | GENERAL ASSET--AKRDFOGA04-AIR PURIFIER | N.A. | - | 0 | 0 | 0.0105 | -0.0105 | 0 | 0 |  |  | 0 | -0.0105
0 | D) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of KLEP Unit for 'HCSD Pump | 0 | - | 3.73 | 3.73 | 3.73 | 0 | 0 | 0 |  |  | 0 | 0
2 | Restoration of Boiler Circulation Pump at 3X660MW KTPS, Koradi | 0 | - | 0 | 4.73 | 4.73 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of Coal Compartment Assemblies for Unit-10 at 3x660MW KTPS, Koradi. | 0 | - | 0 | 3.73 | 3.73 | 0 | 0 | 0 |  |  | 0 | 0
4 | Repairing and Refurbishment of TDBFP cartridge Model FK6E40 installed at 3X660MW KTPS, Koradi | 0 | - | 0 | 11.86 | 11.86 | 0 | 0 | 0 |  |  | 0 | 0
5 | Non-DPR for Upgradation of Honeywell Make PLC for Mill Reject Handling System installed at 3x660MW Balance of Plant (BOP) Unit- 8, 9 & 10 at Koradi TPS | 0 | - | 0 | 0.85 | 0.85 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of Sky Climber for furnace repairing at 3x660MW KTPS, Koradi | 0 | - | 0 | 3.02 | 3.02 | 0 | 0 | 0 |  |  | 0 | 0
7 | Double Roll Clinker Grinder | 0 | - | 0 | 1.68 | 1.68 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement along with Installation of Clear Water Booster Pump with Motor, Panel Cable and other allied accessories in Unit#10 bottom ash area at AHP, 3x660MW, KTPS, Koradi. | N.A. | - | 0 | 2.8112 | 2.56 | 0.25116 | 0 | 0 |  |  | 0 | 0.25116
9 | Procurement of single Roll Clinker Grinder with Feed Pump & Jet Pump Complete Assembly with modified metallurgy installed at AHP ,3x660MW Units, KTPs, Koradi | N.A. | - | 0 | 3.2868 | 2.12 | 1.1668 | 0 | 0 |  |  | 0 | 1.1668
10 | Work of Repairing and Refurbishment of HIP Rotor along with balancing and over speed trial for L&T-MHI make turbine (Type: TC4F-30”) installed at 3X660MW KTPS, Koradi | N.A. | - | 0 | 7.3532 | 7.13 | 0.22316 | 0 | 0 |  |  | 0 | 0.22316
11 | Procurement of spares for Flue gas distribution dampers, PA fan discharge dampers and Coal mill Hot PA Gate and Dampers at 3x660mw KTPS units through OEM | N.A. | - | 0 | 3.7 | 3.7 | 0 | 0 | 0 |  |  | 0 | 0
12 | Work of Modification & Installation of Take up trolley & arrangement for take up lifting for conveyor BCN-13A at CHP 3X660MW,KTPS,Koradi | N.A. | - | 0 | 356.6331 | 0.75 | 355.8831 | 0 | 0 |  |  | 0 | 355.8831
13 | Work of Design, Modification & streingthening of Tripper trolley structure with provision of Antiwear plates discharge chute box at CHP 3X660MW,KTPS,Koradi | N.A. | - | 0 | 1.16 | 1.16 | 0 | 0 | 0 |  |  | 0 | 0
14 | Upgradation of Management Information System (MIS) Server and Associated Software for C&I at 3x660MW Unit- 8, 9 & 10 at Koradi TPS | N.A. | - | 0 | 2.145 | 2.145 | 0 | 0 | 0 |  |  | 0 | 0
15 | Procurement of Vibrating Tranfer chute with double exciter Drive for stacker reclaimer at CHP,3X660MW,KTPS ,Koradi | N.A. | - | 0 | 0.934 | 0.934 | 0 | 0 | 0 |  |  | 0 | 0
16 | Supply & Installation of Ash Slurry Density Transmitter at High Concentrated Slurry Disposal (HCSD) System of BOP area of 3x660MW Unit- 8, 9 & 10 at Koradi TPS | N.A. | - | 0 | 1.26 | 1.26 | 0 | 0 | 0 |  |  | 0 | 0
17 | Supply & Installation of Fiber Optic Sensing System for Conveyor Health Monitoring At CHP 3x660MW KTPS, Koradi | 0 | - | 0 | 11.72 | 11.72 | 0 | 0 | 0 |  |  | 0 | 0
18 | Procurement of Leak- proof make complete Mechanical Seal Assembly for Concrete Volute CW Pump installed at 3X660MW KTPS,Koradi on OEM bASIS. | 0 | - | 0 | 1.94 | 1.94 | 0 | 0 | 0 |  |  | 0 | 0
19 | Work of Design , Engineering , Manufacturing , Supply Erection & Commissioning of Conveyor Belt From Discharge of RBF 1 &2 at Crusher House to Stack Yard At CHP 3x660MW KTPS, Koradi . | 0 | - | 0 | 11.39 | 11.39 | 0 | 0 | 0 |  |  | 0 | 0
20 | Supply & Installation of Artificial Intelligence PMMS Accurex Diagnostic matrix based vibration & temperature monitoring for critical auxiliaries at CHP 3x660MW KTPS, Koradi. | 0 | - | 0 | 6.431 | 6.431 | 0 | 0 | 0 |  |  | 0 | 0
21 | Restoration of online dissolved gas analysers of Unit 8,9,10 | 0 | - | 0 | 1.11 | 1.11 | 0 | 0 | 0 |  |  | 0 | 0
22 | Complete Replacement of Existing Water Separator Drain Tank Control (WDC) Valves with New Valves of modified trim design along with hydraulic Actuators, Power Pack assembly, necessary instrumentation, erection & commissioning 3X660MW KTPS, Koradi. | 0 | - | 0 | 5.33 | 5.33 | 0 | 0 | 0 |  |  | 0 | 0
23 | Procurement of mandatory set of Hydraulic system internals for Wagon Tippler Drive & side arm charger Drive at CHP,3X660MW,KTPS ,Koradi | 0 | - | 0 | 6.35 | 6.35 | 0 | 0 | 0 |  |  | 0 | 0
24 | "Supply & installation of Anodized winding Oil cooled over band magnetic separator & control panel for conveyor 5A,5B &13C at CHP 3x660MW KTPS, Koradi. | 0 | - | 0 | 1.896 | 1.896 | 0 | 0 | 0 |  |  | 0 | 0
25 | Procurement of Grinding Wall Assembly for Impact Crusher At CHP 3x660MW KTPS, Koradi | 0 | - | 0 | 2.01 | 2.01 | 0 | 0 | 0 |  |  | 0 | 0
26 | Restoration of Boiler Circulation Pump of U10 at 3X660MW KTPS, Koradi | 0 | - | 0 | 6.69 | 6.69 | 0 | 0 | 0 |  |  | 0 | 0
27 | Design,Engineering,Customization,Implementation,Installation & testing of Data Analytical/Artificial Intellegence softwae for automated monitoring & diagnostics system to improve Power plant reliability & efficiency,at one unit of 3X660MW KTPS, Koradi. | 0 | - | 0 | 3.27 | 3.27 | 0 | 0 | 0 |  |  | 0 | 0
28 | Supply of Feed Gate Complete Assembly along with installation to enhance the performance of Feed Gate at Ash Handling Plant, 3x660MW, KTPS, Koradi. | 0 | - | 0 | 2.4 | 2.4 | 0 | 0 | 0 |  |  | 0 | 0
29 | Design, Supply, Installation & Commissioning of Instrument Air Dryer Assembly with Prefilters & Stainless steel piping along with valves suitable for Instrument Air Compressors at AHP, 3x660MW Units, KTPS, Koradi | 0 | - | 0 | 5.5 | 5.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Total |  |  |  | 6511.7591 | 6469.3114 | 42.4477 | 122.86 | 122.86 | 0 | 0 | 122.86 | 42.4477